## data
site¦fix00012¦8359047522524182050¦4026888666767723684 | site¦fix00015 | site¦region_name | docata¦ZDCSZ0654995 | docata¦ZDCSZ631062 | docata¦ZDCSZ00894446 | docata¦ZDCSZ646737 | docata¦ZDCSZ640071 | docata¦ZDCSZ640307 | docata¦ZDCSZ01027740 | docata¦ZDCSZ00841006 | WP10400¦AC0000078812¦actual_end_date | WPC000011447¦AC0000078165¦actual_end_date | WPC000011447¦AC0000081984¦actual_end_date | WP10400¦AC0000078166¦actual_end_date | WP10400¦AC0000079922¦actual_end_date | WP10400¦AC0000078166¦doc_delivery_status | WP10400¦AC0000078167¦actual_end_date | WP10400¦AC0000078168¦actual_end_date | docata¦ZDCSZ640327 | docata¦ZDCSZ640323 | docata¦ZDCSZ641766 | du¦du_code | docata¦ZDCSZ634272 | docata¦ZDCSZ646736 | WP11100¦actual_end_date | WP11000¦AC0000078169¦actual_end_date | WPC000011433¦AC0000084312¦actual_end_date | docata¦ZDCSZ630403 | docata¦ZDCSZ645498 | docata¦ZDCSZ630407 | docata¦ZDCSZ640325 | docata¦ZDCSZ642060 | docata¦ZDCSZ642061
Site Basic Info | Site Basic Info | Site Basic Info | DiGi Site ID | Installation | Network Planning | Installation | Survey&Design | Installation | Survey&Design | Survey&Design | Survey&Design | ETSS | ETSS | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Installation | Installation | Installation | Du | Survey&Design | Survey&Design | Telecom Installation | Ready For Installation | Site DECOMM | Survey&Design | Installation | Survey&Design | Installation | Installation | Installation
Site Basic Info | Site Basic Info | Site Basic Info | DiGi Site ID | Wireless RAN | Wireless RAN | Wireless RAN | Wireless RAN | Wireless RAN | Wireless RAN | Wireless RAN | Physical Survey | E-TSS | E-TSS (Decomm) | TSSR Submitted to ZTE | TSSR Submitted to ZTE (Decomm) | TSSR Submitted to ZTE | TSSR Submitted to Customer | TSSR customer Approval | Wireless RAN | Wireless RAN | Wireless RAN | Du | Wireless Site | Wireless RAN | Telecom Installation | Material Collection | Decomm | Wireless Site | Wireless RAN | Wireless Site | Wireless RAN | Wireless RAN | Wireless RAN
customer site code | customer site name | region | DiGi Site ID | SOW | SOW record | Cluster Sequence | Task Handler | SubCon - TI | TSSR Progress NIC v2 | TSSR status remark | actual end time | actual end time | actual end time | actual end time | actual end time | doc delivery status | actual end time | actual end time | TP RF PIC | TP RF Approval | Subcon PR - TSS | du code | Design Change History | TSSR Rejection Reasons | actual end time | actual end time | actual end time | Structure Type | Structure Type | Structure Height(m) | RNP - RRU Solution | MM sector(2025) | Bi-sector(2025)
K00668 | K008A_K00668OD_FOUR_SEASONS_RESORT | Northern | 4624K | Swap | Swap->On Hold->Swap | 2025 Q2 | SM | CCSMY | 4.6 TSSR Approved |  | 2024-10-12 | 2024-12-19 |  | 2024-12-24 |  | Rectificating | 2025-01-09 | 2025-01-24 | CD//Zulakmar | 2025-01-23 | Celcom Digi_RAN-CCSMY-TSS-Northern-20241017_New Contract | DU00003605510 |  |  | 2025-03-12 | 2025-02-19 |  | Watertank |  | 27m | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
4162C | Four Season Resort Langkawi | Northern |  | Decomm | Modernization->Decomm->On Hold->Decomm | 2025 Q2 | HW | GTSB | 4.6 TSSR Approved |  | 2025-03-25 |  | 2025-03-26 |  | 2025-04-08 | To be Submitted | 2025-04-28 |  | E//Hazida | 2026-02-09 | SQ202501060259 - GTSB | DU00003605511 |  |  |  |  | 2025-06-24
4642D | Bukit Jana (REL) | Northern |  | Modernization |  | 2023Q4 | BY | GTSB | 4.6 TSSR Approved |  | 2023-08-10 | 2023-08-15 |  | 2023-08-18 |  | Closed | 2023-08-18 | 2023-09-06 | E//Hazida | 2023-09-06 | Celcom Digi_RAN-GTSB-TSS-Northern-20230810-0023 | DU00002624356 |  |  | 2023-08-30 | 2023-08-29 |  | Monopole | landside | 30m | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x3 | 12
9725C | SAMALAJU PRESS METAL (REL) | Sarawak |  | Modernization |  | 2023Q3 | ZB | YPTT | 4.6 TSSR Approved |  | 2023-09-07 | 2023-09-15 |  | 2023-09-18 |  | Closed | 2023-09-18 | 2023-10-06 | E//Hannah | 2023-09-25 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20230911 | DU00002624357 |  |  | 2023-10-30 | 2023-10-19 |  | Monopole | landside | 30 | Add R9264M M1821 x1+R9264H M901821 x3,Dismantle R9224E M1821(AAB) x4 |  | 2
3178B9 | pBTS Jln Batu Nilam | Central |  | Modernization |  | 2023Q2 | XH | Ascentrack | 4.6 TSSR Approved |  | 2023-10-27 | 2023-10-30 |  | 2023-11-01 |  | Closed | 2023-11-03 | 2023-11-06 | E//Razif | 2023-11-06 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231028 | DU00002624358 |  |  | 2023-11-15 | 2023-11-14 |  | Watertank | landside | 24m | Add R9264M M1821 x1+R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 |  | 2
2809C | TMN MERU JAYA 3 | Central |  | Modernization |  | 2023Q3 | IE | Magicell | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦loading issue,AAU cannot install | 2023-09-12 | 2023-09-13 |  | 2023-09-15 |  | Closed | 2023-09-18 | 2023-09-21 | E//Razif | 2023-09-21 | CelcomDigi_RAN_Magicell_TSS_Central_20230913 | DU00002624359 | NIC_S2_Change MM to BI_loading issue_INFORIENT INRASTUCTURE |  | 2023-09-29 | 2023-09-26 |  | Monopole | Lampole | 30 | Add R9264M M1821 x2+R9264H M901821 x3+R8862A S2601 x2,Dismantle R8894E M1821(A8A) x3 |  | 23
3010M | Pasar Borong Selayang | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002037782 | [6 empty] | Micro Cell
4509C | Gleneagles Hospital (New Building) IB | Northern |  | Modernization |  | 2023Q3 | WP | YPTT | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-13 |  | 2023-05-17 |  | Closed | 2023-05-25 | 2023-06-12 | E//Nazrul | 2023-06-12 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0008 | DU00002037783 |  |  | 2023-09-18 | 2023-09-18 |  |  | In-building system |  | Add R8862A S1800 x3 | 0 | 0
1795A | Seksyen 15 (Opcom) | Central |  | Modernization |  | 2023Q4 | IE | Solusi | 4.6 TSSR Approved |  | 2023-06-16 | 2023-05-31 |  | 2023-07-05 |  | Closed | 2023-07-03 | 2023-07-21 | E//Razif | 2023-07-21 | CelcomDigi_RAN_Datasco_TSS_Central_20230606_0025 | DU00002037784 |  |  | 2023-08-02 | 2023-07-29 |  | Tower | 3m Bipod (RT) | 76M | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2,Dismantle R8894E M1821(A8A) x3 | 1
2161A | MASJID ZAKARIA | Central |  | Modernization |  | 2023Q4 | XH | Datasco | 4.6 TSSR Approved |  | 2023-07-31 | 2023-08-22 |  | 2023-08-24 |  | Closed | 2023-08-29 | 2023-09-01 | E//Kok Keen | 2023-09-01 | CelcomDigi_RAN_Datasco_TSS_Central_20230802 | DU00002037785 |  |  | 2023-09-16 | 2023-09-16 |  | Lampole | 24m Lampole | 30 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8840-U216 x3++
4706C | The Lexis Suites RT | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-15 | 2023-05-17 |  | 2023-05-22 |  | Closed | 2023-05-24 | 2023-06-11 | E//Hazida | 2023-06-11 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002037786 |  |  | 2023-07-05 | 2023-06-28 |  | Pole | Land site | 4m | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R9224E M1821(AAB) x3 | 12
4210C | BBrown M Pasir (REL) | Northern |  | Modernization |  | 2023Q3 | MH | GCI | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-09 |  | 2023-05-10 |  | Closed | 2023-05-11 | 2023-06-17 | E//Hazida | 2023-06-16 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002037787 |  |  | 2023-07-11 | 2023-07-11 |  | Monople Tree | 30m Monopole | 35 | Add A9732 M1821 x1 + R9264M M1821 x2,Dismantle R9224E M1821(AAB) x3 | 2
4992C | Jln Bayan Lepas | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI,L2600 change to 40M¦Space constraint， | 2023-05-20 | 2023-06-15 |  | 2023-06-21 |  | Closed | 2023-06-22 | 2023-07-14 | E//Hazida | 2023-07-05 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002037788 | NIC_S2_Change MM to BI,L2600 change to 40M_Space constraint_Digi OB |  | 2023-07-14 | 2023-07-13 |  | Unipole | 3m Boom (RT) | 3M | Add R9264H M901821 x1 + R9264M M1821 x5,Dismantle R8894E M1821(A8A) x4 |  | 13
4673C | Pine Residence | Northern |  | Modernization |  | 2023Q3 | ZA | YPTT | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-13 |  | 2023-05-16 |  | Closed | 2023-05-18 | 2023-07-07 | E//Hazida | 2023-07-06 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0008 | DU00002037789 |  | 0517 pls revise & SUBMIT by TODAY... minor mistakes only but pls redraw back proper top view dwg// | 2023-08-23 | 2023-08-23 |  |  | 3m Boom (RT) | 3m | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 |  | 2
1155A | Ijok | Central |  | Decomm |  | 2023Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-08-01 | 2023-05-05 |  | 2023-05-07 | 2023-09-19 | Closed | 2024-10-14 | 2023-07-07 | E//Razif | 2024-10-17 | CelcomDigi_RAN_GTSB_TSS_20230505_0023 | DU00002037790 |  | No TX NE & FE info. (Dismantle Microwave Link 1155A-2443A (Remain Antenna for NLOS site, Only IDU RTN03 at NE and FE)). | 2023-06-24 | 2023-06-22 | 2023-10-27 | Pole | 3m Bipod (RT) | 5
4001D | SRAR Kg Assam Kumbang | Northern |  | Modernization |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-06-08 | 2023-06-14 |  | 2023-06-17 |  | Closed | 2023-06-21 | 2023-06-27 | E//Hazida | 2023-06-27 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002037791 |  |  | 2023-08-06 | 2023-07-25 |  | Pole | 24m Lampole | 30 | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 1
3639A2 | pBTS Desa Permai Sg Besar (MCMC) | Central |  | Modernization |  | 2023Q4 | HQ 6 | Magicell | 4.6 TSSR Approved |  | 2023-05-25 | 2023-06-01 |  | 2023-06-06 |  | Closed | 2023-06-07 | 2023-07-21 | E//Razif | 2023-07-21 | CelcomDigi_RAN_GTSB_TSS_Central_20230529_0010 | DU00002037792 |  |  | 2023-07-03 | 2023-06-27 |  | Watertank | 25m pBTS | 24 | Add R9264H M901821 x3,Dismantle R8882 S1800(B) x2+R8882 S1800B(B6B) x1+R8862A S2100(A6A) x3
4085A | Tanjung Bungah | Northern |  | Modernization |  | 2023Q3 | MH | GTSB | 4.6 TSSR Approved |  | 2023-05-02 | 2023-05-05 |  | 2023-05-08 |  | Closed | 2023-05-09 | 2023-07-22 | E//Hazida | 2023-07-21 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002037793 |  |  | 2023-08-17 | 2023-08-15 |  | Wall mount boom | 45m 3 Legged Tower | 35m | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x2+R8881 S2100 x3
2694B | Jln Bkt Kapar 2 | Central |  | Modernization |  | 2023Q3 | AI | Magicell | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-16 |  | 2023-05-18 |  | Closed | 2023-05-20 | 2023-07-06 | E//Razif | 2023-07-06 | CelcomDigi_RAN_Magicell_TSS_Central_20230511_0008 | DU00002037794 |  |  | 2023-07-21 | 2023-07-18 |  | Monopole | 30m Monopole | 45m | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 12
4826C | Pekan Segenting (REL) | Northern |  | Modernization |  | 2023Q3 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-05-11 | 2023-05-17 |  | 2023-05-20 |  | Closed | 2023-05-29 | 2023-06-12 | E//Hazida | 2023-06-12 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0008 | DU00002037795 |  |  | 2023-07-06 | 2023-07-06 |  | Lampole | 30m Lampole | 34m | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
3569B | Sg Rasau Toll Shoplot | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-08 | 2023-06-13 |  | 2023-06-17 |  | Closed | 2023-06-20 | 2023-07-20 | E//Razif | 2023-07-20 | CelcomDigi_RAN_GTSB_TSS_Central_20230609_0027 | DU00002037796 |  |  | 2023-07-24 | 2023-07-18 |  | Wall mount boom | 3m Bipod (RT) | 2m | Add R9264M M1821 x6+R8862A S2601 x2,Dismantle R8894E M1821(A8A) x4 |  | 13
1641H | 99 Speedmart TMN SAUJANA PUTRA 2 | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002037797 | [6 empty] | Small Cell
2770B | Latar 1 (HW Bestari Jaya) | Central |  | Modernization |  | 2023Q3 | YZ | GTSB | 4.6 TSSR Approved |  | 2023-05-02 | 2023-05-04 |  | 2023-05-07 |  | Closed | 2023-05-09 | 2023-06-03 | CD//Syafiq | 2023-05-18 | CelcomDigi_RAN_GTSB_TSS_20230505_0023 | DU00002037798 |  |  | 2023-06-25 | 2023-06-22 |  | Tower | 60m 4 Legged Tower | 60m | Add R9264H M901821 x4+R8862A S2601 x1,Dismantle R8882 S1800(B) x3+R8854D S2100(A4A) x3
3644A1 | pBTS KK Hills GC (KM) | Central |  | Modernization |  | 2023Q3 | IE | AllStar | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-23 |  | 2023-05-25 |  | Closed | 2023-05-25 | 2023-06-07 | E//Sumitra | 2023-06-07 | CelcomDigi_RAN_Allstar_TSS_Central_20230517_0008 | DU00002037799 |  |  | 2023-06-10 | 2023-06-11 |  | Minimast | 25m pBTS | 22 | Add R9264H M901821 x3,Dismantle R8882 S1800(B) x3+R8881 S2100 x3
4062Z | KGCHEMPAKA | Northern |  | MOCN Decomm |  | 2023Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002037800 | [6 empty] | Land site
4331C | Motorola FTZ (REL) | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-02 | 2023-05-18 |  | 2023-05-22 |  | Closed | 2023-05-26 | 2023-07-07 | CD//Quah | 2023-07-05 | Celcom Digi_RAN-GCI-TSS-Northern-20230505-0012 | DU00002037801 |  |  | 2023-07-20 | 2023-07-19 |  | Monople Tree | 3m Boom (RT) | 37 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
3322B | Sky Avenue Genting IB | Central |  | Modernization |  | 2026 | AI | GTSB | 4.6 TSSR Approved |  | 2024-07-20 | 2023-07-10 |  | 2024-07-31 |  | Closed | 2024-08-07 | 2024-12-05 | E//Nazrul | 2024-12-05 | CelcomDigi_RAN_GTSB_TSS_Central_20230622_0031 | DU00002037802 |  |  | 2026-02-26 | 2025-07-08 |  | Portables BTS | In-building system | IBS SURVEY | Add R8862A S9000x2+R8894M 1821x1+R9264H M901821x5+R8862A S2601x5,Dismantle R8862A S1800(B6A)x1+R8862A S2100(A6A)x1+R8882 S2600(B4A)x5+R8894E M1821(A8A)x5
4022B | Gertak Sanggul(Asiaspace) | Northern |  | Modernization |  | 2023Q3 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-24 |  | 2023-05-26 |  | Closed | 2023-06-01 | 2023-06-22 | CD//Shukri | 2023-06-22 | Celcom Digi_RAN-YPTT-TSS-Northern-20230505-0007 | DU00002037803 |  |  | 2023-06-23 | 2023-06-21 |  | Tower | 100m Tower | 80 | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle R8882-GUL1812 x2+R8840-U216 x2 |  | 1
4669A | Alor Janggus (Trunk) | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-06-07 | 2023-06-08 |  | 2023-06-12 |  | Closed | 2023-06-19 | 2023-07-27 | E//Hazida | 2023-07-27 | Celcom Digi_RAN-GCI-TSS-Northern-20230607-0024 | DU00002037804 |  |  | 2023-09-11 | 2023-08-30 |  | Tower | 70m 4 Legged Tower | 100 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x5 | 123
4145B | Penang Airport 2 | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-16 |  | 2023-05-19 |  | Closed | 2023-05-29 | 2023-06-22 | CD//Shukri | 2023-06-22 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002037805 |  |  | 2023-07-12 | 2023-07-12 |  | Monopole | 30m Monopole | 24 | Add R9264M M1821 x3,Dismantle R8882 S1800(B) x3+R8862A S2100(A6A) x3
4282B | Taman Sultan Abdul Halim | Northern |  | Modernization |  | 2023Q4 | ZA | GCI | 4.6 TSSR Approved |  | 2023-05-28 | 2023-06-08 |  | 2023-06-10 |  | Closed | 2023-06-12 | 2023-07-27 | E//Hazida | 2023-07-27 | Celcom Digi_RAN-GCI-TSS-Northern-20230529-0022 | DU00002037806 |  |  | 2023-08-29 | 2023-08-29 |  | Monople Tree | 30m Monopole | 40 | Add A9732 M1821 x1 + R9264M M1821 x2,Dismantle R8894E M1821(A8A) x3 | 1
4976A | Kuala Sg Pinang | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-04 | 2023-05-18 |  | 2023-05-22 |  | Closed | 2023-05-29 | 2023-06-21 | CD//Shukri | 2023-06-21 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002037807 |  |  | 2023-07-10 | 2023-07-08 |  | Tower | 60m 3 Legged Tower | 45 | Add A9732 M1821 x1 + R9264M M1821 x2,Dismantle R8882-GUL1812 x3+R8881 S2100 x3 | 1
3805A | Assam Jawa | Central |  | Modernization |  | 2023Q4 | HQ 6 | AllStar | 4.6 TSSR Approved |  | 2023-05-31 | 2023-06-01 |  | 2023-06-06 |  | Closed | 2023-06-07 | 2023-07-21 | E//Razif | 2023-07-21 | CelcomDigi_RAN_AllStar_TSS_Central_20230601_0010 | DU00002037808 |  |  | 2023-07-15 | 2023-06-28 |  | Tower | Tower | 60 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8882 S1800(B) x3 |  | 1
1153A | Permatang K Selangor | Central |  | Modernization |  | 2023Q4 | HQ 6 | AllStar | 4.6 TSSR Approved |  | 2023-06-02 | 2023-06-15 |  | 2023-06-19 |  | Closed | 2023-06-22 | 2023-07-21 | E//Razif | 2023-07-21 | CelcomDigi_RAN_AllStar_TSS_Central_20230606_0011 | DU00002037809 |  |  | 2023-08-08 | 2023-07-18 |  | Tower | 60m 4 Legged Tower | 60M | Add A9732 M1821 x2 + R9264M M1821 x2,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8854D S2100(A4A) x4 | 23
1643B | Mutiara Bkt Raja(Maxis) | Central |  | Modernization |  | 2023Q3 | IE | Magicell | 4.6 TSSR Approved |  | 2023-04-27 | 2023-05-04 |  | 2023-05-10 |  | Closed | 2023-05-30 | 2024-02-16 | E//Sumitra | 2023-09-19 | CelcomDigi_RAN_Magicell_TSS_Central_20230502_0006 | DU00002037810 |  |  | 2023-09-22 | 2023-09-19 |  | Monopole | 45m Monopole | 45M | Add R9264H M901821 x3 + R9264M M1821 x3 + R8862A S2601 x1,Dismantle R8894E M1821(A8A) x4 + R8862A S9000(A6A) x3 |  | 14
2761B | Genting Resort Hotel | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-16 |  | 2023-07-11 |  | Closed | 2023-07-14 | 2023-07-17 | E//Nazrul | 2023-07-17 | CelcomDigi_RAN_GTSB_TSS_Central_20230620_0030 | DU00002037811 |  |  | 2023-10-28 | 2023-10-16 |  | Portables BTS | INBUILDING |  | Reuse existing RRU
4093A | Bukit Jambul Rooftop | Northern |  | Modernization |  | 2023Q3 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-05-06 | 2023-05-29 |  | 2023-05-31 |  | Closed | 2023-06-07 | 2023-07-14 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0008 | DU00002037812 |  |  | 2023-07-23 | 2023-07-18 |  | Wall mount boom | 2m RT (Boom) | 2 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
1025A | Sri Gombak | Central |  | Modernization |  | 2023Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2023-06-17 | 2023-06-20 |  | 2023-06-22 |  | Closed | 2023-06-23 | 2023-07-14 | E//Kok Keen | 2023-06-29 | CelcomDigi_RAN_Allstar_TSS_Central_20230620_0013 | DU00002037813 |  |  | 2023-08-04 | 2023-07-18 |  | Minimast | 3m RT (Minimast) | 10 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8882-GUL1812 x3 | 12
4373H | 99 Speedmart PK Tmn Mewah | Northern |  | MOCN As-Is |  | 2023Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002037814 | [6 empty] | Rooftop
4157B | Persiaran Gurney 3 | Northern |  | Modernization |  | 2023Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-05-17 | 2023-05-24 |  | 2023-05-27 |  | Closed | 2023-05-29 | 2023-07-22 | E//Hazida | 2023-07-21 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002037815 |  |  | 2023-08-17 | 2023-08-16 |  | H-bracket pole | 3m Boom (RT) | 4 | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x3 |  | 2
1324H | 99 Speedmart SG SEMBILANG | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002037816 | [6 empty] | Small Cell
4524C | Jln Taiping Utara (REL) | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-06-06 | 2023-06-12 |  | 2023-06-15 |  | Under Approval | 2023-07-03 | 2023-07-14 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002037817 |  |  | 2023-07-28 | 2023-07-28 |  |  | 3m Bipod (RT) | 5 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2,Dismantle R8894E M1821(A8A) x3 | 3
1141A | Tg Mallim Toll | Central |  | Modernization |  | 2023Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-06-16 | 2023-06-21 |  | 2023-07-05 |  | Closed | 2023-07-06 | 2023-07-13 | E//Kok Keen | 2023-07-13 | CelcomDigi_RANMW_Ascentrack_TSS_Central_20230616_0006 | DU00002037818 |  |  | 2023-08-05 | 2023-07-31 |  | Tower | 48m 4 Legged Tower | 46 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
4002Q | Sunshine HQ 20 Floor Qcell | Northern |  | MOCN As-Is |  | 2023Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002037819 | [6 empty] | Qcell
4863B | Wisma PKNK | Northern |  | Modernization |  | 2023Q4 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-05-29 | 2023-07-06 |  | 2023-07-10 |  | Closed | 2023-07-20 | 2023-07-27 | E//Hazida | 2023-07-27 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230530-0021 | DU00002037820 |  |  | 2023-10-27 | 2023-10-27 |  | Pole | 3m Boom (RT) | 6m | Add A9732 M1821 x3,Dismantle R8862A S1800(B6A) x6+R8854D S2100(A4A) x4 | 123
4092C | PP Utara (REL) | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-06-02 | 2023-06-08 |  | 2023-06-13 |  | Closed | 2023-06-15 | 2023-07-27 | E//Hazida | 2023-07-27 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002037821 |  |  | 2023-08-30 | 2023-08-30 |  | Monople Tree | 30m Monopole | 37 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
1665C | Surau Haji Ismail Puncak Alam | Central |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-06-16 | 2023-06-13 |  | 2023-06-16 |  | Closed | 2023-07-06 | 2023-07-11 | E//Razif | 2023-07-11 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002037822 |  |  | 2023-07-18 | 2023-07-18 |  | Monopole | Land site | 31 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
4375H | 99 Speedmart PK Medan Saujana | Northern |  | MOCN As-Is |  | 2023Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002037823 | [6 empty] | Rooftop
4002A | Leisure Bay Condo V3 | Northern |  | Modernization |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-05-11 | 2023-05-13 |  | 2023-05-16 |  | Closed | 2023-05-19 | 2023-08-03 | E//Hazida | 2023-08-03 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002037824 |  |  | 2023-08-17 | 2023-08-16 |  | Pole | 3m Boom (RT) | 4.5 | Add A9732 M1821 x1 + R9264M M1821 x3,Dismantle R8882-GUL1812 x2+R8882 S1800B(B6B) x2+R8862A S1800(B6A) x4+R8840-U216 x3+R8881 S2100 x1+ | 1
4658A | Hotel Grand Crystal | Northern |  | Modernization |  | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-06-02 | 2023-06-06 |  | 2023-06-08 |  | Closed | 2023-06-12 | 2023-08-04 | E//Daniel | 2023-08-04 | Celcom Digi_RAN-YPTT-TSS-Northern-20230606-0017 | DU00002037825 |  |  | 2023-09-27 | 2023-09-27 |  | In-Building System | 6.5m RT (Boom) | 5 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
1187B | Tmn Industri Bolton | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-05-26 | 2023-07-11 |  | 2023-07-19 |  | Closed | 2023-07-20 | 2023-07-21 | E//Kok Keen | 2023-07-20 | CelcomDigi_RAN_GTSB_TSS_Central_20230529_0025 | DU00002037826 |  |  | 2023-08-08 | 2023-08-08 |  | Pole | 3m RT (Wall Mounted Pole) | 5M | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3
1009A | Sri Salan | Central |  | Modernization |  | 2023Q4 | SS | YPTT | 4.6 TSSR Approved |  | 2023-06-20 | 2023-07-06 |  | 2023-07-10 |  | Closed | 2023-07-12 | 2023-07-14 | E//Kok Keen | 2023-07-14 | CelcomDigi_RAN_YPTT_TSS_Central_20230622_0007 | DU00002037827 |  |  | 2023-08-03 | 2023-08-03 |  | Pole | 3m RT (Wall Mounted Pole) | 2 | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8894E M1821(A8A) x3 |  | 2
1164C | Taman Bukit Subang | Central |  | Modernization |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-31 | 2023-06-09 |  | 2023-06-13 |  | Closed | 2023-06-14 | 2023-06-21 | E//Kok Keen | 2023-06-21 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002037828 |  |  | 2023-07-25 | 2023-07-24 |  | Pole | 24m Lampole | 24 | Add R9264H M901821 x3,Dismantle R8892N M1821(BAB) x3
2597B | TM Bkt Cherakah | Central |  | Modernization |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-09-20 | 2023-10-09 |  | 2023-10-12 |  | Closed | 2023-10-17 | 2023-10-19 | E//Kok Keen | 2023-10-18 | CelcomDigi_RAN_Datasco_TSS_Central_20230829_Modern+Decom | DU00002037829 |  |  | 2024-01-26 | 2024-01-22 |  | Tower | 4 Legged Tower | 100 | Add R9264H M901821 x3,Dismantle R8882 S1800(B) x3+R8881 S2100 x3
4312H | 99 Speedmart PK Tmn Pertama Taiping | Northern |  | MOCN As-Is |  | 2023Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002037830 | [6 empty] | Rooftop
2037A | Kg Hj Dorani (KJS) | Central |  | Modernization |  | 2023Q4 | HQ 6 | Magicell | 4.6 TSSR Approved |  | 2023-05-29 | 2023-05-30 |  | 2023-06-01 |  | Closed | 2023-06-02 | 2023-07-25 | E//Razif | 2023-07-21 | CelcomDigi_RAN_Magicell_TSS_Central_20230531_0010 | DU00002037831 |  |  | 2023-07-10 | 2023-07-08 |  | Tower | Tower | 60M | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle R8894E M1821(A8A) x3 |  | 3
3763A | Kampung Sungai Masin | Central |  | Modernization |  | 2023Q4 | MA | Futong | 4.6 TSSR Approved |  | 2023-06-19 | 2023-06-21 |  | 2023-06-23 |  | Closed | 2023-06-24 | 2023-07-07 | E//Kok Keen | 2023-07-03 | CelcomDigi_RAN_Futong_TSS_Central_20230620_0002 | DU00002037832 |  |  | 2023-12-05 | 2023-12-05 |  | Tower | Tower | 61 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 12
3781A | Masjid Al-Raudzah Tanjung Karang | Central |  | Modernization |  | 2023Q4 | HQ 6 | AllStar | 4.6 TSSR Approved |  | 2023-05-30 | 2023-06-01 |  | 2023-06-06 |  | Closed | 2023-06-07 | 2023-07-22 | E//Razif | 2023-07-21 | CelcomDigi_RAN_AllStar_TSS_Central_20230529_0009 | DU00002037833 |  |  | 2023-12-28 | 2023-12-11 |  |  | Tower | 77 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x3 | 23
4567D | Lorong Kamunting Jaya | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-06-20 | 2023-07-10 |  | 2023-06-28 |  | Closed | 2023-07-13 | 2023-08-01 | E//Hazida | 2023-07-17 | Celcom Digi_RAN-GCI-TSS-Northern-20230621-0032 | DU00002037834 |  |  | 2023-08-03 | 2023-08-01 |  | Lampole | Land site | 30 | Add R9264H M901821 x3,Dismantle R9224E M1821(AAB) x3
3755C | Bdr Puteri Klang (REL) | Central |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-05-31 | 2023-06-01 |  | 2023-06-06 |  | Closed | 2023-06-07 | 2023-06-09 | E//Razif | 2023-06-09 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002037835 |  |  | 2023-12-22 | 2023-12-11 |  | Unipole | 3m Boom (RT) | 7 | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 2
1200B | Jln Besar (TM) | Central |  | Modernization |  | 2023Q3 | XH | Magicell | 4.6 TSSR Approved |  | 2023-08-02 | 2023-08-04 |  | 2023-08-08 |  | Closed | 2023-08-15 | 2023-08-15 | E//Razif | 2023-08-15 | CelcomDigi_RAN_Magicell_TSS_Central_20230803 | DU00002037836 |  |  | 2024-01-10 | 2023-11-16 |  | Tower | Tower | 75 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x3+R9224E M1821(AAB) x2 | 123
3887C | Central i-City Shopping Centre IB | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-10-19 | 2023-10-23 |  | 2023-10-27 |  | Closed | 2023-10-30 | 2024-03-27 | E//Nazrul | 2024-03-26 | CelcomDigi_RAN_GTSB_TSS_Central_20231020 | DU00002037837 |  |  | 2023-12-21 | 2023-12-09 |  | Portables BTS | In-building system |  | Add + R8862A S2100 x6
1881B | NS Highway KM 422 (KJS) | Central |  | Modernization |  | 2023Q2 | HQ 6 | Datasco | 4.6 TSSR Approved |  | 2023-05-12 | 2023-06-13 |  | 2023-06-15 |  | Closed | 2023-06-17 | 2023-06-24 | E//Kok Keen | 2023-06-23 | CelcomDigi_RAN_Datasco_TSS_Central_20230428_0018 | DU00002037838 |  |  | 2023-07-08 | 2023-06-28 |  | Tower | Tower | 75 | Add R9264H M901821 x3,Dismantle R8860E-GU908 x2+R8882-GUL1812 x3+R8840-U216 x3
2982B | RSC 1 Genting | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-09-26 | 2023-09-18 |  | 2023-10-04 |  | Closed | 2023-09-29 | 2023-10-02 | E//Nazrul | 2023-09-29 | CelcomDigi_RAN_GTSB_TSS_Central_20230811 | DU00002037839 |  |  | 2025-07-31 | 2025-07-19 |  | Portables BTS | In-building system | IBC | Add R8862A S2100 x3
1719B | MB Residence | Central |  | Decomm | On Hold->Decomm | 2023Q4 | SM | Datasco | 4.6 TSSR Approved |  | 2023-10-24 | 2023-10-26 |  | 2023-11-01 | 2024-07-02 | Rectificating | 2024-07-04 | 2025-03-07 | E//Nazrul | 2024-07-26 | CelcomDigi_RAN_Datasco_TSS_Central_20231025 | DU00002037840 |  |  |  |  | 2025-06-05 | Portables BTS | In-building system | N/A
4620C | Kampung Gading | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-28 | 2023-05-31 |  | 2023-06-02 |  | Closed | 2023-06-07 | 2023-07-22 | E//Daniel | 2023-07-22 | Celcom Digi_RAN-GCI-TSS-Northern-20230529-0022 | DU00002037841 |  |  | 2023-08-28 | 2023-08-27 |  | Lampole | 30m Lampole | 30 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
4179D | Lorong Bersatu | Northern |  | Modernization |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-29 | 2023-06-01 |  | 2023-06-06 |  | Closed | 2023-06-09 | 2023-06-21 | E//Hazida | 2023-06-21 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230530-0021 | DU00002037842 |  |  | 2023-07-27 | 2023-07-25 |  | Pole | 3m Boom (RT) | 6 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
1614H | 99 Speedmart SRI MUDA 3 | Central |  | MOCN As-Is | MOCN As-Is->On Hold->MOCN As-Is | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002037843 | [6 empty] | Small Cell
2675B | BdrTasik Puteri 1 (celcom) | Central |  | Modernization |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-04 |  | 2023-05-07 |  | Closed | 2023-05-09 | 2023-06-05 | CD//Syafiq | 2023-05-17 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230428_0015 | DU00002037844 |  |  | 2023-06-17 | 2023-06-16 |  | Pole | 3m Bipod (RT) | 6.5m | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 13
4759B | Kamunting Bus Station (Maxis) | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-06-12 | 2023-06-06 |  | 2023-06-12 |  | Closed | 2023-06-22 | 2023-07-14 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-GCI-TSS-Northern-20230613-0027 | DU00002037845 |  |  | 2023-08-06 | 2023-07-22 |  | Tower | 60m 3 Legged Tower | 60 | Add R9264M M1821 x5,Dismantle R8894E M1821(A8A) x3 |  | 23
1161A | Bkt Rotan | Central |  | Modernization |  | 2023Q4 | SS | YPTT | 4.6 TSSR Approved |  | 2023-06-24 | 2023-07-06 |  | 2023-07-10 |  | Closed | 2023-07-13 | 2023-07-22 | E//Razif | 2023-07-21 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_0009 | DU00002037846 |  |  | 2023-08-10 | 2023-08-02 |  | Monopole | 45m Monopole | 46M | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8894E M1821(A8A) x3 |  | 12
4449C | Karpal Singh Shoplot | Northern |  | Modernization |  | 2023Q3 | MH | YPTT | 4.6 TSSR Approved |  | 2023-05-07 | 2023-05-15 |  | 2023-05-17 |  | Closed | 2023-05-19 | 2023-07-07 | E//Hazida | 2023-07-06 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0008 | DU00002037847 |  |  | 2023-08-30 | 2023-08-24 |  | Minimast | 3m Bipod (RT) | 7.5 | Add R9264M M1821 x5,Dismantle R8854E S1800(A6A) x3+R8854D S2100(A4A) x3 |  | 12
4416A | Bukit Asa(ZED) | Central |  | Modernization |  | 2023Q4 | HQ 6 | Ascentrack | 4.6 TSSR Approved |  | 2023-07-06 | 2023-07-11 |  | 2023-07-13 |  | Closed | 2023-07-17 | 2023-07-25 | E//Kok Keen | 2023-07-18 | CelcomDigi_RANMW_Ascentrack_Central_20230706_0010 | DU00002037848 |  |  | 2023-09-17 | 2023-08-10 |  | Tower | 70m 4 Legged Tower | 70 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x3 | 12
4043A | Victoria Street | Northern |  | Modernization |  | 2023Q3 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-04-28 | 2023-05-02 |  | 2023-05-04 |  | Closed | 2023-05-05 | 2023-05-18 | CD//Affendi | 2023-05-08 | Celcom Digi_RAN-YPTT-TSS-Northern-20230505-0007 | DU00002037849 |  |  | 2023-08-25 | 2023-08-24 |  | A-bracket pole | 60m 4 Legged Tower | 3M | Add R9264M M1821 x3,Dismantle R9224E M1821(AAB) x3
4069B | Persiaran Kelicap | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-12 | 2023-05-16 |  | 2023-05-20 |  | Closed | 2023-05-23 | 2023-06-02 | E//Hazida | 2023-06-02 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002037850 |  |  | 2023-06-24 | 2023-06-24 |  | Wall mount boom | 24m Lampole | 5 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
1553H | 99 Speedmart Tmn Sri Sentosa | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002037851 | [6 empty] | Small Cell
3442B3 | pBTS Batang Berjuntai | Central |  | Modernization |  | 2023Q3 | IE | GTSB | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-05 |  | 2023-05-07 |  | Closed | 2023-05-08 | 2023-06-28 | E//Sumitra | 2023-06-27 | CelcomDigi_RAN_GTSB_TSS_20230505_0023 | DU00002037852 |  |  | 2023-06-10 | 2023-06-10 |  | Tower | 25m pBTS | 25 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
4475A | Sabak Bernam | Central |  | Modernization |  | 2023Q4 | HQ 6 | CCSMY | 4.6 TSSR Approved |  | 2023-07-06 | 2023-07-12 |  | 2023-07-31 |  | Closed | 2023-08-02 | 2023-08-03 | E//Razif | 2023-08-03 | CelcomDigi_RAN_CCSMY_TSS_Central_20230707_0008 | DU00002037853 |  |  | 2023-08-30 | 2023-08-21 |  | Tower | 3m Bipod (RT) | 47M | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8854E S1800(A6A) x3+R8854D S2100(A4A) x3 | 13
2689C | Taman Anggerik | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-25 | 2023-04-27 |  | 2023-05-03 |  | Closed | 2023-05-06 | 2023-05-30 | E//Kok Keen | 2023-05-26 | CelcomDigi_RAN_Datasco_TSS_Central_20230426_0017 | DU00002037854 |  |  | 2023-05-27 | 2023-05-27 |  | Lampole | Land site | 30 | Add R9264H M901821 x4,Dismantle R8894E M1821(A8A) x4
2976A | SetiaEcopark | Central |  | Modernization |  | 2023Q3 | IE | Magicell | 4.6 TSSR Approved |  | 2023-05-03 | 2023-04-29 |  | 2023-05-05 |  | Closed | 2023-05-05 | 2023-06-03 | CD//Norhaliza | 2023-05-17 | CelcomDigi_RAN_Magicell_TSS_20230505_0006 | DU00002037855 |  |  | 2023-06-25 | 2023-06-22 |  | Monople Tree | 36m Monopole | 57m | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x4 |  | 1(Bisector @ New S3)
2777B | Bukit Subang | Central |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-23 |  | 2023-05-25 |  | Closed | 2023-05-25 | 2023-06-07 | E//Kok Keen | 2023-06-07 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002037856 |  |  | 2023-07-15 | 2023-07-13 |  | Petronas Pylon | 25m Pylon | 30 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8892N M1821(BAB) x3
1352A | Oriental Metal | Central |  | Modernization |  | 2023Q4 | SS | Solusi | 4.6 TSSR Approved |  | 2023-05-25 | 2023-06-08 |  | 2023-06-21 |  | Closed | 2023-06-23 | 2023-07-21 | E//Razif | 2023-07-20 | CelcomDigi_RAN_Solusi_TSS_Central_20230620_0002 | DU00002037857 |  |  | 2023-07-18 | 2023-07-18 |  | Wall mount boom | 3m Boom (RT) | 6m | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8882-GUL1812 x3+R8840-U216 x3++ |  | 12
1012Z | KG ASAHAN | Central |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002037858 | [6 empty] | Land site
3424B1 | pBTS Shin Yang HQ Baram (KM) | Sarawak |  | Modernization |  | 2023Q4 | BY | AllStar | 4.6 TSSR Approved |  | 2023-06-28 | 2023-06-22 |  | 2023-06-28 |  | Closed | 2023-07-05 | 2023-07-14 | E//Hannah | 2023-07-14 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230608-0006 | DU00002037859 |  |  | 2023-08-15 | 2023-08-14 |  | Watertank | 25m pBTS | 24 | Add R9264H M901821 x3,Dismantle R8882 S1800B(B6B) x3++R8881 S2100 x3+
1692B | Puncak Perdana (Watertank _ ZED | Central |  | Modernization |  | 2023Q3 | AI | YPTT | 4.6 TSSR Approved |  | 2023-05-06 | 2023-05-17 |  | 2023-05-22 |  | Closed | 2023-06-23 | 2023-07-14 | E//Razif | 2023-07-14 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002037860 |  |  | 2023-07-18 | 2023-07-17 |  | Tower | 60m 3 Legged Tower | 60M | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x2,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x3+R8862A S2100(A6A) x6+R8862A S2601(A6A) x1 | 23
4386D | Lorong Bendahara | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-29 | 2023-05-26 |  | 2023-05-29 |  | Closed | 2023-06-05 | 2023-06-13 | CD//Shamsul | 2023-06-13 | Celcom Digi_RAN-GCI-TSS-Northern-20230529-0022 | DU00002037861 |  |  | 2023-09-03 | 2023-08-29 |  | Pole | 3m Boom (RT) | 6 | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8894E M1821(A8A) x3 |  | 2
1501H | 99 Speedmart SHAH ALAM JLN KRISTAL | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002037862 | [6 empty] | Small Cell
4589A | Taiping Utara (KJS_ZED) RCC | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-25 | 2023-05-26 |  | 2023-05-30 |  | Closed | 2023-06-05 | 2023-07-15 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-GCI-TSS-Northern-20230526-0021 | DU00002037863 |  |  | 2023-08-01 | 2023-07-25 |  | Tower | 60m 4 Legged Tower | 50 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3
1064A | Ulu Yam Baru(Maxis) | Central |  | Modernization |  | 2023Q4 | SS | Futong | 4.6 TSSR Approved |  | 2023-06-26 | 2023-06-28 |  | 2023-06-30 |  | Closed | 2023-07-04 | 2023-07-11 | E//Kok Keen | 2023-07-11 | CelcomDigi_RAN_Futong_TSS_Central_20230627_0005 | DU00002037864 |  |  | 2023-11-06 | 2023-10-31 |  | Tower | 40m 3 Legged Tower | 75 | Add A9732 M1821 x1+R9264M M1821 x1+R9264H M901821 x1,Dismantle R8894E M1821(A8A) x1+R9224E M1821(AAB) x2 | 3
3257B | Fox Plaza RT | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2024-07-11 | 2024-07-14 |  | 2024-07-17 |  | Closed | 2024-07-18 | 2024-07-19 | E//Kok Keen | 2024-07-19 | 0719Central-GTSB-BOQ Template | DU00002037865 |  |  | 2025-09-30 | 2025-09-29 |  | Pole | 3m Boom (RT) | 5m | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
3184A | Kolam Air Seksyen 9 | Central |  | Modernization |  | 2023Q4 | YZ | Datasco | 4.6 TSSR Approved |  | 2023-05-15 | 2023-05-17 |  | 2023-05-25 |  | Closed | 2023-05-26 | 2023-07-22 | E//Razif | 2023-07-21 | CelcomDigi_RAN_Datasco_TSS_Central_20230517_0022 | DU00002037866 |  |  | 2023-07-13 | 2023-07-12 |  | Monople Tree | 24m Lampole | 35 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle R8882 S1800B(B6B) x3+R8881 S2100 x3+
4650B | TmnSeriImpianMergong | Northern |  | Modernization |  | 2023Q4 | MH | GCI | 4.6 TSSR Approved |  | 2023-05-23 | 2023-05-25 |  | 2023-05-31 |  | Closed | 2023-06-01 | 2023-07-28 | E//Hazida | 2023-07-27 | Celcom Digi_RAN-GCI-SS-Northern-20230524-0019 | DU00002037867 |  |  | 2023-09-06 | 2023-09-05 |  | Tower | 60m 3 Legged Tower | 60 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x4+R9224E M1821(AAB) x1 | 123
1142A | Kg. Kalumpang | Central |  | Modernization |  | 2023Q4 | HQ 6 | Ascentrack | 4.6 TSSR Approved |  | 2023-05-25 | 2023-05-27 |  | 2023-06-02 |  | Closed | 2023-06-05 | 2023-06-09 | E//Kok Keen | 2023-06-09 | Celcomdigi_RAN_Ascentrack_TSS_Central_20230529_0020 | DU00002037868 |  |  | 2023-07-10 | 2023-07-04 |  | Tower | 60m 4 Legged Tower | 45M | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882-GUL1812 x3
1116E | FamilyMart Bukit Sentosa Rawang | Central |  | MOCN As-Is |  | 2023Q3 | IE |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | N/A - no need PR for MOCN As-Is | DU00002037869 | [6 empty] | Aircond Compressor
3365A5 | pBTS Tawau Blossom (REL) | Sabah |  | Modernization |  | 2023Q4 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-06-21 | 2023-06-23 |  | 2023-06-24 |  | Closed | 2023-07-03 | 2023-07-11 | E//Hannah | 2023-07-11 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230612-0004 | DU00002037870 |  |  | 2023-08-13 | 2023-08-09 |  | Watertank | 25m pBTS | 24m | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x4 | 12
3765A | Masjid Bandar Utama Batang Kali (REL) | Central |  | Modernization |  | 2023Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2023-09-04 | 2023-09-05 |  | 2023-09-08 |  | Closed | 2023-09-08 | 2023-09-08 | E//Kok Keen | 2023-09-08 | 0626Central-Allstar-BOQ Template (template) | DU00002037871 |  |  | 2023-09-21 | 2023-09-18 |  |  | 24m Lampole | 25 | Add R9264M M1821 x2+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x4 | 23
3427B4 | pBTS OM Material (REL) | Sarawak |  | Site Out (Modernization) | Modernization->MOCN Decomm->Site Out->Replacement, Site Out (Modernization) | 2023Q3 |  | Magicell | [SiteOut]- 1.0 Pending Survey - Subcon | [6 empty] | To be Submitted | [5 empty] | DU00002037872 | [6 empty] | 25m pBTS
4214B | Seri Hussein | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-11 | 2023-06-06 |  | 2023-06-12 |  | Closed | 2023-06-26 | 2023-07-07 | E//Hazida | 2023-07-03 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002037873 |  |  | 2023-12-29 | 2023-07-13 |  | Lampole | 3m Bipod (RT) | 5M | Add R9264H M901821 x4,Dismantle R8862A S1800(B6A) x4+R8862A S2100(A6A) x4 | 0 | 0
3238D | Kota Kemuning Mariamman Temple (REL2) | Central |  | Modernization |  | 2023Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-05-15 | 2023-05-17 |  | 2023-05-19 |  | Closed | 2023-05-20 | 2023-06-10 | E//Sumitra | 2023-06-08 | CelcomDigi_RAN_Allstar_TSS_Central_20230517_0008 | DU00002037874 |  |  | 2023-06-11 | 2023-06-11 |  | Lampole | 18m Lampole | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
2663B | Kesas Bdr Puteri Klang | Central |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-31 |  | 2023-06-02 |  | Closed | 2023-06-05 | 2023-06-10 | E//Sumitra | 2023-06-08 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002037875 |  |  | 2023-08-14 | 2023-08-14 |  | Tower | 45m Tower | 45 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 | 23
1013A | Bkt Tinggi Resort | Central |  | Modernization |  | 2023Q4 | CR | Magicell | 4.6 TSSR Approved |  | 2023-08-02 | 2023-08-07 |  | 2023-08-09 |  | Closed | 2023-08-10 | 2023-08-16 | E//Kok Keen | 2023-08-16 | CelcomDigi_RAN_Magicell_TSS_Central_20230803 | DU00002037876 |  |  | 2023-09-07 | 2023-09-05 |  | Monopole | 30m Monopole | 30 | Add R8852E S9000 x1 + R8894E M1821 x1,Dismantle R8882-GUL1812 x1
4680A | HBR Transport Building | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-06-27 | 2023-07-06 |  | 2023-06-30 |  | Closed | 2023-07-11 | 2023-08-03 | E//Hazida | 2023-08-03 | Celcom Digi_RAN-GCI-TSS-Northern-20230626-0035 | DU00002037877 |  |  | 2023-10-17 | 2023-09-16 |  | In-Building System | 2m RT (Boom) | 10 | Add R9264M M1821 x5 + R8862A S2601 x2,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1 |  | 12
4736A | Jebong (Trunk) | Northern |  | Modernization |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-28 | 2023-06-14 |  | 2023-06-19 |  | Closed | 2023-06-26 | 2023-07-15 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230529-0020 | DU00002037878 |  |  | 2023-07-26 | 2023-07-25 |  | Tower | 76m Tower | 80m | Add R9264M M1821 x3,Dismantle R9224E M1821(AAB) x3
3521A18 | pBTS FIZ4 (REL) | Northern |  | Site Out (Modernization) | Modernization->Decomm->Site Out->Replacement, Site Out (Modernization) | 2023Q3 |  | CCSMY | [SiteOut]- 1.0 Pending Survey - Subcon | ¦ 0129 - CCS remarks, Site Drop | [5 empty] | To be Submitted |  |  |  |  | Celcom Digi_RAN-CCSMY-TSS-Northern-20230509-0018 | DU00002037879 | [6 empty] | Portable BTS
4033A | Institute Victoria | Northern |  | Modernization |  | 2023Q3 | MH | GTSB | 4.6 TSSR Approved |  | 2023-05-02 | 2023-05-05 |  | 2023-05-08 |  | Closed | 2023-05-09 | 2023-07-24 | E//Hazida | 2023-07-22 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002037880 |  |  | 2023-08-10 | 2023-08-10 |  | Wall mount boom | 60m 4 Legged Tower | N/A | Add R9264M M1821 x3,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3
1007C | Green Valley Park | Central |  | Modernization |  | 2023Q2 | HQ 6 | Ascentrack | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-12 |  | 2023-05-14 |  | Closed | 2023-05-16 | 2023-06-07 | E//Kok Keen | 2023-06-06 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230428_0015 | DU00002037881 |  |  | 2023-06-04 | 2023-05-30 |  | Monopole | 24m Lampole | 30m | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
2437A | Lembah Beringin (MAXIS) | Central |  | Modernization |  | 2023Q4 | HQ 1 | Ascentrack | 4.6 TSSR Approved |  | 2023-07-09 | 2023-07-17 |  | 2023-07-20 |  | Closed | 2023-07-22 | 2023-08-15 | E//Kok Keen | 2023-07-26 | Celcomdigi_RAN_Ascentrack_TSS_Central_20230707_0027 | DU00002037882 |  |  | 2023-09-16 | 2023-09-17 |  | Tower | Tower | 60m | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3++
4138C | Tmn Desa Relau | Northern |  | Modernization |  | 2023Q3 | WP | YPTT | 4.6 TSSR Approved |  | 2023-05-04 | 2023-05-12 |  | 2023-05-22 |  | Closed | 2023-06-26 | 2023-07-03 | E//Hazida | 2023-07-03 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0008 | DU00002037883 |  |  | 2023-07-04 | 2023-07-04 |  | Monopole | 25m pBTS | 25 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
1144A | Tmn Bernam Jaya (Asiaspace) | Central |  | Modernization |  | 2023Q4 | HQ 6 | Ascentrack | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦not safe AAU can not install | 2023-06-03 | 2023-06-10 |  | 2023-06-13 |  | Closed | 2023-06-14 | 2024-07-10 | E//Hazida | 2023-09-18 | Celcomdigi_RAN_Ascentrack_TSS_Central_20230606_0021 | DU00002037884 | NIC_S2_Change MM to BI_Space constraint_EDGEPOINT INFRA |  | 2023-10-13 | 2023-08-02 |  | Monople Tree | 45m Monopole | 46 | Add R9264M M1821 x3+R9264H M901821 x3+R8862A S2601 x3,Dismantle R9224E M1821(AAB) x3 |  | 123
4017B | Balik Pulau Town | Northern |  | Modernization |  | 2023Q3 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-05-01 | 2023-05-02 |  | 2023-05-04 |  | Closed | 2023-05-05 | 2023-06-01 | CD//Heng | 2023-06-01 | Celcom Digi_RAN-YPTT-TSS-Northern-20230509-0010 | DU00002037885 |  |  | 2023-06-27 | 2023-06-26 |  | Tower | 60m 3 Legged Tower | 61M | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x4+R8862A S2600(A4A) x1 | 123
1169A | Tg Karang Trunk Road | Central |  | Modernization |  | 2023Q4 | HQ 6 | AllStar | 4.6 TSSR Approved |  | 2023-06-02 | 2023-06-07 |  | 2023-06-09 |  | Closed | 2023-06-12 | 2023-07-22 | E//Razif | 2023-07-21 | CelcomDigi_RAN_AllStar_TSS_Central_20230606_0011 | DU00002037886 |  |  | 2023-08-01 | 2023-07-31 |  |  | 50m 3 Legged Tower | 45 | Add R8852E S9000 x3 + A9732 M1821 x3 + R9264H M901821 x1,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8854D S2100(A4A) x4 | 123
1684B | Section 8 no.2(ZED) | Central |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-05-31 | 2023-06-02 |  | 2023-06-08 |  | Closed | 2023-06-15 | 2023-07-13 | E//Razif | 2023-07-13 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002037887 |  |  | 2023-10-16 | 2023-10-12 |  | Tower | 16m Tower | 61m | Add R9264H M901821 x2 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8882-GUL1812 x2+R8840-U216 x2 |  | 1
3175A | Jalan Setia Prima | Central |  | Modernization |  | 2023Q3 | AI | Magicell | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-05 |  | 2023-05-08 |  | Closed | 2023-05-09 | 2023-06-07 | E//Sumitra | 2023-06-07 | CelcomDigi_RAN_Magicell_TSS_20230505_0006 | DU00002037888 |  |  | 2023-06-14 | 2023-06-13 |  | Pole | 5m RT (Wall Mounted Pole) |  | Add R9264M M1821 x4,Dismantle R8882 S1800(B) x3+R8862A S1800(B6A) x1+R8862A S2100(A6A) x4
1608H | 99 Speedmart Bkt Jelutong 3 | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002037889 | [6 empty] | Small Cell
4001M | Lebuh China Micro | Northern |  | MOCN As-Is |  | 2023Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002037890 | [6 empty] | Micro Cell
4045A | Jelutong Shoplot | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-02 | 2023-05-18 |  | 2023-05-23 |  | Closed | 2023-05-29 | 2023-07-17 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002037891 |  |  | 2023-07-09 | 2023-07-08 |  | Wall mount boom | 60m 4 Legged Tower | 6 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8882-GUL1812 x3+R8882 S2600(B4A) x1+R8894E M1821(A8A) x4 | 12
4819A | Evergreen Laurel Hotel | Northern |  | Modernization |  | 2023Q3 | MH | GTSB | 4.6 TSSR Approved |  | 2023-05-02 | 2023-05-04 |  | 2023-05-12 |  | Closed | 2023-05-17 | 2023-05-29 | E//Nazrul | 2023-05-29 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002037892 |  |  | 2023-08-01 | 2023-08-01 |  | Wall mount boom | In-building system |  | Add R8862A S1800 x1 + R8862A S2100 x1,Dismantle R8882-GUL1812 x1
4480A | Hotel Bunga Raya | Central |  | Modernization |  | 2023Q4 | MS | Magicell | 4.6 TSSR Approved |  | 2023-05-30 | 2023-06-06 |  | 2023-06-08 |  | Closed | 2023-06-09 | 2023-07-22 | E//Razif | 2023-07-21 | CelcomDigi_RAN_Magicell_TSS_Central_20230531_0010 | DU00002037893 |  |  | 2023-07-18 | 2023-07-18 |  | In-Building System | 3m Bipod (RT) | 5 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R8882 S2600(B4A) x1+R8862A S2601(A6A) x1+R8894E M1821(A8A) x2 | 23
4717B | Bagan Bharu | Northern |  | Modernization |  | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-05-28 | 2023-06-02 |  | 2023-06-07 |  | Closed | 2023-06-12 | 2023-07-21 | E//Yadav | 2023-07-21 | Celcom Digi_RAN-YPTT-TSS-Northern-20230530-0014 | DU00002037894 |  |  | 2023-07-30 | 2023-07-26 |  | Tower | 60m 4 Legged Tower | 60 | Add R9264M M1821 x3 +R9264H M901821 x1+ R8862A S2601 x2,Dismantle R8862A S1800(B6A) x2++R8881 S2100 x2+ |  | 2((S1 -> S2,S2->S3,,new sector is S1,rename sector ID,Bisector@new S3)
2637A | Pt16 Sg Panjang | Central |  | Modernization |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-05-26 | 2023-06-01 |  | 2023-06-05 |  | Closed | 2023-06-09 | 2023-07-22 | E//Razif | 2023-07-21 | CelcomDigi_RAN_GTSB_TSS_Central_20230529_0010 | DU00002037895 |  |  | 2023-07-23 | 2023-07-22 |  | Tower | 76m 3 Legged Tower | 75 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x2,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1 | 13
2469A | Kolej Asiah | Central |  | Modernization |  | 2023Q4 | HQ 6 | Datasco | 4.6 TSSR Approved |  | 2023-07-10 | 2023-07-17 |  | 2023-07-20 |  | Closed | 2023-07-21 | 2023-08-11 | E//Kok Keen | 2023-07-25 | CelcomDigi_RAN_Datasco_TSS_Central_20230711 | DU00002037896 |  |  | 2023-09-06 | 2023-08-15 |  | Monopole | 45m 3 Legged Tower | 26 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle R8862A S1800(B6A) x3++R8881 S2100 x3+
4782C | Eastin Hotel Penang | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-20 |  | 2023-05-23 |  | Closed | 2023-05-29 | 2023-06-12 | E//Hazida | 2023-06-12 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002037897 |  |  | 2023-07-12 | 2023-07-10 |  | Pole | 3m Boom (RT) | 5 | Add R9264H M901821 x3 + R9264M M1821 x2,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 |  | 12
4953C | RTM Alor Setar | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-28 | 2023-06-13 |  | 2023-06-17 |  | Closed | 2023-07-04 | 2023-07-28 | E//Hazida | 2023-07-28 | Celcom Digi_RAN-GCI-TSS-Northern-20230529-0022 | DU00002037898 |  |  | 2023-09-13 | 2023-09-08 |  | Minaret | 30M Minaret | 29 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
3428B4 | pBTS Kampung Tohan (C ) | Sabah |  | Modernization |  | 2023Q3 | HQ 1 | Datasco | 4.6 TSSR Approved | Single Phase Power Site. Site require upgrade to 3phase incoming | 2023-05-22 | 2023-07-13 |  | 2023-07-17 |  | Closed | 2023-07-17 | 2023-07-20 | E//Thien | 2023-07-20 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230508-0004 | DU00002037899 |  |  | 2023-07-26 | 2023-07-20 |  | Minimast | 25m pBTS | 24m | Add R9264M M1821 x3,Dismantle R9224E M1821(AAB) x3
1320H | 99 Speedmart SAUJANA UTAMA | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002037900 | [6 empty] | Small Cell
1565H | 99 Speedmart Taman Sri Murni | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002037901 | [6 empty] | Small Cell
3640A8 | pBTS Tmn Meru Jaya 3 | Central |  | Site Out (Modernization) | Modernization->Delete from system(MOCN Decomm)->Site Out->Replacement, Site Out (Modernization) | 2023Q3 | MA | Magicell | [SiteOut]- 4.5 Pending TSSR Review - Customer | AAU Cannot Install-Change MM to BI¦pBTS loading issue,AAU cannot install | 2023-05-08 | 2023-05-10 |  | 2023-05-25 |  | Closed | 2023-06-10 |  | CD//Nik Ashraf |  | CelcomDigi_RAN_Magicell_TSS_Central_20230511_0008 | DU00002037902 | NIC_S2_Change MM to BI_loading issue_Digi OB |  |  |  |  | Tower | 25m pBTS | 24M
2729A | SEKSYEN 15 | Central |  | Modernization |  | 2023Q4 | SS | Solusi | 4.6 TSSR Approved |  | 2023-05-31 | 2023-06-08 |  | 2023-06-22 |  | Closed | 2023-06-23 | 2023-07-21 | E//Razif | 2023-07-21 | CelcomDigi_RAN_Solusi_TSS_Central_20230620_0002 | DU00002037903 |  |  | 2023-08-02 | 2023-08-01 |  | A-bracket pole | 3m Bipod (RT) | 6M | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8882 S1800(B) x3+R8862A S1800(B6A) x2+R8854D S2100(A4A) x5+R8854 S2600(A4A) x2 | 12
1775B | Kg Sg Cincin Gombak (Billboard) | Central |  | Modernization |  | 2023Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2023-06-26 | 2023-06-28 |  | 2023-06-30 |  | Closed | 2023-07-04 | 2023-07-11 | E//Kok Keen | 2023-07-11 | CelcomDigi_RANMW_AllStar_TSS_Central_20230626_0006 | DU00002037904 |  |  | 2023-07-18 | 2023-07-17 |  | BillBoard | Billboard | 20 | Add R9264H M901821 x3 + R9264M M1821 x3 + R8862A S2601 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1 |  | 123
1069A | Lembah Beringin | Central |  | Modernization |  | 2023Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-10-18 | 2023-10-23 |  | 2024-01-15 |  | Closed | 2024-01-16 | 2024-01-17 | E//Kok Keen | 2024-01-16 | CelcomDigi_RANMW_ASCENTRACK_TSS_Central_20230529_0003 | DU00002037905 |  |  | 2024-01-17 | 2024-01-13 |  | Tower | 60m 3 Legged Tower | 65 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3 |  | 1
1193B | Tg Karang 2 | Central |  | Modernization |  | 2023Q4 | HQ 6 | AllStar | 4.6 TSSR Approved |  | 2023-05-29 | 2023-05-30 |  | 2023-06-01 |  | Closed | 2023-06-02 | 2024-07-10 | E//Razif | 2023-07-26 | CelcomDigi_RAN_AllStar_TSS_Central_20230529_0009 | DU00002037906 |  |  | 2023-07-10 | 2023-07-10 |  |  | 45m Tower | 60 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8860E-GU908 x2+R8862A S1800(B6A) x3+R8840-U216 x3++ |  | 2
4053A | Teck Motor | Northern |  | Modernization |  | 2023Q3 | MH | GCI | 4.6 TSSR Approved |  | 2023-05-02 | 2023-05-29 |  | 2023-05-31 |  | Closed | 2023-06-02 | 2023-07-14 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-GCI-TSS-Northern-20230505-0012 | DU00002037907 |  |  | 2023-07-17 | 2023-07-15 |  | Pole | 3m Boom (RT) | 6 | Add A9732 M1821 x3 + R9264H M901821 x1,Dismantle R8854 S2600(A4A) x3+R8894E M1821(A8A) x7 | 234
4238D | Island City Hotel (REL) | Northern |  | Modernization |  | 2023Q3 | MH | GCI | 4.6 TSSR Approved |  | 2023-05-02 | 2023-05-02 |  | 2023-05-05 |  | Closed | 2023-05-07 | 2023-07-27 | E//Hazida | 2023-07-27 | Celcom Digi_RAN-GCI-TSS-Northern-20230502-0011 | DU00002037908 |  |  | 2023-08-24 | 2023-08-23 |  |  | 3m Boom (RT) | 4.2m | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
1502H | 99 Speedmart SETIA ALAM 4 | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002037909 | [6 empty] | Small Cell
4797C | Harbour Trade Centre (Macallum) (REL) | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-18 |  | 2023-05-23 |  | Closed | 2024-04-08 | 2023-07-22 | E//Hazida | 2023-07-22 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002037910 |  |  | 2023-08-16 | 2023-08-16 |  | Pole | 3m Boom (RT) | 9 | Add R9264H M901821 x3 + R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x3 |  | 123
3293A2 | pBTS Setia Damai Migrant | Central |  | Modernization |  | 2023Q3 | AI | Magicell | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-10 |  | 2023-05-12 |  | Closed | 2023-05-20 | 2023-07-14 | E//Sumitra | 2023-07-14 | CelcomDigi_RAN_Magicell_TSS_Central_20230508_0007 | DU00002037911 |  |  | 2023-06-14 | 2023-06-13 |  | Guide mast | 25m pBTS | 30 | Add R9264H M901821 x4 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x4 |  | 3(S2->S3,S3->S4,S4->S2,Rename sector,Bisector@New S4)
3641A2 | pBTS Kampung Kian Sit | Central |  | Modernization |  | 2023Q4 | AI | YPTT | 4.6 TSSR Approved |  | 2023-07-06 | 2023-07-11 |  | 2023-07-17 |  | Closed | 2023-07-17 | 2023-08-01 | E//Kok Keen | 2023-08-01 | CelcomDigi_RAN_YPTT_TSS_Central_20230708_0014 | DU00002037912 |  |  | 2023-08-05 | 2023-08-04 |  | Watertank | 25m pBTS | 25 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
4101Z | Jln Jelai-Redang Panjang | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002037913 | [6 empty] | Land site
4258A | Mayang Pasir 2 | Northern |  | Modernization |  | 2023Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-05-07 | 2023-05-09 |  | 2023-05-12 |  | Closed | 2023-05-19 | 2023-07-07 | E//Hazida | 2023-07-06 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002037914 |  |  | 2023-07-17 | 2023-07-13 |  | Pole | 3m Bipod (RT) | 7 | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8894E M1821(A8A) x3 |  | 3
4255A | Argyll Road | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-04-28 | 2023-05-24 |  | 2023-05-31 |  | Closed | 2023-06-02 | 2023-07-22 | E//Hazida | 2023-07-22 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230502-0012 | DU00002037915 |  |  | 2023-09-13 | 2023-09-13 |  | Pole | 3m Boom (RT) | 6 | Add R9264M M1821 x5 + R8862A S2601 x2,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 |  | 12
2047A | Guthrie HW Km 18.9 | Central |  | Modernization |  | 2023Q4 | HQ 6 | Magicell | 4.6 TSSR Approved |  | 2023-06-02 | 2023-06-08 |  | 2023-06-14 |  | Closed | 2023-06-15 | 2023-06-24 | E//Kok Keen | 2023-06-23 | CelcomDigi_RAN_Magicell_TSS_Central_20230606_0011 | DU00002037916 |  |  | 2023-09-25 | 2023-07-31 |  | Tower | 76m Tower | 80 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
3431B10 | pBTS Tmn Makmur | Central |  | Modernization |  | 2023Q4 | HQ 6 | Magicell | 4.6 TSSR Approved |  | 2023-05-27 | 2023-05-29 |  | 2023-05-31 |  | Closed | 2023-06-06 | 2023-07-24 | E//Razif | 2023-07-24 | CelcomDigi_RAN_GTSB_TSS_Central_20230529_0010 | DU00002037917 |  |  | 2023-07-26 | 2023-07-18 |  | Watertank | 24m PBTS | 24 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+++R8862A S2100(A6A) x3 |  | 23
1766H | 99 Speedmart Tmn Aman Sekinchan | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002037918 | [6 empty] | Rooftop
1002A | Sri Murni | Central |  | Modernization |  | 2023Q4 | XH | YPTT | 4.6 TSSR Approved |  | 2023-06-14 | 2023-06-21 |  | 2023-06-24 |  | Closed | 2023-06-24 | 2023-07-03 | E//Kok Keen | 2023-07-03 | CelcomDigi_RAN_YPTT_TSS_Central_20230616_0005 | DU00002037919 |  |  | 2023-07-13 | 2023-07-13 |  | H-bracket pole | 3m RT (Wall Mounted Pole) | 5m | Add R9264H M901821 x3,Dismantle R8854E S1800(A6A) x3+R8854D S2100(A4A) x3
3352B | Bukit Tinggi (REL) | Central |  | Modernization |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-07-27 | 2023-07-28 |  | 2023-08-01 |  | Closed | 2023-08-04 | 2023-08-04 | E//Kok Keen | 2023-08-04 | CelcomDigi_RAN_Magicell_TSS_Central_20230729 | DU00002037920 |  |  | 2023-12-17 | 2023-12-11 |  | Monopole | 30m Monopole | 45M | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8882 S1800B(B6B) x3++R8881 S2100 x3+ |  | 2
4467A | Assam Kumbang RCC | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-06-01 | 2023-06-13 |  | 2023-06-20 |  | Closed | 2023-06-27 | 2023-07-15 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002037921 |  |  | 2023-08-10 | 2023-08-02 |  | Tower | Tower | 30 | Add R9264M 1821 x3,Dismantle R8860E-GU908 x1+R8882-GUL1812 x2+R8882 S1800B(B6B) x1+R8862A S2100(A6A) x3
4929M | PH Lower Station | Northern |  | MOCN As-Is |  | 2023Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002037922 | [6 empty] | Micro Cell
1691B | UITM Kolej Delima | Central |  | Modernization |  | 2023Q4 | HQ 6 | GTSB | 4.6 TSSR Approved |  | 2023-06-07 | 2023-06-08 |  | 2024-01-19 |  | Closed | 2024-01-19 | 2024-01-22 | E//Razif | 2024-01-22 | CelcomDigi_RAN_GTSB_TSS_Central_20230609_0027 | DU00002037923 |  |  | 2024-01-24 | 2024-01-19 |  |  | 38m Monopole | 35 | Add R9264H M901821 x3+R8854 S2600 x1,Dismantle R8862A S9000(A6A) x3+R8882-GUL1812 x3+R8862A S2100(A6A) x3+R8882-L268 x1 |  | 3(S1->S3,S2->S1,S3->S2,rename Sector ID,Bisector@New s2)
3462C | Genting RSC 9 IB-2 | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-21 | 2023-07-07 |  | 2023-07-14 |  | Closed | 2023-07-17 | 2024-02-20 | E//Nazrul | 2024-02-19 | CelcomDigi_RAN_GTSB_TSS_Central_20230622_0031 | DU00002037924 |  |  | 2023-10-25 | 2023-10-17 |  |  | In-building system |  | Add + R8862A S2100 x4
1525C | Laman Haris | Central |  | Modernization |  | 2023Q3 | XH | YPTT | 4.6 TSSR Approved |  | 2023-05-16 | 2023-05-25 |  | 2023-05-27 |  | Closed | 2023-05-28 | 2023-07-04 | E//Razif | 2023-07-04 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002037925 |  |  | 2023-07-03 | 2023-07-02 |  | Petronas Pylon | Land site | 28.68m | Add R9264H M901821 x3,Dismantle R9224E M1821(AAB) x3
4077A | Lai Lai Warehouse Mart | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-26 |  | 2023-05-30 |  | Closed | 2023-06-07 | 2023-06-12 | E//Hazida | 2023-06-12 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002037926 |  |  | 2023-07-04 | 2023-07-04 |  | Wall mount boom | 3m Boom (RT) | 19 | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x4 |  | 1
4144Z | Kg Sg Dara Tg Malim _ Hulu Bernam Timor | Central |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002037927 | [6 empty] | Land site
3048M | Anggerik Vanilla Car Park 2 | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002037928 | [6 empty] | Micro Cell
4378C | Aman Central Mall IB | Northern |  | Modernization |  | 2023Q4 | WP | CCSMY | 4.6 TSSR Approved |  | 2023-06-05 | 2023-06-08 |  | 2023-06-12 |  | Closed | 2023-07-31 | 2023-07-31 | E//Nazrul | 2023-07-31 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230606-0022 | DU00002037929 |  |  | 2023-09-20 | 2023-09-19 |  |  | In-building system |  | Add R8862A S1800 x2 + R8862A S2100 x3,Dismantle R8882 S1800B(B6B) x2
2941A | Puncak Alam Shoplot | Central |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-11 |  | 2023-05-15 |  | Closed | 2023-05-17 | 2023-07-11 | E//Razif | 2023-07-11 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002037930 |  |  | 2023-07-07 | 2023-07-06 |  | H-bracket pole | 3m Bipod (RT) | 6m | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8882-GUL1812 x3+R8840-U216 x3 |  | 23
3092C | Sky Avenue RT | Central |  | Modernization |  | 2023Q4 | XH | GTSB | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI,L2600 change to 40M¦Space constraint,S1 can dot install AAU due to complex steel structure inside the camouflage cover | 2023-06-19 | 2023-07-06 |  | 2023-07-13 |  | Closed | 2023-07-14 | 2023-07-17 | E//Kok Keen | 2023-07-17 | CelcomDigi_RAN_GTSB_TSS_Central_20230620_0030 | DU00002037931 | NIC_S1_Change MM to BI,L2600 change to 40M_Space constraint_Digi OB |  | 2023-11-16 | 2023-10-23 |  | Pole | 3m Boom (RT) | 4.6m | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 1
4042A | Lone Pine Carpark | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-23 |  | 2023-05-26 |  | Closed | 2023-06-01 | 2023-10-19 | E//Yadav | 2023-08-03 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002037932 |  |  | 2023-08-25 | 2023-08-25 |  | Pole | 45m 4 Legged Tower | 3 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8882 S2600(B4A) x1+R9224E M1821(AAB) x4 | 13
1016A | Genting Ria Aprtment | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2024-03-11 | 2024-06-05 |  | 2024-06-13 |  | Under Approval | 2024-06-19 | 2024-11-29 | E//Kok Keen | 2024-11-29 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240316 | DU00002037933 |  |  | 2024-12-21 | 2024-12-06 |  | In-Building System | 6m RT (Wall Mounted Pole) | 3m | Add R8862A S9000 x4+A9732 M1821 x1+R8854 S2600x1, Dismantle R8862A S2601(A6A)x1 | 1 | 3
2643B | Setia City Mall Outdoor | Central |  | Modernization |  | 2023Q3 | HQ 6 | Magicell | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-20 |  | 2023-05-24 |  | Closed | 2023-05-25 | 2023-06-03 | E//Razif | 2023-06-01 | CelcomDigi_RAN_Magicell_TSS_Central_20230523_0009 | DU00002037934 |  |  | 2023-06-24 | 2023-06-13 |  | Wall mount boom | 3m RT (Wall Mounted Pole) | 6 | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x1
1710H | 99 Speedmart Sunway Batu Caves | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002037935 | [6 empty] | Small Cell
2680A16 | pBTS Hartalega Bestari Jaya (ENT) | Central |  | Modernization |  | 2023Q3 | HQ 6 | GTSB | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-26 |  | 2023-06-02 |  | Closed | 2023-06-02 | 2023-06-07 | E//Sumitra | 2023-06-07 | CelcomDigi_RAN_GTSB_TSS_Central_20230523_0025 | DU00002037936 |  |  | 2023-07-10 | 2023-06-28 |  | Guide mast | 25m pBTS | 24M | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882 S1800B(B6B) x3+R8881 S2100 x3
1668H | 99 Speedmart Kuala Selangor 3 | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002037937 | [6 empty] | Small Cell
1507H | 99 Speedmart Berjaya Park 2 | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002037938 | [6 empty] | Small Cell
4191D | Menara Zakat (REL) | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-06-20 | 2023-06-22 |  | 2023-06-28 |  | Closed | 2023-07-05 | 2023-08-07 | E//Hazida | 2023-08-03 | Celcom Digi_RAN-GCI-TSS-Northern-20230621-0032 | DU00002037939 |  |  | 2023-09-01 | 2023-08-29 |  | Monopole | 36m Monopole | 35 | Add R9264H M901821 x3 + R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 123
3822B | Bus Station (GPO) IB | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-15 | 2023-06-20 |  | 2023-07-11 |  | Closed | 2023-07-11 | 2024-02-20 | E//Nazrul | 2024-02-19 | CelcomDigi_RAN_GTSB_TSS_Central_20230616_0029 | DU00002037940 |  |  | 2023-10-31 | 2023-10-16 |  |  | In-building system | N/A | Add + R8862A S2100 x2
4092D | Kamunting Industrial Area | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-28 | 2023-05-31 |  | 2023-06-02 |  | Closed | 2023-06-07 | 2023-06-21 | E//Hazida | 2023-06-21 | Celcom Digi_RAN-GCI-TSS-Northern-20230529-0022 | DU00002037941 |  |  | 2023-08-07 | 2023-07-22 |  | Lampole | 24m Lampole | 30M | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
1006A | JBA GOMBAK | Central |  | Modernization |  | 2023Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2023-06-26 | 2023-07-03 |  | 2023-07-04 |  | Closed | 2023-07-04 | 2023-07-12 | E//Kok Keen | 2023-07-11 | CelcomDigi_RAN_Allstar_TSS_Central_20230628_0016 | DU00002037942 |  |  | 2023-07-14 | 2023-07-14 |  | Minimast | Tower | 18 | Add R9264M M1821 x5,Dismantle R8894E M1821(A8A) x3 |  | 12
4975A | Bandar Baru Air Putih | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-27 |  | 2023-05-30 |  | Closed | 2023-06-05 | 2023-06-14 | CD//Rohizam | 2023-06-14 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002037943 |  |  | 2023-07-05 | 2023-07-05 |  | Tower | 60m 3 Legged Tower | 45 | Add A9732 M1821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 123
4883A | Wisma Boon Siew | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-09 |  | 2023-05-09 |  | Closed | 2023-05-13 | 2023-07-22 | E//Hazida | 2023-07-22 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002037944 |  |  | 2023-08-25 | 2023-08-23 |  | H-bracket pole | 2m RT (Boom) | 3 | Add R9264M M1821 x3,Dismantle R8882 S1800B(B6B) x1+R8862A S1800(B6A) x2+R8862A S2100(A6A) x3
1783A | Tmn Bkt Sentosa | Central |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-05-07 | 2023-05-11 |  | 2023-05-15 |  | Closed | 2023-05-17 | 2023-06-10 | E//Sumitra | 2023-06-08 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002037945 |  |  | 2023-07-10 | 2023-06-13 |  | Minimast | 3m RT (Minimast) | 8 | Add R9264M M1821 x8 + R8862A S2600 x4,Dismantle R8894E M1821(A8A) x4 |  | 1234
2326A | IIUM | Central |  | Modernization |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-07-31 | 2023-08-03 |  | 2023-08-07 |  | Closed | 2023-08-08 | 2023-08-15 | E//Kok Keen | 2023-08-15 | CelcomDigi_RAN_Datasco_TSS_Central_20230802 | DU00002037946 |  |  | 2023-11-16 | 2023-10-25 |  | Tower | 45m 3 Legged Tower | 46 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
1796A | Bkt Jelutong Asiaspace | Central |  | Modernization |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-31 | 2023-06-08 |  | 2023-06-10 |  | Closed | 2023-06-10 | 2023-07-17 | E//Razif | 2023-07-14 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002037947 |  |  | 2023-07-05 | 2023-07-05 |  |  | 45m Monopole | 46.2 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3++
3809C2 | pBTS Rimbayu 2 (C ) | Central |  | Modernization |  | 2023Q3 | IE | Solusi | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-23 |  | 2023-05-25 |  | Closed | 2023-05-25 | 2023-07-04 | E//Razif | 2023-07-04 | CelcomDigi_RAN_Solusi_TSS_Central_20230511_0001 | DU00002037948 |  |  | 2023-07-19 | 2023-07-13 |  | Guide mast | 25m pBTS | 30M | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
4006A | Sea View Garden | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-18 |  | 2023-05-21 |  | Closed | 2023-05-23 | 2023-07-25 | E//Hazida | 2023-07-22 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002037949 |  |  | 2023-08-02 | 2023-08-02 |  | Pole | 2m RT (Boom) | 2 | Add R9264H M901821 x2,Dismantle R8882 S1800B(B6B) x2
1247C | Jalan Kebun Nenas | Central |  | Modernization |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-11 | 2023-05-13 |  | 2023-05-17 |  | Closed | 2023-05-17 | 2023-06-09 | E//Razif | 2023-06-09 | CelcomDigi_RANMW_YPTT_TSS_Central_20230508_0002 | DU00002037950 |  |  | 2023-06-11 | 2023-06-10 |  | Monopole | 24m Lampole | 25m | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
4049B | Queensbay Mall RT | Northern |  | Modernization |  | 2023Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-07-18 | 2023-07-17 |  | 2023-07-18 |  | Closed | 2023-07-18 | 2023-07-20 | E//Hazida | 2023-07-18 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002037951 |  |  | 2023-07-25 | 2023-07-18 |  | Pole | 2m RT (Boom) | 3m | Add A9732 M1821 x3,Dismantle R9224E M1821(AAB) x3 | 123
3163B4 | pBTS Pekan Kecil Kuala Sungai | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-25 | 2023-05-29 |  | 2023-06-03 |  | Closed | 2023-06-20 | 2023-06-28 | E//Hazida | 2023-06-27 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002037952 |  |  | 2023-08-30 | 2023-08-29 |  | Tower | 24m PBTS | 25 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R9224E M1821(AAB) x3 |  | 3
1312C | Kg Lombong | Central |  | Modernization |  | 2023Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-05-14 | 2023-05-17 |  | 2023-05-19 |  | Closed | 2023-05-20 | 2023-06-09 | E//Sumitra | 2023-06-09 | CelcomDigi_RAN_Allstar_TSS_Central_20230517_0008 | DU00002037953 |  |  | 2023-06-10 | 2023-06-10 |  | Monopole | 30m Lampole | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
3761A | Jalan Kantan 2H | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-19 | 2023-05-04 |  | 2023-05-07 |  | Closed | 2023-05-12 | 2023-06-03 | E//Kok Keen | 2023-05-29 | CelcomDigi_RAN_Datasco_TSS_Central_20230420_0015 | DU00002037954 |  |  | 2023-06-25 | 2023-06-25 |  | Lampole | 30m Monopole | 24 | Add R9264M M1821 x6,Dismantle R8894E M1821(A8A) x3 |  | 123
4751M | Alor Star New DS Micro | Northern |  | MOCN As-Is |  | 2023Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002037955 | [6 empty] | Micro Cell
4391C | Jalan Jelutong | Northern |  | Modernization |  | 2023Q3 | MH | GTSB | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦unipole, Loading & space issue to add AAU. advise to swap sector 1 to 12 port hybrid & use combiner for BIsector | 2023-05-05 | 2023-05-13 |  | 2023-05-19 |  | Closed | 2023-05-30 | 2023-07-14 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002037956 | NIC_S1_Change MM to BI_loading issue_Digi OB |  | 2023-07-11 | 2023-07-11 |  |  | 3m Boom (RT) | 4M | Add R9264M M1821 x5,Dismantle R8894E M1821(A8A) x4 | 0 | 1
4136D | Langgar Town (REL) | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-06-26 | 2023-06-30 |  | 2023-07-04 |  | Closed | 2023-07-14 | 2023-07-28 | E//Hazida | 2023-07-28 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002037957 |  |  | 2023-09-22 | 2023-09-20 |  | Tower | Tower | 45m | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
3527A2 | pBTS Batu Caves Billboard (GE) | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦pBTS loading issue,AAU cannot install | 2023-05-16 | 2023-05-17 |  | 2023-05-24 |  | Closed | 2023-06-19 | 2023-07-14 | E//Kok Keen | 2023-07-14 | CelcomDigi_RAN_GTSB_TSS_Central_20230517_0024 | DU00002037958 | NIC_S1_Change MM to BI_loading issue_Digi OB |  | 2023-07-10 | 2023-07-07 |  |  | PBTS | 30 | Add R9264M M1821 x1+R9264H M901821 x3+R8862A S2601 x1,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 0 | 2
4227A | SHAHABPERDANA2 | Northern |  | Modernization |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-29 | 2023-06-16 |  | 2023-06-22 |  | Closed | 2023-07-03 | 2023-08-03 | E//Hazida | 2023-08-03 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230530-0021 | DU00002037959 |  |  | 2023-08-30 | 2023-08-29 |  |  | 3m RT (Minimast) | 7 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8854D S2100(A4A) x3 |  | 3
4710C | Relau Blok 33 | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-11 | 2023-05-17 |  | 2023-05-19 |  | Closed | 2023-05-24 | 2023-06-10 | E//Hazida | 2023-06-08 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002037960 |  |  | 2023-07-17 | 2023-07-15 |  |  | 30m Monopole | 6 | Add R9264H M901821 x4 + R9264M M1821 x3 + R8862A S2601 x1,Dismantle R8894E M1821(A8A) x6 |  | 134
4300D | Alor Mengkudu (REL) | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-06-16 | 2023-06-22 |  | 2023-06-24 |  | Closed | 2023-06-27 | 2023-07-31 | E//Hazida | 2023-07-31 | Celcom Digi_RAN-GCI-TSS-Northern-20230616-0030 | DU00002037961 |  |  | 2023-08-28 | 2023-08-26 |  | Monopole | 30M Rapole | 30 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R9224E M1821(AAB) x3 | 123
3445B1 | pBTS Bandar Putera Klang ( R ) | Central |  | Modernization |  | 2023Q3 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-06-26 | 2023-07-07 |  | 2023-07-11 |  | Closed | 2023-07-13 | 2023-07-18 | E//Sumitra | 2023-07-18 | CelcomDigi_RANMW_YPTT_TSS_Central_20230508_0002 | DU00002037962 |  |  | 2023-07-28 | 2023-07-26 |  | Watertank | 25m pBTS | 28 | Add R9264M M1821 x6 + R8862A S2601 x3,Dismantle R8894E M1821(A8A) x3 |  | 123
1687B | Bkt Jelutong U8 Shoplot | Central |  | Modernization |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-06 | 2023-05-09 |  | 2023-05-11 |  | Closed | 2023-05-12 | 2023-07-13 | E//Razif | 2023-07-13 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002037963 |  |  | 2023-06-28 | 2023-06-28 |  | Unipole | 6m Unipole RT | 9m | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3
3463B | Genting Premium Outlet IB | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-07-07 | 2023-07-07 |  | 2023-07-15 |  | Closed | 2023-09-07 | 2023-09-14 | E//Nazrul | 2026-04-17 | CelcomDigi_RAN_GTSB_TSS_Central_20230606_0027 | DU00002037964 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed | 2025-08-12 | 2024-03-14 |  | In-Building System | In-building system | N/A | Add R8892N M1821 x3,Dismantle R8862A S1800(B6A) x3
3130B | Taman Nanyang (HSR) | Central |  | Modernization |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-06-24 | 2023-06-27 |  | 2023-07-03 |  | Closed | 2023-07-06 | 2023-07-13 | E//Kok Keen | 2023-07-13 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_0009 | DU00002037965 | Remarks: Solution TSSR/BOM Changed | 1807 Change RRU solution | 2023-07-28 | 2023-07-28 |  | Lampole | 24m Lampole | 25m | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
1885B | Rasa 2 | Central |  | Modernization |  | 2023Q4 | SS | Futong | 4.6 TSSR Approved |  | 2023-06-20 | 2023-06-21 |  | 2023-06-23 |  | Closed | 2023-06-26 | 2024-01-16 | E//Kok Keen | 2024-01-15 | CelcomDigi_RAN_Futong_TSS_Central_20230622_0003 | DU00002037966 |  |  | 2023-07-30 | 2023-07-22 |  | Pole | 3m Boom (RT) | 3 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x3 | 23
4044A | Wisma Sri Relau | Northern |  | Modernization |  | 2023Q3 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-22 |  | 2023-05-31 |  | Closed | 2023-06-01 | 2023-06-14 | CD//Rohizam | 2023-06-14 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002037967 |  |  | 2023-06-27 | 2023-06-26 |  | Pole | 60m 4 Legged Tower | NA | Add R9264M M1821 x5 + R8862A S2601 x2,Dismantle R8894E M1821(A8A) x3 |  | 13
1447C | Felda Sungai Tengi Selatan | Central |  | Modernization |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-07-03 | 2023-07-06 |  | 2023-07-10 |  | Closed | 2023-07-10 | 2023-07-13 | E//Kok Keen | 2023-07-13 | CelcomDigi_RANMW_Magicell_Central_20230706_0009 | DU00002037968 |  |  | 2023-07-24 | 2023-07-24 |  | Lampole | Land site | 25 | Add R9264H M901821 x3,Dismantle R9224E M1821(AAB) x3
2882A | RSC 2 & 3 Indoor | Central |  | Modernization |  | 2023Q4 | XH | GTSB | 4.6 TSSR Approved |  | 2023-06-23 | 2023-06-28 |  | 2023-07-12 |  | Closed | 2023-07-13 | 2023-07-14 | E//Nazrul | 2023-07-14 | CelcomDigi_RANMW_GTSB_TSS_Central_20230626_0007 | DU00002037969 |  |  | 2023-10-21 | 2023-10-16 |  |  | In-building system |  | Add + R8862A S1800 x2 + R8862A S2100 x2,Dismantle R8882-GUL1812 x2
4144B | Desa Permata 2 | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-01 | 2023-05-12 |  | 2023-05-16 |  | Closed | 2023-05-18 | 2023-07-15 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-GTSB-TSS-Northern-20230502-0012 | DU00002037970 |  |  | 2023-08-18 | 2023-08-17 |  | Monopole | 30m Monopole | 40 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 23
2814C | Double Tree Hilton I-City | Central |  | Remote MOCN |  | 2023Q4 | AI | In-House | 4.6 TSSR Approved |  | 2023-06-07 | 2023-06-13 |  | 2023-07-10 |  | Closed | 2023-07-11 | 2023-07-11 | E//Nazrul | 2023-07-11 | CelcomDigi_RAN_GTSB_TSS_Central_20230609_0027 | DU00002037971 | [6 empty] | Land site |  | Reuse existing RRU
4467C | Taman Kamunting Aman (REL) | Northern |  | Modernization |  | 2023Q4 | MH | GTSB | 4.6 TSSR Approved |  | 2023-05-31 | 2023-06-02 |  | 2023-06-09 |  | Closed | 2023-06-12 | 2023-07-24 | E//Yadav | 2023-07-23 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002037972 |  |  | 2023-08-01 | 2023-08-01 |  | Portables BTS | 3m Boom (RT) | 6M | Add R8852E S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R9224E M1821(AAB) x3 | 13 | 0
4041B | Persiaran Mahsuri 1_2 | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-04-28 | 2023-04-29 |  | 2023-05-04 |  | Closed | 2023-05-05 | 2023-05-25 | CD//Affendi | 2023-05-08 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230426-0005 | DU00002037973 |  |  | 2023-07-01 | 2023-06-27 |  | Minimast | 24m Lampole | 3 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
3810A | Surau Nur Syakirin Bakawali | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦Space limitation | 2023-04-19 | 2023-04-29 |  | 2023-05-13 |  | Closed | 2023-05-17 | 2023-05-30 | E//Kok Keen | 2023-05-29 | CelcomDigi_RAN_Datasco_TSS_Central_20230420_0015 | DU00002037974 | NIC_S2_Change MM to BI_Space constraint_OMNIX (M) |  | 2023-05-31 | 2023-05-30 |  | Minaret | 30m Monopole | 25 | Add R9264H M901821 x3 + R9264M M1821 x2+R8862A S2601 x2,Dismantle R9224E M1821(AAB) x3 |  | 13
3682C | Surau Firdaus | Central |  | Modernization |  | 2023Q2 | HQ 6 | Ascentrack | 4.6 TSSR Approved |  | 2023-05-04 | 2023-05-08 |  | 2023-05-10 |  | Closed | 2023-05-11 | 2023-05-29 | E//Kok Keen | 2023-05-26 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230428_0015 | DU00002037975 |  |  | 2023-05-31 | 2023-05-30 |  | Lampole | 24m Lampole | 24m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
3862B | Penjara Sungai Buloh (REL) | Central |  | Decomm | Modernization->Decomm | 2023Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-08-23 | 2023-06-12 |  | 2023-06-15 | 2023-09-19 | Closed | 2023-09-19 | 2023-06-27 | E//Kok Keen | 2023-09-20 | 0626Central-GTSB-BOQ Template (template) | DU00002037976 |  |  |  |  | 2023-12-08 | Lampole | 24M Lampole | 25M
2000C | Janda Baik Industrial (REL) | Central |  | Modernization |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-06-22 | 2023-06-28 |  | 2023-07-01 |  | Closed | 2023-07-07 | 2023-07-22 | E//Kok Keen | 2023-07-13 | CelcomDigi_RAN_Magicell_TSS_Central_20230623_0016 | DU00002037977 |  |  | 2023-08-18 | 2023-08-15 |  | Tower | 60m 4 Legged Tower | 82 | Add R9224E M1821 x3+R8854E S1800 x3 + R8862A S2601 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
3498B | Jalan Plumbum | Central |  | Modernization |  | 2023Q4 | XH | GTSB | 4.6 TSSR Approved |  | 2023-05-29 | 2023-06-15 |  | 2023-06-22 |  | Closed | 2023-06-23 | 2023-07-21 | E//Razif | 2023-07-20 | CelcomDigi_RAN_GTSB_TSS_Central_20230531_0026 | DU00002037978 |  |  | 2023-07-15 | 2023-07-13 |  | In-Building System | 3m Bipod (RT) | 7 | Add R9264M M1821 x5 + R8862A S2601 x2,Dismantle R8894E M1821(A8A) x3 |  | 13
4802C | Lengkok Burma | Northern |  | Modernization |  | 2023Q3 | MH | GTSB | 4.6 TSSR Approved |  | 2023-05-06 | 2023-05-10 |  | 2023-05-15 |  | Closed | 2023-05-18 | 2023-06-01 | E//Hazida | 2023-06-01 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002037979 |  |  | 2023-08-03 | 2023-08-01 |  | Minimast | 3m Boom (RT) | 4 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
3780A | Masjid Sultan Ibrahim | Central |  | Modernization |  | 2023Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2023-06-10 | 2023-06-14 |  | 2023-10-13 |  | Closed | 2023-10-02 | 2024-02-14 | E//Razif | 2023-11-21 | CelcomDigi_RANMW_AllStar_TSS_Central_20230612_0003 | DU00002037980 |  |  | 2024-01-27 | 2024-01-11 |  | H-bracket pole | 3m Bipod (RT) | 6 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 12
1756C | Kampung Sungai Tua | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-05-16 | 2023-05-13 |  | 2023-05-18 |  | Closed | 2023-05-18 | 2023-06-03 | E//Kok Keen | 2023-05-23 | CelcomDigi_RAN_GTSB_TSS_Central_20230517_0024 | DU00002037981 |  |  | 2023-06-27 | 2023-06-27 |  |  | Land site | 18 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
3535C | Tmn Bukit Rimau Watertank (REL) | Central |  | Decomm | Modernization->Decomm | 2023Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-11 |  | 2023-05-15 | 2023-09-26 | Closed | 2023-05-16 | 2024-06-14 | E//Razif | 2023-06-09 | 0626Central-Allstar-BOQ Template (template) | DU00002037982 |  |  |  |  | 2023-10-02 | Monopole | 30m Monopole | 30
1783B | Karak Highway Bt 18 | Central |  | Modernization |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-07-07 | 2023-07-11 |  | 2023-07-16 |  | Closed | 2023-08-09 | 2023-08-17 | E//Kok Keen | 2023-08-17 | CelcomDigi_RAN_Magicell_TSS_Central_20230707_0021 | DU00002037983 |  |  | 2023-09-07 | 2023-08-17 |  | Tower | Tower | 75 | Add R9264H M901821 x3+R8862A S2601 x1,Dismantle R8882-GUL1812 x2+R8840-U216 x2
1686H | 99 Speedmart Pekan Kerling | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002037984 | [6 empty] | Small Cell
1366A | Sek 3 | Central |  | Modernization |  | 2023Q4 | HQ 6 | Datasco | 4.6 TSSR Approved |  | 2023-05-15 | 2023-05-30 |  | 2023-06-01 |  | Closed | 2023-06-06 | 2023-08-01 | E//Razif | 2023-08-01 | CelcomDigi_RAN_Datasco_TSS_Central_20230517_0022 | DU00002037985 |  |  | 2023-07-11 | 2023-07-10 |  | Minimast | 3m RT (Minimast) | 9 | Add R9264H M901821 x3,Dismantle R8860E-GU908 x3+R8882-GUL1812 x3+R8840-U216 x3++
3838B | Bkt Jelutong (REL) | Central |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-06-06 | 2023-06-09 |  | 2023-06-12 |  | Closed | 2023-06-13 | 2023-07-14 | E//Razif | 2023-07-14 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002037986 |  |  | 2023-11-16 | 2023-11-15 |  | Unipole | Tower | 4 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
4321C | Century Bay (REL) | Northern |  | Modernization |  | 2023Q3 | MH | GTSB | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-09 |  | 2023-05-12 |  | Closed | 2023-05-18 | 2023-05-31 | E//Hazida | 2023-05-31 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002037987 |  |  | 2023-06-27 | 2023-06-26 |  | Wall mount boom | 3m Bipod (RT) |  | Add R9264M M1821 x6+R8862A S2601 x2,Dismantle R8862A S1800(B6A) x4+R8854D S2100(A4A) x4 |  | 12
1162B | Saujana Putra | Central |  | Modernization |  | 2023Q3 | AI | Solusi | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-22 |  | 2023-05-25 |  | Closed | 2023-05-25 | 2023-06-06 | E//Sumitra | 2023-05-26 | CelcomDigi_RANMW_Solusi_TSS_Central_20230511_0001 | DU00002037988 |  |  | 2023-07-05 | 2023-06-28 |  | Wall mount boom | 3m Bipod (RT) | 7m | Add R9264M M1821 x5,Dismantle R8894E M1821(A8A) x3 |  | 12
1933B | Seksyen U8 | Central |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-05-31 | 2023-06-02 |  | 2023-06-08 |  | Closed | 2023-06-09 | 2023-07-14 | E//Razif | 2023-07-14 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002037989 |  |  | 2023-07-08 | 2023-06-28 |  | H-bracket pole | 3m Boom (RT) | 6 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3++
1083A | Bt 15 Jln Kapar | Central |  | Modernization |  | 2023Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-28 | 2023-05-02 |  | 2023-05-05 |  | Closed | 2023-05-06 | 2023-06-28 | CD//Tee | 2023-06-26 | CelcomDigi_RAN_GTSB_TSS_20230505_0023 | DU00002037990 |  |  | 2023-06-16 | 2023-06-16 |  | Monopole | 50m Monopole | 45 | Add A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x3 | 12(FDD MM@new S1/S3)
4045C | Kuala Kangkong | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-06-06 | 2023-06-14 |  | 2023-06-21 |  | Closed | 2023-07-03 | 2023-07-15 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002037991 |  |  | 2023-08-04 | 2023-08-04 |  | Monopole | 30m Monopole | 30 | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8862A S2601(A6A) x1+R8894E M1821(A8A) x4 | 12 | 0
1228A | Kg Jaya Sepakat (Maxis) | Central |  | Modernization |  | 2023Q3 | SS | AllStar | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI,L2600 change to 40M¦Maxis still insisted to limit 3x RRU/Antennas on top | 2023-05-07 | 2023-05-11 |  | 2023-05-15 |  | Closed | 2023-05-16 | 2024-02-16 | E//Razif | 2023-09-22 | CelcomDigi_RAN_AllStar_TSS_Central_20230508_0006 | DU00002037992 | NIC_S3_Change MM to BI,L2600 change to 40M_owner reject_MAXIS |  | 2023-09-30 | 2023-09-27 |  | Tower | Tower | 60 | Add R9264H M901821 x3 + R9264M M1821 x3,Dismantle R8862A S9000(A6A) x3+R8894E M1821(A8A) x3 |  | 123
4140A | ALORSTAR2 | Northern |  | Modernization |  | 2023Q4 | HQ 2 | CCSMY | 4.6 TSSR Approved |  | 2023-05-25 | 2023-06-06 |  | 2023-06-08 |  | Closed | 2023-06-13 | 2023-08-03 | E//Hazida | 2023-08-03 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230526-0019 | DU00002037993 |  |  | 2023-08-28 | 2023-08-28 |  | Pole | 6m RT (Boom) | 6 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3 | 13
2901A | Saujana Putra (Watertank) | Central |  | Modernization |  | 2023Q3 | AI | Solusi | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-24 |  | 2023-06-01 |  | Closed | 2023-06-13 | 2023-07-13 | E//Razif | 2023-07-13 | CelcomDigi_RANMW_Solusi_TSS_Central_20230511_0001 | DU00002037994 |  |  | 2023-07-22 | 2023-07-18 |  | Monopole | 30m Monopole | 45M | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
1222H | 99 Speedmart JLN SG TUA | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002037995 | [6 empty] | Small Cell
2725B | Jln Sg Jati | Central |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-05-06 | 2023-05-13 |  | 2023-05-16 |  | Closed | 2023-05-18 | 2023-06-07 | E//Razif | 2023-06-06 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002037996 |  |  | 2023-06-10 | 2023-06-10 |  | Wall mount boom | 3m Bipod (RT) | 6m | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x2+R8862A S2100(A6A) x3
1963B | Kg Kuantan(Smart) | Central |  | Modernization | Modernization->Maintain USP MOCN->On Hold->Maintain USP MOCN->Modernization | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2025-03-07 | 2025-03-13 |  | 2025-03-21 |  | Closed | 2025-03-24 | 2025-04-15 | E//Razif | 2025-03-24 | SQ202505080070 | DU00002037997 |  |  | 2025-04-27 | 2025-04-27 |  | Tower | Tower | 60M | Add R8894E M1821x1 | 0 | 1
2043A | Bukit Tinggi Junction | Central |  | Modernization |  | 2023Q4 | HQ 6 | Magicell | 4.6 TSSR Approved |  | 2023-07-26 | 2023-07-27 |  | 2023-07-30 |  | Closed | 2023-07-31 | 2023-11-15 | E//Kok Keen | 2023-11-10 | CelcomDigi_RAN_Magicell_TSS_Central_20230727 | DU00002037998 |  |  | 2024-01-21 | 2023-09-27 |  | Tower | 60m 4 Legged Tower | 60 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3++
1651H | 99 Speedmart Bdr Tasik Puteri 1 | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002037999 | [6 empty] | Rooftop
1893B | Bukit Sentosa Town | Central |  | Modernization |  | 2023Q2 | HQ 6 | Datasco | 4.6 TSSR Approved |  | 2023-04-17 | 2023-04-27 |  | 2023-05-04 |  | Closed | 2023-05-18 | 2023-06-03 | E//Kok Keen | 2023-05-26 | CelcomDigi_RAN_Datasco_TSS_Central_20230418_0013 | DU00002038000 |  |  | 2023-07-05 | 2023-06-25 |  | Wall mount boom | 3m Bipod (RT) | 6m | Add A9732 M1821 x3 + R9264M M1821 x1,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x3+R8854D S2100(A4A) x6+R8882 S2600(B4A) x2 | 124
4176B | Masjid Bayan Lepas | Northern |  | Modernization |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI,L2600 change to 40M¦site owner not allow to add AAU | 2023-05-02 | 2023-05-16 |  | 2023-05-18 |  | Closed | 2023-05-23 | 2023-06-22 | E//SoonHo | 2023-06-22 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038001 | NIC_S3_Change MM to BI,L2600 change to 40M_loading issue_OMNIX (M) |  | 2023-07-20 | 2023-07-18 |  | Minaret | 30m Minaret | 30 | Add R9264M M1821 x6 + R8862A S2601 x3,Dismantle R8894E M1821(A8A) x3 |  | 123
4100A | Jln Batu Maung | Northern |  | Modernization |  | 2023Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-04-28 | 2023-05-09 |  | 2023-05-15 |  | Closed | 2023-05-17 | 2023-05-25 | CD//Affendi | 2023-05-18 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230426-0005 | DU00002038002 |  |  | 2023-06-26 | 2023-06-26 |  | Monopole | 30m Monopole | 46m | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x3+R9224E M1821(AAB) x2 | 13
1015A | Awana Golf & Country | Central |  | Modernization |  | 2023Q4 | IE | GTSB | 4.6 TSSR Approved |  | 2023-05-26 | 2023-06-17 |  | 2023-06-22 |  | Closed | 2023-07-03 | 2023-07-10 | E//Kok Keen | 2023-07-10 | CelcomDigi_RAN_GTSB_TSS_Central_20230529_0025 | DU00002038003 |  |  | 2024-03-22 | 2023-07-31 |  | In-Building System | 3m RT (Wall Mounted Pole) | 4m | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R9224E M1821(AAB) x3 | 13
1438H | 99 Speedmart SHAH ALAM SEK 24 | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038004 | [6 empty] | Small Cell
4555D | St Keretapi Taiping (REL) | Northern |  | Modernization |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-07-12 | 2023-07-13 |  | 2023-07-18 |  | Closed | 2023-07-18 | 2023-07-20 | CD//Shamsul | 2023-07-19 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230626-0029 | DU00002038005 |  |  | 2023-08-08 | 2023-07-31 |  | Tower | Land site | 46 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1026A | Genting Hotel | Central |  | Modernization |  | 2023Q4 | HQ 6 | GTSB | 4.6 TSSR Approved |  | 2023-05-25 | 2023-05-31 |  | 2023-06-07 |  | Closed | 2023-06-12 | 2023-07-28 | E//Kok Keen | 2023-07-28 | CelcomDigi_RAN_GTSB_TSS_Central_20230529_0025 | DU00002038006 |  |  | 2023-08-03 | 2023-07-22 |  | In-Building System | 6m RT (Wall Mounted Pole) | 4m | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x5+R8862A S2100(A6A) x3
1540B | Setia Impian | Central |  | Modernization |  | 2023Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-13 |  | 2023-05-17 |  | Closed | 2023-05-24 | 2023-06-07 | E//Razif | 2023-06-07 | CelcomDigi_RAN_Magicell_TSS_20230505_0006 | DU00002038007 |  |  | 2023-06-24 | 2023-06-18 |  | Monople Tree | 30m Monopole Tree | 30 | Add R9264H M901821 x4,Dismantle R8894E M1821(A8A) x4
1967B | Sg Terap (CELCOM) | Central |  | Modernization |  | 2023Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-20 |  | 2023-06-23 |  | Closed | 2023-07-17 | 2023-07-24 | E//Razif | 2023-07-24 | CelcomDigi_RANMW_AllStar_TSS_Central_20230612_0003 | DU00002038008 |  |  | 2023-12-10 | 2023-12-09 |  | Tower | 45m 4 Legged Tower | 45M | Add R9264H M901821 x4 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x2+R8862A S2100(A6A) x4 |  | 4
4008A | Jln Tengah Flats | Northern |  | Modernization |  | 2023Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-10 |  | 2023-05-15 |  | Closed | 2023-05-17 | 2023-05-25 | CD//Affendi | 2023-05-18 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002038009 |  |  | 2023-06-26 | 2023-06-25 |  |  | 60m 4 Legged Tower | 8.8m | Add A9732 M1821 x3,Dismantle R8882 S2600(B4A) x3+R8894E M1821(A8A) x6 | 123
2496A | Sek 6 | Central |  | Modernization |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-05-15 | 2023-07-04 |  | 2023-07-06 |  | Closed | 2023-07-28 | 2023-08-01 | E//Razif | 2023-08-01 | CelcomDigi_RAN_Datasco_TSS_Central_20230517_0022 | DU00002038010 |  |  | 2023-10-07 | 2023-10-06 |  | Monopole | 30m Monopole | 25m | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3
4423C | One Precinct DS | Northern |  | Modernization |  | 2023Q3 | WP | GCI | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-12 |  | 2023-05-22 |  | Rectificating | 2023-05-25 | 2023-06-12 | E//Nazrul | 2023-06-12 | Celcom Digi_RAN-GCI- TSS-Northern-20230509-0016 | DU00002038011 |  |  | 2023-06-25 | 2023-06-25 |  |  | In-building system |  | Add R8862A S1800 x1 + R8862A S2100 x1,Dismantle R8882 S1800B(B6B) x1
3053A | Setia City Mall Shah Alam | Central |  | Remote MOCN |  | 2023Q3 | IE | Magicell | 4.6 TSSR Approved |  | 2023-05-25 | 2023-05-31 |  | 2023-06-20 |  | Closed | 2023-06-26 | 2023-06-28 | E//Nazrul | 2023-06-28 | CelcomDigi_RANMW_Magicell_TSS_Central_20230529_0003 | DU00002038012 | [5 empty] | Portables BTS | In-building system |  | Reuse existing RRU
1611B | Batu 8 Kapar Monopole | Central |  | Modernization |  | 2023Q3 | HQ 6 | Magicell | 4.6 TSSR Approved |  | 2023-05-22 | 2023-05-23 |  | 2023-05-30 |  | Closed | 2023-05-31 | 2023-06-07 | E//Razif | 2023-06-07 | CelcomDigi_RAN_Magicell_TSS_Central_20230523_0009 | DU00002038013 |  |  | 2023-07-03 | 2023-06-28 |  | Tower | 24m Lampole | 50m | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x3+R8894E M1821(A8A) x6 | 123
1465H | 99 Speedmart ALAM BUDIMAN | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038014 | [6 empty] | Small Cell
1757H | 99 Speedmart Kuala Selangor 2 | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038015 | [6 empty] | Rooftop
3031C | Setia Prima (REL) | Central |  | Modernization |  | 2023Q3 | HQ 6 | Magicell | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-08 |  | 2023-05-10 |  | Closed | 2023-05-11 | 2023-06-07 | E//Razif | 2023-06-07 | CelcomDigi_RAN_Magicell_TSS_20230505_0006 | DU00002038016 |  |  | 2023-06-16 | 2023-06-13 |  | Monopole | 30M Monopole | 30 | Add R8852E S9000 x3
1965B | Simpang Punchak Alam (KJS) | Central |  | Modernization |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-17 | 2023-05-22 |  | 2023-05-24 |  | Closed | 2023-06-01 | 2023-10-19 | E//Kok Keen | 2023-10-19 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002038017 |  |  | 2023-07-04 | 2023-07-03 |  | Tower | 60m 4 Legged Tower | 61 | Add R9264H M901821 x1 + R9264M M1821 x3,Dismantle R9224E M1821(AAB) x4
2133A | Surau Al-Hidayah Saujana Utama | Central |  | Modernization |  | 2023Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-05-15 | 2023-06-07 |  | 2023-06-10 |  | Closed | 2023-06-11 | 2023-06-22 | E//Razif | 2023-06-22 | CelcomDigi_RANMW_GTSB_TSS_Central_20230517_0001 | DU00002038018 |  |  | 2023-08-11 | 2023-08-09 |  | Lampole | 30m Lampole | 30M | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
4070A | Desa Permata | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-07 | 2023-05-05 |  | 2023-05-08 |  | Closed | 2023-05-10 | 2023-05-25 | CD//Affendi | 2023-05-11 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002038019 |  |  | 2023-08-22 | 2023-08-22 |  | Minimast | 6m Tripod (RT) | 11 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x4 | 12
4546D | Majestic Height Phase 2 (REL) | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-02 | 2023-05-09 |  | 2023-05-11 |  | Closed | 2023-05-13 | 2023-05-25 | CD//Shamsul | 2023-05-16 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038020 |  |  | 2023-08-21 | 2023-08-18 |  | Guide mast | Land site | 30m | Add R8852E S9000 x2 + A9732 M1821 x2,Dismantle R8862A S2600(A4A) x2+R8894E M1821(A8A) x4 | 12
3764A | Jalan Mahagoni | Central |  | Modernization |  | 2023Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-06-08 | 2023-06-14 |  | 2023-06-17 |  | Closed | 2023-06-18 | 2023-06-26 | E//Kok Keen | 2023-06-26 | CelcomDigi_RANMW_Futong_TSS_Central_20230609_0002 | DU00002038021 |  |  | 2023-07-29 | 2023-07-22 |  | BillBoard | 3m Bipod (RT) | 19 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
4156B | Jln Gurdwara | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-06 | 2023-05-10 |  | 2023-05-12 |  | Closed | 2023-05-15 | 2023-06-01 | E//Hazida | 2023-06-01 | Celcom Digi_RAN-GTSB-TSS-Northern-20230509-0017 | DU00002038022 |  |  | 2023-08-25 | 2023-08-24 |  |  | 3m Boom (RT) | 5 | Add R9264H M901821 x3,Dismantle R9224E M1821(AAB) x3
3129B | Taman Wilayah (HSR) | Central |  | Modernization |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-06-24 | 2023-07-05 |  | 2023-07-09 |  | Closed | 2023-07-11 | 2023-07-14 | E//Kok Keen | 2023-07-14 | CelcomDigi_RANMW_YPTT_TSS_Central_20230626_0006 | DU00002038023 |  |  | 2023-08-10 | 2023-08-09 |  | Minaret | Minaret | 30 | Add R9264H M901821 x3 + R9264M M1821 x2,Dismantle R8882 S1800B(B6B) x3+R8862A S1800(B6A) x1+R8854D S2100(A4A) x4 |  | 13
2641A | Sek24 Housing | Central |  | Modernization |  | 2023Q4 | SS | Solusi | 4.6 TSSR Approved |  | 2023-05-28 | 2023-06-08 |  | 2023-06-21 |  | Closed | 2023-06-26 | 2023-07-21 | E//Razif | 2023-07-20 | CelcomDigi_RAN_Solusi_TSS_Central_20230620_0002 | DU00002038024 |  |  | 2024-02-05 | 2023-08-04 |  | Wall mount boom | 6m RT (Boom) | 3m | Add A9732 M1821 x3,Dismantle R8854E S1800(A6A) x3+R8854D S2100(A4A) x2+A9722 M1821 | 123
1023A | Bukit Idaman | Central |  | Modernization |  | 2023Q4 | SS | YPTT | 4.6 TSSR Approved |  | 2023-06-20 | 2023-06-26 |  | 2023-07-06 |  | Closed | 2023-07-06 | 2023-08-07 | CD//Sapian | 2023-08-04 | CelcomDigi_RANMW_YPTT_TSS_Central_20230622_0004 | DU00002038025 |  |  | 2023-07-20 | 2023-07-18 |  | Minimast | 3m RT (Minimast) | 6m | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3
2137A | 1 Plaza Kuala Selangor | Central |  | Modernization |  | 2023Q4 | AI | AllStar | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI,L2600 change to 40M¦Space constraint， | 2023-05-29 | 2023-05-30 |  | 2023-06-12 |  | Closed | 2023-06-26 | 2023-07-21 | E//Razif | 2023-07-20 | CelcomDigi_RAN_AllStar_TSS_Central_20230529_0009 | DU00002038026 | NIC_S2_Change MM to BI,L2600 change to 40M_Space constraint_Digi OB |  | 2023-07-17 | 2023-07-17 |  |  | 3m Bipod (RT) | 8 | Add R9264M M1821 x5 + R8862A S2601 x2,Dismantle R8894E M1821(A8A) x3+R8892E M1821(BAA) x3 |  | 23
1017A | Serdang Libai | Central |  | Modernization |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-07-17 | 2023-07-27 |  | 2023-07-29 |  | Closed | 2023-08-01 | 2023-08-01 | E//Kok Keen | 2023-08-01 | CelcomDigi_RAN_Magicell_TSS_Central_20230721 | DU00002038027 |  |  | 2023-08-15 | 2023-08-10 |  | Tower | 76m 4 Legged Tower |  | Add R9264H M901821 x3,Dismantle R8860E-GU908 x2+R8882-GUL1812 x3
4183D | Jalan Sungai Pinang Balik Pulau | Northern |  | Modernization |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-12 |  | 2023-05-24 |  | Closed | 2023-05-25 | 2023-06-20 | MSP | 2023-06-20 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038028 |  |  | 2023-07-06 | 2023-07-06 |  | Monopole | 24m Lampole | 30 | Add R9264H M901821 x4+R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
1612H | 99 Speedmart SURIA JELUTONG | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038029 | [6 empty] | Small Cell
4252B | Straits Quay Penang | Northern |  | Modernization |  | 2023Q3 | WP | GCI | 4.6 TSSR Approved |  | 2023-05-08 | 2023-06-14 |  | 2023-06-15 |  | Closed | 2023-07-31 | 2023-08-07 | E//Hazida | 2023-08-03 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038030 |  |  | 2023-08-16 | 2023-08-15 |  | Portables BTS | In-building system |  | Add R8862A S1800 x3 + R8862A S2100 x3,Dismantle R8882 S1800(B) x3
4341H | Alor Setar DS iMACRO | Northern |  | MOCN As-Is |  | 2023Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038031 | [6 empty] | Small Cell
1584C | Bandar Tasik Puteri (REL) | Central |  | Modernization |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-08 |  | 2023-05-12 |  | Closed | 2023-05-13 | 2023-06-05 | E//Kok Keen | 2023-05-24 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230428_0015 | DU00002038032 |  |  | 2023-06-11 | 2023-06-11 |  | Lampole | 24M Lampole | 30 | Add R8852E S9000 x3
1725C | Gamudaland Quayside Mall IB | Central |  | Remote MOCN |  | 2023Q3 | CR | In-House | 4.6 TSSR Approved |  | 2023-05-17 | 2023-06-09 |  | 2023-07-19 |  | Closed | 2023-07-21 | 2023-08-01 | E//Razif | 2023-08-01 | CelcomDigi_RAN_Solusi_TSS_Central_20230511_0001 | DU00002038033 | [5 empty] | Portables BTS | In-building system |  | Reuse existing RRU
2719C | Tmn Sri Batang Kali | Central |  | Modernization |  | 2023Q4 | SS | Futong | 4.6 TSSR Approved |  | 2023-06-17 | 2023-06-21 |  | 2023-06-23 |  | Closed | 2023-07-03 | 2023-07-10 | E//Kok Keen | 2023-07-10 | CelcomDigi_RANMW_Futong_TSS_Central_20230620_0003 | DU00002038034 |  |  | 2023-07-18 | 2023-07-17 |  | Lampole | Land site | 25 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1777B | Selayang Capitol Outdoor | Central |  | Modernization |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-06-19 | 2023-06-21 |  | 2023-06-23 |  | Closed | 2023-06-24 | 2023-07-04 | E//Kok Keen | 2023-07-04 | CelcomDigi_RANMW_YPTT_TSS_Central_20230620_0003 | DU00002038035 |  |  | 2023-08-02 | 2023-08-01 |  | H-bracket pole | 3m Bipod (RT) | 6.4 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 12
3063M | Jalan Dato Yusuf Shahbudin 29b | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038036 | [6 empty] | Small Cell
2828A | Genting Hotel Casino Indoor | Central |  | Modernization | Modernization->On Hold>Modernization | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-07-11 | 2023-07-26 |  | 2023-08-01 |  | Closed | 2023-08-28 | 2023-08-28 | E//Nazrul | 2023-08-28 | CelcomDigi_RAN_GTSB_TSS_Central_20230712 | DU00002038037 |  |  | 2025-11-12 | 2025-11-06 |  | In-Building System | In-building system |  | Add R8862A S1800 x3 + R8862A S2100 x3 + R8862A S2601 x3,Dismantle R8882-GUL1812 x3
2691B | Meru Tower 1 | Central |  | Modernization |  | 2023Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2023-05-11 | 2023-05-15 |  | 2023-05-17 |  | Closed | 2023-05-20 | 2023-07-18 | E//Razif | 2023-07-18 | CelcoDigi_RAN_Magicell_TSS_Central_20230517_0009 | DU00002038038 |  |  | 2023-07-17 | 2023-07-15 |  | Tower | 45m 3 Legged Tower | 60 | Add A9732 M1821 x3 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x4+R8892E M1821(BAA) x4 | 123
4977A | Anson Road | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-31 |  | 2023-06-03 |  | Closed | 2023-06-08 | 2023-06-13 | E//Hazida | 2023-06-13 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038039 |  |  | 2023-09-11 | 2023-09-08 |  | H-bracket pole | 2m RT (Boom) | 3.5 | Add R9264M M1821 x3,Dismantle R9224E M1821(AAB) x3
3174A | Setia Damai Billboard | Central |  | Modernization |  | 2023Q3 | HQ 6 | Magicell | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-12 |  | 2023-05-16 |  | Closed | 2023-05-18 | 2023-06-21 | E//Razif | 2023-06-21 | CelcomDigi_RAN_Magicell_TSS_Central_20230511_0008 | DU00002038040 |  |  | 2023-06-22 | 2023-06-10 |  | Monopole | Billboard | 30 | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x4
3585C | Top Glove Tower IB | Central |  | Modernization |  | 2023Q3 | IE | Magicell | 4.6 TSSR Approved |  | 2023-05-26 | 2023-05-30 |  | 2023-06-17 |  | Closed | 2023-06-20 | 2023-06-28 | E//Razif | 2023-06-21 | CelcomDigi_RAN_GTSB_TSS_Central_20230529_0010 | DU00002038041 |  |  | 2023-07-07 | 2023-06-28 |  | Portables BTS | In-building system | 6th & 17th Floor | Add + R8862A S2100 x2
2028A | Kg Gerachi Jaya | Central |  | Modernization |  | 2023Q4 | SS | Futong | 4.6 TSSR Approved |  | 2023-06-18 | 2023-06-19 |  | 2023-06-23 |  | Closed | 2023-07-03 | 2023-07-10 | E//Kok Keen | 2023-07-10 | CelcomDigi_RAN_Futong_TSS_Central_20230620_0002 | DU00002038042 |  |  | 2023-07-15 | 2023-07-13 |  | Tower | 45m 3 Legged Tower | 61 | Add R9264H M901821 x3,Dismantle R8860E-GU908 x1+R8862A S1800(B6A) x3+R8840-U216 x2+R8840-U216 x1++
4840B | First Avenue IB (Beside trader hotel) | Northern |  | Modernization |  | 2023Q3 | WP | YPTT | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-10 |  | 2023-05-19 |  | Closed | 2023-07-31 | 2023-08-07 | E//Nazrul | 2023-07-31 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0008 | DU00002038043 |  |  | 2023-09-07 | 2023-09-07 |  |  | In-building system | NA | Add R8862A S1800 x3 + R8862A S2100 x3,Dismantle R8882 S1800(B) x3
1077A | BKT RAJA | Central |  | Modernization |  | 2023Q4 | HQ 6 | GTSB | 4.6 TSSR Approved |  | 2023-05-26 | 2023-06-10 |  | 2023-06-14 |  | Closed | 2023-06-17 | 2023-07-20 | E//Razif | 2023-07-20 | CelcomDigi_RAN_GTSB_TSS_Central_20230529_0025 | DU00002038044 |  |  | 2023-07-06 | 2023-07-04 |  | Minimast | 60m 3 Legged Tower | 24 | Add R9264M M1821 x4,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8854D S2100(A4A) x4 |  | 1
4059A | Wisma Katholik | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-13 |  | 2023-05-19 |  | Closed | 2023-05-24 | 2023-06-02 | E//Hazida | 2023-06-02 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038045 |  |  | 2023-08-16 | 2023-08-14 |  | H-bracket pole | 3m Boom (RT) | 4 | Add R9264M M1821 x5+R8862A S2601 x1,Dismantle R9224E M1821(AAB) x4 |  | 3
2648B | SRI PRISTANA WATERTANK | Central |  | Modernization |  | 2023Q3 | XH | GTSB | 4.6 TSSR Approved |  | 2023-06-07 | 2023-06-21 |  | 2023-07-11 |  | Under Approval | 2023-07-13 | 2023-07-15 | E//Kok Keen | 2023-07-14 | CelcomDigi_RANMW_GTSB_TSS_Central_20230609_0002 | DU00002038046 |  |  | 2023-09-25 | 2023-08-24 |  | Monopole | 20m Lampole | 30 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 | 123
4154B | Pintal Tali St | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-17 | 2023-05-18 |  | 2023-05-22 |  | Closed | 2023-05-24 | 2023-07-25 | E//Daniel | 2023-07-25 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002038047 |  |  | 2023-08-18 | 2023-08-18 |  | Minimast | 3m Bipod (RT) | 6 | Add R9264M M1821 x3,Dismantle R8882 S1800(B) x3+R8862A S2100(A6A) x3
4096A | Plaza Gurney | Northern |  | Modernization |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-10 |  | 2023-05-22 |  | Closed | 2023-05-24 | 2023-07-21 | E//Hazida | 2023-07-21 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038048 |  |  | 2023-08-15 | 2023-08-10 |  | Wall mount boom | 3m Boom (RT) | 6 | Add R9264M M1821 x5 + R8862A S2601 x2,Dismantle R8862A S1800(B6A) x6+R8854D S2100(A4A) x4 |  | 13
4018B | Taman Tun Sardon | Northern |  | Modernization |  | 2023Q3 | SM | YPTT | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-24 |  | 2023-05-27 |  | Closed | 2023-06-08 | 2023-07-14 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-YPTT-TSS-Northern-20230509-0010 | DU00002038049 |  |  | 2023-07-27 | 2023-07-18 |  | Tower | Tower | 80 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8882 S1800(B) x3+R8881 S2100 x3 | 23
2967A | Karak HW KM34.8 (Billboard) | Central |  | Modernization |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-07-21 | 2023-07-24 |  | 2023-07-26 |  | Closed | 2023-08-02 | 2023-08-02 | E//Kok Keen | 2023-08-02 | CelcomDigi_RAN_Magicell_TSS_Central_20230722 | DU00002038050 |  |  | 2024-02-20 | 2023-08-23 |  | BillBoard | Billboard | 16 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882 S1800(B) x3+R8881 S2100 x3
1477B | Genting Mushroom 2 (Celcom) | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-09-26 | 2023-09-29 |  | 2023-10-14 |  | Closed | 2023-10-16 | 2023-10-18 | E//Kok Keen | 2023-10-17 | CelcomDigi_RAN_GTSB_TSS_Central_20230927 | DU00002038051 |  |  | 2024-07-03 | 2024-07-01 |  | Monople Tree | 30m Monopole Tree | 25 | Add R9264H M901821 x3 + R8862A S2601 x1,Dismantle R8882-GUL1812 x2
1688H | 99 Speedmart Kalumpang | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038052 | [6 empty] | Small Cell
3453B1 | pBTS Bkt Tinggi (HW) | Central |  | Modernization |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-07-07 | 2023-07-18 |  | 2023-07-21 |  | Closed | 2023-07-26 | 2023-07-27 | E//Kok Keen | 2023-07-27 | CelcomDigi_RAN_Magicell_TSS_Central_20230707_0021 | DU00002038053 |  |  | 2023-08-11 | 2023-08-10 |  | Watertank | 25m pBTS | 24 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882 S1800B(B6B) x3+R8881 S2100 x3
2651A | Mutiara Kemuning 2 | Central |  | Modernization |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-06-21 | 2023-06-30 |  | 2023-07-09 |  | Closed | 2023-07-10 | 2023-07-22 | E//Razif | 2023-07-20 | CelcomDigi_RAN_YPTT_TSS_Central_20230623_0008 | DU00002038054 |  |  | 2023-08-01 | 2023-07-31 |  | Lampole | 20m Lampole | 20 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x3+R9224E M1821(AAB) x2 | 23
2620A | Kemuning KJS | Central |  | Modernization |  | 2023Q3 | HQ 6 | AllStar | 4.6 TSSR Approved |  | 2023-05-11 | 2023-05-19 |  | 2023-05-23 |  | Closed | 2023-05-24 | 2023-06-07 | E//Razif | 2023-06-07 | CelcomDigi_RAN_Allstar_TSS_Central_20230511_0007 | DU00002038055 |  |  | 2023-06-15 | 2023-06-15 |  | Lampole | 24m Lampole | 30 | Add R9264M M1821 x3 + R8862A S2600 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3+
3829B | GENTING HOTEL (IB) | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-07-25 | 2023-07-28 |  | 2023-08-02 |  | Closed | 2023-08-29 | 2023-08-29 | E//Kok Keen | 2023-08-29 | CelcomDigi_RAN_GTSB_TSS_Central_20230726 | DU00002038056 |  |  | 2025-07-29 | 2025-07-23 |  | In-Building System | In-building system |  | Add R8862A S2100 x3
3240B | Gamuda Walk Mall | Central |  | Modernization |  | 2023Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-05-12 | 2023-06-12 |  | 2023-06-15 |  | Closed | 2023-06-20 | 2023-06-20 | E//Nazrul | 2023-06-20 | CelcomDigi_RAN_Allstar_TSS_Central_20230517_0008 | DU00002038057 |  |  | 2024-03-26 | 2023-07-26 |  |  | In-building system |  | Add + R8862A S2100 x2
4064A | Orange Crush | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-05 | 2023-06-21 |  | 2023-06-23 |  | Closed | 2023-06-26 | 2023-07-05 | E//Hazida | 2023-07-05 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002038058 |  |  | 2023-07-17 | 2023-07-13 |  | Wall mount boom | 60m 4 Legged Tower | 3 | Add A9732 M1821 x3,Dismantle R8882 S1800B(B6B) x3+R8854D S2100(A4A) x3 | 123
4197C | Kg Batu 6 Ulu Selama Perak | Northern |  | Modernization |  | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-05-29 | 2023-05-31 |  | 2023-06-04 |  | Closed | 2023-06-08 | 2024-05-15 | CD//Shamsul | 2023-07-18 | Celcom Digi_RAN-YPTT-TSS-Northern-20230531-0015 | DU00002038059 |  |  | 2023-08-04 | 2023-08-02 |  | Monopole | 30m Monopole | 45 | Add R9264M 1821 x3,Dismantle R8894E M1821(A8A) x3
4839B | Komtar Tower | Northern |  | Modernization |  | 2023Q3 | WP | GCI | 4.6 TSSR Approved |  | 2023-06-26 | 2023-07-04 |  | 2023-07-10 |  | Closed | 2023-07-11 | 2024-04-24 | E//Hazida | 2024-04-24 | Celcom Digi_RAN-GCI- TSS-Northern-20230509-0016 | DU00002038060 |  |  | 2024-01-09 | 2023-08-29 |  | Portables BTS | In-building system |  | Add R8894E M1821 x2+R8862A S1800 x1,Dismantle R8882-GUL1812 x1+R8862A S2100(A6A) x1
1797A | Plaza Perangsang | Central |  | Modernization |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-06-22 | 2023-06-30 |  | 2023-07-03 |  | Closed | 2023-07-05 | 2023-07-21 | E//Razif | 2023-07-20 | CelcomDigi_RAN_Datasco_TSS_Central_20230623_0029 | DU00002038061 |  |  | 2023-08-09 | 2023-08-07 |  | Wall mount boom | 3m Bipod (RT) | 5 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8894E M1821(A8A) x3 |  | 12
1204B | GUNUNG NUANG | Central |  | Modernization |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-22 | 2023-05-24 |  | 2023-05-26 |  | Closed | 2023-05-29 | 2023-07-07 | E//Razif | 2023-07-07 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002038062 |  |  | 2023-08-16 | 2023-08-15 |  | Monople Tree | 30m Monopole Tree | 30.4 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2 + R8862A S2601 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 3
4040A | Northern Elevator | Northern |  | Modernization |  | 2023Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-05-11 | 2023-07-07 |  | 2023-07-10 |  | Rectificating | 2023-07-11 | 2023-07-14 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002038063 |  |  | 2023-07-31 | 2023-07-18 |  |  | 6m RT (Boom) | 18 | Add R9264H M901821 x1 + R9264M M1821 x7,Dismantle R8894E M1821(A8A) x5+R9224E M1821(AAB) x3 |  | 1234
1156A | Btg. Berjuntai | Central |  | Modernization |  | 2023Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-27 | 2023-05-10 |  | 2023-05-12 |  | Closed | 2023-05-16 | 2023-06-07 | E//Razif | 2023-06-07 | CelcomDigi_RAN_GTSB_TSS_Central_20230428_0022 | DU00002038064 |  |  | 2023-06-24 | 2023-06-22 |  | Rooftop | 60m 4 Legged Tower | 26 | Add R9264M M1821 x8 + R8862A S2601 x4,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x2+R8862A S2100(A6A) x4 |  | 1234
3425B11 | pBTS Taman Apas Permai (KM) | Sabah |  | Modernization | Modernization->On Hold->Modernization->Site Out->On Hold->Modernization | 2023Q4 | MS | Datasco | 4.6 TSSR Approved | TI Issue to proceed. Site require upgrade to 3phase incoming | 2023-06-20 | 2023-07-05 |  | 2023-07-07 |  | Under Approval | 2023-07-10 | 2023-07-21 | E//Thien | 2023-07-20 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007 | DU00002038065 | Remarks: Solution TSSR/BOM Changed |  | 2025-07-06 | 2025-06-18 |  | Watertank | 24m PBTS | 25 | Reuse Existing RRU | 0 | 0
1075C | Kuarters Institusi Pendidikan | Central |  | Modernization |  | 2023Q4 | HQ 6 | GTSB | 4.6 TSSR Approved |  | 2023-06-17 | 2023-06-22 |  | 2023-06-24 |  | Closed | 2023-06-26 | 2023-07-21 | E//Razif | 2023-07-20 | CelcomDigi_RAN_GTSB_TSS_Central_20230620_0030 | DU00002038066 |  |  | 2023-07-26 | 2023-07-18 |  | Lampole | 18m Lampole | 19M | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
4715B | Kg Jelai | Northern |  | Modernization |  | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-05-28 | 2023-06-13 |  | 2023-06-15 |  | Closed | 2023-06-20 | 2023-07-14 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-YPTT-TSS-Northern-20230530-0014 | DU00002038067 |  |  | 2023-07-27 | 2023-07-26 |  |  | 60m 3 Legged Tower | 45 | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x3 |  | 2
4067A | Wisma Tylo | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-11 | 2023-05-12 |  | 2023-05-22 |  | Closed | 2023-05-25 | 2023-07-04 | E//SoonHo | 2023-07-04 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038068 |  |  | 2023-07-03 | 2023-07-03 |  | Pole | 60m 4 Legged Tower | 4 | Add A9732 M1821 x3 + R9264M M1821 x1,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8854 S2600(A4A) x3+R8894E M1821(A8A) x4+R9224E M1821(AAB) x3 | 123
4089B | St Han Chiang | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-13 | 2023-05-19 |  | 2023-05-24 |  | Closed | 2023-06-01 | 2023-06-11 | CD//Affendi | 2023-06-11 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038069 |  |  | 2023-07-23 | 2023-07-22 |  | Monopole | 24m Lampole | 24 | Add R8894E M1821 x3,Dismantle R8882 S1800B(B6B) x3+R8881 S2100 x3+
3255A | MASJIDKSELANGOR1 | Central |  | Modernization |  | 2023Q4 | HQ 6 | AllStar | 4.6 TSSR Approved |  | 2023-05-25 | 2023-05-27 |  | 2023-05-30 |  | Closed | 2023-05-31 | 2023-07-21 | E//Razif | 2023-07-20 | CelcomDigi_RAN_AllStar_TSS_Central_20230529_0009 | DU00002038070 |  |  | 2023-07-21 | 2023-07-13 |  | Minaret | 30m Minaret | 29 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8854D S2100(A4A) x3 |  | 3
1802B | Mushroom Farm Genting | Central |  | Modernization |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-06-20 | 2023-07-06 |  | 2023-07-10 |  | Closed | 2023-07-17 | 2023-07-20 | E//Kok Keen | 2023-07-20 | CelcomDigi_RAN_Magicell_TSS_Central_20230622_0015 | DU00002038071 |  |  | 2024-03-01 | 2024-02-27 |  | Monople Tree | 45m Tower | 45m | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882-GUL1812 x2+R8840-U216 x2++
1966B | Pekan Kuala Selangor | Central |  | Decomm | Modernization->Decomm | 2023Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2023-08-18 | 2023-05-31 |  |  | 2024-02-14 |  | 2024-02-15 | 2024-04-29 | E//Razif | 2024-02-16 | CelcomDigi_RAN_AllStar_TSS_Central_20230529_0009/CelcomDigi_RAN_AllStar_TSS_Central_20240618 | DU00002038072 |  |  |  |  | 2024-03-21 |  | 3m Bipod (RT) | 5
3839C | Taman Ria Sekinchan | Central |  | Modernization |  | 2023Q4 | YZ | YPTT | 4.6 TSSR Approved |  | 2023-07-08 | 2023-07-14 |  | 2023-07-18 |  | Closed | 2023-07-20 | 2023-07-26 | E//Razif | 2023-07-26 | CelcomDigi_RAN_YPTT_TSS_Central_20230710 | DU00002038073 |  |  | 2023-12-06 | 2023-12-06 |  | Lampole | 30m Monopole | 30 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x3 | 12
1889H | Dewan Agong Tuanku Canselor OD IB | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038074 | [6 empty] | Land site
1266C | Bandar Putera 2 | Central |  | Modernization |  | 2023Q3 | AI | AllStar | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦Space issue,if use bi-sector solution need to reduce the feeder numer,L2600 1T1R? | 2023-05-10 | 2023-05-19 |  | 2023-05-24 |  | Closed | 2023-06-21 | 2023-06-27 | E//Razif | 2023-06-27 | CelcomDigi_RANMW_Allstar_TSS_Central_20230511_0002 | DU00002038075 | NIC_S2_Change MM to BI_Space constraint_NAZA COMMUNICATIONS |  | 2023-07-11 | 2023-07-10 |  | Monopole | 30m Monopole | 30 | Add R9264M M1821 x2+R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 | 0 | 23
4769B | Jln Tun Razak (maxis) | Northern |  | Modernization |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦Maxis not allowed add AAU | 2023-06-12 | 2023-06-14 |  | 2023-06-20 |  | Closed | 2023-06-23 | 2023-09-07 | E//Hazida | 2023-09-07 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230613-0025 | DU00002038076 | NIC_S2_Change MM to BI_owner reject_MAXIS |  | 2023-09-12 | 2023-08-31 |  | Lampole | 36m Monopole Tree | 30m | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 13
1524C | Eco Ardence_4 | Central |  | Modernization |  | 2023Q3 | AI | Magicell | 4.6 TSSR Approved |  | 2023-04-28 | 2023-05-05 |  | 2023-05-08 |  | Closed | 2023-05-10 | 2023-06-07 | E//Razif | 2023-06-07 | CelcomDigi_RAN_Magicell_TSS_Central_20230502_0006 | DU00002038077 |  |  | 2023-07-19 | 2023-06-13 |  | Lampole | Land site | 30M | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
4088Z | T3E_0628_KgSgSiputeh | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038078 | [6 empty] | 76m 4 Legged Tower
4005A | Merit Sri Sayang | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-25 | 2023-05-31 |  | 2023-06-02 |  | Closed | 2023-06-06 | 2023-08-03 | E//Yadav | 2023-08-03 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002038079 |  |  | 2023-08-17 | 2023-08-16 |  | H-bracket pole | 3m Boom (RT) | 3m | Add A9732 M1821 x1 + R9264M M1821 x2,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3 | 2
2583A | Sg Besar 2 (Maxis) | Central |  | Modernization |  | 2023Q4 | HQ 6 | Magicell | 4.6 TSSR Approved |  | 2023-05-30 | 2023-06-02 |  | 2023-06-08 |  | Closed | 2023-06-12 | 2023-07-21 | E//Razif | 2023-07-21 | CelcomDigi_RAN_Magicell_TSS_Central_20230601_0011 | DU00002038080 |  |  | 2023-09-30 | 2023-09-26 |  | Tower | 60m 3 Legged Tower | 75m | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 |  | 23
2659B | Kg Tok Muda | Central |  | Modernization | Modernization->On hold->Modernization | 2023Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-29 | 2023-05-05 |  | 2023-05-08 |  | Closed | 2023-05-10 | 2023-06-03 | CD//Syafiq | 2023-05-18 | CelcomDigi_RAN_GTSB_TSS_20230505_0023 | DU00002038081 |  |  | 2023-12-14 | 2023-10-26 |  | Tower | 60m 3 Legged Tower | 60 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8882-GUL1812 x3+R8840-U216 x3 |  | 23
4042C | Kamunting Lama | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-28 | 2023-05-31 |  | 2023-06-06 |  | Closed | 2023-06-13 | 2023-07-15 | E//Daniel | 2023-07-14 | Celcom Digi_RAN-GCI-TSS-Northern-20230529-0022 | DU00002038082 |  |  | 2023-08-07 | 2023-07-25 |  | H-bracket pole | 3m Bipod (RT) | 5 | Add R8852E S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 13 | 0
1639H | 99 Speedmart BDR RIMBAYU | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038083 | [6 empty] | Small Cell
1434H | 99 Speedmart BDR SERI COALFIELDS | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038084 | [6 empty] | Small Cell
1101A | Menara Acmar V6 | Central |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-08 |  | 2023-05-31 |  | Closed | 2023-05-18 | 2023-07-27 | E//Razif | 2023-07-27 | CelcomDigi_RANMW_YPTT_TSS_Central_20230505_0001 | DU00002038085 |  | 13052023 TSSR Rejected. 1. propose antenna height wrong - at all related pages 2. sec 2 - schematic wrong 3. height and tilt not follow RF para 4. SOW pages not complete. 5. dcpd10b photo? 6. BBU proposal not complete 7. weight summary missing info | 2023-06-25 | 2023-06-22 |  | Pole | 3m Boom (RT) | 7 | Add R9264M M1821 x5 + R8862A S2601 x1,Dismantle R8894E M1821(A8A) x4 |  | 13
1206H | 99 Speedmart BATANG KALI 1 | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038086 | [6 empty] | Small Cell
3762A | Jalan Seroja 1 Batang Kali | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-19 | 2023-05-02 |  | 2023-05-06 |  | Closed | 2023-05-08 | 2023-06-22 | E//Kok Keen | 2023-06-22 | CelcomDigi_RAN_Datasco_TSS_Central_20230419_0014 | DU00002038087 |  |  | 2023-05-30 | 2023-05-27 |  | Pole | 3m Boom (RT) | 7m | Add A9732 M1821 x3,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 | 123
1435B | Kesas Bkt Kemuning | Central |  | Modernization |  | 2023Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-18 |  | 2023-05-25 |  | Closed | 2023-05-26 | 2023-06-07 | E//Razif | 2023-06-07 | CelcomDigi_RANMW_Allstar_TSS_Central_20230511_0002 | DU00002038088 |  |  | 2023-06-25 | 2023-06-22 |  | Monopole | 30m Monopole | 30 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8882 S2600(B4A) x1+R9224E M1821(AAB) x4 +R8862A S9000(A6A) x1 | 13
4277B | Kuala Kedah 2 (Celcom) | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-31 | 2023-06-02 |  | 2023-06-07 |  | Closed | 2023-06-10 | 2023-07-28 | E//Daniel | 2023-07-28 | Celcom Digi_RAN-GCI-TSS-Northern-20230601-0023 | DU00002038089 |  |  | 2023-08-28 | 2023-08-26 |  | Tower | 45m 3 Legged Tower | 60 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
4805B | G Hotel IB | Northern |  | Modernization | Modernization->On Hold->Modernization | 2023Q3 | WP | YPTT | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-12 |  | 2023-05-17 |  | Closed | 2023-08-18 | 2023-08-19 | E//Nazrul | 2023-08-18 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0008 | DU00002038090 |  |  | 2024-08-26 | 2024-08-20 |  | In-Building System | In-building system |  | Add R8862A S2100 x3+R8862A S2601 x3+R8862A S1800 x3,Dismantle R8882 S1800(B) x2
1964B | Kg Bt Badong | Central |  | Modernization |  | 2023Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-29 | 2023-05-09 |  | 2023-05-11 |  | Closed | 2023-05-11 | 2023-07-28 | E//Zulakmar | 2023-07-28 | CelcomDigi_RAN_GTSB_TSS_20230505_0023 | DU00002038091 |  |  | 2023-06-15 | 2023-06-13 |  | Tower | 45m Tower | 60m | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2600 x2,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 |  | 12
2609A2 | pBTS Kg Bagan Pasi (MS) | Central |  | Modernization |  | 2023Q4 | HQ 6 | AllStar | 4.6 TSSR Approved |  | 2023-05-30 | 2023-05-31 |  | 2023-06-02 |  | Closed | 2023-06-03 | 2023-07-21 | E//Razif | 2023-07-21 | CelcomDigi_RAN_AllStar_TSS_Central_20230531_0010 | DU00002038092 |  |  | 2023-07-17 | 2023-07-13 |  | Watertank | Land site | 24 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3
2675C | Kg Bukit Cherakah | Central |  | Modernization |  | 2023Q3 | MA | GTSB | 4.6 TSSR Approved |  | 2023-04-29 | 2023-05-04 |  | 2023-05-07 |  | Closed | 2023-05-09 | 2023-06-14 | E//Kok Keen | 2023-06-14 | CelcomDigi_RAN_GTSB_TSS_20230505_0023 | DU00002038093 |  |  | 2023-06-16 | 2023-06-16 |  | Tower | Land site | 46m | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2,Dismantle R8894E M1821(A8A) x3 | 2
4582A | Kamunting 2 RCC | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-06-06 | 2023-06-15 |  | 2023-06-21 |  | Closed | 2023-07-03 | 2023-07-14 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002038094 |  |  | 2023-08-03 | 2023-07-31 |  | Wall mount boom | Tower | 8 | Add R8852E S9000 x2+R9264H M901821 x2+A9732 M1821 x2+R8862A S2601x1,Dismantle R8860E-GU908 x1+R8882-GUL1812 x3+R8854D S2100(A4A) x3 | 34 | 0
4991C | Lintang Sungai Pinang | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-04-28 | 2023-05-19 |  | 2023-05-23 |  | Closed | 2023-05-29 | 2023-07-14 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230426-0005 | DU00002038095 |  |  | 2023-07-15 | 2023-07-13 |  | Pole | Rooftop | 2.5 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8894E M1821(A8A) x3 |  | 13
2630B | Bdr Nusa Rhu MP | Central |  | Modernization |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-17 | 2023-05-26 |  | 2023-05-29 |  | Closed | 2023-05-29 | 2023-07-07 | E//Razif | 2023-07-07 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002038096 |  |  | 2023-07-03 | 2023-07-02 |  | Lampole | 24m Lampole | 24 | Add R9264H M901821 x3,Dismantle R8892N M1821(BAB) x3
4810A | Eastern&Oriental Hotel | Northern |  | Modernization |  | 2023Q3 | WP | GCI | 4.6 TSSR Approved |  | 2023-06-20 | 2023-06-15 |  | 2023-07-10 |  | Rectificating | 2023-07-31 | 2023-07-31 | E//Nazrul | 2023-07-31 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038097 |  |  | 2024-01-30 | 2024-01-17 |  | Portables BTS | In-building system |  | Add R8852E S9000 x2+R8862A S2100 x2+R8862A S1800 x2,Dismantle R8882-GUL1812 x1+R8882 S1800(B) x1 | 0 | 0
2470A | Kulliyah A&E | Central |  | Modernization |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-07-31 | 2023-07-28 |  | 2023-08-01 |  | Closed | 2023-08-03 | 2023-08-04 | E//Kok Keen | 2023-08-04 | CelcomDigi_RAN_Datasco_TSS_Central_20230802 | DU00002038098 |  |  | 2024-02-29 | 2024-02-26 |  | Monople Tree | 30m Monopole | 46 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3
4952C | Taman Nuri | Northern |  | Modernization |  | 2023Q4 | HQ 2 | CCSMY | 4.6 TSSR Approved |  | 2023-05-25 | 2023-06-02 |  | 2023-06-08 |  | Closed | 2023-06-13 | 2023-08-08 | E//Hazida | 2023-08-08 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230526-0019 | DU00002038099 |  |  | 2023-09-09 | 2023-08-29 |  | Wall mount boom | 30m Monopole | 6 | Add R9264M M1821 x4 + R8862A S2601 x4,Dismantle R8862A S1800(B6A) x4+R8854D S2100(A4A) x4
4112B | Batu Maung Monopole (Maxis) | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-18 |  | 2023-05-22 |  | Closed | 2023-05-29 | 2023-06-21 | CD//Shukri | 2023-06-21 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002038100 |  |  | 2023-07-08 | 2023-07-07 |  | Monopole | 20m Monopole | 25m | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3+R8882 S1800B(B6B) x2+R8862A S1800(B6A) x2+R8862A S2100(A6A) x3
4251H | 99 Speedmart PK Tmn Kamunting Mutiara | Northern |  | MOCN As-Is |  | 2023Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038101 | [6 empty] | Small Cell
2430A | Jln 29 Selayang Baru | Central |  | Modernization |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-06-19 | 2023-06-23 |  | 2023-06-27 |  | Closed | 2023-06-27 | 2023-07-07 | E//Kok Keen | 2023-07-06 | CelcomDigi_RANMW_YPTT_TSS_Central_20230620_0003 | DU00002038102 |  |  | 2023-07-21 | 2023-07-18 |  | In-Building System | 3m Boom (RT) | 6.4 | Add R9264M M1821 x6+R8862A S2601 x2,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8862A S2100(A6A) x1+R8840-U216 x3++ |  | 24(S3->S4,S4->S3,Rename sectorID,Bisector@New S2S3)
2666B | MSJD Saugjana | Central |  | Modernization |  | 2023Q3 | HQ 6 | GTSB | 4.6 TSSR Approved |  | 2023-06-07 | 2023-06-21 |  | 2023-06-24 |  | Closed | 2023-06-26 | 2023-07-06 | E//Razif | 2023-07-05 | CelcomDigi_RANMW_GTSB_TSS_Central_20230609_0002 | DU00002038103 |  |  | 2023-07-14 | 2023-07-14 |  | Lampole | 20m Lampole | 19 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
3950B4 | pBTS Menawan Wood | Sarawak |  | Modernization | Modernization->Site Out->Modernization->On Hold->Modernization | 2026 | SH | Datasco | 4.6 TSSR Approved | Solution changed add L26 in 2026 | 2023-06-22 | 2023-06-30 |  | 2023-07-04 |  | Under Approval | 2023-07-07 | 2023-07-15 | E//Hannah | 2023-07-14 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230516-0006 | DU00002038104 | [5 empty] | Tower | 25m pBTS | 25m | Add R8862A S9000x3+R9264M M1821x3, Dismantle R8862A S1800(B6A)x3R8862A S2100(A6A)x3
3613B | AEON D Kayangan Outdoor | Central |  | Modernization |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-05-26 | 2023-06-13 |  | 2023-06-16 |  | Closed | 2023-06-23 | 2023-07-21 | E//Razif | 2023-07-21 | CelcomDigi_RAN_Datasco_TSS_Central_20230529_0023 | DU00002038105 |  |  | 2023-12-13 | 2023-10-12 |  | Pole | 3m Boom (RT) | 5.5 | Add R9264M M1821 x6 + R8862A S2601 x3,Dismantle R8894E M1821(A8A) x3 |  | 123
4590C | Sg Nibong (REL) | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-19 |  | 2023-05-22 |  | Closed | 2023-05-24 | 2023-06-11 | E//Hazida | 2023-06-11 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038106 |  |  | 2023-08-30 | 2023-08-16 |  | Minaret | 30m Minaret | 30 | Add R8852E S9000 x4 + R8894E M1821 x4,Dismantle R8862A S1800(B6A) x4+R8862A S2100(A6A) x3+R8862A S2100(A6A) x1
1158A | Tanjung Karang | Central |  | Modernization |  | 2023Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2023-05-31 | 2023-06-01 |  | 2023-06-05 |  | Closed | 2023-06-06 | 2023-07-21 | E//Razif | 2023-07-21 | CelcomDigi_RAN_AllStar_TSS_Central_20230529_0009 | DU00002038107 |  |  | 2023-07-07 | 2023-07-05 |  | In-Building System | 3m RT (Minimast) | 6 | Add R9264H M901821 x4,Dismantle R9224E M1821(AAB) x4
2440A | Elmina Sg Buloh | Central |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-05-27 | 2023-05-27 |  | 2023-05-30 |  | Closed | 2023-05-31 | 2023-07-25 | E//Kok Keen | 2023-07-18 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002038108 |  |  | 2023-09-01 | 2023-08-10 |  | Tower | 45m Tower | 46m | Add R9264H M901821 x3 + R9264M M1821 x2,Dismantle R8894E M1821(A8A) x2+R9224E M1821(AAB) x1 |  | 13
2041A | UITM Palapes | Central |  | Modernization |  | 2023Q4 | HQ 6 | GTSB | 4.6 TSSR Approved |  | 2023-05-22 | 2023-05-25 |  | 2023-06-07 |  | Closed | 2023-06-08 | 2023-07-21 | E//Razif | 2023-07-21 | CelcomDigi_RAN_GTSB_TSS_Central_20230523_0025 | DU00002038109 |  |  | 2024-02-13 | 2024-01-22 |  | Monople Tree | 30m Monopole | 30m | Add R9224E M1821 x3+R8854E S1800 x3,Dismantle R8882-GUL1812 x3+R8882 S1800(B) x1+R8862A S2100(A6A) x3
4446C | Taman Kumbar Apartment | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-20 | 2023-05-27 |  | 2023-06-01 |  | Closed | 2023-06-05 | 2023-06-17 | CD//Quah | 2023-06-15 | Celcom Digi_RAN-GTSB-TSS-Northern-20230509-0017 | DU00002038110 |  |  | 2023-08-14 | 2023-07-31 |  | Pole | 3m Bipod (RT) | 4M | Add A9732 M1821 x3 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x4 | 123
2676B | JALAN Nakhoda kanan | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-05-23 | 2023-05-27 |  | 2023-06-09 |  | Closed | 2023-06-09 | 2023-06-13 | E//Kok Keen | 2023-06-13 | CelcomDigi_RAN_GTSB_TSS_Central_20230529_0025 | DU00002038111 |  |  | 2023-06-26 | 2023-06-26 |  | Lampole | 24m Lampole | 20M | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1790A | Sek 13 Shah Alam | Central |  | Modernization |  | 2023Q4 | HQ 6 | Datasco | 4.6 TSSR Approved |  | 2023-05-16 | 2023-05-25 |  | 2023-05-29 |  | Closed | 2023-05-30 | 2023-07-21 | E//Razif | 2023-07-21 | CelcomDigi_RAN_Datasco_TSS_Central_20230517_0022 | DU00002038112 |  |  | 2023-07-06 | 2023-07-05 |  | Pole | 6m RT (Boom) | 6m | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3++
1198B | Jln Padang Gajah | Central |  | Modernization |  | 2023Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-29 | 2023-05-05 |  | 2023-05-07 |  | Closed | 2023-05-10 | 2023-06-14 | E//Kok Keen | 2023-06-14 | CelcomDigi_RAN_GTSB_TSS_20230505_0023 | DU00002038113 |  |  | 2023-06-12 | 2023-06-10 |  | Monopole | 45m Monopole | 45M | Add R9264H M901821 x3,Dismantle R8892E M1821(BAA) x3
2671B | Taman Rahmat Jaya | Central |  | Modernization |  | 2023Q4 | XH | Magicell | 4.6 TSSR Approved |  | 2023-05-24 | 2023-05-25 |  | 2023-05-27 |  | Closed | 2023-05-28 | 2023-06-07 | E//Kok Keen | 2023-06-07 | CelcomDigi_RAN_GTSB_TSS_Central_20230529_0010 | DU00002038114 |  |  | 2023-07-14 | 2023-07-14 |  | Lampole | 24m Lampole | 24 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1395H | 99 Speedmart Jln Pekan Meru 2 | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038115 | [6 empty] | Small Cell
2527A | Fruit Valley | Central |  | Modernization |  | 2023Q3 | HQ 6 | GTSB | 4.6 TSSR Approved |  | 2023-05-15 | 2023-06-12 |  | 2023-06-15 |  | Closed | 2023-06-17 | 2023-06-26 | E//Kok Keen | 2023-06-26 | CelcomDigi_RAN_GTSB_TSS_Central_20230517_0024 | DU00002038116 |  |  | 2023-07-10 | 2023-07-05 |  | Tower | 76m 3 Legged Tower | 70 | Add R9264H M901821 x3 + R8862A S2601 x1,Dismantle R8882-GUL1812 x2+R8840-U216 x2
3090B | Pinggiran Batu Caves (REL) | Central |  | Modernization |  | 2023Q4 | XH | AllStar | 4.6 TSSR Approved |  | 2023-06-20 | 2023-06-21 |  | 2023-06-23 |  | Closed | 2023-06-23 | 2023-07-07 | CD//Bala | 2023-06-29 | CelcomDigi_RANMW_AllStar_TSS_Central_20230620_0004 | DU00002038117 |  |  | 2023-07-18 | 2023-07-17 |  | Lampole | 24m Lampole | 30 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 | 12(S1->S3,S2->S1，S3->S2,rename sector ID,FDD MM@ new S1S3)
4025A | Msian Credit | Northern |  | Modernization |  | 2023Q3 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-05-06 | 2023-05-15 |  | 2023-05-18 |  | Closed | 2023-05-25 | 2023-06-28 | E//Hazida | 2023-06-21 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0008 | DU00002038118 |  |  | 2023-07-11 | 2023-07-07 |  | Wall mount boom | 60m 4 Legged Tower | 3 | Add R9264M M1821 x5 + R8862A S2601 x2,Dismantle R8882-GUL1812 x3+R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 |  | 13
4311D | Jazz Hotel RT | Northern |  | Modernization |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-16 |  | 2023-05-18 |  | Closed | 2023-05-22 | 2023-07-21 | E//Hazida | 2023-07-21 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038119 |  |  | 2023-08-18 | 2023-08-18 |  | Unipole | 3m Boom (RT) | 3m | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 |  | 23
4003A | Park Royal | Northern |  | Modernization |  | 2023Q3 | HQ 5 | GTSB | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-09 |  | 2023-05-11 |  | Closed | 2023-05-13 | 2023-07-22 | E//Hazida | 2023-07-22 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002038120 |  |  | 2023-08-19 | 2023-08-19 |  |  | 6m RT (Boom) | 7 | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8882 S1800(B) x1+R8882 S1800B(B6B) x1+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3 |  | 3
1791A | Sek 25 Sri Muda | Central |  | Modernization |  | 2023Q4 | SS | YPTT | 4.6 TSSR Approved |  | 2023-06-19 | 2023-06-26 |  | 2023-07-10 |  | Closed | 2023-07-11 | 2023-09-07 | MSP | 2023-09-07 | CelcomDigi_RANMW_YPTT_TSS_Central_20230620_0003 | DU00002038121 |  |  | 2023-08-06 | 2023-08-02 |  | H-bracket pole | 20m Monopole | 7m/3m | Add R9264M M1821 x7,Dismantle R8894E M1821(A8A) x4 |  | 123
1780B | Tmn Sri Gombak Fasa 8 | Central |  | Modernization |  | 2023Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2023-06-26 | 2023-07-05 |  | 2023-07-07 |  | Closed | 2023-07-07 | 2023-07-13 | E//Kok Keen | 2023-07-13 | CelcomDigi_RAN_Allstar_TSS_Central_20230623_0015 | DU00002038122 |  |  | 2023-07-25 | 2023-07-22 |  |  | 3m Boom (RT) | 4 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x2,Dismantle R8882-GUL1812 x2+R8840-U216 x2++ |  | 1
1430B | Seksyen 7 Watertank | Central |  | Modernization |  | 2023Q4 | HQ 6 | Datasco | 4.6 TSSR Approved |  | 2023-05-15 | 2023-06-19 |  | 2023-06-20 |  | Closed | 2023-06-21 | 2023-07-22 | E//Razif | 2023-07-21 | CelcomDigi_RAN_Datasco_TSS_Central_20230517_0022 | DU00002038123 |  |  | 2023-07-11 | 2023-07-10 |  |  | 30m Monopole | 30 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3
1346A | Giant | Central |  | Modernization |  | 2023Q4 | SS | Solusi | 4.6 TSSR Approved |  | 2023-05-27 | 2023-06-01 |  | 2023-06-21 |  | Closed | 2023-06-23 | 2023-07-22 | E//Razif | 2023-07-21 | CelcomDigi_RAN_Solusi_TSS_Central_20230620_0002 | DU00002038124 |  |  | 2023-07-26 | 2023-07-18 |  | Wall mount boom | 3m Boom (RT) | 6M | Add R9264M M1821 x6 + R8862A S2601 x3,Dismantle R8894E M1821(A8A) x3 |  | 123
2045A | Dusun Eco | Central |  | Modernization |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-06-24 | 2023-07-07 |  | 2023-07-10 |  | Closed | 2023-07-25 | 2023-07-28 | E//Kok Keen | 2023-07-26 | CelcomDigi_RAN_Magicell_TSS_Central_20230626_0017 | DU00002038125 |  |  | 2023-09-04 | 2023-08-29 |  | Tower | 60m 3 Legged Tower | 60 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8860E-GU908 x1+R8882-GUL1812 x3+R8840-U216 x3++
4370C | Changkat Bukit Belah | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-02 | 2023-05-04 |  | 2023-05-08 |  | Closed | 2023-05-09 | 2023-06-17 | E//Hazida | 2023-06-16 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038126 |  |  | 2023-07-17 | 2023-07-13 |  | Minimast | Monopole | 8 | Add R9264H M901821 x3 + R9264M M1821 x3 + R8862A S2601 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 123
3777A | Surau Al-Furqan | Central |  | Modernization |  | 2023Q3 | AI | YPTT | 4.6 TSSR Approved |  | 2023-05-17 | 2023-05-24 |  | 2023-05-26 |  | Closed | 2023-05-31 | 2023-07-13 | E//Razif | 2023-07-13 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002038127 |  |  | 2023-07-15 | 2023-07-14 |  | Lampole | 20m Lampole | 21 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8892E M1821(BAA) x3 |  | 23
3265A | VLSGBURUNG | Central |  | Modernization |  | 2023Q4 | HQ 6 | AllStar | 4.6 TSSR Approved |  | 2023-06-02 | 2023-06-06 |  | 2023-06-07 |  | Closed | 2023-06-08 | 2023-07-28 | E//Razif | 2023-07-28 | CelcomDigi_RAN_AllStar_TSS_Central_20230606_0011 | DU00002038128 |  |  | 2023-06-28 | 2023-06-27 |  | Tower | 30m Monopole | 70 | Add R9264H M901821 x4,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8854D S2100(A4A) x4
4145A | TMNMUHIBAH | Northern |  | Modernization |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-26 | 2023-06-21 |  | 2023-06-23 |  | Closed | 2023-07-03 | 2023-07-28 | E//Hazida | 2023-07-28 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230529-0020 | DU00002038129 |  |  | 2023-08-28 | 2023-08-27 |  | In-Building System | 6m Tripod (RT) | 6 | Add R9264H M901821 x4 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 |  | 1(S1->S2,S2->S3,S3->S4,S4->S1,rename sector ID,Bisector@New S2)
4955A | Kepala Batas Airport | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-31 | 2023-06-02 |  | 2023-06-07 |  | Closed | 2023-06-13 | 2023-08-08 | E//Hazida | 2023-08-03 | Celcom Digi_RAN-GCI-TSS-Northern-20230601-0023 | DU00002038130 |  |  | 2023-09-11 | 2023-08-29 |  | Tower | 45m 3 Legged Tower | 35 | Add R9264H M901821 x3 + R9264M M1821 x3 + R8862A S2601 x1,Dismantle R9224E M1821(AAB) x5 |  | 123
1152A | Sekinchan Town | Central |  | Modernization |  | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-07-05 | 2023-07-10 |  | 2023-07-12 |  | Closed | 2023-07-14 | 2023-07-25 | E//Sumitra | 2023-07-25 | CelcomDigi_RAN_YPTT_TSS_Central_20230707_0013 | DU00002038131 |  |  | 2023-08-07 | 2023-08-06 |  | Unipole | 3m Bipod (RT) | 6m | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8894E M1821(A8A) x3 |  | 13
4068D | Koperasi Polis Diraja Pinang | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-17 | 2023-06-06 |  | 2023-06-09 |  | Closed | 2023-06-13 | 2023-07-25 | E//Hazida | 2023-07-22 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002038132 |  |  | 2023-09-13 | 2023-09-11 |  | Minimast | 3m Boom (RT) | 7 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x2,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x4+R9224E M1821(AAB) x2 | 23
1615B | Bandar Puteri Klang(ZED) | Central |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-05-06 | 2023-05-11 |  | 2023-05-13 |  | Closed | 2023-05-16 | 2023-06-10 | E//Razif | 2023-06-07 | CelcomDigi_RANMW_YPTT_TSS_Central_20230508_0002 | DU00002038133 |  |  | 2023-06-12 | 2023-06-12 |  | H-bracket pole | 3m Bipod (RT) | 7m | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3
4062A | Kompleks Midlands | Northern |  | Modernization |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-23 |  | 2023-05-25 |  | Closed | 2023-05-26 | 2023-07-22 | E//Hazida | 2023-07-22 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038134 |  |  | 2023-09-02 | 2023-08-23 |  | Rooftop | 45m 4 Legged Tower | 36 | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8882-GUL1812 x3+R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 |  | 2
2771B | LATAR HW Puncak Alam | Central |  | Modernization |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-06-16 | 2023-06-13 |  | 2023-06-16 |  | Closed | 2023-07-26 | 2023-07-28 | E//Razif | 2023-07-28 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002038135 |  | 2306 - TSSR reject again by ZTE 1806 TSSR Reject | 2023-08-07 | 2023-08-06 |  | Tower | Tower | 45 | Add R9264H M901821 x3 + R9264M M1821 x2,Dismantle R8894E M1821(A8A) x3 |  | 23
3263B | AEON Shah Alam | Central |  | Modernization |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-06-22 | 2023-06-26 |  | 2023-07-04 |  | Closed | 2023-07-06 | 2023-07-11 | E//Nazrul | 2023-07-10 | CelcomDigi_RAN_Datasco_TSS_Central_20230623_0029 | DU00002038136 |  |  | 2023-08-30 | 2023-08-28 |  |  | In-building system | NA | Reuse existing RRU
1770B | Genting Sempah | Central |  | Modernization |  | 2023Q4 | HQ 6 | Magicell | 4.6 TSSR Approved |  | 2023-07-12 | 2023-07-17 |  | 2023-07-24 |  | Closed | 2023-07-26 | 2023-07-27 | E//Kok Keen | 2023-07-27 | CelcomDigi_RAN_Magicell_TSS_Central_20230714 | DU00002038137 |  |  | 2023-10-12 | 2023-10-07 |  | Tower | 76m 3 Legged Tower | 70m | Add R9264H M901821 x3,Dismantle R8860E-GU908 x3+R8882-GUL1812 x1+R8882 S1800B(B6B) x2+R8840-U216 x3++
3748C3 | pBTS Hospital Semporna (KM) | Sabah |  | Modernization | Modernization->On Hold->Modernization->Site Out->On Hold->Modernization | 2026 | AD | Futong | 4.6 TSSR Approved | TI Issue to proceed. Site require upgrade to 3phase incoming | 2023-06-22 | 2023-06-16 |  | 2023-06-22 |  | Closed | 2023-06-21 | 2023-07-07 | E//Hannah | 2023-07-07 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0011 | DU00002038138 |  |  | 2026-02-02 | 2025-06-18 |  | Tower | 25m pBTS | 30 | Reuse Existing RRU | 0 | 123
4885A | Queensbay Mall IB | Northern |  | Modernization |  | 2023Q3 | WP | CCSMY | 4.6 TSSR Approved |  | 2023-07-24 |  |  | 2023-07-24 |  | Closed | 2023-07-31 | 2023-07-31 | E//Nazrul | 2023-07-31 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002038139 |  |  | 2023-07-27 | 2023-07-22 |  |  | In-building system |  | Reuse existing RRU
1624C | Tateyama Auto (REL) | Central |  | Modernization |  | 2023Q4 | HQ 6 | GTSB | 4.6 TSSR Approved |  | 2023-05-22 | 2023-05-23 |  | 2023-05-29 |  | Closed | 2023-05-30 | 2023-07-20 | E//Razif | 2023-07-20 | CelcomDigi_RAN_GTSB_TSS_Central_20230523_0025 | DU00002038140 |  |  | 2023-07-08 | 2023-07-05 |  | Lampole | Land site | 19m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
4973B | Tajar | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-06-21 | 2023-06-27 |  | 2023-06-26 |  | Closed | 2023-07-05 | 2023-08-03 | E//Hazida | 2023-08-03 | Celcom Digi_RAN-GCI-TSS-Northern-20230622-0033 | DU00002038141 |  |  | 2023-08-28 | 2023-08-28 |  | Tower | Tower | 60 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x3 | 23
4678C | Penang Bridge BT (REL) | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-18 |  | 2023-05-31 |  | Closed | 2023-06-05 | 2023-07-14 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002038142 |  |  | 2023-07-13 | 2023-07-12 |  | BillBoard | Billboard | 31 | Add R9264M M1821 x6 + R8862A S2601 x3,Dismantle R9224E M1821(AAB) x3 |  | 123
1881A | Selayang Summit Square | Central |  | Modernization |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-06-19 | 2023-06-21 |  | 2023-06-23 |  | Closed | 2023-06-24 | 2023-06-28 | E//Nazrul | 2023-06-23 | CelcomDigi_RAN_YPTT_TSS_Central_20230620_0006 | DU00002038143 |  |  | 2023-07-17 | 2023-07-17 |  | Portables BTS | In-building system |  | Add R8862A S2100 x1,Dismantle R8840-U216 x1
1446H | 99 Speedmart BDR PUTERA | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038144 | [6 empty] | Small Cell
1671H | 99 Speedmart Tmn Selangat Jeram | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038145 | [6 empty] | Rooftop
1624H | 99 Speedmart Johan Setia | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038146 | [6 empty] | Small Cell
1146A | Kuala Kubu Baru Tower | Central |  | Modernization |  | 2023Q4 | HQ 6 | Futong | 4.6 TSSR Approved |  | 2023-07-20 | 2023-07-21 |  | 2023-07-26 |  | Closed | 2023-07-27 | 2023-07-27 | E//Kok Keen | 2023-07-27 | CelcomDigi_RAN_Futong_TSS_Central_20230721 | DU00002038147 |  |  | 2023-08-17 | 2023-08-10 |  | Tower | 48m 3 Legged Tower | 48 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 1
1475H | 99 Speedmart PEKAN MERU 1 | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038148 | [6 empty] | Small Cell
4666A | Anak Bukit | Northern |  | Modernization |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-25 | 2023-05-30 |  | 2023-06-02 |  | Closed | 2023-06-07 | 2023-07-14 | E//Hazida | 2023-06-13 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230526-0019 | DU00002038149 |  |  | 2023-08-28 | 2023-08-26 |  | Tower | 48m 3 Legged Tower | 47 | Add R8852E S9000 x1 + A9732 M1821 x2 + R9264H M901821 x2,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 | 12
1154A | Sekinchan | Central |  | Modernization |  | 2023Q4 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-07-07 | 2023-07-20 |  | 2023-07-25 |  | Closed | 2023-07-26 | 2023-07-27 | CD//Sapian | 2023-07-27 | CelcomDigi_RAN_YPTT_TSS_Central_20230708_0014 | DU00002038150 |  |  | 2023-08-13 | 2023-08-09 |  | Tower | 60m 4 Legged Tower | 46m | Add R9264H M901821 x3,Dismantle R8860E-GU908 x1+R8894E M1821(A8A) x3
1188B | Puratos Selayang | Central |  | Modernization |  | 2023Q4 | XH | YPTT | 4.6 TSSR Approved |  | 2023-06-20 | 2023-06-22 |  | 2023-06-24 |  | Closed | 2023-06-24 | 2023-07-04 | E//Kok Keen | 2023-07-04 | CelcomDigi_RAN_YPTT_TSS_Central_20230622_0007 | DU00002038151 |  |  | 2023-07-13 | 2023-07-12 |  | H-bracket pole | 3m Bipod (RT) | 3m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
2598B | Giant Sek13 Shah Alam | Central |  | Modernization |  | 2023Q4 | HQ 6 | Datasco | 4.6 TSSR Approved |  | 2023-05-16 | 2023-06-23 |  | 2023-06-26 |  | Closed | 2023-07-06 | 2023-07-25 | E//Razif | 2023-07-25 | CelcomDigi_RAN_Datasco_TSS_Central_20230517_0022 | DU00002038152 |  |  | 2023-08-30 | 2023-08-24 |  | Pole | 3m Bipod (RT) | 7m | Add R9264M M1821 x4,Dismantle R8882 S1800(B) x3+R8862A S1800(B6A) x2+R8882 S2600(B4A) x1 |  | 3
2479A | NS HW KM402 (MAXIS) | Central |  | Site Out (Modernization) | Modernization->Site Out->Replacement, Site Out (Modernization) | 2023Q4 | MA | GCI | 4.6 TSSR Approved |  | 2023-06-27 | 2023-07-26 |  | 2023-08-01 |  | Closed | 2023-08-08 | 2023-08-15 | E//Kok Keen | 2023-09-25 | CelcomDigi_RANMW_Ascentrack_TSS_Central_20230703_0009 | DU00002038153 | [5 empty] | Monopole | 45m Monopole | 46
4584B | Kg Banting (Celcom) | Central |  | Modernization |  | 2023Q4 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-07-08 | 2023-07-24 |  | 2023-07-28 |  | Closed | 2023-07-31 | 2023-12-22 | E//Razif | 2023-12-20 | CelcomDigi_RAN_CCSMY_TSS_Central_20230710 | DU00002038154 |  |  | 2023-12-21 | 2023-12-11 |  | Tower | 45m 4 Legged Tower | 49M | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
4673A | Pekan Simpang Kuala | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-14 |  | 2023-06-16 |  | Closed | 2023-06-20 | 2023-07-28 | E//Hazida | 2023-07-28 | Celcom Digi_RAN-GCI-TSS-Northern-20230612-0026 | DU00002038155 |  |  | 2023-08-28 | 2023-08-24 |  | Rooftop | 60m 4 Legged Tower | 24 | Add A9732 M1821 x3,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3 | 123
4351H | 99 SM PG BDR BARU AIR PUTIH | Northern |  | MOCN As-Is |  | 2023Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038156 | [6 empty] | Rooftop
3104A | BKT Cherakah (REL) | Central |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-06-01 | 2023-06-01 |  | 2023-06-07 |  | Closed | 2023-06-08 | 2023-07-14 | E//Razif | 2023-07-14 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002038157 |  |  | 2023-09-26 | 2023-09-26 |  | Monopole | 30m Monopole | 31 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8840-U216 x3++
2933A | Taman Selatan | Central |  | Modernization |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-06 |  | 2023-05-09 |  | Closed | 2023-05-09 | 2023-06-22 | CD//Norhaliza | 2023-06-22 | CelcomDigi_RAN_YPTT_TSS_20230505_0002 | DU00002038158 |  |  | 2023-06-09 | 2023-06-08 |  | Unipole | 30m Monopole | 6M | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
1891B | Sg Tengi (Celcom) | Central |  | Modernization |  | 2023Q4 | HQ 1 | Magicell | 4.6 TSSR Approved |  | 2023-06-28 | 2023-07-10 |  | 2023-07-12 |  | Closed | 2023-07-18 | 2023-07-20 | E//Kok Keen | 2023-07-20 | CelcomDigi_RAN_Magicell_TSS_Central_20230630_0019 | DU00002038159 |  |  | 2023-09-11 | 2023-09-10 |  | Tower | 45m 3 Legged Tower | 70 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3 | 1
4082B | Kg Seronok | Northern |  | Modernization |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-05-02 | 2023-05-09 |  | 2023-05-08 |  | Closed | 2023-05-12 | 2023-06-17 | E//Hannah | 2023-06-15 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038160 |  |  | 2023-07-06 | 2023-07-03 |  | Monopole | 30m Monopole | 36 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8892E M1821(BAA) x3 | 13(S1->S3,S2->S1,S3->S2,rename sectorID, MM@ new S2/S3)
2821B | First World Hotel Tower 2 | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-16 | 2023-07-21 |  | 2023-07-26 |  | Closed | 2023-07-28 | 2023-07-28 | E//Nazrul | 2023-07-28 | CelcomDigi_RAN_GTSB_TSS_Central_20230620_0030 | DU00002038161 |  |  | 2024-03-17 | 2024-02-27 |  | Portables BTS | In-building system |  | Add R8852E S9000 x5+R8892N M1821 x5,Dismantle R8892E M1821(BAA) x5
1701A | Kerling (Trunk) | Central |  | Modernization |  | 2023Q4 | HQ 6 | Ascentrack | 4.6 TSSR Approved |  | 2023-06-08 | 2023-06-17 |  | 2023-06-20 |  | Closed | 2023-06-23 | 2023-06-28 | E//Kok Keen | 2023-06-28 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230609_0021 | DU00002038162 |  |  | 2023-07-18 | 2023-07-18 |  | Tower | 60m 3 Legged Tower | 75 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
4876B | Sunshine Farlim 2 | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-17 | 2023-05-22 |  | 2023-05-25 |  | Closed | 2023-05-29 | 2023-07-25 | E//Hazida | 2023-07-21 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002038163 |  |  | 2023-10-02 | 2023-09-27 |  | Pole | 6m RT (Boom) | 7 | Add R9264M M1821 x1+A9732 M1821 x3,Dismantle R8894E M1821(A8A) x4 | 134
1576B5 | pBTS Arulmigu Sri Muneeswarar Temple | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-05-16 | 2023-05-13 |  | 2023-05-18 |  | Closed | 2023-05-18 | 2023-07-15 | E//Kok Keen | 2023-07-14 | CelcomDigi_RAN_GTSB_TSS_Central_20230517_0024 | DU00002038164 |  |  | 2023-07-05 | 2023-07-04 |  |  | 25m pBTS | 24 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3
3583B | Kampung Jaya Setia | Central |  | Modernization |  | 2023Q3 | YZ | GTSB | 4.6 TSSR Approved |  | 2023-05-04 | 2023-05-10 |  | 2023-05-13 |  | Closed | 2023-05-15 | 2023-09-13 | CD//Syafiq | 2023-09-13 | CelcomDigi_RAN_GTSB_TSS_20230505_0023 | DU00002038165 |  |  | 2023-09-29 | 2023-09-05 |  | Tower | 60m 3 Legged Tower | 65 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8881 S2100 x3
1782B | Berjuntai Bestari(UNISEL) | Central |  | Modernization |  | 2023Q3 | HQ 6 | GTSB | 4.6 TSSR Approved |  | 2023-04-28 | 2023-05-10 |  | 2023-05-13 |  | Closed | 2023-05-15 | 2023-07-22 | CD//Syafiq | 2023-07-21 | CelcomDigi_RAN_GTSB_TSS_20230505_0023 | DU00002038166 |  |  | 2023-06-24 | 2023-06-22 |  | Tower | 76m 3 Legged Tower | 80 | Add A9732 M1821 x3,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3 | 123
4625D | TM Teluk Bahang (Rel) | Northern |  | Modernization |  | 2023Q3 | SM | GCI | 4.6 TSSR Approved |  | 2023-05-17 | 2023-05-20 |  | 2023-05-24 |  | Under Approval | 2023-05-25 | 2023-07-22 | E//Hazida | 2023-07-22 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038167 |  |  | 2023-08-23 | 2023-08-10 |  |  | Tower | 47 | Add R9264H M901821 x3,Dismantle R9224E M1821(AAB) x3
3746C2 | pBTS Alpha Seiko Plastics | Central |  | Modernization |  | 2023Q3 | IE | Magicell | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦pBTS loading issue,AAU cannot install | 2023-05-13 | 2023-05-15 |  | 2023-05-24 |  | Closed | 2023-06-09 | 2023-07-13 | E//Razif | 2023-07-12 | CelcomDigi_RANMW_Magicell_TSS_Central_20230517_0002 | DU00002038168 | NIC_S3_Change MM to BI_loading issue_Digi OB |  | 2023-07-06 | 2023-07-05 |  | Tower | 25m pBTS | 24 | Add R9264M M1821 x3 + R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x2 | 0 | 123
1328H | 99 Speedmart BATANG KALI 2 | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038169 | [6 empty] | Small Cell
4652A | TmnRakyat Mergong (maxis) | Northern |  | Modernization |  | 2023Q4 | ZA | CCSMY | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI,L2600 change to 40M¦Maxis reject add AAU,Bi sector only can install 1 sector | 2023-06-12 | 2023-06-07 |  | 2023-06-12 |  | Closed | 2023-06-15 | 2023-08-08 | E//Hazida | 2023-08-08 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230613-0025 | DU00002038170 | NIC_S3_Change MM to BI,L2600 change to 40M_owner reject_MAXIS |  | 2023-09-20 | 2023-09-20 |  |  | 45m Monopole Tree | 50 | Add R9264M M1821 x1+R9264H M901821 x3+R8862A S2600 x1,Dismantle R9224E M1821(AAB) x3 |  | 1
4094A | Kassim Mustafa | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-17 |  | 2023-05-22 |  | Closed | 2023-05-29 | 2023-07-05 | CD//Affendi | 2023-07-05 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002038171 |  |  | 2023-07-03 | 2023-07-03 |  | Pole | 6m RT (Boom) | 6m | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 12
2776B | Denai Alam 2 | Central |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-06-06 | 2023-06-10 |  | 2023-06-14 |  | Closed | 2023-06-17 | 2023-07-13 | E//Razif | 2023-07-13 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002038172 |  |  | 2023-07-15 | 2023-07-14 |  | Monopole | 45m Monopole | 12 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x2,Dismantle R8882 S1800B(B6B) x3+R8862A S1800(B6A) x1+R8862A S2100(A6A) x4 | 23
1612C | Politeknik Sabak Bernam (REL) | Central |  | Modernization |  | 2023Q4 | HQ 6 | CCSMY | 4.6 TSSR Approved |  | 2023-07-09 | 2023-07-12 |  | 2023-07-17 |  | Closed | 2023-07-18 | 2023-07-26 | E//Razif | 2023-07-26 | CelcomDigi_RAN_CCSMY_TSS_Central_20230710 | DU00002038173 |  |  | 2023-08-04 | 2023-08-02 |  | Tower | Lampole | 62m | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2,Dismantle R8894E M1821(A8A) x3 | 3
4126B | Taman Desa Green | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-12 |  | 2023-05-15 |  | Closed | 2023-05-18 | 2023-06-01 | E//Hazida | 2023-05-31 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002038174 |  |  | 2023-06-27 | 2023-06-27 |  | Pole | 3m Bipod (RT) | 3 | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x4
1422A | Kundang | Central |  | Modernization |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-04-28 | 2023-05-10 |  | 2023-05-13 |  | Closed | 2023-05-15 | 2023-05-25 | E//Kok Keen | 2023-05-25 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230428_0015 | DU00002038175 |  |  | 2023-05-27 | 2023-05-27 |  | H-bracket pole | 3m Boom (RT) | 4.5m | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8840-U216 x3
3181B6 | pBTS Masjid Kunak | Sabah |  | Modernization |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved | Single Phase Power Site. Site require upgrade to 3phase incoming | 2023-06-16 | 2023-06-19 |  | 2023-06-22 |  | Closed | 2023-06-23 | 2023-08-09 | E//Nizar | 2023-08-04 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0010 | DU00002038176 |  |  | 2023-09-19 | 2023-09-13 |  | Watertank | 25m pBTS | 25m | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8882 S1800(B) x3+R8862A S1800(B6A) x1+R8854D S2100(A4A) x4+R8862A S2600(A4A) x1 | 23
4100Z | Jln Kamunting Selama | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038177 | [6 empty] | Land site
4267A | Bukit Bendera Penang | Northern |  | Modernization |  | 2023Q3 | BY | CCSMY | 4.6 TSSR Approved | ¦ 0123 - TP rejected by BM, not allow to carry cabinet using tram. Need revise power solution. | 2023-11-21 | 2023-11-21 |  | 2023-12-04 |  | Closed | 2023-12-05 | 2023-12-13 | E//Hazida | 2023-12-12 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002038178 |  |  | 2024-03-27 | 2024-01-13 |  | Pole | 3m Bipod (RT) | Antenna Wall Mounted | Add R9264H M901821 x2,Dismantle R8882 S1800(B) x1+R8862A S1800(B6A) x1+R8862A S2100(A6A) x2
1038C | GPO Shah Alam | Central |  | Modernization |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-06-21 | 2023-07-06 |  | 2023-07-10 |  | Closed | 2023-07-17 | 2023-07-25 | E//Razif | 2023-07-25 | CelcomDigi_RAN_Datasco_TSS_Central_20230622_0028 | DU00002038179 |  |  | 2023-09-21 | 2023-09-18 |  | Pole | 3m Boom (RT) | 6m | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2,Dismantle R8894E M1821(A8A) x3 | 3
4753M | LCF Foodcourt | Northern |  | MOCN As-Is |  | 2023Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038180 | [6 empty] | Micro Cell
2007B | Tmn Bunga Raya | Central |  | Modernization |  | 2023Q2 | HQ 6 | Datasco | 4.6 TSSR Approved |  | 2023-05-26 | 2023-05-31 |  | 2023-06-06 |  | Closed | 2023-06-06 | 2023-06-12 | E//Kok Keen | 2023-06-12 | CelcomDigi_RAN_Datasco_TSS_Central_20230428_0018 | DU00002038181 |  |  | 2023-08-24 | 2023-08-17 |  | Tower | Tower | 77 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2,Dismantle R8894E M1821(A8A) x3 | 2
4672C | Idaman Lavendar | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-24 |  | 2023-06-02 |  | Closed | 2023-06-07 | 2023-06-21 | CD//Affendi | 2023-06-21 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002038182 |  |  | 2023-07-05 | 2023-07-05 |  |  | 3m Boom (RT) | 5M | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x3+R9224E M1821(AAB) x2 | 123
4169B | Tmn cheeseman | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-06-20 | 2023-06-01 |  | 2023-06-23 |  | Closed | 2023-06-27 | 2023-07-14 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002038183 |  |  | 2023-07-25 | 2023-07-13 |  |  | 30M Pylon | 30 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8894E M1821(A8A) x3 |  | 1
4058A | Mutiara View Complex | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-08 |  | 2023-05-09 |  | Closed | 2023-05-10 | 2023-06-24 | CD//Affendi | 2023-05-11 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038184 |  |  | 2023-07-11 | 2023-07-11 |  | Rooftop | 6m RT (Boom) | 20 | Add R9264M M1821 x3,Dismantle R8882 S1800(B) x3+R8882 S1800B(B6B) x3+R8881 S2100 x3+
3804A | Alam Jaya Commercial Centre | Central |  | Modernization |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-06 | 2023-05-16 |  | 2023-05-19 |  | Closed | 2023-05-19 | 2023-07-25 | E//Razif | 2023-07-18 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002038185 |  |  | 2023-07-12 | 2023-07-08 |  | Unipole | 3m Bipod (RT) | 9m | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8894E M1821(A8A) x3 |  | 12
4037H | WORLD MOBILE PHONE ENTERPRISE | Northern |  | MOCN As-Is |  | 2023Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038186 | [6 empty] | Small Cell
4263D | Singer Jln Dato Keramat (REL) | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-11 |  | 2023-05-16 |  | Closed | 2023-05-19 | 2023-07-20 | E//Hazida | 2023-05-31 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002038187 |  |  | 2023-08-20 | 2023-08-19 |  | Minimast | 3m Boom (RT) | 7 | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x2+R9224E M1821(AAB) x1 |  | 2
2259A | Kg SG Kertas | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-17 |  | 2023-06-10 |  | Closed | 2023-06-11 | 2023-07-15 | E//Kok Keen | 2023-07-14 | CelcomDigi_RAN_GTSB_TSS_Cental_20230511_0024 | DU00002038188 |  |  | 2023-07-09 | 2023-07-07 |  | Monopole | 30m Lampole | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1705B | Federal Highway Sek15(ZED) | Central |  | Modernization |  | 2023Q4 | IE | Solusi | 4.6 TSSR Approved |  | 2023-06-16 | 2023-06-07 |  | 2023-06-12 |  | Closed | 2023-07-28 | 2023-07-28 | E//Razif | 2023-07-28 | CelcomDigi_RAN_Datasco_TSS_Central_20230606_0025 | DU00002038189 |  |  | 2023-08-28 | 2023-08-21 |  | Tower | Tower | 30m | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8882-L268 x1+R8894E M1821(A8A) x4 | 12
3644B | Jalan Keretapi Lama | Central |  | Modernization |  | 2023Q3 | YZ | GTSB | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-09 |  | 2023-05-13 |  | Closed | 2023-05-14 | 2023-06-17 | CD//Ali akaram | 2023-06-15 | CelcomDigi_RAN_GTSB_TSS_Cental_20230511_0024 | DU00002038190 |  |  | 2023-06-10 | 2023-06-10 |  | Lampole | 24m Lampole | 30 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
1074E | FamilyMart Caltex Kuala Selangor | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038191 | [6 empty] | Small Cell
2632A | Ecopark | Central |  | Modernization |  | 2023Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-13 |  | 2023-05-17 |  | Closed | 2023-05-20 | 2023-06-26 | E//Razif | 2023-06-26 | CelcomDigi_RAN_Magicell_TSS_Central_20230511_0008 | DU00002038192 |  |  | 2023-07-17 | 2023-06-19 |  | Monopole | 45m Monopole | 35 | Add A9732 M1821 x2 + R9264M M1821 x2,Dismantle R8894E M1821(A8A) x4 | 24
2676C | Kg Permatang | Central |  | Modernization |  | 2023Q4 | HQ 1 | AllStar | 4.6 TSSR Approved |  | 2023-05-26 | 2023-05-30 |  | 2023-06-01 |  | Closed | 2023-06-02 | 2023-07-28 | E//Razif | 2023-07-25 | CelcomDigi_RAN_AllStar_TSS_Central_20230529_0009 | DU00002038193 |  |  | 2023-07-05 | 2023-07-05 |  | Monopole | Land site | 31 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
4185D | Taman Kiara | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-29 | 2023-06-07 |  | 2023-06-22 |  | Closed | 2023-07-03 | 2023-07-28 | E//Hazida | 2023-07-28 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002038194 |  |  | 2023-08-29 | 2023-08-29 |  | Tower | 60m 4 Legged Tower | 55m | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 13
4679A | Leong Say Tong | Northern |  | Modernization |  | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-05-30 | 2023-06-12 |  | 2023-06-15 |  | Closed | 2023-06-20 | 2023-08-04 | E//Hazida | 2023-08-04 | Celcom Digi_RAN-YPTT-TSS-Northern-20230531-0015 | DU00002038195 |  |  | 2023-08-29 | 2023-08-28 |  | In-Building System | 30m Monopole | 3m | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3
3651A6 | pBTS Hospital Puncak Alam | Central |  | Modernization |  | 2023Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-05-17 | 2023-05-30 |  | 2023-06-03 |  | Closed | 2023-06-04 | 2023-07-12 | E//Razif | 2023-07-12 | CelcomDigi_RAN_GTSB_TSS_Central_20230523_0025 | DU00002038196 |  |  | 2023-08-17 | 2023-07-02 |  |  | Land site | 24 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
4032B | PDC Bayan Bay | Northern |  | Modernization |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-08 |  | 2023-05-20 |  | Closed | 2023-05-19 | 2023-07-14 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038197 |  |  | 2023-07-08 | 2023-07-05 |  | Tower | Tower | 50 | Add A9732 M1821 x3,Dismantle R8882 S2600(B4A) x1+R9224E M1821(AAB) x4 | 123
4001B | Majestic Heights | Northern |  | Modernization |  | 2023Q3 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-05-02 | 2023-07-06 |  | 2023-07-08 |  | Closed | 2023-07-10 | 2023-07-22 | E//Hazida | 2023-07-22 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230502-0013 | DU00002038198 |  |  | 2023-08-19 | 2023-08-15 |  | Tower | Tower | 60 | Add A9732 M1821 x1+R9264M M1821 x1+R9264H M901821 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R8862A S2600(A4A) x1+R8894E M1821(A8A) x1 | 1
2084B | Kemuning Utama Billboard | Central |  | Modernization |  | 2023Q3 | HQ 6 | AllStar | 4.6 TSSR Approved |  | 2023-05-23 | 2023-05-27 |  | 2023-05-30 |  | Closed | 2023-05-31 | 2023-06-19 | CD//Nik Ashraf | 2023-06-19 | CelcomDigi_RAN_Allstar_TSS_Central_20230511_0007 | DU00002038199 |  |  | 2023-07-16 | 2023-06-27 |  | BillBoard | Billboard | 21 | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x4
4047A | Sunny Point | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-31 |  | 2023-06-02 |  | Closed | 2023-06-06 | 2023-06-28 | CD//Shukri | 2023-06-22 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002038200 |  |  | 2023-07-13 | 2023-07-13 |  | Wall mount boom | 3m RT (Wall Mounted Pole) | 4 | Add R9264M M1821 x3,Dismantle R9224E M1821(AAB) x3
4667B | Kolej Insaniah | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-06-06 | 2023-06-12 |  | 2023-06-22 |  | Closed | 2023-06-27 | 2023-07-28 | E//Hazida | 2023-07-28 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002038201 |  |  | 2023-09-20 | 2023-09-20 |  | Wall mount boom | 3m Boom (RT) | 4 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
4019A | Kelab Gelugor | Northern |  | Modernization |  | 2023Q3 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-05-02 | 2023-05-29 |  | 2023-06-01 |  | Closed | 2023-06-02 | 2023-06-19 | CD//Shukri | 2023-06-19 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0008 | DU00002038202 |  |  | 2023-07-17 | 2023-07-17 |  | Pole | 60m 4 Legged Tower | 6m(pole) + 25m(building) | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8882 S1800B(B6B) x3+R8892E M1821(BAA) x3 | 23
1417H | 99 Speedmart SHAH ALAM SEK 15 | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038203 | [6 empty] | Small Cell
2712B | Sek 16 Shah Alam | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-15 | 2023-06-28 |  | 2023-07-07 |  | Closed | 2023-07-20 | 2023-07-28 | E//Razif | 2023-07-28 | CelcomDigi_RAN_GTSB_TSS_Central_20230616_0029 | DU00002038204 |  |  | 2023-10-07 | 2023-08-21 |  |  | 3m Boom (RT) | 2m | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8862A S1800(B6A) x4+R8854D S2100(A4A) x4+R8862A S2601(A6A) x1 | 23
4061A | Dato Keramat | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-19 | 2023-05-27 |  | 2023-05-31 |  | Closed | 2023-06-02 | 2023-07-03 | CD//Shukri | 2023-06-19 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002038205 |  |  | 2023-07-20 | 2023-07-20 |  | Pole | 60m 4 Legged Tower | 6 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 13
1471H | 99 Speedmart SRI PRISTANA | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038206 | [6 empty] | Small Cell
2721C | Taman Alam Perdana | Central |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-05-06 | 2023-05-12 |  | 2023-05-15 |  | Closed | 2023-05-18 | 2023-07-12 | E//Razif | 2023-07-12 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002038207 |  |  | 2023-07-02 | 2023-07-02 |  | Lampole | Land site | 24m | Add R9264H M901821 x3,Dismantle R9224E M1821(AAB) x3
2603A | Setia Alam | Central |  | Modernization |  | 2023Q3 | HQ 6 | Magicell | 4.6 TSSR Approved |  | 2023-05-22 | 2023-05-26 |  | 2023-05-29 |  | Closed | 2023-05-30 | 2023-06-24 | CD//Ali akaram | 2023-06-23 | CelcomDigi_RAN_Magicell_TSS_Central_20230523_0009 | DU00002038208 |  |  | 2023-06-20 | 2023-06-19 |  | Lampole | 20m Lampole | 20M | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
3005C | Jalan Menteri | Central |  | Modernization |  | 2023Q4 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-07-06 | 2023-07-25 |  | 2023-08-01 |  | Closed | 2023-08-01 | 2023-08-03 | E//Razif | 2023-08-03 | CelcomDigi_RAN_CCSMY_TSS_Central_20230707_0008 | DU00002038209 |  |  | 2023-08-10 | 2023-08-10 |  | In-Building System | 3m Bipod (RT) | 3m | Add R9264H M901821 x4 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x4+R8881 S2100 x3+R8862A S2100(A6A) x1 |  | 4
4694B | Hutan Kampung(ZED) | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-06-07 | 2023-06-21 |  | 2023-06-23 |  | Closed | 2023-07-03 | 2023-07-28 | E//Hazida | 2023-07-28 | Celcom Digi_RAN-GCI-TSS-Northern-20230607-0024 | DU00002038210 |  |  | 2023-09-09 | 2023-08-28 |  | Tower | Tower | 50 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
2660B | Cahaya SPK LP 1 | Central |  | Modernization |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-23 |  | 2023-05-25 |  | Closed | 2023-05-27 | 2023-07-13 | E//Sumitra | 2023-07-13 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002038211 |  |  | 2023-07-06 | 2023-07-05 |  | Lampole | 24m Lampole | 25 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882 S1800B(B6B) x3++R8881 S2100 x3+
4041C | Tmn Saujana Jaya | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-06-16 | 2023-06-19 |  | 2023-06-23 |  | Closed | 2023-06-28 | 2023-07-15 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002038212 |  |  | 2023-08-02 | 2023-07-31 |  | Monopole | Tower | 30 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3++R8881 S2100 x3+
4690B | Kubang Rotan (maxis) | Northern |  | Modernization |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦Maxis not allowed add AAU | 2023-06-15 | 2023-06-10 |  | 2023-06-15 |  | Closed | 2023-07-04 | 2023-09-07 | E//Hazida | 2023-09-07 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230616-0026 | DU00002038213 | NIC_S3_Change MM to BI_owner reject_MAXIS |  | 2023-08-28 | 2023-08-26 |  | Tower | 60m 3 Legged Tower | 60 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 123
1056C | Hartalega Batang Berjuntai | Central |  | Modernization |  | 2023Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-05-01 | 2023-05-04 |  | 2023-05-06 |  | Closed | 2023-05-16 | 2023-07-21 | CD//Syafiq | 2023-07-21 | CelcomDigi_RAN_GTSB_TSS_20230505_0023 | DU00002038214 |  |  | 2023-06-16 | 2023-06-13 |  | Lampole | 24m Lampole | 25 | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x4 |  | 1
2685B | Pinggiran Rahman Putra | Central |  | Modernization |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-05-30 | 2023-06-01 |  | 2023-06-04 |  | Closed | 2023-06-10 | 2023-07-25 | E//Kok Keen | 2023-07-18 | CelcomDigi_RAN_Magicell_TSS_Central_20230531_0010 | DU00002038215 |  |  | 2023-10-14 | 2023-10-10 |  | Tower | 45m Tower | 60 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 | 12
1683H | 99 Speedmart Sg Besar 2 | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038216 | [6 empty] | Small Cell
3839B | Volvo Malaysia | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-19 | 2023-06-23 |  | 2023-06-28 |  | Closed | 2023-07-13 | 2023-07-21 | E//Razif | 2023-07-20 | CelcomDigi_RAN_GTSB_TSS_Central_20230612_0028 | DU00002038217 |  |  | 2023-08-24 | 2023-08-10 |  | Lampole | 18m street pole | 19 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
3919B | Jalan Utas 15_7 | Central |  | Modernization |  | 2023Q4 | HQ 6 | Solusi | 4.6 TSSR Approved |  | 2023-06-19 | 2023-06-21 |  | 2023-07-18 |  | Closed | 2023-07-20 | 2023-07-27 | E//Razif | 2023-07-27 | CelcomDigi_RAN_Futong_TSS_Central_20230620_0002 | DU00002038218 |  |  | 2023-09-10 | 2023-08-21 |  | Lampole | 18M street pole | 18 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
2582A | UPSI (Maxis) | Central |  | Modernization |  | 2023Q4 | MS | Ascentrack | 4.6 TSSR Approved |  | 2024-01-21 | 2024-01-24 |  | 2024-01-26 |  | Closed | 2024-01-26 | 2024-03-26 | E//Kok Keen | 2024-03-25 | Celcomdigi_RAN_Ascentrack_TSS_Central_20230707_0027 | DU00002038219 |  |  | 2024-02-28 | 2024-02-26 |  | Tower | 60m 3 Legged Tower | 60 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8854D S2100(A4A) x3 | 123
4265C | Taiping Sentral Mall IB | Northern |  | Modernization |  | 2023Q4 | WP | GTSB | 4.6 TSSR Approved |  | 2023-06-07 | 2023-06-09 |  | 2023-06-13 |  | Closed | 2023-07-19 | 2023-07-20 | E//Hazida | 2023-07-20 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002038220 |  |  | 2023-08-02 | 2023-08-01 |  |  | In-building system |  | Reuse existing RRU
3409B | Pangsapuri IRIS | Central |  | Modernization |  | 2023Q3 | HQ 6 | GTSB | 4.6 TSSR Approved |  | 2023-05-16 | 2023-05-22 |  | 2023-05-24 |  | Closed | 2023-05-25 | 2023-06-07 | E//Kok Keen | 2023-06-07 | CelcomDigi_RAN_GTSB_TSS_Central_20230517_0024 | DU00002038221 |  |  | 2023-06-26 | 2023-06-22 |  | Pole | 3m Bipod (RT) | 10 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8894E M1821(A8A) x3 |  | 13
3643A4 | pBTS Tmn Damai Utama | Central |  | Modernization |  | 2023Q4 | SS | Futong | 4.6 TSSR Approved |  | 2023-06-17 | 2023-06-19 |  | 2023-06-21 |  | Closed | 2023-06-28 | 2023-08-07 | E//Kok Keen | 2023-08-07 | CelcomDigi_RANMW_Futong_TSS_Central_20230620_0003 | DU00002038222 |  |  | 2023-07-18 | 2023-07-15 |  | Watertank | 25m pBTS | 25 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
3646C | Selayang Baru | Central |  | Modernization |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved | 19/01 Change RRU Solution | 2023-07-17 | 2023-07-24 |  | 2024-01-18 |  | Closed | 2024-01-19 | 2024-01-29 | E//Kok Keen | 2024-01-24 | CelcomDigi_RAN_YPTT_TSS_Central_20230722 | DU00002038223 |  |  | 2024-02-29 | 2024-02-19 |  | Pole | 30m Monopole | 4M | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 |  | 123
2705C | Bandar Tasik Puteri 5 | Central |  | Modernization |  | 2023Q2 | YZ | Ascentrack | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-18 |  | 2023-05-21 |  | Closed | 2023-05-22 | 2023-06-05 | E//Kok Keen | 2023-05-24 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230428_0015 | DU00002038224 |  |  | 2023-06-10 | 2023-06-10 |  | Lampole | Land site | 30m | Add R9264H M901821 x3,Dismantle R9224E M1821(AAB) x3
1195B | Pekan K. Selangor 2 | Central |  | Modernization |  | 2023Q4 | HQ 6 | AllStar | 4.6 TSSR Approved |  | 2023-05-25 | 2023-05-30 |  | 2023-06-02 |  | Closed | 2023-06-03 | 2023-07-25 | E//Razif | 2023-07-25 | CelcomDigi_RAN_AllStar_TSS_Central_20230529_0009 | DU00002038225 |  |  | 2023-07-05 | 2023-07-04 |  | Tower | 45m Tower | 58 | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x3 |  | 3
3819A | Jln Paya Barat Bkt Kapar | Central |  | Modernization |  | 2023Q3 | MA | Magicell | 4.6 TSSR Approved |  | 2023-05-12 | 2023-05-22 |  | 2023-05-24 |  | Closed | 2023-05-30 | 2023-07-12 | E//Sumitra | 2023-07-12 | CelcomDigi_RANMW_Magicell_TSS_Central_20230517_0002 | DU00002038226 |  |  | 2023-09-19 | 2023-09-15 |  | Tower | Monopole | 60M | Add A9732 M1821 x3,Dismantle R8882 S1800B(B6B) x2+R8862A S1800(B6A) x1+R8854D S2100(A4A) x3 | 123
4076A | Batu Feringghi | Northern |  | Modernization |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-15 |  | 2023-05-17 |  | Closed | 2023-05-22 | 2023-07-24 | E//Hazida | 2023-07-22 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038227 |  |  | 2023-08-16 | 2023-08-15 |  | Unipole | 3m Boom (RT) | 3.7 | Add R8852E S9000 x3 + R8894E M1821 x3 + R8862A S2601 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3
1145A | Batang Kali | Central |  | Modernization |  | 2023Q4 | HQ 6 | Ascentrack | 4.6 TSSR Approved |  | 2023-07-15 | 2023-07-21 |  | 2023-07-27 |  | Closed | 2023-07-31 | 2023-08-01 | E//Kok Keen | 2023-08-01 | Celcomdigi_RAN_Ascentrack_TSS_Central_20230707_0027 | DU00002038228 |  |  | 2023-11-22 | 2023-08-10 |  | Tower | Tower | 48m | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 | 23
1375A | Bdr Baru Selayang Fasa2 | Central |  | Modernization |  | 2023Q4 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-06-20 | 2023-07-11 |  | 2023-07-17 |  | Closed | 2023-07-18 | 2023-07-20 | E//Kok Keen | 2023-07-20 | CelcomDigi_RAN_YPTT_TSS_Central_20230622_0007 | DU00002038229 |  |  | 2023-08-06 | 2023-08-06 |  | Minimast | 3m RT (Minimast) | 12.2m | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 |  | 13
3809A | Lingkaran Seroja | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-16 |  | 2023-05-18 |  | Closed | 2023-05-19 | 2023-06-03 | E//Kok Keen | 2023-05-29 | CelcomDigi_RAN_Datasco_TSS_Central_20230428_0018 | DU00002038230 |  |  | 2023-06-17 | 2023-06-16 |  | H-bracket pole | 3m Bipod (RT) | 6 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 23
1799A | Seksyen 11 | Central |  | Modernization |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-05-22 | 2023-06-01 |  | 2023-06-06 |  | Closed | 2023-06-14 | 2023-07-25 | E//Razif | 2023-07-25 | CelcomDigi_RAN_Datasco_TSS_Central_20230523_0023 | DU00002038231 |  |  | 2023-08-09 | 2023-07-31 |  | Rooftop | 6m RT (Boom) | 2m | Add A9732 M1821 x1 + R9264M M1821 x2,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 3
3807A | Taman Radin Jaya | Central |  | Modernization |  | 2023Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2023-05-24 | 2023-05-26 |  | 2023-05-29 |  | Closed | 2023-05-29 | 2023-07-25 | E//Razif | 2023-07-25 | CelcomDigi_RAN_AllStar_TSS_Central_20230606_0011 | DU00002038232 |  |  | 2023-07-07 | 2023-07-04 |  | Pole | 3m Bipod (RT) | 4 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882 S1800B(B6B) x3++R8881 S2100 x3+
1219H | 99 Speedmart SELAYANG HEIGHTS | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038233 | [6 empty] | Small Cell
4873B | Sanyo FTZ | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-20 | 2023-06-15 |  | 2023-06-20 |  | Closed | 2023-06-27 | 2023-07-05 | E//Hazida | 2023-07-05 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002038234 |  |  | 2023-07-14 | 2023-07-13 |  | Lampole | 24m Lampole | 25M | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
4599D | Pala Place Apartment (REL) | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-12 |  | 2023-05-12 |  | Closed | 2023-05-19 | 2023-05-31 | E//Hazida | 2023-05-31 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038235 |  |  | 2023-08-07 | 2023-08-07 |  | Pole | Land site | 4m | Add R9264H M901821 x3,Dismantle R9224E M1821(AAB) x3
1809A | Selayang Mall | Central |  | Modernization |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-06-22 | 2023-06-26 |  | 2023-07-03 |  | Closed | 2023-07-04 | 2023-07-05 | E//Nazrul | 2023-07-04 | CelcomDigi_RAN_YPTT_TSS_Central_20230623_0008 | DU00002038236 |  |  | 2023-10-10 | 2023-10-10 |  | Wall mount boom | In-building system | IBC | Add R8852E S9000 x1 + R8862A S2100 x1,Dismantle R8862A S1800(B6A) x1
4017A | Wisma Rajab | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-06-26 | 2023-07-04 |  | 2023-07-01 |  | Closed | 2023-07-06 | 2023-07-26 | E//Hazida | 2023-07-26 | Celcom Digi_RAN-GCI-TSS-Northern-20230502-0011 | DU00002038237 |  |  | 2023-09-11 | 2023-08-24 |  | In-Building System | 60m 4 Legged Tower | WALL MOUNT | Add R8894E M1821 x3,Dismantle R8882-GUL1812 x4+R8882 S1800B(B6B) x3++R8881 S2100 x3+
4335C | Aman Sentral Outdoor | Northern |  | Modernization |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-06-12 | 2023-06-20 |  | 2023-06-25 |  | Closed | 2023-06-28 | 2023-08-09 | E//Hazida | 2023-08-03 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230613-0025 | DU00002038238 |  |  | 2023-09-19 | 2023-09-19 |  | Wall mount boom | 3m Boom (RT) |  | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 2
4830B | Bukit Jambul IB | Northern |  | Modernization |  | 2023Q3 | WP | YPTT | 4.6 TSSR Approved |  | 2023-05-06 | 2023-05-10 |  | 2023-05-17 |  | Closed | 2023-09-26 | 2023-10-02 | E//Nazrul | 2023-09-27 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0008 | DU00002038239 |  |  | 2023-07-26 | 2023-07-22 |  |  | In-building system | IBC SITE | Add R8862A S1800 x1 + R8862A S2100 x1,Dismantle R8882-GUL1812 x1
4464A | Taiping Headworks | Northern |  | Modernization |  | 2023Q4 | SM | GTSB | 4.6 TSSR Approved |  | 2023-05-26 | 2023-06-07 |  | 2023-06-12 |  | Closed | 2023-06-26 | 2023-07-24 | E//Daniel | 2023-07-23 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002038240 |  |  | 2023-08-03 | 2023-07-22 |  | Tower | Tower | 12m | Add R9264H M901821 x3 + R9264M M1821 x3 + R8862A S2601 x3,Dismantle R8882-GUL1812 x1+R8882 S1800B(B6B) x2+R8840-U216 x2+R8881 S2100 x1+ |  | 123
4816A | Island Plaza | Northern |  | Modernization | Modernization->->Decomm->On Hold->Modernization | 2023Q3 | SHA | CCSMY | 4.6 TSSR Approved | ¦ 1025 - Major Cme requirement emailed. ¦ 0926 - PLanner to confirm omnni antenna sector to maintain or decomm ¦ 0823 - SOW: Decomm>MOD ¦ 0528 - CCS: Pending TX Solution for resurvey | 2023-05-15 | 2023-06-14 |  | 2023-06-17 | 2024-05-31 | Rectificating | 2024-10-25 | 2024-10-25 | E//Hazida | 2024-10-25 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230509-0018 | DU00002038241 |  |  | 2025-01-09 | 2025-01-09 |  | Portables BTS | In-building system | IBC SURVEY | Add R8862A S1800 x3 + R8862A S2100 x3 + R8862A S2601 x3,Dismantle R8882-GUL1812 x1+R8881 S2100x1
1547B | Ulu Bernam R&R (KJS) | Central |  | Modernization |  | 2023Q4 | HQ 6 | Ascentrack | 4.6 TSSR Approved |  | 2023-06-30 | 2023-07-17 |  | 2023-07-20 |  | Closed | 2023-07-21 | 2023-07-28 | E//Kok Keen | 2023-07-25 | CelcomDigi_RANMW_Ascentrack_TSS_Central_20230626_0008 | DU00002038242 |  |  | 2023-08-12 | 2023-08-09 |  | Tower | Tower | 75 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2,Dismantle R8894E M1821(A8A) x3 | 1
4755C | Setia Vista | Northern |  | Modernization |  | 2023Q3 | MH | GCI | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-05 |  | 2023-05-06 |  | Closed | 2023-05-08 | 2023-05-16 | CD//Shamsul | 2023-05-15 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038243 |  |  | 2023-07-03 | 2023-06-23 |  | Pole | 3m Boom (RT) |  | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x3+R9224E M1821(AAB) x2 | 12
4279H | 99 Speedmart PK KG Boyan | Northern |  | MOCN As-Is |  | 2023Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038244 | [6 empty] | Small Cell
3373A3 | pBTS Jalan Menteri ( C ) | Central |  | Modernization |  | 2023Q4 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-07-05 | 2023-07-12 |  | 2023-07-20 |  | Closed | 2023-07-20 | 2023-07-26 | E//Razif | 2023-07-26 | CelcomDigi_RAN_CCSMY_Central_20230706_0008 | DU00002038245 |  |  | 2023-08-03 | 2023-08-01 |  | Tower | 25m pBTS | 29M | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1
1984B | JBA Sunway Kayangan (KJS) | Central |  | Modernization |  | 2023Q3 | XH | YPTT | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-25 |  | 2023-05-27 |  | Closed | 2023-05-28 | 2023-07-20 | E//Sumitra | 2023-07-18 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002038246 |  |  | 2023-07-07 | 2023-07-05 |  | Monople Tree | 30m Monopole Tree | 32 | Add R9264H M901821 x4,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8862A S2100(A6A) x4
1018A | Club House | Central |  | MOCN As-Is | Modernization->MOCN As-Is | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-07-18 | 2023-07-21 |  | 2023-07-26 |  | Closed | 2023-07-27 | 2023-07-27 | E//Kok Keen | 2023-07-27 | CelcomDigi_RAN_Magicell_TSS_Central_20230721 | DU00002038247 | [5 empty] | Wall mount boom | 3m RT (Wall Mounted Pole) | 5
3064C6 | pBTS Presint 17 Setia Alam (REL) | Central |  | Modernization |  | 2023Q3 | AI | Magicell | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-05 |  | 2023-05-08 |  | Closed | 2023-05-10 | 2023-06-20 | E//Razif | 2023-06-20 | CelcomDigi_RAN_Magicell_TSS_20230505_0006 | DU00002038248 |  |  | 2023-06-11 | 2023-06-10 |  | Guide mast | 25m pBTS | 24m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
2307A | UIA Sumaiyah | Central |  | Modernization |  | 2023Q4 | CR | Datasco | 4.6 TSSR Approved |  | 2023-07-24 | 2023-08-17 |  | 2023-08-21 |  | Closed | 2023-08-23 | 2023-10-31 | E//Kok Keen | 2023-08-30 | CelcomDigi_RAN_Datasco_TSS_Central_20230726 | DU00002038249 |  |  | 2024-02-15 | 2024-02-14 |  | Lampole | 30m Lampole | 30 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle R8882 S1800B(B6B) x3
3637A3 | pBTS Kg Perenggan (MCMC) | Central |  | Modernization |  | 2023Q4 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-07-05 | 2023-08-16 |  | 2023-08-28 |  | Closed | 2023-08-28 | 2023-09-07 | E//Razif | 2023-09-06 | CelcomDigi_RAN_CCSMY_Central_20230706_0008 | DU00002038250 |  |  | 2023-09-06 | 2023-09-02 |  | Watertank | Portable BTS | 28 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
4020A | New Bob Centre | Northern |  | Modernization |  | 2023Q3 | HQ 2 | CCSMY | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-09 |  | 2023-05-11 |  | Closed | 2023-05-16 | 2023-08-03 | E//Yadav | 2023-08-03 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002038251 |  |  | 2023-12-27 | 2023-08-17 |  | Pole | 60m 4 Legged Tower | 5 (wall mounted) | Add R9264M M1821 x6 + R8862A S2601 x3,Dismantle R9224E M1821(AAB) x3 |  | 123
2984B | SSAAS Building Indoor | Central |  | Modernization | Modernization->On Hold->Decomm->Modernization | 2023Q4 | CR | Datasco | 4.6 TSSR Approved |  | 2023-07-31 | 2023-08-02 |  | 2024-07-03 | 2024-05-20 | Under Approval | 2024-07-04 | 2024-07-05 | E//Nazrul | 2024-07-05 | CelcomDigi_RAN_Datasco_TSS_Central_20230802 | DU00002038252 |  |  | 2024-10-06 | 2024-09-26 |  |  | In-building system |  | Add R8852E S9000 x1+R8862A S2100 x1,Dismantle | 0 | 0
3047M | Anggerik Vanilla Car Park 1 | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038253 | [6 empty] | Micro Cell
4875B | Bandar Baru Mergong | Northern |  | Modernization |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-26 | 2023-06-26 |  | 2023-07-04 |  | Closed | 2023-07-06 | 2023-07-28 | E//Hazida | 2023-07-28 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230529-0020 | DU00002038254 |  |  | 2023-09-01 | 2023-08-28 |  | In-Building System | 6m Unipole RT | 8 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8882-GUL1812 x1+R8882 S1800(B) x2+R8840 U216 x3 | 13
3900B | Puteri Business Avenue | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-07 | 2023-06-16 |  | 2023-06-21 |  | Closed | 2023-06-28 | 2023-07-20 | E//Razif | 2023-07-20 | CelcomDigi_RANMW_GTSB_TSS_Central_20230609_0002 | DU00002038255 |  |  | 2023-12-17 | 2023-12-17 |  | Lampole | 3m Boom (RT) | 20 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 12
4184C | AEON Taiping | Northern |  | Modernization |  | 2023Q4 | WP | GTSB | 4.6 TSSR Approved |  | 2023-06-07 | 2023-06-09 |  | 2023-06-21 |  | Closed | 2023-07-19 | 2023-07-22 | E//Hazida | 2023-07-20 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002038256 |  |  | 2024-01-26 | 2023-08-01 |  |  | In-building system |  | Add R8862A S2100 x3
4398C | Bukit Relau 2 Telestructure | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-13 | 2023-05-20 |  | 2023-05-24 |  | Closed | 2023-05-26 | 2023-06-10 | E//Hazida | 2023-06-08 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230509-0018 | DU00002038257 |  |  | 2023-06-19 | 2023-06-19 |  |  | 24m Lampole | 30 | Add R9264M M1821 x3,Dismantle R8854E S1800(A6A) x3+R8862A S2100(A6A) x3
3887A | Tmn Mesra Jln Meru | Central |  | Modernization |  | 2023Q3 | IE | Magicell | 4.6 TSSR Approved |  | 2023-05-16 | 2023-05-17 |  | 2023-05-19 |  | Closed | 2023-05-24 | 2023-06-21 | E//Razif | 2023-06-19 | CelcoDigi_RAN_Magicell_TSS_Central_20230517_0009 | DU00002038258 |  |  | 2023-07-15 | 2023-07-13 |  | Tower | 45m 3 Legged Tower | 60M | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
2833A | First World Hotel Indoor | Central |  | Modernization |  | 2026 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-16 | 2023-06-28 |  | 2023-07-10 |  | Closed | 2023-07-12 | 2023-07-17 | E//Nazrul | 2026-04-17 | CelcomDigi_RANMW_GTSB_TSS_Central_20230620_0005 | DU00002038259 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed |  | 2026-01-16 |  | Watertank | In-building system | MDF Level B1, Level T2A, Level T2M, Rooftop | Add R8852E S9000 x13
1685B | Bkt Jelutong (Maxis_ZED) | Central |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-05-31 | 2023-05-27 |  | 2023-05-31 |  | Closed | 2023-06-06 | 2023-08-15 | E//Razif | 2023-07-14 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002038260 |  |  | 2023-09-26 | 2023-09-26 |  | Monople Tree | 24m Lampole | 33m | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x2+R8840-U216 x6++
3903B | Surau Ar-Rahman | Central |  | Modernization |  | 2023Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-05-07 | 2023-05-17 |  | 2023-05-19 |  | Closed | 2023-05-24 | 2023-07-06 | E//Razif | 2023-07-06 | CelcomDigi_RANMW_Allstar_TSS_Central_20230508_0001 | DU00002038261 |  |  | 2023-06-27 | 2023-06-22 |  | Monopole | 24m Lampole | 30 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
3582B | Pekan Sungai Buloh | Central |  | Modernization |  | 2023Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-29 | 2023-05-10 |  | 2023-05-12 |  | Closed | 2023-05-13 | 2023-06-28 | CD//Ali akaram | 2023-06-23 | CelcomDigi_RAN_GTSB_TSS_20230505_0023 | DU00002038262 |  |  | 2023-09-25 | 2023-09-15 |  | Unipole | 3m Bipod (RT) | 6 | Add R9264M M1821 x5 + R8862A S2601 x5,Dismantle R9224E M1821(AAB) x3 |  | 12
1444B | Ladang Jany (Smart) | Central |  | Modernization | Modernization->Maintain USP MOCN->On Hold->Modernization | 2023Q4 | AI | YPTT | 4.6 TSSR Approved |  | 2023-06-24 | 2023-06-28 |  | 2023-07-03 |  | Closed | 2023-07-04 | 2024-03-05 | E//Razif | 2023-11-14 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_0009 | DU00002038263 |  |  | 2023-12-21 | 2023-07-18 |  | Tower | Tower | 60.4 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
1774H | 99 Speedmart Ijok | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038264 | [6 empty] | Rooftop
1377A | Tmn Sri Batu Caves | Central |  | Modernization |  | 2023Q4 | IE | GTSB | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-10 |  | 2023-05-23 |  | Closed | 2023-05-23 | 2023-06-03 | E//Kok Keen | 2023-06-01 | CelcomDigi_RAN_GTSB_TSS_Cental_20230511_0024 | DU00002038265 |  |  | 2023-07-08 | 2023-07-07 |  | Unipole | 3m Boom (RT) | 6 | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8894E M1821(A8A) x3 |  | 1
4762A | Jln Anak Bukit | Northern |  | Modernization |  | 2023Q4 | MH | GCI | 4.6 TSSR Approved |  | 2023-05-28 | 2023-05-27 |  | 2023-05-31 |  | Closed | 2023-06-07 | 2023-07-28 | E//Hazida | 2023-07-28 | Celcom Digi_RAN-GCI-TSS-Northern-20230529-0022 | DU00002038266 |  |  | 2023-09-14 | 2023-09-11 |  | Minaret | 30m Minaret | 18 | Add R9264H M901821 x4 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3
1587H | 99 Speedmart SHAH ALAM SEK 7 (1) | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038267 | [6 empty] | Small Cell
4097A | Bukit Segenting | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-19 |  | 2023-05-24 |  | Closed | 2023-06-01 | 2023-07-07 | CD//Quah | 2023-07-06 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002038268 |  |  | 2023-07-20 | 2023-07-18 |  | Tower | 45m 3 Legged Tower | 61 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R9224E M1821(AAB) x3 | 123
4095C | Al Bukhary (DD) | Northern |  | Modernization |  | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-06-14 | 2023-06-19 |  | 2023-06-20 |  | Closed | 2023-06-23 | 2023-07-28 | E//Hazida | 2023-07-28 | Celcom Digi_RAN-YPTT-TSS-Northern-20230606-0017 | DU00002038269 |  |  | 2023-08-30 | 2023-08-28 |  | A-bracket pole | 3m Bipod (RT) | 9M | Add R9264H M901821 x4,Dismantle R8882 S1800(B) x3+R8862A S1800(B6A) x1+R8862A S2100(A6A) x4
3387C | Fox Theme Park IB | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-07-12 | 2023-07-18 |  | 2023-07-22 |  | Closed | 2023-07-25 | 2023-07-28 | E//Nazrul | 2026-04-17 | CelcomDigi_RAN_GTSB_TSS_Central_20230714 | DU00002038270 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed | 2025-10-31 | 2025-10-28 |  | Portables BTS | In-building system | IBC | Add R8892N M1821 x8+R8862A S1800 x1,Dismantle R8892E M1821(BAA) x8
4086A | Wisma Sri Mata | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-23 |  | 2023-05-25 |  | Closed | 2023-05-29 | 2023-06-19 | CD//Shukri | 2023-06-19 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002038271 |  |  | 2023-07-07 | 2023-07-06 |  | Pole | 60m 4 Legged Tower | 3 | Add R9264M M1821 x5,Dismantle R8854E S1800(A6A) x4+R8854D S2100(A4A) x4 |  | 23
4816B | Times Square Penang IB | Northern |  | Modernization |  | 2023Q3 | WP | YPTT | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-12 |  | 2023-05-22 |  | Closed | 2023-08-28 | 2023-09-12 | E//Hazida | 2023-09-12 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0008 | DU00002038272 |  |  | 2023-09-06 | 2023-09-06 |  |  | In-building system |  | Add + R8862A S1800 x3 + R8862A S2100 x3,Dismantle R8882-GUL1812 x3+R8881 S2100 x3
4952A | Taman Golf | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-06-08 | 2023-06-14 |  | 2023-06-23 |  | Closed | 2023-06-27 | 2023-07-28 | E//Hazida | 2023-07-27 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002038273 |  |  | 2023-08-30 | 2023-08-29 |  | Tower | Tower | 45 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3 |  | 1
1614B | Jln Kebun | Central |  | Modernization |  | 2023Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-13 |  | 2023-05-16 |  | Closed | 2023-05-22 | 2023-07-06 | E//Razif | 2023-07-04 | CelcomDigi_RANMW_Allstar_TSS_Central_20230511_0002 | DU00002038274 |  |  | 2023-06-23 | 2023-06-22 |  | Tower | 45m 3 Legged Tower | 45 | Add A9732 M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R8862A S2600(A4A) x2+R8894E M1821(A8A) x2 | 123
4033B | Bayan Baru Industrial Zone | Northern |  | Modernization |  | 2023Q3 | MH | GTSB | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-23 |  | 2023-05-26 |  | Closed | 2023-05-30 | 2023-07-07 | CD//Quah | 2023-07-05 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002038275 |  |  | 2023-07-05 | 2023-07-05 |  | Pole | 60m 4 Legged Tower | 7 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8882 S2600(B4A) x1+R9224E M1821(AAB) x4 | 13
2596B | Seroja Aparments | Central |  | Modernization |  | 2023Q3 | XH | Datasco | 4.6 TSSR Approved |  | 2023-09-03 | 2023-09-13 |  | 2023-09-15 |  | Closed | 2023-09-19 | 2023-09-21 | E//Razif | 2023-09-21 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002038276 |  |  | 2023-11-29 | 2023-10-26 |  | BillBoard | 3m Boom (RT) | 37m | Add R9264M M1821 x5+R8862A S2601 x1,Dismantle R8894E M1821(A8A) x4 |  | 1
4078A | Jalan Scotland | Northern |  | Modernization |  | 2023Q3 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-05-01 | 2023-05-25 |  | 2023-05-29 |  | Closed | 2023-06-07 | 2023-06-12 | E//Hazida | 2023-06-12 | Celcom Digi_RAN-YPTT-TSS-Northern-20230505-0007 | DU00002038277 |  |  | 2023-08-20 | 2023-08-19 |  | Pole | 3m Boom (RT) | 2 | Add R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8882 S1800B(B6B) x3+R8881 S2100 x3
1163A | Merbau Berdarah 2 | Central |  | Modernization |  | 2023Q4 | HQ 6 | Magicell | 4.6 TSSR Approved |  | 2023-06-01 | 2023-06-07 |  | 2023-06-09 |  | Closed | 2023-06-12 | 2023-07-25 | E//Razif | 2023-07-25 | CelcomDigi_RAN_Magicell_TSS_Central_20230606_0011 | DU00002038278 |  |  | 2023-07-04 | 2023-06-28 |  | Tower | 60m 4 Legged Tower | 50 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x2+R8881 S2100 x2
4268A | Jelutong Hw 2 | Northern |  | Modernization |  | 2023Q3 | SM | YPTT | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-04 |  | 2023-05-07 |  | Closed | 2023-05-09 | 2023-07-25 | E//Hazida | 2023-07-25 | Celcom Digi_RAN-YPTT-TSS-Northern-20230505-0007 | DU00002038279 |  |  | 2023-08-28 | 2023-08-24 |  | Minaret | 4 Legged Tower | 8m | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x3 |  | 2
3072A | Prima Selayang Shoplot | Central |  | Modernization |  | 2023Q4 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-06-20 | 2023-06-22 |  | 2023-06-26 |  | Closed | 2023-06-27 | 2023-07-07 | E//Kok Keen | 2023-07-06 | CelcomDigi_RAN_YPTT_TSS_Central_20230622_0007 | DU00002038280 |  |  | 2023-07-19 | 2023-07-18 |  | In-Building System | 3m Bipod (RT) | 6.4m | Add R9264M M1821 x5 + R8862A S2601 x1,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8862A S2100(A6A) x4 |  | 23
1637H | 99 Speedmart Putera Avenue | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038281 | [6 empty] | Small Cell
4008B | Farlim | Northern |  | Modernization |  | 2023Q3 | SM | YPTT | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-16 |  | 2023-05-18 |  | Closed | 2023-05-24 | 2023-07-25 | E//Hazida | 2023-07-22 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0008 | DU00002038282 |  |  | 2023-08-24 | 2023-08-23 |  | Pole | 3m Bipod (RT) | 4 | Add R9264M M1821 x5 + R8862A S2601 x1,Dismantle R8894E M1821(A8A) x4 |  | 12
4171D | Taman Paduka Setia Kg Boyan | Northern |  | Modernization |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-29 | 2023-05-31 |  | 2023-06-09 |  | Closed | 2023-06-14 | 2023-06-27 | E//Hazida | 2023-06-27 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230530-0021 | DU00002038283 |  |  | 2023-07-28 | 2023-07-25 |  |  | 30m Lampole | 30 | Add R9264H M901821 x4,Dismantle R8862A S1800(B6A) x4+R8854D S2100(A4A) x4
4170B | Tmn Hutchings | Northern |  | Modernization |  | 2023Q3 |  | GCI | 4.6 TSSR Approved |  | 2023-09-06 | 2023-12-08 |  | 2023-12-18 |  | Closed | 2023-12-19 | 2023-12-26 | E//Hazida | 2023-12-23 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038284 |  |  | 2024-02-09 | 2023-12-28 |  |  | Land site | 6 | Add R9264H M901821 x4,Dismantle R9224E M1821(AAB) x4
4119D | BJCC PDC (REL) | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-02 | 2023-05-27 |  | 2023-05-31 |  | Closed | 2023-06-02 | 2023-07-07 | CD//Quah | 2023-07-05 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230502-0013 | DU00002038285 |  |  | 2023-07-17 | 2023-07-13 |  | Monopole | 30m Monopole | 31 | Add R9264M M1821 x6,Dismantle R8862A S1800(B6A) x4+R8854D S2100(A4A) x4 |  | 123
4313C | Penang Expo (Billboard) (REL) | Northern |  | Modernization |  | 2023Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-05-02 | 2023-05-04 |  | 2023-05-06 |  | Rectificating | 2023-05-10 | 2023-05-11 | CD//Affendi | 2023-05-11 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002038286 |  |  | 2023-07-05 | 2023-06-27 |  |  | 3m Boom (RT) | 10 | Add R9264H M901821 x3 + R9264M M1821 x2,Dismantle R8894E M1821(A8A) x3 |  | 23
3348A6 | pBTS Stadium Malawati | Central |  | Modernization |  | 2023Q4 | SS | Datasco | 4.6 TSSR Approved |  | 2023-05-17 | 2023-05-19 |  | 2023-05-25 |  | Closed | 2023-05-31 | 2023-07-25 | E//Razif | 2023-07-25 | CelcomDigi_RAN_Datasco_TSS_Central_20230523_0023 | DU00002038287 |  |  | 2023-07-10 | 2023-07-05 |  | Guide mast | Land site | 30 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
4102Z | Kg Pondok Tanjung | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038288 | [6 empty] | Land site
4072A | Penang Sports Club | Northern |  | Modernization |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-05-12 | 2023-05-15 |  | 2023-05-22 |  | Closed | 2023-05-25 | 2023-07-22 | E//Hazida | 2023-07-22 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038289 |  |  | 2023-08-24 | 2023-08-24 |  | Pole | 30m 3-legged tower | 6 | Add R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8882 S1800B(B6B) x3+R8881 S2100 x3
2030A | Kapar Power Plant | Central |  | Modernization |  | 2023Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-08-24 | 2023-08-29 |  | 2023-09-02 |  | Closed | 2023-09-04 | 2023-09-06 | E//Razif | 2023-09-06 | CelcomDigi_RAN_GTSB_TSS_Central_20230901 | DU00002038290 |  |  | 2023-11-20 | 2023-11-15 |  | Wall mount boom | 30m Monopole Tree | 6M | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3++
2597A | Sek 18 Shah Alam (Masjid) | Central |  | Modernization |  | 2023Q4 | SS | Solusi | 4.6 TSSR Approved |  | 2023-06-04 | 2023-06-08 |  | 2023-06-21 |  | Closed | 2023-06-23 | 2023-07-25 | E//Sumitra | 2023-07-25 | CelcomDigi_RAN_Solusi_TSS_Central_20230620_0002 | DU00002038291 |  |  | 2023-08-06 | 2023-08-04 |  | Lampole | 24m Lampole | 20M | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8840-U216 x3++
3749A | WT Kelab Golf Sultan Abdul Aziz Shah | Central |  | Modernization |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-05-18 | 2023-06-20 |  | 2023-06-22 |  | Closed | 2023-06-26 | 2023-07-27 | E//Razif | 2023-07-27 | CelcomDigi_RAN_Datasco_TSS_Central_20230523_0023 | DU00002038292 |  |  | 2023-12-16 | 2023-12-11 |  | Tower | 30m Monopole | 30M | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8894E M1821(A8A) x3 |  | 1
1197H | 99 Speedmart DATARAN SELAYANG | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038293 | [6 empty] | Rooftop
3723C | Tmn Mewah Jaya (REL) | Central |  | Modernization |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-31 | 2023-06-07 |  | 2023-06-10 |  | Closed | 2023-06-15 | 2023-07-12 | E//Sumitra | 2023-07-12 | CelcomDigi_RANMW_YPTT_TSS_Central_20230508_0002 | DU00002038294 |  | TSSR many blank page | 2023-12-06 | 2023-12-05 |  | In-Building System | 3m Boom (RT) | 7 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x4 | 23
2692B | Surau Jln Jambu | Central |  | Modernization |  | 2023Q3 | IE | Magicell | 4.6 TSSR Approved |  | 2023-05-06 | 2023-05-19 |  | 2023-05-23 |  | Closed | 2023-05-29 | 2023-09-06 | CD//Tee | 2023-06-14 | CelcomDigi_RAN_Magicell_TSS_Central_20230508_0007 | DU00002038295 |  |  | 2023-07-14 | 2023-07-13 |  | Lampole | 24m Lampole | 27 | Add A9732 M1821 x2 + R9264M M1821 x2,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8862A S2100(A6A) x4 | 23
3039C | Seksyen 7 Flat (REL) | Central |  | Decomm | Modernization->Decomm | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-08-23 | 2023-06-12 |  | 2023-06-16 | 2023-09-13 | Rectificating | 2023-09-13 | 2024-01-22 | E//Razif | 2023-09-14 | 0626Central-GTSB-BOQ Template (template) | DU00002038296 |  |  |  |  | 2023-11-30 | Monopole | 24m Lampole | 25
4239Z | Kampung Sumpit Beras | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038297 | [6 empty] | Land site
1713B | SEK 7 BKT RAJA | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI,L2600 change to 40M¦Maxis reject add AAU | 2023-05-26 | 2023-06-14 |  | 2024-01-19 |  | Closed | 2024-01-20 | 2024-02-16 | E//Razif | 2024-02-16 | CelcomDigi_RAN_GTSB_TSS_Central_20230529_0025 | DU00002038298 | NIC_S2_Change MM to BI,L2600 change to 40M_owner reject_MAXIS |  | 2024-01-31 | 2024-01-26 |  |  | 45m 3 Legged Tower | 45m | Add R9264H M901821 x3+R8854 S2600 x2,Dismantle R8862A S9000(A6A) x3+R8882 S2600(B4A) x2+R8894E M1821(A8A) x3 |  | 23
1178C | Tesco Puncak Alam | Central |  | Modernization |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-27 | 2023-05-25 |  | 2023-05-31 |  | Closed | 2023-05-31 | 2023-07-21 | E//Sumitra | 2023-07-18 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002038299 |  |  | 2023-06-27 | 2023-06-28 |  | Pole | 4.5 wall mount boom | 10 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
4090A | Shoplot Permatang Damar | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-13 |  | 2023-05-21 |  | Closed | 2023-05-23 | 2023-06-02 | E//Hazida | 2023-06-02 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002038300 |  |  | 2023-06-24 | 2023-06-24 |  | H-bracket pole | 60m 4 Legged Tower | 6 | Add R8894E M1821 x3,Dismantle R8882 S1800(B) x3+R8882 S1800B(B6B) x3+R8881 S2100 x3
4620D | Balai Bomba Jalan Perak Penang (REL) | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-07 | 2023-05-11 |  | 2023-05-16 |  | Closed | 2023-05-22 | 2023-06-01 | E//Hazida | 2023-06-01 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002038301 |  |  | 2023-07-25 | 2023-07-25 |  | Monopole | Land site | 30 | Add R9264H M901821 x3 + R9264M M1821 x2,Dismantle R9224E M1821(AAB) x3 |  | 13
3779A | Masjid Pekan Jeram | Central |  | Modernization |  | 2023Q3 | HQ 6 | GTSB | 4.6 TSSR Approved |  | 2023-04-29 | 2023-05-09 |  | 2023-05-12 |  | Closed | 2023-05-15 | 2023-06-28 | CD//Ali akaram | 2023-06-28 | CelcomDigi_RAN_GTSB_TSS_20230505_0023 | DU00002038302 |  |  | 2023-06-15 | 2023-06-13 |  | Lampole | 30m Lampole | 30 | Add R9264H M901821 x3,Dismantle R8882 S1800B(B6B) x3+R8854D S2100(A4A) x3
3665C | Surau Al-Ikhlas Bkt Jelutong | Central |  | Modernization |  | 2023Q3 | SS | YPTT | 4.6 TSSR Approved |  | 2023-06-16 | 2023-06-13 |  | 2023-06-16 |  | Closed | 2023-06-19 | 2023-07-13 | E//Razif | 2023-07-13 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002038303 |  |  | 2023-09-15 | 2023-09-12 |  | Monopole | 30m Monopole | 24 | Add R9264M M1821 x3 + R8862A S2601 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
1012A | Fusu Plastic | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-10 |  | 2023-05-12 |  | Closed | 2023-05-15 | 2023-06-06 | E//Kok Keen | 2023-05-24 | CelcomDigi_RAN_GTSB_TSS_Cental_20230511_0024 | DU00002038304 |  |  | 2023-07-03 | 2023-06-28 |  | H-bracket pole | 3m Boom (RT) | 6 | Add R9264H M901821 x4,Dismantle R8882-GUL1812 x3+R8882 S1800B(B6B) x1+R8854D S2100(A4A) x4
3464B | Hospital Shah Alam IB | Central |  | Remote MOCN |  | 2023Q4 | AI | In-House | 4.6 TSSR Approved |  | 2023-06-19 | 2023-06-13 |  | 2023-07-08 |  | Closed | 2023-07-10 | 2023-07-11 | E//Nazrul | 2023-07-10 | CelcomDigi_RANMW_GTSB_TSS_Central_20230612_0003 | DU00002038305 | [5 empty] | Portables BTS | IN-BUILDING | IBC | Reuse existing RRU
3241D | Taman Bunga Raya | Central |  | Modernization |  | 2023Q2 | HQ 6 | Datasco | 4.6 TSSR Approved |  | 2023-04-17 | 2023-05-13 |  | 2023-06-07 |  | Closed | 2023-06-08 | 2023-06-13 | E//Kok Keen | 2023-06-13 | CelcomDigi_RAN_Datasco_TSS_Central_20230418_0013 | DU00002038306 |  |  | 2023-07-05 | 2023-06-28 |  | Lampole | 30m Lampole | 30m | Add A9732 M1821 x1 + R9264M M1821 x2,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x2+A9722 M1821 x1 | 3
2591B | Jalan Puteri 2_12 | Central |  | Modernization |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-08 |  | 2023-05-11 |  | Closed | 2023-05-11 | 2023-05-25 | E//Kok Keen | 2023-05-25 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230428_0015 | DU00002038307 |  |  | 2023-06-01 | 2023-05-30 |  | Lampole | 24m Lampole | 24 | Add R8862A S9000 x3 + R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
4591A | Kg.Tebok Pulai | Central |  | Modernization |  | 2023Q4 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-09-29 | 2023-11-14 |  | 2023-11-17 |  | Closed | 2023-11-20 | 2023-11-22 | E//Razif | 2023-11-21 | CelcomDigi_RAN_CCSMY_TSS_Central_20231005 | DU00002038308 |  |  | 2023-12-15 | 2023-12-09 |  | Tower | 45m 4 Legged Tower | 47 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x5,Dismantle R8860E-GU908 x1+R8894E M1821(A8A) x3 |  | 13
1772H | 99 Speedmart Sasaran 1 | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038309 | [6 empty] | Rooftop
3345A7 | pBTS Curtin University (M) | Sarawak |  | Modernization |  | 2023Q4 | ZB | South Pacific | 4.6 TSSR Approved |  | 2023-07-13 | 2023-07-24 |  | 2023-08-01 |  | Closed | 2023-08-03 | 2023-08-11 | E//Hannah | 2023-08-11 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230606-0003 | DU00002038310 |  | 2/8)Missing Schematic Antenna | 2023-09-14 | 2023-09-11 |  | Watertank | 25m pBTS | 30 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3
3221C | PUSPAKOM Sungai Besar | Central |  | Modernization |  | 2023Q4 | CR | Magicell | 4.6 TSSR Approved |  | 2023-06-19 | 2023-08-01 |  | 2023-08-03 |  | Closed | 2023-08-10 | 2023-08-11 | E//Razif | 2023-08-11 | CelcomDigi_RANMW_Magicell_TSS_Central_20230620_0007 | DU00002038311 |  |  | 2023-10-07 | 2023-09-30 |  |  | 30m Monopole | 31M | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
4924A | Malim Prima | Central |  | Modernization |  | 2023Q4 | HQ 1 | Ascentrack | 4.6 TSSR Approved |  | 2023-06-02 | 2023-06-13 |  | 2023-06-15 |  | Closed | 2023-06-20 | 2023-06-28 | E//Kok Keen | 2023-06-27 | Celcomdigi_RAN_Ascentrack_TSS_Central_20230606_0021 | DU00002038312 |  |  | 2023-07-28 | 2023-07-18 |  |  | Tower | 60 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2,Dismantle R8882 S1800B(B6B) x3 | 1
4427D | Taman Simpang | Northern |  | Modernization |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-06-12 | 2023-06-12 |  | 2023-06-16 |  | Closed | 2023-06-20 | 2023-06-27 | E//Hazida | 2023-06-27 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230613-0025 | DU00002038313 |  |  | 2023-07-26 | 2023-07-22 |  | Lampole | 30M Lampole | 31M | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
2012B | KOLEJ AMINAH UIA Tx | Central |  | Modernization |  | 2023Q4 | CR | Datasco | 4.6 TSSR Approved |  | 2023-07-24 | 2023-08-02 |  | 2023-08-04 |  | Closed | 2023-08-15 | 2023-10-17 | E//Kok Keen | 2023-10-13 | CelcomDigi_RAN_Datasco_TSS_Central_20230726 | DU00002038314 |  |  | 2023-10-24 | 2023-10-20 |  | Tower | 60m 4 Legged Tower | 100 | Add R9264M M1821 x5 + R8862A S2601 x2,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3,Reuse R8862A S2600 x3 + R8862A S9000 x3 |  | 23
4466A | Taman Rakyat RDD | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-28 | 2023-05-30 |  | 2023-06-01 |  | Closed | 2023-06-07 | 2023-07-15 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-GCI-TSS-Northern-20230529-0022 | DU00002038315 |  |  | 2023-07-31 | 2023-07-22 |  | Tower | 50m 3 Legged Tower | 45 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 13
4089A | BMW | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-18 |  | 2023-05-22 |  | Closed | 2023-05-24 | 2023-06-02 | E//Hazida | 2023-06-02 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002038316 |  |  | 2023-07-08 | 2023-07-07 |  |  | 60m 4 Legged Tower | 3m | Add R9264H M901821 x1 + R9264M M1821 x5,Dismantle R8882 S1800B(B6B) x3+R8862A S1800(B6A) x1+R8854D S2100(A4A) x4 |  | 13(S3->S4,S4->S3,Rename sectorID,Bisector@New S1/S4)
1348A | Sect 8 | Central |  | Modernization |  | 2023Q4 | HQ 6 | Datasco | 4.6 TSSR Approved |  | 2023-05-16 | 2023-05-30 |  | 2023-06-01 |  | Closed | 2023-06-02 | 2023-07-27 | E//Razif | 2023-07-27 | CelcomDigi_RAN_Datasco_TSS_Central_20230517_0022 | DU00002038317 |  |  | 2023-07-13 | 2023-07-13 |  | Minimast | 3m RT (Minimast) | 10 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8894E M1821(A8A) x3 |  | 3
1164A | Kg Baru Kuala Selangor | Central |  | Modernization |  | 2023Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2023-06-12 | 2023-06-19 |  | 2023-06-21 |  | Closed | 2023-06-27 | 2023-07-26 | E//Razif | 2023-07-26 | CelcomDigi_RAN_AllStar_TSS_Central_20230612_0011 | DU00002038318 |  |  | 2023-07-14 | 2023-07-14 |  | Monopole | 45m Monopole | 45M | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R9224E M1821(AAB) x3 |  | 2
4894A | General Hospital IB | Northern |  | Remote MOCN |  | 2023Q3 | WP | GTSB | 14.3 Drop (Done Survey + TSSR) |  | 2023-05-15 | 2023-05-18 |  | 2023-05-24 |  | Under Approval | 2023-12-08 |  |  |  | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002038319 | [5 empty] | Wall mount boom | In-building system |  | Reuse exsitng RRU
1711B | Sekyen 24 | Central |  | Modernization |  | 2023Q4 | HQ 6 | Datasco | 4.6 TSSR Approved |  | 2023-05-23 | 2023-06-01 |  | 2023-06-03 |  | Closed | 2023-06-12 | 2023-07-20 | E//Razif | 2023-07-20 | CelcomDigi_RAN_Datasco_TSS_Central_20230606_0025 | DU00002038320 |  |  | 2023-08-03 | 2023-08-01 |  | Monopole | 20m Monopole | 25M | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 23
1893H | Dewan Jubli Perak IB | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038321 | [6 empty] | Land site
3630C | Pangsapuri Mesra Tmn Industri Bolton | Central |  | Modernization |  | 2023Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2023-06-19 | 2023-06-21 |  | 2023-06-23 |  | Closed | 2023-06-26 | 2023-07-06 | E//Kok Keen | 2023-07-04 | CelcomDigi_RANMW_AllStar_TSS_Central_20230620_0004 | DU00002038322 |  |  | 2023-07-17 | 2023-07-15 |  | Monopole | Tower | 30 | Add R9264H M901821 x3 + R9264M M1821 x2,Dismantle R8894E M1821(A8A) x4 |  | 23
4147D | Olive Tree Hotel | Northern |  | Modernization |  | 2023Q3 | SM | YPTT | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-16 |  | 2023-05-19 |  | Closed | 2023-05-23 | 2023-06-27 | E//Hazida | 2023-06-27 | Celcom Digi_RAN-YPTT-TSS-Northern-20230509-0010 | DU00002038323 |  |  | 2024-01-03 | 2023-07-18 |  | Wall mount boom | 3m Boom (RT) | N/A | Add R9264H M901821 x4,Dismantle R8894E M1821(A8A) x4
1897B | KKB Town 2 | Central |  | Modernization |  | 2023Q4 | SS | Futong | 4.6 TSSR Approved |  | 2023-07-06 | 2023-08-18 |  | 2023-08-22 |  | Closed | 2023-08-24 | 2023-08-25 | E//Kok Keen | 2023-08-25 | CelcomDigi_RAN_Futong_TSS_Central_20230707_0008 | DU00002038324 |  |  | 2023-09-07 | 2023-08-30 |  | In-Building System | 3m Bipod (RT) | 7 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8882-GUL1812 x3 |  | 12
1372C | Syabas Rimbayu (REL) | Central |  | Modernization |  | 2023Q3 | MA | Solusi | 4.6 TSSR Approved |  | 2023-04-27 | 2023-05-17 |  | 2023-05-19 |  | Closed | 2023-05-20 | 2023-07-07 | E//Sumitra | 2023-07-06 | CelcomDigi_RANMW_Solusi_TSS_Central_20230609_0002 | DU00002038325 |  |  | 2023-07-08 | 2023-07-06 |  | Monople Tree | 30m RDS | 30M | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1007A | Mimaland | Central |  | Modernization |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-06-21 | 2023-06-28 |  | 2023-07-04 |  | Closed | 2023-07-06 | 2023-07-12 | E//Kok Keen | 2023-07-12 | CelcomDigi_RANMW_Magicell_TSS_Central_20230622_0008 | DU00002038326 |  |  | 2023-07-22 | 2023-07-18 |  | Tower | 30m 3-legged tower | 45 | Add R9264H M901821 x1 + R9264M M1821 x4 + R8862A S2601 x5,Dismantle R8882-GUL1812 x2 |  | 12
4127B | Gembira Parade | Northern |  | Modernization |  | 2023Q3 | MH | GTSB | 4.6 TSSR Approved |  | 2023-04-28 | 2023-05-13 |  | 2023-05-19 |  | Closed | 2023-05-23 | 2023-06-21 | E//Hazida | 2023-06-21 | Celcom Digi_RAN-GTSB-TSS-Northern-20230502-0012 | DU00002038327 |  |  | 2023-07-12 | 2023-07-12 |  | Wall mount boom | 3m Boom (RT) | 4M | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 |  | 2
2822A | Plaza Alam Sentral | Central |  | Modernization | Decomm->On hold->Swap->On Hold->Modernization | 2023Q4 | SY1 | Datasco | 4.6 TSSR Approved |  | 2023-08-14 | 2023-08-22 |  | 2023-08-28 | 2023-09-25 | Rectificating | 2024-09-11 | 2024-09-12 | E//Nazrul | 2024-09-12 | CelcomDigi_RAN_Datasco_TSS_Central_20230815 | DU00002038328 |  |  | 2024-09-24 | 2024-09-23 |  |  | In-building system |  | Add + R8862A S1800 x1 + R8862A S2100 x1 + R8862A S2601,Dismantle R8882-GUL1812 x1 | 0 | 0
4562D | RECS (REL) | Northern |  | Modernization |  | 2023Q3 | MH | YPTT | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-09 |  | 2023-05-11 |  | Closed | 2023-05-12 | 2023-05-16 | CD//Shamsul | 2023-05-15 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0008 | DU00002038329 |  |  | 2023-06-26 | 2023-06-26 |  | BillBoard | Land site | 25 | Add R9264H M901821 x4,Dismantle R9224E M1821(AAB) x4
2300A | JHEOA | Central |  | Modernization |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-07-10 | 2023-07-13 |  | 2023-07-19 |  | Closed | 2023-07-27 | 2023-07-28 | E//Kok Keen | 2023-07-28 | CelcomDigi_RAN_Magicell_TSS_Central_20230711 | DU00002038330 |  |  | 2023-08-08 | 2023-08-07 |  | Lampole | 24m Lampole | 30 | Add R9264H M901821 x2 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8882 S1800(B) x2 |  | 2
3784A | Pangsapuri Alam Perdana | Central |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-06-06 | 2023-06-07 |  | 2023-06-09 |  | Closed | 2023-06-12 | 2023-07-13 | E//Razif | 2023-07-12 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002038331 |  |  | 2023-10-30 | 2023-09-22 |  | Lampole | 3M Boom | 24m | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x3 | 23
4820B | Gurney Paragon IB | Northern |  | Modernization |  | 2023Q3 | WP | GCI | 4.6 TSSR Approved |  | 2023-06-16 | 2023-06-20 |  | 2023-06-21 |  | Closed | 2023-07-20 | 2023-07-24 | E//Hazida | 2023-07-23 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038332 |  |  | 2023-08-24 | 2023-08-22 |  | Portables BTS | In-building system |  | Add R8862A S1800 x3 + R8862A S2100 x3,Dismantle R8882 S1800(B) x3+R8881 S2100 x3
1099A | Hong Fatt Auto | Central |  | Modernization |  | 2023Q3 | IE | Magicell | 4.6 TSSR Approved |  | 2023-05-17 | 2023-05-24 |  | 2023-05-26 |  | Closed | 2023-05-27 | 2023-07-12 | E//Razif | 2023-07-12 | CelcomDigi_RAN_Magicell_TSS_Central_20230523_0009 | DU00002038333 |  |  | 2023-07-22 | 2023-07-18 |  | Tower | 60m 3 Legged Tower | 45M | Add A9732 M1821 x3 + R9264M M1821 x1,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x5 | 124(S4->S3,S3->S4,MM@NEW S1/S2/S3)
3465B | Taman Bukit Idaman (REL) | Central |  | Modernization |  | 2023Q4 | AI | YPTT | 4.6 TSSR Approved |  | 2023-06-14 | 2023-06-28 |  | 2023-07-03 |  | Closed | 2023-07-12 | 2023-07-17 | E//Kok Keen | 2023-07-14 | CelcomDigi_RAN_YPTT_TSS_Central_20230616_0005 | DU00002038334 |  |  | 2023-07-23 | 2023-07-22 |  | Monople Tree | 30m Monopole | 30 | Add R9264M M1821 x5,Dismantle R8882 S1800(B) x3+R8862A S1800(B6A) x2+R8862A S2100(A6A) x5 |  | 23
2516A | Jeram Bt 20 | Central |  | Modernization |  | 2023Q3 | HQ 6 | GTSB | 4.6 TSSR Approved |  | 2023-04-27 | 2023-05-10 |  | 2023-05-13 |  | Closed | 2023-05-14 | 2023-06-21 | CD//Ali akaram | 2023-06-21 | CelcomDigi_RAN_GTSB_TSS_Central_20230428_0022 | DU00002038335 |  |  | 2023-07-06 | 2023-07-05 |  | Tower | 60m 4 Legged Tower | 60 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x3 | 23
1605B | Kemuning Green Ville (Kota Kem | Central |  | Modernization |  | 2023Q3 | HQ 6 | AllStar | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-29 |  | 2023-05-31 |  | Closed | 2023-06-01 | 2023-07-04 | E//Razif | 2023-07-04 | CelcomDigi_RAN_Allstar_TSS_Central_20230511_0007 | DU00002038336 |  |  | 2023-06-25 | 2023-06-22 |  | Tower | 45m 3 Legged Tower | 48 | Add A9732 M1821 x3,Dismantle R9224E M1821(AAB) x3 | 123
4674C | Lorong Semarak Api | Northern |  | Modernization |  | 2023Q3 | MH | GCI | 4.6 TSSR Approved |  | 2023-05-12 | 2023-05-20 |  | 2023-05-24 |  | Closed | 2023-05-25 | 2023-07-22 | E//Hazida | 2023-07-22 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038337 |  |  | 2023-08-17 | 2023-08-16 |  | Unipole | Land site | 5.4 | Add R9264H M901821 x4,Dismantle R9224E M1821(AAB) x4
1373A | Kean Huat Motor | Central |  | Modernization |  | 2023Q4 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-06-21 | 2023-06-23 |  | 2023-06-24 |  | Closed | 2023-06-26 | 2023-07-06 | E//Kok Keen | 2023-07-05 | CelcomDigi_RANMW_YPTT_TSS_Central_20230623_0005 | DU00002038338 |  |  | 2023-07-24 | 2023-07-24 |  | Pole | 6m Unipole RT | 6.6 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
3111A | Surau al-Mawaddah Seksyen 7 | Central |  | Modernization |  | 2023Q4 | IE | GTSB | 4.6 TSSR Approved |  | 2023-05-27 | 2023-06-02 |  | 2023-06-10 |  | Closed | 2023-06-19 | 2023-07-21 | E//Razif | 2023-07-20 | CelcomDigi_RAN_GTSB_TSS_Central_20230529_0025 | DU00002038339 |  |  | 2023-07-29 | 2023-07-29 |  | Lampole | 20m Lampole | 21 | Add R9264M M1821 x3,Dismantle R8892E M1821(BAA) x3
1151A | 22 Mile Kapar | Central |  | Modernization |  | 2023Q3 | XH | GTSB | 4.6 TSSR Approved |  | 2023-04-27 | 2023-05-09 |  | 2023-05-12 |  | Closed | 2023-05-13 | 2023-08-10 | CD//Ali akaram | 2023-08-10 | CelcomDigi_RAN_GTSB_TSS_Central_20230428_0022 | DU00002038340 |  |  | 2023-07-07 | 2023-06-13 |  | Monopole | 30m Monopole | 45M | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3
3028C | Bandar Bkt Raja (REL) | Central |  | Modernization |  | 2023Q3 | XH | Magicell | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-22 |  | 2023-05-10 |  | Closed | 2023-05-27 | 2023-06-17 | E//Razif | 2023-06-16 | CelcomDigi_RAN_Magicell_TSS_Central_20230511_0008 | DU00002038341 |  |  | 2023-06-14 | 2023-06-13 |  | BillBoard | Land site | 6m | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2600 x1,Dismantle R8894E M1821(A8A) x3 |  | 1
4197D | Apartment Green Garden Bus Stop | Northern |  | Modernization |  | 2023Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-05-19 | 2023-05-30 |  | 2023-07-08 |  | Rectificating | 2023-07-12 | 2023-07-22 | E//Hazida | 2023-07-22 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230509-0018 | DU00002038342 |  |  | 2023-08-03 | 2023-08-03 |  | Lampole | 24M Lampole | 27m | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
4835A | City Bayview Penang | Northern |  | Modernization | Decomm->On hold->Swap->On Hold->Modernization->On Hold->Modernization | 2023Q3 | SHA | GCI | 4.6 TSSR Approved | ¦ 0823 - SOW: Decomm>MOD | 2023-05-22 | 2023-05-25 |  | 2023-05-29 | 2024-04-22 | Under Approval | 2024-10-15 | 2025-10-16 | E//Nazrul | 2025-10-15 | 0918CD-Northern-GCI-BOQ Template (old contract) | DU00002038343 |  |  | 2025-12-02 | 2024-10-09 |  |  | In-building system | IN BUILDING | R9264H M901821(AIA)x1+R8852E S9000 x2+R8862A S2100 x2, Dismantle R8882-GUL1812 x1
3144B | KPJ Specialist Selangor | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-26 | 2023-07-14 |  | 2023-07-25 |  | Closed | 2023-07-28 | 2023-07-28 | E//Nazrul | 2023-07-28 | CelcomDigi_RAN_GTSB_TSS_Central_20230627_0033 | DU00002038344 |  |  | 2023-09-06 | 2023-08-30 |  |  | In-building system |  | Reuse existing RRU
4074A | Shoplot Relau | Northern |  | Modernization |  | 2023Q3 | MH | GTSB | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-11 |  | 2023-05-15 |  | Closed | 2023-05-18 | 2023-06-21 | E//Hannah | 2023-06-21 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002038345 |  |  | 2023-07-13 | 2023-07-13 |  | Pole | 60m 4 Legged Tower | 5 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x4 | 13
3208B | Petronas Kota Kemuning (REL) | Central |  | Modernization |  | 2023Q3 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-06-22 | 2023-07-03 |  | 2023-07-10 |  | Closed | 2023-07-20 | 2023-09-27 | E//Razif | 2023-09-27 | CelcomDigi_RANMW_CCSMY_TSS_Central_20230623_0003 | DU00002038346 |  |  | 2023-09-04 | 2023-08-21 |  | Petronas Pylon | 24m Pylon | 30M | Add R9264M M1821 x2+R9264H M901821 x2,Dismantle R8894E M1821(A8A) x4 | 0 | 1
1009Z | JLN PARIT 2 | Central |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 |  | AllStar | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038347 | [6 empty] | Land site
4757B | Felda Ijok | Northern |  | Modernization |  | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-05-28 | 2023-05-29 |  | 2023-06-04 |  | Closed | 2023-06-14 | 2023-07-15 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-YPTT-TSS-Northern-20230531-0015 | DU00002038348 |  |  | 2023-08-10 | 2023-08-07 |  | Tower | Tower | 60 | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3++R8881 S2100 x4+R8862A S2100(A6A) x2 |  | 3
1427A | PKNS Shah Alam | Central |  | Modernization |  | 2023Q4 | HQ 6 | Datasco | 4.6 TSSR Approved |  | 2023-05-19 | 2023-05-26 |  | 2023-05-29 |  | Closed | 2023-05-30 | 2023-07-26 | E//Razif | 2023-07-26 | CelcomDigi_RAN_Datasco_TSS_Central_20230523_0023 | DU00002038349 |  |  | 2023-12-15 | 2023-12-09 |  | Pole | 3m Boom (RT) | 7M | Add R9264H M901821 x3 + R9264M M1821 x3 + R8862A S2601 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x2++R8862A S2100(A6A) x1 |  | 123
4133B | Rifle Range | Northern |  | Modernization |  | 2023Q3 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-18 |  | 2023-05-21 |  | Closed | 2023-05-24 | 2023-08-03 | E//Yadav | 2023-08-03 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0008 | DU00002038350 |  |  | 2023-08-20 | 2023-08-20 |  | Pole | 3m Bipod (RT) | 2m | Add A9732 M1821 x1 + R9264M M1821 x2,Dismantle R8862A S2601(A6A) x1+R9224E M1821(AAB) x4 | 1
4216B | Lembah Ria | Northern |  | Modernization |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-09 |  | 2023-05-22 |  | Closed | 2023-05-22 | 2023-07-15 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038351 |  |  | 2023-08-17 | 2023-08-17 |  | Pole | 3m Bipod (RT) | 4 | Add A9732 M1821 x1+R9264M M1821 x2+R9264H M901821 x1,Dismantle R8894E M1821(A8A) x4 | 1
2069B | WT_UITMPNCKALAM | Central |  | Modernization |  | 2023Q3 | HQ 6 | GTSB | 4.6 TSSR Approved |  | 2023-05-19 | 2023-05-22 |  | 2023-05-31 |  | Closed | 2023-06-01 | 2023-07-12 | E//Razif | 2023-07-12 | CelcomDigi_RAN_GTSB_TSS_Central_20230523_0025 | DU00002038352 |  |  | 2023-12-20 | 2023-12-11 |  | Monople Tree | Tower | 45M | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 23
2457A | Sek 9A | Central |  | Modernization |  | 2023Q4 | HQ 1 | Datasco | 4.6 TSSR Approved |  | 2023-05-26 | 2023-06-23 |  | 2023-06-28 |  | Closed | 2023-07-04 | 2023-07-28 | E//Razif | 2023-07-28 | CelcomDigi_RAN_Datasco_TSS_Central_20230529_0023 | DU00002038353 |  |  | 2023-08-23 | 2023-08-21 |  | Wall mount boom | 3m Boom (RT) | 6m | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x3 | 12
1472B | Jalan Lombong Kebun | Central |  | Modernization |  | 2023Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-05-07 | 2023-05-12 |  | 2023-05-16 |  | Closed | 2023-05-17 | 2023-06-28 | E//Razif | 2023-06-28 | CelcomDigi_RAN_AllStar_TSS_Central_20230508_0006 | DU00002038354 |  |  | 2023-06-27 | 2023-06-26 |  | Monopole | 45m Monopole | 45 | Add R9264M M1821 x7,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 |  | 134
4465A | Taman Long Jaafar RDD | Northern |  | Modernization |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-06-08 | 2023-06-16 |  | 2023-06-19 |  | Closed | 2023-06-20 | 2023-07-17 | E//Hazida | 2023-07-15 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002038355 |  |  | 2023-08-08 | 2023-07-22 |  | Tower | 45m 4 Legged Tower | 37 | Add R9264M M1821 x7 + R8862A S2601 x3,Dismantle R9224E M1821(AAB) x4 |  | 134
2086B | SYABAS TMN INTAN BAIDURI ASIASPACE (REL) | Central |  | Modernization |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-06-24 | 2023-06-28 |  | 2023-07-04 |  | Closed | 2023-07-05 | 2023-07-12 | E//Kok Keen | 2023-07-12 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_0009 | DU00002038356 |  |  | 2023-08-18 | 2023-08-17 |  | Monople Tree | 30m Monopole | 35m | Add R9224E M1821 x3+R8854E S1800 x3,Dismantle R8894E M1821(A8A) x3
3159B5 | pBTS Taman Bentara (KM) | Central |  | Modernization |  | 2023Q4 | HQ 6 | AllStar | 4.6 TSSR Approved |  | 2023-05-26 | 2023-05-30 |  | 2023-06-01 |  | Closed | 2023-06-04 | 2023-07-27 | E//Razif | 2023-07-27 | CelcomDigi_RAN_AllStar_TSS_Central_20230529_0009 | DU00002038357 |  |  | 2023-07-06 | 2023-07-05 |  | Watertank | 25m pBTS | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
4266A | Masjid Terapung | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-27 |  | 2023-05-31 |  | Closed | 2023-06-05 | 2023-06-12 | E//Hazida | 2023-06-12 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002038358 |  |  | 2023-08-22 | 2023-08-22 |  | Wall mount boom | 60m 4 Legged Tower | 25 | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R9224E M1821(AAB) x3 |  | 1
4925B | Bukit Jana | Northern |  | Site Out (Modernization) | Modernization->Delete from system(MOCN Decomm)->Site Out->Replacement, Site Out (Modernization) | 2023Q4 |  | GCI | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2025-02-06 | 2025-08-06 | [8 empty] | SQ202508120598 | DU00002038359 | [6 empty] | 45m Monopole
1185C | Eco Sanctuary | Central |  | Modernization |  | 2023Q3 | AI | Solusi | 4.6 TSSR Approved |  | 2023-04-27 | 2023-05-11 |  | 2023-05-17 |  | Closed | 2023-05-20 | 2023-07-07 | E//Razif | 2023-07-06 | CelcomDigi_RANMW_Solusi_TSS_Central_20230609_0002 | DU00002038360 |  |  | 2023-08-17 | 2023-08-16 |  | Monopole | Land site | 30 | Add R9264H M901821 x4,Dismantle R9224E M1821(AAB) x4
4099A | Teluk Kumbar | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-17 | 2023-05-20 |  | 2023-05-24 |  | Closed | 2023-05-26 | 2023-06-10 | E//Hazida | 2023-06-08 | Celcom Digi_RAN-GTSB-TSS-Northern-20230509-0017 | DU00002038361 |  |  | 2023-06-21 | 2023-06-19 |  | Pole | 3m RT (Minimast) | 3.2 | Add R8894E M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8840-U216 x3+
4149A | TMNPKNK | Northern |  | Modernization |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-29 | 2023-06-21 |  | 2023-06-23 |  | Closed | 2023-06-28 | 2023-07-27 | E//Hazida | 2023-07-27 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230530-0021 | DU00002038362 |  |  | 2023-08-30 | 2023-08-29 |  | Minimast | 3m RT (Minimast) | 7 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2 + R8862A S2601 x3,Dismantle R8882 S1800B(B6B) x3+R8854D S2100(A4A) x3 | 3
4824A | City Plaza Alor | Northern |  | Modernization |  | 2023Q4 | WP | GTSB | 4.6 TSSR Approved |  | 2023-06-10 | 2023-06-12 |  | 2023-06-22 |  | Closed | 2023-07-19 | 2023-07-20 | E//Hazida | 2023-07-20 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002038363 |  |  | 2023-09-19 | 2023-09-19 |  | Wall mount boom | In-building system |  | Add R8852E S9000 x1 + R8862A S2100 x1,Dismantle R8882-GUL1812 x1+R8840-U216 x1+R8862A S1800 x1
1431B | Sek 13 Shah Alam Club | Central |  | Modernization |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-05-16 | 2023-06-19 |  | 2023-06-21 |  | Closed | 2023-06-23 | 2023-07-27 | E//Razif | 2023-07-27 | CelcomDigi_RAN_Datasco_TSS_Central_20230517_0022 | DU00002038364 |  |  | 2023-07-06 | 2023-07-05 |  | Monople Tree | 30m Monopole Tree | 31 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3
3788A | UiTM Kolej Rafflesia | Central |  | Modernization |  | 2023Q3 | HQ 6 | GTSB | 4.6 TSSR Approved |  | 2023-05-17 | 2023-05-22 |  | 2023-05-27 |  | Closed | 2023-05-29 | 2023-09-13 | E//Razif | 2023-09-13 | CelcomDigi_RAN_GTSB_TSS_Central_20230523_0025 | DU00002038365 |  |  | 2023-09-13 | 2023-09-12 |  | Monople Tree | 24m Lampole | 30M | Add R9264M M1821 x3,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3
1372A | Jln. Sg.Tua | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI,L2600 change to 40M¦Suggest to change solution to Bi-sector 1st,FF rejected sites,they suggest to change achor. 2nd,the rooftop site,tower structure is unable to support AAU+antenna. | 2023-05-08 | 2023-05-10 |  | 2023-05-13 |  | Closed | 2023-05-20 | 2023-06-06 | E//Kok Keen | 2023-05-22 | CelcomDigi_RAN_GTSB_TSS_Cental_20230511_0024 | DU00002038366 | NIC_S2_Change MM to BI,L2600 change to 40M_loading issue_Digi OB |  | 2023-08-16 | 2023-07-18 |  | Pole | 6m RT (Boom) | 6 | Add R9264M M1821 x2+R9264H M901821 x3+R8862A S2601 x1,Dismantle R8894E M1821(A8A) x4 | 0 | 23
4417C | Penang Times Square Phase 2 IB | Northern |  | Modernization |  | 2023Q3 | WP | GTSB | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-10 |  | 2023-05-26 |  | Closed | 2023-07-19 | 2023-07-21 | E//Hazida | 2023-07-20 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002038367 |  |  | 2023-08-25 | 2023-08-24 |  | Wall mount boom | In-building system |  | Add + R8862A S1800 x4 + R8862A S2100 x4,Dismantle R8882 S1800B(B6B) x4
1130H | ITEC MOBILE ENTERPRISE | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038368 | [6 empty] | Small Cell
4180B | QDOS Outdoor | Northern |  | Modernization |  | 2023Q3 | MH | GTSB | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦Space constraint for new AAU. Advise by solution to swap sector 1,2 & 3 to 12 port hybrid & use combiner | 2023-05-12 | 2023-05-15 |  | 2023-05-17 |  | Closed | 2023-05-23 | 2025-05-27 | E//Hannah | 2023-06-21 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002038369 | NIC_S2_Change MM to BI_Space constraint_Digi OB |  | 2023-07-04 | 2023-07-03 |  | Unipole | 3m Bipod (RT) | 6 | Add R9264M M1821 x6,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 |  | 23
4856A | Rasa Sayang Hotel | Northern |  | Modernization |  | 2023Q3 | WP | GTSB | 4.6 TSSR Approved |  | 2023-05-11 | 2023-05-17 |  | 2023-05-23 |  | Rectificating | 2023-07-19 | 2023-07-21 | E//Hazida | 2023-07-20 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002038370 |  |  | 2023-08-21 | 2023-08-21 |  | Wall mount boom | In-building system |  | Add R8862A S1800 x1 + R8862A S2601 x1,Dismantle R8882-GUL1812 x1
1245H | 99 Speedmart DENAI ALAM 2 | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038371 | [6 empty] | Small Cell
4923A | Tanjung Malim 2 | Central |  | Modernization |  | 2023Q4 | HQ 6 | Ascentrack | 4.6 TSSR Approved |  | 2023-06-02 | 2023-06-08 |  | 2023-06-13 |  | Closed | 2023-06-14 | 2023-06-28 | E//Hazida | 2023-06-22 | Celcomdigi_RAN_Ascentrack_TSS_Central_20230606_0021 | DU00002038372 |  |  | 2023-07-23 | 2023-07-18 |  | Lampole | 30M Lampole | 31 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle R8894E M1821(A8A) x3
2069A | Sek 8 Bkt Sentosa | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-21 | 2023-05-11 |  | 2023-05-15 |  | Closed | 2023-05-17 | 2023-06-08 | E//Kok Keen | 2023-05-30 | CelcomDigi_RAN_Datasco_TSS_Central_20230425_0015 | DU00002038373 |  |  | 2023-06-25 | 2023-06-19 |  | Tower | 60m 4 Legged Tower | 63 | Add A9732 M1821 x2 + R9264M M1821 x2,Dismantle R8894E M1821(A8A) x4 | 23
4456B | Bukit Larut RCC | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-06-14 | 2023-06-27 |  | 2023-07-04 |  | Closed | 2023-10-19 | 2023-10-20 | E//Daniel | 2023-10-20 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002038374 |  |  | 2023-08-09 | 2023-08-08 |  | Tower | 76m 4 Legged Tower | 60 | Add R9264M 1821 x3 + R8862A S2601 x3,Dismantle R8894E M1821(A8A) x3
4988B | Jln Mah-Sel (maxis E1 sharing) | Northern |  | Modernization |  | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-05-30 | 2023-06-02 |  | 2023-06-14 |  | Closed | 2023-06-21 | 2023-07-17 | E//Hazida | 2023-07-15 | Celcom Digi_RAN-YPTT-TSS-Northern-20230531-0015 | DU00002038375 |  |  | 2023-08-01 | 2023-07-28 |  | Tower | 60m 3 Legged Tower | 45m | Add A9732 M1821 x1+R9264M M1821 x2+R9264H M901821 x1,Dismantle R8894E M1821(A8A) x3 | 2
4020B | Kg Bkt Kecil | Northern |  | Modernization |  | 2023Q3 | MH | GTSB | 4.6 TSSR Approved |  | 2023-05-13 | 2023-05-18 |  | 2023-05-27 |  | Closed | 2023-05-30 | 2023-07-07 | CD//Quah | 2023-07-05 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002038376 |  |  | 2023-07-14 | 2023-07-13 |  | Tower | Tower | 60m | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle R8860E-GU908 x2+R8882-GUL1812 x1+R8882 S1800B(B6B) x3+R8881 S2100 x3 |  | 2
4678A | Jalan Langgar | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-31 | 2023-06-12 |  | 2023-06-26 |  | Closed | 2023-06-28 | 2023-07-27 | E//Hazida | 2023-07-27 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002038377 |  |  | 2023-09-08 | 2023-09-08 |  | Tower | 60m 4 Legged Tower | 60m | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x4 | 123
1197B | KG BUKIT KUCHING | Central |  | Modernization |  | 2023Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-28 | 2023-04-29 |  | 2023-05-03 |  | Closed | 2023-05-05 | 2023-06-06 | CD//Tee | 2023-05-15 | CelcomDigi_RAN_GTSB_TSS_Central_20230428_0022 | DU00002038378 |  |  | 2023-06-28 | 2023-06-28 |  | Tower | 60m 4 Legged Tower | 60M | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 1
4149C | Green Lane (REL) | Northern |  | Modernization |  | 2023Q3 | MH | GTSB | 4.6 TSSR Approved |  | 2023-05-02 | 2023-05-16 |  | 2023-05-19 |  | Closed | 2023-05-24 | 2023-06-21 | E//Hazida | 2023-06-21 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002038379 |  |  | 2023-07-07 | 2023-07-05 |  | H-bracket pole | 3m Bipod (RT) | 5M | Add R9264M M1821 x4,Dismantle R8882 S1800(B) x3+R8882 S1800B(B6B) x5+R8862A S2100(A6A) x4
4040C | Tmn Kami | Northern |  | Modernization |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-06-08 | 2023-06-20 |  | 2023-06-22 |  | Closed | 2023-06-27 | 2023-07-15 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002038380 |  |  | 2023-07-27 | 2023-07-26 |  | Pole | 6m Unipole RT | 5 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3++R8881 S2100 x3+
2647B | Jln Paip Meru | Central |  | Modernization |  | 2023Q3 | YZ | Magicell | 4.6 TSSR Approved |  | 2023-05-13 | 2023-05-18 |  | 2023-05-22 |  | Closed | 2023-05-23 | 2023-06-17 | E//Razif | 2023-06-15 | CelcoDigi_RAN_Magicell_TSS_Central_20230517_0009 | DU00002038381 |  |  | 2023-06-13 | 2023-06-12 |  | Monople Tree | 30m Monopole | 30m | Add R9264H M901821 x3,Dismantle R9224E M1821(AAB) x3
3367B | Giant Hypermarket Shah Alam Outdoor | Central |  | Modernization |  | 2023Q4 | XH | GTSB | 4.6 TSSR Approved |  | 2023-06-01 | 2023-06-07 |  | 2023-06-14 |  | Closed | 2023-06-15 | 2023-07-21 | E//Razif | 2023-07-20 | CelcomDigi_RAN_GTSB_TSS_Central_20230606_0027 | DU00002038382 |  |  | 2023-10-24 | 2023-07-18 |  | In-Building System | 3m Boom (RT) | 3M | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8894E M1821(A8A) x3 |  | 2
4766A | Tmn Mal | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GCI | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦Maxis reject add AAU | 2023-06-07 | 2023-06-12 |  | 2023-06-14 |  | Closed | 2023-06-21 | 2023-07-28 | E//Hazida | 2023-07-28 | Celcom Digi_RAN-GCI-TSS-Northern-20230607-0024 | DU00002038383 | NIC_S3_Change MM to BI_owner reject_MAXIS |  | 2023-09-08 | 2023-08-29 |  | Tower | 45m 3 Legged Tower | 50 | Add R9264M M1821 x6,Dismantle R8882 S1800B(B6B) x3+R8854D S2100(A4A) x3 |  | 123
4073D | Autocity Jelutong (REL) | Northern |  | Modernization |  | 2023Q3 | MH | GCI | 4.6 TSSR Approved |  | 2023-05-01 | 2023-05-02 |  | 2023-05-05 |  | Closed | 2023-05-07 | 2023-05-25 | CD//Shamsul | 2023-05-15 | Celcom Digi_RAN-GCI-TSS-Northern-20230502-0011 | DU00002038384 |  |  | 2023-08-24 | 2023-08-23 |  | Minimast | 3m Boom (RT) | 6.2m | Add R9264M M1821 x4,Dismantle R8882 S1800B(B6B) x3+R8862A S1800(B6A) x1+R8854D S2100(A4A) x4 |  | 3
1365B | Tmn Bukit Subang (REL) | Central |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-05-27 | 2023-06-01 |  | 2023-06-06 |  | Closed | 2023-06-11 | 2023-06-21 | E//Kok Keen | 2023-06-21 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002038385 |  |  | 2023-08-30 | 2023-07-02 |  | Monople Tree | 30m Monopole | 25 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1
3176B8 | pBTS Tropicana Aman (MCMC) | Central |  | Modernization |  | 2023Q3 | AI | Solusi | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-25 |  | 2023-05-26 |  | Closed | 2023-05-27 | 2023-07-13 | E//Razif | 2023-07-13 | CelcomDigi_RAN_Solusi_TSS_Central_20230511_0001 | DU00002038386 |  |  | 2023-07-09 | 2023-07-08 |  | Guide mast | Land site | 24M | Add R9264H M901821 x3,Dismantle R9224E M1821(AAB) x3
1764B | Balai Polis Genting Highland | Central |  | Modernization |  | 2023Q4 | XH | GTSB | 4.6 TSSR Approved |  | 2023-05-25 | 2023-05-31 |  | 2023-06-08 |  | Closed | 2023-06-09 | 2023-06-28 | E//Kok Keen | 2023-06-20 | CelcomDigi_RAN_GTSB_TSS_Central_20230529_0025 | DU00002038387 |  |  | 2023-07-28 | 2023-07-18 |  | In-Building System | 3m Bipod (RT) | 4m | Add R9264M M1821 x3+R8862A S2601 x1 ,Dismantle R8854D S2100(A4A) x2+R8892N M1821(BAB) x2 |  | 2
4052A | Island Plaza | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-15 | 2023-07-18 |  | 2023-07-21 |  | Closed | 2023-07-25 | 2023-07-28 | E//Hazida | 2023-07-28 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002038388 |  |  | 2023-09-10 | 2023-08-30 |  | Pole | 3m Boom (RT) | 33 | Add A9732 M1821 x3,Dismantle R8854E S1800(A6A) x3+R8854D S2100(A4A) x3 | 123
4001A | Crown Prince Hotel V6 | Northern |  | Modernization |  | 2023Q3 | MH | GTSB | 4.6 TSSR Approved |  | 2023-05-06 | 2023-05-11 |  | 2023-05-15 |  | Closed | 2023-05-18 | 2023-07-22 | E//Hazida | 2023-07-22 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002038389 |  |  | 2023-08-14 | 2023-08-14 |  | Wall mount boom | 6m RT (Boom) |  | Add R9264M M1821 x5 + R8862A S2601 x2,Dismantle R8894E M1821(A8A) x3 |  | 23
4628D | JPS Sungai Pinang (REL) | Northern |  | Modernization |  | 2023Q3 | SM | YPTT | 4.6 TSSR Approved |  | 2023-05-02 | 2023-05-06 |  | 2023-05-10 |  | Rectificating | 2023-05-12 | 2023-05-25 | CD//Shamsul | 2023-05-16 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0008 | DU00002038390 |  |  | 2023-08-24 | 2023-08-25 |  | Monopole | Land site | 45 | Add R9264H M901821 x3,Dismantle R9224E M1821(AAB) x3
2611A12 | pBTS Hartalega Bestari Jaya REL | Central |  | Modernization |  | 2023Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-25 |  | 2023-06-02 |  | Closed | 2023-06-02 | 2023-06-19 | CD//Nik Ashraf | 2023-06-19 | CelcomDigi_RAN_GTSB_TSS_Central_20230523_0025 | DU00002038391 |  |  | 2023-07-10 | 2023-06-28 |  | Guide mast | 25m pBTS | 24M | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1++R8881 S2100 x3+
4082A | St Johns Ambulans | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-10 |  | 2023-05-15 |  | Closed | 2023-05-18 | 2023-06-17 | E//Hazida | 2023-06-16 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002038392 |  |  | 2023-07-05 | 2023-06-28 |  | Pole | 76m Tower | 3 | Add R9264M M1821 x3,Dismantle R8882 S1800(B) x3+R8882 S1800B(B6B) x3+R8881 S2100 x1+
1673C | Setia Avenue | Central |  | Modernization |  | 2023Q3 | AI | Magicell | 4.6 TSSR Approved |  | 2023-04-28 | 2023-05-04 |  | 2023-05-07 |  | Closed | 2023-05-08 | 2023-06-17 | E//Razif | 2023-06-15 | CelcomDigi_RAN_Magicell_TSS_Central_20230502_0006 | DU00002038393 |  |  | 2023-06-29 | 2023-06-13 |  | Monopole | Land site | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
4253A | Macalister Road | Northern |  | Modernization |  | 2023Q3 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-04-29 | 2023-05-05 |  | 2023-05-08 |  | Closed | 2023-05-09 | 2023-05-10 | CD//Affendi | 2023-05-09 | Celcom Digi_RAN-GTSB-TSS-Northern-20230502-0012 | DU00002038394 |  |  | 2023-08-25 | 2023-08-24 |  | Pole | 3m Boom (RT) | N/A | Add R9264M M1821 x3,Dismantle R9224E M1821(AAB) x3
1490H | 99 Speedmart TMN SELAYANG JAYA | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038395 | [6 empty] | Small Cell
4640C | Bkt Jambul | Northern |  | Modernization |  | 2023Q3 | SM | YPTT | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-11 |  | 2023-05-14 |  | Closed | 2023-05-23 | 2023-06-17 | E//Hazida | 2023-06-16 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0008 | DU00002038396 |  |  | 2023-07-03 | 2023-07-03 |  | BillBoard | Billboard | 23m | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
4034A | Bukit Relau | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-06-17 | 2023-07-05 |  | 2023-07-06 |  | Closed | 2023-07-06 | 2023-07-14 | E//Hazida | 2023-07-07 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002038397 |  |  | 2023-07-21 | 2023-07-18 |  | Tower | 70m 4 Legged Tower | 60m | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8882 S1800(B) x3+R8862A S1800(B6A) x2+R8862A S2100(A6A) x4+R8854 S2600(A4A) x2 | 23
3103A | Tengku Kelana (REL) | Central |  | Modernization |  | 2023Q3 | XH | YPTT | 4.6 TSSR Approved |  | 2023-05-16 | 2023-05-18 |  | 2023-05-22 |  | Closed | 2023-05-22 | 2023-06-20 | E//Sumitra | 2023-06-20 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002038398 |  |  | 2023-06-23 | 2023-06-22 |  | Unipole | 6m Unipole RT | 8m | Add R9264M M1821 x6 + R8862A S2601 x3,Dismantle R8894E M1821(A8A) x3 |  | 123
4049A | Sunshine Square | Northern |  | Modernization |  | 2023Q3 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-05-06 | 2023-05-15 |  | 2023-05-18 |  | Closed | 2023-06-22 | 2023-07-07 | E//Hazida | 2023-07-05 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0008 | DU00002038399 |  |  | 2023-07-23 | 2023-07-18 |  | Pole | 6m RT (Wall Mounted Pole) | 5 | Add A9732 M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R8882 S2600(B4A) x1+R8862A S2600(A4A) x2+R8854 S2600(A4A) x1+R8894E M1821(A8A) x4 | 123
3713C | Sek 20 Shah Alam (REL) | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-05-30 | 2023-06-07 |  | 2023-06-12 |  | Closed | 2023-06-17 | 2023-07-21 | E//Razif | 2023-07-20 | CelcomDigi_RAN_GTSB_TSS_Central_20230531_0026 | DU00002038400 |  |  | 2023-12-18 | 2023-12-17 |  | In-Building System | 3m Boom (RT) | 6M | Add R9264M M1821 x4+R8854 S2600 x1,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x2+R8862A S2100(A6A) x3+R8882-L268 x1 |  | 1
3026C | Kg Sg Sembilang (REL) | Central |  | Modernization |  | 2023Q3 | IE | GTSB | 4.6 TSSR Approved |  | 2023-04-29 | 2023-05-05 |  | 2023-05-08 |  | Closed | 2023-05-10 | 2023-06-28 | CD//Ali akaram | 2023-06-21 | CelcomDigi_RAN_GTSB_TSS_20230505_0023 | DU00002038401 |  |  | 2023-06-17 | 2023-06-13 |  | Monople Tree | Tower | 30 | Add R9264M M1821 x5 + R8862A S2600 x2,Dismantle R8894E M1821(A8A) x3 |  | 12
3046M | Jalan Teratai Klang | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038402 | [6 empty] | Micro Cell
2093A | Proton City (Asiaspace) | Central |  | Modernization |  | 2023Q4 | HQ 6 | Ascentrack | 4.6 TSSR Approved |  | 2023-05-26 | 2023-06-23 |  | 2023-06-25 |  | Closed | 2023-06-26 | 2023-07-31 | E//Kok Keen | 2023-07-31 | Celcomdigi_RAN_Ascentrack_TSS_Central_20230529_0020 | DU00002038403 |  |  | 2023-08-05 | 2023-07-18 |  | Monopole | 45m Monopole | 45 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x3,Dismantle R8892E M1821(BAA) x3+R9224E M1821(AAB) x1 | 1
4637D | Akasia Apartment (REL) | Northern |  | Modernization |  | 2023Q3 | MH | YPTT | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-13 |  | 2023-05-16 |  | Closed | 2023-05-17 | 2023-05-30 | E//Hazida | 2023-05-30 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0008 | DU00002038404 |  |  | 2023-07-28 | 2023-07-18 |  | Pole | Land site | 4m | Add R9264H M901821 x3 + R9264M M1821 x2,Dismantle R9224E M1821(AAB) x3 |  | 12
1816A | Shah Alam Mall | Central |  | Modernization |  | 2023Q4 | CR | Datasco | 4.6 TSSR Approved |  | 2023-08-08 | 2023-08-11 |  | 2023-08-17 |  | Closed | 2023-09-21 | 2023-10-01 | E//Nazrul | 2023-09-22 | CelcomDigi_RAN_Datasco_TSS_Central_20230808 | DU00002038405 |  |  | 2023-10-10 | 2023-10-03 |  | Portables BTS | In-building system | NA | Add R8862A S1800 x2 + R8862A S2100 x2,Dismantle R8882-GUL1812 x2
4029B | Bkt Bendera Upper Station | Northern |  | Modernization | Modernization->TBD->Modernization | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-19 |  | 2023-05-23 |  | Closed | 2023-05-29 | 2023-07-27 | E//Hazida | 2023-07-27 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002038406 |  |  | 2024-06-15 | 2023-08-04 |  | Wall mount boom | 3m Bipod (RT) | N/A | Add R9264H M901821 x4,Dismantle R8882-GUL1812 x2+R8882 S1800(B) x1+R8862A S1800(B6A) x1+R8881 S2100 x3+R8862A S2100(A6A) x1
4144A | TMN BADLISHAH | Northern |  | Modernization |  | 2023Q4 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-05-30 | 2023-06-06 |  | 2023-06-09 |  | Closed | 2023-06-12 | 2023-07-17 | E//Hazida | 2023-07-17 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002038407 |  |  | 2023-09-06 | 2023-08-29 |  | Wall mount boom | 6m Tripod (RT) | 6 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R9224E M1821(AAB) x3 |  | 13
3719B | Hulu Yam Baharu | Central |  | Modernization |  | 2023Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2023-09-07 | 2023-09-11 |  | 2023-09-13 |  | Closed | 2023-09-13 | 2023-09-15 | E//Kok Keen | 2023-09-15 | CelcomDigi_RAN_Allstar_TSS_Central_20230911 | DU00002038408 |  |  | 2023-09-30 | 2023-09-26 |  |  | 24m Lampole | 25 | Add R9264H M901821 x4,Dismantle R8862A S1800(B6A) x4+R8862A S2100(A6A) x4
4757C | Wisma Yatim Islam | Northern |  | Modernization |  | 2023Q3 | WP | GCI | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦wall mpount pole, Structure unable to load AAU weight | 2023-05-08 | 2023-05-09 |  | 2023-06-07 |  | Closed | 2023-06-13 | 2023-07-22 | E//Hazida | 2023-07-22 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038409 | NIC_S1_Change MM to BI_loading issue_Digi OB |  | 2023-08-19 | 2023-08-18 |  | Pole | 6m Unipole RT | 4 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 2
3738B | Jalan Yeo Guan Hup | Central |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-05-23 | 2023-05-25 |  | 2023-05-27 |  | Closed | 2023-05-29 | 2023-06-24 | CD//Ali akaram | 2023-06-23 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002038410 |  |  | 2023-06-17 | 2023-06-16 |  | Pole | 3m Bipod (RT) | 6 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
4021A | Public Finance | Northern |  | Modernization |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-05-01 | 2023-05-19 |  | 2023-05-18 |  | Closed | 2023-05-24 | 2023-07-26 | E//Hazida | 2023-07-26 | Celcom Digi_RAN-GCI-TSS-Northern-20230502-0011 | DU00002038411 |  |  | 2023-08-24 | 2023-08-18 |  | Rooftop | 60m 4 Legged Tower | 16 | Add R9264H M901821 x1 + R9264M M1821 x6 + R8862A S2601 x3,Dismantle R9224E M1821(AAB) x4 |  | 134
4653B | TiTi Gajah | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GCI | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI,L2600 change to 40M¦Maxis reject add AAU | 2023-05-28 | 2023-05-30 |  | 2023-06-02 |  | Closed | 2023-06-07 | 2023-07-25 | E//Daniel | 2023-07-25 | Celcom Digi_RAN-GCI-TSS-Northern-20230529-0022 | DU00002038412 | NIC_S3_Change MM to BI,L2600 change to 40M_owner reject_MAXIS |  | 2023-09-11 | 2023-08-29 |  | Tower | 45m 3 Legged Tower | 50 | Add R9264M M1821 x1+R9264H M901821 x3+R8862A S2600 x1,Dismantle R8894E M1821(A8A) x3 |  | 3
1667H | 99 Speedmart PK Tmn Bernam Baru | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038413 | [6 empty] | Small Cell
4021B | Tropical Fruit Farm | Northern |  | Modernization |  | 2023Q3 | HQ 2 | YPTT | 4.6 TSSR Approved |  | 2023-05-04 | 2023-05-09 |  | 2023-05-11 |  | Closed | 2023-05-13 | 2023-07-22 | E//Hazida | 2023-07-22 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0008 | DU00002038414 |  |  | 2023-08-22 | 2023-08-10 |  | Tower | Tower | 61m | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8892E M1821(BAA) x2
3447C | Eco Grandeur | Central |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-05-07 | 2023-05-11 |  | 2023-05-31 |  | Closed | 2023-05-18 | 2023-08-15 | E//Razif | 2023-08-15 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002038415 |  |  | 2023-07-04 | 2023-07-03 |  | BillBoard | Land site | 27m | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 |  | 1
1170C | KFC I-City | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-08-08 | 2023-08-09 |  | 2023-08-17 |  | Closed | 2023-08-19 | 2023-08-28 | E//Razif | 2023-08-22 | CelcomDigi_RAN_GTSB_TSS_Central_20230808 | DU00002038416 |  |  | 2023-09-12 | 2023-09-11 |  | In-Building System | Land site | 4 | Add R9264H M901821 x4 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 |  | 2
1882B | NS Highway KM414.9 (Timecel) | Central |  | Modernization |  | 2023Q4 | YZ | Ascentrack | 4.6 TSSR Approved |  | 2023-07-07 | 2023-07-14 |  | 2023-07-18 |  | Closed | 2023-07-20 | 2023-08-15 | E//Kok Keen | 2023-07-20 | CelcomDigi_RANMW_Ascentrack_Central_20230706_0010 | DU00002038417 |  |  | 2023-09-27 | 2023-09-27 |  | Monopole | 60m 4 Legged Tower | 45 | Add R9264M M1821 x2,Dismantle R8894E M1821(A8A) x2
4171B | Beach Street 2 | Northern |  | Modernization |  | 2023Q3 | WP | GTSB | 4.6 TSSR Approved |  | 2023-04-28 | 2023-05-13 |  | 2023-05-19 |  | Closed | 2023-05-23 | 2023-07-27 | E//Hazida | 2023-07-27 | Celcom Digi_RAN-GTSB-TSS-Northern-20230505-0013 | DU00002038418 |  |  | 2023-08-19 | 2023-08-19 |  | Wall mount boom | 3m Bipod (RT) | N/A | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 12
3782A | Taman Makmur | Central |  | Modernization |  | 2023Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2023-05-29 | 2023-05-30 |  | 2023-05-31 |  | Closed | 2023-06-01 | 2023-08-01 | E//Razif | 2023-07-27 | CelcomDigi_RAN_AllStar_TSS_Central_20230529_0009 | DU00002038419 |  |  | 2023-07-09 | 2023-07-05 |  | Portables BTS | Tower | 5 | Add R9264H M901821 x3,Dismantle R8882 S1800(B) x1+R8882 S1800B(B6B) x2+R8862A S2100(A6A) x3
3648B | Taman Mewah Jaya 3 | Central |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-05-11 | 2023-05-13 |  | 2023-05-16 |  | Closed | 2023-05-18 | 2023-06-22 | CD//Sapian | 2023-06-22 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002038420 |  |  | 2023-06-10 | 2023-06-10 |  | Pole | 3m Boom (RT) | 5m | Add R9264H M901821 x3,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3
4586A | Tmn Berkat Taiping | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-25 | 2023-05-29 |  | 2023-06-06 |  | Closed | 2023-06-12 | 2023-07-17 | E//Hazida | 2023-07-15 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002038421 |  |  | 2023-08-03 | 2023-07-22 |  | Tower | 60m 3 Legged Tower | 45M | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 23
4559D | Sri Saujana Macallum | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-10 |  | 2023-05-13 |  | Closed | 2023-05-15 | 2023-06-02 | E//Hazida | 2023-05-29 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038422 |  |  | 2023-08-24 | 2023-08-24 |  | Pole | 3M Bipod - RT | 4 | Add R9264H M901821 x3,Dismantle R9224E M1821(AAB) x3
4039C | Tmn Long Jaafar | Northern |  | Modernization |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-29 | 2023-06-13 |  | 2023-06-16 |  | Closed | 2023-06-20 | 2023-07-15 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230530-0021 | DU00002038423 |  |  | 2023-07-26 | 2023-07-22 |  | Monople Tree | 30m Monopole Tree | 27m | Add R9264H M901821 x4,Dismantle R8862A S1800(B6A) x4+R8854D S2100(A4A) x4
4475C | Marina Bay Penang | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved | ¦ 0206 - fup to SA by WA, Dila informed, TP Approved and issue closed 30/1 - Design trigger SA to check with SO parapet wall type ¦11/6- PE revert can proceed if aparapet is concret. | 2023-05-17 | 2023-05-26 |  | 2023-05-31 |  | Closed | 2023-06-05 | 2023-06-13 | CD//Shamsul | 2023-06-13 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002038424 |  |  | 2024-02-08 | 2023-08-18 |  | Pole | 3m Boom (RT) | 3 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 13
3240D | Jalan Seri Pagi | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-17 | 2023-04-25 |  | 2023-04-28 |  | Closed | 2023-05-01 | 2023-06-03 | CD//Sapian | 2023-05-16 | CelcomDigi_RAN_Datasco_TSS_Central_20230418_0013 | DU00002038425 |  |  | 2023-06-12 | 2023-06-11 |  | Lampole | 24m Lampole | 35m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1398B | Saujana Utama Sg Buloh (MAXIS) | Central |  | Modernization |  | 2023Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-23 | 2023-07-06 |  | 2023-07-14 |  | Closed | 2023-07-24 | 2023-08-17 | E//Kok Keen | 2023-08-17 | CelcomDigi_RANMW_GTSB_TSS_Central_20230626_0007 | DU00002038426 |  |  | 2023-10-05 | 2023-10-02 |  | Tower | 60m 3 Legged Tower | 60m | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8894E M1821(A8A) x3 |  | 13
1709H | 99 Speedmart Tmn Bidara | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038427 | [6 empty] | Small Cell
4716B | Redang Panjang | Northern |  | Modernization |  | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-05-27 | 2023-06-10 |  | 2023-06-14 |  | Closed | 2023-06-21 | 2023-07-15 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-YPTT-TSS-Northern-20230530-0014 | DU00002038428 |  |  | 2023-07-29 | 2023-07-26 |  | Tower | 60m 4 Legged Tower | 60 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1 |  | 2
4540C | Macallum Construction | Northern |  | Modernization |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-15 |  | 2023-05-17 |  | Closed | 2023-06-26 | 2023-07-27 | E//Hazida | 2023-07-27 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038429 |  |  | 2023-08-23 | 2023-08-23 |  | Lampole | 18M Lampole | 19 | Add R9264M M1821 x2,Dismantle R8894E M1821(A8A) x2
2436A | Bukit Beruntung (CELCOM) | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-05-17 | 2023-06-09 |  | 2023-06-12 |  | Closed | 2023-06-19 | 2023-06-27 | E//Kok Keen | 2023-06-27 | CelcomDigi_RAN_Datasco_TSS_Central_20230428_0018 | DU00002038430 |  |  | 2023-10-27 | 2023-09-27 |  | Tower | Tower | 74 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 | 23
4711M | Love Lane | Northern |  | MOCN As-Is |  | 2023Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038431 | [6 empty] | Micro Cell
1194B | Pekan Tg Karang | Central |  | Modernization |  | 2023Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2023-06-12 | 2023-06-19 |  | 2023-06-22 |  | Closed | 2023-06-27 | 2023-08-22 | E//Razif | 2023-07-18 | CelcomDigi_RAN_AllStar_TSS_Central_20230606_0011 | DU00002038432 |  |  | 2023-08-22 | 2023-08-21 |  | Tower | 45m Tower | 60M | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8892E M1821(BAA) x3 |  | 13
2722A | Anggerik Eria Watertank | Central |  | Modernization |  | 2023Q3 | SS | AllStar | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-13 |  | 2023-05-16 |  | Closed | 2023-05-16 | 2023-06-06 | E//Razif | 2023-05-23 | CelcomDigi_RAN_Allstar_TSS_Central_20230511_0007 | DU00002038433 |  |  | 2023-06-21 | 2023-06-13 |  | Monople Tree | 45m Monopole | 45 | Add R9264M M1821 x3,Dismantle R8892E M1821(BAA) x3
1961B | Sg Sembilang(TMTouch) | Central |  | Modernization |  | 2023Q3 | YZ | GTSB | 4.6 TSSR Approved |  | 2023-04-29 | 2023-05-02 |  | 2023-05-04 |  | Closed | 2023-05-10 | 2023-06-06 | CD//Syafiq | 2023-05-18 | CelcomDigi_RAN_GTSB_TSS_20230505_0023 | DU00002038434 |  |  | 2023-06-16 | 2023-06-13 |  | Tower | Tower | 60M | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2600 x3,Dismantle R9224E M1821(AAB) x2 |  | 12
3321A2 | pBTS Kg Sungai Kajang (MS) | Central |  | Modernization |  | 2023Q4 | YZ | AllStar | 4.6 TSSR Approved |  | 2023-05-30 | 2023-05-31 |  | 2023-06-02 |  | Closed | 2023-06-03 | 2023-07-27 | E//Razif | 2023-07-27 | CelcomDigi_RAN_AllStar_TSS_Central_20230531_0010 | DU00002038435 |  |  | 2023-07-11 | 2023-07-11 |  | Watertank | Land site | 24 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
2727A | Extreme Park Shah Alam | Central |  | Modernization |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-05-16 | 2023-06-20 |  | 2023-07-07 |  | Closed | 2023-07-15 | 2023-07-31 | E//Razif | 2023-07-31 | CelcomDigi_RAN_Datasco_TSS_Central_20230517_0022 | DU00002038436 |  |  | 2023-08-03 | 2023-08-03 |  | Lampole | 20m Lampole | 22 | Add R9264H M901821 x3 + R9264M M1821 x2,Dismantle R8892E M1821(BAA) x5 |  | 23
4048A | Genting Shoplot | Northern |  | Modernization |  | 2023Q3 | MH | GTSB | 4.6 TSSR Approved |  | 2023-05-01 | 2023-05-15 |  | 2023-05-19 |  | Closed | 2023-05-22 | 2023-07-15 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-GTSB-TSS-Northern-20230502-0012 | DU00002038437 |  |  | 2023-08-18 | 2023-08-18 |  | Minimast | 3m Boom (RT) | 8 | Add A9732 M1821 x1 + R9264M M1821 x2,Dismantle R8862A S1800(B6A) x2+R8862A S2100(A6A) x3+R8882 S2600(B4A) x2+R9224E M1821(AAB) x3 | 2
2046A | Karak HW KM35.6 (Billboard) | Central |  | Modernization |  | 2023Q4 | HQ 6 | Magicell | 4.6 TSSR Approved |  | 2023-06-22 | 2023-07-10 |  | 2023-07-13 |  | Closed | 2023-07-18 | 2023-07-20 | E//Kok Keen | 2023-07-20 | CelcomDigi_RAN_Magicell_TSS_Central_20230623_0016 | DU00002038438 |  |  | 2023-08-29 | 2023-08-23 |  | BillBoard | Billboard | 16 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882 S1800(B) x3
4715M | Farlim Topaire | Northern |  | MOCN As-Is |  | 2023Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038439 | [6 empty] | Micro Cell
2560B | Surau Ar-Rahim | Central |  | Modernization |  | 2023Q4 | HQ 6 | YPTT | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI,L2600 change to 40M¦Owner rejected, so that can not install due to loading issue | 2023-07-04 | 2023-07-07 |  | 2023-07-18 |  | Closed | 2023-07-21 | 2023-07-25 | E//Kok Keen | 2023-07-25 | CelcomDigi_RANMW_YPTT_Central_20230706_0007 | DU00002038440 | NIC_S2_Change MM to BI,L2600 change to 40M_loading issue_BANGKIT SETIA |  | 2023-09-27 | 2023-09-27 |  | Lampole | 24m Lampole | 24 | Add R9264H M901821 x3 + R9264M M1821 x2+R8862A S2601 x2,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 12
4069A | Green Hall | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-04-28 | 2023-06-02 |  | 2023-06-07 |  | Closed | 2023-06-09 | 2023-07-22 | E//Hazida | 2023-07-22 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230502-0012 | DU00002038441 |  |  | 2023-08-28 | 2023-08-24 |  |  | 6m RT (Boom) | 6 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x1+R8882 S1800(B) x1+R8882 S1800B(B6B) x3+R8862A S1800(B6A) x2+R8840-U216 x3
2669B | Taman Jasa Sungai Tua | Central |  | Modernization |  | 2023Q4 | HQ 6 | Magicell | 4.6 TSSR Approved |  | 2023-05-29 | 2023-05-31 |  | 2023-06-02 |  | Closed | 2023-06-05 | 2023-06-09 | E//Kok Keen | 2023-06-09 | CelcomDigi_RAN_Magicell_TSS_Central_20230531_0010 | DU00002038442 |  |  | 2023-07-06 | 2023-07-05 |  | In-Building System | 3m Boom (RT) | 3m | Add R9264M M1821 x6,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 |  | 123
3772A | SKVE Bandar Saujana Putra | Central |  | Modernization |  | 2023Q3 | XH | Solusi | 4.6 TSSR Approved |  | 2023-04-27 | 2023-05-10 |  | 2023-05-15 |  | Closed | 2023-05-29 | 2023-07-13 | E//Razif | 2023-07-13 | CelcomDigi_RANMW_Solusi_TSS_Central_20230609_0002 | DU00002038443 |  |  | 2023-07-11 | 2023-06-28 |  | Monople Tree | 24m Pylon | 45m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1024A | Genting Hotel 2 | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-05-25 | 2023-06-06 |  | 2023-06-10 |  | Closed | 2023-06-12 | 2023-11-14 | E//Razif | 2023-11-10 | CelcomDigi_RAN_GTSB_TSS_Central_20230529_0025 | DU00002038444 |  |  | 2023-11-14 | 2023-07-18 |  | In-Building System | 8m RT (Wall Mounted Pole) | 6m | Add R9264M M1821 x2 + R8862A S2601 x1,Dismantle R8894E M1821(A8A) x1 |  | 1
1149A | KJS Bukit Beruntung | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-19 | 2023-05-03 |  | 2023-05-06 |  | Closed | 2023-05-10 | 2024-02-16 | E//Kok Keen | 2023-05-31 | CelcomDigi_RAN_Datasco_TSS_Central_20230420_0015 | DU00002038445 |  |  | 2023-06-01 | 2023-05-30 |  | Tower | 60m 4 Legged Tower | 60m | Add A9732 M1821 x3,Dismantle R9224E M1821(AAB) x3 | 123
1608B | Puncak Alam Tower | Central |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-06-06 | 2023-06-06 |  | 2023-06-09 |  | Closed | 2023-06-13 | 2023-07-12 | E//Razif | 2023-07-11 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002038446 |  |  | 2023-08-14 | 2023-08-02 |  | Monopole | 6m Unipole RT | 31M | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 |  | 3
2638A | RASA ULU SELANGOR | Central |  | Modernization |  | 2023Q4 | HQ 6 | Futong | 4.6 TSSR Approved |  | 2023-06-22 | 2023-06-22 |  | 2023-06-28 |  | Closed | 2023-06-30 | 2023-07-07 | E//Kok Keen | 2023-07-07 | CelcomDigi_RAN_Futong_TSS_Central_20230623_0004 | DU00002038447 |  |  | 2023-07-27 | 2023-07-25 |  | Tower | 60m 4 Legged Tower | 61 | Add A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2601 x1,Dismantle R8894E M1821(A8A) x2 | 12(S1->S3,S2->S1，Addition Sector name S2,rename sector ID,FDD MM@ new S1S3)
2710C | Bandar Seri Coalfield | Central |  | Modernization |  | 2023Q4 | HQ 6 | Magicell | 4.6 TSSR Approved |  | 2023-05-25 | 2023-05-30 |  | 2023-06-02 |  | Closed | 2023-06-05 | 2023-11-22 | E//Razif | 2023-06-09 | CelcomDigi_RAN_GTSB_TSS_Central_20230529_0010 | DU00002038448 |  |  | 2023-07-06 | 2023-07-05 |  | Monopole | Lampole | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
3623B | Jln Jenjarum 1g | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-17 | 2023-04-25 |  | 2023-05-03 |  | Closed | 2023-05-06 | 2023-06-03 | CD//Norhaliza | 2023-05-19 | CelcomDigi_RAN_Datasco_TSS_Central_20230418_0013 | DU00002038449 |  |  | 2023-06-10 | 2023-06-08 |  |  | 3m Boom (RT) | 6m | Add R9264M M1821 x3,Dismantle R8892E M1821(BAA) x3
1702A | Bkt. Tagar (Trunk) | Central |  | Modernization |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-06-28 | 2023-07-05 |  | 2023-07-07 |  | Closed | 2023-07-10 | 2023-07-13 | E//Kok Keen | 2023-07-13 | CelcomDigi_RAN_Magicell_TSS_Central_20230630_0019 | DU00002038450 |  |  | 2023-07-25 | 2023-07-24 |  | Tower | 60m 4 Legged Tower | 75 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
3825B | GENTING STAFF(RSC) 5 | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-08-18 | 2023-08-10 |  | 2023-08-17 |  | Closed | 2023-08-28 | 2023-08-28 | E//Nazrul | 2023-08-28 | CelcomDigi_RAN_GTSB_TSS_Central_20230819 | DU00002038451 |  |  | 2025-07-30 | 2025-07-23 |  | Portables BTS | In-building system | IBC | Add R8862A S2100x1+R8894E M1821x2, Dismantle R8862A S1800(B6A)x2 | 0 | 0
3173A | Setia Indah Shoplots | Central |  | Modernization |  | 2023Q3 | MA | Magicell | 4.6 TSSR Approved |  | 2023-05-19 | 2023-05-22 |  | 2023-05-24 |  | Closed | 2023-05-25 | 2023-06-17 | E//Razif | 2023-06-15 | CelcomDigi_RAN_Magicell_TSS_Central_20230523_0009 | DU00002038452 |  |  | 2023-06-21 | 2023-06-13 |  |  | 3m RT (Wall Mounted Pole) | 6 | Add R9264M M1821 x4 + R8862A S2600 x1,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 |  | 3
4028B | Bayview Beach Resort | Northern |  | Modernization |  | 2023Q3 | SM | YPTT | 4.6 TSSR Approved |  | 2023-05-07 | 2023-05-24 |  | 2023-05-27 |  | Closed | 2023-06-02 | 2023-07-25 | E//Hazida | 2023-07-22 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0008 | DU00002038453 |  |  | 2023-08-20 | 2023-08-19 |  | Pole | 6m RT (Boom) | 6 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x2+R8882 S1800B(B6B) x4++R8881 S2100 x3+
4587A | Taman Emas Taiping | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-06-06 | 2023-06-27 |  | 2023-07-04 |  | Closed | 2023-07-05 | 2023-07-15 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002038454 |  |  | 2023-07-31 | 2023-07-22 |  | Portables BTS | 3m Boom (RT) | 5 M | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800 x1+R8862A S2100(A6A) x3
4999C | SPICE Convention Centre Penang IB | Northern |  | Remote MOCN |  | 2023Q3 | WP | GTSB | 4.6 TSSR Approved |  | 2023-05-11 | 2023-05-15 |  | 2023-05-18 |  | Under Approval | 2023-05-25 | 2023-05-30 | E//Hazida | 2023-05-30 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002038455 | [5 empty] | Wall mount boom | In-building system
1494H | 99 Speedmart JLN KAPAR BATU 13 | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038456 | [6 empty] | Small Cell
1665H | 99 Speedmart Bkt Sentosa 1 | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038457 | [6 empty] | Small Cell
1800B | Awana Resort & Hotel | Central |  | MOCN As-Is | On Hold->Decomm->Site Out->Site Out (Modernization)->Modernization->MOCN AS-IS | 2023Q4 | AI | GTSB | 14.0 TSSR Not Required (Reuse Existing BBU/RRU) | [6 empty] | To be Submitted |  |  |  |  | SQ202506170074 | DU00002038458 | [6 empty] | In-building system |  | Reuse Exiting RRU
1794A | Sek 7 | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-05-26 | 2023-06-06 |  | 2023-06-11 |  | Closed | 2023-06-12 | 2023-07-20 | E//Razif | 2023-07-20 | CelcomDigi_RAN_GTSB_TSS_Central_20230529_0025 | DU00002038459 |  |  | 2023-08-03 | 2023-08-01 |  |  | 6m RT (Minimast) | 15 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8860E-GU908 x2+R8882-GUL1812 x3+R8840-U216 x3++ | 13
3644C | Gemilang Setia Alam | Central |  | Modernization |  | 2023Q3 | HQ 6 | Magicell | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-11 |  | 2023-05-13 |  | Closed | 2023-05-16 | 2023-06-26 | E//Kok Keen | 2023-06-26 | CelcomDigi_RAN_Magicell_TSS_Central_20230508_0007 | DU00002038460 |  |  | 2023-06-17 | 2023-06-13 |  | Wall mount boom | 3m Boom (RT) | 7 | Add R9264H M901821 x4 + R9264M M1821 x1 + R8862A S2600 x1,Dismantle R8894E M1821(A8A) x4 |  | 1
4810B | Adventist Hospital IB | Northern |  | Modernization |  | 2023Q3 | WP | CCSMY | 4.6 TSSR Approved |  | 2023-05-17 | 2023-05-27 |  | 2023-06-01 |  | Closed | 2023-07-22 | 2023-07-24 | E//Nazrul | 2023-07-22 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002038461 |  |  | 2023-11-16 | 2023-10-26 |  | Portables BTS | In-building system | IBC SSITE | Add + R8862A S1800 x2 + R8862A S2100 x2,Dismantle R8882-GUL1812 x2
4679B | Sg Kedah | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-25 | 2023-05-31 |  | 2023-06-06 |  | Closed | 2023-06-21 | 2023-07-27 | E//Hazida | 2023-07-27 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002038462 |  |  | 2023-08-30 | 2023-08-30 |  | Tower | 60m 3 Legged Tower | 61 | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 | 123
4039A | Sg Jelutong | Northern |  | Modernization |  | 2023Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-04-28 | 2023-05-15 |  | 2023-05-20 |  | Closed | 2023-05-24 | 2023-06-02 | E//Hazida | 2023-06-02 | Celcom Digi_RAN-GTSB-TSS-Northern-20230502-0012 | DU00002038463 |  |  | 2023-08-27 | 2023-08-24 |  | Minimast | 3m Boom (RT) | 6 | Add R9264M M1821 x5,Dismantle R8882 S1800B(B6B) x3+R8862A S1800(B6A) x1+R8854D S2100(A4A) x4 |  | 13
4107C | Jln Bunga Kaca | Northern |  | Modernization |  | 2023Q3 | SM | GTSB | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦no space owner reject add new pole | 2023-05-01 | 2023-05-02 |  | 2023-05-06 |  | Closed | 2023-05-09 | 2023-07-03 | CD//Affendi | 2023-05-10 | Celcom Digi_RAN-GTSB-TSS-Northern-20230502-0012 | DU00002038464 | NIC_S1_Change MM to BI_owner reject_Digi OB |  | 2023-08-10 | 2023-08-09 |  | Wall mount boom | 30m Monopole |  | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 2
3593B12 | pBTS Kesas Kebun Interchange (C) | Central |  | Modernization |  | 2023Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-13 |  | 2023-05-18 |  | Closed | 2023-05-20 | 2023-06-28 | E//Razif | 2023-06-28 | CelcomDigi_RAN_Allstar_TSS_Central_20230511_0007 | DU00002038465 |  |  | 2023-06-17 | 2023-06-10 |  | Guide mast | 25m pBTS | 24 | Add R9264M M1821 x3,Dismantle R8882 S1800B(B6B) x2+R8862A S1800(B6A) x1+R8881 S2100 x3
1258H | 99 Speedmart TMN DESA PERMAI | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038466 | [6 empty] | Small Cell
4146A | Tmn Seri (DD) | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-23 | 2023-05-24 |  | 2023-05-26 |  | Closed | 2023-06-02 | 2023-06-12 | E//Hazida | 2023-06-12 | Celcom Digi_RAN-GCI-SS-Northern-20230524-0019 | DU00002038467 |  |  | 2023-08-30 | 2023-08-29 |  | Unipole | 3m Bipod (RT) | 9.5 | Add R9264H M901821 x3 + R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3 |  | 123
1937B | Kemuning Jln Tamborin (KJS) | Central |  | Modernization |  | 2023Q3 | YZ | AllStar | 4.6 TSSR Approved |  | 2023-05-11 | 2023-05-18 |  | 2023-05-21 |  | Closed | 2023-05-22 | 2023-06-17 | CD//Sapian | 2023-06-15 | CelcomDigi_RAN_Allstar_TSS_Central_20230511_0007 | DU00002038468 |  |  | 2023-06-10 | 2023-06-08 |  | Lampole | 30m Lampole | 30 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x2+R8840-U216 x3+
4258B | Hard Rock Hotel Pg IB | Northern |  | Modernization |  | 2023Q3 | WP | CCSMY | 4.6 TSSR Approved |  | 2023-05-17 | 2023-06-02 |  | 2023-06-13 |  | Closed | 2023-07-31 | 2023-07-31 | E//Nazrul | 2023-07-31 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002038469 |  |  | 2023-08-17 | 2023-08-16 |  | Portables BTS | In-building system | N/A | Add R8862A S1800 x2 + R8862A S2100 x2,Dismantle R8882 S1800(B) x2
2438A | Kerling Town (CELCOM) | Central |  | Modernization |  | 2023Q4 | HQ 6 | Ascentrack | 4.6 TSSR Approved |  | 2023-07-14 | 2023-07-27 |  | 2023-07-31 |  | Closed | 2023-08-02 | 2023-08-03 | E//Kok Keen | 2023-08-03 | Celcomdigi_RAN_Ascentrack_TSS_Central_20230707_0027 | DU00002038470 |  |  | 2023-10-12 | 2023-10-07 |  | Tower | Tower | 60 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1
1433B | UiTM Cempaka(Clm) | Central |  | Modernization |  | 2023Q4 | XH | GTSB | 4.6 TSSR Approved |  | 2023-05-27 | 2023-06-13 |  | 2023-06-17 |  | Closed | 2023-06-19 | 2023-07-26 | E//Razif | 2023-07-25 | CelcomDigi_RAN_GTSB_TSS_Central_20230529_0025 | DU00002038471 |  |  | 2023-11-16 | 2023-10-12 |  | Monople Tree | 45m Monopole | 45m | Add R9224E M1821 x3+R8854E S1800 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3
2723A | Anggerik Mokara | Central |  | Modernization |  | 2023Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-12 |  | 2023-05-15 |  | Closed | 2023-05-16 | 2023-06-17 | CD//Sapian | 2023-06-16 | CelcomDigi_RAN_AllStar_TSS_Central_20230508_0006 | DU00002038472 |  |  | 2023-06-24 | 2023-06-22 |  | Pole | 3m Bipod (RT) | 4 | Add A9732 M1821 x1 + R9264M M1821 x2 + R8862A S2601 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3 | 1(S1->S3,S2->S1，S3->S2,rename sector ID,FDD MM@ new S3)
1503C | Syabas Setia Alam | Central |  | Modernization |  | 2023Q3 | AI | Magicell | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-17 |  | 2023-05-19 |  | Closed | 2023-05-21 | 2023-06-19 | E//Razif | 2023-06-19 | CelcomDigi_RAN_Magicell_TSS_Central_20230511_0008 | DU00002038473 |  |  | 2023-06-23 | 2023-06-13 |  | Lampole | Land site | 30m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1969B | Sekinchan 2 | Central |  | Modernization |  | 2023Q4 | CR | YPTT | 4.6 TSSR Approved |  | 2023-10-05 | 2023-10-16 |  | 2023-10-20 |  | Closed | 2023-10-24 | 2023-10-27 | E//Razif | 2023-10-25 | CelcomDigi_RAN_YPTT_TSS_Central_20230725 | DU00002038474 |  |  | 2024-02-14 | 2024-02-06 |  | Tower | Tower | 45 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x3 | 12
4049Z | KGKLIANGNG | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038475 | [6 empty] | Land site
1350A | Sri Muda | Central |  | Modernization |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-06-15 | 2023-06-23 |  | 2023-07-04 |  | Closed | 2023-07-06 | 2023-07-20 | E//Razif | 2023-07-20 | CelcomDigi_RAN_YPTT_TSS_Central_20230620_0006 | DU00002038476 |  |  | 2023-08-02 | 2023-07-31 |  | In-Building System | 6m RT (Boom) | 6 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8882 S1800B(B6B) x2+R8862A S1800(B6A) x3+R8854D S2100(A4A) x3+R8854 S2600(A4A) x2 | 23
1705H | 99 Speedmart Pinggiran Batu Caves 1 | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038477 | [6 empty] | Small Cell
2480A | NS HW KM390.9 (MAXIS) | Central |  | Modernization |  | 2023Q4 | YZ | Magicell | 4.6 TSSR Approved |  | 2023-05-29 | 2023-05-30 |  | 2023-06-01 |  | Closed | 2023-06-06 | 2023-06-09 | E//Razif | 2023-06-09 | CelcomDigi_RAN_Magicell_TSS_Central_20230531_0010 | DU00002038478 |  |  | 2023-10-31 | 2023-10-02 |  | Tower | 60m 3 Legged Tower | 60 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x2+R8862A S2100(A6A) x3 |  | 23
2932A | Meru Utama | Central |  | Modernization |  | 2023Q3 | HQ 6 | Magicell | 4.6 TSSR Approved |  | 2023-05-22 | 2023-05-25 |  | 2023-05-27 |  | Closed | 2023-05-30 | 2023-07-26 | CD//Syafiq | 2023-07-25 | CelcomDigi_RAN_Magicell_TSS_Central_20230523_0009 | DU00002038479 |  |  | 2023-06-17 | 2023-06-13 |  | Monopole | 30m Monopole | 25M | Add R9264M M1821 x5 + R8862A S2600 x2,Dismantle R8882-GUL1812 x3+R8894E M1821(A8A) x3 |  | 13
4004A | Telok Bahang Flats | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-26 | 2023-05-23 |  | 2023-05-26 |  | Closed | 2023-06-02 | 2023-07-25 | E//Hazida | 2023-07-21 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038480 |  |  | 2023-08-08 | 2023-08-08 |  | Unipole | Tower | 3.1 | Add R9264M M1821 x5 + R8862A S2601 x2,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3 |  | 23
3313A1 | pBTS Bandar Bkt Raja | Central |  | Modernization |  | 2023Q3 | HQ 6 | Magicell | 4.6 TSSR Approved |  | 2023-04-28 | 2023-05-03 |  | 2023-05-06 |  | Closed | 2023-05-10 | 2023-06-19 | E//Razif | 2023-06-19 | CelcomDigi_RAN_Magicell_TSS_Central_20230502_0006 | DU00002038481 |  |  | 2023-06-16 | 2023-06-13 |  | Tower | 25m pBTS | 31 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
4261B | TUALANG | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-06-10 | 2023-06-15 |  | 2023-06-22 |  | Closed | 2023-07-05 | 2023-07-27 | E//Hazida | 2023-07-27 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002038482 |  |  | 2023-09-25 | 2023-09-08 |  | Tower | Tower | 65 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
2086A | Balai Polis Bkt Tinggi | Central |  | Modernization |  | 2023Q4 | HQ 6 | Magicell | 4.6 TSSR Approved |  | 2023-07-06 | 2023-07-10 |  | 2023-07-11 |  | Closed | 2023-07-12 | 2023-07-14 | E//Kok Keen | 2023-07-14 | CelcomDigi_RAN_Magicell_TSS_Central_20230707_0020 | DU00002038483 |  |  | 2023-08-12 | 2023-08-11 |  | In-Building System | 3m Bipod (RT) | 3 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8882 S1800(B) x3+R8862A S2100(A6A) x3 | 13
1165A | Pt.13 Bagan Terap | Central |  | Decomm | Modernization->Decomm | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-08-01 | 2023-05-30 |  | 2023-06-01 | 2023-09-07 | Closed | 2023-06-20 | 2024-06-25 | E//Razif | 2023-07-24 | 0626Central-Magicell-BOQ Template (template) | DU00002038484 |  |  |  |  | 2023-12-05 | Tower | 60m 4 Legged Tower | 45M
4458A | LAP Lake Viep RDD | Northern |  | Modernization |  | 2023Q4 | MH | GTSB | 4.6 TSSR Approved |  | 2023-05-29 | 2023-06-06 |  | 2023-06-09 |  | Closed | 2023-06-12 | 2023-07-15 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002038485 |  |  | 2023-08-03 | 2023-07-22 |  | Monopole | 45m Monopole | 30 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 12
2258A | Batu Cave 26 | Central |  | Modernization |  | 2023Q4 | HQ 6 | GTSB | 4.6 TSSR Approved |  | 2023-05-23 | 2023-05-31 |  | 2023-06-09 |  | Closed | 2023-06-14 | 2023-07-15 | E//Kok Keen | 2023-07-14 | CelcomDigi_RAN_GTSB_TSS_Central_20230529_0025 | DU00002038486 |  |  | 2023-07-16 | 2023-07-14 |  |  | 20m monopole | 20 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8854E S1800(A6A) x3+R8854D S2100(A4A) x3 | 13
3211A | Jalan Langsat | Central |  | Modernization |  | 2023Q4 | HQ 6 | AllStar | 4.6 TSSR Approved |  | 2023-06-21 | 2023-06-26 |  | 2023-06-28 |  | Closed | 2023-07-03 | 2023-07-07 | E//Kok Keen | 2023-07-07 | CelcomDigi_RANMW_AllStar_TSS_Central_20230622_0005 | DU00002038487 |  |  | 2023-07-17 | 2023-07-17 |  | Monopole | 24m Lampole | 20 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882 S1800(B) x3
1464H | 99 Speedmart SHAH ALAM SEK 19 | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038488 | [6 empty] | Small Cell
3494A4 | pBTS Masjid Keningau (REL) | Sabah |  | Modernization |  | 2023Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2023-05-07 | 2023-05-06 |  | 2023-05-10 |  | Closed | 2023-05-13 | 2023-05-25 | CD//Ray Amos | 2023-05-16 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230508-0005 | DU00002038489 |  |  | 2023-07-25 | 2023-07-14 |  | Guide mast | 25m pBTS | 25 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x5 | 123
1598H | 99 Speedmart Tmn Tasik Biru | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038490 | [6 empty] | Small Cell
3827B | Theme Park Hotel Genting Highland | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-07-24 | 2023-07-25 |  | 2023-07-31 |  | Closed | 2023-09-04 | 2023-09-04 | E//Nazrul | 2025-04-25 | CelcomDigi_RAN_GTSB_TSS_Central_20230725 | DU00002038491 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed | 2025-12-01 | 2025-11-25 |  | Portables BTS | In-building system | IBC SURVEY | Add R8862A S1800x1+R8862A S2100x3+R8854 S2600x1
4073A | Koay Eng Chong | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-01 | 2023-05-13 |  | 2023-05-18 |  | Closed | 2023-05-22 | 2023-06-22 | E//Hazida | 2023-06-22 | Celcom Digi_RAN-GTSB-TSS-Northern-20230502-0012 | DU00002038492 |  |  | 2023-07-15 | 2023-07-14 |  | Monopole | 60m 4 Legged Tower | 3M | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 12
1445B | Ladang Bukit Cherakah | Central |  | Modernization |  | 2023Q3 | MA | GTSB | 4.6 TSSR Approved |  | 2023-04-27 | 2023-05-08 |  | 2023-05-11 |  | Closed | 2023-05-11 | 2023-06-26 | CD//Ali akaram | 2023-06-26 | CelcomDigi_RAN_GTSB_TSS_Central_20230428_0022 | DU00002038493 |  |  | 2023-09-04 | 2023-08-30 |  | Tower | Tower | 60 | Add R9264H M901821 x2 + R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3 |  | 13
3775A | Lorong Pending 2B | Central |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-25 |  | 2023-05-27 |  | Closed | 2023-05-29 | 2023-06-19 | CD//Sapian | 2023-06-19 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002038494 |  |  | 2023-07-03 | 2023-06-28 |  | Lampole | 20m Lampole | 20m | Add R9264M M1821 x3,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3
1982B | Kg Sg Serdang | Central |  | Modernization |  | 2023Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-10 |  | 2023-05-12 |  | Closed | 2023-05-15 | 2023-06-17 | CD//Ali akaram | 2023-06-15 | CelcomDigi_RAN_GTSB_TSS_Cental_20230511_0024 | DU00002038495 |  |  | 2023-06-14 | 2023-06-13 |  | Monopole | 45m Monopole | 45m | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2600 x1,Dismantle R8882 S1800(B) x3+R8862A S2100(A6A) x3 |  | 2
4419C | Wisma Rahmat | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-04-28 | 2023-05-31 |  | 2023-06-02 |  | Closed | 2023-06-05 | 2023-07-22 | E//Hazida | 2023-07-22 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230502-0012 | DU00002038496 |  |  | 2023-08-27 | 2023-08-24 |  | Wall mount boom | 3m Bipod (RT) | WALL MOUNTED BOOM 2m | Add R9264M M1821 x4,Dismantle R8862A S1800(B6A) x4+R8862A S2100(A6A) x4
1006R | BB1_B060B_B00680OD_JLNRAJAMUSA | Central |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2023Q4 |  | CCSMY | 15.3 Decomm Done without TSSR | [6 empty] | To be Submitted |  |  |  |  | SQ202506110090 | DU00002038497 |  |  |  |  | 2025-08-05 |  | Land site
4184D | Taman Datuk Kumbar | Northern |  | Modernization |  | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-09-04 | 2023-09-06 |  | 2023-09-13 |  | Closed | 2023-09-16 | 2023-10-02 | E//Hazida | 2023-09-29 | Celcom Digi_RAN-YPTT- TSS-Northern-20230626-0022 | DU00002038498 |  |  | 2023-10-01 | 2023-10-01 |  | Lampole | 30m Lampole | 30m | Add R9224E M1821 x3+R8854E S1800 x3,Dismantle R8894E M1821(A8A) x3
4801A | Komtar | Northern |  | Modernization |  | 2023Q3 | WP | YPTT | 4.6 TSSR Approved |  | 2023-05-10 | 2023-06-02 |  | 2023-06-27 |  | Closed | 2023-07-31 | 2023-08-02 | E//Nazrul | 2023-07-31 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0008 | DU00002038499 |  |  | 2024-01-06 | 2023-11-15 |  | Portables BTS | In-building system | In Building + Rooftop | Add R8862A S1800 x2 + R8862A S2100 x2 + R8862A S2601 x2,Dismantle R8882-GUL1812 x2
3820A | Jalan Bahtera 1B | Central |  | Modernization |  | 2023Q4 | HQ 1 | Ascentrack | 4.6 TSSR Approved |  | 2023-07-05 | 2023-07-11 |  | 2023-07-13 |  | Closed | 2023-07-19 | 2023-12-04 | E//Kok Keen | 2023-12-04 | CelcomDigi_RANMW_Ascentrack_TSS_Central_20230626_0008 | DU00002038500 |  |  | 2023-12-09 | 2023-12-02 |  | Minimast | 3m Bipod (RT) | 9 | Add A9732 M1821 x1 + R9264M M1821 x2,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 1
2474A | Jln Bkt Kapar | Central |  | Modernization |  | 2023Q3 | HQ 6 | Magicell | 4.6 TSSR Approved |  | 2023-05-12 | 2023-05-19 |  | 2023-05-23 |  | Closed | 2023-05-25 | 2023-07-17 | E//Razif | 2023-07-11 | CelcoDigi_RAN_Magicell_TSS_Central_20230517_0009 | DU00002038501 |  |  | 2023-07-05 | 2023-07-05 |  | Tower | 50m Tower | 46M | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8894E M1821(A8A) x3 |  | 2
1157A | Sg. Nibong | Central |  | Modernization |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-06-13 | 2023-06-21 |  | 2023-06-23 |  | Closed | 2023-06-26 | 2023-07-25 | E//Razif | 2023-07-25 | CelcomDigi_RAN_Magicell_TSS_Central_20230616_0013 | DU00002038502 |  |  | 2023-07-17 | 2023-07-13 |  | Tower | 45m 3 Legged Tower | 45m | Add R9264H M901821 x4,Dismantle R8894E M1821(A8A) x4
4803A | Sunshine Square | Northern |  | Modernization |  | 2023Q3 | WP | YPTT | 4.6 TSSR Approved |  | 2023-05-12 | 2023-05-16 |  | 2023-05-30 |  | Closed | 2023-07-11 | 2023-08-02 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0008 | DU00002038503 |  |  | 2023-11-30 | 2023-07-18 |  | Wall mount boom | In-building system |  | Add R8862A S1800 x1 + R8862A S2100 x1 + R8862A S2601 x1,Dismantle R8882-GUL1812 x1
4056A | Vistana Hotel | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-29 | 2023-06-01 |  | 2023-06-09 |  | Closed | 2023-06-13 | 2023-06-21 | E//Hazida | 2023-06-20 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002038504 |  |  | 2023-07-13 | 2023-07-12 |  | H-bracket pole | 6m RT (Wall Mounted Pole) | 2 | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x5 | 123
4477A | Bagan Nakhoda Omar | Central |  | Modernization |  | 2023Q4 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-07-09 |  |  | 2023-09-02 |  | Closed | 2023-09-05 | 2023-09-06 | E//Razif | 2023-09-05 | CelcomDigi_RAN_CCSMY_TSS_Central_20230710 | DU00002038505 |  |  | 2023-09-17 | 2023-09-12 |  | Tower | 150ft 4 legged Tower | 46m | Add R9264M M1821 x2+R9264H M901821 x3+R8862A S2601 x2,Dismantle R8860E-GU908 x3+R8882-GUL1812 x3+R8854D S2100(A4A) x3 |  | 13
1347A | Sect 9 | Central |  | Modernization |  | 2023Q4 | HQ 1 | Datasco | 4.6 TSSR Approved |  | 2023-05-26 | 2023-06-17 |  | 2023-06-20 |  | Closed | 2023-06-21 | 2023-07-25 | E//Razif | 2023-07-25 | CelcomDigi_RAN_Datasco_TSS_Central_20230529_0023 | DU00002038506 |  |  | 2023-08-04 | 2023-08-02 |  | Wall mount boom | 6m RT (Boom) | 6m | Add R9264H M901821 x3 + R9264M M1821 x3 + R8862A S2601 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 |  | 123
3002A9 | pBTS Pahang Pharmacy | Central |  | Modernization |  | 2023Q3 | IE | Magicell | 4.6 TSSR Approved |  | 2023-05-11 | 2023-05-13 |  | 2023-05-16 |  | Closed | 2023-05-30 | 2023-06-20 | CD//Tee | 2023-06-20 | CelcoDigi_RAN_Magicell_TSS_Central_20230517_0009 | DU00002038507 |  |  | 2023-07-07 | 2023-06-27 |  | Minimast | 25m pBTS | 25 | Add R9264H M901821 x3 + R9264M M1821 x3 + R8862A S2601 x1,Dismantle R9224E M1821(AAB) x5 |  | 123
1006C | Taman Bidara Selayang | Central |  | Modernization |  | 2023Q4 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-07-01 | 2023-07-11 |  | 2023-07-13 |  | Closed | 2023-07-14 | 2023-07-17 | E//Kok Keen | 2023-07-17 | CelcomDigi_RAN_YPTT_TSS_Central_20230703_0012 | DU00002038508 |  |  | 2023-08-02 | 2023-08-01 |  | Lampole | 24m Lampole | 27 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
4318B | Desa Ria (REL) | Northern |  | Modernization |  | 2023Q3 | MH | GTSB | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-20 |  | 2023-05-27 |  | Closed | 2023-05-31 | 2023-07-05 | CD//Quah | 2023-07-05 | Celcom Digi_RAN-GTSB-TSS-Northern-20230509-0017 | DU00002038509 |  |  | 2023-07-13 | 2023-07-13 |  | Minimast | 3m Boom (RT) | 6 | Add R9264M M1821 x5 + R8862A S2601 x2,Dismantle R9224E M1821(AAB) x3 |  | 12
4456A | Aulong | Northern |  | Modernization |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-28 | 2023-06-20 |  | 2023-06-22 |  | Closed | 2023-06-26 | 2023-07-15 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230529-0020 | DU00002038510 |  |  | 2023-07-29 | 2023-07-22 |  | Portables BTS | 2m RT (Boom) | 6M | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8840-U216 x3++ |  | 1
1890B | Felda Gedangsa | Central |  | Modernization |  | 2023Q4 | HQ 6 | Magicell | 4.6 TSSR Approved |  | 2023-05-26 | 2023-05-30 |  | 2023-06-02 |  | Closed | 2023-06-17 | 2023-06-26 | E//Kok Keen | 2023-06-26 | CelcomDigi_RANMW_Magicell_TSS_Central_20230529_0003 | DU00002038511 |  |  | 2023-07-12 | 2023-07-04 |  | Tower | Tower | 77 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3 | 1
1449B | Jeram2 | Central |  | Modernization |  | 2023Q3 | YZ | GTSB | 4.6 TSSR Approved |  | 2023-04-28 | 2023-05-03 |  | 2023-05-04 |  | Closed | 2023-05-09 | 2023-06-19 | CD//Ali akaram | 2023-06-19 | CelcomDigi_RAN_GTSB_TSS_20230505_0023 | DU00002038512 |  |  | 2023-07-03 | 2023-06-27 |  | Tower | 60m 4 Legged Tower | 60m | Add A9732 M1821 x2 + R9264M M1821 x2,Dismantle R8862A S1800(B6A) x4+R8854D S2100(A4A) x4 | 13
3443B10 | pBTS PPR Balung | Sabah |  | Modernization |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved | Single Phase Power Site. Site require upgrade to 3phase incoming | 2023-06-07 | 2023-06-26 |  | 2023-07-01 |  | Closed | 2023-07-03 | 2023-07-31 | E//Thien | 2023-07-31 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007 | DU00002038513 |  |  | 2023-08-12 | 2023-08-09 |  | Monopole | 25m pBTS | 25 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
4972B | Kg Masjid Lama | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GCI | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦Maxis not allowed add AAU | 2023-06-20 | 2023-06-21 |  | 2023-06-23 |  | Closed | 2023-06-28 | 2023-09-07 | E//Hazida | 2023-09-07 | Celcom Digi_RAN-GCI-TSS-Northern-20230621-0032 | DU00002038514 | NIC_S3_Change MM to BI_owner reject_MAXIS |  | 2023-08-28 | 2023-08-26 |  | Tower | 60m 3 Legged Tower | 60 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R9224E M1821(AAB) x3 | 123
4719B | Sg Bayor | Northern |  | Modernization |  | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-05-27 | 2023-06-06 |  | 2023-06-12 |  | Closed | 2023-06-15 | 2023-07-15 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-YPTT-TSS-Northern-20230530-0014 | DU00002038515 |  |  | 2023-08-01 | 2023-07-26 |  | Tower | 60m 4 Legged Tower | 45 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x2 + R8862A S2601 x1,Dismantle R8860E-GU908 x1+R8894E M1821(A8A) x3 | 14
4587D | General Hospital (REL) | Northern |  | Modernization |  | 2023Q3 | MH | GTSB | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-17 |  | 2023-05-22 |  | Closed | 2023-05-25 | 2023-07-25 | E//Hazida | 2023-07-22 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002038516 |  |  | 2023-08-01 | 2023-08-01 |  | Monople Tree | Land site | 35 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123(S1->S2,S2->S3，S3->S1,rename sector ID)
4692M | Pulau Tikus Digi Store | Northern |  | Decomm | MOCN As-Is->Site out->Decomm | 2023Q3 |  | GTSB | 14.1 TSSR Not Required (Decomm by CD) | [6 empty] | To be Submitted |  |  |  |  | 0925CD-Northern-GTSB-BOQ Template(new contract) | DU00002038517 |  |  |  |  | 2024-12-05 |  | Micro Cell
1799B | Behrang Ulu | Central |  | Modernization |  | 2023Q4 | HQ 1 | Ascentrack | 4.6 TSSR Approved |  | 2023-05-25 | 2023-06-01 |  | 2023-06-07 |  | Closed | 2023-06-10 | 2023-06-21 | E//Kok Keen | 2023-06-21 | CelcomDigi_RANMW_ASCENTRACK_TSS_Central_20230529_0003 | DU00002038518 |  |  | 2023-08-03 | 2023-08-03 |  | Tower | 60m 3 Legged Tower | 60 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x3 | 13
4550C | Penang Aiport | Northern |  | Modernization |  | 2023Q3 | WP | GTSB | 4.6 TSSR Approved |  | 2023-06-27 | 2023-07-04 |  | 2023-07-07 |  | Closed | 2023-07-07 | 2023-08-07 | E//Nazrul | 2023-07-07 | Celcom Digi_RAN-GTSB-TSS-Northern-20230509-0017 | DU00002038519 |  |  | 2023-09-15 | 2023-07-18 |  | Wall mount boom | In-building system |  | Add R8862A S1800 x3
3153B9 | pBTS Kampung Padang Kunyit | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-30 | 2023-06-06 |  | 2023-06-22 |  | Closed | 2023-07-04 | 2023-08-07 | E//Hazida | 2023-07-27 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002038520 |  |  | 2023-08-29 | 2023-08-27 |  | Guide mast | 25m pBTS | 30m | Add R9264H M901821 x3,Dismantle R8854E S1800(A6A) x3+R8862A S2100(A6A) x3
4762B | Tongkang Yard | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-29 | 2023-06-01 |  | 2023-06-07 |  | Closed | 2023-06-13 | 2023-07-28 | E//Hazida | 2023-07-28 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002038521 |  |  | 2023-08-28 | 2023-08-26 |  | Monople Tree | 45m Monopole Tree | 31 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
3093C | Bomba House RT | Central |  | Modernization |  | 2026 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-06-01 | 2023-07-07 |  | 2023-07-18 |  | Closed | 2023-07-18 | 2023-07-21 | E//Kok Keen | 2023-07-20 | CelcomDigi_RAN_GTSB_TSS_Central_20230606_0027 | DU00002038522 |  |  | 2026-05-08 | 2026-02-25 |  | In-Building System | 3m Boom (RT) | N/A | Add R8894E M1821x3,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 | 0 | 0
4663A | Derga Jaya | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-29 | 2023-05-26 |  | 2023-05-29 |  | Closed | 2023-06-01 | 2023-06-11 | E//Hazida | 2023-06-11 | Celcom Digi_RAN-GCI-TSS-Northern-20230529-0022 | DU00002038523 |  |  | 2023-09-02 | 2023-08-29 |  | Tower | 30m 3-legged tower | 60 | Add R9264H M901821 x3 + R9264M M1821 x2,Dismantle R8894E M1821(A8A) x3 |  | 23
4092B | Taman Chee Hang | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-20 |  | 2023-05-24 |  | Closed | 2023-05-29 | 2023-07-14 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038524 |  |  | 2023-07-23 | 2023-07-06 |  | Pole | 45m 4 Legged Tower | 2 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x1+R8882 S1800B(B6B) x2+R8862A S2100(A6A) x3
1804B | RSC 8 HOSTEL IB | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-09-26 | 2023-09-29 |  | 2023-10-05 |  | Closed | 2023-10-09 | 2023-10-17 | E//Nazrul | 2023-10-09 | CelcomDigi_RAN_GTSB_TSS_Central_20230927 | DU00002038525 |  |  | 2025-07-28 | 2025-07-23 |  | In-Building System | In-building system |  | Add R8862A S2100 x3
4564C | SPICE Penang IB | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2023Q3 | WP | CCSMY | 4.6 TSSR Approved |  | 2023-05-12 | 2023-05-18 |  | 2023-05-22 |  | Under Approval | 2023-05-25 | 2023-05-30 | E//Hazida | 2023-05-30 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002038526 | [5 empty] | Pole | In-building system
1120A | Kota Kemuning | Central |  | Modernization |  | 2023Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-05-07 | 2023-05-10 |  | 2023-05-12 |  | Closed | 2023-05-13 | 2023-06-19 | CD//Sapian | 2023-06-19 | CelcomDigi_RAN_AllStar_TSS_Central_20230508_0006 | DU00002038527 |  |  | 2023-06-19 | 2023-06-16 |  |  | 3m RT (Minimast) | 5 | Add A9732 M1821 x1+R9264M M1821 x2+R9264H M901821 x1,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8854D S2100(A4A) x4 | 2
3414C | Subang Utama IND | Central |  | Modernization |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-06-22 | 2023-07-03 |  | 2023-07-05 |  | Closed | 2023-07-10 | 2023-07-20 | E//Razif | 2023-07-20 | CelcomDigi_RAN_YPTT_TSS_Central_20230623_0008 | DU00002038528 |  |  | 2023-08-03 | 2023-08-01 |  | Lampole | 30m Lampole | 30m | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x3+R9224E M1821(AAB) x2 | 123
4007B | Bukit Dumbar(Celcom) | Northern |  | Modernization |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-05-11 | 2023-05-13 |  | 2023-05-16 |  | Closed | 2023-05-18 | 2023-06-23 | E//Hazida | 2023-06-21 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038529 |  |  | 2023-07-25 | 2023-06-28 |  | Tower | 45m 3 Legged Tower | 60 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 13
1387H | 99 Speedmart SENTOSA 2 | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038530 | [6 empty] | Small Cell
2687A3 | pBTS Batu Maung (R ) | Northern |  | Modernization |  | 2023Q3 | MH | GTSB | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦pBTS site,can not install AAU on site，Loading issuu to add AAU. advise by solution to swap sector 2 & 3 to 12 port hybrid & use combiner | 2023-05-14 | 2023-05-16 |  | 2023-05-18 |  | Closed | 2023-05-23 | 2023-06-17 | E//Hannah | 2023-06-15 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002038531 | NIC_S2_Change MM to BI_loading issue_Digi OB |  | 2023-06-25 | 2023-06-24 |  | Guide mast | 25m pBTS | 30 | Add R9264M M1821 x2+R9264H M901821 x3+R8862A S2601 x2,Dismantle R8894E M1821(A8A) x4 |  | 23
4701C | DNP Land | Northern |  | Modernization |  | 2023Q3 | MH | GCI | 4.6 TSSR Approved |  | 2023-05-04 | 2023-05-06 |  | 2023-05-10 |  | Closed | 2023-05-11 | 2023-05-16 | CD//Affendi | 2023-05-16 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038532 |  |  | 2023-08-18 | 2023-08-18 |  | Pole | 3m Boom (RT) | N/A | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x3 | 12
1134C | Saujana Putra 2 | Central |  | Modernization |  | 2023Q3 | AI | Solusi | 4.6 TSSR Approved |  | 2023-05-15 | 2023-05-24 |  | 2023-06-02 |  | Closed | 2023-06-02 | 2023-07-13 | E//Razif | 2023-07-13 | CelcomDigi_RAN_Solusi_TSS_Central_20230511_0001 | DU00002038533 |  |  | 2023-08-21 | 2023-08-17 |  | Unipole | Lampole | 6m | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle R9224E M1821(AAB) x3 |  | 3
1546B | Tmn Bkt Permata | Central |  | Modernization |  | 2023Q4 | HQ 6 | AllStar | 4.6 TSSR Approved |  | 2023-06-21 | 2023-06-22 |  | 2023-06-24 |  | Closed | 2023-06-26 | 2023-07-07 | E//Kok Keen | 2023-07-06 | CelcomDigi_RAN_Allstar_TSS_Central_20230622_0014 | DU00002038534 |  |  | 2023-07-15 | 2023-07-15 |  | Monopole | 24m Lampole | 20 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882 S1800(B) x3++R8881 S2100 x3+
3242D | Masjid Jamek Sultan Hisyamuddin | Central |  | Modernization |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-07-08 | 2023-07-14 |  | 2023-07-20 |  | Closed | 2023-07-24 | 2023-07-26 | E//Razif | 2023-07-26 | CelcomDigi_RAN_CCSMY_TSS_Central_20230711 | DU00002038535 |  |  | 2023-08-14 | 2023-08-10 |  | Lampole | 24m Lampole | 28 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
1011A | Selayang Mall | Central |  | Modernization |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-06-22 | 2023-08-07 |  | 2023-08-11 |  | Closed | 2023-08-16 | 2023-10-31 | E//Kok Keen | 2023-10-30 | CelcomDigi_RAN_YPTT_TSS_Central_20230623_0008 | DU00002038536 |  |  | 2024-03-23 | 2023-12-01 |  | In-Building System | 3m RT (Wall Mounted Pole) | 5.8m | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
1445H | 99 Speedmart Bukit Kapar | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038537 | [6 empty] | Small Cell
1196B | Bukit Belimbing | Central |  | Modernization |  | 2023Q4 | XH | AllStar | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-14 |  | 2023-06-17 |  | Closed | 2023-06-19 | 2023-07-27 | E//Razif | 2023-07-27 | CelcomDigi_RANMW_AllStar_TSS_Central_20230612_0003 | DU00002038538 |  |  | 2023-07-16 | 2023-07-16 |  | Tower | 60m 4 Legged Tower | 60 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1 |  | 1
3659B | Jalan Hulubalang | Central |  | Modernization |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-06 | 2023-05-10 |  | 2023-05-12 |  | Closed | 2023-05-13 | 2023-07-03 | CD//Sapian | 2023-07-03 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002038539 |  |  | 2023-06-24 | 2023-06-22 |  | Unipole | 3m Bipod (RT) | 6M | Add R9264M M1821 x6 + R8862A S2601 x3,Dismantle R8894E M1821(A8A) x3 |  | 123
4000B | Mount Erskine (PDC) | Northern |  | Modernization |  | 2023Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-05-07 | 2023-05-08 |  | 2023-05-09 |  | Closed | 2023-05-16 | 2024-02-16 | E//Hazida | 2023-09-22 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002038540 |  |  | 2023-08-19 | 2023-08-16 |  | Tower | Tower | 30 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8882 S1800B(B6B) x2+R8862A S1800(B6A) x1+R8854D S2100(A4A) x3 | 13
1781B | Tmn Bahtera | Central |  | Modernization |  | 2023Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2023-06-16 | 2023-06-19 |  | 2023-06-21 |  | Closed | 2023-06-23 | 2023-07-10 | E//Kok Keen | 2023-07-04 | CelcomDigi_RAN_Allstar_TSS_Central_20230620_0013 | DU00002038541 |  |  | 2023-07-22 | 2023-07-22 |  | In-Building System | 3m Bipod (RT) | 7 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 | 23
1448H | 99 Speedmart Jln Besar Pekan Kapar | Central |  | MOCN As-Is | MOCN As-Is->Decomm->MOCN As-Is | 2023Q3 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | 0925CD-Central-GCI-BOQ Template(new contract) | DU00002038542 | [6 empty] | Small Cell
2048A | Hentian Sebelah Lentang | Central |  | Modernization |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-06-22 | 2023-07-11 |  | 2023-07-14 |  | Closed | 2023-07-17 | 2023-07-18 | E//Kok Keen | 2023-07-18 | CelcomDigi_RAN_Magicell_TSS_Central_20230623_0016 | DU00002038543 |  |  | 2023-10-02 | 2023-09-29 |  | Tower | 45m Tower | 45 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x2+R8854D S2100(A4A) x2
2799A | Kemuning Utama Apartment | Central |  | Modernization |  | 2023Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-13 |  | 2023-05-17 |  | Closed | 2023-05-18 | 2023-06-19 | CD//Sapian | 2023-06-18 | CelcomDigi_RAN_Allstar_TSS_Central_20230511_0007 | DU00002038544 |  |  | 2023-06-22 | 2023-06-22 |  | A-bracket pole | 3m Bipod (RT) | 26 | Add R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3
2627B | TM Spg Renggam | Central |  | Modernization |  | 2023Q4 | SS | GTSB | 4.6 TSSR Approved |  | 2023-10-05 | 2023-10-10 |  | 2023-10-14 |  | Closed | 2023-10-16 | 2023-10-18 | E//Razif | 2023-10-17 | CelcomDigi_RAN_GTSB_TSS_Central_20231006 | DU00002038545 |  |  | 2024-01-19 | 2024-01-15 |  | H-bracket pole | 3m Boom (RT) | 7M | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3
4428B | Air Putih RCC | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-31 | 2023-06-09 |  | 2023-06-14 |  | Rectificating | 2023-07-18 | 2023-07-26 | E//Hazida | 2023-07-26 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002038546 |  |  | 2023-08-04 | 2023-08-02 |  | Tower | 45m 3 Legged Tower | 60m | Add R8894E M1821 x3 + R8862A S2601 x3,Dismantle R8882-GUL1812 x2+R8882 S1800(B) x1
1005R | LADANG SUNGAI BELATA (REPLACEMENT FOR LATAM1) | Central |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 | IE | CCSMY | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038547 | [6 empty] | Land site
2666A14 | pBTS Sin Hai Hong Miri | Sarawak |  | Modernization |  | 2023Q4 | SH | South Pacific | 4.6 TSSR Approved |  | 2023-07-12 | 2023-07-17 |  | 2023-07-20 |  | Closed | 2023-07-21 | 2023-09-08 | E//SoonHo | 2023-09-08 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230606-0003 | DU00002038548 |  |  | 2023-10-02 | 2023-09-21 |  |  | 25m pBTS | 30 | Add R8852E S9000 x2 + R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3++
4087Z | T3E_0627_KgTuaHuluKerian | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038549 | [6 empty] | 76m 4 Legged Tower
4443C | Taman Desa Mutiara | Northern |  | Modernization |  | 2023Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-04-28 | 2023-05-04 |  | 2023-05-04 |  | Closed | 2023-05-10 | 2023-06-22 | E//Hazida | 2023-06-22 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230426-0005 | DU00002038550 |  |  | 2023-07-15 | 2023-07-13 |  | H-bracket pole | 30m Monopole | 4.6 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x5,Dismantle R8894E M1821(A8A) x3 |  | 23
4584A | Batu Kurau | Northern |  | Modernization |  | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI,L2600 change to 40M¦Maxis reject add AAU,Bi sector only can install 1 sector | 2023-06-04 | 2023-06-12 |  | 2023-06-15 |  | Closed | 2023-06-20 | 2023-07-18 | E//Daniel | 2023-07-18 | Celcom Digi_RAN-YPTT-TSS-Northern-20230606-0017 | DU00002038551 | NIC_S3_Change MM to BI,L2600 change to 40M_owner reject_MAXIS |  | 2023-08-02 | 2023-07-27 |  | Tower | 76m 3 Legged Tower | 75M | Add R9264M M1821 x4+R8862A S2601 x4,Dismantle R8894E M1821(A8A) x3 |  | 2
4953A | Mutiara Mergong | Northern |  | Modernization |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-06-12 | 2023-06-12 |  | 2023-06-17 |  | Closed | 2023-07-04 | 2023-07-28 | E//Hazida | 2023-07-28 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230613-0025 | DU00002038552 |  |  | 2023-08-28 | 2023-08-27 |  | In-Building System | 6m RT (Boom) | 4M | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8840-U216 x3++ |  | 1
4152B | Dewan Perniagaan Melayu PP | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-07 | 2023-05-18 |  | 2023-05-23 |  | Closed | 2023-06-01 | 2023-07-25 | E//Daniel | 2023-07-25 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002038553 |  |  | 2023-08-28 | 2023-08-24 |  | Pole | 3m Bipod (RT) | N/A | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 23
2659C | Sumurwang Tower IB | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-12-19 | 2023-12-26 |  | 2024-01-07 |  | Closed | 2026-04-17 | 2025-05-27 |  | 2024-06-05 | CelcomDigi_RAN_GTSB_TSS_Central_20231224 | DU00002038554 |  |  | 2023-08-30 | 2023-08-30 |  |  | Land site | NA | Reuse existing RRU
4030A | TAR(AsiaSpace) | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-04 | 2023-05-06 |  | 2023-05-09 |  | Closed | 2023-05-10 | 2023-05-25 | CD//Affendi | 2023-05-11 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038555 |  |  | 2023-08-22 | 2023-08-18 |  | Tower | 45m 3 Legged Tower | 40m | Add A9732 M1821 x3,Dismantle R8882 S1800B(B6B) x3+R8862A S1800(B6A) x2+R8854D S2100(A4A) x5+R8882 S2600(B4A) x2 | 123
4088A | MBF | Northern |  | Modernization |  | 2023Q3 | SM | YPTT | 4.6 TSSR Approved |  | 2023-05-06 | 2023-05-15 |  | 2023-05-17 |  | Closed | 2023-05-24 | 2023-08-03 | E//Hazida | 2023-08-03 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0008 | DU00002038556 |  |  | 2023-09-11 | 2023-09-11 |  | H-bracket pole | 2m RT (Boom) | S1,S2=3M,S3=2M | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
1754C | Alam Suria | Central |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-05-22 | 2023-05-22 |  | 2023-05-24 |  | Closed | 2023-05-25 | 2023-07-12 | E//Razif | 2023-07-11 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002038557 |  |  | 2023-12-18 | 2023-07-02 |  | Lampole | Land site | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
4057A | Goldhill Complex | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-15 | 2023-05-31 |  | 2023-06-02 |  | Closed | 2023-06-07 | 2023-07-25 | E//Hazida | 2023-07-21 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230509-0018 | DU00002038558 |  |  | 2023-08-20 | 2023-08-19 |  | Pole | 4m RT (Boom) | 4 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8882-GUL1812 x3+R8854 S2600(A4A) x1+R8894E M1821(A8A) x4 | 12
3434A | TMN_SLYG_SEGAR1 | Central |  | Modernization |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-06-21 | 2023-07-03 |  | 2023-07-05 |  | Closed | 2023-07-07 | 2023-07-13 | E//Kok Keen | 2023-07-13 | CelcomDigi_RANMW_YPTT_TSS_Central_20230623_0005 | DU00002038559 |  |  | 2023-12-14 | 2023-12-11 |  | In-Building System | 30m Monopole | 11 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3
4424A | Ulu Sepetang | Northern |  | Modernization |  | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-05-26 | 2023-05-29 |  | 2023-06-06 |  | Closed | 2023-06-13 | 2023-07-18 | E//Daniel | 2023-07-18 | Celcom Digi_RAN-YPTT-TSS-Northern-20230530-0014 | DU00002038560 |  |  | 2023-09-07 | 2023-07-31 |  | Tower | 60m 4 Legged Tower | 60M | Add R9264H M901821 x1+R8862A S2601 x1+A9732 M1821 x2,Dismantle R8882 S1800B(B6B) x2+R8862A S2100(A6A) x2 | 12 | 0
4185B | North Avenue | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-17 | 2023-06-13 |  | 2023-06-16 |  | Closed | 2023-06-20 | 2023-07-22 | E//Hazida | 2023-07-22 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002038561 |  |  | 2023-09-06 | 2023-09-04 |  | Minimast | 3m Boom (RT) | 3.5m | Add R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
1462H | 99 Speedmart KEMUNING TAIPAN | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038562 | [6 empty] | Small Cell
2968A | Karak HW Tunnel West Entrance | Central |  | Modernization |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-06-24 | 2023-07-06 |  | 2023-07-10 |  | Closed | 2023-07-10 | 2023-07-13 | E//Kok Keen | 2023-07-13 | CelcomDigi_RAN_Magicell_TSS_Central_20230626_0017 | DU00002038563 |  |  | 2023-07-25 | 2023-07-22 |  | BillBoard | Billboard | 16 | Add R9264M M1821 x2,Dismantle R8894E M1821(A8A) x2
3359A5 | pBTS Shin Yang Melinau (M) | Sarawak |  | Modernization |  | 2023Q4 | HQ 1 | Datasco | 4.6 TSSR Approved |  | 2023-07-12 | 2023-07-20 |  | 2023-07-26 |  | Closed | 2023-07-27 | 2023-07-28 | E//Hannah | 2023-07-28 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230608-0007 | DU00002038564 |  |  | 2023-09-06 | 2023-08-28 |  | Watertank | 25m pBTS | 30 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882 S1800B(B6B) x3
4427B | Spg Taiping RCD | Northern |  | Modernization |  | 2023Q4 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-06-08 | 2023-07-27 |  | 2023-07-28 |  | Closed | 2023-07-31 | 2023-08-04 | E//Hazida | 2023-08-04 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002038565 |  |  | 2023-08-11 | 2023-08-11 |  | Tower | 60m 4 Legged Tower | 62 | Add A9732 M1821 x3 + R9264M M1821 x1,Dismantle R8862A S1800(B6A) x4+R8862A S2100(A6A) x4+R8862A S2600(A4A) x2+R8894E M1821(A8A) x2 | 123
3296A5 | pBTS Kg Baru Sentosa | Central |  | Modernization |  | 2023Q4 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-07-06 | 2023-07-11 |  | 2023-07-17 |  | Closed | 2023-07-18 | 2023-07-26 | E//Razif | 2023-07-26 | CelcomDigi_RAN_YPTT_TSS_Central_20230708_0014 | DU00002038566 |  |  | 2023-12-20 | 2023-08-24 |  | Watertank | 25m pBTS | 25 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
3470B | Sunshine Business Park | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-05-29 | 2023-06-09 |  | 2023-06-12 |  | Closed | 2023-06-15 | 2023-06-28 | E//Kok Keen | 2023-06-23 | CelcomDigi_RAN_Datasco_TSS_Central_20230428_0018 | DU00002038567 |  |  | 2023-08-10 | 2023-07-13 |  | Pole | 3m Bipod (RT) | 5 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3++R8881 S2100 x3+ |  | 2
3024A | Taman Jasa Utama | Central |  | Modernization |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-06-20 | 2023-07-31 |  | 2023-08-07 |  | Closed | 2023-08-10 | 2023-08-16 | E//Kok Keen | 2023-08-16 | CelcomDigi_RANMW_YPTT_TSS_Central_20230622_0004 | DU00002038568 |  |  | 2023-08-30 | 2023-08-30 |  | Lampole | 20m Lampole | 20m | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3 | 23
1110A | Berjaya Industrial Park | Central |  | Modernization |  | 2023Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-05-12 | 2023-05-22 |  | 2023-05-24 |  | Closed | 2023-05-25 | 2023-07-04 | E//Razif | 2023-07-04 | CelcomDigi_RAN_Allstar_TSS_Central_20230511_0007 | DU00002038569 |  |  | 2023-06-22 | 2023-06-21 |  |  | 30m 4 Legged Tower | 30 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
4071A | Perkaka Sq | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved | AAU Cannot Install-S12 remain MM,S3 change to normal¦NOK,Space constraint， | 2023-05-09 | 2023-05-12 |  | 2023-05-22 |  | Closed | 2023-05-24 | 2023-06-21 | E//Hazida | 2023-06-21 | Celcom Digi_RAN-GCI-TSS-Northern-20230502-0011 | DU00002038570 | NIC_S1_S12 remain MM,S3 change to normal_Space constraint_Digi OB |  | 2023-07-14 | 2023-07-12 |  | Pole | 60m 4 Legged Tower | 8m | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R8862A S2600(A4A) x2+R8894E M1821(A8A) x2 | 12
4046A | USM(Watertank) | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-05 | 2023-06-01 |  | 2023-06-06 |  | Closed | 2023-06-22 | 2023-07-14 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002038571 |  |  | 2023-07-21 | 2023-07-13 |  | Wall mount boom | Watertank Structure | 28M | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8882 S1800(B) x3+R8862A S2100(A6A) x1 |  | 3
4923B | Masjid Kuala Sepetang | Northern |  | Modernization |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved | AAU Cannot Install-Change MM to normal sector¦Space limitted AAU and Bi sector can not install | 2023-06-08 | 2023-06-15 |  | 2023-06-17 |  | Closed | 2023-06-22 | 2024-05-15 | E//Hazida | 2023-09-04 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002038572 | NIC_S2_Change MM to normal sector_Space constraint_PROSONTECH SDN BHD |  | 2023-09-05 | 2023-07-31 |  | Minaret | 30m Minaret | 30m | Add R9264M M1821 x3,Dismantle R8882 S1800(B) x3+R8862A S2100(A6A) x3
1770H | 99 Speedmart Tmn Desa Bkt Delima | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038573 | [6 empty] | Rooftop
3755A | Lorong Intan Baiduri 3c | Central |  | Modernization |  | 2023Q4 | XH | YPTT | 4.6 TSSR Approved |  | 2023-07-17 | 2023-07-18 |  | 2023-07-24 |  | Closed | 2023-07-29 | 2023-08-01 | E//Kok Keen | 2023-09-25 | CelcomDigi_RAN_YPTT_TSS_Central_20230725 | DU00002038574 |  |  | 2023-10-17 | 2023-09-29 |  | Petronas Pylon | 24m Pylon | 29M | Add R9264M M1821 x3,Dismantle R8892E M1821(BAA) x3
1424A | Maxis Tower Batu Arang | Central |  | Modernization |  | 2023Q2 | HQ 1 | Ascentrack | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI,L2600 change to 40M¦loading issue,AAU cannot install | 2023-05-15 | 2023-05-22 |  | 2023-05-25 |  | Closed | 2023-05-29 | 2023-06-10 | E//Kok Keen | 2023-06-08 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230428_0015 | DU00002038575 | NIC_S2_Change MM to BI,L2600 change to 40M_loading issue_MAXIS |  | 2023-09-06 | 2023-08-23 |  | Tower | 60m 4 Legged Tower | 40 | Add R9264H M901821 x1 + R9264M M1821 x4 ,Dismantle R8894E M1821(A8A) x2+R9224E M1821(AAB) x2 |  | 12
1150A | KJS Bukit Rasa | Central |  | Modernization |  | 2023Q4 | SS | Futong | 4.6 TSSR Approved |  | 2023-08-08 | 2023-07-25 |  | 2023-08-08 |  | Closed | 2023-08-17 | 2023-08-24 | E//Kok Keen | 2023-08-24 | CelcomDigi_RAN_Futong_TSS_Central_20230809 | DU00002038576 |  |  | 2023-09-02 | 2023-09-01 |  | Tower | Tower | 76 | Add R9264H M901821 x3,Dismantle R8860E-GU908 x3+R8862A S1800(B6A) x3+R8840-U216 x3++
1075A | Jensen | Central |  | Modernization |  | 2023Q3 | YZ | GTSB | 4.6 TSSR Approved |  | 2023-05-01 | 2023-05-16 |  | 2023-05-19 |  | Closed | 2023-05-20 | 2023-06-14 | CD//Ali akaram | 2023-06-14 | CelcomDigi_RAN_GTSB_TSS_20230505_0023 | DU00002038577 |  |  | 2023-06-19 | 2023-06-19 |  | Pole | 60m 3 Legged Tower | 20 | Add A9732 M1821 x1 + R9264M M1821 x2,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 | 1
4263A | USM Sains Computer | Northern |  | Modernization |  | 2023Q3 | HQ 2 | CCSMY | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-18 |  | 2023-05-21 |  | Closed | 2023-05-23 | 2023-06-21 | E//Hazida | 2023-06-21 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002038578 |  |  | 2023-07-28 | 2023-07-20 |  | H-bracket pole | 30m 3-legged tower | 4 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R9224E M1821(AAB) x3 | 23
4334C | Mutiara View Complex (REL) | Northern |  | Decomm | Modernization->Decomm | 2023Q3 | SM | GTSB | 4.6 TSSR Approved | ¦ 0126 - TSSR with correct location submitted | 2023-05-02 | 2023-05-19 |  |  | 2023-06-02 |  | 2024-01-26 | 2024-10-29 | E//Hazida | 2024-03-04 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2/0612Northern-GTSB-BOQ Template (template) | DU00002038579 |  |  |  |  | 2025-06-23 |  | 5m RT (Boom) | 5
1504H | 99 Speedmart MEDAN BATU CAVES | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038580 | [6 empty] | Small Cell
1004R | KG GERACHI | Central |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2023Q4 |  | CCSMY | 15.3 Decomm Done without TSSR | [6 empty] | To be Submitted |  |  |  |  | SQ202506110090 | DU00002038581 |  |  |  |  | 2025-08-05 |  | Land site
1373H | Elektrisola | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038582 | [6 empty] | Small Cell
4035B | Farlim Business Center | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-13 | 2023-05-19 |  | 2023-05-26 |  | Closed | 2023-06-19 | 2023-07-25 | E//Hazida | 2023-07-21 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0014 | DU00002038583 |  |  | 2023-08-22 | 2023-08-22 |  | Minimast | 3m Boom (RT) | 10M | Add R9264H M901821 x4 + R9264M M1821 x3 + R8862A S2601 x3,Dismantle R8894E M1821(A8A) x4 |  | 124
4954A | Taman Anggerik | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-06-07 | 2023-06-12 |  | 2023-06-14 |  | Closed | 2023-06-21 | 2023-07-28 | E//Daniel | 2023-07-28 | Celcom Digi_RAN-GCI-TSS-Northern-20230607-0024 | DU00002038584 |  |  | 2023-08-30 | 2023-08-29 |  | In-Building System | 6m RT (Boom) | 9 | Add R9264H M901821 x4 + R8862A S2601 x1,Dismantle R8882-GUL1812 x3+R8892E M1821(BAA) x1+R8840-U216 x3++
1771B | Gohtong Jaya | Central |  | Modernization |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-06-27 | 2023-07-06 |  | 2023-07-10 |  | Closed | 2023-07-12 | 2023-07-14 | E//Kok Keen | 2023-07-14 | CelcomDigi_RAN_Magicell_TSS_Central_20230628_0018 | DU00002038585 |  |  | 2023-07-31 | 2023-07-22 |  | Monopole | 30m Monopole | 45 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3
1020A | Tea House | Central |  | Modernization |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-06-21 | 2023-07-05 |  | 2023-07-07 |  | Closed | 2023-07-10 | 2023-07-13 | E//Kok Keen | 2023-07-13 | CelcomDigi_RAN_Magicell_TSS_Central_20230622_0015 | DU00002038586 |  |  | 2023-07-26 | 2023-07-22 |  | Monopole | 45m Monopole | 46 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8860E-GU908 x2+R8882-GUL1812 x3+R8840-U216 x3
4438D | Surau Al-Munawwarah | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-06-06 | 2023-06-14 |  | 2023-06-21 |  | Closed | 2023-07-03 | 2023-08-07 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002038587 |  |  | 2023-08-07 | 2023-08-02 |  | Monopole | 30M RDS | 30 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
1761B | Wisma SAP | Central |  | Modernization |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-06-24 | 2023-07-06 |  | 2023-07-09 |  | Closed | 2023-07-11 | 2023-07-14 | E//Kok Keen | 2023-07-14 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_0009 | DU00002038588 |  |  | 2023-08-30 | 2023-08-21 |  | Minimast | 3m RT (Minimast) | 10 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8882-GUL1812 x3 |  | 1
4108C | Pearl Hill | Northern |  | Modernization |  | 2023Q3 | SM | YPTT | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-13 |  | 2023-05-17 |  | Closed | 2023-05-22 | 2023-07-06 | E//Hazida | 2023-07-06 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0008 | DU00002038589 |  |  | 2023-08-18 | 2023-08-16 |  | Monopole | 30m Lampole | 30 | Add R9264H M901821 x4,Dismantle R8894E M1821(A8A) x4
4132B | PG 2nd Link Bt Maung (PDC pBTS) | Northern |  | Modernization |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-05-06 | 2023-05-08 |  | 2023-05-10 |  | Closed | 2023-05-11 | 2023-06-24 | E//Hannah | 2023-06-23 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038590 |  |  | 2023-07-17 | 2023-07-16 |  | Monopole | 25m pBTS | 24m | Add R9264M M1821 x3,Dismantle R8882 S1800B(B6B) x3+R8881 S2100 x3
4478A | Sg Ayer Tawar | Central |  | Decomm | Modernization->Decomm | 2023Q4 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-09-29 | 2023-11-29 |  |  | 2023-10-24 |  | 2023-10-25 | 2025-09-19 | E//Razif | 2023-10-26 | CelcomDigi_RAN_CCSMY_TSS_Central_20231005 | DU00002038591 |  |  |  |  | 2023-12-14 | Tower | Tower | 47
4591C | Masjid Jamek Al-Istiglal | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GTSB | 4.6 TSSR Approved | AAU Cannot Install-Change MM to normal sector¦Space limitted AAU and Bi sector can not install | 2023-05-26 | 2023-06-23 |  | 2023-06-26 |  | Closed | 2023-07-03 | 2023-08-07 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002038592 | NIC_S3_Change MM to normal sector_Space constraint_EDGEPOINT INFRA |  | 2023-09-18 | 2023-08-02 |  | Minaret | 30m Monopole | 30M | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3
4331D | Kg Ambar AS | Northern |  | Modernization |  | 2023Q4 | HQ 2 | YPTT | 4.6 TSSR Approved |  | 2023-05-31 | 2023-06-06 |  | 2023-06-08 |  | Closed | 2023-06-12 | 2023-07-27 | E//Hazida | 2023-07-27 | Celcom Digi_RAN-YPTT-TSS-Northern-20230602-0016 | DU00002038593 |  |  | 2023-09-22 | 2023-08-29 |  | Monopole | 30m Monopole | 25 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8892N M1821(BAB) x3 | 13
1054C | Taman Sentosa Dinasti (REL) | Central |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-22 |  | 2023-05-24 |  | Closed | 2023-05-25 | 2023-06-19 | CD//Sapian | 2023-06-18 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002038594 |  |  | 2023-06-10 | 2023-06-10 |  | Lampole | 24m Lampole | 25m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
4758B | Lake Garden Taiping | Northern |  | Modernization |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-06-12 | 2023-06-13 |  | 2023-06-15 |  | Closed | 2023-06-21 | 2023-07-15 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230613-0025 | DU00002038595 |  |  | 2023-08-20 | 2023-07-29 |  | Monople Tree | 30m Monopole | 31 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8840-U216 x3++
4474A | Sg Besar | Central |  | Modernization |  | 2023Q4 | XH | Magicell | 4.6 TSSR Approved |  | 2023-05-24 | 2023-05-30 |  | 2023-06-01 |  | Closed | 2023-06-04 | 2023-07-25 | E//Razif | 2023-07-25 | CelcomDigi_RAN_GTSB_TSS_Central_20230529_0010 | DU00002038596 |  |  | 2023-07-21 | 2023-07-20 |  | Tower | Tower | 45M | Add A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2601 x1,Dismantle R8882-GUL1812 x2+R8862A S2100(A6A) x2 | 12(S1->S2,S2->S3,Addition Sector,name S1,Rename sectorID ,MM@ new S2/S3)
2262A | Jalan Manggies Watertank | Central |  | Modernization |  | 2023Q4 | YZ | GTSB | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-13 |  | 2023-05-19 |  | Closed | 2023-05-22 | 2023-06-06 | E//Kok Keen | 2023-05-23 | CelcomDigi_RAN_GTSB_TSS_Cental_20230511_0024 | DU00002038597 |  |  | 2023-07-05 | 2023-07-04 |  | Monopole | Land site | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
3926B | Jalan Meru Tambahan | Central |  | Modernization |  | 2023Q3 | YZ | Magicell | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦Space constraint | 2023-05-12 | 2023-05-19 |  | 2023-05-23 |  | Closed | 2023-06-12 | 2023-07-04 | E//Razif | 2023-07-04 | CelcoDigi_RAN_Magicell_TSS_Central_20230517_0009 | DU00002038598 | NIC_S2_Change MM to BI_Space constraint_EDOTCO (M) - NONE CSU |  | 2023-07-06 | 2023-07-05 |  | Minimast | 3m RT (Minimast) | 9M | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 |  | 13(S2->S1，S3->S2，S1->S3，Rename sectorID,MM@New S2/S3)
3685C | Bandar Tasik Puteri 6 | Central |  | Modernization |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-10 |  | 2023-05-20 |  | Closed | 2023-05-20 | 2023-06-02 | E//Kok Keen | 2023-06-02 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230428_0015 | DU00002038599 |  |  | 2023-05-30 | 2023-05-30 |  | Lampole | 24m Lampole | 24 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1412H | 99 Speedmart SENTOSA HULUBALANG | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038600 | [6 empty] | Small Cell
1883B | NS Highway KM406.2(KJS _ ZED) | Central |  | Modernization |  | 2023Q4 | CR | Ascentrack | 4.6 TSSR Approved |  | 2023-06-30 | 2023-07-14 |  | 2023-07-19 |  | Closed | 2023-07-21 | 2023-07-25 | E//Kok Keen | 2023-07-25 | Celcomdigi_RAN_Ascentrack_TSS_Central_20230703_0026 | DU00002038601 |  |  | 2023-08-04 | 2023-08-04 |  | Tower | Tower | 60 | Add R9264H M901821 x3,Dismantle R8860E-GU908 x2+R8882-GUL1812 x2 + R8840 U216 x1
1115C | Taman Amaniah Mulia | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-21 | 2023-06-28 |  | 2023-07-05 |  | Closed | 2023-07-05 | 2023-07-12 | E//Kok Keen | 2023-07-12 | CelcomDigi_RANMW_GTSB_TSS_Central_20230622_0006 | DU00002038602 |  |  | 2023-07-21 | 2023-07-18 |  | Lampole | 24m Lampole | 30m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
4301D | Tesco Mergong (REL) | Northern |  | Modernization |  | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-05-31 | 2023-06-06 |  | 2023-06-10 |  | Closed | 2023-06-13 | 2023-06-21 | E//Hazida | 2023-06-20 | Celcom Digi_RAN-YPTT-TSS-Northern-20230602-0016 | DU00002038603 |  |  | 2023-09-03 | 2023-09-03 |  | Tower | 45m Tower | 45m | Add R8852E S9000 x3 + A9732 M1821 x3 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x4 | 134
2468A | Kolej Ali | Central |  | Modernization |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-07-31 | 2023-08-03 |  | 2023-08-07 |  | Closed | 2023-08-10 | 2023-08-16 | E//Kok Keen | 2023-08-16 | CelcomDigi_RAN_Datasco_TSS_Central_20230802 | DU00002038604 |  |  | 2024-04-20 | 2024-03-27 |  | Monople Tree | 45m Monopole Tree | 37m | Add R9224E M1821 x3+R8854E S1800 x3,Dismantle R8882-GUL1812 x3
1367A | WorldWideBusiness | Central |  | Modernization |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-06-19 | 2023-06-20 |  | 2023-06-22 |  | Closed | 2023-06-26 | 2023-07-27 | E//Razif | 2023-07-27 | CelcomDigi_RAN_Datasco_TSS_Central_20230620_0027 | DU00002038605 |  |  | 2023-08-19 | 2023-07-18 |  | H-bracket pole | 3m Boom (RT) | 6 | Add R9264M M1821 x5 + R8862A S2601 x2,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8840-U216 x3++ |  | 23
1061A | Tg Malim | Central |  | Modernization |  | 2023Q4 | HQ 6 | Ascentrack | 4.6 TSSR Approved |  | 2023-07-05 | 2023-07-10 |  | 2023-07-11 |  | Closed | 2023-07-12 | 2023-07-14 | E//Kok Keen | 2023-07-14 | CelcomDigi_RANMW_Ascentrack_TSS_Central_20230626_0008 | DU00002038606 |  |  | 2023-08-24 | 2023-08-21 |  | Pole | 3m RT (Wall Mounted Pole) | 4 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2,Dismantle R8882-GUL1812 x3 | 2
4678B | Gunung Keriangan(MXS) | Northern |  | Modernization |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-26 | 2023-05-31 |  | 2023-06-06 |  | Closed | 2023-06-21 | 2023-08-02 | E//Daniel | 2023-07-30 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230529-0020 | DU00002038607 |  |  | 2023-09-20 | 2023-09-14 |  | Tower | 60m 3 Legged Tower | 60 | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x3 |  | 1
1085A | Pekan Meru | Central |  | Modernization |  | 2023Q3 | IE | Magicell | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-10 |  | 2023-05-12 |  | Closed | 2023-05-20 | 2023-06-03 | E//Razif | 2023-05-24 | CelcomDigi_RAN_Magicell_TSS_20230505_0006 | DU00002038608 |  |  | 2023-06-16 | 2023-06-13 |  | Monopole | 60m 4 Legged Tower | 30m | Add R9264M M1821 x5 + R8862A S2600 x2,Dismantle R9224E M1821(AAB) x4 |  | 12(S1->S3,S2->S1，S3->S2,rename sector ID,Bisector@ new S1/S2)
3284A | JLNHAMZAHALANG1 | Central |  | Modernization |  | 2023Q3 | HQ 6 | Magicell | 4.6 TSSR Approved |  | 2023-06-14 | 2023-06-21 |  | 2023-06-26 |  | Closed | 2023-06-28 | 2023-07-20 | E//Razif | 2023-07-20 | CelcomDigi_RANMW_Magicell_TSS_Central_20230616_0006 | DU00002038609 |  |  | 2023-11-20 | 2023-11-20 |  | Tower | 60m 4 Legged Tower | 60 | Add A9732 M1821 x3,Dismantle R8854E S1800(A6A) x3+R8854D S2100(A4A) x3 | 123
4047B | Pantai Acheh | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-12 | 2023-05-15 |  | 2023-05-22 |  | Closed | 2023-05-23 | 2023-07-07 | E//Hazida | 2023-07-06 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038610 |  |  | 2023-07-20 | 2023-07-18 |  | Tower | Tower | 61 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle R8892E M1821(BAA) x3
3364C | Kuaters Guru Seksyen 24 Shah Alam (REL) | Central |  | Modernization |  | 2023Q4 | XH | GTSB | 4.6 TSSR Approved |  | 2023-05-29 | 2023-06-07 |  | 2023-06-14 |  | Closed | 2023-06-20 | 2023-07-20 | E//Razif | 2023-07-20 | CelcomDigi_RAN_GTSB_TSS_Central_20230531_0026 | DU00002038611 |  |  | 2024-01-18 | 2023-12-11 |  |  | Rooftop 3M Boom |  | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2,Dismantle R8894E M1821(A8A) x3 | 1
4136B | Sg Batu (PDC pBTS) | Northern |  | Modernization |  | 2023Q3 | MH | GTSB | 4.6 TSSR Approved |  | 2023-05-13 | 2023-05-18 |  | 2023-05-27 |  | Closed | 2023-05-30 | 2023-06-17 | CD//Shukri | 2023-06-16 | Celcom Digi_RAN-GTSB-Standard PR TSS-Northern-20230508-0014 | DU00002038612 |  |  | 2023-06-27 | 2023-06-27 |  | Monopole | 25m pBTS | 21M | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
4822A | Gurney Plaza | Northern |  | Modernization |  | 2023Q3 | WP | GCI | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-08 |  | 2023-05-09 |  | Closed | 2023-05-13 | 2023-08-15 | E//Nazrul | 2023-08-15 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038613 |  |  | 2023-08-16 | 2023-08-16 |  |  | In-building system |  | Add + R8862A S1800 x4,Dismantle R8882-GUL1812 x1+R8882 S1800(B) x3
1763B | Wisma Eagle | Central |  | Modernization |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-07-07 | 2023-07-17 |  | 2023-07-21 |  | Closed | 2023-07-28 | 2023-08-01 | E//Kok Keen | 2023-08-01 | CelcomDigi_RAN_YPTT_TSS_Central_20230708_0014 | DU00002038614 |  |  | 2023-08-23 | 2023-08-21 |  | In-Building System | 3m Bipod (RT) | 5 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x3 | 12
1071A | Chi Liung | Central |  | Modernization |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-06 |  | 2023-05-09 |  | Closed | 2023-05-10 | 2023-06-22 | E//Sumitra | 2023-06-20 | CelcomDigi_RAN_YPTT_TSS_20230505_0002 | DU00002038615 |  |  | 2023-06-10 | 2023-06-08 |  | Pole | 45m 3 Legged Tower | 8 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
2946A | Taman Setia | Central |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-05-31 | 2023-06-01 |  | 2023-06-07 |  | Closed | 2023-06-12 | 2023-07-04 | E//Sumitra | 2023-07-04 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002038616 |  |  | 2023-06-22 | 2023-06-19 |  | Pole | 3m Bipod (RT) | 4 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3++
3473C2 | pBTS Masjid Al-Baraqah ( C ) | Central |  | Modernization |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦pBTS loading issue,AAU cannot install | 2023-05-03 | 2023-05-06 |  | 2023-05-09 |  | Closed | 2023-05-20 | 2023-06-05 | E//Razif | 2023-05-24 | CelcomDigi_RANMW_YPTT_TSS_Central_20230505_0001 | DU00002038617 | NIC_S3_Change MM to BI_loading issue_Digi OB |  | 2023-06-17 | 2023-06-14 |  | Guide mast | 25m pBTS | 25m | Add R9264H M901821 x3 + R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 |  | 123
4633D | Changkat Bukit Gambir (REL) | Northern |  | Modernization |  | 2023Q3 | YZ | GCI | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-08 |  | 2023-05-05 |  | Closed | 2023-05-11 | 2023-05-25 | CD//Affendi | 2023-05-16 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038618 |  |  | 2023-07-04 | 2023-07-04 |  | Monopole | Land site | 35m | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R9224E M1821(AAB) x3 | 23
4722A | Jelutong Expressway (REL) | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-13 | 2023-05-16 |  | 2023-05-22 |  | Closed | 2023-05-24 | 2023-06-10 | E//Hazida | 2023-06-08 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0013 | DU00002038619 |  |  | 2023-07-04 | 2023-07-03 |  | Monopole | 30m Monopole | 24 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
1758H | 99 Speedmart Shah Alam Sek 18 | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038620 | [6 empty] | Rooftop
1851H | 99 Speedmart Prima Beruntung | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038621 | [6 empty] | Rooftop
3406C | Johan Setia (REL) | Central |  | Modernization |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-06 | 2023-05-10 |  | 2023-05-12 |  | Closed | 2023-05-15 | 2023-06-19 | CD//Sapian | 2023-06-18 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002038622 |  |  | 2023-06-17 | 2023-06-13 |  | Tower | 3m Boom (RT) | 45M | Add R9264H M901821 x3 + R9264M M1821 x2,Dismantle R8894E M1821(A8A) x5 |  | 13
4585B | Kg Bagan Nira (Celcom) | Central |  | Modernization |  | 2023Q4 | HQ 6 | CCSMY | 4.6 TSSR Approved |  | 2023-07-04 | 2023-07-11 |  | 2023-07-17 |  | Closed | 2023-07-20 | 2023-07-28 | E//Kok Keen | 2023-07-28 | CelcomDigi_RAN_CCSMY_Central_20230706_0008 | DU00002038623 |  |  | 2023-09-14 | 2023-09-12 |  | Tower | Tower | 82 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 23
3462B | Genting RSC 9 IB | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-21 | 2023-07-12 |  | 2024-04-19 |  | Closed | 2024-05-20 | 2024-05-27 | E//Nazrul | 2024-05-20 | CelcomDigi_RANMW_GTSB_TSS_Central_20230622_0006 | DU00002038624 |  |  | 2025-08-22 | 2025-07-25 |  | Portables BTS | In-building system |  | Add R8892N M1821 x9,Dismantle R8882 S1800B(B6B) x5+R8892E M1821(BAA) x4 | 0 | 0
4006B | Jln Bukit Gambir | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-13 | 2023-06-01 |  | 2023-06-12 |  | Closed | 2023-06-15 | 2023-07-15 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0015 | DU00002038625 |  |  | 2023-07-17 | 2023-07-13 |  | Lampole | Tower | 30M | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8894E M1821(A8A) x4 |  | 13
4073B | Turf Club Penang | Northern |  | Modernization |  | 2023Q3 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-13 |  | 2023-05-18 |  | Closed | 2023-05-22 | 2023-07-15 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0008 | DU00002038626 |  |  | 2023-08-22 | 2023-08-22 |  | Wall mount boom | 3m Boom (RT) | NA | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3
1360C | Antara Gapi LP | Central |  | Modernization |  | 2023Q4 | SS | AllStar | 4.6 TSSR Approved |  | 2023-09-07 | 2023-09-13 |  | 2023-09-15 |  | Closed | 2023-09-18 | 2023-09-20 | E//Kok Keen | 2023-09-20 | CelcomDigi_RAN_Allstar_TSS_Central_20230911 | DU00002038627 |  |  | 2023-09-30 | 2023-09-30 |  | Lampole | 24m Lampole | 25 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 1
4156H | 99 Speedmart PK TMN JANA SETIA | Northern |  | MOCN As-Is | MOCN As-Is->Site Out->On Hold->MOCN As-Is | 2023Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038628 | [6 empty] | Small Cell
3808A | Surau Taman Bendena Jaya | Central |  | Modernization |  | 2023Q4 | HQ 6 | Magicell | 4.6 TSSR Approved |  | 2023-06-06 | 2023-06-13 |  | 2023-06-15 |  | Closed | 2023-07-28 | 2023-08-15 | E//Razif | 2023-07-27 | CelcomDigi_RAN_Magicell_TSS_Central_20230607_0012 | DU00002038629 |  |  | 2023-08-16 | 2023-08-10 |  | Lampole | 24m Lampole | 30m | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
4865A | Cititel Penang | Northern |  | Modernization |  | 2023Q3 | WP | CCSMY | 4.6 TSSR Approved |  | 2023-05-17 | 2023-05-19 |  | 2023-05-23 |  | Closed | 2023-07-31 | 2023-07-31 | E//Nazrul | 2023-07-31 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0015 | DU00002038630 |  |  | 2023-08-29 | 2023-08-29 |  | Wall mount boom | In-building system |  | Add R8862A S1800 x1
1659C | Taman Bunga Raya Rawang 1 | Central |  | Decomm | Modernization->Decomm | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-08-01 | 2023-06-15 |  | 2023-05-12 | 2023-08-09 | Closed | 2023-05-13 | 2024-06-20 | E//Kok Keen | 2023-09-05 | 0626Central-Datasco-BOQ Template (template) | DU00002038631 |  |  |  |  | 2023-12-16 | Monopole | Land site | 35
1256B | Sek 2 Shah Alam | Central |  | Modernization |  | 2023Q4 | YZ | Datasco | 4.6 TSSR Approved |  | 2023-05-16 | 2023-05-30 |  | 2023-06-02 |  | Closed | 2023-06-03 | 2023-07-28 | E//Razif | 2023-07-28 | CelcomDigi_RAN_Datasco_TSS_Central_20230517_0022 | DU00002038632 |  |  | 2023-07-05 | 2023-07-04 |  | Lampole | 20m Lampole | 24 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3
4032E | Kamunting Inds Park | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-28 | 2023-05-30 |  | 2023-06-01 |  | Closed | 2023-06-02 | 2023-06-13 | CD//Shamsul | 2023-06-13 | Celcom Digi_RAN-GCI-TSS-Northern-20230529-0022 | DU00002038633 |  |  | 2023-07-28 | 2023-07-22 |  | Unipole | Land site | 30 | Add R9264H M901821 x3,Dismantle R9224E M1821(AAB) x3
1269H | 99 Speedmart BDR BARU SELAYANG 1 | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038634 | [6 empty] | Small Cell
4000M | Little India Penang St | Northern |  | MOCN As-Is |  | 2023Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038635 | [6 empty] | Micro Cell
1439H | 99 Speedmart TMN INTAN BAIDURI | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038636 | [6 empty] | Small Cell
1670H | 99 Speedmart Pekan Sabak Bernam | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038637 | [6 empty] | Rooftop
2038A | Antara Gapi (KJS) | Central |  | Modernization |  | 2023Q4 | SS | Futong | 4.6 TSSR Approved |  | 2023-07-06 | 2023-07-04 |  | 2023-07-06 |  | Closed | 2023-07-07 | 2023-07-13 | E//Kok Keen | 2023-07-13 | CelcomDigi_RAN_Futong_TSS_Central_20230707_0008 | DU00002038638 |  |  | 2023-07-29 | 2023-07-25 |  | Tower | Tower | 76 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8882-GUL1812 x3+R8840-U216 x3++ |  | 1
1612B | Bkt Cherakah Kapar | Central |  | Modernization |  | 2023Q3 | IE | Magicell | 4.6 TSSR Approved |  | 2023-05-23 | 2023-05-24 |  | 2023-05-26 |  | Closed | 2023-05-29 | 2023-07-12 | E//Razif | 2023-07-11 | CelcomDigi_RAN_GTSB_TSS_Central_20230529_0010 | DU00002038639 |  |  | 2023-07-24 | 2023-07-22 |  | Tower | 60m 4 Legged Tower | 61 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x3 | 23
2443A | Ijok (CELCOM) | Central |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-06-06 | 2023-06-08 |  | 2023-06-12 |  | Closed | 2023-06-13 | 2023-07-12 | E//Razif | 2023-07-12 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002038640 |  |  | 2023-09-15 | 2023-09-12 |  | Tower | Tower | 46 | Add R9264H M901821 x4 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R9224E M1821(AAB) x4 |  | 3
4307C | Four Season Condo | Northern |  | Modernization |  | 2023Q3 | MH | GTSB | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-13 |  | 2023-05-19 |  | Closed | 2023-05-22 | 2023-07-07 | E//Hazida | 2023-07-06 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0015 | DU00002038641 |  |  | 2023-08-10 | 2023-08-10 |  | Minimast | 3m Boom (RT) | 8 | Add R9264H M901821 x2 + R9264M M1821 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R9224E M1821(AAB) x1+R8862A S2600(A4A) x1 |  | 2
1853H | 99 Speedmart Tmn Emas | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038642 | [6 empty] | Rooftop
1184B | Selayang Mulia | Central |  | Modernization |  | 2023Q4 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-06-16 | 2023-07-20 |  | 2023-07-26 |  | Closed | 2023-07-27 | 2023-07-28 | E//Kok Keen | 2023-07-28 | CelcomDigi_RAN_YPTT_TSS_Central_20230620_0006 | DU00002038643 |  |  | 2023-08-07 | 2023-08-07 |  | Monople Tree | 30m Monopole Tree | 30m | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 | 123
4895B | Straits Quay RT | Northern |  | Modernization |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-10 |  | 2023-05-17 |  | Closed | 2023-05-23 | 2023-07-22 | E//Hazida | 2023-07-22 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0014 | DU00002038644 |  |  | 2023-08-17 | 2023-08-17 |  | Pole | 3m Boom (RT) | 3 | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8882 S1800B(B6B) x3+R8881 S2100 x3 |  | 2
1762H | 99 Speedmart Panchang Bedena | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038645 | [6 empty] | Small Cell
1566C | Surau Kemuning Utama (REL 2) | Central |  | Modernization |  | 2023Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-05-12 | 2023-05-18 |  | 2023-05-22 |  | Closed | 2023-05-23 | 2023-06-17 | CD//Sapian | 2023-06-16 | CelcomDigi_RAN_Allstar_TSS_Central_20230511_0007 | DU00002038646 |  |  | 2023-06-16 | 2023-06-16 |  | Lampole | 20m Lampole | 20 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
2626B | Persiaran Sultan | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-01 | 2023-06-06 |  | 2023-06-12 |  | Closed | 2023-06-13 | 2023-07-20 | E//Razif | 2023-07-20 | CelcomDigi_RAN_GTSB_TSS_Central_20230606_0027 | DU00002038647 |  |  | 2023-09-14 | 2023-07-31 |  | In-Building System | 3m RT (Wall Mounted Pole) | 3 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
3535B | Taman Mas 2 Putra Prima | Central |  | Modernization |  | 2023Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-05-23 | 2023-05-24 |  | 2023-05-26 |  | Closed | 2023-05-29 | 2023-07-06 | CD//Norhaliza | 2023-07-04 | CelcomDigi_RANMW_Allstar_TSS_Central_20230511_0002 | DU00002038648 |  |  | 2023-06-16 | 2023-06-16 |  | Lampole | Billboard | 33 | Add R9264H M901821 x3,Dismantle R8882 S1800B(B6B) x2+R8862A S1800(B6A) x1+R8854D S2100(A4A) x3
4053Z | KGHULUTERAS | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038649 | [6 empty] | Land site
3679B | Jalan Elektron U16_N | Central |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-05-06 | 2023-05-09 |  | 2023-05-11 |  | Closed | 2023-05-18 | 2023-08-15 | E//Kok Keen | 2023-08-15 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002038650 |  |  | 2023-06-27 | 2023-06-26 |  | Pole | 3m Bipod (RT) | 4m | Add R9264H M901821 x4 + R9264M M1821 x1,Dismantle R8882 S1800B(B6B) x3+R8862A S1800(B6A) x1+R8881 S2100 x3 |  | 4
3629B | Jalan Johan Setia | Central |  | Modernization |  | 2023Q3 | HQ 6 | AllStar | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦Unipole can not install 3 AAUS due to loading issueremove S3 AAU | 2023-05-17 | 2023-05-19 |  | 2023-05-31 |  | Closed | 2023-06-04 | 2023-07-04 | E//Razif | 2023-07-04 | CelcomDigi_RAN_AllStar_TSS_Central_20230523_0009 | DU00002038651 | NIC_S3_Change MM to BI_loading issue_Digi OB |  | 2023-06-22 | 2023-06-22 |  | Rooftop | 45m 4 Legged Tower | 27M | Add R9264M M1821 x6,Dismantle R8894E M1821(A8A) x3 |  | 123
2302A | Chin Swee Skyway Station (Station 2) Macro | Central |  | Modernization |  | 2023Q4 | HQ 6 | GTSB | 4.6 TSSR Approved |  | 2023-05-25 | 2023-06-17 |  | 2023-06-21 |  | Closed | 2023-06-21 | 2023-06-27 | E//Kok Keen | 2023-06-27 | CelcomDigi_RAN_GTSB_TSS_Central_20230529_0025 | DU00002038652 |  |  | 2023-11-16 | 2023-07-25 |  | In-Building System | 3m Bipod (RT) | 4m | Add R9264H M901821 x4,Dismantle R8892E M1821(BAA) x4
1606B | Kota Kemuning 3 | Central |  | Modernization |  | 2023Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-05-11 | 2023-05-18 |  | 2023-05-22 |  | Closed | 2023-05-23 | 2023-06-17 | CD//Norhaliza | 2023-06-15 | CelcomDigi_RAN_Allstar_TSS_Central_20230511_0007 | DU00002038653 |  |  | 2023-06-22 | 2023-06-21 |  | Wall mount boom | 3m Boom (RT) | 5 | Add R8894E M1821 x4,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8840-U216 x3
3291A5 | pBTS Jalan Bukit Kapar ( C ) | Central |  | Modernization |  | 2023Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-08 |  | 2023-05-10 |  | Closed | 2023-05-10 | 2023-06-14 | CD//Ali akaram | 2023-06-14 | CelcomDigi_RAN_GTSB_TSS_Cental_20230511_0024 | DU00002038654 |  |  | 2023-06-14 | 2023-06-13 |  | Guide mast | 25m pBTS | 25m | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle R8882 S1800(B) x3+R8862A S1800(B6A) x1+R8862A S2100(A6A) x4 |  | 2
1518C | Kg Bukit Kerayong | Central |  | Modernization |  | 2023Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-05-17 | 2023-05-26 |  | 2023-06-02 |  | Closed | 2023-06-02 | 2023-06-13 | E//Kok Keen | 2023-06-13 | CelcomDigi_RAN_GTSB_TSS_Central_20230523_0025 | DU00002038655 |  |  | 2023-07-03 | 2023-07-02 |  | Lampole | 30M Lampole | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
4427A | Pondok Tanjung | Northern |  | Modernization | Modernization->Maintain USP MOCN->Modernization->On Hold->Modernization | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-05-26 | 2023-06-01 |  | 2023-06-04 |  | Closed | 2023-06-08 | 2023-07-15 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-YPTT-TSS-Northern-20230530-0014 | DU00002038656 |  |  | 2023-07-28 | 2023-07-28 |  | Tower | 60m 3 Legged Tower | 45 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
2467A | Kolej Nusaibah | Central |  | Modernization |  | 2023Q4 | SS | Datasco | 4.6 TSSR Approved |  | 2023-07-31 | 2023-08-01 |  | 2023-08-04 |  | Closed | 2023-08-08 | 2023-11-30 | E//Kok Keen | 2023-11-30 | CelcomDigi_RAN_Datasco_TSS_Central_20230802 | DU00002038657 |  |  | 2024-02-27 | 2024-02-26 |  | Monople Tree | 30m Monopole Tree | 38 | Add R9264M M1821 x3,dismantle R9224E M1821(AAB) x3
4068A | Shoplot Sg Ara | Northern |  | Modernization |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-05-02 | 2023-05-12 |  | 2023-05-08 |  | Closed | 2023-05-16 | 2023-06-20 | E//Hannah | 2023-06-19 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0014 | DU00002038658 |  |  | 2023-07-15 | 2023-07-15 |  | Pole | 40m Monopole | 3 | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 | 123
1094C | Jalan Pesona 25_116 | Central |  | Modernization |  | 2023Q4 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-06-16 | 2023-06-22 |  | 2023-06-26 |  | Closed | 2023-06-27 | 2023-07-20 | E//Razif | 2023-07-13 | CelcomDigi_RANMW_YPTT_TSS_Central_20230620_0003 | DU00002038659 |  |  | 2023-08-10 | 2023-08-04 |  | Lampole | 24m Lampole | 24 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x3+R9224E M1821(AAB) x2 | 123
1510H | 99 Speedmart Setia Alam 6 | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038660 | [6 empty] | Rooftop
4016H | KS LIANG TELECOMMUNICATION | Northern |  | MOCN As-Is |  | 2023Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038661 | [6 empty] | Small Cell
4462A | Taiping Poly RDD | Northern |  | Modernization |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-06-12 | 2023-06-16 |  | 2023-06-20 |  | Closed | 2023-06-27 | 2023-07-15 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230613-0025 | DU00002038662 |  |  | 2023-07-26 | 2023-07-22 |  | Pole | 6m RT (Boom) | 15 | Add R9264H M901821 x4 + R9264M M1821 x3 + R8862A S2601 x3,Dismantle R8894E M1821(A8A) x4 |  | 124
4063A | Komplek Tabung Haji | Northern |  | Modernization |  | 2023Q3 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-05-04 | 2023-05-13 |  | 2023-05-22 |  | Closed | 2023-05-26 | 2023-06-28 | CD//Quah | 2023-06-22 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0008 | DU00002038663 |  |  | 2023-07-12 | 2023-07-12 |  | Pole | 6m Tripod (RT) | 6 | Add R9264M M1821 x6 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R8894E M1821(A8A) x2 |  | 123
1603H | 99 Speedmart SHAH ALAM SEK 13 (1) | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038664 | [6 empty] | Small Cell
4077B | Kg Jln Baru | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-02 | 2023-05-19 |  | 2023-05-24 |  | Closed | 2023-05-26 | 2023-07-04 | E//Hazida | 2023-07-04 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230502-0013 | DU00002038665 |  |  | 2023-07-17 | 2023-07-13 |  | Tower | 60m 4 Legged Tower | 60 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
4254B | Island Hospital Penang | Northern |  | Site Out (Modernization) | Modernization->Site Out->Replacement, Site Out (Modernization) | 2023Q3 |  | CCSMY | [SiteOut]- 2.1 Pending ETSS Submission - Subcon | ¦ 20230804 - Recieved termination notice from LL | 2023-05-25 |  |  |  |  | To be Submitted |  |  |  |  | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0015 | DU00002038666 | [6 empty] | In-building system
1363A | Tmn Perindustrian | Central |  | Modernization |  | 2023Q4 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-06-19 | 2023-07-17 |  | 2023-07-24 |  | Closed | 2023-07-26 | 2023-07-26 | E//Razif | 2023-07-26 | CelcomDigi_RANMW_YPTT_TSS_Central_20230620_0003 | DU00002038667 |  |  | 2023-08-17 | 2023-08-16 |  | Minimast | 6m RT (Minimast) | 10 | Add R9264M M1821 x6,Dismantle R8894E M1821(A8A) x4+R9224E M1821(AAB) x2 |  | 34
4821C | Pulau Betong PDC (REL) | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-07 | 2023-05-10 |  | 2023-05-16 |  | Closed | 2023-05-18 | 2023-06-28 | E//Hazida | 2023-06-28 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0015 | DU00002038668 |  |  | 2023-07-20 | 2023-07-13 |  | Tower | 76m 4 Legged Tower | 60 | Add R9264M M1821 x5 + R8862A S2601 x5,Dismantle R8892E M1821(BAA) x3 |  | 12
4583B | Kg Parit Baru | Central |  | Modernization |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-07-09 | 2023-07-12 |  | 2023-07-20 |  | Closed | 2023-07-24 | 2023-07-28 | E//Razif | 2023-07-26 | CelcomDigi_RAN_CCSMY_TSS_Central_20230711 | DU00002038669 |  |  | 2023-09-30 | 2023-08-10 |  | Tower | 60m 3 Legged Tower | 62m | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8882-GUL1812 x3 |  | 1
3753A | Masjid Al-Huda Seksyen 19 | Central |  | Modernization |  | 2023Q4 | SS | Solusi | 4.6 TSSR Approved |  | 2023-05-31 | 2023-06-07 |  | 2023-06-21 |  | Closed | 2023-06-23 | 2023-07-18 | E//Razif | 2023-07-18 | CelcomDigi_RANMW_Solusi_TSS_Central_20230620_0003 | DU00002038670 |  |  | 2023-08-05 | 2023-08-04 |  | Lampole | 20m Lampole | 20m | Add R9264M M1821 x3 + R8862A S2601 x3,Dismantle R8882 S1800B(B6B) x3++R8881 S2100 x3+
4015A | Axis Complex V4 | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-09 |  | 2023-05-11 |  | Closed | 2023-05-15 | 2023-07-10 | E//Hazida | 2023-07-22 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0015 | DU00002038671 |  |  | 2023-08-16 | 2023-08-14 |  | Wall mount boom | 3m Boom (RT) | 6 | Add R9264M M1821 x6+R8862A S2601 x2,Dismantle R9224E M1821(AAB) x4 |  | (S2->S3,S3->S4,S4->S2,Rename sectorID,Bisector@newS1/S3)
1755C | Eco Ardence | Central |  | Modernization |  | 2023Q3 | IE | Magicell | 4.6 TSSR Approved |  | 2023-05-11 | 2023-05-12 |  | 2023-05-15 |  | Closed | 2023-05-18 | 2023-06-28 | E//Razif | 2023-06-16 | CelcomDigi_RANMW_Magicell_TSS_Central_20230517_0002 | DU00002038672 |  |  | 2023-06-14 | 2023-06-13 |  | Lampole | Land site | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
2636A | Berjuntai Bestari 2 | Central |  | Modernization |  | 2023Q3 | HQ 6 | GTSB | 4.6 TSSR Approved |  | 2023-04-28 | 2023-05-05 |  | 2023-05-08 |  | Closed | 2023-05-13 | 2023-06-14 | E//Razif | 2023-06-14 | CelcomDigi_RAN_GTSB_TSS_20230505_0023 | DU00002038673 |  |  | 2023-06-13 | 2023-06-13 |  | Tower | 4 Legged Tower | 45 | Add R9264H M901821 x2 + R9264M M1821 x2,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x1+R8862A S2100(A6A) x2
1761H | 99 Speedmart Tmn Daya Maju | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038674 | [6 empty] | Rooftop
3580C | Persiaran Setia Prima | Central |  | Modernization |  | 2023Q3 | HQ 6 | Magicell | 4.6 TSSR Approved |  | 2023-05-06 | 2023-05-10 |  | 2023-05-12 |  | Closed | 2023-05-14 | 2023-06-17 | E//Razif | 2023-06-16 | CelcomDigi_RAN_Magicell_TSS_Central_20230508_0007 | DU00002038675 |  |  | 2023-06-13 | 2023-06-13 |  | Lampole | 24m Lampole | 25m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
4044C | KEMTA | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-06-20 | 2023-06-21 |  | 2023-06-23 |  | Closed | 2023-07-03 | 2023-08-22 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-GCI-TSS-Northern-20230621-0032 | DU00002038676 |  |  | 2023-08-10 | 2023-07-31 |  |  | 30m Monopole | 45 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x3 | 23
1342A | MBSA | Central |  | Modernization |  | 2023Q4 | SS | Datasco | 4.6 TSSR Approved |  | 2023-07-24 | 2023-08-02 |  | 2023-08-04 |  | Closed | 2023-08-08 | 2023-08-22 | E//Razif | 2023-08-10 | CelcomDigi_RAN_Datasco_TSS_Central_20230726 | DU00002038677 |  |  | 2023-12-13 | 2023-10-23 |  | In-Building System | 6m RT (Boom) |  | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 |  | 1
4067B | Taman Lip Sin | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-04 | 2023-05-08 |  | 2023-05-08 |  | Closed | 2023-05-11 | 2023-07-04 | E//Hazida | 2023-07-04 | Celcom Digi_RAN-GCI- TSS-Northern-20230509-0016 | DU00002038678 |  |  | 2023-07-25 | 2023-07-18 |  | Rooftop | 60m 4 Legged Tower | 30 | Add A9732 M1821 x3,Dismantle R8882 S1800(B) x3+R8894E M1821(A8A) x3 | 123
1008Z | TJG MEDAN | Central |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038679 | [6 empty] | Land site
1192B | Kampung Segemal | Central |  | Modernization |  | 2023Q4 | XH | AllStar | 4.6 TSSR Approved |  | 2023-05-27 | 2023-06-01 |  | 2023-06-06 |  | Closed | 2023-06-07 | 2023-07-26 | E//Razif | 2023-07-26 | CelcomDigi_RAN_AllStar_TSS_Central_20230529_0009 | DU00002038680 |  |  | 2023-07-31 | 2023-07-25 |  | Tower | Tower | 77 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x3 | 12
4080R | KG REPOH | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038681 | [6 empty] | Land site
1368A | Tmn Sri Muda | Central |  | Modernization |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-06-17 | 2023-07-05 |  | 2023-07-09 |  | Closed | 2023-07-13 | 2023-07-18 | E//Razif | 2023-07-18 | CelcomDigi_RANMW_YPTT_TSS_Central_20230620_0003 | DU00002038682 |  |  | 2023-08-15 | 2023-08-02 |  | In-Building System | 6m RT (Minimast) | 10 | Add R9264M M1821 x5 + R8862A S2601 x2,Dismantle R8894E M1821(A8A) x3 |  | 13
3459C | Tower 3 Podium IB-2 | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-10-27 | 2023-10-30 |  | 2023-11-07 |  | Closed | 2023-11-08 | 2024-12-24 | E//Nazrul | 2024-12-24 | CelcomDigi_RAN_GTSB_TSS_Central_20231028 | DU00002038683 |  |  | 2025-09-26 | 2025-09-24 |  | Portables BTS | In-building system |  | Add R8862A S2100 x3+R8862A S2601 x1+R8892N M1821 x1,Dismantle R8892E M1821(BAA) x1++R8881 S2100 x3+
4752B | Bendang Rawa | Northern |  | Maintain USP MOCN | Modernization->Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-14 |  | 2023-06-16 |  | Closed | 2023-07-04 | 2023-07-15 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-YPTT-TSS-Northern-20230606-0017 | DU00002038684 | [5 empty] | Tower | 60m 3 Legged | 60
1795H | IDCC Shah Alam Indoor | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038685 | [6 empty] | Rooftop
2680B | Taman industry Alam Jaya | Central |  | Modernization |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-31 | 2023-06-01 |  | 2023-06-07 |  | Closed | 2023-06-11 | 2023-07-12 | E//Razif | 2023-07-12 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002038686 |  |  | 2023-07-03 | 2023-06-28 |  | In-Building System | 3m Bipod (RT) | 5 | Add R9264M M1821 x4,Dismantle R9224E M1821(AAB) x4 |  | 3
4200B | Tmn Derga Jaya | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-06-06 | 2023-06-23 |  | 2023-06-26 |  | Closed | 2023-06-28 | 2023-07-27 | E//Hazida | 2023-07-27 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002038687 |  |  | 2023-08-30 | 2023-08-29 |  | Tower | Tower | 60m | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x4 | 13
2299A | Taman Desa Gemilang Gombak | Central |  | Modernization |  | 2023Q4 | CR | Datasco | 4.6 TSSR Approved |  | 2023-07-07 | 2023-08-08 |  | 2023-08-15 |  | Closed | 2023-08-16 | 2023-08-17 | CD//Sapian | 2023-08-17 | CelcomDigi_RAN_Datasco_TSS_Central_20230707_0031 | DU00002038688 |  |  | 2023-08-29 | 2023-08-24 |  | Lampole | 30m Monopole | 24 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3
4463A | Bandar Kamunting Shoplot | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-31 | 2023-06-01 |  | 2023-06-07 |  | Closed | 2023-06-22 | 2023-07-15 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-GCI-TSS-Northern-20230601-0023 | DU00002038689 |  |  | 2023-08-03 | 2023-07-22 |  | Pole | 6m RT (Boom) | 6 | Add A9732 M1821 x3,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8862A S2100(A6A) x4+R8882 S2600(B4A) x1 | 123
1798B | Gombak Utara | Central |  | Modernization |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-07-07 | 2023-07-18 |  | 2023-07-21 |  | Closed | 2023-07-25 | 2023-07-27 | E//Kok Keen | 2023-07-27 | CelcomDigi_RAN_Datasco_TSS_Central_20230707_0031 | DU00002038690 |  |  | 2023-08-09 | 2023-08-07 |  | Pole | 3m Bipod (RT) | 4 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3++
4137B | SG KAYU ARA (PDC PBTS) | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-06 | 2023-05-11 |  | 2023-05-11 |  | Closed | 2023-05-16 | 2023-05-25 | CD//Affendi | 2023-05-18 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0014 | DU00002038691 |  |  | 2023-07-08 | 2023-07-05 |  | Monopole | 25m pBTS | 24 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8881 S2100 x3
1694B | Puncak Alam Highway 3(ZED) | Central |  | Modernization |  | 2023Q3 | AI | YPTT | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-06 |  | 2023-05-09 |  | Closed | 2023-05-12 | 2023-07-13 | E//Razif | 2023-07-13 | CelcomDigi_RAN_YPTT_TSS_20230505_0002 | DU00002038692 |  |  | 2023-07-13 | 2023-07-10 |  |  | 60m 3 Legged Tower | 60 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2601 x3,Dismantle R8882-GUL1812 x2+R8862A S2100(A6A) x2 | 12
4036A | Rentokil | Northern |  | Modernization |  | 2023Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-23 |  | 2023-05-26 |  | Closed | 2023-05-30 | 2023-07-28 | E//Hazida | 2023-07-28 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0015 | DU00002038693 |  |  | 2023-09-13 | 2023-09-11 |  | Pole | 60m 4 Legged Tower | 6 | Add R9264M M1821 x6 + R8862A S2601 x2,Dismantle R8894E M1821(A8A) x4 |  | 123
4675C | Jalan Transfer | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-18 |  | 2023-05-22 |  | Closed | 2023-05-29 | 2023-06-12 | E//Hazida | 2023-06-12 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0015 | DU00002038694 |  |  | 2023-08-25 | 2023-08-24 |  | Wall mount boom | 3m Boom (RT) | 3 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 1
2434A | Bdr Tasik Puteri (Celcom) | Central |  | Modernization |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-05-16 | 2023-06-03 |  | 2023-06-03 |  | Closed | 2023-06-06 | 2023-10-02 | E//Kok Keen | 2023-10-02 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230428_0015 | DU00002038695 |  |  | 2023-11-21 | 2023-11-15 |  | Tower | 60m 3 Legged Tower | 40m | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8894E M1821(A8A) x3 |  | 13
1899B | KKB Town (TMB) | Central |  | Modernization |  | 2023Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2023-10-04 | 2023-10-05 |  | 2023-10-09 |  | Closed | 2023-10-13 | 2023-11-15 | E//Kok Keen | 2023-11-10 | CelcomDigi_RAN_AllStar_TSS_Central_20231005 | DU00002038696 |  |  | 2024-02-23 | 2024-02-03 |  | Tower | 76m Tower | 70 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
4946B | Sg Baharu (Tele) | Northern |  | Modernization |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-06-12 | 2023-06-13 |  | 2023-06-16 |  | Closed | 2023-06-21 | 2023-07-27 | E//Hazida | 2023-07-27 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230613-0025 | DU00002038697 |  |  | 2023-09-10 | 2023-08-29 |  | Tower | Tower | 50 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8860E-GU908 x1+R8882-GUL1812 x2+R8882 S1800(B) x1+R8854D S2100(A4A) x3 | 23
1019A | Selayang Telemart | Central |  | Modernization |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-07-05 | 2023-07-18 |  | 2023-07-21 |  | Closed | 2023-08-11 | 2023-09-07 | E//Kok Keen | 2023-08-16 | CelcomDigi_RAN_YPTT_TSS_Central_20230707_0013 | DU00002038698 |  |  | 2023-09-13 | 2023-09-12 |  | Pole | 3m RT (Wall Mounted Pole) | S1S2S3: 11m & S4: 10m | Add R9264M M1821 x7,Dismantle R8894E M1821(A8A) x5 |  | 124
2303A | Genting Permai Park & Resort | Central |  | Modernization |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2024-01-09 | 2023-07-28 |  | 2024-01-16 |  | Closed | 2023-08-25 | 2023-12-05 | E//Kok Keen | 2023-08-25 | CelcomDigi_RAN_Magicell_TSS_Central_20230727 | DU00002038699 |  |  | 2024-03-27 | 2024-02-24 |  | Tower | 60m 4 Legged Tower | 95 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R9224E M1821(AAB) x3 | 13
3823B | Arena of Stars | Central |  | Remote MOCN | Modernization->Remote MOCN | 2023Q4 | AI | GTSB | 14.3 Drop (Done Survey + TSSR) |  | 2023-07-24 | 2023-07-25 |  | 2023-07-31 |  | Closed | 2023-09-27 |  | E//Nazrul |  | CelcomDigi_RAN_GTSB_TSS_Central_20230725 | DU00002038700 | [5 empty] | Portables BTS | In-building system | IBC SURVEY | Reuse exsiting RRU
4113B | Kampung Permatang Bendak | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-19 |  | 2023-05-24 |  | Rectificating | 2023-06-07 | 2023-06-21 | CD//Shukri | 2023-06-21 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0015 | DU00002038701 |  |  | 2023-07-05 | 2023-07-04 |  | Pole | 3m Boom (RT) | 6m | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8882 S2600(B4A) x2+R9224E M1821(AAB) x5 | 23
4651B | Alor Merah | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-06-08 | 2023-06-12 |  | 2023-06-19 |  | Closed | 2023-06-26 | 2023-07-26 | E//Hazida | 2023-07-26 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002038702 |  |  | 2023-08-29 | 2023-08-26 |  | Monople Tree | 30m Monopole Tree |  | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3
2604A | Tmn Daya Meru (TM) -132 | Central |  | Modernization |  | 2023Q3 | XH | Magicell | 4.6 TSSR Approved |  | 2023-08-03 | 2023-08-04 |  | 2023-08-08 |  | Closed | 2023-08-10 | 2023-08-18 | E//Razif | 2023-08-10 | CelcomDigi_RAN_Magicell_TSS_Central_20230804 | DU00002038703 |  |  | 2024-01-31 | 2024-01-15 |  | Tower | Tower | 75M | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
1601B | Jln Anggerik Vanilla | Central |  | Modernization |  | 2023Q3 | YZ | AllStar | 4.6 TSSR Approved |  | 2023-05-07 | 2023-05-11 |  | 2023-05-22 |  | Closed | 2023-05-23 | 2023-08-04 | CD//Norhaliza | 2023-08-04 | CelcomDigi_RANMW_Allstar_TSS_Central_20230508_0001 | DU00002038704 |  |  | 2023-06-20 | 2023-06-19 |  | H-bracket pole | 3m Boom (RT) | 6 | Add R9264M M1821 x2+A9732 M1821 x2,Dismantle R9224E M1821(AAB) x4 | 23
4583A | Kuala Sepetang (Maxis) RCC | Northern |  | Modernization |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-06-12 | 2023-06-16 |  | 2023-06-20 |  | Closed | 2023-07-03 | 2023-07-15 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230613-0025 | DU00002038705 |  |  | 2023-08-09 | 2023-07-22 |  | Tower | 60m 3 Legged Tower | 80m | Add R9264H M901821 x2 + R9264M M1821 x1 + R8862A S2601 x2,Dismantle R8882-GUL1812 x1
4481C | Thai Pak Koong | Northern |  | Modernization |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦nok,site onwer not allow to add AAU on the structure for loading issue | 2023-05-09 | 2023-05-10 |  | 2023-05-12 |  | Closed | 2023-05-22 | 2023-07-07 | E//Hazida | 2023-07-06 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0014 | DU00002038706 | NIC_S1_Change MM to BI_loading issue_EDGEPOINT INFRA |  | 2023-08-28 | 2023-08-18 |  | Pole | 3m Boom (RT) | 4 | Add R9264M M1821 x1+R9264H M901821 x3+R8862A S2601 x1,Dismantle R8894E M1821(A8A) x3 |  | 1
4165B | Jln Lembah Permai | Northern |  | Modernization |  | 2023Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-05-01 | 2023-05-03 |  | 2023-05-06 |  | Closed | 2023-05-09 | 2023-07-18 | CD//Affendi | 2023-05-10 | Celcom Digi_RAN-GTSB-TSS-Northern-20230502-0012 | DU00002038707 |  |  | 2023-08-01 | 2023-08-01 |  | Tower | 30m RDS | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
2531A | Puas Puncak Alam 2A | Central |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-05-27 | 2023-06-01 |  | 2023-06-06 |  | Closed | 2023-06-06 | 2023-07-12 | E//Razif | 2023-07-12 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002038708 |  |  | 2023-07-06 | 2023-07-04 |  | Tower | 45m Tower | 49 | Add A9732 M1821 x3,Dismantle R8854E S1800(A6A) x3+R8854D S2100(A4A) x3 | 123
1255B | Tesco Extra Outdoor | Central |  | Modernization |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-05-15 | 2023-05-23 |  | 2023-05-26 |  | Closed | 2023-05-29 | 2023-07-28 | E//Razif | 2023-07-28 | CelcomDigi_RAN_Datasco_TSS_Central_20230517_0022 | DU00002038709 |  |  | 2023-07-08 | 2023-07-05 |  | H-bracket pole | 3m Bipod (RT) | 7m | Add R9264M M1821 x5,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3 |  | 23
4918A | Jelutong BB | Northern |  | Modernization |  | 2023Q3 | MH | GTSB | 4.6 TSSR Approved |  | 2023-04-28 | 2023-05-11 |  | 2023-05-17 |  | Closed | 2023-05-19 | 2023-07-07 | E//Hazida | 2023-07-06 | Celcom Digi_RAN-GTSB-TSS-Northern-20230502-0012 | DU00002038710 |  |  | 2023-07-13 | 2023-07-13 |  | BillBoard | Billboard |  | Add R9264M M1821 x5 + R8862A S2601 x2,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 23
2431A | Bangunan Sultan Sulaiman | Central |  | Modernization |  | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-06-26 | 2023-07-12 |  | 2023-07-20 |  | Closed | 2023-07-22 | 2023-07-26 | E//Zulakmar | 2023-07-26 | CelcomDigi_RANMW_YPTT_TSS_Central_20230627_0007 | DU00002038711 |  |  | 2023-08-24 | 2023-08-21 |  | In-Building System | 6m Unipole RT | 3m | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8894E M1821(A8A) x3 |  | 13
1051C | BB Selayang | Central |  | Modernization |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-07-21 | 2023-07-18 |  | 2023-07-21 |  | Closed | 2023-07-27 | 2023-07-28 | E//Kok Keen | 2023-07-28 | CelcomDigi_RAN_YPTT_TSS_Central_20230721 | DU00002038712 |  |  | 2023-08-10 | 2023-08-09 |  | Lampole | 24m Lampole | 24M | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
2639A | Hulu Rening | Central |  | Modernization |  | 2023Q4 | SS | Futong | 4.6 TSSR Approved |  | 2023-06-19 | 2023-06-20 |  | 2023-06-22 |  | Closed | 2023-06-23 | 2023-06-28 | E//Kok Keen | 2023-06-28 | CelcomDigi_RAN_Futong_TSS_Central_20230620_0002 | DU00002038713 |  |  | 2023-07-17 | 2023-07-13 |  | Tower | 76m 4 Legged Tower | 78 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
3778A | Jalan Tebuk Sri Makmur | Central |  | Modernization |  | 2023Q4 | HQ 1 | Magicell | 4.6 TSSR Approved |  | 2023-06-06 | 2023-06-13 |  | 2023-06-15 |  | Closed | 2023-06-17 | 2023-07-26 | E//Razif | 2023-07-26 | CelcomDigi_RAN_Magicell_TSS_Central_20230607_0012 | DU00002038714 |  |  | 2023-07-21 | 2023-07-18 |  | Tower | Tower | 60 | Add A9732 M1821 x1 + R9264M M1821 x2 + R8862A S2601 x3,Dismantle R8894E M1821(A8A) x3 | 1
2733A | Concorde Hotel SA IB | Central |  | Modernization |  | 2023Q4 | CR | Datasco | 4.6 TSSR Approved |  | 2023-08-08 | 2023-08-04 |  | 2023-08-08 |  | Closed | 2023-09-07 | 2023-09-12 | E//Nazrul | 2023-09-11 | CelcomDigi_RAN_Datasco_TSS_Central_20230808 | DU00002038715 |  |  | 2024-01-24 | 2024-01-22 |  |  | In-building system | IBC | Add + R8862A S1800 x2 + R8862A S2100 x2,Dismantle R8882-GUL1812 x2
4676C | Mr Diy Balik Pulau | Northern |  | Modernization |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-12 |  | 2023-05-16 |  | Closed | 2023-05-22 | 2023-07-06 | E//Hazida | 2023-07-05 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0014 | DU00002038716 |  |  | 2023-07-13 | 2023-07-12 |  | Monopole | Land site | 31 | Add R9264H M901821 x4,Dismantle R9224E M1821(AAB) x3
1597H | 99 Speedmart Bdr Baru Kundang | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038717 | [6 empty] | Small Cell
1677H | 99 Speedmart Sekinchan 2 | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038718 | [6 empty] | Small Cell
4675A | Mergong Barrage | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-31 | 2023-06-06 |  | 2023-06-12 |  | Closed | 2023-06-15 | 2023-07-26 | E//Hazida | 2023-07-26 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002038719 |  |  | 2023-08-29 | 2023-08-29 |  | Rooftop | 6m RT (Boom) | 10 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2,Dismantle R8894E M1821(A8A) x3 | 1
3883B | Jalan 21 Selayang Baru | Central |  | Modernization |  | 2023Q4 | SS | YPTT | 4.6 TSSR Approved |  | 2023-10-25 | 2023-10-30 |  | 2023-11-02 |  | Closed | 2023-11-03 | 2023-11-07 | E//Kok Keen | 2023-11-06 | CelcomDigi_RAN_YPTT_TSS_Central_20231028 | DU00002038720 |  |  | 2023-11-20 | 2023-11-18 |  | H-bracket pole | 3m Bipod (RT) | 3 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8862A S2601(A6A) x1+R8894E M1821(A8A) x4 | 13
2541A | GSkm14 | Central |  | Modernization |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-06-21 | 2023-07-05 |  | 2023-07-08 |  | Closed | 2023-07-10 | 2023-07-25 | E//Kok Keen | 2023-07-18 | CelcomDigi_RANMW_Magicell_TSS_Central_20230622_0008 | DU00002038721 |  |  | 2023-10-20 | 2023-10-18 |  | Monople Tree | 30m Monopole | 24m | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3++
4022A | Lahat Court Apartment | Northern |  | Modernization |  | 2023Q3 | MH | GTSB | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-09 |  | 2023-05-12 |  | Closed | 2023-05-17 | 2023-05-25 | CD//Affendi | 2023-05-18 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0015 | DU00002038722 |  |  | 2023-08-17 | 2023-08-16 |  | Pole | 6m RT (Boom) | 7 | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8882 S1800(B) x2+R8882 S1800B x1+R8882 S1800B(B6B) x3+R8881 S2100 x3 |  | 2
4248C | SSK Furniture Taiping | Northern |  | Modernization |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-28 | 2023-06-15 |  | 2023-06-17 |  | Closed | 2023-06-20 | 2023-07-15 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230529-0020 | DU00002038723 |  |  | 2023-07-27 | 2023-07-22 |  | Unipole | 6m Unipole RT | 6 | Add R9264H M901821 x4,Dismantle R8894E M1821(A8A) x4
1685C | Tateyama Auto 2 (REL) | Central |  | Modernization |  | 2023Q4 | HQ 6 | GTSB | 4.6 TSSR Approved |  | 2023-05-22 | 2023-05-24 |  | 2023-05-30 |  | Closed | 2023-05-31 | 2023-07-18 | E//Razif | 2023-07-18 | CelcomDigi_RAN_GTSB_TSS_Central_20230523_0025 | DU00002038724 |  |  | 2023-07-07 | 2023-07-05 |  | Lampole | Land site | 19m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1326H | 99 Speedmart DESA COALFIELDS | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038725 | [6 empty] | Small Cell
1162A | Kg Baru Tiram Buruk | Central |  | Modernization |  | 2023Q4 | HQ 6 | AllStar | 4.6 TSSR Approved |  | 2023-06-01 | 2023-06-06 |  | 2023-06-08 |  | Closed | 2023-06-12 | 2023-07-27 | E//Zulakmar | 2023-07-27 | CelcomDigi_RAN_AllStar_TSS_Central_20230606_0011 | DU00002038726 |  |  | 2023-07-09 | 2023-07-08 |  | Tower | 45m 4 Legged Tower | 45 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x3,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x2+R8862A S2100(A6A) x4 | 2
3588C | Surau Taman Widuri | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-25 | 2023-04-27 |  | 2023-05-03 |  | Closed | 2023-05-04 | 2023-06-03 | E//Kok Keen | 2023-05-30 | CelcomDigi_RAN_Datasco_TSS_Central_20230426_0017 | DU00002038727 |  |  | 2023-06-19 | 2023-06-17 |  | Lampole | 24m Lampole | 36 | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8892E M1821(BAA) x3 |  | 1
4092A | Beach Street | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-04-29 | 2023-05-08 |  | 2023-05-10 |  | Closed | 2023-05-13 | 2023-05-25 | CD//Affendi | 2023-05-16 | Celcom Digi_RAN-GTSB-TSS-Northern-20230502-0012 | DU00002038728 |  |  | 2023-08-22 | 2023-08-17 |  | Wall mount boom | 3m Boom (RT) | N/A | Add R9264M M1821 x3,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x2+R8892E M1821(BAA) x1
4012A | Prime Plaza | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-31 |  | 2023-06-02 |  | Closed | 2023-06-06 | 2023-06-13 | E//Hazida | 2023-06-13 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0015 | DU00002038729 |  |  | 2023-09-12 | 2023-09-12 |  | H-bracket pole | 3m Boom (RT) | 16 | Add A9732 M1821 x1 + R9264M M1821 x2,Dismantle R8882-GUL1812 x2+R8882 S1800B(B6B) x3+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3 | 3
4295B | Taman Seri Ampang | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-06-06 | 2023-06-01 |  | 2023-06-06 |  | Closed | 2023-06-13 | 2023-07-26 | E//Hazida | 2023-07-26 | Celcom Digi_RAN-GCI-TSS-Northern-20230607-0024 | DU00002038730 |  |  | 2023-08-30 | 2023-08-29 |  | Monople Tree | 30m Monopole | 40 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
1353C | Surau Al-Falah Kundang | Central |  | Modernization |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-08 |  | 2023-05-10 |  | Closed | 2023-05-12 | 2023-05-25 | E//Kok Keen | 2023-05-25 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230428_0015 | DU00002038731 |  |  | 2023-06-11 | 2023-06-08 |  | Lampole | 24m Lampole | 24 | Add R9264H M901821 x3,Dismantle R9224E M1821(AAB) x3
4063Z | KGKURNIA | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038732 | [6 empty] | Land site
1267H | 99 Speedmart PRIMA SELAYANG | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038733 | [6 empty] | Small Cell
4156Z | Kg Ulu Mengkuang | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038734 | [6 empty] | Land site
3750A | UITM Kejuruteraan | Central |  | Modernization |  | 2023Q4 | HQ 6 | GTSB | 4.6 TSSR Approved |  | 2023-05-31 | 2023-06-06 |  | 2023-06-12 |  | Closed | 2023-06-14 | 2023-07-18 | E//Razif | 2023-07-18 | CelcomDigi_RAN_GTSB_TSS_Central_20230601_0026 | DU00002038735 |  |  | 2023-09-21 | 2023-09-18 |  |  | 30m Monopole | 30 | Add R9264M M1821 x5 + R8862A S2601 x2,Dismantle R9224E M1821(AAB) x3 |  | 23
1203B | SetiaDamai(Stealth) | Central |  | Modernization |  | 2023Q3 | YZ | Magicell | 4.6 TSSR Approved |  | 2023-05-12 | 2023-05-18 |  | 2023-05-21 |  | Closed | 2023-06-07 | 2023-07-28 | CD//Nik Ashraf | 2023-07-27 | CelcomDigi_RANMW_Magicell_TSS_Central_20230517_0002 | DU00002038736 |  |  | 2023-08-19 | 2023-08-17 |  | Lampole | 24m Pylon | 13 | Add R9264H M901821 x3,Dismantle R8882 S1800(B) x3+R8862A S2100(A6A) x3
1787B | Karak HW KM 33.9 | Central |  | Modernization |  | 2023Q4 | HQ 6 | Magicell | 4.6 TSSR Approved |  | 2023-07-06 | 2023-07-10 |  | 2023-07-13 |  | Closed | 2023-07-14 | 2023-07-17 | E//Kok Keen | 2023-07-17 | CelcomDigi_RAN_Magicell_TSS_Central_20230707_0020 | DU00002038737 |  |  | 2023-08-10 | 2023-08-09 |  | Tower | 76m Tower | 70 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8892E M1821(BAA) x3
4457A | Kamunting Industry | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-25 | 2023-05-30 |  | 2023-06-02 |  | Closed | 2023-06-08 | 2023-07-15 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-GCI-TSS-Northern-20230526-0021 | DU00002038738 |  |  | 2023-07-28 | 2023-07-22 |  | Monopole | 30m Monopole | 30 | Add R9264H M901821 x3,Dismantle R8860E-GU908 x1+R8882-GUL1812 x3+R8840-U216 x3
4682C | Menara IJM Land | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-06-14 | 2023-06-23 |  | 2023-06-28 |  | Closed | 2023-07-05 | 2023-07-14 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0014 | DU00002038739 |  |  | 2023-07-26 | 2023-07-18 |  | In-Building System | 3m Bipod (RT) | 8 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8862A S1800(B6A) x4+R8854D S2100(A4A) x4+R8854 S2600(A4A) x1 | 123
2761A | Jln Hulu Genting 2 | Central |  | Modernization |  | 2023Q4 | SS | Futong | 4.6 TSSR Approved |  | 2023-06-28 | 2023-08-15 |  | 2023-08-18 |  | Closed | 2023-08-21 | 2023-08-24 | E//Kok Keen | 2023-08-24 | CelcomDigi_RANMW_Futong_TSS_Central_20230630_0005 | DU00002038740 |  |  | 2023-09-15 | 2023-09-12 |  | Tower | 60m 4 Legged Tower | 60 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle R8860E-GU908 x2+R8862A S1800(B6A) x3+R8892E M1821(BAA) x3
3289B | Taman Inai | Central |  | Modernization |  | 2023Q2 | HQ 6 | Datasco | 4.6 TSSR Approved |  | 2023-04-17 | 2023-04-25 |  | 2023-05-08 |  | Closed | 2023-05-16 | 2023-08-03 | E//Kok Keen | 2023-08-02 | CelcomDigi_RAN_Datasco_TSS_Central_20230418_0013 | DU00002038741 |  |  | 2023-07-11 | 2023-05-30 |  | Unipole | 3m Boom (RT) | 9 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8882 S1800B(B6B) x3+R8881 S2100 x3 |  | 1
3289C | Taman Seri Cahaya (REL) | Central |  | Modernization |  | 2023Q3 | HQ 6 | GTSB | 4.6 TSSR Approved |  | 2023-05-16 | 2023-06-16 |  | 2023-06-20 |  | Closed | 2023-06-23 | 2023-07-04 | E//Razif | 2023-07-04 | CelcomDigi_RAN_GTSB_TSS_Central_20230517_0024 | DU00002038742 |  |  | 2023-07-05 | 2023-07-05 |  | Lampole | 3m Bipod (RT) | 5 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 |  | 1
4056Z | KG TJG LENGKONG | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038743 | [6 empty] | Land site
4993C | Balai Polis Dato Keramat | Northern |  | Modernization |  | 2023Q3 | SM | YPTT | 4.6 TSSR Approved |  | 2023-05-04 | 2023-05-15 |  | 2023-05-17 |  | Closed | 2023-05-22 | 2023-05-29 | E//Hazida | 2023-05-29 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0008 | DU00002038744 |  |  | 2023-09-13 | 2023-08-29 |  | Pole | 3m Boom (RT) | 7m | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8894E M1821(A8A) x3 |  | 3
4404C | Desa Permai Indah (REL) | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-06 |  | 2023-05-08 |  | Closed | 2023-05-09 | 2023-05-25 | CD//Shamsul | 2023-05-11 | Celcom Digi_RAN-GCI-TSS-Northern-20230502-0011 | DU00002038745 |  |  | 2023-07-05 | 2023-06-23 |  |  | 3m Bipod (RT) | 5 | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x4 | 123
4810M | Armenian Street Micro | Northern |  | MOCN As-Is |  | 2023Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038746 | [6 empty] | Micro Cell
1690H | 99 Speedmart Sg Gulang Gulang | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038747 | [6 empty] | Rooftop
2593B | Saujana Putra LP | Central |  | Modernization |  | 2023Q3 | AI | Solusi | 4.6 TSSR Approved |  | 2023-05-15 | 2023-06-07 |  | 2023-06-12 |  | Closed | 2023-06-12 | 2023-06-26 | E//Razif | 2023-06-26 | CelcomDigi_RANMW_Solusi_TSS_Central_20230511_0001 | DU00002038748 |  |  | 2023-07-03 | 2023-06-28 |  | Lampole | 20m Lampole | 20m | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3++
4002B | Jalan Sg Pinang | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-17 |  | 2023-05-19 |  | Closed | 2023-05-23 | 2024-12-16 | E//Hazida | 2024-12-16 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0015 | DU00002038749 |  |  | 2023-06-26 | 2023-06-25 |  | Pole | 3m Bipod (RT) | 6 | Add A9732 M1821 x3 + R9264H M901821 x1,Dismantle R8862A S2601(A6A) x1+R8894E M1821(A8A) x4+R9224E M1821(AAB) x1 | 123
1094A | Bt 12 Jln Kapar | Central |  | Modernization |  | 2023Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-28 | 2023-04-29 |  | 2023-05-03 |  | Closed | 2023-05-05 | 2023-06-06 | CD//Tee | 2023-05-15 | CelcomDigi_RAN_GTSB_TSS_20230505_0023 | DU00002038750 |  |  | 2023-06-19 | 2023-06-19 |  |  | 30m Monopole Tree | 45 | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x3+R9224E M1821(AAB) x2 | 123
4764A | Lubok Peringgi | Northern |  | Modernization |  | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-05-30 | 2023-06-10 |  | 2023-06-13 |  | Closed | 2023-06-15 | 2023-07-26 | E//Hazida | 2023-07-26 | Celcom Digi_RAN-YPTT-TSS-Northern-20230531-0015 | DU00002038751 |  |  | 2023-08-30 | 2023-08-29 |  | H-bracket pole | 3m Bipod (RT) | 2 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 3
4140B | Bukit Jambul Indah (PDC PBTS) | Northern |  | Modernization |  | 2023Q3 | YZ | YPTT | 4.6 TSSR Approved |  | 2023-05-04 | 2023-05-10 |  | 2023-05-12 |  | Closed | 2023-05-15 | 2023-05-22 | CD//Affendi | 2023-05-17 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0008 | DU00002038752 |  |  | 2023-06-25 | 2023-06-25 |  | Lampole | 25m pBTS | 25 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x2+R8882 S1800B(B6B) x1+R8894E M1821(A8A) x3
4038C | Seri Larut | Northern |  | Modernization |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-06-08 | 2023-06-21 |  | 2023-06-26 |  | Closed | 2023-07-03 | 2023-07-17 | E//Hazida | 2023-07-15 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230612-0024 | DU00002038753 |  |  | 2023-07-27 | 2023-07-26 |  | In-Building System | 6m Unipole RT | 5 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 2
4230C | Imperial Residence | Northern |  | Modernization |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-12 |  | 2023-05-15 |  | Closed | 2023-05-17 | 2023-05-24 | CD//Affendi | 2023-05-18 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0014 | DU00002038754 |  |  | 2023-07-06 | 2023-07-05 |  | Wall mount boom | 3m Bipod (RT) | 2m | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x2 |  | 2
3658B | Pangsapuri Impian Sentosa | Central |  | Modernization |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-29 |  | 2023-05-31 |  | Closed | 2023-05-31 | 2023-06-17 | CD//Nik Ashraf | 2023-06-16 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002038755 |  |  | 2023-07-05 | 2023-06-28 |  | H-bracket pole | 3m Bipod (RT) | 6 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x3+R8854 S2600(A4A) x3 | 123
2473A | Kg Ijok | Central |  | Modernization |  | 2023Q3 | HQ 6 | GTSB | 4.6 TSSR Approved |  | 2023-04-27 | 2023-05-03 |  | 2023-05-06 |  | Closed | 2023-05-10 | 2023-06-06 | CD//Syafiq | 2023-05-18 | CelcomDigi_RAN_GTSB_TSS_Central_20230428_0022 | DU00002038756 |  |  | 2023-06-11 | 2023-06-11 |  | Tower | Tower | 60m | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3
4119H | MIKI PHOTO AND TELECOMMUNICATION | Northern |  | MOCN As-Is |  | 2023Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038757 | [6 empty] | Small Cell
1759H | 99 Speedmart Pelangi Seri Alam | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038758 | [6 empty] | Small Cell
3828B | Valley Wing Hotel | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-07-24 | 2023-07-25 |  | 2023-07-31 |  | Closed | 2023-07-31 | 2023-07-31 | E//Nazrul | 2023-07-31 | CelcomDigi_RAN_GTSB_TSS_Central_20230725 | DU00002038759 |  |  | 2025-12-01 | 2025-11-25 |  | Portables BTS | In-building system | IBC | Add R8862A S2100 x3
1693B | Puncak Alam Highway 2 (ZED) | Central |  | Modernization |  | 2023Q3 | IE | Magicell | 4.6 TSSR Approved |  | 2023-05-15 | 2023-05-22 |  | 2023-05-24 |  | Closed | 2023-05-29 | 2023-06-28 | CD//Tee | 2023-06-20 | CelcoDigi_RAN_Magicell_TSS_Central_20230517_0009 | DU00002038760 |  |  | 2023-08-04 | 2023-08-04 |  | Tower | 60m 4 Legged Tower | 61 | Add A9732 M1821 x2 + R9264M M1821 x2,Dismantle R8894E M1821(A8A) x4 | 23
2724A | Kebun Batu 7 | Central |  | Modernization |  | 2023Q3 | HQ 6 | AllStar | 4.6 TSSR Approved |  | 2023-05-11 | 2023-05-12 |  | 2023-05-15 |  | Closed | 2023-05-17 | 2023-06-27 | E//Razif | 2023-06-27 | CelcomDigi_RAN_Allstar_TSS_Central_20230511_0007 | DU00002038761 |  |  | 2023-06-12 | 2023-06-12 |  | Lampole | 20m Lampole | 30 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
3503A11 | pBTS South Sekinchan | Central |  | Modernization |  | 2023Q4 | SS | YPTT | 4.6 TSSR Approved |  | 2023-07-04 | 2023-07-10 |  | 2023-07-13 |  | Closed | 2023-07-14 | 2023-07-26 | E//Razif | 2023-07-26 | CelcomDigi_RANMW_YPTT_Central_20230706_0007 | DU00002038762 |  |  | 2023-08-05 | 2023-08-04 |  | Watertank | 25m pBTS | 25m | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3
4038A | Air Itam Market | Northern |  | Modernization |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-10 |  | 2023-05-26 |  | Closed | 2023-05-30 | 2023-07-22 | E//Hazida | 2023-07-22 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0014 | DU00002038763 |  |  | 2023-08-17 | 2023-08-17 |  | Pole | 30m Monopole | 2 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x4+R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3
1603B | Taman Sentosa | Central |  | Modernization |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-22 | 2023-06-01 |  | 2023-06-06 |  | Closed | 2023-06-17 | 2023-07-04 | E//Sumitra | 2023-07-04 | CelcomDigi_RANMW_YPTT_TSS_Central_20230508_0002 | DU00002038764 |  |  | 2023-07-08 | 2023-07-05 |  | H-bracket pole | 3m Boom (RT) | 6 | Add R9264M M1821 x5 + R8862A S2601 x2,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 |  | 13
3530C | Precinct 12 Setia Alam | Central |  | Modernization |  | 2023Q3 | HQ 6 | Magicell | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-09 |  | 2023-05-11 |  | Closed | 2023-05-12 | 2023-06-19 | E//Razif | 2023-06-19 | CelcomDigi_RAN_Magicell_TSS_Central_20230508_0007 | DU00002038765 |  |  | 2023-06-17 | 2023-06-14 |  | Lampole | 18m street pole | 24M | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
1895B | Kg Soeharto | Central |  | Modernization |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-05-27 | 2023-05-29 |  | 2023-05-31 |  | Closed | 2023-06-06 | 2023-06-12 | E//Kok Keen | 2023-06-12 | CelcomDigi_RAN_GTSB_TSS_Central_20230529_0010 | DU00002038766 |  |  | 2023-09-08 | 2023-08-03 |  | Tower | 90m 4 Legged Tower | 122 | Add R9264H M901821 x3,Dismantle R8860E-GU908 x1+R8862A S1800(B6A) x2+R8881 S2100 x2++R8881 S2100 x2+
3091C | Genting New Skyway Station (GPO) Macro | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-15 | 2023-07-10 |  | 2023-07-15 |  | Closed | 2023-07-17 | 2023-07-25 | E//Kok Keen | 2023-07-20 | CelcomDigi_RAN_GTSB_TSS_Central_20230616_0029 | DU00002038767 |  |  | 2023-11-16 | 2023-10-23 |  | Tower | 3m Boom (RT) | 3 | Add R9264H M901821 x4 + R8862A S2601 x4,Dismantle R8882 S1800B(B6B) x2+R8862A S1800(B6A) x2+R8854D S2100(A4A) x4
2709C | Hospital Selayang | Central |  | Modernization |  | 2023Q4 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-07-06 | 2023-07-12 |  | 2023-07-17 |  | Closed | 2023-07-22 | 2023-07-26 | E//Kok Keen | 2023-07-26 | CelcomDigi_RAN_YPTT_TSS_Central_20230707_0013 | DU00002038768 |  |  | 2023-12-07 | 2023-12-07 |  | Monopole | Lampole | 45 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2601 x3,Dismantle R9224E M1821(AAB) x3 | 12
3181A | Surau Al-Falah | Central |  | Modernization |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-06-20 | 2023-07-11 |  | 2023-07-14 |  | Closed | 2023-07-20 | 2023-07-21 | E//Kok Keen | 2023-07-21 | CelcomDigi_RANMW_YPTT_TSS_Central_20230622_0004 | DU00002038769 |  |  | 2023-08-16 | 2024-05-25 |  |  | 24m Lampole | 25 | Add A9732 M1821 x2 + R9264M M1821 x1 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x4 | 13
1898B | Proton City (MAXIS) | Central |  | Modernization |  | 2023Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-06-16 | 2023-06-13 |  | 2023-06-15 |  | Closed | 2023-06-22 | 2023-06-28 | E//Kok Keen | 2023-06-28 | Celcomdigi_RAN_Ascentrack_TSS_Central_20230616_0022 | DU00002038770 |  |  | 2023-08-15 | 2023-08-15 |  | Tower | 60m 3 Legged Tower | 60 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2,Dismantle R8892E M1821(BAA) x3 | 2
4005H | Dawood Enterprise | Northern |  | MOCN As-Is |  | 2023Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038771 | [6 empty] | Small Cell
1001Z | LMN BISTARI | Central |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 | AI | GTSB | 14.2 Drop (Done Survey) |  | 2023-06-19 |  |  |  |  | To be Submitted |  |  |  |  | N/A - no need PR for MOCN Decomm | DU00002038772 | [6 empty] | Land site
3230B | Bandar Rimbayu | Central |  | Modernization |  | 2023Q3 | SS | Solusi | 4.6 TSSR Approved |  | 2023-05-15 | 2023-06-30 |  | 2023-07-04 |  | Closed | 2023-07-07 | 2023-07-13 | E//Razif | 2023-07-13 | CelcomDigi_RANMW_Solusi_TSS_Central_20230511_0001 | DU00002038773 |  |  | 2023-11-30 | 2023-11-20 |  | Monople Tree | 30m Monopole | 24m | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
4155H | 99 Speedmart PK TMN KOTA JAYA | Northern |  | MOCN As-Is |  | 2023Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038774 | [6 empty] | Small Cell
3459B | Tower 3 Podium IB | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-10-27 | 2023-11-06 |  | 2023-11-09 |  | Closed | 2023-11-09 | 2024-05-24 | E//Nazrul | 2024-05-23 | CelcomDigi_RAN_GTSB_TSS_Central_20231028 | DU00002038775 |  |  | 2024-04-30 | 2024-03-04 |  |  | In-building system |  | Add + R8862A S1800 x6 + R8862A S2100 x6,Dismantle R8882 S1800(B) x1+R8882 S1800B(B6B) x5
2439A | Sg Leman (KJS) | Central |  | Modernization |  | 2023Q4 | HQ 1 | Magicell | 4.6 TSSR Approved |  | 2023-06-01 | 2023-06-13 |  | 2023-06-15 |  | Closed | 2023-06-17 | 2023-07-27 | E//Zulakmar | 2023-07-27 | CelcomDigi_RAN_Magicell_TSS_Central_20230606_0011 | DU00002038776 |  |  | 2023-07-13 | 2023-07-13 |  | Tower | 60m 4 Legged Tower | 70 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8854D S2100(A4A) x3 |  | 1
1205H | 99 Speedmart PASIR PENAMBANG | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038777 | [6 empty] | Small Cell
1689H | 99 Speedmart PK Tmn Intan Setia | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038778 | [6 empty] | Rooftop
1027A | RSC Hostel | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-05-31 | 2023-06-16 |  | 2023-06-20 |  | Closed | 2023-07-08 | 2023-07-14 | E//Kok Keen | 2023-07-14 | CelcomDigi_RAN_GTSB_TSS_Central_20230601_0026 | DU00002038779 |  |  | 2023-11-29 | 2023-10-17 |  | In-Building System | 6m RT (Wall Mounted Pole) | 5 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R9224E M1821(AAB) x3 | 123
2558B | Tmn Jasa Sg Tua | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-13 |  | 2023-05-19 |  | Closed | 2023-05-19 | 2023-06-06 | E//Kok Keen | 2023-05-22 | CelcomDigi_RAN_GTSB_TSS_Cental_20230511_0024 | DU00002038780 |  |  | 2023-07-03 | 2023-06-27 |  |  | 6m Unipole RT | 8 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8894E M1821(A8A) x3 |  | 3
1679H | 99 Speedmart Hulu Bernam | Central |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038781 | [6 empty] | Small Cell
9017C | Kampung Panglima | Sarawak |  | Modernization |  | 2023Q4 | SH | Magicell | 4.6 TSSR Approved |  | 2023-06-24 | 2023-06-28 |  | 2023-06-30 |  | Closed | 2023-07-04 | 2023-07-18 | E//Hannah | 2023-07-18 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002038782 |  |  | 2023-08-04 | 2023-07-31 |  | Monopole | 30M Rapole | 80 | Add R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3
7188Z | KG PAKALANGAN | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 |  | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002038783 | [6 empty] | Tower
7628B | Fajar Shoplot | Sabah |  | Modernization |  | 2023Q4 | AD | AllStar | 4.6 TSSR Approved |  | 2023-06-14 | 2023-06-30 |  | 2023-07-04 |  | Closed | 2023-07-10 | 2023-07-21 | E//Hannah | 2023-07-20 | Celcom Digi_RAN-Allstar-TSS-Sabah-20230608-0004 | DU00002038784 |  |  | 2023-08-22 | 2023-08-07 |  | In-Building System | 3m RT (Wall Mounted Pole) | 2M | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 12
7671B | Bandar Sri Indah | Sabah |  | Modernization |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-06-13 | 2023-08-25 |  | 2023-08-31 |  | Closed | 2023-09-08 | 2023-09-08 | CD//Ray Amos | 2023-09-07 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007 | DU00002038785 |  |  | 2023-09-12 | 2023-09-09 |  | Monopole | 20m Monopole | 30m | Add A9732 M1821 x2 + R9264M M1821 x1 + R9264H M901821 x1,Dismantle R8862A S1800(B6A) x4+R8854D S2100(A4A) x4 | 12
7010C | Log Pond | Sabah |  | Modernization |  | 2023Q4 | MS | YPTT | 4.6 TSSR Approved |  | 2023-06-24 | 2023-07-10 |  | 2023-07-14 |  | Closed | 2023-07-17 | 2023-07-28 | E//Hannah | 2023-07-25 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002038786 |  |  | 2023-08-13 | 2023-08-07 |  | Tower | Tower | 45 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x5 | 123
7062C | Jalan Limbawan | Sabah |  | Modernization |  | 2023Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2023-05-07 | 2023-05-06 |  | 2023-05-10 |  | Closed | 2023-05-11 | 2023-05-15 | CD//Mohidi Jaan | 2023-05-14 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230508-0005 | DU00002038787 |  |  | 2023-07-18 | 2023-07-14 |  | Lampole | 30m Monopole | 31 | Add R9264H M901821 x3,Dismantle R9224E M1821(AAB) x3
7100R | BUKIT TAJAM | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2025-07-16 |  | 2025-07-16 |  | 2025-07-19 |  | 2025-09-10 | 2025-10-31 | E//Hannah | 2025-09-16 | SQ202506100849 - GTSB / SQ202507010442 - GTSB | DU00002038788 |  |  |  |  | 2025-09-26 |  | Tower
9532A | Pujut 9 | Sarawak |  | Modernization |  | 2023Q4 | BY | South Pacific | 4.6 TSSR Approved |  | 2023-06-16 | 2023-06-16 |  | 2023-06-19 |  | Closed | 2023-06-20 | 2023-07-07 | E//Hannah | 2023-07-04 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230606-0003 | DU00002038789 |  |  | 2023-08-14 | 2023-08-08 |  | Monopole | 30m Monopole | 40m | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x3 | 23
7963A | Luasong | Sabah |  | Modernization |  | 2023Q3 | AD | Futong | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-16 |  | 2023-05-19 |  | Closed | 2023-05-22 | 2023-06-28 | E//Hannah | 2023-06-19 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0004 | DU00002038790 |  |  | 2023-08-13 | 2023-08-02 |  | Tower | Tower | 75 | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x3 |  | 1
7474A | Kg Tumalasak | Sabah |  | Remote MOCN | Modernization->Maintain USP MOCN->Remote MOCN | 2023Q3 | AD | Futong | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-12 |  | 2023-05-18 |  | Closed | 2023-05-18 | 2023-05-22 | CD//Ray Amos | 2023-05-21 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0004 | DU00002038791 | [5 empty] | Tower | Tower | 60
9593A | Jalan Cahaya Miri | Sarawak |  | Modernization |  | 2023Q4 | ZB | Datasco | 4.6 TSSR Approved |  | 2024-03-08 | 2024-03-25 |  | 2024-03-26 |  | Closed | 2024-03-26 | 2024-04-04 | E//Hannah | 2024-04-03 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230608-0007 | DU00002038792 |  |  | 2024-06-21 | 2024-06-06 |  | Lampole | 15m_Rapole | 15 | Add R9264H M901821 x3,Dismantle R8882 S1800B(B6B) x3
7685B | Kabogan | Sabah |  | Modernization |  | 2023Q4 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-12 | 2023-06-14 |  | 2023-06-16 |  | Closed | 2023-06-19 | 2023-06-28 | CD//Mohidi Jaan | 2023-06-28 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0011 | DU00002038793 |  |  | 2023-09-12 | 2023-09-07 |  | Monopole | 30m Monopole | 30 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8854 S2600(A4A) x3+R8894E M1821(A8A) x6 | 123
7362B | Kalabakan Timur SBC | Sabah |  | Modernization |  | 2023Q3 | AD | Futong | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-11 |  | 2023-05-25 |  | Closed | 2023-05-18 | 2023-05-22 | CD//Ray Amos | 2023-05-22 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0004 | DU00002038794 |  |  | 2023-08-01 | 2023-07-27 |  | Tower | Tower | 60 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
7886A | Kota Ayangan | Sabah |  | Modernization |  | 2023Q3 | MS | Datasco | 4.6 TSSR Approved |  | 2023-05-26 | 2023-06-06 |  | 2023-06-13 |  | Closed | 2023-06-16 | 2023-06-24 | E//Hannah | 2023-06-23 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230508-0004 | DU00002038795 |  |  | 2023-07-17 | 2023-07-13 |  | Monopole | 30m Monopole | 30 | Add A9732 M1821 x3,Dismantle R9224E M1821(AAB) x3 | 123
9030A | Santubong Resort | Sarawak |  | Modernization |  | 2023Q4 | SH | Datasco | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-09 |  | 2023-06-26 |  | Closed | 2023-06-28 | 2023-07-24 | E//SoonHo | 2023-07-24 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230608-0007 | DU00002038796 |  |  | 2023-11-04 | 2023-08-10 |  | Tower | Tower | 24 | Add R8852E S9000 x3 + R8894E M1821 x3 + R8862A S2601 x1,Dismantle R8882-GUL1812 x2
7160Z | KM50 Kalabakan-Nabawan | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | AD |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002038797 | [6 empty] | Tower
9108A | Chinese Chamber | Sarawak |  | Modernization |  | 2023Q3 | BY | AllStar | 4.6 TSSR Approved |  | 2023-05-26 | 2023-05-26 |  | 2023-06-13 |  | Closed | 2023-06-14 | 2023-06-30 | E//Hannah | 2023-06-30 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230516-0005 | DU00002038798 |  |  | 2023-08-04 | 2023-07-06 |  | Minimast | 3m RT (Minimast) | 13 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 | 23(S1->S2,S2->S3,S3->S1,rename Sector ID,MM@New S1/S3)
7626B | Kg. Kubang (Celcom) | Sabah |  | Modernization |  | 2023Q4 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-06-28 | 2023-07-21 |  | 2023-07-26 |  | Closed | 2023-07-27 | 2023-08-03 | CD//Jahganathan | 2023-08-03 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230703.xls | DU00002038799 |  |  | 2023-09-22 | 2023-09-13 |  | Tower | 76m 4 Legged Tower | 70M | Add A9732 M1821 x3,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 | 123
9345B | Bkt Orang | Sarawak |  | Modernization |  | 2023Q3 | BY | YPTT | 4.6 TSSR Approved |  | 2023-05-28 | 2023-06-12 |  | 2023-06-15 |  | Closed | 2023-06-15 | 2023-07-07 | E//Hannah | 2023-07-06 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20230529-0004 | DU00002038800 |  |  | 2023-07-21 | 2023-07-13 |  | Monopole | 30m Monopole | 40 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8882 S2600(B4A) x1+R9224E M1821(AAB) x4 | 123
9126B | Taman Sukma | Sarawak |  | Modernization |  | 2023Q4 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-06-19 | 2023-06-28 |  | 2023-07-03 |  | Closed | 2023-07-04 | 2023-07-21 | E//Hannah | 2023-07-20 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 - Copy | DU00002038801 |  |  | 2023-08-11 | 2023-08-08 |  | Tower | 30m Monopole | 36 | Add R9264H M901821 x3,Dismantle R8882 S1800(B) x3+R8862A S2100(A6A) x3
9575B | Long Urun | Sarawak |  | Modernization |  | 2023Q3 | BY | Trintel | 4.6 TSSR Approved |  | 2023-06-12 | 2023-06-17 |  | 2023-06-23 |  | Closed | 2023-06-23 | 2023-07-15 | E//Hannah | 2023-07-14 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230516-0007 | DU00002038802 |  |  | 2023-08-18 | 2023-08-09 |  | Monopole | Tower | 47 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
7930A | Kunak Town | Sabah |  | Modernization |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-06-12 | 2023-06-14 |  | 2023-06-17 |  | Closed | 2023-06-20 | 2023-07-22 | E//Nizar | 2023-07-21 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0010 | DU00002038803 |  |  | 2023-08-28 | 2023-08-23 |  | H-bracket pole | 3m RT (Wall Mounted Pole) | 6m | Add R9264M M1821 x1+A9732 M1821 x3,Dismantle R8894E M1821(A8A) x6 + R8854 S2600(A4A) x2 | 124
9536A | Pujut 2 MP | Sarawak |  | Modernization |  | 2023Q4 | SH | Magicell | 4.6 TSSR Approved |  | 2023-06-20 | 2023-06-21 |  | 2023-06-23 |  | Closed | 2023-06-26 | 2023-07-06 | E//Hannah | 2023-07-06 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002038804 |  |  | 2023-08-03 | 2023-07-17 |  | Monopole | 30m Monopole | 37 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8882 S1800B(B6B) x3+R8840-U216 x3
9072B | Kampung Gita Lama | Sarawak |  | Modernization |  | 2023Q4 | SH | South Pacific | 4.6 TSSR Approved |  | 2023-06-17 | 2023-06-20 |  | 2023-06-24 |  | Closed | 2023-06-26 | 2023-07-06 | E//Hannah | 2023-07-05 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230612-0004 | DU00002038805 |  |  | 2023-08-15 | 2023-08-11 |  | Monopole | 30m Monopole | 35M | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
7066C | Taman Tawau | Sabah |  | Modernization |  | 2023Q4 | MS | YPTT | 4.6 TSSR Approved |  | 2023-06-23 | 2023-06-26 |  | 2023-07-03 |  | Closed | 2023-07-04 | 2023-07-12 | E//Hannah | 2023-07-12 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002038806 |  |  | 2023-08-14 | 2023-07-31 |  | Monopole | 30m Lampole | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
7225Z | Tibow Research Center | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | AD |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002038807 | [6 empty] | Tower
7931A | Hospital Kunak | Sabah |  | Modernization |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-06-14 | 2023-06-19 |  | 2023-06-20 |  | Closed | 2023-06-22 | 2023-07-10 | CD//Ray Amos | 2023-07-10 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0010 | DU00002038808 |  |  | 2023-09-26 | 2023-09-19 |  | Tower | 60m 4 Legged Tower | 61M | Add R9264M M1821 x5,Dismantle R8894E M1821(A8A) x3 |  | 12
7936B | LADANG AUMKAR 1 | Sabah |  | Modernization |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-14 |  | 2023-06-17 |  | Closed | 2023-06-19 | 2023-07-14 | CD//Ray Amos | 2023-07-07 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0010 | DU00002038809 |  |  | 2023-08-28 | 2023-08-23 |  | Tower | 45m 3 Legged Tower | 61 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
9606A | Taman Greenville | Sarawak |  | Modernization |  | 2023Q4 | SH | YPTT | 4.6 TSSR Approved |  | 2023-06-12 | 2023-06-26 |  | 2023-07-03 |  | Closed | 2023-07-05 | 2023-07-18 | E//Hannah | 2023-07-18 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20230613-0007 | DU00002038810 |  |  | 2023-08-25 | 2023-08-15 |  | Tower | 30m Rapole | 30 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 |  | 12
9413A | Jln. Stadium | Sarawak |  | Modernization |  | 2023Q4 | BY | Magicell | 4.6 TSSR Approved |  | 2023-06-21 | 2023-06-26 |  | 2023-06-28 |  | Closed | 2023-07-06 | 2023-07-24 | E//Zulakmar | 2023-07-24 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002038811 |  |  | 2023-09-09 | 2023-09-04 |  | Monople Tree | 30m Monopole | 46 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8882-GUL1812 x3+R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 | 13
7043C | Kg Cina Kunak Jaya 2 | Sabah |  | Modernization |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-06-12 | 2023-06-14 |  | 2023-06-16 |  | Closed | 2023-06-19 | 2023-07-12 | CD//Ray Amos | 2023-07-07 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0010 | DU00002038812 |  |  | 2023-09-03 | 2023-08-23 |  | Monopole | 30m Lampole | 30m | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
7686B | Tanjong Batu | Sabah |  | Modernization |  | 2023Q4 | HQ 2 | YPTT | 4.6 TSSR Approved |  | 2023-06-27 | 2023-07-12 |  | 2023-07-18 |  | Closed | 2023-07-20 | 2023-07-26 | E//Hannah | 2023-07-25 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002038813 |  |  | 2023-08-29 | 2023-07-31 |  | Lampole | 24m Lampole | 24 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
7573B | Kg Wakuba | Sabah |  | Modernization |  | 2023Q4 | AD | Datasco | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-23 |  | 2023-06-27 |  | Closed | 2023-08-17 | 2023-07-11 | E//Hannah | 2023-07-11 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007 | DU00002038814 |  |  | 2023-08-15 | 2023-08-14 |  | Tower | Tower | 50 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R9224E M1821(AAB) x3 |  | 2
9179B | Taman Seberkas | Sarawak |  | Modernization |  | 2023Q3 | BY | AllStar | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦loading issue,AAU cannot install | 2023-05-17 | 2023-06-07 |  | 2023-06-13 |  | Closed | 2023-06-14 | 2023-06-24 | E//Hannah | 2023-06-23 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230516-0005 | DU00002038815 | NIC_S3_Change MM to BI_loading issue_SACOFA SDN BHD |  | 2023-07-26 | 2023-07-14 |  | Monopole | 30m Monopole | 30m | Add R9264M M1821 x6+R8862A S2600 x3,Dismantle R9224E M1821(AAB) x3 | 0 | 123
9079A | Crocodile Farm | Sarawak |  | Modernization |  | 2023Q4 | BY | Datasco | 4.6 TSSR Approved |  | 2023-06-14 | 2023-06-14 |  | 2023-06-19 |  | Rectificating | 2023-06-30 | 2023-07-10 | E//Hannah | 2023-07-10 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230608-0007 | DU00002038816 |  |  | 2023-08-18 | 2023-08-10 |  | Tower | Tower | 60m | Add R8852E S9000 x3 + A9732 M1821 x3 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x4 | 124
7612A | Da Hua Garden | Sabah |  | Modernization |  | 2023Q4 | MS | YPTT | 4.6 TSSR Approved |  | 2023-06-24 | 2023-07-17 |  | 2023-07-21 |  | Rectificating | 2023-07-25 | 2023-07-28 | E//Hannah | 2023-07-28 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002038817 |  |  | 2023-08-07 | 2023-08-02 |  | Tower | 60m 3 Legged Tower | 50 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
9098R | MILE46BTUMYY | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2023Q3 | AI | Magicell | 4.6 TSSR Approved |  | 2025-06-17 |  | 2025-06-17 |  | 2025-07-10 |  | 2025-08-22 | 2025-11-03 | E//John | 2025-09-09 | SQ202506110081-Magicell/SQ202507140221-Magicell | DU00002038818 |  |  |  |  | 2025-09-18 |  | Land site
7768B | Kg. Lanas | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2023Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-06-09 |  |  |  | 2023-06-09 |  | 2023-06-14 | 2023-10-04 | E//Hannah | 2023-06-14 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230608-0007 | DU00002038819 |  | 2023-07-20 missing tx photos and info |  |  | 2025-11-28 |  | Tower
7244C | Kinabutan Besar | Sabah |  | Modernization |  | 2023Q4 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-06-21 | 2023-06-28 |  | 2023-07-03 |  | Closed | 2023-07-05 | 2023-08-28 | E//Hannah | 2023-08-25 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230612-0004 | DU00002038820 |  | No TX Decom TSSR Required (Under upgrade) | 2023-09-05 | 2023-08-15 |  | Tower | 45m Tower | 45m | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x2,Dismantle R8894E M1821(A8A) x4 | 23
7051C | Masjid Quba | Sabah |  | Modernization |  | 2023Q4 | MS | YPTT | 4.6 TSSR Approved |  | 2023-06-17 | 2023-06-28 |  | 2023-07-06 |  | Closed | 2023-07-07 | 2023-07-12 | E//Hannah | 2023-07-12 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002038821 |  |  | 2023-08-13 | 2023-08-05 |  | Monopole | 24m Lampole | 30 | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
9111A | Jalan Sibiyu (SACOFA) | Sarawak |  | Modernization |  | 2023Q3 | BY | YPTT | 4.6 TSSR Approved |  | 2023-05-27 | 2023-06-27 |  | 2023-07-07 |  | Closed | 2023-07-07 | 2023-07-25 | E//Hannah | 2023-07-25 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20230622 | DU00002038822 |  |  | 2023-08-14 | 2023-08-10 |  | Tower | Tower | 60m | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x2,Dismantle R8882-GUL1812 x2+R8882 S1800B(B6B) x3+R8862A S1800(B6A) x1+R8854D S2100(A4A) x3+R8894E M1821(A8A) x1 | 23
7583B | LADANG SERAYA | Sabah |  | Modernization |  | 2023Q3 | AD | Futong | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-20 |  | 2023-05-23 |  | Closed | 2023-05-24 | 2023-06-21 | E//Nizar | 2023-06-21 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0004 | DU00002038823 |  |  | 2023-08-17 | 2023-07-31 |  | Tower | 45m 3 Legged Tower | 76 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 | 2
9127B | Samalaju-Tokuyama | Sarawak |  | Modernization |  | 2023Q3 | BY | Magicell | 4.6 TSSR Approved |  | 2023-05-17 | 2023-05-20 |  | 2023-05-23 |  | Closed | 2023-05-26 | 2023-05-27 | E//Hannah | 2023-05-26 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230518-0010 | DU00002038824 |  |  | 2023-06-30 | 2023-06-26 |  | Pole | 24m Lampole | 15M | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2600 x2,Dismantle R8882 S1800B(B6B) x3+R8854D S2100(A4A) x3 |  | 23
7222Z | Kg Ulu Mosopoh | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038825 | [6 empty] | Land site
9086A | Kuala Baram | Sarawak |  | Modernization |  | 2023Q4 | HQ 1 | Datasco | 4.6 TSSR Approved |  | 2023-06-16 | 2023-07-10 |  | 2023-07-13 |  | Closed | 2023-07-26 | 2023-08-03 | E//Hannah | 2023-08-03 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230608-0007 | DU00002038826 |  |  | 2023-11-29 | 2023-10-06 |  | Tower | 45m 4 Legged Tower | 50 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x4+R8862A S2100(A6A) x3
7638B | Ladang Iman (Celcom) | Sabah |  | Modernization |  | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-06-17 | 2023-07-24 |  | 2023-07-27 |  | Closed | 2023-07-28 | 2023-08-24 | CD//Jahganathan | 2023-07-28 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002038827 |  |  | 2023-09-08 | 2023-08-09 |  | Tower | 76m 4 Legged Tower | 76 | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle R9224E M1821(AAB) x4 |  | 2
7698B | Taman LCN (REL) | Sabah |  | Modernization |  | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-06-18 | 2023-07-18 |  | 2023-07-24 |  | Closed | 2023-07-28 | 2023-07-28 | CD//Mohidi Jaan | 2023-07-28 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002038828 |  |  | 2023-08-11 | 2023-08-05 |  |  | Tower | 30 | Add R9264M M1821 x6,Dismantle R8894E M1821(A8A) x3 |  | 123
7966A | Batu Payung | Sabah |  | Modernization |  | 2023Q4 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-06-13 | 2023-06-16 |  | 2023-06-20 |  | Closed | 2023-07-03 | 2023-07-17 | E//Hannah | 2023-07-07 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230612-0004 | DU00002038829 |  |  | 2023-09-08 | 2023-08-09 |  | Tower | Tower | 76m | Add R9264H M901821 x3 + R9264M M1821 x3 + R8862A S2601 x3,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x2+R8862A S2100(A6A) x3 |  | 123
9046R | BAKUN | Sarawak |  | Maintain USP MOCN(Dismantle Passive) | Maintain USP MOCN(Dismantle Passive)->On Hold->Maintain USP MOCN(Dismantle Passive) | 2023Q3 | HW | Magicell | 4.6 TSSR Approved |  | 2025-06-17 |  | 2025-06-18 |  | 2025-07-10 |  | 2025-08-08 | 2026-01-20 | E//John | 2025-09-19 | SQ202506110081-Magicell/SQ202507140221-Magicell | DU00002038830 |  |  |  |  | 2025-10-09 |  | Land site
9571B | Murun Dam | Sarawak |  | Modernization |  | 2023Q3 | SH | Datasco | 4.6 TSSR Approved |  | 2023-06-15 | 2023-07-03 |  | 2023-07-05 |  | Closed | 2023-07-05 | 2023-07-17 | E//Hannah | 2023-07-14 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230516-0006 | DU00002038831 |  |  | 2023-08-07 | 2023-07-26 |  | Tower | Tower | 80 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
7041R | KG TONGULUN JAYA | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2023Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2025-09-25 |  | 2025-10-13 |  | 2025-10-24 |  | 2025-10-28 | 2025-12-04 | E//Faiz | 2025-11-06 | SQ202509220707 - YPTT | DU00002038832 |  |  |  |  | 2025-11-27 |  | Tower
9028B | Moyan Height | Sarawak |  | Modernization |  | 2023Q4 | SH | South Pacific | 4.6 TSSR Approved |  | 2023-06-16 | 2023-06-23 |  | 2023-06-26 |  | Closed | 2023-06-30 | 2023-07-18 | E//Zulakmar | 2023-07-18 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230612-0004 | DU00002038833 |  |  | 2023-09-26 | 2023-09-24 |  | Tower | 60m 3 Legged Tower | 60M | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x3 | 12
7626A | Bukit 700 Trunk | Sabah |  | Modernization |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-06-16 | 2023-07-27 |  | 2023-08-01 |  | Closed | 2023-08-02 | 2023-08-09 | CD//Jahganathan | 2023-08-02 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007 | DU00002038834 |  |  | 2023-08-22 | 2023-08-14 |  | Tower | Tower | 45 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x2+R8882 S1800B(B6B) x1++R8881 S2100 x3+
7308A9 | pBTS PPR Tmn Sri Semarak (KM) | Sabah |  | Modernization |  | 2023Q4 | MS | YPTT | 4.6 TSSR Approved |  | 2023-06-17 | 2023-07-17 |  | 2023-07-21 |  | Closed | 2023-07-24 | 2023-11-30 | E//Hannah | 2023-11-29 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002038835 |  |  | 2023-08-11 | 2023-07-31 |  | Watertank | 25m pBTS | 24.1 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
9356B | Taman Ria 1 MP | Sarawak |  | Modernization |  | 2023Q3 | BY | AllStar | 4.6 TSSR Approved |  | 2023-05-13 | 2023-05-13 |  | 2023-05-18 |  | Closed | 2023-05-22 | 2023-06-08 | E//Hannah | 2023-06-09 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230516-0005 | DU00002038836 |  |  | 2024-03-20 | 2023-07-04 |  | Monopole | 30m Monopole | 30 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8882 S1800B(B6B) x3+R8854D S2100(A4A) x3 | 23
7964A | Jln Tawau-Semporna | Sabah |  | Modernization |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-06-20 | 2023-07-03 |  | 2023-07-01 |  | Rectificating | 2023-07-10 | 2023-08-02 | E//Hannah | 2023-08-01 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0010 | DU00002038837 |  |  | 2023-09-08 | 2023-08-23 |  | Tower | 76m Tower | 76 | Add R9264M M1821 x4+R8862A S2601 x1,Dismantle R8882-GUL1812 x2+R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 |  | 1
7446A | Bingkor (Celcom) | Sabah |  | Modernization |  | 2023Q3 | MS | Datasco | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-12 |  | 2023-06-15 |  | Closed | 2023-06-19 | 2023-06-26 | CD//Jahganathan | 2023-06-26 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230508-0004 | DU00002038838 |  |  | 2023-07-21 | 2023-07-11 |  | Tower | 60m 4 Legged Tower | 76 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
7221Z | Kg Pemuntarian | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038839 | [6 empty] | Land site
7681B | Berkeley Park | Sabah |  | Modernization |  | 2023Q4 | MS | YPTT | 4.6 TSSR Approved |  | 2023-06-27 | 2023-07-17 |  | 2023-07-21 |  | Rectificating | 2023-07-25 | 2023-07-28 | E//Hannah | 2023-07-28 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002038840 |  |  | 2024-06-18 | 2024-05-27 |  | Monopole | 24m Lampole | 24M | Add R9264H M901821 x3,Dismantle R8882 S1800B(B6B) x3+R8854D S2100(A4A) x3
7132Z | Kg Bigor | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038841 | [6 empty] | Tower
7606A | MTANDRASSY | Sabah |  | Modernization |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-06-17 | 2023-07-07 |  | 2023-07-11 |  | Closed | 2023-07-14 | 2023-07-18 | E//Hannah | 2023-07-17 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007 | DU00002038842 |  |  | 2023-08-29 | 2023-08-12 |  | Tower | 76m 4 Legged Tower | 76 | Add R9264H M901821 x3 + R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3 |  | 123
7068A | Jalan Luangan | Sabah |  | Modernization |  | 2023Q3 | MS | GTSB | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-12 |  | 2023-05-17 |  | Closed | 2023-05-20 | 2023-06-24 | E//Hannah | 2023-07-05 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230508-0005 | DU00002038843 |  |  | 2023-07-18 | 2023-07-14 |  | Tower | 45m 3 Legged Tower | 48m | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 23
9170B | Kampung Semerah Padi | Sarawak |  | Modernization |  | 2023Q4 | BY | Datasco | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦NO,SACOFA lampole not allow to add AAU | 2023-07-06 | 2023-07-20 |  | 2023-07-24 |  | Closed | 2023-07-26 | 2023-08-02 | E//Hannah | 2023-08-01 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230726 | DU00002038844 | NIC_S2_Change MM to BI_owner reject_SACOFA SDN BHD |  | 2023-08-22 | 2023-08-15 |  |  | 30m Rapole | 30 | Add R9264M M1821 x5+R8862A S2600 x1,Dismantle R8862A S1800(B6A) x4+R8862A S2100(A6A) x4 |  | 23
7057C | Pusat Komersial Bintang Kubota | Sabah |  | Modernization |  | 2023Q4 | MS | YPTT | 4.6 TSSR Approved |  | 2023-06-17 | 2023-07-27 |  | 2023-08-04 |  | Closed | 2023-08-09 | 2023-08-18 | E//Hannah | 2023-08-16 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002038845 |  |  | 2023-09-19 | 2023-08-15 |  | In-Building System | 3m Boom (RT) | 14 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2,Dismantle R8894E M1821(A8A) x3+R8892E M1821(BAA) x3 | 2
7019R | Kg Serudong Baru Jln Garson Spur | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038846 | [6 empty] | Land site
9071B | Taman Hijrah | Sarawak |  | Modernization |  | 2023Q4 | SH | Datasco | 4.6 TSSR Approved |  | 2023-06-17 | 2023-07-03 |  | 2023-07-05 |  | Closed | 2023-07-06 | 2023-07-18 | E//Hannah | 2023-07-18 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 - Copy | DU00002038847 |  |  | 2023-08-08 | 2023-08-04 |  | Tower | 30m Monopole | 30 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x2+R8882 S1800B(B6B) x3+R8862A S1800(B6A) x1+R8840-U216 x3
9020C | Piasau Industrial Area | Sarawak |  | Modernization |  | 2023Q4 | BY | South Pacific | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦ Sacofa lamppoe not allow to add antenna on tower | 2023-06-09 | 2023-06-14 |  | 2023-06-19 |  | Closed | 2023-07-07 | 2023-07-14 | E//Hannah | 2023-07-14 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230606-0003 | DU00002038848 | NIC_S2_Change MM to BI_owner reject_SACOFA SDN BHD |  | 2023-08-29 | 2023-08-21 |  | Monopole | Tower | 35 | Add R9264M M1821 x5 + R8862A S2601 x2,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 13
7469A | Dangulad Tampak | Sabah |  | Modernization |  | 2023Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-07-14 | 2023-07-20 |  | 2023-07-24 |  | Closed | 2023-07-27 | 2023-07-28 | CD//Ray Amos | 2023-07-24 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230508-0005 | DU00002038849 |  |  | 2023-07-30 | 2023-07-29 |  | Monopole | 30m Monopole | 35 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
7680B | Batu Payung | Sabah |  | Modernization |  | 2023Q4 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-06-21 | 2023-06-23 |  | 2023-06-27 |  | Closed | 2023-08-17 | 2023-07-12 | E//Hannah | 2023-07-11 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230612-0004 | DU00002038850 |  |  | 2023-08-29 | 2023-08-14 |  | Lampole | 24m Lampole | 24 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
7199H | Taman Ambar iMacro | Sabah |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038851 | [6 empty] | Land site
7093R | LADANG JATIKA | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2025-07-17 |  | 2025-07-17 |  | 2025-07-22 |  | 2025-10-06 | 2025-11-03 | E//Ali | 2025-10-15 | SQ202506100849 - GTSB / SQ202507010442 - GTSB | DU00002038852 |  |  |  |  | 2025-09-26 |  | Tower
9411A | Tmn Sri Wangi | Sarawak |  | Modernization |  | 2023Q4 | SH | Trintel | 4.6 TSSR Approved |  | 2023-07-04 | 2023-07-17 |  | 2023-07-27 |  | Closed | 2023-07-27 | 2023-08-01 | E//Hannah | 2023-08-01 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230622 | DU00002038853 |  |  | 2023-08-26 | 2023-08-21 |  | Monopole | 36m Monopole | 36m | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8882-GUL1812 x3+R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 | 12
7444A | Kg Biah | Sabah |  | Modernization |  | 2023Q3 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-05-13 | 2023-05-16 |  | 2023-05-19 |  | Closed | 2023-05-26 | 2023-06-02 | E//Hannah | 2023-06-02 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230516-0001 | DU00002038854 |  |  | 2023-07-20 | 2023-07-08 |  | Tower | Tower | 65 | Add R9264M M1821 x6,Dismantle R8894E M1821(A8A) x3 |  | 123
9570B | Kampung Hulu Nyalau | Sarawak |  | Modernization |  | 2023Q3 | BY | Magicell | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-11 |  | 2023-05-13 |  | Closed | 2023-05-17 | 2023-05-19 | CD//John | 2023-05-17 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230512-0007 | DU00002038855 |  |  | 2024-04-03 | 2024-03-25 |  | Tower | Tower | 60 | Add R9264H M901821 x3 + R9264M M1821 x3 + R8862A S2601 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 123
8008Z | KgHuluChemperuh | Central |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  |  | 14.1 Drop (No Survey) |  |  | 2025-12-05 |  |  |  | To be Submitted | [5 empty] | DU00002038856 | [5 empty] | Tower | 76m 4 Legged Tower | 76m
7359B | Kg. Magatang | Sabah |  | Modernization |  | 2023Q3 | MS | Datasco | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-07 |  | 2023-06-13 |  | Closed | 2023-06-14 | 2023-07-06 | CD//Mohidi Jaan | 2023-07-05 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230508-0004 | DU00002038857 |  |  | 2023-07-18 | 2023-07-13 |  | Monopole | Tower | 60m | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
7185Z | KG SUNGAI BUAYA | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 |  | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002038858 | [6 empty] | Tower
9130B | Samalaju-Port | Sarawak |  | Modernization |  | 2023Q3 | SH | Magicell | 4.6 TSSR Approved |  | 2023-05-11 | 2023-05-13 |  | 2023-05-16 |  | Closed | 2023-05-20 | 2023-05-25 | E//Hannah | 2023-05-26 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230512-0007 | DU00002038859 |  |  | 2023-06-30 | 2023-06-26 |  | Monopole | 30m Monopole | 30M | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882 S1800(B) x3
7457A | Survey Keningau | Sabah |  | Modernization |  | 2023Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-05-07 | 2023-05-10 |  | 2023-05-13 |  | Closed | 2023-05-16 | 2023-05-17 | CD//Mohidi Jaan | 2023-05-16 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230508-0005 | DU00002038860 |  |  | 2023-07-18 | 2023-07-14 |  | Wall mount boom | 3m RT (Wall Mounted Pole) | 5.1 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
7175Z | Jln Keningau-Sook | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038861 | [6 empty] | Tower
7082R | MUISMELEWAR | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2025-07-17 |  | 2025-07-18 |  | 2025-07-19 |  | 2025-08-06 | 2025-11-03 | E//Hannah | 2025-09-24 | SQ202506100849 - GTSB / SQ202507010442 - GTSB | DU00002038862 |  |  |  |  | 2025-11-28 |  | Tower
7116R | KG.PADIWAN | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2023Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2025-09-24 |  | 2025-10-13 |  | 2025-10-24 |  | 2025-10-28 | 2025-12-04 | E//Faiz | 2025-11-06 | SQ202509220707 - YPTT | DU00002038863 |  |  |  |  | 2025-10-31 |  | Tower
9132B | Petronas Punj Lloyd | Sarawak |  | Modernization |  | 2023Q3 | HQ 5 | Trintel | 4.6 TSSR Approved |  | 2023-05-15 | 2023-05-19 |  | 2023-05-23 |  | Closed | 2023-05-25 | 2023-05-27 | E//Hannah | 2023-05-26 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230516-0007 | DU00002038864 |  |  | 2023-09-19 | 2023-06-20 |  | Monopole | Tower | 30m | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
7143R | Skim Mesej Ladang Sungai Labah | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038865 | [6 empty] | Land site
7224Z | KM100 Kalabakan-Nabawan | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | AD |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002038866 | [6 empty] | Tower
7462A | Adika Complex Keningau RT | Sabah |  | Modernization |  | 2023Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-05-07 | 2023-05-13 |  | 2023-05-16 |  | Closed | 2023-05-17 | 2023-05-18 | CD//Ray Amos | 2023-05-18 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230508-0005 | DU00002038867 |  |  | 2023-07-24 | 2023-07-14 |  | Pole | 3m RT (Wall Mounted Pole) | 15.7 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 13
7625A | Kalabakan Town | Sabah |  | Modernization |  | 2023Q3 | AD | Futong | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-10 |  | 2023-05-25 |  | Closed | 2023-05-18 | 2023-05-19 | CD//Jahganathan | 2023-05-19 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0004 | DU00002038868 |  |  | 2023-07-27 | 2023-07-20 |  | Tower | Tower | 60 | Add R9264H M901821 x1 + R9264M M1821 x2 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x2
9300C | Permai Jaya (REL) | Sarawak |  | Modernization |  | 2023Q4 | BY | Datasco | 4.6 TSSR Approved |  | 2023-07-10 | 2023-07-18 |  | 2023-07-22 |  | Closed | 2023-07-24 | 2023-07-26 | E//Hannah | 2023-07-25 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230726 | DU00002038869 |  |  | 2023-09-04 | 2023-08-25 |  | Lampole | 30M Rapole | 30 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
7197A | Tg Batu Laut(Maxis) | Sabah |  | Modernization |  | 2023Q4 | MS | YPTT | 4.6 TSSR Approved |  | 2023-06-22 | 2023-07-17 |  | 2023-07-21 |  | Closed | 2023-07-24 | 2023-07-27 | E//Hannah | 2023-07-27 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002038870 |  |  | 2023-08-17 | 2023-08-02 |  | Tower | 76m 3 Legged Tower | 60 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8854E S1800(A6A) x3+R8854D S2100(A4A) x3 | 123
9627B | Spring Mall Bintulu | Sarawak |  | Modernization |  | 2023Q3 | SH | Datasco | 4.6 TSSR Approved |  | 2023-06-17 | 2023-06-20 |  | 2023-06-26 |  | Closed | 2023-06-27 | 2023-08-10 | E//Nazrul | 2023-08-10 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230516-0006 | DU00002038871 |  |  | 2023-08-23 | 2023-08-14 |  | Wall mount boom | In-building system |  | Add R8892E M1821 x3,Dismantle R8862A S1800(B6A) x3
9315A | Sungei Cina Kuching | Sarawak |  | Modernization |  | 2023Q4 | SH | AllStar | 4.6 TSSR Approved |  | 2023-07-08 | 2023-07-14 |  | 2023-07-18 |  | Closed | 2023-07-18 | 2023-07-28 | E//Hannah | 2023-07-24 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230726 | DU00002038872 |  |  | 2023-08-24 | 2023-08-18 |  | Tower | 45m 3 Legged Tower | 45 | Add R8852E S9000x2 + R8894E M1821x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3++
7029R | Kg Sungai Atas | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038873 | [6 empty] | Land site
9158R | COASTAL HIGHWAY PLANTATION CAMP #3 | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | N/A - no need PR for MOCN Decomm | DU00002038874 | [6 empty] | Land site
9582A | RPR Quadruplex | Sarawak |  | Modernization |  | 2023Q4 | BY | YPTT | 4.6 TSSR Approved |  | 2023-06-15 | 2023-06-21 |  | 2023-06-26 |  | Closed | 2023-07-05 | 2023-07-13 | E//Hannah | 2023-07-14 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20230622 | DU00002038875 |  |  | 2023-08-24 | 2023-08-15 |  | Monopole | 30m Rapole | 30 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 |  | 12(S1->S2,S2->S3,S3->S1,rename Sector ID,Bisector@New S2S3)
7201Z | Kg Simatuoh | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038876 | [6 empty] | Land site
7805M | Sabindo Tawau | Sabah |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038877 | [6 empty] | Micro Cell
9137B | RPR Sibiyu | Sarawak |  | Site Out (Modernization) | Modernization->Site Out(Modernization) | 2023Q3 |  | Trintel | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2025-06-12 | 2025-06-24 | [8 empty] | S1MY2024071018WBF1-321-Trintel | DU00002038878 |  |  |  |  | 2025-09-20 |  | 30m Rapole |  | Add R9264H M901821 x3,Dismantle R8882 S1800(B) x3+R8862A S2100(A6A) x3
7635B | TGBATUKERAMAT (Celcom) | Sabah |  | Modernization |  | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-06-20 | 2023-07-24 |  | 2023-07-28 |  | Closed | 2023-08-08 | 2023-08-08 | CD//Jahganathan | 2023-08-04 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002038879 |  |  | 2023-08-20 | 2023-08-15 |  | Tower | Tower | 60 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R8862A S2600(A4A) x2+R8894E M1821(A8A) x2 | 12
9581A | Tudan | Sarawak |  | Modernization |  | 2023Q4 | BY | YPTT | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦sacofa Reject to install AAU | 2023-06-11 | 2023-06-21 |  | 2023-06-24 |  | Rectificating | 2023-07-04 | 2023-09-01 | E//SoonHo | 2023-07-28 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20230612-0006 | DU00002038880 | NIC_S2_Change MM to BI_owner reject_SACOFA SDN BHD |  | 2025-07-06 | 2025-03-21 |  | Monopole | Rapole | 25 | Add R8862A S9000x3+ R8894E M1821 x1 | 0 | 3
7068C | Taman Sempul | Sabah |  | Modernization |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved | 24/1: TSSR Shared to TI Subcon. TSS & Pre-Installation concurrent//Backlog site. TI & TSS Concurrent due to Spider Skylift limitation. BOM & TSSR released without RF solution. Pending Li Jie to provide RF solution | 2024-01-29 | 2024-02-16 |  | 2024-02-20 |  | Closed | 2024-02-22 | 2024-03-15 | E//Hannah | 2024-03-13 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230703.xls | DU00002038881 |  |  | 2024-01-31 | 2024-01-22 |  | Lampole | 30m Lampole | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
9167B | Bandar Baru Samariang | Sarawak |  | Modernization |  | 2023Q4 | ZB | Trintel | 4.6 TSSR Approved |  | 2023-06-17 | 2023-07-26 |  | 2024-03-08 |  | Closed | 2024-03-05 | 2024-03-25 | E//Hannah | 2024-03-23 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230622 | DU00002038882 |  | Need resurvey to check connection RRU to Antenna | 2023-09-02 | 2023-08-22 |  | Monopole | 30m Rapole | 30m | Add R9264M M1821 x2+R9264H M901821 x3,Dismantle R8854E S1800(A6A) x3+R8854D S2100(A4A) x3 |  | 23
7063A | Guang Ji Temple | Sabah |  | Modernization |  | 2023Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-05-07 | 2023-05-25 |  | 2023-05-27 |  | Closed | 2023-05-30 | 2023-07-06 | E//Hannah | 2023-07-05 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230508-0005 | DU00002038883 |  |  | 2023-07-21 | 2023-07-14 |  |  | 60m 3 Legged Tower | 65 | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x3+R8894E M1821(A8A) x6 | 123
7659B | PETRONAS – KUHARA 2 | Sabah |  | Modernization |  | 2023Q4 | AD | YPTT | 4.6 TSSR Approved | Bisector Cannot Install, Change to Normal | 2023-06-27 | 2023-08-17 |  | 2023-08-21 |  | Closed | 2023-08-24 | 2023-08-28 | E//Hannah | 2023-08-28 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002038884 | NIC_S1_Change BI to normal sector_Space constraint_STEALTH |  | 2023-09-22 | 2023-09-13 |  | Petronas Pylon | 24m Pylon | 26 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x1+R8882 S1800(B) x1+R8882 S1800B(B6B) x3+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3
7044H | 99 Speedmart 1 PLAZA | Sabah |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038885 | [6 empty] | Small Cell
7624B | Walitehan Height SBC | Sabah |  | Modernization |  | 2023Q4 | AD | Datasco | 4.6 TSSR Approved |  | 2023-06-21 | 2023-07-27 |  | 2023-08-02 |  | Closed | 2023-08-03 | 2023-08-11 | E//Hannah | 2023-08-11 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007 | DU00002038886 |  |  | 2023-08-20 | 2023-08-15 |  | Tower | Tower | 76m | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
7628A | Kabogan Junction | Sabah |  | Modernization |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-06-25 | 2023-07-13 |  | 2023-07-17 |  | Closed | 2023-07-18 | 2023-08-18 | E//Yadav | 2023-07-21 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230703.xls | DU00002038887 |  |  | 2023-09-15 | 2023-09-04 |  | Tower | Tower | 60 | Add R8852E S9000 x2 + A9732 M1821 x3,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x5 | 123
9510A | Jln Krukup | Sarawak |  | Modernization |  | 2023Q4 | BY | Datasco | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-15 |  | 2023-06-19 |  | Closed | 2023-06-26 | 2023-07-07 | E//Hannah | 2023-07-06 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230608-0007 | DU00002038888 |  |  | 2023-08-04 | 2023-07-17 |  | Monopole | 30m Monopole | 30 | Add R9264H M901821 x4+ R9264M M1821 x2 + R8862A S2600 x2,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x2+R8894E M1821(A8A) x4 |  | 34
9604A | Stadium Miri | Sarawak |  | Modernization |  | 2023Q4 | BY | Trintel | 4.6 TSSR Approved |  | 2023-06-15 | 2023-07-06 |  | 2023-07-10 |  | Closed | 2023-07-12 | 2023-07-15 | E//Hannah | 2023-07-14 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230622 | DU00002038889 |  |  | 2023-08-24 | 2023-08-18 |  | Monopole | 30m Rapole | 30m | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 13
7762B | Mangrove Sanctuary | Sabah |  | Modernization |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-07-06 | 2023-07-12 |  | 2023-07-14 |  | Closed | 2023-07-17 | 2023-07-25 | E//Hannah | 2023-07-25 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230703.xls | DU00002038890 |  | No TX Decom TSSR Required (Under upgrade) | 2023-10-16 | 2023-09-18 |  | Tower | 76M TOWER | 60 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3
7647C | Taman Miramas Semporna | Sabah |  | Modernization |  | 2023Q4 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-19 | 2023-06-21 |  | 2023-06-23 |  | Closed | 2023-06-24 | 2023-07-25 | CD//Mohidi Jaan | 2023-07-21 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0011 | DU00002038891 |  |  | 2023-08-30 | 2023-08-24 |  | Tower | 45m 3 Legged Tower | 45 | Add R9264M M1821 x1+A9732 M1821 x3,Dismantle R8862A S1800(B6A) x4+R8862A S2100(A6A) x4 | 124 | 0
7968A | Kg Indera Sabah | Sabah |  | Modernization |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦isuue on tower loading | 2023-06-08 | 2023-07-17 |  | 2023-07-20 |  | Closed | 2023-07-21 | 2023-07-26 | E//Hannah | 2023-07-25 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007 | DU00002038892 | NIC_S3_Change MM to BI_loading issue_EDOTCO(M)-CSU |  | 2023-09-11 | 2023-09-07 |  | Tower | 45m 4 Legged Tower | 45 | Add R9264H M901821 x3 + R9264M M1821 x3 + R8862A S2601 x3,Dismantle R8894E M1821(A8A) x3 |  | 123
7000D | Kampung Simunul | Sabah |  | Modernization |  | 2023Q4 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-20 | 2023-06-16 |  | 2023-06-24 |  | Closed | 2023-07-03 | 2023-07-10 | E//Hannah | 2023-07-10 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0011 | DU00002038893 |  |  | 2023-09-22 | 2023-09-07 |  | Monopole | Land site | 30 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3+R8892E M1821(BAA) x3 | 123
7933B | Simpang Kunak | Sabah |  | Modernization |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-06-19 | 2023-06-26 |  | 2023-06-27 |  | Closed | 2023-06-28 | 2023-07-13 | E//Hannah | 2023-07-12 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0010 | DU00002038894 |  |  | 2023-09-11 | 2023-09-04 |  |  | Tower | 60 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 12
7975A | Seaventures Mabul | Sabah |  | Modernization | Modernization->Site Out->Modernization | 2023Q4 | AD | Futong | 4.6 TSSR Approved |  | 2023-07-05 | 2023-07-10 |  | 2023-07-11 |  | Closed | 2023-07-13 | 2023-08-02 | E//Hannah | 2023-08-01 | Celcom Digi_RAN-Futong-TSS-Sabah-20230726 | DU00002038895 |  |  | 2024-04-25 | 2024-04-17 |  | Pole | 30m Monopole | 13 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3
7324B | SMK Kuhara (REL) | Sabah |  | Modernization |  | 2023Q4 | MS | YPTT | 4.6 TSSR Approved | Single phase power issue - Temporary Limited RRUs Usage(SESB Application WIP) | 2023-06-22 | 2023-06-27 |  | 2023-07-03 |  | Closed | 2023-07-04 | 2023-07-28 | E//Hannah | 2023-07-25 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002038896 |  |  | 2023-08-20 | 2023-08-07 |  | Monopole | 30m Rapole | 30 | Add R9264H M901821 x4 + R9264M M1821 x3 + R8862A S2601 x2,Dismantle R8894E M1821(A8A) x4 |  | 134
7616A | Taman Megah Jaya | Sabah |  | Modernization |  | 2023Q4 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-06-26 | 2023-07-05 |  | 2023-07-09 |  | Closed | 2023-07-10 | 2023-07-24 | E//Hannah | 2023-07-24 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230612-0004 | DU00002038897 |  |  | 2023-09-04 | 2023-08-24 |  | Wall mount boom | 3m RT (Wall Mounted Pole) | 6m | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8882-GUL1812 x2+R8882 S1800(B) x1+R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 | 13
7058C | Pu Zhao Temple | Sabah |  | Site Out (Modernization) | Modernization->Site out->Site Out (Modernization) | 2023Q4 | MS | YPTT | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2025-07-16 | 2025-07-10 |  |  |  | To be Submitted |  |  | CD//Mohidi Jaan |  | SQ202506160230 - YPTT | DU00002038898 | [6 empty] | 30m Monopole
7472A | Masjid Al Taqwa | Sabah |  | Modernization |  | 2023Q3 | AD | Magicell | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-17 |  | 2023-05-19 |  | Closed | 2023-05-23 | 2023-07-12 | E//Hannah | 2023-07-11 | Celcom Digi_RAN-Magicell-TSS-Sabah-20230508-0001 | DU00002038899 |  |  | 2023-07-30 | 2023-07-14 |  | Minaret | 24m Lampole | 48 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
7195Z | KG BLOK 31 (SD LADANG TABLE) | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 | MS | Datasco | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002038900 | [6 empty] | Tower
7355C | Pulau Mataking | Sabah |  | Modernization |  | 2023Q4 | AD | Futong | 4.6 TSSR Approved |  | 2023-07-03 | 2023-07-04 |  | 2023-07-06 |  | Closed | 2023-07-07 | 2023-07-14 | E//Hannah | 2023-07-14 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0011 | DU00002038901 |  |  | 2023-09-22 | 2023-09-13 |  | Tower | 60M Tower 3 Legged | 60 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
7159Z | KM45 Kalabakan-Nabawan | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | AD |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002038902 | [6 empty] | Tower
7965A | Felda Kalabakan Tengah | Sabah |  | Modernization |  | 2023Q3 | AD | Futong | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-20 |  | 2023-05-24 |  | Closed | 2023-05-25 | 2023-06-07 | E//Nizar | 2023-06-06 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0004 | DU00002038903 |  |  | 2023-08-03 | 2023-07-20 |  | Tower | 76m 3 Legged Tower | 76 | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x3 |  | 3
9069R | SUNGAI ASAP 2 | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2023Q3 | AI | Magicell | 4.6 TSSR Approved |  | 2025-06-18 |  | 2025-07-09 |  | 2025-07-14 |  | 2025-08-06 | 2025-11-03 | E//John | 2025-10-10 | SQ202506110081-Magicell/SQ202507140221-Magicell | DU00002038904 |  |  |  |  | 2025-10-10 |  | Land site
7470A | Keningau Kg Bayangan | Sabah |  | Modernization |  | 2023Q3 | AD | Magicell | 4.6 TSSR Approved |  | 2023-05-16 | 2023-05-17 |  | 2023-05-19 |  | Closed | 2023-05-23 | 2023-05-25 | E//Hannah | 2023-05-26 | Celcom Digi_RAN-Magicell-TSS-Sabah-20230508-0001 | DU00002038905 |  |  | 2023-07-16 | 2023-07-08 |  | Monopole | 30m Monopole | 31 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 12
7088R | BANDAUAUMKAR | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2025-07-17 |  | 2025-07-18 |  | 2025-07-21 |  | 2025-08-08 | 2025-11-03 | E//Hannah | 2025-09-16 | SQ202506100849 - GTSB / SQ202507010442 - GTSB | DU00002038906 |  |  |  |  | 2025-09-26 |  | Tower
9092A | Sg Tujuh(SACOFA) | Sarawak |  | Modernization |  | 2023Q4 | ZB | Datasco | 4.6 TSSR Approved |  | 2024-02-15 | 2024-04-22 |  | 2024-03-01 |  | Closed | 2024-03-06 | 2024-03-18 | E//Hannah | 2024-03-14 | PR raised | DU00002038907 |  | G900 RRU connection unable to see at the antenna port, need resurvey to get the photo | 2024-06-14 | 2024-06-06 |  | Tower | Tower | 60 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8860E-GU908 x2+R8882-GUL1812 x3 |  | 1
7969A | Seaventures Resort | Sabah |  | Modernization |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-07-10 | 2023-08-03 |  | 2023-08-10 |  | Closed | 2023-08-16 | 2023-08-16 | CD//Ray Amos | 2023-08-16 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007 | DU00002038908 |  |  | 2023-09-07 | 2023-08-22 |  | Tower | Tower | 76 | Add R9264M M1821 x5 + R8862A S2601 x3,Dismantle R8882 S1800B(B6B) x2+R8862A S2100(A6A) x2 |  | 12
9060Z | COASTALHIGHWAYPLANTATIONCAMP#2 | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038909 | [6 empty] | Land site
9161B | Kpg Buntal Celcom | Sarawak |  | Modernization |  | 2023Q4 | BY | AllStar | 4.6 TSSR Approved |  | 2023-06-16 | 2023-06-20 |  | 2023-06-28 |  | Closed | 2023-06-30 | 2023-07-17 | E//Hannah | 2023-07-17 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230608-0006 | DU00002038910 |  |  | 2023-12-27 | 2023-12-06 |  | Tower | Tower | 45 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8854 S2600 x2,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+ R8862A S2600(A4A) x2 |  | 12
7196A | Jalan Sin On | Sabah |  | Modernization |  | 2023Q4 | MS | YPTT | 4.6 TSSR Approved |  | 2023-06-19 | 2023-06-27 |  | 2023-07-05 |  | Closed | 2023-07-05 | 2023-07-12 | E//Hannah | 2023-07-12 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002038911 |  |  | 2023-08-11 | 2023-08-08 |  | Tower | 45m 4 Legged Tower | 47 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 23
7069C | Batu Apas | Sabah |  | Modernization |  | 2023Q4 | AD | Datasco | 4.6 TSSR Approved |  | 2023-06-10 | 2023-06-27 |  | 2023-07-02 |  | Rectificating | 2023-07-21 | 2023-07-28 | E//Hannah | 2023-07-28 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007 | DU00002038912 |  |  | 2023-09-01 | 2023-08-24 |  | Monopole | 30m Monopole | 30 | Add R8852E S9000 x3 + A9732 M1821 x3 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x4 | 123
7649C | Taman Ria Heights | Sabah |  | Modernization |  | 2023Q4 | MS | YPTT | 4.6 TSSR Approved |  | 2023-06-22 | 2023-06-27 |  | 2023-07-05 |  | Closed | 2023-07-05 | 2023-07-13 | CD//Jahganathan | 2023-07-13 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002038913 |  |  | 2023-08-10 | 2023-08-05 |  | Tower | Tower | 60 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 12
9074A | MSC Miri | Sarawak |  | Modernization |  | 2023Q4 | AD | Magicell | 4.6 TSSR Approved |  | 2023-07-12 | 2023-07-13 |  | 2023-07-17 |  | Closed | 2023-07-17 | 2023-07-21 | E//Hannah | 2023-07-21 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230726 | DU00002038914 |  |  | 2023-09-09 | 2023-08-14 |  | Tower | Tower | 76 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
9122A | Sg. Plant | Sarawak |  | Modernization |  | 2023Q3 | BY | AllStar | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-24 |  | 2023-06-07 |  | Closed | 2023-06-08 | 2023-07-05 | E//Hannah | 2023-07-03 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230516-0005 | DU00002038915 |  |  | 2023-09-05 | 2023-08-21 |  | Tower | 45m 3 Legged Tower | 76 | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x4 | 1 | 0
9337A | Siol Kandis | Sarawak |  | Modernization |  | 2023Q4 | BY | Datasco | 4.6 TSSR Approved |  | 2023-06-15 | 2023-06-20 |  | 2023-06-22 |  | Closed | 2023-06-23 | 2023-07-17 | E//Hannah | 2023-07-17 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 - Copy | DU00002038916 |  |  | 2023-08-15 | 2023-08-08 |  | Tower | 30m Monopole | 36 | Add R8852E S9000 x3 + A9732 M1821 x3 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x4 | 123
7675B | Taman Semarak | Sabah |  | Modernization |  | 2023Q4 | MS | YPTT | 4.6 TSSR Approved |  | 2023-06-20 | 2023-06-27 |  | 2023-07-06 |  | Closed | 2023-07-07 | 2023-08-03 | E//Hannah | 2023-08-02 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002038917 |  |  | 2023-08-11 | 2023-08-05 |  | Lampole | 24m Lampole | 24 | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 12 | 0
9580A | Boulevard Mall Miri Outdoor | Sarawak |  | Modernization |  | 2023Q4 | ZB | AllStar | 4.6 TSSR Approved |  | 2023-06-15 | 2023-08-01 |  | 2023-08-07 |  | Closed | 2023-08-14 | 2023-09-01 | E//Hannah | 2023-09-01 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230608-0006 | DU00002038918 |  | Drawing not complete | 2023-10-24 | 2023-10-06 |  | In-Building System | 3m Bipod (RT) | 6m | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R9224E M1821(AAB) x3 | 123
7184Z | KG SUNGAI PUKUL | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | AD |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002038919 | [6 empty] | Tower
9011C | Matang Hub Kuching | Sarawak |  | Modernization |  | 2023Q4 | SH | South Pacific | 4.6 TSSR Approved |  | 2023-06-12 | 2023-06-23 |  | 2023-06-27 |  | Closed | 2023-06-28 | 2023-07-25 | E//Zulakmar | 2023-07-18 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230612-0004 | DU00002038920 |  |  | 2023-08-24 | 2023-08-22 |  | Monopole | 30m Rapole | 30m | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3
9027A | Buntal | Sarawak |  | Modernization |  | 2023Q4 | ZB | AllStar | 4.6 TSSR Approved |  | 2023-08-28 | 2023-08-30 |  | 2023-09-04 |  | Closed | 2023-09-04 | 2023-09-08 | E//Hannah | 2023-09-07 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230608-0006 | DU00002038921 |  |  | 2023-09-15 | 2023-09-12 |  | Tower | Tower | 45 | Add R8894E M1821 x3,Dismantle R8892E M1821(BAA) x3
7617A | Jalan Kao Sing | Sabah |  | Modernization |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-06-11 | 2023-07-17 |  | 2023-07-20 |  | Closed | 2023-07-21 | 2023-07-28 | E//Zulakmar | 2023-07-28 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007 | DU00002038922 |  |  | 2023-09-15 | 2023-09-07 |  | Monopole | 60m 3 Legged Tower | 60 | Add R8852E S9000 x3 + A9732 M1821 x3 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x4 | 123
7664B | LADANG MERBAU_T3 | Sabah |  | Modernization |  | 2023Q3 | AD | Futong | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-13 |  | 2023-05-25 |  | Closed | 2023-05-19 | 2023-07-04 | E//Hannah | 2023-07-04 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0004 | DU00002038923 |  |  | 2023-08-06 | 2023-07-28 |  | Tower | 45m 3 Legged Tower | 76 | Add A9732 M1821 x1 + R9264M M1821 x2,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 | 2
7697B | Perdana Square Tawau | Sabah |  | Modernization |  | 2023Q4 | HQ 2 | YPTT | 4.6 TSSR Approved |  | 2023-06-23 | 2023-07-12 |  | 2023-07-18 |  | Closed | 2023-07-20 | 2023-07-25 | CD//Ray Amos | 2023-07-25 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002038924 |  |  | 2023-08-11 | 2023-08-04 |  | Monopole | 30m Rapole | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
7455A | Kg. Buang Sayang | Sabah |  | Modernization |  | 2023Q3 | MS | Datasco | 4.6 TSSR Approved |  | 2023-05-18 | 2023-06-12 |  | 2023-06-16 |  | Closed | 2023-06-16 | 2023-07-06 | CD//Jahganathan | 2023-07-05 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230508-0004 | DU00002038925 |  |  | 2023-07-18 | 2023-07-13 |  | Monopole | Tower | 76 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
9529A | Sanadin | Sarawak |  | Modernization |  | 2023Q4 | SH | Trintel | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI,L2600 change to 40M¦sacofa reject install AAU | 2023-07-13 | 2023-07-25 |  | 2023-08-01 |  | Closed | 2023-08-11 | 2023-09-01 | E//Hannah | 2023-09-01 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230622 | DU00002038926 | NIC_S3_Change MM to BI,L2600 change to 40M_owner reject_SACOFA SDN BHD |  | 2023-10-27 | 2023-08-25 |  | Monopole | 30m Monopole | 25m | Add R9264M M1821 x6,Dismantle R8894E M1821(A8A) x3 | 0 | 123
9017Z | SG ASSEP | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | N/A - no need PR for MOCN Decomm | DU00002038927 | [6 empty] | Land site
9323A | Semariang(Celcom) | Sarawak |  | Modernization |  | 2023Q4 | BY | Datasco | 4.6 TSSR Approved |  | 2023-06-16 | 2023-06-19 |  | 2023-06-20 |  | Closed | 2023-06-21 | 2023-08-16 | E//SoonHo | 2023-08-16 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 - Copy | DU00002038928 |  |  | 2023-10-09 | 2023-09-15 |  | Tower | Tower | 60 | Add A9732 M1821 x3,Dismantle R8882-GUL1812 x3+R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 | 123
9609A | Jalan Pujut 4 | Sarawak |  | Modernization |  | 2023Q4 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-08-04 | 2023-08-15 |  | 2023-08-17 |  | Closed | 2023-08-18 | 2023-09-01 | E//Hannah | 2023-09-01 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002038929 |  |  | 2023-11-11 | 2023-09-24 |  | Pole | 30m Rapole | 46 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 3
7001C | Kampung Batu 2 | Sabah |  | Modernization |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-06-13 | 2023-07-06 |  | 2023-07-10 |  | Closed | 2023-07-14 | 2023-07-20 | E//Hannah | 2023-07-20 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007 | DU00002038930 |  |  | 2023-09-12 | 2023-08-24 |  | Monopole | 30m Lampole | 30 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x4 | 123
9107B | Matang Indah | Sarawak |  | Modernization |  | 2023Q4 | BY | Trintel | 4.6 TSSR Approved |  | 2023-07-13 | 2023-07-18 |  | 2023-07-25 |  | Closed | 2023-07-25 | 2023-07-28 | E//Hannah | 2023-07-28 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230622 | DU00002038931 |  |  | 2023-09-01 | 2023-08-18 |  | Monopole | 24m Lampole | 15 | Add R9264H M901821 x3,Dismantle R8892E M1821(BAA) x3
7063C | Nabawan | Sabah |  | Modernization |  | 2023Q3 | AD | Datasco | 4.6 TSSR Approved |  | 2023-06-27 | 2023-07-04 |  | 2023-07-06 |  | Closed | 2023-07-07 | 2023-07-11 | E//Hannah | 2023-07-11 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230703.xls | DU00002038932 |  |  | 2023-07-31 | 2023-07-18 |  | Monopole | 30m Lampole | 31 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
9275A | Jalan Sebiew | Sarawak |  | Modernization |  | 2023Q3 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-05-16 | 2023-05-23 |  | 2023-05-29 |  | Closed | 2023-05-30 | 2023-06-17 | E//Hannah | 2023-06-14 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230516-0006 | DU00002038933 |  |  | 2023-07-03 | 2023-06-28 |  | Monopole | Guyed Mast | 30M | Add R9264M M1821 x4 + R8862A S2600 x1,Dismantle R8862A S1800(B6A) x3++R8881 S2100 x3+ |  | 3
7442A | Sook | Sabah |  | Modernization | Modernization->Maintain USP MOCN->Modernization->On Hold->Modernization | 2023Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2023-05-17 | 2025-04-22 |  | 2025-04-23 |  | Under Approval | 2023-06-03 | 2023-07-07 | E//Hannah | 2025-05-23 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230508-0005 | DU00002038934 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed | 2025-06-09 | 2025-05-26 |  | Tower | Tower | 76 | Add R8894E M1821x3+R8854E S2600x3+R8862A S2601x1, Dismantle 8854E S1800(A6A)x4 | 0 | 123
7931B | Kg Pangi Kunak | Sabah |  | Modernization |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-06-19 | 2023-06-22 |  | 2023-06-24 |  | Closed | 2023-06-27 | 2023-07-12 | E//Hannah | 2023-07-12 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0010 | DU00002038935 |  |  | 2023-09-22 | 2023-09-13 |  | Tower | Tower | 60 | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 |  | 3
9068B | Kg Sg Tengah (REL) | Sarawak |  | Modernization |  | 2023Q4 | SH | AllStar | 4.6 TSSR Approved |  | 2023-07-08 | 2023-07-12 |  | 2023-07-20 |  | Closed | 2023-07-20 | 2023-07-26 | E//Hannah | 2023-07-26 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230726 | DU00002038936 |  |  | 2023-09-28 | 2023-09-21 |  |  | 30m Monopole | 30 | Add R9264H M901821 x3,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3
7144R | Sabah Softwoods | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038937 | [6 empty] | Land site
7682B | LUASONG HILL | Sabah |  | Modernization |  | 2023Q3 | AD | Futong | 4.6 TSSR Approved |  | 2023-10-19 | 2023-10-23 |  | 2023-10-26 |  | Closed | 2023-10-26 | 2023-11-22 | E//Hannah | 2023-11-22 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0004 | DU00002038938 |  |  | 2024-01-31 | 2023-11-23 |  | Tower | 4 Legged Tower | 76 | Add R9264M M1821 x3 + R8862A S2601 x3,Dismantle R8894E M1821(A8A) x3
7468A | Taman Anika | Sabah |  | Modernization |  | 2023Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-05-21 | 2023-05-22 |  | 2023-06-30 |  | Closed | 2023-05-25 | 2023-07-06 | E//Hannah | 2023-07-05 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230508-0005 | DU00002038939 |  |  | 2023-07-24 | 2023-07-14 |  | Monopole | Tower | 30 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 13
9066A | Pacific Orient Hotel | Sarawak |  | Modernization |  | 2023Q4 | SH | Datasco | 4.6 TSSR Approved |  | 2023-07-25 | 2023-07-24 |  | 2023-08-02 |  | Closed | 2023-08-02 | 2023-08-11 | E//Hannah | 2023-08-11 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230608-0007 | DU00002038940 |  |  | 2023-09-21 | 2023-09-15 |  | H-bracket pole | 3m RT (Wall Mounted Pole) | 6 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8882 S2600(B4A) x1+R8894E M1821(A8A) x4 | 13
7124Z | Kretam Kalabakan | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | AD |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002038941 | [6 empty] | Tower
7018R | Kg Bukit Qouin - Ladang Sg Kawa | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038942 | [6 empty] | Land site
7676B | TM Tawau | Sabah |  | Modernization |  | 2023Q4 | HQ 2 | YPTT | 4.6 TSSR Approved |  | 2023-06-27 | 2023-07-12 |  | 2023-07-18 |  | Closed | 2023-07-20 | 2023-07-25 | E//Hannah | 2023-07-25 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002038943 |  |  | 2023-08-18 | 2023-08-04 |  | Lampole | 24m Lampole | 24.7 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
9080A | Tudan | Sarawak |  | Modernization |  | 2023Q4 | SH | Magicell | 4.6 TSSR Approved |  | 2023-06-21 | 2023-06-23 |  | 2023-06-26 |  | Closed | 2023-06-26 | 2023-07-07 | E//Hannah | 2023-07-06 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002038944 |  |  | 2023-08-21 | 2023-08-16 |  | Pole | Tower | 45 | Add R9264M M1821 x5 + R8862A S2601 x2,Dismantle R8882 S1800B(B6B) x3 |  | 23
9471A | Sri Matang | Sarawak |  | Modernization |  | 2023Q4 | SH | South Pacific | 4.6 TSSR Approved |  | 2023-06-10 | 2023-06-21 |  | 2023-06-27 |  | Closed | 2023-06-30 | 2023-07-25 | E//Zulakmar | 2023-07-25 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230612-0004 | DU00002038945 |  |  | 2023-09-25 | 2023-09-14 |  | Tower | Tower | 76 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
7463A | Jln Kg Lingkudau RT (REL) | Sabah |  | Modernization |  | 2023Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-05-07 | 2023-05-11 |  | 2023-05-20 |  | Closed | 2023-05-25 | 2023-07-07 | E//Hannah | 2023-07-05 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230508-0005 | DU00002038946 |  |  | 2023-07-23 | 2023-07-14 |  |  | 3m Boom (RT) | 9 | Add R9264M M1821 x5,Dismantle R8894E M1821(A8A) x3 |  | 12
9017A | Wisma Sesco | Sarawak |  | Site Out (Modernization) | Modernization->Site Out->Replacement, Site Out (Modernization) | 2023Q4 |  | Magicell | [SiteOut]- 1.0 Pending Survey - Subcon | [6 empty] | To be Submitted | [5 empty] | DU00002038947 | [6 empty] | 6m RT (Wall Mounted Pole)
9556A | Miri Port | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038948 | [6 empty] | 45m 3 Legged Tower
9541A | Permyjaya MP | Sarawak |  | Modernization |  | 2023Q4 | SHA | Trintel | 4.6 TSSR Approved |  | 2023-06-20 | 2023-07-10 |  | 2023-07-13 |  | Closed | 2024-11-15 | 2024-12-05 | E//Hannah | 2024-12-05 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230622 | DU00002038949 |  |  | 2025-02-27 | 2024-11-19 |  |  | 30m Monopole | 30 | Add R8862A S9000x3+A9732 M1821x2, Dismantle R9224E M1821(AAB)x4 | 13 | 0
7034R | SLDB PLANTATION | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2023Q3 | AD | Datasco | 4.6 TSSR Approved | [5 empty] | 2023-05-22 |  | 2025-09-10 | 2025-10-22 | E//Hannah | 2025-09-16 | SQ202508010264 - Datasco | DU00002038950 |  |  |  |  | 2025-11-28 |  | Tower
7243C | Taman Hong Yee | Sabah |  | Modernization |  | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-06-21 | 2023-06-28 |  | 2023-07-03 |  | Closed | 2023-07-04 | 2023-07-14 | E//Hannah | 2023-07-14 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002038951 |  |  | 2023-08-07 | 2023-08-02 |  | Monopole | 30M Monopole | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
9053H | iMacro Eastwood Valley | Sarawak |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038952 | [6 empty] | Rooftop
9608A | Jalan Desa Indah | Sarawak |  | Modernization |  | 2023Q4 | BY | Magicell | 4.6 TSSR Approved |  | 2023-06-24 | 2023-06-26 |  | 2023-06-29 |  | Closed | 2023-07-04 | 2023-07-18 | E//Hannah | 2023-07-18 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002038953 |  |  | 2023-08-07 | 2023-08-01 |  | Monopole | 30m Rapole | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
7627B | Sapang-Semporna Trunk Road | Sabah |  | Modernization |  | 2023Q4 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-27 | 2023-06-27 |  | 2023-06-30 |  | Closed | 2023-07-02 | 2023-07-21 | E//Yadav | 2023-07-20 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0011 | DU00002038954 |  |  | 2023-09-04 | 2023-08-15 |  | Tower | Tower | 76 | Add R9264M M1821 x5+R8862A S2601 x2,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 23
9041C | Yayasan Sarawak | Sarawak |  | Modernization |  | 2023Q4 | BY | Trintel | 4.6 TSSR Approved |  | 2023-06-21 | 2023-06-26 |  | 2023-06-28 |  | Closed | 2023-06-30 | 2023-07-15 | E//Zulakmar | 2023-07-14 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230622 | DU00002038955 |  |  | 2023-08-15 | 2023-08-09 |  |  | 30m Rapole | 31 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
9610A | Taman Piasau | Sarawak |  | Modernization |  | 2023Q4 | SH | Magicell | 4.6 TSSR Approved |  | 2023-06-21 | 2023-06-23 |  | 2023-06-26 |  | Closed | 2023-06-27 | 2023-07-07 | E//Hannah | 2023-07-06 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002038956 |  |  | 2023-07-23 | 2023-07-17 |  | Monopole | 30m Rapole | 30.6m | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
9586A | Permy Mall Outdoor | Sarawak |  | Modernization |  | 2023Q4 | HQ 1 | AllStar | 4.6 TSSR Approved |  | 2023-06-28 | 2023-06-22 |  | 2023-06-28 |  | Closed | 2023-07-03 | 2023-08-16 | E//Hannah | 2023-08-16 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230608-0006 | DU00002038957 |  |  | 2023-09-02 | 2023-08-25 |  | Wall mount boom | 3m Bipod (RT) | 4 | Add R9264H M901821 x3,Dismantle R8882 S1800B(B6B) x3++R8881 S2100 x3+
7666A | Taman Mulia | Sabah |  | Modernization |  | 2023Q4 | MS | YPTT | 4.6 TSSR Approved |  | 2023-06-21 | 2023-07-14 |  | 2023-07-20 |  | Closed | 2023-07-20 | 2023-07-28 | CD//Ray Amos | 2023-07-27 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002038958 |  |  | 2023-08-09 | 2023-08-05 |  | Monopole | 3m Bipod (RT) | 30 | Add R9264M M1821 x6+R8862A S2601 x2,Dismantle R8882 S1800B(B6B) x3+R8862A S1800(B6A) x1+R8862A S2100(A6A) x4 |  | 13
7250C | PPR Taman Seri Apas | Sabah |  | Modernization |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-06-28 | 2023-07-12 |  | 2023-07-15 |  | Closed | 2023-07-17 | 2023-07-25 | E//Hannah | 2023-07-25 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007 | DU00002038959 |  |  | 2023-09-25 | 2023-08-14 |  | Monopole | 30M Pole | 30M | Add R9264H M901821 x3 + R9264M M1821 x2,Dismantle R8862A S1800(B6A) x2+R8862A S2100(A6A) x2+R8894E M1821(A8A) x2 |  | 23
9134B | Bintulu Port | Sarawak |  | Modernization |  | 2023Q3 | BY | Trintel | 4.6 TSSR Approved |  | 2023-05-15 | 2023-05-25 |  | 2023-05-31 |  | Closed | 2023-06-02 | 2023-06-08 | E//Hannah | 2023-06-09 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230516-0007 | DU00002038960 |  |  | 2024-04-29 | 2023-07-04 |  |  | 3m Boom (RT) | 3m | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x3 |  | 2
9140B | Politeknik Matang 3G Den | Sarawak |  | Modernization |  | 2023Q4 | BY | AllStar | 4.6 TSSR Approved |  | 2023-07-06 | 2023-07-12 |  | 2023-07-18 |  | Closed | 2023-07-18 | 2023-07-22 | E//Hannah | 2023-07-21 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230726 | DU00002038961 |  |  | 2023-08-22 | 2023-08-18 |  | Monopole | 24m Lampole | 30 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3
9109A | Bintulu Hospital (SACOFA) | Sarawak |  | Modernization |  | 2023Q3 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-05-17 | 2023-06-09 |  | 2023-06-26 |  | Closed | 2023-07-06 | 2023-07-13 | E//Hannah | 2023-07-12 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230516-0006 | DU00002038962 |  |  | 2023-08-10 | 2023-08-04 |  | Tower | Tower | 64M | Add R8852E S9000 x1 + R9264H M901821 x2 + A9732 M1821 x1,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 | 1
7976A | Kunak-Semporna Roudabout | Sabah |  | Modernization |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-07-12 | 2023-07-26 |  | 2023-07-31 |  | Closed | 2023-08-01 | 2023-08-11 | CD//Ray Amos | 2023-08-11 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230703.xls | DU00002038963 |  |  | 2023-08-24 | 2023-08-15 |  | Tower | Tower | 60 | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3
7465A | KG TATALUAN_T3 | Sabah |  | Modernization |  | 2023Q3 | MS | Futong | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-11 |  | 2023-05-25 |  | Closed | 2023-05-18 | 2023-06-13 | CD//Jahganathan | 2023-06-13 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0004 | DU00002038964 |  |  | 2023-07-31 | 2023-07-08 |  | Tower | Tower | 76 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
9363B | Similajau Industrial Junction (Sacofa) | Sarawak |  | Modernization |  | 2023Q3 | SH | Datasco | 4.6 TSSR Approved |  | 2023-05-15 | 2023-05-22 |  | 2023-05-25 |  | Closed | 2023-05-29 | 2023-08-07 | E//Hannah | 2023-08-07 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230516-0006 | DU00002038965 |  |  | 2024-05-18 | 2024-03-18 |  | Tower | 45m 3 Legged Tower | 76 | Add R8852E S9000 x2+R9264H M901821 x1 x1+A9732 M1821 x2,Dismantle R8860E-GU908 x3+R8882 S1800B(B6B) x4+R8862A S2100(A6A) x3 | 13(S1->S2,S2->S3,new sector is S1,rename sectorID,MM@S1/S2)
7074B | Kg. Mosopoh | Sabah |  | Decomm, MOCN By Other Vendor | Decomm->On Hold->Decomm->On Hold->Decomm | 2023Q3 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-22 |  |  |  | 2023-07-05 |  | 2023-07-11 | 2023-07-21 | CD//Jahganathan | 2023-07-12 | Celcom Digi_RAN-Futong-TSS-Sabah-20230531-0008 | DU00002038966 |  |  |  |  | 2025-11-14 |  | Tower
7693B | Semporna Paskal Semporna | Sabah |  | Modernization |  | 2023Q4 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-14 | 2023-06-17 |  | 2023-06-20 |  | Closed | 2023-06-21 | 2023-07-10 | E//Hannah | 2023-07-10 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0011 | DU00002038967 |  |  | 2023-09-18 | 2023-09-13 |  | Monopole | 30m Monopole | 30 | Add A9732 M1821 x1 + R9264M M1821 x2,Dismantle R8862A S1800(B6A) x3 | 1
7191Z | KG SIPIT MAGAI | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 |  | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002038968 | [6 empty] | Tower
7042H | 99 Speedmart ADIKA COMMERCIAL COMPLEX | Sabah |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038969 | [6 empty] | Small Cell
9003R | KAMPUNG MASKAT | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038970 | [6 empty] | Land site
7005D | Taman Jutaya | Sabah |  | Modernization |  | 2023Q3 | MS | GTSB | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-08 |  | 2023-05-11 |  | Closed | 2023-05-13 | 2023-05-17 | CD//Mohidi Jaan | 2023-05-17 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230508-0005 | DU00002038971 |  |  | 2023-07-20 | 2023-07-19 |  | Monopole | Land site | 30m | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x3,Dismantle R8894E M1821(A8A) x4 | 1
7152H | iMacro Dse Keningau | Sabah |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038972 | [6 empty] | Rooftop
7128Z | KM30 Kalabakan-Nabawan | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | AD |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002038973 | [6 empty] | Tower
7223Z | KM90 Kalabakan-Nabawan | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | AD |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002038974 | [6 empty] | Tower
7443A | Nabawan | Sabah |  | Modernization |  | 2023Q3 | MS | Futong | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-22 |  | 2023-05-26 |  | Closed | 2023-06-02 | 2023-06-22 | CD//Mohidi Jaan | 2023-06-22 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0004 | DU00002038975 |  |  | 2023-07-18 | 2023-07-11 |  | Tower | 25m pBTS | 60 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
9527A | Bintang Jaya | Sarawak |  | Modernization |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-07-14 | 2023-07-20 |  | 2023-07-27 |  | Closed | 2023-07-28 | 2023-08-07 | E//Hannah | 2023-08-03 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230613-0007 | DU00002038976 |  |  | 2023-08-29 | 2023-08-25 |  | Monopole | 30m Monopole | 30 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R9224E M1821(AAB) x3 | 123
7268C | Kampung Limbawan | Sabah |  | Modernization |  | 2023Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-15 |  | 2023-05-20 |  | Closed | 2023-05-22 | 2023-06-20 | E//Hannah | 2023-06-20 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230508-0005 | DU00002038977 |  |  | 2023-07-25 | 2023-07-08 |  | Lampole | 30M Monopole | 33 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
9076B | Kesuma Resort | Sarawak |  | Modernization |  | 2023Q4 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-08-15 | 2023-08-25 |  | 2023-09-01 |  | Closed | 2023-09-01 | 2023-09-20 | E//Hannah | 2023-09-20 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230608-0007 | DU00002038978 |  |  | 2023-09-15 | 2023-09-15 |  |  | 30m Monopole | 30 | Add R9264H M901821 x3,Dismantle R8892E M1821(BAA) x3
7192Z | KG TAMPI KAPOR | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 |  | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002038979 | [6 empty] | Tower
7264B | Ladang Binuang | Sabah |  | Modernization |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-06-21 | 2023-07-03 |  | 2023-07-06 |  | Closed | 2023-07-08 | 2023-07-13 | E//Hannah | 2023-07-13 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0010 | DU00002038980 |  |  | 2023-10-09 | 2023-09-18 |  | Tower | 45m 3 Legged Tower | 75m | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 12
7195A | Taliyan Sedu Light Ind. | Sabah |  | Modernization |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-06-17 | 2023-07-07 |  | 2023-07-17 |  | Closed | 2023-07-17 | 2023-07-28 | E//Hannah | 2023-07-28 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007 | DU00002038981 |  |  | 2023-08-22 | 2023-08-16 |  | In-Building System | 3m RT (Wall Mounted Pole) | 4m | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8882 S2600(B4A) x1+R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 | 23
9343B | Yan Min Garden | Sarawak |  | Modernization |  | 2023Q3 | BY | South Pacific | 4.6 TSSR Approved |  | 2023-05-15 | 2023-05-16 |  | 2023-05-20 |  | Closed | 2023-06-06 | 2023-06-12 | E//Hannah | 2023-06-12 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230512-0001 | DU00002038982 |  |  | 2023-08-07 | 2023-07-26 |  | Monopole | 30m Monopole | 36m | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
9316A | Sekolah Teknik Matang | Sarawak |  | Modernization |  | 2023Q4 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-09-26 | 2023-10-03 |  | 2023-10-06 |  | Closed | 2023-10-18 | 2023-11-03 | E//Hannah | 2023-11-01 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230913 | DU00002038983 |  |  | 2023-11-01 | 2023-10-28 |  | Tower | 45m 3 Legged Tower | 45 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
7004C | Selera Indah | Sabah |  | Site Out (Modernization) | Modernization->Site out->Replacement, Site Out (Modernization) | 2023Q4 | MS | YPTT | [SiteOut]- 4.5 Pending TSSR Review - Customer | Site Relocate to 7071D under CD BAU GF (Rel) Project | 2023-06-20 | 2023-07-03 |  | 2023-07-09 |  | Rectificating | 2023-07-11 |  | E//Hannah |  |  | DU00002038984 | NIC_S2_Change MM to BI,L2600 change to 40M_loading issue_OCK TELCO INFRA |  |  |  |  | Tower | 30m Monopole | 30
9007M | Miri DS Micro | Sarawak |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038985 | [6 empty] | Micro Cell
7750B | Kg. Skim Kokos | Sabah |  | Modernization |  | 2023Q4 | HQ 1 | Futong | 4.6 TSSR Approved |  | 2023-07-27 | 2023-07-26 |  | 2023-07-29 |  | Closed | 2023-07-31 | 2023-08-18 | CD//Ray Amos | 2023-08-12 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0011 | DU00002038986 |  |  | 2023-08-28 | 2023-08-23 |  | Tower | 76m 3 legged tower | 60 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
9564A | RH Akai | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038987 | [6 empty] | 60m 3 Legged Tower
9069B | TM Matang Jaya | Sarawak |  | Modernization |  | 2023Q4 | SH | South Pacific | 4.6 TSSR Approved |  | 2023-06-15 | 2023-06-20 |  | 2023-06-24 |  | Closed | 2023-06-26 | 2023-07-06 | E//Hannah | 2023-07-05 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230612-0004 | DU00002038988 |  |  | 2023-09-04 | 2023-08-21 |  | Monopole | 30m Monopole | 45M | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
9089B | Wisma Haji Suaidi | Sarawak |  | Modernization |  | 2023Q4 | BY | AllStar | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦NO,SACOFA lampole not allow to add AAU | 2023-07-10 | 2023-07-12 |  | 2023-07-18 |  | Closed | 2023-07-18 | 2023-08-16 | E//SoonHo | 2023-08-16 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230726 | DU00002038989 | NIC_S2_Change MM to BI_owner reject_SACOFA SDN BHD |  | 2023-09-05 | 2023-08-21 |  |  | 3m Bipod (RT) | 30 | Add R9264M M1821 x2+R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 23
7062A | Mile 27 | Sabah |  | Modernization |  | 2023Q3 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-05-23 | 2023-05-20 |  | 2023-05-25 |  | Closed | 2023-06-01 | 2023-06-28 | E//Hannah | 2023-06-23 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230516-0001 | DU00002038990 |  |  | 2023-07-21 | 2023-07-08 |  | Tower | 45m 3 Legged Tower | 48 | Add R9264H M901821 x3 + R9264M M1821 x2,Dismantle R8894E M1821(A8A) x3 |  | 12
7178Z | Sinua Pekan Pensiangan_Kg Senang | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038991 | [6 empty] | Tower
7622A | Bukit Tiger | Sabah |  | Modernization |  | 2023Q3 | MS | Futong | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-13 |  | 2023-05-25 |  | Closed | 2023-05-18 | 2023-05-22 | CD//Jahganathan | 2023-05-19 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0004 | DU00002038992 |  |  | 2023-08-05 | 2023-07-21 |  | Tower | Tower | 62 | Add R9264M M1821 x6 + R8862A S2601 x3,Dismantle R8894E M1821(A8A) x3 |  | 123
7129R | Ladang STS Agricultural | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038993 | [6 empty] | Tower
7461A | Nabawan RT (REL) | Sabah |  | Modernization |  | 2023Q3 | AD | Futong | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-10 |  | 2023-05-25 |  | Closed | 2023-05-20 | 2023-07-06 | E//Hannah | 2023-07-05 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0004 | DU00002038994 |  |  | 2023-07-14 | 2023-07-11 |  | Monopole | 30m Monopole | 46 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
7005H | MULTI LINE MOBILE SDN. BHD. | Sabah |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002038995 | [6 empty] | Small Cell
7058R | KG BASANAN | Sabah |  | Maintain USP MOCN(Dismantle Passive) | Maintain USP MOCN(Dismantle Passive)->On Hold->Maintain USP MOCN(Dismantle Passive) | 2023Q3 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2025-07-17 |  | 2025-07-18 |  | 2025-07-22 |  | 2025-08-05 | 2025-10-27 | E//Hannah | 2025-09-16 | SQ202508130660 - Seri Pancar | DU00002038996 |  |  |  |  | 2025-11-27 |  | Tower
9350B | KKN Similajau | Sarawak |  | Site Out (Modernization) | Modernization->Site Out->Site Out (Modernization) | 2023Q3 |  | Magicell | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2025-08-04 |  | 2025-08-25 |  |  | To be Submitted |  |  |  |  | SQ202507160538-Magicell | DU00002038997 | [6 empty] | Tower
7254C | Kolam Rekreasi Keningau | Sabah |  | Site Out (Modernization) | Modernization->On Hold->Site out->Replacement, Site Out (Modernization) | 2023Q3 | AD | GTSB | [SiteOut]- 4.5 Pending TSSR Review - Customer | Site relocate to 7065D under CD BAU GF (Rel) | 2023-05-09 | 2023-05-12 |  | 2023-05-17 |  | Rectificating | 2023-05-25 |  | E//Hannah |  | Celcom Digi_RAN-GTSB-TSS-Sabah-20230508-0005 | DU00002038998 | [5 empty] | Monopole | 30M Rapole | 30m
7125Z | KM80 Kalabakan-Nabawan | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | AD |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002038999 | [6 empty] | Tower
7171Z | Kg Maatol | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039000 | [6 empty] | Tower
7024R | Kg Tarapuli | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039001 | [6 empty] | Land site
7360A | Jeti Balimbang | Sabah |  | Modernization |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-06-26 | 2023-07-10 |  | 2023-07-01 |  | Closed | 2023-07-17 | 2023-07-27 | E//Zulakmar | 2023-07-27 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230703.xls | DU00002039002 |  |  | 2023-11-11 | 2023-08-16 |  | Tower | 45m Tower | 40M | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8862A S1800(B6A) x2+R8862A S2100(A6A) x2+R8862A S2600(A4A) x1+R8894E M1821(A8A) x2 | 123
7130Z | KM10 Kalabakan-Nabawan | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | AD |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002039003 | [6 empty] | Tower
7201A | Jalan Kuhara | Sabah |  | Modernization |  | 2023Q4 | AD | AllStar | 4.6 TSSR Approved |  | 2023-06-13 | 2023-06-21 |  | 2023-06-24 |  | Closed | 2023-06-24 | 2023-07-18 | CD//Jahganathan | 2023-07-18 | Celcom Digi_RAN-Allstar-TSS-Sabah-20230608-0004 | DU00002039004 |  |  | 2023-08-18 | 2023-08-07 |  | In-Building System | 3m RT (Minimast) | 6M | Add R9264M M1821 x5 + R8862A S2601 x2,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 |  | 13
9321A | Politeknik Matang (SACOFA) | Sarawak |  | Modernization |  | 2023Q4 | SH | Datasco | 4.6 TSSR Approved |  | 2023-07-06 | 2023-07-11 |  | 2023-07-17 |  | Closed | 2023-07-17 | 2023-07-28 | E//Hannah | 2023-07-28 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230726 | DU00002039005 |  |  | 2023-08-19 | 2023-08-11 |  | Tower | Tower | 61 | Add A9732 M1821 x1 + R9264H M901821 x2,Dismantle R8882-GUL1812 x1+R8882 S1800(B) x1+R8862A S1800(B6A) x2+R8854D S2100(A4A) x3 | 3
9332A | Rampangi(SACOFA) | Sarawak |  | Modernization |  | 2023Q4 | BY | Trintel | 4.6 TSSR Approved |  | 2023-06-22 | 2023-07-20 |  | 2023-07-25 |  | Closed | 2023-07-25 | 2023-08-03 | E//Hannah | 2023-08-03 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230622 | DU00002039006 |  |  | 2023-09-07 | 2023-08-25 |  | Tower | Tower | 77m | Add R8852E S9000 x2 + A9732 M1821 x3 + R9264H M901821 x1,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x5 | 124
7096H | Kubota Central | Sabah |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039007 | [6 empty] | Small Cell
7625B | Pulau Bum-Bum | Sabah |  | Modernization |  | 2023Q4 | AD | Futong | 4.6 TSSR Approved |  | 2023-07-13 | 2023-07-25 |  | 2023-08-01 |  | Closed | 2023-08-02 | 2023-08-11 | E//Hannah | 2023-08-11 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0011 | DU00002039008 |  |  | 2023-10-06 | 2023-08-16 |  | Tower | Tower | 60 | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 |  | 1
7695B | Tawau Taman Air Panas | Sabah |  | Modernization |  | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-06-22 | 2023-06-28 |  | 2023-07-03 |  | Closed | 2023-07-04 | 2023-07-14 | E//Hannah | 2023-07-14 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002039009 |  |  | 2023-08-07 | 2023-08-02 |  | Monopole | 30m Monopole | 30 | Add R9264H M901821 x3,Dismantle R8882 S1800(B) x2+R8882 S1800B(B6B) x1+R8862A S2100(A6A) x3
7642B | Bromas SBC | Sabah |  | Modernization |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-12 |  | 2023-06-14 |  | Closed | 2023-06-16 | 2023-07-04 | CD//Ray Amos | 2023-07-04 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0010 | DU00002039010 |  |  | 2023-08-28 | 2023-08-23 |  | Tower | Tower | 76 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
9042R | T3_0334 - KG SRIKANDUNG | Sarawak |  | Maintain USP MOCN(Dismantle Passive) | Maintain USP MOCN(Dismantle Passive)->On Hold->Maintain USP MOCN(Dismantle Passive) | 2023Q4 | HW | Magicell | 4.6 TSSR Approved |  | 2025-06-25 |  | 2025-06-26 |  | 2025-07-10 |  | 2025-08-08 | 2026-01-20 | E//John | 2025-08-11 | SQ202506110081-Magicell/SQ202507140221-Magicell | DU00002039011 |  |  |  |  | 2025-10-20 |  | Land site
7098R | KG SINULIHAN | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2023Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2025-09-25 |  | 2025-09-30 |  | 2025-10-14 |  | 2025-10-22 | 2025-10-30 | E//Hannah | 2025-10-23 | SQ202509220707 - YPTT | DU00002039012 |  |  |  |  | 2025-11-27 |  | Tower
7189Z | KG TONGKALLOH | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 |  | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002039013 | [6 empty] | Tower
7419B | Palm Oil Plantation | Sabah |  | Modernization |  | 2023Q4 | AD | Futong | 4.6 TSSR Approved |  | 2023-07-06 | 2023-07-10 |  | 2023-07-12 |  | Closed | 2023-07-14 | 2023-07-28 | CD//Mohidi Jaan | 2023-07-28 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0011 | DU00002039014 |  |  | 2023-08-20 | 2023-08-15 |  | Tower | Tower | 61 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 | 3
7070C | Kalabakan Church | Sabah |  | Modernization |  | 2023Q3 | MS | Futong | 4.6 TSSR Approved | Single Phase Power Site. Site require upgrade to 3phase incoming | 2023-05-18 | 2023-05-10 |  | 2023-05-24 |  | Rectificating | 2023-05-24 | 2023-06-01 | E//Hannah | 2023-06-01 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0004 | DU00002039015 |  |  | 2023-08-02 | 2023-07-25 |  | Monopole | 30m 3-legged tower | 30 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 | 13
7107R | KG KEBULU | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2023Q3 | AD | Datasco | 4.6 TSSR Approved | [5 empty] | 2023-05-15 |  | 2025-09-10 | 2025-10-22 | E//Hannah | 2025-09-16 | SQ202508010264 - Datasco | DU00002039016 |  |  |  |  | 2025-10-15 |  | Tower
9014B2 | pBTS Marzuki | Sarawak |  | Modernization |  | 2023Q4 | BY | South Pacific | 4.6 TSSR Approved |  | 2023-06-15 | 2023-06-26 |  | 2023-07-04 |  | Closed | 2023-07-06 | 2023-08-07 | E//Zulakmar | 2023-08-07 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230612-0004 | DU00002039017 |  |  | 2023-08-14 | 2023-08-08 |  | Watertank | 25m pBTS | 25m | Add R9264H M901821 x3,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3
9546A | Tudan Housing | Sarawak |  | Modernization |  | 2023Q4 | ZB | South Pacific | 4.6 TSSR Approved |  | 2023-06-13 | 2023-08-25 |  | 2023-09-19 |  | Closed | 2023-09-26 | 2023-10-06 | E//Hannah | 2023-10-05 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230606-0003 | DU00002039018 |  | Wrong antenna Schematic and to confirm combiner at site | 2023-10-23 | 2023-10-10 |  | Monopole | 30m Monopole | 30m | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8882 S2600(B4A) x2+R8894E M1821(A8A) x6 | 123
9583A | Teknik Miri | Sarawak |  | Modernization |  | 2023Q4 | SH | Trintel | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦no, Sacofa lampole not allow to add antenna | 2023-06-16 | 2023-06-27 |  | 2023-07-05 |  | Closed | 2023-07-14 | 2023-07-24 | E//Zulakmar | 2023-07-24 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230622 | DU00002039019 | NIC_S2_Change MM to BI_owner reject_SACOFA SDN BHD |  | 2023-08-25 | 2023-08-14 |  | Monopole | Tower | 30m | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 | 0 | 13
7651C | Masjid Babus Salam | Sabah |  | Modernization |  | 2023Q4 | AD | YPTT | 4.6 TSSR Approved |  | 2023-06-20 | 2023-06-23 |  | 2023-06-28 |  | Closed | 2023-07-02 | 2023-07-12 | E//Hannah | 2023-07-12 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002039020 |  |  | 2023-08-13 | 2023-08-08 |  |  | 30m Monopole | 30 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 23
8005Z | KgCeringingHulu | Central |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039021 | [6 empty] | 76m 4 Legged Tower
9352B | Rumah Mamat | Sarawak |  | Modernization | Maintain USP MOCN->On Hold->Maintain USP MOCN->Modernization | 2023Q3 | AI | Trintel | 4.6 TSSR Approved |  | 2025-06-09 | 2025-06-24 |  | 2025-07-02 |  | Closed | 2025-07-02 | 2025-09-24 | E//John | 2025-07-03 | SQ202506170396-Trintel | DU00002039022 |  |  | 2025-09-28 | 2025-09-26 |  | Tower | Tower | 76 | Add R8894E M1821x1 | 0 | 2
7582B | KG BERGOSONG | Sabah |  | Modernization |  | 2023Q3 | MS | Futong | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-18 |  | 2023-05-20 |  | Closed | 2023-05-23 | 2023-05-25 | E//Hannah | 2023-05-26 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0004 | DU00002039023 |  |  | 2023-08-04 | 2023-07-24 |  | Tower | 45m 3 Legged Tower | 77 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x2+R8862A S2100(A6A) x1
7700B | Kg Ulu Liawan | Sabah |  | Modernization |  | 2023Q3 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-06-06 | 2023-06-02 |  | 2023-06-07 |  | Closed | 2023-06-09 | 2023-06-22 | CD//Ray Amos | 2023-06-22 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230516-0001 | DU00002039024 |  |  | 2023-07-13 | 2023-07-08 |  | Tower | 60m 3 Legged Tower | 60m | Add R9264M M1821 x5,Dismantle R8894E M1821(A8A) x3 |  | 23
7203Z | KM120 Kalabakan-Nabawan | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | AD |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002039025 | [6 empty] | Tower
9484A | Jalan Astana 2 MP | Sarawak |  | Modernization |  | 2023Q4 | SH | Datasco | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦sacofa Reject to install AAU | 2023-07-08 | 2023-07-14 |  | 2023-07-18 |  | Closed | 2023-07-18 | 2023-08-17 | E//Hannah | 2023-07-21 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230726 | DU00002039026 | NIC_S3_Change MM to BI_owner reject_SACOFA SDN BHD |  | 2023-09-13 | 2023-09-05 |  | Tower | Tower | 30 | Add R9264M M1821 x6+R8862A S2601 x3,Dismantle R8894E M1821(A8A) x3 |  | 123
9102A | Li Hua Hotel | Sarawak |  | Modernization |  | 2023Q3 | SH | YPTT | 4.6 TSSR Approved |  | 2023-05-18 | 2023-06-22 |  | 2023-06-27 |  | Closed | 2023-07-03 | 2023-08-07 | E//Hannah | 2023-08-07 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20230524-0002 | DU00002039027 |  |  | 2023-08-02 | 2023-07-20 |  | In-Building System | 6m RT (Wall Mounted Pole) | 3 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8881 S2100 x1+R8862A S2100(A6A) x1+R8894E M1821(A8A) x3 | 123
7639B | Cowie Bay (7639B) | Sabah |  | Modernization |  | 2023Q4 | AD | Datasco | 4.6 TSSR Approved |  | 2023-06-14 | 2023-07-31 |  | 2023-08-02 |  | Closed | 2023-08-03 | 2023-08-18 | E//Hannah | 2023-08-11 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007 | DU00002039028 |  |  | 2023-08-30 | 2023-08-22 |  | In-Building System | 3m Boom (RT) |  | Add A9732 M1821 x3 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x4 | 123
9157B | Kg Samariang | Sarawak |  | Modernization |  | 2023Q4 | SH | Trintel | 4.6 TSSR Approved |  | 2023-07-15 | 2023-07-26 |  | 2023-08-03 |  | Closed | 2023-08-21 | 2023-09-01 | E//Hannah | 2023-09-01 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230622 | DU00002039029 |  |  | 2023-10-26 | 2023-09-14 |  | Lampole | 30m Rapole | 15m | Add R9264M M1821 x5 + R8862A S2601 x2,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 |  | 12
7299A8 | pBTS Damai Auto Shine (KM) | Sabah |  | Modernization |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-08-21 | 2023-09-06 |  | 2023-09-08 |  | Closed | 2023-09-08 | 2023-09-08 | CD//Ray Amos | 2023-09-08 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007 | DU00002039030 |  |  | 2023-09-12 | 2023-09-09 |  | Watertank | Portable BTS | 24m | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
9009B3 | pBTS Uma Belor Sg Asap | Sarawak |  | Modernization |  | 2023Q3 | SH | Datasco | 4.6 TSSR Approved |  | 2023-06-20 | 2023-07-03 |  | 2023-07-04 |  | Closed | 2023-07-05 | 2023-07-31 | E//Zulakmar | 2023-07-31 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230516-0006 | DU00002039031 |  |  | 2023-08-23 | 2023-08-14 |  | Tower | 25m pBTS | 29 | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3
7194A | Wisma Fuji | Sabah |  | Modernization |  | 2023Q4 | AD | YPTT | 4.6 TSSR Approved |  | 2023-06-23 | 2023-07-18 |  | 2023-07-24 |  | Closed | 2023-07-24 | 2023-07-27 | E//Hannah | 2023-07-27 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002039032 |  |  | 2023-08-13 | 2023-08-10 |  | In-Building System | 6m RT (Wall Mounted Pole) | 7 | Add R9264M M1821 x7 + R8862A S2601 x3,Dismantle R8894E M1821(A8A) x4 |  | 134
7672B | Promenade Hotel RT | Sabah |  | Modernization |  | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-06-21 | 2023-07-24 |  | 2023-07-27 |  | Closed | 2023-07-28 | 2024-02-20 | E//Hannah | 2023-10-05 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002039033 |  |  | 2023-11-11 | 2023-10-18 |  | In-Building System | 3m RT (Wall Mounted Pole) | 7 | Add R8852E S9000 x3+A9732 M1821 x3,Dismantle R8862A S2600(A4A) x1+R8894E M1821(A8A) x4 | 123 | 0
7806M | L.A studio Tawau | Sabah |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039034 | [6 empty] | Micro Cell
9130A | Rumah Minggu bintulu | Sarawak |  | Modernization |  | 2023Q3 | BY | Trintel | 4.6 TSSR Approved |  | 2023-05-15 | 2023-05-25 |  | 2023-05-31 |  | Rectificating | 2023-06-08 | 2023-06-14 | E//Hannah | 2023-06-14 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230516-0007 | DU00002039035 |  |  | 2023-07-05 | 2023-07-01 |  | Tower | 45m 3 Legged Tower | 76m | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3
9106A | Bukit Nyabau (SACOFA) (RBSC) | Sarawak |  | Modernization |  | 2023Q3 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-05-19 | 2023-06-15 |  | 2023-06-20 |  | Closed | 2023-06-27 | 2023-07-06 | E//Hannah | 2023-07-05 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230516-0006 | DU00002039036 |  |  | 2023-08-10 | 2023-07-14 |  | Tower | Tower | 115 | Add R9264M M1821 x3,Dismantle R8882 S1800B(B6B) x3
9018C | Taman Sumber Alam | Sarawak |  | Modernization |  | 2023Q4 | BY | Datasco | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-12 |  | 2023-06-15 |  | Closed | 2023-06-16 | 2023-06-27 | E//Hannah | 2023-06-27 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230608-0007 | DU00002039037 |  |  | 2023-08-11 | 2023-08-08 |  | Monopole | Tower | 30 | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
7629A | TLDM Quarters | Sabah |  | Modernization |  | 2023Q4 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-19 | 2023-06-20 |  | 2023-06-22 |  | Closed | 2023-06-23 | 2023-07-25 | CD//Jahganathan | 2023-07-21 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0011 | DU00002039038 |  |  | 2023-08-27 | 2023-08-15 |  | Tower | Tower | 76 | Add R9264M M1821 x7+R8862A S2601 x2,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8862A S2100(A6A) x4 |  | 124
7069A | MILE16KIMANIS | Sabah |  | Modernization | Modernization->Maintain USP MOCN->Modernization->Modernization->On Hold->Modernization | 2023Q3 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-05-26 | 2023-06-15 |  | 2023-06-17 |  | Closed | 2023-06-19 | 2023-06-26 | CD//Jahganathan | 2023-06-26 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230516-0001 | DU00002039039 |  |  | 2023-07-18 | 2023-07-17 |  | Tower | 106m 4 Legged Tower | 108m | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
7665B | LADANG BELIAN_T3 | Sabah |  | Decomm, MOCN By Other Vendor | Decomm->On Hold->Decomm->On Hold->Decomm | 2023Q3 | AD | Futong | 4.6 TSSR Approved |  | 2023-07-08 |  |  |  | 2023-07-10 |  | 2023-07-11 | 2023-07-21 | CD//Jahganathan | 2023-07-12 | Celcom Digi_RAN-Futong-TSS-Sabah-20230531-0008 | DU00002039040 |  |  |  |  | 2024-01-15 |  | 45m 3 Legged Tower
9597A | Marina Bay Commercial | Sarawak |  | Site Out (Modernization) | Modernization->Site Out->Site Out (Modernization) | 2023Q4 | SH | Trintel | 4.6 TSSR Approved |  | 2023-07-20 | 2023-08-02 |  | 2023-08-11 |  | Closed | 2023-08-15 | 2023-09-01 | E//Hannah | 2023-09-01 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230726 | DU00002039041 | [5 empty] | In-Building System | 3m Bipod (RT) | 3m
7066A | Perkasa Hotel KNG | Sabah |  | Modernization |  | 2023Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-05-07 | 2023-05-13 |  | 2023-05-20 |  | Closed | 2023-05-22 | 2023-05-24 | E//Hannah | 2023-05-24 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230508-0005 | DU00002039042 |  |  | 2024-01-29 | 2023-08-09 |  | Wall mount boom | 3m Boom (RT) | 9 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
9011B3 | pBTS Shin Yang Shipyard | Sarawak |  | Modernization |  | 2023Q4 | SH | Datasco | 4.6 TSSR Approved |  | 2023-06-19 | 2023-07-06 |  | 2023-07-11 |  | Closed | 2023-07-11 | 2023-07-28 | E//Hannah | 2023-07-27 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230608-0007 | DU00002039043 |  |  | 2023-09-02 | 2023-08-28 |  | Watertank | 25m pBTS | 30 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3
7646C | DMart (REL) | Sabah |  | Modernization |  | 2023Q4 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-10 |  | 2023-06-15 |  | Closed | 2023-06-16 | 2023-07-07 | CD//Mohidi Jaan | 2023-07-04 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0011 | DU00002039044 |  |  | 2023-09-27 | 2023-09-06 |  | Pole | Land site | 6 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8862A S1800(B6A) x2+R8862A S2100(A6A) x2+R8862A S2601(A6A) x2+R8854 S2600(A4A) x1+R8894E M1821(A8A) x2+R9224E M1821(AAB) x2 | 123
7888A | Taman MDK | Sabah |  | Modernization |  | 2023Q3 | AD | Trintel | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-12 |  | 2023-05-22 |  | Closed | 2023-05-22 | 2023-06-28 | E//Hannah | 2023-06-23 | Celcom Digi_RAN-Trintel-TSS-Sabah-20230508-0001 | DU00002039045 |  |  | 2023-07-14 | 2023-07-08 |  | Monopole | 30m Monopole | 30 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2,Dismantle R9224E M1821(AAB) x3 | 3
7263B | Ladang Sunggang | Sabah |  | Modernization |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-06-19 | 2023-07-04 |  | 2023-06-30 |  | Closed | 2023-07-11 | 2023-07-18 | E//Hannah | 2023-07-17 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0010 | DU00002039046 |  |  | 2023-10-01 | 2023-09-14 |  | Tower | 45m 3 Legged Tower | 75 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
9369B | Taman Bamboo | Sarawak |  | Modernization |  | 2023Q3 | BY | South Pacific | 4.6 TSSR Approved |  | 2023-07-30 | 2023-08-10 |  | 2023-08-15 |  | Closed | 2023-08-17 | 2023-09-01 | E//Hannah | 2023-09-01 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230512-0001 | DU00002039047 |  |  | 2023-10-04 | 2023-09-21 |  | Monopole | 30m Rapole | 12 | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8882 S1800(B) x3+R8862A S2100(A6A) x3 |  | 1
7480A | Taman Sabana | Sabah |  | Site Out (Modernization) | Modernization->Site out->Replacement, Site Out (Modernization) | 2023Q3 | MS | YPTT | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2025-06-21 |  | 2025-06-24 | [5 empty] | CD//Ray Amos |  | SQ202506160230 - YPTT | DU00002039048 | [6 empty] | 30m Monopole
9515A | Pasar Lutong MP | Sarawak |  | Modernization |  | 2023Q4 | HQ 1 | Magicell | 4.6 TSSR Approved |  | 2023-06-22 | 2023-06-26 |  | 2023-06-28 |  | Closed | 2023-07-03 | 2023-07-25 | E//Hannah | 2023-07-18 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002039049 |  |  | 2023-08-07 | 2023-08-01 |  | Monopole | 30m Monopole | 30m | Add R9264H M901821 x4,Dismantle R8882 S1800B(B6B) x3+R8862A S1800(B6A) x1+R8862A S2100(A6A) x4
7653C | Taman Uni Villa | Sabah |  | Modernization |  | 2023Q4 | AD | YPTT | 4.6 TSSR Approved |  | 2023-06-22 | 2023-06-27 |  | 2023-07-05 |  | Closed | 2023-07-05 | 2023-07-15 | CD//Jahganathan | 2023-07-14 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002039050 |  |  | 2023-08-13 | 2023-08-08 |  | Monopole | 30m Monopole | 30 | Add A9732 M1821 x1 + R9264M M1821 x3,Dismantle R8894E M1821(A8A) x4 | 3
7665A | Petronas Kalabakan | Sabah |  | Modernization |  | 2023Q3 | MS | Futong | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-12 |  | 2023-05-25 |  | Closed | 2023-05-20 | 2023-05-22 | CD//Mohidi Jaan | 2023-05-21 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0004 | DU00002039051 |  |  | 2023-08-03 | 2023-07-27 |  | Monopole | 30m Monopole | 45 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 123
7207A | Sim Seng Lee | Sabah |  | Modernization |  | 2023Q4 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-19 | 2023-06-19 |  | 2023-06-21 |  | Closed | 2023-06-22 | 2023-07-21 | CD//Jahganathan | 2023-07-21 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0011 | DU00002039052 |  |  | 2023-09-27 | 2023-09-07 |  | Tower | Tower | 45 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8854E S1800(A6A) x5+R8854D S2100(A4A) x5+R8854 S2600(A4A) x2 | 123
7855A | Promenade Hotel Tawau IB | Sabah |  | Modernization |  | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-06-22 | 2023-07-17 |  | 2023-07-28 |  | Closed | 2023-07-31 | 2023-08-08 | E//Nazrul | 2023-08-08 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002039053 |  |  | 2023-09-04 | 2023-08-30 |  | Portables BTS | In-building system |  | Add R8862A S2100 x3
9004C | Batu 5 Bintulu | Sarawak |  | Modernization |  | 2023Q3 | SH | South Pacific | 4.6 TSSR Approved |  | 2023-05-15 | 2023-06-22 |  | 2023-07-03 |  | Closed | 2023-07-04 | 2023-07-13 | E//Hannah | 2023-07-13 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230512-0001 | DU00002039054 |  |  | 2023-07-29 | 2023-07-26 |  | Monopole | 30m Rapole | 31 | Add R9264H M901821 x1 + R9264M M1821 x3,Dismantle R8862A S1800(B6A) x4+++R8862A S2100(A6A) x4
7649B | Seafest Hotel | Sabah |  | Modernization |  | 2023Q4 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-27 | 2023-06-26 |  | 2023-06-28 |  | Closed | 2023-07-03 | 2023-07-21 | E//Yadav | 2023-07-20 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0011 | DU00002039055 |  |  | 2023-09-11 | 2023-09-06 |  | Wall mount boom | 3m RT (Wall Mounted Pole) | 3 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x5 | 12
7574B | Bukit Forbes | Sabah |  | Modernization |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-06-21 | 2023-06-26 |  | 2023-06-30 |  | Closed | 2023-07-02 | 2023-07-14 | E//Yadav | 2023-07-13 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0010 | DU00002039056 |  |  | 2023-10-02 | 2023-09-14 |  | Tower | 45m 3 Legged Tower | 75 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3
7447A | Patikang | Sabah |  | Modernization |  | 2023Q3 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-05-15 | 2023-05-19 |  | 2023-05-23 |  | Closed | 2023-05-25 | 2023-06-02 | E//Nizar | 2023-06-02 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230516-0001 | DU00002039057 |  |  | 2023-07-14 | 2023-07-11 |  | Tower | 60m 3 Legged Tower | 60 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
7141R | Jalan Kimanis-Keningau_1 | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039058 | [6 empty] | Land site
9289B | Times Square Bintulu RT | Sarawak |  | Modernization |  | 2023Q3 | ZB | YPTT | 4.6 TSSR Approved |  | 2023-06-08 | 2023-08-23 |  | 2023-08-27 |  | Closed | 2023-08-28 | 2023-09-15 | E//Hannah | 2023-09-15 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20230622 | DU00002039059 |  |  | 2023-10-30 | 2023-09-24 |  | Pole | 3m Bipod (RT) | 3 | Add A9732 M1821 x3 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x4 | 123
7091H | Bas Terminal Tawau | Sabah |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039060 | [6 empty] | Small Cell
9006M | Bintulu DS Micro | Sarawak |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039061 | [6 empty] | Micro Cell
7960A | Umas | Sabah |  | Modernization |  | 2023Q3 | AD | Futong | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-13 |  | 2023-05-25 |  | Closed | 2023-05-20 | 2023-06-24 | E//Hannah | 2023-06-23 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0004 | DU00002039062 |  |  | 2023-08-09 | 2023-08-02 |  | Tower | Tower | 75 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8881 S9000 x3+R8854E S1800(A6A) x3+R8854D S2100(A4A) x3 | 123
7230C | Kampung Terusan Tengah Lama | Sabah |  | Modernization |  | 2023Q4 | MS | Futong | 4.6 TSSR Approved |  | 2023-07-03 | 2023-07-03 |  | 2023-07-05 |  | Closed | 2023-07-06 | 2023-07-14 | E//Hannah | 2023-07-14 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0011 | DU00002039063 |  |  | 2023-09-19 | 2023-09-07 |  | Tower | 60m 4 Legged Tower | 60 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 12
7009C | Kg Kongsi 8 | Sabah |  | Modernization |  | 2023Q4 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-06-13 | 2023-06-15 |  | 2023-06-18 |  | Closed | 2023-06-19 | 2023-07-14 | CD//Ray Amos | 2023-07-14 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230612-0004 | DU00002039064 |  |  | 2023-08-16 | 2023-08-09 |  | Monopole | 30m Lampole | 30m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
7194Z | LADANG KERUING | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | AD |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002039065 | [6 empty] | Tower
9483A | CIDB Petra Jaya | Sarawak |  | Modernization |  | 2023Q4 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-07-15 | 2023-08-25 |  | 2023-08-30 |  | Closed | 2023-09-07 | 2023-10-02 | E//Hannah | 2023-09-25 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230726 | DU00002039066 |  | Awaiting final solution Sector 3 | 2023-10-10 | 2023-09-19 |  | Tower | Tower | 76 | Add R9264M M1821 x5+R8862A S2601 x1,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x2 |  | 3
7704B | Kg. Kandang Besar | Sabah |  | Modernization |  | 2023Q3 | AD | Datasco | 4.6 TSSR Approved |  | 2023-05-25 | 2023-07-10 |  | 2023-07-12 |  | Closed | 2023-07-13 | 2023-07-15 | E//Hannah | 2023-07-14 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230508-0004 | DU00002039067 |  |  | 2023-07-23 | 2023-07-19 |  | Tower | Tower | 76m | Add R9264M M1821 x6 + R8862A S2601 x6,Dismantle R8894E M1821(A8A) x3 |  | 123
9016Z | UMA BALOI LIKO | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | N/A - no need PR for MOCN Decomm | DU00002039068 | [6 empty] | Land site
7579B | Balung Cocos | Sabah |  | Modernization |  | 2023Q4 | HQ 1 | Datasco | 4.6 TSSR Approved |  | 2023-06-11 | 2023-06-27 |  | 2023-06-30 |  | Closed | 2023-07-03 | 2023-07-14 | E//Hannah | 2023-07-14 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007 | DU00002039069 |  |  | 2023-08-16 | 2023-08-12 |  | Monopole | Tower | 60 | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle R9224E M1821(AAB) x3 |  | 1
7667B | Bromas Camp Tawau | Sabah |  | Modernization |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-13 |  | 2023-06-17 |  | Closed | 2023-06-19 | 2023-07-06 | CD//Ray Amos | 2023-07-04 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0010 | DU00002039070 |  |  | 2023-10-02 | 2023-09-19 |  | Tower | 4 Legged Tower | 80m | Add R9264H M901821 x3 + R9264M M1821 x2,Dismantle R8894E M1821(A8A) x3 |  | 13
7633B | Luasong Junction SBC | Sabah |  | Modernization |  | 2023Q3 | AD | Futong | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-12 |  | 2023-05-24 |  | Closed | 2023-05-24 | 2023-06-24 | E//Hannah | 2023-06-23 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0004 | DU00002039071 |  |  | 2023-08-21 | 2023-08-02 |  | Tower | Tower | 60m | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3+R8881 S2100 x3 |  | 2
9330B | Upmbtu | Sarawak |  | Modernization |  | 2023Q3 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-05-15 | 2023-05-25 |  | 2023-05-31 |  | Rectificating | 2023-06-12 | 2023-06-22 | E//Hannah | 2023-06-22 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230516-0006 | DU00002039072 |  |  | 2023-08-09 | 2023-08-03 |  | Monopole | 30m Monopole | 36m | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8882-GUL1812 x4+R8894E M1821(A8A) x3 | 123
7224H | 99 Speedmart Plaza Palma | Sabah |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039073 | [6 empty] | Rooftop
7669B | Kg Melati | Sabah |  | Modernization |  | 2023Q3 | AD | Futong | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-15 |  | 2023-05-19 |  | Closed | 2023-05-24 | 2023-07-14 | E//Hannah | 2023-07-14 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0004 | DU00002039074 |  |  | 2023-08-07 | 2023-08-03 |  | Tower | 45m 3 Legged Tower | 61 | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 |  | 2
7655B | HOSPITAL TAWAU RT | Sabah |  | Modernization |  | 2023Q4 | AD | YPTT | 4.6 TSSR Approved | Single Phase Power Site. Site require upgrade to 3phase incoming | 2023-06-23 | 2023-06-28 |  | 2023-07-05 |  | Closed | 2023-07-05 | 2023-07-13 | E//Thien | 2023-07-13 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002039075 |  |  | 2023-08-07 | 2023-08-02 |  | Lampole | 24m Lampole | 30 | Add R9264H M901821 x3,Dismantle R8882 S1800B(B6B) x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3
7670B | Great Eastern Tawau | Sabah |  | Modernization |  | 2023Q4 | AD | AllStar | 4.6 TSSR Approved |  | 2023-06-11 | 2023-06-28 |  | 2023-07-04 |  | Closed | 2023-07-04 | 2023-07-12 | E//Hannah | 2023-07-12 | Celcom Digi_RAN-Allstar-TSS-Sabah-20230608-0004 | DU00002039076 |  |  | 2023-08-14 | 2023-08-07 |  | In-Building System | 3m Bipod (RT) | 6m | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2,Dismantle R8882 S1800B(B6B) x3++R8881 S2100 x3+ | 3
9123A | Kidurong Residential (SACOFA) | Sarawak |  | Modernization |  | 2023Q3 | SH | CCSMY | 4.6 TSSR Approved |  | 2023-05-17 | 2023-06-09 |  | 2023-06-22 |  | Closed | 2023-07-03 | 2023-09-01 | E//Hannah | 2023-09-01 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230516-0006 | DU00002039077 |  |  | 2023-08-22 | 2023-08-02 |  | Tower | Tower | 47M | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x2,Dismantle R8882 S1800B(B6B) x2 |  | 2(existing S2 -> S3,Addition Sector, name S2,need rename Sector ID,Bisector@new S3)
7694B | Tawau Taman Indah Bt 10 Tawau | Sabah |  | Modernization |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-06-21 | 2023-07-27 |  | 2023-08-09 |  | Closed | 2023-08-16 | 2023-09-01 | CD//Ray Amos | 2023-08-16 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007 | DU00002039078 |  |  | 2023-08-29 | 2023-08-22 |  | Monopole | 30m Monopole | 30 | Add R9264H M901821 x3,Dismantle R8882 S1800(B) x1+R8882 S1800B(B6B) x2+R8862A S2100(A6A) x3
9514A | Piasau Jaya Anchi MP | Sarawak |  | Modernization |  | 2023Q4 | BY | South Pacific | 4.6 TSSR Approved |  | 2023-06-10 | 2023-06-20 |  | 2023-06-23 |  | Closed | 2023-06-23 | 2023-07-13 | E//Hannah | 2023-07-14 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230606-0003 | DU00002039079 |  |  | 2023-08-26 | 2023-08-21 |  | Monopole | 30m Monopole | 31m | Add R8852E S9000 x3 + A9732 M1821 x3 + R9264H M901821 x1,Dismantle R8882 S1800B(B6B) x3+R8862A S1800(B6A) x1+R8854D S2100(A4A) x4 | 123
7448A | Jln Low Cost | Sabah |  | Modernization |  | 2023Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-20 |  | 2023-05-25 |  | Closed | 2023-05-26 | 2023-06-24 | E//Hannah | 2023-06-23 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230508-0005 | DU00002039080 |  |  | 2023-07-16 | 2023-07-11 |  | Tower | Tower | 46 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
7075B | Kg. Karamatoi Ulu | Sabah |  | Modernization |  | 2023Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-13 |  | 2023-05-17 |  | Closed | 2023-05-18 | 2023-08-07 | CD//Mohidi Jaan | 2023-05-21 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230508-0005 | DU00002039081 |  |  | 2023-07-13 | 2023-07-11 |  | Tower | Tower | 76 | Add R9264M M1821 x4+R9264H M901821 x1,Dismantle R8894E M1821(A8A) x3 |  | 2
7937A | Ladang Giram | Sabah |  | Modernization | Modernization->Maintain USP MOCN->Modernization->On Hold->Modernization | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-06-16 | 2023-06-20 |  | 2023-06-22 |  | Under Approval | 2023-06-23 | 2025-07-18 | E//Hannah | 2025-06-13 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0010 | DU00002039082 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed |  |  |  | Tower | Tower | 60 | Add R8894E M1821x1 | 0 | 1
7726B | Surau Kurnia Jaya | Sabah |  | Modernization |  | 2023Q4 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-06-15 | 2023-06-21 |  | 2023-06-24 |  | Closed | 2023-07-03 | 2023-07-13 | E//Hannah | 2023-07-12 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230612-0004 | DU00002039083 |  |  | 2023-08-29 | 2023-08-11 |  | Monopole | 30m Monopole | 30m | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x4 | 13
7202Z | KM110 Kalabakan-Nabawan | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | AD |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002039084 | [6 empty] | Tower
7683B | Semporna Town | Sabah |  | Modernization |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-09-07 | 2023-10-03 |  | 2023-10-11 |  | Closed | 2023-10-11 | 2023-11-15 | E//Hannah | 2023-11-08 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230703.xls | DU00002039085 |  |  | 2023-12-12 | 2023-11-11 |  | Lampole | 30m Monopole | 30 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
7108R | KG KAPAYAN LAMA | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2023Q3 | AD | Datasco | 4.6 TSSR Approved | [5 empty] | 2023-05-16 |  | 2025-09-10 | 2025-10-22 | E//Hannah | 2025-09-16 | SQ202508010264 - Datasco | DU00002039086 |  |  |  |  | 2025-11-27 |  | Tower
9465A | Telega Air | Sarawak |  | Modernization |  | 2023Q4 | SH | Datasco | 4.6 TSSR Approved |  | 2023-06-22 | 2023-07-04 |  | 2023-07-07 |  | Closed | 2023-07-07 | 2023-07-20 | E//Zulakmar | 2023-07-20 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230608-0007 | DU00002039087 |  |  | 2023-08-24 | 2023-08-15 |  | Tower | 45m 3 Legged Tower | 76 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
9120A | Mile 16 Bintulu | Sarawak |  | Modernization |  | 2023Q3 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-05-24 | 2023-06-26 |  | 2023-06-30 |  | Closed | 2023-07-03 | 2023-07-14 | E//Hannah | 2023-07-13 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20230526-0003 | DU00002039088 |  |  | 2023-08-08 | 2023-08-01 |  | Tower | Tower | 65 | Add R9264M M1821 x4,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 2
9027B | Kg Sejijak | Sarawak |  | Modernization |  | 2023Q4 | SH | AllStar | 4.6 TSSR Approved |  | 2023-06-21 | 2023-06-27 |  | 2023-07-03 |  | Closed | 2023-07-04 | 2023-07-25 | E//Hannah | 2023-07-18 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230622 | DU00002039089 |  |  | 2023-08-14 | 2023-08-08 |  | Tower | Tower | 76M | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2,Dismantle R8894E M1821(A8A) x3 | 3
7186Z | PEKAN KALABAKAN | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | AD |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002039090 | [6 empty] | Tower
7620A | Plaza Tinagat | Sabah |  | Modernization |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-06-15 | 2023-07-05 |  | 2023-07-08 |  | Closed | 2023-07-10 | 2023-07-21 | E//Hannah | 2023-07-20 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007 | DU00002039091 |  |  | 2023-08-23 | 2023-08-14 |  | Wall mount boom | 3m RT (Wall Mounted Pole) | 6m | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R9224E M1821(AAB) x3 |  | 2
7355A | Semporna Batu 2 | Sabah |  | Modernization |  | 2023Q4 | MS | Futong | 4.6 TSSR Approved |  | 2023-06-20 | 2023-06-17 |  | 2023-06-21 |  | Closed | 2023-06-22 | 2023-07-17 | CD//Mohidi Jaan | 2023-07-17 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0011 | DU00002039092 |  |  | 2023-09-19 | 2023-09-07 |  | Monopole | 30m Monopole | 30 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x2,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x4+R9224E M1821(AAB) x2 | 24
9588A | ShinYang Celcom | Sarawak |  | Modernization |  | 2023Q4 | SH | Datasco | 4.6 TSSR Approved |  | 2023-06-19 | 2023-07-17 |  | 2023-08-01 |  | Closed | 2023-08-02 | 2023-08-11 | E//Hannah | 2025-05-18 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230608-0007 | DU00002039093 |  | Remarks: Solution Changed | 2025-04-12 | 2025-02-24 |  | Monopole | Tower | 30 | Add R8852E S9000 x3+R8894E M1821 x3+R8862A S2601 x1,Dismantle R8882 S1800B(B6B) x3+R8881 S2100 x2+R8862A S2600(A4A) x1
7449A | Desa Kim Loong | Sabah |  | Modernization |  | 2023Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-05-17 | 2023-05-09 |  | 2023-05-26 |  | Closed | 2023-06-01 | 2023-06-11 | E//Hannah | 2023-06-11 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230508-0005 | DU00002039094 |  |  | 2023-07-16 | 2023-07-14 |  | Tower | 76m 3 Legged Tower | 76 | Add R9264M M1821 x6,Dismantle R8894E M1821(A8A) x3 |  | 123
7025R | Kg Ranggu | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039095 | [6 empty] | Land site
7936A | Pengkalan Madai (Celcom) | Sabah |  | Modernization |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-06-21 | 2023-06-26 |  | 2023-06-28 |  | Closed | 2023-07-02 | 2023-07-13 | E//Hannah | 2023-07-13 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0010 | DU00002039096 |  |  | 2023-10-18 | 2023-09-14 |  | Tower | 60m 4 Legged Tower | 65m | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 23
9004B13 | pBTS 7 Inn Hotel | Sabah |  | Modernization |  | 2023Q4 | MS | Futong | 4.6 TSSR Approved |  | 2023-06-20 | 2023-06-13 |  | 2023-06-22 |  | Closed | 2023-06-19 | 2023-07-06 | E//Hannah | 2023-07-04 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0011 | DU00002039097 |  |  | 2023-08-29 | 2023-08-22 |  | Tower | 24m PBTS | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
7046B | Taman Semarak | Sabah |  | Modernization |  | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-06-20 | 2023-06-23 |  | 2023-07-03 |  | Closed | 2023-07-04 | 2023-07-12 | E//Hannah | 2023-07-12 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002039098 |  |  | 2023-08-18 | 2023-08-02 |  | Monopole | 30m Monopole | 30 | Add A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 | 12
7258C | Kinabutan Garden | Sabah |  | Modernization |  | 2023Q4 | HQ 1 | South Pacific | 4.6 TSSR Approved |  | 2023-07-12 | 2023-07-14 |  | 2023-07-18 |  | Closed | 2023-07-20 | 2023-07-28 | CD//Mohidi Jaan | 2023-07-28 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230612-0004 | DU00002039099 |  |  | 2023-08-22 | 2023-08-14 |  | Monopole | Land site | 31 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
7674B | Taman Melinium Tawau | Sabah |  | Modernization |  | 2023Q4 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-06-14 | 2023-06-20 |  | 2023-06-22 |  | Closed | 2023-06-23 | 2023-07-24 | CD//Ray Amos | 2023-07-24 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230612-0004 | DU00002039100 |  |  | 2023-08-16 | 2023-08-11 |  | Monopole | 30m Monopole | 30 | Add R9264H M901821 x3,Dismantle R9224E M1821(AAB) x3
9342B | Puspakom Bintulu | Sarawak |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-06-20 | 2023-07-11 |  | 2023-07-16 |  | Closed | 2023-07-20 | 2023-07-26 | E//Hannah | 2023-07-25 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230516-0006 | DU00002039101 |  |  | 2023-12-26 | 2023-08-15 |  | Tower | 45m 3 Legged Tower | 60m | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8882 S1800B(B6B) x3 | 12
7202B | Tawau SMK Tawau | Sabah |  | Modernization |  | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-06-22 | 2023-07-17 |  | 2023-07-24 |  | Closed | 2023-07-28 | 2023-07-28 | CD//Ray Amos | 2023-07-28 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002039102 |  |  | 2023-08-16 | 2023-08-08 |  | Monopole | 30m Monopole | 30 | Add A9732 M1821 x1 + R9264M M1821 x2,Dismantle R8882 S1800(B) x1+R8882 S1800B(B6B) x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x4+R8862A S2601(A6A) x1 | 2
9128B | Samalaju-Lodging | Sarawak |  | Modernization |  | 2023Q3 | BY | Magicell | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI,L2600 change to 40M¦site owner Maxis not allow to add AAU | 2023-05-11 | 2023-05-12 |  | 2023-05-16 |  | Closed | 2023-05-18 | 2023-05-19 | CD//John | 2023-05-18 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230512-0007 | DU00002039103 | NIC_S2_Change MM to BI,L2600 change to 40M_owner reject_SACOFA SDN BHD |  | 2023-08-22 | 2023-08-09 |  | Monopole | 24m Lampole | 30m | Add R9264H M901821 x3 + R9264M M1821 x2,Dismantle R8894E M1821(A8A) x4 |  | 23
7621B | Kelumpang | Sabah |  | Modernization |  | 2023Q4 | MS | Futong | 4.6 TSSR Approved |  | 2023-06-20 | 2023-06-21 |  | 2023-06-23 |  | Closed | 2023-07-03 | 2023-07-25 | E//Yadav | 2023-07-21 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0011 | DU00002039104 |  |  | 2023-08-28 | 2023-08-22 |  | Tower | Tower | 60 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R9224E M1821(AAB) x3 | 13
7636B | Heritage Hotel | Sabah |  | Modernization |  | 2023Q4 | AD | AllStar | 4.6 TSSR Approved |  | 2023-06-21 | 2023-06-28 |  | 2023-07-05 |  | Closed | 2023-07-08 | 2023-07-12 | E//Hannah | 2023-07-12 | Celcom Digi_RAN-Allstar-TSS-Sabah-20230608-0004 | DU00002039105 |  |  | 2023-08-20 | 2023-08-07 |  | In-Building System | 6m RT (Wall Mounted Pole) | 7M | Add R9264M M1821 x5,Dismantle R8894E M1821(A8A) x4 |  | 4
7137R | Jalan Batu 63 Nabawan-Sapulot | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039106 | [6 empty] | Land site
9168B | Taman Malihah 1 | Sarawak |  | Modernization |  | 2023Q4 | ZB | AllStar | 4.6 TSSR Approved |  | 2023-07-06 | 2023-07-11 |  | 2023-07-31 |  | Closed | 2023-08-01 | 2023-08-14 | E//Hannah | 2023-08-14 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230726 | DU00002039107 |  |  | 2023-09-18 | 2023-08-22 |  | Monopole | 30m Rapole | 30 | Add R9264M M1821 x5,Dismantle R8894E M1821(A8A) x3 |  | 13
7269B | Taman Adika Phase 2 | Sabah |  | Modernization |  | 2023Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-05-07 | 2023-05-09 |  | 2023-05-16 |  | Closed | 2023-05-17 | 2023-05-18 | CD//Mohidi Jaan | 2023-05-18 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230508-0005 | DU00002039108 |  |  | 2023-07-14 | 2023-07-08 |  | Lampole | 30M Monopole | 33 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x2,Dismantle R8862A S1800(B6A) x2+R8862A S2100(A6A) x2+R8894E M1821(A8A) x3+R8862A S2601(A6A) x1 | 24
7204A | Balung New Airport | Sabah |  | Decomm | On Hold->Decomm | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-11-27 |  |  |  | 2023-12-01 |  | 2023-12-01 |  | CD//Jahganathan | 2023-12-14 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007/0920CD-Sabah-Datasco-BOQ Template (old contract) | DU00002039109 |  |  |  |  | 2023-12-22 |  | Watertank Structure
7203A | Pasir Putih | Sabah |  | Modernization |  | 2023Q4 | AD | YPTT | 4.6 TSSR Approved |  | 2023-06-20 | 2023-07-03 |  | 2023-07-06 |  | Closed | 2023-07-07 | 2023-07-15 | E//Hannah | 2023-07-14 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002039110 |  |  | 2023-08-03 | 2023-07-28 |  | Tower | 45m 3 Legged Tower | 60 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
9625B | Masjid Jamek Kuching | Sarawak |  | Modernization |  | 2023Q4 | ZB | Datasco | 4.6 TSSR Approved |  | 2024-01-25 | 2024-01-26 |  | 2024-02-03 |  | Closed | 2024-02-06 | 2024-02-13 | E//Hannah | 2024-02-13 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20240124 | DU00002039111 |  |  | 2024-03-14 | 2024-03-05 |  | Monopole | Tower | 30 | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 3 | 0
7207Z | Kapilit Estate | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039112 | [6 empty] | Land site
9429A | Tmn Maliha 2 MP | Sarawak |  | Modernization |  | 2023Q4 | SH | Datasco | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦sacofa Reject to install AAU | 2023-07-05 | 2023-07-14 |  | 2023-07-18 |  | Closed | 2023-07-18 | 2023-07-22 | E//Hannah | 2023-07-21 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230726 | DU00002039113 | NIC_S3_Change MM to BI_owner reject_SACOFA SDN BHD |  | 2023-11-11 | 2023-09-05 |  | Tower | 30m Monopole | 45 | Add R9264M M1821 x6+R8862A S2601 x3,Dismantle R8894E M1821(A8A) x3 |  | 123
7647B | SMK Bum Bum SBC | Sabah |  | Modernization |  | 2023Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-06-26 | 2023-07-05 |  | 2023-06-30 |  | Closed | 2023-07-11 | 2023-07-22 | E//Hannah | 2023-07-21 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230703.xls | DU00002039114 |  |  | 2023-10-19 | 2023-09-13 |  | Tower | Tower | 60M | Add R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3
9063R | TM TUBAU BINTULU | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2023Q3 | BY | South Pacific | 4.6 TSSR Approved |  | 2023-05-23 | 2023-06-26 |  |  | 2023-06-14 |  | 2023-06-19 | 2026-01-20 | E//Hannah | 2025-10-23 | SQ202511180354 - Southpac | DU00002039115 |  |  |  |  | 2025-11-20 | Tower | Tower | 80
7022C | UMW Tawau | Sabah |  | Modernization |  | 2023Q4 | AD | AllStar | 4.6 TSSR Approved |  | 2023-06-15 | 2023-06-26 |  | 2023-06-29 |  | Closed | 2023-07-02 | 2023-07-12 | E//Hannah | 2023-07-12 | Celcom Digi_RAN-Allstar-TSS-Sabah-20230608-0004 | DU00002039116 |  |  | 2023-08-13 | 2023-08-07 |  | Monopole | 30m Lampole | 30M | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
7610A | Merotai (Maxis) | Sabah |  | Modernization |  | 2023Q3 | AD | Futong | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-26 |  | 2023-05-31 |  | Closed | 2023-06-01 | 2023-06-22 | E//Hannah | 2023-06-22 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0004 | DU00002039117 |  |  | 2023-07-23 | 2023-07-14 |  | Tower | 76m 4 Legged Tower | 78 | Add R9264H M901821 x4 + R9264M M1821 x3,Dismantle R8860E-GU908 x3+R8894E M1821(A8A) x4 |  | 124
9355B | Kidurong Ind (Celcom) | Sarawak |  | Modernization |  | 2023Q3 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-05-20 | 2023-07-04 |  | 2023-07-11 |  | Closed | 2023-08-01 | 2023-08-14 | E//Hannah | 2023-08-14 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230516-0006 | DU00002039118 |  |  | 2024-02-29 | 2024-01-29 |  | Tower | 60m 3 Legged Tower | 60M | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
7047C | Taman Gaya Tawau | Sabah |  | Modernization |  | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-06-23 | 2023-06-26 |  | 2023-07-03 |  | Closed | 2023-07-04 | 2023-07-12 | E//Hannah | 2023-07-12 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002039119 |  |  | 2023-08-09 | 2023-08-05 |  | Unipole | Tower | 12 | Add R9264M M1821 x5 + R8862A S2601 x2,Dismantle R9224E M1821(AAB) x3 |  | 23
7129Z | KM20 Kalabakan-Nabawan | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | AD |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002039120 | [6 empty] | Tower
9021A | Pasir Pandak | Sarawak |  | Modernization |  | 2023Q4 | BY | Datasco | 4.6 TSSR Approved |  | 2023-06-15 | 2023-06-10 |  | 2023-06-15 |  | Closed | 2023-06-16 | 2023-07-22 | E//Hannah | 2023-07-21 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230608-0007 | DU00002039121 |  |  | 2023-08-22 | 2023-08-14 |  | Tower | Tower | 30 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x2,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x1+R8862A S2100(A6A) x2 |  | 1
7176H | 99 Speedmart Jutaya Commercial | Sabah |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039122 | [6 empty] | Small Cell
7935A | Bukit Cenderawasih | Sabah |  | Modernization | Modernization->Decomm->Modernization->On Hold->Modernization | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-06-19 | 2023-06-21 |  | 2023-06-24 |  | Closed | 2023-07-03 | 2025-05-21 | E//Hannah | 2025-05-18 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0010 | DU00002039123 |  | Remarks: Solution Changed SOW Changed Decomm to Mod | 2025-06-12 | 2025-06-11 |  | Tower | Tower | 76 | Add R9264M M1821x3, Dismantle R8894E M1821(A8A)x3 | 0 | 123
7313B | Rich Park | Sabah |  | Modernization |  | 2023Q4 | HQ 1 | Datasco | 4.6 TSSR Approved |  | 2023-06-10 | 2023-06-26 |  | 2023-06-30 |  | Closed | 2023-07-03 | 2023-07-17 | E//Hannah | 2023-07-17 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007 | DU00002039124 |  |  | 2023-08-28 | 2023-08-23 |  | Monopole | 30m Monopole | 30 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8854 S2600(A4A) x2+R9224E M1821(AAB) x5 | 12
7613A | JALANMAKTAB | Sabah |  | Modernization |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-07-11 | 2023-07-13 |  | 2023-07-18 |  | Closed | 2023-07-21 | 2023-07-25 | E//Hannah | 2023-07-25 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007 | DU00002039125 |  |  | 2023-08-23 | 2023-08-22 |  | Tower | 76m 4 Legged Tower | 76m | Add R9264H M901821 x2 + R9264M M1821 x3 + R8862A S2601 x2,Dismantle R8881 S9000 x2+R9224E M1821(AAB) x3 |  | 13
9118A | Tmn Pertanian Sarawak | Sarawak |  | Modernization |  | 2023Q3 | ZB | YPTT | 4.6 TSSR Approved |  | 2023-06-10 | 2023-08-16 |  | 2023-08-22 |  | Closed | 2023-08-23 | 2023-10-06 | E//Hannah | 2023-10-05 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20230612-0006 | DU00002039126 |  |  | 2023-10-09 | 2023-09-19 |  | Tower | 45m 3 Legged Tower | 75 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8860E-GU908 x2+R8882 S1800B(B6B) x3+R8854D S2100(A4A) x3 | 23
9347B | Sg Asap | Sarawak |  | Modernization |  | 2023Q3 | BY | Datasco | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦Sector2 MM change to BI | 2023-05-16 | 2023-05-18 |  | 2023-05-23 |  | Rectificating | 2023-06-08 | 2023-08-07 | E//Hannah | 2023-08-07 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230516-0006 | DU00002039127 | NIC_S1_Change MM to BI_owner reject_SACOFA SDN BHD |  | 2024-05-20 | 2024-04-20 |  | Tower | 60m 4 Legged Tower | 90 | Add R9264M M1821 x5,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 |  | 3
7459A | Kg. Malima Sook | Sabah |  | Modernization | Modernization->Maintain USP MOCN->Modernization->Modernization->On Hold->Modernization | 2023Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-09 |  | 2023-05-11 |  | Closed | 2023-05-12 | 2023-05-15 | CD//Jahganathan | 2023-05-15 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230508-0005 | DU00002039128 |  |  | 2023-07-13 | 2023-07-11 |  | Tower | 60m 4 Legged Tower | 61 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
7308B | Kinabutan Tiku | Sabah |  | Modernization |  | 2023Q4 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-06-13 | 2023-06-19 |  | 2023-06-21 |  | Closed | 2023-06-22 | 2023-07-17 | CD//Ray Amos | 2023-07-14 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230612-0004 | DU00002039129 |  |  | 2023-08-13 | 2023-08-08 |  | Tower | 30m Monopole | 45m | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x3 | 13
9164B | Wisma Bapa Malaysia IB | Sarawak |  | Modernization |  | 2023Q4 | BY | AllStar | 4.6 TSSR Approved |  | 2023-06-28 | 2023-08-02 |  | 2023-08-08 |  | Closed | 2024-01-04 | 2024-01-05 | E//Nazrul | 2024-01-04 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230608-0006 | DU00002039130 |  |  | 2024-05-03 | 2024-04-22 |  | Portables BTS | In-building system |  | Add R8862A S1800 x1 + R8862A S2100 x4 + R8862A S2601 x1
7624A | Dumpas | Sabah |  | Modernization |  | 2023Q3 | AD | Futong | 4.6 TSSR Approved |  | 2023-05-25 | 2023-05-26 |  | 2023-05-31 |  | Closed | 2023-06-01 | 2023-06-22 | E//Hannah | 2023-06-22 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0004 | DU00002039131 |  |  | 2023-07-24 | 2023-07-15 |  | Tower | Tower | 76 | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 2
7230B | Taman Adika (KM) | Sabah |  | Modernization |  | 2023Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-08 |  | 2023-05-10 |  | Closed | 2023-05-13 | 2023-05-15 | CD//Ray Amos | 2023-05-15 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230508-0005 | DU00002039132 |  |  | 2023-07-14 | 2023-07-08 |  | Monopole | 30M Monopole | 35 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x3 | 23
9359B | Sg Asap 3 | Sarawak |  | Modernization |  | 2023Q3 | BY | Datasco | 4.6 TSSR Approved |  | 2023-05-23 | 2023-05-26 |  | 2023-05-30 |  | Rectificating | 2023-06-16 | 2023-07-07 | E//Hannah | 2023-07-04 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230516-0006 | DU00002039133 |  |  | 2025-05-17 | 2025-04-07 |  | Tower | Tower | 76 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
7660B | Mile 5 Tawau (REL) | Sabah |  | Modernization |  | 2023Q4 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2024-01-30 | 2024-01-23 |  | 2025-02-11 |  | Under Approval | 2024-02-01 | 2024-02-02 | E//Hannah | 2024-02-02 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230612-0004 | DU00002039134 |  |  | 2024-03-12 | 2024-02-22 |  | Tower | GF 90m Tower | 92 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8881 S9000 x1+R8894E M1821(A8A) x3 | 12
7205A | Mile 15 Tawau | Sabah |  | Modernization |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-06-15 | 2023-06-28 |  | 2023-07-06 |  | Closed | 2023-07-07 | 2023-07-22 | E//Zulakmar | 2023-07-21 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007 | DU00002039135 |  |  | 2023-08-29 | 2023-08-14 |  | Tower | 60m 4 Legged Tower | 60 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8854E S1800(A6A) x3+R8854D S2100(A4A) x3 | 123
7035R | KPOM - YUN FOOK MILL | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2023Q3 | AD | Datasco | 4.6 TSSR Approved | [5 empty] | 2023-05-11 |  | 2025-09-10 | 2025-10-22 | E//Hannah | 2025-09-16 | SQ202508010264 - Datasco | DU00002039136 |  |  |  |  | 2025-10-03 |  | Tower
7663A | Sabindo Square | Sabah |  | Modernization |  | 2023Q4 | AD | AllStar | 4.6 TSSR Approved |  | 2023-06-14 | 2023-07-13 |  | 2023-07-18 |  | Closed | 2023-07-20 | 2023-07-28 | CD//Ray Amos | 2023-07-28 | Celcom Digi_RAN-Allstar-TSS-Sabah-20230608-0004 | DU00002039137 |  |  | 2023-08-14 | 2023-08-08 |  | H-bracket pole | 3m Bipod (RT) | 6m | Add R9264M M1821 x4,Dismantle R8862A S1800(B6A) x4+R8862A S2100(A6A) x4 |  | 1
7643B | Sebatik SBC | Sabah |  | Modernization |  | 2023Q3 | MS | Futong | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-17 |  | 2023-05-20 |  | Closed | 2023-05-23 | 2023-07-10 | E//Nizar | 2023-07-10 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0004 | DU00002039138 |  |  | 2023-08-18 | 2023-08-07 |  | Tower | Tower | 60 | Add A9732 M1821 x1 + R9264M M1821 x2,Dismantle R8894E M1821(A8A) x3 | 3
7687B | Jalan Damai Tawau (REL) | Sabah |  | Modernization |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved | Single Phase Power Site. Site require upgrade to 3phase incoming | 2023-06-27 | 2023-07-14 |  | 2023-07-18 |  | Closed | 2023-07-21 | 2023-08-15 | E//Hannah | 2023-07-25 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007 | DU00002039139 |  |  | 2023-08-22 | 2023-08-14 |  | Lampole | 24m Lampole | 30 | Add R8852E S9000 x3+A9732 M1821 x3,Dismantle R8854E S1800(A6A) x3+R8854D S2100(A4A) x3 | 123 | 0
7127H | iMacro Pusat Internet Bum-Bum | Sabah |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039140 | [6 empty] | Small Cell
9518A | Yi Hah Hai MP | Sarawak |  | Modernization |  | 2023Q4 | BY | AllStar | 4.6 TSSR Approved |  | 2023-06-07 | 2023-06-10 |  | 2023-06-16 |  | Closed | 2023-06-19 | 2023-07-07 | E//Hannah | 2023-07-06 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230608-0006 | DU00002039141 |  |  | 2023-08-04 | 2023-07-17 |  | Monopole | Tower | 30 | Add R9264H M901821 x3 + R9264M M1821 x3 + R8862A S2600 x3,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 |  | 123
9088A | CURTINSACOFA | Sarawak |  | Modernization |  | 2023Q4 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-06-15 | 2023-07-10 |  | 2023-07-14 |  | Closed | 2023-07-17 | 2023-08-02 | E//Zulakmar | 2023-08-02 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230608-0007 | DU00002039142 |  |  | 2023-08-25 | 2023-08-14 |  | Tower | Tower | 60 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x4 | 23
9010C | Matang Metro City | Sarawak |  | Modernization |  | 2023Q4 | HQ 1 | South Pacific | 4.6 TSSR Approved |  | 2023-06-13 | 2023-07-21 |  | 2023-07-28 |  | Closed | 2023-07-31 | 2023-09-01 | E//Hannah | 2023-09-01 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230612-0004 | DU00002039143 |  |  | 2023-09-07 | 2023-08-29 |  | In-Building System | 6M Rooftop | 5m | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x3,Dismantle R8894E M1821(A8A) x4 | 1
7893A | Taman Jaya Keningau | Sabah |  | Modernization |  | 2023Q3 | AD | Trintel | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-18 |  | 2023-05-22 |  | Rectificating | 2023-06-06 | 2023-06-17 | E//Hannah | 2023-06-16 | Celcom Digi_RAN-Trintel-TSS-Sabah-20230508-0001 | DU00002039144 |  |  | 2023-07-13 | 2023-07-08 |  | Monopole | 30m Monopole | 26 | Add R9264M M1821 x7 + R8862A S2601 x3,Dismantle R8892N M1821(BAB) x4 |  | 134
7193Z | SAPANG OIL MILLS | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002039145 | [6 empty] | Tower
7627A | Tg Kapor | Sabah |  | Modernization |  | 2023Q4 | AD | Datasco | 4.6 TSSR Approved |  | 2023-07-12 | 2023-07-28 |  | 2023-08-02 |  | Closed | 2023-08-03 | 2023-08-11 | E//Hannah | 2023-08-11 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230703.xls | DU00002039146 |  |  | 2023-09-04 | 2023-08-22 |  | Tower | Tower | 60 | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x3+R8894E M1821(A8A) x4+R9224E M1821(AAB) x2 | 123
9083A | Piasau Industrial Estate | Sarawak |  | Modernization |  | 2023Q4 | BY | Magicell | 4.6 TSSR Approved |  | 2023-07-03 | 2023-07-04 |  | 2023-07-07 |  | Closed | 2023-07-10 | 2023-07-17 | E//Hannah | 2023-07-17 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002039147 |  |  | 2023-12-01 | 2023-09-21 |  | In-Building System | 3m RT (Minimast) | 15 | Add R9264H M901821 x3 + R9264M M1821 x3 + R8862A S2601 x3,Dismantle R8882-GUL1812 x3+R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 |  | 123
7630B | Kg.Tas | Sabah |  | Modernization |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-06-19 | 2023-07-14 |  | 2023-09-09 |  | Closed | 2023-09-11 | 2023-09-12 | E//Hannah | 2023-09-11 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007 | DU00002039148 |  |  | 2023-09-22 | 2023-09-13 |  | Tower | Tower | 76 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
9533A | Serway Hypermarket | Sarawak |  | Modernization |  | 2023Q4 | SH | Datasco | 4.6 TSSR Approved |  | 2023-06-14 | 2023-07-04 |  | 2023-07-31 |  | Closed | 2023-08-01 | 2023-08-23 | E//SoonHo | 2023-08-23 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230608-0007 | DU00002039149 |  |  | 2023-09-27 | 2023-08-29 |  | Monopole | 30m Monopole | 30 | Add R9264M M1821 x1+R9264H M901821 x3+R8862A S2600 x1,Dismantle R8882 S1800B(B6B) x3+R8854D S2100(A4A) x3 | 0 | 1
9032B | Red Bridge | Sarawak |  | Modernization |  | 2023Q4 | SH | Datasco | 4.6 TSSR Approved |  | 2023-08-21 | 2023-08-29 |  | 2023-09-01 |  | Closed | 2023-09-04 | 2023-09-08 | E//Hannah | 2023-09-08 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230823 | DU00002039150 |  |  | 2023-11-24 | 2023-09-30 |  |  | Tower | 76 | Add R9264H M901821 x2 + R9264M M1821 x3 + R8862A S2601 x3,Dismantle R8882-GUL1812 x2+R8862A S2100(A6A) x2 |  | 12
9012B4 | pBTS Piasau slipway | Sarawak |  | Modernization |  | 2023Q4 | ZB | AllStar | 4.6 TSSR Approved |  | 2023-06-28 | 2023-07-03 |  | 2023-07-05 |  | Closed | 2023-07-07 | 2023-07-20 | E//Hannah | 2023-07-20 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230608-0006 | DU00002039151 |  |  | 2023-08-08 | 2023-08-02 |  | Watertank | 25m pBTS | 30 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3
7652C | Taman Ambar | Sabah |  | Modernization |  | 2023Q4 | AD | YPTT | 4.6 TSSR Approved |  | 2023-06-17 | 2023-07-13 |  | 2023-07-18 |  | Closed | 2023-07-18 | 2023-07-24 | E//Hannah | 2023-07-24 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002039152 |  |  | 2023-08-03 | 2023-07-31 |  | Monopole | 30m Monopole | 30 | Add A9732 M1821 x3 + R9264M M1821 x1,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x4+R9224E M1821(AAB) x2 | 124
9601A | Curtin Water Senadin | Sarawak |  | Modernization |  | 2023Q4 | BY | South Pacific | 4.6 TSSR Approved |  | 2023-06-10 | 2023-06-15 |  | 2023-06-17 |  | Closed | 2023-06-19 | 2023-07-12 | E//Hannah | 2023-07-12 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230606-0003 | DU00002039153 |  |  | 2023-07-31 | 2023-07-28 |  | Monopole | 30m Rapole | 30M | Add R9264H M901821 x3,Dismantle R8854E S1800(A6A) x3+R8862A S2100(A6A) x3
7013R | Pulau Bum Bum - Kg Igang-Igang | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039154 | [6 empty] | Land site
7618A | Hot Spring Tawau | Sabah |  | Modernization |  | 2023Q4 | AD | YPTT | 4.6 TSSR Approved |  | 2023-06-17 | 2023-07-12 |  | 2023-07-17 |  | Closed | 2023-07-18 | 2023-07-24 | E//Hannah | 2023-07-24 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002039155 |  |  | 2023-08-07 | 2023-07-31 |  | Tower | 45m 3 Legged Tower | 45 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 12
9574B | Long Urun Plantation | Sarawak |  | Modernization |  | 2023Q3 | BY | Datasco | 4.6 TSSR Approved |  | 2023-06-13 | 2023-06-17 |  | 2023-06-26 |  | Closed | 2023-06-28 | 2023-07-10 | E//Hannah | 2023-07-10 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230516-0006 | DU00002039156 |  |  | 2023-08-11 | 2023-08-02 |  | Tower | 30m Monopole | 60 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
9444A | Matang Jaya 2 MP | Sarawak |  | Modernization |  | 2023Q4 | BY | South Pacific | 4.6 TSSR Approved |  | 2023-06-17 | 2023-06-22 |  | 2023-06-26 |  | Closed | 2023-07-04 | 2023-07-25 | E//Zulakmar | 2023-07-25 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230612-0004 | DU00002039157 |  |  | 2023-08-14 | 2023-08-09 |  | Monopole | 30m Monopole | 30m | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 12
9090A | Krokop Yakin MP | Sarawak |  | Modernization |  | 2023Q4 | HQ 1 | AllStar | 4.6 TSSR Approved |  | 2023-06-12 | 2023-06-12 |  | 2023-06-27 |  | Closed | 2023-07-03 | 2023-07-11 | E//Hannah | 2023-07-11 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230608-0006 | DU00002039158 |  |  | 2023-08-25 | 2023-08-01 |  | Monopole | Tower | 30 | Add A9732 M1821 x3,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 | 123
7629B | Bandar Sabindo | Sabah |  | Modernization |  | 2023Q4 | AD | AllStar | 4.6 TSSR Approved |  | 2023-06-11 | 2023-06-23 |  | 2023-06-27 |  | Closed | 2023-06-28 | 2023-07-13 | E//Hannah | 2023-07-13 | Celcom Digi_RAN-Allstar-TSS-Sabah-20230608-0004 | DU00002039159 |  |  | 2023-08-16 | 2023-08-08 |  |  | 3m RT (Wall Mounted Pole) | 2M | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8882 S1800B(B6B) x3+R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 |  | 1
7196Z | PJ NAGUS ESTATE | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 |  | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002039160 | [6 empty] | Tower
7014R | Pulau Bum Bum - Kg Kabimbangan | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039161 | [6 empty] | Land site
7692B | Kg. Indani Jaya | Sabah |  | Modernization |  | 2023Q4 | MS | Futong | 4.6 TSSR Approved |  | 2023-06-20 | 2023-06-17 |  | 2023-06-22 |  | Closed | 2023-07-03 | 2023-07-17 | E//Hannah | 2023-07-17 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0011 | DU00002039162 |  |  | 2023-08-23 | 2023-08-15 |  | Tower | 45m 3 Legged Tower | 60 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2,Dismantle R8862A S2600(A4A) x1+R9224E M1821(AAB) x4 | 1
9021C | Jln Krokop 9 | Sarawak |  | Modernization |  | 2023Q4 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-12-14 | 2024-02-01 |  | 2024-02-16 |  | Closed | 2025-03-14 | 2024-02-21 | E//Hannah | 2025-01-20 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230608-0007 | DU00002039163 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed | 2025-02-19 | 2025-02-10 |  | Lampole | 24m Lampole | 24 | Add R8894E M1821x2+R9264H M901821x1+R8854 S2600x1,Dismantle R8862A S9000(A6A)x1+R8862A S1800(B6A)x3+R8862A S2100(A6A)x3+R8862A S2600(A4A)x1 | 0 | 3
7039R | KG SENAGANG ULU | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | AD | South Pacific | 14.2 Drop (Done Survey) |  | 2023-05-20 |  |  |  | 2023-05-20 | To be Submitted |  |  |  |  | N/A - no need PR for MOCN Decomm | DU00002039164 | [6 empty] | Tower
7202A | Jalan Utara Baru | Sabah |  | Modernization |  | 2023Q4 | AD | YPTT | 4.6 TSSR Approved |  | 2023-06-18 | 2023-06-23 |  | 2023-07-05 |  | Closed | 2023-07-05 | 2023-07-13 | E//Thien | 2023-07-12 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002039165 |  |  | 2023-08-20 | 2023-08-02 |  |  | 25m Guyed Mast | 26 | Add R8852E S9000 x3+A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
7095R | KG TAKUL | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2023Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2025-09-24 |  | 2025-09-29 |  | 2025-09-30 |  | 2025-10-07 | 2025-10-30 | E//Hannah | 2025-10-15 | SQ202509220707 - YPTT | DU00002039166 |  |  |  |  | 2025-11-04 |  | Tower
9107A | Tanjong Kidurong (SACOFA) | Sarawak |  | Modernization |  | 2023Q3 | SM | AllStar | 4.6 TSSR Approved |  | 2023-05-17 | 2023-05-20 |  | 2023-05-25 |  | Closed | 2024-12-03 | 2024-12-10 | E//Hannah | 2024-12-09 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230516-0005 | DU00002039167 |  |  | 2025-05-04 | 2025-04-22 |  |  | Tower | 61 | Add R8862A S9000x2+R9264H M901821x2+R8854 S2600x2, Dismantle R8882 S2600(B4A)x2+R9224E M1821(AAB)x2 | 0 | 13
7972A | Sapang (Celcom) | Sabah |  | Modernization |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-06-28 | 2023-07-10 |  | 2023-07-13 |  | Closed | 2023-07-14 | 2023-07-28 | CD//Ray Amos | 2023-07-25 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0010 | DU00002039168 |  |  | 2023-10-30 | 2023-09-14 |  | Tower | 60m 4 Legged Tower | 76 | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x3 |  | 3
9461A | Kg Bintawa Hilir | Sarawak |  | Modernization |  | 2023Q4 | SH | Datasco | 4.6 TSSR Approved |  | 2023-07-12 | 2023-07-17 |  | 2023-07-19 |  | Closed | 2023-07-20 | 2023-07-27 | E//Hannah | 2023-07-27 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230726 | DU00002039169 |  |  | 2023-08-26 | 2023-08-21 |  |  | Tower | 30 | Add A9732 M1821x2 + R9264M M1821x1,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x4 | 12
9579A | Miri Tudan Housing | Sarawak |  | Modernization |  | 2023Q4 | BY | Magicell | 4.6 TSSR Approved |  | 2023-06-22 | 2023-06-23 |  | 2023-06-26 |  | Closed | 2023-06-28 | 2023-07-15 | E//Hannah | 2023-07-14 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002039170 |  |  | 2023-08-17 | 2023-08-11 |  | Monopole | 30m Rapole | 31m | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
7008Z | T3_Kg. Ulu Kimanis | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039171 | [6 empty] | Tower
7939B | Kg Cina Kunak Jaya | Sabah |  | Modernization |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-06-12 | 2023-06-14 |  | 2023-06-16 |  | Closed | 2023-06-19 | 2023-07-21 | CD//Mohidi Jaan | 2023-07-20 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0010 | DU00002039172 |  |  | 2023-09-19 | 2023-09-08 |  | Monopole | Tower | 30m | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
7611A | Kg Titinggian | Sabah |  | Modernization |  | 2023Q4 | HQ 1 | Datasco | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI,L2600 change to 40M¦no sapce to add H pole | 2023-06-13 | 2023-07-10 |  | 2023-07-12 |  | Closed | 2023-07-17 | 2023-07-25 | E//Hannah | 2023-07-25 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007 | DU00002039173 | NIC_S2_Change MM to BI,L2600 change to 40M_Space constraint_Digi OB |  | 2023-09-26 | 2023-08-14 |  | In-Building System | 6m RT (Wall Mounted Pole) | 6m | Add R9264M M1821 x5 + R8862A S2601 x2,Dismantle R9224E M1821(AAB) x3 |  | 23
7007R | Pulau Sebatik Kg Tamang | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039174 | [6 empty] | Land site
9175B | Taman Bandar Jaya | Sarawak |  | Modernization |  | 2023Q3 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-05-18 | 2023-06-08 |  | 2023-06-17 |  | Rectificating | 2023-06-22 | 2023-07-07 | E//Hannah | 2023-07-04 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230516-0006 | DU00002039175 |  |  | 2024-01-06 | 2023-12-18 |  | Monopole | 3m Bipod (RT) | 30M | Add A9732 M1821 x3 + R9264M M1821 x1,Dismantle R8882 S1800B(B6B) x3+R8862A S1800(B6A) x1+R8854D S2100(A4A) x4 | 123
9156B | Matang Jaya 3 MP | Sarawak |  | Modernization |  | 2023Q4 | ZB | Trintel | 4.6 TSSR Approved |  | 2023-07-14 | 2023-08-01 |  | 2023-08-07 |  | Closed | 2023-08-15 | 2023-10-02 | E//Hannah | 2023-09-22 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230622 | DU00002039176 |  | Wrong schematic drawing | 2023-09-29 | 2023-09-26 |  | Monopole | 30m Rapole | 15m | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882 S1800B(B6B) x3
7699B | Kg Sungai Imam | Sabah |  | Modernization |  | 2023Q3 | MS | Futong | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-15 |  | 2023-05-19 |  | Closed | 2023-05-22 | 2023-07-10 | E//Hannah | 2023-07-10 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0004 | DU00002039177 |  |  | 2023-08-27 | 2023-07-31 |  | Monopole | Tower | 40 | Add R8852E S9000 x3 + A9732 M1821 x3 + R9264H M901821 x1,Dismantle R8862A S2600(A4A) x1+R9224E M1821(AAB) x5 | 123
9128A | Similajau National Park | Sarawak |  | Modernization |  | 2023Q3 | BY | YPTT | 4.6 TSSR Approved |  | 2023-05-29 | 2023-07-04 |  | 2023-07-06 |  | Closed | 2023-07-06 | 2023-07-14 | E//Hannah | 2023-07-14 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20230622 | DU00002039178 |  |  | 2023-11-25 | 2023-11-10 |  | Tower | Tower | 65 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8860E-GU908 x3+R8862A S1800(B6A) x3
9439A | Kpg. Gita 2 MP | Sarawak |  | Modernization |  | 2023Q4 | BY | Magicell | 4.6 TSSR Approved |  | 2023-06-16 | 2023-06-26 |  | 2023-07-04 |  | Closed | 2023-07-05 | 2023-07-20 | E//Hannah | 2023-07-20 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002039179 |  |  | 2023-08-22 | 2023-08-09 |  | Monopole | 30m Monopole | 25M | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 | 13
9024C | Jalan Picasso Lutong | Sarawak |  | Modernization |  | 2023Q4 | BY | Trintel | 4.6 TSSR Approved |  | 2023-06-16 | 2023-06-21 |  | 2023-07-03 |  | Closed | 2023-07-03 | 2023-07-15 | E//Hannah | 2023-07-14 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230622 | DU00002039180 |  |  | 2023-08-23 | 2023-08-14 |  | Lampole | 30m Lampole | 30 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
7677B | Hilltop Supermarket (RT) | Sabah |  | Modernization |  | 2023Q4 | AD | YPTT | 4.6 TSSR Approved |  | 2023-06-18 | 2023-07-14 |  | 2023-07-20 |  | Closed | 2023-07-21 | 2023-07-25 | E//Hannah | 2023-07-25 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002039181 |  |  | 2023-08-11 | 2023-08-09 |  | In-Building System | 3m Bipod (RT) | 5 | Add A9732 M1821 x2 + R9264M M1821 x2,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x5 | 34
9067B | Kg Santubong | Sarawak |  | Modernization |  | 2023Q4 | BY | AllStar | 4.6 TSSR Approved |  | 2023-06-14 | 2023-06-16 |  | 2023-06-22 |  | Closed | 2023-06-23 | 2023-07-15 | E//Hannah | 2023-07-14 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230608-0006 | DU00002039182 |  |  | 2023-08-17 | 2023-08-15 |  | Monopole | 30m Rapole | 30< | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
9022C | Jalan Pujut 9 | Sarawak |  | Modernization |  | 2023Q4 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-06-28 | 2023-07-04 |  | 2023-07-06 |  | Closed | 2023-07-07 | 2023-07-18 | E//Hannah | 2023-07-18 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002039183 |  |  | 2025-04-12 | 2025-04-05 |  | Monopole | Tower | 30 | Add R8894E M1821x3, Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3 | 0 | 0
7668B | MEROTAI BESAR_T3 | Sabah |  | Modernization |  | 2023Q3 | MS | Futong | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-19 |  | 2023-05-25 |  | Closed | 2023-06-01 | 2023-06-20 | E//Hannah | 2023-06-20 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0004 | DU00002039184 |  |  | 2023-08-07 | 2023-07-24 |  | Tower | Tower | 60 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8894E M1821(A8A) x3 |  | 23
9458A | Heng Guan (Sacofa) | Sarawak |  | Modernization |  | 2023Q4 | SH | AllStar | 4.6 TSSR Approved |  | 2023-06-28 | 2023-07-21 |  | 2023-08-01 |  | Closed | 2023-08-01 | 2023-08-09 | E//Hannah | 2023-08-09 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230622 | DU00002039185 |  |  | 2024-07-23 | 2024-06-20 |  | Tower | Tower | 60 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x2,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 | 23
9001C | Permyjaya Technology Park (Emart Tudan) | Sarawak |  | Modernization |  | 2023Q4 | SHA | Magicell | 4.6 TSSR Approved |  | 2023-06-23 | 2023-06-27 |  | 2023-06-30 |  | Closed | 2025-03-14 | 2023-07-20 | E//Hannah | 2023-07-20 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002039186 |  |  | 2025-04-12 | 2025-03-21 |  | Monopole | 30m Rapole | 29m | Add R8862A S9000x2+R9264H M901821x1+A9732 M1821x1+R8854 S2600x1, Dismantle R8862A S2600(A4A)x1+R8894E M1821(A8A)x2 | 3 | 2
9023H | Dry Bulk Bintulu Port | Sarawak |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039187 | [6 empty] | Small Cell
7644B | Tanah Merah Merotai SBC | Sabah |  | Modernization |  | 2023Q3 | MS | Futong | 4.6 TSSR Approved |  | 2023-05-22 | 2023-05-25 |  | 2023-06-17 |  | Closed | 2023-06-19 | 2023-06-22 | CD//Ray Amos | 2023-06-22 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0004 | DU00002039188 |  |  | 2023-07-21 | 2023-07-15 |  | Tower | Tower | 60 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2,Dismantle R8860E-GU908 x1+R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 | 1
9075B | Taman Amina | Sarawak |  | Modernization |  | 2023Q4 | SH | Datasco | 4.6 TSSR Approved |  | 2023-10-05 | 2023-10-10 |  | 2023-10-12 |  | Closed | 2023-10-13 | 2023-11-03 | E//Hannah | 2023-11-01 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230923 | DU00002039189 |  |  | 2023-11-02 | 2023-10-27 |  | Tower | 30m Monopole | 45 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8882 S1800B(B6B) x3+R8854D S2100(A4A) x3
7354A | SG NASIP | Sabah |  | Modernization |  | 2023Q4 | MS | GTSB | 4.6 TSSR Approved | TI Issue. Access Road Broken (1km to site). Need Manual Handling 1km | 2023-06-25 | 2023-07-04 |  | 2023-07-01 |  | Closed | 2023-07-20 | 2023-08-24 | E//Hannah | 2023-08-16 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230703.xls | DU00002039190 |  |  | 2024-01-30 | 2023-09-14 |  | Tower | 45m 3 Legged Tower | 76 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8854 S2600 x1,Dismantle R8882 S1800B(B6B) x3+R8862A S2600(A4A) x1 |  | 2
7001D | Bubul | Sabah |  | Modernization |  | 2023Q4 | MS | Futong | 4.6 TSSR Approved |  | 2023-06-20 | 2023-06-13 |  | 2023-06-22 |  | Closed | 2023-06-19 | 2023-07-07 | E//Hannah | 2023-07-04 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0011 | DU00002039191 |  |  | 2023-08-20 | 2023-08-15 |  | Monopole | 30M Monopole | 30 | Add R9264H M901821 x3 + R9264M M1821 x2,Dismantle R9224E M1821(AAB) x3 |  | 13
9129B | Samalaju-Press Metal | Sarawak |  | Site Out (Modernization) | Modernization->Delete from system(MOCN Decomm)->Site Out->Replacement, Site Out (Modernization) | 2023Q3 |  | Magicell | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2025-07-24 |  | 2025-08-08 |  |  | To be Submitted |  |  |  |  | SQ202507160538-Magicell | DU00002039192 | [6 empty] | 30m Monopole
9076A | Pujut 7 | Sarawak |  | Modernization |  | 2023Q4 | BY | South Pacific | 4.6 TSSR Approved |  | 2023-06-08 | 2023-06-26 |  | 2023-07-05 |  | Closed | 2023-07-07 | 2023-07-24 | E//SoonHo | 2023-07-24 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230606-0003 | DU00002039193 |  |  | 2023-09-05 | 2023-08-18 |  | In-Building System | 5m RT (Wall Mounted Pole) | 16.450 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x2,Dismantle R8882 S1800B(B6B) x3+R8862A S1800(B6A) x1+R8862A S2100(A6A) x4 | 24
7664A | Taman Sri Balung | Sabah |  | Modernization |  | 2023Q4 | HQ 1 | Datasco | 4.6 TSSR Approved |  | 2023-06-16 | 2023-07-12 |  | 2023-07-14 |  | Closed | 2023-07-17 | 2023-07-25 | E//Hannah | 2023-07-21 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007 | DU00002039194 |  |  | 2023-08-18 | 2023-08-14 |  | In-Building System | 3m Bipod (RT) | 8m & 4m | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3++R8881 S2100 x3+ |  | 1
7036R | KG.KABULU KENINGAU | Sabah |  | Maintain USP MOCN(Dismantle Passive) | Maintain USP MOCN(Dismantle Passive)->On Hold->Maintain USP MOCN(Dismantle Passive) | 2023Q3 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2025-07-17 |  | 2025-07-29 |  | 2025-07-29 |  | 2025-09-09 | 2025-10-27 | E//Hannah | 2025-09-16 | SQ202508130660 - Seri Pancar | DU00002039195 |  |  |  |  | 2025-11-27 |  | Tower
7977A | LDWS | Sabah |  | Modernization |  | 2023Q4 | MS | Futong | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-10 |  | 2023-06-14 |  | Rectificating | 2023-06-16 | 2023-07-04 | CD//Ray Amos | 2023-07-04 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0011 | DU00002039196 |  |  | 2023-08-28 | 2023-08-24 |  | Tower | Tower | 76 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
9592A | Shin Yang Industrial | Sarawak |  | Modernization |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-07-08 | 2023-07-11 |  | 2023-07-17 |  | Closed | 2023-07-20 | 2023-07-26 | E//Hannah | 2023-07-26 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230613-0007 | DU00002039197 |  |  | 2023-09-01 | 2023-08-15 |  | Lampole | 30m Rapole | 30M | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3 |  | 1
9530A | Desa Pujut 2 | Sarawak |  | Modernization |  | 2023Q4 | HQ 2 | Datasco | 4.6 TSSR Approved |  | 2023-06-13 | 2023-06-26 |  | 2023-06-28 |  | Closed | 2023-07-03 | 2023-07-21 | E//SoonHo | 2023-07-21 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230608-0007 | DU00002039198 |  |  | 2023-09-01 | 2023-08-14 |  | Monopole | 30m Monopole | 30 | Add A9732 M1821 x2 + R9264M M1821 x2,Dismantle R8862A S2600(A4A) x2+R9224E M1821(AAB) x6 | 13
7180Z | Kg.Dumbun | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039199 | [6 empty] | Tower
7684B | Kg Simunul Semporna | Sabah |  | Modernization |  | 2023Q4 | MS | Futong | 4.6 TSSR Approved |  | 2023-06-14 | 2023-06-19 |  | 2023-06-21 |  | Closed | 2023-06-22 | 2023-07-07 | CD//Ray Amos | 2023-07-07 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0011 | DU00002039200 |  |  | 2023-09-24 | 2023-09-06 |  | Monopole | 30m Monopole | 30 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
9005C | Sungai Plan 3 | Sarawak |  | Modernization |  | 2023Q3 | AI | AllStar | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI,L2600 change to 40M¦reject by site Owner Sacofa. Site owner don't allow DIGI add antenna on tower. | 2023-05-16 | 2023-05-18 |  | 2023-05-22 |  | Closed | 2023-05-25 | 2023-06-01 | E//Hannah | 2025-06-09 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230516-0005 | DU00002039201 | Remarks: Solution TSSR/BOM Changed NIC_S3_Change MM to BI,L2600 change to 40M_owner reject_SACOFA SDN BHD | Remarks: Solution Changed | 2025-03-28 | 2025-03-13 |  | Monopole | 30m Monopole | 31 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle R9224E M1821(AAB) x3 |  | 123
9003C | Kidurong Industrial | Sarawak |  | Modernization |  | 2023Q3 | BY | South Pacific | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦SACOFA rejected to add new AAU, the maximum antenna is 3 | 2023-05-17 | 2023-05-19 |  | 2023-05-25 |  | Closed | 2023-06-06 | 2023-09-01 | E//Hannah | 2023-09-01 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230512-0001 | DU00002039202 | NIC_S2_Change MM to BI_owner reject_SACOFA SDN BHD |  | 2023-08-25 | 2023-08-15 |  | Monopole | Tower | 30m | Add R9264M M1821 x2+R9264H M901821 x3+R8862A S2601 x2,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 |  | 13
7312B | Tanjung Batu Laut | Sabah |  | Modernization |  | 2023Q4 | AD | YPTT | 4.6 TSSR Approved |  | 2023-06-19 | 2023-06-30 |  | 2023-07-06 |  | Closed | 2023-07-07 | 2023-07-15 | E//Hannah | 2023-07-14 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002039203 |  |  | 2023-08-16 | 2023-08-02 |  | Monopole | 30m Monopole | 30 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
9603A | Marina Bay | Sarawak |  | Modernization |  | 2023Q4 | BY | Trintel | 4.6 TSSR Approved |  | 2023-06-27 | 2023-07-18 |  | 2023-07-21 |  | Closed | 2023-07-24 | 2023-07-26 | E//Hannah | 2023-07-25 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230622 | DU00002039204 |  |  | 2023-09-02 | 2023-08-18 |  | In-Building System | 3m Boom (RT) | 3m | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x3 | 12
9025C | Tudan | Sarawak |  | Modernization |  | 2023Q4 | SH | Magicell | 4.6 TSSR Approved |  | 2023-06-26 | 2023-06-28 |  | 2023-07-01 |  | Closed | 2023-07-03 | 2023-07-25 | E//Hannah | 2023-07-20 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002039205 |  |  | 2023-08-21 | 2023-08-11 |  | Monopole | 30m Rapole | 29m | Add R9264M M1821 x5 + R8862A S2601 x2,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 23
9402A | Tmn Sourabaya(SACOFA) | Sarawak |  | Modernization |  | 2023Q4 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-07-08 | 2023-07-17 |  | 2023-07-20 |  | Closed | 2023-07-20 | 2023-07-28 | E//SoonHo | 2023-07-27 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002039206 |  |  | 2023-09-25 | 2023-09-19 |  | Monopole | Tower | 46 | Add R9264H M901821 x4 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8882 S1800B(B6B) x2+R8862A S1800(B6A) x2 |  | 3
9336B | Rh Bunsu | Sarawak |  | Modernization |  | 2023Q3 | BY | YPTT | 4.6 TSSR Approved |  | 2023-06-12 | 2023-06-12 |  | 2023-06-15 |  | Closed | 2023-06-15 | 2023-06-26 | E//Hannah | 2023-06-26 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20230613-0007 | DU00002039207 |  |  | 2023-08-08 | 2023-08-01 |  | Tower | Tower | 75 | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3
9063A | Piasau Inn | Sarawak |  | Modernization |  | 2023Q4 | BY | Magicell | 4.6 TSSR Approved |  | 2023-06-27 | 2023-07-10 |  | 2023-07-13 |  | Closed | 2023-07-13 | 2023-07-18 | E//Hannah | 2023-07-18 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002039208 |  |  | 2023-08-25 | 2023-08-18 |  | In-Building System | 6m Unipole RT | 6 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3++
7199A | Air Panas Prison | Sabah |  | Modernization |  | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-06-18 | 2023-06-20 |  | 2023-07-03 |  | Closed | 2023-07-04 | 2023-07-17 | E//Hannah | 2023-07-14 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002039209 |  |  | 2023-08-22 | 2023-08-02 |  | Minimast | 3m RT (Minimast) | 9m | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8882-GUL1812 x1+R8882 S1800B(B6B) x3+R8862A S1800(B6A) x2+R8862A S2100(A6A) x3 |  | 2
7601A | Brantian Tawau | Sabah |  | Modernization |  | 2023Q3 | MS | Futong | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-25 |  | 2023-05-30 |  | Closed | 2023-06-02 | 2023-07-10 | E//Hannah | 2023-07-10 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0004 | DU00002039210 |  |  | 2023-07-18 | 2023-07-14 |  |  | 60m 4 Legged Tower | 60m | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x3 |  | 1
9470A | PP Junction | Sarawak |  | Modernization |  | 2023Q4 | BY | Datasco | 4.6 TSSR Approved |  | 2023-06-07 | 2023-06-13 |  | 2023-06-17 |  | Rectificating | 2023-06-19 | 2023-07-17 | E//Hannah | 2023-07-17 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230608-0007 | DU00002039211 |  |  | 2023-09-04 | 2023-08-15 |  | Tower | 45m 3 Legged Tower | 76 | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3
7934A | Tong Len Kunak | Sabah |  | Modernization |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-06-19 | 2023-06-21 |  | 2023-06-23 |  | Closed | 2023-06-24 | 2023-07-12 | CD//Ray Amos | 2023-07-11 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0010 | DU00002039212 |  |  | 2023-09-04 | 2023-08-26 |  | Tower | Tower | 75m | Add R9264M M1821 x3 + R8862A S2601 x3,Dismantle R8894E M1821(A8A) x3
9143B | Kg Tungku Housing Kuching | Sarawak |  | Modernization |  | 2023Q4 | HQ 1 | Trintel | 4.6 TSSR Approved |  | 2023-07-03 | 2023-07-10 |  | 2023-07-13 |  | Closed | 2023-07-26 | 2023-08-09 | E//Hannah | 2023-08-03 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230622 | DU00002039213 |  |  | 2023-08-21 | 2023-08-14 |  | Monopole | 30m Rapole | 30m | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 12
7206Z | Kg Larapan Hujung | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039214 | [6 empty] | Land site
7309C | Madai Baturong | Sabah |  | Modernization |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-06-14 | 2023-06-13 |  | 2023-06-16 |  | Closed | 2023-06-19 | 2023-07-21 | CD//Mohidi Jaan | 2023-07-20 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0010 | DU00002039215 |  |  | 2023-08-28 | 2023-08-22 |  | Tower | 60m 4 Legged Tower | 65m | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
7688B | Brantian | Sabah |  | Modernization |  | 2023Q3 | MS | Futong | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-13 |  | 2023-05-18 |  | Closed | 2023-05-22 | 2023-07-07 | E//Hannah | 2023-07-03 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0004 | DU00002039216 |  |  | 2023-08-24 | 2023-08-15 |  | Tower | Tower | 60 | Add R9264M M1821 x3 + R8862A S2601 x3,Dismantle R8894E M1821(A8A) x3
7209A | Bubul Road Semporna (Maxis) | Sabah |  | Modernization |  | 2023Q4 | MS | Futong | 4.6 TSSR Approved |  | 2023-06-22 | 2023-06-26 |  | 2023-06-28 |  | Closed | 2023-07-03 | 2023-07-28 | E//Yadav | 2023-07-24 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0011 | DU00002039217 |  |  | 2023-09-12 | 2023-09-04 |  | Tower | Tower | 60 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 23
7810M | Fajar Communication | Sabah |  | MOCN As-Is |  | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039218 | [6 empty] | Micro Cell
9508A | Bayshore | Sarawak |  | Modernization |  | 2023Q4 | HQ 2 | Magicell | 4.6 TSSR Approved |  | 2023-06-26 | 2023-06-26 |  | 2023-06-28 |  | Closed | 2023-07-03 | 2023-07-18 | E//Hannah | 2023-07-17 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002039219 |  |  | 2023-08-21 | 2023-08-16 |  | Monopole | 36m Monopole | 36.5 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R9224E M1821(AAB) x3 | 123
7615A | Wisma Pang | Sabah |  | Modernization |  | 2023Q4 | HQ 1 | AllStar | 4.6 TSSR Approved |  | 2023-06-23 | 2023-07-06 |  | 2023-07-13 |  | Closed | 2023-07-20 | 2023-07-24 | CD//Mohidi Jaan | 2023-07-24 | Celcom Digi_RAN-Allstar-TSS-Sabah-20230608-0004 | DU00002039220 |  |  | 2023-08-14 | 2023-08-08 |  | In-Building System | 3m RT (Wall Mounted Pole) | 6m/9m/4m | Add R9264M M1821 x7,Dismantle R8862A S1800(B6A) x1+R8854E S1800(A6A) x3+R8854D S2100(A4A) x4 |  | 234
7933A | AnlongHill | Sabah |  | Decomm, MOCN By Other Vendor | Decomm->On Hold->Decomm->On Hold->Decomm | 2023Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-06-19 |  |  |  | 2023-06-19 |  | 2023-06-22 | 2025-10-24 | CD//Jahganathan | 2023-06-22 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0009 | DU00002039221 |  |  |  |  | 2025-12-12 |  | 76m Tower
9435A | Matang Wildlife Centre | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039222 | [6 empty] | 45m 3 Legged Tower
9159R | COASTAL HIGHWAY PLANTATION CAMP #4 SAMALAJU INDUSTRIAL PARK | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | N/A - no need PR for MOCN Decomm | DU00002039223 | [6 empty] | Land site
7648B | Ldg Kompleks LLS SBC | Sabah |  | Modernization |  | 2023Q4 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-08 |  | 2023-06-14 |  | Closed | 2023-06-16 | 2023-07-11 | E//Hannah | 2023-07-11 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0011 | DU00002039224 |  |  | 2023-08-29 | 2023-08-22 |  | Tower | Tower | 60 | Add R9264M M1821 x4,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 3
7453A | Kg.Ansip | Sabah |  | Modernization |  | 2023Q3 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-05-17 | 2023-05-19 |  | 2023-05-23 |  | Closed | 2023-05-25 | 2023-06-07 | E//Nizar | 2023-06-06 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230516-0001 | DU00002039225 |  |  | 2023-07-18 | 2023-07-12 |  | Tower | Tower | 70m | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 12
7126Z | KM70 Kalabakan-Nabawan | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | AD |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002039226 | [6 empty] | Tower
9022H | Bi-Port Bulkers Bintulu | Sarawak |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039227 | [6 empty] | Small Cell
7269C | Jalan Sin San Tawau | Sabah |  | Modernization |  | 2023Q4 | AD | YPTT | 4.6 TSSR Approved |  | 2023-06-19 | 2023-07-10 |  | 2023-07-13 |  | Closed | 2023-07-14 | 2023-07-26 | CD//Mohidi Jaan | 2023-07-25 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002039228 |  |  | 2023-08-09 | 2023-08-05 |  | Monopole | Land site | 30M | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8894E M1821(A8A) x3 |  | 2
7048C | Taman Hot Spring Jaya | Sabah |  | Modernization |  | 2023Q4 | MS | YPTT | 4.6 TSSR Approved |  | 2023-06-21 | 2023-06-27 |  | 2023-07-05 |  | Closed | 2023-07-05 | 2023-07-13 | CD//Ray Amos | 2023-07-13 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002039229 |  |  | 2023-08-11 | 2023-08-03 |  | Tower | 45m Tower | 50 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
7641B | Tmn Bkt. Tawau (Celcom) | Sabah |  | Modernization |  | 2023Q3 | MS | Futong | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-13 |  | 2023-05-25 |  | Closed | 2023-05-20 | 2023-05-25 | E//Hannah | 2023-05-26 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0004 | DU00002039230 |  |  | 2023-08-01 | 2023-07-24 |  | Tower | 76m 4 Legged Tower | 75 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882-GUL1812 x1+R8882 S1800(B) x1+R8862A S1800(B6A) x1
9594A | Jalan Helenium | Sarawak |  | Modernization |  | 2023Q4 | HQ 2 | AllStar | 4.6 TSSR Approved |  | 2023-06-15 | 2023-06-15 |  | 2023-06-27 |  | Closed | 2023-07-03 | 2023-07-12 | E//Hannah | 2023-07-12 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230608-0006 | DU00002039231 |  |  | 2023-08-02 | 2023-07-27 |  | Monopole | Tower | 30 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8882 S1800B(B6B) x3+R8854D S2100(A4A) x3 | 12
7206A | Mile 9 Tawau | Sabah |  | Modernization |  | 2023Q4 | HQ 1 | Datasco | 4.6 TSSR Approved |  | 2023-06-16 | 2023-06-23 |  | 2023-07-01 |  | Closed | 2023-07-03 | 2023-07-25 | E//Yadav | 2023-07-21 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007 | DU00002039232 |  |  | 2023-08-18 | 2023-08-14 |  | Monopole | 45m 3 Legged Tower | 50 | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 |  | 2
7569B | Kg. Meninpir | Sabah |  | Modernization |  | 2023Q3 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-07-05 | 2023-07-07 |  | 2023-07-11 |  | Closed | 2023-07-12 | 2023-07-14 | E//Hannah | 2023-07-14 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230516-0001 | DU00002039233 |  |  | 2023-07-26 | 2023-07-18 |  | Tower | Tower | 60m | Add R9264M M1821 x5,Dismantle R8894E M1821(A8A) x3 |  | 23
9042B | Wisma Sultan Tengah | Sarawak |  | Modernization |  | 2023Q4 | BY | AllStar | 4.6 TSSR Approved |  | 2023-07-06 | 2023-07-11 |  | 2023-07-18 |  | Closed | 2023-07-18 | 2023-07-26 | E//Hannah | 2023-07-25 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230608-0006 | DU00002039234 |  |  | 2023-09-08 | 2023-08-25 |  | Pole | 3m Bipod (RT) | 14 | Add A9732 M1821 x3,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3 | 123
7630A | Jalan Gudang 4 | Sabah |  | Modernization |  | 2023Q3 | MS | Futong | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-12 |  | 2023-05-25 |  | Closed | 2023-05-20 | 2023-05-25 | E//Hannah | 2023-05-26 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0004 | DU00002039235 |  |  | 2023-08-17 | 2023-08-17 |  | Tower | Tower | 77 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x3 | 13
9367B | RPR Sg Plant | Sarawak |  | Modernization |  | 2023Q3 | SH | South Pacific | 4.6 TSSR Approved |  | 2023-07-30 | 2023-08-07 |  | 2023-08-10 |  | Closed | 2023-08-11 | 2023-09-01 | E//Hannah | 2023-09-01 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230512-0001 | DU00002039236 |  |  | 2023-09-07 | 2023-09-04 |  | Monopole | 30m Rapole | 20m | Add R9264H M901821x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
7310B | Kg Pisang | Sabah |  | Modernization |  | 2023Q4 | AD | YPTT | 4.6 TSSR Approved |  | 2023-06-19 | 2023-06-21 |  | 2023-06-30 |  | Rectificating | 2023-07-03 | 2023-07-12 | E//Hannah | 2023-07-12 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002039237 |  |  | 2023-08-23 | 2023-08-08 |  | Monopole | Tower | 30 | Add R9264H M901821 x3 + R9264M M1821 x3 + R8862A S2601 x3,Dismantle R8894E M1821(A8A) x3 |  | 123
9009A | Holiday Inn Damai | Sarawak |  | Modernization |  | 2023Q4 | BY | AllStar | 4.6 TSSR Approved |  | 2023-06-15 | 2023-08-04 |  | 2023-08-15 |  | Closed | 2023-08-16 | 2023-09-01 | E//Hannah | 2023-09-01 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230608-0006 | DU00002039238 |  |  | 2023-09-25 | 2023-09-19 |  | Guide mast | Tower | 22m | Add R9264H M901821 x3,Dismantle R8860E-GU908 x2+R8882-GUL1812 x2+R8840-U216 x3
7158Z | KM40 Kalabakan-Nabawan | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | AD |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002039239 | [6 empty] | TOWER
7218Z | Pulau Selakan | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039240 | [6 empty] | Land site
7667A | Sg Uding | Sabah |  | Modernization |  | 2023Q3 | MS | Futong | 4.6 TSSR Approved |  | 2023-05-22 | 2023-05-24 |  | 2023-05-26 |  | Closed | 2023-05-29 | 2023-07-07 | E//Hannah | 2023-07-07 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0004 | DU00002039241 |  |  | 2023-08-13 | 2023-08-02 |  | Monopole | 30m Monopole | 45 | Add R9264H M901821 x3,Dismantle R8881 S9000 x1+R8882 S1800(B) x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3
7309B | Kg Kongsi 10 | Sabah |  | Modernization |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-06-14 | 2023-07-07 |  | 2023-07-10 |  | Closed | 2023-07-14 | 2023-07-24 | E//Hannah | 2023-07-24 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007 | DU00002039242 |  |  | 2023-08-18 | 2023-08-14 |  | Monopole | Tower | 45 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x5 | 123
9170A | Padang Kerbau | Sarawak |  | Modernization |  | 2023Q4 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-06-17 | 2023-07-21 |  | 2023-08-01 |  | Closed | 2023-08-03 | 2023-08-09 | CD//Michael | 2023-08-09 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230613-0007 | DU00002039243 |  |  | 2023-09-15 | 2023-08-21 |  | Tower | Tower | 40 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3 |  | 2
7602A | Bombalai Tawau | Sabah |  | Modernization |  | 2023Q3 | MS | Futong | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-18 |  | 2023-05-20 |  | Closed | 2023-05-23 | 2023-07-10 | E//Nizar | 2023-07-10 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0004 | DU00002039244 |  |  | 2023-08-09 | 2023-07-08 |  | Tower | Tower | 61 | Add R8852E S9000 x3 + A9732 M1821 x3+R8862A S2601(A6A) x3,Dismantle R8862A S2600(A4A) x3+R8862A S2601(A6A) x2+R8894E M1821(A8A) x5 | 123
7015C | Taman Berjaya | Sabah |  | Modernization |  | 2023Q4 | HQ 1 | Datasco | 4.6 TSSR Approved |  | 2023-06-12 | 2023-07-06 |  | 2023-07-11 |  | Closed | 2023-07-17 | 2023-07-25 | E//Hannah | 2023-07-25 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007 | DU00002039245 |  |  | 2023-08-18 | 2023-08-14 |  | Monopole | 30m Monopole | 30 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x5 | 123
7456A | Kg. Lunguyan | Sabah |  | Modernization |  | 2023Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-11 |  | 2023-05-13 |  | Closed | 2023-05-16 | 2023-05-17 | CD//Mohidi Jaan | 2023-05-17 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230508-0005 | DU00002039246 |  |  | 2023-07-18 | 2023-07-14 |  | Tower | Tower | 60 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
7192A | Wisma DAT | Sabah |  | Modernization |  | 2023Q4 | AD | AllStar | 4.6 TSSR Approved |  | 2023-06-22 | 2023-07-04 |  | 2023-07-12 |  | Closed | 2023-07-17 | 2023-07-21 | E//Hannah | 2023-07-21 | Celcom Digi_RAN-Allstar-TSS-Sabah-20230608-0004 | DU00002039247 |  |  | 2023-09-05 | 2023-08-12 |  | In-Building System | 3m RT (Wall Mounted Pole) | 5M | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8854 S2600(A4A) x1+R9224E M1821(AAB) x4 | 23
7127Z | KM60 Kalabakan-Nabawan | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | AD |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002039248 | [6 empty] | TOWER
7752B | Kg.Tulid | Sabah |  | Decomm | Decomm->On Hold->Decomm->On Hold->Decomm | 2023Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-06-07 |  |  |  | 2023-06-30 |  | 2023-06-14 | 2023-08-30 | CD//Jahganathan | 2023-06-14 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230608-0007 | DU00002039249 |  | 20230727: FE photos & info missing |  |  | 2024-01-19 |  | Tower
7064A | Pulutan | Sabah |  | Modernization |  | 2023Q3 | MS | GTSB | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-09 |  | 2023-05-15 |  | Closed | 2023-05-16 | 2023-05-17 | CD//Jahganathan | 2023-05-17 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230508-0005 | DU00002039250 |  |  | 2023-07-16 | 2023-07-10 |  | Tower | 45m 3 Legged Tower | 50m | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
7620B | Ladang Pegagau | Sabah |  | Modernization |  | 2023Q4 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-08 |  | 2023-06-15 |  | Closed | 2023-06-19 | 2023-08-04 | E//Hannah | 2023-08-03 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0011 | DU00002039251 |  |  | 2023-09-01 | 2023-08-22 |  | Tower | Tower | 60 | Add R9264M M1821 x5 + R8862A S2601 x2,Dismantle R8862A S1800(B6A) x3 |  | 23
7650B | USP PattonHill | Sabah |  | Modernization |  | 2023Q3 | MS | Futong | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-15 |  | 2023-05-25 |  | Closed | 2023-05-26 | 2023-06-14 | E//Hannah | 2023-06-14 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0004 | DU00002039252 |  |  | 2023-08-09 | 2023-08-02 |  | Tower | 60m 4 Legged Tower | 32 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3
7174Z | Ladang Melaka | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039253 | [6 empty] | TOWER
7450A | Crocker Range Research Centre | Sabah |  | Modernization |  | 2023Q3 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-05-17 | 2023-05-19 |  | 2023-05-23 |  | Closed | 2024-06-11 | 2024-06-27 | E//Hannah | 2023-07-05 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230516-0001 | DU00002039254 |  |  | 2023-07-25 | 2023-07-14 |  | Tower | Tower | 76m | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
7937B | LADANG JELATA BUMI | Sabah |  | Modernization |  | 2023Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-06-20 | 2023-06-22 |  | 2023-06-26 |  | Closed | 2023-07-03 | 2023-07-12 | E//Hannah | 2023-07-12 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0010 | DU00002039255 |  |  | 2023-08-29 | 2023-08-22 |  | Tower | 45m 3 Legged Tower | 76m | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
7689B | SgKawa | Sabah |  | Modernization |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-06-30 | 2023-07-25 |  | 2023-08-04 |  | Closed | 2023-08-09 | 2023-08-18 | E//Hannah | 2023-08-16 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007 | DU00002039256 |  |  | 2023-08-29 | 2023-08-29 |  | Tower | 30m Monopole | 54M | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 3 | 0
9070B | Lee Ling Commercial @ Choice Ria Matang | Sarawak |  | Modernization |  | 2023Q4 | SH | Trintel | 4.6 TSSR Approved |  | 2023-06-15 | 2023-07-31 |  | 2023-08-04 |  | Closed | 2023-08-04 | 2023-08-24 | E//Hannah | 2023-08-11 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230622 | DU00002039257 |  |  | 2023-09-01 | 2023-08-25 |  | Monopole | 30m Monopole | 32m | Add A9732 M1821 x3 + R9264H M901821 x1,Dismantle R8862A S2600(A4A) x2+R8894E M1821(A8A) x6 | 123
7691B | TUN FUAD T3 | Sabah |  | Modernization |  | 2023Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-06-19 | 2023-06-22 |  | 2023-06-24 |  | Rectificating | 2023-07-03 | 2023-07-11 | E//Hannah | 2023-07-10 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0010 | DU00002039258 |  |  | 2023-08-28 | 2023-08-22 |  | Tower | 45m 3 Legged Tower | 76 | Add A9732 M1821 x1 + R9264M M1821 x2 + R8862A S2601 x3,Dismantle R8894E M1821(A8A) x3 | 2
7809M | Pasar Tamu Keningau | Sabah |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039259 | [6 empty] | Micro Cell
7725B | Kg Pasir Putih Darat | Sabah |  | Modernization |  | 2023Q4 | AD | YPTT | 4.6 TSSR Approved |  | 2023-06-19 | 2023-07-10 |  | 2023-07-13 |  | Closed | 2023-07-14 | 2023-07-24 | CD//Mohidi Jaan | 2023-07-24 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002039260 |  |  | 2023-08-09 | 2023-08-01 |  | Monopole | 30m Monopole | 30 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
7938A | IOI Baturong 2 | Sabah |  | Modernization |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-06-16 | 2023-06-22 |  | 2023-06-26 |  | Closed | 2023-06-28 | 2023-07-13 | E//Hannah | 2023-07-12 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0010 | DU00002039261 |  |  | 2023-08-29 | 2023-08-22 |  | Tower | Tower | 75m | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x4
7096R | KG MATIKU | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2023Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2025-09-24 |  | 2025-09-29 |  | 2025-09-30 |  | 2025-10-07 | 2025-10-30 | E//Hannah | 2025-10-21 | SQ202509220707 - YPTT | DU00002039262 |  |  |  |  | 2025-11-18 |  | TOWER
7065A | Kg Kandalakan | Sabah |  | Modernization |  | 2023Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-05-07 | 2023-05-18 |  | 2023-05-23 |  | Closed | 2023-05-25 | 2023-07-06 | E//Nizar | 2023-07-05 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230508-0005 | DU00002039263 |  |  | 2023-07-18 | 2023-07-14 |  | Tower | 45m 3 Legged Tower | 50 | Add A9732 M1821 x3 + R9264M M1821 x1,Dismantle R8854E S1800(A6A) x4+R8854D S2100(A4A) x4 | 123
7190Z | KG GUDANG 4 | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | AD | Futong | 14.2 Drop (Done Survey) |  | 2023-06-02 |  |  |  |  | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002039264 | [6 empty] | TOWER
7023D | Kampung Bugaya | Sabah |  | Modernization |  | 2023Q4 | MS | Futong | 4.6 TSSR Approved |  | 2023-06-12 | 2023-06-15 |  | 2023-06-17 |  | Closed | 2023-06-19 | 2023-06-28 | CD//Mohidi Jaan | 2023-06-28 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0011 | DU00002039265 |  |  | 2023-08-22 | 2023-08-22 |  | Monopole | 30M Monopole | 30 | Add R9264H M901821 x4,Dismantle R9224E M1821(AAB) x4
7673B | Mile 4 Tawau | Sabah |  | Modernization |  | 2023Q4 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-06-21 | 2023-06-22 |  | 2023-06-25 |  | Closed | 2023-07-03 | 2023-08-04 | E//Hannah | 2023-08-04 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230612-0004 | DU00002039266 |  |  | 2023-08-13 | 2023-08-09 |  | Monopole | 30m Monopole | 30 | Add A9732 M1821 x3 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x4 | 123
9351B | BDA Housing Kidurong MP | Sarawak |  | Modernization |  | 2023Q3 | BY | AllStar | 4.6 TSSR Approved |  | 2023-05-13 | 2023-05-13 |  | 2023-05-18 |  | Closed | 2023-05-24 | 2023-06-01 | E//Hannah | 2023-06-01 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230516-0005 | DU00002039267 |  |  | 2023-06-30 | 2023-06-22 |  | Monopole | Tower | 36M | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2600 x1,Dismantle R8882 S1800B(B6B) x3 |  | 2
7454A | TMB Sook | Sabah |  | Modernization |  | 2023Q3 | AD | Datasco | 4.6 TSSR Approved |  | 2023-08-01 | 2023-08-09 |  | 2025-02-07 |  | Closed | 2023-08-14 | 2023-08-28 | E//Hannah | 2023-08-28 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230703.xls | DU00002039268 |  |  | 2024-02-14 | 2024-01-16 |  | Tower | Tower | 90m | Add R9264H M901821 x1 + R9264M M1821 x2 + R8854 S2600 x1,Dismantle R8862A S1800(B6A) x2
9009C | Matang Malihah | Sarawak |  | Modernization |  | 2023Q4 | ZB | AllStar | 4.6 TSSR Approved |  | 2023-06-29 | 2023-07-05 |  | 2023-07-07 |  | Closed | 2023-07-10 | 2023-07-25 | E//Zulakmar | 2023-07-21 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230622 | DU00002039269 |  |  | 2023-09-26 | 2023-09-21 |  |  | 30m Monopole | 30 | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
9125B | Semarian Aman | Sarawak |  | Modernization |  | 2023Q4 | SH | Trintel | 4.6 TSSR Approved |  | 2023-06-27 | 2023-08-01 |  | 2023-08-04 |  | Closed | 2023-08-04 | 2023-09-08 | E//Hannah | 2023-09-08 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230622 | DU00002039270 |  |  | 2023-09-06 | 2023-09-04 |  | Monopole | 30m Monopole | 25m | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8892E M1821(BAA) x3 |  | 2
7094R | KG ULU TIKU | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | AD | Futong | 14.2 Drop (Done Survey) |  | 2023-06-02 |  |  |  |  | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002039271 | [6 empty] | TOWER
7445A | Kg Apin | Sabah |  | Modernization |  | 2023Q3 | MS | Datasco | 4.6 TSSR Approved |  | 2023-05-18 | 2023-06-06 |  | 2023-06-14 |  | Closed | 2023-06-15 | 2023-06-17 | E//Hannah | 2023-06-16 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230508-0004 | DU00002039272 |  |  | 2023-07-13 | 2023-07-11 |  | Tower | Tower | 60 | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x3 |  | 3
7187Z | PULAU DANAWAN | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 |  | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002039273 | [6 empty] | TOWER
7849A | Giant Tawau IB | Sabah |  | Modernization |  | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-06-21 | 2023-07-07 |  | 2023-07-26 |  | Closed | 2023-07-27 | 2023-07-29 | E//Hannah | 2023-07-29 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002039274 |  |  | 2023-08-14 | 2023-08-01 |  | Portables BTS | In-building system |  | Add R8862A S1800 x1 + R8862A S2100 x1,Dismantle R8882-GUL1812 x1
7458A | Sapulut Town | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2023Q3 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-02 |  |  |  | 2023-06-15 |  | 2023-06-20 | 2023-08-23 | CD//Jahganathan | 2023-06-21 | Celcom Digi_RAN-Futong-TSS-Sabah-20230531-0008 | DU00002039275 |  | 2023-07-06 missing tx photos and info |  |  | 2025-10-21 |  | 60m 4 Legged Tower
7346B | Bandar Seri Indah 2 | Sabah |  | Modernization |  | 2023Q4 | AD | Datasco | 4.6 TSSR Approved |  | 2023-06-11 | 2023-06-23 |  | 2023-06-26 |  | Closed | 2023-06-28 | 2023-07-17 | E//Hannah | 2023-07-17 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007 | DU00002039276 |  |  | 2023-08-18 | 2023-08-16 |  | Tower | Tower | 60 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8862A S2600(A4A) x1+R9224E M1821(AAB) x4 | 23(S1->S2,S2->S3,S3->S1,rename Sector ID,FDD MM@NEW S1S2)
9520A | Saberkas Miri MP | Sarawak |  | Modernization |  | 2023Q4 | SH | Magicell | 4.6 TSSR Approved |  | 2023-06-14 | 2023-06-15 |  | 2023-06-20 |  | Closed | 2023-06-21 | 2023-07-04 | E//Hannah | 2023-07-04 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002039277 |  |  | 2023-08-08 | 2023-07-27 |  | Monopole | 30m Monopole | 36M | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
7099R | LADANG LKSK | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2025-07-15 |  | 2025-07-16 |  | 2025-07-19 |  | 2025-08-07 | 2025-11-03 | E//Hannah | 2025-09-16 | SQ202506100849 - GTSB / SQ202507010442 - GTSB | DU00002039278 |  |  |  |  | 2025-11-22 |  | TOWER
7015R | Kg Kunak 3 | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039279 | [6 empty] | Land site
7965B | Masjid Tawau | Sabah |  | Modernization |  | 2023Q4 | AD | YPTT | 4.6 TSSR Approved |  | 2023-06-19 | 2023-06-27 |  | 2023-07-03 |  | Closed | 2023-07-05 | 2023-07-13 | CD//Ray Amos | 2023-07-13 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002039280 |  |  | 2023-08-13 | 2023-08-08 |  | Monopole | 30m Lampole | 30 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8862A S1800(B6A) x2+R8862A S2100(A6A) x2+R8854 S2600(A4A) x1+R8894E M1821(A8A) x2 | 13
9004R | RUMAH LIBAU | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039281 | [6 empty] | Land site
B00810 | B060B_B00810OD_TMNTIRAMBARU | Central |  | Decomm |  | 2023Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2023-07-27 |  |  |  | 2023-09-15 |  | 2023-09-15 | 2024-05-10 | CD//Norhaliza | 2023-10-04 | CelcomDigi_RAN_AllStar_TSS_Central_20230802 | DU00002039282 |  |  |  |  | 2023-09-09 |  | TOWER
B01298 | B065B_B01298OD_FELDATENGISLN | Central | 1117K | Swap |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-07-03 | 2023-07-05 |  | 2023-07-10 |  | Closed | 2023-07-17 | 2023-08-02 | CD//Ali akaram | 2023-08-02 | CelcomDigi_RANMW_Magicell_Central_20230706_0009 | DU00002039283 |  |  | 2023-09-04 | 2023-08-29 |  | Tower | TOWER | 75 | Add R9264H M901821 x3 + R9264M M1821 x3 + R8862A S2601 x6,Dismantle Celcom all RRU&BBU |  | 123
K00675 | K004A_K00675OD_BANDAR_BARU_MERGONG | Northern |  | Decomm |  | 2023Q4 | MH | CCSMY | 4.6 TSSR Approved |  | 2023-05-26 |  |  |  | 2023-06-21 |  | 2023-06-23 | 2023-08-28 | CD//Rohizam | 2023-08-04 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230529-0020 | DU00002039284 |  |  |  |  | 2023-10-10 |  | UNIPOLE
Q00509 | Q132A_Q00509OD_CB_MYYBTUTRUNK | Sarawak | 9179P | Swap | Swap->Maintain USP MOCN->On Hold->Maintain USP MOCN->On Hold->Swap | 2023Q3 | AD | Magicell | 4.6 TSSR Approved |  | 2023-05-16 | 2023-05-19 |  | 2023-05-23 |  | Closed | 2023-05-25 | 2025-12-19 | CD//John | 2025-10-21 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230517-0009 | DU00002039285 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution changed | 2025-09-21 | 2025-09-18 |  | Tower | TOWER | 76 | Add R8894E M1821x3+R9264H M901821x3, Dismantle | 0 | 0
P00044 | P035C_P00044OD_WISMAGETAH | Northern | 4120K | Swap |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-23 | 2023-05-29 |  | 2023-06-03 |  | Closed | 2023-06-07 | 2023-07-26 | CD//Heng | 2023-07-25 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0015 | DU00002039286 |  |  | 2023-08-24 | 2023-08-21 |  |  | BOOM | 6 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 3
P00083 | P031B_P00083OD_KASTAMBATUMAUNG | Northern | 4122K | Swap |  | 2023Q3 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-06-16 | 2023-06-23 |  | 2023-06-26 |  | Closed | 2023-07-03 | 2023-07-06 | CD//Heng | 2023-07-04 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0008 | DU00002039287 |  |  | 2023-07-23 | 2023-07-18 |  | In-Building System | BOOM | 5m Boom | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 13
9921A | Wisma Yong Lung (REL) | Sarawak |  | Modernization |  | 2023Q4 | ZB | Trintel | 4.6 TSSR Approved |  | 2023-06-13 | 2023-07-03 |  | 2023-07-07 |  | Closed | 2023-07-14 | 2023-07-28 | E//Zulakmar | 2023-07-28 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230614-0010 | DU00002039288 |  |  | 2023-09-01 | 2023-08-18 |  | Monopole | 3m Bipod (RT) | 30m | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 |  | 13
A01213 | Lata Iskandar _ Kg Tua Ulu Kerian | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039289 | [6 empty] | TOWER
P00626 | P031B_P00626IB_PLEXUS | Northern | 4155K | Swap |  | 2023Q3 | WP | YPTT | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-13 |  | 2023-05-22 |  | Closed | 2023-07-11 | 2023-07-18 | CD//Shamsul | 2023-07-18 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0008 | DU00002039290 |  |  | 2023-07-27 | 2023-07-18 |  |  | IN-BUILDING | N/A | Add R8852E S9000 x2 + R8862A S2100 x2 + R8862A S2601 x2,Dismantle all celcom BBU&RRU
P00577 | P031A_P00577OD_KGJLNBHARU | Northern |  | Decomm |  | 2023Q3 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-05-25 |  |  |  | 2023-06-26 |  | 2023-06-27 | 2024-02-29 | CD//Shamsul | 2023-07-06 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002039291 |  | No TX Info, Photo not enough |  |  | 2023-09-26 |  | TOWER
A01187 | T3E_0620_Jalan Jelai-Redang Panjang | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039292 | [6 empty] | TOWER
K00108 | K004A_K00108OD_MENARASENTOSA | Northern | 4090K | Swap |  | 2023Q4 | WP | GTSB | 4.6 TSSR Approved |  | 2023-07-17 | 2023-07-18 |  | 2023-07-21 |  | Closed | 2023-07-25 | 2023-08-04 | CD//Rohizam | 2023-08-04 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002039293 |  |  | 2023-10-06 | 2023-09-20 |  | Rooftop | BOOM | 70 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x5,Dismantle Celcom all RRU&BBU |  | 12
Q00346 | Q132C_Q00346OD_CB_PADANGKERBAU | Sarawak |  | Decomm |  | 2023Q4 | ZB | NR services | 4.6 TSSR Approved |  | 2023-07-18 |  |  |  | 2023-07-20 |  | 2023-08-15 | 2024-03-21 | CD//John | 2023-08-17 | Celcom Digi_RAN-NR Services-TSS-Sarawak-20230823/0619Sarawak-NR services-BOQ Template (template) | DU00002039294 |  | TP not prepared by NR which is prepared by CCS. Awaiting NR to Resurvey. |  |  | 2025-01-27 |  | TOWER
P00289 | P035D_P00289OD_HABOURCITY | Northern |  | Decomm |  | 2023Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-05-08 | [5 empty] | 2023-08-08 | 2024-02-27 | CD//Affendi | 2023-08-09 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230829-0032/Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2 | DU00002039295 |  |  |  |  | 2024-10-29 |  | BOOM
9922A | Miri Housing Ph 2 ( R ) | Sarawak |  | Modernization |  | 2023Q4 | SH | South Pacific | 4.6 TSSR Approved |  | 2023-06-16 | 2023-06-19 |  | 2023-06-22 |  | Closed | 2023-06-23 | 2023-09-18 | E//Hannah | 2023-09-08 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230606-0003 | DU00002039296 |  |  | 2023-08-16 | 2023-08-11 |  | Monopole | 30m Rapole | 30m | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8882 S1800B(B6B) x3++R8881 S2100 x3+ |  | 23
Q00109 | Q124F_Q00109OD_TMMATANGJAYA | Sarawak |  | Decomm |  | 2023Q4 | ZB | South Pacific | 4.6 TSSR Approved |  | 2023-06-22 |  |  |  | 2023-07-21 |  | 2023-07-27 | 2023-08-30 | CD//John | 2023-07-28 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230622 | DU00002039297 |  | Drawing not match with info data |  |  | 2023-10-03 |  | MONOPOLE
B02734 | B061A_B02734OD_APRTSEK7JLNPLUMBUMSHAHALAM | Central | 1168K | Swap |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-07 | 2023-06-14 |  | 2023-06-20 |  | Closed | 2023-06-21 | 2023-07-07 | CD//Sapian | 2023-07-04 | CelcomDigi_RANMW_GTSB_TSS_Central_20230609_0002 | DU00002039298 |  |  | 2023-10-05 | 2023-09-29 |  | Monopole | UNIPOLE | 8Meter | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 12
B00367 | B058B_B00367OD_TMBKTKLG | Central | 1077K | Swap |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-05-22 | 2023-05-25 |  | 2023-05-27 |  | Closed | 2023-05-30 | 2023-06-05 | CD//Sapian | 2023-06-01 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002039299 |  |  | 2023-09-22 | 2023-08-29 |  |  | 4LEGGED | 51 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 23
B01820 | B058B_B01820OD_RAJAMUDAMUSA | Central |  | Decomm |  | 2023Q3 | MA | Futong | 4.6 TSSR Approved |  | 2023-05-12 |  |  | 2023-06-03 | 2024-05-06 | Closed | 2023-07-21 | 2023-12-19 | CD//Norhaliza | 2023-09-04 | CelcomDigi_RAN_Futong_TSS_Central_20230626_decom reraise | DU00002039300 |  |  |  |  | 2023-07-28 |  | BOOM
P00684 | P031B_P00684OD_KEM_TUN_RAZAK_PG | Northern | 4156K | Swap |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-15 | 2023-06-28 |  | 2023-07-04 |  | Closed | 2023-07-05 | 2023-07-12 | CD//Shamsul | 2023-07-11 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0014 | DU00002039301 |  |  | 2023-08-29 | 2023-07-18 |  |  | RAPID ASSEMBLY POLE (RAPOLE) | 30 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 12
B00109 | B065B_B00109OD_KM405BELATAHOT | Central |  | Decomm |  | 2023Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-07-20 |  |  |  | 2023-10-24 |  | 2024-05-06 | 2024-11-05 | CD//Norhaliza | 2024-08-07 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230721 | DU00002039302 |  |  |  |  | 2023-09-27 |  | 3LEGGED
C00785 | Kg Hulu Chemperuh_T3_0029_RAN SHARING | Central |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039303 | [6 empty] | 3LEGGED
C00782 | Kg Ceringing Hulu_T3_0021_RAN SHARING | Central |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039304 | [6 empty] | 3LEGGED
Q00674 | Q118B_Q00674OD_KGHULUNYALAU | Sarawak |  | Decomm |  | 2023Q3 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-05-26 |  |  |  | 2023-07-26 |  | 2023-07-26 | 2024-02-15 | CD//John | 2023-07-28 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230529-0012/Celcom Digi_RAN-Magicell-TSS DECOMM-Sarawak-20230818 | DU00002039305 |  |  |  |  | 2024-04-04 |  | 3LEGGED
A00468 | A042A_A00468OD_CB_KGSGARA | Northern | 4069K | Swap |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-06-05 | 2023-07-13 |  | 2023-07-17 |  | Closed | 2023-07-18 | 2023-07-22 | CD//Quah | 2023-07-21 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230606-0022 | DU00002039306 |  |  | 2023-08-16 | 2023-08-10 |  | Tower | TOWER | 60 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 2
Q00564 | Q132C_Q00564OD_JLNKROKOP | Sarawak |  | Decomm |  | 2023Q4 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-07-01 |  |  | 2023-07-10 |  | Closed | 2023-07-11 | 2023-10-13 | CD//John | 2023-07-12 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 | DU00002039307 |  |  |  |  | 2025-06-20 |  | MONOPOLE
P00040 | P035D_P00040OD_SGPINANG | Northern |  | Decomm |  | 2023Q3 | MH | CCSMY | 4.6 TSSR Approved |  | 2023-05-19 |  |  |  | 2023-06-20 |  | 2023-06-21 | 2023-08-30 | CD//Affendi | 2023-06-28 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002039308 |  |  |  |  | 2023-08-14 |  | BOOM
B01126 | B065B_B01126OD_FELDAGEDANGSA | Central |  | Decomm |  | 2023Q4 | MA | Magicell | 4.6 TSSR Approved |  | 2023-06-02 |  |  |  | 2023-06-15 |  | 2023-06-21 | 2023-08-18 | CD//Sapian | 2023-07-04 | CelcomDigi_RAN_Magicell_TSS_Central_20230606_0011 / CelcomDigi_TX_Magicell_TSS_Decom_Central_20230714 | DU00002039309 |  |  |  |  | 2023-09-14 |  | TOWER
Q00137 | Q124F_Q00137OD_JLNHELANG | Sarawak |  | Decomm |  | 2023Q4 | SH | Datasco | 4.6 TSSR Approved |  | 2023-06-23 |  |  |  | 2023-07-28 |  | 2023-07-28 | 2023-09-19 | CD//John | 2023-07-28 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 | DU00002039310 |  | 8/9: uncompleted info & photos |  |  | 2023-09-29 |  | TOWER
B00447 | B062A_B00447OD_SEKINCHAN2 | Central | 1081K | Swap |  | 2023Q4 | HQ 1 | Magicell | 4.6 TSSR Approved |  | 2023-06-12 | 2023-06-12 |  | 2023-06-14 |  | Closed | 2023-06-17 | 2023-06-28 | CD//Sapian | 2023-06-27 | CelcomDigi_RAN_Magicell_TSS_Central_20230612_0012 | DU00002039311 |  |  | 2023-08-15 | 2023-08-10 |  | Tower | 4LEGGED | 60M | Add R9264H M901821 x3 + R9264M M1821 x3 + R8862A S2601 x6,Dismantle Celcom all RRU&BBU |  | 123
P00514 | P035E_P00514OD_TMNISLANDGLADE | Northern |  | Decomm |  | 2023Q3 | MH | GTSB | 4.6 TSSR Approved |  | 2023-05-02 |  |  |  | 2023-06-15 |  | 2023-06-15 | 2023-07-21 | CD//Heng | 2023-07-18 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230720-0023/Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2 | DU00002039312 |  |  |  |  | 2023-08-02 |  | BOOM
P00084 | P035C_P00084OD_HTLMALAYSIA | Northern | 4123K | Swap |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-25 | 2023-06-26 |  | 2023-07-05 |  | Closed | 2023-07-06 | 2023-07-13 | CD//Affendi | 2023-07-12 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0015 | DU00002039313 |  |  | 2023-08-29 | 2023-08-24 |  | Wall mount boom | BOOM | 5m | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 2
9815A | Boulevard Shopping Mall Indoor | Sarawak |  | Modernization | Modernization->On hold->Decomm->On Hold->Modernization | 2023Q4 | AD | AllStar | 4.6 TSSR Approved |  | 2023-06-14 | 2023-06-22 |  | 2024-05-15 |  | Under Approval | 2024-05-06 | 2026-03-02 | E//Nazrul | 2025-11-20 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230608-0006 | DU00002039314 | Remarks: Solution TSSR/BOM Changed | Require TSSR Revision, Solution Changed | 2025-09-25 | 2025-09-19 |  |  | In-building system |  | Add R8862A S1800x1 + R8862A S2100x1 + R8862A S2601x1,Dismantle R8882-GUL1812 x1+R8882 S2600(B4A) x1 | 0 | 0
B00897 | B061B_B00897IB_CONCORDESHLM | Central |  | Decomm |  | 2023Q4 | MA | Datasco | 4.6 TSSR Approved |  | 2023-08-08 |  |  |  | 2023-08-16 |  | 2023-08-19 | 2023-12-19 | CD//Syafiq | 2023-08-29 | CelcomDigi_RAN_Datasco_TSS_Central_20230808 | DU00002039315 |  |  |  |  | 2024-02-07 |  | IN-BUILDING
B02693 | B065B_B02693OD_PELANGIHILLKERLING | Central | 1164K | Swap |  | 2023Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-06-26 | 2023-06-28 |  | 2023-07-06 |  | Closed | 2023-07-08 | 2023-07-17 | CD//Sapian | 2023-07-17 | CelcomDigi_RANMW_Ascentrack_TSS_Central_20230622_0006 | DU00002039316 |  |  | 2023-09-28 | 2023-09-22 |  | Tower | 3LEGGED | 60 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
Q00136 | Q124F_Q00136OD_PERYATIM | Sarawak | 9058K | Swap |  | 2023Q4 | HQ 1 | Trintel | 4.6 TSSR Approved |  | 2023-07-01 | 2023-07-25 |  | 2023-07-29 |  | Closed | 2023-07-31 | 2023-08-03 | CD//John | 2023-08-02 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230622 | DU00002039317 |  |  | 2023-10-10 | 2023-09-19 |  | Tower | GUYED MAST | 45 | Add R9264M M1821 x2+R9264H M901821 x3+R8862A S2601 x5,Dismantle | 0 | 23
P00759 | P031B_P00759OD_DESARIA_PNG | Northern | 4160K | Swap |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-15 | 2023-07-10 |  | 2023-07-06 |  | Closed | 2023-07-06 | 2023-07-12 | CD//Shamsul | 2023-07-11 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0015 | DU00002039318 |  |  | 2023-07-19 | 2023-07-18 |  | Lampole | PBTS | 25 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
B01279 | B061A_B01279IB_QUALITYHOTEL | Central | 1116K | Swap |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-06-23 | 2023-06-27 |  | 2023-07-10 |  | Closed | 2023-07-14 | 2023-08-28 | IBC pic | 2023-08-28 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_0030 | DU00002039319 |  |  | 2023-12-28 | 2023-12-28 |  |  | IN-BUILDING | NA | Add R8862A S2100 x3+R8862A S1800 x3,Dismantle all celcom BBU&RRU
Q00660 | Q124B_Q00660OD_CB_TELAGAAIR | Sarawak |  | Decomm |  | 2023Q4 | SH | Datasco | 4.6 TSSR Approved |  | 2023-06-26 |  |  | 2023-07-20 |  | Closed | 2023-07-21 | 2023-10-13 | CD//John | 2023-07-23 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 | DU00002039320 |  | 8/9: uncompleted info & photos |  |  | 2023-10-27 |  | TOWER
B01215 | B065A_B01215OD_FRUITVALLEY2 | Central |  | Decomm |  | 2023Q3 | SS | GTSB | 4.6 TSSR Approved |  | 2023-05-18 |  |  |  | 2023-06-15 |  | 2023-06-21 | 2023-10-17 | CD//Sapian | 2023-07-12 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002039321 |  |  |  |  | 2023-09-04 |  | TOWER
P00218 | P035A_P002180D_BKTBENDERA | Northern |  | Decomm |  | 2023Q3 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-07-21 |  |  |  | 2023-08-15 |  | 2023-07-27 | 2023-08-28 | CD//Affendi | 2023-07-31 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1/Celcom Digi_RAN-CCSMY-TSS Decomm-Northern-20240131-0091 | DU00002039322 |  |  |  |  | 2024-08-28 |  | BOOM
A00165 | A00165OD_CB_ULUSEPETANG_RDD | Northern |  | Decomm |  | 2023Q4 | ZA | YPTT | 4.6 TSSR Approved |  | 2023-06-09 |  |  |  | 2023-08-01 |  | 2023-08-03 | 2023-10-09 | CD//Shamsul | 2023-08-06 | Celcom Digi_RAN-YPTT-TSS Decomm-Northern-20230720-0025/Celcom Digi_RAN-YPTT-TSS-Northern-20230612-0019 | DU00002039323 |  |  |  |  | 2023-09-18 |  | TOWER
B02579 | B065B_B02579OD_TMNINAISCT | Central |  | Decomm |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-17 |  |  |  | 2024-04-04 |  | 2023-06-22 | 2023-11-15 | CD//Norhaliza | 2023-09-07 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002039324 |  |  |  |  | 2023-07-24 |  | UNIPOLE
B01258 | B061C_B01258OD_TMNBKTRIMAU2 | Central | 1814K | Swap | Decomm->Swap | 2023Q3 | SS | AllStar | 4.6 TSSR Approved |  | 2023-06-20 | 2023-10-03 |  | 2023-10-11 |  | Closed | 2023-07-17 | 2023-10-20 | CD//Sapian | 2023-07-24 | 0626Central-Allstar-BOQ Template (template) | DU00002039325 |  |  | 2023-09-10 | 2023-09-05 |  | Monopole | MONOPOLE | 30 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle
B01216 | B061A_B01216OD_PR_JLNZAMRUDSEK7 | Central |  | Decomm |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-06-14 |  |  |  | 2024-04-17 |  | 2023-08-01 | 2024-05-24 | CD//Norhaliza | 2023-08-15 | CelcomDigi_RAN_Datasco_TSS_Central_20230616_0026 | DU00002039326 |  |  |  |  | 2023-10-28 |  | MONOPOLE
P00404 | P035C_P00404OD_JLNGURNEY | Northern |  | Decomm |  | 2023Q3 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-05-17 |  |  |  | 2023-06-28 |  | 2023-06-28 | 2023-08-30 | CD//Rohizam | 2023-08-02 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002039327 |  | No TX Info, Photo not enough 11/8:Need include Zoom in photo ODF&E1 |  |  | 2023-09-05 |  | MINARET
K00402 | K004A_K00402OD_KGKBGLINTAH | Northern | 4097K | Swap |  | 2023Q4 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-06-29 | 2023-06-27 |  | 2023-06-30 |  | Closed | 2023-07-04 | 2023-08-04 | CD//Rohizam | 2023-08-04 | Celcom Digi_RAN-GCI-TSS-Northern-20230626-0035 | DU00002039328 |  |  | 2023-09-27 | 2023-09-09 |  |  | TOWER | 60 | Add R8852E S9000 x3 + A9732 M1821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 123
C00001 | C046C_C00001OD_GOHTONGJAYA | Central |  | Decomm |  | 2023Q4 | CR | Magicell | 4.6 TSSR Approved |  | 2023-08-07 |  |  |  | 2023-08-08 |  | 2023-08-09 | 2023-12-19 | CD//Norhaliza | 2023-08-18 | CelcomDigi_RAN_Magicell_TSS_Central_20230808 | DU00002039329 |  |  |  |  | 2024-01-22 |  | BOOM
Q00254 | Q118B_Q00254OD_BKTNYABAU | Sarawak |  | Decomm |  | 2023Q3 | ZB | CCSMY | 4.6 TSSR Approved |  | 2023-07-29 |  |  |  | 2023-08-02 |  | 2023-08-15 | 2024-07-19 | CD//John | 2023-08-15 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230614-0008 | DU00002039330 |  | 4/9: wrong proposal uncompleted photos & info |  |  | 2023-12-26 |  | TOWER
B00600 | B057C_B00600OD_UIA1GBK | Central |  | Decomm |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-07-31 |  |  |  | 2024-08-22 |  | 2023-08-04 | 2023-08-24 | CD//Norhaliza | 2023-08-18 | CelcomDigi_RAN_Datasco_TSS_Central_20230802 | DU00002039331 |  |  |  |  | 2024-04-19 |  | AESTHETIC MONOPOLE
Q00572 | Q124F_Q00572OD_JLNDEMAK | Sarawak |  | Decomm |  | 2023Q4 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-06-20 |  |  | 2023-07-28 |  | Closed | 2023-07-28 | 2023-10-06 | CD//John | 2023-07-29 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 | DU00002039332 |  | 8/9: uncompleted info & phoots |  |  | 2023-10-05 |  | TOWER
B01305 | B061C_B01305OD_PR_MRBSSEK312SHLM | Central | 1833K | Decomm | Decomm->Swap->Decomm | 2023Q3 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-06-17 |  |  |  | 2023-07-17 |  | 2023-07-24 | 2023-09-11 | CD//Norhaliza | 2023-07-09 | CelcomDigi_RAN_CCSMY_TSS_Central_20230620_0003 | DU00002039333 |  |  |  |  | 2023-09-09 |  | LAMP_POLE
Q00247 | Q118B_Q00247OD_JLNKEMENA | Sarawak |  | Decomm |  | 2023Q3 | SH | AllStar | 4.6 TSSR Approved |  | 2023-08-14 |  |  |  | 2023-09-01 |  | 2023-09-01 | 2024-08-16 | CD//John | 2023-09-03 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230622/0612Sarawak-AllStar-BOQ Template (template).xls | DU00002039334 |  | 16/8: Uncompleted info & photos |  |  | 2023-12-20 |  | GUYED MAST
Q00667 | Q118B_Q00667OD_TMNYANMIN | Sarawak |  | Decomm |  | 2023Q3 | SH | South Pacific | 4.6 TSSR Approved |  | 2023-05-18 |  |  |  | 2023-05-19 |  | 2023-05-25 | 2023-07-21 | CD//John | 2023-05-27 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230622 | DU00002039335 |  |  |  |  | 2023-11-23 |  | MONOPOLE
B00806 | B058C_B00806OD_TMNSENTOSA | Central |  | Decomm |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-07-07 |  |  |  | 2024-05-20 |  | 2023-07-18 | 2023-09-19 | CD//Norhaliza | 2023-09-13 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230626_decom reraise | DU00002039336 |  | Approved 28/7 |  |  | 2023-08-14 |  | TRIPOD
B02778 | B061B_B02778OD_TRWSEKU8SA | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-31 |  |  |  | 2023-05-31 |  | 2023-06-14 |  | CD//Sapian | 2023-11-21 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002039337 |  |  |  |  | 2023-12-19 |  | BOOM WALL-MOUNTED
B01802 | B057B_B01802OD_JLNSGTUA | Central |  | Decomm |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-07-30 |  |  |  | 2023-07-30 |  | 2023-08-03 | 2023-10-17 | CD//Ali Akaram | 2023-08-14 | CelcomDigi_RAN_YPTT_TSS_Central_20230727 | DU00002039338 |  |  |  |  | 2023-09-24 |  | TOWER
Q00064 | Q124B_Q00064OD_MATANGJAYA | Sarawak |  | Decomm |  | 2023Q4 | SH | Trintel | 4.6 TSSR Approved |  | 2023-07-28 |  |  |  | 2023-08-19 |  | 2023-08-21 | 2023-08-23 | CD//John | 2023-08-21 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230622 | DU00002039339 |  |  |  |  | 2025-09-20 |  | BOOM
B01955 | B061A_B01955OD_SEKU10TMNPCKPDANA | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-17 |  |  |  | 2023-05-31 |  | 2023-08-09 | 2023-09-19 | CD//Sapian | 2023-08-15 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002039340 |  |  |  |  | 2023-09-04 |  | RAPID ASSEMBLY POLE (RAPOLE)
B01326 | B057B_B01326OD_TMNJASAUTAMA | Central |  | Decomm |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-07-30 |  |  |  | 2023-07-31 |  | 2023-08-02 | 2023-12-19 | CD//Norhaliza | 2023-08-15 | CelcomDigi_RAN_YPTT_TSS_Central_20230727 | DU00002039341 |  |  |  |  | 2023-09-23 |  | LAMP_POLE
B00035 | B065B_B00035OD_KM419UPEGOHHOT | Central |  | Decomm |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-05-12 |  |  |  | 2024-04-03 |  | 2023-06-22 | 2024-05-10 | CD//Ali Akaram | 2023-08-18 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002039342 |  |  |  |  | 2023-07-25 |  | TOWER
B00295 | B060B_B00295OD_TMKUALASGR | Central |  | Decomm |  | 2023Q4 | BY | AllStar | 4.6 TSSR Approved |  | 2023-09-15 |  |  |  | 2024-06-14 |  | 2024-01-15 | 2024-12-31 | CD//Ali akaram | 2024-01-31 | CelcomDigi_RAN_AllStar_TSS_Central_20230915_Decom | DU00002039343 |  |  |  |  | 2024-03-19 |  | BOOM
B01451 | B058B_B01451OD_TMNMAZNAH | Central |  | Decomm |  | 2023Q3 | SS | Futong | 4.6 TSSR Approved |  | 2023-05-23 |  |  | 2023-05-29 | 2024-05-06 | Closed | 2023-06-06 | 2023-07-17 | CD//Sapian | 2023-06-08 | CelcomDigi_RAN_Futong_TSS_Central_20230626_decom reraise | DU00002039344 |  |  |  |  | 2023-07-28 |  | UNIPOLE
B00539 | B058A_B00539OD_BT9KAPAR | Central |  | Decomm |  | 2023Q3 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-08-05 |  |  |  | 2023-08-21 |  | 2023-08-22 | 2023-12-19 | CD//Sapian | 2023-08-24 | CelcomDigi_RAN_CCSMY_TSS_Central_20230626_decom reraise | DU00002039345 |  |  |  |  | 2024-02-07 |  | TOWER
P00689 | P034D_P00689OD_AUTOMALL_KARPALSINGH | Northern |  | Decomm |  | 2023Q3 | ZA | YPTT | 4.6 TSSR Approved |  | 2023-05-07 |  |  |  | 2023-06-14 |  | 2023-06-15 | 2023-11-23 | CD//Affendi | 2023-06-27 | Celcom Digi_RAN-YPTT-TSS-Northern-20230609-0018 | DU00002039346 |  |  |  |  | 2023-10-04 |  | MINIMAST
C01194 | C046C_C01194IB_20THCENTURYFOX_THEMEPARK | Central |  | Decomm |  | 2023Q4 | CR | GTSB | 4.6 TSSR Approved |  | 2023-07-13 |  |  |  | 2023-07-28 |  | 2023-07-28 | 2023-11-29 | CD//Sofiah | 2023-11-23 | CelcomDigi_RAN_GTSB_TSS_Central_20230714 | DU00002039347 |  |  |  |  | 2025-12-10 |  | IN-BUILDING
B00770 | B065B_B00770OD_BKTTAGAR | Central |  | Decomm |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-06-28 |  |  |  | 2023-07-11 |  | 2023-07-24 | 2023-08-04 | CD//Ali akaram | 2023-08-01 | CelcomDigi_RAN_Magicell_TSS_Central_20230630_0019 | DU00002039348 |  |  |  |  | 2023-09-04 |  | 4LEGGED
B02489 | B058A_B02489OD_TMNINTANKAPAR | Central |  | Decomm |  | 2023Q3 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-06-09 |  |  | 2023-06-14 | 2023-06-14 | Closed | 2023-07-20 | 2023-08-19 | CD//Sapian | 2023-07-26 | CelcomDigi_RAN_CCSMY_TSS_Central_20230626_decom reraise | DU00002039349 |  |  |  |  | 2023-08-28 | Lampole | LAMP_POLE | 30M
B00560 | B061F_B00560OD_IJUK | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-16 |  |  |  | 2023-05-24 |  | 2023-06-15 | 2023-12-19 | CD//Sapian | 2023-07-03 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002039350 |  |  |  |  | 2023-09-15 |  | TOWER
B00554 | B057B_B00554OD_TMNSRISLYG | Central |  | Decomm |  | 2023Q4 | CR | YPTT | 4.6 TSSR Approved |  | 2023-09-23 |  |  |  | 2023-09-24 |  | 2023-09-25 | 2023-10-17 | CD//Sapian | 2023-10-01 | CelcomDigi_RAN_YPTT_TSS_Central_20231005 | DU00002039351 |  |  |  |  | 2023-09-26 |  | BOOM
B02284 | B061C_B02284IB_GAMUDAWALKKOTAKEMUNING | Central |  | Decomm |  | 2023Q3 | AI | GCI | 4.6 TSSR Approved |  | 2024-06-10 |  | 2024-07-01 |  | 2024-07-16 |  | 2024-07-17 | 2025-03-24 | CD//Sofiah | 2024-07-23 | 0920CD-Central-GCI-BOQ Template (old contract)/Celcom Digi_RAN-GCI-Standard PR TSS-Central-20241016 | DU00002039352 |  |  |  |  | 2024-09-05 |  | IN-BUILDING
Q00590 | Q124B_Q00590OD_MOYANHEIGHT | Sarawak |  | Decomm |  | 2023Q4 | ZB | South Pacific | 4.6 TSSR Approved |  | 2023-06-16 |  |  |  | 2023-07-25 |  | 2023-07-25 | 2023-09-19 | CD//John | 2023-07-26 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230622 | DU00002039353 |  | 24/8: uncompleted info |  |  | 2023-09-29 |  | TOWER
P00345 | P031B_P00345OD_ACDC | Northern |  | Decomm |  | 2023Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-05-23 |  |  |  | 2023-07-27 |  | 2023-06-23 | 2023-07-21 | CD//Affendi | 2023-06-28 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2 | DU00002039354 |  |  |  |  | 2023-10-04 |  | BOOM
B01089 | B061F_B01089OD_PCKALAM3 | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-08 |  |  | 2023-05-22 | 2023-05-22 | Under Approval | 2023-06-14 | 2023-07-17 | CD//Sapian | 2023-07-03 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002039355 |  |  |  |  | 2023-08-16 |  | TRIPOD
K00764 | K004A_K00764IB_AMAN_CENTRAL | Northern |  | Decomm |  | 2023Q4 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-11-20 |  |  |  | 2023-11-20 |  | 2023-11-21 | 2023-12-18 | CD//Affendi | 2023-12-01 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231122-0072 | DU00002039356 |  |  |  |  | 2023-10-05 |  | IN-BUILDING
A00232 | A042A_A00232OD_TMKAMUNTING | Northern | 4064K | Swap |  | 2023Q4 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-08-08 | 2023-08-07 |  | 2023-08-09 |  | Rectificating | 2023-08-11 | 2023-08-18 | CD//Quah | 2023-08-18 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230626-0029 | DU00002039357 |  |  | 2023-08-28 | 2023-08-10 |  | Tower | 4LEGGED | 37 | Add R8852E S9000 x3 + A9732 M1821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 123
B02292 | B057B_B02292OD_PST_BDR_SELAYANG | Central |  | Decomm |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-09-08 |  |  |  | 2023-09-21 |  | 2023-09-22 | 2023-12-19 | CD//Norhaliza | 2023-10-31 | CelcomDigi_RAN_YPTT_TSS_Central_20231005 | DU00002039358 |  |  |  |  | 2024-03-08 |  | BOOM
B02244 | B058B_B02244OD_JLNRODAT1KU5KLG | Central |  | Decomm |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-05-08 |  |  |  | 2023-07-26 |  | 2023-06-15 | 2023-08-18 | CD//Sapian | 2023-09-21 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002039359 |  |  |  |  | 2023-08-16 |  | MINI STRUCTURE
B00652 | B065B_B00652OD_ULUSELANGOR | Central |  | Decomm |  | 2023Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-01-11 |  |  |  | 2024-01-12 |  | 2024-01-15 | 2024-02-15 | CD//Sapian | 2024-01-29 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240115 | DU00002039360 |  |  |  |  | 2023-10-12 |  | TOWER
B00137 | B061B_B00137OD_PR_SEK13SA | Central |  | Decomm |  | 2023Q4 | CR | Datasco | 4.6 TSSR Approved |  | 2023-07-31 |  |  |  | 2023-08-04 |  | 2023-08-08 | 2023-10-17 | CD//Sapian | 2023-08-17 | CelcomDigi_RAN_Datasco_TSS_Central_20230802 | DU00002039361 |  |  |  |  | 2023-09-21 |  | TRIPOD
K00973 | K004A_K00973OD_KGALORMENONGAS | Northern | 4111K | Decomm | Swap->Decomm | 2023Q4 | BY | GTSB | 4.6 TSSR Approved | ¦ 0131 - To submit CD Decomm TSSR | 2023-06-14 | 2023-06-15 |  | 2023-06-23 |  | Closed | 2023-06-28 | 2023-09-18 | CD//Rohizam | 2024-02-01 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230829-0032_V2/Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002039362 |  |  |  |  | 2024-06-11 | Monopole | MONOPOLE | 37
B02383 | B062B_B02383OD_STDSGBESAR | Central |  | Decomm |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-06-07 |  |  |  | 2024-05-27 |  | 2023-07-14 | 2023-11-29 | CD//Sapian | 2023-08-04 | CelcomDigi_RAN_Magicell_TSS_Central_20230607_0012 | DU00002039363 |  |  |  |  | 2023-10-19 |  | LAMP_POLE
Q00721 | Q132C_Q00721OD_JLNSTAPELIA | Sarawak |  | Decomm |  | 2023Q4 | ZB | AllStar | 4.6 TSSR Approved |  | 2023-07-24 |  |  |  | 2023-08-17 |  | 2023-08-18 | 2023-10-04 | CD//John | 2023-08-18 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230608-0006 | DU00002039364 |  | 21/8: uncompleted info & photos |  |  | 2025-01-27 |  | MONOPOLE
Q00289 | Q118B_Q00289OD_KEMENA | Sarawak |  | Decomm |  | 2023Q3 | SH | AllStar | 4.6 TSSR Approved |  | 2023-08-14 |  |  |  | 2023-09-01 |  | 2023-09-01 | 2023-09-07 | CD//John | 2023-09-03 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230622 | DU00002039365 |  |  |  |  | 2024-01-16 |  | 4LEGGED
Q00712 | Q132C_Q00712OD_TMNPELITA | Sarawak |  | Decomm |  | 2023Q4 | BY | Datasco | 4.6 TSSR Approved |  | 2023-07-05 |  |  | 2023-07-11 |  | Under Approval | 2023-07-11 | 2023-09-23 | CD//John | 2023-07-12 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 | DU00002039366 |  |  |  |  | 2025-08-08 |  | MONOPOLE
B00411 | B058E_B00411OD_JLNKEBUN | Central |  | Decomm |  | 2023Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-06-19 |  |  |  | 2023-07-31 |  | 2023-08-02 | 2023-08-19 | CD//Sapian | 2023-08-16 | CelcomDigi_RAN_Allstar_TSS_Central_20230620_0013 | DU00002039367 |  |  |  |  | 2023-09-09 |  | TOWER
B00276 | B062A_B00276OD_VLPASIRPJG | Central | 1068K | Swap |  | 2023Q4 | HQ 1 | Magicell | 4.6 TSSR Approved |  | 2023-06-13 | 2023-06-16 |  | 2023-06-19 |  | Closed | 2023-06-21 | 2023-07-05 | CD//Sapian | 2023-07-04 | CelcomDigi_RAN_Magicell_TSS_Central_20230616_0013 | DU00002039368 |  |  | 2023-10-13 | 2023-08-10 |  | Tower | TOWER | 60 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 2
9834B | Sakura Ferraalloy | Sarawak |  | Modernization |  | 2023Q3 | BY | Magicell | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-12 |  | 2023-05-15 |  | Closed | 2023-05-17 | 2023-05-19 | CD//John | 2023-05-17 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230512-0007 | DU00002039369 |  |  | 2023-06-26 | 2023-06-20 |  | Monopole | TOWER | 30m | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
K00710 | K004A_K00710OD_KGANAKBUKIT | Northern | 4102K | Swap |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-28 | 2023-06-23 |  | 2023-06-27 |  | Closed | 2023-07-03 | 2023-08-03 | CD//Rohizam | 2023-08-02 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230529-0020 | DU00002039370 |  |  | 2024-02-23 | 2023-11-15 |  | Unipole | UNIPOLE | 7 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 3
Q00298 | Q118B_Q00298OD_JLNLUTONGBARAM | Sarawak | 9383K | Swap | Decomm->On Hold->Swap | 2023Q4 | SHA | Trintel | 4.6 TSSR Approved |  | 2024-10-08 | 2024-10-23 |  | 2024-11-18 | 2023-08-03 | Under Approval | 2024-11-18 | 2024-11-23 | CD//John | 2024-11-22 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230622/0823CD-Sarawak-South Pacific-BOQ Template(new contract)/0911MW-Sarawak-SOUTH PACIFIC-BOQ Template (old contract)/SQ202509040331-Trintel | DU00002039371 |  | 16/8: Uncompleted info & photos | 2025-07-06 | 2025-06-06 |  | Guide mast | TOWER | 60 | Add R8862A S9000x3+R8894E M1821x3, Dismantle | 0 | 0
K00487 | K004A_K00487OD_SOUQBUKHARI | Northern | 4099K | Swap |  | 2023Q4 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-06-16 | 2023-06-19 |  | 2023-06-23 |  | Closed | 2023-06-28 | 2023-08-03 | CD//Rohizam | 2023-08-02 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002039372 |  |  | 2023-09-25 | 2023-09-22 |  | Lampole | LAMP_POLE | 19 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x5,Dismantle Celcom all RRU&BBU |  | 12
B01214 | B061D_B01214OD_KM14FEDHWY | Central | 1113K | Swap |  | 2023Q4 | HQ 6 | Datasco | 4.6 TSSR Approved |  | 2023-05-29 | 2023-05-30 |  | 2023-06-02 |  | Closed | 2023-06-05 | 2023-07-03 | CD//Sapian | 2023-07-03 | CelcomDigi_RAN_Datasco_TSS_Central_20230531_0024 | DU00002039373 |  |  | 2023-08-29 | 2023-08-29 |  | Tower | MINI STRUCTURE | 20 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x5,Dismantle Celcom all RRU&BBU |  | 12
A00720 | A042B_A00720IB_TAIPING_SENTRAL | Northern |  | Decomm |  | 2023Q4 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-06-07 | [5 empty] | 2023-08-04 | 2023-08-19 | CD//Quah | 2023-08-17 | Celcom Digi_RAN-GTSB-TSS-Northern-20230529-0020/Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230726-0024 | DU00002039374 |  |  |  |  | 2023-09-05 |  | IN-BUILDING
B00354 | B061A_B00354OD_PR_SEK7SA | Central |  | Decomm |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-12 |  |  |  | 2023-07-13 |  | 2023-07-13 | 2023-12-19 | CD//Norhaliza | 2023-07-20 | CelcomDigi_RAN_GTSB_TSS_Central_20230616_0029 | DU00002039375 |  |  |  |  | 2023-10-10 |  | BOOM
B02500 | B065B_B02500OD_SURAUALMUTTAQINANTARAGAPI | Central |  | Decomm |  | 2023Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-10-13 |  |  |  | 2023-10-24 |  | 2023-10-24 | 2025-03-24 | CD//Ali akaram | 2023-11-14 | CelcomDigi_RAN_Ascentrack_TSS_Central_20240513 | DU00002039376 |  |  |  |  | 2023-10-13 |  | LAMP_POLE
Q00681 | Q116A_Q00681OD_BAKUNHYDRO | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2023Q3 | AD | Magicell | 4.6 TSSR Approved |  | 2025-06-18 |  | 2025-06-30 |  | 2025-07-10 |  | 2025-08-07 | 2025-10-31 | E//John | 2025-08-11 | SQ202506110081-Magicell/SQ202507140221-Magicell | DU00002039377 |  |  |  |  | 2025-10-09 |  | TOWER
9701B | Surau Darul Aman Miri | Sarawak |  | Modernization |  | 2023Q4 | SH | Trintel | 4.6 TSSR Approved |  | 2023-06-12 | 2023-07-03 |  | 2023-07-07 |  | Closed | 2023-07-11 | 2023-07-21 | E//Hannah | 2023-07-21 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230613-0009 | DU00002039378 |  |  | 2023-08-25 | 2023-08-10 |  | Monopole | 30M Rapole | 30m | Add R9264M M1821 x6+R8862A S2601 x2,Dismantle R8894E M1821(A8A) x4 |  | 23
B01731 | B061C_B01731OD_JLNKEMBUMIJATI | Central |  | Decomm |  | 2023Q3 | AI | YPTT | 4.6 TSSR Approved |  | 2023-08-08 |  |  |  | 2023-08-08 |  | 2023-08-09 | 2023-08-19 | CD//Ali Akaram | 2023-08-16 | CelcomDigi_RAN_YPTT_TSS_Central_20230727 | DU00002039379 |  |  |  |  | 2023-07-26 |  | MONOPOLE
B01794 | B065B_B01794OD_T3_SGDUSUN | Central |  | Decomm |  | 2023Q4 | CR | Magicell | 4.6 TSSR Approved |  | 2023-06-08 |  |  |  | 2023-06-12 |  | 2023-07-20 | 2023-10-17 | CD//Norhaliza | 2023-08-18 | CelcomDigi_RANMW_Magicell_TSS_Central_20230609_0004 / CelcomDigi_TX-RAN_Magicell_TSS_Central_20230818 | DU00002039380 |  |  |  |  | 2023-09-12 |  | TOWER
Q00581 | Q118B_Q00581OD_CB_TNSIMILAJAU | Sarawak |  | Decomm |  | 2023Q3 | SH | NR services | 4.6 TSSR Approved |  | 2023-08-11 |  |  |  | 2023-09-11 |  | 2023-09-12 | 2023-09-29 | CD//John | 2023-09-12 | Celcom Digi_RAN-NR Services-TSS-Sarawak-20230823 | DU00002039381 |  |  |  |  | 2023-11-27 |  | TOWER
A00225 | A042C_A00225OD_TAIPINGUTARA_RCC | Northern |  | Decomm |  | 2023Q4 | ZA | GCI | 4.6 TSSR Approved |  | 2023-05-25 |  |  |  | 2023-06-26 |  | 2023-06-27 | 2023-08-19 | CD//Shamsul | 2023-07-06 | Celcom Digi_RAN-GCI-TSS-Northern-20230529-0022/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240529-0109 | DU00002039382 |  | No TX Info, Photo not enough |  |  | 2023-08-29 |  | TOWER
P00285 | P031A_P00285OD_KGSERONOK | Northern |  | Decomm |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-05-04 |  |  |  | 2023-07-26 |  | 2023-06-21 | 2023-08-08 | CD//Shamsul | 2023-06-27 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1 | DU00002039383 |  | No TX Info, Photo not enough |  |  | 2023-07-28 |  | LAMP_POLE
B00512 | B061A_B00512OD_UITMSA | Central | 1087K | Swap |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-14 | 2023-06-26 |  | 2023-07-03 |  | Closed | 2023-07-03 | 2023-07-13 | CD//Sapian | 2023-07-12 | CelcomDigi_RAN_GTSB_TSS_Central_20230616_0029 | DU00002039384 |  |  | 2023-10-06 | 2023-09-27 |  | Pole | BOOM | 6 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
B00302 | B060C_B00302OD_KGMAHANG | Central |  | Decomm |  | 2023Q3 | SS | GTSB | 4.6 TSSR Approved |  | 2023-04-27 | 2023-06-26 |  |  | 2023-06-16 |  | 2023-06-21 | 2024-06-19 | CD//Norhaliza | 2023-09-13 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002039385 |  |  |  |  | 2023-08-24 | Tower | TOWER | 60
P00021 | P035B_P00021OD_SEA_RANGE | Northern |  | Decomm |  | 2023Q3 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-05-19 |  |  |  | 2023-06-16 |  | 2023-06-19 | 2023-08-08 | CD//Affendi | 2023-06-27 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002039386 |  |  |  |  | 2023-09-13 |  | BOOM
Q00670 | Q124F_Q00670OD_CIDB | Sarawak |  | Decomm |  | 2023Q4 | SH | South Pacific | 4.6 TSSR Approved |  | 2023-08-14 |  |  |  | 2023-08-18 |  | 2023-08-21 | 2023-09-29 | CD//John | 2023-08-21 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230913 | DU00002039387 |  | 23/8: Uncomploted info & photos |  |  | 2023-10-09 |  | TOWER
B01572 | B065B_B01572OD_T3_HTINGGITENGI | Central | 1130K | Swap |  | 2023Q4 | HQ 6 | Magicell | 4.6 TSSR Approved |  | 2023-06-21 | 2023-06-22 |  | 2023-06-26 |  | Closed | 2023-06-27 | 2023-07-06 | CD//Sapian | 2023-07-05 | CelcomDigi_RAN_Magicell_TSS_Central_20230622_0015 | DU00002039388 |  |  | 2023-09-10 | 2023-08-30 |  | Tower | TOWER | 62 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
A00472 | A042C_A00472OD_KAMUNTINGRAYA | Northern |  | Decomm |  | 2023Q4 | MH | GCI | 4.6 TSSR Approved |  | 2023-05-28 |  |  |  | 2023-06-23 |  | 2023-06-26 | 2023-08-24 | CD//Rohizam | 2023-08-02 | Celcom Digi_RAN-GCI-TSS-Northern-20230529-0022/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002039389 |  | 10/8:Please Include Celcom TX Cabinet |  |  | 2023-09-12 |  | BOOM
A00701 | A042B_A00701OD_KAMUNTINGBRANCH | Northern |  | Decomm |  | 2023Q4 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-06-14 |  |  |  | 2023-08-25 |  | 2023-08-11 | 2024-02-29 | CD//Quah | 2023-08-22 | Celcom Digi_RAN-GTSB-TSS-Northern-20230529-0020 | DU00002039390 |  | 18/8 No TSSR in EPMS |  |  | 2023-10-03 |  | BOOM
P00101 | P035D_P00101OD_WELDQUAY | Northern |  | Decomm |  | 2023Q3 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-05-03 |  |  |  | 2023-06-16 |  | 2023-06-19 | 2023-07-21 | CD//Affendi | 2023-06-27 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2 | DU00002039391 |  |  |  |  | 2023-09-14 |  | BOOM
B01947 | B065B_B01947OD_BKTSENTOSA | Central |  | Decomm |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-17 |  |  |  | 2023-07-26 |  | 2023-06-22 | 2023-10-17 | CD//Sapian | 2023-07-12 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002039392 |  |  |  |  | 2023-07-21 | Wall mount boom | BOOM | 6m
Q00282 | Q118A_Q00282OD_CHINESECHAMBER | Sarawak |  | Decomm |  | 2023Q3 | ZB | AllStar | 4.6 TSSR Approved |  | 2023-08-10 |  |  |  | 2023-09-22 |  | 2023-08-10 | 2023-09-23 | CD//John | 2023-08-11 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230622/0612Sarawak-AllStar-BOQ Template (template).xls | DU00002039393 |  |  |  |  | 2023-11-13 |  | UNIPOLE
K00034 | K004A_K00034OD_SHAHABPERDANA2 | Northern |  | Decomm |  | 2023Q4 | MH | CCSMY | 4.6 TSSR Approved |  | 2023-05-29 |  |  |  | 2023-06-13 |  | 2023-06-14 | 2023-08-30 | CD//Shamsul | 2023-06-27 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230530-0021 | DU00002039394 |  | need include equipment inside cabinet celcom |  |  | 2023-09-30 |  | MINI STRUCTURE
B02798 | B065B_B02798OD_KYUEMLMBHBERINGIN | Central | 1174K | Swap |  | 2023Q4 | HQ 6 | Ascentrack | 4.6 TSSR Approved |  | 2023-07-12 | 2023-07-21 |  | 2023-07-25 |  | Closed | 2023-07-26 | 2023-08-04 | CD//Sapian | 2023-08-04 | Celcomdigi_RAN_Ascentrack_TSS_Central_20230707_0027 | DU00002039395 |  |  | 2023-11-20 | 2023-09-22 |  | Watertank | RAMO | 30m | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
B02179 | B065B_B02179OD_APARTMENTTERATAI | Central | 1212K | Swap | Decomm->Swap | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-10-03 | 2023-10-03 |  | 2023-10-05 | 2023-05-26 | Closed | 2024-02-20 | 2024-02-20 | CD//Sapian | 2024-02-19 | 0626Central-Datasco-BOQ Template (template) | DU00002039396 |  |  | 2023-11-27 | 2023-11-26 |  | Monopole | LAMP_POLE | 24 | Add R8852E S9000 x3+R8862A S2601 x3+A9732 M1821 x3,Dismantle | 123
C00019 | C046C_C00019IB_FIRSTWORLD | Central |  | Decomm |  | 2023Q4 | IE | GTSB | 4.6 TSSR Approved |  | 2023-06-16 |  |  |  | 2024-06-28 |  | 2023-08-23 | 2023-12-19 | CD//Sofiah | 2023-08-29 | CelcomDigi_RAN_GTSB_TSS_Central_20230620_0030 | DU00002039397 | [6 empty] | IN-BUILDING
B00547 | B060B_B00547OD_KGPASIRTUTONG | Central | 1088K | Swap |  | 2023Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2023-07-04 | 2023-07-07 |  | 2023-07-11 |  | Closed | 2023-07-11 | 2023-07-21 | CD//Norhaliza | 2023-07-20 | CelcomDigi_RAN_Allstar_TSS_Central_20230703_0017 | DU00002039398 |  |  | 2023-08-23 | 2023-08-21 |  | Tower | TOWER | 60 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 1
B02541 | B061B_B02541OD_ELAEISCONDOBKTJELUTONG | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-31 |  |  |  | 2023-05-31 |  | 2023-06-06 | 2023-11-16 | CD//Sapian | 2023-06-08 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002039399 |  |  |  |  | 2023-09-21 |  | UNIPOLE
C00538 | C046C_C00538OD_KM4GENTING | Central | 1190K | Swap |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-10-16 | 2023-10-17 |  | 2023-10-21 |  | Closed | 2023-10-24 | 2023-11-08 | CD//Ali akaram | 2023-11-07 | CelcomDigi_RAN_GTSB_TSS_Central_20231017 | DU00002039400 |  |  | 2024-12-12 | 2024-12-09 |  | Monopole | LAMP_POLE | 25 | Add R8852E S9000 x3 + R8894E M1821 x3
Q00099 | Q124F_Q00099OD_CB_KGBUNTAL | Sarawak |  | Decomm |  | 2023Q4 | SH | AllStar | 4.6 TSSR Approved |  | 2023-08-01 |  |  |  | 2023-08-08 |  | 2023-08-09 | 2023-09-16 | CD//John | 2023-08-11 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230608-0006 | DU00002039401 |  | 22/8: uncompleted info & photos |  |  | 2024-02-19 |  | TOWER
B01513 | B060B_B01513OD_LDGPDGGAJAH | Central |  | Decomm |  | 2023Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-29 |  |  |  | 2023-08-25 |  | 2023-08-28 | 2023-10-17 | CD//Sapian | 2023-08-30 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002039402 |  |  |  |  | 2023-08-29 |  | MONOPOLE
B02856 | B061C_B02856IB_QUAYSIDEMALL | Central |  | Decomm |  | 2023Q3 | SS | Solusi | 4.6 TSSR Approved |  | 2023-07-26 |  |  |  | 2023-07-31 |  | 2023-07-31 | 2023-09-11 | CD//Sofiah | 2023-09-06 | CelcomDigi_RAN_Solusi_TSS_Central_20230626_decom reraise / CelcomDigi_TX_Solusi_TSS_Decom_Central_20230714 | DU00002039403 |  |  |  |  | 2023-10-16 |  | IN-BUILDING
B01360 | B061F_B01360OD_FAKULTIFARMASI | Central | 1122K | Swap |  | 2023Q3 | HQ 6 | GTSB | 4.6 TSSR Approved |  | 2023-06-21 | 2023-07-04 |  | 2023-07-11 |  | Closed | 2023-07-14 | 2023-08-28 | CD//Ali Akaram | 2023-08-26 | CelcomDigi_RAN_GTSB_TSS_Central_20230622_0031 | DU00002039404 |  |  | 2024-05-04 | 2024-04-26 |  | In-Building System | MONOPOLE | 3 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 2
9677B | Jalan Bangau | Sarawak |  | Modernization |  | 2023Q4 | BY | Datasco | 4.6 TSSR Approved |  | 2023-06-19 | 2023-07-06 |  | 2023-07-08 |  | Closed | 2023-07-10 | 2023-07-20 | E//Zulakmar | 2023-07-20 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 - Copy | DU00002039405 |  |  | 2023-08-19 | 2023-08-18 |  |  | 30m Lampole | 31 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3
B01122 | B065B_B01122OD_KM415BKTTAREK | Central |  | Decomm |  | 2023Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-10-17 |  |  |  | 2023-12-12 |  | 2023-12-22 | 2025-03-24 | CD//Sapian | 2024-01-02 | CelcomDigi_RANMW_Ascentrack_Central_20230706_0010 | DU00002039406 |  |  |  |  | 2023-10-17 |  | MONOPOLE
B00540 | B058B_B00540OD_KLGSELATAN | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-11 |  |  | 2023-05-22 | 2023-05-22 | Under Approval | 2023-06-12 | 2023-08-09 | CD//Sapian | 2023-06-13 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002039407 |  |  |  |  | 2023-07-24 |  | BOOM
Q00470 | Q132A_Q00470OD_CB_SUAIBTUTRUNK | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039408 | [6 empty] | TOWER
P00336 | P031A_P00336OD_TELUKKUMBAR | Northern | 4136K | Swap |  | 2023Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-05-17 | 2023-05-19 |  | 2023-05-25 |  | Closed | 2023-05-30 | 2023-06-10 | CD//Affendi | 2023-06-09 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0015 | DU00002039409 |  |  | 2023-07-19 | 2023-07-13 |  | Unipole | BOOM | 10 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x5,Dismantle Celcom all RRU&BBU |  | 23
P00341 | P035B_P00341IB_TESCO_TANJUNG_PINANG | Northern | 4137K | Swap |  | 2023Q3 | WP | YPTT | 4.6 TSSR Approved |  | 2023-05-14 | 2023-05-19 |  | 2023-05-31 |  | Closed | 2023-07-13 | 2023-08-01 | CD//Shamsul | 2023-07-18 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0008 | DU00002039410 |  |  | 2023-08-22 | 2023-08-22 |  | Wall mount boom | IN-BUILDING |  | Add + R8862A S2100 x2 + R8862A S1800 x2+R8862A S2601 x2,Dismantle all celcom BBU&RRU
B00300 | B060B_B00300OD_VLASSAMJAWA | Central |  | Decomm |  | 2023Q4 | CR | AllStar | 4.6 TSSR Approved |  | 2023-07-21 |  |  |  | 2023-07-21 |  | 2023-07-26 | 2023-10-17 | CD//Sapian | 2023-08-14 | CelcomDigi_RAN_AllStar_TSS_Central_20230722 | DU00002039411 |  |  |  |  | 2023-08-28 |  | TOWER
Q00444 | QE10126_BLUECUBE_BINTULU | Sarawak | 9072K | Swap |  | 2023Q3 | SH | Datasco | 4.6 TSSR Approved |  | 2023-05-16 | 2023-05-25 |  | 2023-06-13 |  | Closed | 2023-06-14 | 2023-06-14 | CD//John | 2023-06-14 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230516-0006 | DU00002039412 |  |  | 2023-08-11 | 2023-07-24 |  | Wall mount boom | SMALL CELL |  | Add BS8932 x1,Dismantle Celcom all RRU&BBU
C00092 | C046C_C00092OD_CB_LENTANG | Central |  | Decomm |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-07-27 |  |  |  | 2023-07-28 |  | 2023-08-02 | 2023-12-05 | CD//Norhaliza | 2023-08-18 | CelcomDigi_RAN_Magicell_TSS_Central_20230729 | DU00002039413 |  | Pending FE |  |  | 2023-10-03 |  | TOWER
P00049 | P035E_P00049OD_KLBGLUGOR | Northern |  | Decomm |  | 2023Q3 | ZA | YPTT | 4.6 TSSR Approved |  | 2023-07-08 |  |  |  | 2023-07-17 |  | 2023-07-20 | 2024-02-15 | CD//Affendi | 2023-09-25 | Celcom Digi_RAN-YPTT-TSS-Northern-20230609-0018 | DU00002039414 |  | 22/8: need antenna and ODU unused link 15/9: need antenna and ODU unused link |  |  | 2023-08-22 |  | BOOM
Q00571 | Q132B_Q00571OD_DESAPUJUT | Sarawak |  | Decomm |  | 2023Q4 | SH | Trintel | 4.6 TSSR Approved |  | 2023-06-21 |  |  |  | 2023-08-16 |  | 2023-08-16 | 2023-09-16 | CD//John | 2023-08-17 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230622 | DU00002039415 |  | 28/8: uncompleted info |  |  | 2025-03-27 |  | MONOPOLE
P00208 | P031B_P00208OD_TMBATUMAUNG | Northern | 4129K | Swap |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-06-20 | 2023-06-26 |  | 2023-06-27 |  | Closed | 2023-06-28 | 2023-07-03 | CD//Affendi | 2025-04-23 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0015 | DU00002039416 | Remarks: Solution TSSR/BOM Changed |  | 2025-03-16 | 2025-03-03 |  | Tower | GUYED MAST | 26 | Add R9264H M901821x3+R8862A S2601x3,Dismantle | 0 | 0
P00280 | P035C_P00280IB_GHOTEL | Northern |  | Decomm | Decomm->On Hold->Decomm | 2023Q3 | ZA | YPTT | 4.6 TSSR Approved |  | 2023-06-17 |  |  |  | 2023-07-03 |  | 2023-07-05 |  | CD//Quah | 2023-07-13 | Celcom Digi_RAN-YPTT-TSS-Northern-20230609-0018 | DU00002039417 |  | No TX Info, Photo not enough 29/3: Mention clearly location at drawing for xD and xC |  |  | 2024-11-06 |  | IN-BUILDING
B00639 | B058A_B00639OD_JLNBKTKAPAR | Central |  | Decomm |  | 2023Q3 | MA | Magicell | 4.6 TSSR Approved |  | 2023-06-19 |  |  |  | 2023-07-04 |  | 2023-07-12 | 2023-10-17 | CD//Norhaliza | 2023-07-27 | CelcomDigi_RAN_Magicell_TSS_Central_20230620_0014 | DU00002039418 |  |  |  |  | 2023-08-30 |  | TOWER
B00077 | B060B_B00077OD_BKCERAKAHJERAM | Central |  | Decomm |  | 2023Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-27 | 2023-06-26 |  |  | 2023-10-10 |  | 2023-06-20 | 2023-12-19 | CD//Sapian | 2023-10-24 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002039419 |  |  |  |  | 2023-09-23 | Tower | TOWER | 60
B00537 | B061C_B00537OD_SRIMUDA | Central |  | Decomm |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-08-07 |  |  |  | 2023-09-11 |  | 2023-09-13 | 2023-10-17 | CD//Ali Akaram | 2023-09-21 | CelcomDigi_RAN_YPTT_TSS_Central_20230815 | DU00002039420 |  |  |  |  | 2023-09-15 |  | TRIPOD
B00527 | B065B_B00527OD_ANTARAGAPI | Central |  | Decomm |  | 2023Q4 | SS | Futong | 4.6 TSSR Approved |  | 2023-06-30 |  |  |  | 2023-08-08 |  | 2023-07-28 | 2023-10-17 | CD//Ali Akaram | 2023-08-26 | CelcomDigi_RAN_Futong_TSS_Central_20230703_0007 | DU00002039421 |  | RESUBMISSION |  |  | 2023-09-22 |  | 4LEGGED
P00564 | P035C_P00564IB_1STAVENUEMALL | Northern |  | Decomm |  | 2023Q3 | SM | YPTT | 4.6 TSSR Approved |  | 2023-06-17 |  |  |  | 2023-08-03 |  | 2023-08-04 |  | CD//Quah | 2023-09-14 | Celcom Digi_RAN-YPTT-TSS-Northern-20230609-0018 | DU00002039422 |  | Please fill NE info, please state which one Cabinet xC & xD, Please fill dismantle item for TX, Please fill FE info. 23/11: FE not complete. Wrong Photo FE IDU 7/2: Photo not tally for NE,IDU was NEC but Antenna and ODU SM. FE photo not complete |  |  | 2023-10-19 |  | IN-BUILDING
K00379 | K004A_K00379OD_LTAS | Northern |  | Decomm |  | 2023Q4 | ZA | GCI | 4.6 TSSR Approved |  | 2023-06-14 |  |  |  | 2023-06-23 |  | 2023-06-26 | 2023-08-24 | CD//Rohizam | 2023-08-02 | Celcom Digi_RAN-GCI-TSS-Northern-20230615-0029/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002039423 |  |  |  |  | 2023-10-17 |  | LAMP_POLE
P00176 | P035D_P00176OD_BPOLISDKRMT | Northern |  | Decomm |  | 2023Q3 | SM | YPTT | 4.6 TSSR Approved |  | 2023-05-07 |  |  |  | 2023-05-22 |  | 2023-05-31 | 2023-08-19 | CD//Quah | 2023-07-18 | Celcom Digi_RAN-YPTT-TSS-Northern-20230609-0018 | DU00002039424 |  |  |  |  | 2023-09-14 |  | BOOM
B01574 | B061D_B01574OD_PR_JLNKMDTSEK23SA | Central |  | Decomm |  | 2023Q4 | MA | Solusi | 4.6 TSSR Approved |  | 2024-02-22 |  |  |  | 2024-05-14 |  | 2024-05-16 | 2024-09-26 | CD//Norhaliza | 2024-08-23 | CelcomDigi_RAN_Solusi_TSS_Central_20240513 | DU00002039425 |  |  |  |  | 2024-03-25 |  | BOOM
B00076 | B065B_B00076OD_SPGKKUBUBARU | Central |  | Decomm |  | 2023Q4 | SS | Futong | 4.6 TSSR Approved |  | 2023-07-20 |  |  |  | 2023-08-08 |  | 2023-08-10 | 2024-01-22 | CD//Norhaliza | 2023-08-18 | CelcomDigi_RAN_Futong_TSS_Central_20230721 | DU00002039426 |  |  |  |  | 2023-09-22 |  | 3LEGGED
K00126 | K004B_K00126OD_KUALAKEDAH | Northern |  | Decomm |  | 2023Q4 | MH | GCI | 4.6 TSSR Approved |  | 2023-05-31 |  |  |  | 2023-06-23 |  | 2023-06-23 | 2023-08-19 | CD//Affendi | 2023-06-28 | Celcom Digi_RAN-GCI-TSS-Northern-20230601-0023/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002039427 |  |  |  |  | 2023-10-03 |  | TOWER
B00023 | B057A_B00023OD_BKTIDAMAN | Central |  | Decomm |  | 2023Q4 | SS | YPTT | 4.6 TSSR Approved |  | 2023-09-08 |  |  |  | 2023-09-13 |  | 2023-09-15 | 2023-10-17 | CD//Sapian | 2023-09-23 | CelcomDigi_RAN_YPTT_TSS_Central_20231005 | DU00002039428 |  |  |  |  | 2023-09-26 |  | TRIPOD
C00543 | C046C_C00543OD_TMNCENDAWAN | Central |  | Decomm |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-05-31 |  |  |  | 2023-10-06 |  | 2023-10-07 | 2023-12-19 | CD//Norhaliza | 2023-11-17 | CelcomDigi_RAN_GTSB_TSS_Central_20230601_0026 | DU00002039429 |  |  |  |  | 2025-06-24 |  | AESTHETIC MONOPOLE
9830B | Miri Port (REL) | Sarawak |  | Modernization |  | 2023Q4 | SH | Datasco | 4.6 TSSR Approved |  | 2023-08-02 | 2023-08-03 |  | 2023-08-10 |  | Closed | 2023-08-10 | 2023-09-01 | E//Hannah | 2023-09-01 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230608-0007 | DU00002039430 |  |  | 2023-08-24 | 2023-08-21 |  | Tower | TOWER | 45 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
B00399 | B061A_B00399OD_BT5KLGMERU | Central |  | Decomm |  | 2023Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2023-06-26 |  |  |  | 2023-07-11 |  | 2023-07-27 | 2023-12-05 | CD//Sapian | 2023-08-01 | CelcomDigi_RAN_Magicell_TSS_Central_20230714 | DU00002039431 |  |  |  |  | 2023-08-24 |  | TOWER
B01059 | B057C_B01059OD_PGGRNBTCAVES | Central |  | Decomm |  | 2023Q4 | MA | AllStar | 4.6 TSSR Approved |  | 2023-07-11 |  |  |  | 2023-07-12 |  | 2023-07-14 | 2023-08-18 | CD//Norhaliza | 2023-08-03 | CelcomDigi_RAN_Allstar_TSS_Central_20230707_0018 | DU00002039432 |  |  |  |  | 2023-09-21 | Lampole | LAMP_POLE | 30
Q00638 | Q132C_Q00638OD_HOSPMYY | Sarawak | 9077K | Swap |  | 2023Q4 | ZB | Trintel | 4.6 TSSR Approved |  | 2023-06-28 | 2023-07-07 |  | 2023-07-10 |  | Closed | 2023-07-18 | 2023-07-19 | CD//John | 2025-01-13 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230622 | DU00002039433 |  |  | 2025-07-06 | 2025-04-15 |  | Tower | TOWER | 60m | Add R8862A S9000x3+R8894E M1821x3+R8862A S2601x3,Dismantle | 0 | 0
A00206 | A036B_A00206OD_PROTONCT | Central |  | Decomm |  | 2023Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-06-16 |  |  |  | 2023-10-05 |  | 2023-10-06 | 2024-08-22 | CD//Sapian | 2023-10-11 | Celcomdigi_RAN_Ascentrack_TSS_Central_20230616_0022 | DU00002039434 |  |  |  |  | 2023-10-19 |  | MONOPOLE
B00287 | B062A_B00287OD_KGBANTINGBNO | Central |  | Decomm |  | 2023Q4 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-08-01 |  |  |  | 2023-08-01 |  | 2023-08-01 | 2023-08-19 | CD//Ali Akaram | 2023-08-11 | CelcomDigi_RAN_CCSMY_TSS_Central_20230815 | DU00002039435 |  |  |  |  | 2024-01-08 |  | TOWER
C00900 | C046C_C00900OD_ELEKTRISOLA | Central | 1193K | Swap |  | 2023Q4 | HQ 6 | Magicell | 4.6 TSSR Approved |  | 2023-07-21 | 2023-07-24 |  | 2023-07-27 |  | Closed | 2023-07-31 | 2023-08-15 | CD//Sapian | 2023-08-15 | CelcomDigi_RAN_Magicell_TSS_Central_20230722 | DU00002039436 |  |  | 2024-01-02 | 2023-12-18 |  | Lampole | LAMP_POLE | 31 | Add R8852E S9000 x3 + R8894E M1821 x3
B01964 | B061B_B01964OD_KM9NKVE | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-07-05 |  |  |  | 2023-07-05 |  | 2023-07-12 |  | CD//Norhaliza | 2023-08-15 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002039437 |  | Subcon need to resurvey due to SOW changed to DISMANTLE DIGI MICRWAVE LINK 3838B-1362A RELOCATE CELCOM TM LL B01964 |  |  | 2023-11-30 |  | UNIPOLE
B01855 | B060C_B01855OD_LATAR1 | Central |  | Decomm |  | 2023Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-05-18 |  |  |  | 2023-05-29 |  | 2023-06-12 | 2023-10-02 | CD//Sapian | 2023-06-13 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002039438 |  | CT07804, Different IDU ID with solution |  |  | 2023-07-21 |  | TOWER
P00216 | P035D_P00216OD_JLNPERAK | Northern |  | Decomm |  | 2023Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-05-19 |  |  |  | 2023-08-07 |  | 2023-07-26 | 2023-08-28 | CD//Quah | 2023-08-03 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1/Celcom Digi_RAN-CCSMY-TSS Decomm-Northern-20240131-0091 | DU00002039439 |  | 18/8:Please include Celcom Cabinet and Zoom in photo TX |  |  | 2023-08-17 |  | BOOM
B00284 | B061F_B00284OD_PENJARASGBULOH | Central | 1809K | Swap | Decomm->Swap | 2023Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-08-23 | 2023-09-15 |  | 2023-09-19 | 2023-08-03 | Closed | 2023-09-19 | 2024-02-20 | CD//Norhaliza | 2024-02-20 | 0626Central-GTSB-BOQ Template (template) | DU00002039440 |  |  | 2023-12-05 | 2023-12-05 |  | Tower | TOWER | 75 | Add R8852E S9000 x2+R9264H M901821 x1+R8862A S2601 x3+A9732 M1821 x2,Dismantle | 23
Q00580 | Q118B_Q00580OD_RHMINGGU | Sarawak |  | Decomm |  | 2023Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2023-08-12 |  |  |  | 2023-08-18 |  | 2023-08-18 | 2023-10-04 | CD//John | 2023-08-18 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230531-0008/Celcom Digi_RAN-Trintel-TSS DECOMM-Sarawak-20231130 | DU00002039441 |  | 21/8: UNCOMPLETED INFO |  |  | 2023-12-11 |  | TOWER
B01949 | B058E_B01949OD_SURAUSAUJANAPUTRA | Central |  | Decomm |  | 2023Q3 | CR | Solusi | 4.6 TSSR Approved |  | 2023-07-26 |  |  |  | 2023-07-28 |  | 2023-07-28 | 2024-01-30 | CD//Sapian | 2023-08-15 | CelcomDigi_RAN_Solusi_TSS_Central_20230626_decom reraise | DU00002039442 |  |  |  |  | 2023-08-28 | Lampole | LAMP_POLE | 24
B02755 | B061D_B02755OD_BELAIANBAYUJLNPETOLASEK24SA | Central |  | Decomm |  | 2023Q4 | CR | GTSB | 4.6 TSSR Approved |  | 2023-05-29 |  |  |  | 2024-02-22 |  | 2023-07-28 | 2024-05-10 | CD//Sapian | 2023-08-04 | CelcomDigi_RAN_GTSB_TSS_Central_20230601_0026 | DU00002039443 |  |  |  |  | 2024-02-23 |  | BOOM WALL-MOUNTED
B00457 | B057C_B00457OD_UIA4 | Central | 1083K | Swap |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-07-31 | 2023-08-04 |  | 2023-08-08 |  | Closed | 2023-08-09 | 2023-08-17 | CD//Sapian | 2023-08-17 | CelcomDigi_RAN_Datasco_TSS_Central_20230802 | DU00002039444 |  |  | 2024-02-29 | 2023-10-18 |  | Monopole | LAMP_POLE | 21 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
A00125 | A036B_A00125OD_BEHRANGULU | Central |  | Decomm |  | 2023Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-06-08 |  |  |  | 2023-09-21 |  | 2023-09-22 | 2024-12-09 | CD//Ali Akaram | 2023-10-03 | CelcomDigi_RANMW_Ascentrack_TSS_Central_20230609_0004 | DU00002039445 |  |  |  |  | 2023-09-21 |  | TOWER
B00362 | B058B_B00362OD_TMKLGSELATAN | Central |  | Decomm |  | 2023Q3 | SM | Ascentrack | 4.6 TSSR Approved |  | 2024-01-05 |  |  |  | 2024-02-16 |  | 2024-02-19 | 2024-05-31 | CD//Ali Akaram | 2024-03-04 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240108 | DU00002039446 |  |  |  |  | 2024-01-07 |  | BOOM
B00565 | B065B_B00565OD_KERLINGTOWN | Central |  | Decomm |  | 2023Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-07-20 |  |  |  | 2023-11-15 |  | 2023-11-20 | 2025-03-24 | CD//Sapian | 2023-11-21 | Celcomdigi_RAN_Ascentrack_TSS_Central_20230707_0027 | DU00002039447 |  |  |  |  | 2023-10-24 |  | TOWER
P00335 | P031A_P00335OD_CB_KGBKTKECIL | Northern |  | Decomm |  | 2023Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-05-03 |  |  |  | 2023-06-02 |  | 2023-06-06 | 2024-02-15 | CD//Affendi | 2023-06-12 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2/Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230726-0024 | DU00002039448 |  | 22/8: need antenna and ODU unused link, drawing for location rack, and digi link to be decom |  |  | 2023-08-07 |  | TOWER
Q00606 | Q124B_Q00606OD_TMNSURIAJAYA | Sarawak |  | Decomm |  | 2023Q4 | SH | AllStar | 4.6 TSSR Approved |  | 2023-07-24 |  |  |  | 2023-08-08 |  | 2023-08-10 | 2023-09-08 | CD//John | 2023-08-10 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230622 | DU00002039449 |  | 22/8: UNCOMPLETED INFO & PHOTOS |  |  | 2024-07-31 |  | TOWER
Q00302 | Q132C_Q00302OD_PUJUT5 | Sarawak |  | Decomm |  | 2023Q4 | ZB | South Pacific | 4.6 TSSR Approved |  | 2023-06-23 |  |  |  | 2023-09-18 |  | 2023-09-18 | 2023-10-06 |  | 2023-09-19 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230622/0612Sarawak-South Pacific-BOQ Template (template) | DU00002039450 |  |  |  |  | 2025-01-17 |  | BOOM
A00800 | A042A_A00800OD_MN_KGCHEMPAKA | Northern | 4210P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039451 | [6 empty] | TOWER
K00660 | K004A_K00660IB_HOSPITALSULTANAH | Northern | 4101K | Swap |  | 2023Q4 | WP | GCI | 4.6 TSSR Approved |  | 2023-06-29 | 2023-07-03 |  | 2023-06-30 |  | Closed | 2023-07-19 | 2023-07-21 | CD//Shamsul | 2023-07-20 | Celcom Digi_RAN-GCI-TSS-Northern-20230626-0035 | DU00002039452 |  |  | 2024-02-10 | 2023-09-09 |  | Portables BTS | IN-BUILDING |  | Add R8852E S9000 x3 + R8862A S2100 x3 + R8862A S2601 x3,Dismantle all celcom BBU&RRU
B00116 | B057C_B00116OD_UIA5 | Central |  | Decomm |  | 2023Q4 | MA | Datasco | 4.6 TSSR Approved |  | 2023-08-14 |  |  |  | 2023-08-19 |  | 2023-08-19 | 2023-09-01 | CD//Sapian | 2023-08-23 | CelcomDigi_RAN_Datasco_TSS_Central_20230815 | DU00002039453 |  |  |  |  | 2023-12-07 |  | MONOPOLE
P00086 | P035A_P00086OD_PAYATERUBONG | Northern |  | Decomm |  | 2023Q3 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-05-19 |  |  |  | 2023-08-10 |  | 2023-08-03 | 2023-09-07 | CD//Affendi | 2023-08-07 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002039454 |  | 21/8: Wrong SOW, please refer SOW in EPMS |  |  | 2023-09-18 |  | BOOM
B00890 | B058B_B00890IB_JUSCOBKTRAJA | Central |  | Decomm |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-05-31 |  |  | 2023-06-08 | 2023-09-25 | Under Approval | 2023-06-21 | 2023-12-19 | CD//Sofiah | 2023-08-29 | CelcomDigi_RAN_Datasco_TSS_Central_20230601_0024 | DU00002039455 |  |  |  |  | 2023-09-30 |  | IN-BUILDING
P00276 | P035F_P00276OD_PANPALACE | Northern |  | Decomm |  | 2023Q3 | MH | GCI | 4.6 TSSR Approved |  | 2023-05-04 |  |  |  | 2023-07-26 |  | 2023-06-13 | 2024-03-26 | CD//Affendi | 2023-06-21 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002039456 |  | 15/9 - SOW change to dismantle digi microwave and relocate celcom fiber as requested by CD planner No TX Info 1) Wrong SOW 2) Why Celcom equipment Dismantle? 3) Please update drawing to show xD and xC location |  |  | 2023-08-03 |  | BOOM
K00889 | K004A_K00889OD_QUARTERS_PDRMERGA_JAYA | Northern | 4108K | Swap |  | 2023Q4 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-06-14 | 2023-06-16 |  | 2023-06-26 |  | Closed | 2023-07-03 | 2023-08-03 | CD//Rohizam | 2023-08-02 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002039457 |  |  | 2023-09-22 | 2023-09-18 |  | Lampole | LAMP_POLE | 30 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2,Dismantle Celcom all RRU&BBU | 3
B00459 | B065B_B00459OD_KBSKKUBUBARU | Central | 1084K | Swap |  | 2023Q4 | SS | Futong | 4.6 TSSR Approved |  | 2023-07-06 | 2023-06-28 |  | 2023-07-07 |  | Closed | 2023-07-10 | 2023-08-02 | CD//Sapian | 2023-08-02 | CelcomDigi_RANMW_Futong_Central_20230706_0006 | DU00002039458 |  |  | 2023-09-19 | 2023-09-15 |  | Pole | WATER TANK | 6/3 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 3
B00301 | B062B_B00301OD_VLJLNHJDORANI | Central |  | Decomm |  | 2023Q4 | CR | Magicell | 4.6 TSSR Approved |  | 2023-05-29 |  |  |  | 2023-08-28 |  | 2023-07-20 | 2023-10-17 | CD//Ali Akaram | 2023-08-26 | CelcomDigi_RAN_Magicell_TSS_Central_20230601_0011/Celcom Digi_RAN-Magicell-TSS Decomm-Central-20230722 | DU00002039459 |  |  |  |  | 2023-08-19 |  | TOWER
B00895 | B058B_B00895IB_KLGPARADE | Central |  | Decomm |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-08-08 |  |  |  | 2023-08-09 |  | 2023-08-10 | 2023-09-07 | CD//Sofiah | 2023-08-29 | CelcomDigi_RAN_Datasco_TSS_Central_20230808 | DU00002039460 |  |  |  |  | 2024-01-05 |  | BOOM
B00645 | B065B_B00645OD_ULUYAM | Central |  | Decomm |  | 2023Q4 | SS | Futong | 4.6 TSSR Approved |  | 2023-07-20 |  |  |  | 2024-05-06 |  | 2023-08-22 |  | CD//Sapian | 2023-08-23 | CelcomDigi_RAN_Futong_TSS_Central_20230721 | DU00002039461 |  | 1- Please provide clear photo for all existing TX equipment with clear labelling (CAN READ). including existing IDU. |  |  | 2023-10-13 |  | TOWER
P00343 | FRUITFARM | Northern |  | Decomm |  | 2023Q3 | BY | YPTT | 4.6 TSSR Approved |  | 2023-06-17 |  |  |  | 2023-08-16 |  | 2023-08-17 | 2023-10-09 | CD//Affendi | 2023-08-18 | Celcom Digi_RAN-YPTT-TSS-Northern-20230609-0018 | DU00002039462 |  |  |  |  | 2023-08-24 |  | TOWER
B00678 | B062A_B00678OD_SGPJG | Central |  | Decomm |  | 2023Q4 | CR | Magicell | 4.6 TSSR Approved |  | 2023-06-02 |  |  |  | 2023-06-12 |  | 2023-07-24 | 2023-11-22 | CD//Sapian | 2023-08-02 | CelcomDigi_RAN_Magicell_TSS_Central_20230606_0011 | DU00002039463 |  |  |  |  | 2023-09-30 |  | TOWER
Q00266 | Q118B_Q00266OD_PDRMBTU | Sarawak | 9062K | Swap |  | 2023Q3 | SH | Datasco | 4.6 TSSR Approved |  | 2023-05-17 | 2023-05-20 |  | 2023-05-24 |  | Closed | 2023-05-29 | 2023-05-30 | CD//John | 2023-05-30 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230516-0006 | DU00002039464 |  |  | 2024-11-28 | 2024-10-22 |  | Tower | TOWER | 30 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 1 | 0
9980A | Kampung Tanjung Kuching | Sarawak |  | Modernization |  | 2023Q4 | HQ 1 | Datasco | 4.6 TSSR Approved |  | 2023-07-13 | 2023-07-25 |  | 2023-07-27 |  | Closed | 2023-07-28 | 2023-07-31 | E//Hannah | 2023-07-31 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230726 | DU00002039465 |  |  | 2023-08-26 | 2023-08-23 |  | Tower | 30m Rapole | 30 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
B02014 | B061F_B02014OD_SERIPRISTANA | Central |  | Decomm |  | 2023Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-07 |  |  |  | 2023-09-22 |  | 2023-09-22 | 2023-10-17 | CD//Sapian | 2023-10-01 | CelcomDigi_RANMW_GTSB_TSS_Central_20230609_0002 | DU00002039466 |  | RESUBMISSION |  |  | 2023-10-02 | Lampole | LAMP_POLE
K00038 | K004A_K00038OD_TMJALANRAJA | Northern | 4084K | Swap |  | 2023Q4 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-06-27 | 2023-07-06 |  | 2023-07-11 |  | Closed | 2023-07-12 | 2023-08-18 | CD//Quah | 2023-08-17 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002039467 |  |  | 2023-10-05 | 2023-10-05 |  | Rooftop | BOOM | 20 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x5,Dismantle Celcom all RRU&BBU |  | 13
B00068 | B058B_B00068OD_TMNSRIRANTAU | Central |  | Decomm |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-05-11 |  |  |  | 2023-08-03 |  | 2023-06-21 | 2023-12-19 | CD//Norhaliza | 2023-09-13 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002039468 |  |  |  |  | 2023-07-28 |  | 3LEGGED
A00507 | A042A_A00507OD_FELDAIJOK | Northern |  | Decomm |  | 2023Q4 | ZA | YPTT | 4.6 TSSR Approved |  | 2023-06-09 |  |  |  | 2023-07-20 |  | 2023-07-21 | 2024-05-06 | CD//Rohizam | 2023-08-04 | Celcom Digi_RAN-YPTT-TSS-Northern-20230612-0019/Celcom Digi_RAN-YPTT-TSS Decomm-Northern-20240311-0048 | DU00002039469 |  | 250723: need resurvey for Capture unused |  |  | 2023-08-23 |  | TOWER
B01404 | B061F_B01404OD_PR_WTUITMPNCKALAM | Central |  | Decomm |  | 2023Q3 | CR | GTSB | 4.6 TSSR Approved |  | 2023-05-19 |  |  |  | 2024-02-01 |  | 2023-07-26 | 2023-11-16 | CD//Sapian | 2023-08-04 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002039470 |  |  |  |  | 2024-01-23 |  | AESTHETIC MONOPOLE
P00010 | P035B_P00010OD_JLNTGBUNGAH | Northern |  | Decomm |  | 2023Q3 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-05-02 |  |  |  | 2023-06-16 |  | 2023-06-19 | 2023-07-21 | CD//Shamsul | 2023-06-27 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2 | DU00002039471 |  |  |  |  | 2023-09-28 |  | BOOM
P00198 | P035E_P00198OD_BKTCOOMBE | Northern | 4128K | Swap |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-29 | 2023-06-06 |  | 2023-06-12 |  | Closed | 2023-06-15 | 2023-07-13 | CD//Affendi | 2023-06-27 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0015 | DU00002039472 |  |  | 2023-07-26 | 2023-07-18 |  | Lampole | LAMP_POLE | 27M | Add R9264H M901821 x4 + R8862A S2601 x4,Dismantle all celcom BBU&RRU
B00567 | B058B_B00567OD_TMNBERKELEY | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-06-01 |  |  |  | 2023-06-08 |  | 2023-06-15 | 2023-12-19 | CD//Sapian | 2023-07-03 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002039473 |  |  |  |  | 2023-08-15 |  | BOOM
B02295 | B061B_B02295OD_SURAUALIKHLASBKTJELUTONG | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-16 |  |  | 2023-05-31 | 2023-05-31 | Closed | 2023-07-20 | 2023-12-19 | CD//Sapian | 2023-07-25 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002039474 |  |  |  |  | 2023-09-18 |  | LAMP_POLE
9714B | Samariang Batu | Sarawak |  | Modernization |  | 2023Q4 | BY | Magicell | 4.6 TSSR Approved |  | 2023-06-22 | 2023-07-10 |  | 2023-07-13 |  | Closed | 2023-07-13 | 2023-07-21 | E//Hannah | 2023-07-21 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002039475 |  |  | 2023-08-08 | 2023-08-07 |  | Monopole | Land site | 30M | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
A00407 | A042A_A00407OD_TMNKAMUNTINGTIMUR | Northern |  | Decomm |  | 2023Q4 | MH | GCI | 4.6 TSSR Approved |  | 2023-05-31 |  |  |  | 2023-07-07 |  | 2023-06-22 | 2024-02-29 | CD//Shamsul | 2023-07-04 | Celcom Digi_RAN-GCI-TSS-Northern-20230601-0023 | DU00002039476 |  |  |  |  | 2023-09-19 |  | BOOM
B00129 | B061D_B00129OD_SEK24SHLM | Central |  | Decomm |  | 2023Q4 | SS | Datasco | 4.6 TSSR Approved |  | 2023-08-08 |  |  |  | 2023-09-21 |  | 2023-09-22 | 2023-10-20 | CD//Norhaliza | 2023-10-16 | CelcomDigi_RAN_Datasco_TSS_Central_20230808 | DU00002039477 |  |  |  |  | 2023-09-26 |  | TRIPOD
9944A | Jalan Padang Kerbau | Sarawak |  | Modernization |  | 2023Q4 | SHA | Datasco | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-26 |  | 2023-06-29 |  | Closed | 2023-07-03 | 2025-05-27 | E//Hannah | 2023-07-14 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230608-0007 | DU00002039478 |  |  | 2025-03-28 | 2025-03-21 |  | Monopole | 30m Rapole | 30m | Add R8894E M1821x4+R8854 S2600x1,Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3+R8862A S2600(A4A)x1 | 0 | 1
P00384 | P031B_P00384OD_DHLBTMAUNG | Northern |  | Decomm |  | 2023Q3 | SM | GCI | 4.6 TSSR Approved |  | 2023-06-16 |  |  |  | 2023-06-27 |  | 2023-07-07 | 2023-08-24 | CD//Shamsul | 2023-07-12 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002039479 |  | No TX Info, Photo not enough 10/8:Please Include Celcom TX Cabinet |  |  | 2023-08-21 | Lampole | MONOPOLE | 27m
Q00102 | Q128A_Q00102OD_KUBAH | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2023Q4 | AD | Magicell | 4.6 TSSR Approved |  | 2025-06-25 |  | 2025-07-02 |  | 2025-07-07 |  | 2025-08-07 | 2025-10-31 | E//John | 2025-08-11 | SQ202506110081-Magicell/SQ202507140221-Magicell | DU00002039480 |  |  |  |  | 2025-10-20 |  | TOWER
P00213 | P031A_P00213OD_TMTLKBAHANG | Northern |  | Decomm |  | 2023Q3 | MH | GCI | 4.6 TSSR Approved |  | 2023-05-17 |  |  |  | 2023-06-20 |  | 2023-06-22 | 2024-07-11 | CD//Quah | 2023-07-18 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1/GCI Northern TX TSS | DU00002039481 |  |  |  |  | 2023-08-30 |  | 4LEGGED
B00030 | B058B_B00030OD_RAJAMUDAMUSA2 | Central |  | Decomm |  | 2023Q3 | AI | Futong | 4.6 TSSR Approved |  | 2023-06-06 |  |  | 2023-06-07 | 2024-05-06 | Under Approval | 2023-07-20 | 2023-10-25 | CD//Norhaliza | 2023-09-13 | CelcomDigi_RAN_Futong_TSS_Central_20230626_decom reraise/CelcomDigi_TX_Futong_TSS_Decom_Central_20230922 | DU00002039482 |  |  |  |  | 2023-09-15 |  | BOOM
P00596 | ALFRESCOGURNEY | Northern | 4153K | Swap |  | 2023Q3 | SM | GCI | 4.6 TSSR Approved |  | 2023-05-13 | 2023-05-16 |  | 2023-08-04 |  | Rectificating | 2023-08-07 | 2023-10-02 | CD//Quah | 2023-09-29 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0014 | DU00002039483 |  |  | 2023-08-24 | 2023-08-21 |  | Wall mount boom | SMALL CELL |  | Add BS8932 x1,Dismantle Celcom small cell
B00714 | B065B_B00714OD_FELDASOEHARTO | Central |  | Decomm |  | 2023Q4 | CR | Magicell | 4.6 TSSR Approved |  | 2023-06-07 |  |  |  | 2024-05-02 |  | 2023-07-24 | 2024-12-10 | CD//Norhaliza | 2023-08-18 | CelcomDigi_RAN_Magicell_TSS_Central_20230607_0012 | DU00002039484 |  |  |  |  | 2023-10-17 |  | 4LEGGED
Q00032 | Q124B_Q00032OD_TMSERAPI | Sarawak | 9055K | Swap |  | 2023Q4 | SH | Datasco | 4.6 TSSR Approved |  | 2023-08-28 | 2023-09-14 |  | 2023-09-19 |  | Closed | 2023-09-19 | 2023-09-20 | CD//John | 2023-09-20 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230726 | DU00002039485 |  |  | 2023-10-18 | 2023-10-10 |  | Tower | TOWER | 22 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 2
C00260 | C046C_C00260OD_CB_SERDANGLAYBY | Central |  | Decomm |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-07-20 |  |  |  | 2023-07-26 |  | 2023-08-02 | 2023-10-17 | CD//Ali akaram | 2023-08-11 | CelcomDigi_RAN_Magicell_TSS_Central_20230721 | DU00002039486 |  |  |  |  | 2023-09-23 |  | TOWER
B01269 | B057C_B01269OD_KM32KARAKHWY | Central |  | Decomm |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-07-10 |  |  |  | 2023-08-02 |  | 2023-08-02 | 2023-08-19 | CD//Sapian | 2023-08-15 | CelcomDigi_RAN_Magicell_TSS_Central_20230721 | DU00002039487 |  | Please include link ID in TSSR |  |  | 2023-10-26 |  | TOWER
P00559 | P035A_P00559OD_BPOLISAIRITAM | Northern |  | Decomm |  | 2023Q3 | MH | GCI | 4.6 TSSR Approved |  | 2023-05-17 |  |  |  | 2023-06-26 |  | 2023-06-26 |  | CD//Affendi | 2023-07-03 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1/GCI Northern TX TSS | DU00002039488 |  | No TX Info, Photo not enough |  |  | 2023-11-28 |  | BOOM
B00037 | B057D_B00037OD_BATUCAVESBB | Central |  | Decomm |  | 2023Q4 | CR | GTSB | 4.6 TSSR Approved |  | 2023-06-07 |  |  |  | 2023-08-03 |  | 2023-07-27 | 2023-10-17 | CD//Sapian | 2023-08-03 | CelcomDigi_RANMW_GTSB_TSS_Central_20230609_0002 | DU00002039489 |  |  |  |  | 2023-08-24 |  | BILLBOARD
P00411 | P031B_P00411OD_PSSBAYANBARU | Northern | 4144K | Swap |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved | AAU Cannot Install-Change MM to normal sector,L2600 change to 40M¦Pylon site, Space constraint， | 2023-05-19 | 2023-05-31 |  | 2023-06-12 |  | Closed | 2023-06-22 | 2023-07-05 | CD//Affendi | 2023-06-28 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0015 | DU00002039490 | NIC_S3_Change MM to normal sector,L2600 change to 40M_Space constraint_STEALTH |  | 2023-07-25 | 2023-07-13 |  | Petronas Pylon | PYLON | 27m | Add R9264M M1821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 0 | 0
B01136 | B065B_B01136OD_RSAUULUSLGRHOT | Central |  | Decomm |  | 2023Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-01-11 |  |  |  | 2024-08-22 |  | 2023-10-09 | 2025-03-24 | CD//Norhaliza | 2023-10-31 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240625/Celcom Digi_RAN-Ascentrack-Standard PR TSS-Central-20241016 | DU00002039491 |  |  |  |  | 2023-09-25 |  | TOWER
9697A | Taman kemena Sutera | Sarawak |  | Modernization |  | 2023Q3 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-05-19 | 2023-06-08 |  | 2023-06-19 |  | Closed | 2023-06-23 | 2023-07-07 | E//Hannah | 2023-07-07 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230516-0006 | DU00002039492 |  |  | 2023-11-24 | 2023-11-18 |  | Monopole | 30m Rapole | 30M | Add R9264H M901821 x3,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3
Q00142 | Q124F_Q00142OD_CB_PASIRPANJANG | Sarawak |  | Decomm | On Hold->Decomm | 2023Q4 | SH | Datasco | 4.6 TSSR Approved |  | 2023-06-17 |  |  |  | 2023-07-01 |  | 2023-07-24 | 2023-09-19 | CD//John | 2023-07-25 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 | DU00002039493 |  | 8/9: uncompleted info & photos |  |  | 2025-06-19 |  | TOWER
Q00252 | Q118B_Q00252OD_KIDURONGIND | Sarawak |  | Decomm |  | 2023Q3 | ZB | CCSMY | 4.6 TSSR Approved |  | 2023-06-22 |  |  |  | 2023-06-26 |  | 2023-07-24 | 2024-07-19 | CD//John | 2023-07-28 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230614-0008 | DU00002039494 |  | 1/9: uncompleted info |  |  | 2024-03-05 |  | TOWER
P00202 | P035E_P00202OD_JELUTONG | Northern |  | Decomm |  | 2023Q3 | MH | GTSB | 4.6 TSSR Approved |  | 2023-05-23 |  |  |  | 2023-06-22 |  | 2023-06-23 | 2023-09-07 | CD//Rohizam | 2023-08-03 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230720-0023/Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2 | DU00002039495 |  |  |  |  | 2023-08-18 |  | BOOM
A01094 | A042A_A01094OD_KG_ANAK_KURAU | Northern | 4079K | Swap |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-06-05 | 2023-06-19 |  | 2023-06-23 |  | Closed | 2023-07-04 | 2023-07-13 | CD//Quah | 2023-07-13 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230606-0022 | DU00002039496 |  |  | 2023-08-10 | 2023-07-22 |  | Minaret | MINARET | 31m | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
B01343 | B060B_B01343OD_KGBKTKUCHNGHOT | Central |  | Decomm |  | 2023Q3 | SS | GTSB | 4.6 TSSR Approved |  | 2023-04-28 | 2023-06-26 |  |  | 2023-06-16 |  | 2023-06-21 | 2023-12-19 | CD//Ali Akaram | 2023-08-26 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002039497 |  | Please provide celcom cabinet photo |  |  | 2023-08-01 | Tower | TOWER | 60M
9849A | Park City Mall IB | Sarawak |  | Modernization |  | 2023Q3 | BY | Datasco | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-14 |  | 2023-06-14 |  | Closed | 2023-06-14 | 2023-07-04 | E//Hannah | 2023-06-16 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230516-0006 | DU00002039498 |  |  | 2023-07-19 | 2023-07-10 |  | Wall mount boom | In-building system | 44 | Add R8862A S1800 x1
A00123 | A042C_A00123OD_KAMUNTINGIND | Northern |  | Decomm |  | 2023Q4 | MH | GCI | 4.6 TSSR Approved |  | 2023-05-25 |  |  |  | 2023-06-23 |  | 2023-06-23 | 2023-08-19 | CD//Shamsul | 2023-07-04 | Celcom Digi_RAN-GCI-TSS-Northern-20230529-0022/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002039499 |  |  |  |  | 2023-08-28 |  | TOWER
B01970 | B057D_B01970OD_BTCAVESIND | Central |  | Decomm |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-05-08 |  |  |  | 2023-08-18 |  | 2023-08-19 | 2023-10-20 | CD//Sapian | 2023-08-23 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002039500 |  |  |  |  | 2023-08-28 |  | BOOM-BYPOD
B01937 | B061D_B01937IB_NIROCERAMICSHLM | Central | 1145K | Swap | Swap->Site Out->Swap | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-10 | 2023-11-30 |  | 2024-05-31 |  | Closed | 2025-07-07 | 2025-08-12 | CD//Sofiah | 2025-07-11 | CelcomDigi_RAN_GTSB_TSS_Central_20231201 | DU00002039501 | Remarks: Solution TSSR/BOM Changed |  | 2025-07-18 | 2025-07-18 |  | Portables BTS | IN-BUILDING |  | Add R8894E M1821x2+R8862A S2601x2, Dismantle
B01409 | B061F_B01409OD_KOLEJRAFFLESIA | Central |  | Decomm |  | 2023Q3 | CR | GTSB | 4.6 TSSR Approved |  | 2023-06-01 |  |  |  | 2023-06-17 |  | 2023-07-27 | 2023-10-17 | CD//Ali Akaram | 2023-08-26 | CelcomDigi_RAN_GTSB_TSS_Central_20230606_0027 | DU00002039502 |  | Please amend link id CT05468 to CT08558. Link id not change during installation. Tq |  |  | 2023-09-30 |  | LAMP_POLE
B00824 | B058B_B00824OD_SGRASAU | Central |  | Decomm |  | 2023Q4 | CR | GTSB | 4.6 TSSR Approved |  | 2023-05-26 |  |  |  | 2024-05-28 |  | 2023-07-28 | 2023-12-19 | CD//Ali Akaram | 2023-08-26 | CelcomDigi_RAN_GTSB_TSS_Central_20230529_0025 | DU00002039503 |  |  |  |  | 2023-10-23 |  | TRIPOD
B01348 | B062B_B01348OD_T3_PT7SGPJG | Central | 1120K | Swap |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-06-06 | 2023-06-20 |  | 2023-06-22 |  | Closed | 2023-07-15 | 2023-08-02 | CD//Ali akaram | 2023-08-02 | CelcomDigi_RAN_Magicell_TSS_Central_20230607_0012 | DU00002039504 |  |  | 2023-09-22 | 2023-09-11 |  | Tower | TOWER | 76 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 13
B02037 | B057B_B02037OD_MN_LMNBISTARI | Central | 1003P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039505 | [6 empty] | TOWER
B01528 | B057C_B01528OD_TMNBKTPERMATA_BTCAVES | Central | 1861K | Decomm |  | 2023Q4 | HW | AllStar | 4.6 TSSR Approved |  | 2024-01-11 |  |  | 2024-06-14 | 2024-02-27 | Under Approval | 2023-09-18 | 2025-03-20 | CD//Sapian | 2025-03-17 | CelcomDigi_RAN_AllStar_TSS_Central_20230802 | DU00002039506 |  |  |  |  | 2023-09-12 |  | TOWER
P00222 | P031A_P00222OD_SGRUSA | Northern |  | Decomm |  | 2023Q3 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-05-23 |  |  |  | 2023-07-27 |  | 2023-06-21 | 2023-07-21 | CD//Affendi | 2023-06-28 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2 | DU00002039507 |  |  |  |  | 2023-07-26 |  | TOWER
9934A | Taman Lopeng Jaya | Sarawak |  | Modernization |  | 2023Q4 | BY | Datasco | 4.6 TSSR Approved |  | 2023-06-08 | 2023-06-21 |  | 2023-06-26 |  | Closed | 2023-06-28 | 2023-07-07 | E//Hannah | 2023-07-06 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230614-0010 | DU00002039508 |  |  | 2023-08-22 | 2023-08-07 |  |  | Tower | 30 | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 2
P00197 | P035C_P00197IB_PRANGINMALL | Northern |  | Decomm |  | 2023Q3 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-06-13 |  |  |  | 2023-07-14 |  | 2023-07-14 | 2023-09-18 | CD//Quah | 2023-09-14 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2 | DU00002039509 |  |  |  |  | 2024-08-15 |  | IN-BUILDING
B00401 | B058C_B00401OD_TMNKLGJAYA | Central |  | Decomm |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-05-19 |  |  |  | 2023-07-08 |  | 2023-07-11 | 2023-08-04 | CD//Sapian | 2023-07-14 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230626_decom reraise | DU00002039510 |  | Approved 28/7 |  |  | 2023-07-21 |  | UNIPOLE
K00366 | K004A_K00366OD_ALORSETAROFFICE | Northern | 4095K | Swap |  | 2023Q4 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-06-06 | 2023-06-12 |  | 2023-06-15 |  | Closed | 2023-06-23 | 2023-08-03 | CD//Rohizam | 2023-08-02 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002039511 |  |  | 2023-09-19 | 2023-09-18 |  | Wall mount boom | BOOM | 6 | Add R8852E S9000 x3 + R8894E M1821 x3 + R8862A S2601 x3
P00189 | P035D_P00189OD_LBHMACCALUM | Northern |  | Decomm |  | 2023Q3 | MH | CCSMY | 4.6 TSSR Approved |  | 2023-05-17 |  |  |  | 2023-06-13 |  | 2023-06-14 | 2023-08-28 | CD//Affendi | 2023-06-26 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002039512 |  |  |  |  | 2023-10-06 |  | UNIPOLE
9854A | Park City Everly Hotel IB | Sarawak |  | Modernization |  | 2023Q3 | BY | AllStar | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-20 |  | 2023-06-06 |  | Closed | 2023-06-06 | 2023-06-11 | E//Nazrul | 2023-06-11 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230516-0005 | DU00002039513 |  |  | 2023-07-07 | 2023-07-04 |  | Wall mount boom | In-building system | N/A | Add + R8862A S1800 x2,Dismantle R8882-GUL1812 x2
B00377 | B058C_B00377OD_TMNMWHJAYA | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-16 |  |  | 2023-05-22 | 2023-05-22 | Under Approval | 2023-06-12 | 2023-12-19 | CD//Sapian | 2023-06-13 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002039514 |  |  |  |  | 2023-12-15 |  | BOOM
Q00299 | Q132B_Q00229OD_KUALABARAM | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2023Q4 | SH | Datasco | 4.6 TSSR Approved |  | 2023-08-22 |  |  |  | 2023-08-29 |  | 2023-08-29 | 2024-07-30 | CD//John | 2023-08-30 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 | DU00002039515 |  |  |  |  | 2025-06-23 |  | TOWER
B01695 | B062A_B01695OD_T3_PT2SEKINCHAN | Central | 1138K | Swap |  | 2023Q4 | CR | YPTT | 4.6 TSSR Approved |  | 2023-07-17 | 2023-07-24 |  | 2023-07-27 |  | Closed | 2023-08-08 | 2023-08-19 | CD//Norhaliza | 2023-08-18 | CelcomDigi_RAN_YPTT_TSS_Central_20230725 | DU00002039516 |  |  | 2023-09-19 | 2023-09-18 |  | Tower | TOWER | 60 | Add R8852E S9000 x3 + A9732 M1821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 123
P00575 | P031B_P00575IB_OSRAM_PENANG | Northern | 4151K | Swap |  | 2023Q3 | WP | GCI | 4.6 TSSR Approved |  | 2023-06-07 | 2023-06-09 |  | 2023-06-13 |  | Closed | 2023-07-07 | 2023-07-12 | CD//Shamsul | 2023-07-11 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0014 | DU00002039517 |  |  | 2023-08-18 | 2023-07-18 |  |  | IN-BUILDING |  | Add + R8862A S1800 x4 + R8862A S2100 x4 + R8862A S2601 x4,Dismantle all celcom BBU&RRU
K00592 | K004A_K00592OD_HUTANKANDIS | Northern |  | Decomm |  | 2023Q4 | ZA | GCI | 4.6 TSSR Approved |  | 2023-06-13 |  |  |  | 2023-06-23 |  | 2023-06-26 | 2023-08-19 | CD//Rohizam | 2023-08-02 | Celcom Digi_RAN-GCI-TSS-Northern-20230614-0028/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002039518 |  |  |  |  | 2023-10-13 |  | TOWER
B00075 | B060A_B00075OD_BT10TGKARANG | Central |  | Decomm |  | 2023Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2023-06-14 |  |  |  | 2023-06-15 |  | 2023-07-06 | 2023-12-19 | CD//Norhaliza | 2023-07-26 | CelcomDigi_RAN_Allstar_TSS_Central_20230616_0012 | DU00002039519 |  |  |  |  | 2023-09-01 |  | 3LEGGED
A00494 | A042A_A00494OD_BGNBARU | Northern |  | Decomm |  | 2023Q4 | SM | YPTT | 4.6 TSSR Approved |  | 2023-06-11 |  |  |  | 2023-06-26 |  | 2023-06-27 | 2024-02-22 | CD//Rohizam | 2023-08-02 | Celcom Digi_RAN-YPTT-TSS-Northern-20230613-0020 | DU00002039520 |  | 22/8: Photo IDU Label Blur, Please include Photo Antena, ODU, FE to be Decom 11/9: No Antenna TX photo, No FE Photo, Dismantle part for xC Dismantle 24/1: Please include Digi Cabinet for relocation |  |  | 2023-08-24 |  | TOWER
B02748 | B061A_B02748OD_WISMAMAISSEK3SHLM | Central |  | Decomm |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-08-04 |  |  |  | 2023-08-17 |  | 2024-08-13 | 2024-09-26 | CD//Ali Akaram | 2024-09-03 | CelcomDigi_RAN_Datasco_TSS_Central_20231213 | DU00002039521 |  |  |  |  | 2023-10-28 |  | BOOM WALL-MOUNTED
Q00539 | Q132B_Q00539OD_TUDANLOT | Sarawak | 9074K | Swap |  | 2023Q4 | HQ 1 | Datasco | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦nok, no space to add AAU | 2023-07-08 | 2023-07-20 |  | 2023-07-26 |  | Closed | 2023-07-27 | 2023-07-28 | CD//John | 2023-07-28 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 - Copy | DU00002039522 | NIC_S2_Change MM to BI_Space constraint_EDOTCO (M) - NONE CSU |  | 2025-01-27 | 2025-01-13 |  | Unipole | RAPID ASSEMBLY POLE (RAPOLE) | 18 | Add R8862A S9000x3+R8894E M1821x4+R8862A S2601x2+R8854 S2600x1,Dismantle | 0 | 1
B00945 | B065B_B00945OD_ULURENING | Central |  | Decomm |  | 2023Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-01-11 |  |  |  | 2024-01-22 |  | 2024-01-23 | 2024-02-15 | CD//Norhaliza | 2024-02-06 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240115 | DU00002039523 |  |  |  |  | 2023-09-22 |  | TOWER
B02745 | B061A_B02745OD_PSRNSETIADAMAISETIAALAM | Central |  | Decomm |  | 2023Q3 | IE | Magicell | 4.6 TSSR Approved |  | 2023-05-05 |  |  |  | 2023-07-31 |  | 2023-08-02 | 2023-08-18 | CD//Sapian | 2023-08-16 | CelcomDigi_RAN_Magicell_TSS_Central_20230626_decom reraise/CelcomDigi_RAN-TX_Magicell_TSS_Central_20230816_Decom | DU00002039524 |  |  |  |  | 2023-09-04 |  | MONOPOLE
K00032 | KMC_AS_4G | Northern | 4083K | Swap |  | 2023Q4 | WP | GCI | 4.6 TSSR Approved |  | 2023-06-27 | 2023-06-28 |  | 2023-06-27 |  | Closed | 2023-07-20 | 2023-07-26 | CD//Shamsul | 2023-07-26 | Celcom Digi_RAN-GCI-TSS-Northern-20230626-0035 | DU00002039525 |  |  | 2023-09-29 | 2023-09-27 |  | Portables BTS | IN-BUILDING |  | Add R8862A S2100 x3 + R8862A S1800 x3+R8862A S2601 x3,Dismantle all celcom BBU&RRU
B02805 | B061F_B02805OD_KGCHEMPEDAK_KUANG | Central | 1177K | Swap |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-13 |  | 2023-06-15 |  | Closed | 2023-06-20 | 2023-07-13 | CD//Sapian | 2023-07-12 | CelcomDigi_RAN_Magicell_TSS_Central_20230612_0012 | DU00002039526 |  |  | 2023-08-17 | 2023-08-16 |  | Lampole | LAMP_POLE | 30m | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle Celcom all RRU&BBU | 23(S1->S2,S2->S3,S3->S1,rename Sector ID,MM @newS1S3)
B00828 | B061A_B00828SL_PR_MBRESIDENTSL | Central | 1100K | Swap |  | 2023Q4 | CR | Datasco | 4.6 TSSR Approved |  | 2023-10-24 | 2023-10-30 |  | 2024-03-22 |  | Closed | 2024-03-26 | 2024-04-15 | CD//Sapian | 2024-04-08 | CelcomDigi_RAN_Datasco_TSS_Central_20231025 | DU00002039527 |  |  | 2025-05-06 | 2025-02-20 |  | Pole | BOOM | 9m | Add R9264M M1821 x1,Dismantle
B02626 | B061B_B02626OD_PSNSUKANSEK13SHLM | Central |  | Decomm |  | 2023Q4 | CR | Datasco | 4.6 TSSR Approved |  | 2023-08-08 |  |  |  | 2023-08-15 |  | 2023-08-16 | 2023-08-24 | CD//Sapian | 2023-08-18 | CelcomDigi_RAN_Datasco_TSS_Central_20230808 | DU00002039528 |  |  |  |  | 2023-08-29 |  | LAMP_POLE
A00183 | A036B_A00183OD_TANJUNGMALIM | Central |  | Decomm |  | 2023Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-07-20 |  |  |  | 2023-08-03 |  | 2023-08-08 | 2024-05-27 | CD//Ali Akaram | 2024-05-06 | Celcomdigi_RAN_Ascentrack_TSS_Central_20230707_0027 | DU00002039529 |  |  |  |  | 2024-03-15 |  | TOWER
B02276 | B061D_B02276OD_PSNRAJAMUDA | Central |  | Decomm |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-07-07 |  |  |  | 2023-08-13 |  | 2023-08-15 | 2023-08-24 | CD//Sapian | 2023-08-18 | Celcomdigi_RAN_Ascentrack_TSS_Central_20230707_0027 | DU00002039530 |  |  |  |  | 2023-08-30 | Lampole | LAMP_POLE | 30M
A00237 | TMSPG4TPG | Northern | 4178P | Swap |  | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-13 |  | 2023-06-15 |  | Closed | 2023-07-03 | 2023-07-13 | CD//Quah | 2023-07-13 | Celcom Digi_RAN-YPTT-TSS-Northern-20230612-0019 | DU00002039531 |  |  | 2023-08-08 | 2023-08-08 |  | Minimast | BOOM | 15 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 2
B01694 | B062B_B01694OD_T3_PT5SGPJG | Central |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  | CCSMY | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039532 | [6 empty] | TOWER
B02533 | B058B_B02533OD_PSNSGKERAMATKLG2 | Central |  | Decomm |  | 2023Q3 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-05-13 |  |  |  | 2023-07-04 |  | 2023-07-17 | 2023-09-19 | CD//Norhaliza | 2023-09-13 | CelcomDigi_RAN_CCSMY_TSS_Central_20230626_decom reraise | DU00002039533 |  |  |  |  | 2023-08-15 |  | BOOM
B01174 | B061B_B01174OD_PSNKAYANGAN | Central |  | Decomm |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-06-17 |  |  |  | 2023-06-26 |  | 2023-07-26 | 2023-11-16 | CD//Sapian | 2023-08-14 | CelcomDigi_RAN_Datasco_TSS_Central_20230620_0027 | DU00002039534 |  |  |  |  | 2023-08-30 |  | MONOPOLE
B02743 | B061D_B02743OD_JLNBAWANGSEK14SHAHALAM | Central | 1170K | Swap |  | 2023Q4 | IE | GTSB | 4.6 TSSR Approved |  | 2023-06-11 | 2023-06-16 |  | 2023-06-21 |  | Closed | 2023-06-23 | 2023-07-06 | CD//Sapian | 2023-07-05 | CelcomDigi_RANMW_GTSB_TSS_Central_20230612_0003 | DU00002039535 |  |  | 2023-09-19 | 2023-09-18 |  |  | BOOM | 6 | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle Celcom all RRU&BBU |  | 3
B00669 | B057C_B00669OD_TOLGOMBAK | Central | 1093K | Swap |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-07-31 | 2023-08-09 |  | 2023-08-11 |  | Closed | 2023-08-16 | 2023-09-14 | CD//Norhaliza | 2023-09-13 | CelcomDigi_RAN_Datasco_TSS_Central_20230802 | DU00002039536 |  |  | 2023-10-26 | 2023-10-18 |  | BillBoard | BILLBOARD | 24 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 3
B01336 | B060B_B01336OD_SGGULANGGULANG | Central |  | Decomm |  | 2023Q4 | CR | AllStar | 4.6 TSSR Approved |  | 2023-07-27 |  |  |  | 2023-07-31 |  | 2023-08-02 | 2023-10-17 | CD//Norhaliza | 2023-08-18 | CelcomDigi_RAN_AllStar_TSS_Central_20230731 | DU00002039537 |  | RESUBMISSION 1) Please provide clear photo for all existing TX equipment (zzom in photo) with clear labelling, including existing IDU |  |  | 2023-09-08 |  | TOWER
B01096 | B065B_B01096OD_KGSGMASIN | Central |  | Decomm |  | 2023Q4 | SS | Futong | 4.6 TSSR Approved |  | 2023-06-19 |  |  |  | 2023-07-24 |  | 2023-07-27 | 2024-02-23 | CD//Sapian | 2024-02-19 | CelcomDigi_RAN_Futong_TSS_Central_20230620_0002 | DU00002039538 |  | Please verify why use xD link since xC MW have bigger capacity and pointing to same LOS. Tq |  |  | 2023-12-27 |  | TOWER
A00063 | A042A_A00063OD_CB_REDANGPANJANG | Northern |  | Decomm |  | 2023Q4 | ZA | YPTT | 4.6 TSSR Approved |  | 2023-06-11 |  |  |  | 2023-06-24 |  | 2023-06-26 | 2024-02-15 | CD//Rohizam | 2023-08-02 | Celcom Digi_RAN-YPTT-TSS-Northern-20230613-0020 | DU00002039539 |  | 22/8: Please Include 2nd IDU Photo Zoom in, Please put clear Photo with clear label for 1st and 2nd IDU 11/9: Wrong SOW, Suppose remain digi and Relocate Celcom |  |  | 2023-08-28 |  | TOWER
B02590 | B058B_B02590OD_AMANPDANAKLG2 | Central |  | Decomm |  | 2023Q3 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-06-08 |  |  |  | 2023-06-16 |  | 2023-07-17 | 2023-08-10 | CD//Ali akaram | 2023-08-02 | CelcomDigi_RAN_CCSMY_TSS_Central_20230626_decom reraise | DU00002039540 |  |  |  |  | 2023-08-15 |  | LAMP_POLE
P00550 | P035D_P00550OD_JLNSGPINANG | Northern |  | Decomm |  | 2023Q3 | ZA | YPTT | 4.6 TSSR Approved |  | 2023-07-03 |  |  |  | 2023-07-18 |  | 2023-07-20 | 2023-08-08 | CD//Rohizam | 2023-08-04 | Celcom Digi_RAN-YPTT-TSS-Northern-20230609-0018 | DU00002039541 |  |  |  |  | 2023-09-20 |  | BOOM
Q00548 | Q118B_Q00548OD_BKTORANG | Sarawak |  | Decomm |  | 2023Q3 | BY | YPTT | 4.6 TSSR Approved |  | 2023-06-01 |  |  |  | 2023-06-08 |  | 2023-06-14 | 2024-01-05 | CD//John | 2023-06-14 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20230608-0005 | DU00002039542 |  | 2023-06-26 Missing TX photos and info |  |  | 2024-02-20 |  | TOWER
B00007 | B060C_B00007OD_SPGPCKALAM | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-17 |  |  | 2023-05-22 | 2023-05-22 | Under Approval | 2023-06-01 | 2023-12-19 | CD//Sapian | 2023-06-04 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002039543 |  |  |  |  | 2023-08-14 |  | TOWER
B00710 | B061C_B00710OD_SEK30SHLM | Central |  | Decomm |  | 2023Q3 | MA | AllStar | 4.6 TSSR Approved |  | 2023-06-10 |  |  |  | 2023-06-15 |  | 2023-07-12 | 2023-08-18 | CD//Norhaliza | 2023-07-26 | CelcomDigi_RANMW_AllStar_TSS_Central_20230612_0003 | DU00002039544 |  |  |  |  | 2023-07-21 |  | BOOM-TRIPOD
9983A | Demak Siol Kandis | Sarawak |  | Modernization |  | 2023Q4 | BY | Datasco | 4.6 TSSR Approved |  | 2023-07-31 | 2023-08-02 |  | 2023-08-04 |  | Closed | 2023-08-04 | 2023-08-11 | E//Hannah | 2023-08-11 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230802 | DU00002039545 |  |  | 2023-08-26 | 2023-08-22 |  | Tower | 30M Rapole | 30 | Add R9264H M901821 x4,Dismantle R8894E M1821(A8A) x4
P00428 | P035B_P00428OD_TMTGBUNGAH | Northern | 4146K | Swap |  | 2023Q3 | SM | GCI | 4.6 TSSR Approved |  | 2023-05-17 | 2023-05-19 |  | 2023-05-24 |  | Rectificating | 2023-05-26 | 2023-06-10 | CD//Affendi | 2023-06-08 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0014 | DU00002039546 |  |  | 2023-08-30 | 2023-08-24 |  | Rooftop | BOOM | 21 | Add R8852E S9000 x3 + R8894E M1821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
Q00284 | Q118B_Q00284OD_CB_TMBKTNYABAU | Sarawak | 9065K | Swap |  | 2023Q3 | SH | AllStar | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-26 |  | 2023-06-08 |  | Closed | 2023-06-09 | 2023-06-10 | CD//John | 2023-06-10 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230516-0005 | DU00002039547 |  |  | 2023-11-24 | 2023-11-13 |  | Tower | TOWER | 100 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
B00663 | B061B_B00663OD_PR_U8BKTJLTONG | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-10-03 |  |  |  | 2023-10-03 |  | 2023-10-16 | 2025-10-01 | CD//Sapian | 2023-10-23 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise/Celcom Digi_RAN-YPTT-TSS Decomm-Central-20230722 | DU00002039548 |  |  |  |  | 2023-10-06 |  | AESTHETIC MONOPOLE
9827A | Imperial Hotel Miri | Sarawak |  | Modernization |  | 2023Q4 | SH | Trintel | 4.6 TSSR Approved |  | 2023-07-18 | 2023-07-28 |  | 2023-08-07 |  | Closed | 2023-08-15 | 2023-09-01 | E//Hannah | 2023-09-01 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230726 | DU00002039549 |  |  | 2023-09-07 | 2023-09-04 |  | Portables BTS | In-building system |  | Reuse existing RRU
K00107 | K004A_K00107OD_ASPKNK | Northern |  | Decomm |  | 2023Q4 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-05-29 |  |  |  | 2023-06-13 |  | 2023-06-14 | 2024-02-29 | CD//Affendi | 2023-06-26 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230530-0021 | DU00002039550 |  |  |  |  | 2023-11-28 |  | BOOM
B02847 | B061B_B02847OD_PLAZAJELUTONGSHAHALAM | Central | 1183K | Swap |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-05-31 | 2023-06-01 |  | 2023-06-06 |  | Closed | 2023-06-12 | 2023-07-31 | CD//Sapian | 2023-07-31 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002039551 |  |  | 2023-08-29 | 2023-08-16 |  | Pole | TRIPOD | 9 | Add R8852E S9000 x3 + R8894E M1821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
B01514 | B061A_B01514OD_ALAMBUDIMAN | Central | 1129K | Swap |  | 2023Q3 | IE | Magicell | 4.6 TSSR Approved |  | 2023-05-15 | 2023-05-17 |  | 2023-05-19 |  | Closed | 2023-05-20 | 2023-07-15 | CD//Sapian | 2023-05-24 | CelcomDigi_RANMW_Magicell_TSS_Central_20230517_0002 | DU00002039552 |  |  | 2023-07-21 | 2023-07-18 |  | Wall mount boom | MINI STRUCTURE | 5 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
9702B | Jalan Desa Senadin Miri | Sarawak |  | Modernization |  | 2023Q4 | BY | Magicell | 4.6 TSSR Approved |  | 2023-07-05 | 2023-07-06 |  | 2023-07-10 |  | Closed | 2023-07-10 | 2023-07-25 | E//Hannah | 2023-07-18 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002039553 |  |  | 2023-08-13 | 2023-08-09 |  |  | 30M Rapole | 30M | Add R9264M M1821 x4,Dismantle R8892N M1821(BAB) x4
B00671 | B058A_B00671OD_JLNHAMZAHALANG | Central |  | Decomm |  | 2023Q3 | CR | Magicell | 4.6 TSSR Approved |  | 2023-06-14 |  |  |  | 2023-06-16 |  | 2023-07-24 | 2023-12-05 | CD//Ali akaram | 2023-08-01 | CelcomDigi_RAN_Magicell_TSS_Central_20230616_0013 | DU00002039554 |  |  |  |  | 2023-12-15 |  | TOWER
B00412 | B061B_B00412OD_WORLDWIDEBC | Central |  | Decomm |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-06-01 |  |  |  | 2023-08-03 |  | 2023-08-04 | 2024-05-10 | CD//Ali akaram | 2023-08-14 | CelcomDigi_RAN_Datasco_TSS_Central_20230606_0025 | DU00002039555 |  |  |  |  | 2023-12-04 |  | MINI STRUCTURE
P00180 | P035B_P00180OD_MIAMIBEACH | Northern |  | Decomm |  | 2023Q3 | MH | GCI | 4.6 TSSR Approved |  | 2023-06-13 |  |  |  | 2023-07-07 |  | 2023-06-22 | 2023-07-21 | CD//Shamsul | 2023-07-04 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1 | DU00002039556 |  |  |  |  | 2023-10-06 |  | BOOM
K00088 | K004A_K00088OD_HOSPITALBARU | Northern |  | Decomm |  | 2023Q4 | SM | GTSB | 4.6 TSSR Approved |  | 2023-05-31 |  |  |  | 2023-07-06 |  | 2023-07-07 | 2024-05-10 | CD//Rohizam | 2023-08-04 | Celcom Digi_RAN-GTSB-TSS-Northern-20230529-0020 | DU00002039557 |  | 25/7: No TX Info 7/8: Pending TX solution, Have E1&IDU |  |  | 2023-10-11 |  | TOWER
9696C | Kg Sg Plan | Sarawak |  | Modernization |  | 2023Q3 | BY | Trintel | 4.6 TSSR Approved |  | 2023-05-15 | 2023-05-16 |  | 2023-05-18 |  | Closed | 2023-05-23 | 2023-07-26 | E//Hannah | 2023-07-25 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230516-0007 | DU00002039558 |  |  | 2023-08-01 | 2023-07-28 |  | Tower | TOWER | 30m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
B02167 | B061A_B02167OD_JLNPLBMACSEK7SHLM | Central |  | Decomm |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-08 |  |  |  | 2023-08-18 |  | 2023-08-21 | 2023-12-19 | CD//Sapian | 2023-08-24 | CelcomDigi_RANMW_GTSB_TSS_Central_20230609_0002 | DU00002039559 |  |  |  |  | 2023-10-23 |  | BOOM
B01925 | B060C_B01925OD_IJOKINDUSTRI | Central | 1144K | Swap |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-05-31 | 2023-06-06 |  | 2023-06-08 |  | Closed | 2023-06-15 | 2023-06-28 | CD//Sapian | 2023-06-27 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002039560 |  |  | 2023-08-11 | 2023-07-31 |  | Monopole | RAMO | 25M | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
Q00263 | Q118A_Q00263OD_PARKCITY | Sarawak |  | Decomm |  | 2023Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2023-08-14 |  |  |  | 2023-08-25 |  | 2023-08-25 | 2023-10-04 | CD//John | 2023-08-28 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230913/Celcom Digi_RAN-Trintel-TSS DECOMM-Sarawak-20231130 | DU00002039561 |  | 28/8:uncompleted odu photo |  |  | 2023-11-23 |  | MINI STRUCTURE
B02440 | B061A_B02440OD_SURAULUQMANSETIAALAM | Central |  | Decomm |  | 2023Q3 | MA | Magicell | 4.6 TSSR Approved |  | 2023-06-12 |  |  |  | 2023-06-16 |  | 2023-06-21 | 2023-10-17 | CD//Ali Akaram | 2023-08-26 | CelcomDigi_RANMW_Magicell_TSS_Central_20230612_0005/CelcomDigi_RAN-TX_Magicell_TSS_Central_20230816_Decom | DU00002039562 |  |  |  |  | 2023-07-26 | Lampole | LAMP_POLE | 30M
P00030 | P031A_P00030OD_BKTRELAU | Northern |  | Decomm |  | 2023Q3 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-05-19 |  |  |  | 2023-08-07 |  | 2023-07-26 | 2024-02-29 | CD//Affendi | 2023-09-25 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002039563 |  | 1)Please include other TX equipment in 19rack |  |  | 2023-08-18 |  | TOWER
B01690 | B065B_B01690OD_T3_KGHULUTAMU | Central | 1136K | Swap |  | 2023Q4 | SS | Futong | 4.6 TSSR Approved |  | 2023-06-28 | 2023-06-28 |  | 2023-07-03 |  | Closed | 2023-07-06 | 2023-08-07 | CD//Ali akaram | 2023-08-07 | CelcomDigi_RAN_Futong_TSS_Central_20230630_0006 | DU00002039564 |  |  | 2023-09-19 | 2023-09-15 |  | Tower | TOWER | 76 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 1
B02048 | B060A_B02045OD_MN_JLNPARIT2 | Central | 1012P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039565 | [6 empty] | TOWER
9974A | Kampung Gersik | Sarawak |  | Modernization |  | 2023Q4 | BY | Magicell | 4.6 TSSR Approved |  | 2023-07-04 | 2023-07-10 |  | 2023-07-12 |  | Closed | 2023-07-18 | 2023-07-22 | E//Hannah | 2023-07-21 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002039566 |  |  | 2023-09-01 | 2023-08-25 |  | Monopole | Tower | 30m | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
B02234 | B057A_B02234OD_SURAUALFALAHTMNSLYGJYGBK | Central |  | Decomm |  | 2023Q4 | SS | YPTT | 4.6 TSSR Approved |  | 2023-07-29 |  |  |  | 2023-09-08 |  | 2023-09-08 | 2024-01-22 | CD//Sapian | 2023-09-16 | CelcomDigi_RAN_YPTT_TSS_Central_20230729 | DU00002039567 |  |  |  |  | 2023-09-24 |  | LAMP_POLE
B00045 | B060C_B00045OD_PR_PCKALAM2 | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-07-05 |  |  |  | 2023-07-05 |  | 2023-07-07 | 2024-02-23 | CD//Ali akaram | 2023-08-07 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002039568 |  |  |  |  | 2023-08-14 |  | TOWER
C00010 | C046C_C00010OD_TMNTEMAGENTING | Central |  | Decomm |  | 2023Q4 | AI | YPTT | 15.3 Decomm Done without TSSR | [6 empty] | To be Submitted |  |  | CD//Sapian |  | 0924CD-Central-Magicell-BOQ Template(new contract) | DU00002039569 |  |  |  |  | 2025-12-10 |  | BOOM
Q00607 | Q124B_Q00607OD_POLIKCH | Sarawak |  | Decomm |  | 2023Q4 | SH | South Pacific | 4.6 TSSR Approved |  | 2023-08-16 |  |  |  | 2023-08-17 |  | 2023-08-18 | 2023-08-24 | CD//John | 2023-08-18 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230913 | DU00002039570 |  |  |  |  | 2023-09-26 |  | TOWER
K00722 | K004A_K00722OD_JLN_MAHKOTA_AS | Northern |  | Decomm |  | 2023Q4 | BY | YPTT | 4.6 TSSR Approved |  | 2023-08-15 |  |  |  | 2023-08-16 |  | 2023-08-17 | 2023-11-23 | CD//Rohizam | 2023-11-30 | Celcom Digi_RAN-YPTT-TSS-Northern-20230706-0023 | DU00002039571 |  |  |  |  | 2023-10-05 |  | TRIPOD
B00439 | B061C_B00439OD_SEK32SHLM | Central |  | Decomm |  | 2023Q3 | MA | AllStar | 4.6 TSSR Approved |  | 2023-06-13 |  |  |  | 2023-06-16 |  | 2023-07-12 | 2023-08-10 | CD//Norhaliza | 2023-07-26 | CelcomDigi_RAN_Allstar_TSS_Central_20230616_0012 | DU00002039572 |  |  |  |  | 2023-07-21 |  | 4LEGGED
B01813 | B058C_B01813OD_RD_TMNSENTOSA2 | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-31 |  |  |  | 2023-08-08 |  | 2023-06-01 | 2023-09-01 | CD//Sapian | 2023-06-04 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002039573 |  | Solution provided - 10/8 |  |  | 2023-08-03 |  | MONOPOLE
C00259 | C046C_C00259OD_CB_BKTTINGGI | Central | 1207K | Decomm |  | 2023Q4 | SS | Magicell | 4.6 TSSR Approved |  | 2023-07-24 |  |  |  | 2023-07-26 |  | 2023-08-02 | 2023-10-17 | CD//Ali akaram | 2023-08-11 | CelcomDigi_RAN_Magicell_TSS_Central_20230727 | DU00002039574 |  |  |  |  | 2023-09-28 |  | BOOM
B01264 | B061A_B01264IB_WISMAMBSA | Central | 1115K | Swap |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-06-03 | 2023-06-09 |  | 2023-06-27 |  | Closed | 2023-07-03 | 2023-08-28 | CD//Sofiah | 2023-08-28 | CelcomDigi_RAN_Datasco_TSS_Central_20230606_0025 | DU00002039575 |  |  | 2023-11-15 | 2023-10-20 |  | Pole | IN-BUILDING |  | Add R8862A S1800 x3 + R8862A S2100 x3,Dismantle all celcom BBU&RRU
P00346 | P031B_P00346OD_SGNIBONG | Northern |  | Decomm |  | 2023Q3 | ZA | YPTT | 4.6 TSSR Approved |  | 2023-05-05 |  |  |  | 2023-06-20 |  | 2023-06-22 | 2023-08-08 | CD//Affendi | 2023-06-28 | Celcom Digi_RAN-YPTT-TSS-Northern-20230609-0018 | DU00002039576 |  | No TX Info, Photo not enough |  |  | 2023-08-09 |  | BOOM
B00281 | B062A_B00281OD_KGSGLEMAN | Central |  | Decomm |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-06-12 |  |  |  | 2023-08-16 |  | 2023-08-02 | 2023-12-19 | CD//Sapian | 2023-08-16 | CelcomDigi_RANMW_Magicell_TSS_Central_20230612_0005 | DU00002039577 |  |  |  |  | 2023-08-19 |  | TOWER
K00083 | K004A_K00083OD_TMNPKNK | Northern |  | Decomm |  | 2023Q4 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-05-29 |  |  |  | 2023-06-26 |  | 2023-06-27 | 2023-08-28 | CD//Shamsul | 2023-07-06 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230530-0021 | DU00002039578 |  |  |  |  | 2023-10-10 |  | MINI STRUCTURE
K00843 | K004A_K00843OD_JLNTEMBAGA_AS | Northern |  | Decomm |  | 2023Q4 | SM | YPTT | 4.6 TSSR Approved |  | 2023-06-13 |  |  |  | 2024-11-01 |  | 2023-07-20 | 2025-10-01 | CD//Quah | 2023-08-17 | Celcom Digi_RAN-YPTT-TSS-Northern-20230613-0020 | DU00002039579 |  |  |  |  | 2023-12-27 |  | RAPID ASSEMBLY POLE (RAPOLE)
C00059 | C046C_C00059OD_CB_TIJU | Central |  | Decomm |  | 2023Q4 | SS | Magicell | 4.6 TSSR Approved |  | 2023-07-25 |  |  |  | 2023-07-29 |  | 2023-08-02 | 2023-12-05 | CD//Norhaliza | 2023-08-18 | CelcomDigi_RAN_Magicell_TSS_Central_20230727 | DU00002039580 |  |  |  |  | 2024-02-08 |  | TOWER
9763B | Desa Murni (REL) | Sarawak |  | Modernization |  | 2023Q4 | BY | South Pacific | 4.6 TSSR Approved |  | 2023-06-08 | 2023-06-12 |  | 2023-06-15 |  | Closed | 2023-06-16 | 2023-06-27 | E//Hannah | 2023-06-27 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230606-0003 | DU00002039581 |  |  | 2023-07-13 | 2023-07-06 |  | Monopole | TOWER | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
B00431 | B058A_B00431OD_PEKANMERU | Central |  | Decomm |  | 2023Q3 | IE | Magicell | 4.6 TSSR Approved |  | 2023-06-17 |  |  |  | 2023-07-06 |  | 2023-07-12 | 2023-10-17 | CD//Sapian | 2023-07-17 | CelcomDigi_RAN_Magicell_TSS_Central_20230620_0014 | DU00002039582 |  |  |  |  | 2023-08-29 |  | MINI STRUCTURE
B01462 | B061C_B01462OD_KOTAKEMUNING4 | Central |  | Decomm |  | 2023Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-06-15 |  |  |  | 2024-05-16 |  | 2023-08-16 | 2024-09-26 | CD//Ali Akaram | 2023-08-26 | CelcomDigi_RAN_Allstar_TSS_Central_20230616_0012 | DU00002039583 |  |  |  |  | 2023-07-24 |  | MONOPOLE
K00915 | K004B_K00915OD_KOMP_HIJAU_KUNING | Northern | 4110K | Swap |  | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-06-02 | 2023-06-06 |  | 2023-06-08 |  | Closed | 2023-06-12 | 2023-07-03 | CD//Heng | 2023-07-03 | Celcom Digi_RAN-YPTT-TSS-Northern-20230606-0017 | DU00002039584 |  |  | 2023-11-16 | 2023-10-01 |  | Monopole | MONOPOLE | 30 | Add R9264H M901821 x3 + R9264M M1821 x3,Dismantle Celcom all RRU&BBU |  | 123
B01338 | B062A_B01338OD_LDGGAGASNSGPJG | Central | 1119K | Swap |  | 2023Q4 | HQ 1 | Magicell | 4.6 TSSR Approved |  | 2023-05-31 | 2023-06-06 |  | 2023-06-08 |  | Closed | 2023-06-12 | 2023-06-22 | CD//Sapian | 2023-06-22 | CelcomDigi_RAN_Magicell_TSS_Central_20230601_0011 | DU00002039585 |  |  | 2023-08-15 | 2023-08-10 |  | Tower | TOWER | 70 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
B02843 | B061D_B02843OD_SHLMAUTOCITY2 | Central | 1180K | Swap |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-09-21 | 2023-09-26 |  | 2023-10-03 |  | Closed | 2023-10-05 | 2023-10-17 | CD//Sapian | 2023-10-11 | CelcomDigi_RAN_GTSB_TSS_Central_20230921 | DU00002039586 |  |  | 2023-10-19 | 2023-10-17 |  |  | TRIPOD | 6m | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 1
A00522 | A042A_A00522OD_CB_PANTAIBESAR | Northern | 4071K | Swap |  | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-05-29 | 2023-06-06 |  | 2023-06-07 |  | Closed | 2023-06-12 | 2023-07-13 | CD//Quah | 2023-07-13 | Celcom Digi_RAN-YPTT-TSS-Northern-20230531-0015 | DU00002039587 |  |  | 2023-08-16 | 2023-08-04 |  | Tower | TOWER | 61 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 2
B00272 | B060B_B00272OD_TMBKTROTAN | Central |  | Decomm |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-08-13 |  |  |  | 2023-08-13 |  | 2023-08-17 | 2024-05-29 | CD//Ali Akaram | 2024-02-23 | CelcomDigi_RAN_YPTT_TSS_Central_20230815 | DU00002039588 |  | 1. For NE, Please provide IDU label photo showing link ID 2. For NE, Please provide clear ODU label photo |  |  | 2023-10-05 |  | TOWER
Q00703 | Q118B_Q00703OD_JLNBELIMBING | Sarawak |  | Decomm |  | 2023Q3 | ZB | CCSMY | 4.6 TSSR Approved |  | 2023-06-26 |  |  |  | 2023-07-04 |  | 2023-08-15 | 2024-05-14 | CD//John | 2023-08-15 | Celcom Digi_RAN-Satellite-TSS-Sarawak-20231009/0920CD-Sarawak-CCSMY-BOQ Template (old contract)/Celcom Digi_RAN_CCSMY_TSS_Sarawak_20241112 | DU00002039589 |  | 22/8: uncompleted info & photos Wrong drawing attached |  |  | 2023-12-06 |  | TOWER
B01801 | B061C_B01801OD_RD_TMNPERINDSTRIAN | Central |  | Decomm |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-08-09 |  |  | 2023-08-24 | 2023-09-05 | Closed | 2023-08-25 | 2023-12-19 | CD//Sapian | 2023-08-25 | CelcomDigi_RAN_YPTT_TSS_Central_20230810 | DU00002039590 |  |  |  |  | 2023-09-13 |  | BOOM
A00006 | A036B_A00006OD_KOTAPRIMA | Central |  | Decomm |  | 2023Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-06-11 |  |  |  | 2023-08-08 |  | 2023-08-08 | 2023-12-19 | CD//Sapian | 2023-08-17 | CelcomDigi_RANMW_Ascentrack_TSS_Central_20230612_0005 | DU00002039591 |  |  |  |  | 2023-09-20 |  | TOWER
P00362 | P035F_P00362OD_WATERTANKUSM | Northern |  | Decomm |  | 2023Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-05-20 |  |  |  | 2023-06-21 |  | 2023-06-23 | 2023-08-08 | CD//Affendi | 2023-06-28 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2/Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230726-0024/Celcom Digi_CD CONSOLIDATION-GTSB-TI-Northern-20240920_Old Contract | DU00002039592 |  |  |  |  | 2023-10-06 |  | WATER TANK
B00558 | B061A_B00558OD_MERU | Central |  | Decomm |  | 2023Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2023-06-15 |  |  |  | 2023-07-06 |  | 2023-07-31 | 2023-12-19 | CD//Sapian | 2023-08-15 | CelcomDigi_RAN_Magicell_TSS_Central_20230616_0013 | DU00002039593 |  | Can we maintain the OB and for xD NLOS, maintain using xD MW. |  |  | 2023-08-29 |  | TOWER
C00002 | C046C_C00002OD_KM14GENTING | Central |  | Decomm |  | 2023Q4 | CR | Magicell | 4.6 TSSR Approved |  | 2023-07-14 |  |  |  | 2023-07-18 |  | 2023-07-28 | 2023-12-19 | CD//Sapian | 2023-08-15 | CelcomDigi_RAN_Magicell_TSS_Central_20230717 | DU00002039594 |  | RESUBMISSION-Please provide clear DIGI ODU label photo for NE & FE |  |  | 2024-02-14 |  | MONOPOLE
Q00684 | Q118B_Q00684OD_TMNBDA | Sarawak |  | Decomm |  | 2023Q3 | ZB | AllStar | 4.6 TSSR Approved |  | 2023-08-14 |  |  |  | 2023-08-24 |  | 2023-08-24 | 2023-09-11 | CD//John | 2023-09-06 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230622 | DU00002039595 |  | 4/9: uncompleted photos & info |  |  | 2023-11-28 |  | MONOPOLE
B02536 | B058C_B02536OD_SURAUTMNSERISENTOSAKLG | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-18 |  |  |  | 2023-08-09 |  | 2023-06-13 | 2023-08-18 | CD//Sapian | 2023-07-02 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002039596 |  |  |  |  | 2023-08-17 |  | LAMP_POLE
P00096 | P035F_P00096OD_RELAU | Northern |  | Decomm |  | 2023Q3 | MH | GTSB | 4.6 TSSR Approved |  | 2023-05-23 |  |  |  | 2023-07-27 |  | 2023-06-08 | 2023-09-07 | CD//Shamsul | 2023-06-21 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2 | DU00002039597 |  |  |  |  | 2023-07-26 |  | BOOM
B01701 | B062A_B01701OD_T3_RZBSGDUSUN | Central | 1140K | Swap |  | 2023Q4 | HQ 6 | Datasco | 4.6 TSSR Approved |  | 2023-07-10 | 2023-07-14 |  | 2023-07-18 |  | Closed | 2023-07-21 | 2023-08-28 | CD//Ali Akaram | 2023-08-26 | CelcomDigi_RAN_DATASCO_TSS_Central_20230710 | DU00002039598 |  |  | 2023-12-28 | 2023-10-20 |  | Tower | TOWER | 62 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
B00469 | B061D_B00469OD_KM12FEDHWY | Central |  | Decomm |  | 2023Q4 | SS | Datasco | 4.6 TSSR Approved |  | 2023-07-31 |  |  |  | 2024-07-15 |  | 2023-08-05 | 2024-09-26 | CD//Ali akaram | 2024-02-23 | CelcomDigi_RAN_Datasco_TSS_Central_20230802 | DU00002039599 |  |  |  |  | 2023-09-22 |  | 3LEGGED
P00062 | BKTPENARA2 | Northern | 4121K | Site Out (Swap) | Swap->Site Out->Site Out (Swap) | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-06-01 | 2023-05-24 |  | 2023-06-01 |  | Closed | 2023-06-07 | 2023-06-13 | CD//Heng | 2023-06-13 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0014 | DU00002039600 | [5 empty] | Tower | TOWER | 120
B00122 | B057C_B00122OD_UIA2GBK | Central |  | Decomm |  | 2023Q4 | CR | Datasco | 4.6 TSSR Approved |  | 2023-07-31 |  |  |  | 2023-08-21 |  | 2023-08-22 |  | CD//Sapian | 2023-08-23 | CelcomDigi_RAN_Datasco_TSS_Central_20230802 | DU00002039601 |  | Wrong TX antenna photo |  |  | 2024-03-13 |  | AESTHETIC MONOPOLE
B00498 | B060B_B00498OD_KAPAR | Central |  | Decomm |  | 2023Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-28 | 2023-06-26 |  |  | 2023-08-03 |  | 2023-07-24 | 2023-10-18 | CD//Sapian | 2023-08-02 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002039602 |  | EXTRA IDU |  |  | 2023-07-21 | Tower | TOWER | 45
C00009 | C046C_C00009OD_GENTINGSEMPAH | Central |  | Decomm |  | 2023Q4 | CR | Magicell | 4.6 TSSR Approved |  | 2023-07-12 |  |  |  | 2023-07-13 |  | 2023-07-28 | 2023-12-21 | CD//Sapian | 2023-08-15 | CelcomDigi_RAN_Magicell_TSS_Central_20230714 | DU00002039603 |  |  |  |  | 2024-01-08 |  | 3LEGGED
B01566 | B061G_B01566OD_SUNWAYKAYANGAN | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-18 |  |  | 2023-05-22 | 2023-05-22 | Under Approval | 2023-06-02 | 2023-12-19 | CD//Sapian | 2023-06-04 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002039604 |  | Approved. Please amend this site from OB to TM since this site using fiber TM NGBH. |  |  | 2023-08-28 |  | AESTHETIC MONOPOLE
B02524 | B061F_B02524OD_SURAUALHIDAYAHSAUJANAUTAMA | Central |  | Decomm |  | 2023Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-05-22 |  |  |  | 2023-09-23 |  | 2023-09-25 | 2023-10-20 | CD//Sapian | 2023-10-17 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002039605 |  |  |  |  | 2023-09-27 |  | LAMP_POLE
P00191 | P035B_P00191OD_NBPLACE | Northern |  | Decomm |  | 2023Q3 | MH | CCSMY | 4.6 TSSR Approved |  | 2023-05-05 |  |  |  | 2023-06-13 |  | 2023-06-14 | 2023-08-08 | CD//Affendi | 2023-06-26 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002039606 |  |  |  |  | 2023-09-14 |  | BOOM
B02846 | B061A_B02846OD_PSNSETIAPRIMASETIAALAM2 | Central | 1182K | Swap |  | 2023Q3 | IE | Magicell | 4.6 TSSR Approved |  | 2023-05-12 | 2023-05-15 |  | 2023-05-17 |  | Closed | 2023-05-18 | 2023-08-07 | CD//Sapian | 2023-07-18 | CelcomDigi_RANMW_Magicell_TSS_Central_20230517_0002 | DU00002039607 |  |  | 2023-07-20 | 2023-07-13 |  | Lampole | LAMP_POLE | 18 | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle Celcom all RRU&BBU |  | 3
B02731 | B061C_B02731OD_KEMUNINGANGGERIK | Central |  | Decomm |  | 2023Q3 | MA | AllStar | 4.6 TSSR Approved |  | 2023-06-16 |  |  |  | 2023-06-16 |  | 2023-07-03 | 2023-08-10 | CD//Sapian | 2023-07-07 | CelcomDigi_RAN_Allstar_TSS_Central_20230620_0013 | DU00002039608 |  |  |  |  | 2023-08-18 |  | BOOM
P00481 | P035B_P00481OD_GOLDENSANDRESORT | Northern | 4147K | Swap |  | 2023Q3 | ZA | YPTT | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-13 |  | 2023-05-16 |  | Closed | 2023-05-18 | 2023-05-31 | CD//Shamsul | 2023-05-31 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0008 | DU00002039609 |  | 0517 rejected.. minor only.. pls revise asap | 2024-02-23 | 2023-11-15 |  | Wall mount boom | BOOM | 4.5m | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 2
B00946 | B065B_B00946OD_SGTENGI | Central |  | Decomm |  | 2023Q4 | MA | Magicell | 4.6 TSSR Approved |  | 2023-07-03 |  |  |  | 2023-07-05 |  | 2023-07-13 | 2023-12-05 | CD//Ali akaram | 2023-07-27 | CelcomDigi_RAN_Magicell_TSS_Central_20230630_0019 | DU00002039610 |  | xD using celcom MW for Bw sharing. @khairul.amat@zte.com.cn, Please check and verify. Tq |  |  | 2023-09-23 |  | TOWER
B02537 | B058A_B02537OD_TMNPERINDUSTRIANMERUINDAH | Central |  | Decomm |  | 2023Q3 | IE | Magicell | 4.6 TSSR Approved |  | 2023-06-15 |  |  |  | 2023-07-07 |  | 2023-07-12 | 2023-10-18 | CD//Sapian | 2023-07-18 | CelcomDigi_RAN_Magicell_TSS_Central_20230616_0013 / CelcomDigi_TX_Magicell_TSS_Decom_Central_20230714 | DU00002039611 |  |  |  |  | 2023-08-29 |  | BOOM
C00004 | C046C_C00004OD_TMULUKALI | Central |  | Decomm |  | 2023Q4 | SH | GTSB | 4.6 TSSR Approved |  | 2024-05-17 |  |  |  | 2024-05-27 |  | 2024-05-31 | 2024-07-19 | CD//Ali akaram | 2024-07-03 | CelcomDigi_RAN_GTSB_TSS_Central_20240423 | DU00002039612 |  |  |  |  | 2024-12-20 |  | 4LEGGED
B00656 | B061A_B00656OD_PR_SEK4SA | Central | 1092K | Swap |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-06-20 | 2023-06-22 |  | 2023-06-27 |  | Closed | 2023-06-28 | 2023-08-28 | CD//Ali Akaram | 2023-08-26 | CelcomDigi_RAN_Datasco_TSS_Central_20230622_0028 | DU00002039613 |  |  | 2023-10-26 | 2023-10-20 |  | Tower | TOWER | 70 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
P00756 | P035D_P00756OD_PERSIARAN_KARPAL_SINGH | Northern | 4159K | Swap |  | 2023Q3 | SM | YPTT | 4.6 TSSR Approved | ¦ 20231123 - sent proposal for Option 1. Propose change to smaller RRU type. To be confirmed by Planner. Option 2. Propose additional cabinet and relocate 2 nos RRU inside new cabinet to provide more space for cable management. Additional cabinet may be installed on groud or mounted at existing pole subject to Structure Owner approval. Additional cabinet propose is as below photo for reference. Remarks: RRU not allowed to be exposed | 2023-05-18 | 2023-05-24 |  | 2023-05-27 |  | Closed | 2023-06-28 | 2023-07-05 | CD//Shamsul | 2023-07-04 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0008 | DU00002039614 |  |  | 2023-07-26 | 2023-07-18 |  | Lampole | STREET POLE | 20m | Add R9264M M1821 x3
Q00517 | Q124B_Q00517OD_TMNMALIHAH | Sarawak |  | Decomm |  | 2023Q4 | SH | South Pacific | 4.6 TSSR Approved |  | 2023-08-11 |  |  |  | 2023-09-15 |  | 2023-09-15 | 2023-09-23 | CD//John | 2023-09-18 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230913 | DU00002039615 |  |  |  |  | 2023-10-07 |  | TOWER
B02592 | B065B_B02592OD_TMNSEROJABKTSENTOSARWG | Central |  | Decomm |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-25 |  |  |  | 2023-07-26 |  | 2023-07-18 | 2023-09-19 | CD//Norhaliza | 2023-09-13 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002039616 |  |  |  |  | 2023-07-27 | Lampole | LAMP_POLE | 30
B01687 | B060C_B01687OD_TMNALAMSURIAPCKALAM | Central | 1135K | Swap |  | 2023Q3 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-06-23 | 2023-07-04 |  | 2023-07-11 |  | Closed | 2023-07-13 | 2023-07-27 | CD//Ali akaram | 2023-07-27 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002039617 |  |  | 2023-10-12 | 2023-10-10 |  | Lampole | LAMP_POLE | 25 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 2
K00430 | K004B_K00430OD_CB_TAJAR | Northern |  | Decomm |  | 2023Q4 | ZA | GCI | 4.6 TSSR Approved |  | 2023-08-03 |  |  |  | 2025-02-26 |  | 2023-08-17 | 2023-08-30 | CD//Rohizam | 2023-08-17 | Celcom Digi_RAN-GCI-TSS-Northern-20230801-0037 | DU00002039618 |  |  |  |  | 2023-10-16 |  | TOWER
Q00307 | Q132C_Q00307OD_PACIFICORIENT | Sarawak |  | Decomm |  | 2023Q4 | SH | Datasco | 4.6 TSSR Approved |  | 2023-08-02 |  |  |  | 2023-08-07 |  | 2023-08-07 | 2023-08-30 | CD//John | 2023-08-07 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 | DU00002039619 |  | 22/8: 22-Aug-23 |  |  | 2025-04-10 |  | BOOM
B02384 | B061D_B02384OD_SEK16INDUSTRYSCT | Central |  | Decomm |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-01-11 |  |  |  | 2024-08-22 |  | 2023-09-20 | 2025-04-07 | CD//Norhaliza | 2023-10-05 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240115 | DU00002039620 |  |  |  |  | 2023-09-14 |  | AESTHETIC MONOPOLE
B01042 | B061A_B01042OD_PR_BKTBDRAYASHLM | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-31 |  |  | 2023-07-31 | 2023-05-31 | Under Approval | 2023-06-02 | 2023-09-19 | CD//Sapian | 2023-06-09 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002039621 |  |  |  |  | 2023-08-28 |  | AESTHETIC MONOPOLE
P00188 | P035C_P00188IB1_KOMTARID | Northern |  | Decomm |  | 2023Q3 | SM | GCI | 4.6 TSSR Approved |  | 2023-06-13 |  |  |  | 2023-07-25 |  | 2023-07-31 | 2023-08-24 | CD//Quah | 2023-08-22 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1 | DU00002039622 |  |  |  |  | 2024-10-10 |  | IN-BUILDING
Q00158 | Q124F_Q00158IB_NORMAHMEDICAL | Sarawak |  | Decomm |  | 2023Q4 | ZB | AllStar | 4.6 TSSR Approved |  | 2023-07-24 |  |  | 2023-08-14 | 2023-08-02 | Closed | 2023-08-15 | 2023-09-08 | CD//John | 2023-08-17 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230622 | DU00002039623 |  | 2/8) only Celcom Equipment can dismantle A lot of info and photo missing |  |  | 2025-11-22 |  | IN-BUILDING
P00624 | P031B_P00624OD_TMNSRIBAYAN_PNG | Northern |  | Decomm |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-05-15 |  |  |  | 2023-06-22 |  | 2023-06-23 | 2023-08-08 | CD//Rohizam | 2023-08-04 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1 | DU00002039624 |  |  |  |  | 2023-08-03 |  | MINARET
P00045 | P031B_P00045OD_BAYANBAY | Northern |  | Decomm |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-05-03 |  |  |  | 2023-09-08 |  | 2023-09-11 | 2023-11-23 | CD//Rohizam | 2023-09-12 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1 | DU00002039625 |  |  |  |  | 2023-08-18 |  | TOWER
B02507 | B058C_B02507OD_TMNSENTOSAJLNSGJATIKLG | Central |  | Decomm |  | 2023Q3 | SS | Futong | 4.6 TSSR Approved |  | 2023-05-23 |  |  | 2023-06-02 | 2024-05-06 | Closed | 2023-07-20 | 2023-10-25 | CD//Ali Akaram | 2023-08-26 | CelcomDigi_RAN_Futong_TSS_Central_20230626_decom reraise | DU00002039626 |  |  |  |  | 2023-08-29 |  | RAPID ASSEMBLY POLE (RAPOLE)
K00050 | K004B_K00050OD_ALORMENGKUDU | Northern | 4085K | Swap |  | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-06-05 | 2023-06-07 |  | 2023-06-10 |  | Closed | 2023-06-13 | 2023-08-18 | CD//Quah | 2023-08-18 | Celcom Digi_RAN-YPTT-TSS-Northern-20230606-0017 | DU00002039627 |  |  | 2023-09-25 | 2023-09-25 |  | Tower | TOWER | 65 | Add R8852E S9000 x3 + A9732 M1821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 123
P00001 | P031B_P00001OD_MASCARGO | Northern | 4112K | Swap |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-06-22 | 2023-06-26 |  | 2023-06-28 |  | Closed | 2023-07-03 | 2023-08-01 | CD//Heng | 2023-07-04 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0015 | DU00002039628 |  |  | 2023-07-27 | 2023-07-13 |  | Pole | MINI STRUCTURE | 9m | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 1
A01285 | Kampung Sumpit Beras | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039629 | [6 empty] | 3LEGGED
B02496 | B061C_B02496OD_BLTNTUNTEJASEK34SALAM | Central |  | Decomm |  | 2023Q3 | SS | GCI | 4.6 TSSR Approved |  | 2023-06-06 |  |  |  | 2024-06-07 |  | 2023-09-12 | 2023-10-17 | CD//Sapian | 2023-09-16 | CelcomDigi_RAN_Futong_TSS_Central_20230626_decom reraise/CelcomDigi_TX_Futong_TSS_Decom_Central_20230922 | DU00002039630 |  |  |  |  | 2023-09-19 |  | LAMP_POLE
P00094 | P035B_P00094OD_MERIT | Northern |  | Decomm |  | 2023Q3 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-05-25 |  |  |  | 2023-07-27 |  | 2023-08-01 | 2023-08-30 | CD//Affendi | 2023-08-01 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002039631 |  |  |  |  | 2023-10-06 |  | BOOM
P00161 | P031B_P00161OD_SANYO | Northern |  | Decomm |  | 2023Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-05-20 |  |  |  | 2023-07-27 |  | 2023-06-28 | 2023-08-08 | CD//Rohizam | 2023-08-04 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2 | DU00002039632 |  |  |  |  | 2023-08-02 | Lampole | MONOPOLE | 20m
B02732 | B061C_B02732OD_JLNSGJELUHSEK32SHAHALAM | Central |  | Decomm |  | 2023Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-07-24 |  |  |  | 2023-07-31 |  | 2023-08-02 | 2023-10-02 | CD//Ali akaram | 2023-09-19 | CelcomDigi_RAN_AllStar_TSS_Central_20230802 | DU00002039633 |  |  |  |  | 2023-09-14 |  | UNIPOLE
B01608 | B061D_B01608OD_UMWTOYOTSK15SHLM | Central |  | Decomm |  | 2023Q4 | SS | Solusi | 4.6 TSSR Approved |  | 2024-01-11 |  |  | 2024-03-19 | 2024-03-20 | Under Approval | 2024-08-13 |  | CD//Sapian | 2024-08-14 | BOQ CelcomDigi_RAN_Solusi_Standard PR TSS_Central_20240115 | DU00002039634 |  | MISSING FE PART |  |  | 2023-10-27 |  | WATER TANK
K00029 | K004A_K00029OD_KOPERASIKESIHATAN | Northern |  | Decomm |  | 2023Q4 | SM | GTSB | 4.6 TSSR Approved |  | 2023-06-01 |  |  |  | 2023-06-16 |  | 2023-06-18 | 2024-04-16 | CD//Quah | 2023-07-20 | Celcom Digi_RAN-GTSB-TSS-Northern-20230529-0020 | DU00002039635 |  | Please include unused link |  |  | 2024-03-29 |  | BOOM
Q00348 | Q132B_Q00348OD_TMLUTONGEX | Sarawak | 9069K | Swap |  | 2023Q4 | SH | Magicell | 4.6 TSSR Approved |  | 2023-08-02 | 2023-08-03 |  | 2023-08-08 |  | Closed | 2023-08-08 | 2023-08-09 | CD//John | 2023-08-09 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002039636 |  |  | 2025-07-06 | 2025-05-24 |  | In-Building System | BOOM | 6m | Add R8852E S9000 x3 + R8894E M1821 x3
K00528 | K004A_K00528OD_SPG4HOSPITALAS | Northern | 4100K | Swap |  | 2023Q4 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-06-19 | 2023-06-15 |  | 2023-06-19 |  | Closed | 2023-06-23 | 2023-08-04 | CD//Rohizam | 2023-08-04 | Celcom Digi_RAN-GCI-TSS-Northern-20230613-0027 | DU00002039637 |  |  | 2023-09-19 | 2023-09-16 |  | Monopole | LAMP_POLE | 35 | Add R8852E S9000 x3 + A9732 M1821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 123
B01975 | B061A_B01975OD_RD_SEK11SHLM | Central |  | Decomm |  | 2023Q4 | MA | Datasco | 4.6 TSSR Approved |  | 2023-06-20 |  |  |  | 2024-06-24 |  | 2023-09-29 | 2024-07-19 | CD//Sapian | 2023-11-16 | CelcomDigi_RAN_Datasco_TSS_Central_20230622_0028 | DU00002039638 |  |  |  |  | 2023-10-31 |  | TOWER
B00042 | B062A_B00042OD_KGPRTBARU | Central |  | Decomm |  | 2023Q4 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-08-23 |  | 2025-10-30 |  | 2024-02-15 |  | 2024-02-16 |  | CD//Sapian | 2024-02-26 | CelcomDigi_RAN_CCSMY_TSS_Central_20230824 | DU00002039639 |  | DISMANTLE CELCOM MICROWAVE LINK B00042-B00647 |  |  | 2023-11-24 |  | TOWER
Q00101 | Q124B_Q00101OD_SMSMATANG | Sarawak | 9057K | Swap |  | 2023Q4 | ZB | Datasco | 4.6 TSSR Approved |  | 2024-02-20 | 2024-02-21 |  | 2024-02-21 |  | Closed | 2024-02-21 | 2024-02-23 | CD//John | 2024-02-23 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 - Copy | DU00002039640 |  |  | 2024-03-01 | 2024-02-24 |  | Tower | WATER TANK | 20 | Add R8852E S9000 x3 + R8894E M1821 x3
B00514 | B057B_B00514OD_BDRBARUSLYG | Central |  | Decomm |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-09-23 |  |  |  | 2023-09-25 |  | 2023-09-26 | 2023-11-22 | CD//Sapian | 2023-10-03 | CelcomDigi_RAN_YPTT_TSS_Central_20231005 | DU00002039641 |  |  |  |  | 2023-09-23 |  | TOWER
P00263 | P035D_P00263OD1_PSCJLNUTAMA | Northern |  | Decomm |  | 2023Q3 | BY | GCI | 4.6 TSSR Approved |  | 2023-06-06 |  |  |  | 2023-10-13 |  | 2023-10-17 | 2023-10-27 | CD//Affendi | 2023-10-18 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1 | DU00002039642 |  |  |  |  | 2023-09-27 |  | BOOM
P00508 | P031A_P00508OD_SAUJANAHEIGHT | Northern |  | Decomm |  | 2023Q3 | SM | GCI | 4.6 TSSR Approved |  | 2023-08-11 |  |  |  | 2024-03-28 |  | 2023-08-22 | 2023-08-24 | CD//Rohizam | 2023-08-22 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002039643 |  |  |  |  | 2023-08-06 |  | BOOM
B02715 | B061A_B02715OD_PSRNBESTARI2SK7SHLM | Central | 1167K | Swap |  | 2023Q4 | XH | GTSB | 4.6 TSSR Approved |  | 2023-06-12 | 2023-06-20 |  | 2023-06-24 |  | Closed | 2023-06-24 | 2023-07-13 | CD//Sapian | 2023-07-12 | CelcomDigi_RAN_GTSB_TSS_Central_20230616_0029 | DU00002039644 |  |  | 2023-09-29 | 2023-09-27 |  | In-Building System | BOOM | 6M | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle Celcom all RRU&BBU |  | 1
P00366 | P031A_P00366OD_PBATLKBAHANG | Northern | 4140K | Swap |  | 2023Q3 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-05-14 | 2023-05-19 |  | 2023-05-23 |  | Closed | 2023-05-25 | 2023-06-10 | CD//Affendi | 2023-06-08 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0009 | DU00002039645 |  |  | 2023-08-22 | 2023-08-22 |  | Tower | TOWER | 60M | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
P00066 | P035F_P00066OD_SUNNYPOINT | Northern |  | Decomm |  | 2023Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-05-19 |  |  |  | 2023-07-27 |  | 2023-07-25 | 2023-08-08 | CD//Rohizam | 2023-08-04 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002039646 |  |  |  |  | 2023-08-16 |  | BOOM
K00522 | K004B_K00522OD_TMNSRIAMPANG | Northern |  | Decomm |  | 2023Q4 | MH | GCI | 4.6 TSSR Approved |  | 2023-06-20 |  |  |  | 2023-06-23 |  | 2023-06-23 | 2023-09-21 | CD//Shamsul | 2023-07-04 | Celcom Digi_RAN-GCI-TSS-Northern-20230621-0032/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240529-0109 | DU00002039647 |  | 15/8:Need include unused link NT05083 antenna,ODU |  |  | 2023-10-16 |  | MONOPOLE
P00269 | P035A_P00269OD_LONEPINEPLAZA | Northern |  | Decomm |  | 2023Q3 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-05-19 |  |  |  | 2023-06-16 |  | 2023-06-19 | 2023-07-28 | CD//Affendi | 2023-06-27 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002039648 |  |  |  |  | 2023-09-13 |  | BOOM
9971A | Masjid Matang Jaya Baru | Sarawak |  | Modernization |  | 2023Q4 | HQ 1 | Magicell | 4.6 TSSR Approved |  | 2023-07-22 | 2023-07-25 |  | 2023-07-27 |  | Closed | 2023-07-28 | 2023-08-30 | E//Hannah | 2023-08-01 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002039649 |  |  | 2023-09-14 | 2023-08-18 |  | Monopole | Tower | 30m | Add R9264M M1821 x6 + R8862A S2601 x3,Dismantle R9224E M1821(AAB) x3 |  | 123
A01199 | T3_0627_Kg Tua Hulu Kerian | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039650 | [6 empty] | TOWER
Q00292 | Q118B_Q00292OD_TMTUBAU | Sarawak | 9477P | Swap | Swap->TBD->Swap->On Hold->Swap | 2023Q3 | SH | South Pacific | 4.6 TSSR Approved |  | 2023-05-23 | 2023-06-02 |  | 2023-06-13 |  | Closed | 2023-06-19 | 2023-08-25 | CD//John | 2023-06-21 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230512-0001 | DU00002039651 |  |  | 2024-03-07 | 2024-01-23 |  | Tower | TOWER | 80m | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
C00595 | C046C_C00595IB_RSC8GENTING | Central |  | Decomm |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-09-29 |  |  |  | 2023-10-11 |  | 2023-10-12 | 2023-12-19 | CD//Sofiah | 2023-11-07 | CelcomDigi_RAN_GTSB_TSS_Central_20231003 | DU00002039652 |  |  |  |  | 2025-12-10 |  | IN-BUILDING
B01085 | B057C_B01085OD_BT8JLNGOMBAK | Central |  | Decomm |  | 2023Q4 | MA | Datasco | 4.6 TSSR Approved |  | 2023-07-31 |  |  |  | 2023-08-03 |  | 2023-08-10 | 2025-09-19 | CD//Ali Akaram | 2023-08-16 | CelcomDigi_RAN_Datasco_TSS_Central_20230802 | DU00002039653 |  |  |  |  | 2023-12-06 |  | TOWER
A00083 | A042A_A00083OD_CB_BKTLARUT_RCC | Northern |  | Decomm |  | 2023Q4 | ZA | CCSMY | 4.6 TSSR Approved | ¦ 0129 - Pending FE, Plan submission 30/1 | 2023-06-12 |  |  |  | 2024-01-30 |  | 2024-01-31 | 2024-02-22 | CD//Affendi | 2024-02-06 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230613-0025 | DU00002039654 |  |  |  |  | 2024-01-22 |  | TOWER
P00551 | P035D_P00551OD_TMNABIDIN | Northern | 4149K | Swap |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-26 | 2023-05-29 |  | 2023-06-03 |  | Closed | 2023-06-26 | 2023-07-03 | CD//Shamsul | 2023-07-03 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0015 | DU00002039655 |  |  | 2023-07-26 | 2023-07-18 |  | Wall mount boom | BOOM | 20m | Add R8852E S9000 x3 + R8894E M1821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
K00114 | K004B_K00114OD_PKNSMPGKUALA | Northern |  | Decomm |  | 2023Q4 | MH | GCI | 4.6 TSSR Approved |  | 2023-06-09 |  |  |  | 2023-06-21 |  | 2023-06-22 | 2024-06-19 | CD//Rohizam | 2023-08-04 | Celcom Digi_RAN-GCI-TSS-Northern-20230612-0026 | DU00002039656 |  |  |  |  | 2023-09-30 |  | MINI STRUCTURE
Q00004 | Q124F_Q00004OD_CB_SGLUMUT | Sarawak | 9054K | Swap |  | 2023Q4 | BY | Datasco | 4.6 TSSR Approved |  | 2023-06-19 | 2023-06-22 |  | 2023-06-24 |  | Closed | 2023-06-26 | 2023-07-26 | CD//John | 2023-07-25 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 - Copy | DU00002039657 |  |  | 2024-01-31 | 2023-12-13 |  | Tower | TOWER | 45 | Add R8852E S9000 x3 + R8894E M1821 x3
B00886 | B058C_B00886OD_TMNSRIANDALAS2 | Central |  | Decomm |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-06-02 |  |  |  | 2023-06-21 |  | 2023-06-22 | 2023-09-01 | CD//Ali Akaram | 2023-08-26 | Celcomdigi_RAN_Ascentrack_TSS_Central_20230606_0021 | DU00002039658 |  |  |  |  | 2023-07-21 |  | UNIPOLE
B02492 | B062B_B02492OD_JLNRIASGBESAR | Central |  | Decomm |  | 2023Q4 | MA | Magicell | 4.6 TSSR Approved |  | 2023-07-25 |  |  |  | 2023-07-26 |  | 2023-08-02 | 2023-10-20 | CD//Sapian | 2023-08-16 | CelcomDigi_RAN_Magicell_TSS_Central_20230727 | DU00002039659 |  |  |  |  | 2023-08-28 |  | LAMP_POLE
K00523 | K004B_K00523OD_TMNSABDHALIM | Northern |  | Decomm |  | 2023Q4 | ZA | GCI | 4.6 TSSR Approved |  | 2023-05-28 |  |  |  | 2023-06-24 |  | 2023-06-26 | 2024-04-23 | CD//Shamsul | 2023-07-06 | Celcom Digi_RAN-GCI-TSS-Northern-20230529-0022/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002039660 |  | No TX Info, Photo not enough 9/8: Need include Digi Equipment 22/8: Please include Antenna,ODU, FE for Link Digi to be Decom |  |  | 2023-10-16 |  | MONOPOLE
B00280 | B060B_B00280OD_KGPERMATANG | Central | 1069K | Swap |  | 2023Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2023-07-05 | 2023-07-06 |  | 2023-07-09 |  | Closed | 2023-07-10 | 2023-07-24 | CD//Sapian | 2023-07-24 | CelcomDigi_RANMW_AllStar_TSS_Central_20230703_0008 | DU00002039661 |  |  | 2023-08-23 | 2023-08-16 |  | Tower | 4LEGGED | 61 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
9715C | Senadin Industrial (EB) | Sarawak |  | Modernization |  | 2023Q4 | SH | Trintel | 4.6 TSSR Approved |  | 2023-06-17 | 2023-07-10 |  | 2023-07-14 |  | Closed | 2023-07-14 | 2023-08-02 | E// Zulakmar | 2023-07-31 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230622 | DU00002039662 |  |  | 2023-08-22 | 2023-08-18 |  | Pole | TOWER | 30m | Add R9264H M901821 x3,Dismantle R9224E M1821(AAB) x3
9764B | Kidurong Ind 2 (REL) | Sarawak |  | Modernization |  | 2023Q3 | BY | South Pacific | 4.6 TSSR Approved |  | 2023-05-16 | 2023-06-10 |  | 2023-06-14 |  | Closed | 2023-06-14 | 2023-06-24 | E//Hannah | 2023-06-23 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230512-0001 | DU00002039663 |  |  | 2023-07-16 | 2023-07-06 |  | Lampole | TOWER | 30m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
B00242 | B061C_B00242OD_PUTRAHEIGHT | Central |  | Decomm |  | 2023Q3 | MA | AllStar | 4.6 TSSR Approved |  | 2023-06-12 |  |  |  | 2023-06-19 |  | 2023-06-20 | 2023-09-01 | CD//Sapian | 2023-07-04 | CelcomDigi_RANMW_YPTT_TSS_Centra3l_20230612_000 | DU00002039664 |  |  |  |  | 2023-10-09 |  | TOWER
B00299 | B062B_B00299OD_VLPEKET60 | Central |  | Decomm |  | 2023Q4 | CR | Magicell | 4.6 TSSR Approved |  | 2023-06-06 |  |  |  | 2023-06-15 |  | 2023-07-21 | 2023-10-02 | CD//Norhaliza | 2023-08-18 | CelcomDigi_RAN_Magicell_TSS_Central_20230607_0012 | DU00002039665 |  | EXTRA IDU, CT5853 |  |  | 2023-08-18 |  | TOWER
B02741 | B061F_B02741OD_JLN61BDRTSKPUTRI3 | Central | 1169K | Swap |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-05-04 | 2023-05-06 |  | 2023-05-11 |  | Closed | 2023-05-13 | 2023-06-05 | CD//Tee | 2023-05-20 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230428_0015 | DU00002039666 |  |  | 2023-06-20 | 2023-06-16 |  | Lampole | LAMP_POLE | 18m | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
C00014 | C046C_C00014IB_GENTINGSTAFF3 | Central | 1187K | Swap |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-08-01 | 2023-08-02 |  | 2023-08-07 |  | Closed | 2024-12-23 | 2025-11-11 | CD//Sofiah | 2025-10-17 | CelcomDigi_RAN_GTSB_TSS_Central_20230802 | DU00002039667 |  |  | 2025-07-17 | 2025-07-08 |  | Portables BTS | BOOM | IBC | Add R8862A S1800 x2 + R8862A S2100 x2 + R8862A S2601 x2 ,Dismantle all celcom BBU&RRU
K00491 | K004A_K00491OD_TONGKANGYARD | Northern |  | Decomm |  | 2023Q4 | MH | GTSB | 4.6 TSSR Approved |  | 2023-05-29 |  |  |  | 2023-06-20 |  | 2023-06-21 | 2023-08-10 | CD//Rohizam | 2023-08-04 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230829-0032_V2/Celcom Digi_RAN-GTSB-TSS-Northern-20230529-0020 | DU00002039668 |  |  |  |  | 2023-09-29 |  | AESTHETIC MONOPOLE
B01803 | B061F_B01803OD_BBKUNDANG | Central |  | Decomm |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-05-10 |  |  |  | 2023-06-10 |  | 2023-06-13 | 2023-07-22 | CD//Tee | 2023-06-30 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230626_decom reraise | DU00002039669 |  |  |  |  | 2023-06-30 |  | TOWER
B01351 | B061A_B01351OD_PR_UITMKEJKIMIA | Central | 1121K | Swap |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-19 | 2023-07-04 |  | 2023-07-08 |  | Closed | 2023-07-14 | 2024-01-02 | CD//Norhaliza | 2024-01-02 | CelcomDigi_RAN_GTSB_TSS_Central_20230620_0030 | DU00002039670 |  |  | 2023-10-12 | 2023-10-09 |  | Lampole | LAMP_POLE | 32m | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x5,Dismantle Celcom all RRU&BBU |  | 13
B01654 | B061B_B01654OD_BLTNKAYANGAN | Central | 1132K | Swap |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-09-11 | 2023-09-20 |  | 2023-09-22 |  | Closed | 2023-09-25 | 2023-10-02 | CD//Sapian | 2023-10-01 | CelcomDigi_RAN_Datasco_TSS_Central_20230829_Modern+Decom | DU00002039671 |  |  | 2024-03-15 | 2024-03-04 |  | Lampole | LAMP_POLE | 20 | Add R8852E S9000 x3 + R8894E M1821 x3
B00507 | B062B_B00507OD_SGBESAR | Central |  | Decomm |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-06-09 |  |  |  | 2023-07-04 |  | 2023-07-26 | 2023-10-18 | CD//Sapian | 2023-08-04 | CelcomDigi_RANMW_Magicell_TSS_Central_20230612_0005 | DU00002039672 |  | EXTRA IDU |  |  | 2023-08-28 |  | MINI STRUCTURE
B01693 | B065B_B01693OD_T3_ROCKRESORT | Central | 1137K | Swap |  | 2023Q4 | SS | Futong | 4.6 TSSR Approved |  | 2023-07-07 | 2023-07-03 |  | 2023-07-07 |  | Closed | 2023-07-10 | 2023-07-17 | CD//Norhaliza | 2023-07-17 | CelcomDigi_RAN_Futong_TSS_Central_20230707_0009 | DU00002039673 |  |  | 2023-09-19 | 2023-09-15 |  | Tower | TOWER | 76 | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle Celcom all RRU&BBU |  | 3
9839A | Normah Medical Centre | Sarawak |  | Modernization |  | 2023Q4 | ZB | AllStar | 4.6 TSSR Approved |  | 2023-07-08 | 2023-07-05 |  | 2023-07-11 |  | Closed | 2023-09-20 | 2023-09-21 | E//Nazrul | 2023-09-20 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230608-0006 | DU00002039674 |  |  | 2023-10-26 | 2023-10-20 |  | Portables BTS | In-building system |  | Add R8862A S1800 x1 + R8862A S2100 x1,Dismantle R8882-GUL1812 x1
A01081 | A042B_A01081OD_LAKE_GARDEN_TPG | Northern |  | Decomm |  | 2023Q4 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-06-20 |  |  |  | 2023-06-26 |  | 2023-06-27 | 2023-08-15 | CD//Rohizam | 2023-08-04 | Celcom Digi_RAN-CCSMY- TSS-Northern-20230621-0027/Celcom Digi_RAN-CCSMY-TSS Decomm-Northern-20240131-0091 | DU00002039675 |  | No TX Info, Photo not enough |  |  | 2023-08-29 |  | AESTHETIC MONOPOLE
B00638 | B058B_B00638OD_BT2JLNKAPAR | Central |  | Decomm |  | 2023Q3 | MA | Datasco | 4.6 TSSR Approved |  | 2023-08-08 |  |  |  | 2023-08-19 |  | 2023-08-19 | 2023-10-18 | CD//Sapian | 2023-08-23 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002039676 |  |  |  |  | 2023-09-30 |  | TRIPOD
C00016 | C046C_C00016IB_RSC6GENTING | Central | 1188K | Swap |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-08-01 | 2023-08-02 |  | 2023-08-07 |  | Closed | 2023-08-10 | 2023-08-29 | CD//Sofiah | 2023-08-29 | CelcomDigi_RAN_GTSB_TSS_Central_20230802 | DU00002039677 |  |  | 2025-07-15 | 2025-07-15 |  | Portables BTS | BOOM | IBC | Add R8862A S1800 x1 + R8862A S2100 x1,Dismantle all celcom BBU&RRU
Q00704 | Q118B_Q00704ODA_SPGSIMILIJAU | Sarawak |  | Decomm |  | 2023Q3 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-10-26 |  |  |  | 2023-11-07 |  | 2023-11-08 | 2024-06-21 | CD//John | 2023-11-08 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 | DU00002039678 |  |  |  |  | 2024-07-25 |  | TOWER
B02694 | B065B_B02694OD_CB_KGMELAYUSERIGALAHULUBERNAM | Central | 1165K | Swap |  | 2023Q4 | HQ 1 | Magicell | 4.6 TSSR Approved |  | 2023-06-01 | 2023-06-02 |  | 2023-06-07 |  | Closed | 2023-06-15 | 2023-06-28 | CD//Sapian | 2023-06-15 | CelcomDigi_RAN_Magicell_TSS_Central_20230606_0011 | DU00002039679 |  |  | 2023-09-12 | 2023-09-07 |  | Tower | TOWER | 61 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
B00468 | B065B_B00468OD_BERNAMJAYA | Central |  | Decomm |  | 2023Q4 | BY | Ascentrack | 4.6 TSSR Approved |  | 2024-01-11 |  |  |  | 2024-02-20 |  | 2024-02-21 | 2024-05-29 | CD//Norhaliza | 2024-03-22 | Celcomdigi_RAN_Ascentrack_TSS_Central_20230616_0022 | DU00002039680 |  |  |  |  | 2023-09-24 |  | TOWER
B01086 | B061A_B01086OD_TMNMUTIARAKLG | Central |  | Decomm |  | 2023Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2023-05-29 | 2023-06-26 |  |  | 2023-05-31 |  | 2023-06-16 |  | CD//Sapian | 2023-06-30 | CelcomDigi_RAN_Magicell_TSS_Central_20230601_0011 / CelcomDigi_TX_Magicell_TSS_Decom_Central_20230714 | DU00002039681 |  | TSSR Rejected. Site currently running through TM LL |  |  | 2023-09-28 | Monopole | TOWER | 45
B00488 | B061F_B00488OD_PCKALAMHWY4 | Central |  | Decomm |  | 2023Q3 | AI | YPTT | 4.6 TSSR Approved |  | 2023-07-21 |  |  |  | 2023-07-24 |  | 2023-07-26 | 2023-10-18 | CD//Sapian | 2023-08-03 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002039682 |  |  |  |  | 2023-08-28 |  | 3LEGGED
B00197 | B057B_B00197OD_PEJDAERAHGOMBAK | Central |  | Decomm |  | 2023Q4 | AI | GCI | 4.6 TSSR Approved |  | 2023-09-04 |  |  |  | 2023-10-05 |  | 2023-10-05 | 2024-09-26 | CD//Ali akaram | 2023-10-11 | CelcomDigi_RAN_GCI_TSS_Central_20230905_Decom | DU00002039683 |  |  |  |  | 2023-10-05 |  | BOOM
Q00722 | Q132C_Q00722OD_JLNMURIA | Sarawak |  | Decomm |  | 2023Q4 | SH | Magicell | 4.6 TSSR Approved |  | 2023-06-20 |  |  |  | 2023-06-21 |  | 2023-07-25 | 2023-08-06 | CD//John | 2023-07-26 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002039684 |  |  |  |  | 2025-06-18 |  | MONOPOLE
P00090 | P035B_P00090OD_PULAUTIKUS | Northern | 4124K | Decomm | Swap->Decomm | 2023Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-05-17 | 2023-05-19 |  | 2023-05-25 | 2023-07-26 | Under Approval | 2023-06-07 | 2023-09-07 | CD//Affendi | 2023-06-13 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2/Celcom Digi_CD CONSOLIDATION-GTSB-TI-Northern-20240920_Old Contract | DU00002039685 |  | No TX Info, Photo not enough |  |  | 2023-09-15 |  | TRIPOD | 7
P00416 | P035C_P00416OD_PENANGROAD | Northern | 4145K | Swap |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-11 | 2023-06-12 |  | 2023-06-16 |  | Closed | 2023-07-03 | 2023-07-06 | CD//Affendi | 2023-07-04 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230509-0018 | DU00002039686 |  |  | 2023-08-30 | 2023-08-24 |  | Pole | BOOM | 2m, 3m | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 2
B02437 | B061C_B02437OD_KEMUNINGUTAMAANGGERIK | Central |  | Decomm |  | 2023Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-07-23 |  |  |  | 2023-07-24 |  | 2023-07-26 | 2023-08-18 | CD//Sapian | 2023-08-14 | CelcomDigi_RAN_Allstar_TSS_Central_20230721 | DU00002039687 |  |  |  |  | 2023-08-05 |  | BOOM
B02480 | B060A_ B02480OD_WTUNISEL | Central | 1158K | Swap |  | 2023Q3 | YZ | GTSB | 4.6 TSSR Approved |  | 2023-05-01 | 2023-05-10 |  | 2023-05-13 |  | Closed | 2023-05-15 | 2023-06-06 | CD//Tee | 2023-05-28 | CelcomDigi_RAN_GTSB_TSS_20230505_0023 | DU00002039688 |  |  | 2023-07-13 | 2023-07-13 |  | Pole | POLE | 4 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
Q00711 | Q132C_Q00711OD_TMNYAKIN | Sarawak |  | Decomm |  | 2023Q4 | ZB | AllStar | 4.6 TSSR Approved |  | 2023-06-28 |  |  |  | 2023-06-28 |  | 2023-07-26 | 2023-10-04 | CD//John | 2023-07-28 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230608-0006 | DU00002039689 |  | 21/8: ALL TX info & photos are missing |  |  | 2025-01-25 |  | MONOPOLE
K00681 | K004A_K00681OD_TMNNURIAS | Northern |  | Decomm |  | 2023Q4 | MH | CCSMY | 4.6 TSSR Approved |  | 2023-05-25 |  |  |  | 2023-06-21 |  | 2023-06-23 | 2023-08-28 | CD//QUAH | 2023-07-20 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230529-0020/Celcom Digi_RAN-CCSMY-TSS Decomm-Northern-20240131-0091 | DU00002039690 |  |  |  |  | 2023-09-30 |  | RAPID ASSEMBLY POLE (RAPOLE)
B00408 | B058B_B00408OD_PDGJAWA | Central |  | Decomm |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-07-20 |  |  |  | 2023-08-08 |  | 2023-08-09 | 2023-10-18 | CD//Norhaliza | 2023-10-13 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230721 | DU00002039691 |  | additional E// & NEC link |  |  | 2024-08-17 |  | TOWER
B00278 | B060B_B00278OD_KGKUANTAN | Central |  | Decomm | Decomm->On Hold->Decomm | 2023Q4 | CR | YPTT | 4.6 TSSR Approved |  | 2023-07-28 |  |  |  | 2023-08-03 |  | 2023-08-04 | 2025-05-27 | CD//Sapian | 2025-05-08 | CelcomDigi_RAN_YPTT_TSS_Central_20230729 | DU00002039692 |  |  |  |  | 2023-12-31 |  | TOWER
B01080 | B061A_B01080OD_PR_UITMKJUTRAN | Central |  | Decomm |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-07 |  |  |  | 2023-08-16 |  | 2023-08-17 | 2023-12-19 | CD//Sapian | 2023-08-18 | CelcomDigi_RAN_GTSB_TSS_Central_20230606_0027 | DU00002039693 |  |  |  |  | 2023-10-22 |  | AESTHETIC MONOPOLE
B02620 | B057B_B02620OD_JLNJASA25_TMNJASA_SLYG | Central | 1162K | Swap |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-18 |  | 2023-05-26 |  | Closed | 2023-05-30 | 2023-06-06 | CD//Sapian | 2023-06-01 | CelcomDigi_RAN_GTSB_TSS_Cental_20230511_0024 | DU00002039694 |  |  | 2023-08-18 | 2023-08-10 |  | Lampole | LAMP_POLE | 24 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle Celcom all RRU&BBU | 12
B02044 | B062A_B02044OD_MN_TJGMEDAN | Central | 1013P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN->Swap | 2026 | AI | GCI | 4.6 TSSR Approved |  | 2025-12-11 | 2025-12-18 |  | 2025-12-30 |  | Closed | 2026-01-05 | 2026-01-23 |  | 2026-01-21 |  | DU00002039695 |  |  | 2026-04-17 | 2026-04-17 |  | Tower | TOWER | 76m | Add R8852E S9000 x6+R9264M M1821 x4 |  | 1
C00003 | C046C_C00003OD_KM17GENTING | Central |  | Decomm |  | 2023Q4 | CR | Magicell | 4.6 TSSR Approved |  | 2023-08-04 |  |  |  | 2023-08-07 |  | 2023-08-08 | 2024-06-25 | CD//Norhaliza | 2023-08-18 | CelcomDigi_RAN_Magicell_TSS_Central_20230808 | DU00002039696 |  |  |  |  | 2024-03-15 |  | MONOPOLE
Q00739 | Q132A_Q00739OD_GAYANIS | Sarawak | 9078K | Swap |  | 2023Q3 | SH | YPTT | 4.6 TSSR Approved |  | 2023-11-30 | 2023-12-08 |  | 2023-12-19 |  | Closed | 2023-12-20 | 2024-01-18 | CD//John | 2024-01-16 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20230608-0005 | DU00002039697 |  |  | 2024-04-19 | 2024-04-03 |  | Minaret | GUYED MAST | 45m | Add R9264H M901821 x3,Dismantle |  | 3
B00646 | B062B_B00646OD_SGNIBONGHOT | Central | 1091K | Swap |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-06-14 | 2023-07-05 |  | 2023-07-07 |  | Closed | 2023-07-25 | 2023-07-29 | CD//Sapian | 2023-07-29 | CelcomDigi_RAN_Magicell_TSS_Central_20230616_0013 | DU00002039698 |  |  | 2023-11-07 | 2023-10-10 |  | Tower | TOWER | 105.6m | Add R8852E S9000 x3 + A9732 M1821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 123
B02822 | B058B_B02822OD_TMNTELUKPULAUINDAHKLG | Central | 1210K | Swap | Decomm->Swap | 2023Q3 | SS | GCI | 4.6 TSSR Approved |  | 2023-10-02 | 2023-09-27 |  | 2023-10-04 |  | Closed | 2023-10-04 | 2023-10-06 | CD//Sapian | 2023-10-06 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240302-reraise missing item | DU00002039699 |  | Missing FE part | 2023-11-16 | 2023-10-21 |  | Monopole | RAPID ASSEMBLY POLE (RAPOLE) | 30 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle
P00329 | P035F_P00329OD_MAJESTICHEIGHT | Northern |  | Decomm |  | 2023Q3 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-05-19 |  |  |  | 2023-06-16 |  | 2023-06-19 | 2023-07-28 | CD//Affendi | 2023-06-27 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002039700 |  |  |  |  | 2023-09-18 |  | TOWER
P00654 | P031B_P00654IB_PENANG_INTERNATIONAL_AIRPORT_ID | Northern |  | Decomm |  | 2023Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-06-27 |  |  |  | 2023-07-27 |  | 2023-07-17 | 2023-09-07 | CD//Quah | 2023-08-02 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2 | DU00002039701 |  |  |  |  | 2023-09-15 |  | IN-BUILDING
A01240 | KG REPOH | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039702 | [6 empty] | TOWER
B01368 | B065B_B01368OD_T3_KGJAWAKRLING | Central | 1123K | Swap |  | 2023Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-06-23 | 2023-06-28 |  | 2023-07-06 |  | Closed | 2023-07-08 | 2023-07-17 | CD//Norhaliza | 2023-07-17 | CelcomDigi_RANMW_Ascentrack_TSS_Central_20230623_0007 | DU00002039703 |  |  | 2023-09-27 | 2023-09-22 |  | Tower | TOWER | 75 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
B00288 | B060B_B00288OD_BPMSGBULOH | Central |  | Decomm |  | 2023Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-29 |  |  |  | 2024-05-03 |  | 2023-08-02 | 2024-01-30 | CD//Norhaliza | 2023-09-18 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002039704 |  |  |  |  | 2023-10-04 |  | BOOM
P00059 | P031A_P00059OD_BKTSEGENTING | Northern |  | Decomm |  | 2023Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-05-25 |  |  | 2023-07-14 |  | Closed | 2023-07-27 | 2025-10-01 | CD//Quah | 2023-08-06 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002039705 |  |  |  |  | 2023-08-15 |  | TOWER
9635B | Bintulu LNG | Sarawak |  | Modernization |  | 2023Q3 | BY | South Pacific | 4.6 TSSR Approved |  | 2023-07-31 | 2023-08-03 |  | 2023-08-09 |  | Closed | 2023-08-10 | 2023-09-01 | E//Hannah | 2023-09-01 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230512-0001 | DU00002039706 |  |  | 2023-09-22 | 2023-09-13 |  | Monopole | Tower | 30m | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 1
Q00330 | Q132B_Q00330OD_SPGTUDAN | Sarawak |  | Decomm |  | 2023Q4 | SH | Magicell | 4.6 TSSR Approved |  | 2023-07-07 |  |  |  | 2023-07-13 |  | 2023-07-25 | 2023-08-06 | CD//John | 2023-07-26 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002039707 |  |  |  |  | 2025-01-19 |  | TOWER
B01320 | B061A_B01320OD_PR_SEK7SHLM | Central |  | Decomm |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-19 |  |  |  | 2023-10-06 |  | 2023-10-07 | 2024-10-29 | CD//Norhaliza | 2023-10-31 | CelcomDigi_RAN_GTSB_TSS_Central_20230620_0030 | DU00002039708 |  |  |  |  | 2023-10-22 |  | BOOM
K00065 | K004A_K00065OD_JALANGANGSA | Northern | 4088K | Swap |  | 2023Q4 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-31 | 2023-06-07 |  | 2023-06-14 |  | Closed | 2023-06-21 | 2023-08-22 | CD//Quah | 2023-08-22 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002039709 |  |  | 2023-09-25 | 2023-09-23 |  | In-Building System | TRIPOD | 5 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x5,Dismantle Celcom all RRU&BBU |  | 12
B02488 | B061C_B02488OD_JLNSGTERAPSEK32SALAM | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-06-27 |  |  |  | 2023-07-20 |  | 2023-07-25 | 2023-08-09 | CD//Ali akaram | 2023-08-03 | CelcomDigi_RAN_YPTT_TSS_Central_20230628_0011 | DU00002039710 |  |  |  |  | 2023-08-01 |  | LAMP_POLE
A00010 | A039B_A00010OD_CB_PONDOKTANJUNG | Northern |  | Decomm | Decomm->On Hold->Decomm | 2023Q4 | ZA | YPTT | 4.6 TSSR Approved |  | 2023-06-09 |  |  |  | 2023-07-05 |  | 2023-07-07 | 2023-08-24 | CD//Affendi | 2023-07-12 | Celcom Digi_RAN-YPTT-TSS Decomm-Northern-20230720-0025/Celcom Digi_RAN-YPTT-TSS-Northern-20230612-0019 | DU00002039711 |  | No TX Info, Photo not enough 11/8: Need include Antenna NE info |  |  | 2023-12-27 |  | TOWER
B02274 | B061F_B02274OD_SURAUARRAHIMAHSEK2PALAM | Central | 1152K | Swap |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-16 |  | 2023-05-19 |  | Closed | 2023-05-19 | 2023-06-05 | CD//Sapian | 2023-06-01 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002039712 |  |  | 2023-08-10 | 2023-07-31 |  | Monopole | MONOPOLE | 24 m | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle Celcom all RRU&BBU |  | 1
B01797 | B058B_B01797OD_RD_TMNANDALASJY | Central |  | Decomm |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-07-07 |  |  |  | 2023-07-18 |  | 2023-07-22 | 2023-08-10 | CD//Sapian | 2023-08-02 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230626_decom reraise | DU00002039713 |  | RESUBMISSION - 1. Please provide clear label photo of NE IDU. 2. Please provide ODU label photo if available 3. Missing FE IDU photo. please check correct cabinet 4. Please provide ODU photo for FE |  |  | 2023-07-11 |  | BOOM
B02800 | B061D_B02800OD_JLNPAHATSEK15SHLM | Central |  | Decomm |  | 2023Q4 | SS | Solusi | 4.6 TSSR Approved |  | 2023-10-09 |  |  | 2023-10-13 | 2024-08-08 | Under Approval | 2023-10-13 |  | CD//Ali Akaram | 2023-10-17 | CelcomDigi_RAN_Solusi_TSS_Central_20231011 | DU00002039714 |  | Missing FE part |  |  | 2023-10-09 |  | TRIPOD
P00359 | P035F_P00359OD_CKTBKTGAMBIR | Northern |  | Decomm |  | 2023Q3 | SM | GCI | 4.6 TSSR Approved |  | 2023-05-11 |  |  |  | 2023-08-17 |  | 2023-08-17 | 2024-06-19 | CD//Quah | 2023-09-01 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002039715 |  | 15/9 - SOW change to dismantle digi microwave and relocate celcom fiber as requested by CD planner |  |  | 2023-08-04 |  | MONOPOLE
9927A | Celcom Permy Jaya | Sarawak |  | Modernization |  | 2023Q4 | SHA | Datasco | 4.6 TSSR Approved |  | 2023-06-13 | 2023-06-21 |  | 2023-06-28 |  | Closed | 2024-11-14 | 2024-12-05 | E//Hannah | 2025-03-20 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230614-0010 | DU00002039716 | Remarks: Solution TSSR/BOM Changed |  | 2025-04-27 | 2025-04-22 |  | Tower | Tower | 45m | Add R9264M M1821x3, Dismantle R8894E M1821(A8A)x3 | 0 | 0
B02003 | B058E_B02003OD_SYABASSAUJANAPUTRA | Central |  | Decomm |  | 2023Q3 | SY1 | Solusi | 4.6 TSSR Approved |  | 2023-04-27 |  |  | 2023-08-01 | 2024-08-27 | Closed | 2024-08-28 | 2024-01-30 | CD//Sapian | 2024-09-04 | CelcomDigi_RANMW_Solusi_TSS_Central_20230609_0002 | DU00002039717 |  |  |  |  | 2023-08-29 |  | WATER TANK
P00212 | P035C_P00212OD_TMPGCENTRAL | Northern | 4131K | Swap |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-31 | 2023-06-07 |  | 2023-06-09 |  | Closed | 2023-06-13 | 2023-06-17 | CD//Affendi | 2023-06-15 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0014 | DU00002039718 |  |  | 2023-09-15 | 2023-08-29 |  | Tower | 4LEGGED | 94 | Add R8852E S9000 x3 + R8894E M1821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
B00807 | B061A_B00807OD_PR_SEK8SA | Central |  | Decomm |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-08-08 |  |  |  | 2023-08-09 |  | 2023-08-10 | 2023-12-19 | CD//Sapian | 2023-08-18 | CelcomDigi_RAN_Datasco_TSS_Central_20230802 | DU00002039719 |  |  |  |  | 2023-10-30 |  | MINARET
B01703 | B061B_B01703OD_JLNBOLINGPDGSHLM | Central |  | Decomm |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-06-23 |  |  |  | 2023-08-03 |  | 2023-08-08 | 2023-12-21 | CD//Ali Akaram | 2023-08-16 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_0030 | DU00002039720 |  |  |  |  | 2023-12-19 |  | BOOM WALL-MOUNTED
B00211 | B057B_B00211OD_SLYGBARU3 | Central |  | Decomm |  | 2023Q4 | SS | YPTT | 4.6 TSSR Approved |  | 2023-09-08 |  |  |  | 2023-09-13 |  | 2023-09-14 | 2024-01-22 | CD//Sapian | 2023-09-16 | CelcomDigi_RAN_YPTT_TSS_Central_20231005 | DU00002039721 |  |  |  |  | 2023-09-27 |  | MINI STRUCTURE
B00842 | B061B_B00842IB_GIANTSEK13SHLM | Central | 1102K | Swap |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-07-31 | 2023-07-18 |  | 2023-08-17 |  | Closed | 2023-08-17 | 2023-08-29 | CD//Sofiah | 2023-08-29 | CelcomDigi_RAN_Datasco_TSS_Central_20230802 | DU00002039722 |  |  | 2023-09-28 | 2023-09-27 |  | Portables BTS | IN-BUILDING |  | Add R8862A S1800 x1 + R8862A S2100 x1,Dismantle all celcom BBU&RRU
B02795 | B061A_B02795OD_MERUINDPARK2 | Central | 1173K | Swap |  | 2023Q3 | IE | Magicell | 4.6 TSSR Approved |  | 2023-05-15 | 2023-05-17 |  | 2023-05-19 |  | Closed | 2023-05-30 | 2023-06-03 | CD//Sapian | 2023-06-02 | CelcomDigi_RANMW_Magicell_TSS_Central_20230517_0002 | DU00002039723 |  |  | 2023-08-23 | 2023-07-22 |  | Lampole | RAPID ASSEMBLY POLE (RAPOLE) | 30 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x5,Dismantle Celcom all RRU&BBU |  | 12
B00164 | B061A_B00164OD_UITMCEMPAKA | Central |  | Decomm |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-01 |  |  |  | 2023-07-24 |  | 2023-07-24 | 2023-12-20 | CD//Norhaliza | 2023-09-18 | CelcomDigi_RAN_GTSB_TSS_Central_20230606_0027 | DU00002039724 |  |  |  |  | 2023-11-02 |  | MONOPOLE
B01828 | B065B_B01828OD_RD_BTGKALI | Central |  | Decomm |  | 2023Q4 | SS | Futong | 4.6 TSSR Approved |  | 2023-07-20 |  |  |  | 2023-08-08 |  | 2023-08-10 | 2024-01-22 | CD//Norhaliza | 2023-08-18 | CelcomDigi_RAN_Futong_TSS_Central_20230721 | DU00002039725 |  |  |  |  | 2023-12-04 |  | TOWER
B00058 | B061F_B00058OD_BDRTSKPUTRI3 | Central |  | Decomm |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-06-03 |  |  |  | 2023-12-07 |  | 2023-12-08 |  | CD//Sapian | 2023-12-20 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230626_decom reraise | DU00002039726 |  | Missing FE part |  |  | 2023-12-19 |  | 3LEGGED
B00682 | B058A_B00682OD_BKTASMARA | Central |  | Decomm |  | 2023Q3 | MA | Magicell | 4.6 TSSR Approved |  | 2023-06-15 |  |  |  | 2023-07-04 |  | 2023-08-03 | 2023-12-20 | CD//Norhaliza | 2023-09-20 | CelcomDigi_RAN_Magicell_TSS_Central_20230616_0013 | DU00002039727 |  | This is CP site. Please include all existing Tx equipment(Fiber & IDU) photo inside cabin. Please include label photo as well. |  |  | 2023-09-20 |  | TOWER
B02823 | B062A_B02823ODA_JLNPDGSBKBERNAM | Central | 1178K | Swap |  | 2023Q4 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-06-20 | 2023-06-30 |  | 2023-07-07 |  | Closed | 2023-07-11 | 2023-08-02 | CD//Sapian | 2023-08-02 | CelcomDigi_RANMW_CCSMY_TSS_Central_20230620_0002 | DU00002039728 |  |  | 2023-09-15 | 2023-09-07 |  | Tower | TOWER | 46m | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 13
P00327 | P031B_P00327OD_KRISTAL_POINT | Northern |  | Decomm |  | 2023Q3 | ZA | YPTT | 4.6 TSSR Approved |  | 2023-07-03 |  |  |  | 2023-07-18 |  | 2023-07-20 | 2023-08-08 | CD//Rohizam | 2023-08-04 | Celcom Digi_RAN-YPTT-TSS-Northern-20230609-0018 | DU00002039729 |  |  |  |  | 2023-08-25 |  | UNIPOLE
B00203 | B058A_B00203OD_VLKGPEREPAT | Central |  | Decomm |  | 2023Q3 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-05-30 |  |  | 2023-06-12 | 2023-06-26 | Rectificating | 2023-06-20 | 2023-08-19 | CD//Tee | 2023-07-22 | CelcomDigi_RAN_CCSMY_TSS_Central_20230626_decom reraise | DU00002039730 |  |  |  |  | 2023-08-28 |  | TOWER
A00651 | A042B_A00651OD_TMNSAUJANAJAYA | Northern | 4075K | Site Out (Swap) | Swap->Site out->Replacement, Site Out (Swap) | 2023Q4 | HQ 1 | NR services | 4.6 TSSR Approved |  | 2023-05-30 | 2023-06-09 |  | 2023-06-13 |  | Closed | 2023-06-20 | 2023-07-13 | CD//Quah | 2023-07-13 | Celcom Digi_RAN-YPTT-TSS-Northern-20230531-0015 | DU00002039731 | [5 empty] | Tower | TOWER | 28
9670A | Parkcity commercial | Sarawak |  | Modernization |  | 2023Q3 | BY | AllStar | 4.6 TSSR Approved |  | 2023-05-23 | 2023-05-24 |  | 2023-06-13 |  | Closed | 2023-06-14 | 2023-06-28 | E//Hannah | 2023-06-20 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230516-0005 | DU00002039732 |  |  | 2023-07-31 | 2023-07-21 |  |  | 3m Bipod (RT) | 3 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 13
B00549 | B061B_B00549OD_PR_BKTJELUTONG | Central |  | Decomm |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-06-14 |  |  |  | 2023-09-21 |  | 2023-09-22 | 2024-05-31 | CD//Sapian | 2023-10-26 | CelcomDigi_RAN_Datasco_TSS_Central_20230616_0026 | DU00002039733 |  |  |  |  | 2023-12-20 |  | TOWER
P00363 | P035F_P00363OD_USMCANSELORI | Northern | 4139K | Swap |  | 2023Q3 | SM | YPTT | 4.6 TSSR Approved |  | 2023-05-22 | 2023-05-24 |  | 2023-05-26 |  | Closed | 2023-05-30 | 2023-06-08 | CD//Affendi | 2023-06-09 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0009 | DU00002039734 |  |  | 2023-07-25 | 2023-07-18 |  | Pole | BOOM | 4m | Add R8852E S9000 x3 + R8894E M1821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
A00191 | A042A_A00191OD_KGJELAI | Northern |  | Decomm |  | 2023Q4 | SM | YPTT | 4.6 TSSR Approved |  | 2023-06-09 |  |  |  | 2023-08-01 |  | 2023-08-02 | 2024-03-26 | CD//Rohizam | 2023-08-02 | Celcom Digi_RAN-YPTT-TSS Decomm-Northern-20230720-0025/Celcom Digi_RAN-YPTT-TSS-Northern-20230612-0019 | DU00002039735 |  | 11/9: FE photo wrong, please fill info in NE,IDU,Dismantle part 24/1:Wrong NE Info and photo, Wrong Fe Info Photo |  |  | 2023-08-25 |  | TOWER
A01153 | A042B_A01153OD_KAMUNTINGRAYAIND | Northern | 4081K | Swap |  | 2023Q4 | SM | YPTT | 4.6 TSSR Approved |  | 2023-07-30 | 2023-07-25 |  | 2023-07-30 |  | Rectificating | 2023-07-31 | 2023-08-03 | CD//Quah | 2023-08-02 | Celcom Digi_RAN-YPTT- TSS-Northern-20230626-0022 | DU00002039736 |  |  | 2023-08-17 | 2023-08-17 |  | Monopole | MONOPOLE | 46m | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 13
B01841 | B061G_B01841OD_WTTMNBKTSUBANG | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-27 |  |  |  | 2023-05-31 |  | 2023-06-06 | 2023-09-19 | CD//Sapian | 2023-06-08 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002039737 |  |  |  |  | 2023-09-05 |  | MONOPOLE
K00526 | K004A_K00526OD_SPG4TMNSELAYANG | Northern |  | Decomm |  | 2023Q4 | SM | YPTT | 4.6 TSSR Approved |  | 2023-06-12 |  |  |  | 2023-07-18 |  | 2023-07-20 | 2023-08-08 | CD//Rohizam | 2023-08-04 | Celcom Digi_RAN-YPTT-TSS-Northern-20230613-0020 | DU00002039738 |  |  |  |  | 2023-10-27 |  | LAMP_POLE
B00044 | B058B_B00044OD_BT1JLNKAPAR | Central |  | Decomm |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-08-08 |  |  |  | 2023-08-10 |  | 2023-08-11 | 2023-10-18 | CD//Norhaliza | 2023-09-26 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002039739 |  |  |  |  | 2023-09-30 |  | BOOM
Q00105 | Q124B_Q00105OD_JLNSEMARAKKCH | Sarawak |  | Decomm |  | 2023Q4 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-06-16 |  |  |  | 2023-06-22 |  | 2023-07-25 | 2023-09-07 | CD//John | 2023-07-28 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002039740 |  |  |  |  | 2023-10-02 |  | MONOPOLE
9969A | Padang Kerbau (REL) | Sarawak |  | Modernization |  | 2023Q4 | SH | YPTT | 4.6 TSSR Approved |  | 2023-07-03 | 2023-06-21 |  | 2023-07-03 |  | Closed | 2023-07-04 | 2023-07-14 | E//Yadav | 2023-07-14 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20230622 | DU00002039741 |  |  | 2023-08-11 | 2023-08-07 |  | Monopole | 30M Rapole | 30 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
B01439 | B061A_B01439OD_SEK73SHLM | Central |  | Decomm |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-05-29 |  |  |  | 2024-05-03 |  | 2023-07-13 | 2024-01-30 | CD//Ali akaram | 2023-07-27 | CelcomDigi_RAN_GTSB_TSS_Central_20230601_0026 | DU00002039742 |  |  |  |  | 2023-10-05 |  | TRIPOD
P00190 | P035B_P00190IB_MIDLANDPARK | Northern |  | Decomm |  | 2023Q3 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-05-19 |  |  |  | 2023-08-08 |  | 2024-01-30 | 2023-09-18 | CD//Quah | 2024-02-05 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002039743 |  |  |  |  | 2023-11-30 |  | IN-BUILDING
K00222 | K004A_K00222OD_ALORMERAH | Northern | 4093K | Swap |  | 2023Q4 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-06-13 | 2023-06-16 |  | 2023-06-20 |  | Closed | 2023-06-26 | 2023-08-04 | CD//Rohizam | 2023-08-04 | Celcom Digi_RAN-GCI-TSS-Northern-20230613-0027 | DU00002039744 |  |  | 2023-09-19 | 2023-09-09 |  | Tower | GUYED MAST | 19 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 1
9630B | Hillstone Miri | Sarawak |  | Modernization |  | 2023Q4 | SH | Trintel | 4.6 TSSR Approved |  | 2023-06-15 | 2023-06-21 |  | 2023-06-27 |  | Closed | 2023-06-30 | 2023-07-10 | E//SoonHo | 2023-07-10 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230622 | DU00002039745 |  |  | 2023-09-12 | 2023-07-28 |  | Monopole | 30m Rapole | 30m | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
B00971 | B057C_B00971OD_TMGOMBAK | Central | 1106K | Swap |  | 2023Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2024-01-17 | 2024-01-18 |  | 2024-01-19 |  | Under Approval | 2024-01-22 | 2024-07-15 | CD//Norhaliza | 2024-07-12 | CelcomDigi_RAN_Allstar_TSS_Central_20240124 | DU00002039746 |  |  | 2024-03-26 | 2024-03-06 |  |  | BOOM | 6 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 23
A01198 | T3_0628_Kg Sg Siputeh | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039747 | [6 empty] | TOWER
Q00286 | Q118B_Q00286ODA_SGPLAN | Sarawak |  | Decomm |  | 2023Q3 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-07-31 |  |  |  | 2023-07-31 |  | 2023-08-03 | 2023-09-11 | CD//John | 2023-08-03 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230913 | DU00002039748 |  | 1/9: uncompleted info |  |  | 2025-02-08 |  | RAPID ASSEMBLY POLE (RAPOLE)
Q00242 | Q118A_Q00242OD_PBSMBTU | Sarawak | 9060K | Swap |  | 2023Q3 | SH | AllStar | 4.6 TSSR Approved |  | 2023-05-19 | 2023-05-26 |  | 2023-06-15 |  | Closed | 2023-06-27 | 2023-06-28 | CD//John | 2023-06-27 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230516-0005 | DU00002039749 |  |  | 2023-09-06 | 2023-09-03 |  | Guide mast | BOOM | 8 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle Celcom all RRU&BBU | 13
B00263 | B057B_B00263OD_TMNSLYGSEGAR | Central |  | Decomm |  | 2023Q4 | SS | YPTT | 4.6 TSSR Approved |  | 2023-10-31 |  |  |  | 2023-11-03 |  | 2023-11-07 |  | CD//Ali akaram | 2023-11-16 | CelcomDigi_RAN_YPTT_TSS_Central_20231101 | DU00002039750 |  | Missing FE Part |  |  | 2023-12-28 |  | MINI STRUCTURE
B01129 | B065B_B01129OD_CB_KGPERTAK | Central | 1021P | Swap |  | 2023Q4 | SS | Futong | 4.6 TSSR Approved |  | 2023-06-28 | 2023-06-30 |  | 2023-07-03 |  | Closed | 2023-07-06 | 2023-08-10 | CD//Ali akaram | 2023-08-10 | CelcomDigi_RAN_Futong_TSS_Central_20230630_0006 | DU00002039751 |  |  | 2023-09-19 | 2023-09-17 |  | Tower | TOWER | 76 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
B02454 | B060B_B02454OD_KGBARUKUALASNGORSCT | Central |  | Decomm |  | 2023Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2023-06-14 |  |  |  | 2023-06-15 |  | 2023-07-27 | 2023-11-29 | CD//Sapian | 2023-08-04 | CelcomDigi_RAN_Allstar_TSS_Central_20230616_0012 | DU00002039752 |  |  |  |  | 2023-08-29 |  | MONOPOLE
B00056 | B061C_B00056OD_TMNBKTRIMAU | Central |  | Decomm |  | 2023Q3 | IE | AllStar | 4.6 TSSR Approved |  | 2023-06-13 |  |  |  | 2023-06-19 |  | 2023-07-18 | 2023-10-18 | CD//Norhaliza | 2023-10-05 | CelcomDigi_RAN_Allstar_TSS_Central_20230616_0012 | DU00002039753 |  | Pls state in the TP to re-engineer traffic at 1435B for all child site T-1 before dismantle |  |  | 2023-07-21 |  | MONOPOLE
A00796 | A042A_A00796OD_MN_TJGLENGKONG | Northern | 4209P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039754 | [6 empty] | TOWER
K00376 | K004A_K00376OD_HSBAS | Northern | 4096K | Swap |  | 2023Q4 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-06-22 | 2023-06-26 |  | 2023-06-27 |  | Closed | 2023-07-03 | 2023-08-04 | CD//Rohizam | 2023-08-04 | Celcom Digi_RAN-GCI-TSS-Northern-20230623-0034 | DU00002039755 |  |  | 2023-09-15 | 2023-09-09 |  | Monopole | LAMP_POLE | 30 | Add R9264H M901821 x3 + R9264M M1821 x3 + R8862A S2601 x6,Dismantle Celcom all RRU&BBU |  | 123
P00569 | P035C_P00569OD_LEBUHLIGHT | Northern |  | Decomm |  | 2023Q3 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-08-04 |  |  |  | 2023-08-04 |  | 2023-08-09 | 2023-09-25 | CD//Affendi | 2023-08-17 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002039756 |  | 21/8: Wrong SOW |  |  | 2023-09-05 |  | BOOM
B00470 | B061C_B00470OD_BT4JLNKEBUN | Central |  | Decomm |  | 2023Q3 | SS | Futong | 4.6 TSSR Approved |  | 2023-05-30 |  |  | 2023-06-03 | 2024-05-06 | Closed | 2023-07-26 | 2023-10-17 | CD//Sapian | 2023-08-04 | CelcomDigi_RAN_Futong_TSS_Central_20230626_decom reraise/CelcomDigi_TX_Futong_TSS_Decom_Central_20230922 | DU00002039757 |  |  |  |  | 2023-09-08 |  | TRIPOD
B00027 | B061G_B00027OD_TMNBKTSUBANG2 | Central | 1065K | Swap |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-12 |  | 2023-05-17 |  | Closed | 2023-05-18 | 2023-06-05 | CD//Ali akaram | 2023-05-26 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002039758 |  |  | 2023-08-24 | 2023-08-16 |  | Pole | BOOM | 5m | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
Q00243 | Q118B_Q00243OD_CB_JLNNYABAU | Sarawak |  | Decomm |  | 2023Q3 | ZB | Satellite | 4.6 TSSR Approved |  | 2023-06-27 |  |  |  | 2023-07-08 |  | 2023-08-15 | 2024-02-15 | CD//John | 2023-08-17 | Celcom Digi_RAN-Satellite-TSS-Sarawak-20231009 | DU00002039759 |  | Wrong drawing attached |  |  | 2023-12-08 |  | TOWER
K00101 | K004A_K00101OD_JLNDTKKUMBAR | Northern |  | Decomm |  | 2023Q4 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-05-29 |  |  |  | 2023-07-21 |  | 2023-07-24 | 2023-08-19 | CD//Quah | 2023-08-17 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230829-0032/Celcom Digi_RAN-GTSB-TSS-Northern-20230529-0020 | DU00002039760 |  |  |  |  | 2023-10-04 |  | TOWER
B02925 | B061B_B02925OD_PSRANGERBANGUTAMA | Central | 1184K | Swap |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-05-27 | 2023-05-26 |  | 2023-05-29 |  | Closed | 2023-05-30 | 2023-06-05 | CD//Sapian | 2023-06-02 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002039761 |  |  | 2023-08-24 | 2023-08-16 |  | Lampole | LAMP_POLE | 19 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
B01344 | B061C_B01344OD_PR_BKTNAGA | Central |  | Decomm |  | 2023Q3 | IE | GCI | 4.6 TSSR Approved |  | 2023-10-10 |  |  |  | 2024-07-01 |  | 2023-10-16 | 2024-11-26 | CD//Sapian | 2023-10-23 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240302-reraise missing item | DU00002039762 |  |  |  |  | 2023-09-19 |  | TOWER
B00472 | B058B_B00472OD_KGDELEK | Central |  | Decomm |  | 2023Q3 | MA | Futong | 4.6 TSSR Approved |  | 2023-08-23 |  |  | 2024-05-06 | 2024-05-06 | Under Approval | 2023-08-19 | 2023-12-21 | CD//Sapian | 2023-08-23 | CelcomDigi_RAN_Futong_TSS_Central_20230626_decom reraise/CelcomDigi_TX_Futong_TSS_Decom_Central_20230922 | DU00002039763 |  |  |  |  | 2023-09-14 |  | MINARET
B00436 | B061D_B00436OD_SEK152SHLM | Central |  | Decomm |  | 2023Q4 | CR | GCI | 4.6 TSSR Approved |  | 2023-12-15 |  |  |  | 2023-12-18 |  | 2023-12-21 | 2024-02-15 | CD//Ali Akaram | 2024-01-02 | CelcomDigi_RAN_GCI_TSS_Central_20231224 | DU00002039764 |  |  |  |  | 2024-06-12 |  | TOWER
9732B | Vista Perdana (REL) | Sarawak |  | Modernization |  | 2023Q4 | SH | Trintel | 4.6 TSSR Approved |  | 2023-06-13 | 2023-07-07 |  | 2023-07-12 |  | Closed | 2023-07-12 | 2023-07-21 | E//Hannah | 2023-07-21 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230614-0010 | DU00002039765 |  |  | 2023-08-25 | 2023-08-18 |  | Monopole | TOWER | 30m | Add R9264H M901821 x4,Dismantle R8894E M1821(A8A) x4
B01805 | B057B_B01805OD_SLYGBARU2 | Central |  | Decomm |  | 2023Q4 | CR | YPTT | 4.6 TSSR Approved |  | 2023-07-26 |  |  |  | 2023-07-31 |  | 2023-07-27 | 2023-11-29 | CD//Ali Akaram | 2023-08-26 | CelcomDigi_RAN_YPTT_TSS_Central_20230725 | DU00002039766 |  |  |  |  | 2023-09-26 |  | BOOM
B02013 | B061G_B02013OD_SURAUCAHAYASPK | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-18 |  |  | 2023-05-22 | 2023-05-22 | Rectificating | 2023-06-02 | 2023-08-19 | CD//Sapian | 2023-06-09 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002039767 |  |  |  |  | 2023-08-24 |  | LAMP_POLE
A01075 | A036B_A01075OD_JLN_SLIM_BARU | Central |  | Decomm |  | 2023Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-01-11 |  |  |  | 2024-06-25 |  | 2023-10-13 | 2024-09-26 | CD//Sapian | 2023-10-25 | Celcomdigi_RAN_Ascentrack_TSS_Central_20230707_0027 | DU00002039768 |  |  |  |  | 2023-09-27 |  | LAMP_POLE
Q00353 | Q132B_Q00353OD_PERMYJAYA | Sarawak |  | Decomm |  | 2023Q4 | SH | Datasco | 4.6 TSSR Approved |  | 2023-06-23 |  |  | 2023-07-24 |  | Closed | 2023-07-24 | 2024-09-06 | CD//John | 2023-07-25 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622/0612Sarawak-Datasco-BOQ Template (template) | DU00002039769 |  | 22/8: all tx info & photos are missing |  |  | 2025-04-28 |  | TOWER
K00227 | K004A_K00227OD_TITIGAJAH | Northern |  | Decomm |  | 2023Q4 | MH | GCI | 4.6 TSSR Approved |  | 2023-06-20 |  |  |  | 2023-07-12 |  | 2023-07-12 | 2024-05-10 | CD//Rohizam | 2023-08-04 | Celcom Digi_RAN-GCI-TSS-Northern-20230615-0029/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002039770 |  | No TX Info, Photo not enough |  |  | 2023-09-30 | Minaret | MINARET | 20
K00281 | K004A_K00281OD_MASJIDSULTANAH | Northern |  | Decomm |  | 2023Q4 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-06-12 |  |  |  | 2023-06-25 |  | 2023-06-27 | 2024-02-29 | CD//Rohizam | 2023-08-04 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230613-0025 | DU00002039771 |  | 21/8: Please include all TX equipment Photo and 2xIDU |  |  | 2023-10-04 |  | AESTHETIC MONOPOLE
B00033 | B058B_B00033OD_TMNSRIMEWAH | Central |  | Decomm |  | 2023Q3 | MA | Futong | 4.6 TSSR Approved |  | 2023-05-12 |  |  |  | 2023-05-18 |  | 2023-06-14 | 2023-10-18 | CD//Tee | 2023-07-03 | CelcomDigi_RAN_Futong_TSS_Central_20230626_decom reraise | DU00002039772 |  |  |  |  | 2023-08-19 |  | BOOM
B02168 | B058C_B02168OD_LRGSANGGULBDRPUTERIKLG | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-16 |  |  | 2023-05-22 | 2023-05-22 | Under Approval | 2023-06-12 | 2023-12-20 | CD//Sapian | 2023-06-13 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002039773 |  |  |  |  | 2023-12-20 |  | UNIPOLE
B00528 | B057C_B00528OD_TMNGBK | Central | 1818K | Decomm |  | 2023Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2023-09-19 |  |  |  | 2023-09-19 |  | 2023-09-20 | 2025-03-07 | CD//Ali Akaram | 2023-10-03 | CelcomDigi_RAN_Allstar_TSS_Central_20230920 | DU00002039774 |  | RAN anchor change after BBU done dismantle, kindly refer DUID B00528_1 |  |  | 2023-09-18 |  | BOOM
B01636 | B058B_B01636OD_KGDELEKINDAH | Central |  | Decomm |  | 2023Q3 | MA | Futong | 4.6 TSSR Approved |  | 2023-05-15 |  |  |  | 2023-05-18 |  | 2023-06-09 | 2023-10-18 | CD//Sapian | 2023-06-11 | CelcomDigi_RAN_Futong_TSS_Central_20230626_decom reraise | DU00002039775 |  |  |  |  | 2023-07-28 |  | TOWER
B02924 | B061B_B02924OD_JALANLELANGITU8 | Central |  | Decomm |  | 2023Q3 | CR | YPTT | 4.6 TSSR Approved |  | 2023-07-24 |  |  |  | 2023-07-26 |  | 2023-08-01 | 2023-10-18 | CD//Norhaliza | 2023-09-20 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002039776 |  |  |  |  | 2023-08-24 |  | LAMP_POLE
B02608 | B058C_B02608OD_LBHKEBUNNENASBDRPUTERAKLG | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-11 |  |  | 2023-05-22 | 2023-05-22 | Under Approval | 2023-06-06 | 2023-09-01 | CD//Sapian | 2023-06-09 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002039777 |  | Solution provided - 10/8 |  |  | 2023-08-03 |  | LAMP_POLE
B01356 | B060B_B01356OD_PERMATANG2 | Central |  | Decomm |  | 2023Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2023-07-28 |  |  |  | 2023-10-13 |  | 2023-10-13 | 2024-02-23 | CD//Norhaliza | 2023-12-15 | CelcomDigi_RAN_AllStar_TSS_Central_20230802 | DU00002039778 |  |  |  |  | 2023-08-30 |  | TOWER
B02249 | B058B_B02249OD_JLNMAKYONG2MKU5 | Central |  | Decomm |  | 2023Q3 | SS | Datasco | 4.6 TSSR Approved |  | 2023-06-17 |  |  |  | 2023-07-26 |  | 2023-07-26 | 2023-09-01 | CD//Ali Akaram | 2023-08-26 | CelcomDigi_RAN_Datasco_TSS_Central_20230620_0027 | DU00002039779 |  |  |  |  | 2023-09-19 |  | BOOM
B00159 | B065B_B00159OD_T3_ULUYAMBARU | Central |  | Decomm |  | 2023Q4 | SS | Futong | 4.6 TSSR Approved |  | 2023-07-20 |  |  |  | 2023-08-08 |  | 2023-08-10 | 2023-10-18 | CD//Ali Akaram | 2023-08-16 | CelcomDigi_RAN_Futong_TSS_Central_20230721 | DU00002039780 |  |  |  |  | 2023-11-23 |  | TOWER
B00866 | B061A_B00866IB_ALAMSENTRAL | Central |  | Decomm | Decomm->On hold->Swap->On Hold->Decomm | 2023Q4 | SY1 | Datasco | 4.6 TSSR Approved |  | 2023-08-25 | 2024-04-16 |  | 2024-04-26 | 2024-10-08 | Under Approval | 2024-10-09 | 2024-12-31 | CD//Sofiah | 2024-11-07 | CelcomDigi_RAN_Datasco_TSS_Central_20240513 | DU00002039781 |  |  |  |  | 2024-12-06 | In-Building System | IN-BUILDING
B01489 | B061C_B01489OD_KOTAKEMUNING3 | Central |  | Decomm |  | 2023Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-06-15 |  |  |  | 2023-06-15 |  | 2023-06-28 | 2023-07-17 | CD//Sapian | 2023-07-07 | CelcomDigi_RAN_Allstar_TSS_Central_20230616_0012 | DU00002039782 |  |  |  |  | 2023-07-22 |  | TOWER
B01846 | B058B_B01846OD_RD_TMNMEWHBARUKLG | Central |  | Decomm |  | 2023Q3 | MA | Datasco | 4.6 TSSR Approved |  | 2023-04-28 |  |  |  | 2023-08-18 |  | 2023-08-19 | 2023-12-18 | CD//Sapian | 2023-08-23 | CelcomDigi_RANMW_Datasco_TSS_Central_20230609_0005 | DU00002039783 |  |  |  |  | 2023-08-17 |  | BOOM-BYPOD
B00062 | B060C_B00062OD_KGBKTBADONG | Central |  | Decomm |  | 2023Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-29 |  |  |  | 2023-07-28 |  | 2023-07-31 | 2023-09-19 | CD//Norhaliza | 2023-09-15 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002039784 |  | RESUBMISSION. |  |  | 2023-07-22 |  | 3LEGGED
A00469 | A042A_A00469OD_CB_KGMASJIDIJOK | Northern | 4070K | Swap |  | 2023Q4 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-06-06 | 2023-06-08 |  | 2023-06-13 |  | Closed | 2023-06-15 | 2023-07-13 | CD//Quah | 2023-07-13 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002039785 |  |  | 2023-08-17 | 2023-08-17 |  | Tower | TOWER | 60 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
P00182 | P035A_P00182OD_FRUPENANG | Northern |  | Decomm |  | 2023Q3 | ZA | YPTT | 4.6 TSSR Approved |  | 2023-06-28 |  |  |  | 2023-07-28 |  | 2023-07-28 | 2023-08-24 | CD//Rohizam | 2023-08-05 | Celcom Digi_RAN-YPTT-TSS Decomm-Northern-20230810-0027/Celcom Digi_RAN-YPTT-TSS-Northern-20230609-0018 | DU00002039786 |  |  |  |  | 2023-09-27 |  | BOOM
Q00666 | Q118B_Q00666OD_TGBTCOMM | Sarawak |  | Decomm |  | 2023Q3 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-06-19 |  |  | 2023-09-07 |  | Closed | 2023-09-07 | 2023-10-04 | CD//John | 2023-10-03 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 | DU00002039787 |  |  |  |  | 2024-10-30 |  | MONOPOLE
P00223 | P031A_P00223OD_PULAUBETONG | Northern |  | Decomm |  | 2023Q3 | MH | CCSMY | 4.6 TSSR Approved |  | 2023-05-17 |  |  |  | 2023-06-16 |  | 2023-06-18 | 2024-02-15 | CD//QUAH | 2023-07-14 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002039788 |  | Need Include Antenna&FE |  |  | 2023-08-02 |  | TOWER
K00816 | K011A_K00816OD_TJG_MUSANG_PSENA | Northern | 4105K | Swap |  | 2023Q4 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-09-09 | 2023-09-13 |  | 2023-09-15 |  | Closed | 2023-09-18 | 2023-10-11 | CD//Rohizam | 2023-10-10 | Celcom Digi_RAN-GCI-TSS-Northern-20230626-0035 | DU00002039789 |  |  | 2023-09-30 | 2023-09-25 |  | Tower | TOWER | 45 | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle Celcom all RRU&BBU |  | 3
K00524 | K004A_K00524OD_TMNDERGAJAYA | Northern |  | Decomm |  | 2023Q4 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-06-06 |  |  |  | 2023-07-06 |  | 2023-07-07 | 2023-09-07 | CD//Shamsul | 2023-07-12 | Celcom Digi_RAN-GTSB-TSS-Northern-20230529-0020 | DU00002039790 |  | No TX Info |  |  | 2023-10-12 |  | TOWER
B01640 | B057A_B01640OD_ONESELAYANG | Central |  | Decomm |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-09-08 |  |  |  | 2023-09-12 |  | 2023-09-13 | 2023-12-18 | CD//Sapian | 2023-09-16 | CelcomDigi_RAN_YPTT_TSS_Central_20231005 | DU00002039791 |  |  |  |  | 2023-11-29 |  | TRIPOD
A01030 | A042A_A01030OD_KG_EXPO_KAMUNTING | Northern | 4076K | Swap |  | 2023Q4 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-07-20 | 2023-07-25 |  | 2023-07-28 |  | Closed | 2023-08-01 | 2023-08-03 | CD//Quah | 2023-08-02 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230626-0029 | DU00002039792 |  |  | 2023-08-10 | 2023-08-09 |  |  | RAPID ASSEMBLY POLE (RAPOLE) | 30 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 3
B02938 | B061F_B02938OD_ACASIA_BDRTASIKPUTERI | Central |  | Decomm |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-05-03 |  |  |  | 2023-08-09 |  | 2023-08-10 | 2023-08-19 | CD//Sapian | 2023-08-18 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230626_decom reraise | DU00002039793 |  |  |  |  | 2023-09-29 |  | LAMP_POLE
A00649 | A036B_A00649OD_MASJIDATTAQWA | Northern | 4074K | Swap |  | 2023Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-06-16 | 2023-06-20 |  | 2023-06-22 |  | Closed | 2023-06-26 | 2023-08-25 | CD//Sapian | 2023-08-25 | Celcomdigi_RAN_Ascentrack_TSS_Central_20230616_0022 | DU00002039794 |  |  | 2023-12-21 | 2023-09-20 |  |  | MINARET | 20 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 1
P00016 | P035B_P00016OD_SRIINTANTGBGH | Northern | 4114K | Swap |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-07 |  | 2023-06-09 |  | Closed | 2023-06-13 | 2023-07-03 | CD//Heng | 2023-07-03 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0014 | DU00002039795 |  |  | 2023-08-22 | 2023-08-18 |  | Pole | IN-BUILDING | 1.5m wall mounted boom | Add R8852E S9000 x3 + R8894E M1821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
B01707 | B057C_B01707OD_UIA7GBK | Central |  | Decomm |  | 2023Q4 | CR | Datasco | 4.6 TSSR Approved |  | 2023-07-31 |  |  |  | 2024-07-04 |  | 2023-11-16 | 2024-09-26 | CD//Ali Akaram | 2023-11-28 | CelcomDigi_RAN_Datasco_TSS_Central_20230802 | DU00002039796 |  |  |  |  | 2023-12-07 |  | TOWER
B00629 | B061C_B00629OD_SEK25SALAM2 | Central |  | Decomm |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-08-08 |  |  |  | 2023-09-11 |  | 2023-09-13 | 2024-02-23 | CD//Norhaliza | 2023-09-20 | CelcomDigi_RAN_YPTT_TSS_Central_20230815 | DU00002039797 |  |  |  |  | 2023-09-18 |  | MINI STRUCTURE
B02668 | B061A_B02668OD_SIRIMSHLM | Central | 1163K | Swap |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-05-26 | 2023-05-31 |  | 2023-06-02 |  | Closed | 2023-06-03 | 2023-06-09 | CD//Sapian | 2023-06-09 | CelcomDigi_RAN_Datasco_TSS_Central_20230529_0023 | DU00002039798 |  |  | 2023-10-25 | 2023-10-19 |  | Petronas Pylon | RAPID ASSEMBLY POLE (RAPOLE) | 31 | Add R8852E S9000 x3 + R8894E M1821 x3
P00093 | P031B_P00093OD_NTHELEVATOR | Northern |  | Decomm |  | 2023Q3 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-05-19 |  |  |  | 2023-08-11 |  | 2023-08-17 | 2023-10-02 | CD//Affendi | 2023-08-17 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002039799 |  | 21/8: Please include IDU Zoom in Photo with Label |  |  | 2023-08-09 |  | BOOM
B01046 | B058A_B01046OD_JLNJABARMERU | Central |  | Decomm |  | 2023Q3 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-06-16 |  |  |  | 2023-06-19 |  | 2023-06-21 | 2023-09-11 | CD//Tee | 2023-07-22 | CelcomDigi_RAN_CCSMY_TSS_Central_20230626_decom reraise | DU00002039800 |  | Please include link ID and strategy for MW link below |  |  | 2023-11-30 |  | TOWER
B02828 | B061F_B02828OD_PENJARASGBULOHDESACOALFIELDS | Central | 1179K | Swap |  | 2023Q4 | HQ 6 | Magicell | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦Site owner give feedback,the bracket structure can not support 3*Antenna+3*AAU+5*RRU,suggest to change to bi-sector | 2023-07-17 | 2023-07-18 |  | 2023-07-24 |  | Closed | 2023-07-26 | 2023-08-14 | CD//Sapian | 2023-09-25 | CelcomDigi_RAN_Magicell_TSS_Central_20230721 | DU00002039801 | NIC_S2_Change MM to BI_loading issue_RIYYALCOMM SDN BHD |  | 2024-04-23 | 2024-04-23 |  | Lampole | LAMP_POLE | 30 | Add R9264H M901821 x3 + R9264M M1821 x2+R8854 S2600 x2+R8862A S2600 x1,Dismantle Celcom RRU |  | 23
P00310 | P035B_P00310IB_SHANGRI_LA_RASA_SAYANG_PNG | Northern |  | Decomm |  | 2023Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-06-16 |  |  |  | 2023-08-09 |  | 2023-08-11 | 2023-09-06 | CD//Quah | 2023-08-17 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2/Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230726-0024 | DU00002039802 |  |  |  |  | 2023-10-18 |  | IN-BUILDING
Q00678 | Q124F_Q00678OD_TMNSRIWANGI | Sarawak |  | Decomm |  | 2023Q4 | SH | Trintel | 4.6 TSSR Approved |  | 2023-07-05 |  |  |  | 2023-08-16 |  | 2023-08-16 | 2023-08-23 | CD//John | 2023-08-17 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230622 | DU00002039803 |  |  |  |  | 2023-10-17 |  | TOWER
9930A | Bintulu Port MP | Sarawak |  | Modernization |  | 2023Q3 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-05-19 | 2023-05-27 |  | 2023-06-03 |  | Closed | 2023-06-09 | 2023-06-28 | E//John | 2025-05-19 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230512-0001 | DU00002039804 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed | 2025-03-11 | 2025-02-10 |  | Monopole | Rapole | 30 | Add R8862A S9000x3+R8894E M1821x3, Dismantle R8862A S1800(B6A)x4+R8862A S2100(A6A)x4+R8862A S2600(A4A)x1 | 0 | 0
B00277 | B062A_B00277OD_PR_VLBAGANNIRA | Central |  | Decomm |  | 2023Q4 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-06-22 |  |  |  | 2023-07-14 |  | 2023-07-27 | 2024-01-30 | CD//Sapian | 2023-08-15 | CelcomDigi_RAN_CCSMY_TSS_Central_20230623_0005 | DU00002039805 |  |  |  |  | 2023-09-24 |  | 4LEGGED
P00749 | P035F_P00749OD_TMN_GAMBIR_PNG | Northern | 4158K | Swap |  | 2023Q3 | SM | YPTT | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-15 |  | 2023-05-17 |  | Closed | 2023-05-19 | 2023-06-13 | CD//Shamsul | 2023-06-13 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0009 | DU00002039806 |  |  | 2023-08-01 | 2023-07-18 |  | Pole | POLE | 3 | Add R8852E S9000 x3 + A9732 M1821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 123
B00275 | B058A_B00275OD_VLBKTKAPAR | Central |  | Decomm |  | 2023Q3 | IE | Magicell | 4.6 TSSR Approved |  | 2023-05-16 |  |  |  | 2024-05-27 |  | 2023-09-11 | 2023-12-18 | CD//Ali Akaram | 2023-09-13 | CelcomDigi_RAN_Magicell_TSS_Central_20230626_decom reraise | DU00002039807 |  |  |  |  | 2023-09-29 |  | TOWER
P00536 | P035C_P00536IB_GURNEYPARAGON | Northern |  | Decomm |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-06-20 |  |  |  | 2023-06-27 |  | 2023-07-10 |  | CD//Quah | 2023-09-26 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002039808 |  | No TX Info, Photo not enough |  |  | 2023-10-18 |  | IN-BUILDING
Q00124 | Q124F_Q00124OD_JLNSTD | Sarawak |  | Decomm |  | 2023Q4 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-06-22 |  |  |  | 2023-07-21 |  | 2023-07-25 | 2024-07-11 | CD//John | 2023-07-28 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002039809 |  | 1/9: uncompleted info & photos |  |  | 2023-10-05 |  | MONOPOLE
B00644 | B058E_B00644OD_JOHANSETIA | Central | 1090K | Swap |  | 2023Q3 | AI | YPTT | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-16 |  | 2023-05-19 |  | Closed | 2023-05-30 | 2023-08-16 | CD//Tee | 2023-08-16 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002039810 |  |  | 2023-08-24 | 2023-08-17 |  | Tower | TOWER | 60m | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 12
B00084 | B058B_B00084OD_BDRBARUKLG2 | Central |  | Decomm |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-06-19 |  |  |  | 2024-07-15 |  | 2023-07-18 | 2024-12-09 | CD//Ali Akaram | 2023-08-26 | CelcomDigi_RAN_Datasco_TSS_Central_20230620_0027 | DU00002039811 |  |  |  |  | 2024-02-05 |  | BOOM
B02062 | B061A_B02062OD_SETIAPRIMA | Central |  | Decomm |  | 2023Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2023-05-08 |  |  |  | 2023-05-31 |  | 2023-06-16 | 2023-10-17 | CD//Tee | 2023-07-13 | CelcomDigi_RAN_Magicell_TSS_Central_20230626_decom reraise/CelcomDigi_RAN-TX_Magicell_TSS_Central_20230816_Decom | DU00002039812 |  |  |  |  | 2023-08-23 |  | BOOM
P00032 | P031B_P00032OD_BKTGEDUNG | Northern | 4119K | Swap |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-15 | 2023-05-23 |  | 2023-05-26 |  | Closed | 2023-06-05 | 2023-06-14 | CD//Heng | 2023-06-14 | Celcom Digi_RAN-GCI- TSS-Northern-20230509-0016 | DU00002039813 |  |  | 2023-07-18 | 2023-07-18 |  | Monople Tree | AESTHETIC MONOPOLE | 46 | Add R8852E S9000 x3 + A9732 M1821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 123
B00312 | B061F_B00312OD_TMBTARANG | Central |  | Decomm |  | 2023Q3 | MA | Solusi | 4.6 TSSR Approved |  | 2024-03-14 |  |  |  | 2024-05-14 |  | 2024-05-15 | 2024-07-16 | CD//Ali Akaram | 2024-06-06 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230626_decom reraise/CelcomDigi_RAN_Solusi_TSS_Central_20240618 | DU00002039814 |  |  |  |  | 2024-03-14 |  | TOWER
Q00333 | Q132C_Q00333OD_PIASAUIND | Sarawak |  | Decomm |  | 2023Q4 | SH | Magicell | 4.6 TSSR Approved |  | 2023-07-03 |  |  |  | 2023-07-11 |  | 2023-07-25 | 2023-08-18 | CD//John | 2023-07-26 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002039815 |  |  |  |  | 2025-06-24 |  | BOOM
P00266 | P035F_P00266OD_PESTA2 | Northern | 4133K | Swap |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved | Bisector Cannot Install, Change to Normal | 2023-05-14 | 2023-05-18 |  | 2023-05-23 |  | Closed | 2023-05-25 | 2023-07-31 | CD//Affendi | 2023-06-08 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0015 | DU00002039816 | NIC_S2_Change BI to normal sector_owner reject_SBC PDC |  | 2023-07-26 | 2023-07-22 |  | Lampole | MONOPOLE | 25M | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 0 | 0
Q00008 | Q124F_Q00008OD_RAMPANGI | Sarawak |  | Decomm |  | 2023Q4 | SH | Trintel | 4.6 TSSR Approved |  | 2023-07-10 |  |  |  | 2023-08-08 |  | 2023-08-08 | 2023-10-04 | CD//John | 2023-08-09 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230622 | DU00002039817 |  |  |  |  | 2023-09-29 |  | TOWER
K00145 | K004A_K00145OD_JLNMERGONG | Northern |  | Decomm |  | 2023Q4 | SM | YPTT | 4.6 TSSR Approved |  | 2023-06-13 |  |  |  | 2023-07-18 |  | 2023-07-20 | 2023-11-29 | CD//Rohizam | 2023-08-05 | Celcom Digi_RAN-YPTT-TSS-Northern-20230613-0020 | DU00002039818 |  | Please fill NE info, please state which one IDU, Please fill dismantle item for TX, Please fill FE info. |  |  | 2023-10-11 |  | BOOM
K00085 | K011A_K00085OD_CB_TITIHAJIIDRIS | Northern |  | Decomm |  | 2023Q4 | ZA | GCI | 4.6 TSSR Approved |  | 2023-06-21 |  |  |  | 2023-06-28 |  | 2023-07-06 | 2023-09-21 | CD//Rohizam | 2023-08-05 | Celcom Digi_RAN-GCI-TSS-Northern-20230622-0033/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002039819 |  | 18/8 - Not Enough TX Photo No TX Info, Photo not enough |  |  | 2023-10-10 |  | TOWER
B01148 | B061A_B01148OD_PCKALAMHWY2 | Central |  | Decomm |  | 2023Q3 | IE | Magicell | 4.6 TSSR Approved |  | 2023-06-20 |  |  |  | 2023-07-05 |  | 2023-07-12 | 2023-10-17 | CD//Sapian | 2023-07-18 | CelcomDigi_RAN_Magicell_TSS_Central_20230622_0015 / CelcomDigi_TX_Magicell_TSS_Decom_Central_20230714 | DU00002039820 |  |  |  |  | 2023-08-15 |  | TOWER
P00219 | P035C_P00219OD_AURORACOURT | Northern | 4132K | Swap |  | 2023Q3 | ZA | YPTT | 4.6 TSSR Approved |  | 2023-05-11 | 2023-05-13 |  | 2023-05-16 |  | Closed | 2023-05-18 | 2023-05-30 | CD//Affendi | 2023-05-30 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0009 | DU00002039821 |  | 0517 rejected... minor only after 2nd review... pls revise asap... | 2023-09-12 | 2023-09-08 |  | A-bracket pole | BOOM | 2 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
B00043 | B057C_B00043OD_TMNSRIGOMBAK | Central | 1862K | Decomm |  | 2023Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2023-08-03 |  |  |  | 2023-08-04 |  | 2023-08-08 | 2023-08-19 | CD//Sapian | 2023-08-17 | CelcomDigi_RAN_Allstar_TSS_Central_20230707_0018 | DU00002039822 |  |  |  |  | 2023-09-19 |  | TRIPOD
A01089 | A036B_A01089OD_UPSI_PROTON_CITY | Northern | 4078K | Swap |  | 2023Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-06-14 | 2023-06-21 |  | 2023-06-23 |  | Closed | 2023-06-26 | 2023-08-25 | CD//Sapian | 2023-08-25 | CelcomDigi_RANMW_Ascentrack_TSS_Central_20230616_0006 | DU00002039823 |  |  | 2023-10-05 | 2023-09-05 |  | Watertank | RAMO | 30 | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle Celcom all RRU&BBU |  | 1
Q00290 | Q118B_Q00290OD_AUSTRAL | Sarawak | 9066K | Swap |  | 2023Q3 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-05-23 | 2023-05-25 |  | 2023-05-30 |  | Rectificating | 2024-01-24 | 2024-01-30 | CD//John | 2024-01-29 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230516-0006 | DU00002039824 |  |  | 2024-06-12 | 2024-06-07 |  | Tower | GUYED MAST | 18 | Add R9264H M901821 x3+R8862A S2601 x2+R8854 S2600 x1,Dismantle |  | 3
Q00012 | Q124B_Q00012OD_SMTMATANG | Sarawak |  | Decomm |  | 2023Q4 | ZB | South Pacific | 4.6 TSSR Approved |  | 2023-06-16 |  |  |  | 2023-08-03 |  | 2023-08-03 | 2023-08-30 | CD//John | 2023-08-07 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230622 | DU00002039825 |  |  |  |  | 2023-11-27 |  | TOWER
P00331 | P035F_P00331OD_BBOARDBRIDGE | Northern |  | Decomm |  | 2023Q3 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-05-30 |  |  |  | 2023-07-25 |  | 2023-07-26 | 2024-03-26 | CD//Quah | 2023-09-29 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2/Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230726-0024 | DU00002039826 |  | 22/8: missing Celcom Cabinet info |  |  | 2023-08-24 |  | BILLBOARD
A00525 | A042A_A00525OD_CB_SGSIPUTEH | Northern | 4072K | Swap |  | 2023Q4 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-06-18 | 2023-06-23 |  | 2023-06-27 |  | Closed | 2023-07-03 | 2023-07-13 | CD//Quah | 2023-07-13 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002039827 |  |  | 2023-08-16 | 2023-08-09 |  | Tower | TOWER | 55 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 13
B02054 | B058E_B02054OD_BT5JLNJOHANSETIA | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-31 |  |  |  | 2023-06-24 |  | 2023-06-28 | 2023-10-17 | CD//Norhaliza | 2023-10-09 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002039828 |  |  |  |  | 2023-08-24 |  | TOWER
B00306 | B065B_B00306OD_TMRASA | Central | 1073K | Swap |  | 2023Q4 | SS | GCI | 4.6 TSSR Approved |  | 2024-01-30 | 2024-01-31 |  | 2024-01-31 |  | Closed | 2024-01-31 | 2024-02-16 | CD//Ali Akaram | 2024-02-15 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240202 | DU00002039829 |  |  | 2024-04-03 | 2024-03-20 |  | Monopole | GUYED MAST | 45 | Add R9264H M901821 x3,Dismantle |  | 2
B00496 | B057C_B00496OD_MIMALAND | Central |  | Decomm |  | 2023Q4 | CR | Magicell | 4.6 TSSR Approved |  | 2023-08-03 |  |  |  | 2023-08-05 |  | 2023-08-08 | 2023-12-18 | CD//Norhaliza | 2023-08-18 | CelcomDigi_RAN_Magicell_TSS_Central_20230804_Decom | DU00002039830 |  |  |  |  | 2024-01-05 |  | TOWER
K00063 | K004A_K00063OD_TMNJAYA | Northern | 4086K | Swap |  | 2023Q4 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-06-01 | 2023-06-07 |  | 2023-06-26 |  | Closed | 2023-07-10 | 2023-08-22 | CD//Quah | 2023-08-22 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002039831 |  |  | 2023-09-22 | 2023-09-22 |  | Guide mast | GUYED MAST | 19m | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 1
P00557 | P035F_P00557OD_BATUUBAN | Northern | 4150K | Swap |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-17 | 2023-06-19 |  | 2023-06-21 |  | Closed | 2023-06-27 | 2023-07-12 | CD//Shamsul | 2023-07-11 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0015 | DU00002039832 |  |  | 2023-07-27 | 2023-07-18 |  | Pole | BOOM | 6 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x2 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU | 13
B00768 | B060B_B00768OD_BT12KAPAR | Central |  | Decomm |  | 2023Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-28 | 2023-06-26 |  |  | 2023-08-03 |  | 2023-07-21 | 2023-10-17 | CD//Ali akaram | 2023-08-01 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002039833 |  | Tx part reject, please provide full photo of cisco router and existing IDU with clear label |  |  | 2023-07-28 | Tower | 3LEGGED | 45
9805A | Bintang Plaza | Sarawak |  | Modernization |  | 2023Q4 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-07-15 | 2023-07-24 |  | 2023-08-04 |  | Closed | 2023-08-08 | 2023-08-09 | E//Sirus | 2023-08-08 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230613-0007 | DU00002039834 |  |  | 2023-10-06 | 2023-09-24 |  |  | In-building system |  | Add R8862A S1800 x3 + R8862A S2100 x3,Dismantle R8882-GUL1812 x2+R8882 S1800B(B6B) x1
B00285 | B065B_B00285OD_TMNKERUING | Central | 1815K | Decomm |  | 2023Q4 | MA | CCSMY | 4.6 TSSR Approved |  | 2023-06-30 | 2024-03-01 |  | 2024-04-29 | 2023-07-25 | Under Approval | 2023-08-01 |  | CD//Sapian | 2023-08-14 | 0920CD-Central-CCSMY-BOQ Template (old contract) | DU00002039835 |  | Misiing FE part |  |  | 2024-04-17 | In-Building System | BOOM | 6m
Q00677 | Q118B_Q00677OD_CB_RHGILAN | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039836 | [6 empty] | 3LEGGED
B00209 | B057B_B00209OD_TMSLYBARU | Central | 1066K | Swap |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2024-01-22 | 2024-01-23 |  | 2024-01-24 |  | Closed | 2024-01-24 | 2024-05-29 | CD//Norhaliza | 2024-05-29 | BOQ_Celcom Digi_RAN-YPTT-Standard PR TSS-20240128 | DU00002039837 |  |  | 2024-03-30 | 2024-02-24 |  | In-Building System | BOOM | 6m | Add R9264H M901821 x3+R8862A S2601 x1+R8854 S2600 x2,Dismantle |  | 23
Q00506 | Q132B_Q00506OD_CB_KUALABARAMCOMM | Sarawak | 9384K | Swap | Decomm->On Hold | 2027 | AD | Magicell | 4.6 TSSR Approved | Change SOW, new TSSR claim in CR2023 DU | 2025-09-18 | 2025-09-24 |  |  | 2023-10-06 |  | 2023-10-07 | 2023-10-13 | E//John | 2025-10-03 | SQ202509240313-Magicell | DU00002039838 | [5 empty] | Monopole | TOWER | 30 | Add R9264H M901821x3+R8862A S2601x3, Dismantle | 0 | 0
B00283 | B065B_B00283OD_LBHBERINGIN | Central |  | Decomm |  | 2023Q4 | ZB | Ascentrack | 4.6 TSSR Approved |  | 2023-10-19 |  |  |  | 2024-03-29 |  | 2024-04-01 | 2025-03-25 | CD//Sapian | 2024-04-29 | Celcomdigi_RAN_Ascentrack_TSS_Central_20230707_0027 | DU00002039839 |  |  |  |  | 2024-02-21 |  | TOWER
K00328 | K004A_K00328OD_ALORMADI | Northern | 4094K | Swap |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-28 | 2023-06-12 |  | 2023-06-16 |  | Closed | 2023-06-20 | 2023-08-07 | CD//Rohizam | 2023-08-05 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230529-0020 | DU00002039840 |  |  | 2023-09-14 | 2023-09-13 |  | Tower | MONOPOLE | 50m | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 23
B00066 | B058A_B00066OD_KGTOKMUDA | Central |  | Decomm | Decomm->On hold->Decomm | 2023Q3 | SS | GTSB | 4.6 TSSR Approved |  | 2023-04-29 |  |  |  | 2023-08-08 |  | 2023-06-21 | 2023-07-31 | CD//Tee | 2023-07-22 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002039841 |  |  |  |  | 2023-12-22 |  | 3LEGGED
B01459 | B061A_B01459OD_JLNKRISTAL2SEK7 | Central | 1124K | Swap |  | 2023Q4 | HQ 6 | GTSB | 4.6 TSSR Approved |  | 2023-06-08 | 2023-06-14 |  | 2023-06-20 |  | Closed | 2023-06-22 | 2023-07-24 | CD//Tee | 2023-07-22 | CelcomDigi_RAN_GTSB_TSS_Central_20230609_0027 | DU00002039842 |  |  | 2023-10-09 | 2023-09-30 |  | Monopole | LAMP_POLE | 20m | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x5,Dismantle Celcom all RRU&BBU |  | 12
P00126 | P035C_P00126IB_ENOHOTEL | Northern |  | Decomm |  | 2023Q3 | MH | GCI | 4.6 TSSR Approved |  | 2023-06-20 |  |  |  | 2023-06-26 |  | 2023-06-28 | 2023-08-24 | CD//QUAH | 2023-07-14 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002039843 |  |  |  |  | 2024-03-22 |  | IN-BUILDING
B02395 | B057B_B02395OD_JLN_MUTIARA_SELAYANG | Central |  | Decomm |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-08-29 |  |  | 2023-08-29 | 2023-08-29 | Closed | 2023-08-29 | 2023-11-16 | CD//Sapian | 2023-08-30 | CelcomDigi_RAN_YPTT_TSS_Central_20230727 | DU00002039844 |  |  |  |  | 2023-10-02 |  | LAMP_POLE
B02070 | B061A_B02070OD_SETIAALAM2 | Central |  | Decomm |  | 2023Q3 | IE | Magicell | 4.6 TSSR Approved |  | 2023-06-20 |  |  |  | 2023-09-15 |  | 2023-09-18 | 2023-12-18 | CD//Ali Akaram | 2023-10-03 | CelcomDigi_RAN_Magicell_TSS_Central_20230626_0017/CelcomDigi_RAN-TX_Magicell_TSS_Central_20230816_Decom | DU00002039845 |  |  |  |  | 2023-09-29 |  | BOOM
K00248 | K004A_K00248OD_JLNSTADIUM | Northern |  | Decomm |  | 2023Q4 | SM | YPTT | 4.6 TSSR Approved |  | 2023-07-08 |  |  |  | 2023-08-03 |  | 2023-08-04 | 2023-11-29 | CD//Affendi | 2023-08-07 | Celcom Digi_RAN-YPTT-TSS-Northern-20230706-0023//Celcom Digi_RAN-YPTT-TSS Decomm-Northern-20240311-0048 | DU00002039846 |  | Please fill NE info, please state which one IDU, Please fill dismantle item for TX, Please fill FE info. |  |  | 2023-10-16 |  | BOOM
K00091 | K004A_K00091OD_ALORSTAR2 | Northern |  | Decomm |  | 2023Q4 | MH | CCSMY | 4.6 TSSR Approved |  | 2023-05-25 |  |  |  | 2023-06-21 |  | 2023-06-23 | 2023-09-18 | CD//Shamsul | 2023-07-04 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230529-0020 | DU00002039847 |  | include all TX Equipment in rack, include Zoom Photo for TX equipment related, Ensure in Drawing involve Location Digi and Location Celcom |  |  | 2023-09-30 |  | BOOM
B02467 | B065B_B02467OD_KGGESIRULUSGOR2 | Central | 1157K | Swap |  | 2023Q4 | HQ 1 | Magicell | 4.6 TSSR Approved |  | 2023-05-31 | 2023-06-06 |  | 2023-06-08 |  | Closed | 2023-06-12 | 2023-06-13 | CD//Sapian | 2023-06-13 | CelcomDigi_RAN_Magicell_TSS_Central_20230601_0011 | DU00002039848 |  |  | 2023-09-12 | 2023-09-07 |  | Tower | TOWER | 60 | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle Celcom all RRU&BBU |  | 2
B01948 | B060C_B01948OD_INDBDRALAMJAYA | Central | 1146K | Swap |  | 2023Q3 | SS | YPTT | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-12 |  | 2023-05-24 |  | Closed | 2023-06-12 | 2023-11-17 | CD//Sapian | 2023-10-25 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002039849 |  |  | 2023-08-11 | 2023-07-31 |  | Minimast | MINI STRUCTURE | 8.20m | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2,Dismantle Celcom all RRU&BBU | 1
C00639 | C046C_C00639OD_SELESAHILLHOMES | Central |  | Decomm |  | 2023Q4 | SS | Magicell | 4.6 TSSR Approved |  | 2023-07-27 |  |  |  | 2023-07-28 |  | 2023-08-02 | 2023-11-16 | CD//Ali akaram | 2023-08-14 | CelcomDigi_RAN_Magicell_TSS_Central_20230729 | DU00002039850 |  |  |  |  | 2024-01-07 |  | AESTHETIC MONOPOLE
B01127 | B061A_B01127OD_SETIAECOPARK | Central |  | Decomm |  | 2023Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2023-05-08 |  |  |  | 2023-06-16 |  | 2023-06-16 | 2023-10-17 | CD//Tee | 2023-07-13 | CelcomDigi_RAN_Magicell_TSS_Central_20230626_decom reraise / CelcomDigi_TX-RAN_Magicell_TSS_Central_20230818 | DU00002039851 |  | RESUBMISSION. |  |  | 2023-07-25 |  | TOWER
A01188 | Kg Ulu Mengkuang | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039852 | [6 empty] | TOWER
B00680 | B060B_B00680OD_CB_JLNRAJAMUSA | Central | 1002P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039853 | [6 empty] | TOWER
A00644 | A042B_A00644OD_TMNLONGJAAFAR_RDD | Northern |  | Decomm |  | 2023Q4 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-06-20 |  |  |  | 2023-08-15 |  | 2023-08-17 | 2023-08-28 | CD//Rohizam | 2023-08-17 | Celcom Digi_RAN-CCSMY- TSS-Northern-20230621-0027 | DU00002039854 |  |  |  |  | 2023-08-21 |  | TOWER
P00369 | P035B_P00369OD_NAZAHOTEL | Northern |  | Decomm |  | 2023Q3 | MH | GCI | 4.6 TSSR Approved |  | 2023-05-11 |  |  |  | 2023-06-20 |  | 2023-06-22 |  | CD//QUAH | 2023-07-18 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240529-0109 | DU00002039855 |  | Pls verify MW link to P00358 (NT04683) to remain or dismantle. |  |  | 2023-09-23 |  | BOOM
A00122 | A042B_A00122OD_KAMUNTING_RCC | Northern |  | Decomm |  | 2023Q4 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-06-01 |  |  |  | 2023-06-12 |  | 2023-06-13 |  | CD//Shamsul | 2023-06-21 | Celcom Digi_RAN-GTSB-TSS-Northern-20230529-0020 | DU00002039856 |  |  |  |  | 2023-08-10 |  | TOWER
9703B | Jln Sealine | Sarawak |  | Modernization |  | 2023Q4 | HQ 3 | Magicell | 4.6 TSSR Approved |  | 2023-06-21 | 2023-06-22 |  | 2023-06-27 |  | Closed | 2023-07-03 | 2023-07-15 | E//Hannah | 2023-07-14 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002039857 |  |  | 2023-08-15 | 2023-08-09 |  | Pole | 30M Rapole | 30 | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3 |  | 3
K00795 | K004A_K00795OD_KG_SEMATANG_GUNUNG | Northern | 4104K | Swap |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-28 | 2023-06-23 |  | 2023-06-28 |  | Closed | 2023-07-03 | 2023-08-07 | CD//Rohizam | 2023-08-05 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230529-0020 | DU00002039858 |  |  | 2023-09-13 | 2023-09-10 |  | Tower | TOWER | 50 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x5,Dismantle Celcom all RRU&BBU |  | 23
A00228 | A042A_A00228OD_CB_TMBTKURAU | Northern |  | Decomm |  | 2023Q4 | MH | YPTT | 4.6 TSSR Approved |  | 2023-06-13 |  |  |  | 2023-06-30 |  | 2023-07-03 | 2024-03-26 | CD//Shamsul | 2023-07-11 | Celcom Digi_RAN-YPTT-TSS-Northern-20230613-0020//Celcom Digi_RAN-YPTT-TSS Decomm-Northern-20240311-0048 | DU00002039859 |  | No TX Info, Photo not enough |  |  | 2023-12-15 |  | 4LEGGED
A00466 | A042A_A00466OD_KGCKTMASJID | Northern | 4067K | Swap |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-06-05 | 2023-07-24 |  | 2023-07-26 |  | Closed | 2023-07-28 | 2023-08-03 | CD//Quah | 2023-08-02 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230606-0022 | DU00002039860 |  |  | 2023-08-10 | 2023-08-06 |  | Tower | TOWER | 75M | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 1
C00015 | C046C_C00015IB_GENTINGSTAFF5 | Central |  | Decomm |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-08-09 |  |  |  | 2023-08-11 |  | 2023-08-15 | 2023-12-18 | CD//Sofiah | 2023-08-29 | CelcomDigi_RAN_GTSB_TSS_Central_20230810 | DU00002039861 |  |  |  |  | 2025-12-10 |  | BOOM
B00359 | B061D_B00359OD_TMSGRENGGAM | Central |  | Decomm |  | 2023Q4 | SH | Solusi | 4.6 TSSR Approved |  | 2024-04-26 |  |  | 2024-04-26 | 2024-05-24 | Under Approval | 2024-04-30 |  | CD//Ali Akaram | 2024-05-16 | CelcomDigi_RAN_Solusi_TSS_Central_20240513 | DU00002039862 |  | 1) Pls provide digi cabinet/rack photo 2) Missing antenna tx photo at NE & FE part |  |  | 2024-03-19 |  | BOOM
P00632 | P031B_P00632OD_FTZFASA4_BYNLEPAS | Northern |  | Decomm |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-06-07 |  |  |  | 2023-06-16 |  | 2023-06-16 | 2024-10-01 | CD//Affendi | 2023-06-27 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1/GCI Northern TX TSS | DU00002039863 |  | Missing TM LL & Fiber equipment to relocate into Digi Cabinet 25/6: Missing TM LL |  |  | 2023-08-25 |  | AESTHETIC MONOPOLE
B02816 | B061A_B02816IB_CENTRALPLAZAICITY | Central |  | Decomm |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-16 |  |  |  | 2024-01-20 |  | 2024-01-21 | 2024-02-15 | CD//Sofiah | 2024-02-13 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240117 | DU00002039864 |  |  |  |  | 2024-07-30 |  | IN-BUILDING
B01064 | B062A_B01064OD_BAGANTERAP | Central | 1108K | Swap |  | 2023Q4 | HQ 6 | Magicell | 4.6 TSSR Approved |  | 2023-06-07 | 2023-06-08 |  | 2023-06-13 |  | Closed | 2023-06-14 | 2023-06-17 | CD//Sapian | 2023-06-15 | CelcomDigi_RAN_Magicell_TSS_Central_20230607_0012 | DU00002039865 |  |  | 2023-08-15 | 2023-08-10 |  | Tower | TOWER | 61 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x5,Dismantle Celcom all RRU&BBU |  | 23
B01768 | B061C_B01768IB_CARREFOURBKTRIMAU | Central | 1142K | Swap |  | 2023Q3 | AI | YPTT | 4.6 TSSR Approved |  | 2023-06-26 | 2023-06-30 |  | 2023-07-09 |  | Closed | 2023-07-10 | 2023-10-02 | CD//Syafiq | 2023-09-26 | CelcomDigi_RAN_YPTT_TSS_Central_20230627_0010 | DU00002039866 |  |  | 2023-09-25 | 2023-09-25 |  | Portables BTS | IN-BUILDING |  | Add R8862A S1800 x1 + R8862A S2100 x1,Dismantle all celcom BBU&RRU
B00715 | B065B_B00715OD_CB_KM410LBRIGNHOT | Central |  | Decomm |  | 2023Q4 | MA | Ascentrack | 4.6 TSSR Approved | 0216 ZTE Rejec | 2023-07-14 |  |  |  | 2024-02-15 |  | 2024-02-19 | 2024-08-22 | CD//Sapian | 2024-02-27 | Celcomdigi_RAN_Ascentrack_TSS_Central_20230707_0027 | DU00002039867 |  |  |  |  | 2023-10-26 |  | TOWER
C00017 | C046C_C00017IB_GENTINGSTAFF7 | Central |  | Decomm | Decomm->On Hold | 2023Q4 | SHA | GTSB | 4.3 Pending TSSR Resubmission - ZTE |  | 2023-07-24 |  |  |  | 2023-07-29 |  | 2023-09-11 |  | CD//Sofiah |  | CelcomDigi_RAN_GTSB_TSS_Central_20230725 | DU00002039868 | [6 empty] | BOOM
B01804 | B061D_B01804OD_RD_SEK17SHLM | Central |  | Decomm |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-05-19 |  |  |  | 2023-09-20 |  | 2023-09-20 | 2025-03-24 | CD//Sapian | 2023-09-25 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230626_decom reraise | DU00002039869 |  |  |  |  | 2023-09-14 |  | BOOM-BYPOD
B01137 | B065B_B01137OD_PR_KM399BERNAMJAY | Central |  | Decomm |  | 2023Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-01-11 |  |  |  | 2024-01-17 |  | 2024-01-18 | 2025-06-04 | CD//Sapian | 2024-01-24 | CelcomDigi_RANMW_Ascentrack_Central_20230706_0010 | DU00002039870 |  |  |  |  | 2023-09-24 |  | 4LEGGED
Q00061 | Q124B_Q00061OD_JLNPERUPOK | Sarawak |  | Decomm |  | 2023Q4 | ZB | South Pacific | 4.6 TSSR Approved |  | 2023-06-22 |  |  |  | 2023-08-09 |  | 2023-08-10 | 2023-09-29 | CD//John | 2023-08-11 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230622 | DU00002039871 |  | 24/8: uncompleted info & photos |  |  | 2024-01-17 |  | TOWER
Q00267 | Q118B_Q00267OD_BT34BTU | Sarawak |  | Decomm |  | 2023Q3 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-06-30 |  |  |  | 2023-07-20 |  | 2023-07-24 | 2024-05-14 | CD//John | 2023-08-01 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002039872 |  |  |  |  | 2024-01-12 |  | TOWER
A00512 | A042A_A00512OD_BENDANGRAWA | Northern |  | Decomm | Decomm->On Hold->Decomm | 2023Q4 | SM | YPTT | 4.6 TSSR Approved |  | 2023-06-10 |  |  |  | 2023-07-03 |  | 2023-07-04 | 2025-10-01 | CD//Affendi | 2023-07-04 | Celcom Digi_RAN-YPTT-TSS-Northern-20230613-0020 | DU00002039873 |  | No TX Info, Photo not enough |  |  | 2024-01-05 |  | TOWER
A00330 | A036B_A00330OD_TMTGMALIM | Central |  | Decomm |  | 2023Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-01-08 |  |  |  | 2024-03-08 |  | 2024-03-11 | 2025-03-24 | CD//Sapian | 2024-04-21 | 0920CD-Central-Ascentrack-BOQ Template (old contract) | DU00002039874 |  |  |  |  | 2024-01-08 |  | BOOM
A00478 | A042A_A00478OD_TPGGOLFRESORT | Northern |  | Site Out (Decomm) | Decomm->Site Out->Replacement, Site Out (Decomm) | 2023Q4 | MH | GCI | 4.6 TSSR Approved |  | 2023-06-19 |  | 2025-08-05 |  | 2023-06-20 |  | 2023-06-21 | 2025-10-22 | CD//Rohizam | 2023-08-05 | Celcom Digi_RAN-GCI-TSS-Northern-20230619-0031 | DU00002039875 |  | Site already Dismantle by third party |  |  | 2025-06-26 |  | TOWER
C00007 | C046C_C00007OD_BKTCINCIN | Central | 1185K | Swap |  | 2023Q4 | SY1 | GTSB | 4.6 TSSR Approved |  | 2023-06-15 | 2023-07-07 |  | 2023-07-12 |  | Closed | 2023-07-14 | 2023-07-22 | CD//Sapian | 2023-07-21 | CelcomDigi_RAN_GTSB_TSS_Central_20230616_0029 | DU00002039876 |  |  | 2024-12-05 | 2024-12-04 |  | Tower | TOWER | 95 | Add R8862A S9000x3+R8894E M1821x3+R8862A S2601x3,Dismantle | 0 | 0
Q00428 | Q118B_Q00428OD_BTUPORT | Sarawak |  | Decomm |  | 2023Q3 | SH | South Pacific | 4.6 TSSR Approved |  | 2023-05-19 |  |  |  | 2023-05-20 |  | 2023-05-25 | 2024-08-09 | CD//John | 2023-05-26 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230622/0612Sarawak-South Pacific-BOQ Template (template) | DU00002039877 |  | 2023-06-26 Missing TX photos and info |  |  | 2025-03-27 |  | RAPID ASSEMBLY POLE (RAPOLE)
B00350 | B061D_B00350OD_SEK15SA | Central |  | Decomm |  | 2023Q4 | SS | Solusi | 4.6 TSSR Approved |  | 2023-10-06 |  |  | 2023-10-14 | 2024-08-08 | Under Approval | 2023-10-14 | 2023-12-18 | CD//Sapian | 2023-10-21 | CelcomDigi_RAN_Solusi_TSS_Central_20231011 | DU00002039878 |  |  |  |  | 2023-10-06 |  | BOOM
B00853 | B058B_B00853OD_AMANPDANAKLG | Central |  | Decomm |  | 2023Q3 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-06-07 |  |  |  | 2023-06-15 |  | 2023-07-13 | 2023-08-18 | CD//Ali akaram | 2023-08-16 | CelcomDigi_RAN_CCSMY_TSS_Central_20230626_decom reraise | DU00002039879 |  |  |  |  | 2023-08-18 |  | MONOPOLE
P00035 | P035B_P00035OD_PEARLHILL | Northern |  | Decomm |  | 2023Q3 | ZA | YPTT | 4.6 TSSR Approved |  | 2023-05-13 |  |  |  | 2023-07-24 |  | 2023-07-25 | 2023-08-08 | CD//Rohizam | 2023-08-05 | Celcom Digi_RAN-YPTT-TSS-Northern-20230609-0018 | DU00002039880 |  |  |  |  | 2023-09-27 |  | GUYED MAST
K00898 | K004B_K00898OD_KG_ALOR_BINJAL_AS | Northern | 4109K | Swap |  | 2023Q4 | ZA | YPTT | 4.6 TSSR Approved |  | 2023-07-08 | 2023-07-07 |  | 2023-07-10 |  | Closed | 2023-07-11 | 2023-08-07 | CD//Rohizam | 2023-08-05 | Celcom Digi_RAN-YPTT-TSS-Northern-20230606-0017 | DU00002039881 |  |  | 2023-10-13 | 2023-10-01 |  | Tower | TOWER | 45m | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
B02465 | B060B_B02465OD_TMNDESAUTAMABESTARIJAYA | Central | 1155K | Swap |  | 2023Q4 | CR | YPTT | 4.6 TSSR Approved |  | 2023-07-21 | 2023-07-25 |  | 2023-08-01 |  | Closed | 2023-08-08 | 2023-08-16 | CD//Ali Akaram | 2023-08-16 | CelcomDigi_RAN_YPTT_TSS_Central_20230722 | DU00002039882 |  |  | 2023-09-23 | 2023-09-21 |  | Monopole | LAMP_POLE | 30 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
A00769 | A036B_A00769OD_PROTONCT_RDC | Central |  | Decomm |  | 2023Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-07-07 |  |  |  | 2023-10-10 |  | 2023-08-09 | 2023-10-20 | CD//Ali Akaram | 2023-08-16 | Celcomdigi_RAN_Ascentrack_TSS_Central_20230707_0027 | DU00002039883 |  |  |  |  | 2023-09-23 |  | TOWER
Q00054 | Q124F_Q00054OD_JLNASTANA | Sarawak | 9056K | Swap |  | 2023Q4 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-07-06 | 2023-07-12 |  | 2023-07-16 |  | Closed | 2024-01-08 | 2024-02-28 | CD//John | 2024-02-28 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002039884 |  |  | 2024-01-12 | 2024-01-08 |  | Tower | TOWER | 48M | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x1+R8854 S2600×2,Dismantle Celcom all RRU&BBU |  | 12
9734B | Park City Commercial 2 (REL) | Sarawak |  | Modernization |  | 2023Q3 | BY | Datasco | 4.6 TSSR Approved |  | 2023-05-27 | 2023-06-08 |  | 2023-06-12 |  | Closed | 2023-06-13 | 2023-07-07 | E//Hannah | 2023-07-05 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230516-0006 | DU00002039885 |  |  | 2023-07-13 | 2023-07-10 |  | Pole | TOWER | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
B00525 | B060B_B00525OD_KUALASELANGOR | Central |  | Decomm |  | 2023Q4 | CR | AllStar | 4.6 TSSR Approved |  | 2023-07-05 |  |  |  | 2023-07-06 |  | 2023-07-27 | 2023-12-18 | CD//Sapian | 2023-08-04 | CelcomDigi_RAN_Allstar_TSS_Central_20230707_0018 | DU00002039886 |  | Resubmission |  |  | 2023-09-05 |  | TOWER
P00304 | P035C_P00304IB_CITITELPENANG | Northern |  | Decomm |  | 2023Q3 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-05-19 |  |  |  | 2023-08-11 |  | 2023-08-08 | 2023-09-18 | CD//Quah | 2023-09-29 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002039887 |  |  |  |  | 2023-09-15 |  | IN-BUILDING
B02245 | B061C_B02245OD_JLNKEMUNINGINDAHSEK32SHLM | Central |  | Decomm |  | 2023Q3 | SS | GCI | 4.6 TSSR Approved |  | 2023-06-01 |  |  |  | 2024-06-27 |  | 2023-07-26 | 2024-10-29 | CD//Sapian | 2023-08-04 | CelcomDigi_RAN_Futong_TSS_Central_20230626_decom reraise | DU00002039888 |  |  |  |  | 2023-09-11 |  | TRIPOD
B02154 | B065B_B02154OD_ADENIUMBERUNTUNG | Central |  | Decomm |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-06-01 |  |  | 2023-06-07 | 2024-06-19 | Rectificating | 2023-08-09 | 2024-07-12 | CD//Sapian | 2023-07-25 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002039889 |  |  |  |  | 2023-09-20 |  | UNIPOLE
K00064 | K004A_K00064OD_MERGONGINDAH | Northern | 4087K | Swap |  | 2023Q4 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-06-21 | 2023-06-26 |  | 2023-06-27 |  | Closed | 2023-07-05 | 2023-08-22 | CD//Quah | 2023-08-22 | Celcom Digi_RAN-GCI-TSS-Northern-20230622-0033 | DU00002039890 |  |  | 2023-10-12 | 2023-09-16 |  | In-Building System | BOOM | 5 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 3
P00042 | P035D_P00042OD_BEACH_ST | Northern |  | Decomm |  | 2023Q3 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-04-28 |  |  |  | 2023-06-20 |  | 2023-06-20 | 2023-08-28 | CD//Rohizam | 2023-08-05 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2/Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230726-0024 | DU00002039891 |  |  |  |  | 2023-09-13 |  | BOOM
B02799 | B061A_B02799OD_BGNJAISUTARASEK5SA | Central | 1175K | Swap |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-05-26 | 2023-05-31 |  | 2023-06-02 |  | Closed | 2023-06-03 | 2023-06-10 | CD//Ali akaram | 2023-06-08 | CelcomDigi_RAN_Datasco_TSS_Central_20230529_0023 | DU00002039892 |  |  | 2023-10-25 | 2023-10-19 |  | Pole | BOOM WALL-MOUNTED | 4 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x5,Dismantle Celcom all RRU&BBU |  | 12
9687B | Rampangi 2 | Sarawak |  | Modernization |  | 2023Q4 | SH | Trintel | 4.6 TSSR Approved |  | 2023-06-17 | 2023-07-05 |  | 2023-07-08 |  | Closed | 2023-07-10 | 2023-07-18 | E//Hannah | 2023-07-18 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230622 | DU00002039893 |  |  | 2023-08-05 | 2023-07-31 |  | Pole | 30M Rapole | 32 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
B00286 | B061F_B00286OD_BDRTSKPUTRI | Central |  | Decomm |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-06-23 |  |  |  | 2023-06-22 |  | 2023-06-22 | 2023-10-17 | CD//Norhaliza | 2023-10-09 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230626_decom reraise | DU00002039894 |  |  |  |  | 2023-07-19 |  | UNIPOLE
B00681 | B065B_B00681OD_SERENDAH | Central | 1095K | Swap |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-06-03 | 2023-06-28 |  | 2023-07-03 |  | Closed | 2023-07-04 | 2024-01-02 | CD//Norhaliza | 2024-01-02 | CelcomDigi_RAN_Datasco_TSS_Central_20230428_0018 | DU00002039895 |  |  | 2023-08-23 | 2023-08-21 |  | Tower | TOWER | 61 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 1
A00207 | KGBARUAULONG | Northern | 4063K | Swap |  | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-06-04 | 2023-06-14 |  | 2023-06-16 |  | Closed | 2023-06-21 | 2023-07-13 | CD//Quah | 2023-07-13 | Celcom Digi_RAN-YPTT-TSS-Northern-20230606-0017 | DU00002039896 |  |  | 2023-08-12 | 2023-08-11 |  | Minaret | MINARET | 3M | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
B00101 | B060A_B00101OD_BJUNTAIBISTARI | Central |  | Decomm |  | 2023Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-27 | 2023-06-26 |  |  | 2023-06-15 |  | 2023-06-19 | 2023-11-16 | CD//Tee | 2023-07-13 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002039897 |  |  |  |  | 2023-07-22 | Tower | 3LEGGED | 80
K00890 | K004B_K00890OD_TMN_ANGGERIK_AS | Northern |  | Decomm |  | 2023Q4 | ZA | GCI | 4.6 TSSR Approved |  | 2023-07-26 |  |  |  | 2023-07-26 |  | 2023-07-21 | 2023-08-24 | CD//Quah | 2023-08-17 | Celcom Digi_RAN-GCI-TSS-Northern-20230612-0026/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002039898 |  | No TX Info, Photo not enough |  |  | 2023-09-18 |  | MINARET
B02623 | B058B_B02623OD_TMNGEMBIRAKLG | Central |  | Decomm |  | 2023Q3 | SS | Futong | 4.6 TSSR Approved |  | 2023-06-30 |  |  |  | 2023-07-22 |  | 2023-07-24 | 2023-08-18 | CD//Ali akaram | 2023-08-14 | CelcomDigi_RAN_Futong_TSS_Central_20230626_decom reraise | DU00002039899 |  |  |  |  | 2023-07-28 | Lampole | LAMP_POLE | 24M
Q00265 | Q118B_Q00265OD_MLNGKIDURONG | Sarawak |  | Decomm |  | 2023Q3 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-07-31 |  |  |  | 2023-08-02 |  | 2023-08-03 | 2023-09-11 | CD//John | 2023-08-03 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230913 | DU00002039900 |  | 1/9: uncompleted info |  |  | 2025-10-30 |  | TOWER
B01771 | B061A_B01771OD_KJSSETIAALAM | Central |  | Decomm |  | 2023Q3 | MA | Magicell | 4.6 TSSR Approved |  | 2023-06-09 |  |  |  | 2024-05-02 |  | 2023-06-21 | 2024-05-29 | CD//Tee | 2023-07-22 | CelcomDigi_RANMW_Magicell_TSS_Central_20230612_0005 / CelcomDigi_TX-RAN_Magicell_TSS_Central_20230818 | DU00002039901 |  |  |  |  | 2023-07-25 |  | MONOPOLE
P00036 | P035E_P00036OD_BKTDUMBAR | Northern |  | Decomm |  | 2023Q3 | SM | GCI | 4.6 TSSR Approved |  | 2023-05-11 |  |  |  | 2023-06-28 |  | 2023-07-14 | 2023-10-09 | CD//Affendi | 2023-07-17 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1 | DU00002039902 |  | No TX Info, Photo not enough |  |  | 2023-08-07 |  | TOWER
Q00246 | Q118B_Q00246OD_JLNSEBIEW | Sarawak |  | Decomm |  | 2023Q3 | SH | YPTT | 4.6 TSSR Approved |  | 2023-05-27 |  |  |  | 2023-06-24 |  | 2023-07-26 | 2023-12-09 | CD//John | 2023-07-27 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20230622 | DU00002039903 |  |  |  |  | 2023-12-13 |  | MONOPOLE
B02754 | B057C_B02754OD_BT_8_2 JLN_GOMBAK | Central |  | Decomm |  | 2023Q4 | CR | Datasco | 4.6 TSSR Approved |  | 2023-08-08 |  |  |  | 2024-08-02 |  | 2023-08-22 | 2025-03-24 | CD//Sapian | 2023-08-23 | CelcomDigi_RAN_Datasco_TSS_Central_20230808 | DU00002039904 |  |  |  |  | 2023-12-06 |  | BOOM WALL-MOUNTED
B00999 | B058B_B00999IB_SHAWCENTREPOINT | Central |  | Decomm |  | 2023Q3 | CR | Datasco | 4.6 TSSR Approved |  | 2023-05-26 |  |  |  | 2023-08-15 |  | 2023-08-16 | 2023-10-02 | CD//Sofiah | 2023-09-19 | CelcomDigi_RAN_Datasco_TSS_Central_20230529_0023 | DU00002039905 |  |  |  |  | 2023-09-30 |  | BOOM
B01057 | B057C_B01057OD_UIA6GBK | Central |  | Decomm |  | 2023Q4 | CR | Datasco | 4.6 TSSR Approved |  | 2023-07-31 |  |  |  | 2023-11-15 |  | 2023-11-16 |  | CD//Norhaliza | 2023-12-15 | CelcomDigi_RAN_Datasco_TSS_Central_20230802 | DU00002039906 |  | 1) Missing antenna tx photo at NE 2) Missing FE part |  |  | 2024-03-13 |  | AESTHETIC MONOPOLE
Q00593 | Q132C_Q00593IB_IMPERIALMALLID | Sarawak | 9076K | Swap |  | 2023Q4 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-07-03 | 2023-07-14 |  | 2023-08-18 |  | Closed | 2023-08-29 | 2023-08-30 | CD//John | 2023-08-30 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 - Copy | DU00002039907 |  | Wrong site id, missing ODF photo | 2024-01-19 | 2023-11-01 |  | Portables BTS | IN-BUILDING |  | Add R8862A S1800 x3 + R8862A S2100 x3 + R8862A S2601 x3,Dismantle all celcom BBU&RRU
B00419 | B061D_B00419OD_SEK20SA2 | Central |  | Decomm |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-01 |  |  |  | 2023-08-02 |  | 2023-07-06 | 2023-12-18 | CD//Sapian | 2023-11-21 | CelcomDigi_RAN_GTSB_TSS_Central_20230606_0027 | DU00002039908 |  |  |  |  | 2023-12-26 |  | BOOM
C00013 | C046C_C00013IB_GENTINGSTAFF2 | Central |  | Decomm |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-23 |  |  |  | 2023-10-10 |  | 2023-10-20 |  | CD//Sofiah | 2023-11-23 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_0032 | DU00002039909 |  | Please provide celcom cabinet/rack photo |  |  | 2025-12-10 |  | BOOM
A00467 | CBKGRELANG | Northern | 4179P | Swap |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-06-12 | 2023-06-19 |  | 2023-06-22 |  | Closed | 2023-07-05 | 2023-07-13 | CD//Quah | 2023-07-13 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230613-0025 | DU00002039910 |  |  | 2023-08-21 | 2023-08-15 |  | Tower | TOWER | 62 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 1
B02538 | B060A_B02538OD_KGSRITIRAMJAYA | Central | 1161K | Swap |  | 2023Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2023-07-04 | 2023-07-06 |  | 2023-07-10 |  | Closed | 2023-07-11 | 2023-08-14 | CD//Ali akaram | 2023-08-14 | CelcomDigi_RANMW_AllStar_TSS_Central_20230627_0007 | DU00002039911 |  |  | 2023-10-12 | 2023-10-09 |  | Monopole | LAMP_POLE | 30 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 1
K00850 | K004B_K00850OD_TMNKERANJI_AS | Northern |  | Decomm |  | 2023Q4 | SM | GCI | 4.6 TSSR Approved |  | 2023-06-16 |  |  |  | 2023-06-24 |  | 2023-06-26 | 2023-08-19 | CD//Quah | 2023-07-20 | Celcom Digi_RAN-GCI-TSS-Northern-20230616-0030/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002039912 |  | No TX Info, Photo not enough |  |  | 2023-10-16 | Lampole | RAPID ASSEMBLY POLE (RAPOLE) | 30
K00486 | K004B_K00486OD_PASARBESARAS | Northern |  | Decomm |  | 2023Q4 | SM | GCI | 4.6 TSSR Approved |  | 2023-06-22 |  |  |  | 2023-07-05 |  | 2023-07-06 | 2023-08-15 | CD//Rohizam | 2023-08-05 | Celcom Digi_RAN-GCI-TSS-Northern-20230613-0027/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002039913 |  |  |  |  | 2023-10-12 |  | LAMP_POLE
P00179 | P035C_P00179OD_DWNPERNIAGAANMELAYU | Northern |  | Decomm |  | 2023Q3 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-05-19 |  |  |  | 2023-08-03 |  | 2023-08-08 | 2023-09-06 | CD//Rohizam | 2023-08-09 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1/Celcom Digi_RAN-CCSMY-TSS Decomm-Northern-20240131-0091 | DU00002039914 |  | 18/8:Please include Celcom Cabinet and Zoom in photo TX |  |  | 2023-09-04 |  | BOOM
B00081 | B062B_B00081OD_PANCHANGBEDENA | Central |  | Decomm |  | 2023Q4 | CR | Magicell | 4.6 TSSR Approved |  | 2023-05-30 |  |  |  | 2023-08-22 |  | 2023-07-21 | 2023-12-18 | CD//Sapian | 2023-07-26 | CelcomDigi_RAN_Magicell_TSS_Central_20230601_0011 | DU00002039915 |  |  |  |  | 2023-10-04 |  | 3LEGGED
Q00474 | Q124B_Q00474OD_TMNSRIMATANG | Sarawak |  | Decomm |  | 2023Q4 | SH | South Pacific | 4.6 TSSR Approved |  | 2023-10-03 |  |  |  | 2023-10-04 |  | 2023-10-07 | 2023-11-06 |  | 2023-10-07 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230622 | DU00002039916 |  |  |  |  | 2023-11-10 |  | TOWER
B02272 | B061A_B02272SC_FZM2JLNPLUMBUMU7_USHLM | Central | 1151K | Swap |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-13 | 2023-06-27 |  | 2023-07-07 |  | Closed | 2023-07-10 | 2023-07-17 | CD//Sapian | 2023-07-17 | CelcomDigi_RANMW_GTSB_TSS_Central_20230616_0004 | DU00002039917 |  |  | 2023-10-12 | 2023-09-29 |  | Wall mount boom | SMALL CELL | 1M | Add BS8932 x3,Dismantle Celcom small cell
B01049 | B062A_B01049OD_BT37SEKENDI | Central | 1107K | Swap |  | 2023Q4 | HQ 6 | CCSMY | 4.6 TSSR Approved |  | 2023-06-21 | 2023-06-26 |  | 2023-07-04 |  | Closed | 2023-07-05 | 2023-07-26 | CD//Norhaliza | 2023-07-25 | CelcomDigi_RAN_CCSMY_TSS_Central_20230622_0004 | DU00002039918 |  |  | 2023-09-12 | 2023-09-07 |  | Tower | TOWER | 61 | Add R9264H M901821 x3 + R9264M M1821 x3 + R8862A S2601 x6,Dismantle Celcom all RRU&BBU |  | 123
Q00356 | Q132C_Q00356OD_JLNKWANGTUNG | Sarawak | 9071K | Swap |  | 2023Q4 | BY | AllStar | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦nok,site onwer not allow to add AAU on the structure | 2023-06-28 | 2023-06-26 |  | 2023-06-28 |  | Closed | 2023-07-03 | 2023-07-05 | CD//John | 2025-04-22 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230608-0006 | DU00002039919 | Remarks: Solution TSSR/BOM Changed NIC_S2_Change MM to BI_owner reject_EDOTCO (M) - NONE CSU | Remarks: Solution Changed | 2025-09-19 | 2025-09-12 |  | In-Building System | BOOM | 6 | Add R8862A S9000x3+R8894E M1821x3+R8862A S2601x3,Dismantle | 0 | 0
A00801 | A042A_A00801OD_MN_KGKURNIA | Northern | 4132P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039920 | [6 empty] | TOWER
B01986 | B061D_B01986OD_JLNPINANG | Central |  | Decomm |  | 2023Q4 | SS | Solusi | 4.6 TSSR Approved |  | 2024-01-11 | [5 empty] | 2023-10-14 | 2023-12-18 | CD//Ali Akaram | 2023-10-26 | BOQ CelcomDigi_RAN_Solusi_Standard PR TSS_Central_20240115 | DU00002039921 |  |  |  |  | 2023-10-09 |  | MINIMAST
P00325 | P035F_P00325OD_SCSUSM | Northern |  | Decomm |  | 2023Q3 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-05-19 | [5 empty] | 2023-08-08 |  | CD//Affendi | 2023-08-09 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002039922 |  |  |  |  | 2023-10-03 |  | BOOM
9726C | OM Material (REL) | Sarawak |  | Modernization |  | 2023Q3 | BY | Datasco | 4.6 TSSR Approved |  | 2023-05-15 | 2023-05-17 |  | 2023-05-22 |  | Closed | 2023-05-26 | 2023-07-14 | E//Hannah | 2023-07-14 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230516-0006 | DU00002039923 |  |  | 2023-08-18 | 2023-08-02 |  | Monopole | TOWER | 30m | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle R9224E M1821(AAB) x4 |  | 2
K00489 | K004A_K00489OD_TMNUDA | Northern |  | Decomm |  | 2023Q4 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-06-08 |  |  |  | 2023-10-12 |  | 2023-10-20 | 2023-11-29 | CD//Affendi | 2023-10-27 | Celcom Digi_RAN-GTSB-TSS-Northern-20230529-0020 | DU00002039924 |  | IDU photo different location with Cabinet photo |  |  | 2023-11-01 |  | TOWER
A01139 | A042A_A01139OD_KG_SG_RANTING_TPG | Northern | 4080K | Swap |  | 2023Q4 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-08-10 | 2023-08-08 |  | 2023-08-10 |  | Rectificating | 2023-08-17 | 2023-08-22 | E//Hazida | 2023-08-22 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230626-0029 | DU00002039925 |  |  | 2023-08-10 | 2023-08-10 |  | Guide mast | LAMP_POLE | 25 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 23
B02807 | B058C_B02807OD_TMNMEWAHJAYA3KLANG | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-16 |  |  |  | 2023-05-22 |  | 2023-06-13 | 2023-10-17 | CD//Tee | 2023-06-30 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002039926 |  | Resubmit to planner |  |  | 2023-08-17 |  | BOOM
Q00030 | Q124B_Q00030OD_CB_SGCINA | Sarawak |  | Decomm |  | 2023Q4 | SH | South Pacific | 4.6 TSSR Approved |  | 2023-08-16 |  |  |  | 2023-08-19 |  | 2023-08-21 | 2024-02-15 | CD//John | 2023-08-21 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230913 | DU00002039927 |  | 22/8: All tx info & photos are missing |  |  | 2023-10-05 |  | TOWER
B00048 | B060B_B00048OD_BKTKUCINGJERAM | Central |  | Decomm |  | 2023Q3 | SS | GTSB | 4.6 TSSR Approved |  | 2023-04-28 | 2023-06-26 |  |  | 2023-06-15 |  | 2023-06-21 | 2023-07-31 | CD//Tee | 2023-07-22 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002039928 |  |  |  |  | 2023-08-01 | Tower | 4LEGGED | 60m
C00020 | C046C_C00020IB_HIGHLANDHOTEL | Central | 1927K | Swap | Decomm->On hold->Swap | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-07-17 |  |  |  | 2023-08-23 |  | 2024-08-01 | 2024-09-26 | CD//Sofiah | 2024-09-26 | CelcomDigi_RAN_GTSB_TSS_Central_20230721 | DU00002039929 |  |  | 2025-12-09 | 2025-12-05 |  |  | IN-BUILDING |  | Add R8862A S9000 x3+R8862A S1800 x3+R8862A S2100 x3, Dismantle
B01923 | B058B_B01923OD_BDRKLG | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-06 |  |  |  | 2023-06-16 |  | 2023-06-20 | 2023-11-22 | CD//Sapian | 2023-08-17 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002039930 |  |  |  |  | 2023-07-25 |  | BOOM
P00585 | P031B_P00585OD_JLNBAYANLEPAS | Northern |  | Decomm |  | 2023Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-05-20 |  |  |  | 2023-06-21 |  | 2023-06-22 | 2023-08-08 | CD//Quah | 2023-07-07 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2/Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230726-0024 | DU00002039931 |  |  |  |  | 2023-07-26 |  | BOOM
9686B | Taman Alam Sari Samariang | Sarawak |  | Modernization |  | 2023Q4 | SH | Datasco | 4.6 TSSR Approved |  | 2023-06-09 | 2023-07-05 |  | 2023-07-07 |  | Closed | 2023-07-07 | 2023-07-21 | E//Hannah | 2023-07-20 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230612-0008 | DU00002039932 |  |  | 2023-08-16 | 2023-08-10 |  | Pole | 30m Monopole | 30 | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3
B02250 | B061A_B02250OD_PSTPERNIAGAANBKTRAJA | Central | 1150K | Swap |  | 2023Q4 | IE | GTSB | 4.6 TSSR Approved |  | 2023-06-14 | 2023-06-16 |  | 2023-06-21 |  | Closed | 2023-06-27 | 2023-10-31 | CD//Norhaliza | 2023-10-30 | CelcomDigi_RANMW_GTSB_TSS_Central_20230616_0004 | DU00002039933 |  |  | 2023-09-29 | 2023-09-27 |  | In-Building System | UNIPOLE | 5m | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 1
B02769 | B061B_B02769OD_SURIAJELUTONGSA | Central | 1171K | Swap |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-05-31 | 2023-06-06 |  | 2023-06-09 |  | Closed | 2023-06-15 | 2023-07-31 | CD//Tee | 2023-07-31 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002039934 |  |  | 2023-09-05 | 2023-08-21 |  | Pole | TRIPOD | 6m | Add R9264H M901821 x4 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU
P00100 | P035F_P00100OD_PEKAKASQUARE | Northern |  | Decomm |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-05-09 |  |  |  | 2023-06-16 |  | 2023-06-16 | 2024-03-13 | CD//Shamsul | 2023-06-27 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240529-0109 | DU00002039935 |  |  |  |  | 2023-08-21 |  | BOOM
A01154 | A042A_A01154OD_BANGGOLJAS | Northern | 4082K | Swap |  | 2023Q4 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-06-18 | 2023-06-22 |  | 2023-06-26 |  | Closed | 2023-07-03 | 2023-07-14 | CD//Quah | 2023-07-13 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002039936 |  |  | 2023-08-20 | 2023-08-08 |  | Tower | TOWER | 55 | Add R9264H M901821 x3 + R9264M M1821 x3 + R8862A S2601 x6,Dismantle Celcom all RRU&BBU |  | 123
P00206 | P031B_P00206OD_TBGHAJIBYNLPS | Northern |  | Decomm |  | 2023Q3 | ZA | YPTT | 4.6 TSSR Approved |  | 2023-05-17 |  |  |  | 2023-07-14 |  | 2023-07-17 | 2024-06-19 | CD//Affendi | 2023-09-25 | Celcom Digi_RAN-YPTT-TSS-Northern-20230609-0018 | DU00002039937 |  |  |  |  | 2023-07-26 |  | BOOM
P00224 | P031A_P00224OD_KUALASGPINANG | Northern |  | Decomm |  | 2023Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-05-23 |  |  |  | 2023-06-21 |  | 2023-08-09 | 2023-08-15 | CD//Rohizam | 2023-08-09 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230720-0023/Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2 | DU00002039938 |  |  |  |  | 2023-08-17 |  | TOWER
C00713 | C046C_C00713OD_TMAWANA | Central |  | Decomm |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-07-26 |  |  |  | 2023-08-09 |  | 2023-08-10 | 2023-12-18 | CD//Norhaliza | 2023-08-18 | CelcomDigi_RAN_Magicell_TSS_Central_20230727 | DU00002039939 |  |  |  |  | 2024-06-14 |  | TOWER
B01856 | B060C_B01856OD_LATAR2 | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-07-20 |  |  |  | 2023-07-20 |  | 2023-07-26 | 2023-10-17 | CD//Ali akaram | 2023-08-17 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002039940 |  |  |  |  | 2023-08-15 |  | TOWER
A00131 | A042C_A00131OD_SPGTAIPING_RCD | Northern |  | Decomm |  | 2023Q4 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-06-15 |  |  |  | 2023-06-15 |  | 2023-06-16 | 2023-08-19 | CD//Shamsul | 2023-07-03 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230616-0026 | DU00002039941 |  | Pls include all Tx mwave link |  |  | 2023-08-23 |  | TOWER
B00273 | B060A_B00273OD_VLSGBURUNG | Central |  | Decomm |  | 2023Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2023-07-13 |  |  |  | 2023-07-17 |  | 2023-07-24 | 2023-10-17 | CD//Sapian | 2023-10-10 | CelcomDigi_RAN_AllStar_TSS_Central_20230712 | DU00002039942 |  |  |  |  | 2023-08-29 |  | TOWER
B01966 | B061F_B01966OD_LAGUNABIRU | Central | 1147K | Swap |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-06-01 | 2023-06-30 |  | 2023-07-05 |  | Closed | 2023-07-06 | 2023-08-15 | CD//Ali akaram | 2023-08-14 | CelcomDigi_RAN_Magicell_TSS_Central_20230606_0011 | DU00002039943 |  |  | 2023-08-18 | 2023-08-10 |  | Lampole | LAMP_POLE | 24 | Add R8852E S9000 x3 + A9732 M1821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 123
P00023 | P031A_P00023OD_GERTAKSANGGOL | Northern |  | Decomm |  | 2023Q3 | ZA | YPTT | 4.6 TSSR Approved |  | 2023-05-16 |  |  |  | 2023-08-01 |  | 2023-08-04 | 2024-02-15 | CD//Affendi | 2023-08-07 | Celcom Digi_RAN-YPTT-TSS-Northern-20230609-0018 | DU00002039944 |  | 1)Photo too Blur 2) Please put one photo in one Box |  |  | 2023-10-04 |  | TOWER
B01696 | B062A_B01696OD_T3_KGTLKRHU | Central | 1139K | Swap |  | 2023Q4 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-06-20 | 2023-06-26 |  | 2023-07-07 |  | Closed | 2023-07-10 | 2023-07-26 | CD//Norhaliza | 2023-07-26 | CelcomDigi_RAN_CCSMY_TSS_Central_20230620_0003 | DU00002039945 |  |  | 2023-09-12 | 2023-09-07 |  | Tower | TOWER | 46m | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
Q00287 | Q118B_Q00287OD_JLNTGKIDURONG | Sarawak |  | Decomm |  | 2023Q3 | SH | Satellite | 4.6 TSSR Approved |  | 2023-06-21 |  |  |  | 2023-06-26 |  | 2023-07-26 | 2024-07-19 | CD//John | 2023-08-14 | Celcom Digi_RAN-Satellite-TSS-Sarawak-20231009 | DU00002039946 |  | 22/8: uncompleted info & photos |  |  | 2024-02-21 |  | TOWER
B01471 | B058B_B01471OD_LEBUHSGPULOH | Central |  | Decomm |  | 2023Q3 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-05-08 |  |  |  | 2023-06-16 |  | 2023-08-03 | 2023-10-17 | CD//Ali akaram | 2023-08-14 | CelcomDigi_RAN_CCSMY_TSS_Central_20230626_decom reraise | DU00002039947 |  | TSSR and topo does not sync. Please amend topo. Thank you. |  |  | 2023-08-14 |  | MONOPOLE
B02493 | B065B_B02493OD_BDRUTAMABTGKALI | Central |  | Decomm |  | 2023Q4 | SS | GCI | 4.6 TSSR Approved |  | 2023-06-30 |  |  |  | 2023-08-18 |  | 2023-08-21 |  | CD//Sapian | 2023-08-23 | CelcomDigi_RAN_GCI_TSS_Central_20240427 | DU00002039948 |  | Missing FE part |  |  | 2023-09-28 |  | BILLBOARD
P00282 | P031B_P00282OD_TLK_TEMPOYAK | Northern | 4134K | Swap |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-15 | 2023-05-23 |  | 2023-05-30 |  | Closed | 2023-06-05 | 2023-06-12 | CD//Affendi | 2023-06-12 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0015 | DU00002039949 |  |  | 2023-07-18 | 2023-07-13 |  | Monopole | MONOPOLE | 30 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 2
A00606 | A036B_A00606OD_UPSI | Northern | 4073K | Swap |  | 2023Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-06-23 | 2023-06-27 |  | 2023-07-05 |  | Closed | 2023-07-07 | 2023-08-22 | CD//Norhaliza | 2023-08-22 | CelcomDigi_RANMW_Ascentrack_TSS_Central_20230616_0006 | DU00002039950 |  |  | 2023-09-23 | 2023-09-22 |  | Unipole | BILLBOARD | 7 | Add R8852E S9000 x3 + R8894E M1821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
A00047 | A042C_A00047OD_CB_KUALASPTG_RCC | Northern |  | Decomm |  | 2023Q4 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-06-12 |  |  |  | 2023-08-10 |  | 2023-07-27 | 2023-08-28 | CD//Shamsul | 2023-08-06 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230613-0025 | DU00002039951 |  | 21/8: Please Celcom Cabinet and Zoom in photo TX |  |  | 2023-08-21 |  | TOWER
P00207 | P031A_P00207OD_TMBALIKPULAU | Northern |  | Decomm |  | 2023Q3 | ZA | YPTT | 4.6 TSSR Approved |  | 2023-09-15 |  |  |  | 2023-09-15 |  | 2023-09-15 | 2023-11-23 | CD//Affendi | 2023-09-26 | Celcom Digi_RAN-YPTT-TSS-Northern-20230609-0018 | DU00002039952 |  |  |  |  | 2023-12-20 |  | TOWER
B00292 | B062A_B00292OD_TMSEKINCHAN | Central |  | Decomm |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-07-28 |  |  |  | 2023-08-29 |  | 2023-08-30 | 2024-05-29 | CD//Sapian | 2023-11-20 | CelcomDigi_RAN_YPTT_TSS_Central_20230729 | DU00002039953 |  |  |  |  | 2024-03-18 |  | TOWER
B00071 | B062A_B00071OD_PT16SGPJG | Central |  | Decomm |  | 2023Q4 | MA | Magicell | 4.6 TSSR Approved |  | 2023-06-16 |  |  |  | 2023-07-21 |  | 2023-08-03 | 2024-01-30 | CD//Sapian | 2023-08-17 | CelcomDigi_RAN_Magicell_TSS_Central_20230620_0014 | DU00002039954 |  |  |  |  | 2023-08-21 |  | TOWER
P00204 | P031B_P00204OD_JLNDATOISMAIL | Northern |  | Decomm |  | 2023Q3 | SM | GCI | 4.6 TSSR Approved |  | 2023-10-19 |  |  |  | 2023-10-19 |  | 2023-08-17 | 2023-10-27 | CD//Rohizam | 2023-08-17 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1 | DU00002039955 |  |  |  |  | 2023-08-23 |  | TRIPOD
B01303 | B065B_B01303OD_BUKITASA | Central |  | Decomm |  | 2023Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-07-06 |  |  |  | 2023-08-02 |  | 2023-08-04 | 2023-10-17 | CD//Norhaliza | 2023-08-18 | CelcomDigi_RANMW_Ascentrack_Central_20230706_0010 | DU00002039956 |  |  |  |  | 2023-10-11 |  | TOWER
B00500 | B062A_B00500OD_CB_SEKINCHAN | Central | 1086K | Swap |  | 2023Q4 | CR | YPTT | 4.6 TSSR Approved |  | 2023-07-08 | 2023-07-14 |  | 2023-07-18 |  | Closed | 2023-07-24 | 2023-08-17 | CD//Sapian | 2023-08-17 | CelcomDigi_RAN_YPTT_TSS_Central_20230710 | DU00002039957 |  |  | 2023-12-27 | 2023-12-06 |  | Tower | TOWER | 60m | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 1
B01402 | B061A_B01402OD_SEK7JLNPLUMBUMSHLM | Central | 1211K | Swap | Decomm->Swap | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-09-06 | 2023-08-28 |  | 2023-09-04 | 2023-08-03 | Closed | 2023-09-05 | 2023-09-20 | CD//Ali Akaram | 2023-09-18 | 0626Central-GTSB-BOQ Template (template) | DU00002039958 |  |  | 2023-11-26 | 2023-11-26 |  | Monopole | LAMP_POLE | 25 | Add R8852E S9000 x3+R8862A S2601 x3+A9732 M1821 x3,Dismantle | 123
B00647 | B062A_B00647OD_SGAIRTAWAR | Central | 1810K | Swap | Decomm->Swap | 2023Q4 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-09-01 | 2023-08-22 |  | 2023-08-23 | 2023-07-04 | Closed | 2023-07-28 | 2023-11-20 | CD//Ali Akaram | 2023-11-19 | 0626Central-CCSMY-BOQ Template (template) | DU00002039959 |  | Tx part rejected, Please check Tx decom SOW in EPMS - RESURVEY | 2023-12-12 | 2023-11-18 |  | Tower | TOWER | 77M | Add R9264M M1821 x2+R9264H M901821 x3+R8862A S2600 x5,Dismantle |  | 13
Q00468 | Q118B_Q00468OD_CB_RHAMBONG | Sarawak |  | Decomm |  | 2023Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2023-05-25 |  |  |  | 2023-09-07 |  | 2023-09-08 | 2023-09-19 | CD//John | 2023-09-08 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230913/Celcom Digi_RAN-Trintel-TSS DECOMM-Sarawak-20231130 | DU00002039960 |  | 8/9: FE info & photos are mising |  |  | 2023-12-15 |  | TOWER
B00074 | B062B_B00074OD_JLNHJHARUN | Central |  | Decomm |  | 2023Q4 | CR | Magicell | 4.6 TSSR Approved |  | 2023-05-24 |  |  |  | 2023-08-23 |  | 2023-07-21 | 2024-05-14 | CD//Sapian | 2023-07-31 | CelcomDigi_RAN_GTSB_TSS_Central_20230529_0010 | DU00002039961 |  |  |  |  | 2023-08-21 |  | 4LEGGED
C00526 | C046C_C00526IB_ARENAOFSTARS | Central |  | Decomm |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-07-25 |  |  |  | 2023-07-29 |  | 2023-08-02 | 2023-09-01 | CD//Sofiah | 2023-08-29 | CelcomDigi_RAN_GTSB_TSS_Central_20230726 | DU00002039962 |  |  |  |  | 2025-12-10 |  | IN-BUILDING
Q00082 | Q124F_Q00082IB_WISMABAPA | Sarawak |  | Decomm |  | 2023Q4 | ZB | AllStar | 4.6 TSSR Approved |  | 2023-08-01 |  |  |  | 2023-08-02 |  | 2023-08-02 | 2024-09-06 | CD//John | 2023-11-16 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230622 | DU00002039963 |  | 16/8 : wrong proposal |  |  | 2024-07-16 |  | IN-BUILDING
A00470 | A042C_A00470OD_CB_KUALASPTGTOWN | Northern |  | Decomm |  | 2023Q4 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-06-12 |  |  |  | 2023-06-16 |  | 2023-06-19 | 2023-08-28 | CD//Rohizam | 2023-07-03 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230613-0025/Celcom Digi_RAN-CCSMY-TSS Decomm-Northern-20240131-0091 | DU00002039964 |  |  |  |  | 2023-09-15 |  | MINI STRUCTURE
K00269 | K004A_K00269OD_SGKEDAH | Northern |  | Decomm |  | 2023Q4 | SM | GTSB | 4.6 TSSR Approved |  | 2023-05-25 |  |  |  | 2023-06-16 |  | 2023-06-18 | 2023-08-10 | CD//Heng | 2023-07-03 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230829-0032_V2/Celcom Digi_RAN-GTSB-TSS-Northern-20230529-0020 | DU00002039965 |  |  |  |  | 2023-09-29 |  | TOWER
B01104 | B057A_B01104OD_IPDGOMBAK | Central | 1109K | Swap |  | 2023Q4 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-07-07 | 2023-07-11 |  | 2023-07-13 |  | Closed | 2023-07-21 | 2023-11-20 | CD//Norhaliza | 2023-11-16 | CelcomDigi_RAN_YPTT_TSS_Central_20230708_0014 | DU00002039966 |  |  | 2023-12-30 | 2023-12-16 |  | Minimast | MINI STRUCTURE | 13 | Add R9264M M1821 x2+R9264H M901821 x3+R8854 S2600 x3,Dismantle |  | 13
A01196 | Kg Sg Dara Tg Malim _ Hulu Bernam Timor | Central |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 |  | Ascentrack | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002039967 | [6 empty] | TOWER
Q00278 | Q118B_Q00278OD_LIHUAHOTEL | Sarawak |  | Decomm |  | 2023Q3 | SH | YPTT | 4.6 TSSR Approved |  | 2023-05-18 |  |  |  | 2023-06-22 |  | 2023-07-26 | 2024-08-27 | CD//John | 2023-07-27 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20230613-0007 | DU00002039968 |  | 24/8:uncompleted photos & info |  |  | 2024-01-29 |  | MINI STRUCTURE
B01524 | B061F_B01524OD_MSJDSAUJANAU | Central |  | Decomm |  | 2023Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-07 |  |  |  | 2023-08-22 |  | 2023-08-22 | 2024-01-22 | CD//Sapian | 2023-08-24 | CelcomDigi_RANMW_GTSB_TSS_Central_20230609_0002 | DU00002039969 |  |  |  |  | 2023-09-27 | Lampole | LAMP_POLE
B02713 | B061A_B02713OD_TMNDAYAMAJUMERU | Central |  | Decomm |  | 2023Q3 | IE | Magicell | 4.6 TSSR Approved |  | 2023-07-25 |  |  |  | 2023-07-26 |  | 2023-07-31 | 2023-08-18 | CD//Ali Akaram | 2023-08-14 | CelcomDigi_RAN_Magicell_TSS_Central_20230727 / CelcomDigi_TX-RAN_Magicell_TSS_Central_20230818 | DU00002039970 |  |  |  |  | 2023-12-19 |  | LAMP_POLE
K00471 | K004A_K00471OD_MENTALOON | Northern | 4098K | Swap |  | 2023Q4 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-06-16 | 2023-06-26 |  | 2023-06-27 |  | Closed | 2023-07-04 | 2023-08-07 | CD//Rohizam | 2023-08-06 | Celcom Digi_RAN-GCI-TSS-Northern-20230615-0029 | DU00002039971 |  |  | 2024-01-29 | 2023-09-09 |  | Lampole | LAMP_POLE | 30 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x5,Dismantle Celcom all RRU&BBU |  | 12
9658C | Taman Ceria | Sarawak |  | Modernization |  | 2023Q4 | BY | South Pacific | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-12 |  | 2023-06-17 |  | Closed | 2023-06-19 | 2023-06-27 | E//Hannah | 2023-06-27 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230606-0003 | DU00002039972 |  |  | 2023-07-14 | 2023-07-06 |  | Monopole | Land site | 30m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
P00211 | P035E_P00211OD_TMBKTGELUGOR | Northern |  | Decomm |  | 2023Q3 | ZA | YPTT | 4.6 TSSR Approved |  | 2023-05-15 |  |  |  | 2023-07-25 |  | 2023-07-27 | 2024-02-15 | CD//Affendi | 2023-07-31 | Celcom Digi_RAN-YPTT-TSS-Northern-20230609-0018 | DU00002039973 |  | Missing Cabinet Digi and Equipement Digi to be dismantle |  |  | 2023-12-15 |  | TOWER
B01465 | B061A_B01465OD_JLNTOPAZSEK7 | Central | 1126K | Swap |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-06-23 | 2023-06-27 |  | 2023-06-30 |  | Closed | 2023-07-04 | 2023-08-28 | CD//Ali Akaram | 2023-08-26 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_0030 | DU00002039974 |  |  | 2023-10-24 | 2023-10-20 |  | Lampole | LAMP_POLE | 20 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
C00282 | C046A_C00282OD_ECORESORT | Central |  | Decomm |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-08-09 |  |  |  | 2023-09-15 |  | 2023-09-18 | 2023-12-18 | CD//Sapian | 2023-10-17 | CelcomDigi_RAN_Magicell_TSS_Central_20230811 | DU00002039975 |  |  |  |  | 2023-10-02 |  | TOWER
B00849 | B061A_B00849IB_BGNSUKSHLM | Central |  | Decomm | Decomm->On Hold->Swap->Decomm | 2023Q4 | AI | Datasco | 4.6 TSSR Approved |  | 2024-03-21 | 2024-03-25 |  | 2024-03-27 | 2023-08-02 | Under Approval | 2024-03-28 | 2024-07-19 | CD//Sofiah | 2024-07-18 | CelcomDigi_RAN_Datasco_TSS_Central_20230802 | DU00002039976 |  |  |  |  | 2024-11-16 | Portables BTS | IN-BUILDING | NA
B00046 | B061C_B00046OD_JLNKEBUN2 | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-08-29 |  |  |  | 2023-08-29 |  | 2023-09-01 |  | CD//Sapian | 2023-09-16 | 0626Central-YPTT-BOQ Template (template) | DU00002039977 |  | 1) Missing TX antenna photo at NE 2) Missing FE part 3) Pls provide dismantle TX Equipment in Dismantle List Table |  |  | 2023-08-16 |  | TOWER
B00569 | B058B_B00569OD_LUTHKLG | Central |  | Decomm |  | 2023Q3 | CR | Datasco | 4.6 TSSR Approved |  | 2023-08-08 |  |  |  | 2023-08-14 |  | 2023-08-16 | 2023-12-18 | CD//Sapian | 2023-08-23 | CelcomDigi_RAN_Datasco_TSS_Central_20230808 | DU00002039978 |  |  |  |  | 2023-09-19 |  | BOOM
P00558 | P035D_P00558OD_IPDTIMURLAUT | Northern |  | Decomm |  | 2023Q3 | SM | CCSMY | 4.6 TSSR Approved | ¦ 0129 - Pending access for TSS | 2024-05-20 |  |  |  | 2024-05-23 |  | 2024-05-24 | 2024-06-19 | CD//Affendi | 2024-06-06 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002039979 |  |  |  |  | 2023-11-30 |  | BOOM
B01175 | B058B_B01175OD_JLNPASARKLG | Central |  | Decomm |  | 2023Q3 | SS | Datasco | 4.6 TSSR Approved |  | 2023-06-20 |  |  |  | 2023-07-26 |  | 2023-07-26 | 2024-05-31 | CD//Sapian | 2023-08-14 | CelcomDigi_RAN_Datasco_TSS_Central_20230622_0028 | DU00002039980 |  |  |  |  | 2024-02-23 |  | BOOM
B01469 | B057C_B01469OD_UIA8 | Central | 1127K | Swap |  | 2023Q4 | CR | Datasco | 4.6 TSSR Approved |  | 2023-07-31 | 2023-07-27 |  | 2023-07-31 |  | Closed | 2024-06-10 | 2024-08-09 | CD//Ali Akaram | 2024-08-07 | CelcomDigi_RAN_Datasco_TSS_Central_20230726 | DU00002039981 |  |  | 2024-02-29 | 2024-02-24 |  | Monople Tree | TOWER | 38 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
P00720 | P035E_P00720OD_ISLAND_GLADES2_PP | Northern |  | Decomm |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-09-11 |  |  |  | 2023-09-13 |  | 2023-09-13 | 2023-10-09 | CD//Rohizam | 2023-09-13 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002039982 |  |  |  |  | 2023-08-07 |  | MONOPOLE
9674A | Kg Assyarikin | Sarawak |  | Modernization |  | 2023Q3 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-24 |  | 2023-05-30 |  | Closed | 2023-07-05 | 2023-07-12 | E//Hannah | 2023-07-12 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230516-0006 | DU00002039983 |  |  | 2023-08-17 | 2023-08-04 |  | Monopole | 30m Monopole | 30 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8882 S1800B(B6B) x3 | 123
B00051 | B061C_B00051OD_BT8KEMUNING | Central |  | Decomm |  | 2023Q3 | SS | Futong | 4.6 TSSR Approved |  | 2023-06-01 | [5 empty] | 2023-07-26 |  | CD//Sapian | 2023-08-04 | [CelcomDigi_RAN_GCI_TSS_Central_20240427/Celcom Digi_RAN-Futong-Standard PR TSS-Central-20241016 | DU00002039984 |  | 1. Missing antena TX photo at NE 2. Missing FE part |  |  | 2023-08-29 |  | TRIPOD
P00215 | P035E_P00215OD_JLNBTLANCHANG | Northern |  | Decomm |  | 2023Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-05-23 |  |  |  | 2023-06-21 |  | 2023-06-23 | 2023-08-08 | CD//Shamsul | 2023-07-04 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230829-0032/Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2/Celcom Digi_CD CONSOLIDATION-GTSB-TI-Northern-20240920_Old Contract | DU00002039985 |  |  |  |  | 2023-08-29 |  | BOOM
A00130 | A042B_A00130OD_KAMUNTING2_RCC | Northern |  | Decomm |  | 2023Q4 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-06-06 |  |  |  | 2023-07-05 |  | 2023-07-07 | 2024-05-28 | CD//Shamsul | 2023-07-12 | Celcom Digi_RAN-GTSB-TSS-Northern-20230529-0020 | DU00002039986 |  | No TX Info |  |  | 2023-09-19 |  | BOOM
B00822 | B058B_B00822OD_SPG4PULAI | Central |  | Decomm |  | 2023Q3 | SS | Futong | 4.6 TSSR Approved |  | 2023-05-29 |  |  | 2023-06-03 | 2024-05-06 | Closed | 2023-07-26 | 2023-10-25 | CD//Sapian | 2023-08-02 | CelcomDigi_RAN_Futong_TSS_Central_20230626_decom reraise/CelcomDigi_TX_Futong_TSS_Decom_Central_20230922 | DU00002039987 |  |  |  |  | 2023-09-13 |  | BOOM
Q00544 | Q118B_Q00544OD_DERAWAN | Sarawak | 9075K | Swap |  | 2023Q3 | SH | YPTT | 4.6 TSSR Approved |  | 2023-05-26 | 2023-06-19 |  | 2023-06-21 |  | Closed | 2023-06-22 | 2023-06-28 | CD//John | 2023-06-27 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20230529-0004 | DU00002039988 |  |  | 2024-01-16 | 2023-12-11 |  | Pole | WATER TANK | 4m | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 1
C00005 | C046C_C00005OD_TMGENTING | Central |  | Decomm |  | 2023Q4 | SM | GTSB | 4.6 TSSR Approved |  | 2024-05-18 |  |  |  | 2024-07-02 |  | 2024-07-04 |  | CD//Norhaliza | 2024-08-07 | CelcomDigi_RAN_GTSB_TSS_Central_20240423 | DU00002039989 |  |  |  |  | 2025-12-10 |  | BOOM
K00042 | K004A_K00042OD_TMJLNLANGGAR | Northern |  | Decomm |  | 2023Q4 | SM | GTSB | 4.6 TSSR Approved |  | 2023-06-26 |  |  |  | 2023-07-20 |  | 2023-07-21 | 2023-08-19 | CD//Quah | 2023-08-17 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230829-0032/Celcom Digi_RAN-GTSB-TSS-Northern-20230529-0020 | DU00002039990 |  |  |  |  | 2023-09-29 |  | TOWER
P00020 | P035C_P00020OD_HTLCENTRAL | Northern | 4115K | Swap |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-15 | 2023-06-01 |  | 2023-06-07 |  | Closed | 2023-06-12 | 2023-07-03 | CD//Heng | 2023-07-03 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0015 | DU00002039991 |  |  | 2023-09-12 | 2023-09-12 |  | Pole | BOOM | 3/4/5 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x5,Dismantle Celcom all RRU&BBU |  | 12
B00676 | B058A_B00676OD_TNBKAPAR | Central |  | Decomm |  | 2023Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-09-05 |  |  |  | 2023-09-04 |  | 2023-09-07 | 2023-09-07 | CD//Sapian | 2023-10-10 | CelcomDigi_RAN_GTSB_TSS_Central_20230907 | DU00002039992 |  |  |  |  | 2024-11-07 |  | MINI STRUCTURE
B00289 | B065B_B00289OD_TMHULUYAMBHARU | Central | 1070K | Swap |  | 2023Q4 | XH | AllStar | 4.6 TSSR Approved |  | 2023-10-31 | 2023-11-01 |  | 2024-01-22 |  | Closed | 2024-01-15 | 2024-01-22 | CD//Ali akaram | 2023-11-28 | CelcomDigi_RAN_Allstar_TSS_Central_20231101 | DU00002039993 |  |  | 2024-02-26 | 2024-02-03 |  | Tower | GUYED MAST | 45 | Add R9264H M901821 x3,Dismantle |  | 12
9684C | Desa Sejijak MP | Sarawak |  | Modernization |  | 2023Q4 | SH | South Pacific | 4.6 TSSR Approved |  | 2023-06-14 | 2023-06-26 |  | 2023-07-06 |  | Closed | 2023-07-06 | 2023-07-21 | E//Hannah | 2023-07-20 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230612-0004 | DU00002039994 |  |  | 2023-08-11 | 2023-08-07 |  |  | Land site | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
Q00582 | Q118B_Q00582OD_UPMBTU | Sarawak |  | Decomm |  | 2023Q3 | ZB | CCSMY | 4.6 TSSR Approved |  | 2023-07-17 |  |  |  | 2023-07-27 |  | 2023-07-31 | 2023-09-07 | CD//John | 2023-08-01 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230614-0008 | DU00002039995 |  |  |  |  | 2023-11-27 |  | MONOPOLE
B01335 | B060B_B01335OD_LDGTLKPIAH | Central |  | Decomm |  | 2023Q4 | CR | AllStar | 4.6 TSSR Approved |  | 2023-07-25 |  |  |  | 2023-07-31 |  | 2023-08-03 | 2023-10-17 | CD//Norhaliza | 2023-08-18 | CelcomDigi_RAN_AllStar_TSS_Central_20230711 | DU00002039996 |  |  |  |  | 2023-08-29 |  | TOWER
B02056 | B065B_B02056OD_TMNDAMAIKKB | Central | 1148K | Swap |  | 2023Q4 | HQ 6 | Futong | 4.6 TSSR Approved |  | 2023-06-28 | 2023-06-30 |  | 2023-07-04 |  | Closed | 2023-07-05 | 2023-07-31 | CD//Sapian | 2023-07-31 | CelcomDigi_RANMW_Futong_TSS_Central_20230630_0005 | DU00002039997 |  |  | 2023-09-19 | 2023-09-14 |  | Monopole | MONOPOLE | 39 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 23
B01311 | B057B_B01311OD_BTCAVES2 | Central | 1118K | Swap |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-05-16 | 2023-06-26 |  | 2023-07-04 |  | Closed | 2023-07-13 | 2023-07-27 | CD//Ali akaram | 2023-07-27 | CelcomDigi_RAN_GTSB_TSS_Central_20230517_0024 | DU00002039998 |  |  | 2023-08-15 | 2023-08-10 |  | Lampole | TOWER | 20M | Add R9264H M901821 x4 + R9264M M1821 x1 + R8862A S2601 x5,Dismantle Celcom all RRU&BBU |  | 1
B01314 | B061F_B01314OD_KM13GUTRIEHWY | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-27 |  |  |  | 2023-05-31 |  | 2023-06-07 | 2023-09-19 | CD//Sapian | 2023-06-09 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002039999 |  |  |  |  | 2023-09-04 |  | TOWER
Q00339 | Q132C_Q00339OD_TMMYYEX | Sarawak | 9068K | Swap |  | 2027 | SH | Datasco | 4.6 TSSR Approved |  | 2023-07-06 | 2023-07-17 |  | 2023-07-24 |  | Closed | 2024-03-26 | 2024-03-29 | CD//John | 2025-04-26 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 - Copy | DU00002040000 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed |  |  |  | In-Building System | BOOM | 6 | Add R8862A S9000x3+R8894E M1821x3+R8862A S2601x3,Dismantle | 0 | 0
Q00626 | Q132C_Q00626IB_BINTANGPLAZAID | Sarawak |  | Decomm |  | 2023Q4 | SH | Trintel | 4.6 TSSR Approved |  | 2024-04-22 |  |  |  | 2024-04-22 |  | 2024-04-24 | 2024-05-27 | CD//Sofiah | 2024-05-07 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240406 | DU00002040001 |  | 21/8: uncompleted info & photos |  |  | 2024-10-31 |  | IN-BUILDING
Q00141 | Q124F_Q00141OD_SESCOKCH | Sarawak |  | Site Out (Decomm) | Decomm->On Hold->Site Out->Replacement, Site Out (Decomm) | 2023Q4 |  | Magicell | 14.1 TSSR Not Required (Decomm by CD) | E.co revert fully decomm | 2025-09-18 |  |  |  |  | To be Submitted |  |  | CD//John |  | SQ202508220455-Magicell | DU00002040002 |  |  |  |  | 2025-06-26 |  | BOOM
Q00505 | Q132C_Q00505OD_JLNTMNPIASAU | Sarawak |  | Decomm |  | 2023Q4 | SH | Magicell | 4.6 TSSR Approved |  | 2023-06-26 |  |  |  | 2023-07-13 |  | 2023-07-25 | 2023-08-06 | CD//John | 2023-07-26 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622/0612Sarawak-Magicell-BOQ Template (template) | DU00002040003 |  |  |  |  | 2025-06-17 |  | TOWER
B00166 | B061A_B00166OD_UITMDELIMA | Central |  | Decomm |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-07 |  |  |  | 2023-08-15 |  | 2023-08-16 | 2023-10-02 | CD//Norhaliza | 2023-09-20 | CelcomDigi_RANMW_GTSB_TSS_Central_20230609_0002 | DU00002040004 |  |  |  |  | 2024-02-07 |  | MONOPOLE
B01179 | B060A_B01179OD_TMNSULUHBISTRI | Central | 1112K | Swap |  | 2023Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-05-01 | 2023-05-04 |  | 2023-05-06 |  | Closed | 2023-05-19 | 2023-08-21 | CD//Norhaliza | 2023-08-21 | CelcomDigi_RAN_GTSB_TSS_20230505_0023 | DU00002040005 |  |  | 2023-07-13 | 2023-07-10 |  | Tower | MINI STRUCTURE | 25 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
Q00680 | Q132A_Q00680OD_RHMAMAT | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2023Q3 | AD | Magicell | 4.6 TSSR Approved |  | 2025-06-16 |  | 2025-06-17 |  | 2025-07-14 |  | 2025-07-29 | 2025-10-31 | E//John | 2025-09-09 | SQ202506110081-Magicell/SQ202507140221-Magicell | DU00002040006 |  |  |  |  | 2025-10-16 |  | TOWER
B01256 | B058B_B01256OD_PR_JLNSGPUTUS | Central |  | Decomm |  | 2023Q3 | SS | Datasco | 4.6 TSSR Approved |  | 2023-07-05 |  |  |  | 2023-07-26 |  | 2023-07-21 | 2023-10-17 | CD//Norhaliza | 2023-10-09 | CelcomDigi_RAN_DATASCO_Central_20230706_0031 | DU00002040007 |  |  |  |  | 2023-09-14 |  | LAMP_POLE
B00358 | B058B_B00358OD_TMSEMENTA | Central |  | Decomm |  | 2023Q3 | MA | CCSMY | 4.6 TSSR Approved |  | 2024-05-03 |  |  |  | 2024-05-03 |  | 2024-05-20 | 2024-07-16 | CD//Sapian | 2024-05-31 | CelcomDigi_RAN_CCSMY_TSS_Central_20230626_decom reraise | DU00002040008 |  |  |  |  | 2024-04-26 |  | 4LEGGED
B00274 | B060B_B00274OD_VLSGTERAP | Central |  | Decomm |  | 2023Q4 | CR | AllStar | 4.6 TSSR Approved |  | 2023-07-29 |  |  |  | 2023-07-31 |  | 2023-08-02 | 2023-08-19 | CD//Sapian | 2023-08-16 | CelcomDigi_RAN_Allstar_TSS_Central_20230721 | DU00002040009 |  |  |  |  | 2023-12-26 |  | TOWER
P00417 | P035F_P00417OD_PISA | Northern |  | Decomm |  | 2023Q3 | MH | GTSB | 4.6 TSSR Approved |  | 2023-05-18 |  |  |  | 2023-06-15 |  | 2023-06-15 | 2023-08-10 | CD//Affendi | 2023-06-27 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230829-0032/Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2/Celcom Digi_CD CONSOLIDATION-GTSB-TI-Northern-20240920_Old Contract | DU00002040010 |  | Need Capture Unused antenna & ODU photo |  |  | 2023-08-09 |  | BOOM
P00382 | BTNBALIKPULAU_G9 | Northern | 4142K | Swap |  | 2023Q3 | MH | YPTT | 4.6 TSSR Approved |  | 2023-05-11 | 2023-05-13 |  | 2023-05-16 |  | Closed | 2023-05-17 | 2023-05-21 | CD//Affendi | 2023-05-18 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0009 | DU00002040011 |  |  | 2023-06-28 | 2023-06-28 |  | Monopole | LAMP_POLE | 15 | Add R9264H M901821 x2,Dismantle
K00887 | K004B_K00887OD_KG_TLK_CHENGAI_AS | Northern | 4107K | Swap |  | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-06-05 | 2023-06-09 |  | 2023-06-12 |  | Closed | 2023-06-19 | 2023-07-07 | CD//Heng | 2023-07-03 | Celcom Digi_RAN-YPTT-TSS-Northern-20230606-0017 | DU00002040012 |  |  | 2023-09-17 | 2023-09-18 |  | Monopole | POLE | 30 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 13
Q00675 | Q132A_Q00675OD_T3_BT46BTUMYY | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040013 | [6 empty] | 3LEGGED
P00320 | P035E_P00320OD_TMJELUTONG | Northern |  | Decomm |  | 2023Q3 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-07-23 |  |  |  | 2023-08-02 |  | 2023-08-08 | 2023-08-19 | CD//Rohizam | 2023-08-08 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002040014 |  |  |  |  | 2023-10-27 |  | TOWER
B00260 | B057B_B00260OD_TMNJASASGTUA | Central |  | Decomm |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-05-10 |  |  |  | 2023-07-06 |  | 2023-07-06 | 2023-12-18 | CD//Norhaliza | 2023-07-26 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002040015 |  |  |  |  | 2023-10-28 |  | MINI STRUCTURE
B01432 | B061C_B01432OD_JLNBKTNAGA | Central |  | Decomm |  | 2023Q3 | SS | GCI | 4.6 TSSR Approved |  | 2023-05-20 |  |  |  | 2024-06-12 |  | 2023-07-31 | 2024-07-16 | CD//Sapian | 2023-08-16 | CelcomDigi_RAN_GCI_TSS_Central_20240427 | DU00002040016 |  |  |  |  | 2023-08-17 |  | AESTHETIC MONOPOLE
9695A | Desa Bahagia | Sarawak |  | Modernization |  | 2023Q4 | BY | YPTT | 4.6 TSSR Approved |  | 2023-06-12 | 2023-06-21 |  | 2023-06-24 |  | Closed | 2023-07-04 | 2023-07-14 | E//Hannah | 2023-07-21 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20230613-0007 | DU00002040017 |  |  | 2023-08-22 | 2023-08-16 |  | Monopole | 30m Rapole | 30 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
P00186 | P035C_P00186OD_JLNBURMAH | Northern | 4126K | Swap |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-31 | 2023-06-08 |  | 2023-06-10 |  | Closed | 2023-06-13 | 2023-06-17 | CD//Affendi | 2023-06-15 | Celcom Digi_RAN-GCI- TSS-Northern-20230509-0016 | DU00002040018 |  |  | 2023-08-24 | 2023-08-21 |  | Pole | BOOM | 5 | Add R8852E S9000 x3 + R8894E M1821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
B00133 | B061A_B00133OD_SEK2SHLM | Central |  | Decomm |  | 2023Q4 | MA | Datasco | 4.6 TSSR Approved |  | 2023-07-31 |  |  |  | 2023-09-27 |  | 2023-09-29 | 2024-01-22 | CD//Sapian | 2023-10-04 | CelcomDigi_RAN_Datasco_TSS_Central_20230802 | DU00002040019 |  |  |  |  | 2023-12-20 |  | TRIPOD
K00580 | K004A_K00580OD_KOLEJINSANIAH_RDC | Northern |  | Decomm |  | 2023Q4 | MH | GTSB | 4.6 TSSR Approved |  | 2023-06-06 |  |  |  | 2023-06-20 |  | 2023-06-21 | 2023-08-08 | CD//Rohizam | 2023-08-03 | Celcom Digi_RAN-GTSB-TSS-Northern-20230529-0020/Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20240305-0096 | DU00002040020 |  |  |  |  | 2023-09-26 |  | BOOM
B01844 | B058C_B01844OD_RD_BDRPUTERIKLG | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-06-26 |  |  |  | 2023-07-11 |  | 2023-07-11 | 2023-09-01 | CD//Norhaliza | 2023-07-20 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002040021 |  | Solution provided - 10/8 |  |  | 2023-08-03 |  | BOOM
B02737 | B058B_B02737OD_ALAMAVENUESCT | Central |  | Decomm |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-05-19 |  |  |  | 2023-08-24 |  | 2023-08-25 | 2023-09-07 | CD//Sapian | 2023-08-25 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230626_decom reraise | DU00002040022 |  |  |  |  | 2023-09-13 |  | BOOM
C00018 | C046C_C00018IB_RESORTHOTEL | Central |  | Decomm |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-12 |  |  |  | 2023-08-03 |  | 2023-07-25 | 2023-12-18 | CD//Sofiah | 2023-08-29 | CelcomDigi_RAN_GTSB_TSS_Central_20230616_0029 | DU00002040023 |  |  |  |  | 2025-12-10 |  | IN-BUILDING
B00846 | B061A_B00846IB_BGNDARULEHSAN | Central | 1103K | Swap |  | 2023Q4 | CR | Datasco | 4.6 TSSR Approved |  | 2023-08-08 | 2023-08-09 |  | 2023-08-17 |  | Closed | 2023-08-24 | 2023-11-24 | CD//Sofiah | 2023-11-24 | CelcomDigi_RAN_Datasco_TSS_Central_20230808 | DU00002040024 |  |  | 2023-11-22 | 2023-10-20 |  | Portables BTS | IN-BUILDING | NA | Add R8862A S1800 x1 + R8862A S2100 x1,Dismantle all celcom BBU&RRU
A00421 | A042A_A00421OD_BT4KGPASIR | Northern |  | Decomm |  | 2023Q4 | MH | GCI | 4.6 TSSR Approved |  | 2023-06-19 |  |  |  | 2023-06-21 |  | 2023-06-22 | 2023-09-25 | CD//Rohizam | 2023-08-06 | Celcom Digi_RAN-GCI-TSS-Northern-20230619-0031/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240529-0109 | DU00002040025 |  | 15/8: Need include Celcom Cabinet for relocation |  |  | 2023-08-30 |  | TOWER
A00795 | A036B_A00795OD_TMNMALIM | Central |  | Decomm |  | 2023Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-06-05 |  |  |  | 2023-08-17 |  | 2023-08-18 | 2023-12-18 | CD//Sapian | 2023-08-23 | Celcomdigi_RAN_Ascentrack_TSS_Central_20230606_0021 | DU00002040026 |  |  |  |  | 2023-10-11 |  | AESTHETIC MONOPOLE
B00583 | B065A_B00583OD_SNGRFRUITVALEY | Central | 1089K | Swap |  | 2023Q3 | XH | GTSB | 4.6 TSSR Approved |  | 2023-05-22 | 2023-05-29 |  | 2023-06-07 |  | Closed | 2023-06-15 | 2023-06-17 | CD//Sapian | 2023-06-15 | CelcomDigi_RAN_GTSB_TSS_Central_20230523_0025 | DU00002040027 |  |  | 2023-08-25 | 2023-08-21 |  | Minimast | GUYED MAST | 30M | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
B00298 | B062B_B00298OD_VLTEBUKPULAI | Central |  | Decomm |  | 2023Q4 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-06-26 |  |  |  | 2024-01-19 |  | 2024-01-21 | 2024-02-20 | CD//Norhaliza | 2024-02-06 | CelcomDigi_RAN_CCSMY_TSS_Central_20230627_0007 | DU00002040028 |  |  |  |  | 2023-12-22 |  | TOWER
P00200 | P031B_P00200OD_SUNGAITIRAM | Northern |  | Decomm |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-06-07 |  |  |  | 2023-07-10 |  | 2023-06-15 | 2023-10-27 | CD//Affendi | 2023-06-27 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1 | DU00002040029 |  | No TX Info, Photo not enough 30/8:Please include Photo MW antenna & ODU for UNUSED link NT03439 (P00200-P00030) |  |  | 2023-08-24 |  | TRIPOD
B02239 | B061F_B02239OD_JLNSETIAKUANG | Central | 1149K | Swap |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-05-31 | 2023-06-06 |  | 2023-06-12 |  | Closed | 2023-06-12 | 2023-06-13 | CD//Sapian | 2023-06-13 | CelcomDigi_RAN_Magicell_TSS_Central_20230601_0011 | DU00002040030 |  |  | 2023-08-19 | 2023-08-16 |  | Tower | TOWER | 45m | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 2
B01591 | B061A_B01591OD_UITMKOLEJMAWAR | Central | 1131K | Swap |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-17 | 2023-06-26 |  | 2023-07-06 |  | Closed | 2023-07-06 | 2023-08-16 | CD//Ali akaram | 2023-08-16 | CelcomDigi_RANMW_GTSB_TSS_Central_20230620_0005 | DU00002040031 |  |  | 2023-10-22 | 2023-10-09 |  |  | RAPID ASSEMBLY POLE (RAPOLE) | 30 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x5,Dismantle Celcom all RRU&BBU |  | 13
Q00003 | Q124F_Q00003OD_CB_TMSANTUBONG | Sarawak |  | Decomm |  | 2023Q4 | SH | AllStar | 4.6 TSSR Approved |  | 2023-07-24 |  |  |  | 2023-08-02 |  | 2023-08-15 | 2024-02-15 | CD//John | 2023-08-15 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230608-0006/0612Sarawak-AllStar-BOQ Template (template).xls | DU00002040032 |  | 16/8: Uncompleted info & photos 2023-08-02 Missing RAN PHOTO and info 2023-07-07 Missing TX photos and info |  |  | 2023-11-29 |  | TOWER
C00012 | C046C_C00012IB_GENTINGSTAFF1 | Central |  | Decomm |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-08-11 |  |  |  | 2023-09-15 |  | 2023-09-18 | 2025-07-29 | CD//Sofiah | 2023-11-23 | CelcomDigi_RAN_GTSB_TSS_Central_20230815 | DU00002040033 |  |  |  |  | 2025-12-10 |  | IN-BUILDING
B01217 | B057C_B01217OD_KM28ALGSENDAYU | Central |  | Decomm |  | 2023Q4 | CR | Magicell | 4.6 TSSR Approved |  | 2023-07-07 |  |  |  | 2023-07-10 |  | 2023-07-28 | 2023-12-21 | CD//Sapian | 2023-08-15 | CelcomDigi_RAN_Magicell_TSS_Central_20230707_0021 | DU00002040034 |  |  |  |  | 2023-10-26 |  | TOWER
B02315 | B061C_B02315OD_ALAMIMPIANSEK35SHLM | Central |  | Decomm |  | 2023Q3 | SH | GCI | 4.6 TSSR Approved |  | 2023-05-23 |  |  |  | 2024-06-04 |  | 2023-07-26 | 2024-11-05 | CD//Sapian | 2024-06-11 | 0619Central-GCI-BOQ Template (template) | DU00002040035 |  |  |  |  | 2023-08-01 |  | TOWER
B00014 | B061G_B00014OD_PCKPDANA | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-31 |  |  |  | 2023-05-31 |  | 2023-06-07 |  | CD//Tee | 2023-06-13 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002040036 |  |  |  |  | 2023-08-29 |  | TOWER
B00196 | B057D_B00196OD_BATUCAVES | Central |  | Decomm |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-19 |  |  |  | 2023-07-26 |  | 2023-07-26 | 2023-10-17 | CD//Sapian | 2023-08-04 | CelcomDigi_RAN_GTSB_TSS_Central_20230620_0030 | DU00002040037 |  |  |  |  | 2023-08-28 |  | UNIPOLE
B01173 | B061B_B01173OD_PR_BLTNSTDMSHLM | Central | 1111K | Swap |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-10-04 | 2023-10-18 |  | 2023-10-20 |  | Rectificating | 2023-10-24 | 2024-01-02 | CD//Norhaliza | 2024-01-02 | CelcomDigi_RAN_Datasco_TSS_Central_20230829_Modern+Decom | DU00002040038 |  |  | 2024-03-04 | 2023-11-27 |  | Lampole | LAMP_POLE | 18 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x5,Dismantle Celcom all RRU&BBU |  | 13
B00078 | B057C_B00078OD_UIASUMAIYAH | Central |  | Decomm |  | 2023Q4 | CR | Datasco | 4.6 TSSR Approved |  | 2023-08-14 |  |  |  | 2023-08-16 |  | 2023-08-17 | 2023-12-18 | CD//Norhaliza | 2023-08-23 | CelcomDigi_RAN_Datasco_TSS_Central_20230815 | DU00002040039 |  |  |  |  | 2024-03-14 |  | LAMP_POLE
B02281 | B061C_B02281OD_BDRRIMBAYU | Central |  | Decomm |  | 2023Q3 | CR | Solusi | 4.6 TSSR Approved |  | 2023-07-26 |  |  |  | 2023-07-28 |  | 2023-07-28 |  | CD//Sapian | 2023-08-15 | CelcomDigi_RAN_Solusi_TSS_Central_20230626_decom reraise / CelcomDigi_TX_Solusi_TSS_Decom_Central_20230714 | DU00002040040 |  | TX part rejected, missing DIGI MW photos 3230B-1605B. |  |  | 2023-12-08 |  | AESTHETIC MONOPOLE TREE
Q00665 | Q118B_Q00665OD_MEDANJAYA | Sarawak |  | Decomm |  | 2023Q3 | SH | Datasco | 4.6 TSSR Approved |  | 2023-06-22 |  |  |  | 2023-07-28 |  | 2023-07-28 | 2023-09-23 | CD//John | 2023-07-29 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 | DU00002040041 |  |  |  |  | 2024-08-02 |  | MONOPOLE
K00169 | CITYPLAZA | Northern |  | Decomm |  | 2023Q4 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-07-21 |  |  |  | 2023-08-08 |  | 2023-07-31 | 2024-02-29 | CD//Quah | 2023-08-17 | Celcom Digi_RAN-CCSMY-TSS Decomm-Northern-20230729-0030 | DU00002040042 |  | 1) Please include all TX equipment in 19rack |  |  | 2024-10-21 |  | IN-BUILDING
B01054 | B061D_B01054OD_SEK182SHLM | Central |  | Decomm |  | 2023Q4 | SS | Solusi | 4.6 TSSR Approved |  | 2023-10-10 |  |  | 2023-11-07 | 2024-05-15 | Under Approval | 2023-11-16 |  | CD//Ali Akaram | 2023-11-28 | CelcomDigi_RAN_Solusi_TSS_Central_20231113 | DU00002040043 |  | 1) Pls provide antenna TX photo at NE 2) Missing FE part |  |  | 2023-10-10 |  | LAMP_POLE
P00778 | P031A_P00778OD_TMNNELAYANBALIKPULAU | Northern | 4161K | Swap |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-29 | 2023-05-25 |  | 2023-05-29 |  | Closed | 2023-06-06 | 2023-06-13 | CD//Shamsul | 2023-06-13 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0014 | DU00002040044 |  |  | 2023-07-20 | 2023-07-13 |  | Lampole | LAMP_POLE | 25 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
A01071 | A042C_A01071OD_TMN_BERKAT_TPG | Northern |  | Decomm |  | 2023Q4 | MH | GTSB | 4.6 TSSR Approved |  | 2023-05-25 |  |  |  | 2023-07-01 |  | 2023-07-03 | 2023-08-24 | CD//Shamsul | 2023-07-06 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230720-0023/Celcom Digi_RAN-GTSB-TSS-Northern-20230529-0020 | DU00002040045 |  | No TX Info, Photo not enough |  |  | 2023-09-01 |  | TOWER
B00015 | B061D_B00015OD_SEK20SHLM | Central |  | Decomm |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-07 |  |  |  | 2023-07-27 |  | 2023-07-27 | 2023-12-18 | CD//Sapian | 2023-08-15 | CelcomDigi_RANMW_GTSB_TSS_Central_20230609_0002 | DU00002040046 |  |  |  |  | 2024-01-16 |  | TOWER
B00888 | B061A_B00888IB_BLUEWAVEHOTEL | Central | 1104K | Swap |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-08-08 | 2023-08-17 |  | 2023-08-21 |  | Closed | 2023-08-22 | 2023-10-02 | CD//Syafiq | 2023-09-26 | CelcomDigi_RAN_Datasco_TSS_Central_20230808 | DU00002040047 |  |  | 2023-12-26 | 2023-12-11 |  |  | BOOM | N/A | Add R8862A S1800 x3 + R8862A S2100 x3,Dismantle all celcom BBU&RRU
B01240 | B062A_B01240OD_TEBUKMUFRAD | Central | 1114K | Swap |  | 2023Q4 | HQ 6 | CCSMY | 4.6 TSSR Approved |  | 2023-06-21 | 2023-06-26 |  | 2023-07-04 |  | Closed | 2023-07-06 | 2023-07-15 | CD//Sapian | 2023-07-15 | CelcomDigi_RAN_CCSMY_TSS_Central_20230620_0003 | DU00002040048 |  |  | 2023-09-14 | 2023-09-07 |  | Tower | TOWER | 62m | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
C00982 | C046C_C00982IB_SKYAVANUE_GENTING | Central |  | Decomm |  | 2023Q4 | SHA | GTSB | 4.3 Pending TSSR Resubmission - ZTE |  | 2023-06-20 |  |  |  | 2024-06-28 |  | 2023-08-24 |  | CD//Sofiah |  | CelcomDigi_RAN_GTSB_TSS_Central_20230622_0031 | DU00002040049 | [6 empty] | IN-BUILDING
B00442 | B057B_B00442OD_SLYGINDUSTRI | Central |  | Decomm |  | 2023Q4 | SS | YPTT | 4.6 TSSR Approved |  | 2023-10-31 |  |  |  | 2023-11-03 |  | 2023-11-07 | 2023-11-29 | CD//Norhaliza | 2023-11-17 | CelcomDigi_RAN_YPTT_TSS_Central_20231101 | DU00002040050 |  |  |  |  | 2023-11-28 |  | BOOM
Q00709 | Q132C_Q00709OD_PIASAUJAYA | Sarawak |  | Decomm |  | 2023Q4 | ZB | South Pacific | 4.6 TSSR Approved |  | 2023-06-21 |  |  |  | 2023-06-27 |  | 2023-07-25 | 2023-09-23 | CD//John | 2023-07-26 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230622 | DU00002040051 |  | 24/8: uncompletd info & photos |  |  | 2025-06-18 |  | MONOPOLE
B02482 | B061B_B02482OD_WTSEK9SHLM | Central |  | Decomm |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-05-15 |  |  |  | 2024-04-17 |  | 2023-07-26 | 2024-05-31 | CD//Sapian | 2023-08-02 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002040052 |  |  |  |  | 2023-08-29 |  | AESTHETIC MONOPOLE
9982A | Sanctuary Villa | Sarawak |  | Modernization |  | 2023Q3 | BY | Datasco | 4.6 TSSR Approved |  | 2023-05-15 | 2023-05-16 |  | 2023-05-18 |  | Closed | 2023-05-23 | 2023-05-27 | E//Hannah | 2023-05-26 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230516-0006 | DU00002040053 |  |  | 2023-06-26 | 2023-06-22 |  | Monopole | 30M Rapole | 30m | Add R9264M M1821 x4 + R8862A S2600 x1,Dismantle R8892N M1821(BAB) x3 |  | 2
B01954 | B061G_B01954OD_JLNALFASBGPERMAI | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-18 |  |  | 2023-05-22 | 2023-05-22 | Closed | 2023-06-28 | 2023-11-16 | CD//Tee | 2023-07-22 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002040054 |  |  |  |  | 2023-10-03 |  | MINI STRUCTURE
A00240 | A042B_A00240OD_TMSLTTPG | Northern | 4066K | Swap |  | 2023Q4 | SM | GTSB | 4.6 TSSR Approved |  | 2023-07-20 | 2023-07-31 |  | 2023-07-29 |  | Rectificating | 2023-08-01 | 2023-08-03 | CD//Quah | 2023-08-02 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002040055 |  |  | 2023-08-08 | 2023-08-08 |  | Portables BTS | TOWER | 6m | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 23
B00036 | B058A_B00036OD_PEKANKAPAR | Central |  | Decomm |  | 2023Q3 | CR | GTSB | 4.6 TSSR Approved |  | 2023-05-01 |  |  |  | 2023-08-01 |  | 2023-08-03 | 2023-10-17 | CD//Ali akaram | 2023-08-14 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002040056 |  |  |  |  | 2023-07-27 |  | TRIPOD
B00006 | B060B_B00006OD_MSJDKSGOR | Central |  | Decomm |  | 2023Q4 | CR | AllStar | 4.6 TSSR Approved |  | 2023-07-12 |  |  |  | 2023-07-17 |  | 2023-07-26 | 2023-08-24 | CD//Sapian | 2023-08-15 | CelcomDigi_RAN_AllStar_TSS_Central_20230712 | DU00002040057 |  |  |  |  | 2023-09-04 |  | MINARET
B00747 | B065B_B00747OD_KM402TGMALIM | Central |  | Decomm | Decomm->On Hold->Site Out | 2023Q4 | MA | GCI | 4.6 TSSR Approved |  | 2023-07-22 |  |  |  | 2023-08-03 |  | 2023-08-04 | 2023-10-17 | CD//Ali akaram | 2023-08-14 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230725 | DU00002040058 |  |  |  |  | 2025-04-29 |  | MONOPOLE
P00288 | P035D_P00288OD_YORKROAD | Northern |  | Decomm |  | 2023Q3 | MH | CCSMY | 4.6 TSSR Approved |  | 2023-05-19 |  |  |  | 2023-06-20 |  | 2023-06-21 | 2023-07-28 | CD//Affendi | 2023-06-28 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002040059 |  |  |  |  | 2023-08-18 |  | TRIPOD
B00722 | B061C_B00722OD_KOTAKEMUNING | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-06-27 |  |  |  | 2023-06-30 |  | 2023-07-03 | 2023-10-17 | CD//Norhaliza | 2023-10-09 | CelcomDigi_RAN_YPTT_TSS_Central_20230628_0011 | DU00002040060 |  |  |  |  | 2023-07-21 |  | TRIPOD
B01672 | B061A_B01672IB_SETIACITYMALLPH2 | Central |  | Decomm |  | 2023Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2023-05-26 |  |  |  | 2023-05-31 |  | 2023-06-16 | 2024-05-14 | CD//Sofiah | 2024-04-25 | CelcomDigi_RAN_Magicell_TSS_Central_20230601_0011 / CelcomDigi_TX-RAN_Magicell_TSS_Central_20230818 | DU00002040061 |  |  |  |  | 2023-12-26 |  | IN-BUILDING
K00139 | K004B_K00139OD_TGBENDAHARA | Northern | 4091K | Swap |  | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-06-05 | 2023-06-09 |  | 2023-06-13 |  | Closed | 2023-06-19 | 2023-07-07 | CD//Heng | 2023-07-03 | Celcom Digi_RAN-YPTT-TSS-Northern-20230606-0017 | DU00002040062 |  |  | 2023-10-01 | 2023-10-01 |  | In-Building System | BOOM | 7 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x5,Dismantle Celcom all RRU&BBU |  | 13
P00576 | P031A_P00576OD_SGBATU | Northern |  | Decomm |  | 2023Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-04-29 |  |  |  | 2023-07-05 |  | 2023-06-06 | 2023-07-21 | CD//Shamsul | 2023-06-13 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2 | DU00002040063 |  |  |  |  | 2023-07-27 |  | MINARET
B00293 | B060B_B00293OD_TMBKTMELAWATI | Central | 1811K | Swap | Decomm->Swap | 2023Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2023-09-15 | 2023-10-04 |  | 2023-10-05 |  | Closed | 2023-10-06 | 2023-10-17 | CD//Ali akaram | 2023-10-13 | CelcomDigi_RAN_AllStar_TSS_Central_20230915 | DU00002040064 |  |  | 2024-03-07 | 2024-02-19 |  | Tower | TOWER | 125 | Add R8852E S9000 x3+R8862A S2601 x3+A9732 M1821 x3,Dismantle | 123
B02810 | B057B_B02810OD_BATU_CAVE26_SCT | Central |  | Decomm |  | 2023Q4 | CR | GTSB | 4.6 TSSR Approved |  | 2023-06-16 |  |  |  | 2023-08-02 |  | 2023-08-03 | 2023-08-19 | CD//Sapian | 2023-08-17 | CelcomDigi_RAN_GTSB_TSS_Central_20230620_0030 | DU00002040065 |  |  |  |  | 2023-08-23 | Lampole | LAMP_POLE
B00568 | B061A_B00568OD_PSNDTKMENT | Central |  | Decomm |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-06-21 |  |  |  | 2024-07-04 |  | 2023-08-08 | 2025-03-07 | CD//Sapian | 2023-08-17 | CelcomDigi_RAN_Datasco_TSS_Central_20230622_0028 | DU00002040066 |  |  |  |  | 2024-01-17 |  | BOOM
9997A | Samalaju Eco Park | Sarawak |  | Modernization |  | 2023Q3 | BY | Datasco | 4.6 TSSR Approved |  | 2023-05-26 | 2023-06-06 |  | 2023-06-08 |  | Closed | 2023-06-09 | 2023-06-17 | E//Hannah | 2023-06-15 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230516-0006 | DU00002040067 |  |  | 2023-07-06 | 2023-06-28 |  | Pole | 30m Rapole | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
B00305 | B065B_B00305OD_TMKKB | Central |  | Decomm |  | 2023Q4 | MA | GTSB | 4.6 TSSR Approved |  | 2024-04-26 |  |  |  | 2024-05-27 |  | 2024-05-28 | 2024-09-26 | CD//Norhaliza | 2024-08-09 | CelcomDigi_RAN_GTSB_TSS_Central_20240423 | DU00002040068 |  |  |  |  | 2024-04-23 |  | 4LEGGED
P00283 | P035F_P00283OD_JLNBKTGAMBIR | Northern |  | Decomm |  | 2023Q3 | MH | GTSB | 4.6 TSSR Approved |  | 2023-05-14 |  |  |  | 2023-06-15 |  | 2023-06-15 | 2024-02-15 | CD//Affendi | 2023-10-03 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2 | DU00002040069 |  | 22/8: Please include Photo Antenna, ODU, for Unused link to be decom NT04902 (P00100-P00283) |  |  | 2023-08-03 | Lampole | LAMP_POLE | 30m
B00297 | B060B_B00297OD_VLJLNHJZAINAL | Central |  | Decomm |  | 2023Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-29 |  |  |  | 2023-10-03 |  | 2023-10-03 | 2023-11-16 | CD//Norhaliza | 2023-10-25 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002040070 |  |  |  |  | 2023-09-08 |  | TOWER
B00518 | B060A_B00518OD_MSJDALRAUDAH | Central |  | Decomm |  | 2023Q4 | CR | AllStar | 4.6 TSSR Approved |  | 2023-07-11 |  |  |  | 2023-07-29 |  | 2023-08-02 | 2024-01-22 | CD//Norhaliza | 2023-08-18 | CelcomDigi_RAN_AllStar_TSS_Central_20230712 | DU00002040071 |  |  |  |  | 2024-01-03 |  | TOWER
9697B | Samalaju OM | Sarawak |  | Modernization |  | 2023Q3 | BY | Magicell | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-13 |  | 2023-05-16 |  | Closed | 2023-05-18 | 2023-05-19 | CD//John | 2023-05-18 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230512-0007 | DU00002040072 |  |  | 2023-06-27 | 2023-06-26 |  | Monopole | 60m 4 Legged Tower | 30M | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
K00106 | K004A_K00106OD_KDX | Northern |  | Decomm |  | 2023Q4 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-06-12 |  |  |  | 2023-06-23 |  | 2023-06-26 | 2023-08-08 | CD//Rohizam | 2023-08-07 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230613-0025 | DU00002040073 |  | No TX Info, Photo not enough |  |  | 2023-09-30 |  | TOWER
P00517 | P035A_P00517OD_DESAPERMATA | Northern |  | Decomm |  | 2023Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-05-09 |  |  |  | 2023-06-06 |  | 2023-06-11 | 2023-08-08 | CD//Shamsul | 2023-06-22 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2/Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230726-0024 | DU00002040074 |  |  |  |  | 2023-09-05 |  | MONOPOLE
B01277 | B061B_B01277OD_SEKU82SHLM | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-16 |  |  |  | 2023-05-31 |  | 2023-07-26 | 2023-12-18 | CD//Ali Akaram | 2023-08-18 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002040075 |  |  |  |  | 2023-08-30 |  | MINI STRUCTURE
B00130 | B061C_B00130OD_KOTAPERMAIGCC | Central |  | Decomm |  | 2023Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-06-23 |  |  |  | 2023-06-23 |  | 2023-07-18 | 2023-11-29 | CD//Sapian | 2023-07-14 | CelcomDigi_RAN_Allstar_TSS_Central_20230623_0015 | DU00002040076 |  |  |  |  | 2023-08-18 |  | BOOM
B02555 | B061C_B02555OD_KOTAKEMUNINGINDPARK | Central |  | Decomm |  | 2023Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-06-19 |  |  |  | 2023-06-20 |  | 2023-06-26 | 2023-08-10 | CD//Sapian | 2023-07-07 | CelcomDigi_RAN_Allstar_TSS_Central_20230620_0013 | DU00002040077 |  |  |  |  | 2023-07-27 |  | LAMP_POLE
B02396 | B057B_B02396OD_PSRN2_BBSELAYANG | Central |  | Decomm |  | 2023Q4 | SS | YPTT | 4.6 TSSR Approved |  | 2023-07-29 |  |  |  | 2023-09-08 |  | 2023-09-08 | 2023-12-18 | CD//Norhaliza | 2023-11-02 | CelcomDigi_RAN_YPTT_TSS_Central_20230729 | DU00002040078 |  |  |  |  | 2023-09-27 |  | LAMP_POLE
P00640 | P035C_P00640OD_LBH_CAMPBELL | Northern |  | Decomm |  | 2023Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-06-07 |  |  |  | 2023-07-04 |  | 2023-07-06 | 2023-08-08 | CD//Rohizam | 2023-08-06 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2 | DU00002040079 |  |  |  |  | 2023-09-20 |  | UNIPOLE
B00183 | B062A_B00183OD_BGNNAKHODAOMAR | Central |  | Decomm |  | 2023Q4 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-06-26 |  |  |  | 2023-07-03 |  | 2023-07-28 | 2023-10-02 | CD//Sapian | 2023-08-15 | CelcomDigi_RAN_CCSMY_TSS_Central_20230627_0007 | DU00002040080 |  |  |  |  | 2023-09-27 |  | TOWER
P00547 | P035E_P00547OD_TNBGELUGOR | Northern |  | Decomm |  | 2023Q3 | SM | GCI | 4.6 TSSR Approved |  | 2023-11-02 |  |  |  | 2023-11-06 |  | 2023-11-06 |  | CD//Affendi | 2023-11-10 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240529-0109 | DU00002040081 |  |  |  |  | 2024-08-05 |  | BOOM
B00132 | B058A_B00132OD_BT8JLNMERU | Central |  | Decomm |  | 2023Q3 | MA | Magicell | 4.6 TSSR Approved |  | 2023-06-14 |  |  |  | 2023-06-16 |  | 2023-06-26 | 2023-09-01 | CD//Ali Akaram | 2023-08-26 | CelcomDigi_RAN_Magicell_TSS_Central_20230616_0013 / CelcomDigi_TX_Magicell_TSS_Decom_Central_20230714 | DU00002040082 |  | RESUBMISSION. |  |  | 2023-08-23 |  | TOWER
B00975 | B058B_B00975OD_TMNKLGPDANA | Central |  | Decomm |  | 2023Q3 | CR | CCSMY | 4.6 TSSR Approved |  | 2023-06-02 |  |  |  | 2023-06-14 |  | 2023-07-24 | 2024-05-29 | CD//Norhaliza | 2023-10-09 | CelcomDigi_RAN_CCSMY_TSS_Central_20230626_decom reraise | DU00002040083 |  |  |  |  | 2023-10-14 |  | MONOPOLE
K00031 | K004A_K00031OD_KEPALABATASKDH | Northern |  | Decomm |  | 2023Q4 | ZA | GCI | 4.6 TSSR Approved |  | 2023-06-22 |  |  |  | 2023-06-24 |  | 2023-06-26 | 2024-06-19 | CD//Rohizam | 2023-08-06 | Celcom Digi_RAN-GCI-TSS-Northern-20230615-0029/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002040084 |  | 7/7: No TX Info, Photo not enough. 9/8: Need include Digi Equipment 22/8: Missing IDU Label 9/10: Solution change since not cole |  |  | 2023-10-04 |  | GUYED MAST
B00368 | B061B_B00368OD_PR_TMBKTCERAKAH | Central |  | Decomm |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-08-28 |  |  |  | 2024-07-17 |  | 2023-09-21 | 2024-11-05 | CD//Ali Akaram | 2023-10-23 | CelcomDigi_RAN_Datasco_TSS_Central_20230829_Modern+Decom | DU00002040085 |  |  |  |  | 2024-04-03 |  | 4LEGGED
B01333 | B060A_B01333OD_SAWAHSEMPADAN | Central |  | Decomm |  | 2023Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2023-07-24 |  |  |  | 2023-07-25 |  | 2023-07-28 | 2023-10-17 | CD//Sapian | 2023-08-15 | Celcomdigi_RAN_AllStar_TSS_Central_20230726 | DU00002040086 |  |  |  |  | 2023-08-24 |  | TOWER
B01635 | B058B_B01635OD_KGDELEKKIRI | Central |  | Decomm |  | 2023Q3 | MA | Futong | 4.6 TSSR Approved |  | 2023-05-15 |  |  |  | 2023-05-31 |  | 2023-06-09 | 2023-12-18 | CD//Sapian | 2023-06-11 | CelcomDigi_RAN_Futong_TSS_Central_20230626_decom reraise | DU00002040087 |  |  |  |  | 2023-08-01 |  | MONOPOLE
B00683 | B058B_B00683OD_JLNHJSIRAT | Central |  | Decomm |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-05-03 |  |  |  | 2023-06-21 |  | 2023-06-21 | 2023-10-17 | CD//Tee | 2023-07-22 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002040088 |  | 2078B is using TDC LL and will be dismantle by TDC, pls revise TP |  |  | 2023-09-21 |  | TOWER
P00534 | P035C_P00534IB_ISLAND_HOSPITAL | Northern |  | Site Out (Decomm) | Decomm->Site Out->Replacement, Site Out (Decomm) | 2023Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-05-25 | [5 empty] | 2023-07-26 | 2025-10-22 | CD//Quah | 2023-09-29 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002040089 |  |  |  |  | 2025-06-26 |  | IN-BUILDING
P00358 | P035B_P00358OD_MOUNTERSKINE | Northern |  | Decomm |  | 2023Q3 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-05-25 |  |  |  | 2023-09-07 |  | 2023-07-25 | 2023-10-09 | CD//Affendi | 2023-07-26 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002040090 |  |  |  |  | 2023-09-05 |  | LAMP_POLE
B02695 | B065B_B02695OD_CB_LADANGSGJERNIH | Central | 1022P | Swap |  | 2023Q4 | AI | Ascentrack | 4.6 TSSR Approved |  | 2023-06-26 | 2023-06-27 |  | 2023-07-03 |  | Closed | 2023-07-04 | 2023-07-15 | CD//Sapian | 2023-07-14 | Celcomdigi_RAN_Ascentrack_TSS_Central_20230626_0025 | DU00002040091 |  |  | 2023-09-28 | 2023-09-22 |  | Tower | TOWER | 60 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
A00755 | A042C_A00755OD_TAIPINGPOLY_RDD | Northern |  | Decomm |  | 2023Q4 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-06-12 |  |  |  | 2023-06-13 |  | 2023-06-14 | 2024-02-27 | CD//Shamsul | 2023-06-27 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230613-0025 | DU00002040092 |  | need include include DIGI link info Dismantle Digi Microwave 4462A-4427B |  |  | 2023-08-21 |  | BOOM
B02159 | B065B_B02159OD_LGKRNSEROJA | Central |  | Decomm |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-05-12 |  |  |  | 2023-07-26 |  | 2023-07-21 |  | CD//Ali Akaram | 2023-08-18 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002040093 |  | Subcon need to resurvey due to SOW CHANGED (Dismantle Digi Microwave Link 3809A-1893B) |  |  | 2023-09-20 |  | TRIPOD
P00324 | P035B_P00324OD_TARCOLLEGE_PP | Northern | 4135K | Swap |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-14 | 2023-05-27 |  | 2023-06-02 |  | Closed | 2023-06-08 | 2023-06-14 | CD//Affendi | 2023-06-14 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0015 | DU00002040094 |  |  | 2023-08-22 | 2023-08-21 |  | Wall mount boom | BOOM | 3M | Add R9264H M901821 x2 + R9264M M1821 x1 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU |  | 2
K00267 | K003A_K00267OD_CB_SGTAKA | Northern |  | Decomm |  | 2023Q4 | SM | YPTT | 4.6 TSSR Approved |  | 2023-07-07 |  |  |  | 2023-08-01 |  | 2023-08-03 | 2023-11-23 | CD//Rohizam | 2023-08-11 | Celcom Digi_RAN-YPTT-TSS-Northern-20230712-0024//Celcom Digi_RAN-YPTT-TSS Decomm-Northern-20240311-0048 | DU00002040095 |  |  |  |  | 2023-10-03 |  | TOWER
K00103 | K004A_K00103OD_PANTAIJOHOR | Northern | 4089K | Swap |  | 2023Q4 | HQ 2 | GCI | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦Maxis not allowed add AAU | 2023-06-22 | 2023-06-27 |  | 2023-06-30 |  | Closed | 2023-07-04 | 2023-08-22 | CD//Quah | 2023-08-22 | Celcom Digi_RAN-GCI-TSS-Northern-20230613-0027 | DU00002040096 | NIC_S2_Change MM to BI_owner reject_MAXIS |  | 2023-09-28 | 2023-09-09 |  | Tower | TOWER | 60 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 13
C00981 | C046C_C00981IB_RSC9GENTING | Central |  | Decomm |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-21 |  |  |  | 2023-08-03 |  | 2023-07-25 | 2023-12-18 | CD//Sofiah | 2023-08-29 | CelcomDigi_RAN_GTSB_TSS_Central_20230622_0031 | DU00002040097 |  |  |  |  | 2025-12-10 |  | IN-BUILDING
K00926 | K004B_K00926OD_TMN_PADI_EMAS_AS | Northern |  | Decomm |  | 2023Q4 | SM | GCI | 4.6 TSSR Approved |  | 2023-06-15 |  |  |  | 2023-06-20 |  | 2023-06-21 | 2023-08-24 | CD//Quah | 2023-07-20 | Celcom Digi_RAN-GCI-TSS-Northern-20230614-0028/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002040098 |  |  |  |  | 2023-10-17 | Lampole | LAMP_POLE | 30
B00294 | B062B_B00294OD_PR_SGBESAR2 | Central | 1072K | Swap |  | 2023Q4 | CR | Magicell | 4.6 TSSR Approved |  | 2023-07-24 | 2023-07-28 |  | 2023-08-02 |  | Closed | 2023-08-09 | 2023-08-19 | CD//Norhaliza | 2023-08-21 | CelcomDigi_RAN_Magicell_TSS_Central_20230726 | DU00002040099 |  |  | 2023-11-16 | 2023-09-22 |  | Tower | 4LEGGED | 50m | Add R8852E S9000 x3 + A9732 M1821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 123
A00803 | A042A_A00803OD_MN_KGHULUTERAS | Northern | 4212P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040100 | [6 empty] | TOWER
P00174 | P035A_P00174OD_TMAIRITAM | Northern |  | Decomm |  | 2023Q3 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-07-18 |  |  |  | 2023-07-26 |  | 2023-07-27 | 2023-08-08 | CD//Shamsul | 2023-08-06 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2 | DU00002040101 |  |  |  |  | 2025-10-27 |  | BOOM
P00026 | P035B_P00026OD_BTFERINGGHI | Northern | 4117K | Swap |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-13 | 2023-05-26 |  | 2023-06-01 |  | Rectificating | 2023-06-26 | 2023-07-26 | CD//Quah | 2023-07-25 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0015 | DU00002040102 |  |  | 2023-08-23 | 2023-08-22 |  | Tower | TOWER | 48M | Add R9264H M901821 x2 + R9264M M1821 x1 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU |  | 1
B01187 | B058B_B01187IB_CENTROPLAZA | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-06-15 |  |  |  | 2023-06-16 |  | 2023-06-20 | 2023-10-17 | CD//Sofiah | 2023-09-21 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002040103 |  |  |  |  | 2023-08-09 |  | IN-BUILDING
B02619 | B057B_B02619OD_WISMAABDKUTTY_KGLAKSAMANA | Central |  | Decomm |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-07 |  |  |  | 2023-08-21 |  | 2023-08-22 | 2024-07-12 | CD//Sapian | 2023-08-24 | CelcomDigi_RANMW_GTSB_TSS_Central_20230609_0002 | DU00002040104 |  |  |  |  | 2023-10-19 |  | BOOM
A00837 | A042B_A00837IB_AEONTPG | Northern |  | Decomm |  | 2023Q4 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-06-07 |  |  |  | 2023-08-18 |  | 2023-08-18 | 2023-08-24 | CD//Quah | 2023-08-22 | Celcom Digi_RAN-GTSB-TSS-Northern-20230529-0020/Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230726-0024 | DU00002040105 |  |  |  |  | 2024-01-26 |  | IN-BUILDING
P00692 | P035D_P00692OD_HILIR_SG_PINANG | Northern | 4157K | Swap |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved | Bisector Cannot Install, Change to Normal | 2023-06-20 | 2023-07-21 |  | 2023-07-26 |  | Closed | 2023-07-28 | 2023-09-07 | CD//Shamsul | 2023-08-06 | Celcom Digi_RAN-CCSMY- TSS-Northern-20230621-0027 | DU00002040106 | NIC_S1_Change BI to normal sector_Space constraint_OMNIX (M) |  | 2024-01-06 | 2023-08-24 |  | Minaret | MINARET | 36m | Add R9264H M901821 x3+R8854 S2600 x3,Dismantle
B00135 | B065B_B00135OD_SEK8BKTSENTOSA | Central |  | Decomm |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-21 |  |  |  | 2024-06-14 |  | 2023-07-21 | 2024-11-05 | CD//Sapian | 2023-07-29 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002040107 |  |  |  |  | 2023-07-27 | Tower | TOWER | 63
B00466 | B065B_B00466OD_KM426BUNGARAYA | Central |  | Decomm |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-06-14 |  |  |  | 2023-07-21 |  | 2023-07-21 | 2024-05-29 | CD//Ali akaram | 2023-08-01 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002040108 |  |  |  |  | 2023-09-30 |  | TOWER
B02425 | B061A_B02425OD_JLNSETIAGEMILANG | Central | 1154K | Swap |  | 2023Q3 | HQ 6 | Magicell | 4.6 TSSR Approved |  | 2023-05-06 | 2023-05-11 |  | 2023-05-15 |  | Closed | 2023-05-18 | 2023-06-03 | CD//Sapian | 2023-05-24 | CelcomDigi_RAN_Magicell_TSS_Central_20230508_0007 | DU00002040109 |  |  | 2023-07-22 | 2023-07-13 |  |  | UNIPOLE | 6.5 | Add R8852E S9000 x3 + A9732 M1821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 123
A00669 | A042C_A00669OD_LAPLAKEVIEW_RDD | Northern |  | Decomm |  | 2023Q4 | MH | GTSB | 4.6 TSSR Approved |  | 2023-05-29 |  |  |  | 2023-07-01 |  | 2023-07-10 | 2023-08-08 | CD//Shamsul | 2023-07-12 | Celcom Digi_RAN-GTSB-TSS-Northern-20230529-0020/Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230726-0024 | DU00002040110 |  | No TX Info, Photo not enough |  |  | 2023-09-02 |  | GUYED MAST
B01461 | B061A_B01461OD_PR_JLNKRISTALSEK7 | Central | 1125K | Swap |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-07 | 2023-06-16 |  | 2023-06-21 |  | Closed | 2023-06-24 | 2023-07-06 | CD//Sapian | 2023-07-05 | CelcomDigi_RAN_GTSB_TSS_Central_20230609_0027 | DU00002040111 |  |  | 2023-09-29 | 2023-09-28 |  |  | TRIPOD | 5M | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
B00296 | B060C_B00296OD_TMIJOK | Central | 1209K | Swap | Decomm->Swap | 2023Q3 | IE | GTSB | 4.6 TSSR Approved |  | 2023-04-28 | 2023-06-26 |  | 2023-08-15 | 2023-08-03 | Closed | 2023-07-14 | 2023-08-19 | CD//Ali akaram | 2023-08-18 | 0626Central-GTSB-BOQ Template (template) | DU00002040112 |  | change anchor | 2023-10-24 | 2023-09-11 |  | Monopole | MONOPOLE | 45 | Add R9264M M1821 x2+R9264H M901821 x3+R8862A S2601 x5,Dismantle celcom RRU&BBU |  | 12
Q00420 | Q124B_Q00420OD_MATANGJAYA2 | Sarawak |  | Decomm |  | 2023Q4 | ZB | South Pacific | 4.6 TSSR Approved |  | 2023-06-20 |  |  |  | 2023-06-27 |  | 2023-07-25 | 2023-09-19 | CD//John | 2023-07-28 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230622 | DU00002040113 |  | 24/8: uncompleted info & photos |  |  | 2023-10-23 |  | MONOPOLE
K00143 | K004A_K00143OD_TMNMUHIBAH | Northern |  | Decomm |  | 2023Q4 | MH | CCSMY | 4.6 TSSR Approved |  | 2023-05-26 |  |  |  | 2023-06-27 |  | 2023-06-28 | 2024-03-26 | CD//Shamsul | 2023-07-12 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230529-0020 | DU00002040114 |  | 21/8: Please include IDU 950 with label 25/8: Please Include Unused Antenna & ODU for Link NT03871 |  |  | 2023-09-30 |  | BOOM
B01849 | B057C_B01849OD_DESAGEMILANG | Central |  | Decomm |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-08-08 |  |  |  | 2023-08-11 |  | 2023-08-15 |  | CD//Norhaliza | 2023-08-18 | CelcomDigi_RAN_Datasco_TSS_Central_20230808 | DU00002040115 |  | 1) Please provide clear photo for all existing TX equipment (zoom in photo) with clear labelling, including existing IDU. 2) Missing FE part |  |  | 2023-12-23 |  | LAMP_POLE
B01798 | B061B_B01798OD_SEK9SALAM2 | Central |  | Decomm |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-06-07 |  |  |  | 2023-07-26 |  | 2023-07-24 | 2023-12-18 | CD//Ali akaram | 2023-08-02 | CelcomDigi_RANMW_Datasco_TSS_Central_20230609_0005 | DU00002040116 |  |  |  |  | 2023-10-27 |  | BOOM
Q00354 | Q132C_Q00354OD_WISMAYONGLUNG | Sarawak | 9070K | Site Out (Swap) | Swap->MOCN Decomm->Site Out->Site Out (Swap) | 2023Q4 |  | Magicell | 14.1 TSSR Not Required (Decomm by CD) | E.co revert fully decomm | 2025-09-18 |  |  |  |  | To be Submitted |  |  |  |  | SQ202508220455-Magicell | DU00002040117 |  |  |  |  | 2025-09-20 |  | BOOM
A00643 | A042B_A00643OD_TMNKAMI | Northern |  | Decomm |  | 2023Q4 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-06-15 |  |  |  | 2023-06-15 |  | 2023-06-16 | 2024-05-28 | CD//Rohizam | 2023-08-06 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230616-0026/Celcom Digi_RAN-CCSMY-TSS Decomm-Northern-20240131-0091 | DU00002040118 |  | 11/8:Need include 2nd IDU with clear Link ID Zoom in photo |  |  | 2023-08-21 |  | TRIPOD
9871A | DEWAN BDR KUCHING UTARA IB | Sarawak |  | Modernization |  | 2023Q4 | SH | AllStar | 4.6 TSSR Approved |  | 2023-06-29 | 2023-07-12 |  | 2023-07-18 |  | Closed | 2023-07-20 | 2023-07-31 | E//Nazrul | 2023-07-31 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230608-0006 | DU00002040119 |  |  | 2023-09-07 | 2023-09-04 |  | In-Building System | In-building system |  | Add R8862A S1800 x1,Dismantle R8882-GUL1812 x1
P00773 | P035D_P00773OD_HOSPITALBESARPNG | Northern |  | Decomm |  | 2023Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-05-23 |  |  |  | 2023-06-07 |  | 2023-07-14 | 2023-09-18 | CD//Quah | 2023-09-29 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230720-0023/Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2 | DU00002040120 |  |  |  |  | 2023-09-06 |  | AESTHETIC MONOPOLE TREE
P00524 | P035E_P00524OD_PSSJLNGREENLANE | Northern |  | Decomm |  | 2023Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-06-23 |  |  |  | 2023-07-27 |  | 2023-07-21 | 2023-08-08 | CD//Rohizam | 2023-08-06 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2 | DU00002040121 |  |  |  |  | 2023-08-08 | Petronas Pylon | PYLON | 30M
B02711 | B058B_B02711OD_JLNPKNBARUKLG | Central |  | Decomm |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-07-05 |  |  |  | 2023-07-26 |  | 2023-07-06 | 2023-07-31 | CD//Norhaliza | 2023-07-25 | CelcomDigi_RAN_DATASCO_Central_20230706_0031 | DU00002040122 |  |  |  |  | 2023-12-20 |  | BOOM
P00034 | P035C_P00034OD_PITTSTREET | Northern |  | Decomm |  | 2023Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-05-19 |  |  |  | 2023-08-04 |  | 2023-08-07 | 2023-08-19 | CD//Rohizam | 2023-08-07 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002040123 |  |  |  |  | 2023-09-05 |  | BOOM
Q00469 | Q118B_Q00469OD_BT39BTU | Sarawak |  | Decomm |  | 2023Q3 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-05-26 |  |  |  | 2023-07-10 |  | 2023-07-24 | 2024-02-15 | CD//John | 2023-07-28 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230529-0012 | DU00002040124 |  | 1/9: Uncompleted info + photos |  |  | 2023-12-18 |  | TOWER
A00802 | A042A_A00802OD_MN_KGKLIANGNG | Northern | 4211P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040125 | [6 empty] | TOWER
B01683 | B065B_B01683OD_TERATAISERENDAH | Central | 1134K | Swap |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-19 | 2023-05-03 |  | 2023-05-07 |  | Closed | 2023-05-08 | 2023-06-03 | CD//Sapian | 2023-05-21 | CelcomDigi_RAN_Datasco_TSS_Central_20230420_0015 | DU00002040126 |  |  | 2023-07-17 | 2023-07-13 |  | Lampole | LAMP_POLE | 25 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
B00835 | B065B_B00835OD_MAKTABPOLISKK | Central | 1101K | Swap |  | 2023Q4 | HQ 6 | Futong | 4.6 TSSR Approved |  | 2023-06-22 | 2023-06-22 |  | 2023-06-28 |  | Closed | 2023-07-03 | 2023-07-15 | CD//Sapian | 2023-07-14 | CelcomDigi_RANMW_Futong_TSS_Central_20230623_0004 | DU00002040127 |  |  | 2023-09-21 | 2023-09-14 |  | Wall mount boom | TRIPOD | 3m | Add R9264H M901821 x1,Dismantle Celcom all RRU&BBU
P00553 | P031B_P00553OD_SOLOKBERINGIN | Northern |  | Decomm |  | 2023Q3 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-05-19 | [5 empty] | 2023-09-12 | 2023-12-18 | CD//Rohizam | 2023-10-10 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002040128 |  |  |  |  | 2023-08-03 |  | BOOM
C00544 | B065B_C00544OD_GENTINGSKYWAY | Central |  | Decomm |  | 2023Q4 | MA | Futong | 4.6 TSSR Approved |  | 2023-08-04 |  |  |  | 2023-08-19 |  | 2023-08-23 |  | CD//Sapian | 2023-11-19 | CelcomDigi_RAN_Futong_TSS_Central_20230807 | DU00002040129 |  | Missing FE part |  |  | 2025-07-22 |  | BOOM
B00433 | B062A_B00433OD_ILDAS | Central | 1079K | Swap | Swap->Site Out->Swap | 2023Q4 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-08-23 | 2023-08-22 |  | 2023-08-28 |  | Closed | 2023-08-29 | 2023-08-30 | CD//Sapian | 2023-08-30 | CelcomDigi_RAN_CCSMY_TSS_Central_20230824 | DU00002040130 |  |  | 2025-07-15 | 2025-07-09 |  | Tower | WATER TANK | 19 | Add R9264H M901821x3, Dismantle | 0 | 0
9831A | Imperial Mall | Sarawak |  | Modernization |  | 2023Q4 | ZB | Trintel | 4.6 TSSR Approved |  | 2023-07-21 | 2023-07-31 |  | 2023-08-22 |  | Closed | 2023-08-24 | 2023-10-17 | E//Hannah | 2023-10-13 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230726 | DU00002040131 |  | Wrong Schematic IBC | 2023-10-30 | 2023-10-12 |  | Portables BTS | In-building system |  | Add + R8862A S1800 x4 + R8862A S2100 x4 + R8862A S2601 x4,Dismantle R8882 S1800B(B6B) x3
P00073 | P035A_P00073OD_BBFARLIM2 | Northern |  | Decomm |  | 2023Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-05-20 |  |  |  | 2023-07-05 |  | 2023-06-09 | 2023-08-30 | CD//Affendi | 2023-06-14 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2 | DU00002040132 |  | No TX Info |  |  | 2023-09-19 |  | BOOM
B00800 | B062A_B00800OD_POLYSABAKBERNM | Central | 1097K | Swap |  | 2023Q4 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-08-30 | 2023-09-06 |  | 2023-09-11 |  | Closed | 2023-09-13 | 2023-10-17 | CD//Ali Akaram | 2023-10-12 | CelcomDigi_RAN_CCSMY_TSS_Central_20230901 | DU00002040133 |  |  | 2023-11-15 | 2023-10-19 |  | Pole | WATER TANK | 22 | Add R8852E S9000 x1+R9264H M901821 x2+R8862A S2601 x3+A9732 M1821 x1,Dismantle | 2
B00291 | B060A_B00291OD_TMTGKARANG | Central | 1071K | Swap |  | 2023Q4 | XH | AllStar | 4.6 TSSR Approved |  | 2023-07-24 | 2023-07-28 |  | 2023-08-01 |  | Closed | 2023-08-15 | 2023-08-19 | CD//Ali Akaram | 2023-08-18 | CelcomDigi_RAN_AllStar_TSS_Central_20230725 | DU00002040134 |  |  | 2024-01-21 | 2024-01-11 |  | Tower | TOWER | 45 | Add R8852E S9000 x3 + A9732 M1821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 123
Q00723 | Q118B_Q00723OD_TMNRIA2 | Sarawak |  | Decomm |  | 2023Q3 | SH | AllStar | 4.6 TSSR Approved |  | 2023-09-06 |  |  |  | 2023-09-06 |  | 2023-09-06 | 2023-09-16 | CD//John | 2023-09-12 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230622 | DU00002040135 |  |  |  |  | 2024-04-23 |  | MONOPOLE
B00816 | B057C_B00816OD_TMNPINGGIRAN | Central | 1099K | Swap |  | 2023Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2023-06-23 | 2023-07-04 |  | 2023-07-06 |  | Closed | 2023-07-12 | 2023-07-18 | CD//Sapian | 2023-07-19 | CelcomDigi_RAN_Allstar_TSS_Central_20230622_0014 | DU00002040136 |  |  | 2023-08-17 | 2023-08-15 |  | In-Building System | TRIPOD | 8 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x5,Dismantle Celcom all RRU&BBU |  | 12
B00548 | B058B_B00548OD_LIPATKAJANG | Central |  | Decomm |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-06-23 |  |  |  | 2023-07-17 |  | 2023-07-21 | 2023-12-18 | CD//Sapian | 2023-08-04 | Celcomdigi_RAN_Ascentrack_TSS_Central_20230623_0024 | DU00002040137 |  |  |  |  | 2023-08-16 |  | TOWER
B00865 | B061B_B00865IB_SHLMMALL | Central |  | Decomm |  | 2023Q4 | CR | Datasco | 4.6 TSSR Approved |  | 2023-06-01 |  |  |  | 2023-11-02 |  | 2023-11-03 | 2024-07-16 | CD//Sofiah | 2023-11-08 | CelcomDigi_RAN_Datasco_TSS_Central_20230606_0025 | DU00002040138 |  |  |  |  | 2024-01-15 |  | IN-BUILDING
P00194 | P031B_P00194OD_PMTGDAMARLAUT | Northern |  | Decomm |  | 2023Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-05-25 |  |  |  | 2023-06-21 |  | 2023-06-22 | 2024-02-29 | CD//Affendi | 2023-06-28 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002040139 |  |  |  |  | 2023-08-28 |  | BOOM
K00140 | K004A_K00140IB_CITYPOINT | Northern | 4092K | Swap |  | 2023Q4 | WP | GTSB | 4.6 TSSR Approved |  | 2023-06-02 | 2023-06-15 |  | 2023-06-23 |  | Closed | 2023-07-19 | 2023-07-21 | CD//Shamsul | 2023-07-20 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002040140 |  |  | 2023-09-21 | 2023-09-19 |  | Portables BTS | IN-BUILDING |  | Add R8852E S9000 x2 + R8862A S1800 x2 + R8862A S2100 x2,Dismantle all celcom BBU&RRU
B01084 | B061G_B01084OD_TMNBKTSUBANG | Central |  | Decomm |  | 2023Q3 | CR | YPTT | 4.6 TSSR Approved |  | 2023-07-18 |  |  |  | 2023-07-18 |  | 2023-07-25 | 2023-10-17 | CD//Sapian | 2023-07-28 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002040141 |  |  |  |  | 2023-08-29 |  | LAMP_POLE
B00504 | B062A_B00504OD_SABAKBERNAM | Central |  | Decomm |  | 2023Q4 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-06-23 |  |  |  | 2023-06-27 |  | 2023-08-10 | 2024-01-26 | CD//Ali Akaram | 2023-08-16 | CelcomDigi_RAN_CCSMY_TSS_Central_20230626_0006 | DU00002040142 |  |  |  |  | 2023-09-15 |  | TOWER
B02767 | B061C_B02767OD_JLNANGGERIKVANILLATS | Central |  | Decomm |  | 2023Q3 | MA | AllStar | 4.6 TSSR Approved |  | 2023-05-02 |  |  |  | 2023-10-26 |  | 2023-07-03 | 2023-11-29 | CD//Ali Akaram | 2023-08-26 | CelcomDigi_RAN_AllStar_TSS_Central_20230626_decom reraise | DU00002040143 |  |  |  |  | 2023-07-21 |  | BOOM
P00408 | P035E_P00408OD_JLNAIRITAM | Northern |  | Decomm |  | 2023Q3 | SM | GCI | 4.6 TSSR Approved |  | 2023-11-13 |  |  |  | 2023-11-02 |  | 2023-11-16 | 2024-03-13 | CD//Affendi | 2023-11-28 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240529-0109 | DU00002040144 |  |  |  |  | 2023-10-31 |  | BOOM
Q00001 | Q124F_Q00001OD_TMDAMAI | Sarawak | 9053K | Swap |  | 2023Q4 | SH | Datasco | 4.6 TSSR Approved |  | 2023-07-06 | 2023-07-10 |  | 2023-07-12 |  | Closed | 2023-07-12 | 2023-07-13 | CD//John | 2023-07-13 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 - Copy | DU00002040145 |  |  | 2024-01-13 | 2023-12-07 |  | Tower | TOWER | 46 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
B01100 | B065B_B01100OD_TMNBAHTERA | Central |  | Decomm |  | 2023Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-07-05 |  |  |  | 2023-09-25 |  | 2023-09-26 |  | CD//Sapian | 2024-02-20 | CelcomDigi_RANMW_Ascentrack_Central_20230706_0010 | DU00002040146 |  | Missing FE Antenna TX photo |  |  | 2024-01-11 |  | TRIPOD
Q00692 | Q132C_Q00692OD_SESCOPUJUT | Sarawak |  | Decomm |  | 2023Q4 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-06-21 |  |  |  | 2023-06-22 |  | 2023-07-26 | 2023-10-04 | CD//John | 2023-07-28 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002040147 |  | 1/9:uncompleted info & photos |  |  | 2025-01-15 |  | TOWER
K00327 | K011A_K00327OD_TUALANG | Northern |  | Decomm |  | 2023Q4 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-06-10 |  |  |  | 2023-07-27 |  | 2023-07-28 | 2023-09-06 | CD//Shamsul | 2023-08-07 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230829-0032/Celcom Digi_RAN-GTSB-TSS-Northern-20230529-0020 | DU00002040148 |  |  |  |  | 2023-10-14 |  | TOWER
B02045 | B060B_B02048OD_MN_KGASAHAN | Central | 1011P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN->Swap | 2026 | AI | GCI | 4.6 TSSR Approved |  | 2025-12-11 | 2025-12-18 |  | 2026-01-07 |  | Under Approval | 2026-01-16 | 2026-04-17 |  | 2026-03-10 |  | DU00002040149 |  |  |  | 2026-04-21 |  | Tower | TOWER | 76m | Add R8852E S9000 x6+R9264M M1821 x4 |  | 3
B02433 | B058B_B02433OD_SURAUALFAIZINSGKAPARINDAH | Central |  | Decomm |  | 2023Q3 | CR | CCSMY | 4.6 TSSR Approved |  | 2023-06-09 |  |  | 2023-06-13 | 2023-06-14 | Rectificating | 2023-07-24 | 2023-08-10 | CD//Sapian | 2023-08-03 | CelcomDigi_RAN_CCSMY_TSS_Central_20230626_decom reraise | DU00002040150 |  |  |  |  | 2023-08-14 | Lampole | LAMP_POLE | 30M
C00091 | C046C_C00091OD_CB_BUKI | Central | 1189K | Swap |  | 2023Q4 | HQ 6 | Magicell | 4.6 TSSR Approved |  | 2023-07-26 | 2023-07-27 |  | 2023-07-29 |  | Closed | 2023-07-31 | 2023-11-20 | Eastern Region PIC | 2023-11-16 | CelcomDigi_RAN_Magicell_TSS_Central_20230727 | DU00002040151 |  |  | 2024-01-29 | 2024-01-23 |  | Tower | TOWER | 76 | Add R8852E S9000 x3 + R8894E M1821 x3
A01185 | T3E_0619_Jalan Kamunting Selama | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040152 | [6 empty] | TOWER
B00616 | B061F_B00616OD_SAUJANAUTAMA | Central |  | Decomm |  | 2023Q3 | CR | GTSB | 4.6 TSSR Approved |  | 2023-05-18 |  |  |  | 2023-08-03 |  | 2023-08-02 | 2023-12-18 | CD//Ali akaram | 2023-08-14 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002040153 |  |  |  |  | 2023-10-20 |  | 3LEGGED
A00071 | A042C_A00071OD_AIRPUTIH_RCC | Northern |  | Decomm |  | 2023Q4 | MH | GTSB | 4.6 TSSR Approved |  | 2023-05-31 |  |  |  | 2023-07-01 |  | 2023-07-03 | 2023-08-08 | CD//Affendi | 2023-07-04 | Celcom Digi_RAN-GTSB-TSS-Northern-20230529-0020/Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230726-0024 | DU00002040154 |  |  |  |  | 2023-09-26 |  | TOWER
B00131 | B058B_B00131OD_SEMENTA | Central |  | Decomm |  | 2023Q3 | CR | CCSMY | 4.6 TSSR Approved |  | 2023-06-14 |  |  |  | 2023-06-20 |  | 2023-07-25 | 2023-10-17 | CD//Sapian | 2023-08-04 | CelcomDigi_RAN_CCSMY_TSS_Central_20230626_decom reraise | DU00002040155 |  |  |  |  | 2023-08-30 |  | TRIPOD
K00268 | K004A_K00268OD_KUALASUNGAI | Northern |  | Decomm |  | 2023Q4 | MH | CCSMY | 4.6 TSSR Approved |  | 2023-06-12 |  |  |  | 2023-07-03 |  | 2023-07-05 | 2023-08-10 | CD//Rohizam | 2023-08-07 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230613-0025/Celcom Digi_RAN-CCSMY-TSS Decomm-Northern-20240131-0091 | DU00002040156 |  | No TX Info, Photo not enough |  |  | 2023-10-03 |  | TOWER
B00098 | B058B_B00098OD_PR_PSNSGKERAMAT | Central |  | Decomm |  | 2023Q3 | CR | CCSMY | 4.6 TSSR Approved |  | 2023-06-14 |  |  |  | 2023-06-27 |  | 2023-07-25 | 2023-10-17 | CD//Sapian | 2023-08-07 | CelcomDigi_RAN_CCSMY_TSS_Central_20230626_decom reraise | DU00002040157 |  |  |  |  | 2023-08-29 |  | BOOM
P00760 | P035E_P00760OD_MASJIDNEGERIPNG | Northern |  | Decomm |  | 2023Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-06-15 |  |  |  | 2023-06-15 |  | 2023-06-16 | 2023-08-10 | CD//Shamsul | 2023-06-27 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1/Celcom Digi_RAN-CCSMY-TSS Decomm-Northern-20240131-0091 | DU00002040158 |  |  |  |  | 2023-08-07 | Lampole | MONOPOLE | 30m
B02793 | B061B_B02793OD_JLNBALAPANSEK13SA | Central | 1172K | Swap |  | 2023Q4 | HQ 1 | Datasco | 4.6 TSSR Approved |  | 2023-05-26 | 2023-06-21 |  | 2023-06-26 |  | Closed | 2023-06-28 | 2023-07-13 | CD//Sapian | 2023-07-12 | CelcomDigi_RAN_Datasco_TSS_Central_20230529_0023 | DU00002040159 |  |  | 2023-08-30 | 2023-08-28 |  | Pole | BOOM | 5 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
B01472 | B057C_B01472OD_TMNGBKPERMAI | Central | 1128K | Swap |  | 2023Q4 | XH | GTSB | 4.6 TSSR Approved |  | 2023-05-29 | 2023-06-12 |  | 2023-06-16 |  | Closed | 2023-06-18 | 2023-08-01 | CD//Sapian | 2023-08-01 | CelcomDigi_RAN_GTSB_TSS_Central_20230531_0026 | DU00002040160 |  |  | 2023-08-15 | 2023-08-13 |  | Monople Tree | MONOPOLE | 45M | Add R9264H M901821 x3 + R9264M M1821 x3 + R8862A S2601 x6,Dismantle Celcom all RRU&BBU |  | 123
B01443 | B061F_B01443OD_PCKALAMFASA2 | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-17 |  |  | 2023-05-22 | 2023-05-22 | Under Approval | 2023-06-02 | 2023-10-17 | CD//Sapian | 2023-06-11 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002040161 |  |  |  |  | 2023-08-14 |  | LAMP_POLE
P00092 | P035C_P00092IB_SUNWAYHTL | Northern |  | Decomm |  | 2023Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-06-16 |  |  |  | 2023-07-10 |  | 2023-07-12 | 2023-09-18 | CD//Quah | 2023-09-29 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2 | DU00002040162 |  |  |  |  | 2023-10-19 |  | IN-BUILDING
B02349 | B061B_B02349IB_AEONSHLM | Central |  | Decomm |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-06-22 |  |  |  | 2023-07-17 |  | 2023-07-26 | 2024-07-16 | CD//Sofiah | 2023-08-29 | CelcomDigi_RAN_Datasco_TSS_Central_20230623_0029 | DU00002040163 |  |  |  |  | 2023-11-16 |  | IN-BUILDING
B00463 | B057C_B00463OD_TMNBOLTON | Central |  | Decomm |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-07 |  |  |  | 2023-08-25 |  | 2023-08-28 | 2023-10-17 | CD//Sapian | 2023-08-30 | CelcomDigi_RANMW_GTSB_TSS_Central_20230609_0002 | DU00002040164 |  |  |  |  | 2023-09-11 |  | BOOM
B00346 | B058B_B00346OD_VLBTBELAH | Central |  | Decomm |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-05-03 |  |  | 2023-05-24 | 2023-08-04 | Closed | 2023-05-30 | 2024-05-29 | CD//Tee | 2024-02-21 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002040165 |  |  |  |  | 2023-09-20 |  | TOWER
B00643 | B060B_B00643OD_BTGBERJUNTAI | Central |  | Decomm |  | 2023Q3 | SS | GTSB | 4.6 TSSR Approved |  | 2023-04-28 | 2023-06-26 |  |  | 2023-06-21 |  | 2023-06-21 | 2023-08-04 | CD//Tee | 2023-07-22 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002040166 |  |  |  |  | 2023-07-27 | Minimast | TOWER | 12
Q00656 | Q132B_Q00656OD_CB_SGTUJUH | Sarawak |  | Decomm |  | 2023Q4 | SH | NR services | 4.6 TSSR Approved |  | 2023-07-17 |  |  |  | 2023-10-12 |  | 2023-10-12 | 2024-02-15 | CD//John | 2023-10-13 | Celcom Digi_RAN-NR Services-TSS-Sarawak-20230823 | DU00002040167 |  | TP not prepared by NR which is prepared by CCS. Awaiting NR to Resurvey. |  |  | 2025-06-28 |  | TOWER
B00662 | B058B_B00662OD_JLNSGUDANG | Central |  | Decomm |  | 2023Q3 | SS | Futong | 4.6 TSSR Approved |  | 2023-05-26 |  |  | 2023-05-31 | 2024-05-06 | Closed | 2023-06-20 | 2024-01-26 | CD//Norhaliza | 2023-07-07 | CelcomDigi_RAN_Futong_TSS_Central_20230626_decom reraise | DU00002040168 |  |  |  |  | 2023-08-29 |  | TOWER
B02382 | B061D_B02382OD_PSNBUDIMAN | Central | 1153K | Swap |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-11 | 2023-06-15 |  | 2023-06-22 |  | Closed | 2023-06-24 | 2023-08-15 | CD//Ali akaram | 2023-08-14 | CelcomDigi_RAN_GTSB_TSS_Central_20230612_0028 | DU00002040169 |  |  | 2023-09-22 | 2023-09-21 |  | Monopole | MINI STRUCTURE | 30 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 12
B00944 | B065B_B00944OD_KGGERACHIJAYA | Central | 1019P | Decomm | Swap->Decomm->On Hold->Swap->Decomm | 2023Q4 | SS | GCI | 4.6 TSSR Approved |  | 2023-06-28 | 2023-07-10 | 2025-06-30 |  | 2025-07-01 |  | 2025-07-07 |  | E//Ali | 2025-07-11 | CelcomDigi_RANMW_Futong_TSS_Central_20230630_0005 | DU00002040170 |  |  |  |  | 2025-08-05 | Tower | TOWER | 61
P00485 | P035E_P00485OD_TMNLUMBAKUDA | Northern |  | Decomm |  | 2023Q3 | SM | YPTT | 4.6 TSSR Approved |  | 2023-06-16 |  |  |  | 2023-08-02 |  | 2023-08-03 | 2025-10-01 | CD//Quah | 2023-09-29 | Celcom Digi_RAN-YPTT-TSS-Northern-20230609-0018 | DU00002040171 |  | 5/10 - NO TX PICTUERS IN EPMS TSSR |  |  | 2023-09-21 |  | MINI STRUCTURE
B00165 | B061A_B00165OD_PR_UITMPALAPES | Central |  | Decomm |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-19 |  |  |  | 2023-08-03 |  | 2023-08-09 | 2024-05-31 | CD//Norhaliza | 2023-08-04 | CelcomDigi_RAN_GTSB_TSS_Central_20230620_0030 | DU00002040172 |  |  |  |  | 2024-02-19 |  | MONOPOLE
Q00332 | Q132B_Q00332OD_MYYPORT | Sarawak |  | Decomm |  | 2023Q4 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-06-21 |  |  | 2023-06-26 |  | Closed | 2023-07-18 | 2023-09-29 | CD//John | 2023-07-18 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 | DU00002040173 |  |  |  |  | 2025-04-21 |  | TOWER
Q00596 | Q118A_Q00596IB_EVERLYID | Sarawak |  | Decomm |  | 2023Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2023-09-11 |  |  |  | 2023-09-12 |  | 2023-09-12 | 2023-10-04 |  | 2023-09-18 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230913/Celcom Digi_RAN-Trintel-TSS DECOMM-Sarawak-20230921 | DU00002040174 |  |  |  |  | 2023-12-15 |  | IN-BUILDING
9680A | Taman Jason Bintulu | Sarawak |  | Modernization |  | 2023Q3 | BY | South Pacific | 4.6 TSSR Approved |  | 2023-05-19 | 2023-05-20 |  | 2023-05-29 |  | Closed | 2023-06-08 | 2023-07-14 | E//Hannah | 2023-07-14 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230512-0001 | DU00002040175 |  |  | 2023-08-09 | 2023-07-26 |  | Monopole | 30m Rapole | 30.6m | Add R9264M M1821 x3,Dismantle R8892E M1821(BAA) x3
P00706 | P031A_P00706OD_TITI_TERAS_BPULAU | Northern |  | Decomm |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-05-09 |  |  |  | 2023-06-15 |  | 2023-06-16 | 2023-08-19 | CD//Quah | 2023-07-14 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002040176 |  |  |  |  | 2023-08-08 | Monopole | RAPID ASSEMBLY POLE (RAPOLE) | 30m
B01145 | B061D_B01145OD_SEK193SHLM | Central |  | Decomm |  | 2023Q4 | SS | Solusi | 4.6 TSSR Approved |  | 2023-10-11 |  |  | 2023-11-07 |  | Under Approval | 2023-11-17 | 2023-12-18 | CD//Ali Akaram | 2023-11-28 | CelcomDigi_RAN_Solusi_TSS_Central_20231113 | DU00002040177 |  |  |  |  | 2023-10-11 |  | LAMP_POLE
B02964 | B058B_B02964OD_TMNENGANN2 | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-27 |  |  |  | 2023-05-31 |  | 2023-06-13 | 2023-10-17 | CD//Norhaliza | 2023-08-18 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002040178 |  |  |  |  | 2023-08-23 |  | UNIPOLE
P00175 | P035B_P00175OD_AXISCOMPLEX | Northern |  | Decomm |  | 2023Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-05-03 |  |  |  | 2023-07-27 |  | 2023-06-08 | 2023-08-28 | CD//Affendi | 2023-06-13 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2 | DU00002040179 |  |  |  |  | 2023-09-13 |  | BOOM
B01681 | B061F_B01681OD_BDRTSKPUTERI4 | Central | 1133K | Swap |  | 2023Q2 | HQ 6 | Ascentrack | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-13 |  | 2023-05-16 |  | Closed | 2023-05-18 | 2023-06-05 | CD//Sapian | 2023-05-24 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230428_0015 | DU00002040180 |  |  | 2023-06-20 | 2023-06-16 |  | Unipole | TRIPOD | 6 | Add R9264H M901821 x3 + R9264M M1821 x2,Dismantle Celcom all RRU&BBU |  | 23
B02614 | B061A_B02614OD_JLNBUNGARAYAMERUKLG | Central |  | Decomm |  | 2023Q3 | ZA | Magicell | 4.6 TSSR Approved |  | 2024-03-16 |  |  |  | 2024-03-21 |  | 2024-03-26 | 2024-07-26 | CD//Norhaliza | 2024-06-10 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240323 | DU00002040181 |  |  |  |  | 2024-03-13 |  | LAMP_POLE
B00553 | B065B_B00553OD_CB_BKTTUNGGAL | Central | 1018P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  | CCSMY | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040182 | [6 empty] | TOWER
B00497 | B060B_B00497OD_SGBULHJERAMHOT | Central |  | Decomm |  | 2023Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-28 |  |  |  | 2023-08-03 |  | 2023-07-21 | 2024-01-26 | CD//Norhaliza | 2023-09-22 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002040183 |  |  |  |  | 2023-08-29 |  | TOWER
B00050 | B061B_B00050OD_SEK9SA3 | Central |  | Decomm |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-06-15 |  |  |  | 2024-08-22 |  | 2023-09-07 | 2023-12-18 | CD//Ali Akaram | 2023-09-21 | CelcomDigi_RAN_Datasco_TSS_Central_20230616_0026 | DU00002040184 |  |  |  |  | 2023-10-30 |  | BOOM
B00365 | B061A_B00365OD_JLNMERU | Central |  | Decomm |  | 2023Q3 | IE | Magicell | 4.6 TSSR Approved |  | 2023-06-23 |  |  |  | 2023-06-27 |  | 2023-07-22 | 2024-07-26 | CD//Norhaliza | 2023-10-09 | CelcomDigi_RAN_Magicell_TSS_Central_20230626_0017 | DU00002040185 |  |  |  |  | 2024-02-08 |  | MINI STRUCTURE
B01710 | B061D_B01710OD_KARANGKRAFSHLM | Central |  | Decomm |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-06-15 |  |  |  | 2023-10-05 |  | 2023-10-05 | 2024-04-29 | CD//Norhaliza | 2023-10-31 | CelcomDigi_RAN_GTSB_TSS_Central_20230616_0029 | DU00002040186 |  |  |  |  | 2023-10-13 |  | LAMP_POLE
B02512 | B060C_B02512OD_TMNALAMPERDANAPCKALAM | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-16 |  |  |  | 2023-05-23 |  | 2023-07-28 | 2023-12-21 | CD//Sapian | 2023-08-15 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002040187 |  |  |  |  | 2023-10-31 |  | LAMP_POLE
B00314 | B065B_B00314OD_KM432BERUNTUNG | Central |  | Decomm |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-05-31 |  |  |  | 2023-10-10 |  | 2023-10-13 | 2023-12-21 | CD//Sapian | 2023-10-21 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002040188 |  |  |  |  | 2023-08-30 |  | 4LEGGED
C00434 | C046C_C00434OD_RIAAPARTMENT | Central |  | Decomm |  | 2023Q4 | BY | GTSB | 4.6 TSSR Approved |  | 2024-05-28 |  |  |  | 2024-05-30 |  | 2024-06-04 |  | CD//Ali akaram | 2024-06-14 | CelcomDigi_RAN_GTSB_TSS_Central_20240423 | DU00002040189 |  |  |  |  | 2025-12-10 |  | BOOM
A01038 | A042B_A01038OD_TMN TEKKAH PERMAI_TPG | Northern | 4077K | Swap |  | 2023Q4 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-05-29 | 2023-06-07 |  | 2023-06-12 |  | Closed | 2023-06-13 | 2023-07-22 | CD//Rohizam | 2023-07-21 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002040190 |  |  | 2023-08-08 | 2023-08-04 |  | Minimast | UNIPOLE | 7 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 12
B01595 | B061G_B01595OD_DENAIALAM | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-09-03 |  |  |  | 2023-09-03 |  | 2023-09-04 | 2023-10-17 | CD//Sapian | 2023-09-07 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002040191 |  |  |  |  | 2023-08-28 |  | MONOPOLE
P00520 | P035E_P00520IB_TESCO_JELUTONG | Northern | 4148K | Swap |  | 2023Q3 | WP | YPTT | 4.6 TSSR Approved |  | 2023-05-19 | 2023-05-24 |  | 2023-05-31 |  | Closed | 2023-07-13 | 2023-07-25 | CD//Shamsul | 2023-07-18 | Celcom Digi_RAN-YPTT-TSS-Northern-20230509-0010 | DU00002040192 |  |  | 2023-07-25 | 2023-07-18 |  |  | IN-BUILDING |  | Add + R8862A S2100 x2 +R8862A S1800 x2+ R8862A S2601 x2,Dismantle all celcom BBU&RRU
9881A | Permy Mall Miri IB | Sarawak |  | Modernization |  | 2023Q4 | SH | Datasco | 4.6 TSSR Approved |  | 2023-07-10 | 2023-07-15 |  | 2023-07-21 |  | Closed | 2023-07-21 | 2023-07-31 | E//Nazrul | 2023-07-31 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 - Copy | DU00002040193 |  |  | 2023-08-15 | 2023-08-14 |  | Portables BTS | In-building system |  | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8882-GUL1812 x3+R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3
B01976 | B057B_B01976OD_SELAYANGMULIA | Central |  | Decomm |  | 2023Q4 | MA | GCI | 4.6 TSSR Approved |  | 2023-08-29 |  |  |  | 2023-08-29 |  | 2023-09-01 | 2023-11-15 | CD//Norhaliza | 2023-09-25 | CelcomDigi_RAN_YPTT_TSS_Central_20230727 | DU00002040194 |  |  |  |  | 2023-09-27 |  | MONOPOLE
B00679 | B060C_B00679OD_BKTROTAN | Central | 1094K | Swap |  | 2023Q3 | HQ 6 | GTSB | 4.6 TSSR Approved |  | 2023-04-29 | 2023-05-17 |  | 2023-05-23 |  | Closed | 2023-05-24 | 2023-07-13 | CD//Norhaliza | 2023-07-13 | CelcomDigi_RAN_GTSB_TSS_20230505_0023 | DU00002040195 |  |  | 2023-08-23 | 2023-08-21 |  | Tower | TOWER | 75m | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 13
B00465 | B065B_B00465OD_PEKANKALUMPANG | Central | 1085K | Swap |  | 2023Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-07-12 | 2023-07-13 |  | 2023-07-15 |  | Closed | 2023-07-17 | 2023-08-02 | CD//Ali akaram | 2023-08-02 | Celcomdigi_RAN_Ascentrack_TSS_Central_20230707_0027 | DU00002040196 |  |  | 2023-10-07 | 2023-09-22 |  | Minimast | TRIPOD | 7m | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
P00568 | P035B_P00568OD_STRAITSQUAYW9 | Northern |  | Decomm |  | 2023Q3 | BY | GCI | 4.6 TSSR Approved |  | 2023-10-30 |  |  |  | 2023-11-02 |  | 2023-11-02 | 2023-12-18 | CD//Affendi | 2023-11-10 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240529-0109 | DU00002040197 |  |  |  |  | 2023-11-30 |  | MINARET
B00364 | B058A_B00364OD_TMKAPAR | Central |  | Decomm |  | 2023Q3 | IE | Magicell | 4.6 TSSR Approved |  | 2023-08-02 |  |  |  | 2023-08-15 |  | 2023-08-16 | 2023-12-19 | CD//Norhaliza | 2023-10-30 | CelcomDigi_RAN_Magicell_TSS_Central_20230803 | DU00002040198 |  |  |  |  | 2024-03-26 |  | 4LEGGED
B02473 | B061C_B02473OD_DESALATANIASEK36SHLM | Central |  | Decomm |  | 2023Q3 | AI | Futong | 4.6 TSSR Approved |  | 2023-05-18 |  |  | 2023-05-20 |  | Closed | 2025-05-06 | 2023-10-25 | CD//Sapian | 2026-04-17 | CelcomDigi_RAN_Futong_TSS_Central_20230626_decom reraise | DU00002040199 |  | SOW Changed p to Decomm TSSR Mod/Swap submitted by Subcon |  |  | 2023-08-01 |  | AESTHETIC MONOPOLE
B00361 | B061A_B00361OD_PR_KLJSENIBINA | Central | 1076K | Swap |  | 2023Q4 | HQ 6 | GTSB | 4.6 TSSR Approved |  | 2023-06-15 | 2023-06-22 |  | 2023-06-28 |  | Closed | 2023-07-03 | 2023-11-29 | CD//Norhaliza | 2023-11-28 | CelcomDigi_RAN_GTSB_TSS_Central_20230612_0028 | DU00002040200 |  |  | 2023-10-15 | 2023-09-27 |  | Pole | BOOM | 5 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
B02768 | B058B_B02768OD_HARPSOONTS | Central |  | Decomm |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-26 |  |  |  | 2023-05-28 |  | 2023-06-21 | 2023-07-10 | CD//Norhaliza | 2023-07-10 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002040201 |  |  |  |  | 2023-08-03 |  | BOOM
B00805 | B058C_B00805OD_TMNKLGJAYA2 | Central |  | Decomm |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-06-22 |  |  |  | 2023-07-04 |  | 2023-07-07 | 2023-12-19 | CD//Sapian | 2023-07-15 | Celcomdigi_RAN_Ascentrack_TSS_Central_20230622_0023 | DU00002040202 |  |  |  |  | 2023-08-16 |  | 3LEGGED
B01486 | B061C_B01486OD_SURAUANAJIHINKOTAKEMUNING | Central |  | Decomm |  | 2023Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-06-16 |  |  |  | 2023-06-17 |  | 2023-06-28 | 2023-12-19 | CD//Ali Akaram | 2023-11-17 | CelcomDigi_RAN_Allstar_TSS_Central_20230620_0013 | DU00002040203 |  |  |  |  | 2023-07-21 |  | LAMP_POLE
B00175 | B062A_B00175OD_KGSGLANG | Central |  | Decomm |  | 2023Q4 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-07-22 |  |  |  | 2023-08-16 |  | 2023-08-02 | 2024-01-26 | CD//Sapian | 2023-08-16 | CelcomDigi_RAN_CCSMY_TSS_Central_20230815 | DU00002040204 |  | 28/7 |  |  | 2023-09-18 |  | TOWER
P00599 | P031B_P00599SC_BLUECUBEELITEAVENUE | Northern | 4154K | Swap |  | 2023Q3 | WP | CCSMY | 4.6 TSSR Approved |  | 2023-07-10 | 2023-07-12 |  | 2023-07-13 |  | Closed | 2023-07-14 | 2023-07-25 | CD//Shamsul | 2023-07-18 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230509-0018 | DU00002040205 |  |  | 2023-07-19 | 2023-07-18 |  | Portables BTS | IN-BUILDING | IBC | Add BS8932 x1,Dismantle all celcom BBU&RRU
B00435 | B057C_B00435OD_UIA3 | Central | 1080K | Swap |  | 2023Q4 | CR | Datasco | 4.6 TSSR Approved |  | 2023-10-17 | 2023-10-25 |  | 2023-10-30 |  | Closed | 2023-11-01 | 2023-11-07 | CD//Sapian | 2023-11-06 | CelcomDigi_RAN_Datasco_TSS_Central_20231018 | DU00002040206 |  |  | 2024-03-09 | 2024-02-24 |  | Monopole | LAMP_POLE | 27m | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
C00542 | B065B_C00542OD_KM3GNTGWAYDOWN | Central | 1192K | Swap |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-10-16 | 2023-10-17 |  | 2023-10-21 |  | Closed | 2023-10-24 | 2023-11-15 | CD//Sapian | 2023-11-14 | CelcomDigi_RANMW_GTSB_TSS_Central_20230609_0002 | DU00002040207 |  |  | 2024-12-04 | 2024-12-03 |  | Monopole | LAMP_POLE | 23 | Add R8852E S9000 x3 + R8894E M1821 x3
P00330 | P031A_P00330OD_PTACHEH | Northern |  | Decomm |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-05-12 |  |  |  | 2023-06-20 |  | 2023-06-20 | 2023-09-06 | CD//Affendi | 2023-06-21 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1 | DU00002040208 |  |  |  |  | 2023-09-19 |  | TOWER
Q00250 | Q118B_Q00250OD_CB_BT11BTU | Sarawak | 9061K | Swap |  | 2023Q3 | BY | YPTT | 4.6 TSSR Approved |  | 2023-05-19 | 2023-05-26 |  | 2023-06-01 |  | Rectificating | 2023-06-13 | 2023-06-21 | CD//John | 2023-06-21 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20230524-0002 | DU00002040209 |  |  | 2024-01-10 | 2023-12-28 |  | Tower | GUYED MAST | 45 | Add R9264H M901821 x3 + R9264M M1821 x2,Dismantle Celcom all RRU&BBU |  | 13
9692A | RPR Kidurong | Sarawak |  | Modernization |  | 2023Q3 | SH | South Pacific | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI,L2600 change to 40M¦Sacofa lampole not allow to add antenna | 2023-05-27 | 2023-05-27 |  | 2023-06-09 |  | Closed | 2023-06-15 | 2023-06-28 | E//Hannah | 2023-06-26 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230512-0001 | DU00002040210 | NIC_S3_Change MM to BI,L2600 change to 40M_owner reject_SACOFA SDN BHD |  | 2023-12-27 | 2023-12-11 |  | Monopole | 30m Rapole | 30m | Add R9264H M901821 x3 + R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3 |  | 123
K00711 | K004A_K00711OD_KGGUNUNG | Northern | 4103K | Swap |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-28 | 2023-06-15 |  | 2023-06-17 |  | Closed | 2023-07-04 | 2023-08-07 | CD//Rohizam | 2023-08-07 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230529-0020 | DU00002040211 |  |  | 2023-09-13 | 2023-09-12 |  | Lampole | MONOPOLE | 30 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 3
K00596 | K004A_K00596OD_TMNRAKYAT | Northern |  | Decomm |  | 2023Q4 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-06-12 |  |  |  | 2023-06-15 |  | 2023-06-18 | 2023-10-27 | CD//Shamsul | 2023-07-03 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230613-0025 | DU00002040212 |  | Need dismantle Unused link |  |  | 2023-10-03 |  | AESTHETIC MONOPOLE TREE
B02752 | B061A_B02752OD_JLNPEGAGAE12DESAALAMSA | Central |  | Decomm |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-09-08 |  |  |  | 2024-08-22 |  | 2023-10-16 | 2023-11-16 | CD//Norhaliza | 2023-11-06 | CelcomDigi_RAN_Datasco_TSS_Central_20231213 | DU00002040213 |  |  |  |  | 2023-09-26 |  | UNIPOLE
P00691 | P031A_P00691OD_PEKAN_BALIK_PULAU | Northern |  | Decomm |  | 2023Q3 | MH | GCI | 4.6 TSSR Approved |  | 2023-05-03 |  |  |  | 2023-06-12 |  | 2023-06-13 | 2023-08-10 | CD//QUAH | 2023-07-14 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002040214 |  |  |  |  | 2023-07-29 |  | TOWER
B02801 | B065B_B02801OD_JLNBKTSENTOSARWG | Central | 1176K | Swap |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-19 | 2023-04-29 |  | 2023-05-03 |  | Closed | 2023-05-05 | 2023-06-03 | CD//Tee | 2023-05-19 | CelcomDigi_RAN_Datasco_TSS_Central_20230419_0014 | DU00002040215 |  |  | 2023-07-12 | 2023-07-12 |  | Lampole | RAPID ASSEMBLY POLE (RAPOLE) | 30m | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 23
B02268 | B058B_B02268OD_BILLBOARDTOLSGRASAU | Central |  | Decomm |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-10-09 |  |  |  | 2023-10-13 |  | 2023-10-14 | 2024-09-26 | CD//Norhaliza | 2023-11-17 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231011 | DU00002040216 |  |  |  |  | 2023-10-09 |  | LAMP_POLE
A00055 | A042A_A00055OD_TMNLELA_RDD | Northern |  | Decomm |  | 2023Q4 | MH | GCI | 4.6 TSSR Approved |  | 2023-05-28 |  |  |  | 2023-06-22 |  | 2023-06-22 | 2023-08-08 | CD//Shamsul | 2023-07-04 | Celcom Digi_RAN-GCI-TSS-Northern-20230529-0022/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002040217 |  |  |  |  | 2023-09-07 |  | TOWER
B02273 | B061A_B02273OD_U12CAHAYAALAM | Central |  | Decomm |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-05-08 |  |  | 2023-05-24 | 2023-09-21 | Closed | 2023-05-31 | 2024-05-31 | CD//Tee | 2023-06-02 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002040218 |  |  |  |  | 2023-09-21 |  | BOOM
B02059 | B058A_B02059OD_JLNJAMBUMERU | Central | 1819K | Decomm |  | 2023Q3 | MA | Magicell | 4.6 TSSR Approved |  | 2023-06-14 |  |  |  | 2023-06-21 |  | 2023-06-21 | 2023-09-07 | CD//Norhaliza | 2023-10-09 | CelcomDigi_RAN_Magicell_TSS_Central_20230616_0013/CelcomDigi_RAN-TX_Magicell_TSS_Central_20230816_Decom | DU00002040219 |  |  |  |  | 2023-08-28 |  | TOWER
9979A | Taman Matang | Sarawak |  | Modernization |  | 2023Q4 | BY | Magicell | 4.6 TSSR Approved |  | 2023-06-14 | 2023-06-16 |  | 2023-06-20 |  | Closed | 2023-06-20 | 2023-07-17 | E//Hannah | 2023-07-17 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002040220 |  |  | 2023-08-05 | 2023-08-02 |  | Monopole | 30M Rapole | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
K00605 | K004A_K00605OD_PUMPONG | Northern |  | Decomm |  | 2023Q4 | SM | GTSB | 4.6 TSSR Approved |  | 2023-06-02 |  |  |  | 2023-06-16 |  | 2023-06-16 | 2023-08-10 | CD//Affendi | 2023-06-27 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230829-0032_V2/Celcom Digi_RAN-GTSB-TSS-Northern-20230529-0020 | DU00002040221 |  |  |  |  | 2023-10-11 |  | AESTHETIC MONOPOLE TREE
Q00156 | Q124F_Q00156OD_CB_DAMAIBEACH | Sarawak |  | Decomm |  | 2023Q4 | SH | AllStar | 4.6 TSSR Approved |  | 2023-07-24 |  |  |  | 2023-08-09 |  | 2023-08-10 | 2024-02-15 | CD//John | 2023-08-15 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230608-0006 | DU00002040222 |  | 22/8: wrong proposal |  |  | 2023-11-27 |  | TOWER
B02502 | B061F_ B02502OD_ FELDABKTCERAKAH | Central | 1160K | Swap |  | 2023Q3 | XH | Magicell | 4.6 TSSR Approved |  | 2023-05-15 | 2023-05-24 |  | 2023-05-26 |  | Closed | 2023-05-28 | 2023-06-28 | CD//Sapian | 2023-06-22 | CelcomDigi_RANMW_Magicell_TSS_Central_20230517_0002 | DU00002040223 |  |  | 2023-08-24 | 2023-08-17 |  | Tower | LAMP_POLE | 30M | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle Celcom all RRU&BBU |  | 1
B00633 | B061A_B00633OD_SEK6SHLM | Central |  | Decomm |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-06-15 |  |  |  | 2023-08-03 |  | 2023-08-08 | 2024-12-10 | CD//Norhaliza | 2023-10-30 | CelcomDigi_RAN_Datasco_TSS_Central_20230616_0026 | DU00002040224 |  |  |  |  | 2023-10-28 |  | TOWER
C00985 | C046C_C00985OD_SKYWAY_STATION2_CHIN SWEE | Central |  | Decomm |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-08-03 |  |  |  | 2023-08-04 |  | 2023-08-10 | 2023-12-19 | CD//Sapian | 2023-08-17 | CelcomDigi_RAN_GTSB_TSS_Central_20230804 | DU00002040225 |  |  |  |  | 2025-07-28 |  | BOOM
P00523 | P035E_P00523OD_BANKRAKYATJELUTUNG | Northern |  | Decomm |  | 2023Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-05-23 |  |  |  | 2023-06-08 |  | 2023-06-09 | 2024-02-15 | CD//Quah | 2023-07-14 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230720-0023/Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2 | DU00002040226 |  | 22/8: Please include Photo Antenna, ODU, & FE for Unused link to be decom NT03325 (P00523-P00062) |  |  | 2023-09-27 |  | BILLBOARD
B01053 | B060B_B01053OD_BT20JERAM | Central |  | Decomm |  | 2023Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-27 | 2023-06-26 |  |  | 2023-08-29 |  | 2023-08-30 | 2023-10-17 | CD//Sapian | 2023-09-07 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002040227 |  |  |  |  | 2023-09-09 | Tower | TOWER | 60
K00361 | K004B_K00361OD_TAMANBADLISHAH | Northern |  | Decomm |  | 2023Q4 | MH | GTSB | 4.6 TSSR Approved |  | 2023-05-30 |  |  |  | 2023-06-28 |  | 2023-07-03 | 2023-07-28 | CD//Shamsul | 2023-07-06 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230829-0032/Celcom Digi_RAN-GTSB-TSS-Northern-20230529-0020 | DU00002040228 |  |  |  |  | 2023-10-10 |  | BOOM
Q00291 | Q118B_Q00291OD_KKNSIMILAJAU | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2023Q3 | SH | Magicell | 4.6 TSSR Approved |  | 2023-08-01 |  |  |  | 2023-08-02 |  | 2023-08-02 | 2023-09-08 | CD//John | 2023-08-02 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230913/0619Sarawak-Magicell-BOQ Template (template) | DU00002040229 |  | 1/9: UNCOMPLETED INFO |  |  |  |  | TOWER
Q00253 | Q118B_Q00253OD_PUSPAKOMBTU | Sarawak |  | Decomm |  | 2023Q3 | SH | CCSMY | 4.6 TSSR Approved |  | 2023-06-20 |  |  |  | 2023-06-26 |  | 2023-07-27 | 2024-07-19 | CD//John | 2023-07-28 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230614-0008 | DU00002040230 |  | 22/8: All tx info & photos are missing |  |  | 2024-01-24 |  | TOWER
P00750 | P031B_P00750OD_BDR_SUNWAY_TUNAS_PNG | Northern |  | Decomm |  | 2023Q3 | SM | YPTT | 4.6 TSSR Approved |  | 2023-05-15 |  |  |  | 2023-07-09 |  | 2023-07-10 | 2023-09-18 | CD//Quah | 2023-07-14 | Celcom Digi_RAN-YPTT-TSS-Northern-20230609-0018/Celcom Digi_RAN-YPTT-TSS Decomm-Northern-20240311-0048 | DU00002040231 |  |  |  |  | 2024-01-17 |  | BOOM
P00214 | P035C_P00214OD_WISMADAUD | Northern |  | Decomm |  | 2023Q3 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-05-25 |  |  |  | 2023-08-08 |  | 2023-08-09 | 2023-08-28 | CD//Shamsul | 2023-08-09 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002040232 |  |  |  |  | 2023-10-06 |  | BOOM
Q00065 | Q124F_Q00065OD_TMSEMARIANG | Sarawak |  | Decomm |  | 2023Q4 | ZB | AllStar | 4.6 TSSR Approved |  | 2023-07-24 |  |  |  | 2023-08-09 |  | 2023-08-10 | 2024-07-15 | CD//John | 2023-08-12 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230622 | DU00002040233 |  | 21/8: wrong proposal |  |  | 2023-10-31 |  | BOOM
Q00632 | Q118B_Q00632OD_BT16BTU | Sarawak |  | Decomm |  | 2023Q3 | SH | YPTT | 4.6 TSSR Approved |  | 2023-06-08 |  |  |  | 2023-06-23 |  | 2023-07-26 | 2024-07-15 | CD//John | 2023-07-27 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20230612-0006 | DU00002040234 |  | 24/8: wrong proposal |  |  | 2024-01-17 |  | TOWER
B00664 | B061D_B00664OD_SEK19SA | Central |  | Decomm |  | 2023Q4 | CR | GTSB | 4.6 TSSR Approved |  | 2023-06-08 |  |  |  | 2023-08-03 |  | 2023-08-02 | 2024-04-29 | CD//Norhaliza | 2023-10-30 | CelcomDigi_RANMW_GTSB_TSS_Central_20230609_0002 | DU00002040235 |  |  |  |  | 2023-10-09 |  | MINI STRUCTURE
P00014 | P035A_P00014OD_AIRITAM | Northern | 4113K | Swap |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-05-13 | 2023-05-16 |  | 2023-05-22 |  | Closed | 2023-05-24 | 2023-05-29 | CD//Heng | 2023-05-27 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0015 | DU00002040236 |  |  | 2023-09-18 | 2023-09-07 |  | Tower | TOWER | 19 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x5,Dismantle Celcom all RRU&BBU |  | 12
B01092 | B060A_B01092OD_KGSRIMAKMUR | Central |  | Decomm |  | 2023Q3 | CR | GTSB | 4.6 TSSR Approved |  | 2023-04-28 | 2023-06-26 |  |  | 2023-08-03 |  | 2023-08-01 | 2024-01-26 | CD//Sapian | 2023-08-16 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002040237 |  |  |  |  | 2023-09-09 |  | TOWER | 45
P00307 | P035C_P00307IB_EVERGREENHOTEL | Northern |  | Decomm |  | 2023Q3 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-05-02 |  |  |  | 2023-07-26 |  | 2023-06-20 | 2023-07-21 | CD//Quah | 2023-07-14 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2/Celcom Digi_CD CONSOLIDATION-GTSB-TI-Northern-20240920_Old Contract | DU00002040238 |  |  |  |  | 2023-09-12 |  | IN-BUILDING
K00223 | K004A_K00223OD_ALORJANGGUS | Northern |  | Decomm |  | 2023Q4 | ZA | GCI | 4.6 TSSR Approved |  | 2023-06-15 |  |  |  | 2023-06-23 |  | 2023-06-26 | 2024-02-29 | CD//Rohizam | 2023-08-07 | Celcom Digi_RAN-GCI-TSS-Northern-20230616-0030 | DU00002040239 |  |  |  |  | 2023-10-10 |  | TOWER
P00067 | P031B_P00067OD_FIZ2 | Northern | 4172K | Swap | Decomm->Swap | 2023Q3 | MH | CCSMY | 4.6 TSSR Approved |  | 2023-05-19 | 2023-09-04 |  | 2023-09-06 | 2023-06-13 | Closed | 2023-06-14 | 2023-10-19 | CD//QUAH | 2023-10-18 | 0626Northen-CCSMY-BOQ Template (template) | DU00002040240 |  | 27072023: Need resurvey for E1 and IDU | 2023-09-27 | 2023-09-26 |  | Pole | BOOM | 6 | Add R9264M M1821 x3+R9264H M901821 x3+R8862A S2601 x6,Dismantle |  | 123
B00310 | B065B_B00310OD_TMKALUMPANG | Central | 1074K | Swap |  | 2023Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-07-26 | 2023-07-28 |  | 2023-08-01 |  | Closed | 2023-08-09 | 2023-08-16 | CD//Ali Akaram | 2023-08-16 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230726 | DU00002040241 |  |  | 2024-02-09 | 2023-09-22 |  | Monopole | MONOPOLE | 45m | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 1
9681A | ABF Housing | Sarawak |  | Modernization |  | 2023Q3 | BY | South Pacific | 4.6 TSSR Approved |  | 2023-05-16 | 2023-05-22 |  | 2023-06-07 |  | Closed | 2023-06-08 | 2023-06-17 | E//Hannah | 2023-06-16 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230512-0001 | DU00002040242 |  |  | 2023-07-06 | 2023-07-04 |  | Monopole | 30m Monopole | 31m | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882 S1800B(B6B) x3
B01795 | B065B_B01795OD_T3_KALUMPANG | Central | 1143K | Swap |  | 2023Q4 | HQ 6 | Ascentrack | 4.6 TSSR Approved |  | 2023-07-22 | 2023-07-24 |  | 2023-07-26 |  | Closed | 2023-07-27 | 2023-08-28 | CD//Ali Akaram | 2023-08-26 | Celcomdigi_RAN_Ascentrack_TSS_Central_20230707_0027 | DU00002040243 |  |  | 2023-09-25 | 2023-09-23 |  |  | TOWER | 75 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
A00088 | A042A_A00088OD_SGBAYOR | Northern |  | Decomm |  | 2023Q4 | SM | YPTT | 4.6 TSSR Approved |  | 2023-07-18 |  |  |  | 2023-08-07 |  | 2023-08-08 | 2023-09-21 | CD//Rohizam | 2023-08-08 | Celcom Digi_RAN-YPTT-TSS-Northern-20230801-0026 | DU00002040244 |  |  |  |  | 2023-09-04 |  | TOWER
B02466 | B058A_B02466OD_KGBKTKERAYONG | Central | 1156K | Swap |  | 2023Q3 | YZ | YPTT | 4.6 TSSR Approved |  | 2023-05-27 | 2023-05-25 |  | 2023-05-29 |  | Closed | 2023-05-30 | 2023-06-07 | CD//Ali akaram | 2023-06-06 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002040245 |  |  | 2023-08-14 | 2023-08-08 |  | Lampole | LAMP_POLE | 30m | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
K00835 | K004A_K00835OD_TMN_TH_BKT_PINANG | Northern | 4106K | Swap |  | 2023Q4 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-06-01 | 2023-06-06 |  | 2023-06-19 |  | Closed | 2023-06-23 | 2023-08-08 | CD//Rohizam | 2023-08-08 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230606-0022 | DU00002040246 |  |  | 2023-09-14 | 2023-09-14 |  | Tower | TOWER | 40 | Add R9264H M901821 x3 + R9264M M1821 x2,Dismantle Celcom all RRU&BBU |  | 12
B02213 | B065B_B02213OD_SENTOSAINDUSTRI | Central |  | Decomm |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-19 |  |  | 2023-05-17 | 2024-06-24 | Closed | 2023-05-30 | 2024-07-19 | CD//Ali akaram | 2023-06-11 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002040247 |  |  |  |  | 2023-07-26 | Lampole | LAMP_POLE | 24
C00540 | B065B_C00540OD_KM2GENTING | Central | 1191K | Swap |  | 2023Q4 | HQ 6 | GTSB | 4.6 TSSR Approved |  | 2023-06-08 | 2023-06-16 |  | 2023-06-20 |  | Closed | 2023-06-22 | 2023-07-10 | CD//Sapian | 2023-07-10 | CelcomDigi_RAN_GTSB_TSS_Central_20230609_0027 | DU00002040248 |  |  | 2024-11-30 | 2024-11-26 |  | Monopole | LAMP_POLE | 23 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
P00579 | P031A_P00579OD_TELUKKUMBARPERMAI | Northern |  | Decomm |  | 2023Q3 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-05-23 |  |  |  | 2023-06-21 |  | 2023-06-22 | 2023-08-08 | CD//Quah | 2023-07-07 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2 | DU00002040249 |  |  |  |  | 2023-09-01 |  | BOOM
P00370 | P035B_P00370OD_TMBATUFERRINGHI | Northern | 4141K | Swap |  | 2023Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-06-17 | 2023-07-27 |  | 2023-07-31 |  | Rectificating | 2023-08-08 | 2023-08-09 | CD//Affendi | 2023-08-09 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0016 | DU00002040250 |  |  | 2023-08-29 | 2023-08-28 |  | Tower | TOWER | 49 | Add R8852E S9000 x3 + R8894E M1821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
9973A | Kidurong 4 | Sarawak |  | Modernization |  | 2023Q3 | ZB | CCSMY | 4.6 TSSR Approved |  | 2023-05-17 |  |  | 2025-02-14 |  | Under Approval | 2023-09-22 | 2023-11-15 | E//Hannah | 2023-11-10 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230516-0006 | DU00002040251 |  |  | 2023-10-25 | 2023-10-19 |  | Monopole | Tower | 30M | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 3
Q00473 | Q124F_Q00473OD_CB_SPGPASIRPANDAK | Sarawak |  | Decomm |  | 2023Q4 | SH | Datasco | 4.6 TSSR Approved |  | 2023-06-15 |  |  |  | 2023-06-20 |  | 2023-07-24 | 2023-09-19 | CD//John | 2023-07-25 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 | DU00002040252 |  | 8/9: uncompleted info & photos |  |  | 2025-10-30 |  | TOWER
B00308 | B065B_B00308OD_BKTBERUNTUNG | Central |  | Decomm |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-06-03 |  |  |  | 2024-08-13 |  | 2023-07-21 | 2025-03-07 | CD//Sapian | 2023-07-29 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002040253 |  |  |  |  | 2024-01-12 |  | TOWER
B02845 | B061D_B02845OD_JLNLANDAKSEK20SHLM2 | Central | 1181K | Swap |  | 2023Q4 | HQ 6 | GTSB | 4.6 TSSR Approved |  | 2023-06-15 | 2023-06-23 |  | 2023-06-28 |  | Closed | 2023-07-03 | 2023-08-28 | CD//Ali Akaram | 2023-08-26 | CelcomDigi_RANMW_GTSB_TSS_Central_20230616_0004 | DU00002040254 |  |  | 2023-09-19 | 2023-09-18 |  | Lampole | LAMP_POLE | 19 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2,Dismantle Celcom all RRU&BBU | 3
P00209 | P031B_P00209OD_TMBAYANBARU | Northern | 4130K | Swap |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-06-17 | 2023-07-04 |  | 2023-07-05 |  | Closed | 2023-07-06 | 2023-07-14 | CD//Affendi | 2023-07-08 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0016 | DU00002040255 |  |  | 2023-07-25 | 2023-07-18 |  | Pole | BOOM | 7 | Add R8852E S9000 x3 + A9732 M1821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 123
Q00708 | Q132C_Q00708OD_JLNSRIDAGANG | Sarawak |  | Decomm |  | 2023Q4 | ZB | AllStar | 4.6 TSSR Approved |  | 2023-07-24 |  |  |  | 2023-08-10 |  | 2023-08-10 | 2023-08-23 | CD//John | 2023-08-11 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230608-0006 | DU00002040256 |  |  |  |  | 2025-01-28 |  | MONOPOLE
B00279 | B060B_B00279OD_JANYESTATE | Central |  | Decomm | Decomm->On Hold->Decomm | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-08-02 |  |  |  | 2023-08-13 |  | 2023-08-17 | 2024-09-26 | CD//Ali Akaram | 2024-09-11 | CelcomDigi_RAN_YPTT_TSS_Central_20230804 | DU00002040257 |  |  |  |  | 2024-09-08 |  | TOWER
P00413 | P031A_P00413OD_KKTM | Northern |  | Decomm |  | 2023Q3 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-05-25 |  |  |  | 2023-08-02 |  | 2023-08-04 | 2023-09-18 | CD//Quah | 2023-09-29 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002040258 |  |  |  |  | 2023-08-02 |  | LAMP_POLE
B00065 | B058B_B00065OD_RANTAUPJG2 | Central |  | Decomm |  | 2023Q3 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-06-09 |  |  | 2023-06-13 | 2023-06-14 | Closed | 2023-07-07 | 2023-08-10 | CD//Norhaliza | 2023-07-17 | CelcomDigi_RAN_CCSMY_TSS_Central_20230626_decom reraise | DU00002040259 |  |  |  |  | 2024-02-21 |  | GUYED MAST
C01268 | C046C_C01268OD_JANDABAIKBENTONG | Central |  | Decomm |  | 2023Q4 | IE | Magicell | 4.6 TSSR Approved |  | 2023-07-26 |  |  |  | 2023-07-27 |  | 2023-08-02 | 2023-10-17 | CD//Ali akaram | 2023-08-14 | CelcomDigi_RAN_Magicell_TSS_Central_20230727_Decom | DU00002040260 |  |  |  |  | 2023-09-26 |  | TOWER
B00695 | B062A_B00695OD_PT13SGPJG | Central | 1812K | Swap | Decomm->Swap | 2023Q4 | CR | Magicell | 4.6 TSSR Approved |  | 2023-09-04 | 2023-09-06 |  | 2023-09-08 |  | Closed | 2023-08-15 | 2023-12-07 | CD//Sapian | 2023-12-07 | 0626Central-Magicell-BOQ Template (template) | DU00002040261 |  |  | 2023-11-29 | 2023-11-29 |  | Tower | TOWER | 61M | Add R8852E S9000 x2+R9264H M901821 x1+R8862A S2601 x3+A9732 M1821 x2,Dismantle | 12
B00423 | B065B_B00423OD_SEK2BKTSENTOSA | Central | 1078K | Swap |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-19 | 2023-04-25 |  | 2023-05-05 |  | Closed | 2023-05-08 | 2023-06-05 | CD//Ali akaram | 2023-05-22 | CelcomDigi_RAN_Datasco_TSS_Central_20230420_0015 | DU00002040262 |  |  | 2023-09-10 | 2023-08-21 |  | Monopole | MONOPOLE TREE | 30 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x5,Dismantle Celcom all RRU&BBU |  | 12
B00079 | B061C_B00079OD_SGKANDIS | Central |  | Decomm |  | 2023Q3 | SS | Futong | 4.6 TSSR Approved |  | 2023-05-24 |  |  | 2023-06-13 | 2024-05-06 | Closed | 2023-07-12 | 2023-10-17 | CD//Sapian | 2023-07-18 | CelcomDigi_RAN_Futong_TSS_Central_20230626_decom reraise | DU00002040263 |  |  |  |  | 2023-11-29 |  | TOWER
B01171 | B057A_B01171OD_TMNPRIMASLYG | Central |  | Decomm |  | 2023Q4 | SS | YPTT | 4.6 TSSR Approved |  | 2023-10-09 |  |  |  | 2023-10-30 |  | 2023-11-02 | 2023-11-29 | CD//Ali akaram | 2023-11-10 | CelcomDigi_RAN_YPTT_TSS_Central_20231011 | DU00002040264 |  |  |  |  | 2023-12-20 |  | MONOPOLE
Q00717 | Q124F_Q00717OD_KGTUPONG | Sarawak |  | Decomm |  | 2023Q4 | SH | South Pacific | 4.6 TSSR Approved |  | 2023-08-16 |  |  |  | 2023-08-22 |  | 2023-08-23 | 2023-08-30 | CD//John | 2023-08-23 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230913 | DU00002040265 |  |  |  |  | 2023-10-11 |  | MONOPOLE
9935A | Bintulu City Mall | Sarawak |  | Modernization |  | 2023Q3 | BY | YPTT | 4.6 TSSR Approved |  | 2023-05-20 | 2023-07-04 |  | 2023-07-09 |  | Closed | 2023-07-11 | 2023-07-28 | E//Hannah | 2023-07-28 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20230622 | DU00002040266 |  |  | 2023-08-29 | 2023-08-15 |  | Monopole | 30m Rapole | 30 | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 1
B01632 | B058C_B01632OD_BDRPUTERAKLG2 | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-16 |  |  |  | 2023-08-09 |  | 2023-08-11 | 2023-11-22 | CD//Sapian | 2023-08-18 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002040267 |  |  |  |  | 2023-09-04 |  | RAPID ASSEMBLY POLE (RAPOLE)
B00640 | B061A_B00640OD_PR_BKTRAJA | Central |  | Decomm |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-09-28 |  |  |  | 2024-05-03 |  | 2023-06-19 | 2023-11-16 | CD//Norhaliza | 2023-07-11 | CelcomDigi_RAN_GTSB_TSS_Central_20230529_0025 | DU00002040268 |  |  |  |  | 2024-02-21 |  | 3LEGGED
B00545 | B061F_B00545OD_VLPCKALAM | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-16 |  |  | 2023-05-22 | 2023-05-22 | Closed | 2023-07-20 |  | CD//Norhaliza | 2023-10-09 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002040269 |  | Photo not enough |  |  | 2023-08-18 |  | MONOPOLE
B00804 | B057B_B00804OD_KGNAKHODA | Central | 1098K | Swap |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-05-16 | 2023-05-18 |  | 2023-05-26 |  | Closed | 2023-05-27 | 2023-06-06 | CD//Sapian | 2023-05-29 | CelcomDigi_RAN_GTSB_TSS_Central_20230517_0024 | DU00002040270 |  |  | 2023-08-15 | 2023-08-14 |  |  | BOOM | 6 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
B00257 | B057B_B00257OD_SLYGBARU4 | Central | 1067K | Swap |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-06-23 | 2023-06-27 |  | 2023-07-03 |  | Closed | 2023-07-04 | 2023-07-13 | CD//Sapian | 2023-07-12 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_0009 | DU00002040271 |  |  | 2023-09-21 | 2023-09-21 |  | A-bracket pole | BOOM | 4.8M | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
B01113 | B057D_B01113OD_BT7JLNGOMBAK | Central |  | Decomm |  | 2023Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2023-08-03 |  |  |  | 2023-08-04 |  | 2023-08-08 | 2024-02-15 | CD//Ali Akaram | 2023-08-16 | CelcomDigi_RAN_Allstar_TSS_Central_20230721 | DU00002040272 |  |  |  |  | 2023-09-18 |  | BILLBOARD
K00043 | K004A_K00043OD_MENARAALORSETAR | Northern |  | Decomm |  | 2023Q4 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-08-11 |  |  |  | 2023-08-11 |  | 2023-08-17 | 2024-02-29 | CD//Rohizam | 2023-08-18 | Celcom Digi_RAN-CCSMY- TSS-Northern-20230817-0031 | DU00002040273 |  | Please check and include all TX equipment, Include all Zoom photo with clear ID |  |  | 2024-02-05 |  | BOOM
K00039 | K004A_K00039OD_HUTANKAMPUNG | Northern |  | Decomm |  | 2023Q4 | ZA | GCI | 4.6 TSSR Approved |  | 2023-08-01 | [5 empty] | 2023-08-17 | 2023-08-19 | CD//Rohizam | 2023-08-17 | Celcom Digi_RAN-GCI-TSS-Northern-20230612-0026/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002040274 |  |  |  |  | 2023-10-11 |  | TOWER
B02287 | B061C_B02287OD_JLNHJSAIDJLNKEBUN | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-06-27 |  |  |  | 2023-07-24 |  | 2023-07-25 |  | CD//Ali akaram | 2023-08-04 | CelcomDigi_RAN_YPTT_TSS_Central_20230628_0011 | DU00002040275 |  | FE WRONG INFO |  |  | 2023-09-05 |  | LAMP_POLE
B00311 | B065B_B00311OD_TMKERLING | Central | 1075K | Swap |  | 2023Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-07-26 | 2023-08-02 |  | 2023-08-04 |  | Closed | 2023-08-09 | 2023-08-17 | CD//Sapian | 2023-08-17 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230726 | DU00002040276 |  |  | 2023-10-14 | 2023-10-12 |  | Monopole | MONOPOLE | 45m | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
B01411 | B061A_B01411OD_AMSTEELBKTRAJA | Central |  | Decomm |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-06-18 |  |  |  | 2023-07-25 |  | 2023-07-31 | 2024-05-10 | CD//Norhaliza | 2023-10-04 | CelcomDigi_RAN_Datasco_TSS_Central_20230620_0027 | DU00002040277 |  |  |  |  | 2023-09-08 | Lampole | LAMP_POLE | 20
B01316 | B060A_B01316OD_KUNCIAIRBUANG | Central |  | Decomm |  | 2023Q4 | CR | AllStar | 4.6 TSSR Approved |  | 2023-07-21 |  |  |  | 2023-07-21 |  | 2023-07-25 | 2023-08-18 | CD//Sapian | 2023-08-04 | CelcomDigi_RAN_AllStar_TSS_Central_20230722 | DU00002040278 |  |  |  |  | 2023-08-23 |  | TOWER
A01184 | T3E_0621_Kg Pondok Tanjung | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040279 | [6 empty] | TOWER
B02495 | B065B_B02495OD_SURAUATTAQWABKTBERUNTUNG | Central | 1159K | Swap |  | 2023Q2 | YZ | Datasco | 4.6 TSSR Approved |  | 2023-04-25 | 2023-05-11 |  | 2023-05-15 |  | Closed | 2023-05-18 | 2023-06-03 | CD//Tee | 2023-05-24 | CelcomDigi_RAN_Datasco_TSS_Central_20230426_0017 | DU00002040280 |  |  | 2023-07-11 | 2023-07-08 |  | Monopole | RAPID ASSEMBLY POLE (RAPOLE) | 27 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
B02848 | B061F_B02848OD_BDRTSKPUTRI5 | Central |  | Decomm |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-05-03 |  |  |  | 2023-07-14 |  | 2023-07-17 | 2023-08-04 | CD//Sapian | 2023-08-01 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230626_decom reraise | DU00002040281 |  |  |  |  | 2023-07-12 | Lampole | LAMP_POLE | 30m
S00333 | S097A_S00333OD_SAPANG | Sabah |  | Decomm |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-06-28 |  |  |  | 2023-07-05 |  | 2023-08-02 | 2023-12-09 | CD//Ray Amos | 2023-08-03 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0009 | DU00002040282 |  | 1) Please provide clear Cisco Router, OB Fiber & ODF photo. |  |  | 2024-02-07 |  | TOWER
Q00773 | Q132B_Q00773OD_PASARLUTONG | Sarawak |  | Decomm |  | 2023Q4 | SH | Magicell | 4.6 TSSR Approved |  | 2023-06-21 |  |  |  | 2023-06-22 |  | 2023-07-25 | 2023-08-06 | CD//John | 2023-07-26 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002040283 |  |  |  |  | 2025-01-16 |  | MONOPOLE
S00770 | S097A_S00770OD_CB_BANDAUAUMKAR | Sabah | 7141P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN->Swap | 2023Q4 | HW | GTSB | 4.6 TSSR Approved |  | 2025-05-14 | 2025-05-21 |  | 2025-05-23 |  | Under Approval | 2025-05-26 | 2025-07-07 | E//Hannah | 2025-06-03 | SQ202505050115 - GTSB | DU00002040284 |  |  | 2025-06-30 | 2025-06-25 |  | Tower | TOWER | 75 | Add R8862A S9000x3+R8894E M1821x3, Dismantle | 0 | 0
S01783 | FC1_111 Kg Kunak 3 | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 | MS |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002040285 | [6 empty] | TOWER
S00981 | S110C_S00981OD_T3_KGULUTIKU | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040286 | [6 empty] | TOWER
S00810 | S106A_S00810OD_SEMPORNATOWN | Sabah |  | Decomm |  | 2023Q4 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-12-22 |  |  |  | 2023-12-29 |  | 2023-12-29 | 2024-02-15 | CD//Jahganathan | 2024-01-02 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20231231/0612Sabah-South Pacific-BOQ Template (template) | DU00002040287 |  |  |  |  | 2024-05-07 |  | TRIPOD
S01754 | S106A_S01754OD_TMNSEMPAUL2 | Sabah | 7064K | Swap |  | 2023Q4 | MS | Futong | 4.6 TSSR Approved |  | 2023-06-26 | 2023-07-04 |  | 2023-07-06 |  | Closed | 2023-07-07 | 2023-07-10 | CD//Mohidi Jaan | 2023-07-10 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0011 | DU00002040288 |  | No TX Decom TSSR Required (Under upgrade) | 2023-09-21 | 2023-09-13 |  | Tower | TOWER | 60 | Add R8852E S9000 x3 + A9732 M1821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 123
S01844 | Pulau Selakan | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 |  | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002040289 | [6 empty] | 3LEGGED
Q00959 | Q118B_Q00959OD_ABFOFFICE | Sarawak | 9087K | Swap | Swap | 2026 |  | Trintel | 1.1 Pending Survey - Subcon | [6 empty] | To be Submitted |  |  | CD//John |  |  | DU00002040290 | [6 empty] | MINARET |  | Add R8862A S9000x3+R8894E M1821x3+R8862A S2601x3, Dismantle
S00429 | S110B_S00429OD_JLNTIMUR | Sabah |  | Decomm |  | 2023Q4 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-06-14 |  |  |  | 2023-06-15 |  | 2023-06-20 | 2023-07-21 | CD//Ray Amos | 2023-06-21 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230622 | DU00002040291 |  |  |  |  | 2023-10-13 |  | AESTHETIC MONOPOLE
S00798 | S090B_S00798OD_JKRKENINGAU | Sabah |  | Decomm |  | 2023Q3 | MS | Datasco | 4.6 TSSR Approved |  | 2023-07-20 |  |  |  | 2023-07-28 |  | 2023-08-01 | 2023-08-14 | CD//Mohidi Jaan | 2023-08-01 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006 | DU00002040292 |  |  |  |  | 2023-11-11 |  | TOWER
S01003 | S099A_S01003OD_CB_VRT3PAGALUNGAN | Sabah | 7054K | Swap | Swap->Site Out->Swap->On Hold->Swap | 2025 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-30 | 2023-07-13 |  | 2023-07-14 |  | Closed | 2023-07-14 | 2023-07-15 | CD//Mohidi Jaan | 2023-07-14 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0004 | DU00002040293 |  |  | 2025-11-13 | 2025-11-05 |  | Tower | TOWER | 76 | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
S00639 | S090A_S00639OD_KGBIAH | Sabah |  | Decomm |  | 2023Q3 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-05-18 |  |  |  | 2023-05-18 |  | 2023-06-09 | 2023-07-27 | CD//Ray Amos | 2023-06-13 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230517-0002/0626Sabah-South Pacific-BOQ Template (template) | DU00002040294 |  |  |  |  | 2023-09-11 |  | TOWER
Q01487 | Q118B_Q01487OD_TMNSABERKASBTU | Sarawak |  | Decomm |  | 2023Q3 | ZB | AllStar | 4.6 TSSR Approved |  | 2023-08-14 |  |  |  | 2023-09-18 |  | 2023-09-18 | 2023-09-29 | CD//John | 2023-09-23 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230622/0612Sarawak-AllStar-BOQ Template (template).xls | DU00002040295 |  |  |  |  | 2025-04-28 |  | RAMO
Q00780 | Q116A_Q00780OD_SGASAP2 | Sarawak | 9471P | Decomm | TBD->Swap->On Hold->Swap->Decomm | 2023Q3 | SM | Datasco | 4.6 TSSR Approved |  | 2023-08-10 | 2024-02-01 |  | 2025-02-14 |  | Rectificating | 2025-02-19 | 2025-05-21 | CD//John | 2026-01-13 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230516-0006 | DU00002040296 |  |  |  |  | 2025-12-20 |  | TOWER | 90 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU | 0 | 0
Q01356 | Q118B_Q01356OD_PARKCITY2 | Sarawak |  | Decomm |  | 2023Q3 | SH | Datasco | 4.6 TSSR Approved |  | 2023-07-21 |  |  | 2023-07-23 | 2023-07-28 | Closed | 2023-07-24 | 2023-08-08 | CD//John | 2023-07-25 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622/0612Sarawak-Datasco-BOQ Template (template) | DU00002040297 |  | 3/8: pg 1 idu info missing fe info & photos missing |  |  | 2023-08-17 |  | RAPID ASSEMBLY POLE (RAPOLE)
S01455 | S099A_S01455OD_T3_KM120KALABAKANNABAWAN | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040298 | [6 empty] | TOWER
S01430 | S110C_S01430OD_T3_KM80KALABAKANNABAWAN | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040299 | [6 empty] | TOWER
S00987 | S110C_S00987OD_T3_LADANGBELIAN | Sabah | 7048K | MOCN By Other Vendor | Swap->Maintain USP MOCN->On Hold->Maintain USP MOCN->On Hold->MOCN By Other Vendor | 2023Q3 | AD | Futong | 14.2 Drop (Done Survey) |  | 2023-07-07 | 2023-07-14 |  |  |  | To be Submitted |  |  | CD//Jahganathan |  | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0004 | DU00002040300 | [5 empty] | Tower | TOWER | 76
S00246 | JALANMAKTAB | Sabah |  | Decomm |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-07-12 |  |  |  | 2023-07-26 |  | 2023-07-26 | 2023-10-27 | CD//Mohidi Jaan | 2023-07-26 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006 | DU00002040301 |  |  |  |  | 2024-03-27 |  | TOWER
Q01740 | Q118B_Q01740OD_KIDURONG6 | Sarawak |  | Decomm |  | 2023Q3 | BY | South Pacific | 4.6 TSSR Approved |  | 2023-05-22 |  |  |  | 2023-05-26 |  | 2023-06-06 | 2023-08-06 | CD//John | 2023-06-11 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230622/0612Sarawak-South Pacific-BOQ Template (template) | DU00002040302 |  | 2023-06-26 Missing TX photos and info |  |  | 2025-02-04 |  | RAPID ASSEMBLY POLE (RAPOLE)
S01212 | S090B_S01212OD_TMNPASIRPUTIH | Sabah |  | Decomm |  | 2023Q3 | MS | Datasco | 4.6 TSSR Approved |  | 2023-07-20 |  |  |  | 2023-07-21 |  | 2023-07-26 | 2023-08-06 | CD//Mohidi Jaan | 2023-07-26 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006/0612Sabah-Datasco-BOQ Template (template) | DU00002040303 |  | 20230727: FE photos & info missing |  |  | 2023-09-26 |  | TOWER
S00238 | S106A_S00238OD_KELUMPANG | Sabah |  | Decomm |  | 2023Q4 | AD | Futong | 4.6 TSSR Approved |  | 2023-07-20 |  |  |  | 2023-07-21 |  | 2023-07-25 | 2023-08-06 | CD//Mohidi Jaan | 2023-07-26 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009/0612Sabah-Futong-BOQ Template (template) | DU00002040304 |  |  |  |  | 2023-10-19 |  | GUYED MAST
S01614 | S110B_S01614OD_TMNSEMARAK2 | Sabah |  | Decomm |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-07-17 |  |  |  | 2023-07-20 |  | 2023-07-27 | 2023-08-06 | CD//Ray Amos | 2023-07-27 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230726 | DU00002040305 |  |  |  |  | 2023-09-29 |  | RAPID ASSEMBLY POLE (RAPOLE)
S00244 | S110C_S00244OD_MEROTAI | Sabah |  | Decomm |  | 2023Q3 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-09 |  |  |  | 2023-06-14 |  | 2023-06-19 | 2023-07-27 | CD//Mohidi Jaan | 2023-06-20 | Celcom Digi_RAN-Futong-TSS-Sabah-20230531-0008/0612Sabah-Futong-BOQ Template (template) | DU00002040306 |  |  |  |  | 2023-11-07 |  | TOWER
S00967 | S110B_S00967OD_TSHKUNAKCOMPLEX | Sabah | 7042K | Swap |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-06-22 | 2023-06-26 |  | 2023-06-26 |  | Closed | 2023-07-21 | 2023-07-25 | CD//Jahganathan | 2023-07-24 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0010 | DU00002040307 |  |  | 2023-10-16 | 2023-09-19 |  | In-Building System | TRIPOD | 2 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
S00230 | S110C_S00230OD_FELDAUMAS | Sabah |  | Decomm |  | 2023Q3 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-09 |  |  |  | 2023-06-14 |  | 2023-06-20 | 2023-07-21 | CD//Jahganathan | 2023-06-21 | Celcom Digi_RAN-Futong-TSS-Sabah-20230531-0008 | DU00002040308 |  |  |  |  | 2023-11-18 |  | TOWER
S01069 | S090B_S01069OD_KGULULIAWAN | Sabah |  | Decomm |  | 2023Q3 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-05-18 |  |  |  | 2023-05-18 |  | 2023-06-09 | 2023-09-29 | CD//Ray Amos | 2023-06-13 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230517-0002/0612Sabah-South Pacific-BOQ Template (template)/0626Sabah-South Pacific-BOQ Template (template) | DU00002040309 |  | 2023-07-07 missing tx photos and info |  |  | 2023-09-27 |  | RAPID ASSEMBLY POLE (RAPOLE)
S00978 | S097A_S00978OD_T3_LADANGJATIKA | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040310 | [6 empty] | TOWER
S01098 | S110B_S01098OD_KGKONGSI10 | Sabah |  | Decomm |  | 2023Q4 | AD | Datasco | 4.6 TSSR Approved |  | 2023-08-03 |  |  |  | 2023-08-11 |  | 2023-08-14 | 2023-11-06 | CD//Ray Amos | 2023-08-14 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006/0612Sabah-Datasco-BOQ Template (template) | DU00002040311 |  | 18/8: UNCOMPLETED INFO & PHOTO |  |  | 2023-10-29 |  | RAPID ASSEMBLY POLE (RAPOLE)
Q01752 | Q118B_Q01752OD_BTUBIZHUB33IND | Sarawak | 9117K | Swap |  | 2023Q3 | SH | YPTT | 4.6 TSSR Approved |  | 2023-05-21 | 2023-05-22 |  | 2023-05-29 |  | Closed | 2023-05-30 | 2023-05-31 | CD//John | 2023-05-31 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20230524-0002 | DU00002040312 |  |  | 2023-12-08 | 2023-11-28 |  | Monopole | RAPID ASSEMBLY POLE (RAPOLE) | 30m | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
W00012 | B057A_W00012OD_TMNSRIMURNI | Central | 1194K | Swap |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-06-23 | 2023-06-27 |  | 2023-07-03 |  | Closed | 2023-07-10 | 2023-08-15 | CD//Ali akaram | 2023-08-15 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_0009 | DU00002040313 |  |  | 2023-09-21 | 2023-09-20 |  | In-Building System | BOOM | 4 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 1
S00975 | S106A_S00975OD_CB_PULAUTIMBUNMATA | Sabah | 7045K | Swap |  | 2023Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-06-24 | 2023-07-04 |  | 2023-06-27 |  | Closed | 2023-07-20 | 2023-07-22 | CD//Ray Amos | 2023-07-21 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0010 | DU00002040314 |  |  | 2023-10-02 | 2023-09-22 |  | Tower | TOWER | 75 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
Q00952 | Q124F_Q00952OD_KESUMARST | Sarawak |  | Decomm |  | 2023Q4 | SH | Datasco | 4.6 TSSR Approved |  | 2023-08-15 |  |  |  | 2023-08-23 |  | 2023-08-23 | 2024-02-15 | CD//John | 2023-08-23 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622/Celcom Digi_RAN-Datasco-TSS DECOMM-Sarawak-20230818 | DU00002040315 |  | 24/8: wrong photo & info wrong proposal |  |  | 2023-12-11 |  | MONOPOLE
Q00956 | Q116A_Q00956OD_CB_SGKOYAN | Sarawak |  | Decomm |  | 2023Q3 | SH | Datasco | 4.6 TSSR Approved |  | 2023-08-10 |  |  |  | 2023-08-18 |  | 2023-08-18 | 2024-03-05 | CD//John | 2023-08-18 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 | DU00002040316 |  |  |  |  | 2025-06-14 |  | TOWER
S01451 | S106A_S01451OD_T3_KGSIPITMAGAI | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040317 | [6 empty] | TOWER
S01628 | S097A_S01628OD_KGSAPANGAIR | Sabah | 7063K | Swap |  | 2023Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-06-19 | 2023-06-22 |  | 2023-06-30 |  | Closed | 2023-07-03 | 2023-08-02 | CD//Mohidi Jaan | 2023-08-01 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0010 | DU00002040318 |  |  | 2023-09-27 | 2023-09-21 |  | Tower | TOWER | 60M | Add R8852E S9000 x3 + R8894E M1821 x3
S01705 | Kg. Sakaliban | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040319 | [6 empty] | 3LEGGED
S00425 | S110B_S00425OD_CB_SGKAWA | Sabah |  | Decomm |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-07-13 |  |  |  | 2023-07-25 |  | 2023-07-26 | 2023-09-23 | CD//Ray Amos | 2023-07-27 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006/0612Sabah-Datasco-BOQ Template (template) | DU00002040320 |  | 20230731 : NE & FE info missing, NE & FE photos missing |  |  | 2023-11-29 |  | TOWER
S00532 | S110C_S00532OD_BOMBALAI | Sabah |  | Decomm |  | 2023Q3 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-09 |  |  |  | 2023-06-14 |  | 2023-06-20 | 2023-07-28 | CD//Mohidi Jaan | 2023-06-21 | Celcom Digi_RAN-Futong-TSS-Sabah-20230531-0008 | DU00002040321 |  |  |  |  | 2023-11-29 |  | TOWER
S01160 | S106A_S01160OD_KGBANGAUBANGAU | Sabah |  | Decomm |  | 2023Q4 | AD | Futong | 4.6 TSSR Approved |  | 2023-07-22 |  |  |  | 2023-07-22 |  | 2023-07-25 | 2023-08-06 | CD//Mohidi Jaan | 2023-07-26 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009/0612Sabah-Futong-BOQ Template (template) | DU00002040322 |  |  |  |  | 2024-01-25 |  | LAMP_POLE
Q02216 | Q118B_Q02216OD_SAKURASAMALAJU2 | Sarawak |  | Decomm |  | 2023Q3 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-05-26 |  |  |  | 2023-07-20 |  | 2023-07-24 | 2023-09-08 | CD//John | 2023-07-28 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230613-0014/0612Sarawak-Magicell-BOQ Template (template) | DU00002040323 |  | 1/9: uncompleted info & photos fe tx info are mising |  |  | 2024-03-28 |  | RAPID ASSEMBLY POLE (RAPOLE)
Q01390 | Q124B_Q01390OD_KGSGTENGAH | Sarawak |  | Decomm |  | 2023Q4 | SH | Trintel | 4.6 TSSR Approved |  | 2023-08-15 |  |  |  | 2023-08-28 |  | 2023-08-28 | 2023-09-29 | CD//John | 2023-08-29 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230622/Celcom Digi_RAN-Trintel-TSS DECOMM-Sarawak-20231130 | DU00002040324 |  |  |  |  | 2023-10-11 |  | RAPID ASSEMBLY POLE (RAPOLE)
S00997 | S090B_S00997OD_KANDANGBESAR | Sabah |  | Decomm |  | 2023Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2023-05-11 |  |  |  | 2023-05-16 |  | 2023-07-21 | 2023-07-21 | CD//Ray Amos | 2023-07-24 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230608-0008/0612Sabah-GTSB-BOQ Template (template) | DU00002040325 |  |  |  |  | 2023-09-26 |  | TOWER
Q01621 | QS50249_9_0-SKKEMBT18 | Sarawak | 9108K | Swap |  | 2023Q3 | BY | YPTT | 4.6 TSSR Approved |  | 2023-05-22 | 2023-05-26 |  | 2023-06-01 |  | Rectificating | 2023-06-07 | 2023-06-10 | CD//John | 2023-06-07 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20230524-0002 | DU00002040326 |  |  | 2023-12-07 | 2023-11-24 |  | Minaret | TOWER | 30 | Reuse R8852E S9000 x1
W00073 | B057A_W00073OD_WARTASLYG | Central | 1195K | Swap |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-06-23 | 2023-07-05 |  | 2023-07-09 |  | Closed | 2023-07-15 | 2023-10-31 | CD//Norhaliza | 2023-10-26 | CelcomDigi_RANMW_YPTT_TSS_Central_20230626_0006 | DU00002040327 |  |  | 2023-10-07 | 2023-09-22 |  | H-bracket pole | BOOM | 6.1 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 12
S01450 | S106A_S01450OD_T3_SAPANGOILMILLS | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 | MS | AllStar | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | N/A | DU00002040328 | [6 empty] | TOWER
S00966 | S110B_S00966OD_PSSJLNKUHARA | Sabah | 7041K | Swap |  | 2023Q4 | AD | YPTT | 4.6 TSSR Approved |  | 2023-07-12 | 2023-07-17 |  | 2023-07-24 |  | Closed | 2023-07-24 | 2023-07-25 | CD//Mohidi Jaan | 2023-07-25 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002040329 |  |  | 2023-08-29 | 2023-08-18 |  |  | MONOPOLE | 30 | Add R8852E S9000 x3 + R8894E M1821 x3 + R8862A S2601 x3
Q00809 | Q124F_Q00809OD_TMNAMINA | Sarawak |  | Decomm |  | 2023Q4 | ZB | South Pacific | 4.6 TSSR Approved |  | 2023-10-14 |  |  |  | 2023-10-17 |  | 2024-08-19 | 2024-08-27 | CD//John | 2023-10-17 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230622 | DU00002040330 |  |  |  |  | 2023-11-30 |  | MONOPOLE
Q01536 | Q118B_Q01536OD_BTUCITYMALL | Sarawak |  | Decomm |  | 2023Q3 | ZB | YPTT | 4.6 TSSR Approved |  | 2023-08-07 |  |  |  | 2023-08-10 |  | 2023-08-11 | 2024-10-11 | CD//John | 2023-08-14 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20230622/Celcom Digi_RAN-YPTT-TSS DECOMM-Sarawak-20230808 | DU00002040331 |  | 24/8: uncompleted info & photos FE photos & info are missing |  |  | 2023-12-10 |  | RAPID ASSEMBLY POLE (RAPOLE)
Y00048 | A036B_Y00048OD_EMOS_PROTON_CITY3 | Central | 4162K | Swap |  | 2023Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-06-20 | 2023-06-21 |  | 2023-07-01 |  | Closed | 2023-07-04 | 2023-08-25 | CD//Sapian | 2023-08-25 | CelcomDigi_RANMW_Ascentrack_TSS_Central_20230622_0006 | DU00002040332 |  |  | 2023-09-23 | 2023-09-12 |  | Portables BTS | EMOS | 27 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x5,Dismantle Celcom all RRU&BBU |  | 12
S00907 | S110C_S00907OD_CB_KGTIAGAU | Sabah | 7039K | Swap |  | 2023Q3 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-21 | 2023-06-26 |  | 2023-06-28 |  | Closed | 2023-07-02 | 2023-07-03 | CD//Ray Amos | 2023-07-03 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0005 | DU00002040333 |  |  | 2023-08-24 | 2023-08-24 |  | Tower | TOWER | 60 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
S00972 | S097A_S00972OD_T3_TUNFUAD | Sabah |  | Decomm |  | 2023Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-06-19 |  |  |  | 2023-06-21 |  | 2023-06-23 | 2023-07-21 | CD//Jahganathan | 2023-06-23 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0009/Celcom Digi_RAN-GTSB-Standard PR TSS DECOMM-Sabah-20231129 | DU00002040334 |  |  |  |  | 2023-10-11 |  | TOWER
Q01672 | Q132C_Q01672OD_JLNPUJUTBGRAYA | Sarawak |  | Decomm |  | 2023Q4 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-08-24 |  |  |  | 2023-08-30 |  | 2023-08-30 | 2023-09-23 | CD//John | 2023-09-01 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622/0612Sarawak-Datasco-BOQ Template (template) | DU00002040335 |  |  |  |  | 2025-03-26 |  | RAPID ASSEMBLY POLE (RAPOLE)
S00275 | S090A_S00275OD_KENINGAUTOWN | Sabah | 7025K | Swap |  | 2023Q3 | AD | GTSB | 4.6 TSSR Approved | Structure not Safe (CME Edotco WIP) | 2023-05-15 | 2023-05-19 |  | 2023-05-27 |  | Closed | 2023-06-01 | 2023-06-13 | E//Hannah | 2023-06-13 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230508-0005 | DU00002040336 |  |  | 2024-02-06 | 2023-07-22 |  | Pole | BOOM | 6 | Add R8852E S9000 x3 + A9732 M1821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 123
S00235 | S110B_S00235OD_WNLJLNAPAS | Sabah |  | Decomm |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-07-09 |  |  |  | 2023-07-10 |  | 2023-07-31 | 2023-08-23 | CD//Mohidi Jaan | 2023-07-31 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006 | DU00002040337 |  | 20230801: incompleted TX info |  |  | 2023-10-10 |  | BOOM
Q01332 | Q118B_Q01332OD_PERBENAEMASBTU | Sarawak |  | Decomm |  | 2023Q3 | BY | Magicell | 4.6 TSSR Approved |  | 2023-05-26 |  |  |  | 2023-07-21 |  | 2023-06-07 | 2023-07-28 | CD//John | 2023-07-04 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230613-0014/Celcom Digi_RAN-Magicell-TSS DECOMM-Sarawak-20230818 | DU00002040338 |  |  |  |  | 2024-04-02 |  | RAPID ASSEMBLY POLE (RAPOLE)
S01442 | S106A_S01442OD_T3_KGSGBUAYA | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040339 | [6 empty] | TOWER
S00285 | S090A_S00285OD_PATIKANG | Sabah |  | Decomm |  | 2023Q3 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-05-14 |  |  |  | 2023-05-20 |  | 2023-06-06 | 2023-07-27 | CD//Jahganathan | 2023-06-09 | Celcom Digi_RAN-South Pacific-Standard PR TSS-Sabah-20240326 | DU00002040340 |  |  |  |  | 2023-08-15 |  | TOWER
S00402 | S110C_S00402OD_TMMEROTAI | Sabah | 7029K | Swap |  | 2023Q3 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2024-01-18 | 2024-01-22 |  | 2024-01-23 |  | Closed | 2024-01-23 | 2024-01-30 | CD//Jahganathan | 2024-01-24 | Celcom Digi_RAN-Seri Pancar-Standard PR TSS-Sabah-20240124 | DU00002040341 |  |  | 2024-03-06 | 2024-02-20 |  | Tower | GF 60m Tower | 76 | Add R9264H M901821 x3,Dismantle |  | 3
S01867 | KG.RANGGU | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 | MS | Datasco | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002040342 | [6 empty] | TOWER
Q01415 | Q132B_Q01415OD_SENADIN2 | Sarawak |  | Decomm |  | 2023Q4 | BY | Datasco | 4.6 TSSR Approved |  | 2023-06-16 |  |  | 2023-06-26 |  | Under Approval | 2023-07-11 | 2023-12-09 | CD//John | 2023-07-12 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 | DU00002040343 |  | 22/8: UNCOMPLETED INFO & PHOTOS Pending TX |  |  | 2025-10-14 |  | TOWER
S01089 | S110A_S01089OD_KINGPARKHOTEL | Sabah |  | Decomm |  | 2023Q4 | AD | AllStar | 4.6 TSSR Approved |  | 2023-09-06 |  |  |  | 2023-09-10 |  | 2023-09-11 | 2023-09-29 | CD//Jahganathan | 2023-09-11 | Celcom Digi_RAN-Allstar-TSS-Sabah-20230608-0004/Celcom Digi_RAN-Allstar-TSS DECOMM-Sabah-20231206 | DU00002040344 |  |  |  |  | 2023-10-05 |  | BOOM
Q01309 | Q118B_Q01309OD_SAMALAJU | Sarawak | 9100K | Swap |  | 2023Q3 | BY | Magicell | 4.6 TSSR Approved |  | 2023-05-29 | 2023-06-09 |  | 2023-06-13 |  | Closed | 2023-06-13 | 2023-07-03 | CD//John | 2023-06-13 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230531-0013 | DU00002040345 |  |  | 2024-04-20 | 2024-03-16 |  | Minimast | GUYED MAST | 19m | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
X00190 | S090B_X00190OD_DEWANMASYARAKATKGU | Sabah | 7066K | MOCN Decomm | Swap->MOCN Decomm->Swap->MOCN Decomm | 2023Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2023-05-25 | 2023-06-06 |  | 2023-06-12 |  | Under Approval | 2023-06-16 | 2023-06-19 | CD//Mohidi Jaan | 2023-06-16 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230508-0005 | DU00002040346 | [5 empty] | Monopole | RAPID ASSEMBLY POLE (RAPOLE) | 18
S00314 | S099A_S00314OD_CB_NABAWANTOWN | Sabah | 7027K | Swap |  | 2023Q3 | AD | Futong | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-24 |  | 2023-05-27 |  | Closed | 2023-06-01 | 2023-06-13 | E//Hannah | 2023-06-13 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0005 | DU00002040347 |  |  | 2023-08-07 | 2023-07-18 |  | Guide mast | MINIMAST | 12 | Add R9264H M901821 x3 + R9264M M1821 x2,Dismantle Celcom all RRU&BBU |  | 12
S00064 | S110C_S00064OD_KALABAKANTIMUR | Sabah |  | Decomm |  | 2023Q3 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-09 |  |  |  | 2023-06-22 |  | 2023-06-20 | 2023-07-27 | CD//Ray Amos | 2023-06-21 | Celcom Digi_RAN-Futong-TSS-Sabah-20230531-0008/0612Sabah-Futong-BOQ Template (template) | DU00002040348 |  |  |  |  | 2023-11-10 |  | TOWER
Q01938 | Q118B_Q01938OD_TIMESSQBTU | Sarawak |  | Decomm |  | 2023Q3 | SH | YPTT | 4.6 TSSR Approved |  | 2023-08-07 |  |  |  | 2023-08-15 |  | 2023-08-16 | 2023-12-09 | CD//John | 2023-08-17 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20230622/Celcom Digi_RAN-YPTT-TSS DECOMM-Sarawak-20230808 | DU00002040349 |  | 24/8 :uncompleted photos & info FE all tx info & photos are missing |  |  | 2023-12-06 |  | BOOM
S00234 | S106A_S00234OD_SEMPORNA | Sabah |  | Decomm |  | 2023Q4 | AD | Futong | 4.6 TSSR Approved |  | 2023-07-20 |  |  |  | 2023-07-22 |  | 2023-07-25 | 2023-08-06 | CD//Mohidi Jaan | 2023-07-25 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009 | DU00002040350 |  |  |  |  | 2023-10-12 |  | GUYED MAST
S00857 | S110C_S00857OD_TMNWAWASAN | Sabah |  | Decomm |  | 2023Q4 | AD | YPTT | 4.6 TSSR Approved |  | 2023-07-16 |  |  |  | 2023-07-24 |  | 2023-07-27 | 2023-09-08 | CD//Jahganathan | 2023-08-07 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0008/0612Sabah-YPTT-BOQ Template (template) | DU00002040351 |  | 2/8: uncompeted info + cabinet wrong photo Page 8 |  |  | 2023-09-29 |  | TOWER
S00645 | S099A_S00645OD_CB_KGPADIWAN | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040352 | [6 empty] | TOWER
Q01718 | Q132B_Q01718OD_CB_MYYPORT2 | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | N/A - no need PR for MOCN Decomm | DU00002040353 | [6 empty] | 3LEGGED
S01125 | S106A_S01125OD_PASKALSEMPORNA | Sabah |  | Decomm |  | 2023Q4 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-20 |  |  |  | 2023-06-21 |  | 2023-06-21 | 2023-07-21 | CD//Ray Amos | 2023-06-23 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009/0612Sabah-Futong-BOQ Template (template) | DU00002040354 |  |  |  |  | 2023-10-10 |  | MONOPOLE
Q01814 | Q118B_Q01814OD_LDGRASAN | Sarawak | 9128K | Swap |  | 2023Q3 | SH | South Pacific | 4.6 TSSR Approved |  | 2023-05-19 | 2023-06-06 |  | 2023-06-10 |  | Rectificating | 2023-06-15 | 2023-06-17 | CD//John | 2023-06-16 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230512-0001 | DU00002040355 |  |  | 2024-01-15 | 2023-11-09 |  | Tower | TOWER | 55m | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
S00984 | S097A_S00984OD_T3_BUKITTAJAM | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | N/A | DU00002040356 | [6 empty] | TOWER
Q00947 | Q116A_Q00947OD_CB_SPGALOI | Sarawak |  | Decomm |  | 2023Q3 | SH | Datasco | 4.6 TSSR Approved |  | 2023-08-18 |  |  |  | 2023-08-23 |  | 2023-08-23 | 2024-09-13 | CD//John | 2023-08-23 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 | DU00002040357 |  |  |  |  | 2024-09-24 |  | RAPID ASSEMBLY POLE (RAPOLE)
S00583 | S110C_S00583OD_KALABAKANTENGAH | Sabah |  | Decomm |  | 2023Q3 | AD | Futong | 4.6 TSSR Approved |  | 2023-08-05 |  |  |  | 2023-08-05 |  | 2023-08-08 | 2023-09-29 | CD//Ray Amos | 2023-08-08 | Celcom Digi_RAN-Futong-TSS-Sabah-20230531-0008 | DU00002040358 |  | 18/8: P1 - TX info are missing P9 - Existing idu info are mssing |  |  | 2023-09-15 |  | TOWER
S01911 | Kapilit Estate | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | AD |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002040359 | [6 empty] | 3LEGGED
Q01774 | Q118B_Q01774OD_CB_JLNBTUBAKUN | Sarawak | 9122K | Swap |  | 2023Q3 | SH | South Pacific | 4.6 TSSR Approved |  | 2023-05-21 | 2023-05-27 |  | 2023-06-07 |  | Closed | 2023-06-09 | 2023-06-10 | CD//John | 2023-06-10 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230512-0001 | DU00002040360 |  |  | 2024-01-08 | 2023-12-06 |  | Tower | TOWER | 45m | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
Q00775 | Q132B_Q00775OD_TUDAN2 | Sarawak |  | Decomm |  | 2023Q4 | ZB | South Pacific | 4.6 TSSR Approved |  | 2023-06-21 |  |  |  | 2023-07-25 |  | 2023-07-25 | 2023-10-06 | CD//John | 2023-07-26 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230622 | DU00002040361 |  | 24/8:P9 &10,pls change tp clear photos & provide idu labelling |  |  | 2025-02-17 |  | MONOPOLE
S00251 | S110A_S00251OD_HKC | Sabah | 7021K | Swap |  | 2023Q4 | AD | AllStar | 4.6 TSSR Approved |  | 2023-07-03 | 2023-07-07 |  | 2023-07-13 |  | Closed | 2023-07-17 | 2023-07-18 | CD//Jahganathan | 2023-07-17 | Celcom Digi_RAN-Allstar-TSS-Sabah-20230608-0004 | DU00002040362 |  |  | 2023-09-07 | 2023-09-04 |  | In-Building System | BOOM | 13M | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 1
Q00774 | Q124B_Q00774OD_TMNLEELING | Sarawak |  | Decomm |  | 2023Q4 | SH | Trintel | 4.6 TSSR Approved |  | 2023-06-16 |  |  |  | 2023-08-18 |  | 2023-08-18 | 2023-08-24 | CD//John | 2023-08-18 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230622 | DU00002040363 |  |  |  |  | 2023-10-04 |  | MONOPOLE
S00769 | S097A_S00769OD_AUMKAROILMILL | Sabah | 7038K | Swap |  | 2023Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-06-14 | 2023-06-26 |  | 2023-06-26 |  | Rectificating | 2023-07-20 | 2023-07-24 | CD//Ray Amos | 2023-07-24 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0010 | DU00002040364 |  |  | 2023-09-27 | 2023-09-18 |  |  | GUYED MAST | 30 | Add R8852E S9000 x3 + R8894E M1821 x3
S00221 | S110A_S00221OD_TAITAI | Sabah | 7018K | Swap |  | 2023Q4 | AD | AllStar | 4.6 TSSR Approved |  | 2023-06-28 | 2023-07-04 |  | 2023-07-16 |  | Closed | 2023-07-17 | 2023-07-18 | CD//Jahganathan | 2023-07-17 | Celcom Digi_RAN-Allstar-TSS-Sabah-20230726 | DU00002040365 |  |  | 2023-09-07 | 2023-09-04 |  | In-Building System | BOOM | 6 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 2
S00406 | S110B_S00406OD_COWIEBAY | Sabah |  | Decomm |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-08-28 |  |  |  | 2023-09-06 |  | 2023-09-08 | 2023-09-29 | CD//Ray Amos | 2023-09-11 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006 | DU00002040366 |  |  |  |  | 2023-11-21 |  | TOWER
Q01337 | Q132C_Q01337OD_MYYWATERFRONT | Sarawak |  | Site Out (Decomm) | Decomm->Site Out->Site Out (Decomm) | 2023Q4 | SH | Trintel | 4.6 TSSR Approved |  | 2023-09-02 |  |  |  | 2023-09-22 |  | 2023-09-22 | 2023-09-29 |  | 2023-09-22 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230919/Celcom Digi_RAN-Trintel-TSS DECOMM-Sarawak-20231130 | DU00002040367 |  |  |  |  | 2025-06-26 |  | BOOM
S01625 | S110B_S01625IB_GAINTTAWAU | Sabah |  | Decomm |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-07-31 |  |  |  | 2023-07-31 |  | 2023-08-01 | 2023-10-04 | CD//Ray Amos | 2023-08-02 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231028/Celcom Digi_RAN-GTSB-Standard PR TSS DECOMM-Sabah-20231129 | DU00002040368 |  | 2/8:uncompleted photos & info NE & FE |  |  | 2023-09-19 |  | IN-BUILDING
Q01893 | Q118B_Q01893OD_WAWASANSEDAR2 | Sarawak | 9136K | Swap |  | 2023Q3 | SH | DATASCO | 4.6 TSSR Approved |  | 2023-08-02 | 2023-08-04 |  | 2023-08-08 |  | Closed | 2023-08-08 | 2023-08-09 | CD//John | 2023-08-09 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230913 | DU00002040369 |  |  | 2024-02-14 | 2023-12-20 |  | Monopole | RAPID ASSEMBLY POLE (RAPOLE) | 31 | Add R9264H M901821 x3 + R9264M M1821 x2,Dismantle Celcom all RRU&BBU |  | 13
S01004 | S099A_S01004OD_T3_KGSALUNG | Sabah | 7055K | Swap | Swap->Site Out->Swap->On Hold->Swap | 2025 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-30 | 2023-07-05 |  | 2023-07-07 |  | Under Approval | 2023-07-08 | 2023-07-10 | CD//Mohidi Jaan | 2023-07-10 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0005 | DU00002040370 |  |  | 2025-11-17 | 2025-11-14 |  | Tower | TOWER | 76 | Add R8852E S9000 x3+ R8894E x3, Dismantle | 0 | 0
S00387 | S106A_S00387OD_LADANGPEGAGAU | Sabah |  | Decomm |  | 2023Q4 | AD | Futong | 4.6 TSSR Approved |  | 2023-07-13 |  |  |  | 2023-07-14 |  | 2023-08-09 | 2023-08-18 | CD//Mohidi Jaan | 2023-07-21 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009 | DU00002040371 |  |  |  |  | 2023-11-07 |  | TOWER
Q01585 | Q118B_Q01585OD_TMNPELABUHANBTU | Sarawak |  | Decomm |  | 2023Q3 | SH | AllStar | 4.6 TSSR Approved |  | 2023-08-14 |  |  |  | 2023-08-17 |  | 2023-08-17 | 2023-09-07 | CD//John | 2023-08-17 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230622/0612Sarawak-AllStar-BOQ Template (template).xls | DU00002040372 |  |  |  |  | 2023-11-27 |  | RAPID ASSEMBLY POLE (RAPOLE)
S00474 | S090B_S00474OD_KGBUNSIT | Sabah |  | Decomm |  | 2023Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2023-05-10 |  |  |  | 2023-05-16 |  | 2023-06-15 | 2023-08-08 | CD//Mohidi Jaan | 2023-06-16 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230608-0008 | DU00002040373 |  | 2023-07-06 missing tx photos and info |  |  | 2023-09-08 |  | TOWER
Q01817 | Q118B_Q01817OD_STDMUHIBBAHBTU | Sarawak | 9131K | Swap |  | 2023Q3 | SH | Datasco | 4.6 TSSR Approved |  | 2023-05-13 | 2023-05-13 |  | 2023-05-17 |  | Closed | 2023-05-18 | 2023-05-18 | CD//John | 2023-05-18 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230516-0006 | DU00002040374 |  |  | 2024-11-04 | 2024-10-24 |  | Pole | RAPID ASSEMBLY POLE (RAPOLE) | 30 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
W01333 | B057A_W01333OD_JLN_TMN_INTAN_BAIDURI | Central | 1198K | Swap |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-06-21 | 2023-06-26 |  | 2023-07-09 |  | Closed | 2023-07-13 | 2023-07-27 | CD//Ali akaram | 2023-07-27 | CelcomDigi_RANMW_YPTT_TSS_Central_20230623_0005 | DU00002040375 |  |  | 2023-09-22 | 2023-09-22 |  | Lampole | LAMP_POLE | 19m | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 1
W00291 | B057A_W00291OD_SLYGBRANCH | Central | 1197K | Swap |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-06-21 | 2023-06-27 |  | 2023-07-09 |  | Closed | 2023-07-14 | 2023-08-23 | CD//Sapian | 2023-07-24 | CelcomDigi_RAN_YPTT_TSS_Central_20230623_0008 | DU00002040376 |  |  | 2023-11-16 | 2023-10-28 |  | In-Building System | BOOM | 12m | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 13
S01665 | S110B_S01665OD_TMNDAMAITWU | Sabah |  | Decomm |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-07-25 |  |  |  | 2023-12-20 |  | 2023-08-14 | 2023-12-20 | CD//Ray Amos | 2023-08-14 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006/Celcom Digi_RAN-Datasco-TSS DECOMM MW-Sabah-20240419 | DU00002040377 |  |  |  |  | 2023-10-27 |  | LAMP_POLE
Q01374 | Q132B_Q01374OD_RAMODESASENADIN2 | Sarawak |  | Decomm |  | 2023Q4 | ZB | South Pacific | 4.6 TSSR Approved |  | 2023-06-21 |  |  |  | 2023-06-21 |  | 2023-07-26 | 2023-08-23 | CD//John | 2023-08-01 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230622/0612Sarawak-South Pacific-BOQ Template (template) | DU00002040378 |  | 16/8: Uncompleted info & photos |  |  | 2025-10-15 |  | RAMO
Q00935 | Q118B_Q00935OD_TGBT2 | Sarawak |  | Decomm |  | 2023Q3 | SH | Datasco | 4.6 TSSR Approved |  | 2023-08-19 |  |  |  | 2023-08-22 |  | 2023-08-23 | 2023-08-24 | CD//John | 2023-08-23 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 | DU00002040379 |  |  |  |  | 2024-10-31 |  | AESTHETIC MONOPOLE
S00797 | S110B_S00797OD_HOTSPRING | Sabah |  | Decomm |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-07-20 |  |  |  | 2023-07-20 |  | 2023-08-02 | 2023-08-06 | CD//Mohidi Jaan | 2023-08-02 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230726 | DU00002040380 |  |  |  |  | 2024-01-09 |  | TOWER
Q01243 | Q132C_Q01243OD_JLNPDGKERBAU2 | Sarawak | 9094K | Swap |  | 2027 | AD | Datasco | 4.6 TSSR Approved |  | 2023-07-05 | 2023-08-01 |  | 2025-05-13 |  | Under Approval | 2023-08-14 | 2023-08-15 | E//John | 2025-06-13 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 - Copy | DU00002040381 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed |  |  |  | Monopole | RAPID ASSEMBLY POLE (RAPOLE) | 18 | Add R9264H M901821 x3 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 3
S01446 | S106A_S01446OD_T3_KGTONGKALLOH | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040382 | [6 empty] | TOWER
S00287 | MILE16KIMANIS | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2023Q3 | AD | Magicell | 4.6 TSSR Approved |  | 2023-07-03 |  |  |  | 2023-07-05 |  | 2023-07-18 | 2023-09-16 | CD//Jahganathan | 2023-07-20 | Celcom Digi_RAN-Magicell-TSS-Sabah-20230608-0003/Celcom Digi_RAN-Magicell-TSS DECOMM-Sabah-20230818/0919MW-Sabah-Magicell-BOQ Template (old contract) | DU00002040383 |  |  |  |  | 2025-10-01 |  | TOWER
Q00824 | Q132B_Q00824OD_LUTONGBARU | Sarawak | 9084K | Swap |  | 2023Q4 | ZB | South Pacific | 4.6 TSSR Approved |  | 2023-06-21 | 2023-06-26 |  | 2023-07-07 |  | Closed | 2023-07-10 | 2023-07-31 | CD//John | 2025-02-27 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230606-0003 | DU00002040384 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed | 2025-05-11 | 2025-04-15 |  | Tower | TOWER | 60 | Add R8862A S9000x3+R8894E M1821x3+R8862A S2601x3,Dismantle | 0 | 0
Q00804 | Q124B_Q00804OD_KGGITALAMA | Sarawak |  | Decomm |  | 2023Q4 | ZB | South Pacific | 4.6 TSSR Approved |  | 2023-06-19 |  |  |  | 2023-06-21 |  | 2023-07-25 | 2023-07-28 | CD//John | 2023-07-26 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230622 | DU00002040385 |  |  |  |  | 2023-09-26 |  | TOWER
Q01247 | VQ_LDGKAMINSKY | Sarawak | 9095K | Swap | Swap->Site Out->Swap->On Hold->Swap | 2027 | AI | Datasco | 4.6 TSSR Approved |  | 2023-12-02 | 2023-12-07 |  |  |  |  | 2025-03-27 | 2025-04-17 | CD//John | 2025-03-28 |  | DU00002040386 | [6 empty] | TOWER | 24 | Add R8852E S9000 x3+R9264M M1821 x3,Dismantle
Q01477 | Q124B_Q01477OD_SCRIVEREDGEKCH | Sarawak | 9106K | Swap |  | 2023Q4 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-07-12 | 2023-08-24 |  | 2023-08-28 |  | Closed | 2023-08-29 | 2023-08-30 | CD//John | 2023-08-30 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 - Copy | DU00002040387 |  |  | 2023-09-27 | 2023-09-20 |  |  | BOOM |  | Add BS8932 x1,Dismantle Celcom all RRU&BBU | 0 | 0
Q01897 | Q118B_Q01897OD_CB_JAYAFRONTQRTS2 | Sarawak |  | Decomm |  | 2023Q3 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-05-26 |  |  |  | 2023-07-12 |  | 2023-07-24 | 2023-09-08 | CD//John | 2023-07-28 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230529-0012/Celcom Digi_RAN-Magicell-TSS DECOMM-Sarawak-20230818 | DU00002040388 |  | 1/9: uncompleted info |  |  | 2024-03-29 |  | RAPID ASSEMBLY POLE (RAPOLE)
S01774 | FC1_103 Pulau Sebatik Kg Tamang | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | AD |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002040389 | [6 empty] | TOWER
Q01665 | Q132B_Q01665OD_PERMYTECHPARK | Sarawak |  | Decomm |  | 2023Q4 | SH | Magicell | 4.6 TSSR Approved |  | 2023-06-24 |  |  |  | 2023-07-11 |  | 2023-07-25 | 2023-08-23 | CD//John | 2023-07-26 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622/CelcomDigi_RAN_Magicell_TSS_Sarawak_20241018 | DU00002040390 |  |  |  |  | 2025-03-26 |  | RAPID ASSEMBLY POLE (RAPOLE)
Q00903 | Q132C_Q00903OD_JLNKROKOP9 | Sarawak |  | Decomm |  | 2023Q4 | SH | Datasco | 4.6 TSSR Approved |  | 2023-08-26 |  |  |  | 2023-09-12 |  | 2023-09-12 | 2024-01-18 |  | 2023-09-13 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622/0612Sarawak-Datasco-BOQ Template (template) | DU00002040391 |  |  |  |  | 2025-02-28 |  | LAMP_POLE
S00969 | S097A_S00969OD_LADANGAUMKAR1 | Sabah |  | Decomm |  | 2023Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-06-14 |  |  |  | 2023-07-04 |  | 2023-08-01 | 2023-08-14 | CD//Ray Amos | 2023-08-02 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0009/Celcom Digi_RAN-GTSB-Standard PR TSS DECOMM-Sabah-20231129 | DU00002040392 |  | 2/8: INFO & PHOTOS MISSING NE Info & photos are missing (FE) |  |  | 2023-11-15 |  | TOWER
Q01306 | Q118B_Q01306OD_PESTECHBTU | Sarawak |  | Decomm |  | 2023Q3 | SH | Datasco | 4.6 TSSR Approved |  | 2023-07-21 |  |  | 2023-07-23 |  | Closed | 2023-07-24 | 2023-11-18 | CD//John | 2023-07-25 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622/0612Sarawak-Datasco-BOQ Template (template) | DU00002040393 |  |  |  |  | 2024-03-28 |  | RAPID ASSEMBLY POLE (RAPOLE)
S00729 | S106A_S00729OD_PULAUBUMBUM | Sabah |  | Decomm |  | 2023Q4 | AD | Futong | 4.6 TSSR Approved |  | 2023-07-13 |  |  |  | 2023-07-14 |  | 2023-07-20 | 2023-08-06 | CD//Mohidi Jaan | 2023-07-21 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009/0612Sabah-Futong-BOQ Template (template) | DU00002040394 |  |  |  |  | 2023-10-04 |  | TOWER
Q01340 | Q132B_Q01340IB_PETRONASMYYID | Sarawak | 9101K | Site Out (Swap) | Swap->MOCN Decomm->Site Out->Site Out (Swap) | 2023Q4 |  | Magicell | 14.1 TSSR Not Required (Decomm by CD) | E.co revert fully decomm | 2025-09-18 |  |  |  |  | To be Submitted |  |  |  |  | SQ202508220455-Magicell | DU00002040395 |  |  |  |  | 2025-09-20 |  | IN-BUILDING
Q01217 | Q132B_Q01217OD_DESASENADIN | Sarawak | 9093K | Swap |  | 2023Q4 | SH | Datasco | 4.6 TSSR Approved |  | 2023-06-28 | 2023-07-11 |  | 2023-07-18 |  | Closed | 2023-07-18 | 2023-07-20 | CD//John | 2023-07-19 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 - Copy | DU00002040396 |  |  | 2025-07-06 | 2025-06-09 |  | Watertank | RAPID ASSEMBLY POLE (RAPOLE) | 30 | Add R9264H M901821x3,Dismantle Celcom all RRU&BBU
Q00899 | Q124F_Q00899OD_CENDERAWASIH | Sarawak | 9086K | Swap |  | 2023Q4 | SH | Datasco | 4.6 TSSR Approved |  | 2023-07-05 | 2023-07-12 |  | 2023-07-14 |  | Closed | 2023-07-14 | 2023-07-18 | CD//John | 2023-07-18 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 - Copy | DU00002040397 |  |  | 2023-09-21 | 2023-09-19 |  | Guide mast | MINARET | 14 | Add R8852E S9000 x3 + R8894E M1821 x3
S00669 | S110C_S00669OD_WALLACEBAY | Sabah |  | Decomm |  | 2023Q3 | AD | Futong | 4.6 TSSR Approved |  | 2023-07-27 |  |  |  | 2023-08-01 |  | 2023-08-02 | 2023-08-23 | CD//Mohidi Jaan | 2023-08-02 | Celcom Digi_RAN-Futong-TSS-Sabah-20230531-0008/0612Sabah-Futong-BOQ Template (template) | DU00002040398 |  |  |  |  | 2023-12-22 |  | TOWER
S01893 | FC1_091 Jalan Batu 63 Nabawan-Sapulot | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | AD |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002040399 | [6 empty] | TOWER
S01002 | S099A_S01002OD_T3_KGTATALUAN | Sabah |  | Decomm |  | 2023Q3 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-09 |  |  |  | 2023-07-27 |  | 2023-07-31 | 2023-09-12 | CD//Jahganathan | 2023-08-01 | Celcom Digi_RAN-Futong-TSS-Sabah-20230531-0008 | DU00002040400 |  | 20230801: FE info & photos missing |  |  | 2023-09-25 |  | TOWER
Q01759 | Q132B_Q01759OD_DANAUPERMAIMYY | Sarawak | 9120K | Swap |  | 2023Q4 | ZB | South Pacific | 4.6 TSSR Approved |  | 2023-06-21 | 2023-06-26 |  | 2023-07-04 |  | Closed | 2024-10-25 | 2024-12-06 | CD//John | 2024-12-06 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230606-0003 | DU00002040401 |  |  | 2025-01-26 | 2025-01-13 |  | Monopole | RAPID ASSEMBLY POLE (RAPOLE) | 30m | Add R8862A S9000x3+R8894E M1821x3, Dismantle | 0 | 0
S00290 | S090B_S00290OD_PPHKENINGAU | Sabah | 7026K | Swap |  | 2023Q3 | HQ 1 | Datasco | 4.6 TSSR Approved |  | 2023-07-09 | 2023-07-25 |  | 2023-07-28 |  | Closed | 2023-08-07 | 2023-08-07 | CD//Jahganathan | 2023-08-07 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230508-0004 | DU00002040402 |  |  | 2023-08-07 | 2023-08-02 |  | Tower | GUYED MAST | 30 | Add R8852E S9000 x3 + R8894E M1821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
S01895 | FC1_101 Jalan Kimanis-Keningau_1 | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | AD | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A | DU00002040403 | [6 empty] | TOWER
Q00761 | Q118B_Q00761OD_JLNTGBT | Sarawak | 9080K | Swap |  | 2023Q3 | SH | Datasco | 4.6 TSSR Approved |  | 2023-05-14 | 2023-05-19 |  | 2023-05-24 |  | Closed | 2024-10-24 | 2024-10-25 | CD//John | 2024-10-25 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230516-0006 | DU00002040404 |  |  | 2024-11-04 | 2024-10-22 |  | Pole | BOOM | 6m | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle Celcom all RRU&BBU | 0 | 2
S00250 | S106A_S00250OD_CB_TGKAPOR | Sabah |  | Decomm |  | 2023Q4 | AD | Futong | 4.6 TSSR Approved |  | 2023-07-17 |  |  |  | 2023-07-18 |  | 2023-08-09 | 2023-09-19 | CD//Mohidi Jaan | 2023-07-21 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009 | DU00002040405 |  |  |  |  | 2023-10-27 |  | TOWER
Q01338 | Q124B_Q01338OD_AKMALKCH | Sarawak |  | Decomm |  | 2023Q4 | ZB | South Pacific | 4.6 TSSR Approved |  | 2023-06-26 |  |  |  | 2023-08-12 |  | 2023-08-14 | 2023-10-13 | CD//John | 2023-08-14 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230622/0612Sarawak-South Pacific-BOQ Template (template) | DU00002040406 |  | 24/8: Uncompleted info FE info + photos are missing |  |  | 2023-11-08 |  | MONOPOLE
W00025 | B057A_W00025OD_TMNINTANBAIDURI | Central |  | Decomm |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-07-31 |  |  |  | 2023-07-31 |  | 2023-08-02 | 2024-01-30 | CD//Norhaliza | 2023-10-04 | CelcomDigi_RAN_YPTT_TSS_Central_20230731 | DU00002040407 |  |  |  |  | 2023-09-26 |  | AESTHETIC MONOPOLE
S00816 | S090B_S00816OD_TMNSABANA | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2023Q3 | MS | Datasco | 4.6 TSSR Approved |  | 2024-03-05 |  |  |  | 2024-03-14 |  | 2024-03-18 | 2024-08-29 | CD//Ray Amos | 2024-03-18 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006/0919MW-Sabah-Datasco-BOQ Template (old contract) | DU00002040408 |  |  |  |  | 2025-03-26 |  | RAPID ASSEMBLY POLE (RAPOLE)
Q01896 | Q124F_Q01896OD_KAMPUNGGERSIK | Sarawak |  | Decomm |  | 2023Q4 | SH | Magicell | 4.6 TSSR Approved |  | 2023-06-29 |  |  |  | 2023-07-18 |  | 2023-07-24 | 2023-08-06 | CD//John | 2023-07-25 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002040409 |  |  |  |  | 2023-10-05 |  | RAPID ASSEMBLY POLE (RAPOLE)
S01312 | S090A_S01312OD_KGMJD | Sabah |  | Decomm |  | 2023Q3 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-08-02 |  |  |  | 2023-08-03 |  | 2023-08-04 | 2023-09-01 | CD//Mohidi Jaan | 2023-08-08 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230804 | DU00002040410 |  |  |  |  | 2023-09-22 |  | RAPID ASSEMBLY POLE (RAPOLE)
S01517 | S110B_S01517OD_T3_KGBLOK31 | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040411 | [6 empty] | TOWER
Q01839 | Q132C_Q01839OD_EASTWOODGOLFCLUB | Sarawak | 9134K | Swap |  | 2023Q4 | SH | AllStar | 4.6 TSSR Approved |  | 2023-06-19 | 2023-06-19 |  | 2023-06-20 |  | Closed | 2023-06-21 | 2023-06-26 | CD//John | 2023-06-25 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230608-0006 | DU00002040412 |  |  | 2025-05-04 | 2025-04-15 |  | Tower | TOWER | 47 | Add R8852E S9000 x3 + R8894E M1821 x3
Q01656 | Q132B_Q01656OD_TMNRIVERVIEW2 | Sarawak |  | Decomm |  | 2023Q4 | ZB | South Pacific | 4.6 TSSR Approved |  | 2023-06-22 |  |  |  | 2023-08-01 |  | 2023-08-01 | 2023-09-29 | CD//John | 2023-08-02 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230622/0612Sarawak-South Pacific-BOQ Template (template) | DU00002040413 |  | 24/8: undompleted info & photos fe info & photos are missing |  |  | 2025-04-25 |  | RAPID ASSEMBLY POLE (RAPOLE)
Q02226 | Q124B_Q02226OD_TMNBANJARANSERAPI | Sarawak | 9140K | Swap |  | 2023Q4 | SH | Datasco | 4.6 TSSR Approved |  | 2023-07-08 | 2023-08-03 |  | 2023-08-09 |  | Closed | 2023-08-09 | 2023-08-11 | CD//John | 2023-08-11 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230726 | DU00002040414 |  |  | 2023-09-26 | 2023-09-24 |  | Tower | RAPID ASSEMBLY POLE (RAPOLE) | 31 | Add R8852E S9000 x3 + R8894E M1821 x3
Q01263 | Q118B_Q01263OD_PRESSMETALBTU | Sarawak | 9098K | Swap |  | 2023Q3 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-07-08 | 2023-07-12 |  | 2023-07-14 |  | Closed | 2023-07-14 | 2023-07-20 | CD//John | 2023-07-20 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230516-0006 | DU00002040415 |  |  | 2024-04-02 | 2024-03-16 |  | Unipole | RAPID ASSEMBLY POLE (RAPOLE) | 15 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
Q00925 | Q124F_Q00925OD_SANTUBONGRST | Sarawak |  | Decomm |  | 2023Q4 | SH | Datasco | 4.6 TSSR Approved |  | 2023-06-20 |  |  | 2023-06-22 |  | Closed | 2023-06-23 | 2023-09-19 | CD//John | 2023-06-25 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 | DU00002040416 |  | uncompleted info & phoots |  |  | 2023-11-29 |  | TOWER
Q01664 | Q132B_Q01664OD_DESAMURNI | Sarawak |  | Decomm |  | 2023Q4 | SH | NR services | 4.6 TSSR Approved |  | 2023-10-09 |  |  |  | 2023-10-09 |  | 2023-10-09 | 2023-10-21 | CD//John | 2023-10-10 | Celcom Digi_RAN-NR Services-TSS-Sarawak-20230823/0619Sarawak-NR services-BOQ Template (template) | DU00002040417 |  |  |  |  | 2025-07-11 |  | RAPID ASSEMBLY POLE (RAPOLE)
Q01393 | Q132B_Q01393OD_KGTUDAN | Sarawak |  | Decomm |  | 2023Q4 | SH | YPTT | 4.6 TSSR Approved |  | 2023-09-04 |  |  |  | 2023-09-04 |  | 2023-09-04 | 2023-09-23 | CD//John | 2023-09-04 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20230622/Celcom Digi_RAN-YPTT-TSS DECOMM-Sarawak-20231128 | DU00002040418 |  |  |  |  | 2025-03-27 |  | RAPID ASSEMBLY POLE (RAPOLE)
Q01892 | Q118B_Q01892OD_DESALAVANG2 | Sarawak | 9135K | Swap |  | 2023Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2023-05-23 | 2023-05-25 |  | 2023-06-05 |  | Closed | 2023-06-09 | 2023-06-12 | CD//John | 2023-06-10 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230516-0007 | DU00002040419 |  |  | 2023-11-18 | 2023-11-10 |  | Monopole | RAPID ASSEMBLY POLE (RAPOLE) | 30m | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 1(S1->S3,S2->S1,S3->S2,rename Sector ID,MM@new S3)
S00253 | S110A_S00253OD_TMTAWAUCARRIER | Sabah |  | Decomm |  | 2023Q4 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2024-01-22 |  |  |  | 2024-01-22 |  | 2024-01-22 | 2024-02-15 | CD//Ray Amos | 2024-01-23 | Celcom Digi_RAN-Seri Pancar-Standard PR TSS-Sabah-20240124 | DU00002040420 |  |  |  |  | 2024-06-11 |  | RT 6m Tripod Boom
Q01284 | Q132C_Q01284OD_TMPUJUT4 | Sarawak |  | Decomm |  | 2023Q4 | SH | Magicell | 4.6 TSSR Approved |  | 2023-08-04 |  |  |  | 2023-08-07 |  | 2023-08-07 | 2024-07-11 | CD//John | 2023-08-07 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002040421 |  | 1/9:uncompleted info |  |  | 2025-11-17 |  | GUYED MAST
Q01701 | Q118B_Q01701OD_CB_JLNCOASTALBTU1 | Sarawak | 9112K | Swap |  | 2023Q3 | SH | YPTT | 4.6 TSSR Approved |  | 2023-05-21 | 2023-05-24 |  | 2023-05-29 |  | Closed | 2023-06-01 | 2023-06-07 | CD//John | 2023-06-04 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20230524-0002 | DU00002040422 |  |  | 2023-11-24 | 2023-11-09 |  | Tower | TOWER | 45 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
Q01910 | Q124F_Q01910OD_RPRPETRAJAYA | Sarawak |  | Decomm |  | 2023Q4 | SH | Trintel | 4.6 TSSR Approved |  | 2023-07-06 |  |  |  | 2023-07-26 |  | 2023-07-27 | 2023-08-18 | CD//John | 2023-08-08 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230622/Celcom Digi_RAN-Trintel-TSS DECOMM-Sarawak-20231130 | DU00002040423 |  |  |  |  | 2023-09-28 |  | RAPID ASSEMBLY POLE (RAPOLE)
Q01806 | Q124F_Q01806IB_DUNSWKID | Sarawak | 9123K | Swap |  | 2023Q4 | HQ 1 | South Pacific | 4.6 TSSR Approved |  | 2023-07-10 | 2023-07-17 |  | 2023-07-21 |  | Closed | 2023-07-26 | 2023-07-27 | CD//John | 2023-07-27 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230726 | DU00002040424 |  |  | 2023-09-22 | 2023-09-21 |  | Portables BTS | IN-BUILDING |  | Add R8862A S2100 x3 +R8862A S1800 x3+ R8862A S2601 x3,Dismantle all celcom BBU&RRU
S01880 | FC1_090 Ladang STS Agricultural | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | AD |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002040425 | [6 empty] | TOWER
S00276 | S090B_S00276OD_MENAWOH | Sabah |  | Decomm |  | 2023Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-06-15 |  |  |  | 2023-06-19 |  | 2023-06-19 | 2023-09-16 | CD//Mohidi Jaan | 2023-06-19 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230608-0007 | DU00002040426 |  | 2023-07-06 missing tx photos and info |  |  | 2023-09-29 |  | TOWER
S01145 | S110B_S01145OD_KGBALONGCOCOS | Sabah |  | Decomm |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-08-04 |  |  |  | 2023-08-04 |  | 2023-08-09 | 2023-09-16 | CD//Ray Amos | 2023-08-08 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006/0612Sabah-Datasco-BOQ Template (template) | DU00002040427 |  | 18/8 : P1 - wrong TX info P23/24/27 - TX info & TX EQ are missing P28 - TX EQ missing |  |  | 2023-11-18 |  | RAPID ASSEMBLY POLE (RAPOLE)
Q01405 | Q132C_Q01405OD_JLNCAHAYAMYY | Sarawak |  | Decomm |  | 2023Q4 | SH | Datasco | 4.6 TSSR Approved |  | 2023-08-26 |  |  |  | 2023-09-14 |  | 2023-09-14 | 2024-06-28 | CD//John | 2023-09-18 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622/0612Sarawak-Datasco-BOQ Template (template) | DU00002040428 |  |  |  |  | 2025-01-28 |  | RAPID ASSEMBLY POLE (RAPOLE)
S01780 | FC1_109 Pulau Bum Bum - Kg Kabimbangan | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 |  | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002040429 | [6 empty] | TOWER
S01704 | Kg Binanding | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040430 | [6 empty] | 3LEGGED
S00468 | S106A_S00468OD_CB_TAGASAN | Sabah |  | Decomm |  | 2023Q4 | AD | Futong | 4.6 TSSR Approved |  | 2023-07-15 |  |  |  | 2023-08-01 |  | 2023-08-02 | 2023-09-16 | CD//Mohidi Jaan | 2023-08-02 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009/0612Sabah-Futong-BOQ Template (template) | DU00002040431 |  |  |  |  | 2023-10-27 |  | TOWER
S01543 | S090B_S01543OD_TMNBANDUKAN | Sabah | 7292P | Site Out (Swap) | Swap->Site Out->Replacement, Site Out (Swap) | 2023Q3 | HQ 1 | Datasco | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-02 |  | 2023-06-28 |  | Rectificating | 2023-07-03 | 2023-07-07 | CD//Mohidi Jaan | 2023-07-07 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230508-0004 | DU00002040432 | [5 empty] | Monopole | TOWER | 60
S00452 | S090B_S00452OD_PEGALAN | Sabah |  | Decomm |  | 2023Q3 | MS | South Pacific | 4.6 TSSR Approved |  | 2023-07-23 |  |  |  | 2023-07-26 |  | 2023-07-27 | 2023-08-06 | CD//Mohidi Jaan | 2023-07-28 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230726 | DU00002040433 |  |  |  |  | 2023-09-21 |  | BOOM
Q01113 | Q118B_Q01113OD_RHROBIN | Sarawak | 9090K | Swap |  | 2023Q3 | HQ 5 | Magicell | 4.6 TSSR Approved |  | 2023-05-13 | 2023-05-17 |  | 2023-05-19 |  | Closed | 2023-05-25 | 2023-05-25 | CD//John | 2023-05-25 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230516-0008 | DU00002040434 |  |  | 2023-12-14 | 2023-12-06 |  | Tower | 3LEGGED | 76m | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
S01782 | FC1_107 Kg Bukit Qouin - Ladang Sg Kawa | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 | MS | Datasco | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002040435 | [6 empty] | TOWER
S00501 | S106A_S00501OD_CB_BKTKAMIRI | Sabah |  | Decomm |  | 2023Q4 | AD | Futong | 4.6 TSSR Approved |  | 2023-07-20 |  |  |  | 2023-07-22 |  | 2023-07-25 | 2023-08-06 | CD//Jahganathan | 2023-07-26 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009 | DU00002040436 |  |  |  |  | 2023-12-06 |  | TOWER
S00288 | S090B_S00288OD_CB_BINGKOR | Sabah |  | Decomm |  | 2023Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2023-05-15 |  |  |  | 2023-05-19 |  | 2023-06-15 | 2023-10-13 | CD//Mohidi Jaan | 2023-06-16 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230608-0008 | DU00002040437 |  |  |  |  | 2023-08-18 |  | TOWER
S01458 | S099A_S01458OD_T3_KM90KALABAKANNABAWAN | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040438 | [6 empty] | TOWER
Q01044 | Q118B_Q01044OD_JLNABGDEEN | Sarawak |  | Decomm |  | 2023Q3 | SH | South Pacific | 4.6 TSSR Approved |  | 2023-05-16 |  |  |  | 2023-05-19 |  | 2023-05-26 | 2023-07-21 | CD//John | 2023-05-26 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230512-0001 | DU00002040439 |  |  |  |  | 2023-11-30 | Monopole | BOOM | 30m
S00054 | S110B_S00054OD_CB_BATUPAYUNG | Sabah |  | Decomm |  | 2023Q4 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-06-12 |  |  |  | 2023-06-19 |  | 2023-07-25 | 2023-08-06 | CD//Jahganathan | 2023-07-26 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230622 | DU00002040440 |  |  |  |  | 2023-12-22 |  | TOWER
Q01273 | Q132B_Q01273OD_KUALABARAMIND | Sarawak |  | Decomm |  | 2023Q4 | SH | Datasco | 4.6 TSSR Approved |  | 2023-09-04 |  |  |  | 2023-09-15 |  | 2023-09-15 | 2024-06-28 | CD//John | 2023-09-18 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622/0612Sarawak-Datasco-BOQ Template (template) | DU00002040441 |  |  |  |  | 2025-03-11 |  | RAPID ASSEMBLY POLE (RAPOLE)
Q01907 | Q132B_Q01907OD_TMNCERIA | Sarawak |  | Decomm |  | 2023Q4 | ZB | South Pacific | 4.6 TSSR Approved |  | 2023-06-26 |  |  |  | 2023-07-31 |  | 2023-07-31 | 2023-08-23 | CD//John | 2023-08-01 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230622/0612Sarawak-South Pacific-BOQ Template (template) | DU00002040442 |  | 16/8: Uncompleted info & photos |  |  | 2025-07-12 |  | RAPID ASSEMBLY POLE (RAPOLE)
Q01485 | Q118B_Q01485OD_BT5INDBTU | Sarawak |  | Decomm |  | 2023Q3 | SH | South Pacific | 4.6 TSSR Approved |  | 2023-05-17 |  |  |  | 2023-05-23 |  | 2023-05-25 | 2023-10-13 | CD//John | 2023-05-26 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230512-0001/0612Sarawak-South Pacific-BOQ Template (template) | DU00002040443 |  | 2023-06-26 Missing TX photos and info |  |  | 2023-11-29 |  | RAPID ASSEMBLY POLE (RAPOLE)
S00243 | S110C_S00243OD_CB_LUASONG | Sabah |  | Decomm |  | 2023Q3 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-09 |  |  |  | 2023-11-03 |  | 2023-11-04 | 2023-11-18 | CD//Jahganathan | 2023-11-03 | Celcom Digi_RAN-Futong-TSS-Sabah-20230531-0008/0612Sabah-Futong-BOQ Template (template) | DU00002040444 |  |  |  |  | 2023-11-29 |  | TOWER
Q01816 | Q132A_Q01816OD_LDGPAROH | Sarawak | 9130K | Swap |  | 2023Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2023-05-26 | 2023-06-12 |  | 2023-06-20 |  | Closed | 2023-06-20 | 2023-06-21 | CD//John | 2023-06-21 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230516-0007 | DU00002040445 |  |  | 2023-11-17 | 2023-11-07 |  | Tower | TOWER | 45m | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
Q01557 | Q118B_Q01557OD_LRGPAUHBTU | Sarawak |  | Decomm |  | 2023Q3 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-06-19 |  |  | 2023-08-02 |  | Closed | 2023-08-02 | 2024-06-26 | CD//John | 2023-08-02 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009/0612Sarawak-Datasco-BOQ Template (template) | DU00002040446 |  |  |  |  | 2024-10-31 |  | RAPID ASSEMBLY POLE (RAPOLE)
S01163 | S110B_S01163OD_TMNINDAHBT10 | Sabah |  | Decomm |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-07-27 |  |  |  | 2023-07-28 |  | 2023-08-02 | 2023-09-29 | CD//Ray Amos | 2023-08-03 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006/0612Sabah-Datasco-BOQ Template (template) | DU00002040447 |  | 3/8: tx INFO MISSING (DRAWING) INFO & PHOTOS MISISNG (FE) |  |  | 2023-12-06 |  | MONOPOLE
S00968 | S097A_S00968OD_BUKITTAMU | Sabah | 7043K | Swap |  | 2023Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-06-14 | 2023-06-21 |  | 2023-06-24 |  | Closed | 2023-06-28 | 2023-07-24 | CD//Ray Amos | 2023-07-24 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0010 | DU00002040448 |  |  | 2023-09-27 | 2023-09-21 |  | Tower | TOWER | 76 | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle Celcom all RRU&BBU |  | 3
Q01652 | Q118B_Q01652OD_RPRKIDURONG2 | Sarawak |  | Decomm |  | 2023Q3 | SH | South Pacific | 4.6 TSSR Approved |  | 2023-05-22 | 2023-06-26 |  |  | 2023-06-09 |  | 2023-06-09 | 2023-09-19 | CD//John | 2023-06-10 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230512-0001/0612Sarawak-South Pacific-BOQ Template (template) | DU00002040449 |  | 27/7: Unclear photos 2023-06-26 Missing TX photos and info |  |  | 2023-12-26 | Monopole | RAPID ASSEMBLY POLE (RAPOLE) | 28m
S01892 | FC1_104 Pulau Sebatik Skim Mesej Sg.Labah | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | MS |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002040450 | [6 empty] | TOWER
S00515 | S106A_S00515OD_SMKTAGASAN | Sabah |  | Decomm |  | 2023Q4 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-19 |  |  |  | 2023-06-22 |  | 2023-06-21 | 2023-07-21 | CD//Mohidi Jaan | 2023-06-22 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009 | DU00002040451 |  |  |  |  | 2023-12-06 |  | TOWER
S00886 | S090A_S00886OD_KGBASANAN | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2023Q3 | AD | Datasco | 4.6 TSSR Approved | [5 empty] | 2023-05-15 |  | 2025-09-10 | 2025-10-22 | E//Hannah | 2025-09-16 | SQ202508010264 - Datasco | DU00002040452 |  |  |  |  | 2025-10-31 |  | TOWER
S01460 | S099A_S01460OD_T3_TIBOWRESEARCHCENTRE | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040453 | [6 empty] | TOWER
S01091 | S110A_S01091OD_JPJTAWAU | Sabah |  | Decomm |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-07-17 |  |  |  | 2023-07-21 |  | 2023-07-27 | 2023-08-06 | CD//Ray Amos | 2023-07-27 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230726 | DU00002040454 |  |  |  |  | 2023-10-02 |  | RAPID ASSEMBLY POLE (RAPOLE)
S00910 | S110C_S00910OD_SGBERGOSONG | Sabah | 7040K | Swap |  | 2023Q3 | HQ 1 | Futong | 4.6 TSSR Approved |  | 2023-07-11 | 2023-07-13 |  | 2023-07-15 |  | Closed | 2023-07-20 | 2023-07-25 | CD//Ray Amos | 2023-07-25 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0005 | DU00002040455 |  |  | 2023-08-24 | 2023-08-16 |  | Tower | TOWER | 37 | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle Celcom all RRU&BBU |  | 1
S01701 | Kg Bigor | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | MS |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002040456 | [6 empty] | 3LEGGED
Q01771 | Q118B_Q01771OD_TMNEVERGREENBTU | Sarawak | 9121K | Swap |  | 2023Q3 | SH | YPTT | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦Space constraint | 2023-05-21 | 2023-05-22 |  | 2023-05-29 |  | Closed | 2023-06-28 | 2023-06-28 | CD//John | 2023-06-10 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20230524-0002 | DU00002040457 | NIC_S2_Change MM to BI_Space constraint_SACOFA SDN BHD |  | 2023-12-22 | 2023-12-12 |  | Monopole | RAPID ASSEMBLY POLE (RAPOLE) | 30 | Add R9264H M901821 x3 + R9264M M1821 x2,Dismantle all celcom BBU&RRU |  | 23
S00302 | S090B_S00302OD_MJDALTAQWA | Sabah |  | Decomm |  | 2023Q3 | MS | Datasco | 4.6 TSSR Approved |  | 2023-07-20 |  |  |  | 2023-07-22 |  | 2023-07-26 | 2023-08-18 | CD//Ray Amos | 2023-07-27 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006 | DU00002040458 |  | 20230728: Wrong LL photos |  |  | 2023-09-29 |  | MINARET
Q01815 | Q132A_Q01815OD_LDGRUAI | Sarawak | 9129K | Swap |  | 2023Q3 | SH | YPTT | 4.6 TSSR Approved |  | 2023-05-22 | 2023-05-25 |  | 2023-05-29 |  | Closed | 2023-05-30 | 2023-05-31 | CD//John | 2023-05-31 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20230524-0002 | DU00002040459 |  | No TX Decom TSSR Required (Under upgrade) | 2023-11-11 | 2023-11-02 |  | Tower | TOWER | 45 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
S00617 | S106A_S00617OD_LADANGSABDI | Sabah |  | Decomm |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-07-12 |  |  |  | 2023-07-13 |  | 2023-07-27 | 2023-09-08 | CD//Ray Amos | 2023-07-28 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230726/0612Sabah-GTSB-BOQ Template (template) | DU00002040460 |  | 20230731 : IDU labelling missing, cisco info missing, FE info missing, FE photos missing |  |  | 2023-10-27 |  | TOWER
S00229 | S110C_S00229OD_PASIRPUTIH | Sabah |  | Decomm |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-07-17 |  |  |  | 2023-07-20 |  | 2023-07-27 | 2023-09-23 | CD//Mohidi Jaan | 2023-07-27 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230726 | DU00002040461 |  | 20230731 : LL info & photos missing, IDU label missing |  |  | 2023-11-25 |  | GUYED MAST
S00523 | S097A_S00523OD_MOSTYN | Sabah |  | MOCN Decomm(Dismantle Passive) | Swap->Maintain USP MOCN->MOCN Decomm->On Hold->Maintain USP MOCN(Dismantle Passive) | 2026 | MS | GTSB | 4.6 TSSR Approved |  | 2023-06-19 |  |  |  | 2023-06-19 |  | 2023-06-21 | 2023-09-01 | CD//Mohidi Jaan | 2023-06-22 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0009 | DU00002040462 |  | 20230731 : LL info missing, FE photos & info missing |  |  | 2025-11-28 |  | TOWER |  |  |  | 123
Q01791 | Q124F_Q01791OD_TMNSUMBERALAMSACTUARY2 | Sarawak |  | Decomm |  | 2023Q4 | SH | Datasco | 4.6 TSSR Approved |  | 2023-07-31 |  |  |  | 2023-08-02 |  | 2023-08-03 | 2024-02-15 | CD//John | 2023-08-03 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622/0612Sarawak-Datasco-BOQ Template (template) | DU00002040463 |  |  |  |  | 2023-11-15 |  | RAPID ASSEMBLY POLE (RAPOLE)
S01457 | S099A_S01457OD_T3_KM100KALABAKANNABAWAN | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040464 | [6 empty] | TOWER
Q00778 | Q124B_Q00778OD_CB_KGMATANG | Sarawak |  | Decomm |  | 2023Q4 | ZB | South Pacific | 4.6 TSSR Approved |  | 2023-08-17 |  |  |  | 2023-08-22 |  | 2023-08-22 | 2023-09-07 | CD//John | 2023-08-22 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230913 | DU00002040465 |  |  |  |  | 2023-11-08 |  | TOWER
Q01279 | Q132B_Q01279OD_JLNPUJUT9 | Sarawak |  | Decomm |  | 2023Q4 | SH | South Pacific | 4.6 TSSR Approved |  | 2023-06-23 |  |  |  | 2023-07-28 |  | 2023-07-28 | 2023-08-23 | CD//John | 2023-07-29 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230622/0612Sarawak-South Pacific-BOQ Template (template) | DU00002040466 |  | 16/8: Uncompleted info & photos |  |  | 2025-02-17 |  | TOWER
Q01745 | Q132C_Q01745OD_TMNLOPENGJAYA | Sarawak |  | Decomm |  | 2023Q4 | SH | Datasco | 4.6 TSSR Approved |  | 2023-08-25 |  |  |  | 2023-09-19 |  | 2023-09-20 | 2024-03-21 |  | 2023-09-21 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622/0612Sarawak-Datasco-BOQ Template (template) | DU00002040467 |  |  |  |  | 2025-02-12 |  | RAPID ASSEMBLY POLE (RAPOLE)
Q01402 | Q118B_Q01402OD_TMNPERTANIAN | Sarawak |  | Decomm |  | 2023Q3 | SH | NR services | 4.6 TSSR Approved |  | 2023-08-11 |  |  |  | 2023-09-08 |  | 2023-09-08 | 2024-02-15 | CD//John | 2023-09-08 | Celcom Digi_RAN-NR Services-TSS-Sarawak-20230823 | DU00002040468 |  |  |  |  | 2024-01-18 |  | TOWER
S00349 | S097A_S00349OD_TONGLEN | Sabah |  | Decomm |  | 2023Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-06-19 |  |  |  | 2023-06-20 |  | 2023-06-28 | 2023-08-06 | CD//Ray Amos | 2023-06-26 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0009 | DU00002040469 |  |  |  |  | 2023-10-27 |  | TOWER
S01437 | S110C_S01437OD_T3_KM40KALABAKANNABAWAN | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040470 | [6 empty] | TOWER
S00491 | S110C_S00491OD_LADANGIMAM | Sabah |  | Decomm |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-07-17 |  |  |  | 2023-07-20 |  | 2023-07-27 | 2023-09-16 | CD//Mohidi Jaan | 2023-07-27 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230726 | DU00002040471 |  |  |  |  | 2023-12-06 |  | TOWER
S00520 | S106A_S00520OD_KABONGAN | Sabah |  | Decomm |  | 2023Q4 | AD | Futong | 4.6 TSSR Approved |  | 2023-07-15 |  |  |  | 2023-08-01 |  | 2023-08-02 | 2023-09-23 | CD//Mohidi Jaan | 2023-08-02 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009 | DU00002040472 |  | 20230807: pls re arrange TX EQ photos (P10) |  |  | 2023-10-27 |  | TOWER
Q01255 | Q124B_Q01255OD_TMNMALIHA2 | Sarawak |  | Decomm |  | 2023Q4 | SH | AllStar | 4.6 TSSR Approved |  | 2023-07-24 |  |  |  | 2023-09-07 |  | 2023-09-07 | 2023-10-04 | CD//John | 2023-09-19 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230622/0612Sarawak-AllStar-BOQ Template (template).xls | DU00002040473 |  |  |  |  | 2023-11-13 |  | UNIPOLE
Q01357 | Q132C_Q01357OD_LEMBAHKENNY | Sarawak | 9102K | Swap |  | 2023Q4 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-07-12 | 2023-07-13 |  | 2023-07-17 |  | Closed | 2023-07-17 | 2023-07-18 | CD//John | 2023-07-18 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 - Copy | DU00002040474 |  |  | 2025-04-29 | 2025-04-15 |  | Monopole | RAPID ASSEMBLY POLE (RAPOLE) | 15 | Add R8852E S9000 x3 + R8894E M1821 x3
S01668 | LOGPONDTWU | Sabah |  | Decomm |  | 2023Q4 | AD | YPTT | 4.6 TSSR Approved |  | 2023-06-27 |  |  |  | 2023-07-09 |  | 2023-07-27 | 2024-03-21 | CD//Mohidi Jaan | 2024-07-27 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0008/0612Sabah-YPTT-BOQ Template (template) | DU00002040475 |  | 20230801: ALL tx info are missing |  |  | 2023-10-04 |  | TOWER
Q01532 | Q118B_Q01532OD_TMNJADE | Sarawak |  | Decomm |  | 2023Q3 | SH | CCSMY | 4.6 TSSR Approved |  | 2023-07-17 |  |  |  | 2023-08-03 |  | 2023-08-04 | 2023-08-23 | CD//John | 2023-08-08 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230613-0007/Celcom Digi_RAN-CCSMY-TSS DECOMM-Sarawak-20230818 | DU00002040476 |  |  |  |  | 2024-02-27 |  | RAPID ASSEMBLY POLE (RAPOLE)
S00350 | S097A_S00350OD_CB_MUISMELEWAR | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040477 | [6 empty] | TOWER
Q00811 | Q124F_Q00811OD_TMNSUKMA | Sarawak |  | Decomm |  | 2023Q4 | SH | Datasco | 4.6 TSSR Approved |  | 2023-08-03 |  |  |  | 2023-08-07 |  | 2023-08-07 | 2023-09-08 | CD//John | 2023-08-08 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 | DU00002040478 |  |  |  |  | 2023-09-29 |  | MONOPOLE
S00262 | S110A_S00262OD_KUHARAJAYASL | Sabah |  | Decomm |  | 2023Q4 | AD | YPTT | 4.6 TSSR Approved |  | 2023-07-18 |  |  |  | 2023-07-24 |  | 2023-07-27 | 2023-08-14 | CD//Jahganathan | 2023-08-07 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0008 | DU00002040479 |  |  |  |  | 2023-11-07 |  | BOOM
S00812 | S090B_S00812OD_TMNADIKA | Sabah |  | Decomm |  | 2023Q3 | MS | South Pacific | 4.6 TSSR Approved |  | 2023-07-22 |  |  |  | 2024-01-04 |  | 2024-01-05 | 2024-02-23 | CD//Ray Amos | 2024-01-09 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230726 | DU00002040480 |  |  |  |  | 2024-02-07 |  | RAPID ASSEMBLY POLE (RAPOLE)
Q00890 | Q118B_Q00890OD_LAVANGMILL | Sarawak | 9085K | Swap |  | 2023Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2023-05-26 | 2023-05-26 |  | 2023-06-05 |  | Closed | 2023-06-09 | 2023-06-12 | CD//John | 2023-06-10 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230516-0007 | DU00002040481 |  |  | 2024-02-08 | 2024-02-01 |  |  | WATER TANK |  | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
Q00829 | Q124B_Q00829OD_KGSEJIJAK | Sarawak |  | Decomm |  | 2023Q4 | ZB | AllStar | 4.6 TSSR Approved |  | 2023-07-24 |  |  |  | 2023-08-25 |  | 2023-08-28 | 2023-09-08 | CD//John | 2023-08-29 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230622 | DU00002040482 |  | 4/9:uncompleted info & phots |  |  | 2023-09-28 |  | TOWER
Q01045 | Q132B_Q01045IB_EMARTMYY | Sarawak | 9089K | Swap |  | 2023Q4 | ZB | AllStar | 4.6 TSSR Approved |  | 2023-07-06 | 2023-07-04 |  | 2023-07-06 |  | Closed | 2023-07-07 | 2023-07-14 | CD//John | 2023-07-07 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230608-0006 | DU00002040483 |  | 1. Missing reading load from rectifier (measure from Clampmeter) due to display not function | 2023-09-19 | 2023-09-04 |  | Watertank | IN-BUILDING |  | Add R8862A S2100 x1 + R8862A S1800 x1+R8862A S2601 x1,Dismantle all celcom BBU&RRU
Q02028 | Murum Dam | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040484 | [6 empty] | 3LEGGED
W00277 | B057A_W00277OD_TMNSRIMELATI | Central | 1196K | Swap |  | 2023Q4 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-06-26 | 2023-07-11 |  | 2023-07-17 |  | Closed | 2023-07-21 | 2024-01-02 | CD//Norhaliza | 2024-01-02 | CelcomDigi_RAN_YPTT_TSS_Central_20230627_0010 | DU00002040485 |  |  | 2023-12-13 | 2023-12-08 |  | H-bracket pole | BOOM | S1: 4m / S2 & S3: 5.5 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 2
S00252 | S106A_S00252OD_TMSEMPORNA | Sabah | 7022K | Swap |  | 2023Q4 | MS | South Pacific | 4.6 TSSR Approved |  | 2023-08-25 | 2023-10-06 |  | 2023-10-11 |  | Closed | 2023-10-12 | 2024-01-16 | CD//Jahganathan | 2024-01-16 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230830 | DU00002040486 |  |  | 2024-03-06 | 2024-02-17 |  | Tower | 4LEGGED | 74m | Add R9264H M901821 x3+R8854 S2600 x3,Dismantle |  | 123
S00228 | S110B_S00228OD_KUHARA | Sabah |  | Decomm |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-09-01 |  |  |  | 2023-10-05 |  | 2023-10-04 | 2024-02-15 | CD//Mohidi Jaan | 2023-10-07 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230904 | DU00002040487 |  |  |  |  | 2023-12-14 |  | BOOM
S01452 | S106A_S01452OD_T3_KGTAMPIKAPOR | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040488 | [6 empty] | TOWER
S01129 | S110B_S01129OD_TMNAIRPANAS | Sabah |  | Decomm |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-07-17 |  |  |  | 2023-07-20 |  | 2023-07-27 | 2024-07-19 | CD//Ray Amos | 2023-07-28 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230726 | DU00002040489 |  | 20230801: info & photos missing (FE) |  |  | 2024-01-25 |  | MONOPOLE
Q01423 | Q116A_Q01423OD_MN_UMABALOILIKO | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040490 | [6 empty] | 3LEGGED
S00996 | S090A_S00996OD_T3_KGSENAGANGULU | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040491 | [6 empty] | TOWER
S01904 | KG SIMATUOH | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | MS |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002040492 | [6 empty] | 3LEGGED
S00257 | S110A_S00257OD_SABINDO | Sabah | 7023K | Swap |  | 2023Q4 | AD | AllStar | 4.6 TSSR Approved |  | 2023-06-25 | 2023-06-28 |  | 2023-07-07 |  | Closed | 2023-07-08 | 2023-07-10 | CD//Jahganathan | 2023-07-10 | Celcom Digi_RAN-Allstar-TSS-Sabah-20230608-0004 | DU00002040493 |  |  | 2023-09-07 | 2023-09-04 |  | In-Building System | BOOM | 5 | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle Celcom all RRU&BBU |  | 2
S01908 | Kg Larapan Hujung | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 |  | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002040494 | [6 empty] | 3LEGGED
S01215 | S110C_S01215OD_KGSGIMAN | Sabah |  | Decomm |  | 2023Q3 | MS | Futong | 4.6 TSSR Approved |  | 2023-06-09 |  |  |  | 2023-06-15 |  | 2023-06-16 | 2025-10-28 | CD//Ray Amos | 2023-06-17 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009/0612Sabah-Futong-BOQ Template (template) | DU00002040495 |  |  |  |  | 2023-10-04 |  | MONOPOLE
S00264 | S090B_S00264OD_TMRINANTAI | Sabah | 7024K | Swap |  | 2023Q3 | MS | Datasco | 4.6 TSSR Approved |  | 2023-08-25 | 2023-09-14 |  | 2023-09-15 |  | Closed | 2023-09-15 | 2023-09-20 | CD//Mohidi Jaan | 2023-09-19 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230508-0004 | DU00002040496 |  |  | 2024-02-16 | 2024-01-16 |  | Tower | BOOM | 100 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
S00233 | S110B_S00233OD_CB_TATANA | Sabah |  | Decomm |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-07-10 |  |  |  | 2023-07-18 |  | 2023-07-31 | 2023-11-18 | CD//Ray Amos | 2023-08-07 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006/0612Sabah-Datasco-BOQ Template (template) | DU00002040497 |  | 2/8: All tx info & photos are missing (NE & FE) |  |  | 2024-01-04 |  | TOWER
S00259 | S110B_S00259OD_INDERASABAH | Sabah |  | Decomm |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-07-11 |  |  |  | 2023-07-24 |  | 2023-08-14 | 2023-09-29 | CD//Ray Amos | 2023-08-14 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006/0612Sabah-Datasco-BOQ Template (template) | DU00002040498 |  | 18/8: FE INFO & PHOTOS ARE MISSING |  |  | 2023-10-11 |  | TOWER
S01105 | S110C_S01105OD_TMNRIA5TWU | Sabah | 7057K | Swap |  | 2023Q4 | AD | YPTT | 4.6 TSSR Approved |  | 2023-06-30 | 2023-07-12 |  | 2023-07-17 |  | Closed | 2023-07-18 | 2023-07-20 | CD//Mohidi Jaan | 2023-07-19 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0009 | DU00002040499 |  |  | 2023-08-29 | 2023-08-22 |  |  | LAMP_POLE | 28 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 1
S01746 | Kg Pemuntarian | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | MS |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002040500 | [6 empty] | 3LEGGED
S01456 | S099A_S01456OD_T3_KM110KALABAKANNABAWAN | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040501 | [6 empty] | TOWER
Q01891 | Q118B_Q01891OD_SAMALAJUECOPARK | Sarawak |  | Decomm |  | 2023Q3 | SH | Datasco | 4.6 TSSR Approved |  | 2023-06-20 |  |  | 2023-06-22 |  | Closed | 2023-06-23 | 2023-10-13 | CD//John | 2023-06-25 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009/0612Sarawak-Datasco-BOQ Template (template) | DU00002040502 |  |  |  |  | 2024-03-30 |  | RAPID ASSEMBLY POLE (RAPOLE)
S01563 | S110C_S01563OD_CB_KGTANAHMERAH | Sabah |  | Decomm |  | 2023Q3 | MS | Futong | 4.6 TSSR Approved |  | 2023-06-09 |  |  |  | 2023-07-21 |  | 2023-07-24 | 2023-08-08 | CD//Mohidi Jaan | 2023-07-25 | Celcom Digi_RAN-Futong-TSS-Sabah-20230531-0008/0612Sabah-Futong-BOQ Template (template) | DU00002040503 |  |  |  |  | 2023-11-07 |  | TOWER
Q02064 | Q132C_Q02064OD_JLNDATOABGINDEH | Sarawak |  | Decomm |  | 2023Q4 | SH | Trintel | 4.6 TSSR Approved |  | 2023-07-20 |  |  |  | 2023-08-08 |  | 2023-08-09 | 2023-09-01 | CD//John | 2023-08-11 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230622/Celcom Digi_RAN-Trintel-TSS DECOMM-Sarawak-20231130 | DU00002040504 |  |  |  |  | 2025-06-19 |  | RAPID ASSEMBLY POLE (RAPOLE)
S01323 | S090B_S01323OD_CB_KOTAAYANGAN | Sabah |  | Decomm |  | 2023Q3 | MS | Datasco | 4.6 TSSR Approved |  | 2023-06-09 |  |  |  | 2023-06-03 |  | 2023-06-14 | 2023-12-22 | CD//Ray Amos | 2023-06-14 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006/0612Sabah-Datasco-BOQ Template (template) | DU00002040505 |  |  |  |  | 2023-09-28 |  | RAPID ASSEMBLY POLE (RAPOLE)
S01111 | S110B_S01111OD_FUJIMARTSHANGRILA | Sabah |  | Decomm |  | 2023Q4 | AD | YPTT | 4.6 TSSR Approved |  | 2023-07-22 |  |  |  | 2023-07-28 |  | 2023-07-31 | 2023-09-08 | CD//Ray Amos | 2023-08-01 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0008/0612Sabah-YPTT-BOQ Template (template) | DU00002040506 |  | 2/8: 1. IDU LABEL MISSING NE & FE 2. TX INFO MISSING (FE) |  |  | 2023-10-01 |  | RAPID ASSEMBLY POLE (RAPOLE)
S01516 | S106A_S01516OD_SIPADANINN3 | Sabah | 7060K | Swap |  | 2023Q4 | MS | Futong | 4.6 TSSR Approved |  | 2023-06-30 | 2023-07-05 |  | 2023-07-12 |  | Closed | 2023-07-17 | 2023-07-18 | CD//Mohidi Jaan | 2023-07-17 | Celcom Digi_RAN-Futong-TSS-Sabah-20230703.xls | DU00002040507 |  |  | 2023-09-22 | 2023-09-13 |  | Pole | BOOM | 6 | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle Celcom all RRU&BBU |  | 1
S00970 | S097A_S00970OD_LADANGBINUANG | Sabah |  | Decomm |  | 2023Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-06-21 |  |  |  | 2023-06-25 |  | 2023-06-27 | 2023-07-27 | CD//Ray Amos | 2023-06-27 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0009/0612Sabah-GTSB-BOQ Template (template) | DU00002040508 |  |  |  |  | 2023-10-08 |  | TOWER
S00650 | S106A_S00650OD_KGTGKAPOR | Sabah | 7034K | Swap |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-07-12 | 2023-09-01 |  | 2023-09-15 |  | Closed | 2023-09-15 | 2023-09-20 | CD//Ray Amos | 2023-09-19 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230703.xls | DU00002040509 |  |  | 2023-09-27 | 2023-09-21 |  | Tower | TOWER | 60 | Add R8852E S9000 x1 +R9264H M901821 x2+ A9732 M1821 x1 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 2
S01090 | S090A_S01090OD_JLNMASAK1 | Sabah | 7056K | Swap |  | 2023Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-09 |  | 2023-05-11 |  | Closed | 2023-05-12 | 2023-06-13 | CD//Mohidi Jaan | 2023-06-13 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230508-0005 | DU00002040510 |  |  | 2023-08-03 | 2023-07-18 |  | Lampole | RAPID ASSEMBLY POLE (RAPOLE) | 35 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2,Dismantle Celcom all RRU&BBU | 3
S01891 | FC1_105 Sabah Softwood Berhad & Residential Area | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | MS |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002040511 | [6 empty] | TOWER
S01703 | Kg Sandangoh | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040512 | [6 empty] | 3LEGGED
S00400 | S099A_S00400OD_DESAKIMLOONG | Sabah |  | Decomm |  | 2023Q3 | MS | South Pacific | 4.6 TSSR Approved |  | 2023-07-22 |  |  |  | 2023-07-25 |  | 2023-07-26 | 2023-07-28 | CD//Mohidi Jaan | 2023-07-26 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230726 | DU00002040513 |  |  |  |  | 2023-08-18 |  | TOWER
S00973 | S097A_S00973OD_LDGJELATABUMI | Sabah |  | Decomm |  | 2023Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-06-20 |  |  |  | 2023-06-24 |  | 2023-08-14 | 2023-09-08 | CD//Ray Amos | 2023-08-10 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0009/Celcom Digi_RAN-GTSB-Standard PR TSS DECOMM-Sabah-20231129 | DU00002040514 |  |  |  |  | 2024-03-14 |  | TOWER
S00457 | S110B_S00457OD_TMNMEGAHJAYA | Sabah |  | Decomm |  | 2023Q4 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-06-12 |  |  |  | 2023-06-14 |  | 2023-06-22 | 2023-08-30 | CD//Mohidi Jaan | 2023-06-22 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230622 | DU00002040515 |  |  |  |  | 2023-10-10 |  | BOOM
S00635 | S097A_S00635OD_IOIBATURONG2 | Sabah |  | Decomm |  | 2023Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-06-16 |  |  |  | 2023-06-24 |  | 2023-08-03 | 2023-10-27 | CD//Ray Amos | 2023-08-03 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0009 | DU00002040516 |  |  |  |  | 2023-11-07 |  | TOWER
S00560 | S110A_S00560OD_TGBTKERAMA | Sabah |  | Decomm |  | 2023Q4 | AD | YPTT | 4.6 TSSR Approved |  | 2023-07-13 |  |  |  | 2023-07-24 |  | 2023-07-27 | 2023-08-14 | CD//Mohidi Jaan | 2023-07-27 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0008 | DU00002040517 |  | 20230801: unclear cabinet photo |  |  | 2023-12-06 |  | TOWER
Q00953 | Q132B_Q00953OD_JLNPANTAIMYY | Sarawak |  | Decomm |  | 2023Q4 | SH | Magicell | 4.6 TSSR Approved |  | 2023-06-27 |  |  |  | 2023-07-18 |  | 2023-07-24 | 2023-08-06 | CD//John | 2023-07-25 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002040518 |  |  |  |  | 2025-06-17 |  | MONOPOLE
S00231 | S110A_S00231OD_TAWAUBO | Sabah |  | Decomm |  | 2023Q4 | AD | AllStar | 4.6 TSSR Approved |  | 2023-08-24 |  |  |  | 2023-09-10 |  | 2023-09-11 | 2023-09-29 | CD//Mohidi Jaan | 2023-09-11 | Celcom Digi_RAN-Allstar-TSS-Sabah-20230608-0004 | DU00002040519 |  |  |  |  | 2023-09-21 |  | BOOM
S01439 | S110C_S01439OD_T3_KM50KALABAKANNABAWAN | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040520 | [6 empty] | TOWER
Q01808 | Q116A_Q01808OD_LDGSEPAKAU | Sarawak | 9124K | Swap |  | 2023Q3 | HQ 1 | Datasco | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-19 |  | 2023-05-23 |  | Closed | 2023-05-25 | 2023-07-05 | CD//John | 2023-05-25 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230516-0006 | DU00002040521 |  |  | 2024-04-26 | 2024-04-18 |  | Tower | RAMO | 30 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
Q01755 | Q118B_Q01755OD_TMNMATAHARI | Sarawak | 9119K | Swap |  | 2023Q3 | BY | AllStar | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-19 |  | 2023-05-24 |  | Closed | 2023-05-29 | 2023-05-30 | CD//John | 2023-05-30 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230516-0005 | DU00002040522 |  |  | 2023-12-18 | 2023-12-12 |  |  | RAPID ASSEMBLY POLE (RAPOLE) | 30 | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle Celcom all RRU&BBU |  | 2
S01706 | Kg Sigatal Lama | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040523 | [6 empty] | 3LEGGED
S00332 | S097A_S00332OD_CB_PANGKALANMADAI | Sabah |  | Decomm |  | 2023Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-06-22 |  |  |  | 2023-06-25 |  | 2023-06-27 | 2023-10-04 | CD//Ray Amos | 2023-06-28 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0009 | DU00002040524 |  |  |  |  | 2024-05-13 |  | TOWER
S00245 | S110C_S00245OD_BROMAS | Sabah |  | Decomm |  | 2023Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-06-12 |  |  |  | 2023-06-13 |  | 2023-06-15 | 2023-07-28 | CD//Mohidi Jaan | 2023-06-15 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0009/0612Sabah-GTSB-BOQ Template (template) | DU00002040525 |  |  |  |  | 2023-11-07 |  | GUYED MAST
S00991 | S099A_S00991OD_T3_KGKEBULU | Sabah | 7142P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN->Swap | 2023Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2025-03-25 | 2025-04-09 |  | 2025-04-12 |  | Under Approval | 2025-04-14 | 2025-05-02 | CD//Sharidah | 2025-04-22 | SQ202504080105 - YPTT | DU00002040526 |  |  | 2025-07-06 | 2025-06-10 |  | Tower | TOWER | 76 | Add R8852E S9000x3+R8894E M1821x4, Dismantle | 0 | 2
Q02034 | Q118B_Q02034OD_T3_COASTALHIGHWAYPLANTATIONCAMP4 | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040527 | [6 empty] | 3LEGGED
S00559 | S110B_S00559OD_CB_BUKIT700 | Sabah |  | Decomm |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-07-25 |  |  |  | 2023-10-04 |  | 2023-10-04 | 2023-11-18 | CD//Mohidi Jaan | 2023-10-04 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006/0612Sabah-Datasco-BOQ Template (template) | DU00002040528 |  |  |  |  | 2023-12-06 |  | TOWER
Q02032 | COASTAL HIGHWAY PLANTATION CAMP 2 | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | N/A - no need PR for MOCN Decomm | DU00002040529 | [6 empty] | 3LEGGED
Q01116 | Q118B_Q01116OD_RHMABONG | Sarawak | 9091K | Swap |  | 2023Q3 | BY | YPTT | 4.6 TSSR Approved |  | 2023-05-23 | 2023-06-02 |  | 2023-06-13 |  | Closed | 2023-06-13 | 2023-06-21 | CD//John | 2023-06-21 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20230524-0002 | DU00002040530 |  |  | 2023-11-11 | 2023-11-06 |  | Tower | 3LEGGED | 76 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
S00593 | S110B_S00593OD_RANGGU | Sabah |  | Decomm |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-08-04 |  |  |  | 2023-08-03 |  | 2023-08-07 | 2023-09-01 | CD//Mohidi Jaan | 2023-08-07 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006/0612Sabah-Datasco-BOQ Template (template) | DU00002040531 |  |  |  |  | 2023-11-18 |  | TOWER
Q01738 | Q118B_Q01738OD_PEARLGARDEN | Sarawak | 9114K | Swap |  | 2023Q3 | BY | South Pacific | 4.6 TSSR Approved |  | 2023-05-15 | 2023-05-19 |  | 2023-05-26 |  | Closed | 2023-05-31 | 2023-06-08 | CD//John | 2023-06-01 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230512-0001 | DU00002040532 |  |  | 2023-12-20 | 2023-12-11 |  | Lampole | RAPID ASSEMBLY POLE (RAPOLE) | 31m | Add R9264H M901821 x3 + R9264M M1821 x2,Dismantle Celcom all RRU&BBU |  | 12
S00318 | S090B_S00318OD_PULUTAN | Sabah |  | Decomm |  | 2023Q3 | MS | Datasco | 4.6 TSSR Approved |  | 2023-07-17 |  |  |  | 2023-07-25 |  | 2023-07-31 | 2023-08-23 | CD//Mohidi Jaan | 2023-08-01 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006 | DU00002040533 |  | 20230801: uncompleted tx info, cisco photo missing |  |  | 2023-09-12 |  | TOWER
Q01511 | Q124F_Q01511OD_9RESIDENCE | Sarawak |  | Decomm |  | 2023Q4 | ZB | South Pacific | 4.6 TSSR Approved |  | 2024-02-03 |  |  |  | 2024-02-05 |  | 2024-02-05 | 2024-03-21 | CD//John | 2024-02-07 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230919/0612Sarawak-South Pacific-BOQ Template (template) | DU00002040534 |  |  |  |  | 2024-06-06 |  | RAPID ASSEMBLY POLE (RAPOLE)
S01676 | Kg Sumabi | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040535 | [6 empty] | TOWER
Q01260 | Q132C_Q01260OD_VISTAPDANA | Sarawak |  | Decomm |  | 2023Q4 | SH | Trintel | 4.6 TSSR Approved |  | 2023-06-26 |  |  |  | 2023-08-03 |  | 2023-08-03 | 2023-08-18 | CD//John | 2023-08-03 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230622/Celcom Digi_RAN-Trintel-TSS DECOMM-Sarawak-20231130 | DU00002040536 |  |  |  |  | 2025-01-28 |  | POLE
S00979 | S097A_S00979OD_T3_LADANGADC | Sabah | 7046K | Swap |  | 2023Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-06-19 | 2023-06-22 |  | 2023-06-24 |  | Closed | 2023-07-20 | 2023-08-01 | CD//Ray Amos | 2023-08-01 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0010 | DU00002040537 |  |  | 2023-09-27 | 2023-09-22 |  | Tower | TOWER | 75 | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle Celcom all RRU&BBU |  | 1
Q01940 | Q124F_Q01940OD_BORNEOSAMARIANGWATERPARK | Sarawak | 9139K | Swap |  | 2023Q4 | HQ 3 | Datasco | 4.6 TSSR Approved |  | 2023-06-19 | 2023-06-26 |  | 2023-06-28 |  | Closed | 2023-07-03 | 2023-07-13 | CD//John | 2023-07-12 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 - Copy | DU00002040538 |  |  | 2025-04-27 | 2025-04-09 |  | Tower | 3LEGGED | 45 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
S00223 | MTANDRASSY | Sabah |  | Decomm |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-07-12 |  |  |  | 2023-08-10 |  | 2023-08-15 | 2023-09-29 | CD//Mohidi Jaan | 2023-08-15 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006 | DU00002040539 |  | 18/8: wrong proposal |  |  | 2023-10-13 |  | TOWER
S01702 | Kg Kuyoh | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040540 | [6 empty] | 3LEGGED
Q00742 | Q116A_Q00742OD_SGASAP | Sarawak |  | Decomm |  | 2023Q3 | SH | Datasco | 4.6 TSSR Approved |  | 2024-03-20 |  |  |  | 2024-03-20 |  | 2024-03-20 | 2025-10-16 | CD//John | 2024-03-21 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009 | DU00002040541 |  |  |  |  | 2024-05-23 |  | TOWER
S00289 | S090B_S00289OD_PERKASAKENINGAU | Sabah |  | Decomm |  | 2023Q3 | MS | South Pacific | 4.6 TSSR Approved |  | 2023-08-03 |  |  |  | 2023-08-07 |  | 2023-08-09 | 2023-09-16 | CD//Mohidi Jaan | 2023-08-10 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230804 | DU00002040542 |  |  |  |  | 2024-02-23 |  | BOOM
S01534 | kpg sanang | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | MS |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002040543 | [6 empty] | TOWER
Q01880 | Q132B_Q01880OD_DESAINDAH4 | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2023Q4 | SH | Magicell | 4.6 TSSR Approved |  | 2023-06-25 |  |  |  | 2023-07-11 |  | 2023-07-24 | 2023-08-08 | CD//John | 2023-07-25 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002040544 |  |  |  |  | 2025-06-26 |  | RAPID ASSEMBLY POLE (RAPOLE)
S00254 | S110B_S00254OD_TMSINONN | Sabah |  | Decomm |  | 2023Q4 | MS | Seri Pancar | 4.6 TSSR Approved |  | 2024-01-22 |  |  |  | 2024-01-22 |  | 2024-01-22 | 2024-02-15 | CD//Mohidi Jaan | 2024-01-22 | Celcom Digi_RAN-Seri Pancar-Standard PR TSS-Sabah-20240124 | DU00002040545 |  |  |  |  | 2024-05-21 |  | TOWER
S01443 | S106A_S01443OD_T3_PULAUDANAWAN | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040546 | [6 empty] | 3LEGGED
Q01079 | Q132C_Q01079IB_IMPERIALMYYID | Sarawak |  | Decomm |  | 2023Q4 | SH | Trintel | 4.6 TSSR Approved |  | 2023-09-25 |  |  |  | 2023-09-27 |  | 2023-09-27 | 2023-10-04 |  | 2023-09-27 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230919/Celcom Digi_RAN-Trintel-TSS DECOMM-Sarawak-20231130 | DU00002040547 |  |  |  |  | 2023-12-20 |  | IN-BUILDING
Q01783 | Q132C_Q01783IB_PERMAISURIMALLID | Sarawak |  | Decomm |  | 2023Q4 | SH | Trintel | 4.6 TSSR Approved |  | 2023-09-26 |  |  |  | 2023-09-26 |  | 2023-09-26 | 2023-10-04 |  | 2023-09-26 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230919 | DU00002040548 |  |  |  |  | 2024-01-22 |  | IN-BUILDING
Q01292 | Q118B_Q01292OD_SPGSEBIEW | Sarawak |  | Decomm |  | 2023Q3 | SH | NR services | 4.6 TSSR Approved |  | 2023-08-08 |  |  |  | 2023-09-08 |  | 2023-09-08 | 2023-10-21 | CD//John | 2023-09-08 | Celcom Digi_RAN-NR Services-TSS-Sarawak-20230823/0612Sarawak-NR services-BOQ Template (template) | DU00002040549 |  |  |  |  | 2025-09-20 |  | LAMP_POLE
S01106 | S110B_S01106OD_SKTITINGAN | Sabah |  | Decomm |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-08-28 |  |  |  | 2023-09-06 |  | 2023-09-08 | 2023-09-29 | CD//Ray Amos | 2023-09-11 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006 | DU00002040550 |  |  |  |  | 2023-10-19 |  | RAPID ASSEMBLY POLE (RAPOLE)
Q02029 | RUMAHLIBAU | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | N/A - no need PR for MOCN Decomm | DU00002040551 | [6 empty] | 3LEGGED
Q00821 | Q132B_Q00821OD_IKBNMYY | Sarawak | 9083K | Swap |  | 2023Q4 | AD | Datasco | 4.6 TSSR Approved |  | 2023-07-08 | 2023-07-12 |  | 2023-07-17 |  | Closed | 2023-07-20 | 2023-07-21 | CD//John | 2025-04-26 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 - Copy | DU00002040552 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed | 2025-10-23 | 2025-10-21 |  |  | WATER TANK |  | Add R8862A S9000x3+R8894E M1821x3+R8862A S2601x3, Dismantle | 0 | 0
Q01381 | Q124B_Q01381OD_TMNKOMPODIM | Sarawak | 9103K | Swap |  | 2023Q4 | ZB | South Pacific | 4.6 TSSR Approved |  | 2023-08-04 | 2023-08-11 |  | 2023-08-17 |  | Closed | 2023-08-18 | 2023-09-11 | CD//John | 2023-08-18 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230807 | DU00002040553 |  |  | 2023-09-23 | 2023-09-20 |  | Lampole | RAPID ASSEMBLY POLE (RAPOLE) | 25 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 1
S00256 | S110A_S00256OD_TMNRIA | Sabah |  | Decomm |  | 2023Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-08-04 |  |  |  | 2023-08-09 |  | 2023-08-14 | 2023-09-16 | CD//Mohidi Jaan | 2023-08-14 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230807 | DU00002040554 |  |  |  |  | 2023-09-11 |  | TOWER
Q01043 | Q132C_Q01043OD_BINTANGJAYA | Sarawak |  | Decomm |  | 2023Q4 | SH | CCSMY | 4.6 TSSR Approved |  | 2023-07-18 |  |  |  | 2023-09-13 |  | 2023-09-13 | 2023-10-13 | CD//John | 2023-09-13 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230613-0007/Celcom Digi_RAN-CCSMY-TSS DECOMM-Sarawak-20230828 | DU00002040555 |  | 5/9: uncompleted info & photos |  |  | 2025-01-27 |  | AESTHETIC MONOPOLE
Q01810 | Q118B_Q01810OD_PKNNGPANDAN | Sarawak | 9126K | Swap |  | 2023Q3 | BY | YPTT | 4.6 TSSR Approved |  | 2023-05-23 | 2023-05-26 |  | 2023-06-01 |  | Rectificating | 2023-06-02 | 2023-06-11 | CD//John | 2023-06-11 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20230524-0002 | DU00002040556 |  |  | 2023-11-21 | 2023-11-02 |  | Tower | TOWER | 60 | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle Celcom all RRU&BBU |  | 2
S01284 | Kg. Ulu Kimanis | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | AD |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002040557 | [6 empty] | TOWER
Q01739 | Q118B_Q01739OD_KIDURONG4 | Sarawak |  | Decomm |  | 2023Q3 | ZB | Satellite | 4.6 TSSR Approved |  | 2023-06-25 |  |  | 2023-06-27 |  | Closed | 2023-07-18 |  | CD//John | 2023-08-08 | Celcom Digi_RAN-Satellite-TSS-Sarawak-20231009/Celcom Digi_RAN-Satellite-TSS DECOMM MW-Sarawak-20240419/0920CD-Sarawak-CCSMY-BOQ Template (old contract)/CelcomDigi_RAN_Satellite_PR_TSS_Sarawak_20241018 | DU00002040558 |  | 1/9:wrong proposal |  |  | 2023-12-10 |  | RAPID ASSEMBLY POLE (RAPOLE)
Q01898 | Q124B_Q01523OD_THEHUBKCH | Sarawak |  | Decomm |  | 2023Q4 | SH | South Pacific | 4.6 TSSR Approved |  | 2023-06-21 |  |  |  | 2023-08-04 |  | 2023-08-07 | 2023-10-06 | CD//John | 2023-08-08 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230622/0612Sarawak-South Pacific-BOQ Template (template) | DU00002040559 |  | 24/8: uncompleted info & photos FE all tx info & photos are missing |  |  | 2023-11-17 |  | RAPID ASSEMBLY POLE (RAPOLE)
S01699 | Kg Sebulu | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040560 | [6 empty] | 3LEGGED
Q01753 | Q118B_Q01753OD_BTULNG2 | Sarawak |  | Decomm |  | 2023Q3 | SH | South Pacific | 4.6 TSSR Approved |  | 2023-05-22 |  |  |  | 2023-06-09 |  | 2023-06-09 | 2023-09-19 | CD//John | 2023-06-10 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230512-0001/0612Sarawak-South Pacific-BOQ Template (template)/0626Sarawak-South Pacific-BOQ Template (template) | DU00002040561 |  | 27/7: Unclear photos 2023-06-26 Missing TX photos and info |  |  | 2025-11-10 |  | RAPID ASSEMBLY POLE (RAPOLE)
S00694 | S110B_S00694OD_CB_KGWAKUBA | Sabah |  | Decomm |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-08-03 |  |  |  | 2023-08-11 |  | 2023-08-14 | 2023-10-04 | CD//Ray Amos | 2023-08-14 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006/0612Sabah-Datasco-BOQ Template (template) | DU00002040562 |  | 18/8: wrong proposal + fe info & photos are missing |  |  | 2023-12-06 |  | TOWER
S02015 | S106A_S02015OD_KGSEJATI | Sabah |  | Decomm |  | 2023Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-07-14 |  |  |  | 2023-07-17 |  | 2023-08-03 | 2023-08-23 | CD//Ray Amos | 2023-08-03 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230726 | DU00002040563 |  |  |  |  | 2023-10-27 |  | MONOPOLE
S01659 | S110A_S01659OD_JLNDOMINIC | Sabah |  | Decomm |  | 2023Q4 | AD | AllStar | 4.6 TSSR Approved |  | 2023-08-12 |  |  |  | 2023-08-22 |  | 2023-08-17 | 2023-09-16 | CD//Affendi | 2023-08-18 | Celcom Digi_RAN-Allstar-TSS-Sabah-20230608-0004/Celcom Digi_RAN-Allstar-TSS DECOMM-Sabah-20231206 | DU00002040564 |  |  |  |  | 2023-10-04 |  | LAMP_POLE
S01530 | Kampung Maatol Sook | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | MS |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002040565 | [6 empty] | TOWER
S01327 | S097A_S01327OD_MADAICAVE | Sabah | 7059K | Swap |  | 2023Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-06-20 | 2023-06-26 |  | 2023-06-28 |  | Closed | 2023-07-03 | 2023-07-28 | CD//Mohidi Jaan | 2023-07-24 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0010 | DU00002040566 |  |  | 2023-09-27 | 2023-09-20 |  | Tower | RAPID ASSEMBLY POLE (RAPOLE) | 60M | Add R8852E S9000 x3 + R8894E M1821 x3
Q01921 | Q132C_Q01921OD_101COMMMYY | Sarawak | 9138K | Swap |  | 2023Q4 | SH | Datasco | 4.6 TSSR Approved |  | 2023-06-14 | 2023-06-21 |  | 2023-06-22 |  | Rectificating | 2023-08-01 | 2023-08-02 | CD//John | 2023-08-02 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 - Copy | DU00002040567 |  |  | 2025-07-06 | 2025-04-15 |  | Lampole | RAPID ASSEMBLY POLE (RAPOLE) | 30 | Add R9264H M901821 x3,Dismantle | 0 | 0
Q00756 | Q124F_Q00756OD_STDKCH | Sarawak |  | Decomm |  | 2023Q4 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-07-10 |  |  |  | 2023-07-13 |  | 2023-07-25 | 2024-02-15 | CD//John | 2023-07-28 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002040568 |  |  |  |  | 2023-10-09 |  | MONOPOLE
S00286 | S099A_S00286OD_TMNABAWANAEPEATER | Sabah |  | Decomm |  | 2023Q3 | MS | Datasco | 4.6 TSSR Approved |  | 2023-08-07 |  |  |  | 2023-08-10 |  | 2023-11-06 | 2023-12-22 | CD//Mohidi Jaan | 2023-11-06 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230818/0612Sabah-Datasco-BOQ Template (template) | DU00002040569 |  |  |  |  | 2024-02-23 |  | TOWER
S01602 | S090A_S01602OD_CB_KGSENAGANG | Sabah | 7062K | Swap |  | 2023Q3 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-05-26 | 2023-06-14 |  | 2023-06-19 |  | Closed | 2023-06-19 | 2023-06-24 | CD//Mohidi Jaan | 2023-06-24 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230516-0001 | DU00002040570 |  |  | 2023-07-26 | 2023-07-20 |  | Tower | TOWER | 60 | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle Celcom all RRU&BBU |  | 1
Q01675 | Q128A_Q01675OD_CB_KGSRIKANDUNG | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | N/A - no need PR for MOCN Decomm | DU00002040571 | [6 empty] | 3LEGGED
S01779 | FC1_108 Pulau Bum Bum - Kg Igang-Igang | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 |  | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002040572 | [6 empty] | TOWER
Q00901 | Q132B_Q00901OD_DPSSENADIN | Sarawak |  | Decomm |  | 2023Q4 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-07-04 |  |  |  | 2023-07-06 |  | 2023-07-26 | 2023-09-23 | CD//John | 2023-07-28 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002040573 |  | 1/9: uncompleted info |  |  | 2025-10-25 | In-Building System | BOOM | 6M
S01601 | S110B_S01601OD_BATU4.5TAWAU | Sabah |  | Decomm |  | 2023Q4 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-06-15 |  |  |  | 2023-06-15 |  | 2023-06-22 | 2023-07-21 | CD//Ray Amos | 2023-06-23 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230622 | DU00002040574 |  |  |  |  | 2023-10-16 |  | TOWER
S00226 | S110B_S00226OD_MTXTWU | Sabah | 7019K | Swap |  | 2023Q4 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-07-11 | 2023-07-14 |  | 2023-07-20 |  | Closed | 2023-07-20 | 2023-07-25 | CD//Jahganathan | 2023-07-21 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230612-0004 | DU00002040575 |  |  | 2023-10-16 | 2023-09-04 |  |  | TOWER | 76 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 23
S00258 | S110A_S00258OD_KGTITINGAN | Sabah |  | Decomm |  | 2023Q4 | AD | Datasco | 4.6 TSSR Approved |  | 2023-07-25 |  |  |  | 2023-08-02 |  | 2023-08-14 | 2023-09-16 | CD//Ray Amos | 2023-08-14 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006 | DU00002040576 |  |  |  |  | 2023-10-10 |  | BOOM
S00596 | S099A_S00596OD_CB_SOOK | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2023Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-07-12 |  |  |  | 2023-08-07 |  | 2023-08-09 | 2023-09-29 | CD//Jahganathan | 2023-08-09 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230608-0007 | DU00002040577 |  |  |  |  | 2025-08-21 |  | TOWER
S00232 | S110B_S00232OD_FUJIMART | Sabah |  | Decomm |  | 2023Q4 | MS | YPTT | 4.6 TSSR Approved |  | 2023-07-18 |  |  |  | 2023-07-31 |  | 2023-08-02 | 2023-10-04 | CD//Mohidi Jaan | 2023-08-02 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0008 | DU00002040578 |  | 2/8: TX INFO MISSING & IDU LABEL MISSING NE |  |  | 2023-11-10 |  | BOOM
S00442 | S110B_S00442OD_CB_LDGLEELOYSEN | Sabah |  | Decomm |  | 2023Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-07-08 |  |  |  | 2023-07-10 |  | 2023-07-25 | 2023-08-14 | CD//Mohidi Jaan | 2023-07-25 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230726 | DU00002040579 |  | 20230731 : 1. 2nd idu info info missing, 2. NE idu labelling missing, 3. FE photos & info missing |  |  | 2023-10-31 |  | TOWER
Q00950 | Q124F_Q00950OD_TMNHIJRAH | Sarawak |  | Decomm |  | 2023Q4 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-08-02 |  |  |  | 2023-08-03 |  | 2023-08-03 | 2023-09-19 | CD//John | 2023-08-03 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 | DU00002040580 |  | uncompleted info & phoots |  |  | 2023-09-30 |  | MONOPOLE
Q01754 | Q118B_Q01754OD_KIDURONGCLUB | Sarawak | 9118K | Swap |  | 2023Q3 | BY | South Pacific | 4.6 TSSR Approved |  | 2023-05-19 | 2023-06-08 |  | 2023-06-12 |  | Closed | 2023-06-13 | 2023-06-19 | CD//John | 2023-06-19 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230512-0001 | DU00002040581 |  |  | 2023-11-30 | 2023-11-13 |  | Monopole | RAPID ASSEMBLY POLE (RAPOLE) | 30m | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
S01438 | S110C_S01438OD_T3_KM45KALABAKANNABAWAN | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040582 | [6 empty] | TOWER
Q00898 | Q124F_Q00898OD_JLNBANGAU | Sarawak |  | Decomm |  | 2023Q4 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-06-23 |  |  |  | 2023-06-27 |  | 2023-07-25 | 2023-09-08 | CD//John | 2023-07-25 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622/0612Sarawak-Datasco-BOQ Template (template) | DU00002040583 |  | 28/8: uncompleted photos & info FE all tx info & photos are missing |  |  | 2023-10-11 |  | MINARET
S01218 | S110A_S01218OD_SMKTAWAU | Sabah |  | Decomm |  | 2023Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-07-20 |  |  |  | 2023-07-21 |  | 2023-08-01 | 2023-08-30 | CD//Ray Amos | 2023-08-01 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230726 | DU00002040584 |  | 2/8: UNCOMPLTED LL INFO |  |  | 2023-10-02 |  | MONOPOLE
Q01288 | Q132B_Q01288OD_SAMLINGBARAMAS | Sarawak | 9099K | Swap |  | 2023Q4 | HQ 3 | AllStar | 4.6 TSSR Approved |  | 2023-06-16 | 2023-06-22 |  | 2023-06-27 |  | Closed | 2023-07-03 | 2023-07-05 | CD//John | 2023-07-04 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230608-0006 | DU00002040585 |  |  | 2025-06-28 | 2025-04-15 |  | Guide mast | RAMO | 30 | Add R8852E S9000 x3 + R8894E M1821 x3
S00998 | S090B_S00998OD_T3_KGKEPAYANLAMA | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040586 | [6 empty] | TOWER
S00227 | S110C_S00227OD_KALABAKAN | Sabah |  | Decomm |  | 2023Q3 | MS | Futong | 4.6 TSSR Approved |  | 2023-06-09 |  |  |  | 2023-06-22 |  | 2023-06-12 | 2023-07-21 | CD//Mohidi Jaan | 2023-06-13 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009 | DU00002040587 |  |  |  |  | 2023-10-09 |  | GUYED MAST
S00652 | S110C_S00652OD_LUASONGJUNCTION | Sabah |  | Decomm |  | 2023Q3 | MS | Futong | 4.6 TSSR Approved |  | 2023-07-07 |  |  |  | 2023-07-08 |  | 2023-07-20 | 2023-08-08 | CD//Mohidi Jaan | 2023-07-20 | Celcom Digi_RAN-Futong-TSS-Sabah-20230531-0008 | DU00002040588 |  | 20230731 : FE photos & info missing |  |  | 2023-12-06 |  | TOWER
S01333 | S090B_S01333OD_TAMANKALI | Sabah |  | Decomm |  | 2023Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-07-12 |  |  |  | 2023-08-05 |  | 2023-08-09 | 2023-10-21 | CD//Ray Amos | 2023-08-09 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230608-0007 | DU00002040589 |  | 21/8: digi cabinet info & photos are missing |  |  | 2023-10-17 |  | RAPID ASSEMBLY POLE (RAPOLE)
Q00758 | VQ_LDGSEGARMAS | Sarawak | 9079K | Swap | Swap->Site Out->Swap->On Hold->Swap | 2027 |  | Magicell | 2.2 Pending ETSS Resubmission - Subcon |  | 2025-07-26 |  |  |  |  | To be Submitted |  |  | CD//John |  | SQ202512241018-Magicell | DU00002040590 | [6 empty] | BOOM |  | Add R9264H M901821x3, Dismantle | 0 | 0
Q01809 | Q118B_Q01809OD_LDGSAUJANADIV | Sarawak | 9125K | Swap | Swap->Site Out | 2023Q3 | BY | Magicell | 4.6 TSSR Approved |  | 2023-05-15 | 2023-05-19 |  | 2023-05-23 |  | Under Approval | 2023-05-31 | 2023-07-25 | CD//John | 2023-06-02 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230516-0008 | DU00002040591 |  |  | 2025-09-21 | 2025-09-18 |  | Tower | RAMO | 30 | Add R9264H M901821x3, Dismantle | 0 | 0
Q01424 | Q116A_Q01424OD_MN_SGASSEP | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040592 | [6 empty] | 3LEGGED
S01433 | S110C_S01433OD_T3_KM30KALABAKANNABAWAN | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040593 | [6 empty] | 3LEGGED
S00381 | S099A_S00381OD_CB_KGBATULUNGUYAN | Sabah |  | Decomm |  | 2023Q3 | MS | South Pacific | 4.6 TSSR Approved |  | 2023-07-21 |  |  |  | 2023-07-24 |  | 2023-07-26 | 2023-09-01 | CD//Mohidi Jaan | 2023-08-02 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230726 | DU00002040594 |  |  |  |  | 2023-11-13 |  | TOWER
Q01655 | Q118B_Q01655OD_KGSGPLANLOT | Sarawak |  | Decomm |  | 2023Q3 | SH | AllStar | 4.6 TSSR Approved |  | 2023-08-14 |  |  | 2023-08-14 |  | Closed | 2023-08-15 | 2023-09-01 | CD//John | 2023-08-15 | 0612Sarawak-AllStar-BOQ Template (template)/0626Sarawak-Allstar-BOQ Template (template) | DU00002040595 |  | 24/8: uncompleted info & photos FE info & photos are missing |  |  | 2025-04-21 |  | RAPID ASSEMBLY POLE (RAPOLE)
X40005 | S106A_X40005OD_DCABINDWNMSYRKTSEMPORNA | Sabah | 7067K | Site Out (Swap) | Swap->Site out->Site Out (Swap) | 2023Q4 | MS | YPTT | [SiteOut]- 1.0 Pending Survey - Subcon | [6 empty] | To be Submitted |  |  | CD//Mohidi Jaan |  |  | DU00002040596 | [6 empty] | DCABIN
S00663 | S099A_S00663OD_SLDBPLANTATION | Sabah | 7291P | Swap | Swap->TBD->Swap->On Hold->Swap | 2023Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2023-05-15 | 2023-05-23 |  | 2023-05-30 |  | Closed | 2023-06-01 | 2023-06-13 | CD//Ray Amos | 2023-06-13 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230508-0005 | DU00002040597 |  |  | 2023-07-25 | 2023-07-22 |  | Tower | TOWER | 60 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
S01432 | S110C_S01432OD_T3_KM60KALABAKANNABAWAN | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040598 | [6 empty] | 3LEGGED
S00982 | S110B_S00982OD_T3_LADANGLKSK | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040599 | [6 empty] | TOWER
S01700 | Kg Tinaduk | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040600 | [6 empty] | 3LEGGED
S00395 | S106A_S00395OD_SMKBUMBUM | Sabah |  | Decomm |  | 2023Q4 | MS | Futong | 4.6 TSSR Approved |  | 2023-07-13 |  |  |  | 2023-08-01 |  | 2023-08-03 | 2023-08-23 | CD//Mohidi Jaan | 2023-08-03 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009/0612Sabah-Futong-BOQ Template (template) | DU00002040601 |  |  |  |  | 2023-10-09 |  | TOWER
Q00900 | Q124F_Q00900OD_JLNCAHAYADAMAI | Sarawak |  | Decomm |  | 2023Q4 | ZB | Trintel | 4.6 TSSR Approved |  | 2023-07-20 |  |  |  | 2023-08-14 |  | 2023-08-15 | 2023-08-24 | CD//John | 2023-08-18 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230622/Celcom Digi_RAN-Trintel-TSS DECOMM-Sarawak-20231130 | DU00002040602 |  | 22/8: antenna photos are missing |  |  | 2023-11-30 |  | MINARET
Q01797 | Q124B_Q01797OD_KUBAHRIA2 | Sarawak |  | Decomm |  | 2023Q4 | SH | Trintel | 4.6 TSSR Approved |  | 2023-07-21 |  |  |  | 2023-08-08 |  | 2023-08-08 | 2023-09-01 | CD//John | 2023-08-09 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230622/Celcom Digi_RAN-Trintel-TSS DECOMM-Sarawak-20231130 | DU00002040603 |  |  |  |  | 2023-10-03 |  | RAPID ASSEMBLY POLE (RAPOLE)
S00891 | S099A_S00891OD_KGMALIMASOOK | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2023Q3 | MS | South Pacific | 4.6 TSSR Approved |  | 2023-07-21 |  |  |  | 2023-07-25 |  | 2023-07-26 | 2023-09-23 | CD//Ray Amos | 2023-08-01 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230726 | DU00002040604 |  | 27/7: NE & FE wrong photos & info missing |  |  | 2024-01-25 |  | RAPID ASSEMBLY POLE (RAPOLE)
S00977 | S106A_S00977OD_LADANGWINSOME | Sabah |  | Decomm |  | 2023Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-07-10 |  |  |  | 2023-07-12 |  | 2023-08-01 | 2023-08-30 | CD//Ray Amos | 2023-08-07 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230726/0612Sabah-GTSB-BOQ Template (template) | DU00002040605 |  |  |  |  | 2023-10-19 |  | TOWER
S01845 | KG.TARAPULI | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 |  | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002040606 | [6 empty] | 3LEGGED
S01320 | S090B_S01320OD_BINAONG | Sabah | 7058K | Swap |  | 2023Q3 | AD | Datasco | 4.6 TSSR Approved |  | 2023-05-26 | 2023-07-10 |  | 2023-07-13 |  | Closed | 2023-07-13 | 2023-07-14 | CD//Mohidi Jaan | 2023-07-14 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230508-0004 | DU00002040607 |  |  | 2023-07-23 | 2023-07-21 |  | Monopole | RAPID ASSEMBLY POLE (RAPOLE) | 30m | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 23
S01686 | Kg Dumbun | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | MS |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002040608 | [6 empty] | 3LEGGED
S00668 | S097A_S00668OD_CB_SPGKUNAK | Sabah |  | Decomm |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-06-19 |  |  |  | 2023-06-21 |  | 2023-06-23 | 2023-09-16 | CD//Ray Amos | 2023-06-26 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0009 | DU00002040609 |  | 20230727 Missing MW info and photos |  |  | 2023-12-06 |  | TOWER
S00999 | S099A_S00999OD_T3_KGLANAS | Sabah | 7095P | Swap | Swap->Maintain USP MOCN->On Hold->Swap | 2023Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-06-06 | 2023-06-22 |  | 2023-07-03 |  | Rectificating | 2023-07-04 | 2023-07-07 | CD//Sharidah | 2025-04-26 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230508-0005 | DU00002040610 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed | 2025-07-06 | 2025-05-29 |  | Tower | TOWER | 76 | Add R8852E S9000x3+R9224E M1821x7, Dismantle | 0 | 3
Q01654 | Q132B_Q01654OD_JLNDESAINDAH2 | Sarawak |  | Decomm |  | 2023Q4 | SH | Magicell | 4.6 TSSR Approved |  | 2023-06-25 |  |  |  | 2023-07-13 |  | 2023-07-25 | 2023-08-08 | CD//John | 2023-07-26 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002040611 |  |  |  |  | 2024-12-27 |  | MONOPOLE
S01833 | FC1_110 Kg Sungai Atas | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002040612 | [6 empty] | TOWER
Q01293 | Q118B_Q01293OD_KIDURONGIND2 | Sarawak |  | Decomm |  | 2023Q3 | SH | NR services | 4.6 TSSR Approved |  | 2023-10-13 |  |  |  | 2023-10-18 |  | 2023-10-18 | 2023-12-09 | CD//John | 2023-10-22 | Celcom Digi_RAN-NR Services-TSS-Sarawak-20230823/0619Sarawak-NR services-BOQ Template (template) | DU00002040613 |  |  |  |  | 2025-09-28 |  | RAPID ASSEMBLY POLE (RAPOLE)
S00327 | S110B_S00327OD_CB_BKTFORBES | Sabah |  | Decomm |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-06-23 |  |  |  | 2023-07-10 |  | 2023-07-27 | 2024-01-18 | CD//Ray Amos | 2023-07-28 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0009 | DU00002040614 |  | 20230801: ALL tx info are missing (NE & FE) |  |  | 2023-12-06 |  | TOWER
Q01118 | Q118B_Q01118OD_T3_RHAKO | Sarawak | 9092K | Swap |  | 2023Q3 | SH | AllStar | 4.6 TSSR Approved |  | 2023-05-17 | 2023-05-20 |  | 2023-06-05 |  | Closed | 2023-06-06 | 2023-06-28 | CD//John | 2023-06-10 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230516-0005 | DU00002040615 |  |  | 2023-11-10 | 2023-11-06 |  | Tower | 3LEGGED | 76 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
S00247 | S110B_S00247OD_SHANSHUI | Sabah |  | Decomm |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-07-11 |  |  |  | 2023-07-17 |  | 2023-07-26 | 2023-08-06 | CD//Mohidi Jaan | 2023-07-26 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006 | DU00002040616 |  |  |  |  | 2024-05-13 |  | TOWER
Q01518 | Q132B_Q01518OD_DESABAHAGIAMYY | Sarawak |  | Decomm |  | 2023Q4 | ZB | YPTT | 4.6 TSSR Approved |  | 2023-09-08 |  |  |  | 2023-09-08 |  | 2023-09-08 | 2023-09-23 | CD//John | 2023-09-08 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20230622/Celcom Digi_RAN-YPTT-TSS DECOMM-Sarawak-20231128 | DU00002040617 |  |  |  |  | 2025-10-09 |  | RAMO
S00990 | S099A_S00990OD_T3_KGTULID | Sabah | 7094P | Swap | Swap->Maintain USP MOCN->On Hold->Maintain USP MOCN->On Hold->Swap | 2023Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-20 |  | 2023-07-03 |  | Under Approval | 2023-07-04 | 2023-07-06 | CD//Hannah | 2025-08-24 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230508-0005 | DU00002040618 | Remarks: Solution TSSR/BOM Changed |  | 2025-09-18 | 2025-08-15 |  | Tower | TOWER | 76 | Add R8852E S9000x3+R8894E M1821x6, Dismantle | 0 | 0
Q02026 | Tegulang Settlement (Murum Hydro Settlement) | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040619 | [6 empty] | 3LEGGED
Q00941 | Q124F_Q00941OD_SEMARIANGAMAN | Sarawak |  | Decomm |  | 2023Q4 | SH | Trintel | 4.6 TSSR Approved |  | 2023-06-30 |  |  |  | 2023-07-27 |  | 2023-07-31 | 2023-08-14 | CD//John | 2023-08-08 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230622 | DU00002040620 |  | 20230807: all tx info & photos are wrong |  |  | 2023-10-09 |  | LAMP_POLE
S00727 | S110A_S00727OD_MJDRAYA | Sabah |  | Decomm |  | 2023Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-07-25 |  |  |  | 2023-07-28 |  | 2023-08-02 | 2023-08-14 | CD//Ray Amos | 2023-08-03 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230726 | DU00002040621 |  | 20230801: HW OSN 550 missing |  |  | 2023-10-17 |  | LAMP_POLE
S00283 | S090B_S00283OD_CB_APINAPIN | Sabah |  | Decomm |  | 2023Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2023-05-09 |  |  |  | 2023-05-16 |  | 2023-07-27 | 2023-09-08 | CD//Mohidi Jaan | 2023-07-27 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230608-0008 | DU00002040622 |  | 2/8; UNCOMPLETED TX INFO & PHOTOS |  |  | 2023-11-07 |  | TOWER
Q01526 | Q118B_Q01526OD_BTUCENTRAL | Sarawak |  | Decomm |  | 2023Q3 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-07-21 |  |  | 2023-07-28 |  | Closed | 2023-07-28 | 2023-11-18 | CD//John | 2023-07-28 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009/0612Sarawak-Datasco-BOQ Template (template) | DU00002040623 |  |  |  |  | 2024-08-07 |  | RAPID ASSEMBLY POLE (RAPOLE)
Q02030 | KAMPUNG MASKAT | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | N/A - no need PR for MOCN Decomm | DU00002040624 | [6 empty] | 3LEGGED
S01334 | S090B_S01334OD_SMKGUNSANAD | Sabah |  | Decomm |  | 2023Q3 | MS | South Pacific | 4.6 TSSR Approved |  | 2023-07-23 |  |  |  | 2023-07-24 |  | 2023-07-27 | 2023-08-06 | CD//Mohidi Jaan | 2023-07-27 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230726 | DU00002040625 |  |  |  |  | 2023-10-19 |  | RAPID ASSEMBLY POLE (RAPOLE)
S01159 | S106A_S01159OD_KGSIMUNUL | Sabah |  | Decomm |  | 2023Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-07-14 |  |  |  | 2023-07-17 |  | 2023-08-01 | 2023-08-14 | CD//Ray Amos | 2023-08-02 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230726/0612Sabah-GTSB-BOQ Template (template) | DU00002040626 |  |  |  |  | 2023-10-17 |  | MONOPOLE
S01434 | S110C_S01434OD_T3_KM20KALABAKANNABAWAN | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040627 | [6 empty] | 3LEGGED
S00614 | S097A_S00614OD_CB_LADANGGIRAM | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-06-16 |  |  |  | 2023-06-19 |  | 2023-07-27 | 2023-08-08 | CD//Jahganathan | 2023-08-07 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0009/Celcom Digi_RAN-GTSB-Standard PR TSS DECOMM-Sabah-20231129 | DU00002040628 |  |  |  |  | 2025-05-16 |  | TOWER
S00631 | S110B_S00631OD_BATU15APAS | Sabah |  | Decomm |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-08-01 |  |  |  | 2023-08-22 |  | 2023-08-22 | 2023-09-29 | CD//Ray Amos | 2023-08-24 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006 | DU00002040629 |  | 23/8: Uncompeted info |  |  | 2023-09-21 |  | TOWER
Q00765 | Q132B_Q00765OD_KAMPUSCURTIN | Sarawak | 9081K | Swap |  | 2027 | HQ 1 | Datasco | 4.6 TSSR Approved |  | 2023-06-28 | 2023-07-14 |  | 2023-07-20 |  | Closed | 2023-07-26 | 2023-07-27 | CD//John | 2023-07-27 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 - Copy | DU00002040630 | [5 empty] | Wall mount boom | BOOM |  | Add R8852E S9000 x3+R8894E x3,Dismantle
Q01697 | Q132A_Q01697OD_CB_RHAKAI | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | N/A - no need PR for MOCN Decomm | DU00002040631 | [6 empty] | 3LEGGED
S01843 | Kg Ulu Mosopoh | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | MS |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002040632 | [6 empty] | 3LEGGED
Y00058 | P035E_Y00058OD_POTS_PENANGFREESCHOOL | Northern |  | Decomm |  | 2023Q3 | ZA | CCSMY | 4.6 TSSR Approved |  | 2024-01-03 |  | 2025-10-30 |  | 2024-01-03 |  | 2024-01-17 |  | CD//Affendi | 2024-01-18 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002040633 |  | Missing FE Info |  |  | 2023-12-29 |  | POTS
S01017 | S110B_S01017OD_JLNBTPAYUNG | Sabah |  | Decomm |  | 2023Q4 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-06-21 |  |  |  | 2023-06-20 |  | 2023-07-24 | 2023-07-27 | CD//Jahganathan | 2023-07-24 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230622 | DU00002040634 |  |  |  |  | 2023-10-13 |  | RAMO
S01162 | S110A_S01162OD_FAJARKCC | Sabah |  | Decomm |  | 2023Q4 | AD | AllStar | 4.6 TSSR Approved |  | 2023-08-15 |  |  |  | 2023-08-22 |  | 2023-08-23 | 2023-09-29 | CD//Mohidi Jaan | 2023-08-23 | Celcom Digi_RAN-Allstar-TSS-Sabah-20230608-0004/Celcom Digi_RAN-Allstar-TSS DECOMM-Sabah-20231206 | DU00002040635 |  | 24/8: uncompleted info & photos |  |  | 2023-10-09 |  | MINI STRUCTURE
S00478 | S110C_S00478OD_CB_LUASONGHILL | Sabah |  | Decomm |  | 2023Q3 | MS | Futong | 4.6 TSSR Approved |  | 2023-10-19 |  |  |  | 2023-10-21 |  | 2023-11-06 |  | CD//Ray Amos | 2023-11-09 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009/Celcom Digi_RAN-Futong-TSS DECOMM MW-Sabah-20240419 | DU00002040636 |  |  |  |  | 2024-02-23 |  | TOWER
S00242 | S110B_S00242OD_KGKAUSING | Sabah |  | Decomm |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-06-26 |  |  |  | 2023-07-17 |  | 2023-08-08 | 2023-09-08 | CD//Mohidi Jaan | 2023-08-08 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006 | DU00002040637 |  |  |  |  | 2023-09-21 |  | TOWER
S00490 | S110C_S00490OD_CB_TMNBKTTAWAU | Sabah |  | Decomm |  | 2023Q3 | MS | Futong | 4.6 TSSR Approved |  | 2023-06-09 |  |  |  | 2023-06-22 |  | 2023-06-20 | 2023-07-21 | CD//Mohidi Jaan | 2023-06-21 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009 | DU00002040638 |  |  |  |  | 2023-10-03 |  | TOWER
S01511 | S110A_S01511OD_JLNHABIBSHEIKHTWU | Sabah |  | Decomm |  | 2023Q4 | AD | AllStar | 4.6 TSSR Approved |  | 2023-08-12 |  |  |  | 2023-08-22 |  | 2023-08-23 | 2023-09-29 | CD//Mohidi Jaan | 2023-08-23 | Celcom Digi_RAN-Allstar-TSS-Sabah-20230608-0004/Celcom Digi_RAN-Allstar-TSS DECOMM-Sabah-20231206 | DU00002040639 |  | 24/8: uncompleted info & photos |  |  | 2023-10-09 |  | MINI STRUCTURE
S00649 | S110B_S00649OD_KGTAS | Sabah |  | Decomm |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-06-26 |  |  |  | 2023-07-24 |  | 2023-08-02 | 2023-09-29 | CD//Mohidi Jaan | 2023-08-02 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006/0612Sabah-Datasco-BOQ Template (template) | DU00002040640 |  | 2/8: All tx info & photos are missing (NE & FE) |  |  | 2023-12-21 |  | TOWER
Q01305 | Q118B_Q01305OD_SACF1 | Sarawak |  | Site Out (Decomm) | Decomm->MOCN Decomm->Replacement, Site Out (Decomm) | 2023Q3 |  | Magicell | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2025-07-26 |  | 2025-08-04 |  |  | To be Submitted |  |  |  |  | SQ202507160538-Magicell | DU00002040641 |  |  |  |  | 2025-06-26 |  | RAPID ASSEMBLY POLE (RAPOLE)
S00809 | S106A_S00809OD_SEAFESTHOTEL | Sabah |  | Decomm |  | 2023Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-07-14 |  |  |  | 2023-07-18 |  | 2023-08-03 | 2023-08-23 | CD//Mohidi Jaan | 2023-08-03 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230726/0612Sabah-GTSB-BOQ Template (template) | DU00002040642 |  | 3/8: tx INFO MISISING ( DRAWING PAGES) IDU PHOTOS MISSING (FE) |  |  | 2023-11-10 |  | BOOM
S01449 | S110C_S01449OD_T3_KGGUDANG4 | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040643 | [6 empty] | TOWER
S00976 | S106A_S00976OD_T3_SGNASIP | Sabah |  | Decomm |  | 2023Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-07-07 |  |  |  | 2023-07-13 |  | 2023-07-28 | 2023-08-18 | CD//Ray Amos | 2023-07-31 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230726/0612Sabah-GTSB-BOQ Template (template) | DU00002040644 |  | 20230801: FE info & photos missing |  |  | 2024-02-07 |  | TOWER
S01444 | S110C_S01444OD_T3_PEKANKALABAKAN | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  | AllStar | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | N/A | DU00002040645 | [6 empty] | TOWER
S00237 | S110B_S00237OD_TAWAUAIRPORT | Sabah | 7238K | Swap | On Hold->Swap | 2023Q4 | AD | Datasco | 4.6 TSSR Approved |  | 2023-07-27 | 2023-10-05 |  | 2023-10-06 | 2023-07-28 | Closed | 2023-07-31 | 2023-10-06 | CD//Mohidi Jaan | 2023-09-26 | 0626Sabah-Datasco-BOQ Template (template) | DU00002040646 |  |  | 2023-10-19 | 2023-10-09 |  | Pole | MINI STRUCTURE | 6 | Add R9264M M1821 x1+R9264H M901821 x3+R8862A S2600 x4,Dismantle |  | 2
S01778 | FC1_106 Kg Iban Kuala Nansang | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q4 | AD | Datasco | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002040647 | [6 empty] | TOWER
S01532 | ladang melaka | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | MS |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002040648 | [6 empty] | TOWER
S00995 | S099A_S00995OD_KGKARAMATOIULU | Sabah | 7052K | Decomm | Swap->Decomm | 2023Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-06-07 | 2023-07-11 |  | 2023-07-18 | 2023-09-06 | Closed | 2023-07-31 | 2024-02-15 | CD//Ray Amos | 2023-08-03 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0008/0612Sabah-YPTT-BOQ Template (template) | DU00002040649 |  |  |  |  | 2023-11-18 | Tower | TOWER | 76
S01429 | S110C_S01429OD_T3_KRETAMKALABAKAN | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  | AllStar | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | N/A | DU00002040650 | [6 empty] | TOWER
Q01742 | Q132B_Q01742OD_JLNSEALINE | Sarawak |  | Decomm |  | 2023Q4 | SH | Magicell | 4.6 TSSR Approved |  | 2023-07-06 |  |  |  | 2023-07-21 |  | 2023-07-25 | 2023-08-23 | CD//John | 2023-07-26 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622/0612Sarawak-Magicell-BOQ Template (template) | DU00002040651 |  |  |  |  | 2025-06-26 |  | RAPID ASSEMBLY POLE (RAPOLE)
S01109 | S090A_S01109OD_LINKUNDAU | Sabah |  | Decomm |  | 2023Q3 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-08-03 |  |  |  | 2023-08-05 |  | 2023-08-09 | 2023-09-16 | CD//Ray Amos | 2023-08-10 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230804 | DU00002040652 |  |  |  |  | 2023-09-28 |  | MINIMAST
S00433 | S110A_S00433OD_TGBTLAUT | Sabah |  | Decomm |  | 2023Q4 | MS | YPTT | 4.6 TSSR Approved |  | 2023-07-17 |  |  |  | 2023-07-20 |  | 2023-07-25 | 2023-08-06 | CD//Jahganathan | 2023-07-26 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0008 | DU00002040653 |  |  |  |  | 2023-11-25 |  | TOWER
S00993 | S099A_S00993OD_CB_SALAROMTAKA | Sabah | 7051K | Swap |  | 2023Q3 | AD | Futong | 4.6 TSSR Approved |  | 2023-07-03 | 2023-07-04 |  | 2023-07-06 |  | Closed | 2023-07-20 | 2023-07-22 | CD//Ray Amos | 2023-07-21 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0005 | DU00002040654 |  |  | 2023-08-16 | 2023-07-25 |  | Tower | TOWER | 76 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
S01097 | S090B_S01097OD_KGBAYANGAN | Sabah |  | Decomm |  | 2023Q3 | AD | Datasco | 4.6 TSSR Approved |  | 2023-07-13 |  |  |  | 2023-07-25 |  | 2023-08-03 | 2023-09-12 | CD//Ray Amos | 2023-08-03 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006/0612Sabah-Datasco-BOQ Template (template) | DU00002040655 |  |  |  |  | 2023-09-22 |  | MONOPOLE
S00985 | S110C_S00985OD_T3_LADANGSERAYA | Sabah |  | Decomm |  | 2023Q3 | MS | Futong | 4.6 TSSR Approved |  | 2023-06-09 |  |  |  | 2023-07-27 |  | 2023-08-01 | 2023-08-30 | CD//Ray Amos | 2023-08-07 | Celcom Digi_RAN-Futong-TSS-Sabah-20230531-0008/0612Sabah-Futong-BOQ Template (template) | DU00002040656 |  |  |  |  | 2023-09-11 |  | TOWER
Q01479 | Q118B_Q01479OD_KIDURONGIND3 | Sarawak | 9107K | Swap |  | 2023Q3 | SH | AllStar | 4.6 TSSR Approved |  | 2023-05-19 | 2023-06-07 |  | 2023-06-15 |  | Closed | 2023-06-20 | 2023-06-21 | CD//John | 2023-06-21 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230516-0005 | DU00002040657 |  |  | 2025-04-24 | 2025-04-16 |  |  | RAMO | 30 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
S01508 | S110B_S01508OD_MRSMTAWAU | Sabah |  | Decomm |  | 2023Q4 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-06-21 |  |  |  | 2023-06-22 |  | 2023-07-27 | 2023-09-16 | CD//Jahganathan | 2023-08-07 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230622 | DU00002040658 |  | 2/8: Photos of mw antenna & odu missing (NE) |  |  | 2023-10-27 |  | TOWER
Q01699 | Q118B_Q01699OD_CB_PETRONASJLNCOASTAL | Sarawak | 9111K | Swap |  | 2027 | SH | YPTT | 4.6 TSSR Approved |  | 2023-05-21 | 2023-05-26 |  | 2023-05-29 |  | Closed | 2023-06-06 | 2023-06-11 | CD//John | 2023-06-11 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20230524-0002 | DU00002040659 | [6 empty] | 3LEGGED | 76 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
S00522 | S110C_S00522OD_CB_MALIAUBASIN | Sabah | 7030K | Swap | Swap->Site Out->Swap->On Hold->Swap | 2027 | AD | Futong | 4.6 TSSR Approved |  | 2023-07-08 | 2023-07-14 |  | 2023-07-21 |  | Closed | 2023-07-21 | 2023-07-22 | CD//Jahganathan | 2023-07-22 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0005 | DU00002040660 | [5 empty] | Tower | TOWER | 77 | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
Q01836 | Q118B_Q01836OD_TRADEWIND | Sarawak | 9133K | Swap |  | 2023Q3 | HQ 5 | Datasco | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-20 |  | 2023-05-23 |  | Closed | 2023-05-26 | 2023-05-27 | CD//John | 2023-05-26 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230516-0006 | DU00002040661 |  |  | 2024-03-22 | 2024-03-16 |  | Tower | TOWER | 45 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
S00616 | S106A_S00616OD_LADANGPINANG | Sabah |  | Decomm |  | 2023Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-07-08 |  |  |  | 2023-07-12 |  | 2023-07-28 | 2023-08-14 | CD//Ray Amos | 2023-07-31 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230726 | DU00002040662 |  | 20230801: 2nd idu info missing, FE info & photos missing, IDU label missing |  |  | 2023-10-27 |  | TOWER
S01445 | S106A_S01445OD_T3_KGPAKALANGAN | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040663 | [6 empty] | TOWER
S00225 | RL10083_WISMADAT | Sabah |  | Decomm |  | 2023Q4 | AD | AllStar | 4.6 TSSR Approved |  | 2023-09-06 |  |  |  | 2023-09-10 |  | 2023-09-11 | 2023-09-29 | CD//Ray Amos | 2023-09-13 | Celcom Digi_RAN-Allstar-TSS-Sabah-20230608-0004 | DU00002040664 |  |  |  |  | 2023-10-17 |  | BOOM
S00589 | S106A_S00589OD_CB_PULAUMABUL | Sabah | 7032K | Swap |  | 2023Q4 | MS | Futong | 4.6 TSSR Approved |  | 2023-07-05 | 2023-07-11 |  | 2023-07-13 |  | Closed | 2023-07-14 | 2023-07-17 | CD//Ray Amos | 2023-07-17 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0011 | DU00002040665 |  |  | 2023-08-09 | 2023-07-20 |  | Monopole | RAPID ASSEMBLY POLE (RAPOLE) | 30 | Add R8852E S9000 x2+R9264H M901821 x1+R8862A S2600 x3+A9732 M1821 x2,Dismantle | 13
Q01700 | Q118B_Q01700OD_CB_PETRONASPUNJLYOD | Sarawak |  | Decomm |  | 2023Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2023-08-02 |  |  |  | 2023-09-04 |  | 2023-09-04 | 2023-09-11 | CD//John | 2023-09-04 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230613-0009/Celcom Digi_RAN-Trintel-TSS DECOMM-Sarawak-20231130 | DU00002040666 |  | 5/9: uncomleted info |  |  | 2023-12-01 |  | TOWER
X40009 | B060B_X40009OD_STADIUM_TERTUTUP_KOMPLEKS_SUKAN | Central | 1199K | Site Out (Swap) | Swap->Site out->Site Out (Swap) | 2023Q4 | AI | YPTT | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2025-07-16 |  | 2025-07-14 |  |  | To be Submitted |  |  |  |  | SQ202506140184 | DU00002040667 | [6 empty] | MBTS
S00579 | S110C_S00579OD_BROMASCAMP | Sabah |  | Decomm |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-06-14 |  |  |  | 2023-06-26 |  | 2023-07-25 | 2023-08-06 | CD//Ray Amos | 2023-07-26 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0009/Celcom Digi_RAN-GTSB-Standard PR TSS DECOMM-Sabah-20231129 | DU00002040668 |  |  |  |  | 2023-10-27 |  | TOWER
S00607 | S090A_S00607OD_CB_TMSIGAPON | Sabah | 7033K | Swap |  | 2023Q3 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-05-25 | 2023-05-29 |  | 2023-06-02 |  | Closed | 2023-06-02 | 2023-06-07 | CD//Ray Amos | 2023-06-06 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230516-0001 | DU00002040669 |  |  | 2023-10-10 | 2023-09-06 |  | Tower | BOOM | 122 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
Q01285 | Q132B_Q01285OD_PERMYJAYA2 | Sarawak |  | Decomm |  | 2023Q4 | ZB | YPTT | 4.6 TSSR Approved |  | 2023-09-01 |  |  |  | 2023-09-01 |  | 2023-09-01 | 2023-09-19 | CD//John | 2023-09-03 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20230622/Celcom Digi_RAN-YPTT-TSS DECOMM-Sarawak-20231128 | DU00002040670 |  |  |  |  | 2025-08-26 |  | RAPID ASSEMBLY POLE (RAPOLE)
S00653 | S110C_S00653OD_T3_MEROTAIBESAR | Sabah |  | Decomm |  | 2023Q3 | MS | Futong | 4.6 TSSR Approved |  | 2023-06-09 |  |  |  | 2023-06-15 |  | 2023-06-16 | 2023-08-30 | CD//Ray Amos | 2023-06-17 | Celcom Digi_RAN-Futong-TSS-Sabah-20230531-0008/0612Sabah-Futong-BOQ Template (template) | DU00002040671 |  |  |  |  | 2023-09-15 |  | TOWER
S01440 | S110C_S01440OD_T3_LDGKERUING | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040672 | [6 empty] | TOWER
S01448 | S106A_S01448OD_T3_PJNAGUSESTATE | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040673 | [6 empty] | TOWER
Q02085 | Q118B_Q02085OD_T3_LBSKM21 | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | N/A | DU00002040674 | [6 empty] | 3LEGGED
S01435 | S110C_S01435OD_T3_KM10KALABAKANNABAWAN | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040675 | [6 empty] | TOWER
Q01658 | Q132B_Q01658OD_DESAPUJUTSL | Sarawak |  | Decomm |  | 2023Q4 | SH | Datasco | 4.6 TSSR Approved |  | 2023-06-17 |  |  | 2023-08-17 |  | Closed | 2023-08-17 | 2024-06-21 | CD//John | 2023-08-17 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622/0612Sarawak-Datasco-BOQ Template (template) | DU00002040676 |  | 24/8: ALl tx info & photos are missing |  |  | 2024-12-19 |  | RAPID ASSEMBLY POLE (RAPOLE)
S01216 | S110B_S01216OD_TSHJLNAPAS | Sabah |  | Decomm |  | 2023Q4 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-06-21 |  |  |  | 2023-06-21 |  | 2023-08-10 | 2023-10-04 | CD//Ray Amos | 2023-08-11 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230622 | DU00002040677 |  | 16/8: Uncompleted info & photos |  |  | 2023-10-19 |  | MONOPOLE
Q01751 | Q124F_Q01751OD_RAMPANGI2 | Sarawak |  | Decomm |  | 2023Q4 | SH | Trintel | 4.6 TSSR Approved |  | 2023-06-19 |  |  |  | 2023-08-02 |  | 2023-08-02 | 2023-08-18 | CD//John | 2023-08-02 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230622/Celcom Digi_RAN-Trintel-TSS DECOMM-Sarawak-20231130 | DU00002040678 |  |  |  |  | 2023-10-09 |  | RAPID ASSEMBLY POLE (RAPOLE)
S00793 | S110A_S00793OD_BAZHONG | Sabah |  | Decomm |  | 2023Q4 | AD | Datasco | 4.6 TSSR Approved |  | 2023-07-13 |  |  |  | 2023-07-27 |  | 2023-08-02 | 2023-10-21 | CD//Mohidi Jaan | 2023-08-02 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006/0612Sabah-Datasco-BOQ Template (template) | DU00002040679 |  | 20230807: all tx info & photos not complete |  |  | 2023-10-31 |  | UNIPOLE
S00792 | S110B_S00792OD_BDRSRIINDAH | Sabah |  | Decomm |  | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-11-14 |  |  |  | 2024-01-26 |  | 2024-01-29 | 2024-02-15 | CD//Ray Amos | 2024-02-27 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006/0612Sabah-Datasco-BOQ Template (template) | DU00002040680 |  |  |  |  | 2024-03-06 |  | MONOPOLE
S01110 | S090A_S01110OD_ADIKACOMPLEX | Sabah |  | Decomm |  | 2023Q3 | MS | South Pacific | 4.6 TSSR Approved |  | 2023-07-25 |  |  |  | 2023-07-25 |  | 2023-07-27 | 2023-08-06 | CD//Mohidi Jaan | 2023-07-27 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230726 | DU00002040681 |  | 27/7: NE & FE info missing |  |  | 2023-09-20 |  | BOOM
S00661 | S110C_S00661OD_SGBRANTIAN | Sabah |  | Decomm |  | 2023Q3 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-09 |  |  |  | 2023-08-03 |  | 2023-08-04 | 2023-09-16 | CD//Ray Amos | 2023-08-07 | Celcom Digi_RAN-Futong-TSS-Sabah-20230531-0008/Celcom Digi_RAN-Futong- TSS-Sabah-20230810 | DU00002040682 |  |  |  |  | 2023-09-13 |  | TOWER
S00507 | S090A_S00507OD_CB_KGANSIP | Sabah |  | Decomm |  | 2023Q3 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-05-17 |  |  |  | 2023-05-17 |  | 2023-06-06 | 2023-07-21 | CD//Mohidi Jaan | 2023-06-09 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230517-0002/0626Sabah-South Pacific-BOQ Template (template) | DU00002040683 |  |  |  |  | 2023-09-11 |  | TOWER
S00989 | S099A_S00989OD_T3_KGTONGULUNJAYA | Sabah | 7143P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN->Swap | 2023Q3 | HW | YPTT | 4.6 TSSR Approved |  | 2025-03-25 | 2025-04-07 |  | 2025-04-09 |  | Under Approval | 2025-04-10 | 2025-05-02 | CD//Sharidah | 2025-04-22 | SQ202504080105 - YPTT | DU00002040684 |  |  | 2025-06-30 | 2025-06-10 |  | Tower | TOWER | 76 | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
S00980 | S097A_S00980OD_SGMANTRI | Sabah | 7047K | Swap |  | 2023Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-07-05 | 2023-07-11 |  | 2023-07-18 |  | Closed | 2023-07-21 | 2023-07-22 | CD//Ray Amos | 2023-07-21 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0010 | DU00002040685 |  |  | 2023-09-27 | 2023-09-22 |  | Tower | TOWER | 75 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
Q02027 | Metalun Settlement (Murum Hydro Settlement) | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040686 | [6 empty] | 3LEGGED
S00581 | S110C_S00581OD_CB_SERUDONGESTATE | Sabah | 7031K | Swap | Swap->Site Out->Swap->On Hold->Swap | 2027 | AD | Futong | 4.6 TSSR Approved |  | 2023-07-10 | 2023-07-14 |  | 2023-07-18 |  | Closed | 2023-07-20 | 2023-07-22 | CD//Ray Amos | 2023-07-21 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0005 | DU00002040687 | [5 empty] | Pole | WATER TANK | 3 | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
Q01248 | Q118B_Q01248OD_LDGPALMHEAD | Sarawak | 9096K | Swap |  | 2023Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2023-07-14 | 2023-07-18 |  | 2023-07-21 |  | Closed | 2024-01-29 | 2024-01-30 | CD//John | 2024-01-29 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230516-0007 | DU00002040688 |  |  | 2024-02-05 | 2024-01-30 |  | Monopole | MONOPOLE | 25m | Add R9264H M901821 x3+R8862A S2601 x2+R8854 S2600 x1,Dismantle |  | 1
Q02033 | Q118B_Q02033OD_T3_COASTALHIGHWAYPLANTATIONCAMP3 | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040689 | [6 empty] | 3LEGGED
Q01250 | Q132B_Q01250OD_LDGADONG | Sarawak | 9097K | Swap |  | 2023Q4 | AD | AllStar | 4.6 TSSR Approved |  | 2023-07-10 | 2023-07-05 |  | 2023-07-13 |  | Closed | 2023-07-17 | 2023-07-18 | CD//John | 2026-04-17 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230608-0006 | DU00002040690 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed | 2025-09-08 | 2025-08-28 |  | Monopole | MONOPOLE | 24M | Add R9264H M901821 x3 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 1
Q01346 | Q118B_Q01346OD_ASSYAKIRINCOMMSQR | Sarawak |  | Decomm |  | 2023Q3 | SH | Datasco | 4.6 TSSR Approved |  | 2023-06-19 | 2023-06-26 |  | 2023-06-19 |  | Closed | 2023-06-20 | 2023-10-13 | CD//John | 2023-06-21 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009/0612Sarawak-Datasco-BOQ Template (template) | DU00002040691 |  | 2023-06-26 Missing TX photos and info |  |  | 2024-08-16 | Monopole | RAPID ASSEMBLY POLE (RAPOLE) | 30m
Q02087 | Q118A_Q02087IB_THESPRINGMALLBINTULU | Sarawak |  | Decomm |  | 2023Q3 | SH | Datasco | 4.6 TSSR Approved |  | 2023-07-22 |  |  | 2023-07-25 |  | Closed | 2023-07-26 | 2024-02-15 | CD//John | 2023-08-14 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009/0612Sarawak-Datasco-BOQ Template (template) | DU00002040692 |  | 29/8: Wrong proposal |  |  | 2024-03-10 |  | IN-BUILDING
Q01030 | VQ_MURUMPWRH | Sarawak | 9088K | Swap | Swap->Site Out->Swap->On Hold->Swap | 2027 |  | Trintel | 2.2 Pending ETSS Resubmission - Subcon |  | 2023-10-25 |  |  |  |  | To be Submitted |  |  | CD//John |  | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230516-0007 | DU00002040693 | [5 empty] | Guide mast | RAPID ASSEMBLY POLE (RAPOLE) | 24m | Add R9264H M901821x3, Dismantle | 0 | 0
S00316 | S090A_S00316OD_CB_BATU27KENINGAU | Sabah |  | Decomm |  | 2023Q3 | AD | Trintel | 4.6 TSSR Approved |  | 2023-06-07 |  |  |  | 2023-07-27 |  | 2023-07-27 | 2023-09-29 | CD//Mohidi Jaan | 2023-07-27 | Celcom Digi_RAN-Trintell-Standard PR TSS-Sabah-20241108 | DU00002040694 |  | 20230807: all tx info & photos are wrong, 20230728: lack of TX photos |  |  | 2023-08-15 |  | TOWER
S01081 | S110B_S01081OD_TINAGATPLAZA | Sabah |  | Decomm |  | 2023Q4 | AD | Datasco | 4.6 TSSR Approved |  | 2023-07-17 |  |  |  | 2023-07-27 |  | 2023-08-02 | 2023-08-23 | CD//Mohidi Jaan | 2023-08-02 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006 | DU00002040695 |  |  |  |  | 2023-10-27 |  | TRIPOD
S01627 | S106A_S01627OD_PULAUMATAKING | Sabah |  | Decomm |  | 2023Q4 | MS | Futong | 4.6 TSSR Approved |  | 2023-07-04 |  |  |  | 2023-08-01 |  | 2023-08-03 | 2023-08-23 | CD//Ray Amos | 2023-08-03 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009/0612Sabah-Futong-BOQ Template (template) | DU00002040696 |  |  |  |  | 2024-03-20 |  | TOWER
S01641 | S110B_S01641OD_CB_MANGROVESANCTUARY | Sabah |  | Decomm |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-07-12 |  |  |  | 2023-08-03 |  | 2023-08-04 | 2023-09-11 | CD//Mohidi Jaan | 2023-08-08 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230726 | DU00002040697 |  | 20230801: IDU label missing (FE) |  |  | 2023-11-18 |  | TOWER
S00629 | S110B_S00629OD_TMAPAS | Sabah |  | Decomm |  | 2023Q4 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2023-11-15 |  |  |  | 2023-12-20 |  | 2023-12-20 | 2024-03-21 | CD//Mohidi Jaan | 2023-12-20 | Celcom Digi_RAN-Seri Pancar-Standard PR TSS DECOMM-Sabah-20240219/0612Sabah-Seri Pancar-BOQ Template (template) | DU00002040698 |  |  |  |  | 2024-06-10 |  | TOWER
S00557 | S110C_S00557OD_BRANTIAN | Sabah |  | Decomm |  | 2023Q3 | MS | Futong | 4.6 TSSR Approved |  | 2023-06-09 |  |  |  | 2023-06-14 |  | 2023-06-15 | 2023-08-06 | CD//Ray Amos | 2023-06-15 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009 | DU00002040699 |  | 27/7: missing tx photos and info26/7: Pending Solution 2023-07-07 missing tx photos and info |  |  | 2023-10-06 |  | TOWER
S00240 | S110C_S00240OD_MTTIGER | Sabah |  | Decomm |  | 2023Q3 | MS | Futong | 4.6 TSSR Approved |  | 2023-06-13 |  |  |  | 2023-08-11 |  | 2023-08-15 | 2023-09-16 | CD//Mohidi Jaan | 2023-08-14 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009/0612Sabah-Futong-BOQ Template (template) | DU00002040700 |  |  |  |  | 2024-01-05 |  | TOWER
S01332 | S099A_S01332OD_KG4NABAWAN | Sabah |  | Decomm |  | 2023Q3 | MS | Futong | 4.6 TSSR Approved |  | 2023-06-09 |  |  |  | 2023-06-17 |  | 2023-06-20 | 2023-07-27 | CD//Ray Amos | 2023-06-21 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009/0612Sabah-Futong-BOQ Template (template) | DU00002040701 |  |  |  |  | 2023-09-25 |  | LAMP_POLE
Q01923 | Q124B_Q01923OD_POLIKCH2 | Sarawak |  | Decomm |  | 2023Q4 | ZB | South Pacific | 4.6 TSSR Approved |  | 2023-08-15 |  |  |  | 2023-08-18 |  | 2023-08-22 | 2023-09-07 | CD//John | 2023-08-22 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230913/0612Sarawak-South Pacific-BOQ Template (template) | DU00002040702 |  | 1/9: uncompleted info & photos |  |  | 2023-09-29 |  | RAPID ASSEMBLY POLE (RAPOLE)
S00236 | S110B_S00236OD_TMNDAHUA | Sabah |  | Decomm |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-07-25 |  |  |  | 2023-07-27 |  | 2023-08-01 | 2023-08-23 | CD//Mohidi Jaan | 2023-08-01 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230726 | DU00002040703 |  |  |  |  | 2023-09-18 |  | TOWER
Q01412 | Q132C_Q01412OD_JLNBENDAHARA | Sarawak | 9105K | Swap |  | 2023Q4 | AD | Datasco | 4.6 TSSR Approved |  | 2023-06-27 | 2023-08-01 |  | 2023-08-19 |  | Closed | 2023-08-21 | 2023-08-22 | CD//John | 2025-04-25 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 - Copy | DU00002040704 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed | 2025-07-06 | 2025-04-22 |  | Wall mount boom | BOOM | 30 | Add R8862A S9000x3+R8894E M1821x3+R8862A S2601x3,Dismantle | 0 | 0
S00994 | S099A_S00994OD_T3_KGSINULIHAN | Sabah | 7144P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN->Swap | 2023Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2025-03-16 | 2025-04-03 |  | 2025-04-07 |  | Under Approval | 2025-04-08 | 2025-05-23 | CD//Sharidah | 2025-04-09 | SQ202504080105 - YPTT | DU00002040705 |  |  | 2025-08-22 | 2025-06-17 |  | Tower | TOWER | 76 | Add R8852E S9000x3+R8894E M1821x6, Dismantle | 0 | 0
S01128 | S110C_S01128OD_PBTSSGUDING | Sabah |  | Decomm |  | 2023Q3 | MS | Futong | 4.6 TSSR Approved |  | 2023-06-09 |  |  |  | 2023-08-02 |  | 2023-08-03 | 2023-09-16 | CD//Ray Amos | 2023-08-03 | Celcom Digi_RAN-Futong-TSS-Sabah-20230531-0008/Celcom Digi_RAN-Futong- TSS-Sabah-20230810 | DU00002040706 |  |  |  |  | 2023-10-09 |  | MONOPOLE
S01000 | S099A_S01000OD_T3_KGTAKUL | Sabah | 7145P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN->Swap | 2023Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2025-03-16 | 2025-03-25 |  | 2025-03-28 |  | Under Approval | 2025-04-11 | 2025-05-23 | CD//Sharidah | 2025-04-21 | SQ202504080105 - YPTT | DU00002040707 |  |  | 2025-10-02 | 2025-06-10 |  | Tower | TOWER | 76 | Add R8852E S9000x3+R8894E M1821x4, Dismantle | 0 | 1
S00351 | S097A_S00351OD_JLNSELAMAT | Sabah |  | Decomm |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-06-16 |  |  |  | 2023-06-19 |  | 2023-08-01 | 2023-08-14 | CD//Mohidi Jaan | 2023-08-01 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0009 | DU00002040708 |  | 2023-07-21 missing tx photos and info |  |  | 2023-10-09 |  | TOWER
S00974 | S106A_S00974OD_T3_PULAUPOMPOM | Sabah | 7044K | Swap |  | 2023Q4 | MS | Futong | 4.6 TSSR Approved |  | 2023-07-11 | 2023-08-03 |  | 2023-08-07 |  | Closed | 2023-08-09 | 2023-08-18 | CD//Ray Amos | 2023-08-18 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0011 | DU00002040709 |  |  | 2023-09-22 | 2023-09-13 |  | Tower | TOWER | 60 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
S00313 | S090A_S00313OD_CB_CROCKERRANGE | Sabah |  | Decomm |  | 2023Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2023-06-22 |  |  |  | 2023-06-23 |  | 2023-06-12 | 2023-07-21 | CD//Mohidi Jaan | 2023-06-13 | Celcom Digi_RAN-Trintel-TSS-Sabah-20230608-0003/0612Sabah-Trintel-BOQ Template (template) | DU00002040710 |  |  |  |  | 2023-11-07 |  | TOWER
S01431 | S110C_S01431OD_T3_KM70KALABAKANNABAWAN | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040711 | [6 empty] | 3LEGGED
S01533 | Jalan Keningau-Sook | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 | MS | Datasco | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A - no need PR for MOCN Decomm | DU00002040712 | [6 empty] | TOWER
Q01702 | Q118B_Q01702OD_CB_JLNCOASTALBTU2 | Sarawak | 9113K | Swap |  | 2023Q3 | BY | Trintel | 4.6 TSSR Approved |  | 2023-05-19 | 2023-05-24 |  | 2023-05-26 |  | Rectificating | 2023-06-09 | 2023-06-10 | CD//John | 2023-06-10 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230516-0007 | DU00002040713 |  |  | 2023-11-30 | 2023-11-18 |  | Tower | TOWER | 45m | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
S01001 | S099A_S01001OD_T3_KGMATIKU | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040714 | [6 empty] | TOWER
Q01674 | VQ_METANIKMILL | Sarawak | 9110K | Swap | Swap->Site Out->Swap->On Hold->Swap | 2027 | AI | Trintel | 4.4 Pending TSSR Review - Design Team |  | 2025-05-13 | 2025-06-06 |  | 2025-07-08 |  | Under Approval |  |  | CD//John |  | SQ202505150459-Trintel | DU00002040715 | [5 empty] | Monopole | RAPID ASSEMBLY POLE (RAPOLE) | 30 | Add R9264H M901821x3, Dismantle | 0 | 0
S00401 | S097A_S00401OD_CB_IOIBATURONG | Sabah | 7028K | MOCN By Other Vendor | Swap->Maintain USP MOCN->On Hold->Maintain USP MOCN->On Hold->MOCN By Other Vendor | 2023Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-06-19 | 2023-06-20 |  | 2023-06-22 |  | Closed | 2023-06-23 | 2023-09-20 | CD//Jahganathan | 2023-09-20 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0010 | DU00002040716 | [5 empty] | Tower | TOWER | 76
Q01355 | Q124B_Q01355OD_TMNWON | Sarawak |  | Decomm |  | 2023Q4 | SH | Trintel | 4.6 TSSR Approved |  | 2023-08-10 |  |  |  | 2023-08-21 |  | 2023-08-21 | 2023-09-01 | CD//John | 2023-08-21 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230622/Celcom Digi_RAN-Trintel-TSS DECOMM-Sarawak-20231130 | DU00002040717 |  | 22/8: UNCOMPLETED INFO & PHOTOS |  |  | 2023-10-18 |  | RAPID ASSEMBLY POLE (RAPOLE)
Q01749 | Q118B_Q01749OD_GEMPARK | Sarawak | 9116K | Swap |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-06-26 | 2023-07-10 |  | 2023-07-17 |  | Closed | 2023-07-20 | 2023-07-31 | CD//John | 2023-07-31 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230516-0006 | DU00002040718 |  |  | 2024-01-24 | 2023-12-20 |  | Unipole | RAPID ASSEMBLY POLE (RAPOLE) | 30 | Add R9264H M901821 x3 + R9264M M1821 x2,Dismantle Celcom all RRU&BBU |  | 13
S01347 | S110B_S01347OD_PERDANAPARK | Sabah |  | Decomm |  | 2023Q4 | AD | YPTT | 4.6 TSSR Approved |  | 2023-07-22 |  |  |  | 2023-07-28 |  | 2023-08-01 | 2023-09-16 | CD//Ray Amos | 2023-08-02 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0008/0612Sabah-YPTT-BOQ Template (template) | DU00002040719 |  | 3/8: FE info missing |  |  | 2023-10-09 |  | LAMP_POLE
S00241 | S110C_S00241OD_SEBATIK | Sabah | 7020K | Swap |  | 2023Q3 | HQ 1 | Futong | 4.6 TSSR Approved |  | 2023-07-22 | 2023-07-25 |  | 2023-07-28 |  | Closed | 2023-07-31 | 2023-08-07 | CD//Jahganathan | 2023-08-07 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0005 | DU00002040720 |  |  | 2023-09-04 | 2023-08-23 |  | Tower | GUYED MAST | 46 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
S00983 | S110C_S00983OD_KGBERGOSONG | Sabah |  | Decomm |  | 2023Q3 | MS | Futong | 4.6 TSSR Approved |  | 2023-07-11 |  |  |  | 2023-07-12 |  | 2023-07-18 | 2023-08-23 | CD//Ray Amos | 2023-07-20 | Celcom Digi_RAN-Futong-TSS-Sabah-20230531-0008/0612Sabah-Futong-BOQ Template (template) | DU00002040721 |  | 20230728: wrong photos |  |  | 2024-03-14 |  | TOWER
S00475 | S090A_S00475OD_KGBANJAR | Sabah |  | Decomm |  | 2023Q3 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-08-04 |  |  |  | 2023-08-06 |  | 2023-08-09 | 2023-10-27 | CD//Jahganathan | 2023-08-10 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230807 | DU00002040722 |  |  |  |  | 2023-10-02 |  | TOWER
S01564 | S106A_S01564OD_CB_KGINDANIJAYA | Sabah |  | Decomm |  | 2023Q4 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-20 |  |  |  | 2023-08-04 |  | 2023-08-09 | 2023-09-16 | CD//Ray Amos | 2023-08-10 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009/0612Sabah-Futong-BOQ Template (template) | DU00002040723 |  |  |  |  | 2023-10-20 |  | TOWER
S01514 | S097A_S01514OD_MJDDAERAHKUNAK | Sabah |  | Decomm |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-06-22 |  |  |  | 2023-06-30 |  | 2023-07-02 | 2023-07-27 | CD//Ray Amos | 2023-07-03 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0009/0612Sabah-GTSB-BOQ Template (template) | DU00002040724 |  |  |  |  | 2023-10-20 |  | LAMP_POLE
Q01653 | Q118B_Q01653OD_TMNKEMENASUTERA2 | Sarawak |  | Decomm |  | 2023Q3 | ZB | CCSMY | 4.6 TSSR Approved |  | 2023-07-30 |  |  |  | 2023-08-01 |  | 2023-08-02 | 2024-02-15 | CD//John | 2023-08-02 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230613-0007/Celcom Digi_RAN-CCSMY-TSS DECOMM-Sarawak-20230828 | DU00002040725 |  |  |  |  | 2024-01-26 |  | RAPID ASSEMBLY POLE (RAPOLE)
S00704 | S099A_S00704OD_CB_SAPULUTTOWN | Sabah | 7093P | Swap | Swap->Maintain USP MOCN->On Hold->Swap | 2023Q3 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-09 | 2023-05-25 |  | 2023-06-22 |  | Under Approval | 2023-06-02 | 2023-06-10 | CD//Sharidah | 2025-03-04 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0005 | DU00002040726 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed | 2025-10-17 | 2025-10-13 |  | Tower | TOWER | 60 | Add R8852E S9000x3+R8854E S1800x3+R8894E M1821x3, Dismantle | 0 | 0
S00971 | S097A_S00971OD_T3_LADANGSUNGANG | Sabah |  | Decomm |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-06-19 |  |  |  | 2023-06-22 |  | 2023-06-23 | 2023-08-30 | CD//Ray Amos | 2023-06-26 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0009 | DU00002040727 |  |  |  |  | 2023-10-13 |  | TOWER
Q01667 | Q132B_Q01667OD_LRGSEROJAMYY | Sarawak | 9109K | Swap |  | 2023Q4 | HQ 1 | Magicell | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦NO,SACOFA lampole not allow to add AAU | 2023-07-13 | 2023-07-21 |  | 2023-07-25 |  | Closed | 2024-10-24 | 2024-12-10 | CD//John | 2024-12-06 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002040728 | NIC_S2_Change MM to BI_owner reject_SACOFA SDN BHD |  | 2025-05-17 | 2025-04-22 |  | Lampole | RAPID ASSEMBLY POLE (RAPOLE) | 30 | Add R8862A S9000x3+R8894E M1821x3, Dismantle | 0 | 0
Q01287 | Q132B_Q01287OD_TUDAN3 | Sarawak |  | Decomm |  | 2023Q4 | ZB | YPTT | 4.6 TSSR Approved |  | 2023-09-20 |  |  |  | 2023-09-25 |  | 2023-09-25 | 2023-10-04 |  | 2023-09-26 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20230622/Celcom Digi_RAN-YPTT-TSS DECOMM-Sarawak-20231128 | DU00002040729 |  |  |  |  | 2025-04-19 |  | RAPID ASSEMBLY POLE (RAPOLE)
S01763 | S090B_X00190OD_DEWANMASYARAKATKGU | Sabah | 7065K | Swap |  | 2023Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2023-07-24 | [5 empty] | 2023-07-21 | 2023-07-21 | CD//Mohidi Jaan | 2023-07-20 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230508-0005 | DU00002040730 |  |  | 2023-08-01 | 2023-07-25 |  |  | RAPID ASSEMBLY POLE (RAPOLE) |  | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle Celcom all RRU&BBU |  | 2
Q01819 | Q124B_Q01819OD_TMNCHERRYWOOD | Sarawak | 9132K | Swap |  | 2023Q4 | BY | South Pacific | 4.6 TSSR Approved |  | 2023-07-19 | 2023-07-31 |  | 2023-08-09 |  | Closed | 2023-08-14 | 2023-08-14 | CD//John | 2023-08-14 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230726 | DU00002040731 |  |  | 2023-12-04 | 2023-11-20 |  | Monopole | RAPID ASSEMBLY POLE (RAPOLE) | 30 | Add R8852E S9000 x3 + R8894E M1821 x3
S00248 | S110C_S00248OD_DUMPAS | Sabah |  | Decomm |  | 2023Q3 | MS | Futong | 4.6 TSSR Approved |  | 2023-06-09 |  |  |  | 2023-06-22 |  | 2023-06-20 | 2023-07-21 | CD//Mohidi Jaan | 2023-06-21 | Celcom Digi_RAN-Futong-TSS-Sabah-20230531-0008 | DU00002040732 |  |  |  |  | 2023-11-29 |  | TOWER
S00651 | S106A_S00651OD_LADANGSEGARIA | Sabah |  | Decomm |  | 2023Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-07-08 |  |  |  | 2023-07-10 |  | 2023-07-28 | 2023-09-19 | CD//Mohidi Jaan | 2023-07-29 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230726/0612Sabah-GTSB-BOQ Template (template) | DU00002040733 |  | 20230731 : IDU labelling missing, FE info missing, FE photos missing |  |  | 2023-11-07 |  | TOWER
S00340 | S097A_S00340OD_TMKUNAK | Sabah |  | Decomm |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-07-04 |  |  |  | 2023-08-03 |  | 2023-08-03 | 2024-07-19 | CD//Mohidi Jaan | 2023-08-03 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0009/Celcom Digi_RAN-GTSB-TSS DECOMM MW-Sabah-20240419 | DU00002040734 |  |  |  |  | 2024-01-25 |  | BOOM
Q01297 | Q118B_Q01297OD_TMNBAMBOO | Sarawak |  | Decomm |  | 2023Q3 | SH | NR services | 4.6 TSSR Approved |  | 2023-10-13 |  |  |  | 2023-10-16 |  | 2023-10-16 | 2024-02-20 | CD//John | 2023-10-16 | Celcom Digi_RAN-NR Services-TSS-Sarawak-20230823 | DU00002040735 |  |  |  |  | 2024-01-03 |  | LAMP_POLE
S00239 | S110B_S00239OD_CB_MILE38TWU | Sabah |  | Decomm |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-06-20 |  |  |  | 2023-06-23 |  | 2023-06-24 | 2023-08-30 | CD//Ray Amos | 2023-06-26 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230612-0009/Celcom Digi_RAN-GTSB-Standard PR TSS DECOMM-Sabah-20231129 | DU00002040736 |  |  |  |  | 2023-10-09 |  | TOWER
Q01409 | Q118B_Q01409OD_LDGRAJAWALI | Sarawak | 9104K | Swap |  | 2023Q3 | BY | Datasco | 4.6 TSSR Approved |  | 2023-05-21 | 2023-05-24 |  | 2023-05-27 |  | Closed | 2023-05-30 | 2023-05-31 | CD//John | 2023-05-31 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230516-0006 | DU00002040737 |  |  | 2023-11-03 | 2023-10-24 |  | Tower | RAMO | 30 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 3
S00656 | S099A_S00656OD_CB_MILLKPOM | Sabah | 7035K | Swap | Swap->TBD->Swap->On Hold->Swap | 2023Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-13 |  | 2023-05-22 |  | Closed | 2023-06-01 | 2023-06-13 | CD//Ray Amos | 2023-06-13 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230508-0005 | DU00002040738 |  |  | 2023-07-25 | 2023-07-22 |  | Tower | BOOM | 60m | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
S01660 | S110B_S01660OD_TMNDAYAUSAHA | Sabah |  | Decomm |  | 2023Q4 | MS | YPTT | 4.6 TSSR Approved |  | 2023-06-27 |  |  |  | 2023-07-09 |  | 2023-07-27 | 2023-08-14 | CD//Mohidi Jaan | 2023-07-27 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0008/0612Sabah-YPTT-BOQ Template (template) | DU00002040739 |  | 20230801: unclear idu label photo, tx info missing (drawing) |  |  | 2023-10-02 |  | TOWER
Q00803 | Q124F_Q00803OD_KGBINTAWA | Sarawak |  | Decomm |  | 2023Q4 | SH | South Pacific | 4.6 TSSR Approved |  | 2023-08-18 |  |  |  | 2023-08-21 |  | 2023-08-22 | 2023-08-30 | CD//John | 2023-08-22 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230913 | DU00002040740 |  |  |  |  | 2023-09-27 |  | TOWER
S01214 | S110A_S01214OD_HOSPTAWAU | Sabah |  | Decomm |  | 2023Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-07-20 |  |  |  | 2023-07-26 |  | 2023-08-03 | 2023-09-16 | CD//Ray Amos | 2023-08-10 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230726 | DU00002040741 |  |  |  |  | 2023-09-15 |  | MONOPOLE
Q01744 | Q132B_Q01744OD_JLNILMU | Sarawak |  | Decomm |  | 2023Q4 | SH | Magicell | 4.6 TSSR Approved |  | 2023-06-22 |  |  |  | 2023-06-27 |  | 2023-07-25 | 2023-08-08 | CD//John | 2023-07-26 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002040742 |  |  |  |  | 2025-10-22 |  | RAPID ASSEMBLY POLE (RAPOLE)
S01330 | S110B_S01330OD_KGKONGSI6 | Sabah |  | Decomm |  | 2023Q4 | AD | South Pacific | 4.6 TSSR Approved |  | 2023-06-14 |  |  |  | 2023-06-14 |  | 2023-07-25 | 2023-08-06 | CD//Ray Amos | 2023-07-26 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230622 | DU00002040743 |  |  |  |  | 2023-10-17 |  | RAPID ASSEMBLY POLE (RAPOLE)
Q01331 | Q118B_Q01331OD_SACF2 | Sarawak |  | Decomm |  | 2023Q3 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-05-22 |  |  |  | 2023-07-20 |  | 2023-07-24 | 2024-06-21 | CD//John | 2023-07-28 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230613-0014/Celcom Digi_RAN-Magicell-TSS DECOMM-Sarawak-20230818 | DU00002040744 |  | 20230808: TX NE FE info/photo missing |  |  | 2024-04-17 |  | MONOPOLE
S00986 | S110C_S00986OD_T3_LADANGMERBAU | Sabah |  | Decomm |  | 2023Q3 | MS | Futong | 4.6 TSSR Approved |  | 2023-06-09 |  |  |  | 2023-06-15 |  | 2023-06-16 | 2023-08-06 | CD//Ray Amos | 2023-06-17 | Celcom Digi_RAN-Futong-TSS-Sabah-20230531-0008 | DU00002040745 |  | 2023-07-07 missing tx photos and info |  |  | 2023-09-18 |  | TOWER
Q01812 | Q118B_Q01812OD_SABAJUMILL | Sarawak | 9127K | Swap |  | 2023Q3 | BY | AllStar | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-20 |  | 2023-05-24 |  | Closed | 2023-05-29 | 2023-05-30 | CD//John | 2023-05-30 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230516-0005 | DU00002040746 |  |  | 2024-02-03 | 2023-12-11 |  | Tower | TOWER | 60 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 1
S00992 | S099A_S00992OD_T3_KGMOSOPOH | Sabah | 7050K | MOCN By Other Vendor | Swap->Maintain USP MOCN->On Hold->Maintain USP MOCN->On Hold->MOCN By Other Vendor | 2023Q3 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-26 | 2023-07-05 |  | 2023-07-07 |  | Under Approval | 2023-07-08 | 2023-07-10 | CD//Jahganathan | 2023-07-10 | Celcom Digi_RAN-Futong-TSS-Sabah-20230508-0005 | DU00002040747 | [5 empty] | Tower | TOWER | 60
Q01088 | Q132B_Q01088OD_CURTINVILLAGE | Sarawak |  | Decomm |  | 2023Q4 | SH | Trintel | 4.6 TSSR Approved |  | 2023-07-13 |  |  |  | 2023-08-03 |  | 2023-08-03 | 2023-08-08 | CD//John | 2023-08-03 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230622/Celcom Digi_RAN-Trintel-TSS DECOMM-Sarawak-20231130 | DU00002040748 |  |  |  |  | 2025-01-25 |  | RAPID ASSEMBLY POLE (RAPOLE)
Q01743 | Q132B_Q01743OD_KGAPIAPIMYY | Sarawak | 9115K | Swap |  | 2023Q4 | ZB | South Pacific | 4.6 TSSR Approved |  | 2023-06-24 | 2023-06-27 |  | 2023-07-06 |  | Closed | 2024-10-24 | 2024-12-06 | CD//John | 2024-12-06 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230606-0003 | DU00002040749 |  |  | 2025-04-30 | 2025-04-22 |  | Monopole | RAPID ASSEMBLY POLE (RAPOLE) | 30 | Add R8862A S9000x3+R8894E M1821x3, Dismantle | 0 | 0
S00382 | S110C_S00382OD_KGMELATI | Sabah |  | Decomm |  | 2023Q3 | MS | Futong | 4.6 TSSR Approved |  | 2023-06-09 |  |  |  | 2023-06-14 |  | 2023-06-14 | 2023-09-29 | CD//Ray Amos | 2023-06-15 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009 | DU00002040750 |  |  |  |  | 2023-10-02 |  | TOWER
Q01529 | Q132B_Q01529OD_JLNPUJUT7 | Sarawak |  | Decomm |  | 2023Q4 | SH | Magicell | 4.6 TSSR Approved |  | 2023-07-10 |  |  |  | 2023-07-20 |  | 2023-07-20 | 2023-08-23 | CD//John | 2023-07-20 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230622 | DU00002040751 |  | 2023-07-24 Missing TX photos and info |  |  | 2025-06-25 |  | RAPID ASSEMBLY POLE (RAPOLE)
Q01895 | Q124F_Q01895OD_BDRBARUSAMARIANG | Sarawak | 9137K | Swap |  | 2023Q4 | SH | Datasco | 4.6 TSSR Approved |  | 2023-07-08 | 2023-08-01 |  | 2023-08-03 |  | Closed | 2023-08-03 | 2023-08-03 | CD//John | 2023-08-03 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230622 - Copy | DU00002040752 |  |  | 2024-01-09 | 2024-01-08 |  | Tower | RAPID ASSEMBLY POLE (RAPOLE) | 30 | Add R8852E S9000 x3 + A9732 M1821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 123
S01441 | S110C_S01441OD_T3_KGSGPUKUL | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002040753 | [6 empty] | TOWER
Q01264 | Q118B_Q01264OD_SGPLAN2 | Sarawak |  | Decomm |  | 2023Q3 | SH | NR services | 4.6 TSSR Approved |  | 2023-10-12 |  |  |  | 2023-10-25 |  | 2023-10-26 | 2024-08-30 | CD//John | 2023-10-26 | Celcom Digi_RAN-NR Services-TSS-Sarawak-20230823/0612Sarawak-NR services-BOQ Template (template) | DU00002040754 |  |  |  |  | 2025-07-21 |  | LAMP_POLE
P00272_IBC | P035C_P00272OD_DORSETTHOTEL | Northern | 4809B | Swap | TBD->Swap->TBD->Swap | 2023Q3 | BY | GCI | 4.6 TSSR Approved |  | 2024-01-09 | 2024-04-02 |  | 2024-04-05 |  | Closed | 2024-04-08 | 2024-04-15 |  | 2024-04-08 | Celcom Digi_RAN-GCI-TSS-Northern-20240315-0101 | DU00002040755 |  |  | 2024-05-31 | 2024-04-26 |  | Portables BTS | BOOM |  | Add R8862A S9000 x3+R8862A S2100 x3+R8862A S1800 x3,Dismantle
P00195_IBC | P035B_P00195OD_PARKROYAL | Northern | 4127K | Swap |  | 2023Q3 | WP | GTSB | 4.6 TSSR Approved |  | 2023-09-13 | 2023-09-30 |  | 2023-10-04 |  | Closed | 2023-10-04 | 2023-10-23 | CD//Affendi | 2023-10-13 | Celcom Digi_RAN-GTSB-TSS-Northern-20230914-0037 | DU00002040756 |  |  | 2023-12-30 | 2023-12-29 |  | Portables BTS | TOWER |  | R8852E S9000 x3+R8862A S2100 x3+R8862A S2601 x3,Dismantle all celcom BBU&RRU
P00361_IBC | P035C_P00361OD_MENARAKWSP | Northern | 4138K | Site Out (Swap) | Swap->TBD->On Hold->Site Out->Site Out (Swap) | 2023Q3 |  | CCSMY | [SiteOut]- 2.1 Pending ETSS Submission - Subcon |  | 2023-09-05 |  |  |  |  | To be Submitted |  |  | CD//Zulakmar |  | Celcom Digi_RAN-CCSMY-TSS-Northern-20230906-0038 | DU00002040757 | [6 empty] | BOOM
P00344_IBC | P031B_P00344OD_QUEENSBAY | Northern |  | Decomm |  | 2023Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-11-20 |  |  |  | 2023-11-20 |  | 2023-11-21 | 2024-05-06 | CD//Affendi | 2023-11-28 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231122-0072 | DU00002040758 |  |  |  |  | 2023-10-19 |  | BOOM
4826A_IBC | Gurney Hotel | Northern |  | Modernization |  | 2023Q3 | WP | GTSB | 4.6 TSSR Approved |  | 2023-09-13 | 2023-09-30 |  | 2023-10-04 |  | Closed | 2023-10-04 | 2023-10-19 |  | 2023-08-20 | Celcom Digi_RAN-GTSB-TSS-Northern-20230914-0037 | DU00002040759 |  |  | 2024-04-11 | 2024-02-29 |  | Portables BTS | IBS + RT (Boom) |  | Add R8862A S1800 x1,Dismantle R8882-GUL1812 x2+
B00210 | B057A_B00210OD_SLYGMALL | Central |  | Decomm |  | 2023Q4 | ZA | YPTT | 4.6 TSSR Approved |  | 2024-03-20 |  |  |  | 2024-03-22 |  | 2024-03-26 | 2024-09-26 | CD//Sapian | 2024-04-08 | BOQ_Celcom Digi_RAN-YPTT-Standard PR TSS-20240323 | DU00002040760 |  |  |  |  | 2024-04-01 |  | IN-BUILDING
P00388 | P035C_P00388OD_TIMESQUAREPG | Northern | 4143K | Swap |  | 2023Q3 | SM | YPTT | 4.6 TSSR Approved |  | 2023-05-19 | 2023-05-24 |  | 2023-06-11 | 2023-06-22 | Closed | 2023-06-14 | 2023-06-28 | CD//Affendi /Quah | 2023-06-21 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0009 | DU00002040761 |  |  | 2024-06-30 | 2023-09-07 |  |  | IN-BUILDING |  | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
4869A_IBC | HolidayVilla (indoor) | Northern |  | Modernization |  | 2023Q4 | WP | GTSB | 4.6 TSSR Approved |  | 2023-09-13 | 2023-09-30 |  | 2023-10-04 |  | Closed | 2023-10-04 | 2023-10-19 |  | 2023-08-06 | Celcom Digi_RAN-GTSB-TSS-Northern-20230914-0037 | DU00002040762 |  |  | 2024-04-11 | 2024-04-01 |  | Portables BTS | In-building system |  | Add R8862A S2100 x1+R8862A S1800 x1,Dismantle R8882-GUL1812 x1
P00183_IBC | P035C_P00183OD_GURNEYHOTEL | Northern |  | Decomm |  | 2023Q3 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-10-04 |  |  |  | 2024-01-02 |  | 2023-10-04 | 2023-10-23 | CD//Rohizam | 2023-06-22 | Celcom Digi_RAN-GTSB-TSS-Northern-20231108-0064 | DU00002040763 |  |  |  |  | 2024-02-29 |  | BOOM
4809B | Dorsett Penang IB | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-07-22 | 2023-07-18 |  | 2023-07-22 |  | Closed | 2023-07-25 | 2023-08-07 | E//Nazrul | 2023-08-06 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0015 | DU00002040764 |  |  | 2023-09-11 | 2023-09-08 |  | In-Building System | IBS + RT (Boom) | 5 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3 ; Add R8852E S9000 x3+R8862A S1800 x1,Dismantle R8882-GUL1812 x1(IBC)
Q00276_IBC | Q118B_Q00276OD_WISMABDA | Sarawak | 9064K | Swap |  | 2023Q3 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-11-08 | 2023-11-21 |  | 2023-11-23 |  | Closed | 2023-11-27 | 2023-12-04 | CD//John | 2023-11-29 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231112 | DU00002040765 |  | 2311 1. Do not swap existing rectifier, need to remain. 2. Reuse existing module and battery 3. Please propose new breaker with photo for new R8862A S1800(B6A) & R8862A S2100(A6A) 4. Where is combiner and splitter for this site. Please check 5. Change existing type model RRU from KRC 118 73/1 to RRUS 01 B3 | 2024-11-09 | 2024-10-24 |  |  | BOOM | 6 | R8862A S2100 x1+R8862A S1800 x1,Dismantle all celcom BBU&RRU
P00580 | P035A_P00580OD_ALLSEASONPLACE | Northern | 4152K | Decomm |  | 2023Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-05-11 | 2023-06-09 |  | 2023-06-26 | 2023-07-13 | Closed | 2023-08-04 | 2023-10-02 | CD//Quah | 2023-09-29 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230720-0023/Celcom Digi_RAN-GTSB-TSS-Northern-20230509-0017/Celcom Digi_RAN-GTSB-TSS-Northern-20241030_New Contract | DU00002040766 |  |  |  |  | 2023-10-20 | Wall mount boom | BOOM | 8
P00185 | P035B_P00185OD_ISLANDPLAZA | Northern |  | Decomm |  | 2023Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-07-20 |  |  |  | 2023-07-20 |  | 2023-07-25 | 2024-02-29 | CD//Quah | 2023-08-17 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002040767 |  |  |  |  | 2025-01-08 |  | BOOM
P00344 | P031B_P00344OD_QUEENSBAY | Northern |  | Decomm |  | 2023Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-11-14 |  |  |  | 2023-11-21 |  | 2023-11-21 | 2023-12-18 | CD//Affendi | 2023-11-28 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002040768 |  |  |  |  | 2023-10-19 |  | BOOM
P00184 | P035C_P00184OD_GURNEYPLAZA | Northern |  | Decomm |  | 2023Q3 | SM | GCI | 4.6 TSSR Approved |  | 2023-05-08 |  |  |  | 2024-01-04 |  | 2024-01-05 |  | CD//Affendi | 2024-01-09 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1 | DU00002040770 |  | 1) Please include Digi Cabinet to relocate xC equipment, 2) Please amend drawing include location xC and xD cabinet |  |  | 2023-11-30 |  | BOOM
4804A | Berjaya Georgetown | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-08-17 | 2023-08-18 |  | 2023-08-22 |  | Closed | 2023-08-28 | 2023-08-28 | E//Nazrul | 2023-10-03 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0016 | DU00002040771 |  |  | 2023-11-17 | 2023-10-27 |  | In-Building System | IBS + RT (Boom) | 10 | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle R8862A S1800(B6A) x5+R8862A S2100(A6A) x3+R8854D S2100(A4A) x2 |  | 2
B00869 | B058B_B00869OD_MENARAINGKLANGOD | Central |  | Decomm |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-16 |  |  | 2023-05-22 | 2023-05-22 | Under Approval | 2023-06-12 | 2023-08-18 | CD//Norhaliza | 2023-06-13 | CelcomDigi_RAN_YPTT_TSS_Central_20230626_decom reraise | DU00002040772 |  |  |  |  | 2023-10-19 |  | IN-BUILDING
P00127 | P035C_P00127OD_CITYBAYVIEW_PG | Northern | 4605K | Decomm |  | 2023Q3 | SM | GCI | 4.6 TSSR Approved |  | 2023-05-22 |  |  |  | 2023-07-06 |  | 2023-07-06 | 2023-08-08 | CD//Rohizam | 2023-08-06 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1 | DU00002040773 |  | No TX Info |  |  |  |  | BOOM
4054A | Sunway Hotel | Northern |  | Modernization |  | 2023Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-19 |  | 2023-05-25 |  | Rectificating | 2023-07-13 | 2023-07-13 | E//Nazrul | 2023-07-13 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0015 | DU00002040774 |  |  | 2023-09-18 | 2023-08-24 |  | H-bracket pole | IBS + 3m RT (Wall Mounted Pole) | N/A | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle R9224E M1821(AAB) x4 |  | 1
4804A_IBC | Berjaya Georgetown | Northern |  | Modernization |  | 2023Q3 | WP | CCSMY | 4.6 TSSR Approved |  | 2023-09-18 |  |  | 2023-09-18 |  | Closed | 2023-09-26 | 2023-09-27 |  | 2023-08-28 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230919-0042 | DU00002040775 |  |  | 2024-01-22 |  |  |  | IBS + RT (Boom) |  | Add R8862A S2601 x2+R8862A S1800 x2,Dismantle R8882 S1800(B) x2
B00869_IBC | B058B_B00869OD_MENARAINGKLANGOD | Central |  | Decomm |  | 2023Q3 | SS | YPTT | 4.6 TSSR Approved |  | 2023-11-10 |  |  |  | 2023-11-10 |  | 2024-02-19 | 2025-03-24 | CD//Sofiah | 2024-02-23 | CelcomDigi_RAN_YPTT_TSS_Central_20231112 | DU00002040776 |  |  |  |  | 2023-11-09 |  | IN-BUILDING
Q00275 | Q118B_Q00275OD_MLNG | Sarawak | 9063K | Swap |  | 2026 |  | Trintel | 1.1 Pending Survey - Subcon | [6 empty] | To be Submitted |  |  | CD//John |  |  | DU00002040777 | [6 empty] | BOOM |  | Add R8862A S9000x3+R8894E M1821x3+R8862A S2601x3,Dismantle | 0 | 0
4809B_IBC | Dorsett Penang IB | Northern |  | Modernization | TBD->Decomm->TBD->Decomm->Modernization | 2023Q3 | SM | GCI | 4.6 TSSR Approved |  | 2024-08-02 | 2024-08-06 |  | 2024-08-12 |  | Under Approval | 2024-08-13 | 2024-08-14 |  | 2024-08-13 | 0802CD-Northern-GCI-BOQ Template(new contract) | DU00002040778 |  |  | 2025-03-15 | 2024-11-15 |  | Portables BTS | IBS + RT (Boom) |  | Add R8862A S9000 x3+R8862A S1800 x1,Dismantle R8882-GUL1812 x1 | 0 | 0
P00091 | P035B_P00091OD_BAYVIEWBEACHRESORT | Northern | 4125K | Decomm |  | 2023Q3 | SM | YPTT | 4.6 TSSR Approved |  | 2023-05-07 | 2023-06-19 |  | 2023-07-10 | 2023-07-21 | Closed | 2023-07-25 | 2024-02-22 | CD//Affendi | 2023-08-17 | 0626Northen-YPTT-BOQ Template (template) | DU00002040779 |  | Wrong survey.please refer EMPS for SOW 6/2: REJECT, include Cabinet celcom in building photo and include in drawing also |  |  | 2024-01-16 | Wall mount boom | IN-BUILDING | 3m & 5m
B00210_IBC | B057A_B00210OD_SLYGMALL | Central |  | Decomm |  | 2023Q4 | SS | Magicell | 4.6 TSSR Approved |  | 2024-03-20 |  |  |  | 2024-03-22 |  | 2024-03-22 | 2024-05-31 | CD//Sofiah | 2024-05-30 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240323 | DU00002040780 |  |  |  |  | 2024-03-21 |  | BOOM
P00185_IBC | P035B_P00185OD_ISLANDPLAZA | Northern |  | Decomm | Decomm->On hold->Swap->On Hold->Decomm | 2023Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2024-01-17 | 2024-05-06 |  | 2024-05-07 |  | Closed | 2024-05-10 | 2024-05-13 | CD//Rohizam | 2024-05-10 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240402-0102/0823CD-Northern-CCSMY-BOQ Template(new contract) | DU00002040781 |  |  |  |  | 2025-01-08 | Pole | TOWER |  | Add R8862A S2100 x3+R8862A S2601 x3+R8862A S1800 x3,Dismantle
4876A_IBC | E-Gate Penang | Northern |  | Modernization |  | 2023Q3 | WP | GTSB | 4.6 TSSR Approved |  | 2023-09-13 | 2023-09-30 |  | 2023-10-04 |  | Closed | 2023-10-04 | 2023-10-19 |  | 2023-07-06 | Celcom Digi_RAN-GTSB-TSS-Northern-20230914-0037 | DU00002040782 |  |  | 2023-09-21 | 2023-07-13 |  | Portables BTS | IBS + RT (Boom) |  | dismantle R8882-GUL1812 x1
P00195 | P035B_P00195OD_PARKROYAL | Northern | 4127K | Decomm |  | 2023Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-05-03 | 2023-06-06 |  | 2023-06-20 | 2023-06-20 | Closed | 2023-08-21 | 2023-10-17 | CD//Affendi | 2023-08-22 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0016 | DU00002040783 |  |  |  |  | 2024-05-03 | Pole | BOOM | 5
P00361 | P035C_P00361OD_MENARAKWSP | Northern | 4138K | Swap | Swap->TBD->On Hold->Swap | 2023Q3 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-06-21 | 2023-07-18 |  | 2024-05-30 |  | Closed | 2024-12-06 | 2024-12-12 | CD//Zulakmar | 2024-12-12 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230509-0018 | DU00002040784 |  | CD rejected - need resurvey | 2024-08-15 | 2024-08-02 |  | Wall mount boom | IN-BUILDING | 4 | Add R9264M M1821 x2+R9264H M901821 x3+R8862A S2601 x1+R8854 S2600 x2,Dismantle | 0 | 13
S00721_IBC | S110B_S00721OD_EASTERNPLAZA | Sabah |  | Decomm |  | 2023Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2024-01-16 |  |  |  | 2024-01-16 |  | 2024-01-17 | 2024-02-15 | CD//Mohidi Jaan | 2024-01-18 | Celcom Digi_RAN-GTSB-TSS-Sabah-20240124 | DU00002040785 |  |  |  |  | 2024-07-03 |  | IN-BUILDING
B01732_IBC | B061B_B01732SC_BLUECUBE_LMNSERI | Central | 1141K | Site Out (Swap) | Swap->Site Out->Site Out (Swap) | 2023Q4 |  | YPTT | [SiteOut]- 4.4 Pending TSSR Review - Design Team |  | 2025-07-16 |  | 2025-07-14 |  | 2025-07-18 | [5 empty] | SQ202506140184 | DU00002040786 | [6 empty] | BOOM
P00184_IBC | P035C_P00184OD_GURNEYPLAZA | Northern |  | Decomm |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-12-22 |  |  |  | 2024-02-07 |  | 2024-02-09 | 2024-06-19 | CD//Affendi | 2024-02-15 | Celcom Digi_RAN-GCI-TSS-Northern-20231225-0085/Celcom Digi_RAN-GCI-TSS-Northern-20240130-0092 | DU00002040787 |  |  |  |  | 2023-12-25 |  | BOOM
P00183 | P035C_P00183OD_GURNEYHOTEL | Northern |  | Decomm |  | 2023Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-05-09 |  |  |  | 2023-07-07 |  | 2023-06-08 | 2023-07-21 | CD//Shamsul | 2023-06-22 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2 | DU00002040788 |  |  |  |  | 2024-02-29 |  | IN-BUILDING
P00272 | P035C_P00272OD_DORSETTHOTEL | Northern |  | Decomm |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-07-22 |  |  |  | 2023-07-22 |  | 2023-07-24 |  | CD//Rohizam | 2023-08-06 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002040789 |  | No TX Info, Photo not enough 30/8: Missing Digi Link to be decom, Need capture photo Antenna & ODU Celcom for link NT01572 (P00272-P00318) |  |  | 2024-05-15 |  | BOOM
P00028_IBC | P035F_P00028OD_EQUATORIAL | Northern | 4118K | Swap |  | 2023Q3 | WP | CCSMY | 4.6 TSSR Approved |  | 2023-09-18 |  |  | 2023-09-18 |  | Closed | 2023-09-26 | 2023-09-27 | CD//Rohizam | 2023-07-12 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230919-0042 | DU00002040790 |  |  | 2023-09-19 | 2023-07-18 |  |  | BOOM |  | R8852E S9000 x1+R8862A S2100 x1,Dismantle all celcom BBU&RRU
B01732 | B061B_B01732SC_BLUECUBE_LMNSERI | Central | 1141K | Swap |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved |  | 2023-08-08 | 2023-08-17 |  | 2023-09-26 |  | Closed | 2023-09-27 | 2023-10-04 | CD//Sofiah | 2023-10-03 | CelcomDigi_RAN_Datasco_TSS_Central_20230808 | DU00002040791 |  |  | 2023-12-28 | 2023-12-04 |  | In-Building System | SMALL CELL | SMALL CELL | Add BS8932 x1,Dismantle Celcom small cell
Q00729_IBC | Q132C_Q00729OD_WISMAPELITA | Sarawak |  | Decomm |  | 2023Q4 | ZB | AllStar | 4.6 TSSR Approved |  | 2023-10-06 |  |  | 2023-10-19 |  | Closed | 2023-10-20 | 2023-11-18 | CD//John | 2023-10-21 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20231009 | DU00002040792 |  | 1. Please include EDOTCO Summary 2. Missing RBS 6201 to decom |  |  | 2024-01-22 |  | BOOM
B00763 | B061A_B00763OD_PKNSSHLM | Central | 1096K | Decomm |  | 2023Q4 | CR | Datasco | 4.6 TSSR Approved |  | 2023-05-24 | 2023-06-21 |  |  | 2023-08-08 |  | 2023-08-23 | 2023-12-18 | CD//Sapian | 2023-11-27 | 0626Central-Datasco-BOQ Template (template) | DU00002040793 |  | RESUBMISSION - Please check for ODF & other OB fiber equipment in other celcom cabinet. |  |  | 2024-01-28 | Pole | IN-BUILDING | 7
B00456 | B061B_B00456OD_STDMELAWATI | Central | 1082K | Decomm |  | 2023Q4 | IE | Datasco | 4.6 TSSR Approved | 29/1- Change SOW to Decom due to Owner request | 2023-08-28 | 2023-09-26 |  |  | 2023-09-22 |  | 2023-09-25 | 2023-11-16 | CD//Sapian | 2023-10-01 | CelcomDigi_RAN_Datasco_TSS_Central_20230829_Modern+Decom | DU00002040794 |  |  |  |  | 2023-11-20 |  | BOOM | 3
B00763_IBC | B061A_B00763OD_PKNSSHLM | Central | 1096K | Swap |  | 2023Q4 | CR | Datasco | 4.6 TSSR Approved |  | 2023-10-18 | 2023-10-16 |  | 2023-10-10 |  | Closed | 2023-10-19 | 2023-11-28 | CD//Sofiah | 2023-11-27 | CelcomDigi_RAN_Datasco_TI_Central_20231007 | DU00002040795 |  |  | 2024-02-24 | 2024-02-21 |  | Portables BTS | BOOM | N/A | R8852E S9000 x2+R8862A S2100 x2+R8862A S2601 x2,Dismantle all celcom BBU&RRU
B00665_IBC | B057A_B00665OD_SLYGCAPITOL | Central |  | Decomm |  | 2023Q4 | SS | Magicell | 4.6 TSSR Approved |  | 2023-12-01 |  |  |  | 2023-12-05 |  | 2023-12-06 | 2024-03-22 | CD//Sofiah | 2024-03-14 | CelcomDigi_RAN_Magicell_TSS_Central_20231203 | DU00002040796 |  |  |  |  | 2024-05-15 |  | BOOM
B00456_IBC | B061B_B00456OD_STDMELAWATI | Central | 1082K | Decomm | Swap->Decomm | 2023Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2023-10-31 | 2023-11-09 |  | 2023-11-20 | 2024-02-23 | Rectificating | 2024-02-26 | 2023-11-28 | CD//Sofiah | 2024-03-18 | CelcomDigi_RAN_Datasco_TSS_Central_20231101 | DU00002040797 |  |  |  |  | 2024-12-06 | Portables BTS | BOOM | NA
S00721 | S110B_S00721OD_EASTERNPLAZA | Sabah |  | Decomm |  | 2023Q4 | AD | YPTT | 4.6 TSSR Approved |  | 2023-07-13 |  |  |  | 2023-07-24 |  | 2023-08-08 | 2024-03-21 | CD//Mohidi Jaan | 2023-08-08 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0008 | DU00002040798 |  | 21/8: uncompleted info & photos |  |  | 2023-12-06 |  | IN-BUILDING
9061A_IBC | Wisma Pelita Tunku | Sarawak |  | Modernization |  | 2023Q4 | ZB | AllStar | 4.6 TSSR Approved | [7 empty] | 2024-01-19 | 2024-01-19 |  | 2024-01-19 | 0925CD-Sarawak-Allstar-BOQ Template(new contract) | DU00002040799 |  |  | 2023-10-12 | 2023-10-05 |  |  | IBS + RT (Boom) |  | Add R8862A S2100 x1+R8862A S1800 x1,Dismantle R8882-GUL1812 x1
B00665 | B057A_B00665OD_SLYGCAPITOL | Central |  | Decomm |  | 2023Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2023-10-24 |  |  |  | 2023-10-25 |  | 2023-10-27 | 2023-11-29 | CD//Sapian | 2023-11-02 | CelcomDigi_RAN_YPTT_TSS_Central_20231028 | DU00002040800 |  |  |  |  | 2023-11-24 |  | BOOM
Q00161_IBC | Q124F_Q00161OD_SANTUBONGSUITE | Sarawak | 9059K | Swap |  | 2023Q4 |  |  | 4.6 TSSR Approved | [7 empty] | 2024-03-26 | 2024-03-27 | CD//John | 2024-03-27 |  | DU00002040801 |  |  | 2024-01-26 | 2023-12-07 |  |  | TOWER |  | Add R8862A S2100 x1+R8862A S1800 x1,Dismantle all celcom BBU&RRU(IBC)
4827A_IBC | Prangin Mall | Northern |  | Modernization |  | 2023Q3 | WP | GTSB | 4.6 TSSR Approved |  | 2023-09-13 | 2023-09-30 |  | 2023-10-04 |  | Closed | 2023-10-04 | 2023-10-19 |  | 2023-08-06 | Celcom Digi_RAN-GTSB-TSS-Northern-20230914-0037 | DU00002040802 |  |  | 2024-04-11 | 2024-04-01 |  | Portables BTS | IBS + RT (Boom) |  | Add R8862A S1800 x1,Dismantle R8882 S1800(B) x1
4876A | E-Gate Penang | Northern |  | Modernization |  | 2023Q3 | MH | GTSB | 4.6 TSSR Approved |  | 2023-05-17 | 2023-05-24 |  | 2023-05-27 |  | Closed | 2023-05-29 | 2023-07-07 | E//Hazida | 2023-07-06 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0016 | DU00002040803 |  |  | 2023-07-18 | 2023-07-13 |  | Pole | IBS + RT (Boom) | 6 | Add R9264M M1821 x3+R8862A S2601 x1,Dismantle R9224E M1821(AAB) x2 |  | 1
P00028 | P035F_P00028OD_EQUATORIAL | Northern | 4118K | Decomm |  | 2023Q3 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-05-25 | 2023-07-05 |  | 2023-07-10 | 2023-08-11 | Closed | 2023-07-10 | 2023-07-12 | CD//Shamsul | 2023-07-12 | 0626Northen-CCSMY-BOQ Template (template) | DU00002040804 |  |  |  |  | 2023-10-11 | In-Building System | BOOM | 2.5M
P00127_IBC | P035C_P00127OD_CITYBAYVIEW_PG | Northern | 4605K | On Hold | Decomm->On hold->Swap->On Hold->Decomm->On Hold->Decomm->On Hold | 2023Q3 | BY | GCI | 4.6 TSSR Approved | ¦ 0515 - GCI:Need resurvey ¦ 0423 - GCI: Need resurvey | 2023-10-19 | 2024-04-17 |  | 2024-06-24 |  | Under Approval | 2024-06-23 | 2024-07-23 | E//Nazrul | 2024-07-22 | Celcom Digi_RAN-GCI-TSS-Northern-20240402-0105/Celcom Digi_RAN-GCI-TSS-Northern-20241017_New Contract | DU00002040805 | [5 empty] | Portables BTS | BOOM |  | Add R8862A S9000 x2+R8862A S2100 x2,Dismantle
Q00161 | Q124F_Q00161OD_SANTUBONGSUITE | Sarawak | 9059K | Swap |  | 2023Q4 | HQ 1 | AllStar | 4.6 TSSR Approved |  | 2023-06-28 | 2023-07-03 |  | 2023-07-10 |  | Closed | 2024-05-06 | 2024-05-08 | CD//John | 2024-05-06 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230608-0006 | DU00002040806 |  |  | 2024-10-30 | 2024-10-03 |  | Portables BTS | IN-BUILDING | 3.1 | Add R9264H M901821 x3
P00187 | P035F_P00187OD_BKTJAMBUL | Northern |  | Decomm |  | 2023Q3 | ZA | YPTT | 4.6 TSSR Approved |  | 2023-07-21 |  |  |  | 2023-07-21 |  | 2023-07-24 | 2024-02-15 | CD//Rohizam | 2023-08-06 | Celcom Digi_RAN-YPTT-TSS-Northern-20230609-0018 | DU00002040807 |  | 4-Sept: Reject, please include Label ID IDU |  |  | 2024-01-06 |  | IN-BUILDING
Q00276 | Q118B_Q00276OD_WISMABDA | Sarawak | 9064K | Decomm |  | 2023Q3 | SH | Datasco | 4.6 TSSR Approved |  | 2023-09-28 |  |  |  | 2023-09-28 |  | 2023-09-30 | 2023-10-04 |  | 2023-11-29 | 0626Sarawak-Datasco-BOQ Template (template) | DU00002040808 |  |  |  |  | 2025-04-16 | In-Building System | IN-BUILDING
Q00347_IBC | Q132C_Q00347OD_BOULEVARDMYY | Sarawak |  | Decomm | Decomm->On hold->Swap->On Hold->Decomm | 2023Q4 | AD | AllStar | 4.6 TSSR Approved |  | 2023-10-06 | 2024-04-17 |  | 2025-05-14 |  | Under Approval | 2024-04-25 |  | CD//Sofiah | 2025-11-01 | Celcom Digi_RAN-Allstar-Standard PR TSS-Sarawak-20240406 | DU00002040809 |  | Change anchor, xC TSSR need change from swap to decom |  |  | 2025-11-25 | Portables BTS | MINI STRUCTURE |  | Add R8862A S2100 x2+R8862A S2601 x2+R8862A S1800 x2,Dismantle
9061A | Wisma Pelita Tunku | Sarawak |  | Modernization |  | 2023Q4 | BY | AllStar | 4.6 TSSR Approved |  | 2023-06-13 | 2023-07-28 |  | 2023-08-04 |  | Closed | 2023-08-08 | 2023-08-24 | E//Nazrul | 2023-08-08 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230608-0006 | DU00002040810 |  |  | 2023-10-12 | 2023-10-05 |  | In-Building System | IBS + RT (Boom) | 6 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x6+R8882 S2600(B4A) x2 | 123
P00072 | P031B_P00072OD_SUNSHINESQUARE | Northern |  | Decomm |  | 2023Q3 | BY | YPTT | 4.6 TSSR Approved | ¦ 0611 - Decomm PRPO to refer P00072_IBC as work done concurrently | 2023-05-16 |  |  |  | 2024-02-28 |  | 2024-02-29 | 2023-11-23 | CD//Quah | 2024-03-29 | Celcom Digi_RAN-YPTT-TSS-Northern-20230609-0018 | DU00002040811 |  |  |  |  | 2024-04-04 |  | IN-BUILDING
P00072_IBC | P031B_P00072OD_SUNSHINESQUARE | Northern |  | Decomm |  | 2023Q3 | ZA | YPTT | 4.6 TSSR Approved | ¦ 0319 - Change RF approval date to reflect actual approval ¦ 0129 - TSSR IBC Submitted in Outdoor DU, pending TSS for outdoor decomm | 2024-01-02 |  |  |  | 2024-02-28 |  | 2023-07-28 | 2024-03-06 | CD//Quah | 2023-10-29 | Celcom Digi_RAN-YPTT-TSS-Northern-20240108-0051 | DU00002040812 |  |  |  |  | 2024-04-04 |  | BOOM
4054A_IBC | Sunway Hotel | Northern |  | Modernization |  | 2023Q3 | WP | GTSB | 4.6 TSSR Approved |  | 2023-09-13 | 2023-09-30 |  | 2023-10-04 |  | Closed | 2023-10-04 | 2023-10-19 |  | 2023-07-13 | Celcom Digi_RAN-GTSB-TSS-Northern-20230914-0037 | DU00002040813 |  |  | 2023-09-13 | 2023-09-13 |  | Portables BTS | IBS + 3m RT (Wall Mounted Pole) | N/A | Add R8862A S2100 x1,Dismantle
P00187_IBC | P035F_P00187OD_BKTJAMBUL | Northern |  | Decomm |  | 2023Q3 | ZA | YPTT | 4.6 TSSR Approved |  | 2024-01-17 |  |  |  | 2024-01-23 |  | 2024-01-26 | 2024-03-14 | CD//Affendi | 2024-01-30 | Celcom Digi_RAN-YPTT-TSS-Northern-20240124-0056 | DU00002040814 |  |  |  |  | 2024-01-06 |  | MINI STRUCTURE
4827A | Prangin Mall | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-13 | 2023-05-19 |  | 2023-06-03 |  | Closed | 2023-06-28 | 2023-08-08 | E//Daniel | 2023-08-06 | Celcom Digi_RAN-GTSB-TSS-Northern-20230509-0017 | DU00002040815 |  |  | 2023-09-12 | 2023-09-12 |  | Wall mount boom | IBS + RT (Boom) | 2 | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle R9224E M1821(AAB) x4 |  | 3
P00091_IBC | P035B_P00091OD_BAYVIEWBEACHRESORT | Northern | 4125K | Swap |  | 2023Q3 |  | YPTT | 4.6 TSSR Approved |  | 2024-01-16 |  |  | 2024-01-16 |  | Closed | 2024-01-17 | 2024-01-19 | CD//Affendi | 2024-01-18 | Celcom Digi_RAN-YPTT-TSS-Northern-20240116-0054 | DU00002040816 |  |  | 2023-12-27 | 2023-08-21 |  |  | BOOM |  | R8862A S2100 x2+R8862A S1800 x2,Dismantle all celcom BBU&RRU
P00025_IBC | P035B_P00025OD_PARADISETGBUNGAH | Northern | 4116K | Swap |  | 2023Q3 | WP | GTSB | 4.6 TSSR Approved |  | 2023-09-13 | 2023-09-30 |  | 2023-10-04 |  | Closed | 2023-10-04 | 2023-10-19 | CD//Shamsul | 2023-08-07 | Celcom Digi_RAN-GTSB-TSS-Northern-20230914-0037 | DU00002040817 |  |  | 2023-09-21 | 2023-08-28 |  | Portables BTS | BOOM |  | R8862A S2100 x1+R8862A S1800 x1,Dismantle all celcom BBU&RRU
4826A | Gurney Hotel | Northern |  | Modernization |  | 2023Q3 | SM | GTSB | 4.6 TSSR Approved | ¦ 0131 - Rollout instruct to release P1500W, BOM Updated. | 2023-05-09 | 2023-07-05 |  | 2023-08-10 |  | Rectificating | 2023-08-16 | 2023-08-22 | E//Hazida | 2023-08-20 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0016 | DU00002040818 |  |  | 2024-02-24 | 2024-02-03 |  | Wall mount boom | IBS + RT (Boom) | 7/6/4 | Add R9264H M901821 x4 ,Dismantle R8854E S1800(A6A) x4 +R8881 S2100 x4+
Q00347 | Q132C_Q00347OD_BOULEVARDMYY | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2023Q4 | ZB | AllStar | 4.6 TSSR Approved |  | 2023-06-30 |  |  |  | 2023-06-30 |  | 2023-07-28 | 2023-10-13 | CD//John | 2023-07-29 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230608-0006 | DU00002040819 |  | 4/9: uncompleted info & phots A lot of missing information and photo. Need to redo the TSSR |  |  | 2025-05-03 |  | IN-BUILDING
B01185_Small Cell | B058B_B01185OD_BDRBARUKLG | Central | 1009K | Swap |  | 2023Q3 | CR | Datasco | 4.6 TSSR Approved |  | 2023-10-31 | 2023-11-06 |  | 2023-11-09 |  | Closed | 2023-11-10 | 2023-12-21 | CD//Sofiah | 2023-12-14 | CelcomDigi_RAN_Datasco_TSS_Central_20231101 | DU00002040820 |  |  | 2023-12-21 | 2023-12-04 |  | Portables BTS | TOWER | SMALL CELL | Add BS8932 x1,Dismantle Celcom small cell
P00025 | P035B_P00025OD_PARADISETGBUNGAH | Northern | 4116K | Decomm |  | 2023Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-05-04 | 2023-07-11 |  | 2023-07-13 | 2023-07-13 | Rectificating | 2023-08-02 | 2023-08-08 | CD//Affendi | 2023-07-25 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0016 | DU00002040821 |  |  |  |  | 2023-10-20 | Wall mount boom | BOOM | 7
Q00275_IBC | Q118B_Q00275OD_MLNG | Sarawak | 9063K | Swap |  | 2023Q3 |  | Trintel | 1.1 Pending Survey - Subcon | [6 empty] | To be Submitted |  |  | CD//Sofiah |  |  | DU00002040822 | [6 empty] | BOOM |  | Add R8862A S2100 x1+R8862A S1800 x1,Dismantle all celcom BBU&RRU(IBC)
P00388_IBC | P035C_P00388OD_TIMESQUAREPG | Northern | 4143K | Decomm |  | 2023Q3 | ZA | YPTT | 4.6 TSSR Approved |  | 2023-10-04 | [5 empty] | 2023-10-04 | 2024-10-07 | CD//Rohizam | 2023-06-21 | Celcom Digi_RAN-YPTT-TSS-Northern-20231108-0042 | DU00002040823 |  |  |  |  | 2024-08-20 |  | BOOM
4869A | HolidayVilla (indoor) | Northern |  | Modernization |  | 2023Q4 | HQ 1 | GTSB | 4.6 TSSR Approved | ¦ 0222 - Revised BOM to follow new EQ power temination at outdoor rectifier. | 2023-06-01 | 2023-06-16 |  | 2023-07-24 |  | Closed | 2023-08-03 | 2023-08-07 | E//Hazida | 2023-08-06 | Celcom Digi_RAN-GTSB-TSS-Northern-20230526-0019 | DU00002040824 |  |  | 2024-03-09 | 2024-01-22 |  | In-Building System | In-building system | 8 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2601 x1,Dismantle R8894E M1821(A8A) x2 | 12(S2->S3,Addition Sector name S2,,rename sectorID,Bisector @new S1/S3)
Q00729 | Q132C_Q00729OD_WISMAPELITA | Sarawak |  | Decomm |  | 2023Q4 | ZB | AllStar | 4.6 TSSR Approved |  | 2023-06-13 |  |  |  | 2023-06-30 |  | 2023-07-28 | 2023-10-13 | CD//John | 2023-07-29 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230608-0006 | DU00002040825 |  | A lot of missing information and photo. Need to redo the TSSR |  |  | 2024-01-22 |  | IN-BUILDING
C00021 | C046C_C00021IB_GENTINGRSTHEPRK | Central |  | Decomm |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-07-20 |  |  |  | 2023-08-15 |  | 2023-09-05 |  | CD//Sofiah | 2023-10-17 | CelcomDigi_RAN_GTSB_TSS_Central_20230721 | DU00002040826 |  | 1) Pls include TX Equipment in Dismantle List 2) Missing FE |  |  | 2025-12-10 |  | IN-BUILDING
3094C | Cinema IMAX | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2024-03-04 | 2023-06-23 |  | 2024-03-20 |  | Closed | 2024-10-25 | 2024-03-29 | E//Kok Keen | 2025-10-02 | CelcomDigi_RANMW_GTSB_TSS_Central_20230620_0005 | DU00002040827 |  |  | 2025-08-20 | 2025-08-08 |  | Pole | IBC + Rooftop | 5m | Add R8894E M1821x4,Dismantle R8862A S1800(B6A) x4+R8862A S2100(A6A) x4 | 0 | 0
3121C_IBC | Amber Court (REL) | Central |  | Remote MOCN |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2024-03-11 | 2024-03-27 |  | 2024-03-29 |  | Closed | 2024-06-06 | 2024-06-14 | E//Nazrul | 2024-06-07 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240316 | DU00002040828 | [5 empty] | Portables BTS | 3m Boom (RT) | IBC | Resue existing RRU
C01254 | C046C_C01254IB_IMAXPOTA_OD | Central |  | Decomm |  | 2023Q4 | CR | GTSB | 4.6 TSSR Approved |  | 2023-07-07 |  |  |  | 2023-08-03 |  | 2023-08-03 | 2026-01-14 | CD//Sofiah | 2025-10-31 | CelcomDigi_RAN_GTSB_TSS_Central_20230707_0034 | DU00002040829 |  |  |  |  | 2025-12-10 |  | BOOM WALL-MOUNTED
1803B | Genting Skyway | Central |  | Modernization |  | 2023Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2023-09-27 | 2023-10-05 |  | 2023-10-10 |  | Rectificating | 2023-10-10 | 2023-10-17 | E//Kok Keen | 2023-10-12 | CelcomDigi_RAN_AllStar_TSS_Central_20231003 | DU00002040830 |  |  | 2024-03-03 | 2024-02-27 |  | In-Building System | 6m RT (Boom) + IBS | 0 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882-GUL1812 x3 +R8840-U216 x3++
C00986 | C046C_C00986OD_SKYWAY_STATION1_GPO | Central |  | Decomm | Decomm->On Hold->Decomm | 2023Q4 | MA | GTSB | 4.6 TSSR Approved |  | 2023-07-04 |  |  |  | 2024-06-28 |  | 2023-10-07 | 2024-01-22 | CD//Ali akaram | 2023-10-12 | CelcomDigi_RAN_GTSB_Central_20230706_0033 | DU00002040831 |  |  |  |  | 2025-12-10 |  | IN-BUILDING
1803B_IBC | Genting Skyway | Central |  | Modernization |  | 2023Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2023-09-25 | 2023-09-27 |  | 2023-10-02 |  | Closed | 2023-10-03 | 2023-10-31 | E//Nazrul | 2023-10-03 | CelcomDigi_RAN_Allstar_TSS_Central_20230927 | DU00002040832 |  |  | 2024-03-04 | 2024-02-27 |  |  | 6m RT (Boom) + IBS |  | Add R8862A S2100 x1+R8862A S1800 x1,Dismantle R8882-GUL1812 x1
3121C | Amber Court (REL) | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-05-25 | 2023-05-29 |  | 2023-06-12 |  | Closed | 2023-06-13 | 2023-06-28 | E//Kok Keen | 2023-06-20 | CelcomDigi_RAN_GTSB_TSS_Central_20230529_0025 | DU00002040833 |  |  | 2023-08-02 | 2023-07-31 |  | Portables BTS | 3m Boom (RT) | 6m | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x2 | 13
C01254_IBC | C046C_C01254IB_IMAXPOTA_OD | Central |  | Decomm |  | 2023Q4 | SHA | GTSB | 4.6 TSSR Approved |  | 2024-08-14 |  |  |  | 2024-09-12 |  | 2024-09-26 | 2025-03-24 | CD//Sofiah | 2024-10-29 | CelcomDigi_RAN_GTSB_TSS_Central_20231230 | DU00002040834 |  |  |  |  | 2025-12-10 |  | IBC
C00006 | C046C_C00006OD_AWANARESORT | Central |  | Decomm | Decomm->On Hold->Swap | 2023Q4 | SH | GTSB | 4.6 TSSR Approved |  | 2024-04-26 | 2024-11-23 |  |  | 2024-05-14 |  | 2025-02-27 | 2025-07-25 | CD//Ali akaram | 2024-09-30 | SQ202411140053 | DU00002040835 |  |  |  |  | 2025-09-22 | Wall mount boom | BOOM | 4m
C00006_IBC | C046C_C00006OD_AWANARESORT | Central | 1894K | Swap | Decomm->On hold->Swap->On Hold | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2024-04-26 | 2024-05-06 |  | 2024-05-27 |  | Closed | 2024-05-29 | 2024-07-23 | CD//Sofiah | 2024-07-15 | CelcomDigi_RAN_GTSB_TSS_Central_20240513 | DU00002040836 |  |  | 2025-07-16 | 2025-07-08 |  | Portables BTS | BOOM |  | Add R8862A S2100 x3+R8862A S2601 x3+R8862A S1800 x3,Dismantle
3094C_IBC | Cinema IMAX | Central |  | Modernization |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-23 | 2023-11-29 |  | 2023-12-12 |  | Closed | 2023-12-21 | 2023-12-26 | E//Nazrul | 2023-12-23 | CelcomDigi_RAN_GTSB_TSS_Central_20231126 | DU00002040837 |  |  | 2025-09-30 | 2025-09-29 |  | Portables BTS | IBC + Rooftop |  | Add R8894E M1821x2
C00986_IBC | C046C_C00986OD_SKYWAY_STATION1_GPO | Central |  | Decomm | Decomm->On Hold->Decomm | 2023Q4 | AI | GTSB | 4.4 Pending TSSR Review - Design Team |  | 2026-02-04 |  |  |  | 2026-02-04 | To be Submitted |  |  | CD//Sapian |  | SQ202604230192 | DU00002040838 |  |  |  |  | 2025-12-10 |  | BOOM
C00011_IBC | C046C_C00011OD_RESORTHOTELSL | Central | 1186K | Swap |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2024-03-04 | 2023-11-21 |  | 2024-03-11 |  | Closed | 2024-07-03 | 2024-12-06 | CD//Sofiah | 2024-12-06 | CelcomDigi_RAN_GTSB_TSS_Central_20231017 | DU00002040839 |  |  | 2026-01-08 | 2025-11-24 |  | Portables BTS | BOOM |  | Add R8862A S2100 x3+R8862A S1800 x3+R8862A S2601 x3,Dismantle all celcom BBU&RRU(IBC)
C00011 | C046C_C00011OD_RESORTHOTELSL | Central | 1186K | Swap |  | 2023Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2024-03-04 | 2023-07-12 |  | 2024-03-14 |  | Under Approval | 2024-05-10 | 2025-09-29 | CD//Sapian | 2025-06-24 | CelcomDigi_RAN_GTSB_TSS_Central_20230622_0031 | DU00002040840 |  |  | 2026-01-13 | 2025-11-25 |  |  | BOOM | 19 | Add R8852E S9000x3+R8894E M1821x3+R8862A S2601x3, Dismantle | 0 | 0
1243C | Jalan Setia Murni | Central |  | Modernization |  | 2023Q3 | IE | Magicell | 4.6 TSSR Approved |  | 2023-07-14 | 2023-07-21 |  | 2023-07-18 |  | Closed | 2023-07-19 | 2023-07-28 | E//Razif | 2023-07-26 | CelcomDigi_RAN_Magicell_TSS_Central_20230717 | DU00002471804 |  |  | 2023-08-17 | 2023-08-01 |  | Monople Tree | landside | 35m | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x4 | 23
K01072 | K009A_K01072OD_Kg_Tong_Pelu | Northern | 4049P | Swap | Swap | 2025 | AI | CCSMY | 1.1 Pending Survey - Subcon | [6 empty] | To be Submitted | [5 empty] | DU00006291936 | [8 empty] | Add R8852E S9000 x3+R9264M M1821 x3+R8894E M1821x3
K00672 | K008A_K00672OD_PULAUDAYANGBUNTING | Northern |  | Decomm |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-07-13 |  |  |  | 2023-07-22 |  | 2023-08-17 | 2023-09-18 | CD//Quah | 2023-09-29 | Celcom Digi_RAN-GCI-TSS-Northern-20230712-0036/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240529-0109 | DU00002542065 |  | No TX Info, Photo not enough |  |  | 2023-10-27 |  | TOWER
K00465 | K008A_K00465OD_PULAUTUBA | Northern | 4163K | Swap | Swap->On Hold->Swap | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-07-12 | 2023-07-12 |  | 2023-07-12 |  | Closed | 2023-07-15 | 2023-07-15 | CD//Quah | 2023-07-14 | Celcom Digi_RAN-GCI-TSS-Northern-20230712-0036 | DU00002542066 |  |  | 2023-07-31 | 2023-07-17 |  | Tower | TOWER | 60 | Add R9264H M901821 x3,Dismantle all celcom BBU&RRU
4159C | USP_Pulau Dayang Bunting | Northern |  | Modernization |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-07-13 | 2023-07-14 |  | 2023-07-15 |  | Closed | 2023-07-18 | 2023-07-18 | CD//Quah | 2023-07-17 | Celcom Digi_RAN-GCI-TSS-Northern-20230712-0036 | DU00002542067 |  |  | 2023-07-27 | 2023-07-22 |  | Tower | 95m Tower 4 legged | 93 | Add R8852E S9000 x4+R8894E M1821 x4,Dismantle R8862A S1800(B6A) x2+R8862A S2100(A6A) x2
4096R | 6148_PulauTuba_PUBAM1_43 | Northern |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2023Q3 |  | GTSB | 1.1 Pending Survey - Subcon | [6 empty] | To be Submitted |  |  |  |  | SQ202504230446-GTSB | DU00002542068 | [6 empty] | TOWER
4014D | SMK PULAU TUBA_LUBUK CHEMPEDAK PULAU TUBA | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002542069 | [6 empty] | 45M Tower
1726A | Tmn Sri Watan | Central |  | Site Out (Modernization) | Modernization->Site Out->Replacement, Site Out (Modernization) | 2024 Q4 | AI | GCI | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2025-07-04 | 2025-07-14 |  |  |  | To be Submitted |  |  |  |  | SQ202506140192 | DU00002865769 |  |  |  |  | 2025-08-05 |  | 3m Boom (RT) |  |  | 13 | 0
3393A | Putra-Cyber2 | Central |  | Modernization |  | 2024 Additional | SHA | GCI | 4.6 TSSR Approved |  | 2024-02-14 | 2024-03-01 |  | 2024-12-05 |  | Under Approval | 2024-12-15 | 2024-12-16 | E//Razif | 2024-12-16 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240217 | DU00002592769 |  |  | 2025-08-18 | 2025-08-15 |  | Monopole | 30m Monopole | 45 | Add R9264M M1821x5+R8862A S2601x2,Dismantle R8862A S2100(A6A)x3+R8894E M1821(A8A)x3 | 0 | 12
9452A | Gold Jade MP | Sarawak |  | Modernization |  | 2024 Q1 | ZB | AllStar | 4.6 TSSR Approved |  | 2023-09-06 | 2023-08-16 |  | 2023-10-09 |  | Closed | 2024-01-29 | 2024-01-30 | E//Hannah | 2024-01-30 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230915 | DU00002592770 |  |  | 2024-02-03 | 2024-01-30 |  | Monopole | 30m Monopole | 30 | Add R8862A S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3+R8882 S2600(B4A) x1 | 0 | 1
7811A | IOFC Indoor | Sabah |  | Remote MOCN | Modernization->On hold->Modernization->Remote MOCN | 2024 Q3(single site MOCN) |  | YPTT | 14.2 Drop (Done Survey) |  | 2023-12-05 |  |  |  |  | To be Submitted | [5 empty] | DU00002592774
9219B | Kolej Cempaka | Sarawak |  | Modernization |  | 2024 Q2 | SH | Magicell | 4.6 TSSR Approved |  | 2023-12-10 | 2023-12-14 |  | 2023-12-18 |  | Closed | 2024-04-24 | 2024-06-12 | E//Hannah | 2024-06-12 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20240123 | DU00002592775 |  |  | 2024-07-15 | 2024-07-11 |  | Tower | 30m Monopole | 30 | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R8882 S1800B(B6B) x3 | 1 | 0
4620A | Kg Repuh | Northern |  | Modernization |  | 2024 Q4 | BY | YPTT | 4.6 TSSR Approved |  | 2023-10-26 |  |  | 2024-04-23 |  | Rectificating | 2024-04-25 | 2024-05-20 | E//Hazida | 2024-05-17 | Celcom Digi_RAN-YPTT-TSS-Northern-20231028-0040 | DU00002592777 |  |  | 2024-05-20 | 2024-05-16 |  |  | 60m 3 Legged Tower |  | Add R8862A S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882-GUL1812 x3+R8862A S2600(A4A) x1+R8840-U216 x3++ | 0 | 1
7449B | Jalan Leila | Sabah |  | Modernization |  | 2024 Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2024-03-14 | 2024-05-13 |  | 2024-05-16 |  | Closed | 2024-05-16 | 2024-05-30 | E//Hannah | 2024-05-30 | Celcom Digi_RAN-YPTT-Standard PR TSS-Sabah-20240313 | DU00002592782 |  |  | 2024-06-27 | 2024-06-19 |  | In-Building System | 6m RT (Wall Mounted Pole) | 6 | Add R8862A S9000 x3+A9732 M1821 x3,Dismantle R8854 S2600(A4A) x3+R8894E M1821(A8A) x6 | 123 | 0
9224A | Sri Aman Town | Sarawak |  | Modernization | Modernization->On Hold->Modernization | 2025 Q3 | SM | Magicell | 4.6 TSSR Approved | 0218 - Emailedplanning on CD comment 0205 - Emailed Rollout on PE Required | 2024-04-06 | 2024-04-25 |  | 2024-04-30 |  | Rectificating | 2025-02-05 | 2025-03-10 | E//Hannah | 2025-03-04 | 0911CD-Sarawak-Magicell-BOQ Template (old contract) | DU00002592795 |  |  | 2025-04-19 | 2025-04-11 |  | In-Building System | 3m RT (Wall Mounted Pole) | 6M | Add R8862A S9000 x3+R9264H M901821 x1+A9732 M1821 x3,Dismantle R9224E M1821(AAB) x4 | 124 | 0
9392A | Jalan Berus Sarikei | Sarawak |  | Modernization |  | 2024 Q4(single site MOCN)-L21 SSM | SH | Trintel | 4.6 TSSR Approved |  | 2024-01-02 | 2024-01-09 |  | 2024-04-08 |  | Under Approval | 2024-04-16 | 2024-12-16 | E//Hannah | 2024-10-23 | 0920CD-Sarawak-Trintel-BOQ Template (old contract) | DU00002592797 |  |  | 2024-11-13 | 2024-11-02 |  | Monopole | Tower | 31 | Add R8894E M1821 x2,Dismantle | 0 | 13
7419A | Kg Bongaliu | Sabah |  | Modernization |  | 2024 Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-11-03 | 2023-11-03 |  | 2024-03-27 |  | Closed | 2024-03-28 | 2024-04-03 | E//Hannah | 2024-04-03 | N/A-Under BAU | DU00002592800 |  |  | 2024-05-09 | 2024-05-07 |  | Tower | Tower | 60 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882 S1800(B) x2+R8862A S1800(B6A) x1 | 0 | 0
4655B | Kolej Kediaman Bkt Kachi(Maxis) | Northern |  | Modernization |  | 2024 Q3 | SM | YPTT | 4.6 TSSR Approved | ¦ 0330 - Solution updated, need to submit new solution. | 2023-10-26 | 2023-10-31 |  | 2023-11-06 |  | Rectificating | 2024-04-05 | 2024-04-15 | E//Hazida | 2024-04-05 | Celcom Digi_RAN-YPTT-TSS-Northern-20231028-0040 | DU00002592801 |  |  | 2024-04-17 | 2024-04-17 |  | Tower | 60m 4 Legged Tower | 60m | Add R8862A S9000 x2+A9732 M1821 x2,Dismantle R8882-GUL1812 x4+R8862A S2100(A6A) x2 | 12 | 0
7019A | Kg. Lajung | Sabah |  | Modernization |  | 2025 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2023-11-10 | 2024-04-23 |  | 2025-02-18 |  | Under Approval | 2025-04-16 | 2025-05-21 | E//Hannah | 2025-05-07 | Under BAU | DU00002592802 |  |  | 2025-04-29 | 2025-04-24 |  | Tower | Tower | 76 | Add R8852E S9000x1+R8894E M1821x1+R8862A S2601x1, Dismantle R8862A S1800(B6A)x2+R8854D S2100(A4A)x2 | 0 | 0
7525A | Kg Kinuta | Sabah |  | Modernization |  | 2024 Q1 | AD | Futong | 4.6 TSSR Approved |  | 2023-10-04 | 2023-08-07 |  | 2023-10-05 |  | Closed | 2023-12-07 | 2024-02-08 | E//Hannah | 2024-02-08 | Celcom Digi_RAN-Futong-TSS-Sabah-20231006 | DU00002592803 |  |  | 2024-02-01 | 2023-12-18 |  | Tower | 60m 3 Legged Tower | 60 | Add R8862A S9000 x3+R9224E M1821 x2+R8854 S2600 x2,Dismantle R8862A S2600(A4A) x2 | 0 | 13
3142C | Jalan Madrasah | Central |  | Modernization |  | 2024 Q1 | AI | AllStar | 4.6 TSSR Approved |  | 2023-11-17 | 2023-11-20 |  | 2023-12-28 |  | Closed | 2023-12-29 | 2023-12-29 | E//Kok Keen | 2023-12-29 | CelcomDigi_RAN_AllStar_TSS_Central_20231119 | DU00002592807 |  |  | 2024-03-26 | 2024-03-26 |  | Lampole | Tower | 18 | Add R9264M M1821 x3,Dismantle R8892E M1821(BAA) x3
7461B | Tung Hup Estate (Celcom) | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-02-05 | 2025-02-14 |  | 2025-02-17 |  | Under Approval | 2025-02-19 | 2025-03-09 | E//Hannah | 2025-02-26 | SQ202501030059 - Futong | DU00002592808 | Remarks: Solution TSSR/BOM Changed |  | 2025-07-06 | 2025-05-16 |  | Tower | 60m 3 Legged Tower | 60m | Reuse Existing RRU | 0 | 0
9663B | Celcom Kuala Lawas | Sarawak |  | Modernization | Modernization->On Hold->Modernization | 2025 Q2 | AD | CCSMY | 4.6 TSSR Approved |  | 2025-07-03 | 2025-07-14 |  | 2025-07-16 |  | Under Approval | 2025-07-21 | 2025-09-12 | E//John | 2025-07-21 | SQ202506060165-CCSMY | DU00002592811 |  |  | 2025-09-11 | 2025-09-04 |  | Tower | Tower | 60 | Add R8894E M1821x1, Dismantle R8854E S1800(A6A)x3 | 0 | 1
9296A | Long Lama (Celcom) | Sarawak |  | Modernization | Modernization->On Hold->Modernization | 2025 Q2 | AI | Trintel | 4.6 TSSR Approved |  | 2025-03-04 | 2025-03-25 |  | 2025-04-14 |  | Under Approval | 2025-04-14 | 2025-05-02 | E//Hannah | 2025-04-21 | SQ202501070293-Trintel | DU00002592812 |  |  | 2025-07-06 | 2025-05-29 |  | Tower | Tower | 100 | Add R8894E M1821x2, Dismantal R8854E S1800(A6A)x3 | 0 | 23
7575A | Berkat Setia | Sabah |  | Modernization |  | 2024 Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2024-04-04 | 2024-05-08 |  | 2024-09-07 |  | Under Approval | 2024-07-22 | 2024-08-06 | E//Hannah | 2024-07-30 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240406 | DU00002592814 |  |  | 2024-08-30 | 2024-08-15 |  | Tower | Tower | 60m | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle R8862A S2600(A4A) x1 | 0 | 2
7380A | Kg Padas Damit | Sabah |  | Modernization | Modernization->On Hold->Maintain USP MOCN->Modernization | 2025 Q1 | AD | Futong | 4.6 TSSR Approved |  | 2025-04-09 |  |  | 2025-04-09 |  | Under Approval | 2025-04-11 | 2025-04-22 | E//Hannah | 2025-04-22 | SQ202504100607- Futong | DU00002592816 |  |  | 2025-05-31 | 2025-04-28 |  | Tower | 60m 4 Legged Tower | 60 | Add R8894E M1821x2, Dismantle R8854E S1800(A6A)x3 | 0 | 23
9575A | Kg Tiris | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002592819 | [6 empty] | 76m 3 Legged Tower
7385A | Kg Kilugus | Sabah |  | Modernization | Modernization->On Hold->Maintain USP MOCN->Modernization | 2025 Q1 | AD | Futong | 4.6 TSSR Approved |  | 2025-04-09 | 2023-08-07 |  | 2025-04-09 |  | Under Approval | 2025-04-11 | 2025-05-21 | E//Hannah | 2025-04-21 | SQ202504100607- Futong | DU00002592820 | Remarks: Solution TSSR/BOM Changed |  | 2025-05-28 | 2025-05-23 |  | Tower | 45m 3 Legged Tower | 60 | Add R9264M M1821x3, Dismantle R8894E M1821(A8A)x3 | 0 | 0
7403B | Golden Hill (REL) | Sabah |  | Modernization |  | 2024 Q1 | MS | GTSB | 4.6 TSSR Approved |  | 2023-09-11 |  |  | 2023-10-11 |  | Closed | 2023-12-06 | 2023-12-20 | E//Hannah | 2023-12-15 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230913 | DU00002592821 |  |  | 2024-01-19 | 2024-01-13 |  | Monopole | 30m Monopole | 30 | Add R8852E S9000 x3+R8894E M1821 x1+R8854 S2600 x1,Dismantle R8882 S2600(B4A) x1 | 0 | 3
7782B | Bakong-Bakong | Sabah |  | Modernization |  | 2024 Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2024-04-30 | 2024-05-06 |  | 2024-05-15 |  | Closed | 2024-05-16 | 2024-06-14 | E//Hannah | 2024-06-14 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240503 | DU00002592822 |  |  | 2024-09-18 |  |  | Tower | 60m 4 Legged Tower | 75 | Dismantle R8862A S2100(A6A) x3 | 0 | 0
7084A | IOFC | Sabah |  | Modernization |  | 2024 Q3(single site MOCN) | MS | Seri Pancar | 4.6 TSSR Approved |  | 2023-12-15 | 2024-05-15 |  | 2024-06-24 |  | Under Approval | 2024-06-26 | 2024-07-04 | E//Hannah | 2024-07-04 | Celcom Digi_RAN-Seri Pancar-Standard PR TSS-Sabah-20240425 | DU00002592823 |  |  | 2024-10-30 | 2024-10-23 |  | In-Building System | 3m Boom (RT) | 4 | Add R8862A S9000 x3+A9732 M1821 x3,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x5 | 123 | 0
3188A | Jln BRP8 | Central |  | Modernization |  | 2024 Q1 | XH | AllStar | 4.6 TSSR Approved |  | 2023-09-15 | 2023-11-02 |  | 2023-12-01 |  | Closed | 2023-12-04 | 2023-12-20 | E//Kok Keen | 2023-12-20 | CelcomDigi_RAN_AllStar_TSS_Central_20230918 | DU00002592824 |  |  | 2023-12-27 | 2023-12-22 |  | Tower | Tower | 40 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
2265A | Persiaran Wawasan Bangi | Central |  | Modernization |  | 2024 Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-10-19 | 2023-12-14 |  | 2024-04-19 |  | Closed | 2024-05-03 | 2024-05-14 | E//Sumitra | 2024-05-14 | Wireless_Malaysia CD_TSS_ALLSTAR_ 6 site SQ202411010178 | DU00002592826 |  |  | 2024-06-19 | 2024-06-18 |  | In-Building System | 3m Bipod (RT) | 6 | Add R8894E M1821 x3,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 | 0 | 0
9097A | Bukit Lambir(Celcom) | Sarawak |  | Modernization |  | 2025 Q2 | SM | Trintel | 4.6 TSSR Approved |  | 2024-03-20 | 2024-03-27 |  | 2024-04-18 |  | Closed | 2024-04-23 | 2025-03-10 | E//Hannah | 2025-03-04 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20240324 | DU00002592827 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed | 2025-05-23 | 2025-04-15 |  | Tower | Tower | 106m | Add R8852E S9000x1+R8894E M1821x3+R8862A S2601x1, Dismantle RR8862A S1800(B6A)x2 | 0 | 0
7401A | RTM Station | Sabah |  | Modernization |  | 2024 Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-10-24 | 2023-11-06 |  | 2024-03-27 |  | Closed | 2024-03-28 | 2024-04-02 | E//Hannah | 2024-04-02 | N/A-Under BAU | DU00002592828 |  |  | 2024-05-23 | 2024-05-17 |  | Tower | 76m Tower | 100 | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x5 | 123 | 0
7465B | Pangkalan Lalasun (tg Pisau) | Sabah |  | Modernization |  | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2024-04-19 | 2024-04-22 |  | 2024-05-02 |  | Closed | 2024-05-10 | 2024-05-16 | E//Hannah | 2024-05-16 | 0626Sabah-Futong-BOQ Template (template) | DU00002592830 |  |  | 2024-06-15 | 2024-06-04 |  | Tower | 60m 4 Legged Tower | 60 | Add R9224E M1821 x3,Dismantle R8862A S1800(B6A) x3 | 0 | 0
9422B | UiTM Samarahan New | Sarawak |  | Modernization |  | 2024 Q2 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-11-27 | 2023-12-01 |  | 2024-03-08 |  | Closed | 2024-03-05 | 2024-03-07 | E//Hannah | 2024-03-07 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20240123 | DU00002592835 |  |  | 2024-07-04 | 2024-06-26 |  | Monopole | 30m RDS | 30 | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R9224E M1821(AAB) x3 | 23 | 0
9163A | Kg. Simpok | Sarawak |  | Modernization |  | 2025 Q1 | HW | Trintel | 4.6 TSSR Approved |  | 2025-04-15 | 2025-04-28 |  | 2025-04-30 |  | Under Approval | 2025-05-05 | 2025-05-21 | E//Hannah | 2025-05-18 | SQ202505020084-Trintel | DU00002592837 |  |  | 2025-06-12 | 2025-06-09 |  | Tower | Tower | 76 | Add R8894E M1821x1 | 0 | 1
9273B | Tulai(Sacofa) | Sarawak |  | Remote MOCN | Modernization->On Hold->Modernization->Remote MOCN | 2025 Q2 | AI | Trintel | 14.0 TSSR Not Required (Reuse Existing BBU/RRU) |  | 2025-03-11 | 2025-04-28 |  | 2025-05-02 |  | Under Approval | 2025-05-02 |  | E//Hannah |  | SQ202501070293-Trintel | DU00002592838 | [5 empty] | Tower | 45m 3 Legged Tower | 60 | Reuse Existing RRU | 0 | 0
7328A | Kg Napang | Sabah |  | Modernization |  | 131 single site mocn | AD | Futong | 4.6 TSSR Approved |  | 2024-08-13 | 2024-08-16 |  | 2024-08-21 |  | Under Approval | 2024-08-22 | 2024-08-26 |  | 2024-08-23 | 0809CD-Sabah-Futong-BOQ Template(new contract) | DU00002592839 |  |  | 2024-09-26 | 2024-09-20 |  | Tower | Tower | 76 | Add R8894E M1821 x1,Dismantle | 0 | 2
7460B | Kg Sukau TMB | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-03-12 | 2025-03-17 |  | 2025-03-20 |  | Under Approval | 2025-03-22 | 2025-05-21 | E//Hannah | 2025-04-02 | SQ202501030059 - Futong | DU00002592844 |  |  | 2025-09-24 | 2025-09-20 |  | Tower | 76m Tower | 76m | Reuse Existing RRU | 0 | 0
7540A | Tiara Hotel RT | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2025 Q1 | AD | Datasco | 4.6 TSSR Approved |  | 2024-05-23 | 2024-05-28 |  | 2025-01-13 |  | Under Approval | 2025-01-20 | 2025-04-29 | E//Yanie | 2025-04-28 | SQ202501020441 - Datasco | DU00002592845 |  |  | 2025-02-17 | 2025-02-07 |  | Wall mount boom | 3m Boom (RT) | 6 | Add R8852E S9000x3+R9264M M1821x3, Dismantle R8882 S1800B(B6B)x2+R8862A S1800(B6A)x1 | 0 | 0
4435B | Kg Talang Tengah RCD | Northern |  | Modernization |  | 154 single site MOCN | SHA | YPTT | 4.6 TSSR Approved |  | 2023-12-05 | 2023-11-15 |  | 2024-08-20 |  | Under Approval | 2024-09-05 | 2024-09-23 | E//Ajay | 2024-09-22 | Celcom Digi_RAN-YPTT-TSS-Northern-20240513-0064 | DU00002592846 |  |  | 2024-09-30 | 2024-09-26 |  | Tower | 60m 3 Legged Tower | 60 | Add R8862A S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8860E-GU908 x2+R8882-GUL1812 x1+R8862A S1800(B6A) x3 | 0 | 3
7124B | Lembaga Pelabuhan RT | Sabah |  | Modernization |  | 2024 Q2 | MS | NR services | 4.6 TSSR Approved |  | 2023-09-19 | 2024-01-11 |  | 2024-01-16 |  | Closed | 2024-03-11 | 2024-03-18 | E//Hannah | 2024-03-18 | Celcom Digi_RAN-NR Services-TSS-Sabah-20230921 | DU00002592848 |  |  | 2024-07-29 | 2024-04-01 |  | In-Building System | 3m Boom (RT) | 3m | Add R8894E M1821 x5+R9264M M1821 x1+R8854 S2600 x2,Dismantle R8882 S1800(B) x3+R8882 S1800B(B6B) x1+R8881 S2100 x1+R8854D S2100(A4A) x3+R8882 S2600(B4A) x2 | 0 | 14
7036B | Kg. Batu Tulog | Sabah |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q3 | MS | YPTT | 4.1 Pending TSSR Submission - Subcon |  | 2023-11-14 | 2024-07-06 |  |  |  | To be Submitted |  |  |  |  | Under BAU | DU00002592851 | [5 empty] | Tower | Tower | 60 | Add R9264M M1821x4, Dismantle R8894E M1821(A8A)x3 | 0 | 2
4609B | Bt Pahat | Northern |  | Modernization |  | 2024 Q4 | BY | YPTT | 4.6 TSSR Approved |  | 2023-12-29 | 2024-01-10 |  | 2024-04-25 |  | Closed | 2024-05-07 | 2024-05-09 |  | 2024-05-09 | Celcom Digi_RAN-YPTT-TSS-Northern-20240101-0050 | DU00002592852 |  |  | 2024-05-14 | 2024-05-11 |  | Tower | 76m 4 Legged Tower | 76 | Add R8862A S9000 x1+R8894E M1821 x3,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x1+R8862A S2100(A6A) x2 | 0 | 0
7388B | Hospital Lahad Datu | Sabah |  | Modernization |  | 2024 Q3 | MS | GTSB | 4.6 TSSR Approved |  | 2023-10-23 | 2023-11-06 |  | 2024-04-04 |  | Closed | 2024-04-05 | 2024-05-29 | E//Hannah | 2024-05-29 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231130 | DU00002592853 |  |  | 2024-07-12 | 2024-06-04 |  | Monopole | 3m Boom (RT) | 30m | Add R8862A S9000 x3+A9732 M1821 x3,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x5 | 123 | 0
1133B | Kg Sg Lalang | Central |  | Modernization |  | 154 single site MOCN | BY | GCI | 4.6 TSSR Approved |  | 2024-02-14 | 2024-02-26 |  | 2024-05-29 |  | Closed | 2024-05-30 | 2024-06-12 | E//Sumitra | 2024-06-11 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240217 | DU00002592856 |  |  | 2024-06-14 | 2024-06-11 |  | Tower | 60m 4 Legged Tower | 50 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123 | 0
9431A | Kg Sebigo | Sarawak |  | Modernization | Maintain USP MOCN->On Hold->Maintain USP MOCN->Modernization | 2024 Q2 | AI | Trintel | 4.6 TSSR Approved |  | 2025-04-30 | 2025-04-24 |  | 2025-04-30 |  | Closed | 2025-04-30 | 2025-05-17 | E//Hannah | 2025-05-16 | SQ202505020084-Trintel | DU00002592857 |  |  | 2025-05-18 | 2025-05-16 |  | Tower |  | 76 | Add R8894E M1821x1, Dismantle R8854E S1800(A6A)x3 | 0 | 3
4378B | Kati (AsiaSpace) RDD | Northern |  | Modernization |  | 154 single site MOCN | SM | CCSMY | 4.6 TSSR Approved |  | 2024-09-05 | 2024-09-10 |  | 2024-09-10 |  | Under Approval | 2024-09-24 | 2024-09-25 | E//Hazida | 2024-09-25 | 0809CD-Northern-CCSMY-BOQ Template(new contract) | DU00002592859 |  |  | 2024-10-12 | 2024-09-30 |  | Tower | Tower | 70 | Add R8862A S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8860E-GU908 x3+R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3 | 0 | 2
7430A | Kampung Pirasan | Sabah |  | Decomm | Modernization->On Hold-Decomm | 2024 Q3 | AD | YPTT | 4.6 TSSR Approved | 29/3/2024: Email submit to RF Planner as Mr Duan Instruction for change Anchor confirmation. | 2023-10-24 | 2023-11-02 | 2025-03-06 | 2024-03-27 | 2025-03-20 | Under Approval | 2024-05-06 | 2024-07-19 | E//Hannah | 2025-04-21 | 0813CD-Sabah-YPTT-BOQ Template(new contract). | DU00002592860 |  |  |  |  | 2025-03-27 | Monopole | 30m Monopole | 30
7267A | Tmn Penampang PH2 | Sabah |  | Modernization |  | 2024 Q1 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2023-09-17 | 2023-10-16 |  | 2023-10-21 |  | Closed | 2023-10-24 | 2023-10-27 | E//Hannah | 2023-10-26 | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20230923 | DU00002592863 |  |  | 2023-10-27 | 2023-10-27 |  | Tower | 45m 3 Legged Tower | 45 | Add A9732 M1821 x3,Dismantle R8882-L268 x3+R8894E M1821(A8A) x6 | 123
7382A | Kg Kuala Mengalong | Sabah |  | Modernization |  | 2025 Q2 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2023-10-27 | 2023-11-20 |  | 2025-01-22 |  | Under Approval | 2025-02-17 | 2025-03-24 | E//Hannah | 2025-03-10 | Celcom Digi_RAN-Seri Pancar-Standard PR TSS-Sabah-20240425 (The Cluster Sequence of site 7382A is:2025. The survey and design settlement method is being communicated with the customer. - Shi Handing) | DU00002592867 |  |  | 2025-03-24 | 2025-03-13 |  | Tower | 60m 4 Legged Tower | 60 | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8882-GUL1812x2+R8862A S1800(B6A)x1 | 0 | 0
1690C | Apartment Parcel 12 | Central |  | Decomm | Modernization->Decomm | 2024 Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2024-01-18 | 2024-02-23 | 2024-07-18 | 2024-04-18 | 2024-07-23 | Closed | 2024-07-23 | 2024-12-09 | E//Razif | 2024-07-23 | Wireless_Malaysia CD_TSS_ALLSTAR_ 6 site SQ202411010178 | DU00002592869 |  |  |  |  | 2024-11-20 | In-Building System | Building | 3
9831B | KAMPUNG SAMPUN | Sarawak |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002592872 | [6 empty] | #N/A
4408D | Banggol Pasir | Northern |  | Modernization |  | 2024 Q2 | WP | YPTT | 4.6 TSSR Approved | ¦ 0313 - Revised TSSR submitted with explanation for L26 upgrade not uniform. ¦ 0228 - Listed for solution change, pending confirmed solution ¦ 0207 - YPTT, plan re-TSS 13/2 ¦ 0126 - Rejcted: planner comment to confirm if have COLO, Pending YPTT re-TSS | 2023-12-05 | 2024-09-12 |  | 2024-01-10 |  | Closed | 2024-03-06 | 2024-03-26 | E//Hazida | 2024-03-25 | Under BAU | DU00002592873 |  |  | 2024-04-03 | 2024-03-29 |  | Tower | 61M TWR | 60 | Add R8852E S9000 x2+R9264H M901821 x1+R8862A S2601 x2+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3+R8862A S2100(A6A) x3 | 23 | 0
9088B | Foo Chow | Sarawak |  | Modernization |  | 2024 Q1 | SH | AllStar | 4.6 TSSR Approved |  | 2023-09-26 | 2023-10-02 |  | 2023-11-16 |  | Closed | 2023-12-06 | 2024-01-16 | E//Hannah | 2024-01-15 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230930 | DU00002592875 |  |  | 2023-12-27 | 2023-12-13 |  |  | 24m Lampole | 30 | Add R8894E M1821 x5+R8854 S2600 x2,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R8862A S2600(A4A) x2 | 0 | 12
7487B | Kg Gaban | Sabah |  | Modernization |  | 2024 Q3(single site MOCN) | AD | GTSB | 4.6 TSSR Approved | Solution changed MM>Bi | 2023-12-15 | 2024-01-10 |  | 2024-06-21 |  | Under Approval | 2024-07-04 | 2024-08-19 | E//Hannah | 2024-08-19 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240313 | DU00002592876 |  |  | 2024-09-20 | 2024-09-03 |  | Tower | 76m 3 Legged Tower | 76m | Add R8894E M1821 x1,Dismantle R8854 S2600(A4A) x1 | 0 | 13
7399A | Kg. Tigaman SBC | Sabah |  | Maintain USP MOCN | Modernization->On Hold->Maintain USP MOCN | 2025 Q3 |  | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002592879 | [6 empty] | Tower |  | Reuse Existing RRU | 0 | 0
7129A | Secretariet MPS | Sabah |  | Modernization |  | 2024 Q3 | AD | Datasco | 4.6 TSSR Approved |  | 2024-03-30 | 2024-04-22 |  | 2024-04-22 |  | Closed | 2024-04-22 | 2024-04-24 | E//Hannah | 2024-04-24 | Celcom Digi_RAN-Datasco-Standard PR TSS-Sabah-20240406 | DU00002592882 |  |  | 2024-06-26 | 2024-06-21 |  | Minimast | 3m RT (Minimast) | 12 | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x6 | 3 | 0
9386B | Balingian | Sarawak |  | Modernization | Modernization->On Hold->Modernization | 2025 Q2 | AI | Trintel | 4.6 TSSR Approved |  | 2025-03-19 | 2025-04-09 |  | 2025-04-24 |  | Under Approval | 2025-04-24 | 2025-05-21 | E//Hannah | 2025-05-08 | SQ202501070293-Trintel | DU00002592883 |  |  | 2025-07-06 | 2025-06-24 |  | Tower | 60m 4 Legged Tower | 100 | Add R8894E M1821x1, Dismantle R8854E S1800(A6A)x3 | 0 | 2
9442A | Jalan Palm MP | Sarawak |  | Modernization |  | 2024 Q1 | ZB | AllStar | 4.6 TSSR Approved |  | 2023-09-06 | 2023-08-22 |  | 2023-10-09 |  | Closed | 2024-01-29 | 2024-01-30 | E//Hannah | 2024-01-30 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230915 | DU00002592886 |  |  | 2024-02-06 | 2024-01-30 |  | Monopole | 30m Monopole | 30 | Add R8854 S2600 x3,Dismantle R8882 S2600(B4A) x3 | 0 | 123
9060A | Teluk Baruk Samarahan | Sarawak |  | Modernization |  | 2024 Q2 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-11-28 | 2023-12-01 |  | 2023-12-14 |  | Closed | 2024-03-06 | 2024-03-08 | E//Hannah | 2024-03-08 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20240123 | DU00002592887 |  |  | 2024-07-11 | 2024-06-20 |  | Tower | 45m 3 Legged Tower | 61 | Add R8862A S9000 x4+R9224E M1821 x2+R8854 S2600 x2,Dismantle R8862A S2600(A4A) x2 | 0 | 13
7372A | Sinapokon (Celcom) | Sabah |  | Modernization | Modernization->On Hold->Maintain USP MOCN->Modernization | 2025 Q1 | AD | Datasco | 4.6 TSSR Approved |  | 2025-05-19 | 2025-05-21 |  | 2025-05-23 |  | Under Approval | 2025-05-23 | 2025-07-11 | E//Hannah | 2025-05-30 | SQ202505190134 - Datasco | DU00002592888 |  |  | 2025-09-29 | 2025-08-18 |  | Tower | Tower | 76 | Add R8894E M1821x1 | 0 | 1
7344A | Gunung Alab Trunk | Sabah |  | Modernization |  | 2024 Q3(single site MOCN) | AD | Futong | 4.6 TSSR Approved |  | 2023-10-30 | 2023-11-02 |  | 2024-08-19 |  | Under Approval | 2024-08-20 | 2024-09-06 | E//Hannah | 2024-08-23 | 0626Sabah-Futong-BOQ Template (template) | DU00002592889 |  |  | 2024-09-25 | 2024-09-09 |  | Tower | 106m 4 Legged Tower | 110 | Add R9224E M1821 x3,Dismantle R8862A S1800(B6A) x3 | 0 | 0
9521A | Tmn Tunku Junction | Sarawak |  | Modernization |  | 2025 Q1 | AI | Trintel | 4.6 TSSR Approved |  | 2024-03-13 | 2024-03-20 |  | 2025-02-18 |  | Under Approval | 2025-03-11 | 2025-04-15 | E//Hannah | 2025-03-20 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240313 | DU00002592891 | Remarks: Solution TSSR/BOM Changed |  | 2025-07-29 | 2025-05-06 |  | Monopole | 30m Monopole | 36 | Add R8852E S9000x4+R8894E M1821x2+R8854 S2600x1 | 0 | 4
9029A | King s Centre | Sarawak |  | Modernization |  | 2024 Q1 | ZB | AllStar | 4.6 TSSR Approved |  | 2023-10-05 | 2023-10-17 |  | 2023-10-23 |  | Closed | 2023-12-13 | 2023-12-26 | E//Hannah | 2023-12-26 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20231005 | DU00002592892 |  | 2612 1. Wrong site type & structure type. -Done revised 2. Please confirm antenna height for AAU sector 2 & etilit for sector 3. -Antenna Height for AAU Sector is 45m -Etilt for Sector 3 has been changed according to ML 3. Please amend RRU 900 model follow as per ML. -Done revised | 2024-02-09 | 2024-01-06 |  | In-Building System | 6m RT (Wall Mounted Pole) | 6m | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x5 | 12 | 0
7363B | Tambisan SBC | Sabah |  | Modernization |  | 2024 Q3(single site MOCN) | AD | GTSB | 4.6 TSSR Approved | Solution changed MM>Bi | 2023-10-26 | 2024-05-16 |  | 2024-06-21 |  | Under Approval | 2024-07-03 | 2024-08-19 | E//Hannah | 2024-08-19 | 0920CD-Sabah-GTSB-BOQ Template (old contract) | DU00002592895 |  |  | 2024-09-09 | 2024-08-24 |  | Tower | Tower | 76 | Add R9224E M1821 x4,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 3
9318A | Kpg Merdang Gayam (SACOFA) | Sarawak |  | Modernization |  | 2024 Q2 | SH | Magicell | 4.6 TSSR Approved |  | 2023-12-10 | 2023-12-28 |  | 2024-01-09 |  | Closed | 2024-04-01 | 2024-04-02 | E//Hannah | 2024-04-02 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20240123 | DU00002592897 |  |  | 2024-12-27 | 2024-12-09 |  | Tower | Tower | 60M | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x3+R9224E M1821(AAB) x2 | 123 | 0
9563A | Coastal Highway | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002592908 | [6 empty] | 45m 3 Legged Tower
9516A | Morsjaya MP | Sarawak |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | SHA | Trintel | 4.6 TSSR Approved |  | 2023-12-13 | 2024-10-29 |  | 2024-11-06 |  | Under Approval | 2024-11-07 | 2024-11-14 | E//Syahriani | 2024-11-12 | Under BAU/SQ202411180260 | DU00002592911 |  |  | 2024-11-24 | 2024-11-19 |  | Monopole | 30m Monopole | 28M | Add A9732 M1821 x3+R8894E M1821x1, Dismantle R8882 S1800B(B6B)x3+R8862A S1800(B6A)x1+R8862A S2100(A6A)x4+R8854D S2100(A4A)x4 | 123 | 0
3244D | Taman Maluri (REL) | Central |  | Modernization |  | 2024 Q3 | IE | AllStar | 4.6 TSSR Approved |  | 2023-08-02 | 2023-08-04 |  | 2023-10-16 |  | Closed | 2024-03-25 | 2024-03-26 | E//Sumitra | 2024-03-26 | CelcomDigi_RAN_AllStar_TSS_Central_20231025 | DU00002592913 |  |  | 2024-07-21 | 2024-07-12 |  | Monopole | Lampole | 24 | Add R8862A S9000 x3+R8854 S2600 x2,Dismantle | 0 | 12
7141B | Taman Limau Limauan | Sabah |  | Modernization |  | 2024 Q1 | MS | AllStar | 4.6 TSSR Approved |  | 2023-09-19 | 2023-09-23 |  | 2023-09-29 |  | Closed | 2023-12-06 | 2023-12-20 | E//Hannah | 2023-12-19 | Celcom Digi_RAN-Allstar-TSS-Sabah-20230921 | DU00002592915 |  |  | 2024-01-29 | 2023-12-15 |  | Lampole | 45m 3 Legged Tower | 30 | Add R8862A S9000 x3+A9732 M1821 x2,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x2+R9224E M1821(AAB) x2 | 12 | 0
9643B | Batu Biah | Sarawak |  | Remote MOCN | Modernization->On Hold->Modernization->Remote MOCN | 2025 Q2 |  |  | 14.0 TSSR Not Required (Reuse Existing BBU/RRU) | [6 empty] | To be Submitted | [5 empty] | DU00002592917 | [6 empty] | 35m Tower |  | Reuse Existing RRU | 0 | 0
4996B | Kg Sg Setar (Maxis) | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q3 |  | YPTT | 14.2 Drop (Done Survey) |  | 2023-10-26 |  |  |  |  | To be Submitted |  |  |  |  | Under BAU | DU00002592918 | [6 empty] | 60m 3 Legged Tower |  | Reuse Existing RRU | 0 | 0
7441B | Ranau - Sandakan 153 | Sabah |  | Modernization | On hold->Modernization | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-01-16 | 2025-01-17 |  | 2025-01-22 |  | Under Approval | 2025-01-23 | 2025-02-18 | E//Yanie | 2025-02-18 | SQ202501020392 - Futong | DU00002592921 |  |  | 2025-02-24 | 2025-02-18 |  | Tower |  | 65m | Reuse Existing RRU | 0 | 0
4595A | Changkat Jong | Northern |  | Modernization |  | 154 single site MOCN | BY | CCSMY | 4.6 TSSR Approved |  | 2024-03-26 | 2024-03-30 |  | 2024-03-29 |  | Closed | 2024-04-30 | 2024-05-30 |  | 2024-05-30 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240506-0108 | DU00002592922 |  |  | 2024-08-26 | 2024-08-22 |  | Floor Mount Boom | 6.4m RT (Boom) | 6,6,6 | Add R8862A S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3 | 12 | 0
4632B | Lubuk Saga | Northern |  | Modernization |  | 2024 Q1 | SM | GTSB | 4.6 TSSR Approved |  | 2023-12-02 | 2023-12-04 |  | 2023-12-07 |  | Rectificating | 2023-12-08 | 2023-12-20 | E//Hazida | 2023-12-18 | Celcom Digi_RAN-GTSB-TSS-Northern-20231204-0071 | DU00002592927 |  |  | 2024-01-18 | 2024-01-13 |  | Tower | 60m 4 Legged Tower | 60 | Add R9264M M1821 x1+R9264H M901821 x3+R8862A S2601 x1,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3 | 0 | 2
7489A | Kg.Sg. Bedaun (Tmn Kai Nguong) | Sabah |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | MS | Datasco | 4.6 TSSR Approved |  | 2024-05-23 | 2024-05-27 |  | 2024-10-30 |  | Under Approval | 2024-11-04 | 2024-11-29 | E//Hannah | 2024-11-29 | S1MY2021071001WBF1-5645 | DU00002592928 |  |  | 2024-12-16 | 2024-12-06 |  | Tower | 45m 3 Legged Tower | 45m | Add R8852E S9000 x3+A9732 M1821 x3,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x5 | 123 | 0
7023C | Sedco Shophouse | Sabah |  | Modernization |  | 2024 Q3 | MS | GTSB | 4.6 TSSR Approved |  | 2023-10-23 |  |  | 2024-04-05 |  | Closed | 2024-06-10 | 2024-06-12 | E//Hannah | 2024-06-11 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240313 | DU00002592930 |  |  | 2024-06-12 | 2024-06-08 |  | In-Building System | 3m Boom (RT) | 9 | Add R8894E M1821 x1,Dismantle R8862A S2100(A6A) x3 | 0 | 2
4704B | Bagan Panchor RCC | Northern |  | Modernization |  | 2024 Q2 |  | YPTT | 4.6 TSSR Approved |  | 2024-01-05 | 2024-01-10 |  | 2024-01-16 |  | Closed | 2024-01-17 | 2024-01-24 | E//Hazida | 2024-01-23 | Celcom Digi_RAN-YPTT-TSS-Northern-20240108-0051 | DU00002592932 |  |  | 2024-03-09 | 2024-03-07 |  | Tower | 60m 4 Legged Tower | 50+10=60 | Add R8894E M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3
9015C | XFAB Samajaya | Sarawak |  | Modernization |  | 2024 Q1 | ZB | AllStar | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦sacofa lampole not allow to add AAU | 2023-09-30 | 2023-10-24 |  | 2023-11-01 |  | Closed | 2024-09-03 | 2024-09-04 | E//Norsyahriani | 2024-09-03 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20231005 | DU00002592934 | NIC_S2_Change MM to BI_owner reject_SACOFA SDN BHD |  | 2024-01-03 | 2023-12-22 |  | Monopole | 30m Rapole | 30 | Add R8894E M1821 x4+R8854 S2600 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R8862A S2600(A4A) x1 | 0 | 3
7430B | Desa Telisai Junction | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-04-14 | 2025-04-15 |  | 2025-04-23 |  | Under Approval | 2025-04-24 | 2025-05-21 | E//Hannah | 2025-05-20 | SQ202504100607- Futong | DU00002592938 |  | Remarks: Solution Changed | 2025-07-06 | 2025-05-27 |  | Tower | Tower | 60m | Add R8894E M1821x3 | 0 | 123
7097A | Anjung Teduh Tungku | Sabah |  | Modernization |  | 2024 Q3(single site MOCN) | AD | GTSB | 4.6 TSSR Approved |  | 2023-11-06 | 2023-11-17 |  | 2024-07-04 |  | Under Approval | 2024-07-05 | 2024-07-12 | E//Hannah | 2024-07-12 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231130 | DU00002592939 |  |  | 2024-07-31 | 2024-07-29 |  | Tower | Tower | 76 | Add A9732 M1821 x1,Dismantle R9224E M1821(AAB) x1 | 3 | 0
4579A | NS KM335 NB (Maxis) | Northern |  | Decomm | Modernization->On Hold->Decomm | 2024 Additional | SM | CCSMY | 4.6 TSSR Approved |  | 2023-11-20 | 2023-11-23 |  | 2023-12-04 |  | Under Approval | 2023-12-12 | 2023-12-20 | E//Hazida | 2023-12-18 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231122-0072 | DU00002592940 |  |  |  |  | 2025-07-04 | Tower | 60m 3 Legged Tower | 77m | Add R8894E M1821 x4,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x2 |  | 3
9700C | Samarahan Industrial Park (REL) | Sarawak |  | Modernization |  | 2024 Q2 | SH | Magicell | 4.6 TSSR Approved |  | 2023-12-11 | 2023-12-18 |  | 2024-01-03 |  | Closed | 2024-03-11 | 2024-03-13 | E//Hannah | 2024-03-12 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20240123 | DU00002592944 |  |  | 2024-07-04 | 2024-06-25 |  | Tower | 45M 3 Legged Tower | 46 | Add R8862A S9000 x2+R9264H M901821 x2+A9732 M1821 x2,Dismantle R9224E M1821(AAB) x4 | 23 | 0
9495A | Kg Sira | Sarawak |  | Modernization | On hold->Modernization | 2025 Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2025-02-28 | 2025-02-26 |  | 2025-03-20 |  | Closed | 2025-03-22 | 2025-04-15 | E//Hannah | 2025-04-14 | SQ202502050322-Allstar | DU00002592945 |  |  | 2025-09-12 | 2025-09-06 |  | Tower |  | 76m | Add R8894E M1821x1, Dismantle R8854E S1800(A6A)x3 | 0 | 3
7308C | PKT 3 Sandakan | Sabah |  | Modernization |  | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2024-04-23 | 2024-04-23 |  | 2024-04-29 |  | Closed | 2024-06-05 | 2024-06-21 | E//Hannah | 2024-06-06 | Celcom Digi_RAN-Futong-Standard PR TSS-Sabah-20240503 | DU00002592947 |  |  | 2024-06-12 | 2024-06-04 |  | Tower | 60m 4 Legged Tower | 76 | Add R8862A S9000 x3+R8894E M1821 x2+R8854 S2600 x2,Dismantle R8862A S2601(A6A) x2 | 0 | 13
2798B2 | pBTS Oil & Gas Terminal (Kimanis) | Sabah |  | Decomm | Modernization->On Hold->Decomm | 2025 Q1 | HW | Seri Pancar | 4.6 TSSR Approved | 0109 - TSSR rejected, Changed SOW to Decomm | 2023-11-01 | 2023-11-03 | 2025-02-12 | 2023-11-23 | 2025-02-22 | Rectificating | 2025-03-07 |  | CD//Hannah | 2025-03-20 | SQ202501020446 - Seri Pancar | DU00002592949 |  |  |  |  | 2025-11-14 | Watertank | 25m pBTS | 30 | Add R8852E S9000x3+R8894E M1821x4+R8854 S2600x1, Dismantle R8882-GUL1812x2+R8862A S1800(B6A)x1+R8854D S2100(A4A)x3+R8862A S2600(A4A)x1 | 0 | 3
3850A | PRESINT 5 | Central |  | Modernization |  | 2024 Q3 | AI | GCI | 4.6 TSSR Approved |  | 2024-03-03 | 2024-03-01 |  | 2024-04-25 |  | Closed | 2024-05-06 | 2024-05-07 | E//Razif | 2024-05-06 | SQ202411130048 | DU00002592950 |  |  | 2024-06-28 | 2024-06-26 |  | In-Building System | 3m Boom (RT) | 4 | Add R8862A S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8892E M1821(BAA) x3 | 12 | 0
7502B | Ample valley | Sabah |  | Remote MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN->Modernization->Remote MOCN | 2024 Q4 |  |  | 14.0 TSSR Not Required (Reuse Existing BBU/RRU) | [6 empty] | To be Submitted | [5 empty] | DU00002592952 | [6 empty] | 45m 3 Legged Tower |  | Reuse Existing RRU | 0 | 0
7223A | Likas Square | Sabah |  | Modernization |  | 2024 Q2 | AD | Datasco | 4.6 TSSR Approved |  | 2023-09-09 | 2023-10-03 |  |  |  |  | 2024-03-05 | 2024-03-11 | E//Hannah | 2024-03-11 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230915 | DU00002592954 |  |  | 2024-03-12 | 2024-03-06 |  | In-Building System | 3m RT (Wall Mounted Pole) | 4m | Add A9732 M1821 x3,Dismantle R8882-GUL1812 x3+R8882 S1800B(B6B) x1+R8862A S1800(B6A) x1+R8854D S2100(A4A) x4+R8854 S2600(A4A) x1 | 123 | 0
3916A | BDR_SEPANG1 | Central |  | Modernization |  | 2024 Additional | AI | GCI | 4.6 TSSR Approved |  | 2024-12-23 | 2025-01-14 |  | 2024-12-30 |  | Closed | 2025-03-20 | 2025-04-15 | E//Razif | 2025-03-24 | SQ202504210116 | DU00002592957 | Remarks: Solution TSSR/BOM Changed |  | 2025-07-04 | 2025-07-04 |  |  | Tower | 45m | Add R8852E S9000x4+R8894E M1821x6+R8862A S2601x2+R8854 S2600x2,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3+R8862A S2600(A4A) x3 | 0 | 24
1089C | Kampung Melayu Tambahan | Central |  | Modernization |  | 2024 Q4 | BY | AllStar | 4.6 TSSR Approved |  | 2024-01-03 | 2024-05-29 |  | 2024-06-04 |  | Closed | 2024-06-05 | 2024-06-13 | E//Sumitra | 2024-06-13 | BOQ CelcomDigi_RAN_AllStar_Standard PR TSS_Central_20240110 | DU00002592959 |  |  | 2024-06-15 | 2024-06-14 |  | Monopole | 30m Lampole | 30 | Add R8862A S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 23 | 0
9283A | Bukit Tiong-Core | Sarawak |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q2 | AI | Datasco | 4.6 TSSR Approved |  | 2025-02-10 | 2025-03-13 |  | 2025-03-25 |  | Under Approval | 2025-03-25 | 2025-04-24 | E//Hannah | 2025-04-07 | SQ202501070453-Datasco | DU00002592960 | [5 empty] | Tower | Tower | 100m | Reuse Existing RRU | 0 | 0
9481A | Bkt Djin(TM-Sacofa) | Sarawak |  | Modernization |  | 2024 Q1 | ZB | AllStar | 4.6 TSSR Approved |  | 2023-09-06 | 2023-09-16 |  | 2023-09-20 |  | Closed | 2024-01-30 | 2024-02-20 | E//Hannah | 2024-02-20 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230915 | DU00002592961 |  |  | 2024-03-01 | 2024-02-23 |  | Tower | 76m 4 Legged Tower | 100 | Add R8852E S9000 x3+R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8882 S1800B(B6B) x3+R8862A S2100 x3
7572A | Kg Sentosa Baru | Sabah |  | Modernization |  | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2024-03-15 | 2024-03-20 |  | 2024-04-05 |  | Closed | 2024-04-08 | 2024-04-23 | E//Hannah | 2024-04-22 | Celcom Digi_RAN-Futong-TSS-Sabah-20240324 | DU00002592963 |  |  | 2024-06-28 | 2024-06-22 |  | Tower | Tower | 60 | Add R8862A S9000 x2+A9732 M1821 x3,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x5 | 123 | 0
1750C | Ladang Dominion (REL) | Central |  | Modernization | Modernization->On Hold->Modernization | 154 single site MOCN | AI | GCI | 4.6 TSSR Approved |  | 2024-11-20 | 2024-11-29 |  | 2024-11-24 |  | Rectificating | 2024-12-16 | 2025-04-22 | E//Sumitra | 2025-04-22 | SQ202411070025 | DU00002592967 |  |  | 2024-12-10 | 2024-12-06 |  | Lampole | Lampole | 30 | Add R8862A S9000 x3+R8894E M1821 x1,Dismantle | 0 | 3
9641A | Long Tuma | Sarawak |  | Remote MOCN | Modernization->On Hold->Maintain USP MOCN->Remote MOCN | 2025 Q2 |  | Datasco | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002592968 | [6 empty] | Tower |  | Reuse Existing RRU | 0 | 0
2549A | ERL Sg Labu (Celcom) | Central |  | Modernization |  | 154 single site MOCN | AI | AllStar | 4.6 TSSR Approved |  | 2024-09-13 | 2024-09-25 |  | 2024-09-24 |  | Closed | 2024-09-23 | 2024-12-16 | E//Razif | 2024-12-16 | 0924CD-Central-Allstar-BOQ Template(new contract) | DU00002592970 |  |  | 2024-12-28 | 2024-11-15 |  |  | 45m Monopole |  | Add R8862A S9000x3+R8894E M1821x4,Dismantle R8882-GUL1812x2+R8862A S1800(B6A)x1+R8862A S2100(A6A)x3 | 0 | 1
7078R | T3_0889 - Timbua (Kg Lobok Timbua) | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002592971 | [6 empty] | #N/A
7077R | T3_0894 - KG Malinsau | Sabah |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002592974
1695C | Pan gaea Cyberjaya | Central |  | Modernization |  | 2024 Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-10-18 | 2023-11-29 |  | 2024-04-22 |  | Closed | 2024-05-08 | 2024-05-08 | E//Razif | 2024-05-08 | Wireless_Malaysia CD_TSS_ALLSTAR_ 6 site SQ202411010178 | DU00002592980 |  |  | 2024-07-04 | 2024-06-18 |  |  | Building | 4 | Add R8862A S9000 x5+R8894E M1821 x1+R8854 S2600 x1,Dismantle R8862A S2100(A6A) x5 | 0 | 3
4124D | Kompleks Sukan UiTM Merbok | Northern |  | Modernization |  | 2024 Q1 | SM | GTSB | 4.6 TSSR Approved |  | 2023-12-03 | 2023-12-04 |  | 2023-12-07 |  | Rectificating | 2023-12-08 | 2023-12-20 | E//Hazida | 2023-12-18 | Celcom Digi_RAN-GTSB-TSS-Northern-20231204-0071 | DU00002592985 |  |  | 2024-01-08 | 2024-01-08 |  | Lampole | 30m Lampole | 30M | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 | 0 | 0
4656C | Kg Ulu Legong | Northern |  | Remote MOCN |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612826 | [6 empty] | 60m 4 Legged Tower
4823A | Central Square | Northern |  | Modernization | On Hold->Remote MOCN->Modernization | 2024 Q1 | SHA | GCI | 4.6 TSSR Approved |  | 2024-08-20 | 2024-08-07 |  | 2024-08-20 |  | Under Approval | 2024-08-22 | 2024-08-29 | E//Hazida | 2024-08-29 | 0809CD-Northern-GCI-BOQ Template(new contract) | DU00002612827 |  |  | 2024-08-22 | 2024-08-03 |  | In-Building System | In-building system |  | Add R8862A S2601 x1,Dismantle R8882 S2600(B4A) x1
4561A | Sg Siput Selatan | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2026 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612828 | [6 empty] | 60m 4 Legged Tower
4073C | Pinji Seni | Northern |  | Remote MOCN |  | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612829 | [6 empty] | 3m Bipod (RT)
1880A | Mines shopping Complex | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 | MA | Ascentrack | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | Celcom Digi_RAN-Ascentrack-TSS BAU-20230729-0001_V1 | DU00002612830 | [6 empty] | In-building system
2487A | Industri Tekali | Central |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q1 | SS | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612831 | [6 empty] | 3m Bipod (RT) |  | Reuse Existing RRU | 0 | 0
4593C | Kampung Ribu | Northern |  | Remote MOCN |  | 2025 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612832 | [6 empty] | 45m Tower
3351A3 | pBTS Sunsuria City CC | Central |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q1 |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612833 | [6 empty] | 25m pBTS |  | Reuse Existing RRU | 0 | 2
4779C | Lawan Kuda Baru | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2027 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612834 | [6 empty] | 6m Unipole RT
2054B | Sepang 2 (Maxis) | Central |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q1 |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612835 | [6 empty] | 45m 3 Legged Tower
3149B4 | pBTS Kampung Ranggot | Northern |  | Decomm | Modernization->Remote MOCN->On Hold->Decomm | 2024 Q3(single site MOCN) |  | CCSMY | 4.6 TSSR Approved |  | 2024-10-12 |  | 2024-10-17 |  | 2024-10-23 |  | 2024-11-11 | 2025-05-27 | CD//Zulakmar | 2024-11-13 | 0925CD-Northern-CCSMY-BOQ Template(new contract)/Celcom Digi_RAN-CCSMY-TSS-Northern-20241017_New Contract | DU00002612836 |  |  |  |  | 2024-11-13 |  | 25m pBTS |  |  |  | 13
1671B | The Store Sg. Buloh IB | Central |  | Remote MOCN | Moernization->Remote MOCN->TBD->On Hold->Decomm->Modernization | 2024 Q1 | IE | Datasco | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | CelcomDigi_RAN_Datasco_TSS_Central_20231224 | DU00002612837 | [6 empty] | In-building system
S01363 | RS50262_9_0_KGSRIMENANTI | Sabah | 7297K | Swap |  | 2026 | AD | DATASCO | 4.6 TSSR Approved |  | 2025-03-19 | 2025-04-18 |  | 2025-05-02 |  | Under Approval | 2025-12-05 | 2026-01-13 | E//Faiz | 2026-01-05 | SQ202501020441 - Datasco | DU00002612838 | [7 empty] | 30 | Add R8852E S9000x2+R9264M M1821x3, Dismantle | 0 | 0
3434B1 | pBTS Tmn Desa Aman (M ) | Northern |  | Remote MOCN |  | 2024 Q1 |  | NA | 14.1 Drop (No Survey) | [12 empty] | DU00002612839 | [6 empty] | 25m pBTS |  |  |  | 23
1320A | Bintang | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4 | MA | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612840 | [6 empty] | 3m Bipod (RT) |  |  | 3
4608A | Puspakom | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612841 | [6 empty] | 30m Monopole |  |  | 2
1464A | MicasaApart | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q2 |  | GTSB | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612842 | [6 empty] | 6m RT (Boom)
W00270 | W066Q_W00270OD_BDRTASIKSLTN | Central | 1399K | Remote MOCN |  | 2024 Q3 |  | YPTT | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612843 | [6 empty] | MINI STRUCTURE |  |  | 1
B00254 | B061F_B00254OD_TMSGBULOH | Central | 1240K | Remote MOCN |  | 2024 Q1 | IE | Datasco | 14.1 Drop (No Survey) | [9 empty] | CD//Sapian |  |  | DU00002612844 | [6 empty] | BOOM |  |  | 123
Q01595 | QS50227_4_1-KGBOBAK | Sarawak | 9400K | Swap |  | 2024 Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2024-02-06 | 2024-02-13 |  | 2024-03-06 |  | Closed | 2024-03-21 | 2024-03-25 | CD//John | 2024-03-23 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240213 | DU00002612845 |  |  | 2024-05-27 | 2024-05-16 |  | Tower | Smallcell Tower | 30 | Add R8862A S9000 x2+R8894E M1821 x3,Dismantle R8862A S1800(B6A)x1
R00103 | R001B_R00103OD_UTCPERLIS_KGR | Northern | 4357K | Remote MOCN |  | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612846 | [6 empty] | LAMP_POLE
1232C | Pandan Indah | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q2 | SS | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612847 | [6 empty] | 30m Lampole |  |  | 13
Q01630 | KGSIBOBOG | Sarawak | 9290P | Swap |  | 2024 Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2024-02-06 | 2024-02-19 |  | 2024-03-08 |  | Closed | 2024-03-25 | 2024-03-26 | CD//John | 2024-03-25 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240213 | DU00002612848 |  |  | 2024-05-31 | 2024-05-16 |  | Guide mast |  | 30 | Add R8894E M1821 x3,Dismantle R8852E S1800 x3
4606A | Padang Besar | Northern |  | Remote MOCN |  | 2025 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612849 | [6 empty] | Tower |  | Reuse Existing RRU | 0 | 0
K00909 | K005C_K00909OD_WTANK_UITM_MERBOK | Northern | 4241K | Remote MOCN |  | 2024 Q1 |  | NA | 14.1 Drop (No Survey) | [12 empty] | DU00002612850 | [6 empty] | LAMP_POLE
Q01644 | QS50210_9_0-KG BARU KSN | Sarawak |  | Decomm | Swap->On Hold->Decomm | 2024 Q2 | AI | Magicell | 4.6 TSSR Approved |  | 2023-12-14 | 2023-12-15 |  | 2024-01-09 | 2025-06-23 | Closed | 2024-01-16 | 2024-01-18 | E//John | 2026-03-31 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20240123 | DU00002612851 | SOW Changed from On Hold to Decomm, previous Swap TSSR approved |  |  |  | 2025-08-21 |  | TOWER | 30
1496A | BDR TASIK SELATAN | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  | YPTT | 14.1 Drop (No Survey) | AAU Cannot Install-Change MM to BI¦NOK,No sapce to install AAU;xDigi and xCelcom antenna are at the same Y-bracket,Suggest swap and decomm at the same time. | [5 empty] | To be Submitted | [5 empty] | DU00002612852 | BAU_S3_Change MM to BI_Space constraint_DiGi | [5 empty] | 3m RT (Minimast) |  |  |  | 123
3123C | CBD 2 | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612853 | [6 empty] | 3m Boom (RT)
Q01620 | QS50250_4_1-KGGIAM | Sarawak | 9434K | Swap |  | 2027 |  | Trintel | 4.4 Pending TSSR Review - Design Team |  | 2025-11-17 | 2025-11-18 |  | 2025-11-19 |  | Under Approval |  |  |  |  | SQ202511040097 - Trintel | DU00002612854 | [5 empty] | Guide mast |  | 30 | Add R8852E S9000x2+R9264M M1821x3, Dismantle R8862A S1800(B6A)x1 | 0 | 0
4596A | Teluk Intan Shoplot | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q1 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612855 | [6 empty] | 3m RT (Minimast) |  |  | 3
3354A16 | pBTS SP Heights | Northern |  | Remote MOCN |  | 2024 Q1 |  | NA | 14.1 Drop (No Survey) | AAU Cannot Install-Change MM to BI¦pBTS can not install AAU | [11 empty] | DU00002612856 | BAU_S3_Change MM to BI_loading issue_SKYLINE TECHNOLOGY | [5 empty] | 25m pBTS |  |  | 0 | 123
3496A2 | pBTS Cochrean ( TX ) | Central |  | Remote MOCN |  | 2024 Q2 |  | GTSB | 14.1 Drop (No Survey) | AAU Cannot Install-Change MM to BI¦pbts cant install AAU | [5 empty] | To be Submitted | [5 empty] | DU00002612857 | BAU_S1_Change MM to BI_loading issue_DIGI | [5 empty] | 25m pBTS |  |  | 0 | 2
A01097 | A036B_A01097OD_FELDA_SG_BEHRANG | Northern | 4303K | Remote MOCN |  | 2025 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612858 | [6 empty] | TOWER |  |  | 23
S01386 | RS50291_4_1-KGROSOB | Sabah | 7262K | Swap |  | 2025 Q4 | HW | GTSB | 4.6 TSSR Approved |  | 2025-02-25 | 2025-04-24 |  | 2025-05-23 |  | Under Approval | 2025-10-05 | 2025-10-16 | E//Faiz | 2025-10-08 | SQ202501030033 - GTSB | DU00002612859 |  |  | 2025-10-20 | 2025-10-15 |  | Tower | TOWER | 30 | Reuse Existing RRU | 0 | 0
3012A | JLN SRI PERMAISURI 2 | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  | YPTT | 14.1 Drop (No Survey) | AAU Cannot Install-Change MM to BI¦AAU can not install | [5 empty] | To be Submitted | [5 empty] | DU00002612860 | BAU_S1_Change MM to BI_Space constraint_STEALTH SOLUTIONS SDN BHD | [5 empty] | 24m Pylon |  |  |  | 3
3505C | Gleneagles Hospital Ampang IB | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q1 |  | GTSB | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612861 | [6 empty] | IBC
1489A | ERL Water Tank | Central |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q1 |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612862 | [6 empty] | Watertank Structure |  |  | 3
K00051 | K013A_K00051OD_CB_TITIBAKONG | Northern | 4392K | Remote MOCN | Swap->Remote MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612863 | [6 empty] | BOOM |  |  | 13
B00795 | B063B_B00795OD_TMSALAKTINGGI | Central | 1640K | Remote MOCN | Swap->Remote MOCN | 131 single site mocn |  | Magicell | 14.2 Drop (Done Survey) |  | 2024-01-19 |  |  |  |  | To be Submitted |  |  | CD//Norhaliza |  |  | DU00002612864 | [6 empty] | BOOM |  |  | 13
1040A | 13Cheras | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4 |  | GCI | 14.1 Drop (No Survey) | AAU Cannot Install-Change MM to BI¦Space issue AAU can not install | [5 empty] | To be Submitted | [5 empty] | DU00002612865 | BAU_S2_Change MM to BI_Space constraint_DiGi | [5 empty] | 6m RT (Wall Mounted Pole) |  |  |  | 23
Q01601 | QS50218_9_0-KGKARA | Sarawak | 9406K | Swap |  | 2027 |  |  | 1.1 Pending Survey - Subcon | [6 empty] | To be Submitted |  |  | CD//John |  |  | DU00002612866 | [6 empty] | TOWER
B02162 | B064G_B02162OD_BANGIGOLFCLUB | Central | 1669K | Remote MOCN | Swap->Remote MOCN | 2024 Q3 |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Sapian |  |  | DU00002612867 | [6 empty] | UNIPOLE
4901B | Bertam Valley | Northern |  | Remote MOCN |  | 2025 Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612868 | [6 empty] | 76m Tower
Q01619 | QS50251_9_0-SEBENBANASAL | Sarawak | 9415K | Swap |  | 2026 | AD | Trintel | 4.6 TSSR Approved |  | 2026-02-05 | 2026-03-04 |  | 2026-03-06 |  | Under Approval | 2026-03-11 | 2026-04-20 | E//John | 2026-04-06 | SQ202601300355 - Trintel | DU00002612869 | [5 empty] | Guide mast | TOWER | 30 | Add R8862A S9000x3+R8894E M1821 x3, Dismantle
K00783 | K002A_K00783OD_CB_KUALAKETILIND | Northern | 4471K | Remote MOCN |  | 2025 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612870 | [6 empty] | LAMP_POLE |  |  | 12
4956A | Jitra Town | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612871 | [6 empty] | 48m 3 Legged Tower |  |  | 12
4066C | Jln Lahat | Northern |  | Remote MOCN |  | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612872 | [6 empty] | 6m Unipole RT
4767A | Tmn Gunung bintang | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q3 |  | NA | 14.1 Drop (No Survey) | AAU Cannot Install-Change MM to BI¦Minaret can not install due to space limitation | [5 empty] | To be Submitted | [5 empty] | DU00002612873 | BAU_S2_Change MM to BI_Space constraint_OMNIX | [5 empty] | 24m Lampole |  |  | 0 | 23
K00893 | K005C_K00893OD_KAMPUNG_BUJANG | Northern | 4238K | Remote MOCN |  | 2024 Q1 |  | NA | 14.1 Drop (No Survey) | [12 empty] | DU00002612874 | [6 empty] | LAMP_POLE |  |  |  | 12
2585B | Surau Madrasatul Falahiyah | Central |  | Remote MOCN |  | 2024 Q1 | IE | Datasco | 14.1 Drop (No Survey) | [12 empty] | DU00002612875 | [6 empty] | 24m Lampole |  |  | 23
K00454 | K007A_K00454OD_KGPDGCINA | Northern | 4203K | Remote MOCN |  | 2024 Q1 |  | NA | 14.1 Drop (No Survey) |  |  | 2023-10-11 | [9 empty] | DU00002612876 | [5 empty] | Tower | TBC | 60 |  |  | 1
K00911 | K006B_K00911OD_BDR_DARULAMAN_IND | Northern | 4243K | Remote MOCN |  | 2024 Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612877 | [6 empty] | LAMP_POLE |  |  |  | 3
4433D | Masjid Batu Gajah | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612878 | [6 empty] | Concreate Pole |  |  |  | 23
4072D | NS KM326 NB (REL) | Northern |  | Remote MOCN |  | 2026 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612879 | [6 empty] | 45m Monopole
W01492 | W066Y_W01492OD_PDANINDAH_COMMERCIALPARK | Central | 1734K | Remote MOCN |  | 2024 Q4 | SS | Futong | 14.1 Drop (No Survey) | AAU Cannot Install-Change MM to BI¦can not install due to space limitation | [5 empty] | To be Submitted |  |  | CD//Norhaliza |  |  | DU00002612880 | BAU_S2_Change MM to BI_Space constraint_EDOTCO (M) - TBC | [5 empty] | UNIPOLE |  |  |  | 23
1231A | SG.PELEK | Central |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q1 |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612881 | [6 empty] | 3m RT (Minimast) |  |  | 12
4877B | UniMap Perlis (Asia Debut) | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | AAU Cannot Install-Change MM to BI¦can not install due to space limitation | [5 empty] | To be Submitted | [5 empty] | DU00002612882 | BAU_S1_Change MM to BI_Space constraint_Teras Millennium Sdn Bhd | [5 empty] | 3m RT (Minimast) |  |  |  | 3
Q01618 | QS50252_9_0-PUNGUDADAK | Sarawak | 9414K | Swap | Swap | 2026 | AD | Trintel | 4.6 TSSR Approved |  | 2026-02-05 | 2026-03-04 |  | 2026-03-06 |  | Under Approval | 2026-03-11 | 2026-04-20 | E//John | 2026-04-06 | SQ202601300355 - Trintel | DU00002612883 | [6 empty] | TOWER | 30 | Add R8862A S9000x2+R9264M M1821x3
K00336 | K009A_K00336OD_KGPISANG | Northern | 4426K | Remote MOCN | Swap->Remote MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612884 | [6 empty] | TOWER |  |  |  | 1
K00892 | K005C_K00892OD_TMN_LEMBAH_BUJANG | Northern | 4237K | Remote MOCN |  | 2024 Q1 |  | NA | 14.1 Drop (No Survey) | [12 empty] | DU00002612885 | [6 empty] | LAMP_POLE |  |  | 13
Q01623 | QS50247_9_0-KGSTABUT | Sarawak | 9416K | Swap |  | 2026 | AD | Trintel | 4.6 TSSR Approved |  | 2025-12-01 | 2025-12-01 |  | 2026-01-13 |  | Under Approval | 2026-03-05 | 2026-04-20 | E//John | 2026-03-06 | SQ202511040097 - Trintel | DU00002612886 |  |  | 2026-04-27 | 2026-04-24 |  | Guide mast |  | 30 | Add R8852E S9000x2+R9264M M1821x3, Dismantle | 0 | 0
B00575 | B064C_B00575OD_SRISERDANG | Central | 1624K | Remote MOCN | Swap->Remote MOCN | 2024 Q3 | MA | Ascentrack | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | Celcom Digi_RAN-Ascentrack-TSS BAU-20230729-0001_V1 | DU00002612887 | [6 empty] | BOOM
S01393 | RS50295_4_1-KGPINOLOBU | Sabah | 7267K | Swap |  | 2025 Q4 | HW | South Pacific | 4.6 TSSR Approved |  | 2023-10-17 |  |  | 2025-02-19 |  | Under Approval | 2025-10-05 | 2025-10-16 | E//Faiz | 2025-10-07 | Celcom Digi_RAN-Futong-Standard PR TSS-Sabah-20240406 | DU00002612888 |  |  | 2025-10-30 | 2025-10-23 |  | Tower | TOWER | 30 | Add R8852E S9000x2+R8894E M1821x3, Dismantle R8862A S1800(B6A)x1 | 0 | 0
1335A | Tmn Connaught | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 | MA | YPTT | 14.2 Drop (Done Survey) |  | 2023-09-13 |  |  |  |  | To be Submitted |  |  | E//Sumitra |  |  | DU00002612889 | [6 empty] | 3m Bipod (RT) |  |  | 23
W01463 | W066K_W01463OD_LRGRAJAMUDAABDAZIZ | Central | 1492K | Remote MOCN |  | 2024 Q2 |  | GTSB | 14.1 Drop (No Survey) | [12 empty] | DU00002612890 | [6 empty] | LAMP_POLE |  | Reuse Existing RRU | 1
S01388 | RS50287_4_1-KGMENUNGGANG | Sabah | 7310K | Swap |  | 2027 |  | Seri Pancar | 3.1 Pending RF Solution - RF Team |  | 2026-01-29 | 2026-02-04 |  |  |  | To be Submitted |  |  |  |  | SQ202601220834 - Seri Pancar | DU00002612891 | [5 empty] | Tower |  | 30m | Add R8852E S9000x2+R9264M M1821x3, Dismantle R8862A S1800(B6A)x1 | 0 | 0
3649A2 | pBTS 16 Sierra | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 | MA | Ascentrack | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | Celcom Digi_RAN-Ascentrack-TSS BAU-20230729-0001_V1 | DU00002612892 | [6 empty] | PBTS
W00033 | W066V_W00033OD_JLNBANGSAR | Central | 1359K | Remote MOCN |  | 2024 Q2 |  | GTSB | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612893 | [6 empty] | BOOM |  |  | 12
3419B3 | pBTS Kampung Sundang Laut (KM) | Sabah |  | Remote MOCN |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612894 | [6 empty] | 25m pBTS |  |  |  | 3
B02698 | B064F_B02698OD_JLN_KJNGVILLA | Central | 1707K | Remote MOCN | Swap->Remote MOCN | 2025 Q1 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612895 | [6 empty] | LAMP_POLE |  |  | 2
2241A | Salak South Garden | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  | YPTT | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612896 | [6 empty] | 4 Legged Tower |  |  | 2
A01126 | A044A_A01126OD_TMN_PARIT_SETIA | Northern | 4587K | Remote MOCN | Swap->Remote MOCN | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612897 | [6 empty] | TOWER |  |  |  | 3
A01142 | A037A_A01142OD_TMNINTANMAS_TI | Northern | 4590K | Remote MOCN |  | 2025 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612898 | [6 empty] | MINARET |  |  |  | 3
R00011 | R001B_R00011OD_TMJLNKAKIBUKIT | Northern | 4319K | Remote MOCN |  | 2024 Q4 |  | NA | 14.2 Drop (Done Survey) |  | 2024-01-09 | 2024-01-10 |  |  |  | To be Submitted |  |  |  |  | N/A - Remote MOCN | DU00002612899 | [5 empty] | Guide mast | BOOM | 100 |  |  | 12
3524A2 | pBTS Seri Astana Fasa E (KM) | Northern |  | Remote MOCN |  | 2024 Q1 |  | NA | 14.1 Drop (No Survey) | AAU Cannot Install-Change MM to BI¦pBTS site,can not install AAU on site | [11 empty] | DU00002612900 | BAU_S2_Change MM to BI_loading issue_SKYLINE TECHNOLOGY | [5 empty] | 25m pBTS |  |  | 0 | 23
4410C | Uitm Sri Iskandar Perak | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q2 | MNO | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612901 | [6 empty] | 30m Monopole |  |  |  | 13
Q01635 | QS50228_4_1-KGSERUMAH | Sarawak | 9426K | Swap |  | 2027 |  | Trintel | 4.4 Pending TSSR Review - Design Team |  | 2025-12-02 | 2025-12-04 |  | 2025-12-08 |  | Under Approval |  |  |  |  | SQ202511040097 - Trintel | DU00002612902 | [5 empty] | Guide mast |  | 30 | Add R8852E S9000x2+R9264M M1821x3, Dismantle R8862A S1800(B6A)x1 | 0 | 0
2121A | Tesco Kepong IB | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.1 Drop (No Survey) | [12 empty] | DU00002612903 | [6 empty] | In-building system
Q01594 | QS50229_9_0-RHBELAYONG | Sarawak | 9403K | Swap |  | 2027 |  |  | 1.1 Pending Survey - Subcon | [6 empty] | To be Submitted |  |  | CD//John |  |  | DU00002612904 | [6 empty] | TOWER
S01377 | RS50278_4_1-KGKUSILAD | Sabah | 7258K | Swap |  | 2025 Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2025-01-03 | 2025-02-10 |  | 2025-02-18 |  | Under Approval | 2025-10-05 | 2025-10-16 | E//Ali | 2025-10-06 | SQ202501030033 - GTSB | DU00002612905 |  |  | 2025-11-14 | 2025-11-14 |  |  | TOWER | 30 | Add R8852E S9000x2+R8894E M1821x3, Dismantle R8862A S1800(B6A)x1 | 0 | 0
4577D | Taman KangKong | Northern |  | Remote MOCN |  | 2024 Q1 |  | NA | 14.1 Drop (No Survey) | [12 empty] | DU00002612906 | [6 empty] | landside
1065B | Jalan Tun Razak | Central |  | Remote MOCN |  | 2024 Q2 |  | GTSB | 14.1 Drop (No Survey) | [12 empty] | DU00002612907 | [6 empty] | 3m boom (GBT) |  |  | 1
1128B | RMC Sg Besi | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  | YPTT | 14.2 Drop (Done Survey) |  | 2023-09-22 |  |  |  |  | To be Submitted | [5 empty] | DU00002612908 | [6 empty] | 30m Monopole |  |  | 13
B02277 | B064G_B02277OD_SURAUALHIDAYAHSGTANGKAS | Central | 1682K | Swap | Swap->Remote MOCN->Site Out->Swap | 131 single site mocn | AI | GCI | 4.6 TSSR Approved |  | 2025-07-08 |  |  | 2025-07-09 |  | Closed | 2025-07-10 | 2025-10-01 | E//Ali | 2025-07-10 | SQ202508140671 | DU00002612909 |  |  | 2025-09-29 | 2025-09-19 |  |  | RAPOLE |  | Add R9264H M901821x3+R8862A S2601x3, Dismantle | 0 | 0
K00354 | K011A_K00354OD_BT14PKSENAG9 | Northern | 4429K | Remote MOCN | Swap->Remote MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612910 | [6 empty] | TOWER |  |  | 23
4662A | Bkt Tinggi Jitra | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | Under Approval | [5 empty] | DU00002612911 | [6 empty] | 48m 4 Legged Tower |  |  |  | 13
3299A1 | pBTS Bandar Tasik Kesuma | Central |  | Modernization | Modernization->Remote MOCN | 2024 Q4(single site MOCN)-L26 SSM | SY1 | GCI | 4.6 TSSR Approved |  |  |  |  | 2024-10-24 |  | Under Approval | 2024-10-25 | 2024-10-29 | E//Sumitra | 2024-10-29 | SQ202504210116 | DU00002612912 |  |  | 2024-11-22 | 2024-11-19 |  |  | 25m pBTS |  | Remain existing RRU | 0 | 12
3508A3 | pBTS Kampung Jangkang ( C ) | Northern |  | Remote MOCN |  | 2024 Q1 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612913 | [6 empty] | 25m pBTS |  |  |  | 12
K00912 | K002A_K00912OD_TMN_TJG_PUTERI_KKETIL | Northern | 4506K | Remote MOCN |  | 2025 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612914 | [6 empty] | TOWER |  |  | 23
S01325 | S096A_S01325OD_JLNPANGARABAN | Sabah | 7204K | Remote MOCN | Swap->Remote MOCN | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | Under Approval | [5 empty] | DU00002612915 | [6 empty] | RAPOLE |  |  |  | 12
4949B | Kg Bujang | Northern |  | Remote MOCN |  | 2024 Q1 |  | GCI | 14.1 Drop (No Survey) | [12 empty] | DU00002612916 | [6 empty] | Tower |  |  |  | 123
2670A5 | pBTS Kg Sentosa Tambahan ( R ) | Central |  | Remote MOCN |  | 2024 Q1 | SS | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612917 | [5 empty] | Watertank | 25m pBTS | 26 |  |  | 2
K00535 | K007A_K00535OD_TMNSERAISETIA | Northern | 4449K | Remote MOCN | Swap->Remote MOCN->On Hold->Remote MOCN | 2024 Q1 | BY | NA | 14.1 Drop (No Survey) | ¦ 09202023 - TSSR BAU_K00535_K007A_K00535OD_TMNSERAISETIA_V1, reviewed and approved. | [5 empty] | To be Submitted | [5 empty] | DU00002612918 | [6 empty] | LAMP_POLE |  |  | 13
K00858 | K007A_K00858OD_KG_SIDAM_KANAN | Northern | 4494K | Remote MOCN |  | 2024 Q1 |  | NA | 14.1 Drop (No Survey) | [12 empty] | DU00002612919 | [6 empty] | TOWER |  | Reuse Existing RRU | 123
3426B2 | pBTS Pekan Siburan | Sarawak |  | Site Out (Modernization) | Modernization->Site Out->Replacement, Site Out (Modernization) | 2026 |  | Datasco | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612920 | [6 empty] | 25m pBTS |  |  |  | 12
2956B | J Pendaftaran Neg 2G5 (Maxis) | Central |  | Remote MOCN | Remote MOCN->Site Out->Remote MOCN | 2024 Q3 |  | YPTT | 14.2 Drop (Done Survey) |  | 2023-10-19 |  |  |  |  | To be Submitted | [5 empty] | DU00002612921 | [6 empty] | In-building system
B02704 | B064G_B02704OD_PSNKEMAJUAN_SEK9BBBANGI | Central | 1709K | Remote MOCN | Swap->Remote MOCN | 2024 Q3 |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612922 | [6 empty] | BOOM |  | Reuse Existing RRU | 12
2315A | Tmn Kelab Ukay | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q2 | SS | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612923 | [6 empty] | 3m Bipod (RT) |  |  | 13
K00666 | K007A_K00666OD_TMNLAGENDA2 | Northern | 4452K | Remote MOCN |  | 2024 Q1 |  | NA | 14.1 Drop (No Survey) | [11 empty] | N/A - Remote MOCN | DU00002612924 | [6 empty] | LAMP_POLE |  |  | 123
B00550 | B063B_B00550OD_SALAKTINGGI | Central | 1621K | Remote MOCN | Swap->Remote MOCN | 131 single site mocn |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612925 | [6 empty] | TOWER |  |  | 2
K00679 | K012A_K00679OD_KGSIKDALAM | Northern | 4454K | Remote MOCN | Swap->Remote MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612926 | [6 empty] | TOWER |  |  |  | 3
3503C | RHB Center Jalan Tun Razak IB | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q2 |  | GTSB | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612927 | [6 empty] | In-building system
Q01603 | QS50215_4_1-KGBENUK | Sarawak | 9390K | Swap |  | 2027 | SM | Magicell | 4.2 Pending TSSR Resubmission - Subcon |  | 2025-01-14 | 2025-02-10 |  | 2025-02-24 |  | Rectificating |  |  |  |  | SQ202501070146-Magicell | DU00002612928 | [5 empty] | Guide mast |  | 30 | Add R8852E S9000x2+R9264M M1821x3, Dismantle R8862A S1800(B6A)x1 | 0 | 0
K00367 | K005C_K00367OD_AMANJAYA | Northern | 4196K | Remote MOCN |  | 2024 Q1 |  | NA | 14.1 Drop (No Survey) | [12 empty] | DU00002612929 | [6 empty] | BOOM |  |  |  | 2
K00017 | K005C_K00017OD_MERBOK | Northern | 4177K | Remote MOCN |  | 2024 Q1 |  | NA | 14.1 Drop (No Survey) | [12 empty] | DU00002612930 | [6 empty] | TOWER |  |  |  | 123
1804A | Lot 10 | Central |  | Remote MOCN |  | 2024 Q2 |  | GTSB | 14.1 Drop (No Survey) | [12 empty] | DU00002612931 | [6 empty] | In-building system
Q01628 | QS50241_4_1-RHANCHARANG | Sarawak | 9385K | Swap |  | 2025 | AD | Trintel | 4.6 TSSR Approved |  | 2025-05-27 | 2025-06-06 |  | 2025-06-13 |  | Under Approval | 2025-06-13 | 2025-09-20 | E//John | 2025-06-16 | SQ202505020084-Trintel | DU00002612932 |  |  | 2025-09-21 | 2025-09-20 |  | Tower | TOWER | 30 | Add R8894E M1821x3, Dismantle R8862A S1800(B6A)x1+R8852E S1800(A8A)x2 | 0 | 0
4147A | TAMANMANGGIS | Northern |  | Remote MOCN |  | 2024 Q1 |  | NA | 14.1 Drop (No Survey) | [12 empty] | DU00002612933 | [6 empty] | 6m RT (Boom) |  |  | 12
Q01589 | QS50236_9_0-KGENSIKA | Sarawak | 9401K | Swap |  | 2026 | AD | Trintel | 4.6 TSSR Approved |  | 2025-11-16 | 2025-11-18 |  | 2025-11-19 |  | Under Approval | 2026-04-01 | 2026-04-20 | E//John | 2026-04-06 | SQ202511040097 - Trintel | DU00002612934 | [5 empty] | Guide mast |  | 30 | Add R8852E S9000x2+R9264M M1821x3, Dismantle | 0 | 0
3372A3 | pBTS Blue Valley 3 ( C ) | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4(single site MOCN)-L26 SSM |  | GCI | 14.3 Drop (Done Survey + TSSR) | AAU Cannot Install-S23 MM change to BI¦pBTS loading issue,AAU cannot install |  |  |  | 2024-11-06 |  | Under Approval | [5 empty] | DU00002612935 | [6 empty] | 25m pBTS |  | Add A9732 M1821 x2, Dismantle R8854 S2600(A4A)x2+R8894E M1821(A8A)x4 | 23 | 0
Q01631 | QS50245_4_1-KGPRAYA | Sarawak | 9425K | Swap |  | 2026 | AD | Trintel | 4.6 TSSR Approved |  | 2025-12-01 | 2025-12-02 |  | 2025-12-04 |  | Under Approval | 2026-03-05 | 2026-04-20 | E//John | 2026-04-06 | SQ202511040097 - Trintel | DU00002612936 |  |  | 2026-04-27 | 2026-04-20 |  | Guide mast |  | 30 | Add R8852E S9000x2+R9264M M1821x3, Dismantle R8862A S1800(B6A)x1 | 0 | 0
3079C | GREEN APARTMENT | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  | YPTT | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612937 | [6 empty] | Building |  |  | 23
4950B | Pulai | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612938 | [6 empty] | Tower |  |  |  | 12
3329A | PST_BDR_WMJ1 | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q1 | AI | AllStar | 14.2 Drop (Done Survey) | AAU Cannot Install-Change MM to BI¦owner rejected due to loading issue | 2023-10-02 |  |  |  |  | To be Submitted | [5 empty] | DU00002612939 | BAU_S1_Change MM to BI_loading issue_EDOTCO (M) - TBC | [5 empty] | 3m Boom (RT) |  |  |  | 2
2295A | Estana Court | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q2 | SS | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612940 | [6 empty] | Tower |  |  | 12
4051B7 | pBTS Sg Chawang & Sg Erong Estate Office | Northern |  | Remote MOCN |  | 2026 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612941 | [6 empty] | 24m PBTS |  |  |  | 1
3421B7 | pBTS Taman Mawar | Central |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q1 |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612942 | [6 empty] | 25m pBTS |  | Reuse Existing RRU | 0 | 2
3590B8 | pBTS Telupid Town 1 (REL) | Sabah |  | Site Out (Modernization) | Modernization->Site Out->Replacement, Site Out (Modernization) | 2024 Q4 |  | YPTT | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2025-06-21 |  | 2025-06-30 | [7 empty] | SQ202506160230 - YPTT | DU00002612943 | [6 empty] | 24M PBTS |  |  |  | 12
4312B | ULUPAUH | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q3 |  | NA | 14.3 Drop (Done Survey + TSSR) |  | 2023-12-07 |  |  | 2023-12-07 |  | Under Approval |  |  |  |  | N/A - Remote MOCN | DU00002612944 | [6 empty] | 76m Tower |  |  | 2
4590A | NS KM201 NB(MAXIS) | Northern |  | Remote MOCN |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612945 | [6 empty] | 60m 3 Legged Tower
Q01600 | QS50219_9_0-RHAGAN | Sarawak | 9405K | Swap |  | 2026 | AD | Magicell | 4.6 TSSR Approved |  | 2024-05-09 | 2024-05-14 |  | 2026-02-10 |  | Rectificating | 2026-03-05 | 2026-04-20 | E//John | 2026-03-06 | Celcom Digi_RAN-Magicell-Standard PR TSS-Sarawak-20240425 | DU00002612946 |  |  | 2026-04-25 | 2026-04-18 |  | Guide mast |  | 30 | Add R8852E S9000x2+R9264M M1821x3 | 0 | 0
4017D | Kg Bukit Pokok Sena | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612947 | [6 empty] | Tower |  |  |  | 13
2118B | Bandar teknologi kajang 1 | Central |  | Remote MOCN | Modernization->Remote MOCN | 131 single site mocn |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612948 | [6 empty] | 45m Monopole |  | Reconnect RRU | 123 | 4
Q01605 | QS50214_4_1-KGSTUMBINSA | Sarawak | 9408K | Swap |  | 2025 | AD | YPTT | 4.6 TSSR Approved |  | 2025-04-03 | 2025-03-13 |  | 2025-04-02 |  | Under Approval | 2025-04-21 | 2025-05-15 | CD//John | 2025-04-22 | SQ202503040500-YPTT | DU00002612949 |  |  | 2025-05-14 | 2025-05-07 |  | Tower | TOWER | 32 | Add R9264M M1821x3, Dismantle R8892N M1821E(BCB)x3 | 0 | 0
B01724 | B064C_B01724OD_PR_PSSEQUINEPARK | Central | 1663K | Remote MOCN | Swap->Remote MOCN | 2024 Q3 | MA | Ascentrack | 14.1 Drop (No Survey) | AAU Cannot Install-Change MM to normal sector¦Space issue cant install AAU and BI | [5 empty] | To be Submitted | [5 empty] | DU00002612950 | [6 empty] | PSS PYLON
K00277 | BUKITAPING | Northern | 4181P | Remote MOCN | Swap->Remote MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612951 | [6 empty] | TOWER
1514B | PUAS AU3 (Celcom) | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q1 | AI | AllStar | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612952 | [6 empty] | Tower |  |  | 123
B00235 | B064D_B00235OD_SRISEKAMAT | Central | 1610K | Remote MOCN | Swap->Remote MOCN | 2024 Q4 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612953 | [6 empty] | BOOM |  |  | 123
Q01641 | QS50206_4_1-KGSEROMAHBAU | Sarawak | 9429K | Swap |  | 2024 Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2024-02-05 | 2024-02-14 |  | 2024-03-07 | 2024-03-07 | Closed | 2024-03-21 | 2024-03-25 | CD//John | 2024-03-23 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240213 | DU00002612954 |  |  | 2024-05-31 | 2024-05-17 |  | Tower | Smallcell Tower | 30 | Add R8862A S9000 x2+R8894E M1821 x3,Dismantle
7307A4 | pBTS Taman Merpati (KM) | Sabah |  | Site Out (Modernization) | Modernization->Site Out->Site Out (Modernization) | 2024 Q3 |  | YPTT | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2025-06-21 |  | 2025-06-26 | [7 empty] | SQ202506160230 - YPTT | DU00002612955 | [6 empty] | 25m pBTS |  |  |  | 23
Q01616 | QS50257_4_1-KGBARUSERIAN | Sarawak | 9412K | Swap |  | 2027 |  | Trintel | 4.4 Pending TSSR Review - Design Team |  | 2025-12-02 | 2025-12-03 |  | 2025-12-04 |  | Under Approval |  |  |  |  | SQ202511040097 - Trintel | DU00002612956 | [5 empty] | Guide mast |  | 30 | Add R8852E S9000x2+R9264M M1821x3, Dismantle R8862A S1800(B6A)x1 | 0 | 0
1664C | Apartment Permai | Central |  | Remote MOCN |  | 2024 Q2 | IE | Datasco | 14.1 Drop (No Survey) | [12 empty] | DU00002612957 | [6 empty] | landside
Q01633 | QS50233_4_1-KGSEBAT | Sarawak | 9421K | Swap |  | 2024 Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2024-02-07 | 2024-02-14 |  | 2024-03-07 | 2024-03-07 | Closed | 2024-03-21 | 2024-03-25 | CD//John | 2024-03-23 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240213 | DU00002612958 |  |  | 2024-05-27 | 2024-05-17 |  | Tower | Smallcell Tower | 30 | Add R8862A S9000 x2+R8894E M1821 x3,Dismantle
4571C | Kulim Landmark | Northern |  | Remote MOCN |  | 2024 Q1 |  | NA | 14.1 Drop (No Survey) | [12 empty] | DU00002612959 | [6 empty] | 3m Boom (RT) |  |  |  | 13
K00702 | K005C_K00702OD_TMNKURNIAJAYABDG | Northern | 4219K | Remote MOCN |  | 2024 Q1 |  | NA | 14.1 Drop (No Survey) | [12 empty] | DU00002612960 | [6 empty] | RAPOLE |  |  | 1
B00420 | B061G_B00420OD_SEKU3SA | Central | 1248K | Remote MOCN |  | 2024 Q1 | IE | Datasco | 14.1 Drop (No Survey) | [9 empty] | CD//Sapian |  |  | DU00002612961 | [6 empty] | BOOM |  |  | 1
4942B | Baling Mxs | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612962 | [6 empty] | 60m 3 Legged Tower |  |  |  | 12
B02667 | B057D_B02667OD_DESA_GOMBAK | Central | 1306K | Remote MOCN |  | 2024 Q1 | SS | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612963 | [6 empty] | LAMP_POLE |  |  | 123
A00480 | A039A_A00480OD_JLNSEMPADAN | Northern | 4558K | Remote MOCN |  | 2025 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612964 | [6 empty] | TOWER |  |  | 13
3254A | Lestari Perdana | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 | MA | Ascentrack | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612965 | [6 empty] | 20m Monopole
2403A | Dusun Tua(Celcom) | Central |  | Remote MOCN | Modernization->Remote MOCN | 131 single site mocn | SS | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612966 | [6 empty] | Tower |  |  | 12
Q00500 | QS20027_4_1-KGSTASS2 | Sarawak | 9392K | Swap |  | 2024 Q2 | SH | Magicell | 4.6 TSSR Approved |  | 2024-02-14 | 2024-02-27 |  | 2024-03-06 |  | Closed | 2024-03-14 | 2024-03-15 | CD//John | 2024-03-14 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20240123 | DU00002612967 |  |  | 2024-05-27 | 2024-05-18 |  | Watertank |  | 30 | Add R8862A S9000 x2+R8894E M1821 x3,Reuse R8852E S9000 x1,Dismantle
2668AM | pBTS Mayshowa Sdn Bhd | Central |  | Remote MOCN |  | 2024 Q1 | IE | Datasco | 14.1 Drop (No Survey) | AAU Cannot Install-Change MM to BI¦pBTS loading issue,AAU cannot install | [11 empty] | DU00002612968 | BAU_S1_Change MM to BI_loading issue_Digi OB | [5 empty] | 25m pBTS |  |  | 0 | 2
9279A | TM Jalan Glumbia | Sarawak |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4(single site MOCN)-L21 SSM | SHA | Trintel | 14.1 Drop (No Survey) | AAU Cannot Install-S123 MM change to BI¦sacofa not allow to add AAU |  |  |  | 2024-10-28 |  | Under Approval | [5 empty] | DU00002612969 | [6 empty] | 4 Legged Tower |  | Reuse | 0 | 123
2365A | Masjid Jalan 5 | Central |  | Remote MOCN |  | 2024 Q1 | IE | Datasco | 14.1 Drop (No Survey) | [12 empty] | DU00002612970 | [6 empty] | 20m Lampole
W01109 | W066D_W01109OD_TMNSRISINAR2 | Central | 1430K | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.1 Drop (No Survey) | [9 empty] | CD//Sapian |  |  | DU00002612971 | [6 empty] | UNIPOLE |  |  | 12
2799B6 | pBTS Kg Meruntum (KM) | Sabah |  | Remote MOCN | Remote MOCN->On hold->Remote MOCN | 2024 Q1 |  |  | 14.1 Drop (No Survey) | single phase power. We have done modernization at BAU and currently we're having intermittent cell outage,can not do Remote MOCN | [11 empty] | DU00002612972 |  | No TX Decom TSSR Required (Under upgrade) |  |  |  |  | 25m pBTS |  |  | 13
3157B7 | pBTS KG LUBOK SETOL | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612973 | [6 empty] | 25m pBTS |  |  |  | 1
2228A | Lorong Air Bersih | Central |  | Decomm | Remote MOCN->On hold->Decomm | 2024 Q1 | AI | YPTT | 4.6 TSSR Approved |  | 2023-10-06 |  |  | 2024-02-08 | 2024-02-08 | Closed | 2024-02-09 |  | E//Sumitra | 2024-02-14 | BOQ_Celcom Digi_RAN-YPTT-Standard PR TSS-20240218 | DU00002612974 |  |  |  |  | 2024-08-12 |  | 3m Boom (RT) |  |  | 1
2655A13 | pBTS Hartalega Hostel | Central |  | Modernization | Modernization->Remote MOCN | 2024 Q4(single site MOCN)-L26 SSM | AI | In-House | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦pbts cant install AAU |  |  |  | 2024-10-28 |  | Under Approval | 2024-10-28 | 2024-10-28 |  | 2024-10-28 |  | DU00002612975 |  |  | 2025-06-13 | 2025-06-04 |  |  | 25m pBTS |  | Remain existing RRU | 0 | 123
4968A | Inokom Kulim | Northern |  | Remote MOCN |  | 2024 Q1 |  | GTSB | 14.1 Drop (No Survey) | [12 empty] | DU00002612976 | [6 empty] | 60m 3 Legged Tower |  |  | 13
S01367 | RS50273_4_1-KGTEMPASUK | Sabah | 7239K | Swap |  | 2024 Q3 | AD | GTSB | 4.6 TSSR Approved | 1) Subcon captured single power incoming info during TSS// 2) Additional 2 Sectors of Antenna on top, not heavy duty tower structure | 2024-01-24 | 2024-05-14 |  | 2024-05-15 |  | Closed | 2024-05-15 | 2024-09-06 | CD//Mohidi Jaan | 2024-05-20 | Celcom Digi_RAN-GTSB-TSS-Sabah-20240204 | DU00002612977 |  |  | 2024-09-24 | 2024-05-21 |  | Tower | TOWER | 31m | Add R9264M M1821 x1+R9264H M901821 x2,Dismantle R8862A S1800(B6A) x1 | 0 | 0
K00768 | K006B_K00768OD_TMN_KEPALA_BATAS | Northern | 4222K | Remote MOCN |  | 2024 Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612978 | [6 empty] | RAPOLE |  |  |  | 23
1058A | JBA MPI Bangi (TM) | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612979 | [6 empty] | Tower |  |  | 23
3578B | Pekan Dengkil | Central |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q1 |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612980 | [6 empty] | 30m Monopole |  |  | 13
1880B | Kg Limau Manis (Celcom) | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612981 | [6 empty] | Tower |  |  | 1
3097A | NKVE Damansara KM21 (REL) | Central |  | Remote MOCN |  | 2024 Q2 | IE | Datasco | 14.1 Drop (No Survey) | [12 empty] | DU00002612982 | [6 empty] | 30m Monopole
B02327 | W067A_B02327OD_PUTRA_HARMONI_PRISINT9_2 | Central | 1785K | Remote MOCN | Swap->Remote MOCN | 2024 Q3 |  | YPTT | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Ali Akaram |  |  | DU00002612983 | [6 empty] | BOOM |  | Reuse Existing RRU
3363A7 | pBTS Jln Junjong (REL) | Northern |  | Remote MOCN | Remote MOCN->Decomm->Remote MOCN | 2024 Q1 |  | NA | 14.1 Drop (No Survey) | [12 empty] | DU00002612984 | [6 empty] | Structure
W01434 | W066Z_W01434OD_LAMPOLE_SKCOCHRANEPERKASA | Central | 1762K | Remote MOCN |  | 2024 Q2 |  | GTSB | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612985 | [6 empty] | LAMP_POLE |  | Reuse Existing RRU | 1
3043C | Warisan Megah | Central |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q1 |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612986 | [6 empty] | Lampole |  |  | 1
4999A | Kuala Nerang | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612987 | [6 empty] | 75m 4 Legged Tower |  |  | 23
4358B | Pengkalan Ind 3 | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612988 | [6 empty] | 45m Monopole |  |  |  | 12
4412B | NS KM378 NB(ZED) | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q1 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612989 | [6 empty] | 60m 3 Legged Tower
3147B2 | pBTS Surau Taman Permai (KM) | Northern |  | Remote MOCN |  | 2024 Q1 |  | NA | 14.1 Drop (No Survey) | AAU Cannot Install-Change MM to BI¦pBTS loading issue,AAU cannot install | [11 empty] | DU00002612990 | BAU_S1_Change MM to BI_loading issue_Digi OB | [5 empty] | 25m pBTS |  |  | 0 | 3
K00917 | K007B_K00917OD_TMNMUTIARA_KARANGAN | Northern | 4246K | Remote MOCN |  | 2024 Q1 |  | NA | 14.1 Drop (No Survey) | [12 empty] | DU00002612991 | [6 empty] | LAMP_POLE |  |  | 13
S01392 | RS50296_9_0_KGTIDUNG | Sabah | 7311K | Swap |  | 2025 Q4 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2025-10-13 | 2025-10-16 |  | 2025-10-20 |  | Under Approval | 2025-10-23 | 2025-10-29 | E//Ali | 2025-10-28 | SQ202510060580 - Seri Pancar | DU00002612992 |  |  | 2025-10-31 | 2025-10-28 |  | Tower |  | 30 | Reuse Existing RRU | 0 | 0
3836B | Petron Bangi Seksyen 10 | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612993 | [6 empty] | 24m Lampole |  | Reuse Existing RRU | 1 | 0
S00156 | S104A_S00156OD_TMRANAU | Sabah | 7169K | Remote MOCN |  | 2026 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612994 | [6 empty] | TOWER |  |  | 123
3167B4 | pBTS QL Foods Tepi Sungai (M) | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4(single site MOCN)-L26 SSM |  | GTSB | 14.1 Drop (No Survey) | ¦ 1029 - Isma: Remain existing config ¦ 1024 - PBTS, Need revise from AAU solution, emailed planning team | [5 empty] | To be Submitted | [5 empty] | DU00002612995 | [6 empty] | 25m pBTS |  | Reuse exisiting RRU | 0 | 123
Q01587 | QS50239_9_0-KGSPADAH | Sarawak | 9394K | Swap |  | 2024 Q2 | SH | Magicell | 4.6 TSSR Approved |  | 2024-02-15 | 2024-02-20 |  | 2024-03-06 |  | Closed | 2024-03-14 | 2024-03-15 | CD//John | 2024-03-14 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20240123 | DU00002612996 |  |  | 2024-05-31 | 2024-05-18 |  | Watertank |  | 30m | Add R8862A S9000 x2,Reuse R8852E S9000 x1,Dismantle
K00817 | K005B_K00817OD_KG_SG_JAGUNG_SP | Northern | 4227K | Remote MOCN |  | 2024 Q1 |  | NA | 14.1 Drop (No Survey) | [12 empty] | DU00002612997 | [6 empty] | TOWER |  |  | 23
3059C6 | pBTS Jalan Korongkom | Sabah |  | Remote MOCN |  | 2026 |  | Satellite | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612998 | [6 empty] | 24M PBTS
2171A | Syabas Tmn Pelangi | Central |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q1 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612999 | [6 empty] | 30m Monopole |  |  | 23
3056C3 | pBTS SGCC (C) | Sabah |  | Remote MOCN |  | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [12 empty] | DU00002613000 | [6 empty] | 25m pBTS
W01313 | W066K_W01313OD_ISTANABUDAYA_JLNTUNRAZAK | Central | 1451K | Remote MOCN |  | 2024 Q1 | AI | YPTT | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002613001 | [6 empty] | LAMP_POLE |  | Reuse Existing RRU | 1
1873B | Zon Akademik Utara | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 | MA | Ascentrack | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002613002 | [6 empty] | 30m Monopole Tree |  |  | 13
Q01609 | QS50208_4_1-KGPICHIN | Sarawak | 9387K | Remote MOCN | Swap->Remote MOCN | 2026 |  | AllStar | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002613003 | [5 empty] | Minimast | TOWER | 30
1432A | GLENEAGLES | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q1 |  | GTSB | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002613004 | [6 empty] | 3m Bipod (RT) |  |  | 13
2189A8 | pBTS Kasuapan Village Gaya | Sabah |  | Remote MOCN |  | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [12 empty] | DU00002613005 | [6 empty] | 24m PBTS |  |  |  | 3
1385A | Visconti | Central |  | Remote MOCN |  | 2024 Q3 | MA | Ascentrack | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | Celcom Digi_RAN-Ascentrack-TSS BAU-20230729-0001_V1 | DU00002613006 | [6 empty] | 6m RT (Boom)
W00058 | W066S_W00058OD_JLNHUJANEMAS | Central | 1366K | Remote MOCN |  | 2024 Q3 |  | YPTT | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002613007 | [6 empty] | BOOM |  |  | 2
K00860 | K002A_K00860OD_KG_BATU1_KKETIL | Northern | 4495K | Remote MOCN |  | 2025 |  | NA | 14.1 Drop (No Survey) |  |  | 2023-10-13 |  |  |  | To be Submitted | [5 empty] | DU00002613008 | [5 empty] | Tower | TOWER | 46 |  |  | 123
4155D | TMNBDRBARUSP | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q1 |  | YPTT | 14.1 Drop (No Survey) | AAU Cannot Install-Change MM to BI¦can not install due to space limitation |  | 2023-10-23 | [9 empty] | DU00002613009 | BAU_S2_Change MM to BI_Space constraint_STEALTH |  |  |  |  | Monopole | 24m Lampole | 24M |  |  | 13
B02932 | B061F_B02932OD_HOSPITALSGBULOHOD | Central | 1328K | Remote MOCN |  | 2024 Q1 | IE | Datasco | 14.1 Drop (No Survey) | [9 empty] | CD//Sapian |  |  | DU00002613010 | [6 empty] | Lampole |  |  | 3
W00195 | W066H_W00195OD_SETAPAKJAYA | Central | 1388K | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Ali akaram |  |  | DU00002613011 | [6 empty] | BOOM |  |  | 2
S01383 | RS50286_9_0_KGPANTAIEMAS | Sabah | 7244K | Site Out (Modernization) | Swap->On Hold->Swap->Site Out->Site Out (Modernization) | 2024 Q3 | MS | GTSB | 4.6 TSSR Approved | 1) Subcon captured single power incoming info during TSS// 2) Additional 2 Sectors of Antenna on top, not heavy duty tower structure | 2024-01-24 | 2024-04-24 |  | 2024-04-29 |  | Under Approval | 2024-05-03 | 2024-07-03 | CD//Mohidi Jaan | 2024-05-27 | Celcom Digi_RAN-GTSB-TSS-Sabah-20240204 | DU00002613012 | [5 empty] | Tower | TOWER | 31m
1304B | Damansara Damai | Central |  | Remote MOCN |  | 2024 Q2 | IE | Datasco | 14.1 Drop (No Survey) | [12 empty] | DU00002613013 | [6 empty] | 45m Tower |  |  | 123
A00852 | A044A_A00852OD_DESATERATAISBRGPRK | Northern | 4574K | Remote MOCN | Swap->Remote MOCN | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002613014 | [6 empty] | RAPOLE |  |  | 2
1593C | Desa Tunku Mariam Kem Kementah (REL) | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q1 | AI | AllStar | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002613015 | [6 empty] | 30m Monopole |  |  | 12
B00650 | B064I_B00650OD_BRANANGINDLAND | Central | 1632K | Remote MOCN | Swap->Remote MOCN | 131 single site mocn |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002613016 | [6 empty] | TOWER |  |  | 13
1292B | Jalan Imbi | Central |  | Remote MOCN |  | 2024 Q2 |  | GTSB | 14.1 Drop (No Survey) | [12 empty] | DU00002613017 | [6 empty] | 3m Bipod (RT) |  |  | 2
Q01639 | QS50209_4_1-KGPUNAU | Sarawak | 9391K | Swap |  | 2026 | AD | Magicell | 4.6 TSSR Approved |  | 2025-01-15 | 2025-02-07 |  | 2026-02-10 |  | Under Approval | 2026-03-05 | 2026-04-20 | E//John | 2026-03-06 | SQ202501070146-Magicell | DU00002613018 |  |  | 2026-05-08 | 2026-04-22 |  | Guide mast |  | 30 | Add R8852E S9000x2+R9264M M1821x3, Dismantle R8862A S1800(B6A)x1 | 0 | 0
7593A | Hotel Pulau Labuan Inn | Sabah |  | Remote MOCN | Modernization->Remote MOCN->On Hold->Decomm->On Hold->Modernization->Remote MOCN | 2024 Q4(single site MOCN)-L26 SSM | HW | Seri Pancar | 14.0 TSSR Not Required (Reuse Existing BBU/RRU) |  | 2024-10-25 |  | 2025-02-19 | 2025-05-23 | 2025-03-07 | Under Approval | 2025-03-10 |  | E//Hannah |  | Celcom Digi_RAN Seri Pancar-Standard PR TSS-Sabah-20241028 | DU00002613019 | [6 empty] | 6m Unipole RT | 6 | R9264H M901821(AIA)x3+R9264M M1821(AEA)x2+R8854 S2600(A4A)x2+R8862A S2600(A4A)x1 |  | 12
B02556 | B063B_B02556OD_JALAN1_KGBARULANJUT | Central | 1694K | Remote MOCN | Swap->Remote MOCN | 131 single site mocn |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002613020 | [6 empty] | RAPOLE |  |  | 2
Q01637 | QS50223_9_0-RHJANGIT | Sarawak | 9427K | Swap |  | 2026 | AD | Magicell | 4.6 TSSR Approved |  | 2024-05-03 | 2024-05-06 |  | 2026-02-10 |  | Under Approval | 2026-03-05 | 2026-04-20 | E//John | 2026-03-06 | Celcom Digi_RAN-Magicell-Standard PR TSS-Sarawak-20240425 | DU00002613021 |  |  | 2026-04-21 | 2026-04-16 |  | Guide mast |  | 30 | Add R8852E S9000x2+R9264M M1821x3 | 0 | 0
3500A12 | pBTS Kg Rapak | Sabah |  | Remote MOCN |  | 2026 |  | NR services | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002613022 | [6 empty] | 24m PBTS
Q01586 | QS50240_9_0-KGBIDAKPLAMAN | Sarawak | 9396K | Swap |  | 2026 | AD | Trintel | 4.6 TSSR Approved |  | 2025-11-28 | 2025-11-21 |  | 2025-12-04 |  | Under Approval | 2026-03-05 | 2026-04-20 | E//John | 2026-03-06 | SQ202511040097 - Trintel | DU00002613023 |  |  | 2026-05-14 | 2026-04-22 |  | Guide mast |  | 30 | Add R8852E S9000x2+R9264M M1821x3, Dismantle | 0 | 0
2261C | Jalan 27_56 (REL) | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002613024 | [6 empty] | Lampole
B02842 | B063C_B02842OD_KGSGMERAP2 | Central | 1721K | Remote MOCN | Swap->Remote MOCN | 2024 Q3 |  | YPTT | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002613025 | [6 empty] | TOWER |  |  | 12
4946A | Bukit Selambau | Northern |  | Remote MOCN |  | 2024 Q1 |  | GCI | 14.1 Drop (No Survey) | [12 empty] | DU00002613026 | [6 empty] | 60m 3 Legged Tower |  |  |  | 3
K00907 | K006B_K00907OD_TMN_SERIKEMUNING2_JTR | Northern | 4239K | Remote MOCN |  | 2024 Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002613027 | [6 empty] | LAMP_POLE |  |  | 2
4462B | Grik Town (Maxis) | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002613028 | [6 empty] | 60m 3 Legged Tower |  |  |  | 13
K00695 | K007A_K00695OD_TMNSENANGIN | Northern | 4218K | Remote MOCN |  | 2024 Q1 |  | NA | 14.1 Drop (No Survey) |  |  | 2023-09-26 | [9 empty] | DU00002613029 | [6 empty] | MINARET | 30M |  |  | 12
3646A1 | pBTS Jln tempayan Emas (KM) | Central |  | Remote MOCN |  | 2024 Q1 | IE | Datasco | 14.1 Drop (No Survey) | AAU Cannot Install-Change MM to BI¦Space issue AAU can not install | [11 empty] | DU00002613030 | BAU_S3_Change MM to BI_Space constraint_Digi OB | [5 empty] | 25m pBTS |  |  |  | 123
4985A | Baling Town | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002613031 | [5 empty] | Tower | 60m 3 Legged Tower | 60 |  | 13
R00091 | R001C_R00091OD_KG_KATONG_PS | Northern | 4349K | Remote MOCN |  | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002613032 | [6 empty] | LAMP_POLE
3840A | PO Sg Besi | Central |  | Modernization |  | 2024 Q3 | CR | YPTT | 4.6 TSSR Approved |  | 2024-03-22 |  |  | 2024-03-22 |  | Closed | 2024-04-15 | 2024-05-24 | E//Sumitra | 2024-05-24 | BOQ_Celcom Digi_RAN-YPTT-Standard PR TSS-20240323 | DU00002613033 |  |  | 2024-06-15 | 2024-06-15 |  |  | 18m Lampole |  | Add R8862A S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 1
Q01614 | QS50259_4_1-KGMENJAU | Sarawak | 9438K | Swap |  | 2026 | AD | Trintel | 4.6 TSSR Approved |  | 2025-11-17 | 2025-11-20 |  | 2025-11-22 |  | Under Approval | 2026-03-05 | 2026-04-20 | E//John | 2026-03-06 | SQ202511040097 - Trintel | DU00002613034 |  |  | 2026-04-26 | 2026-04-21 |  | Guide mast |  | 30 | Add R8852E S9000x2+R9264M M1821x3, Dismantle R8862A S1800(B6A)x1 | 0 | 0
1842B | Seksyen 2 Bandar Baru Bangi | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002613035 | [6 empty] | 30m Minaret
W01568 | W066Q_W01568OD_JLN_BESAR_SALAK_SOUTH | Central | 1515K | Remote MOCN |  | 2024 Q3 |  | GTSB | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002613036 | [6 empty] | UNIPOLE
S01375 | RS50280_4_1-KGSENADJA | Sabah | 7256K | Swap |  | 2025 Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2025-01-03 | 2025-02-10 |  | 2025-02-18 |  | Under Approval | 2025-10-05 | 2025-10-16 | E//Ali | 2025-10-07 | SQ202501030033 - GTSB | DU00002613037 |  |  | 2025-10-25 | 2025-10-21 |  |  | TOWER | 30 | Reuse Existing RRU | 0 | 0
S01378 | RS50285_4_1-SKPINGGANPINGGAN | Sabah | 7259K | Swap |  | 2025 Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2025-02-25 | 2025-04-07 |  | 2025-04-13 |  | Under Approval | 2025-10-05 | 2025-10-16 | E//Ali | 2025-10-07 | SQ202501030033 - GTSB | DU00002613038 |  |  | 2025-11-13 | 2025-10-15 |  | Tower | TOWER | 30 | Reuse Existing RRU | 0 | 0
1708C | SBK10 Phileo Damansara MRT Station (REL) | Central |  | Modernization |  | 2024 Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2024-06-03 | 2024-06-05 |  | 2024-06-11 |  | Closed | 2024-06-11 | 2024-06-12 | E//Kok Keen | 2024-06-11 | 0607Central-GTSB-BOQ Template | DU00003557043 |  |  | 2024-06-27 | 2024-06-23 |  | A-bracket pole |  | 3m | Add R9264H M901821 x4,Dismantle R8894E M1821(A8A) x4 | 0 | 0
2838C | TAR Campus (REL) | Central |  | Modernization |  | 2024 Q1 | MA | GTSB | 4.6 TSSR Approved |  | 2024-05-21 | 2024-05-24 |  | 2024-06-12 |  | Closed | 2024-06-13 | 2024-06-14 | E//Kok Keen | 2024-06-14 | CelcomDigi_RAN_GTSB_TSS_Central_20240528 | DU00003557044 |  |  | 2024-06-22 | 2024-06-22 |  | Monopole |  | 18M | Add R9264H M901821 x3,Dismantle R9224E M1821(AAB) x3 | 0 | 0
2839C | TARC Hostel (REL) | Central |  | Modernization |  | 2024 Q1 | MA | CCSMY | 4.6 TSSR Approved |  | 2024-06-25 | 2024-06-26 |  | 2024-07-01 |  | Closed | 2024-07-03 | 2024-07-05 |  | 2024-07-03 | 0626Central-CCSMY-BOQ Template (template) | DU00003557045 |  |  | 2024-08-19 | 2024-08-14 |  | Monopole |  | 30m | Add R9264M M1821 x1+R9264H M901821 x4,Dismantle R8894E M1821(A8A) x4 | 0 | 1
4084L | K01764_PPR KPKT LANGKAWI | Northern |  | Remote MOCN |  | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00005321212 | [8 empty] | Reuse Existing RRU
Q02098 | Q124A_Q02098OD_KENYALANGCOMM2 | Sarawak |  | Decomm |  | 2024 Q1_496 | ZB | South Pacific | 4.6 TSSR Approved |  | 2023-10-18 |  |  |  | 2023-10-23 |  | 2023-10-24 | 2023-11-06 | CD//John | 2023-10-24 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20231020/0612Sarawak-South Pacific-BOQ Template (template) | DU00002576630 |  |  |  |  | 2024-03-14 |  | MINIMAST
Q01785 | Q124F_Q01785OD_CB_KGPASIRPUTIHKCH | Sarawak |  | Decomm |  | 2024 Q1_496 | ZB | South Pacific | 4.6 TSSR Approved |  | 2023-09-09 |  |  |  | 2023-09-19 |  | 2023-09-19 | 2023-09-29 |  | 2023-09-19 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230913/0612Sarawak-South Pacific-BOQ Template (template) | DU00002576631 |  |  |  |  | 2023-11-25 |  | TOWER
Q01696 | Q124F_Q01696OD_CB_TNBAKO | Sarawak |  | MOCN Decomm | Swap->Maintain USP MOCN->On Hold->MOCN Decomm | 2024 Q1_496 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002576632 | [6 empty] | TOWER
Q01533 | Q124A_Q01533OD_JLNPLBHKCH | Sarawak |  | Decomm |  | 2024 Q1_496 | SH | South Pacific | 4.6 TSSR Approved |  | 2023-09-19 |  |  |  | 2023-09-22 |  | 2023-09-22 | 2023-11-06 |  | 2023-09-22 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230923/0612Sarawak-South Pacific-BOQ Template (template) | DU00002576633 |  |  |  |  | 2023-11-21 |  | RAMO
Q01521 | Q124A_Q01521OD_THEISTHMUSKCH | Sarawak |  | Decomm |  | 2024 Q1_496 | SH | South Pacific | 4.6 TSSR Approved |  | 2023-09-09 |  |  |  | 2023-09-27 |  | 2023-09-30 | 2023-11-06 |  | 2023-10-01 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230923/0612Sarawak-South Pacific-BOQ Template (template) | DU00002576634 |  |  |  |  | 2023-11-30 |  | RAMO
Q01383 | Q124F_Q01383OD_DEMAKLAUTIND2 | Sarawak |  | Decomm |  | 2024 Q1_496 | ZB | South Pacific | 4.6 TSSR Approved |  | 2023-09-18 |  |  |  | 2023-10-02 |  | 2023-10-02 | 2023-10-13 | CD//John | 2023-10-03 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20231006/0612Sarawak-South Pacific-BOQ Template (template) | DU00002576635 |  |  |  |  | 2023-12-31 |  | RAPOLE
Q01361 | Q124F_Q01361OD_KGDEMAKBARU | Sarawak |  | Decomm |  | 2024 Q1_496 | ZB | South Pacific | 4.6 TSSR Approved |  | 2023-10-18 |  |  |  | 2023-10-19 |  | 2023-10-19 | 2023-11-06 | CD//John | 2023-10-31 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20231020/0612Sarawak-South Pacific-BOQ Template (template) | DU00002576636 |  |  |  |  | 2023-11-27 |  | LAMP_POLE
Q01236 | Q124B_Q01236OD_CB_PLAZAMERDEKA | Sarawak |  | Decomm |  | 2024 Q1_496 | SH | South Pacific | 4.6 TSSR Approved |  | 2023-10-02 |  |  |  | 2023-10-05 |  | 2023-10-07 | 2023-10-13 |  | 2023-10-07 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20231006 | DU00002576637 |  |  |  |  | 2023-11-17 |  | TBC
Q01219 | QP10929_SEBID | Sarawak |  | Decomm |  | 2024 Q1_496 | ZB | South Pacific | 4.6 TSSR Approved |  | 2024-01-03 |  |  |  | 2024-01-03 |  | 2024-01-11 | 2024-01-22 | CD//John | 2024-01-12 | Celcom Digi_RAN-South Pacific-Standard PR TSS-Sarawak-20240109/0612Sarawak-South Pacific-BOQ Template (template) | DU00002576638 |  |  |  |  | 2024-08-08 |  | INBUILDING
Q01218 | Q124B_Q01218OD_MEDANPELITA | Sarawak | 9380K | Swap | Decomm->On Hold->Swap | 2024 Q1_496 | ZB | South Pacific | 4.6 TSSR Approved |  | 2024-08-30 | 2024-09-05 |  | 2024-09-10 | 2023-09-30 | Under Approval | 2024-09-26 | 2024-10-02 | CD//John | 2024-10-02 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230930/0823CD-Sarawak-South Pacific-BOQ Template(new contract) | DU00002576639 |  |  | 2025-06-28 | 2025-05-08 |  | Wall mount boom | TBC | 2.9m & 3m | Add R8862A S9000 x3 + R8894E M1821 x4 + R8862A S2601 x2 + R8854 S2600x1, Dismantle Celcom RRU | 0 | 3
Q01034 | Q124F_Q01034OD_SEJINGKATIND | Sarawak |  | Decomm |  | 2024 Q1_496 | ZB | South Pacific | 4.6 TSSR Approved |  | 2023-09-20 |  |  |  | 2023-09-26 |  | 2023-09-26 | 2023-10-04 |  | 2023-09-26 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230923/0612Sarawak-South Pacific-BOQ Template (template) | DU00002576640 |  |  |  |  | 2024-01-05 |  | RAPOLE
Q00895 | Q124A_Q00895IB_BCCKID | Sarawak |  | Decomm |  | 2024 Q1_496 | SH | Datasco | 4.6 TSSR Approved |  | 2023-09-19 |  |  |  | 2023-09-20 |  | 2023-09-20 | 2023-09-23 |  | 2023-09-21 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230921 | DU00002576641 |  |  |  |  | 2024-04-28 |  | BOOM
Q00881 | Q124A_Q00881OD_LRGSPG3 | Sarawak |  | Decomm |  | 2024 Q1_496 | SH | South Pacific | 4.6 TSSR Approved |  | 2023-09-05 |  |  |  | 2023-09-05 |  | 2023-09-05 | 2023-09-16 | CD//John | 2023-09-06 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230911 | DU00002576642 |  |  |  |  | 2023-11-15 |  | TOWER
Q00877 | Q124F_Q00877OD_SMTSEJINGKAT | Sarawak |  | Decomm |  | 2024 Q1_496 | SH | Trintel | 4.6 TSSR Approved |  | 2023-09-25 |  |  |  | 2023-09-26 |  | 2023-09-26 | 2023-10-13 | CD//John | 2023-10-10 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230930 | DU00002576643 |  |  |  |  | 2023-11-10 |  | BOOM
Q00837 | Q124A_Q00837OD_UMWKCH | Sarawak |  | Decomm |  | 2024 Q1_496 | ZB | South Pacific | 4.6 TSSR Approved |  | 2023-09-05 |  |  |  | 2023-09-15 |  | 2023-09-15 | 2023-10-06 | CD//John | 2023-09-18 | Celcom Digi_RAN-South Pacific-TSS DECOMM-Sarawak-20230901 | DU00002576644 |  |  |  |  | 2023-11-14 |  | BOOM
Q00736 | QT10279_THESPRINGID | Sarawak |  | Decomm |  | 2024 Q1_496 | SH | Datasco | 4.6 TSSR Approved |  | 2023-09-27 |  |  |  | 2023-10-02 |  | 2023-10-02 | 2023-10-13 | CD//John | 2023-10-03 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231006 | DU00002576645 |  |  |  |  | 2024-01-24 |  | UNIPOLE
Q00714 | Q124A_Q00714OD_SGPERIUK | Sarawak |  | Decomm |  | 2024 Q1_496 | ZB | South Pacific | 4.6 TSSR Approved |  | 2023-08-28 |  |  |  | 2023-08-29 |  | 2023-08-29 | 2023-09-10 | CD//John | 2023-08-30 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230830/Celcom Digi_RAN-South Pacific-TSS DECOMM-Sarawak-20230901 | DU00002576646 |  |  |  |  | 2023-11-10 |  | TOWER
Q00634 | Q124F_Q00634OD_CB_MUARATEBAS | Sarawak |  | Decomm |  | 2024 Q1_496 | SH | Trintel | 4.6 TSSR Approved |  | 2023-09-18 |  |  |  | 2023-09-21 |  | 2023-09-21 | 2023-09-29 | CD//John | 2023-09-22 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230919 | DU00002576647 |  |  |  |  | 2023-11-06 |  | TOWER
Q00610 | Q124F_Q00610OD_TMSEJINGKAT | Sarawak |  | Decomm |  | 2024 Q1_496 | SH | Trintel | 4.6 TSSR Approved |  | 2023-09-19 |  |  |  | 2023-09-21 |  | 2023-09-21 | 2023-10-06 | CD//John | 2023-09-22 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230921 | DU00002576648 |  |  |  |  | 2024-02-23 |  | TOWER
Q00549 | Q124F_Q00549OD_DEMAKLAUTIND | Sarawak |  | Decomm |  | 2024 Q1_496 | ZB | Trintel | 4.6 TSSR Approved |  | 2023-09-21 |  |  |  | 2023-09-25 |  | 2023-09-25 | 2024-03-21 |  | 2023-09-25 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230930 | DU00002576649 |  |  |  |  | 2023-11-17 |  | TOWER
Q00513 | Q124F_Q00513OD_BAKO | Sarawak |  | Decomm |  | 2024 Q1_496 | SH | Trintel | 4.6 TSSR Approved |  | 2023-09-19 |  |  |  | 2023-09-22 |  | 2023-09-22 | 2023-09-29 |  | 2023-09-22 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230921 | DU00002576650 |  |  |  |  | 2023-10-23 |  | TOWER
Q00296 | Q124A_Q00296IB_CROWNTOWERID | Sarawak |  | Decomm |  | 2024 Q1_496 | SH | Datasco | 4.6 TSSR Approved |  | 2023-10-06 |  |  |  | 2023-10-13 |  | 2023-10-13 | 2023-10-21 | CD//John | 2023-10-14 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231009 | DU00002576651 |  |  |  |  | 2024-01-02 |  | BOOM
Q00274 | Q124A_Q00274OD_TABUANAPONG | Sarawak |  | Decomm |  | 2024 Q1_496 | ZB | South Pacific | 4.6 TSSR Approved |  | 2023-08-28 |  |  |  | 2023-08-29 |  | 2023-08-29 | 2023-09-16 | CD//John | 2023-08-30 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230830 | DU00002576652 |  | uncompleted info & phoots |  |  | 2023-11-08 |  | TOWER
Q00159 | Q124A_Q00159OD_JLNPENDING | Sarawak |  | Decomm |  | 2024 Q1_496 | SH | South Pacific | 4.6 TSSR Approved |  | 2023-08-28 |  |  |  | 2023-08-29 |  | 2023-08-29 | 2023-09-12 | CD//John | 2023-08-30 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230830/Celcom Digi_RAN-South Pacific-TSS DECOMM-Sarawak-20230901 | DU00002576653 |  |  |  |  | 2023-10-11 |  | TOWER
Q00146 | Q124A_Q00146OD_JLNSEKAMA | Sarawak |  | Decomm |  | 2024 Q1_496 | ZB | South Pacific | 4.6 TSSR Approved |  | 2023-09-03 |  |  |  | 2023-09-04 |  | 2023-09-04 | 2023-09-12 | CD//John | 2023-09-04 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230905 | DU00002576654 |  |  |  |  | 2023-12-21 |  | TOWER
Q00086 | Q124A_Q00086OD_PENVIEW | Sarawak |  | Decomm |  | 2024 Q1_496 | SH | South Pacific | 4.6 TSSR Approved |  | 2023-09-05 |  |  |  | 2023-09-05 |  | 2023-09-05 | 2023-09-12 | CD//John | 2023-09-06 | Celcom Digi_RAN-South Pacific-TSS DECOMM-Sarawak-20230901 | DU00002576655 |  |  |  |  | 2023-11-14 |  | TOWER
Q00085 | Q124A_Q00085OD_PENDING | Sarawak |  | Decomm |  | 2024 Q1_496 | SH | Trintel | 4.6 TSSR Approved |  | 2023-09-19 |  |  |  | 2023-09-22 |  | 2023-09-22 | 2024-02-09 |  | 2023-09-22 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230921 | DU00002576656 |  |  |  |  | 2024-04-25 |  | TOWER
Q00053 | Q124A_Q00053OD_MENGHEECOURT | Sarawak |  | Decomm |  | 2024 Q1_496 | SH | Datasco | 4.6 TSSR Approved |  | 2023-09-27 |  |  |  | 2023-10-06 |  | 2023-10-07 | 2024-04-24 |  | 2023-10-07 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231006 | DU00002576657 |  |  |  |  | 2024-07-31 |  | BOOM
Q00051 | Q124A_Q00051OD_BINTAWAIND | Sarawak |  | Decomm |  | 2024 Q1_496 | ZB | Trintel | 4.6 TSSR Approved |  | 2023-10-11 |  |  |  | 2023-10-11 |  | 2023-10-17 | 2024-04-24 | CD//John | 2023-10-17 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231013 | DU00002576658 |  |  |  |  | 2023-11-30 |  | TOWER
Q00050 | Q124B_Q00050OD_SAUJANA | Sarawak |  | Decomm |  | 2024 Q1_496 | SH | Datasco | 4.6 TSSR Approved |  | 2023-09-26 |  |  |  | 2023-09-29 |  | 2023-10-02 | 2023-10-06 | CD//John | 2023-10-04 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230930 | DU00002576659 |  |  |  |  | 2023-12-28 |  | BOOM
Q00046 | Q124A_Q00046OD_TMNRIVERVIEW | Sarawak |  | Decomm |  | 2024 Q1_496 | ZB | South Pacific | 4.6 TSSR Approved |  | 2023-09-21 |  |  |  | 2023-09-26 |  | 2023-09-26 | 2023-11-06 |  | 2023-09-26 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230923/0612Sarawak-South Pacific-BOQ Template (template) | DU00002576660 |  |  |  |  | 2024-02-23 |  | MONOPOLE
Q00019 | Q124F_Q00019OD_SEJINGKATPWR | Sarawak |  | Decomm |  | 2024 Q1_496 | SH | South Pacific | 4.6 TSSR Approved |  | 2023-09-12 |  |  |  | 2023-09-19 |  | 2023-09-19 | 2023-11-06 |  | 2023-09-19 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20230915/0612Sarawak-South Pacific-BOQ Template (template) | DU00002576661 |  |  |  |  | 2024-04-05 |  | BOOM
4472B | BAGAN DATOH MAXIS | Northern |  | Remote MOCN |  | 2026 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612326 | [6 empty] | 60m 3 Legged Tower
3732B | Jalan Metro Perdana Barat | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.1 Drop (No Survey) | [12 empty] | DU00002612327 | [6 empty] | 24m Lampole
4793B | Kelian Intan | Northern |  | Remote MOCN | Modernization->Remote MOCN | 154 single site MOCN |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612328 | [6 empty] | 60m 3 Legged Tower
4533B | Jln Panglima RDD | Northern |  | Remote MOCN |  | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612329 | [6 empty] | 3m Boom (RT)
4668A | Changloon Town | Northern |  | Remote MOCN |  | 2024 Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612330 | [6 empty] | 3m Boom (RT) |  |  |  | 1
4996A | NS Highway KM6.7 | Northern |  | Remote MOCN |  | 2024 Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612331 | [6 empty] | 60m 4 Legged Tower
4355B | Pasir Puteh Ipoh RCC | Northern |  | Remote MOCN |  | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612332 | [6 empty] | Tower |  |  |  | 1
1079B | Happy Garden | Central |  | Remote MOCN |  | 2024 Q3 |  | YPTT | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612333 | [6 empty] | 3m Boom (RT)
7098A | Tungku Town | Sabah |  | Remote MOCN |  | 2024 Q4(single site MOCN)-L2126 SSM |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612334 | [6 empty] | Tower
4355A | NSKM306 (Maxis) | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q3 |  |  | 14.1 Drop (No Survey) |  | 2024-12-17 |  |  |  |  | To be Submitted | [5 empty] | DU00002612335 | [6 empty] | 45m Monopole |  | Reuse Existing RRU | 0 | 0
4967B | Pdg Lumat | Northern |  | Modernization | Modernization->Remote MOCN->Modernization | 2025 Q3 | HW | GCI | 4.6 TSSR Approved |  | 2025-05-28 |  |  | 2025-06-04 |  | Under Approval | 2025-06-12 | 2025-09-26 | E//Hazida | 2025-06-17 | SQ202506100515 | DU00002612336 |  |  | 2025-09-26 | 2025-09-11 |  |  | 76m 4 Legged Tower | 75m | Add R8862A S9000x1+R8862A S2601x1+A9732 M1821x1 | 2 | 0
4905B | Spg Pulai KM34 | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612337 | [6 empty] | Tower |  | Reuse Existing RRU | 0 | 0
3244A | Presint 15 | Central |  | Site Out (Modernization) | Remote MOCN->Site Out->Site Out (Modernization) | 2024 Q3 |  | YPTT | [SiteOut]- 4.4 Pending TSSR Review - Design Team |  | 2025-06-28 |  | 2025-07-10 |  | 2025-07-11 | [5 empty] | SQ202506140184 | DU00002612338 | [6 empty] | 3m RT (Wall Mounted Pole) |  |  |  | 3
4354B | Jalan Tokong | Northern |  | Remote MOCN |  | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612339 | [6 empty] | 6m RT (Boom)
4578B | Kg Ulu Lengkor | Northern |  | Remote MOCN |  | 2025 Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612340 | [6 empty] | Tower |  | Reuse Existing RRU | 0 | 0
4977B | Tobiar | Northern |  | Modernization |  | 154 single site MOCN | SM | GTSB | 4.6 TSSR Approved |  | 2024-08-29 | 2024-09-06 |  | 2024-09-10 |  | Rectificating | 2024-09-11 | 2024-09-24 | E//Hazida | 2024-09-23 | 0809CD-Northern-GTSB-BOQ Template(new contract) | DU00002612341 |  |  | 2024-09-21 | 2024-09-16 |  | Tower | 60m 3 legged tower | 60 | Add R8852E S9000 x3+R8894E M1821 x4+R8862A S2601 x1,Dismantle R8882-GUL1812 x3 | 0 | 2
4804C | Restoran Tuck Kee | Northern |  | Remote MOCN |  | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612342 | [6 empty] | 6m Unipole RT
9517A | King Centre Miri MP | Sarawak |  | Modernization |  | 2024 Q4(single site MOCN)-L21 SSM | SHA | Datasco | 4.6 TSSR Approved |  | 2023-11-14 | 2023-11-06 |  | 2024-10-25 |  | Under Approval | 2024-10-25 | 2024-10-30 | E//Syahriani | 2024-10-30 | N/A-Under BAU/Celcom Digi_RAN_Datasco_TSS_Sarawak_20241030 | DU00002612343 |  |  | 2024-11-22 | 2024-11-06 |  | Monopole | 30m Monopole | 30 | Add R8862A S9000x3+R8894E M1821x1+A9732 M1821x2, Dismantle R8882 S1800B(B6B)x3 | 13 | 0
4347B | Ritz Garden Hotel (REL) | Northern |  | Remote MOCN |  | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612344 | [6 empty] | 3m Boom (RT)
4657B | BKH Teleflow(ZED) | Northern |  | Remote MOCN |  | 2024 Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612345 | [6 empty] | Tower
4630B | Padang Lembu | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612346 | [6 empty] | Tower |  |  |  | 1
4003D | SMK Raja Perempuan | Northern |  | Modernization |  | 2024 Q2 | SM | GTSB | 4.6 TSSR Approved | ¦ 0123 - BOM uploaded | 2024-01-11 | 2024-01-15 |  | 2024-01-19 |  | Rectificating | 2024-01-22 | 2024-01-30 | E//Hazida | 2024-01-23 | Celcom Digi_RAN-GTSB-TSS-Northern-202401114-0085 | DU00002612347 |  |  | 2024-02-27 | 2024-02-05 |  | Petronas Pylon | 30m Monopole | 25m | Add R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
4181D | Taman Arkid | Northern |  | Remote MOCN |  | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612348 | [6 empty] | 3m Boom (RT)
3102A | DESA PARK CITY NKVE (REL) | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612349 | [6 empty] | 30m Minaret
4956C | Jalan Tiong SP | Northern |  | Modernization |  | 2024 Q1 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-09-21 | 2023-09-26 |  | 2023-10-02 |  | Closed | 2023-10-03 | 2023-10-27 | E//Hazida | 2023-10-25 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230922-0044 | DU00002612350 |  |  | 2024-01-15 | 2024-01-11 |  | Monopole | 30m Lampole | 30M | Add R8862A S9000 x3+R8894E M1821 x5+R8854 S2600 x2,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R8862A S2600(A4A) x2 |  | 12
3317C | Taman Sungai Besi (REL) | Central |  | Remote MOCN |  | 2024 Q3 |  | GTSB | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612351 | [6 empty] | 18m Lampole
9302B | Jln Datuk Mohd Musa | Sarawak |  | Remote MOCN |  | 2024 Q2 |  | Trintel | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612352 | [6 empty] | 30m Monopole |  | Reuse existing RRU |  | 23
4348B | Jaya Jusco Station 18 Ipoh | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612353 | [6 empty] | In-building system
4574B | Bekor RDD | Northern |  | Remote MOCN |  | 2025 Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612354 | [6 empty] | 60m 3 Legged Tower |  | Reuse Existing RRU | 0 | 0
4825C | Lawan Kuda (REL) | Northern |  | Modernization |  | 2024 Additional | SM | CCSMY | 4.6 TSSR Approved |  | 2024-11-19 | 2024-11-28 |  | 2024-12-02 |  | Rectificating | 2024-12-03 | 2024-12-06 | E//Hazida | 2024-12-06 | 1911CD-Northern-TSS-BOQ Template(new contract)_CCSMY_V2 | DU00002612355 |  |  | 2024-12-21 | 2024-12-11 |  | Monopole |  | 30 | Add R8894E M1821x3, Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3 | 0 | 0
2848A | Desa Tun Razak Industry (ZED) | Central |  | Remote MOCN |  | 2024 Q3 |  | YPTT | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612356 | [6 empty] | 3m Boom (RT)
2373A | Hotel Sri Sutra | Central |  | Remote MOCN |  | 2024 Q2 | IE | Datasco | 14.2 Drop (Done Survey) |  | 2023-07-01 |  |  |  |  | To be Submitted | [5 empty] | DU00002612357 | [6 empty] | 3m Bipod (RT)
4325B | Bitis-100Q4 RCC | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612358 | [6 empty] | 60m 3 Legged Tower
2831A | One Utama Phase 2 | Central |  | Modernization | Modernization->Remote MOCN->Modernization | 2024 Q2 | CR | Datasco | 4.6 TSSR Approved |  | 2024-03-29 | 2024-03-29 |  | 2024-04-05 |  | Closed | 2024-04-15 | 2024-04-16 | E//Nazrul | 2024-04-15 | CelcomDigi_RAN_Datasco_TSS_Central_20230901 | DU00002612359 |  |  | 2024-08-21 | 2024-04-27 |  | Portables BTS | In-building system |  | Add R8862A S2601 x2,Dismantle R8882-L268 x2
7718B | Bandar Labuk Square | Sabah |  | Remote MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612360 | [6 empty] | 30m Monopole
1827B | Beranang | Central |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q1 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612361 | [6 empty] | 45m 3 Legged Tower |  | Reuse Existing RRU | 0 | 0
3325A | Sunway Mas | Central |  | Remote MOCN |  | 2024 Q3 | IE | Datasco | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612362 | [6 empty] | 30m Lampole
2273A | Tesco Kajang | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4(single site MOCN)-L2126 SSM |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612363 | [6 empty] | 3m Bipod (RT)
4364A | Bdr Baru Kampar | Northern |  | Modernization |  | 2024 Additional | AI | CCSMY | 4.6 TSSR Approved |  | 2024-12-05 | 2024-12-20 |  | 2024-12-24 |  | Closed | 2024-12-24 | 2025-02-07 | E//Hazida | 2025-01-14 | 1911CD-Northern-TSS-BOQ Template(new contract)_CCSMY_V2 | DU00002612364 |  |  | 2025-06-26 | 2025-01-04 |  | Unipole |  | 9 | Add R8894E M1821x3+R8862A S2601x3, Dismantle R8882-GUL1812x2+R8882 S1800B(B6B)x3+R8862A S1800(B6A)x1+R8862A S2100(A6A)x3+R8882 S2600(B4A)x3 | 0 | 0
2572B | Lingui Sg Buloh 1 | Central |  | Remote MOCN |  | 2024 Q1 | IE | Datasco | 14.2 Drop (Done Survey) |  | 2023-07-01 |  |  |  |  | To be Submitted | [5 empty] | DU00002612365 | [6 empty] | 60m 3 Legged Tower
1136B | Ladang Tenusu UPM | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612366 | [6 empty] | 45m Monopole Tree |  | Add R8862A S2601x3, Dismantle R8882 S2600(B4A)x3 | 0 | 0
4667A | Bukit Kayu Hitam(Celcom) | Northern |  | Remote MOCN |  | 2024 Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612367 | [6 empty] | Tower |  |  |  | 12
3239A | Kg Melayu Ampang | Central |  | Remote MOCN |  | 2024 Q4 | SS | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612368 | [6 empty] | 3m Boom (RT)
4151B | Bdr Puteri Jaya SP (REL) | Northern |  | Remote MOCN |  | 2024 Q1 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612369 | [6 empty] | 3m Boom (RT)
4629B | UiTM Semeling (Mxs) | Northern |  | Modernization |  | 2024 Q1 |  | Ascentrack | 4.6 TSSR Approved |  | 2023-09-21 |  |  | 2024-04-17 |  | Closed | 2024-01-02 | 2024-01-05 | E//Hazida | 2024-01-05 | Celcom Digi_RAN-Ascentrack-TSS-Northern-20230925-0011 | DU00002612370 |  |  | 2024-01-22 | 2024-01-10 |  |  | 60m 3 Legged Tower |  | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3
7248A | SKCC | Sabah |  | Remote MOCN |  | 2024 Q1 | MS | GTSB | 14.2 Drop (Done Survey) |  | 2023-09-11 |  |  |  |  | To be Submitted |  |  |  |  | N/A- Remote MOCN | DU00002612371 | [5 empty] | In-Building System | 3m RT (Minimast) | 8M
4920B | Tupai Industry | Northern |  | Remote MOCN |  | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612372 | [6 empty] | 6m RT (Boom) |  |  |  | 1
7838A | Grand Dorsett Labuan | Sabah |  | Remote MOCN |  | 2024 Q4(single site MOCN)-L26 SSM |  | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612373 | [6 empty] | IBS + 3m RT (Boom)
1048A | Bdr Teknologi Kajang | Central |  | Decomm | Modernization->Remote MOCN->Decomm | 2025 Q1 | AI | GCI | 4.6 TSSR Approved |  | 2025-03-23 |  | 2025-04-03 |  | 2025-04-04 | To be Submitted | 2025-04-13 |  | E//Sumitra | 2025-04-15 | SQ202506120286 | DU00002612374 |  | Pls provide tx equipment photo at Digi & Celcom Cabinet/Rack |  |  | 2025-08-20 |  | 3m RT (Minimast) |  |  |  | 23
3381A | Silk1 | Central |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q1 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612375 | [6 empty] | 30m Monopole |  | Reuse Existing RRU | 0 | 0
2145A | Tesco Kepong Outdoor | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.2 Drop (Done Survey) |  | 2023-05-30 |  |  |  |  | To be Submitted | [5 empty] | DU00002612376 | [6 empty] | 3m RT (Tripod)
4438B | Kg Padang Assam | Northern |  | Remote MOCN |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612377 | [6 empty] | 3m RT (Minimast)
2876A | Tmn Sri Bahtera | Central |  | Remote MOCN |  | 2024 Q3 |  | GTSB | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612378 | [6 empty] | 6m RT (Boom)
4740A | Pantai Tengah | Northern |  | Modernization | Modernization->On Hold->Modernization | 2025 Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2025-04-14 | 2025-04-16 |  | 2025-04-17 |  | Closed | 2025-04-17 | 2025-04-26 | E//Hazida | 2025-04-23 | S1MY2024071003WBF1-2046 | DU00002612379 |  |  | 2025-05-13 | 2025-03-14 |  | Monopole |  | NA | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3 | 0 | 0
3077C | AYER 8 Presint 8 | Central |  | Site Out (Modernization) | Remote MOCN->Site Out->Site Out (Modernization) | 2024 Q3 |  | YPTT | [SiteOut]- 4.4 Pending TSSR Review - Design Team |  | 2025-06-27 |  | 2025-07-10 |  | 2025-07-14 | [5 empty] | SQ202506140184 | DU00002612380 | [6 empty] | 3m RT (Wall Mounted Pole) |  |  |  | 24
4114C | Pekan Assam Kumbang | Northern |  | Remote MOCN |  | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612381 | [6 empty] | 3m Bipod (RT) |  |  |  | 2
4960A | SMT Pokok Tai | Northern |  | Modernization |  | 131 single site mocn | SM | CCSMY | 4.6 TSSR Approved |  | 2024-08-16 | 2024-09-11 |  | 2024-09-13 |  | Under Approval | 2024-09-13 | 2024-09-26 | E//Hazida | 2024-09-25 | 0809CD-Northern-CCSMY-BOQ Template(new contract) | DU00002612382 |  |  | 2024-10-11 | 2024-09-28 |  | Tower | 55m 3 Legged Tower | 55m | Add R8862A S9000 x3+R8894E M1821 x1+A9732 M1821 x2,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3 | 12 | 0
2498A | Kg Kemensah (KJS) | Central |  | Remote MOCN |  | 2024 Q2 | SS | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612383 | [6 empty] | 45m Tower
2976B | PAVILLION | Central |  | Remote MOCN |  | 2024 Q2 |  | GTSB | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612384 | [6 empty] | In-building system
9014C | Gala City | Sarawak |  | Remote MOCN |  | 2024 Q1 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-22 |  |  |  |  | To be Submitted | [5 empty] | DU00002612385 | [6 empty] | 3m Boom (RT)
9150B | E-Mart MJC IB | Sarawak |  | Remote MOCN |  | 2024 Q2 |  |  | 14.1 Drop (No Survey) |  | 2025-08-08 |  |  |  |  | To be Submitted | [5 empty] | DU00002612386 | [6 empty] | In-building system
4743B | Bagan Pasir Laut | Northern |  | Remote MOCN |  | 154 single site MOCN |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612387 | [6 empty] | 76m 4 Legged
2400A | KM290 NS H_way(AsiaSpace _ZED) | Central |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q1 |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612388 | [6 empty] | 60m 3 Legged Tower |  | Reuse Existing RRU | 0 | 0
4615A | Mata Ayer Perlis | Northern |  | Remote MOCN |  | 2026 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612389 | [6 empty] | 60m 3 Legged Tower
2959A | Subang Suria(REL) | Central |  | Remote MOCN |  | 2024 Q1 | IE | Datasco | 14.2 Drop (Done Survey) |  | 2023-10-09 |  |  |  |  | To be Submitted | [5 empty] | DU00002612390 | [6 empty] | 3m Boom (RT) |  |  | 23
7961B | Rose Garden | Sabah |  | Remote MOCN |  | 2024 Q1 |  |  | 14.1 Drop (No Survey) | [12 empty] | DU00002612391 | [6 empty] | 30m Lampole |  |  |  | 12
4260A | NS Highway KM169(Maxis) | Northern |  | Remote MOCN | Modernization->Remote MOCN | 154 single site MOCN |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612392 | [6 empty] | 60m 3 Legged Tower
1657C | Casmaria Apartment | Central |  | Remote MOCN |  | 2024 Q1 | SS | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612393 | [6 empty] | 24m Lampole |  |  |  | 13
3251A | Desa Ria | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612394 | [6 empty] | 3m Bipod (RT)
7416A | USP Kg Barambangan | Sabah |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4(single site MOCN)-L26 SSM |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612395 | [6 empty] | 60m 4 Legged Tower
4430D | Sejati WaterFront | Northern |  | Remote MOCN |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612396 | [6 empty] | 30M Monopole Tree |  |  |  | 1
9579B | Kampung Bersatu Lambir | Sarawak |  | Modernization |  | 2025 Q2 | HW | Datasco | 4.6 TSSR Approved |  | 2023-12-04 | 2023-12-12 |  | 2025-05-13 |  | Under Approval | 2025-05-14 | 2025-05-21 | E//John | 2025-05-20 | N/A-Under BAU | DU00002612397 |  |  | 2025-07-06 | 2025-06-20 |  | Tower | Tower | 45 | Add R8852E S9000x3+R8894E M1821x1+R8854 S2600x1, Dismantle R8862A S2600(A4A)x1 | 0 | 3
3720A | Sri Jalil | Central |  | Remote MOCN |  | 2024 Q3 |  | YPTT | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612398 | [6 empty] | 24m Lampole |  |  |  | 13
1047B | Tmn Bukit Teratai | Central |  | Remote MOCN |  | 2024 Q3 | SS | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612399 | [6 empty] | 6m RT (Wall Mounted Pole) |  |  |  | 2
9766B | RPR Taman Indah Landeh | Sarawak |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q3 |  | Datasco | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612400 | [6 empty] | 30M Rapole |  | Reuse Existing RRU | 12 | 0
9560B | Kampung Rassau | Sarawak |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612401 | [6 empty] | Tower
2715B | Kajang Prima WaterTank | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612402 | [6 empty] | 30m Monopole
4463D | Kerian Sentral Mall (REL) | Northern |  | Remote MOCN |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612403 | [6 empty] | 30M Lampole |  |  | 1
7462B | IOI Syarimol 7 | Sabah |  | Site Out (Modernization) | Modernization->On Hold->Modernization->Site Out->Replacement, Site Out (Modernization) | 2024 Q4 | AD | GTSB | [SiteOut]- 4.5 Pending TSSR Review - Customer |  | 2023-12-15 | 2024-01-10 |  | 2025-02-17 |  | Under Approval | 2025-02-19 |  | E//Hannah |  |  | DU00002612404 | [5 empty] | Tower | Tower | 75m | Reuse Existing RRU | 0 | 0
4161D | Desa Corina | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4(single site MOCN)-L26 SSM |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612405 | [6 empty] | 30m RDS
7259C | Kampung Soka | Sabah |  | Remote MOCN |  | 2024 Q1 |  |  | 14.1 Drop (No Survey) | [12 empty] | DU00002612406 | [6 empty] | 30M Rapole |  |  |  | 2
7561B | Anggerik Perdana | Sabah |  | Modernization |  | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2024-03-13 | 2024-03-14 |  | 2024-04-05 |  | Closed | 2024-04-08 | 2024-04-19 | E//Hannah | 2024-04-19 | Celcom Digi_RAN-Futong-Standard PR TSS-Sabah-20240313 | DU00002612407 |  |  | 2024-06-26 | 2024-06-22 |  | Tower | Tower | 60 | Add R8862A S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 23 | 0
7038A | Lokkawi | Sabah |  | Remote MOCN |  | 2024 Q1 |  |  | 14.1 Drop (No Survey) | [12 empty] | DU00002612408 | [6 empty] | 45m 4 Legged Tower |  |  |  | 13
7733B | Ladang Tas | Sabah |  | Remote MOCN |  | 2024 Q4(single site MOCN)-L2126 SSM |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612409 | [6 empty] | Tower |  |  |  | 3
4975C | Surau Al Solihin Kg Batu Putih | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q3 |  |  | 14.1 Drop (No Survey) | AAU Cannot Install-Change MM to BI¦AAU can not install | [5 empty] | To be Submitted | [5 empty] | DU00002612410 | [6 empty] | 30M Minaret |  | Reuse Existing RRU | 0 | 13
1836B | Desa Sri Jenaris | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612411 | [6 empty] | 3m Bipod (RT) |  |  | 12
7036C | Taman Mutiara | Sabah |  | Remote MOCN |  | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [12 empty] | DU00002612412 | [6 empty] | 24m Lampole |  |  | 23
9164A | Kg. Simboh | Sarawak |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q1 |  | Datasco | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612413 | [6 empty] | 45m 3 Legged Tower |  |  |  | 13
2425A | Tmn Dato Senu | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612414 | [6 empty] | 3m Boom (RT) |  |  | 13
7841A | Warisan Square RT | Sabah |  | Remote MOCN |  | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612415 | [6 empty] | 3m Boom (RT)
1233A | Cosmopleks | Central |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q1 |  | Magicell | 14.1 Drop (No Survey) | [12 empty] | DU00002612416 | [6 empty] | 3m Bipod (RT) |  | Reuse Existing RRU | 0 | 0
1214A | Jalan Kenari Shoplot | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 | MA | Ascentrack | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | Celcom Digi_RAN-Ascentrack-TSS BAU-20230729-0001_V1 | DU00002612417 | [6 empty] | 6m RT (Boom) |  |  |  | 12
3307C | Cheras Hartamas (REL) | Central |  | Remote MOCN |  | 2024 Q3 | SS | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612418 | [6 empty] | 3m Boom (RT)
3390A | Guthrie1 | Central |  | Remote MOCN |  | 2024 Q1 | IE | Datasco | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612419 | [6 empty] | 30m Monopole |  |  |  | 4
2019B | Desa Park City Watertank (REL) | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612420 | [6 empty] | 30m Monopole
9064A | Rhiga Royal Hotel | Sarawak |  | Remote MOCN |  | 2025 Q1 |  | Datasco | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612421 | [6 empty] | 3m RT (Wall Mounted Pole) |  | Reuse Existing RRU | 0 | 2
4560C | Kampung Tok Gula (REL) | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2027 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612422 | [6 empty] | Tower
3258C | Persiaran Hampshire Streetlight (REL) | Central |  | Remote MOCN |  | 2024 Q2 |  | GTSB | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612423 | [6 empty] | 24m Lampole |  |  | 2
1416B | Sg. Buluh (REL) | Central |  | Remote MOCN |  | 2024 Q1 | IE | Datasco | 14.2 Drop (Done Survey) |  | 2023-11-28 |  |  |  |  | To be Submitted | [5 empty] | DU00002612424 | [6 empty] | 24m Lampole
4318A | BIDOR2 | Northern |  | Remote MOCN |  | 2025 Q1 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612425 | [6 empty] | 45m 4 Legged Tower
4557D | St Keretapi Sungkai (REL) | Northern |  | Remote MOCN |  | 2026 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612426 | [6 empty] | 45M Tower |  |  | 12
3608B | Jln Othman | Central |  | Remote MOCN |  | 2024 Q3 | MA | Ascentrack | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612427 | [6 empty] | 24m Lampole |  |  | 2
7690A | Sipitang-Tenom Highway | Sabah |  | Remote MOCN | Modernization->Remote MOCN | 131 single site mocn |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612428 | [6 empty] | Tower |  |  |  | 12
4518B | Maxis Simpang Pulai | Northern |  | Remote MOCN |  | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612429 | [6 empty] | 45m 3 Legged Tower |  |  | 23
7356B | Taman Khazanah Indah | Sabah |  | Remote MOCN | Modernization->On Hold->Modernization->Remote MOCN | 2024 Q4 |  |  | 14.0 TSSR Not Required (Reuse Existing BBU/RRU) | [6 empty] | To be Submitted | [5 empty] | DU00002612430 | [6 empty] | 45m 3 Legged Tower |  | Reuse Existing RRU | 2 | 0
2711B | DATARAN 32 | Central |  | Remote MOCN |  | 2024 Q3 | MA | Ascentrack | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | Celcom Digi_RAN-Ascentrack-TSS BAU-20230729-0001_V1 | DU00002612431 | [6 empty] | 3m Boom (RT) |  |  | 12
4629D | Amanjaya Mall Stealth Tower (REL) | Northern |  | Remote MOCN |  | 2024 Q1 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612432 | [6 empty] | Tower |  |  | 123
2788A | Pelangi Square Shoplot | Central |  | Remote MOCN |  | 2024 Q2 | IE | Datasco | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612433 | [6 empty] | 24m Monopole |  |  |  | 12
3594C | Sekesyen 5 Bandar Rinching | Central |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q1 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612434 | [6 empty] | 3m Boom (RT) |  |  |  | 3
3730B | Metro Prima - Kepong | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612435 | [6 empty] | 24m Lampole |  |  | 3
3869C | KFC Kuchai Lama | Central |  | Remote MOCN |  | 2024 Q3 |  | YPTT | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612436 | [6 empty] | 18m Lampole
4668B | Klj Matric Kedah(Mxs) | Northern |  | Remote MOCN |  | 2024 Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612437 | [6 empty] | 60m 3 Legged Tower |  |  |  | 23
9708B | Kg Baru Samarahan | Sarawak |  | Remote MOCN | Remote MOCN->On Hold->Modernization->Remote MOCN | 2024 Q2 |  | Trintel | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612438 | [6 empty] | 30M Rapole |  | Reuse Existing RRU | 0 | 13
3739B | Kuchai Entrepreneurs Park | Central |  | Remote MOCN |  | 2024 Q3 |  | YPTT | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612439 | [6 empty] | 24m Lampole
2263A | Jln Sg Merab Bangi | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612440 | [5 empty] | In-Building System | 3m RT (Wall Mounted Pole) | 6m |  | 1
3013A | DESA DAMAI | Central |  | Remote MOCN |  | 2024 Q3 |  | YPTT | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612441 | [6 empty] | 3m Boom (RT) |  |  | 3
2667B | Jalan Gajah 9 | Central |  | Remote MOCN |  | 2024 Q1 | IE | Datasco | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612442 | [6 empty] | 45m 3 Legged Tower |  |  |  | 2
9067A | TV3 | Sarawak |  | Remote MOCN | Remote MOCN->On Hold->Remote MOCN | 2025 Q1 |  | Magicell | 3.4 SOW/Solution On Hold | [6 empty] | To be Submitted | [5 empty] | DU00002612443 | [6 empty] | 45m 4 Legged Tower |  | Reuse Existing RRU | 0 | 0
7405A | Kg Kesapang | Sabah |  | Remote MOCN |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612444 | [6 empty] | Tower |  |  |  | 23
1131B | Kajang Perdana | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612445 | [6 empty] | 3m Bipod (RT) |  |  |  | 12
4173D | Jalan Lintang Sg Siput | Northern |  | Remote MOCN |  | 2026 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612446 | [6 empty] | 18m Lampole
1069B | Jalan Yap Kwan Seng(ZED) | Central |  | Remote MOCN |  | 2024 Q2 |  | GTSB | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612447 | [6 empty] | 24m Monopole
9209A | Kelupu Road | Sarawak |  | Remote MOCN |  | 2025 Q2 |  | Trintel | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612448 | [6 empty] | Tower |  |  | 3
3290D | Pudu Hulu (REL) | Central |  | Remote MOCN |  | 2024 Q3 |  | GTSB | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612449 | [6 empty] | Land |  |  | 234
1722A | Tmn Kinrara | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 | MA | Ascentrack | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | Celcom Digi_RAN-Ascentrack-TSS BAU-20230729-0001_V1 | DU00002612450 | [6 empty] | 3m RT (Minimast) |  |  |  | 13
4407D | Taman Kemboja | Northern |  | Remote MOCN |  | 2024 Q1 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612451 | [6 empty] | landside |  |  | 13
1334A | Nagaria Podium | Central |  | Remote MOCN |  | 2024 Q2 |  | GTSB | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612452 | [6 empty] | 6m RT (Boom) |  |  | 1
7020C | Bandar Benoni | Sabah |  | Remote MOCN |  | 2024 Q1 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612453 | [6 empty] | 30m Lampole |  |  |  | 2
4642A | Langkawi Seaview | Northern |  | Remote MOCN | Modernization->Remote MOCN | 154 single site MOCN |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612454 | [6 empty] | 3m Boom (RT) |  |  |  | 2
3266B | Sunway Velocity Mall | Central |  | Remote MOCN |  | 2024 Q3 |  | GTSB | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612455 | [6 empty] | In-building system
3267A | IMPIANINDAH1 | Central |  | Remote MOCN |  | 2024 Q1 | SS | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612456 | [6 empty] | Tower
3113B | Taman Kepong Indah (HSR) | Central |  | Remote MOCN |  | 2024 Q1 | SS | Futong | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612457 | [5 empty] | BillBoard | 3m Bipod (RT) | 32 |  |  | 2
7489B | Simp. Kertam | Sabah |  | Remote MOCN |  | 2024 Q3(single site MOCN) |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612458 | [6 empty] | 76m 3 Legged Tower |  |  | 2
9007C | Batu Kawa Township | Sarawak |  | Remote MOCN |  | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612459 | [6 empty] | 30m Rapole |  |  |  | 1
3861C | DG Food Court | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 | MA | Ascentrack | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | Celcom Digi_RAN-Ascentrack-TSS BAU-20230729-0001_V1 | DU00002612460 | [6 empty] | 3m Boom (RT) |  |  |  | 23
7355B | Kg Melangkap Baru 2 | Sabah |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | MS | Seri Pancar | 4.6 TSSR Approved |  | 2024-10-21 | 2024-10-24 |  | 2024-10-24 |  | Closed | 2024-10-25 | 2024-10-30 | E//Hannah | 2024-10-30 | Celcom Digi_RAN Seri Pancar-Standard PR TSS-Sabah-20241028 | DU00002612461 |  |  | 2024-11-16 | 2024-11-12 |  | Tower | Tower | 76 | Remain existing RRU |  | 1
3301B | Pantai Medical Centre (REL) | Central |  | Remote MOCN | Remote MOCN->On Hold-> Remote MOCN | 2024 Q2 |  | GTSB | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612462 | [6 empty] | 6m Unipole RT |  |  |  | 0
3019A | TAMAN BERJAYA BARU | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612463 | [6 empty] | 3m Boom (RT) |  |  |  | 2
7005A | Beaufort jaya | Sabah |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612464 | [6 empty] | 45m 3 Legged Tower |  |  | 23
4651A | Kedawang | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612465 | [6 empty] | 48m 3 Legged Tower |  |  | 12
3351B | DG Store Balakong | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612466 | [6 empty] | 3m Bipod (RT) |  |  |  | 1
1037C | Taman Suria Warisan | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4(single site MOCN)-L26 SSM |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612467 | [6 empty] | 30m Monopole
4975B | Pdg Pusing | Northern |  | Modernization |  | 2025 Q2 | HW | GTSB | 4.6 TSSR Approved |  | 2025-03-28 | 2025-04-07 |  | 2025-04-11 |  | Under Approval | 2025-04-14 | 2025-05-19 | E//Hazida | 2025-04-23 | SQ202501030229 - GTSB | DU00002612468 | Remarks: Solution TSSR/BOM Changed |  | 2025-06-30 | 2025-06-19 |  | Tower |  | 60M | Add R8862A S9000x1+R8894E M1821x3+R8862A S2601x2+R8854 S2600x2 | 0 | 23
7037C | Pusat Dagangan Putatan | Sabah |  | Remote MOCN |  | 2024 Q1 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612469 | [6 empty] | 3m Boom (RT) |  |  | 13
4409C | Hospital Changkat Melintang | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612470 | [6 empty] | Monopole |  |  |  | 2
1485A | KLIA INTERCHANGE | Central |  | Remote MOCN | Modernization->Remote MOCN | 154 single site MOCN |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612471 | [5 empty] | Tower | 60m 4 Legged Tower | 60M |  |  | 3
1049B | MSC Damansara (Kepong MSC) | Central |  | Remote MOCN |  | 2024 Q2 | SS | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612472 | [6 empty] | 45m Tower |  |  | 123
1977A | Olympia | Central |  | Remote MOCN |  | 2024 Q2 |  | GTSB | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612473 | [6 empty] | 3m Bipod (RT)
4196C | Kg Alor Setanggol Semanggol | Northern |  | Remote MOCN |  | 2026 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612474 | [6 empty] | 30m Monopole
1310C | Jalan Penggawa | Central |  | Remote MOCN | Modernization->Remote MOCN->On Hold->Remote MOCN | 2024 Q4 |  | GCI | 3.4 SOW/Solution On Hold | [6 empty] | To be Submitted | [5 empty] | DU00002612475 | [6 empty] | Land |  |  |  | 1
4527B | Kg Belangkor RCC | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612476 | [6 empty] | Tower |  | Add R8862A S9000x1+R8894E M1821x1 | 0 | 0
3707A | Tmn Cemerlang | Central |  | Remote MOCN |  | 2024 Q1 | SS | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612477 | [5 empty] | Pole | 3m RT (Wall Mounted Pole) | 9 |  | 2
9031C | Taman Uni Garden | Sarawak |  | Modernization |  | 2024 Q2 | SH | Trintel | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦ owner Sacofa reject our TP of adding AAU. | 2023-12-26 | 2024-01-18 |  | 2024-02-19 |  | Closed | 2024-02-20 | 2024-06-10 | E//Hannah | 2024-06-07 | PR raised | DU00002612478 |  |  | 2024-06-21 | 2024-06-14 |  | Monopole | Tower | 31m | Add R8862A S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 | 23
7233A | Kg Novoung | Sabah |  | Remote MOCN |  | 2024 Q1 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612479 | [6 empty] | 45m 3 Legged Tower |  |  |  | 23
2225A | Pulapot water tank Tmn Bunga Raya | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612480 | [6 empty] | 24m Lampole |  |  |  | 23
7162A | Bukit Kuda | Sabah |  | Remote MOCN |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612481 | [6 empty] | 30m Guyed Mast
7249C | Lotong | Sabah |  | Remote MOCN |  | 2027 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612482 | [6 empty] | 45M Tower |  |  |  | 1
3065A | TM Petaling (REL) | Central |  | Remote MOCN |  | 2024 Q3 | MA | Ascentrack | 14.1 Drop (No Survey) |  |  | 2023-10-20 |  |  |  | Closed | [5 empty] | DU00002612483 | [5 empty] | In-Building System | 3m Boom (RT) | 6 |  |  | 2
7370B | Ladang Sabahmas (Celcom) | Sabah |  | Remote MOCN |  | 2024 Q4(single site MOCN)-L2126 SSM |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612484 | [6 empty] | 45m 3 Legged Tower |  | Reuse Existing RRU
4395B | Ldg Soon Lee | Northern |  | Remote MOCN |  | 154 single site MOCN |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612485 | [6 empty] | 45m Tower |  |  |  | 2
3408B | Bandar Teknologi Kajang HUB | Central |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q1 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612486 | [6 empty] | Tower |  | Reuse Existing RRU | 13 | 0
2362A | Subang Bestari 1 | Central |  | Remote MOCN |  | 2024 Q1 | IE | Datasco | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612487 | [6 empty] | 25m Monopole |  |  | 3
2444A | Hiong Kong Supermarket | Central |  | Remote MOCN |  | 2024 Q1 | IE | Datasco | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612488 | [6 empty] | 45m 3 Legged Tower |  |  | 3
2277A | Jalan PJU 10_5 | Central |  | Remote MOCN |  | 2024 Q2 | IE | Datasco | 14.2 Drop (Done Survey) |  | 2023-09-12 |  |  |  |  | To be Submitted | [5 empty] | DU00002612489 | [6 empty] | 24m Lampole |  |  |  | 2
4663B | Kebun Pinang | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2027 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612490 | [6 empty] | 45m 3 Legged Tower |  |  |  | 13
7724B | PPR Taman Sri Murni | Sabah |  | Remote MOCN |  | 2024 Q3 |  | South Pacific | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612491 | [6 empty] | 30m Monopole |  |  | 2
1312A | Jinjang Selatan | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612492 | [6 empty] | 3m Bipod (RT)
4426D | Taman Ria | Northern |  | Modernization |  | 2024 Q2 | BY | GTSB | 4.6 TSSR Approved |  | 2024-01-15 | 2024-01-22 |  | 2024-01-26 |  | Closed | 2024-01-29 | 2024-02-01 | E//Ajay | 2024-01-31 | Celcom Digi_RAN-GTSB-TSS-Northern-202401116-0086 | DU00002612493 |  |  | 2024-04-03 | 2024-04-01 |  | Lampole | 30M Lampole | 30m | Add R8862A S9000 x3+R8894E M1821 x1+R8854 S2600 x1,Dismantle R8862A S2600(A4A) x1 |  | 1
4549D | Masjid Kg Seri Kinta | Northern |  | Remote MOCN |  | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612494 | [6 empty] | 30M Minaret |  |  |  | 2
2245A | Kg Segambut Teng | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612495 | [6 empty] | 24m Pylon
2980B | Galaxy Ampang Mall Indoor | Central |  | Remote MOCN |  | 2024 Q2 | SS | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612496 | [6 empty] | 6m RT (Boom) + IBS |  |  | 1
3292B | Caltex Salak South | Central |  | Remote MOCN |  | 2024 Q3 |  | YPTT | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612497 | [6 empty] | Land site |  |  |  | 1
4532B | Pengkalan Gate (Maxis) | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612498 | [6 empty] | 60m 3 Legged Tower |  |  | 12
2408A | Kg Broga | Central |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q1 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612499 | [6 empty] | 60m 3 Legged Tower |  |  | 2
3089C | Surau Darul Hidayah (REL) | Central |  | Remote MOCN |  | 2024 Q2 | IE | Datasco | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612500 | [6 empty] | 24m Lampole |  |  | 13
7121A | Sandakan Airport | Sabah |  | Remote MOCN |  | 2024 Q3 |  | South Pacific | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612501 | [6 empty] | 25m Monopole |  |  |  | 1
7348C | Kandawayon | Sabah |  | Remote MOCN |  | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612502 | [6 empty] | 60M Tower 3 Legged |  | Reuse Existing RRU | 0 | 1
3237C | Kinrara Low Cost Apt | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 | MA | Ascentrack | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612503 | [6 empty] | 3m Boom (RT) |  |  |  | 123
9711A | Ladang Kosa | Sarawak |  | Remote MOCN |  | 2026 |  | Datasco | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612504 | [6 empty] | Tower |  | Reuse Existing RRU | 0 | 0
4228C | Batu 3 Tapah | Northern |  | Modernization |  | 131 single site mocn | MS | GTSB | 4.6 TSSR Approved |  | 2023-11-21 | 2023-11-27 |  | 2024-08-16 |  | Closed | 2024-08-29 | 2024-08-30 | E//Hazida | 2024-08-30 | Celcom Digi_RAN-GTSB-TSS-Northern-20231122-0067 | DU00002612505 |  |  | 2024-08-31 | 2024-08-23 |  | Monopole | 30m Monopole | 44 | Add R8894E M1821 x2+A9732 M1821 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 1 | 0
2690B | Jln Dinar Subang | Central |  | Remote MOCN |  | 2024 Q1 | IE | Datasco | 14.2 Drop (Done Survey) |  | 2023-10-12 |  |  |  |  | To be Submitted | [5 empty] | DU00002612506 | [6 empty] | 24m Lampole |  |  | 2
2253A | Ampang Avenue 1 | Central |  | Remote MOCN |  | 2024 Q2 | SS | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612507 | [6 empty] | Tower
2817A | Mid Point Shopping Mall | Central |  | Remote MOCN |  | 2024 Q3 | SS | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612508 | [6 empty] | In-building system |  |  | 13
4188D | Jalan Cassia 3A Kg Raja | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4(single site MOCN)-L26 SSM |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612509 | [6 empty] | 3m Boom (RT)
7024C | Ramai-Ramai Shopping Complex | Sabah |  | Remote MOCN |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612510 | [6 empty] | 3m Boom (RT) |  |  |  | 1
7496B | Kg Sri Manis | Sabah |  | Remote MOCN |  | 2024 Q4 |  | Satellite | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612511 | [6 empty] | 76m 3 Legged Tower |  |  |  | 1
2576B | Jalan Kalifah Zakariah | Central |  | Remote MOCN |  | 2024 Q1 | IE | Datasco | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612512 | [6 empty] | 30m Lampole |  |  | 12
1018B | Wisma Dermajaya | Central |  | Remote MOCN |  | 2024 Q2 |  | GTSB | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612513 | [6 empty] | 3m RT (Wall Mounted Pole) |  |  | 12
3256C | Ampang Park 1 (REL) | Central |  | Remote MOCN |  | 2024 Q2 |  | GTSB | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612514 | [6 empty] | 24m Lampole |  |  |  | 12
7123A | Sedco Industry | Sabah |  | Remote MOCN |  | 2024 Q3 |  | South Pacific | 14.1 Drop (No Survey) | [6 empty] | Under Approval | [5 empty] | DU00002612515 | [6 empty] | 3m Boom (RT) |  |  | 1
9450A | Fortune Lane MP | Sarawak |  | Remote MOCN |  | 2024 Q1 |  | AllStar | 14.2 Drop (Done Survey) |  | 2023-10-05 |  |  |  |  | To be Submitted | [5 empty] | DU00002612516 | [6 empty] | 30m Monopole | 30 |  |  | 3
7494B | Kg Koya | Sabah |  | Remote MOCN |  | 2024 Q4(single site MOCN)-L2126 SSM |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612517 | [6 empty] | 76m 3 Legged Tower |  | Reuse Existing RRU
1455A | Wisma HLA | Central |  | Remote MOCN |  | 2024 Q2 |  | GTSB | 14.3 Drop (Done Survey + TSSR) |  | 2023-09-29 |  |  | 2024-01-17 |  | Under Approval | [5 empty] | DU00002612518 | [6 empty] | 6m RT (Boom)
4513A | Leong Kee Seong | Northern |  | Remote MOCN |  | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612519 | [6 empty] | 3m Boom (RT)
4431A | Kemiri Indus | Northern |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | SM | GTSB | 4.6 TSSR Approved |  |  |  |  | 2024-10-28 |  | Rectificating | 2024-10-28 | 2024-10-28 | E//Hazida | 2024-10-28 |  | DU00002612520 |  |  | 2024-11-12 | 2024-11-08 |  |  | 45m Monopole |  | Add A9732 M1821 x3, Dismantle R9264M M1821(AEA)x6 | 123 | 0
3764B | Masjid Al-Najihin | Central |  | Remote MOCN |  | 2024 Q3 |  | GTSB | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612521 | [6 empty] | 30m Monopole |  |  |  | 23
1553C | Mindef | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612522 | [6 empty] | 30m Monopole |  |  |  | 1
4982B | Selarong Panjang | Northern |  | Remote MOCN |  | 2024 Q1 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612523 | [6 empty] | Tower |  |  |  | 1
7589A | Kg. Lot M | Sabah |  | Remote MOCN |  | 2024 Q4(single site MOCN)-L2126 SSM |  | Satellite | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612524 | [6 empty] | Tower |  |  |  | 1
9251B | Kg Pentanak | Sarawak |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612525 | [6 empty] | 30m Rapole |  |  |  | 12
7623B | Bandar Fajar Harapan | Sabah |  | Remote MOCN |  | 2024 Q4(single site MOCN)-L26 SSM |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612526 | [6 empty] | Tower |  |  |  | 1
7288B | Duvanson | Sabah |  | Remote MOCN |  | 2024 Q1 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612527 | [6 empty] | 30m Monopole |  |  | 12
2271A | Persiaran Sg Chua | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612528 | [6 empty] | 20m Lampole
9206A | Min Kiong Hotel Bitangor | Sarawak |  | Remote MOCN | Remote MOCN->Modernization->Remote MOCN | 2026 |  | Trintel | 14.2 Drop (Done Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612529 | [6 empty] | 3m RT (Wall Mounted Pole) |  | Add R9264M M1821 x2 |  | 12
4328A | Tronoh Tower | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2027 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612530 | [6 empty] | 60m 4 Legged Tower
1586C | ILKKM Sg Buloh | Central |  | Remote MOCN |  | 2024 Q1 | IE | Datasco | 14.2 Drop (Done Survey) |  | 2023-11-08 | 2023-11-14 |  |  |  | To be Submitted | [5 empty] | DU00002612531 | [5 empty] | Lampole | Structure | 24
7284C | Sinarut (REL) | Sabah |  | Remote MOCN |  | 2025 Q3 |  | NR services | 14.3 Drop (Done Survey + TSSR) |  | 2023-10-10 |  |  | 2023-10-25 |  | Closed | 2023-11-15 |  | E//Hannah |  |  | DU00002612532 | [6 empty] | 45M Tower |  | Reuse Existing RRU | 0 | 0
2584B | Jalan Merbau | Central |  | Remote MOCN |  | 2024 Q1 | IE | Datasco | 14.2 Drop (Done Survey) |  | 2023-10-18 |  |  |  |  | To be Submitted | 2023-11-02 |  |  |  |  | DU00002612533 | [6 empty] | Structure |  |  | 23
3095C | Taman Usahawan (REL) | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612534 | [5 empty] | Lampole | Tower | 24m |  | 23
3014A | BDR DAMAI PERDANA 2 | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612535 | [6 empty] | 24m Lampole |  |  | 2
7395B | Tanjung Labian | Sabah |  | Remote MOCN |  | 2024 Q4(single site MOCN)-L2126 SSM |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612536 | [6 empty] | Tower |  |  |  | 3
7831A | Sandakan Harbour Square IB | Sabah |  | Remote MOCN |  | 2024 Q3 |  | South Pacific | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612537 | [6 empty] | In-building system
4263B | Surau Taman Cendana(SBC) | Northern |  | Remote MOCN |  | 2024 Q1 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612538 | [6 empty] | 30m Lampole
4934B | Semanggol Spg 4 (REL) | Northern |  | Remote MOCN |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612539 | [6 empty] | 76m Tower |  |  |  | 2
7515A | Kwantas Watertank | Sabah |  | Remote MOCN |  | 2024 Q4(single site MOCN)-L2126 SSM |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612540 | [6 empty] | Watertank Structure |  |  | 3
7186A | Kemabong Opt1 | Sabah |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612541 | [6 empty] | 60m 3 Legged Tower
4985C | Bandar Aman Jaya | Northern |  | Remote MOCN |  | 2024 Q1 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612542 | [6 empty] | 30m Lampole |  |  | 3
1231C | Cempaka | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q2 | SS | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612543 | [6 empty] | 30m Lampole |  |  |  | 23
3855B | Taman Kajang Indah | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612544 | [6 empty] | Billboard |  |  |  | 3
4362A | KTM Kampar | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2026 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612545 | [6 empty] | 4 Legged Tower |  |  | 1
3552A | Sungai Mas (REL) | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612546 | [6 empty] | 3m Boom (RT)
3117B | Taman Segambut Sppk (HSR) | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612547 | [6 empty] | 30m Monopole |  |  | 2
2340A | Taman FRIM | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612548 | [6 empty] | 24m Pylon |  |  |  | 3
1221C | Muhibbah | Central |  | Remote MOCN |  | 2024 Q3 |  | YPTT | 14.2 Drop (Done Survey) | AAU Cannot Install-Change MM to BI¦Space issue cant install AAU | 2023-10-17 |  |  |  |  | To be Submitted | [5 empty] | DU00002612549 | [6 empty] | 3m Boom (RT) |  | Reuse Existing RRU | 0 | 1234
9036A | 40km Kuching-Serian | Sarawak |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q1 |  | Datasco | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612550 | [6 empty] | Tower
7648A | Kg.Kolopis | Sabah |  | Modernization |  | 2024 Q3 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2023-10-22 |  |  | 2023-10-27 |  | Closed | 2024-04-07 | 2024-04-16 | E//Hannah | 2024-04-16 | Celcom Digi_RAN-Seri Pancar-Standard PR TSS-Sabah-20240425 | DU00002612551 |  |  | 2024-04-30 | 2024-04-24 |  |  | Tower |  | Add A9732 M1821 x3,Dismantle R9224E M1821(AAB) x3 | 123 | 0
3618C | Alpha Complex (REL) | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.2 Drop (Done Survey) |  | 2023-11-14 |  |  |  |  | To be Submitted | [5 empty] | DU00002612552 | [6 empty] | 24m Lampole
2728B | Jln Utama | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 | MA | Ascentrack | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | Celcom Digi_RAN-Ascentrack-TSS BAU-20230729-0001_V1 | DU00002612553 | [6 empty] | 3m Boom (RT)
4616C | Masjid Puteri Jaya | Northern |  | Remote MOCN |  | 2024 Q1 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612554 | [6 empty] | 30m Monopole |  |  |  | 2
2579B | Persiaran Delima | Central |  | Remote MOCN |  | 2024 Q1 | IE | Datasco | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612555 | [6 empty] | 30m Lampole |  |  |  | 3
4712B | Ulu Cheh RDC | Northern |  | Remote MOCN |  | 2024 Q2 |  | NA | 14.1 Drop (No Survey) |  |  | 2024-07-22 |  |  |  | To be Submitted | [5 empty] | DU00002612556 | [5 empty] | Tower | 60m 3 Legged Tower | 59m
4317A | Kg Petaling Hulu Bidor | Northern |  | Remote MOCN |  | 154 single site MOCN |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612557 | [6 empty] | 76m 4 Legged Tower |  |  |  | 23
7997B | Cyber City Apartment | Sabah |  | Remote MOCN |  | 2024 Q1 |  |  | 14.2 Drop (Done Survey) |  | 2023-08-19 |  |  |  |  | To be Submitted | [5 empty] | DU00002612558 | [6 empty] | 30m Monopole |  |  |  | 2
4549A | Sg Pari Shoplot | Northern |  | Remote MOCN |  | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612559 | [6 empty] | 3m Boom (RT)
7131A | Bandar Nam Tung | Sabah |  | Remote MOCN |  | 2024 Q3 |  | South Pacific | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612560 | [6 empty] | 3m Boom (RT) |  |  | 12
7431B | Ladang KTS | Sabah |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4 |  | South Pacific | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612561 | [6 empty] | Tower |  | Reuse Existing RRU | 0 | 0
4922A | Pasir Berdampar | Northern |  | Remote MOCN |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612562 | [6 empty] | 3m Bipod (RT) |  |  | 3
3213B | Salak Tinggi (REL) | Central |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q1 |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612563 | [6 empty] | 60m 3 Legged Tower |  | Reuse Existing RRU | 13 | 0
2242A | Jln Sri Petaling 5 | Central |  | Remote MOCN |  | 2024 Q3 |  | YPTT | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612564 | [6 empty] | 30m Monopole
4403A | Pusing | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612565 | [6 empty] | 6m RT (Boom) |  |  |  | 1
3251C | Elite KM35 (REL) | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4(single site MOCN)-L26 SSM |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612566 | [6 empty] | 30m RT (Billboard)
4328B | Changkat Belinggor 2 | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2027 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612567 | [6 empty] | 60m 4 Legged Tower |  |  | 123
4965B | DulangKecil | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612568 | [6 empty] | 60m 4 Legged Tower |  |  | 13
9659B | Kampung Ladang Baru | Sarawak |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q2 |  | Datasco | 14.3 Drop (Done Survey + TSSR) |  | 2023-11-21 | 2023-11-22 |  | 2023-12-05 |  | Under Approval | [5 empty] | DU00002612569 | [5 empty] | Monopole | Rapole | 30
7428A | Taun Gusi Peninting | Sabah |  | Remote MOCN |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612570 | [6 empty] | 30m Monopole |  |  |  | 3
7990B | KK Plaza RT (REL) | Sabah |  | Remote MOCN |  | 2024 Q2 |  |  | 14.2 Drop (Done Survey) |  | 2023-08-24 |  |  |  |  | To be Submitted | [5 empty] | DU00002612571 | [6 empty] | Tower |  |  |  | 1
4187C | Perak River Sand | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612572 | [6 empty] | Tower |  |  |  | 1
1263C | TAMAN SERI HANECO (REL) | Central |  | Remote MOCN | Modernization->Remote MOCN | 154 single site MOCN |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612573 | [6 empty] | 22m Minaret |  |  |  | 3
3205A | SS3 TM SG WAY | Central |  | Remote MOCN |  | 2024 Q1 | MA | Ascentrack | 14.1 Drop (No Survey) | [6 empty] | Under Approval | [5 empty] | DU00002612574 | [6 empty] | 3m Bipod (RT) |  |  | 2
7384A | Taman Sri Panglima (REL) | Sabah |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612575 | [6 empty] | 3m RT (Minimast) |  |  |  | 3
2654B | Jln Dagang Mas | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612576 | [5 empty] | H-bracket pole | 3m Boom (RT) | 5 |  | 2
1087B | Jinjang Utara 2 | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612577 | [6 empty] | 3m Boom (RT)
7442B | Seguntur | Sabah |  | Remote MOCN |  | 2024 Q4 |  | South Pacific | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612578 | [6 empty] | Tower |  |  | 12
1410B | PUAS Bandar Puchong(Maxis) | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 | MA | Ascentrack | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612579 | [5 empty] | Tower | 45m 3 Legged Tower | 60
7143B | Jln Kg Tg Aru | Sabah |  | Remote MOCN |  | 2024 Q2 |  |  | 14.2 Drop (Done Survey) |  | 2023-08-31 |  |  |  |  | To be Submitted | [5 empty] | DU00002612580 | [6 empty] | 30m Lampole |  |  | 13
4400A | Kuala Gula RDD | Northern |  | Remote MOCN |  | 2025 Q1 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612581 | [6 empty] | 60m 3 Legged Tower |  |  | 2
7224A | Sinar Baru | Sabah |  | Remote MOCN |  | 2024 Q2 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-06 |  |  |  |  | To be Submitted | [5 empty] | DU00002612582 | [6 empty] | 3m RT (Minimast) |  |  |  | 3
4420A | NS KM356 NB (Maxis) | Northern |  | Remote MOCN |  | 2025 Q1 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612583 | [6 empty] | 76m Tower
2562A | MV Boulevard Micro | Central |  | Remote MOCN |  | 2024 Q2 |  | GTSB | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612584 | [6 empty] | 3m Bipod (RT) |  |  |  | 1
3376B | Jalan Abdul Rahman Idris (REL) | Central |  | Remote MOCN |  | 2024 Q2 |  | GTSB | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612585 | [6 empty] | 3m Bipod (RT) |  |  |  | 13
7296B | TM Ranau | Sabah |  | Remote MOCN |  | 2025 Q3 |  | South Pacific | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612586 | [6 empty] | 30m Monopole |  | Reuse Existing RRU | 24 | 0
7163B | Kg Sukang 2 | Sabah |  | Remote MOCN |  | 2024 Q2 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-10 |  |  |  |  | To be Submitted | [5 empty] | DU00002612587 | [6 empty] | Tower |  |  |  | 13
7604A | Mount Silam | Sabah |  | Remote MOCN |  | 2024 Q3(single site MOCN) |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612588 | [6 empty] | Tower |  |  |  | 1
4576A | Bukit Pagar Tapah | Northern |  | Decomm | Remote MOCN->On Hold->Decomm | 2025 Q1 | MNO | GCI | 4.6 TSSR Approved |  | 2025-07-10 |  | 2025-07-16 |  | 2025-07-17 | To be Submitted | 2025-07-18 | 2026-03-13 |  | 2025-09-23 | SQ202508270446 | DU00002612589 |  |  |  |  | 2025-09-26 |  | 60m 3 Legged Tower |  | Add R9264M M1821x1, Dismantle A9732 M1821x1 | 0 | 2
4413D | SP KTM | Northern |  | Remote MOCN |  | 2024 Q1 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612590 | [6 empty] | 30M Pole |  |  | 123
4597C | Surau Rpt Desa Rishah | Northern |  | Remote MOCN |  | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | Under Approval | [5 empty] | DU00002612591 | [6 empty] | Tower |  |  |  | 12
1222B | Cova Square Damansara | Central |  | Remote MOCN |  | 2024 Q2 | IE | Datasco | 14.2 Drop (Done Survey) |  | 2023-10-20 |  |  |  |  | To be Submitted | [5 empty] | DU00002612592 | [6 empty] | 38m Tower |  |  | 1
3726A | Jalan Seri Sentosa 12 | Central |  | Remote MOCN |  | 2024 Q3 |  | YPTT | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612593 | [6 empty] | 30m Minaret |  |  | 234
4228D | Taman Resak | Northern |  | Remote MOCN |  | 2024 Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612594 | [6 empty] | 45m Tower
4936A | Bandar Perdana | Northern |  | Remote MOCN |  | 2024 Q1 |  | NA | 14.1 Drop (No Survey) |  |  | 2023-10-09 |  |  |  | To be Submitted | [5 empty] | DU00002612595 | [5 empty] | Tower | 50m 3 Legged Tower | 48 |  | 1
1720A | Sri Desa | Central |  | Remote MOCN |  | 2024 Q3 |  | YPTT | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612596 | [6 empty] | 3m Boom (RT)
2729B | Sports Planet Puchong | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 | MA | Ascentrack | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | Celcom Digi_RAN-Ascentrack-TSS BAU-20230729-0001_V1 | DU00002612597 | [6 empty] | 30m Monopole |  |  |  | 13
9160A | Jakar Sarikei | Sarawak |  | Remote MOCN |  | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612598 | [6 empty] | Tower |  |  |  | 1
2257A | Kelumpuk Sunding Malam | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.1 Drop (No Survey) | AAU Cannot Install-change MM to BI¦owner reject AAU can not install | [5 empty] | To be Submitted | [5 empty] | DU00002612599 | BAU_S2_change MM to BI_owner reject_MAXIS | [5 empty] | 45m 3 Legged Tower |  |  | 12 | 0
2732B | Tmn Cheras Perdana | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4 |  | GCI | 14.1 Drop (No Survey) | AAU Cannot Install-change MM to BI¦NOK,structure issue,can not support 5 Antenna;Suggest to change to bi-sector | [5 empty] | To be Submitted | [5 empty] | DU00002612600 | [6 empty] | 3m Bipod (RT) |  |  |  | 12
3714A | Hospital KL Macro | Central |  | Remote MOCN |  | 2024 Q2 |  | GTSB | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612601 | [6 empty] | 3m Tripod (RT) |  |  |  | 1
1993A | Kompleks Desa | Central |  | Remote MOCN |  | 2024 Q1 | SS | Futong | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612602 | [6 empty] | 3m Bipod (RT) |  |  |  | 1
1674C | Taman Seri Sentosa | Central |  | Remote MOCN |  | 2024 Q3 |  | YPTT | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612603 | [6 empty] | Lampole
4769A | Kuala Kangkong | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q3 | SM |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612604 | [6 empty] | Tower |  |  |  | 14
9006C | Kampung Haji Baki 2 | Sarawak |  | Remote MOCN |  | 2024 Q1 |  | AllStar | 14.2 Drop (Done Survey) |  | 2023-10-05 |  |  |  |  | To be Submitted | [5 empty] | DU00002612605 | [5 empty] | Monopole | Tower | 30M |  |  | 13
4337D | Lapangan Siber | Northern |  | Remote MOCN |  | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612606 | [6 empty] | 30m Monopole |  |  |  | 3
7947A | Taman Beringin | Sabah |  | Remote MOCN |  | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612607 | [6 empty] | Tower |  | Reuse Existing RRU | 0 | 3
3580B | Pandan Indah 3 | Central |  | Remote MOCN |  | 2024 Q3 | SS | Futong | 14.1 Drop (No Survey) | AAU Cannot Install-Change MM to BI¦AAU can not install | [5 empty] | To be Submitted | [5 empty] | DU00002612608 | BAU_S3_Change MM to BI_Space constraint_DiGi | [5 empty] | 6m Unipole RT |  |  |  | 123
3550B | Sungai Balak Toll | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612609 | [6 empty] | 3m Bipod (RT) |  |  | 13
9906A | UiTM Fakulti Kejuruteraan | Sarawak |  | Remote MOCN |  | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612610 | [6 empty] | 30m Rapole |  |  |  | 123
4585A | Ayer Kuning Taiping-100Q4 | Northern |  | Remote MOCN |  | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612611 | [6 empty] | 60m 4 Legged Tower |  |  | 12
9472A | Sin San Du | Sarawak |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612612 | [6 empty] | 45m 3 Legged Tower |  |  |  | 13
2234A | Taman Semboyan | Central |  | Remote MOCN |  | 2024 Q3 |  | YPTT | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612613 | [6 empty] | 30m Monopole |  |  | 123
1266B | CherasJaya Industrial | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612614 | [6 empty] | 6m RT (Boom) |  |  | 1
4306A | Changkat Tin RCC | Northern |  | Modernization |  | 131 single site mocn | SHA | CCSMY | 4.6 TSSR Approved |  | 2024-08-29 | 2024-09-02 |  | 2024-09-06 |  | Under Approval | 2024-09-11 | 2024-09-23 | E//Ajay | 2024-09-23 | 0809CD-Northern-CCSMY-BOQ Template(new contract) | DU00002612615 |  |  | 2024-10-01 | 2024-09-19 |  | Tower |  | 53m | Add R8852E S9000 x2+R9224E M1821 x3+R8854 S2600 x2,Dismantle R8862A S2600(A4A) x1 |  | 23
7541A | Hotel California Labuan | Sabah |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4(single site MOCN)-L26 SSM |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612616 | [6 empty] | 30m Monopole |  |  |  | 123
4954C | Kampung Tepi Laut | Northern |  | Modernization | Modernization->Remote MOCN | 2024 Q4(single site MOCN)-L26 SSM | SM | CCSMY | 4.6 TSSR Approved |  | 2024-12-26 |  |  | 2024-11-01 |  | Rectificating | 2024-11-04 | 2024-11-27 | E//Hazida | 2024-11-05 | SQ202506100502 | DU00002612617 |  |  | 2024-11-11 | 2024-11-08 |  |  | 24m Lampole |  | Add R8862A S9000x1+A9732 M1821x2, Dismantle R9264H M901821(AIA)x1+R9264M M1821(AEA)x2 | 12 | 3
4316A | Ladang Bikam(ZED) | Northern |  | Remote MOCN |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612618 | [6 empty] | 60m 4 Legged Tower
4164D | Gereja Methodist Tamil Teluk Intan | Northern |  | Remote MOCN |  | 2025 Q1 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612619 | [6 empty] | 24m Lampole |  |  |  | 2
2656B | Jln Meranti Permai | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612620 | [6 empty] | 3m Bipod (RT)
7715B | Bundusan Villa | Sabah |  | Remote MOCN |  | 2024 Q1 |  |  | 14.2 Drop (Done Survey) |  | 2023-08-31 |  |  |  |  | To be Submitted | [5 empty] | DU00002612621 | [6 empty] | 24m Monopole |  |  |  | 12
7792B | Taman Harapan | Sabah |  | Remote MOCN |  | 2024 Q1 |  |  | 14.2 Drop (Done Survey) |  | 2023-08-25 |  |  |  |  | To be Submitted | [5 empty] | DU00002612622 | [6 empty] | landside |  |  |  | 23
4979C | Tanjung Piandang Town | Northern |  | Remote MOCN |  | 2026 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612623 | [6 empty] | 30M RDS
7272B | Taman Starland | Sabah |  | Remote MOCN |  | 2024 Q1 |  |  | 14.2 Drop (Done Survey) |  | 2023-08-19 |  |  |  |  | To be Submitted | [5 empty] | DU00002612624 | [6 empty] | 30m Monopole
7337B | Kg Tamau | Sabah |  | Remote MOCN |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [12 empty] | DU00002612625 | [6 empty] | 45m 3 Legged Tower |  |  |  | 2
4473B | Chikus | Northern |  | Remote MOCN |  | 154 single site MOCN |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612626 | [6 empty] | 60m 3 Legged Tower |  |  | 13
3047A | Surian Palm Billboard (REL) | Central |  | Remote MOCN |  | 2024 Q2 | IE | Datasco | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612627 | [6 empty] | 30m Rapole
4366A | Bandar Baru Kampar_2 | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2027 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612628 | [6 empty] | 6m RT (Boom) |  |  |  | 12
7729B | Pemodalan | Sabah |  | Remote MOCN |  | 2024 Q4(single site MOCN)-L26 SSM |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612629 | [6 empty] | Tower
2114B | Pudu | Central |  | Remote MOCN |  | 2024 Q2 |  | GTSB | 14.2 Drop (Done Survey) | AAU Cannot Install-change MM to BI¦NOK,structure issue,can not support 5 Antenna;Suggest to change to bi-sector,or cancel S1 AAU,only install S2 AAU. | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612630 | BAU_S2_change MM to BI_Space constraint_Digi OB | [5 empty] | 3m Boom (RT) |  |  |  | 12
4315A | Tanah Mas Bidor | Northern |  | Remote MOCN |  | 2025 Q1 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612631 | [6 empty] | 60m 3 Legged Tower |  |  | 12
4443A | Shoplot Chenderiang (NS Hway) | Northern |  | Remote MOCN |  | 2026 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612632 | [6 empty] | 6m RT (Boom)
4631B | Ldg Teh Ah Yau | Northern |  | Remote MOCN |  | 2024 Q1 |  | NA | 14.1 Drop (No Survey) |  |  | 2023-11-08 |  |  |  | To be Submitted | [5 empty] | DU00002612633 | [5 empty] | Tower | Tower | 70
1098C | MSS 36 Motorsport | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612634 | [6 empty] | 18m Lampole |  |  | 2
3357C | Sri Damansara Billboard (REL) | Central |  | Remote MOCN |  | 2024 Q2 | IE | Datasco | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612635 | [6 empty] | Billboard |  |  | 12
4657A | Spg 4 Kangkong | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2027 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612636 | [6 empty] | 45m Monopole |  |  |  | 23
4526B | Tmn Gading | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2026 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612637 | [6 empty] | Tower
3753B | South City Plaza (Outdoor) | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 | MA | Ascentrack | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | Celcom Digi_RAN-Ascentrack-TSS BAU-20230729-0001_V1 | DU00002612638 | [6 empty] | 3m Bipod (RT)
3196B | Cheras Central Outdoor (REL) | Central |  | Remote MOCN |  | 2024 Q3 |  | YPTT | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612639 | [6 empty] | 3m Boom (RT) |  |  | 1
2651B | Kg Sg. Rasau | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  | Magicell | 14.2 Drop (Done Survey) |  | 2023-11-14 |  |  |  |  | To be Submitted | [5 empty] | DU00002612640 | [6 empty] | 24m Lampole |  |  | 1
1300B | Jln Sentul Raya | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612641 | [6 empty] | 3m Bipod (RT) |  |  | 1
4759A | Permatang Buluh KK(DD) | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2026 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612642 | [6 empty] | 30m Monopole |  |  |  | 23
4544A | Kwang Tung Assoc | Northern |  | Remote MOCN |  | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612643 | [6 empty] | 76m Tower |  |  |  | 1
1469A | Tmn Sejahtera | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612644 | [6 empty] | 3m Boom (RT)
4636B | Carok Kelian | Northern |  | Remote MOCN |  | 131 single site mocn |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612645 | [6 empty] | Tower |  |  | 13
3647C | TTDI Jln Buharuddin Helmi 3 | Central |  | Remote MOCN |  | 2024 Q2 |  | GTSB | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612646 | [6 empty] | 18m Lampole |  |  | 0 | 2
4755A | Bkt Rawa | Northern |  | Remote MOCN |  | 2024 Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612647 | [6 empty] | Tower |  |  | 12
4988A | Kupang | Northern |  | Remote MOCN |  | 2025 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612648 | [6 empty] | 60m 3 Legged Tower |  |  | 3
4455B | Sg Limau RCC | Northern |  | Remote MOCN |  | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612649 | [6 empty] | 60m 3 Legged Tower
4580B | Jenderata Perak | Northern |  | Remote MOCN |  | 2025 Q1 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612650 | [6 empty] | 45m 4 Legged Tower |  |  | 13
1544B | Batu 6 1_2 Jln Kepong | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612651 | [6 empty] | 6m RT (Boom)
9139B | ST3 Mall Outdoor | Sarawak |  | Remote MOCN |  | 2024 Q1 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-25 |  |  |  |  | To be Submitted |  |  |  |  | N/A-BAU | DU00002612652 | [6 empty] | 3m RT (Wall Mounted Pole)
2338A | Jln 4_16C Perumahan awam Jinjang | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612653 | [6 empty] | 24m Lampole |  |  |  | 3
1598C | Mindef Jln Semarak | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612654 | [6 empty] | 30M Monopole |  |  | 3
2106A | Springhills Bkt Serdang | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 | MA | Ascentrack | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612655 | [6 empty] | 3m Bipod (RT) |  |  |  | 1
7071C | Masjid Kudat | Sabah |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612656 | [6 empty] | 30m Lampole |  | Reuse Existing RRU | 13 | 0
7754B | Kg Entilibon | Sabah |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4 |  | South Pacific | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612657 | [6 empty] | Tower |  |  |  | 1
9057C | Kampong Sg Alo 2 | Sarawak |  | Modernization |  | 2025 Q2 | AI | Trintel | 4.6 TSSR Approved |  | 2025-03-17 | 2025-03-27 |  | 2025-04-02 |  | Closed | 2025-04-24 | 2025-10-10 | E//Hannah | 2025-10-01 | SQ202503030116-Trintel | DU00002612658 |  |  | 2025-06-05 | 2025-05-29 |  | Tower |  | 30 | Add R8894E M1821x1 | 0 | 3
4435D | Buntar Indah | Northern |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | SM | GTSB | 4.6 TSSR Approved |  | 2024-12-17 | 2024-12-23 |  | 2024-12-27 |  | Rectificating | 2024-12-30 | 2024-12-31 | E//Hazida | 2024-12-31 | SQ202501070077 - GTSB | DU00002612659 |  |  | 2025-01-07 | 2025-01-04 |  | Minaret | 30M Minaret | 30m | Add R8862A S9000x3 | 0 | 0
4779B | Guar Nangka Chuping | Northern |  | Remote MOCN |  | 2025 Q3 |  | NA | 14.1 Drop (No Survey) |  |  | 2023-11-10 |  |  |  | To be Submitted | [5 empty] | DU00002612660 | [5 empty] | Tower | Tower | 60 |  |  | 1
1240C | Jalan Sulaiman Kajang | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612661 | [6 empty] | Land |  |  |  | 3
3667C | Caltex Taman Kosas SL | Central |  | Remote MOCN |  | 2024 Q2 | SS | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612662 | [6 empty] | 3m Boom (RT) |  |  |  | 14
7389A | Kg Pelakat | Sabah |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612663 | [6 empty] | 45m 3 Legged Tower |  |  |  | 12
2113B | Bkt Bintang | Central |  | Remote MOCN |  | 2024 Q2 |  | GTSB | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612664 | [6 empty] | 3m Bipod (RT) |  |  | 123
7390B | POIC Lahad Datu | Sabah |  | Remote MOCN |  | 2024 Q4(single site MOCN)-L2126 SSM |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612665 | [6 empty] | 24m Lampole |  |  |  | 13
7128A | Elopura Plaza | Sabah |  | Remote MOCN |  | 2024 Q3 |  | South Pacific | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612666 | [6 empty] | 6m RT (Boom) |  |  |  | 2
1255A | Union Height | Central |  | Remote MOCN |  | 2024 Q3 |  | YPTT | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612667 | [6 empty] | 3m Boom (RT) |  |  | 1
3434C | Pangsapuri Seri Intan (REL) | Central |  | Remote MOCN |  | 2024 Q4 | SS | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612668 | [6 empty] | 3m Boom (RT) |  |  | 3
1200C | PWTC | Central |  | Remote MOCN |  | 2024 Q2 |  | GTSB | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612669 | [6 empty] | 3m Boom (RT)
9699A | E-Mart Batu Kawa | Sarawak |  | Remote MOCN |  | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612670 | [6 empty] | 30m Rapole |  |  |  | 12
4232C | Tmn Timah | Northern |  | Remote MOCN |  | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | AAU Cannot Install-Change MM to BI¦AAU can not install | [5 empty] | To be Submitted |  |  |  |  | N/A - Remote MOCN | DU00002612671 | BAU_S1_Change MM to BI_Space constraint_PERAK INTEGRATED NETWORK | [5 empty] | 30m Monopole |  |  |  | 1
7077A | KG Ganggarak | Sabah |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q1 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612672 | [6 empty] | 60m 3 Legged Tower |  |  | 23
4387D | Taman Seri Kurau | Northern |  | Remote MOCN |  | 2026 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612673 | [6 empty] | 30M Pylon |  |  |  | 2
9230B | Hospital Mukah Sacofa | Sarawak |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612674 | [6 empty] | 30m Rapole |  |  |  | 23
2049A | JLNSANPENG | Central |  | Remote MOCN |  | 2024 Q2 |  | GTSB | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612675 | [6 empty] | 3m Bipod (RT) |  |  |  | 3
7527B | Kg Sebait | Sabah |  | Remote MOCN |  | 2024 Q4 |  | South Pacific | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612676 | [6 empty] | 30m Monopole
4746B | Labu Kubong | Northern |  | Modernization |  | 2025 Q1 | SM | CCSMY | 4.6 TSSR Approved |  | 2025-01-22 | 2025-01-27 |  | 2025-02-05 |  | Rectificating | 2025-02-12 | 2025-02-24 | E//Hazida | 2025-02-21 | SQ202501030037 - CCSMY | DU00002612677 | Remarks: Solution TSSR/BOM Changed |  | 2025-04-12 | 2025-02-18 |  | Tower | Tower | 60M | Add R8852E S9000x3+R8894E M1821x5+R8854 S2600x2, Dismantle R8882-GUL1812x3+R8862A S2100(A6A)x3+R8862A S2600(A4A)x2 | 0 | 12
1036C | Garden Residence | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612678 | [6 empty] | 45M Monopole
4435C | Gopeng 1 (REL) | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2027 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612679 | [6 empty] | 30m Minaret
4434A | Tmn Orkid Shoplot | Northern |  | Remote MOCN |  | 2026 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612680 | [6 empty] | 2m RT (Boom)
3098A | HOSPITAL AMPANG IB | Central |  | Modernization | Remote MOCN->Modernization | 2024 Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2024-07-02 | 2024-07-11 |  | 2024-07-15 |  | Closed | 2024-07-16 | 2024-07-16 | E//Nazrul | 2024-07-16 | 0919CD-Central-GTSB-BOQ Template (old contract) | DU00002612681 |  |  | 2024-08-12 | 2024-08-09 |  | Portables BTS | In-building system |  | Add R8862A S2601 x4,Dismantle R8882 S2600 x4,Reconnect R8892N/R8894E
4479A | Wisma Tan Chiap Sieah | Northern |  | Modernization |  | 2025 Q1 | SM | GTSB | 4.6 TSSR Approved |  | 2025-01-14 | 2025-01-23 |  | 2025-02-07 |  | Rectificating | 2025-02-12 | 2025-02-24 | E//Hazida | 2025-02-21 | SQ202501030229 - GTSB | DU00002612682 |  |  | 2025-02-28 | 2025-02-13 |  | In-Building System | 3m RT (Minimast) | 10M | Add R8852E S9000 x3+R9264M M1821 x3, Dismantle R9224E M1821(AAB)x3 | 0 | 0
7187A | Sapong | Sabah |  | Remote MOCN | Modernization->Remote MOCN | 131 single site mocn |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612683 | [5 empty] | Tower | Tower | 61 |  |  | 3
9315B | Taman Janting | Sarawak |  | Remote MOCN |  | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612684 | [6 empty] | Rapole |  |  |  | 3
4167D | Grand Court Hotel | Northern |  | Modernization |  | 2024 Additional | SHA | GCI | 4.6 TSSR Approved |  | 2024-12-06 | 2024-12-09 |  | 2024-12-11 |  | Under Approval | 2024-12-12 | 2024-12-13 | E//Hazida | 2024-12-13 | SQ202412090146 - GCI | DU00002612685 |  |  | 2024-12-30 | 2024-12-30 |  | In-Building System | 3m Boom (RT) | 6 | Add R8852E S9000 x3+R8894E M1821x3,Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3 | 0 | 0
3972B | Sungai Pelek Town | Central |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q1 |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612686 | [6 empty] | 3m Bipod (RT) |  | Reuse Existing RRU | 0 | 0
2213A | Jln Union | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612687 | [6 empty] | 3m Bipod (RT)
9211A | Sarikei Town(Maxis) | Sarawak |  | Modernization | Modernization | 2024 Q4(single site MOCN)-L26 SSM | SHA | Trintel | 4.6 TSSR Approved |  |  | 2024-10-24 |  | 2024-10-28 |  | Under Approval | 2024-10-29 | 2024-11-11 | E//Syahriani | 2024-11-07 |  | DU00002612688 | Remarks: Solution TSSR/BOM Changed |  | 2025-03-21 | 2025-03-17 |  | Tower | Tower | 60 | Add R8862A S9000x2+A9732 M1821x2, Dismantle R9264H M901821(AIA)x2 | 23 | 0
3985B | Permai Ria Condominium | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612689 | [6 empty] | 3m Boom (RT)
3577B | Bdr Baru Salak Tinggi | Central |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q1 |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612690 | [6 empty] | 3m Bipod (RT) |  | Reuse Existing RRU | 12 | 0
1150B | Pekan Salak (KJS) | Central |  | Modernization | Modernization->Remote MOCN->On Hold->Modernization | 2025 Q1 | AI | GTSB | 4.6 TSSR Approved |  | 2025-03-07 | 2025-03-20 |  | 2025-03-25 |  | Closed | 2025-03-26 | 2025-04-15 | E//Razif | 2025-03-27 | SQ202505080070 | DU00002612691 | Remarks: Solution TSSR/BOM Changed |  | 2025-04-29 | 2025-04-29 |  | Pole | 20m Lampole | 20M | Add R9264H M901821x1+R8862A S2601x1 | 0 | 1
7463B | Kilang Sawit Fortuna | Sabah |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612692 | [6 empty] | 60m 4 Legged Tower
4352B | Bandar Baru Selatan | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612693 | [6 empty] | 3m RT (Wall Mounted Pole) |  | Reuse Existing RRU | 0 | 0
2025A | Taman Segar | Central |  | Remote MOCN |  | 2024 Q3 |  | YPTT | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612694 | [6 empty] | 3m Boom (RT) |  |  |  | 3
1473A | Keramat | Central |  | Remote MOCN |  | 2024 Q1 | SS | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612695 | [5 empty] | Minimast | 3m RT (Minimast) | 11 |  |  | 123
2928A | Bandar Utama | Central |  | Remote MOCN |  | 2024 Q2 | IE | Datasco | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612696 | [6 empty] | 3m Bipod (RT) |  |  | 12
1770A | Tmn Rinching | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4(single site MOCN)-L26 SSM |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612697 | [6 empty] | 3m RT (Minimast) |  |  | 3
4940A | Semeling | Northern |  | Remote MOCN |  | 2024 Q1 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612698 | [6 empty] | 48m 3 Legged Tower |  |  |  | 3
7961A | Bukit Garam | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-01-23 | 2025-01-27 |  | 2025-02-03 |  | Under Approval | 2025-02-06 | 2025-03-09 | E//Yanie | 2025-02-20 | SQ202501020392 - Futong | DU00002612699 |  |  | 2025-03-08 | 2025-02-15 |  | Tower | Tower | 76m | Add R8894E M1821 x2 | 0 | 12
1585B | Jusco Metro Prima | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612700 | [6 empty] | 3m Boom (RT) |  |  |  | 23
4537A | IIOM RDD | Northern |  | Remote MOCN |  | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612701 | [6 empty] | 6m RT (Boom) |  |  | 13
4331A | Bagan Serai | Northern |  | Remote MOCN |  | 2026 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612702 | [6 empty] | 45m 4 Legged Tower
3288B | Taman Maju Jaya | Central |  | Remote MOCN |  | 2024 Q2 | SS | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612703 | [6 empty] | 45m 3 Legged Tower |  |  |  | 1
3602C | Surau Taman Kajang Ria (REL) | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4 |  | GCI | 14.1 Drop (No Survey) | AAU Cannot Install-S2 reamin MM，S3 chagne to BI¦NOK,existing S2 and S3 are bi-sector(8 port),8 port antenna width is 398mm,AAU width is 670mm,S2 can install AAU,S3 can install AAU but only can use 900M(Azimuth 340) antenna location,existing S3-bi-sector antenna location can not insall AAU(zimuth 230)due to space constraint,Need RF to confirm keep existing bi-sector or add AAU. | [5 empty] | To be Submitted | [5 empty] | DU00002612704 | [6 empty] | 30m Monopole |  |  | 2 | 3
2415A | Cheras Indah | Central |  | Remote MOCN |  | 2024 Q3 | SS | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612705 | [6 empty] | 6m RT (Boom) |  |  |  | 123
4606B | Arau (Trunk) | Northern |  | Remote MOCN |  | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612706 | [6 empty] | 75m 4 Legged Tower |  |  | 12
1022C | Kg Segambut Bahagia (REL) | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612707 | [6 empty] | 18m Lampole |  |  |  | 23
2220A | Taman Rowther | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612708 | [6 empty] | 24m Lampole |  |  |  | 23
4945B | Tebengau | Northern |  | Remote MOCN | Modernization->Remote MOCN | 154 single site MOCN |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612709 | [6 empty] | Tower
1265A | Mahamewah | Central |  | Remote MOCN |  | 2024 Q2 |  | GTSB | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612710 | [6 empty] | 3m Bipod (RT) |  |  |  | 2
3698A | Surau Mukhilsin Pelanig Semenyih | Central |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q1 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612711 | [6 empty] | 24m Lampole |  |  |  | 1
4682A | Berjaya Cycle Kulim | Northern |  | Remote MOCN |  | 2024 Q1 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612712 | [6 empty] | 45m 3 Legged Tower |  |  | 4
3680B | LDP (Billboard) | Central |  | Remote MOCN |  | 2024 Q2 | IE | Datasco | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612713 | [6 empty] | Billboard
7052C | Kg. Tebanak hilir | Sabah |  | Remote MOCN |  | 2024 Q4(single site MOCN)-L26 SSM |  |  | 14.2 Drop (Done Survey) |  | 2023-11-10 |  |  |  |  | To be Submitted | [5 empty] | DU00002612714 | [6 empty] | 30M Rapole |  |  | 23
2364A | Jalan Resak | Central |  | Remote MOCN |  | 2024 Q1 | IE | Datasco | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612715 | [6 empty] | Structure |  |  |  | 1
1341B | Jln Bandar Puchong Jaya | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 | MA | Ascentrack | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | Celcom Digi_RAN-Ascentrack-TSS BAU-20230729-0001_V1 | DU00002612716 | [6 empty] | 3m Bipod (RT) |  |  | 1
7885A | Pekan Baru Kinabatangan | Sabah |  | Remote MOCN |  | 2024 Q4 |  | Satellite | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612717 | [6 empty] | 30m Monopole |  |  | 12
3202A | Jaya One | Central |  | Remote MOCN |  | 2024 Q3 | IE | Datasco | 14.2 Drop (Done Survey) |  | 2023-10-09 |  |  |  |  | To be Submitted | [5 empty] | DU00002612718 | [6 empty] | 3m Bipod (RT) |  |  |  | 23
4675B | Tokai(Mxs) | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2026 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612719 | [6 empty] | 60m 3 Legged Tower |  |  |  | 3
1308B | Bukit Rahman Putra Sg Buloh | Central |  | Remote MOCN |  | 2024 Q1 | IE | Datasco | 14.2 Drop (Done Survey) |  | 2023-10-09 |  |  |  |  | To be Submitted | [5 empty] | DU00002612720 | [6 empty] | 6m RT (Minimast) |  |  | 12
7551B | PPRT SG. Manila | Sabah |  | Remote MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612721 | [6 empty] | 30m Monopole |  |  | 12
9214B | Desa Ilmu 3G Den | Sarawak |  | Remote MOCN |  | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612722 | [6 empty] | 3m Bipod (RT) |  |  |  | 12
7505A | Membatu | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2024 Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-06 | 2023-11-17 |  | 2025-02-13 |  | Under Approval | 2025-02-27 | 2025-03-24 | E//Hannah | 2025-03-13 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231130 | DU00002612723 |  |  | 2025-03-24 | 2025-03-18 |  | Tower | Tower | 76m | Add A9732 M1821 x2,Dismantle R8894E M1821(A8A) x2 | 12 | 0
1475A | BSC Sri Kembangan | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 | MA | Ascentrack | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | E//Sumitra |  |  | DU00002612724 | [6 empty] | Tower |  |  |  | 2
7946A | Tandek | Sabah |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4(single site MOCN)-L26 SSM | MS | Seri Pancar | 4.3 Pending TSSR Resubmission - ZTE |  | 2024-10-21 | 2024-10-24 |  | 2024-10-24 |  | Under Approval | 2024-10-30 |  | E//Syahriani |  | Celcom Digi_RAN Seri Pancar-Standard PR TSS-Sabah-20241028 | DU00002612725 | [5 empty] | Tower | Tower | 76 | Reuse exisiting RRU | 0 | 123
1725A | Menjalara | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612726 | [6 empty] | 3m Boom (RT) |  |  |  | 2
3693B | Jalan SS8_2 BB | Central |  | Remote MOCN |  | 2024 Q1 | MA | Ascentrack | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | Celcom Digi_RAN-Ascentrack-TSS BAU-20230729-0001_V1 | DU00002612727 | [6 empty] | Rooftop 3m boom |  |  | 3
7007C | Pulau Gaya | Sabah |  | Remote MOCN |  | 2024 Q2 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-09 |  |  |  |  | To be Submitted | [5 empty] | DU00002612728 | [6 empty] | 45M Slim Tower |  |  |  | 2
2381A | SDMC Desa ParkCity RT | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612729 | [6 empty] | 4m RT (Boom) |  |  | 12
2422A | Tmn Desa Karunmas | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612730 | [6 empty] | 3m Boom (RT) |  |  |  | 1
1328A | Sinny Fashion | Central |  | Remote MOCN |  | 2024 Q2 |  | GTSB | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612731 | [6 empty] | 6m RT (Boom) |  |  | 23
2370A | Jalan Cempaka SD 12_1 | Central |  | Remote MOCN |  | 2024 Q2 | IE | Datasco | 14.2 Drop (Done Survey) |  | 2023-10-14 |  |  |  |  | To be Submitted | [5 empty] | DU00002612732 | [6 empty] | 30m Lampole |  |  | 13
4350C | Jalan Tepi Sungai (REL) | Northern |  | Remote MOCN |  | 2026 |  | NA | 14.1 Drop (No Survey) | [6 empty] | Closed | [5 empty] | DU00002612733 | [6 empty] | 60M 3 Legged Tower |  |  | 1
7238B | Kg Dumpil | Sabah |  | Remote MOCN |  | 2024 Q1 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612734 | [6 empty] | 30M Monopole |  |  | 12
4329B | Tanjung Tualang | Northern |  | Remote MOCN | Modernization->Remote MOCN | 154 single site MOCN |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612735 | [6 empty] | 60m 4 Legged Tower |  |  | 23
1259A | Miharja | Central |  | Remote MOCN |  | 2024 Q3 |  | GTSB | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612736 | [6 empty] | 3m Boom (RT) |  |  | 23
9313A | Tapah (SACOFA) | Sarawak |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q1 |  | Datasco | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612737 | [6 empty] | Tower |  |  |  | 23
1752B | Fadason Park Jinjang3 | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612738 | [6 empty] | 3m Boom (RT) |  |  |  | 1
4335D | Jalan Bakar Arang | Northern |  | Remote MOCN |  | 2024 Q1 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612739 | [6 empty] | 22m Minaret
4043D | Kampung Ikan (REL) | Northern |  | Modernization | Modernization->Remote MOCN | 2024 Q4(single site MOCN)-L26 SSM | SM | GCI | 4.6 TSSR Approved |  | 2024-11-27 |  |  | 2024-11-19 |  | Rectificating | 2024-11-19 | 2024-12-16 | E//Hazida | 2024-12-16 | SQ202504180288-GCI | DU00002612740 |  |  | 2025-02-14 | 2025-02-14 |  |  | 60m 4 Legged Tower |  | Remain existing RRU |  | 1
4541D | Kg Buntong | Northern |  | Modernization |  | 2024 Q2 |  | GTSB | 4.6 TSSR Approved |  | 2024-01-06 | 2024-01-08 |  | 2024-01-10 |  | Closed | 2024-01-11 | 2024-01-15 | E//Hazida | 2024-01-12 | Celcom Digi_RAN-GTSB-TSS-Northern-20240108-0083 | DU00002612741 |  |  | 2024-02-20 | 2024-02-17 |  | Lampole | Lampole | 30m | Add R8862A S9000 x3+R9224E M1821 x1,Dismantle |  | 1
4944B | KG LAHAR BUDI - TANDOP | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2027 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612742 | [6 empty] | 45m Tower
4531A | Spg Pulai Shoplot RDD | Northern |  | Remote MOCN |  | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612743 | [6 empty] | 3m Boom (RT) |  |  | 123
4999B | Lubok Buntar2 | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2027 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612744 | [6 empty] | Tower |  |  | 1
4666B | Taman Seri Kota | Northern |  | Modernization | Modernization->Remote MOCN | 2024 Q4(single site MOCN)-L26 SSM | SM | CCSMY | 4.6 TSSR Approved |  | 2024-12-26 |  |  | 2024-11-01 |  | Rectificating | 2024-11-04 | 2024-12-05 | E//Hazida | 2024-12-05 | SQ202504180279 | DU00002612745 |  |  | 2024-11-11 | 2024-11-08 |  |  | 48m 3 Legged Tower |  | Add A9732 M1821x1, Dismantle R9264M M1821(AEA)x1 | 123
2703A | KLIA CP-B5 | Central |  | Remote MOCN | Modernization->Remote MOCN->On Hold->Remote MOCN | 154 single site MOCN |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612746 | [6 empty] | 16m Monopole |  | Add R8862A S9000x3+R8894E M1821x3, Dismantle R8882-GUL1812x2+R8862A S1800(B6A)x1 | 0 | 0
1400A | Men Mutiara PJ | Central |  | Remote MOCN |  | 2024 Q3 | MA | Ascentrack | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | Celcom Digi_RAN-Ascentrack-TSS BAU-20230729-0001_V1 | DU00002612747 | [6 empty] | 3m Boom (RT)
4345D | Hotel Putra Palace | Northern |  | Remote MOCN |  | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612748 | [6 empty] | 3m Boom (RT) |  |  |  | 3
7570B | Kg Makatabau | Sabah |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | Under Approval | [5 empty] | DU00002612749 | [5 empty] | Tower | Tower | 61 |  |  | 2
4772B | Kilang Gula Cuping | Northern |  | Modernization |  | 131 single site mocn | SM | GCI | 4.6 TSSR Approved |  | 2024-08-16 | 2024-08-25 |  | 2024-08-30 |  | Rectificating | 2024-09-02 | 2024-09-23 | E//Hazida | 2024-09-23 | 0809CD-Northern-GCI-BOQ Template(new contract) | DU00002612750 |  |  | 2024-09-21 | 2024-09-07 |  | Tower | 60m 4 Legged Tower | 60 | Add R8852E S9000 x3+R8862A S2601 x2+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x2 | 23
4517A | Pengkalan Industry | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612751 | [6 empty] | 45m 4 Legged Tower |  |  | 1
2396A | SS 1_31 LP | Central |  | Remote MOCN |  | 2024 Q1 | MA | Ascentrack | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | Celcom Digi_RAN-Ascentrack-TSS BAU-20230729-0001_V1 | DU00002612752 | [6 empty] | 24m Lampole
3763C | SK Pandan Desa Pandan (REL) | Central |  | Remote MOCN |  | 2024 Q2 |  | GTSB | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612753 | [6 empty] | 24m Lampole |  |  |  | 1
9565B | Kampung Tanjung Assam | Sarawak |  | Remote MOCN |  | 2024 Q4(single site MOCN)-L21 SSM |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612754 | [6 empty] | Tower |  | Reuse Existing RRU
3092B | BBB Seksyen 4 P2 | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612755 | [6 empty] | 20m Lampole |  |  | 123
1374C | Kampung Kerdas (REL) | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612756 | [6 empty] | 18m Lampole
9582B | Kg Keranji | Sarawak |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612757 | [6 empty] | Tower |  |  |  | 3
4426A | Gunung Semanggol | Northern |  | Remote MOCN |  | 2025 Q1 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612758 | [6 empty] | 60m 3 Legged Tower |  |  |  | 3
4338A | MATANG PASIR (REL) | Northern |  | Decomm | Remote MOCN->Decomm | 2026 |  | NA | 15.3 Decomm Done without TSSR | [6 empty] | To be Submitted | [5 empty] | DU00002612759 |  |  |  |  | 2025-11-28 |  | 60m 4 Legged Tower
1748A | Taman Setapak Indah | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612760 | [6 empty] | 3m Boom (RT)
1220C | Alam Sutera | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 | MA | Ascentrack | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612761 | [6 empty] | 3m Boom (RT)
7942A | Kg Tagaroh Marudu | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2025 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2025-01-23 | 2025-02-07 |  | 2025-03-04 |  | Under Approval | 2025-03-28 | 2025-05-06 | E//Hannah | 2025-05-02 | SQ202501020343 - GTSB | DU00002612762 |  |  | 2025-04-11 | 2025-04-09 |  | Tower | Tower | 60 | Add R8894E M1821x1 | 0 | 3
1037A | JBA Bangi | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612763 | [6 empty] | 45m 4 Legged Tower |  |  |  | 1
7056C | Taman Fajar lahad datu | Sabah |  | Remote MOCN |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612764 | [6 empty] | 30m Monopole |  |  | 13
3843A | Presint 14 | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  | YPTT | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612765 | [6 empty] | Lampole 30m
3399C | Masjid Subang Perdana (REL) | Central |  | Remote MOCN |  | 2024 Q1 | IE | Datasco | 14.2 Drop (Done Survey) | AAU Cannot Install-Change MM to BI¦no space to add AAU | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612766 | BAU_S2_Change MM to BI_Space constraint_SBC KJS | [5 empty] | 24m Lampole |  |  |  | 23
7492B | Kg Sri Takala | Sabah |  | Remote MOCN |  | 2024 Q4(single site MOCN)-L2126 SSM |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612767 | [6 empty] | 45m 3 Legged Tower |  | Reuse Existing RRU
4461C | Hutan Melintang – Simpang Empat (REL) | Northern |  | Remote MOCN |  | 2025 Q1 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612768 | [6 empty] | 30m Lampole |  |  |  | 12
9340A | Batu Kitang | Sarawak |  | Remote MOCN |  | 2024 Q1 |  | AllStar | 14.2 Drop (Done Survey) |  | 2023-10-05 |  |  |  |  | To be Submitted | [5 empty] | DU00002612769 | [5 empty] | Tower | Tower | 60 |  |  | 123
7041C | Kepayan Plaza 88 | Sabah |  | Remote MOCN |  | 2024 Q1 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612770 | [6 empty] | 30m Lampole |  |  |  | 2
4600C | Masjid RPT Pegoh | Northern |  | Remote MOCN |  | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612771 | [6 empty] | 30m Minaret |  |  |  | 2
7362A | Binsulok | Sabah |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q2 |  |  | 14.2 Drop (Done Survey) |  | 2023-11-01 |  |  |  |  | To be Submitted | [5 empty] | DU00002612772 | [6 empty] | 45m 3 Legged Tower |  |  | 23
4469D | Taman Seri Bunga | Northern |  | Modernization |  | 2024 Additional | SM | GTSB | 4.6 TSSR Approved | 0214 - Reverted SA email requesting advise if owner allow. 0213 - SA: Site owner request RRU to move on ground. Kindly advise. | 2023-11-22 | 2023-11-27 |  | 2024-11-22 |  | Rectificating | 2024-11-25 | 2024-12-16 | E//Hazida | 2024-12-16 | Celcom Digi_RAN-GTSB-TSS-Northern-20231127-0068 | DU00002612773 |  |  | 2024-12-09 | 2024-12-04 |  | Lampole | 24M Lampole | 25 | Add R8852E S9000 x3 | 0 | 0
4178D | Taman Sungai Mas | Northern |  | Remote MOCN |  | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612774 | [6 empty] | 30M Minaret |  |  | 12
1196C | Taman Melati | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612775 | [6 empty] | 6m Unipole RT |  |  |  | 23
7386B | Kg Wawasan | Sabah |  | Remote MOCN |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612776 | [6 empty] | 30m Monopole |  |  | 23
4632A | Taman Kempas(ZED) | Northern |  | Remote MOCN |  | 2024 Q1 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | N/A - subcon NA (22/9) | DU00002612777 | [6 empty] | 60m 3 Legged Tower |  |  | 123
7170A | Eden Condo | Sabah |  | Remote MOCN |  | 2024 Q1 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612778 | [6 empty] | 3m Bipod (RT) |  |  |  | 23
7234A | Kg Benoni | Sabah |  | Remote MOCN |  | 2024 Q1 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612779 | [6 empty] | 45m 3 Legged Tower |  |  |  | 12
2361A | Kg baru Sg Buloh | Central |  | Remote MOCN |  | 2024 Q1 | IE | Datasco | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612780 | [6 empty] | 3m Bipod (RT) |  |  |  | 3
3277A | TMNTEKNOLOGI21 | Central |  | Remote MOCN | Modernization->Remote MOCN | 154 single site MOCN |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612781 | [6 empty] | 3m Bipod (RT) |  |  |  | 2
7596A | Kg. Langkon | Sabah |  | Remote MOCN |  | 2026 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612782 | [6 empty] | Tower |  |  |  | 3
2383A | Syabas Desa Park City | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612783 | [6 empty] | Tower |  |  | 23
7488B | Kg Paris Kwantas | Sabah |  | Remote MOCN |  | 2024 Q3(single site MOCN) |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612784 | [6 empty] | 76m 3 Legged Tower
4362C | Bembam Jaya | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2026 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612785 | [6 empty] | 30m Lampole |  |  | 12
3921B | Bandar Bukit Mahkota | Central |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q1 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612786 | [6 empty] | 45m Monopole |  | Reuse Existing RRU | 0 | 0
7424A | Kg Piasau | Sabah |  | Remote MOCN |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612787 | [6 empty] | 45m 3 Legged Tower |  |  |  | 12
3375B | Jaya Shopping Complex Outdoor | Central |  | Remote MOCN |  | 2024 Q3 | MA | Ascentrack | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | Celcom Digi_RAN-Ascentrack-TSS BAU-20230729-0001_V1 | DU00002612788 | [6 empty] | 3m Bipod (RT)
2056B | Tmn Kenanga Salak Tinggi (AS) | Central |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q1 |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612789 | [6 empty] | 76m Tower |  | Reuse Existing RRU | 1 | 0
4471C | Taman Halia Shoplot | Northern |  | Remote MOCN |  | 2024 Q1 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612790 | [6 empty] | 3m Bipod (RT) |  |  | 12
4967A | Karangan(Mxs) | Northern |  | Remote MOCN |  | 2024 Q1 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612791 | [6 empty] | 60m 3 Legged Tower |  |  | 12
7369A | Kg Bukau SBC | Sabah |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612792 | [6 empty] | Tower
4314C | Jaya Jusco Station 18 RT | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612793 | [6 empty] | 3m Boom (RT)
1323A | Abadiindah | Central |  | Remote MOCN |  | 2024 Q3 |  | YPTT | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612794 | [6 empty] | 6m RT (Boom)
3249B | Masjid Al-Syakirin (REL) | Central |  | Remote MOCN |  | 2024 Q1 | SS | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612795 | [6 empty] | 30m Minaret
4193C | Kg Bahagia | Northern |  | Remote MOCN |  | 2026 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612796 | [6 empty] | 45m Monopole |  |  | 123
4479B | Sg Tiang | Northern |  | Remote MOCN |  | 2025 Q1 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612797 | [6 empty] | 60m 3 Legged Tower |  |  |  | 1
3190A | JlnWelfare | Central |  | Remote MOCN |  | 2024 Q1 | IE | Datasco | 14.2 Drop (Done Survey) |  | 2023-10-21 |  |  |  |  | To be Submitted | [5 empty] | DU00002612798 | [6 empty] | 24m Monopole
4699A | Gurun R&R(ZED) | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612799 | [6 empty] | 60m 3 Legged Tower
1402C | Kg Baru (REL) | Central |  | Remote MOCN |  | 2024 Q2 |  | GTSB | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612800 | [6 empty] | 18m Lampole
3749B | Lengkok Mata Air | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612801 | [6 empty] | 24m Lampole
7556A | Dewan Hakka | Sabah |  | Remote MOCN |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612802 | [6 empty] | 6m RT (Wall Mounted Pole) |  |  |  | 12
7842A | KK New Airport In-building | Sabah |  | Remote MOCN | Modernization->On Hold->Decomm->Modernization | 2024 Q1 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2024-04-05 | 2025-01-09 |  |  | 2024-04-15 |  | 2024-04-15 | 2024-06-20 | E//Nazrul | 2024-05-10 | Celcom Digi_RAN-Seri Pancar-Standard PR TSS-Sabah-20240406 | DU00002612803 | Remarks: Solution TSSR/BOM Changed |  |  |  |  | Portables BTS | In-building system |  | Reuse Existing RRU | 0 | 0
7440B | Pin Besar SBC | Sabah |  | Remote MOCN |  | 2024 Q4(single site MOCN)-L2126 SSM |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612804 | [6 empty] | Tower |  | Reuse Existing RRU
1989B | JLN KUCHING RT | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612805 | [6 empty] | 4m Unipole (RT) |  |  | 2
7413A | Bukit Kukut | Sabah |  | Remote MOCN |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612806 | [6 empty] | Tower |  |  |  | 2
7364A | Kg Luagan | Sabah |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612807 | [6 empty] | Tower
3663A | Tmn Bkt Anggerik (REL) | Central |  | Remote MOCN |  | 2024 Q3 |  | YPTT | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612808 | [6 empty] | 18m Lampole |  |  |  | 2
4433A | LAP Sg Siput | Northern |  | Remote MOCN |  | 2026 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612809 | [6 empty] | 45m Monopole |  |  | 13
1424C | Mariammam Temple Dengkil | Central |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q1 |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612810 | [5 empty] | Monopole | 24M Lampole | 25 | Reuse Existing RRU | 0 | 0
1042B | Desa Gombak | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612811 | [6 empty] | 30m Minaret |  |  | 1
7171B | EDEN CONDO (REL) | Sabah |  | Remote MOCN |  | 2024 Q1 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612812 | [6 empty] | 30m Lampole |  |  | 2
2243A | Persiaran 54B | Central |  | Remote MOCN |  | 2024 Q1 | AI | AllStar | 14.1 Drop (No Survey) | AAU Cannot Install-S123 MM change to normal secotr¦This site owner rejected due to loading issue for AAU. If change to bisector also no space to add feeders. | [5 empty] | To be Submitted | [5 empty] | DU00002612813 | [6 empty] | 30m Monopole |  |  | 123
1394A | Damansarauptown | Central |  | Remote MOCN |  | 2024 Q3 | IE | Datasco | 14.2 Drop (Done Survey) |  | 2023-12-06 |  |  |  |  | To be Submitted | [5 empty] | DU00002612814 | [6 empty] | 3m RT (Minimast)
7512B | New housing Sandakan | Sabah |  | Remote MOCN |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612815 | [6 empty] | 6m Unipole RT |  |  |  | 1
7837A | Asia City KK IB | Sabah |  | Remote MOCN |  | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612816 | [6 empty] | IBS + 6m RT (Boom) |  |  |  | 23
1381A | Tmn Mayang Jaya | Central |  | Remote MOCN |  | 2024 Q3 | IE | Datasco | 14.2 Drop (Done Survey) |  | 2023-10-11 |  |  |  |  | To be Submitted | [5 empty] | DU00002612817 | [6 empty] | 5m RT (Boom)
4780B | Felda Besout 5 | Northern |  | Remote MOCN |  | 2025 Q1 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612818 | [6 empty] | Tower |  |  |  | 1
7233C | Benoni CTT | Sabah |  | Remote MOCN |  | 2024 Q1 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612819 | [6 empty] | 45m Tower |  |  |  | 3
4153D | BDRSERIASTANA | Northern |  | Remote MOCN |  | 2024 Q1 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612820 | [6 empty] | 30m Lampole |  |  | 3
4992A | Pendang | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2026 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612821 | [6 empty] | 60m 3 Legged Tower |  |  |  | 2
7359A | Kg Kinarasan | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2025 Q3 | HW | NR services | 4.6 TSSR Approved |  | 2025-01-13 | 2025-02-14 |  | 2025-03-14 |  | Under Approval | 2025-03-17 | 2025-04-24 | E//Hannah | 2025-04-18 | SQ202501020340 - NR Service | DU00002612822 | Remarks: Solution TSSR/BOM Changed |  | 2025-04-17 | 2025-04-11 |  | Tower | Tower | 76 | Add R8852E S9000x1+R8894E M1821x2 | 0 | 1
1913B | SILK Sg Long KM9 | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612823 | [6 empty] | 60m 4 Legged Tower |  |  |  | 2
1298B | Jln Raja Alang | Central |  | Remote MOCN |  | 2024 Q2 |  | GTSB | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002612824 | [6 empty] | 3m Bipod (RT)
4995A | UUM Highway | Northern |  | Remote MOCN |  | 2024 Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002612825 | [6 empty] | 60m 3 Legged Tower |  |  | 23
7110Z | Kg Gadong | Sabah |  | MOCN Decomm |  | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795521
4098Z | Kg Luat | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795522
S00567 | S104A_S00567OD_CB_KGSAGINDAIBARU | Sabah | 7128P | Swap | On Hold->Swap | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-01-09 | 2025-01-14 |  | 2025-01-22 |  | Under Approval | 2025-01-23 | 2025-02-18 | CD//Sharidah | 2025-02-04 | SQ202501020392 - Futong | DU00003795523 |  |  | 2025-06-28 | 2025-05-23 |  | Tower |  | 65m | Add R8852E S9000x3+R8894E M1821x4, Dismantle | 0 | 2
S00046 | S089A_S00046OD_CB_MILE66 | Sabah |  | Decomm | On Hold->Maintain USP MOCN(Dismantle Passive)->Decomm | 2024 Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2026-04-27 |  |  |  | 2026-04-27 | To be Submitted | 2026-04-27 | 2026-05-06 | E//Faiz | 2026-05-06 | SQ202504100576 - GTSB | DU00003795524 |  |  |  |  | 2025-02-25
S00170 | S104A_S00170OD_CB_MILE110 | Sabah |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795525
4196H | 99 Speedmart PK TMN BEMBAN RAYA | Northern |  | MOCN As-Is |  | 2027 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795526 | [8 empty] | Remain iMacro AAU | 0 | 0
S01486 | S104A_S01486OD_CB_KGPAUS | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795527
Q01607 | QS50212_4_1 SMKMERAPOK | Sarawak | 9393K | Swap |  | 2027 |  | DATASCO | 4.1 Pending TSSR Submission - Subcon |  | 2025-02-04 | 2025-04-29 |  |  |  | To be Submitted |  |  |  |  | SQ202501070453-Datasco | DU00003795528 | [5 empty] | Watertank |  | 30m | Add R8852E S9000x2+R9264M M1821x3, Dismantle R8862A S1800(B6A)x1 | 0 | 0
9003Z | PELAJAU | Sarawak |  | MOCN Decomm |  | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795529
S01283 | Kg Daingin | Sabah |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795530
A00427 | A045A_A00427OD_CB_KGAYERMUSANG | Northern | 4542K | Swap |  | 2027 |  | CCSMY | 1.1 Pending Survey - Subcon | [6 empty] | To be Submitted |  |  |  |  | 1911CD-Northern-TSS-BOQ Template(new contract)_CCSMY_V2 | DU00003795531 | [6 empty] | TOWER |  | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
Q02022 | Rumah Alan Sekeroh (old Rumah Masam Rumah Ugak Rumah Enggam | Sarawak |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795532
Q00397 | Q139A_Q00397OD_CB_BT29KCH | Sarawak |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795533
A00510 | A045A_A00510OD_KGTAWAI | Northern | 4246P | Swap | On Hold->Swap | 2025 Q3 | AI | CCSMY | 4.6 TSSR Approved |  | 2025-01-19 | 2025-01-23 |  | 2025-02-17 |  | Closed | 2025-04-11 | 2025-05-23 | CD//Zulakmar | 2025-04-17 | SQ202501030318 - CCSMY | DU00003795534 |  |  | 2025-05-22 | 2025-05-17 |  | Tower |  | 75M | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
K00264 | K012A_K00264OD_CB_SGSETAR | Northern |  | Decomm |  | 2025 Q3 | HW | PERNEC | 4.6 TSSR Approved |  | 2025-04-04 |  | 2025-04-10 |  | 2025-04-16 |  | 2025-04-17 |  | CD//Zulakmar | 2025-04-25 | SQ202501060289 - PERNEC | DU00003795535 |  |  |  |  | 2025-06-13 | Tower |  | 60
S01580 | S088A_S01580OD_CB_KGKEBIDANG | Sabah |  | Decomm | On Hold->Decomm | 2025 Q2 | MNO | Datasco | 4.6 TSSR Approved |  | 2025-03-13 |  | 2025-04-14 |  | 2025-04-20 |  | 2025-04-24 | 2025-10-13 | CD//Sharidah | 2025-09-29 | SQ202504100595 - Datasco | DU00003795536 |  |  |  |  | 2025-06-18
7692A | USP Kg Mendulong | Sabah |  | Modernization |  | 2025 Q4 | AD | DATASCO | 4.6 TSSR Approved |  | 2025-01-17 | 2025-04-23 |  | 2025-05-03 |  | Under Approval | 2025-10-06 | 2025-10-31 | E//Hannah | 2025-10-13 | SQ202501020441 - Datasco | DU00003795537 |  |  | 2025-11-09 | 2025-10-27 |  | Tower |  | 45 | Add R8894E M1821x3, Dismantle R8862A S1800(B6A)x3 | 0 | 0
K00282 | A045A_K00282OD_CB_TMBUKITPALONG | Northern | 4597K | Swap |  | 131 single site mocn | SHA | CCSMY | 4.6 TSSR Approved |  | 2024-10-29 | 2024-11-05 |  | 2024-11-07 |  | Under Approval | 2024-11-10 | 2024-11-14 | CD//Zulakmar | 2024-11-13 | 0809CD-Northern-CCSMY-BOQ Template(new contract) | DU00003795538 |  |  | 2025-01-09 | 2025-01-09 |  | Tower |  | 80m | Add R8862A S9000x3+R8894E M1821x3+R8862A S2601x3,Dismantle | 0 | 0
S01421 | S107A_S01421OD_T3_LONGPASIA | Sabah |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795539
K00210 | K008A_K00210OD_DATAI | Northern |  | Decomm |  | 2024 Additional | AD | GTSB | 4.6 TSSR Approved |  | 2024-12-04 |  | 2025-01-08 |  | 2024-12-19 |  | 2024-12-22 | 2026-02-16 | CD//Zulakmar | 2026-03-31 | SQ202412090105 - GTSB | DU00003795540 |  | Missing Photo Cisco Router ODF PTN |  |  | 2025-04-09
7102R | TELUK MENYAGIT | Sabah |  | MOCN Decomm |  | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795541
K00627 | K009A_K00627OD_MN_KGMALAU | Northern | 4117P | Swap | On Hold->Swap | 2025 Q3 | AI | CCSMY | 4.6 TSSR Approved |  | 2025-01-03 | 2025-01-10 |  | 2025-01-17 |  | Under Approval | 2025-04-11 | 2025-05-19 | CD//Zulakmar | 2025-04-17 | SQ202501030318 - CCSMY | DU00003795542 |  |  | 2025-05-17 | 2025-04-25 |  | Tower |  | 76M | Add R8852E S9000x3+R8854E S1800x3+R8894E M1821x3, Dismantle | 0 | 0
K01017 | Kg Kuala Sin | Northern |  | MOCN Decomm |  | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795543
4022Z | PONDOK INABAH | Northern |  | MOCN Decomm |  | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795544
7325A | Kg Nunuk Ragang SBC | Sabah |  | Decomm | On Hold->Decomm | 2024 Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2025-06-26 |  | 2025-07-21 |  | 2025-08-11 | To be Submitted | 2025-08-21 |  | E//Hannah | 2025-09-25 | SQ202508120138 - GTSB | DU00003795545 |  |  |  |  | 2025-10-25
7016Z | T3_Kg Marau | Sabah |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795546
7089Z | Kg Kuamut | Sabah |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795547
4147Z | KM 34 Baling Gerik Highway | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795548
S01506 | S099A_S01506OD_CB_KGMILURU | Sabah |  | Decomm |  | 2024 Q4 | SHA | Futong | 4.6 TSSR Approved |  | 2024-07-05 |  | 2024-07-14 |  | 2024-07-16 |  | 2024-07-17 | 2024-08-16 | CD//Ray Amos | 2024-07-18 | Celcom Digi_RAN-Futong-Standard PR TSS-Sabah-20240619 / Celcom Digi_RAN Futong Standard PR TSS-Sabah-20241129 | DU00003795549 |  |  |  |  | 2024-12-11
3179B13 | pBTS Chec Construction (EB) | Sarawak |  | Remote MOCN | On Hold->Remote MOCN | 2025 |  |  | 3.4 SOW/Solution On Hold | [6 empty] | To be Submitted | [5 empty] | DU00003795550
K00066 | K010A_K00066OD_PDGPUSING | Northern |  | Decomm |  | 2025 Q2 | HW | GTSB | 4.6 TSSR Approved |  | 2025-02-14 |  | 2025-03-03 |  | 2025-03-17 | To be Submitted | 2025-04-13 |  | CD//Zulakmar | 2025-04-17 | SQ202501060259 - GTSB | DU00003795551 |  |  |  |  | 2025-08-18
S00430 | S111A_S00430OD_CB_JLNPAAL | Sabah |  | MOCN By Other Vendor | On Hold->Maintain USP MOCN->On Hold->MOCN By Other Vendor | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795552
9198Z | KG JAMBU | Sarawak |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795553
9022R | KG TEMONG MAWANG | Sarawak |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795554
7005Z | T3_Kg Lubok Darat | Sabah |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795555
2616A2 | pBTS Borneo Height | Sarawak |  | Decomm | On Hold->Decomm | 2025 Q1 | NA | Magicell | 4.6 TSSR Approved |  | 2025-04-24 |  | 2025-04-28 |  | 2025-05-06 | To be Submitted | 2025-05-07 |  | E//John | 2025-05-22 | SQ202501070146-Magicell/SQ202502270609-Magicell | DU00003795556 | [8 empty] | Add R8852E S9000x2+R8894E M1821x3+R8862A S2601x1, Dismantle R8882-GUL1812x1+R8862A S1800(B6A)x1+R8862A S2601(A6A)x2 | 0 | 0
4010Z | Kg Tekia | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795557
K00865 | K008A_K00865OD_CB_KDNLANGKAWI | Northern |  | Decomm |  | 2025 Q2 | HW | GTSB | 4.6 TSSR Approved |  | 2025-01-27 |  | 2025-03-19 |  | 2025-03-21 |  | 2025-04-18 |  | CD//Zulakmar | 2025-04-25 | SQ202501060259 - GTSB | DU00003795558 |  |  |  |  | 2025-04-28
K00950 | Kg Landai | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795559
S01399 | RS50300_4_1 KGMELIKAI | Sabah | 7316K | Swap |  | 2025 Q4 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2025-10-09 | 2025-10-13 |  | 2025-10-15 |  | Under Approval | 2025-10-29 | 2025-12-01 | E//Hannah | 2025-11-03 | SQ202510060580 - Seri Pancar | DU00003795560 |  |  | 2025-10-29 | 2025-10-29 |  | Tower |  | 30 | Reuse Existing RRU | 0 | 0
S00563 | S104A_S00563OD_CB_HILL2000 | Sabah |  | Maintain USP MOCN | On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795561
7054Z | T3_Kg Lumou | Sabah |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795562
S00551 | S089A_S00551OD_CB_BAKONGBAKONG | Sabah |  | Decomm |  | 2024 Q4 | ZB | Futong | 4.6 TSSR Approved |  | 2024-07-13 |  | 2024-07-18 |  | 2024-07-18 |  | 2024-07-19 | 2024-08-29 | CD//Ray Amos | 2024-07-22 | Celcom Digi_RAN-Futong-Standard PR TSS-Sabah-20240619 | DU00003795563 |  |  |  |  | 2024-12-05
K00869 | K011A_K00869OD_CB_KG_KUBANG_LEREK | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795564
4295H | 99 Speedmart 2462 (PH) Barrington Square | Northern |  | MOCN As-Is |  | 2025 Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795565 | [8 empty] | Remain iMacro AAU | 0 | 0
A00578 | A040D_A00578OD_CB_POSSLIM13_RCC | Northern |  | Decomm |  | 2024 Additional | AD | GTSB | 4.6 TSSR Approved |  | 2024-12-06 |  | 2025-01-27 |  | 2025-02-21 |  | 2025-02-22 | 2026-02-16 | CD//Zulakmar | 2025-02-26 | SQ202501070513-GTSB (RAN)/SQ202510220217 | DU00003795566 |  |  |  |  | 2025-01-24
9056C | Kampung Gelapas | Sarawak |  | Modernization |  | 2027 |  |  | 1.1 Pending Survey - Subcon | [6 empty] | To be Submitted | [5 empty] | DU00003795567 | [8 empty] | Reuse Existing RRU
Q01377 | Q125A_Q01377OD_KGLDGBARU | Sarawak |  | Decomm |  | 2025 Q2 | AD | CCSMY | 4.6 TSSR Approved |  | 2025-06-05 |  | 2025-08-11 |  | 2025-08-15 | To be Submitted | 2025-08-21 |  | E//John | 2025-08-21 | SQ202506060165-CCSMY | DU00003795568 |  |  |  |  | 2025-11-11
4128Z | Kg Kubang Larik | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795569
4055R | Kg Kuala Sin | Northern |  | Maintain USP MOCN |  | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795570
A01206 | T3_0630_Kg Talung Luat | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795571
K00955 | Kg Kuala Beris | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795572
S01722 | Kg Muaya | Sabah |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795573
S00640 | S088A_S00640OD_CB_KGINUMAN | Sabah |  | Decomm |  | 2025 Q2 | NA | DATASCO | 4.6 TSSR Approved |  | 2025-01-08 |  | 2025-04-18 |  | 2025-04-23 |  | 2025-04-24 | 2025-10-28 | CD//Sharidah | 2025-04-26 | SQ202501020441 - Datasco | DU00003795574 |  |  |  |  | 2025-06-23
9011Z | NANGA SUT | Sarawak |  | Decomm, MOCN By Other Vendor | MOCN Decomm->On Hold->Decomm | 2024 Q4 |  | YPTT | 14.1 TSSR Not Required (Decomm by CD) |  | 2025-11-12 |  |  |  |  | To be Submitted | [5 empty] | DU00003795575 |  |  |  |  | 2025-11-12
4014Z | Simpang 3 Kg Perangkap | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795576
Q01758 | Q125A_Q01758OD_JLNLAWASPUNANG | Sarawak | 9348K | Swap |  | 2026 | AI | DATASCO | 4.6 TSSR Approved |  | 2025-02-10 | 2025-02-24 |  | 2025-03-07 |  | Closed | 2025-03-10 | 2025-10-01 | CD//John | 2025-10-01 | SQ202501070453-Datasco | DU00003795577 |  |  | 2025-10-23 | 2025-10-13 |  | Monopole |  | 30 | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
S00305 | S111A_S00305OD_KALLANG | Sabah |  | Decomm |  | 2025 Q2 | HW | YPTT | 4.6 TSSR Approved |  | 2025-01-09 |  | 2025-01-14 |  | 2025-01-24 |  | 2025-02-21 | 2025-05-02 | CD//Sharidah | 2025-02-26 | SQ202501030034 - YPTT | DU00003795578 |  |  |  |  | 2025-07-30
7164Z | Kg Ulu Mailo | Sabah |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795579
9203Z | SK TUBA | Sarawak |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795580
Q01657 | Q137A_Q01657OD_DESAPAHABANAN2 | Sarawak |  | Decomm |  | 2025 Q2 | NA | Futong | 4.6 TSSR Approved |  | 2025-04-14 |  | 2025-04-23 |  | 2025-04-25 |  | 2025-05-02 | 2026-01-07 | CD//John | 2025-05-04 | Previous PO cancellation in progress | DU00003795581 |  |  |  |  | 2025-10-29
A00437 | A045A_A00437OD_CB_SGBELANG | Northern | 4552K | Swap |  | 2027 | SM | CCSMY | 4.6 TSSR Approved |  | 2025-02-05 | 2025-02-12 |  | 2025-02-18 |  | Rectificating | 2025-02-21 | 2025-02-26 | CD//Zulakmar | 2025-02-25 | SQ202411290550 - CCSMY | DU00003795582 | [5 empty] | Tower | TOWER | 80m | Add R8852E S9000 x3+R8894E M1821x3,Dismantle | 0 | 0
S01275 | Batu Enam Puluh Satu | Sabah |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795583
4976C | Mambang Diawan Town | Northern |  | Modernization |  | 2024 Additional | SHA | GCI | 4.6 TSSR Approved |  | 2024-12-15 | 2024-12-16 |  | 2024-12-23 |  | Under Approval | 2024-12-24 | 2025-03-10 | E//Hazida | 2025-02-18 | 1911CD-Northern-TSS-BOQ Template(new contract)_GCI | DU00003795584 |  |  | 2025-01-13 | 2025-01-13 |  | Lampole |  | 30 | Add R8894E M1821x3, Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3 | 0 | 0
3005A5 | pBTS Lafarge Langkawi | Northern |  | Site Out (Modernization) | Decomm->On Hold->Site Out->Site Out (Modernization) | 2025 Q2 |  | NR services | [SiteOut]- 1.0 Pending Survey - Subcon | [6 empty] | To be Submitted | [5 empty] | DU00003795585
7042R | MILE86 | Sabah |  | MOCN Decomm(Dismantle Passive) |  | 2024 Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2025-07-21 |  | 2025-07-23 |  | 2025-07-24 |  | 2025-08-08 | 2025-09-20 | E//Hannah | 2025-09-16 | SQ202506100849 - GTSB / SQ202507010442 - GTSB | DU00003795586 |  |  |  |  | 2025-11-28
K00448 | K011A_K00448OD_CB_BUKITPAYONG | Northern |  | Decomm |  | 2025 Q2 | HW | PERNEC | 4.6 TSSR Approved |  | 2025-05-16 |  | 2025-05-19 |  | 2025-05-22 |  | 2025-06-03 |  | E//Hazida | 2025-06-10 | SQ202501060289 - PERNEC | DU00003795587 |  |  |  |  | 2025-09-17
9217B | Tanjung Bilukuk | Sarawak |  | Decomm, MOCN By Other Vendor | On Hold->Decomm->On Hold->Decomm | 2025 | NA | Magicell | 4.6 TSSR Approved |  | 2025-04-02 |  | 2025-04-08 |  | 2025-05-01 |  | 2025-05-06 | 2025-10-13 | E//Hannah | 2025-05-20 | SQ202503170852-Magicell | DU00003795588 |  |  |  |  | 2025-11-15
7217Z | Kg Bukit Besi | Sabah |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795589
K00629 | K010A_K00629OD_MN_KGLINCHAN | Northern | 4189P | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795590
4097Z | Kg Chepor | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795591
Q01380 | Q124E_Q01380OD_KGPAYAMEBI | Sarawak | 9333K | Swap |  | 2027 |  | Trintel | 3.1 Pending RF Solution - RF Team |  | 2025-12-18 | 2026-03-04 |  |  |  | To be Submitted |  |  |  |  | SQ202511040097 - Trintel | DU00003795592 | [5 empty] | Monopole |  | 25 | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
S01232 | Tongod | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795593
S01724 | kpg kelangsat | Sabah |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795594
K00338 | K012A_K00338OD_PAYATERENDAM | Northern | 4121P | Swap | On Hold->Swap | 2025 Q3 | HW | GCI | 4.6 TSSR Approved |  | 2025-01-13 | 2025-01-16 |  | 2025-02-25 |  | Under Approval | 2025-04-23 | 2025-05-06 | CD//Zulakmar | 2025-05-02 | SQ202501030328 - GCI | DU00003795595 |  |  | 2025-07-06 | 2025-06-25 |  | Tower |  | 60m | Add R8852E S9000x3+R8894E M1821x8,Dismantle | 0 | 12
S00388 | S089A_S00388OD_CB_MILE43 | Sabah |  | Decomm | On Hold->Maintain USP MOCN(Dismantle Passive)->Decomm | 2024 Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2025-04-04 |  | 2025-05-22 |  | 2025-06-18 |  | 2025-06-19 | 2025-10-13 | E//Hannah | 2025-09-11 | SQ202504100576 - GTSB | DU00003795596 |  |  |  |  | 2025-03-08
S00921 | S111A_S00921OD_CB_MELALAP | Sabah | 7102P | Swap | On Hold->Swap | 2025 Q2 | SM | YPTT | 4.6 TSSR Approved |  | 2025-01-06 | 2025-01-13 |  | 2025-01-16 |  | Rectificating | 2025-03-17 | 2025-03-19 | CD//Sharidah | 2025-03-19 | SQ202501020336 - YPTT | DU00003795597 |  |  | 2025-06-14 | 2025-05-25 |  | Tower |  | 60 | Add R8852E S9000x3+R9224E M1821x8, Dismantle | 0 | 12
A00023 | A045A_A00023OD_TNBHIDRO | Northern |  | Decomm |  | 2024 Additional | HW | NR services | 4.6 TSSR Approved |  | 2024-12-01 |  | 2025-01-28 | 2025-11-07 | 2025-02-09 | Under Approval | 2025-02-18 |  | CD//Hazwan | 2025-02-24 | SQ202501070548-NR (RAN) | DU00003795598 |  | Missing MW TX info (NE/FE) |  |  | 2025-02-04
7341B | Indarason (Celcom) | Sabah |  | Decomm, MOCN By Other Vendor | On Hold->Decomm->On Hold->Decomm | 2025 | AD | GTSB | 4.6 TSSR Approved |  | 2025-04-22 |  | 2025-05-08 |  | 2025-06-13 |  | 2025-06-16 | 2025-10-31 | E//Hannah | 2025-10-27 | SQ202504100576 - GTSB | DU00003795599 |  |  |  |  | 2025-11-28
S01642 | S096A_S01642OD_KGBINGOLON | Sabah |  | Decomm |  | 2025 Q3 | HW | GTSB | 4.6 TSSR Approved |  | 2025-02-06 |  | 2025-02-10 |  | 2025-02-25 |  | 2025-02-26 | 2025-09-10 | CD//Sharidah | 2025-03-03 | SQ202501020455 - GTSB | DU00003795600 |  |  |  |  | 2025-07-16
9662B | Kampung Sasa | Sarawak |  | Remote MOCN | On Hold->Maintain USP MOCN->Remote MOCN | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795601 | [8 empty] | Reuse Existing RRU | 0 | 0
Q01458 | Q126A_Q01458OD_MN_KUBONG | Sarawak |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795602
7115R | KGSAGINDAIBARU | Sabah |  | MOCN Decomm(Dismantle Passive) | On Hold->MOCN Decomm | 2024 Q4 |  | GTSB | 15.3 Decomm Done without TSSR | [6 empty] | To be Submitted |  |  |  |  | SQ202506100849 - GTSB / SQ202507010442 - GTSB | DU00003795603 |  |  |  |  | 2025-11-28
S01369 | RS50267_4_1 SKKOTAKLIAS | Sabah | 7300K | Swap |  | 2027 | AD | DATASCO | 4.6 TSSR Approved |  | 2025-03-13 | 2025-06-10 |  | 2025-12-23 |  | Under Approval | 2025-12-29 | 2026-01-13 | E//Hannah | 2026-01-05 | SQ202501020441 - Datasco | DU00003795604 | [5 empty] | Tower |  | 30 | Add R8852E S9000x2+R8894E M1821x3, Dismantle R8862A S1800(B6A)x1 | 0 | 0
S00265 | TMMELALAP | Sabah | 7173K | Swap |  | 2025 Q2 | AD | YPTT | 4.6 TSSR Approved | 22/8 Bushes clearance wip // 12/8- High Bushes, cannot climb // 6/8- TM expired team no enter SA Feedback | 2025-10-18 | 2025-10-23 |  | 2025-10-24 |  | Under Approval | 2025-10-27 | 2025-10-29 | E//Faiz | 2025-10-28 | SQ202501030045 - YPTT | DU00003795605 |  |  | 2025-11-21 | 2025-11-12 |  | Tower |  | 46 | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
A01385 | Kg Telok Batu | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795606
7001R | Kg Toporoi | Sabah |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795607
7099H | iMacro Sekuati | Sabah |  | MOCN As-Is |  | 2025 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795608 | [8 empty] | Remain iMacro AAU | 0 | 0
4745A | Keda | Northern |  | Modernization |  | 2025 Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2025-02-27 | 2025-02-13 |  | 2025-03-04 |  | Rectificating | 2025-03-07 | 2025-03-17 | E//Hazida | 2025-03-17 | SQ202501030229 - GTSB | DU00003795609 |  |  | 2025-04-16 | 2025-04-10 |  | Tower |  | 60m | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8882 S1800B(B6B)x3 | 0 | 0
4024Z | Kg Banggul Berangan | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795610
4001Z | Kg Sg Senam | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795611
9299A | Jalan Pandaruan | Sarawak |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795612
S01224 | Kg Suguon | Sabah |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795613
4099R | 4255_KuakTown_KUAKM1_27 | Northern |  | Maintain USP MOCN(Dismantle Passive) | On Hold->Maintain USP MOCN(Dismantle Passive) | 2025 Q3 | HW | CCSMY | 4.6 TSSR Approved |  | 2025-09-30 |  | 2025-09-11 |  | 2025-10-01 |  | 2025-10-02 | 2026-01-22 | E//Hazida | 2025-10-09 | SQ202504230451-CCSMY | DU00003795614 |  |  |  |  | 2025-09-09
4037Z | Kg Sg Semiar | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795615
7011Z | T3_Batu Enam Puluh Satu | Sabah |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795616
7654C | Taman Seri Awana | Sabah |  | Modernization |  | 2025 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2025-02-06 | 2025-02-10 |  | 2025-02-27 |  | Under Approval | 2025-02-28 | 2025-03-24 | E//Hannah | 2025-03-16 | SQ202501030028 - GTSB | DU00003795617 |  |  | 2025-03-29 | 2025-03-15 |  | Lampole |  | 30 | Add R8852E S9000 x3+R9264M M1821 x3, Dismantle R8894E M1821(A8A)x3 | 0 | 0
9253Z | Long Rayah | Sarawak |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795618
7003R | Kg Rondomon | Sabah |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795619
Q02057 | UluLubai | Sarawak |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795620
4205Z | Kg Paya Lipai | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795621
4158C | USP_Jln Bkt Malut 2 | Northern |  | Modernization |  | 2025 Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2025-01-27 | 2025-02-23 |  | 2025-02-27 |  | Rectificating | 2025-03-04 | 2025-03-10 | E//Hazida | 2025-03-06 | SQ202501030229 - GTSB | DU00003795622 | Remarks: Solution TSSR/BOM Changed |  | 2025-03-18 | 2025-03-08 |  | Tower |  | 60m | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8881 S9000x2+R8882 S1800B(B6B)x2+R8881 S2100x2 | 0 | 0
A00032 | A045A_A00032OD_CB_AYERJADA | Northern | 4228P | Maintain USP MOCN(Dismantle Passive) |  | 2025 Q3 | HW | CCSMY | 4.6 TSSR Approved |  | 2025-07-26 |  | 2025-07-29 |  | 2025-08-01 |  | 2025-09-29 | 2026-01-22 | E//Hazida | 2025-10-09 | SQ202504230451-CCSMY | DU00003795623 |  |  |  |  | 2025-10-10
S01731 | imbak canyon | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795624
K00943 | Kg Bkt Jagung | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795625
S01684 | T3E_0223_ Paitan Nangoh 3 | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795626
S01680 | T3E_0219_ Kg Pantai Boring | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795627
Q00023 | Q141A_Q00023OD_SADONGJAYA | Sarawak |  | Decomm |  | 2024 | AI | Trintel | 4.6 TSSR Approved |  | 2025-02-04 |  | 2024-11-29 |  | 2025-02-04 |  | 2025-01-22 | 2025-05-02 | CD//John | 2025-01-22 | CelcomDigi_RAN_Trintel_PR_TSS_Sarawak_20241101 | DU00003795628 |  |  |  |  | 2025-05-29
K01006 | Kg Sukamari | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795629
S01262 | Kg Kawiyan | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795630
7204Z | Tanjung Nipis Estate | Sabah |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795631
4737B | Kg Kuala Kenering | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795632 | [8 empty] | Reuse Existing RRU | 0 | 0
4058Z | TJG KALA | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795633
K00626 | K009A_K00626OD_MN_KGPADANG | Northern | 4187P | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795634
A01202 | T3_0632_Kg Temin | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795635
7366A | Weston Junction SBC | Sabah |  | Modernization |  | 2025 Q2 | AD | DATASCO | 4.6 TSSR Approved |  | 2025-02-05 | 2025-02-27 |  | 2025-03-05 |  | Under Approval | 2025-03-10 | 2025-03-26 | E//Hannah | 2025-03-19 | SQ202501020441 - Datasco | DU00003795636 |  |  | 2025-05-11 | 2025-03-21 |  | Tower |  | 60 | Add R8894E M1821x3, Dismantle 8862A S1800(B6A)x3 | 0 | 0
7001Z | T3_Kg Lubok Weston | Sabah |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795637
4540B | POS SLIM 13 RCC | Northern |  | Modernization |  | 2024 Additional | SM | GTSB | 4.6 TSSR Approved |  | 2024-11-29 | 2024-12-03 |  | 2024-12-04 |  | Rectificating | 2024-12-05 | 2024-12-19 | E//Hazida | 2024-12-18 | 1911CD-Northern-TSS-BOQ Template(new contract)_GTSB | DU00003795638 |  |  | 2025-01-06 | 2025-01-02 |  | Tower |  | 80m | Add R8852E S9000x4+R8894E M1821x4, Dismantle R8860E-GU908x2+R8892E M1821(BAA)x3 | 0 | 0
Q01370 | Q125A_Q01370OD_LAWASAIRPORT | Sarawak | 9331K | Swap |  | 2026 | AI | DATASCO | 4.6 TSSR Approved |  | 2025-02-05 | 2025-02-27 |  | 2025-03-06 |  | Closed | 2025-03-10 | 2025-04-15 | CD//John | 2025-03-10 | SQ202501070453-Datasco | DU00003795639 |  |  | 2025-05-28 | 2025-05-27 |  | Monopole |  | 16 | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
9597C | Kampung Kakeng | Sarawak |  | Modernization |  | 2027 | AD | Trintel | 4.6 TSSR Approved |  | 2025-12-02 | 2025-12-04 |  | 2025-12-05 |  | Under Approval | 2025-12-16 | 2026-01-13 | E//John | 2025-12-16 | SQ202511040097 - Trintel | DU00003795640 | [5 empty] | Tower |  | 30 | Reuse Existing RRU
9007Z | NANGA TEKALIT | Sarawak |  | Decomm, MOCN By Other Vendor | MOCN Decomm->On Hold->Decomm | 2025 |  | YPTT | 14.1 TSSR Not Required (Decomm by CD) |  | 2025-11-12 |  |  |  |  | To be Submitted | [5 empty] | DU00003795641 |  |  |  |  | 2025-11-12
9248A | Ranchan Pools | Sarawak |  | Decomm, MOCN By Other Vendor | On Hold->Decomm->On Hold->Decomm | 2025 Q3 | HW | Magicell | 4.6 TSSR Approved |  | 2025-02-20 |  | 2025-02-24 |  | 2025-02-26 |  | 2025-02-27 | 2025-10-31 | E//Hannah | 2025-10-23 | SQ202502050300-Magicell | DU00003795642 |  |  |  |  | 2025-11-10
A01277 | Jln Bukit Sapi Ayer Kala | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795643
4147H | Gaharu Tea Valley | Northern |  | MOCN As-Is |  | 2027 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795644 | [8 empty] | Remain iMacro AAU | 0 | 0
K00659 | K008A_K00659OD_LICC_STREGIS | Northern | 4168K | Swap |  | 2025 Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2025-03-17 | 2025-03-26 |  | 2025-04-04 |  | Under Approval | 2025-04-08 | 2025-04-15 | CD//Zulakmar | 2025-04-14 | SQ202501030229 - GTSB | DU00003795645 | Remarks: Solution TSSR/BOM Changed |  | 2025-04-30 | 2025-04-16 |  | In-Building System |  | 3M | Add R8852E S9000x1+R8894E M1821x1, Dismantle | 0 | 0
S00944 | S096A_S00944OD_T3_KGDAMARAN | Sabah | 7129P | Swap | On Hold->Swap | 2025 Q3 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2025-09-09 | 2025-09-09 |  | 2025-09-10 |  | Under Approval | 2025-09-17 | 2025-10-13 | E//Hannah | 2025-09-19 | SQ202508120212 - Seri Pancar | DU00003795646 |  |  | 2025-10-07 | 2025-09-24 |  | Tower |  | 76m | Add R8852E S9000x3+R8894E M1821x5, Dismantle | 0 | 23
9256Z | Kg Long Bidang | Sarawak |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795647
S01637 | S088A_S01637OD_KGMAWAO | Sabah |  | Decomm |  | 2025 Q2 | AD | DATASCO | 4.6 TSSR Approved |  | 2025-01-09 |  | 2025-03-28 |  | 2025-04-11 |  | 2025-04-29 | 2025-10-28 | CD//Sharidah | 2025-04-30 | SQ202501020441 - Datasco | DU00003795648 |  |  |  |  | 2025-03-27
A01205 | T3_0624_Bukit Sapi | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795649
4153C | USP_Telaga Harbour | Northern |  | Modernization |  | 2024 Additional | SHA | GTSB | 4.6 TSSR Approved |  | 2024-12-02 | 2024-12-16 |  | 2024-12-17 |  | Under Approval | 2024-12-18 | 2024-12-19 | E//Hazida | 2024-12-27 | SQ202411290524 - GTSB | DU00003795650 |  |  | 2025-02-05 | 2025-01-29 |  | Tower |  | 60m | Add R8852E S9000 x3+R8894E M1821x3,Dismantle R8881 S9000x1+R8882 S1800B(B6B)x3 | 0 | 0
K00712 | K008A_K00712OD_MERITUSPELANGI2 | Northern | 4463K | Swap |  | 2025 Q2 | HW | GTSB | 4.6 TSSR Approved |  | 2025-03-20 | 2025-03-24 |  | 2025-03-26 |  | Under Approval | 2025-03-27 | 2025-04-24 | CD//Zulakmar | 2025-04-08 | SQ202501030229 - GTSB | DU00003795651 |  |  | 2025-05-17 | 2025-04-23 |  | Monopole |  | 30M | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
7058H | 99 Speedmart 1 BEAUFORT | Sabah |  | MOCN As-Is |  | 2025 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795652 | [8 empty] | Remain iMacro AAU | 0 | 0
9600C | Kampung Engkeroh | Sarawak |  | Modernization |  | 2027 | AD | Trintel | 4.5 Pending TSSR Review - Customer |  | 2025-11-26 | 2025-11-21 |  | 2025-12-04 |  | Under Approval | 2025-12-16 |  | E//John |  | SQ202511040097 - Trintel | DU00003795653 | [5 empty] | Tower |  | 30 | Reuse Existing RRU
S01689 | T3E_0229_ Kg Kuamut | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795654
4133Z | Kg Belukar | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795655
4052Z | KGAYERPANAS | Northern |  | MOCN Decomm |  | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795656
Q01822 | Q126A_Q01822OD_KGTANJUNGLBG | Sarawak | 9354K | Swap |  | 2025 Q2 | AI | DATASCO | 4.6 TSSR Approved |  | 2025-02-04 | 2025-03-25 |  | 2025-04-08 |  | Under Approval | 2025-04-08 | 2025-04-15 | CD//John | 2025-04-08 | SQ202501070453-Datasco | DU00003795657 |  |  | 2025-07-06 | 2025-06-14 |  | Tower |  | 60 | Add R8862A S9000x3+R8894E M1821x3, Dismantle | 0 | 0
4251C | LICC IBC | Northern |  | Modernization |  | 2025 Q2 | AD | GTSB | 4.6 TSSR Approved |  | 2025-03-10 | 2025-03-14 |  | 2025-03-19 |  | Under Approval | 2025-03-20 | 2025-05-21 | E//Nazrul | 2025-03-20 | SQ202501030229 - GTSB | DU00003795658 |  |  | 2025-04-26 | 2025-04-24 |  | Portables BTS |  | NA | Add R8894E M1821x1, Dismantle R8882 S1800B(B6B)x1 | 0 | 0
8260Z | Lojing | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795659
S01287 | Kg Marau | Sabah |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795660
4234Z | Kg Datok | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795661
K00096 | K008A_K00096OD_MUTIARACOURT | Northern |  | Decomm |  | 2025 Q2 | HW | GTSB | 4.6 TSSR Approved |  | 2025-01-27 |  | 2025-02-19 |  | 2025-03-21 |  | 2025-04-18 | 2026-01-30 | CD//Zulakmar | 2025-04-25 | SQ202501060259 - GTSB | DU00003795662 |  |  |  |  | 2025-05-02
Q02135 | KPG LONG BIDANG | Sarawak |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795663
A00564 | A040D_A00564OD_CB_POSSLIM | Northern |  | Decomm |  | 2024 Additional | HW | CCSMY | 4.6 TSSR Approved |  | 2025-01-21 |  | 2025-02-03 |  | 2025-02-17 |  | 2025-02-18 | 2025-05-20 | CD//Hazwan | 2025-02-24 | SQ202502100375 | DU00003795664 |  |  |  |  | 2025-02-17
Q01958 | Q139A_Q01958OD_T3_KGRETEHMAWANG | Sarawak |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795665
7131R | Kg Pengalat | Sabah |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795666
K00625 | K009A_K00625OD_MN_KGSGLONG | Northern | 4116P | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795667
7036Z | T3_Kg Tangkarason | Sabah |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795668
K00656 | Kg Telok Sera | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795669
4232Z | Kg Lintang | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795670
9022Z | ULU PANDARUAN | Sarawak |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795671
9153R | BUNANGEGA | Sarawak |  | MOCN Decomm(Dismantle Passive) |  | 2024 Q4 | HW | Magicell | 4.6 TSSR Approved |  | 2025-07-04 |  | 2025-07-15 |  | 2025-07-16 |  | 2025-08-07 | 2026-01-20 | E//Hannah | 2025-09-09 | SQ202506110081-Magicell/SQ202507140221-Magicell | DU00003795672 |  |  |  |  | 2025-09-26
S00483 | S088A_S00483OD_CB_KGBATANDOK | Sabah | 7092P | Swap | On Hold->Swap | 2025 Q2 | AD | DATASCO | 4.6 TSSR Approved |  | 2025-01-20 | 2025-03-07 |  | 2025-03-13 |  | Under Approval | 2025-03-26 | 2025-05-21 | CD//Sharidah | 2025-04-08 | SQ202501020331 - Datasco | DU00003795673 |  |  | 2025-08-17 | 2025-08-11 |  | Tower |  | 60 | Add R8852E S9000x3+R8894E M1821x9, Dismantle | 0 | 123
4044Z | POSPIAH | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795674
K00949 | Kg Hj Din | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795675
Q01459 | Q126A_Q01459OD_MN_KGBELIMBING | Sarawak |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795676
9701A | Gunung Ampangan | Sarawak |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q3 | HW | Magicell | 4.6 TSSR Approved |  | 2025-02-10 | 2025-03-27 |  | 2025-04-11 |  | Under Approval | 2025-04-14 | 2025-04-24 | E//Hannah | 2025-04-21 | SQ202501070146-Magicell | DU00003795677 | [5 empty] | Tower |  | 77 | Reuse Existing RRU | 0 | 0
Q01023 | Q141A_Q01023OD_T3_KGMAWANG | Sarawak |  | Maintain USP MOCN |  | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795678
7085Z | LadangSungaiSapi | Sabah |  | Modernization | On hold->Modernization | 2024 Q4 | AI | Futong | 4.6 TSSR Approved |  | 2025-01-20 | 2025-01-27 |  | 2025-02-01 |  | Under Approval | 2025-02-03 | 2025-02-27 | E//Norsyahriani | 2025-02-18 | SQ202501020392 - Futong | DU00003795679 |  |  | 2025-02-20 | 2025-02-18 |  | Tower |  | 76m | Add R8894E M1821x1 | 0 | 1
4129Z | Kg Keda Kubang Palas | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795680
7092R | KG TELUTU | Sabah |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795681
Q01461 | Q126A_Q01461OD_MN_NANGAMEDAMIT | Sarawak |  | Maintain USP MOCN |  | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795682
Q01956 | Q139A_Q01956OD_T3_KGMONGKOS | Sarawak |  | Maintain USP MOCN |  | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795683
Q01010 | Q139A_Q01010OD_CB_KGMAYANG | Sarawak |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795684
S00141 | S096A_S00141OD_CB_PINAWANTAI | Sabah |  | Decomm |  | 2025 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2025-02-25 |  | 2025-04-07 |  | 2025-04-10 |  | 2025-05-05 | 2025-10-28 | E//Sharidah | 2025-05-06 | SQ202501020455 - GTSB | DU00003795685 |  |  |  |  | 2025-04-29
Q00192 | VQ_PUTAI | Sarawak | 9289K | Swap |  | 2027 |  | Trintel | 1.1 Pending Survey - Subcon | [6 empty] | To be Submitted |  |  |  |  | SQ202601300355 - Trintel | DU00003795686
7041Z | T3_Kg Tampat | Sabah |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795687
S01581 | S088A_S01581OD_CB_KGLUPAK | Sabah |  | MOCN Decomm(Dismantle Passive) |  | 2025 Q2 | HW | Datasco | 4.6 TSSR Approved |  | 2025-07-07 |  | 2025-07-09 |  | 2025-10-24 |  | 2025-10-29 | 2026-01-20 | E//Faiz | 2025-11-06 | SQ202506100762 - Datasco /SQ202507010433 - Datasco | DU00003795688 |  |  |  |  | 2025-10-31
4040Z | Sg Batu Lata Bkt Hijau | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795689
S01696 | Kg Kaindangan | Sabah |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795690
A01204 | KM 39 Baling Gerik Highway KM37 Baling Gerik Highway | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795691
4240Z | Jln Bukit Sapi Ayer Kala | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795692
7571B | kg baru jumpa | Sabah |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q2 | AD | YPTT | 4.6 TSSR Approved |  | 2025-01-07 | 2025-01-10 |  | 2025-01-20 |  | Under Approval | 2025-02-17 | 2025-07-16 | E//Hannah | 2025-03-10 | SQ202501030041 - YPTT | DU00003795693 | [5 empty] | Tower |  | 60 | Reuse Existing RRU | 0 | 0
4237Z | Jalan Lepang Nenering | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795694
A00435 | A045A_A00435OD_CB_MENDELUM | Northern | 4550K | Swap |  | 2027 |  | CCSMY | 4.4 Pending TSSR Review - Design Team |  | 2025-02-05 | 2025-02-23 |  | 2025-02-28 |  | Under Approval |  |  |  |  | SQ202411290550 - CCSMY | DU00003795695 | [5 empty] | Tower | TOWER | 80m | Add R8852E S9000 x3+R8894E M1821x3,Dismantle | 0 | 0
S00506 | S088A_S00506OD_KGLUAGAN | Sabah |  | Decomm |  | 2025 Q2 | NA | DATASCO | 4.6 TSSR Approved |  | 2025-01-07 |  | 2025-04-23 |  | 2025-04-25 |  | 2025-04-28 | 2025-10-13 | E//Saiful | 2025-09-25 | SQ202501020441 - Datasco | DU00003795696 |  |  |  |  | 2025-08-11
7085R | KGBATULUANG | Sabah |  | MOCN Decomm(Dismantle Passive) |  | 2025 Q1 |  | Datasco | 14.1 TSSR Not Required (Decomm by CD) | 9/2/2026: Confirmed by Datasco, during survey team found out site already dismantled | 2025-07-07 |  | 2025-07-09 |  | 2025-09-10 | To be Submitted |  |  |  |  | SQ202506100762 - Datasco /SQ202507010433 - Datasco | DU00003795697 |  |  |  |  | 2025-08-05
Q01966 | Q141A_Q01966OD_T3_JLNSIMUNJANKENION | Sarawak |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795698
S00805 | S107A_S00805OD_PEKANSIPITANG | Sabah |  | Decomm |  | 2025 Q2 | NA | DATASCO | 4.6 TSSR Approved |  | 2025-01-13 |  | 2025-04-17 |  | 2025-04-23 |  | 2025-04-24 | 2025-10-28 | CD//Sharidah | 2025-04-26 | SQ202501020441 - Datasco | DU00003795699 |  |  |  |  | 2025-06-06
4011Z | Kg Wat Paya Mat Insun | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795700
7081Z | BerakanMajuEstate | Sabah |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795701
S01734 | T3E_0235_ Tampasak | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795702
Q02256 | NANGA DAP PELAGUS | Sarawak |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795703
K00650 | Kg Sg Semiar | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795704
A01189 | T3E_0046_KM 44 Baling Gerik Highway | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795705
K00933 | T3E_0058_Kg Bendang Bukit | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795706
7075H | 99 Speedmart Wisma SQS | Sabah |  | MOCN As-Is |  | 2025 Q4 | BY |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | 2024-07-29 |  |  |  |  | DU00003795707 | [8 empty] | Remain iMacro AAU | 0 | 0
S01424 | S107A_S01424OD_T3_MENDULONGLONGPASIAROAD2 | Sabah |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795708
7432B | Beluran 61 | Sabah |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795709
4134Z | Kg Bendang Bukit | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795710
S01231 | Tongkulap | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795711
9019Z | KGBELIMBING | Sarawak |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795712
4229H | 99 Speedmart PK Mambang Di Awan | Northern |  | MOCN As-Is |  | 2027 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795713 | [8 empty] | Remain iMacro AAU | 0 | 0
S01257 | Karagasan | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795714
Q01955 | Kg Temong Mawang | Sarawak |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795715
S00943 | S096A_S00943OD_T3_KGLIMBUAKLAUT | Sabah | 7253P | Swap | On Hold->Maintain USP MOCN->On Hold->MOCN By Other Vendor->Swap | 2026 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2025-10-17 | 2025-10-23 |  | 2025-10-23 |  | Under Approval | 2025-10-27 | 2026-01-13 | E//Faiz | 2025-10-29 | SQ202510090551 - Seri Pancar | DU00003795716 | [5 empty] | Tower |  | 76 | Add R8852E S9000 x6+R8894E x6, Dismantle
9965A | Taman Payan Jaya (REL) | Sarawak |  | Modernization |  | 2025 Q2 | AD | Futong | 4.6 TSSR Approved |  | 2025-05-02 | 2025-05-14 |  | 2025-05-23 |  | Under Approval | 2025-05-27 | 2025-06-30 | E//John | 2025-05-28 | SQ202505020080-Futong | DU00003795717 |  |  | 2025-07-06 | 2025-06-27 |  | Monopole |  | 30 | Add R8852E S9000x3 | 0 | 0
K00661 | K008A_K00661OD_JLNBKTMALUT2 | Northern |  | Decomm |  | 2025 Q2 | HW | GTSB | 4.6 TSSR Approved |  | 2025-01-27 |  | 2025-02-10 |  | 2025-03-19 |  | 2025-04-13 | 2025-05-27 | CD//Zulakmar | 2025-04-17 | SQ202501060259 - GTSB | DU00003795718 |  |  |  |  | 2025-03-20
Q01551 | Q123A_Q01551OD_MN_SKANTAROH | Sarawak |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795719
A00813 | A045A_A00813OD_MN_KGSUMPITAN | Northern | 4155P | Swap | On Hold->Swap | 2025 Q3 | HW | GCI | 4.6 TSSR Approved |  | 2025-01-17 | 2025-03-17 |  | 2025-03-24 |  | Under Approval | 2025-04-08 | 2025-05-19 | CD//Zulakmar | 2025-04-11 | SQ202501030328 - GCI | DU00003795720 |  |  | 2025-05-26 | 2025-05-17 |  | Tower |  | 75m | Add R8852E S9000x3+R8894E M1821x4, Dismantle | 0 | 3
7046Z | T3_Reka Halus Plantation | Sabah |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795721
K00779 | K009A_K00779OD_CB_KGULU_PDGTERAP | Northern | 4467K | Swap |  | 2025 Q3 | AI | PERNEC | 4.6 TSSR Approved |  | 2025-01-23 | 2025-02-04 |  | 2025-02-10 |  | Under Approval | 2025-04-11 | 2025-04-25 | CD//Zulakmar | 2025-04-25 | SQ202501030191 - PERNEC | DU00003795722 |  |  | 2025-07-06 | 2025-05-21 |  | Tower |  | 46 | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
S01271 | Pinangatuan | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795723
9178R | KG PAON GAHAT | Sarawak |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795724
Q01077 | Q124E_Q01077OD_KGANAHRAIS | Sarawak |  | Decomm | On Hold->Decomm | 2025 Q1 | HW | Magicell | 4.6 TSSR Approved |  | 2025-02-19 |  | 2025-02-23 |  | 2025-03-04 |  | 2025-03-07 | 2025-10-28 | CD//John | 2025-03-10 | SQ202502050300-Magicell/SQ202502270609-Magicell | DU00003795725 |  |  |  |  | 2025-10-31
4089Z | T3E_0629_KgTanjungKekabu | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795726
9093Z | Kg Gadong | Sarawak |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795727
7077Z | Paitan Nangoh2 | Sabah |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795728
S01720 | T3_0700_Kg Bahanan Pulau Jambongan | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795729
S01261 | Kg Kapoi | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795730
S01528 | Skim Penempatan Getah Lagud Seberang | Sabah |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795731
4113Z | Kg Paya Serdang | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795732
4730B | Selat Pagar | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q3 |  | GCI | 4.4 Pending TSSR Review - Design Team |  | 2025-01-17 | 2025-03-12 |  | 2025-03-24 |  | Under Approval |  |  |  |  | SQ202501030261 - GCI | DU00003795733 | [5 empty] | Tower |  | 60m | Reuse Existing RRU | 0 | 0
7052Z | T3_Sk Sungai sungai | Sabah |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795734
K00636 | Kg Paya Sulaiman | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795735
A01210 | KM 29 Baling Gerik Highway | Northern |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795736
7130R | Kg Mandalom Baru | Sabah |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795737
Q02002 | Nanga Banjor (old SK Lubok Bedil RumahJinggai Rumah Rantai) | Sarawak |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795738
9251A | Krusen | Sarawak |  | Decomm, MOCN By Other Vendor | On Hold->Decomm->On Hold->Decomm | 2025 | AD | Magicell | 4.6 TSSR Approved |  | 2025-04-09 |  | 2025-04-09 |  | 2025-05-12 |  | 2025-05-14 | 2025-10-13 | E//John | 2025-05-27 | SQ202503170852-Magicell | DU00003795739 |  |  |  |  | 2025-11-11
4097R | 6049_Kenayat_KYATM1_35 | Northern |  | Decomm | On Hold->Maintain USP MOCN(Dismantle Passive) | 2025 Q3 | AI | CCSMY | 4.6 TSSR Approved |  | 2025-09-30 |  | 2025-09-23 |  | 2025-10-01 | To be Submitted | 2026-02-16 |  |  | 2026-02-20 | SQ202504230451-CCSMY | DU00003795740 |  |  |  |  | 2025-08-05
4238H | 99 Speedmart PK Tmn Perak Mewah | Northern |  | MOCN As-Is |  | 2027 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795741 | [8 empty] | Remain iMacro AAU | 0 | 0
S00823 | S088A_S00823OD_TMNSRIPANGLIMA | Sabah |  | Decomm |  | 2025 Q2 | AD | DATASCO | 4.6 TSSR Approved |  | 2025-01-09 |  | 2025-05-06 |  | 2025-05-15 |  | 2025-05-19 | 2025-10-13 | E//Saiful | 2025-09-25 | SQ202501020441 - Datasco | DU00003795742 |  |  |  |  | 2025-06-15
Q02142 | NANGA TEMALAT | Sarawak |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795743
4261H | 99 Speedmart PK Tmn Kampar Barat | Northern |  | MOCN As-Is |  | 2027 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795744 | [8 empty] | Remain iMacro AAU | 0 | 0
A00667 | A045A_A00667OD_CB_NORTHGATE | Northern | 4570K | Swap |  | 2025 | HW | GCI | 4.6 TSSR Approved | 12/8 - team plan go in wk34 | 2025-09-04 | 2025-09-09 |  | 2025-09-10 |  | Under Approval | 2025-09-11 | 2025-09-26 | E//Hazida | 2025-09-17 | SQ202511040238 | DU00003795745 |  |  | 2025-10-31 | 2025-10-23 |  |  |  | 18m | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
S01285 | Kg Lubok Weston | Sabah |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795746
Q02061 | LongSukang | Sarawak |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795747
A01268 | Tanjung Kekabu Dalam | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795748
4229Z | Kg Kelian Malau | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795749
K00803 | K012A_K00803OD_T3_KG_PERANGIN_GULAU | Northern | 4190P | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795750
7142R | Skim Mesej Kg Kinolosodon | Sabah |  | Maintain USP MOCN |  | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795751
Q01960 | Q139A_Q01960OD_T3_KGSEMADAMAWANG | Sarawak |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795752
S01223 | Kg Sinuba | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795753
Q00683 | Q144A_Q00683OD_RH_SAID | Sarawak |  | MOCN By Other Vendor | On Hold->Maintain USP MOCN->On Hold->MOCN By Other Vendor | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795754
A00575 | A040D_A00575OD_CB_MTD | Northern |  | Decomm |  | 2024 Additional | HW | GCI | 4.6 TSSR Approved |  | 2024-12-31 |  | 2025-02-26 |  | 2025-03-04 |  | 2025-03-07 | 2025-10-01 | CD//Zulakmar | 2025-03-11 | SQ202502100378 | DU00003795755 |  |  |  |  | 2025-01-24
S00218 | S112A_S00218OD_CB_KGWONOD | Sabah |  | Decomm |  | 2024 Q4 | SHA | Futong | 4.6 TSSR Approved |  | 2024-06-27 |  |  |  | 2024-07-04 |  | 2024-07-05 | 2024-10-31 | CD//Ray Amos | 2024-07-10 | Celcom Digi_RAN-Futong-Standard PR TSS-Sabah-20240619 | DU00003795756 |  |  |  |  | 2024-11-12
4060R | Kg Sukamari | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795757
7111Z | Kg Kinolosodon | Sabah |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795758
7015Z | T3_Kg Bambangan | Sabah |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795759
4114Z | Kg Sg Putan | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795760
Q01999 | SK Ulu Melipis (old Rumah Taboh Nanga Embuau Rumah Geruma) | Sarawak |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795761
Q02067 | Q124E_Q02067OD_CB_SERATAU2 | Sarawak |  | Decomm |  | 2025 Q1 | HW | Trintel | 4.6 TSSR Approved |  | 2025-02-14 |  | 2025-02-17 |  | 2025-03-18 |  | 2025-03-21 | 2025-05-02 | CD//John | 2025-03-24 | SQ202502260543-Trintel | DU00003795762 |  |  |  |  | 2025-08-26
K00609 | K008A_K00609OD_JLNBKTMALUT1 | Northern |  | Decomm |  | 2025 Q2 | HW | GTSB | 4.6 TSSR Approved |  | 2025-01-27 |  | 2025-02-10 |  | 2025-02-24 |  | 2025-02-26 |  | CD//Hazwan | 2025-02-28 | SQ202501060259 - GTSB | DU00003795763 |  |  |  |  | 2025-03-22
S01225 | Kg Kuia Karamuak | Sabah |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795764
Q01024 | Q141A_Q01024OD_CB_KGSERUYUK | Sarawak |  | Decomm |  | 2025 Q3 | AI | Trintel | 4.6 TSSR Approved |  | 2025-02-17 |  | 2025-03-05 |  | 2025-03-24 |  | 2025-04-14 | 2026-01-19 | CD//John | 2025-05-21 | SQ202502260543-Trintel/SQ202502270531-Trintel | DU00003795765 |  |  |  |  | 2025-05-27
9497A | Kg Semaru | Sarawak |  | Remote MOCN | On Hold->Maintain USP MOCN->Remote MOCN | 2025 Q1 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795766 | [8 empty] | Reuse Existing RRU | 0 | 0
K00694 | K010A_K00694OD_KUBURPANJANG | Northern |  | Decomm |  | 2025 Q2 | HW | CCSMY | 4.6 TSSR Approved |  | 2025-02-18 |  | 2025-04-08 |  | 2025-05-02 |  | 2025-05-06 | 2025-10-13 | E//Hazida | 2025-05-13 | SQ202501060201 - CCSMY | DU00003795767 |  |  |  |  | 2025-06-24
K00940 | T3E_0659_Kg KEDA Kubang Palas | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795768
Q01427 | Q123A_Q01427OD_MN_PELAJAU | Sarawak | 9269P | Swap | On Hold->Swap | 2025 Q3 | HW | Trintel | 4.6 TSSR Approved |  | 2025-03-20 | 2025-04-09 |  | 2025-09-03 |  | Under Approval | 2025-04-29 | 2025-05-02 | CD//John | 2025-04-30 | SQ202503030411-Trintel | DU00003795769 |  |  | 2025-09-09 | 2025-09-04 |  | Tower |  | 76 | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
4029Z | Kg Batu Seketul | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795770
S01682 | T3E_0221_ Berakan Maju Estate | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795771
K00664 | K008A_K00664OD_JLNDATAI1 | Northern |  | Decomm |  | 2024 Additional | HW | GTSB | 4.6 TSSR Approved |  | 2024-12-03 |  | 2024-12-04 |  | 2025-03-12 | To be Submitted | 2025-03-13 | 2026-03-04 | CD//Hazwan | 2025-03-13 | SQ202412090105 - GTSB | DU00003795772 |  | No FE Tx Part |  |  | 2025-01-24
Q00395 | Q124E_Q00395OD_BT27KCH | Sarawak |  | Decomm |  | 2025 Q1 | HW | Trintel | 4.6 TSSR Approved |  | 2025-02-18 |  | 2025-02-26 |  | 2025-03-10 |  | 2025-03-11 | 2025-05-02 | CD//John | 2025-03-12 | SQ202502260543-Trintel | DU00003795773 |  |  |  |  | 2025-07-03
7168Z | Skim Penempatan Getah Lagud Seberang | Sabah |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795774
9070R | KG BATU DANAU LIMBANG | Sarawak |  | Maintain USP MOCN(Dismantle Passive) | On Hold->Maintain USP MOCN(Dismantle Passive) | 2025 Q2 | AD | CCSMY | 4.6 TSSR Approved |  | 2025-07-21 |  | 2025-07-30 |  | 2025-09-19 |  | 2025-09-29 | 2025-10-31 | E//John | 2025-10-03 | SQ202506060165-CCSMY | DU00003795775 |  |  |  |  | 2025-10-22
Q01553 | Digi_Q123A_Q01553OD_MN_NANGAPELAGUS | Sarawak | 9474P | Swap |  | 2027 |  | Trintel | 2.1 Pending ETSS Submission - Subcon |  | 2025-03-17 |  |  |  |  | To be Submitted |  |  |  |  | SQ202503030411-Trintel | DU00003795776 | [8 empty] | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
9023Z | LUBAI TENGAH | Sarawak |  | MOCN Decomm |  | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795777
4012Z | Kg Charok Tok Pong | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795778
S01588 | S096A_S01588OD_CB_JLNKGINDARASON | Sabah |  | Decomm |  | 2025 Q3 | HW | GTSB | 4.6 TSSR Approved |  | 2025-02-06 |  | 2025-02-10 |  | 2025-03-13 | To be Submitted | 2025-03-14 |  | CD//Sharidah | 2025-03-17 | SQ202501020455 - GTSB | DU00003795779 |  | Missing FE info |  |  | 2025-09-05
S00158 | S104A_S00158OD_MATUPANG | Sabah |  | Site Out (Decomm) | Decomm->On Hold->Decomm->Site Out->Replacement, Site Out (Decomm) | 2024 Q4 |  | YPTT | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2025-07-01 |  | 2025-06-30 |  |  | To be Submitted |  |  |  |  | SQ202506160238 - YPTT | DU00003795780 |  |  |  |  | 2025-06-26
Q01951 | Kg Sadir | Sarawak |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795781
S00939 | S096A_S00939OD_T3_KGINDRASONLAUT | Sabah |  | MOCN By Other Vendor | On Hold->Maintain USP MOCN->On Hold->MOCN By Other Vendor | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795782
4005Z | Jalan Padang Sanai Sintok | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795783
K00615 | Jalan Dari Kuala Nerang Tasek Pedu | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795784
9229Z | KG SENAH RAYANG | Sarawak |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795785
K00419 | K012A_K00419OD_TELOITIMUR | Northern | 4122P | Swap | On Hold->Swap | 2025 Q3 | HW | GCI | 4.6 TSSR Approved |  | 2025-01-09 | 2025-02-17 |  | 2025-03-03 |  | Under Approval | 2025-04-11 | 2025-04-26 | CD//Zulakmar | 2025-04-25 | SQ202501030328 - GCI | DU00003795786 |  |  | 2025-07-06 | 2025-06-14 |  | Tower |  | 76 | Add R8852E S9000x4+R8854E S1800x4+R8894E M1821x5+R8862A S2601x3+R8854 S2600x1, Dismantle | 0 | 2
A00451 | A038A_A00451OD_TARCOLLEGEKAMPAR | Northern |  | Decomm |  | 2024 Additional | HW | CCSMY | 4.6 TSSR Approved |  | 2025-01-20 |  | 2025-01-23 |  | 2025-02-10 |  | 2025-02-18 | 2025-05-27 | CD//Hazwan | 2025-02-28 | SQ202502100375 | DU00003795787 |  | CD Hazwan reviewed but Hold wait for upg tssr ready first |  |  | 2025-03-20
S00220 | S112A_S00220OD_CB_WASAI | Sabah |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795788
9021R | Kg Keranji A | Sarawak |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795789
7082Z | MelapiSugut | Sabah |  | Maintain USP MOCN | On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795790
7120Z | Mendulong Long Pasia Road 1 | Sabah |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795791
Q01429 | Q123A_Q01429OD_MN_ULUYONG | Sarawak |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795792
S00047 | S089A_S00047OD_CB_MILE63 | Sabah |  | MOCN Decomm(Dismantle Passive) |  | 2024 Q4 | HW | GTSB | 4.6 TSSR Approved |  | 2025-07-20 |  | 2025-07-22 |  | 2025-07-23 |  | 2025-09-10 | 2026-01-20 | E//Hannah | 2025-09-17 | SQ202506100849 - GTSB / SQ202507010442 - GTSB | DU00003795793 |  |  |  |  | 2025-11-20
4063R | Kg Paya Terap | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795794
S01425 | S107A_S01425OD_T3_MENDULONGLONGPASIAROAD1 | Sabah |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795795
A00810 | A045A_A00810OD_MN_POSPIAH | Northern | 4225P | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795796
A00426 | A045A_A00426OD_CB_KGAYERKANGAR | Northern | 4541K | Swap |  | 2027 |  | CCSMY | 4.4 Pending TSSR Review - Design Team |  | 2025-03-10 | 2025-03-13 |  | 2025-03-19 |  | Under Approval |  |  |  |  | 1911CD-Northern-TSS-BOQ Template(new contract)_CCSMY_V2 | DU00003795797 | [6 empty] | TOWER | 80m | Add R8852E S9000x3+R8894E M1821x3+R8862A S2601x3, Dismantle | 0 | 0
A01211 | KM 24 Baling Gerik Highway | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795798
S01170 | S107A_S01170OD_SAMUR | Sabah | 7319K | Swap | Decomm->On Hold->Swap | 2025 Q2 | AD | Datasco | 4.6 TSSR Approved |  | 2025-01-21 |  |  | 2025-02-04 |  | Under Approval | 2025-02-05 | 2025-03-10 | CD//Sharidah | 2025-02-05 | SQ202504080101 - Datasco | DU00003795799 |  |  | 2025-02-13 | 2025-02-06 |  | Monopole |  | 25m | Add R8852E S9000x3+R8894E M1821x3+R8862A S2601x3, Dismantle | 0 | 0
4116Z | Kg Bkt Tunku | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795800
7096Z | KgInarad | Sabah |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795801
A00429 | A045A_A00429OD_CB_GADANG | Northern | 4544K | Swap |  | 2027 | AI | GTSB | 4.6 TSSR Approved |  | 2025-01-24 | 2025-02-03 |  | 2025-02-06 |  | Closed | 2025-02-06 | 2025-03-10 | CD//Zulakmar | 2025-02-26 | 1911CD-Northern-TSS-BOQ Template(new contract)_GTSB | DU00003795802 | [5 empty] | Tower |  | 75m | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
7043Z | T3_Kg Ranpik | Sabah |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795803
9018Z | KG BINJAI | Sarawak |  | MOCN Decomm |  | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795804
7083Z | Paitan Nangoh3 | Sabah |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795805
K00256 | K005C_K00256OD_CB_LEMBAHBUJANG | Northern | 4418K | Swap |  | 2027 |  | GTSB | 1.1 Pending Survey - Subcon | [6 empty] | To be Submitted |  |  |  |  | SQ202501030229 - GTSB | DU00003795806
4112Z | KG Kubang Lintah | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795807
9024R | KAMPUNG LUBOK PUNGGOR | Sarawak |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795808
4146H | TNY TELECOMMUNICATION | Northern |  | MOCN As-Is |  | 2027 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795809 | [8 empty] | Remain iMacro AAU | 0 | 0
4055Z | KGPONG | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795810
4027Z | Kg Lebai Saman | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795811
7211Z | Ladang Kawananan | Sabah |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795812
S00445 | S107A_S00445OD_CB_MESAPOL | Sabah | 7106P | Swap | On Hold->Swap | 2025 Q2 | SM | DATASCO | 4.6 TSSR Approved |  | 2025-01-15 | 2025-03-04 |  | 2025-03-06 |  | Rectificating | 2025-03-11 | 2025-03-17 | CD//Sharidah | 2025-03-14 | SQ202501020331 - Datasco | DU00003795813 |  |  | 2025-07-06 | 2025-03-21 |  | Tower |  | 60m | Add R8852E S9000x3+R8854E S1800x3+R8894E M1821x4, Dismantle | 0 | 2
Q00167 | Q139A_Q00167OD_CB_KGTAEE | Sarawak | 9284P | Swap | Maintain USP MOCN->Swap | 2024 Q4 | HW | Trintel | 4.6 TSSR Approved |  | 2025-04-16 | 2025-04-21 |  | 2025-04-25 |  | Under Approval | 2025-04-28 | 2025-04-29 | CD//John | 2025-04-28 | SQ202505020084-Trintel | DU00003795814 |  |  | 2025-09-18 | 2025-09-10 |  | Tower |  | 76 | Add R8852E S9000x3+R8894E M1821x4, Dismantle | 0 | 3
S01280 | Mentalik | Sabah |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795815
S01733 | T3E_0234_ Sawit Tongod Plantation | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795816
A00431 | A045A_A00431OD_CB_CHERUAN | Northern | 4546K | Swap |  | 2027 |  | CCSMY | 4.4 Pending TSSR Review - Design Team |  | 2025-02-07 | 2025-03-05 |  | 2025-04-10 |  | Under Approval |  |  |  |  | SQ202411290550 - CCSMY | DU00003795817 | [5 empty] | Tower | TOWER | 75M | Add R8852E S9000 x3+R8894E M1821x3,Dismantle | 0 | 0
Q00115 | Q139A_Q00115OD_TEBAKANG | Sarawak | 9286K | Swap |  | 2027 |  | Magicell | 4.4 Pending TSSR Review - Design Team |  | 2025-01-27 | 2025-02-26 |  | 2025-04-20 |  | Under Approval |  |  |  |  | SQ202501070146-Magicell | DU00003795818 | [5 empty] | Tower |  | 46m | Add R8852E S9000x3+R9264M M1821x3, Dismantle | 0 | 0
S00637 | S096A_S00637OD_KGBATULAYAR | Sabah |  | Decomm |  | 2025 Q3 |  | GTSB | 15.3 Decomm Done without TSSR | Pending CR Boat | [5 empty] | To be Submitted |  |  |  |  | SQ202501020455 - GTSB | DU00003795819 |  |  |  |  | 2025-11-30
S00274 | S088A_S00274OD_KOTAKLIAS | Sabah |  | Decomm | On Hold->Decomm | 2025 Q2 | NA | Datasco | 4.6 TSSR Approved |  | 2025-03-13 |  | 2025-04-10 |  | 2025-04-16 |  | 2025-04-28 | 2025-10-13 | CD//Sharidah | 2025-09-26 | SQ202504100595 - Datasco | DU00003795820 |  |  |  |  | 2025-06-25
K00954 | Kg Carok Tenang | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795821
S01721 | kpg mendulong | Sabah |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795822
4737A | HM Aerospace | Northern |  | Modernization |  | 2025 Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2025-01-25 | 2025-02-10 |  | 2025-02-21 |  | Rectificating | 2025-02-24 | 2025-02-27 | E//Hazida | 2025-02-27 | SQ202501030229 - GTSB | DU00003795823 |  |  | 2025-03-16 | 2025-03-10 |  |  |  | 4M | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8882 S1800B(B6B)x2+R8862A S1800(B6A)x1 | 0 | 0
4205H | Panorama Cable Car Middle Station | Northern |  | MOCN As-Is |  | 2025 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795824 | [8 empty] | Remain iMacro AAU | 0 | 0
4230Z | Pulau Belayar | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795825
A01207 | T3_0623_RPS DALA | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795826
K01118 | Kg Kuala Cham | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795827
S01728 | Kg Gumisi Laut | Sabah |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795828
7033Z | T3_Kg Singgahmata | Sabah |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795829
4007Z | Kg Pinang Gubir Pedu Kg Lahat | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795830
7028Z | T3_Kg Tongodon | Sabah |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795831
9025Z | KUALABRIWAN | Sarawak |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795832
7050R | BORNEO GOLF AND COUNTRY CLUB | Sabah |  | Maintain USP MOCN(Dismantle Passive) | On Hold->Maintain USP MOCN(Dismantle Passive) | 2025 Q2 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2025-07-17 |  | 2025-07-18 |  | 2025-07-22 |  | 2025-08-06 | 2025-09-20 | E//Hannah | 2025-09-16 | SQ202508130660 - Seri Pancar | DU00003795833 |  |  |  |  | 2025-09-28
7113Z | Kg Sg Gerama | Sabah |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795834
Q01012 | Q139A_Q01012OD_T3_KGJAYARIAG | Sarawak |  | Decomm |  | 2025 Q3 | NA | Trintel | 4.6 TSSR Approved |  | 2025-02-14 |  | 2025-05-09 |  | 2025-05-13 |  | 2025-05-21 | 2025-10-28 | E//John | 2025-05-27 | SQ202502260543-Trintel/SQ202502270531-Trintel | DU00003795835 |  |  |  |  | 2025-07-24
4736B | FELDA Bersia | Northern |  | Modernization |  | 2024 Additional | AD | CCSMY | 4.6 TSSR Approved |  | 2024-12-04 | 2024-12-18 |  | 2024-12-19 |  | Under Approval | 2024-12-22 | 2024-12-24 | E//Hazida | 2024-12-23 | 1911CD-Northern-TSS-BOQ Template(new contract)_CCSMY_V2 | DU00003795836 |  |  | 2025-02-06 | 2025-02-06 |  | Tower |  | 60m | Add R8852E S9000 x1+R8894E M1821x3+R8862A S2601x1, Dismantle R8862A S1800(B6A)x2 | 0 | 0
K00932 | Kg Lengkuas | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795837
9177R | KG MONGKOS | Sarawak |  | MOCN Decomm |  | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795838
4002Z | Kg Telok Sera | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795839
9139R | KGSEBINTIN | Sarawak |  | MOCN Decomm(Dismantle Passive) |  | 2024 Q4 | HW | Magicell | 4.6 TSSR Approved |  | 2025-07-02 |  | 2025-07-17 |  | 2025-07-17 |  | 2025-08-07 | 2026-01-20 | E//Hannah | 2025-08-11 | SQ202506110081-Magicell/SQ202507140221-Magicell | DU00003795840 |  |  |  |  | 2025-09-25
A01160 | KG BATU HAMPAR (T3_0364) | Northern |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795841
K00068 | K008A_K00068OD_LKW_LAGOON | Northern | 4397K | Swap |  | 2025 Q2 | HW | GTSB | 4.6 TSSR Approved |  | 2025-03-12 | 2025-03-20 |  | 2025-03-24 |  | Under Approval | 2025-03-25 | 2025-05-19 | CD//Zulakmar | 2025-04-10 | SQ202501030229 - GTSB | DU00003795842 |  |  | 2025-05-04 | 2025-04-23 |  | In-Building System |  | 6M | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
4046Z | KGSUMPITAN | Northern |  | MOCN Decomm |  | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795843
9006Z | SMK BALEH | Sarawak |  | Decomm, MOCN By Other Vendor | MOCN Decomm->On Hold->Decomm | 2024 Q4 |  | YPTT | 14.1 TSSR Not Required (Decomm by CD) |  | 2025-11-12 |  |  |  |  | To be Submitted | [5 empty] | DU00003795844 |  |  |  |  | 2025-11-12
S01273 | Pulau Jambongan | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795845
7039Z | T3_Kg Buis | Sabah |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795846
K00631 | Durian Burung Kg Peraduan Songkeh | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795847
7031R | Kg Tepoh | Sabah |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795848
7119Z | Mendulong Long Pasia Road 2 | Sabah |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795849
S01770 | FC1_120 Kg Indarason Laut | Sabah |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795850
4032Z | Kg Bukit Tegur | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795851
Q00789 | Q124E_Q00789OD_KGSIRA | Sarawak |  | Decomm | On Hold->Decomm | 2025 | AD | Magicell | 4.6 TSSR Approved |  | 2025-04-09 |  | 2025-04-08 |  | 2025-05-13 |  | 2025-05-14 |  | E//John | 2025-05-15 | SQ202503170852-Magicell | DU00003795852 |  |  |  |  | 2025-09-09
A01209 | T3E_0044_KM 34 Baling Gerik Highway | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795853
S01269 | Lingkabau | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795854
2598A15 | pBTS Kompleks PAS Simpang Ampat | Northern |  | Modernization | On Hold->Modernization | 2026 | HW | GCI | 4.6 TSSR Approved |  | 2025-12-03 | 2025-12-08 |  | 2025-12-11 |  | Under Approval | 2025-12-16 | 2025-12-29 |  | 2025-12-19 | SQ202511050343 | DU00003795855 |  |  | 2026-03-17 | 2026-03-17 |  | Tower |  | 24m | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8882 S1800(B)x2+R8862A S1800(B6A)x1+R8862A S2100(A6A)x3
A00817 | A045A_A00817OD_MN_LEPANGNENERING | Northern | 4142P | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795856
S01416 | S107A_S01416OD_T3_KGLONGMIO | Sabah |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795857
4207Z | Kg Kedundong | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795858
K00662 | K008A_K00662OD_MATAAYERLKW | Northern |  | Decomm |  | 2025 Q2 | HW | GTSB | 4.6 TSSR Approved |  | 2025-01-27 |  | 2025-02-10 |  | 2025-03-05 |  | 2025-03-07 |  | CD//Zulakmar | 2025-03-11 | SQ202501060259 - GTSB | DU00003795859 |  |  |  |  | 2025-04-30
3165B7 | pBTS Ulu Melaka | Northern |  | Remote MOCN | On Hold->Remote MOCN | 2025 Q2 |  |  | 3.4 SOW/Solution On Hold | [6 empty] | To be Submitted | [5 empty] | DU00003795860 | [8 empty] | Reuse Existing RRU | 0 | 0
K00427 | K008A_K00427OD_TGLEMBONG | Northern |  | Decomm |  | 2025 Q2 | HW | GTSB | 4.6 TSSR Approved |  | 2025-01-27 |  | 2025-02-04 |  | 2025-02-24 |  | 2025-02-26 |  | CD//Hazwan | 2025-02-28 | SQ202501060259 - GTSB | DU00003795861 |  |  |  |  | 2025-04-27
7116Z | Long Pasia | Sabah |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795862
9004Z | NANGA MUJUNG | Sarawak |  | Decomm, MOCN By Other Vendor | MOCN Decomm->On Hold->Decomm | 2024 Q4 |  | Trintel | 14.1 TSSR Not Required (Decomm by CD) |  | 2025-11-12 |  |  |  |  | To be Submitted | [5 empty] | DU00003795863 |  |  |  |  | 2025-11-12
4181Z | KG PERAGIN_GULAU (Pos Gedong) | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795864
K00637 | Kg Bukit Tegur | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795865
K00632 | Kg Lebai Saman | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795866
7026Z | T3_Genting Permai estate | Sabah |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795867
K00952 | Kg Bukit Tunku | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795868
9005Z | ULU YONG | Sarawak |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795869
9083R | Kg Sadir | Sarawak |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795870
S01279 | Kg Padas Damit | Sabah |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795871
A00804 | A045A_A00804OD_MN_FELDAPAPULUT | Northern | 4223P | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795872
4178Z | KAMPUNG LUBUK RAMBAI (Pos Keding) | Northern |  | MOCN Decomm |  | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795873
9027Z | ULU MERAPOK | Sarawak |  | MOCN Decomm |  | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795874
4018Z | KGPADANG | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795875
9530B | Kampung Seruyuk | Sarawak |  | Modernization |  | 2025 Q3 | AI | Magicell | 4.6 TSSR Approved |  | 2025-02-11 | 2025-02-19 |  | 2025-02-28 |  | Closed | 2025-04-07 | 2025-05-21 | E//Hannah | 2025-04-21 | SQ202501070146-Magicell | DU00003795876 | Remarks: Solution TSSR/BOM Changed |  | 2025-05-23 | 2025-05-20 |  | Tower |  | 61m | Add R8862A S2601x3 | 0 | 0
A01061 | A038A_A01061OD_CB_PKNGOPENG | Northern |  | Decomm |  | 2024 Additional | HW | GCI | 4.6 TSSR Approved |  | 2025-01-21 |  | 2025-02-25 |  | 2025-03-04 |  | 2025-03-07 | 2025-10-01 | CD//Zulakmar | 2025-03-11 | SQ202502100378 | DU00003795877 |  |  |  |  | 2025-01-24
7170Z | Maxland Bridge | Sabah |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795878
A01280 | KG BEKUAI (T3_0371) | Northern |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795879
S00278 | S095A_S00278OD_CB_SAWANGAN | Sabah |  | Maintain USP MOCN |  | 2025 Q1 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795880
S01426 | S088A_S01426OD_T3_KGBINTUKA | Sabah | 7130P | Swap | On Hold->Swap | 2025 Q1 | AD | YPTT | 4.6 TSSR Approved |  | 2025-01-08 | 2025-02-19 |  | 2025-02-24 |  | Under Approval | 2025-02-25 | 2025-03-09 | CD//Sharidah | 2025-02-26 | SQ202501020336 - YPTT | DU00003795881 |  |  | 2025-07-06 | 2025-03-25 |  | Tower |  | 76 | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
K00305_IBC | K008A_K00305OD_LANGKAWISERVICECTR | Northern | 4167K | Swap |  | 2025 | HW | GTSB | 4.6 TSSR Approved |  | 2025-03-17 | 2025-03-20 |  | 2025-03-24 |  | Under Approval | 2025-03-25 | 2025-03-26 | CD//Zulakmar | 2025-03-26 | SQ202501030229 - GTSB | DU00003795882 |  |  | 2025-04-30 | 2025-04-10 |  | In-Building System |  | NA | Add R8862A S1800x1+R8862A S2100x1, Dismantle | 0 | 0
4467B | Tasik Banding (Maxis) | Northern |  | Modernization |  | 2024 Additional | AI | GCI | 4.6 TSSR Approved |  | 2024-12-15 | 2024-12-17 |  | 2024-12-24 |  | Closed | 2025-01-08 | 2025-02-07 | E//Hazida | 2025-01-14 | SQ202411290568 - GCI | DU00003795883 |  |  | 2025-02-06 | 2025-02-06 |  | Tower |  | 60m | Add R8852E S9000x1+R8894E M1821x1 | 0 | 0
Q02025 | Rumah Sait Nanga Puro (old Rumah Kupa Rumah mamat Rumah Jaing) | Sarawak |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795884
K00053 | K005D_K00053OD_CB_JENIANG | Northern | 4393K | Swap | Swap | 2026 | AI | GCI | 1.1 Pending Survey - Subcon | [6 empty] | To be Submitted |  |  |  |  | SQ202501030261 - GCI | DU00003795885 | [8 empty] | Add R8862A S9000x3+R8894E M1821x3+R8862A S2601x3, Dismantle
4119Z | Kg Landai | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795886
7144Z | KG Kaindangan | Sabah |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795887
9228Z | KG TEMONG PUTAH | Sarawak |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795888
4117Z | Kg Sg Mas | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795889
7017R | Kg Bangau Bangau | Sabah |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795890
K00635 | T3_0246_Kg Mahawangsa | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795891
S01291 | Kg Katubu | Sabah |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795892
S01736 | KgInarad | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795893
9255Z | Kpg Tegarai | Sarawak |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795894
9009Z | NANGA SERIAN | Sarawak |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795895
K00618 | T3_0237_Jln Kg Pinang Gubir Pedu | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795896
K00663 | K008A_K00663OD_KEDALKW | Northern |  | Decomm |  | 2025 Q2 | HW | GTSB | 4.6 TSSR Approved |  | 2025-01-27 |  | 2025-02-04 |  | 2025-02-20 |  | 2025-02-21 |  | CD//Hazwan | 2025-02-28 | SQ202501060259 - GTSB | DU00003795897 |  | CD Hazwan reviewed but Hold wait for upg tssr ready first |  |  | 2025-04-28
7040R | KG SAUBIL | Sabah |  | MOCN Decomm(Dismantle Passive) |  | 2025 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2025-07-26 |  | 2025-07-31 |  | 2025-08-01 |  | 2025-09-09 | 2025-09-20 | E//Hannah | 2025-09-17 | SQ202506100836 - YPTT / SQ202507010450 - YPTT | DU00003795898 |  |  |  |  | 2025-09-19
K00428 | K012A_K00428OD_KGKROMAN | Northern | 4443K | Swap | Swap | 2027 | HW | CCSMY | 4.6 TSSR Approved |  | 2025-01-12 | 2025-01-16 |  | 2025-02-14 |  | Under Approval | 2025-11-14 | 2025-12-29 | E//Hazida | 2025-11-24 | SQ202501030037 - CCSMY | DU00003795899 | [5 empty] | Tower |  | 60M | Add R8852E S9000x3+R8894E M1821x3,Dismantle
S00386 | S104A_S00386OD_CB_KGTOUPOS | Sabah | 7089P | Swap | On Hold->Swap | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-01-10 | 2025-01-14 |  | 2025-01-22 |  | Under Approval | 2025-01-23 | 2025-02-18 | E//Sharidah | 2025-02-04 | SQ202501020392 - Futong | DU00003795900 |  |  | 2025-09-26 | 2025-09-23 |  | Tower |  | 65m | Add R8852E S9000x6+R8854E S1800x3+R9264M M1821x4, Dismantle | 0 | 3
4362H | 99 Speedmart KH Tmn Suria | Northern |  | MOCN As-Is |  | 2027 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795901 | [8 empty] | Remain iMacro AAU | 0 | 0
K00334 | K009A_K00334OD_LUBUKPERUN | Northern | 4425K | Swap |  | 131 single site mocn | SH | GCI | 4.6 TSSR Approved |  | 2024-08-13 | 2024-08-27 |  | 2024-09-02 |  | Under Approval | 2024-09-03 | 2024-09-05 | CD//Hazwan | 2024-09-05 | 0809CD-Northern-GCI-BOQ Template(new contract) | DU00003795902 |  |  | 2024-11-06 | 2024-10-29 |  | Tower |  | 60 | Add R8862A S9000 x3+R8894E M1821 x1+R8862A S2601 x3+A9732 M1821 x2,Dismantle | 13 | 0
7014Z | T3_Kg Katubu | Sabah |  | Maintain USP MOCN |  | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795903
7027R | Kg Bamban | Sabah |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795904
S01718 | T3_0693_Kg Tanjung Nipis 1 | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795905
A00414 | A045A_A00414OD_CB_SELATPAGAR | Northern |  | Decomm |  | 2025 Q3 | NA | GCI | 4.6 TSSR Approved |  | 2025-04-17 |  | 2025-04-24 |  | 2025-04-28 | To be Submitted | 2025-05-05 |  | CD//Zulakmar | 2025-05-08 | SQ202501060244 - GCI | DU00003795906 |  | Missing TX mw part (NE/FE) |  |  | 2025-06-30
K00938 | T3E_0654_Kg Dalam Sg Karkap | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795907
7476B | Segaliud Lokan | Sabah |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795908
4091Z | T3E_0631_KgPahitDalam | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795909
4732B | Kuak | Northern |  | Modernization |  | 2025 Q3 | SM | PERNEC | 4.6 TSSR Approved |  | 2025-01-21 | 2025-02-04 |  | 2025-02-07 |  | Under Approval | 2025-02-27 | 2025-02-28 | E//Hazida | 2025-02-28 | SQ202501030191 - PERNEC | DU00003795910 |  |  | 2025-03-29 | 2025-03-19 |  | Guide mast |  | 61m | Add R8894E M1821x1 | 0 | 1
4469B | Padang Grus | Northern |  | Remote MOCN | On hold->Modernization->Remote MOCN | 2025 Q3 | AI | CCSMY | 14.3 Drop (Done Survey + TSSR) |  | 2025-01-16 | 2025-01-27 |  | 2025-02-14 |  | Closed | 2025-03-26 |  | E//Hazida |  | SQ202501030318 - CCSMY | DU00003795911 | [5 empty] | Tower |  | 60M | Reuse Existing RRU | 0 | 0
9968A | Seratau REL | Sarawak |  | Modernization |  | 2025 Q1 | HW | Magicell | 4.6 TSSR Approved |  | 2025-02-11 | 2025-02-17 |  | 2025-02-28 |  | Under Approval | 2025-03-06 | 2025-03-26 | E//Hannah | 2025-03-26 | SQ202501070146-Magicell | DU00003795912 |  |  | 2025-04-24 | 2025-04-21 |  | Tower |  | 60m | Add R8852E S9000x4+R9264M M1821x4, Dismantle R8862A S1800(B6A)x4+R8862A S2100(A6A)x4 | 0 | 0
Q00616 | Q141A_Q00616OD_CB_TMSEBANGAN | Sarawak | 9270P | Swap | On Hold->Swap | 2025 Q3 | AD | Magicell | 4.6 TSSR Approved |  | 2025-02-13 | 2025-02-17 |  | 2025-02-26 |  | Under Approval | 2025-02-28 | 2025-05-21 | CD//John | 2025-05-07 | SQ202501070146-Magicell | DU00003795913 |  |  | 2025-07-06 | 2025-06-27 |  | Tower |  | 30m | Add R8852E S9000x3+R8854E S1800x3+R8894E M1821x3, Dismantle | 0 | 0
4120Z | Kg Bkt Jagung | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795914
9278A | Tmn Cahaya Limbang | Sarawak |  | Remote MOCN | On Hold->Maintain USP MOCN->Remote MOCN | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795915 | [8 empty] | Reuse Existing RRU | 0 | 0
S00723 | S112A_S00723OD_PEKANTELUPID | Sabah |  | Site Out (Decomm) | On Hold-> Site Out->Site Out (Decomm) | 2024 Q4 |  | YPTT | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2025-06-21 |  | 2025-06-26 | [7 empty] | SQ202506160238 - YPTT | DU00003795916 |  |  |  |  | 2025-04-29
S01260 | Kg Derumderum | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795917
7112R | SUNGAISUNGAI | Sabah |  | MOCN Decomm(Dismantle Passive) | On Hold->MOCN Decomm | 2024 Q4 | AD | NR services | 4.6 TSSR Approved |  | 2025-10-07 |  | 2025-10-01 |  | 2025-10-07 |  | 2025-10-23 | 2025-10-31 | E//Hannah | 2025-10-29 |  | DU00003795918 |  |  |  |  | 2025-11-20
7053Z | T3_Kg Melapi | Sabah |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795919
9256A | Kerait | Sarawak |  | Decomm, MOCN By Other Vendor | On Hold->Decomm->On Hold->Decomm | 2025 | HW | Magicell | 4.6 TSSR Approved |  | 2025-04-02 |  | 2025-04-04 |  | 2025-04-15 |  | 2025-04-16 | 2025-10-13 | E//Hannah | 2025-05-23 | SQ202503170852-Magicell | DU00003795920 |  |  |  |  | 2025-11-24
K00098 | K009A_K00098OD_LUBOKMERBAU | Northern | 4156P | Swap | On Hold->Swap | 2025 Q3 | HW | GCI | 4.6 TSSR Approved |  | 2025-01-09 | 2025-02-18 |  | 2025-03-06 |  | Under Approval | 2025-04-11 | 2025-05-19 | CD//Zulakmar | 2025-04-22 | SQ202501030328 - GCI | DU00003795921 |  |  | 2025-07-06 | 2025-06-23 |  | Tower |  | 60m | Add R8852E S9000x3+R8894E M1821x4+R8862A S2601x2+R8854 S2600x1, Dismantle | 0 | 3
S01365 | RS50266_9_0_KGPURUN | Sabah | 7299K | Swap |  | 2027 |  | Seri Pancar | 2.1 Pending ETSS Submission - Subcon |  | 2026-01-29 | 2026-05-11 |  |  |  | To be Submitted |  |  |  |  | SQ202601220834 - Seri Pancar | DU00003795922 | [5 empty] | Tower |  | 30m | Add R9264M M1821x3, Dismantle R8852E S1800(A8A)x3 | 0 | 0
Q01406 | Q125A_Q01406OD_SMKLAWAS | Sarawak | 9335K | Swap | Swap | 2026 |  | Redtone | 1.1 Pending Survey - Subcon | [6 empty] | To be Submitted |  |  |  |  | SQ202605110147 - Redtone | DU00003795923 | [8 empty] | Add R8862A S9000x3+R8894E M1821x3+R8862A S2601x3, Dismantle
A01003 | A038A_A01003IB_TESCO_KAMPAR | Northern | 4600K | Swap |  | 2024 Additional | AD | CCSMY | 4.6 TSSR Approved |  | 2024-12-10 | 2024-12-17 |  | 2024-12-19 |  | Under Approval | 2024-12-19 | 2025-02-18 | CD//Sofiah | 2025-02-18 | 1911CD-Northern-TSS-BOQ Template(new contract)_CCSMY_V2 | DU00003795924 |  |  | 2025-01-18 | 2025-01-18 |  | Portables BTS |  |  | Add R8862A S1800 x2+R8862A S2100 x2+ R8862A S2601 x2, Dismantle | 0 | 0
7021R | Kg Tilis | Sabah |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795925
7437B | Lungmanis | Sabah |  | Modernization | On hold->Modernization | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-01-15 | 2025-01-17 |  | 2025-01-22 |  | Under Approval | 2025-01-23 | 2025-02-18 | E//Yanie | 2025-02-18 | SQ202501020392 - Futong | DU00003795926 |  |  | 2025-03-08 | 2025-02-21 |  | Tower |  | 60m | Reuse Existing RRU | 0 | 0
A00430 | A045A_A00430OD_CB_TENOK | Northern | 4545K | Swap |  | 2027 |  | GCI | 1.1 Pending Survey - Subcon | [6 empty] | To be Submitted |  |  |  |  | 1911CD-Northern-TSS-BOQ Template(new contract)_GCI | DU00003795927 | [6 empty] | TOWER |  | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
9257Z | Buduk Bui | Sarawak |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795928
4092Z | T3E_0632_KgTemin | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795929
S00947 | S096A_S00947OD_T3_KGTELUTU | Sabah |  | Maintain USP MOCN |  | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795930
K00648 | Kg Charok Tok Pong | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795931
9001Z | NANGA IBAU | Sarawak |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795932
9590C | Jalan Sundar | Sarawak |  | Modernization |  | 2027 |  |  | 2.1 Pending ETSS Submission - Subcon |  | 2025-10-25 |  |  |  |  | To be Submitted | [5 empty] | DU00003795933 | [8 empty] | Reuse Existing RRU
S01417 | S088A_S01417OD_T3_KGSGGERAMA | Sabah | 7158P | Swap | Maintain USP MOCN->Swap | 2025 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2025-10-13 | 2025-10-13 |  | 2025-10-15 |  | Rectificating | 2025-10-16 | 2025-10-27 | E//Hannah | 2025-10-23 | SQ202510090551 - Seri Pancar | DU00003795934 |  |  | 2025-12-22 | 2025-12-17 |  | Tower |  | 76m | Add R8852E S9000x6+R9264M M1821 x4, Dismantle |  | 3
7057R | KG BANTADOK | Sabah |  | Maintain USP MOCN(Dismantle Passive) |  | 2025 Q2 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2025-07-17 |  | 2025-07-23 |  | 2025-07-23 |  | 2025-08-06 | 2025-09-20 | E//Hannah | 2025-09-16 | SQ202508130660 - Seri Pancar | DU00003795935 |  |  |  |  | 2025-09-26
Q02058 | Kg Gadong | Sarawak |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795936
S01227 | Kg Wonod | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795937
K00928 | Kg Belukar | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795938
9122R | KAMPUNG SIJAJAG PLAMAN | Sarawak |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795939
7114R | HILL2000 | Sabah |  | MOCN Decomm(Dismantle Passive) | On Hold->MOCN Decomm | 2024 Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2025-07-21 |  | 2025-07-29 |  | 2025-07-24 |  | 2025-09-10 | 2025-09-20 | E//Hannah | 2025-09-16 | SQ202506100849 - GTSB / SQ202507010442 - GTSB | DU00003795940 |  |  |  |  | 2025-09-26
S00440 | S089A_S00440OD_CB_MILE70 | Sabah |  | Maintain USP MOCN(Dismantle Passive) | On Hold->Maintain USP MOCN(Dismantle Passive) | 2026 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2025-07-22 |  | 2025-07-22 |  | 2025-07-23 |  | 2025-08-06 | 2025-09-20 | E//Hannah | 2025-09-16 | SQ202508130660 - Seri Pancar | DU00003795941 |  |  |  |  | 2025-11-20
S01294 | Pangi | Sabah |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795942
9244A | Palah | Sarawak |  | Modernization |  | 2027 | AI | Trintel | 14.0 TSSR Not Required (Reuse Existing BBU/RRU) |  | 2025-11-17 | 2025-11-18 |  | 2025-11-19 |  | Under Approval |  |  |  |  | SQ202511040097 - Trintel | DU00003795943 | [5 empty] | Tower |  | 45 | Reuse Existing RRU
7580B | Kg Miluru | Sabah |  | Modernization |  | 2024 Q4 | MS | Futong | 4.6 TSSR Approved |  | 2024-07-09 | 2024-07-18 |  | 2024-07-23 |  | Under Approval | 2024-08-15 | 2024-08-16 | E//Hannah | 2024-08-16 | Celcom Digi_RAN-Futong-Standard PR TSS-Sabah-20240619 | DU00003795944 |  |  | 2024-08-29 | 2024-08-26 |  | Tower |  | 65 | Add R8852E S9000 x1+R8894E M1821 x1,Dismantle | 0 | 0
S01730 | maxland bridge | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795945
S01228 | Kuamut | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795946
7034Z | T3_Kg Imbak | Sabah |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795947
9024Z | LONG SEBANGANG | Sarawak |  | MOCN Decomm |  | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795948
S01727 | Kg Maluyan Ulu | Sabah |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795949
4148Z | KM 39 Baling Gerik Highway KM37 Baling Gerik Highway | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795950
S00390 | S089A_S00390OD_PAITAN | Sabah |  | Decomm |  | 2024 Q4 | SHA | Futong | 4.6 TSSR Approved |  | 2024-07-04 |  | 2024-07-14 |  | 2024-07-16 |  | 2024-07-17 | 2024-08-29 | CD//Ray Amos | 2024-07-18 | Celcom Digi_RAN-Futong-Standard PR TSS-Sabah-20240619 | DU00003795951 |  |  |  |  | 2024-11-08
7049Z | T3_Kg Asuan | Sabah |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795952
Q00152 | Q139A_Q00152OD_CB_TEBEDU | Sarawak |  | MOCN By Other Vendor | On Hold->Maintain USP MOCN->On Hold->MOCN By Other Vendor | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795953
Q01964 | Q139A_Q01964OD_T3_KGLANCHANG | Sarawak | 9271P | Swap | On Hold->Swap | 2025 Q3 | AI | Magicell | 4.6 TSSR Approved |  | 2025-02-01 | 2025-02-07 |  | 2025-02-27 |  | Closed | 2025-03-17 | 2025-05-21 | CD//John | 2025-05-13 | SQ202501070146-Magicell | DU00003795954 |  |  | 2025-07-06 | 2025-06-09 |  | Tower |  | 76 | Add R8852E S9000x3+R8854E S1800x3+R8894E M1821x3, Dismantle | 0 | 0
K00620 | T3_0241_Kg Watt Paya Mat Insun | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795955
7076B | Kg Nobusong | Sabah |  | Decomm | On Hold->Decomm->On Hold->Decomm | 2025 | AD | GTSB | 4.6 TSSR Approved |  | 2025-04-22 |  | 2025-05-14 |  | 2025-06-16 |  | 2025-06-19 | 2025-10-13 | E//Hannah | 2025-09-25 | SQ202504100576 - GTSB | DU00003795956 |  |  |  |  | 2025-11-30
4042Z | KGBENG | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795957
S00938 | S096A_S00938OD_T3_KGSAUBIL | Sabah | 7131P | Swap | On Hold->Swap | 2025 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2025-02-25 | 2025-03-19 |  | 2025-03-24 |  | Under Approval | 2025-03-24 | 2025-05-21 | CD//Sharidah | 2025-04-08 | SQ202501020343 - GTSB | DU00003795958 |  |  | 2025-07-10 | 2025-07-02 |  | Tower |  | 60 | Add R8852E S9000x3+R8894E M1821x6, Dismantle | 0 | 0
7013Z | T3_Mentalik | Sabah |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795959
Q00905 | Q141A_Q00905OD_CB_KGRUAN | Sarawak |  | Maintain USP MOCN |  | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795960
A01120 | A045A_A01120OD_CB_KG_PLANG_GERIK | Northern | 4256P | Swap |  | 2024 Additional | SHA | CCSMY | 4.6 TSSR Approved |  | 2024-12-04 | 2024-12-16 |  | 2024-12-24 |  | Under Approval | 2024-12-27 | 2024-12-27 | CD//Zulakmar | 2024-12-27 | 1911CD-Northern-TSS-BOQ Template(new contract)_CCSMY_V2 | DU00003795961 |  |  | 2025-01-19 | 2025-01-19 |  | Tower |  | 61 | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
K00642 | Kg Perangkap | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795962
S01414 | S100A_S01414OD_T3_KGGADONG | Sabah | 7132P | Swap | On Hold->Swap | 2025 Q2 | SM | YPTT | 4.6 TSSR Approved |  | 2025-01-05 | 2025-01-13 |  | 2025-01-15 |  | Rectificating | 2025-03-11 | 2025-03-17 | CD//Sharidah | 2025-03-14 | SQ202501020336 - YPTT | DU00003795963 |  |  | 2025-05-13 | 2025-05-08 |  | Tower |  | 76 | Add R8852E S9000x3+R8894E M1821x4, Dismantle | 0 | 2
7051Z | T3_Kg Basai Baru | Sabah |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795964
Q00399 | Q141A_Q00399OD_BKTSEMUPOH | Sarawak |  | Decomm |  | 2025 Q3 | HW | Trintel | 4.6 TSSR Approved |  | 2025-02-18 |  | 2025-02-27 |  | 2025-03-10 | To be Submitted | 2025-03-11 |  | CD//John | 2025-03-12 | SQ202502260543-Trintel | DU00003795965 |  |  |  |  | 2025-10-29
7035Z | T3_Kg Napagang | Sabah |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795966
4090Z | T3E_0630_KgTalungLuat | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795967
9577B | Kampung Sri Arjuna | Sarawak |  | Modernization |  | 2025 Q1 | AD | Magicell | 4.6 TSSR Approved |  | 2025-02-08 | 2025-02-14 |  | 2025-02-25 |  | Under Approval | 2025-02-26 | 2025-04-09 | E//Hannah | 2025-03-10 | SQ202501070146-Magicell | DU00003795968 |  |  | 2025-04-04 | 2025-03-25 |  | Monopole |  | 30 | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3 | 0 | 0
9199Z | KG SEBEMBAN | Sarawak |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795969
S01281 | Kg Paringon | Sabah |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795970
K01030 | Kg Sungai Siput | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795971
4073Z | KGPDGBERLIKU | Northern |  | MOCN Decomm |  | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795972
K00774 | K009A_K00774OD_CB_YB_DURIANBURUNG | Northern | 4465K | Swap |  | 2027 |  | GTSB | 3.1 Pending RF Solution - RF Team |  | 2025-11-19 | 2026-03-26 |  |  |  | To be Submitted |  |  |  |  | SQ202511050350 | DU00003795973 | [5 empty] | Tower |  | 60m
7139R | Skim Mesej Ulu Patian | Sabah |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795974
4180Z | KG TANDOP (Kg Sg Bot Dalam) | Northern |  | MOCN Decomm |  | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795975
A00805 | A045A_A00805OD_MN_KGBENG | Northern | 4224P | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795976
K00616 | Jalan Dari Padang Sanai Sintok PadangTerap Kedah | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795977
4155C | USP_Datai 2 | Northern |  | Modernization |  | 2024 Additional | SHA | GTSB | 4.6 TSSR Approved |  | 2024-12-03 | 2024-12-16 |  | 2024-12-17 |  | Under Approval | 2024-12-18 | 2024-12-19 | E//Hazida | 2024-12-19 | SQ202411290524 - GTSB | DU00003795978 |  |  | 2025-02-05 | 2025-01-29 |  | Tower |  | 60m | Add R8852E S9000 x2+R8894E M1821x3,Dismantle R8881 S9000x1+R8882 S1800B(B6B)x1+R8862A S1800(B6A)x1+R8881 S2100x2 | 0 | 0
4123Z | Kg Pong Utara | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795979
Q00835 | Q124E_Q00835OD_KGBENGOH2 | Sarawak |  | Decomm | On Hold->Decomm | 2025 Q1 | NA | Magicell | 4.6 TSSR Approved |  | 2025-02-24 |  | 2025-02-26 |  | 2025-04-22 |  | 2025-04-25 | 2025-10-28 | CD//John | 2025-04-26 | SQ202502050300-Magicell/SQ202502270609-Magicell | DU00003795980 |  |  |  |  | 2025-08-29
S00396 | S100A_S00396OD_BORNEOGOLF | Sabah | 7295P | Swap | On Hold->Swap | 2025 Q2 | AD | YPTT | 4.6 TSSR Approved |  | 2025-01-08 | 2025-01-13 |  | 2025-01-22 |  | Under Approval | 2025-02-18 | 2025-03-09 | CD//Sharidah | 2025-02-19 | SQ202501020336 - YPTT | DU00003795981 |  |  | 2025-06-07 | 2025-05-20 |  | Tower |  | 60 | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
4219Z | Kg Kuala Pai | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795982
7054R | TERUSAN | Sabah |  | Maintain USP MOCN(Dismantle Passive) | On Hold->Maintain USP MOCN(Dismantle Passive) | 2024 Q4 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2025-07-22 |  | 2025-09-25 |  | 2025-09-29 |  | 2025-10-07 | 2025-10-27 | E//Hannah | 2025-10-21 | SQ202508130660 - Seri Pancar | DU00003795983 |  |  |  |  | 2025-11-25
A01281 | Kg Kelian Malau | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795984
7017Z | T3_Kg Solob | Sabah |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795985
9096R | KGTAEE | Sarawak |  | MOCN Decomm(Dismantle Passive) |  | 2024 Q4 | HW | Magicell | 4.6 TSSR Approved |  | 2025-07-02 |  | 2025-07-15 |  | 2025-07-16 |  | 2025-08-07 | 2026-01-20 | E//Hannah | 2025-08-11 | SQ202506110081-Magicell/SQ202507140221-Magicell | DU00003795986 |  |  |  |  | 2025-09-09
S01427 | S088A_S01427OD_T3_KGSUASA | Sabah | 7133P | Swap | On Hold->Swap | 2025 Q1 | AD | YPTT | 4.6 TSSR Approved |  | 2025-01-07 | 2025-01-31 |  | 2025-02-04 |  | Under Approval | 2025-02-06 | 2025-02-18 | CD//Sharidah | 2025-02-07 | SQ202501020336 - YPTT | DU00003795987 |  |  | 2025-07-06 | 2025-03-25 |  | Tower |  | 76 | Add R8852E S9000x3+R8854E S1800x3+R8894E M1821x3, Dismantle | 0 | 0
4118C | Padang Mat Sirat | Northern |  | Modernization |  | 2025 Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2025-01-27 | 2025-02-12 |  | 2025-02-14 |  | Under Approval | 2025-02-14 | 2025-05-23 | E//Hazida | 2025-05-22 | SQ202501030229 - GTSB | DU00003795988 |  |  | 2025-04-18 | 2025-04-10 |  | Tower |  | 60 | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8882 S1800B(B6B)x3 | 0 | 0
7080R | PULAU SIBOGO | Sabah |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795989
S01678 | T3E_0216_ Paitan Nangoh 1 | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795990
Q01372 | Q125A_Q01372OD_KGGAYA | Sarawak | 9332K | Swap |  | 2026 | AI | DATASCO | 4.6 TSSR Approved |  | 2025-02-05 | 2025-03-07 |  | 2025-03-20 |  | Closed | 2025-03-21 | 2025-04-15 | CD//John | 2025-03-21 | SQ202501070453-Datasco | DU00003795991 | [5 empty] | Monopole |  | 16m | Add R8852E S9000 x3+R8894E x3,Dismantle
S01200 | Kg Adian | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795992
9200Z | KG MUNGGU KOPI | Sarawak |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795993
A01275 | KG KALA (T3_0359) | Northern |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795994
7045Z | T3_Kg Bauto | Sabah |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795995
A00439 | A045A_A00439OD_CB_SGBANUM | Northern | 4554K | Swap |  | 2027 |  | GCI | 1.1 Pending Survey - Subcon | [6 empty] | To be Submitted |  |  |  |  | SQ202411290568 - GCI | DU00003795996 | [6 empty] | TOWER |  | Add R8852E S9000 x3+R8894E M1821x3,Dismantle | 0 | 0
7354C | Kampung Tuhau | Sabah |  | Modernization |  | 2025 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2025-02-06 | 2025-02-22 |  | 2025-02-27 |  | Under Approval | 2025-03-28 | 2025-04-22 | E//Hannah | 2025-04-22 | SQ202501030028 - GTSB | DU00003795997 |  |  | 2025-07-06 | 2025-05-22 |  | Tower |  | 75 | Add R9224E M1821x1 | 0 | 3
7023Z | T3_Kg Maliau | Sabah |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003795998
4878A | Langkawi Fair | Northern |  | Modernization |  | 2025 Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2025-01-24 | 2025-02-03 |  | 2025-03-04 |  | Rectificating | 2025-03-11 | 2025-03-13 | E//Nazrul | 2025-03-12 | SQ202501030229 - GTSB | DU00003795999 |  |  | 2025-04-25 | 2025-04-18 |  | In-Building System |  |  | Add R8894E M1821x1, Dismantle R8882-GUL1812x1+R8862A S2100(A6A)x1 | 0 | 0
S01267 | Kg Ubah | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796000
S01402 | RS50297_4_1 KGKEKAPOR | Sabah | 7318K | Swap |  | 2027 |  | Seri Pancar | 3.1 Pending RF Solution - RF Team |  | 2026-01-29 | 2026-02-04 |  |  |  | To be Submitted |  |  |  |  | SQ202601220834 - Seri Pancar | DU00003796001 | [5 empty] | Tower |  | 30m | Add R8852E S9000x2+R9264M M1821x3, Dismantle R8862A S1800(B6A)x1 | 0 | 0
4003Z | HUJUNGKETUN | Northern |  | MOCN Decomm |  | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796002
K00234 | K008A_K00234OD_THEDATAI | Northern |  | Decomm |  | 2024 Additional | SM | GTSB | 15.4 Decomm Done without TSSR Approval |  | 2024-12-07 |  | 2025-01-09 |  | 2024-12-20 | To be Submitted | 2024-12-23 |  | CD//Zulakmar |  | SQ202412090105 - GTSB | DU00003796003 |  |  |  |  | 2025-05-14
4974C | Kopisan Baru | Northern |  | Modernization |  | 2024 Additional | SM | CCSMY | 4.6 TSSR Approved |  | 2024-11-19 | 2024-11-28 |  | 2024-12-02 |  | Rectificating | 2024-12-03 | 2024-12-06 | E//Hazida | 2024-12-06 | 1911CD-Northern-TSS-BOQ Template(new contract)_CCSMY_V2 | DU00003796004 |  |  | 2024-12-12 | 2024-12-11 |  | Monopole |  | 30 | Add R8894E M1821x3, Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3 | 0 | 0
Q02059 | RuanSepakui | Sarawak |  | MOCN Decomm |  | 2026 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796005
S01278 | Kg Bambangan | Sabah |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796006
Q02207 | KG SEBEMBAN | Sarawak |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796007
7181Z | Segalong Camp (Jalan Sidumin Siputol) | Sarawak |  | Maintain USP MOCN |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796008
9176R | KG KARAN PONEG | Sarawak |  | MOCN Decomm |  | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796009
K00674 | K008A_K00674OD_TELAGAHARBOUR | Northern |  | Decomm |  | 2024 Additional | AD | GTSB | 4.6 TSSR Approved |  | 2024-12-05 |  | 2024-12-05 |  | 2024-12-19 |  | 2024-12-22 |  | CD//Zulakmar | 2024-12-23 | SQ202412090105 - GTSB | DU00003796010 |  | No OB Fiber and Cisco Photo |  |  | 2025-02-04
K01029 | Kg Bukit Batu | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796011
K00870 | A040D_K00870OD_CB_JLNKGSGBATU_GNGBONGSU | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796012
7792A | Kg Limbuak Laut | Sabah |  | Decomm, MOCN By Other Vendor | On Hold->Decomm->On Hold->Decomm | 2025 |  | GTSB | 1.1 Pending Survey - Subcon | [6 empty] | To be Submitted |  |  |  |  | SQ202504100576 - GTSB | DU00003796013
7027A | Limbawang | Sabah |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q4 |  | DATASCO | 14.0 TSSR Not Required (Reuse Existing BBU/RRU) |  | 2025-01-13 | 2025-03-05 |  |  |  | To be Submitted |  |  |  |  | SQ202501020441 - Datasco | DU00003796014 | [5 empty] | Monopole |  | 30 | Reuse Existing RRU | 0 | 0
Q00646 | Q124E_Q00646OD_CB_KGBAYOR | Sarawak |  | Decomm |  | 2025 Q1 | AI | Trintel | 4.6 TSSR Approved |  | 2025-02-14 |  | 2025-02-27 |  | 2025-03-24 |  | 2025-04-14 | 2025-09-10 | CD//John | 2025-05-02 | SQ202502260543-Trintel/SQ202502270531-Trintel | DU00003796015 |  |  |  |  | 2025-07-25 | Tower
Q01959 | Kg Resak | Sarawak |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796016
4135Z | Kg Durian Burong | Northern |  | Maintain USP MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796017
S01771 | FC1_119 Kg Lodung | Sabah |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796018
7087R | KGBATULINTING | Sabah |  | MOCN Decomm(Dismantle Passive) |  | 2025 | AD | Datasco | 4.6 TSSR Approved |  | 2025-07-07 |  | 2025-07-09 |  | 2025-09-10 | To be Submitted | 2025-10-28 | 2026-04-17 | E//Faiz | 2025-11-10 | SQ202506100762 - Datasco /SQ202507010433 - Datasco | DU00003796019 |  |  |  |  | 2025-08-05
A01284 | Pulau Belayar | Northern |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796020
S01830 | FC1_126 Jalan Teringai_2 | Sabah |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796593
S01905 | Kg Terusan | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796594
S01923 | S095A_S01923OD_RAMOPDMENUMBOK | Sabah | 7228K | Swap |  | 2025 | AD | YPTT | 4.6 TSSR Approved |  | 2025-01-06 | 2025-01-13 |  | 2025-01-16 |  | Under Approval | 2025-01-20 | 2025-03-09 | CD//Sharidah | 2025-02-19 | SQ202501030045 - YPTT | DU00003796595 |  |  | 2025-09-10 | 2025-08-23 |  | Tower |  | 45 | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
S01864 | MERIDIAN PLANTATION | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796596
S01896 | FC1_102 Skim Mesej Kg Kinolosodon | Sabah |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796597
S01917 | Pulau Tetabuan | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796598
S01786 | FC1_122 Kg Membatu | Sabah |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796599
S01777 | FC1_124 Kg Panikuan | Sabah |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796600
S01785 | FC1_123 Kg Inukiran | Sabah |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796601
S01903 | Kg Klagan | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796602
S01918 | Pelita Jujur Estate | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796603
S01899 | FC1_093 Kg Katubu | Sabah |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796604
S01909 | Ladang Sungai sungai 2 | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796605
S01894 | FC1_097 Kg Kalanyaan | Sabah |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796606
S01784 | FC1_114 Kg Tembidung Bidung | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796607
S01832 | FC1_095 Kg Bamban | Sabah |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796608
S01913 | Tanjung Nipis Estate | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796609
S01916 | Kg Tibatu | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796610
S01781 | FC1_092 Kg Tilis | Sabah |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796611
S01856 | Segaliud Lokan | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796612
S01878 | FC1_098 Kg Pengalat | Sabah |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796613
S01865 | KG SUNGAI SAPI | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796614
S01879 | FC1_096 Kg Mandalom Baru | Sabah |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796615
S01897 | FC1_115 Pekan Kecil Paitan | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796616
S01900 | FC1_094 Skim Mesej Ulu Patian | Sabah |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796617
S01787 | FC1_113 Kg Bangau Bangau | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796618
S01877 | FC1_116 Ladang Tangkulap (IOI Plantation) | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796619
S01776 | FC1_112 Jalan Ranau Sandakan 1 | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796620
S01915 | Ladang Kawananan | Sabah |  | MOCN Decomm |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796621
S01831 | FC1_099 Kg Tepoh | Sabah |  | MOCN Decomm |  | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003796622
9049R | T3_0341 - TN BAKO | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q1_496 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002558955 | [6 empty] | TBC
1213C | USJ 7 | Central |  | Remote MOCN |  | 2024 Q1_496 |  | DATASCO | 14.3 Drop (Done Survey + TSSR) |  | 2023-11-23 |  |  | 2023-12-16 |  | Under Approval | [5 empty] | DU00002558956 | [6 empty] | 3m Boom (RT) |  |  | 4
4341D | Masjid Abdullah Fahim | Northern |  | Remote MOCN | Modernization->Modernization(MOCN)->Remote MOCN | 2024 Q1_496 |  | GTSB | 14.2 Drop (Done Survey) |  | 2023-12-07 | 2023-09-22 |  |  |  | To be Submitted |  |  |  |  | N/A - Remote MOCN | DU00002558957 | [5 empty] | Monopole | 30m Lampole | 30m |  | 23
4347D | UMNO Kepala Batas | Northern |  | Modernization |  | 2024 Q1_496 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-08-21 | 2023-08-28 |  | 2023-08-30 |  | Closed | 2023-08-31 | 2023-09-14 | E//Hazida | 2023-09-12 | Celcom Digi_RAN-GTSB-TSS-Northern-20230821-0027 | DU00002558958 |  |  | 2024-01-16 | 2024-01-08 |  | In-Building System | 3m Boom (RT) | 7 | Add R8852E S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 12 | 0
4391D | Taman Tasik Mutiara | Northern |  | Remote MOCN |  | 2024 Q1_496 | HQ 1 | YPTT | 14.1 Drop (No Survey) |  |  | 2023-09-06 |  |  |  | To be Submitted |  |  | E//Hazida |  | N/A - site move to BAU | DU00002558959 | [5 empty] | Monopole | 36M Monopole | 37 |  | 12
1215C | Wawasan | Central |  | Modernization |  | 2024 Q1_496 | XH | Magicell | 4.6 TSSR Approved | AAU Cannot Install-S2 MM change to BI¦unipole,full of antenna,space constraint | 2023-11-29 | 2023-12-01 |  | 2024-01-15 |  | Closed | 2024-01-17 | 2024-01-18 | E//Kok Keen | 2024-01-17 | CelcomDigi_RAN_Magicell_TSS_Central_20231201 | DU00002558960 |  |  | 2024-01-31 | 2024-01-29 |  | In-Building System | 6m Unipole RT | 9 | Add R9264H M901821 x4+R8854 S2600 x1,Dismantle R8862A S2600(A4A) x1+R8894E M1821(A8A) x4 | 0 | 2
4348D | Bertam Indah | Northern |  | Modernization |  | 2024 Q1_496 | SM | GTSB | 4.6 TSSR Approved |  | 2023-08-21 | 2023-09-04 |  | 2023-09-07 |  | Rectificating | 2023-09-12 | 2023-10-02 | E//Hazida | 2023-10-01 | Celcom Digi_RAN-GTSB-TSS-Northern-20230821-0027 | DU00002558961 |  |  | 2024-01-10 | 2024-01-10 |  | Lampole | 30m Lampole | 35 | Add R8852E S9000 x3+A9732 M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 123 | 0
1425B | Summit USJ Complex | Central |  | Modernization |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-10-12 | 2023-10-20 |  | 2023-10-24 |  | Closed | 2023-11-08 | 2023-11-14 | E//Kok Keen | 2023-11-08 | CelcomDigi_RAN_Datasco_TSS_Central_20231005 | DU00002558962 |  |  | 2023-12-27 | 2023-12-11 |  | Pole | 3m RT (Wall Mounted Pole) | 4m & 8m | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 13 | 0
1171A | SubangJaya | Central |  | Modernization |  | 2024 Q1_496 | CR | Datasco | 4.6 TSSR Approved |  | 2023-10-01 | 2023-09-26 |  | 2023-10-13 |  | Closed | 2023-10-03 | 2023-10-06 | E//Kok Keen | 2023-10-04 | CelcomDigi_RAN_Datasco_TSS_Central_20230907 | DU00002558963 |  |  | 2023-11-30 | 2023-10-16 |  | Wall mount boom | 3m RT (Minimast) | 3m | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3 | 1 | 0
1184A | Indah Villa | Central |  | Modernization |  | 2024 Q1_496 | CR | Datasco | 4.6 TSSR Approved |  | 2023-10-03 | 2023-10-27 |  | 2023-11-01 |  | Closed | 2023-11-09 | 2023-11-14 | E//Kok Keen | 2023-11-10 | CelcomDigi_RAN_Datasco_TSS_Central_20231003 | DU00002558964 |  |  | 2023-12-22 | 2023-12-08 |  | In-Building System | 3m Bipod (RT) | Sec 1 - 3m & 4m, Sec 2 - 3m & 4m & Sec 3 -3m | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 12
1195A | Jln 19 Shoplot | Central |  | Modernization |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦Space issue AAU can not install | 2023-08-22 | 2023-08-30 |  | 2023-09-03 |  | Closed | 2023-09-05 | 2023-09-07 | E//Kok Keen | 2023-09-07 | CelcomDigi_RAN_Datasco_TSS_Central_20230823 | DU00002558965 | NIC_S1_Change MM to BI_Space constraint_Digi OB |  | 2023-09-23 | 2023-09-22 |  | Unipole | 6m RT (Boom) | 11 | Add R9264M M1821 x4+R8862A S2601 x1,Dismantle R8894E M1821(A8A) x3 |  | 1
1217A | Favellafavco | Central |  | Modernization |  | 2024 Q1_496 | SS | DATASCO | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦site onwer not allow to add AAU on the structure | 2023-09-03 | 2023-09-16 |  | 2023-09-19 |  | Closed | 2023-10-06 | 2023-10-17 | E//Kok Keen | 2023-10-12 | CelcomDigi_RAN_Datasco_TSS_Central_20230901 | DU00002558966 | NIC_S1_Change MM to BI_loading issue_Digi OB |  | 2023-10-20 | 2023-10-18 |  | In-Building System | 45m Tower | 7 | Add R9264M M1821 x4+R8862A S2601 x1,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 0 | 2
1251B | Putra Persiaran Perdana | Central |  | Modernization |  | 2024 Q1_496 | IE | DATASCO | 4.6 TSSR Approved |  | 2023-08-23 | 2023-09-01 |  | 2023-09-05 |  | Closed | 2023-09-06 | 2023-09-21 | E//Razif | 2023-09-21 | CelcomDigi_RAN_Datasco_TSS_Central_20230824 | DU00002558967 |  |  | 2023-09-22 | 2023-09-22 |  | In-Building System | 3m Boom (RT) | 6 | Add R8894E M1821 x4,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8840-U216 x3+R8881 S2100 x1+
1302B | SS19 Subang Jaya | Central |  | Modernization |  | 2024 Q1_496 | SS | DATASCO | 4.6 TSSR Approved |  | 2023-09-03 | 2023-09-15 |  | 2023-09-18 |  | Closed | 2023-09-19 | 2023-09-20 | E//Kok Keen | 2023-09-20 | CelcomDigi_RAN_Datasco_TSS_Central_20230824 | DU00002558968 |  |  | 2023-09-28 | 2023-09-28 |  | Wall mount boom | 6m RT (Boom) | S1 A & S3 A: 6m S2 S1B S3B: 8m | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3++
1344A | Section 28 | Central |  | Modernization |  | 2024 Q1_496 | SS | DATASCO | 4.6 TSSR Approved |  | 2023-08-29 | 2023-09-18 |  | 2023-09-20 |  | Closed | 2023-10-02 | 2023-10-06 | E//Razif | 2023-09-22 | CelcomDigi_RAN_Datasco_TSS_Central_20230901 | DU00002558969 |  |  | 2023-10-11 | 2023-10-10 |  | In-Building System | 3m Boom (RT) | 3 | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3 | 2
1347B | SS13 Sunway | Central |  | Modernization |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-09-19 | 2023-09-25 |  | 2023-09-28 |  | Closed | 2023-10-02 | 2023-10-03 | E//Kok Keen | 2023-10-03 | CelcomDigi_RAN_Datasco_TSS_Central_20230920 | DU00002558970 |  |  | 2023-10-13 | 2023-10-12 |  | Wall mount boom | 3m Boom (RT) | 3 | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8882-GUL1812 x3 | 23 | 0
1349A | JBA Ebor | Central |  | Remote MOCN |  | 2024 Q1_496 | CR | DATASCO | 14.3 Drop (Done Survey + TSSR) |  | 2023-08-29 | 2023-09-06 |  | 2023-09-09 |  | Rectificating |  |  | E//Kok Keen |  | CelcomDigi_RAN_Datasco_TSS_Central_20230901 | DU00002558971 | [5 empty] | Monopole | 30m Monopole | 31 |  | 13
1360A | Hicom Glenmarie | Central |  | Modernization |  | 2024 Q1_496 | SS | DATASCO | 4.6 TSSR Approved |  | 2023-09-03 | 2023-09-13 |  | 2023-10-13 |  | Closed | 2023-09-29 | 2023-10-02 | E//Kok Keen | 2023-10-02 | Celcom Digi_RAN-Datasco-TSS-Central-20230919 | DU00002558972 |  |  | 2024-02-15 | 2024-02-08 |  | Wall mount boom | 3m Boom (RT) | 6 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3
1399A | USJ 21Shoplot | Central |  | Modernization |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-09-03 | 2023-09-13 |  | 2023-10-13 |  | Closed | 2023-09-27 | 2023-10-02 | E//Kok Keen | 2023-09-29 | CelcomDigi_RAN_Datasco_TSS_Central_20230901 | DU00002558973 |  |  | 2023-10-10 | 2023-10-07 |  | Pole | 3m Boom (RT) | 6 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3++
1404B | PJS7(ZED) | Central |  | Modernization |  | 2024 Q1_496 | SS | CCSMY | 4.6 TSSR Approved |  | 2024-01-09 | 2024-01-16 |  | 2024-01-18 |  | Closed | 2024-01-19 | 2024-03-27 | E//Sumitra | 2024-03-27 | CelcomDigi_RAN_CCSMY_TSS_Central_20231213 | DU00002558974 |  |  | 2024-02-20 | 2024-02-06 |  | In-Building System | 3m RT (Minimast) | 8m | Add R9264H M901821 x3+R8854 S2600 x1,Dismantle R8862A S9000(A6A) x3+R8882-GUL1812 x4+R8862A S2100(A6A) x3+R8862A S2600(A4A) x1 |  | 2
1421B | USJ4 | Central |  | Modernization |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-08-22 | 2023-09-01 |  | 2023-09-05 |  | Closed | 2023-09-06 | 2023-09-08 | E//Kok Keen | 2023-09-08 | CelcomDigi_RAN_Datasco_TSS_Central_20230823 | DU00002558975 |  |  | 2023-09-24 | 2023-09-22 |  | Monopole | 30m Monopole | 31 | Add R9264M M1821 x4,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8854D S2100(A4A) x4
1704B | Seksyen U2 | Central |  | Modernization |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-10-03 | 2023-10-06 |  | 2023-10-10 |  | Closed | 2023-10-11 | 2023-12-28 | E//Kok Keen | 2023-12-26 | CelcomDigi_RAN_Datasco_TSS_Central_20230901 | DU00002558976 |  |  | 2023-12-30 | 2023-12-29 |  | Monopole | 45m Monopole | 46m | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 23
1710B | Seksyen 27_89 | Central |  | Modernization |  | 2024 Q1_496 | XH | DATASCO | 4.6 TSSR Approved |  | 2023-08-23 | 2023-09-05 |  | 2023-09-07 |  | Closed | 2023-09-11 | 2023-10-01 | E//Razif | 2023-09-22 | CelcomDigi_RAN_Datasco_TSS_Central_20230824 | DU00002558977 |  |  | 2023-11-16 | 2023-10-18 |  | H-bracket pole | 3m Boom (RT) | 7m | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8862A S2601(A6A) x2+R9224E M1821(AAB) x5 | 23
4566C | Kuala Muda Trunk (REL) | Northern |  | Remote MOCN | Modernization->Modernization(MOCN)->Remote MOCN | 2024 Q1_496 | BY | Ascentrack | 14.1 Drop (No Survey) |  |  | 2023-08-24 |  |  |  | To be Submitted |  |  | E//Hazida |  | N/A - site move to BAU | DU00002558978 | [5 empty] | Tower | 60m 4 Legged Tower | 50m |  | 14
1946B | Putra Height Tower 2 (REL) | Central |  | Modernization |  | 2024 Q1_496 | IE | DATASCO | 4.6 TSSR Approved |  | 2023-10-17 | 2023-10-19 |  | 2023-10-20 |  | Closed | 2024-09-26 | 2024-10-08 | E//Razif | 2024-10-08 | CelcomDigi_RAN_Datasco_TSS_Central_20230907 | DU00002558979 |  |  | 2023-12-13 | 2023-11-07 |  | Monople Tree | 30m Monopole | 35 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3
1950A | Tmn Desa Ria | Central |  | Remote MOCN |  | 2024 Q1_496 | AI | DATASCO | 14.3 Drop (Done Survey + TSSR) |  | 2023-08-22 | 2023-08-30 |  | 2023-09-04 |  | Closed | 2023-09-05 | 2023-09-06 | E//Kok Keen |  | CelcomDigi_RAN_Datasco_TSS_Central_20230823 | DU00002558980 | [5 empty] | Pole | 3m Boom (RT) | 6 |  |  | 3
1960A | Intercity Subang | Central |  | Modernization |  | 2024 Q1_496 | SS | DATASCO | 4.6 TSSR Approved |  | 2023-08-22 | 2023-08-30 |  | 2023-09-04 |  | Closed | 2023-09-05 | 2023-09-06 | E//Razif | 2023-09-06 | CelcomDigi_RAN_Datasco_TSS_Central_20230823 | DU00002558981 |  |  | 2023-09-25 | 2023-09-22 |  | In-Building System | 3m Bipod (RT) | 3 | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 2 | 0
4285A | Tmn Bertam Indah | Northern |  | Modernization |  | 2024 Q1_496 | BY | GTSB | 4.6 TSSR Approved |  | 2023-08-15 | 2023-08-21 |  | 2023-08-28 |  | Closed | 2023-08-29 | 2023-09-13 | E//Hazida | 2023-09-13 | Celcom Digi_RAN-GTSB-TSS-Northern-20230817-0025 | DU00002558982 |  |  | 2023-10-09 | 2023-10-07 |  | Minimast | 3m RT (Minimast) | 6 | Add R8852E S9000 x3+R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3
4328C | K.Matrikulasi PP(REL) | Northern |  | Modernization |  | 2024 Q1_496 | BY | Ascentrack | 4.6 TSSR Approved |  | 2023-08-10 | 2023-08-23 |  | 2023-08-25 |  | Closed | 2023-08-28 | 2023-09-06 | E//Hazida | 2023-09-05 | Celcom Digi_RAN-Ascentrack-TSS-Northern-20230824-0001 | DU00002558983 |  |  | 2023-11-06 | 2023-09-26 |  | Tower | Tower | 61m | Add R8852E S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8882 S1800(B) x1+R8862A S1800(B6A) x5+R8854D S2100(A4A) x5+R8862A S2601(A6A) x2 | 13
2397A | USJ 9 | Central |  | Modernization |  | 2024 Q1_496 | SS | Datasco | 4.6 TSSR Approved |  | 2023-09-03 | 2023-09-14 |  | 2023-09-18 |  | Closed | 2023-09-19 | 2023-09-21 | E//Kok Keen | 2023-09-20 | Celcom Digi_RAN-Datasco-TSS-Central-20230919 | DU00002558984 |  |  | 2023-09-30 | 2023-09-28 |  | In-Building System | 3m Boom (RT) | 5 | Add R9264M M1821 x4,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8840-U216 x3+R8881 S2100 x1+
2456A | NKVE Saujana Glenmarie 2 | Central |  | Modernization |  | 2024 Q1_496 | XH | DATASCO | 4.6 TSSR Approved |  | 2023-10-13 | 2023-10-16 |  | 2023-10-19 |  | Closed | 2023-10-24 | 2023-10-27 | E//Kok Keen | 2023-10-24 | CelcomDigi_RAN_Datasco_TSS_Central_20230901 | DU00002558985 |  |  | 2024-02-02 | 2024-01-20 |  | Monople Tree | 30m Monopole Tree | 31 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3++
4291C | Bukit Tambun (REL) | Northern |  | Remote MOCN |  | 2024 Q1_496 | HQ 1 | GCI | 14.1 Drop (No Survey) |  |  | 2023-09-06 |  |  |  | To be Submitted |  |  | E//Ajay |  | N/A - site move to BAU | DU00002558986 | [6 empty] | 30m Monopole | 50 |  | 123
2550A | Glenmarie (Celcom) | Central |  | Site Out (Modernization) | Modernization->Site Out->Replacement, Site Out (Modernization) | 2024 Q1_496 |  | YPTT | 15.3 Decomm Done without TSSR |  | 2025-07-25 |  |  |  |  | To be Submitted |  |  |  |  | SQ202506140184 | DU00002558987 |  |  |  |  | 2025-08-05 |  | 45m Tower
2556B | USJ 21 | Central |  | Modernization |  | 2024 Q1_496 | SS | Datasco | 4.6 TSSR Approved |  | 2023-09-03 | 2023-09-16 |  | 2023-09-19 |  | Closed | 2023-09-20 | 2023-09-21 | E//Kok Keen | 2023-09-21 | CelcomDigi_RAN_Datasco_TSS_Central_20230905 | DU00002558988 |  |  | 2023-09-28 | 2023-09-28 |  | Lampole | 24m Lampole | 30m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
2600B | Panasonic Shah Alam | Central |  | Modernization |  | 2024 Q1_496 | SS | DATASCO | 4.6 TSSR Approved |  | 2023-09-03 | 2023-09-16 |  | 2023-09-19 |  | Closed | 2023-09-20 | 2023-09-21 | E//Razif | 2023-09-21 | CelcomDigi_RAN_Datasco_TSS_Central_20230828 | DU00002558989 |  |  | 2023-12-07 | 2023-10-18 |  | Monople Tree | 30m Monopole | 30 | Add R9264M M1821 x2+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x6+R8882 S2600(B4A) x2 | 13 | 0
2603B | USJ Heights LP 2 | Central |  | Remote MOCN |  | 2024 Q1_496 |  | DATASCO | 14.2 Drop (Done Survey) |  | 2024-01-02 |  |  |  |  | To be Submitted | [5 empty] | DU00002558990 | [6 empty] | Tower |  |  |  | 3
2612B | Putra Bistari RT | Central |  | Modernization |  | 2024 Q1_496 | XH | Ascentrack | 4.6 TSSR Approved |  | 2023-08-31 | 2023-09-06 |  | 2023-09-10 |  | Closed | 2023-09-11 | 2023-09-14 | E//Razif | 2023-09-12 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230901 | DU00002558991 |  |  | 2023-09-23 | 2023-09-23 |  | Monople Tree | 30m Monopole | 33 | Add R8852E S9000 x1+R9264H M901821 x2+R8862A S2601 x3+A9732 M1821 x1,Dismantle R8892E M1821(BAA) x3 | 3
2616B | Jln Teluk Gadung | Central |  | Modernization |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-09-04 | 2023-09-07 |  | 2023-09-11 |  | Closed | 2023-09-12 | 2024-12-06 | E//Razif | 2023-09-12 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230905 | DU00002558992 |  |  | 2023-09-23 | 2023-09-23 |  | In-Building System | 3m Boom (RT) | 5 | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 1
2617B | Putra Height MP | Central |  | Modernization |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-10-07 | 2023-11-29 |  | 2023-10-18 |  | Closed | 2023-10-18 | 2023-10-19 | E//Razif | 2023-10-19 | CelcomDigi_RAN_Datasco_TSS_Central_20230901 | DU00002558993 |  |  | 2023-10-25 | 2023-10-23 |  | Monopole | 30m Monopole | 30 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
4113A | Berapit(Maxis) | Northern |  | Remote MOCN |  | 2024 Q1_496 |  | Ascentrack | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002558994 | [6 empty] | 76m 3 Legged Tower |  |  |  | 2
2629B | Jln Batu Tiga Lama | Central |  | Modernization |  | 2024 Q1_496 | XH | Ascentrack | 4.6 TSSR Approved |  | 2023-08-28 | 2023-08-30 |  | 2023-09-04 |  | Closed | 2023-09-05 | 2023-09-06 | E//Razif | 2023-09-06 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230829 | DU00002558995 |  |  | 2023-09-15 | 2023-09-15 |  | H-bracket pole | 3m Bipod (RT) | 9 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3
2642A | Pinggiran USJ | Central |  | Modernization |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-09-06 | 2023-09-11 |  | 2023-09-13 |  | Closed | 2023-09-18 | 2023-09-21 | E//Razif | 2023-09-21 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230907 | DU00002558996 |  |  | 2023-09-26 | 2023-09-26 |  | Lampole | 20m Lampole | 20 | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3 | 3(S1 -> S2,S2->S3,S3->S1,,need rename sector ID,FDD MM@NEW S3) | 0
2648A | Sunway Shoplots | Central |  | Modernization |  | 2024 Q1_496 | IE | DATASCO | 4.6 TSSR Approved |  | 2023-08-23 | 2023-09-07 |  | 2023-09-10 |  | Closed | 2023-09-12 | 2023-09-21 | E//Razif | 2023-09-20 | CelcomDigi_RAN_Datasco_TSS_Central_20230824 | DU00002558997 |  |  | 2023-09-26 | 2023-09-25 |  | In-Building System | 3m Bipod (RT) | 11 | Add R9264M M1821 x5+R8862A S2601 x2,Dismantle R8882-GUL1812 x3+R8840-U216 x3++ |  | 13
2649A | Putra Height 1(surau nurul) | Central |  | Modernization |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-08-24 | 2023-09-04 |  | 2023-09-07 |  | Closed | 2023-09-12 | 2023-09-14 | E//Razif | 2023-09-13 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230825 | DU00002558998 |  |  | 2023-10-14 | 2023-10-12 |  | Lampole | 20m Lampole | 20 | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 1 | 0
2650A | PutraHeight2(Surau Baiturahman) | Central |  | Modernization |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-08-24 | 2023-08-28 |  | 2023-09-01 |  | Closed | 2023-09-02 | 2023-09-21 | E//Razif | 2023-09-21 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230825 | DU00002558999 |  |  | 2023-09-08 | 2023-09-07 |  | Lampole | 20m Lampole | 20 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8840-U216 x3++
2652A | SUNWAY COLLEGE UNIVERSITY | Central |  | Remote MOCN |  | 2024 Q1_496 |  | Datasco | 14.2 Drop (Done Survey) | AAU Cannot Install-Change MM to BI¦NOK,Space constraint,to avoid blocking issue,suggest to change to bi-sector | 2023-09-01 | 2023-09-08 |  |  |  |  | 2024-07-18 |  |  |  | CelcomDigi_RAN_Datasco_TSS_Central_20230901 | DU00002559000 | BAU_S1_Change MM to BI_Space constraint_Digi OB |  |  |  |  | In-Building System | 3m Boom (RT) | 4 |  |  | 2
4014B | Valdor | Northern |  | Remote MOCN |  | 2024 Q1_496 |  | CCSMY | 14.1 Drop (No Survey) |  |  | 2023-09-06 |  |  |  | To be Submitted |  |  |  |  | N/A - site move to BAU | DU00002559001 | [5 empty] | Tower | 60m 3 Legged Tower | 60M |  | 4
4234B | Kg Permatang Ara | Northern |  | Modernization |  | 2024 Q1_496 | BY | GCI | 4.6 TSSR Approved |  | 2024-01-17 | 2024-01-20 |  | 2024-01-24 |  | Closed | 2024-01-24 | 2024-01-26 |  | 2024-01-25 | Celcom Digi_RAN-GCI-TSS-Northern-20240124-0090 | DU00002559002 |  |  | 2024-02-24 | 2024-02-05 |  | Tower | Tower | 90 | Add R8852E S9000 x2+R9264H M901821 x2+A9732 M1821 x2,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8840-U216 x3+R8862A S2100(A6A) x1 | 13
4327C | Tasek Gelugor 2 (REL) | Northern |  | Modernization |  | 2024 Q1_496 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-09-01 | 2023-09-07 |  | 2023-09-11 |  | Closed | 2023-09-13 | 2023-10-27 | E//Zamran | 2023-10-26 | Celcom Digi_RAN-GCI-TSS-Northern-20230904-0044 | DU00002559003 |  |  | 2023-10-09 | 2023-10-07 |  | Monople Tree | Tower | 45 | Add R8852E S9000 x2+R9264H M901821 x2+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x4 | 14 | 0
4188A | Nibong Tebal 2 | Northern |  | Modernization |  | 2024 Q1_496 |  | CCSMY | 4.6 TSSR Approved |  | 2023-11-03 | 2023-11-08 |  | 2023-11-20 |  | Closed | 2023-11-23 | 2023-11-28 | E//Hazida | 2023-11-24 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231106-0068 | DU00002559004 |  |  | 2023-12-14 | 2023-12-13 |  | Tower | 60m 4 Legged Tower | 49m | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8860E-GU908 x1+R8894E M1821(A8A) x3 | 12
4279A | Pinang Tunggal (KJS) | Northern |  | Remote MOCN |  | 2024 Q1_496 |  | GCI | 14.1 Drop (No Survey) |  |  | 2023-09-13 |  |  |  | To be Submitted |  |  |  |  | N/A - site move to BAU | DU00002559005 | [5 empty] | Tower | 60m 4 Legged Tower | 61m |  | 2
2926A | Subang SS14 | Central |  | Modernization |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-08-29 | 2023-09-19 |  | 2023-09-21 |  | Closed | 2023-09-22 | 2023-10-01 | E//Kok Keen | 2023-09-26 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230901 | DU00002559006 |  |  | 2023-10-06 | 2023-09-30 |  | In-Building System | 3m RT (Wall Mounted Pole) | 6 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3
3185A | Persiaran Aman | Central |  | Remote MOCN |  | 2024 Q1_496 | AI | GTSB | 14.3 Drop (Done Survey + TSSR) | AAU Cannot Install-Change MM to BI¦AAU can not install | 2023-08-18 | 2023-08-24 |  | 2023-08-29 |  | Under Approval |  |  |  |  | CelcomDigi_RAN_GTSB_TSS_Central_20230819 | DU00002559007 | BAU_S2_Change MM to BI_Space constraint_Digi OB |  |  |  |  | In-Building System | 3m Bipod (RT) | 8 |  | 0 | 13
3207A | Jln Subang 8 | Central |  | Modernization |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-08-29 | 2023-09-01 |  | 2023-09-06 |  | Closed | 2023-09-06 | 2023-09-07 | E//Sumitra | 2023-09-07 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230901 | DU00002559008 |  |  | 2023-09-23 | 2023-09-22 |  | Lampole | 24m Lampole | 20 | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 1 | 0
4084B | Kg Tok Bedu | Northern |  | Modernization |  | 2024 Q1_496 | ZA | GCI | 4.6 TSSR Approved |  | 2023-09-20 | 2023-09-25 |  | 2025-01-24 |  | Under Approval | 2023-10-02 | 2023-10-24 | E//Hazida | 2023-10-24 | Celcom Digi_RAN-GCI-TSS-Northern-20230819-0038 | DU00002559009 |  |  | 2024-01-17 | 2024-01-09 |  | Tower | Tower | 61 | Add R8852E S9000 x2+R9264H M901821 x1+R8854 S2600 x3+A9732 M1821 x2,Dismantle R8892E M1821(BAA) x3 | 23
4097B | Jalan Kebun Sireh (Maxis) | Northern |  | Remote MOCN |  | 2024 Q1_496 | BY | Ascentrack | 14.1 Drop (No Survey) | AAU Cannot Install-Change MM to BI¦Maxis rejected to add more Antenna |  | 2023-08-18 |  |  |  | To be Submitted |  |  | E//Hazida |  | N/A - site move to BAU | DU00002559010 | BAU_S1_Change MM to BI_owner reject_MAXIS |  |  |  |  | Monopole | 45m Monopole | 30m |  |  | 2
4098B | Jalan Tembikai (PDC pBTS) | Northern |  | Remote MOCN |  | 2024 Q1_496 | ZA | Ascentrack | 14.1 Drop (No Survey) |  |  | 2023-08-21 |  |  |  | To be Submitted |  |  | E//Hazida |  | N/A - site move to BAU | DU00002559011 | [5 empty] | Lampole | 25m pBTS | 24m
4104A | Bank Pacific | Northern |  | Remote MOCN |  | 2024 Q1_496 |  | Ascentrack | 14.1 Drop (No Survey) |  |  | 2023-10-18 |  |  |  | To be Submitted | [5 empty] | DU00002559012 | [6 empty] | 6m RT (Boom) | 6m |  | 1
4108B | Jalan Paboi | Northern |  | Remote MOCN | Modernization->Modernization(MOCN)->Remote MOCN | 2024 Q1_496 | ZA | CCSMY | 14.1 Drop (No Survey) | AAU Cannot Install-Change MM to BI¦Maxis not allowed add AAU |  | 2023-08-30 |  |  |  | To be Submitted |  |  | E//Hazida |  | N/A - site move to BAU | DU00002559013 | [5 empty] | Tower | 76m 4 Legged Tower | 90m
4110A | KTM Bukit Mertajam | Northern |  | Modernization |  | 2024 Q1_496 | WP | Ascentrack | 4.6 TSSR Approved |  | 2023-10-04 | 2023-10-16 |  | 2024-04-17 |  | Closed | 2023-10-24 | 2023-10-27 | E//Hazida | 2023-10-27 | Celcom Digi_RAN-Ascentrack-TSS-Northern-20231006-0013 | DU00002559014 |  |  | 2024-02-23 | 2024-02-07 |  | Tower | 45m 4 Legged Tower | 92 | Add R8852E S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3 | 13 | 0
4116B | Sg Bakap 2 Monopole (Celcom) | Northern |  | Remote MOCN | Modernization->Modernization(MOCN)->Remote MOCN | 2024 Q1_496 |  | YPTT | 14.2 Drop (Done Survey) |  | 2024-05-01 | 2023-09-25 |  |  |  | To be Submitted |  |  |  |  | N/A - site move to BAU | DU00002559015 | [5 empty] | Monopole | 45m Monopole | 46m |  | 13
4117A | Bandar Perda BM | Northern |  | Modernization |  | 2024 Q1_496 | ZA | GCI | 4.6 TSSR Approved |  | 2023-08-22 | 2023-08-25 |  | 2023-09-05 |  | Closed | 2023-09-04 | 2023-09-21 | E//Hazida | 2023-09-21 | Celcom Digi_RAN-GCI-TSS-Northern-20230824-0041 | DU00002559016 |  |  | 2023-09-30 | 2023-09-30 |  | In-Building System | 3m RT (Minimast) | 5.9 | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 12 | 0
4119A | Kulim HWY | Northern |  | Remote MOCN |  | 2024 Q1_496 |  | Ascentrack | 14.1 Drop (No Survey) |  |  | 2023-09-13 |  |  |  | To be Submitted |  |  |  |  | N/A - site move to BAU | DU00002559017 | [5 empty] | Tower | 76m Tower | 76m
4120A | Tmn Ara Indah (PDC) | Northern |  | Modernization |  | 2024 Q1_496 | SM | GTSB | 4.6 TSSR Approved |  | 2023-08-03 | 2023-08-21 |  | 2023-08-25 |  | Rectificating | 2023-08-28 | 2023-09-21 | E//Hazida | 2023-09-20 | Celcom Digi_RAN-GTSB-TSS-Northern-20230804-0022 | DU00002559018 |  |  | 2023-09-25 | 2023-09-25 |  | Tower | Tower | 55M | Add R8852E S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R9224E M1821(AAB) x3 | 13
4125A | Perkampungan Sg Lembu(Maxis) | Northern |  | Modernization |  | 2024 Q1_496 | SM | GTSB | 4.6 TSSR Approved |  | 2023-08-14 | 2023-08-18 |  | 2023-08-23 |  | Closed | 2023-08-23 | 2023-09-06 | E//Hazida | 2023-09-06 | Celcom Digi_RAN-GTSB-TSS-Northern-20230817-0025 | DU00002559019 |  |  | 2023-10-02 | 2023-09-30 |  | Tower | 60m 3 Legged Tower | 55 | Add R8852E S9000 x3+R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3
4151A | Yong Seng Co Sdn Bhd | Northern |  | Remote MOCN |  | 2024 Q1_496 |  | Ascentrack | 14.1 Drop (No Survey) |  |  | 2023-09-13 |  |  |  | To be Submitted |  |  |  |  | N/A - site move to BAU | DU00002559020 | [5 empty] | H-bracket pole | 6m RT (Boom) | 5m |  | 23
4195B | Jalan Padang Benggali | Northern |  | Modernization |  | 2024 Q1_496 | SM | Ascentrack | 4.6 TSSR Approved |  | 2023-08-18 | 2023-08-23 |  | 2023-08-25 |  | Closed | 2023-08-25 | 2023-09-13 | E//Hazida | 2023-09-13 | Celcom Digi_RAN-Ascentrack-TSS-Northern-20230824-0001 | DU00002559021 |  |  | 2023-09-29 | 2023-09-21 |  | Tower | 45m 3 Legged Tower | 40m | Add R8852E S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 12
4198A | Pekan Darat | Northern |  | Modernization |  | 2024 Q1_496 | ZA | Ascentrack | 4.6 TSSR Approved |  | 2023-08-30 | 2023-09-18 |  | 2023-09-29 |  | Closed | 2023-10-03 | 2023-10-25 | E//Hazida | 2023-10-25 | Celcom Digi_RAN-Ascentrack-TSS-Northern-20230824-0001 | DU00002559022 |  |  | 2023-12-15 | 2023-12-14 |  | Tower | Tower | 43m | Add R8852E S9000 x3+A9732 M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1 | 123 | 0
4199A | TUDM PRAI (PDC) | Northern |  | Modernization |  | 2024 Q1_496 | BY | GTSB | 4.6 TSSR Approved |  | 2023-08-13 | 2023-08-17 |  | 2023-08-23 |  | Closed | 2023-08-24 | 2023-09-06 | E//Hazida | 2023-09-06 | Celcom Digi_RAN-GTSB-TSS-Northern-20230817-0025 | DU00002559023 |  |  | 2023-09-22 | 2023-09-21 |  |  | 24m Lampole | 25 | Add R8852E S9000 x1+R9264H M901821 x2+R8862A S2601 x3+A9732 M1821 x1,Dismantle R8882-GUL1812 x3+R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 | 1 | 0
4209A | Kepala Batas Town | Northern |  | Modernization |  | 2024 Q1_496 | ZA | GCI | 4.6 TSSR Approved |  | 2023-08-19 | 2023-09-05 |  | 2023-09-07 |  | Closed | 2023-09-12 | 2023-10-02 | E//Hazida | 2023-10-01 | Celcom Digi_RAN-GCI-TSS-Northern-20230819-0038 | DU00002559024 |  |  | 2023-10-09 | 2023-10-09 |  | In-Building System | 6m RT (Boom) | 6 | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8860E-GU908 x1+R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8840-U216 x3 | 3 | 0
4217A | Junjong-100Q4(Celcom) | Northern |  | Modernization |  | 2024 Q1_496 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-08-10 | 2023-08-15 |  | 2023-08-22 |  | Closed | 2023-08-23 | 2023-09-06 | E//Hazida | 2023-09-05 | Celcom Digi_RAN-GTSB-TSS-Northern-20230810-0023 | DU00002559025 |  |  | 2023-11-11 | 2023-10-22 |  | Tower | 60m 4 Legged Tower | 69 | Add R8852E S9000 x1+R9264H M901821 x3+A9732 M1821 x1,Dismantle R8860E-GU908 x1+R8854E S1800(A6A) x4+R8854D S2100(A4A) x4 | 12
4222A | Bukit Panchor | Northern |  | Remote MOCN |  | 2024 Q1_496 | ZA | YPTT | 14.1 Drop (No Survey) |  |  | 2023-09-08 |  |  |  | To be Submitted |  |  | E//Hazida |  | N/A - site move to BAU | DU00002559026 | [5 empty] | Tower | 60m 3 Legged Tower | 60M |  | 123
4223A | Sg Kechil (PDC) | Northern |  | Modernization |  | 2024 Q1_496 | SM | GTSB | 4.6 TSSR Approved |  | 2023-08-13 | 2023-08-15 |  | 2023-08-18 |  | Rectificating | 2023-08-18 | 2023-08-23 | E//Hazida | 2023-08-23 | Celcom Digi_RAN-GTSB-TSS-Northern-20230817-0025 | DU00002559027 |  |  | 2023-11-15 | 2023-10-30 |  | Tower | Tower | 60 | Add R8852E S9000 x3+R8854E S1800 x3+R9224E M1821 x3,Dismantle R8892E M1821(BAA) x3
4224A | PEKAN SG KECHIL | Northern |  | Modernization |  | 2024 Q1_496 | BY | GTSB | 4.6 TSSR Approved |  | 2023-08-13 | 2023-08-21 |  | 2023-08-24 |  | Closed | 2023-08-24 | 2023-09-06 | E//Hazida | 2023-09-06 | Celcom Digi_RAN-GTSB-TSS-Northern-20230817-0025 | DU00002559028 |  |  | 2024-01-27 | 2023-11-15 |  |  | 60m 4 Legged Tower | 55 | Add R9264M M1821 x5+R8862A S2601 x2,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 |  | 12
4233A | Sungai Bakap Town | Northern |  | Modernization |  | 2024 Q1_496 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-09-01 | 2023-09-19 |  | 2023-09-21 |  | Closed | 2023-09-22 | 2023-10-30 | E//Hazida | 2023-10-27 | Celcom Digi_RAN-YPTT-TSS-Northern-20230904-0032 | DU00002559029 |  |  | 2023-10-28 | 2023-10-28 |  | In-Building System | 6m RT (Boom) | 7 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3
4234A | Jalan Tasek Valdor | Northern |  | Modernization |  | 2024 Q1_496 | HQ 1 | Ascentrack | 4.6 TSSR Approved |  | 2023-10-04 | 2023-10-06 |  | 2023-10-14 |  | Closed | 2023-10-16 | 2023-10-27 | E//Hazida | 2023-10-25 | Celcom Digi_RAN-Ascentrack-TSS-Northern-20231006-0013 | DU00002559030 |  |  | 2023-12-02 | 2023-11-30 |  | Tower | Tower | 60m | Add R9264M M1821 x1+R9264H M901821 x3+R8862A S2601 x1,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x2+R8840-U216 x3 |  | 2
4238A | Ladang Changkat | Northern |  | Modernization |  | 2024 Q1_496 |  | GCI | 4.6 TSSR Approved |  | 2023-10-31 | 2023-11-03 |  | 2023-11-08 |  | Closed | 2023-11-15 | 2023-11-20 |  | 2023-11-15 | Celcom Digi_RAN-GCI-TSS-Northern-20231101-0069 | DU00002559031 |  |  | 2023-12-13 | 2023-12-11 |  | Tower | Tower | 60 | Add R9264H M901821 x3,Dismantle R8892E M1821(BAA) x2
4247A | Bkt Tengah Industry (PDC) | Northern |  | Remote MOCN |  | 2024 Q1_496 |  | GCI | 14.1 Drop (No Survey) |  |  | 2023-09-13 |  |  |  | To be Submitted |  |  |  |  | N/A - site move to BAU | DU00002559032 | [5 empty] | Tower | Tower | 65 |  | 123
1362A | Electroscon | Central |  | Modernization |  | 2024 Q1_496 | IE | Magicell | 4.6 TSSR Approved |  | 2023-09-11 | 2023-09-14 |  | 2023-09-18 |  | Closed | 2023-09-19 | 2023-09-20 | E//Kok Keen | 2023-09-20 | CelcomDigi_RAN_Magicell_TSS_Central_20230912 | DU00002559033 |  |  | 2023-09-30 | 2023-09-29 |  | In-Building System | 6m RT (Boom) | 6M | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 1
4271A | Kg Bumbong 5(Asiaspace) | Northern |  | Modernization |  | 2024 Q1_496 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-08-20 | 2023-09-04 |  | 2023-09-06 |  | Closed | 2023-09-07 | 2023-09-15 | E//Hazida | 2023-09-14 | Celcom Digi_RAN-GCI-TSS-Northern-20230819-0038 | DU00002559034 |  |  | 2024-01-09 | 2024-01-06 |  | Tower | 45m Tower | 50 | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 2
4272A | Permatang Bera 2 | Northern |  | Modernization |  | 2024 Q1_496 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-09-01 | 2023-09-14 |  | 2023-09-18 |  | Closed | 2023-09-18 | 2023-10-27 | E//Hazida | 2023-10-26 | Celcom Digi_RAN-GCI-TSS-Northern-20230904-0044 | DU00002559035 |  |  | 2023-10-16 | 2023-10-13 |  | Tower | 60m 3 Legged Tower | 61 | Add R9264M M1821 x1+R9264H M901821 x3+R8862A S2601 x1,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8840-U216 x3++ |  | 3
4274A | Pokok Sena 2 | Northern |  | Remote MOCN |  | 2024 Q1_496 | BY | GTSB | 14.2 Drop (Done Survey) |  | 2023-12-07 | 2023-08-25 |  |  |  | To be Submitted |  |  | E//Hazida |  | N/A - site move to BAU | DU00002559036 | [5 empty] | Tower | 60m 3 Legged Tower | 61 |  | 13
2618B | Tmn Alam Megah RT | Central |  | Modernization |  | 2024 Q1_496 | AI | GTSB | 4.6 TSSR Approved |  | 2023-08-16 | 2023-08-18 |  | 2023-08-24 |  | Closed | 2023-08-25 | 2023-08-30 | E//Razif | 2023-08-30 | CelcomDigi_RAN_GTSB_TSS_Central_20230818 | DU00002559037 |  |  | 2023-10-07 | 2023-09-05 |  | Unipole | 6m Unipole RT | 7 | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 1 | 0
4280A | Guar Perahu (Maxis) | Northern |  | Remote MOCN | Modernization->Modernization(MOCN)->Remote MOCN | 2024 Q1_496 | HQ 1 | GTSB | 14.2 Drop (Done Survey) |  | 2023-12-07 | 2023-08-18 | [6 empty] | E//Hazida |  | N/A - site move to BAU | DU00002559038 | [5 empty] | Tower | 60m 3 Legged Tower | 55 |  | 123
4281A | Kg Selamat | Northern |  | Remote MOCN |  | 2024 Q1_496 | SM | YPTT | 14.1 Drop (No Survey) |  |  | 2023-09-04 |  |  |  | To be Submitted |  |  | E//Hazida |  | N/A - site move to BAU | DU00002559039 | [5 empty] | Tower | 76m 4 Legged Tower | 61m |  | 1
4282A | Pongsu Seribu | Northern |  | Modernization |  | 2024 Q1_496 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-08-23 | 2023-08-29 |  | 2023-09-02 |  | Closed | 2023-09-05 | 2023-09-15 | E//Hazida | 2023-09-14 | Celcom Digi_RAN-GTSB-TSS-Northern-20230824-0029 | DU00002559040 |  |  | 2023-09-25 | 2023-09-18 |  | Tower | 60m 4 Legged Tower | 61 | Add R8852E S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 23
4283A | Paya Keladi Tengah(Celcom) | Northern |  | Modernization |  | 2024 Q1_496 | SM | YPTT | 4.6 TSSR Approved |  | 2023-09-03 | 2023-09-22 |  | 2023-09-25 |  | Rectificating | 2023-09-26 | 2023-10-27 | E//Hazida | 2023-10-24 | Celcom Digi_RAN-YPTT-TSS-Northern-20230905-0033 | DU00002559041 |  |  | 2024-01-27 | 2024-01-08 |  |  | 60m 4 Legged Tower | 62 | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8882-GUL1812 x3+R8881 S2100 x3 | 1 | 0
4284A | Padang Menora | Northern |  | Remote MOCN |  | 2024 Q1_496 | WP | GTSB | 14.2 Drop (Done Survey) |  | 2023-12-07 | 2023-08-24 |  |  |  | To be Submitted |  |  | E//Hazida |  | N/A - site move to BAU | DU00002559042 | [5 empty] | Tower | 60m 4 Legged Tower | 60 |  | 13
4286A | Penaga Town(Maxis) | Northern |  | Remote MOCN |  | 2024 Q1_496 | ZA | GTSB | 14.2 Drop (Done Survey) | AAU Cannot Install-Change MM to BI¦owner rejected due to loading issue | 2023-12-07 | 2023-08-21 |  |  |  | To be Submitted |  |  | E//Hazida |  | N/A - site move to BAU | DU00002559043 | [5 empty] | Tower | 60m 3 Legged Tower | 54 |  |  | 3
4294A | Kg Kbg Menderung | Northern |  | Modernization |  | 2024 Q1_496 | HQ 1 | YPTT | 4.6 TSSR Approved | ¦ 0227 - SA to resubmit MOD+Decomm TP together with load comparison. ¦ 0206 - CD request 2024 simulation, Li Jie to provide TBC ¦ 0129 - Follow up update from Planning team on solution as AAU proposal is rejected | 2023-08-24 | 2023-10-02 |  | 2023-10-06 |  | Closed | 2023-10-09 | 2023-10-27 | E//Hazida | 2023-10-26 | Celcom Digi_RAN-YPTT-TSS-Northern-20230825-0029 | DU00002559044 |  |  | 2024-04-01 | 2024-01-08 |  | Tower | 60m 4 Legged Tower | 60 | Add R8852E S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 23
4300A | Bertam (REL) | Northern |  | Remote MOCN |  | 2024 Q1_496 | YZ | YPTT | 14.1 Drop (No Survey) |  |  | 2023-09-13 |  |  |  | To be Submitted |  |  | E//Hazida |  | N/A - site move to BAU | DU00002559045 | [5 empty] | Tower | 45m 4 Legged Tower | 52 |  | 123
1380B | Taman Industri Subang | Central |  | Modernization |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-08-23 | 2023-08-29 |  | 2023-09-01 |  | Closed | 2023-09-02 | 2023-09-06 | E//Sumitra | 2023-09-05 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230824 | DU00002559046 |  |  | 2023-09-10 | 2023-09-09 |  | H-bracket pole | 6m RT (Boom) | 4m | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 1 | 0
4683A | Bkt Tok Alang | Northern |  | Modernization |  | 2024 Q1_496 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-08-21 | 2023-09-04 |  | 2023-09-06 |  | Closed | 2023-09-07 | 2023-09-15 | E//Hazida | 2023-09-14 | Celcom Digi_RAN-GCI-TSS-Northern-20230822-0039 | DU00002559047 |  |  | 2023-09-20 | 2023-09-16 |  | Tower | 30m 4 Legged Tower | 33m | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x2+R8882 S1800B(B6B) x1+R8881 S2100 x3
4700A | Kg Sg Aceh | Northern |  | Modernization |  | 2024 Q1_496 | BY | GTSB | 4.6 TSSR Approved |  | 2023-08-16 | 2023-08-21 |  | 2023-08-25 |  | Closed | 2023-08-25 | 2023-09-20 | E//Hazida | 2023-09-19 | Celcom Digi_RAN-GTSB-TSS-Northern-20230817-0025 | DU00002559048 |  |  | 2023-10-06 | 2023-10-06 |  | Tower | 60m 4 Legged Tower | 70 | Add R8852E S9000 x3+A9732 M1821 x3,Dismantle R9224E M1821(AAB) x3 | 123
3761B | Sunway Mentari Business Park | Central |  | Remote MOCN |  | 2024 Q1_496 |  | DATASCO | 14.3 Drop (Done Survey + TSSR) |  | 2023-08-23 | 2023-09-06 |  | 2023-09-09 |  | Rectificating | 2024-07-18 | 2024-07-18 |  |  | CelcomDigi_RAN_Datasco_TSS_Central_20230824 | DU00002559049 | [6 empty] | 3m Bipod (RT) | 8 |  | 24
1378B | PJS 10 | Central |  | Modernization |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-10-13 | 2023-10-16 |  | 2023-10-19 |  | Closed | 2023-10-20 | 2023-10-25 | E//Kok Keen | 2023-10-23 | CelcomDigi_RAN_Datasco_TSS_Central_20230911 | DU00002559050 |  |  | 2023-10-31 | 2023-10-28 |  | Monopole | 20m Lampole | 20.6m | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 1
3232C | PJS 10 | Central |  | Remote MOCN |  | 2024 Q1_496 |  | Ascentrack | 14.2 Drop (Done Survey) |  | 2023-10-15 |  |  |  |  | To be Submitted | 2023-10-27 |  |  |  |  | DU00002559051 | [6 empty] | 24m Lampole |  |  | 3
9010A | Yeo Hong Chuan | Sarawak |  | Decomm | Modernization->On Hold->Decomm | 2024 Q1_496 | ZB | AllStar | 4.6 TSSR Approved |  | 2023-08-14 | 2023-08-22 |  | 2023-08-28 | 2024-09-11 | Closed | 2024-09-24 | 2024-10-31 | E//Hannah | 2024-10-28 | Celcom Digi_RAN-AllStar-TSS-Sarawak-20230815/0823CD-Sarawak-Allstar-BOQ Template(new contract)/0903MW-Sarawak-AllStar-BOQ Template(new contract) | DU00002559052 |  |  |  |  | 2025-11-28 | In-Building System | 6m RT (Wall Mounted Pole) | 7
9039B | Muara Tebas | Sarawak |  | Modernization |  | 2024 Q1_496 | SH | Datasco | 4.6 TSSR Approved |  | 2023-08-11 | 2023-08-16 |  | 2023-08-22 |  | Closed | 2023-08-22 | 2023-09-04 | E//Hannah | 2023-09-01 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230815 | DU00002559053 |  |  | 2023-10-27 | 2023-09-24 |  | Tower | Tower | 76 | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8860E-GU908 x2+R8882-GUL1812 x1+R8882 S1800B(B6B) x3+R8840-U216 x3 | 2 | 0
2553B | PJS 6 | Central |  | Remote MOCN |  | 2024 Q1_496 |  | Ascentrack | 14.2 Drop (Done Survey) |  | 2023-09-02 | 2023-09-13 | [8 empty] | CelcomDigi_RAN_Ascentrack_TSS_Central_20230904 | DU00002559054 | [5 empty] | Lampole | 24m Lampole | 27m |  | 23
9050B | Jln Simpang Tiga MP | Sarawak |  | Modernization |  | 2024 Q1_496 | SH | Trintel | 4.6 TSSR Approved |  | 2023-08-17 | 2023-10-13 |  | 2023-10-18 |  | Closed | 2023-10-18 | 2023-11-03 | E//Hannah | 2023-11-01 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230823 | DU00002559055 |  |  | 2023-10-27 | 2023-10-25 |  | Monopole | 30m Monopole | 30m | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R9224E M1821(AAB) x5 | 12 | 0
9052B | Ming Hee Apartment | Sarawak |  | Modernization |  | 2024 Q1_496 | SH | Datasco | 4.6 TSSR Approved |  | 2023-08-29 | 2023-09-04 |  | 2023-09-06 |  | Closed | 2023-09-06 | 2023-10-01 | E//Hannah | 2023-09-25 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230830 | DU00002559056 |  |  | 2023-11-24 | 2023-11-08 |  | In-Building System | 3m Bipod (RT) | 3 | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x4 | 3 | 0
9064B | Demak Baru Kuching | Sarawak |  | Modernization |  | 2024 Q1_496 | SH | Datasco | 4.6 TSSR Approved |  | 2023-08-24 | 2023-09-01 |  | 2023-09-07 |  | Closed | 2023-09-07 | 2023-10-01 | E//Hannah | 2023-09-25 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230830 | DU00002559057 |  |  | 2023-09-27 | 2023-09-23 |  | Monopole | 24m Lampole | 30 | Add R9264H M901821 x3,Dismantle R9224E M1821(AAB) x3
9083B | Hock Lee MP (Sacofa) | Sarawak |  | Modernization |  | 2024 Q1_496 | SH | Trintel | 4.6 TSSR Approved |  | 2023-08-14 | 2023-08-24 |  | 2023-08-29 |  | Closed | 2023-09-01 | 2023-09-08 | E//Hannah | 2023-09-08 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230815 | DU00002559058 |  |  | 2023-09-15 | 2023-09-12 |  | Monopole | 30m Monopole | 30m | Add R8852E S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 12
9110B | Tmn Riverview | Sarawak |  | Remote MOCN |  | 2024 Q1_496 |  |  | 14.2 Drop (Done Survey) | 30-4 - SOW change to remote MOCN 15-3 - ZTE planner to update slide ¦ AAU Cannot Install-S12 MM change to BI¦Site owner rejected,loading issue,Sacofa site | 2023-11-22 |  |  |  |  | To be Submitted | [5 empty] | DU00002559059 | [5 empty] | Tower | Tower | 75m |  | 0 | 12
9308A | Serjingkat Power House | Sarawak |  | Modernization |  | 2024 Q1_496 | ZB | Trintel | 4.6 TSSR Approved |  | 2023-09-11 | 2023-10-10 |  | 2023-10-13 |  | Closed | 2024-01-29 | 2024-01-30 | E//Hannah | 2024-01-29 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230913 | DU00002559060 |  |  | 2024-04-06 | 2024-03-04 |  |  | 3m RT (Wall Mounted Pole) | 120m | Add R9264H M901821 x3+R8854 S2600 x2,Dismantle R8862A S9000(A6A) x2+R8882 S1800B(B6B) x2+R8862A S1800(B6A) x2+R8862A S2100(A6A) x3+R8862A S2600(A4A) x2 |  | 12
9408A | Sg. Apong | Sarawak |  | Remote MOCN |  | 2024 Q1_496 | SH |  | 14.3 Drop (Done Survey + TSSR) |  | 2023-08-05 | 2023-08-11 |  | 2023-08-23 |  | Closed | 2023-08-24 |  | E//Hannah |  | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230804 | DU00002559061 | [5 empty] | Monopole | Tower | 30 |  | 23
9440A | Pending Heights MP | Sarawak |  | Modernization |  | 2024 Q1_496 | ZB | Trintel | 4.6 TSSR Approved |  | 2023-08-11 | 2023-08-21 |  | 2023-08-29 |  | Closed | 2023-08-30 | 2023-09-08 | E//Hannah | 2023-09-08 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230815 | DU00002559062 |  |  | 2023-09-13 | 2023-09-11 |  | Monopole | 30m Monopole | 30m | Add R8852E S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 13
9451A | Jalan Pending MP | Sarawak |  | Modernization |  | 2024 Q1_496 | ZB | Trintel | 4.6 TSSR Approved |  | 2023-08-14 | 2023-08-29 |  | 2023-09-02 |  | Closed | 2023-09-08 | 2023-10-01 | E//Hannah | 2023-09-25 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230815 | DU00002559063 |  |  | 2023-10-03 | 2023-09-20 |  | Monopole | 30m Monopole | 30m | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 12
9454A | UMW Motor MP | Sarawak |  | Modernization |  | 2024 Q1_496 | SH | Datasco | 4.6 TSSR Approved |  | 2023-08-21 | 2023-08-29 |  | 2023-09-05 |  | Closed | 2023-09-05 | 2023-09-08 | E//Hannah | 2023-09-08 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230823 | DU00002559064 |  |  | 2023-09-19 | 2023-09-12 |  | Monopole | 30m Monopole | 30 | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 3 | 0
9463A | Kg Bako | Sarawak |  | Remote MOCN |  | 2024 Q1_496 | SH |  | 14.3 Drop (Done Survey + TSSR) |  | 2023-08-07 | 2023-08-09 |  | 2023-08-18 |  | Closed | 2023-08-22 | 2023-09-08 | E//Hannah |  | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230807 | DU00002559065 | [5 empty] | Tower | 45m 3 Legged Tower | 75 |  | 23
9467A | Bintawa Industry | Sarawak |  | Modernization |  | 2024 Q1_496 | ZB | Trintel | 4.6 TSSR Approved |  | 2023-08-17 | 2023-09-13 |  | 2023-09-18 |  | Closed | 2023-09-19 | 2023-10-01 | E//Hannah | 2023-09-25 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230818 | DU00002559066 |  |  | 2023-10-31 | 2023-10-30 |  | Monopole | 30m Monopole | 30m | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 | 1
9475A | Electra House | Sarawak |  | Modernization |  | 2024 Q1_496 | SH | AllStar | 4.6 TSSR Approved |  | 2023-08-05 | 2023-08-21 |  | 2023-08-24 |  | Closed | 2023-08-25 | 2023-09-13 | E//Hannah | 2023-09-13 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230807 | DU00002559067 |  |  | 2023-09-22 | 2023-09-19 |  | In-Building System | 3m RT (Wall Mounted Pole) | 4.7m | Add R9264H M901821 x3,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x4
9999A | MSC Sarawak | Sarawak |  | Modernization |  | 2024 Q1_496 | SH | Trintel | 4.6 TSSR Approved |  | 2023-08-15 | 2023-10-13 |  | 2023-10-23 |  | Closed | 2023-10-23 | 2023-11-20 | E//Hannah | 2023-11-15 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230816 | DU00002559068 |  |  | 2024-02-29 | 2023-11-03 |  | Tower | 76m Tower | 75m | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x2,Dismantle R9224E M1821(AAB) x4 | 23
2153A | KTM Subang (REL) | Central |  | Modernization |  | 2024 Q1_496 | XH | GTSB | 4.6 TSSR Approved |  | 2023-08-21 | 2023-08-24 |  | 2023-08-29 |  | Closed | 2023-09-01 | 2023-09-06 | E//Razif | 2023-09-06 | CelcomDigi_RAN_GTSB_TSS_Central_20230823 | DU00002559069 |  |  | 2023-09-10 | 2023-09-09 |  | Monopole | 30m Monopole | 31M | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 2 | 0
2344A | USJ 14 | Central |  | Modernization |  | 2024 Q1_496 | XH | Ascentrack | 4.6 TSSR Approved |  | 2023-08-28 | 2023-09-06 |  | 2023-09-09 |  | Closed | 2023-09-11 | 2023-09-12 | E//Kok Keen | 2023-09-12 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230825 | DU00002559070 |  |  | 2023-09-30 | 2023-09-22 |  | In-Building System | 3m Bipod (RT) | 5.1 | Add R9264M M1821 x3,Dismantle R8882 S1800B(B6B) x3++R8881 S2100 x3+
4641C | Perda Timur | Northern |  | Remote MOCN |  | 2024 Q1_496 |  | GCI | 14.1 Drop (No Survey) |  |  | 2023-09-21 |  |  |  | To be Submitted | [5 empty] | DU00002559071 | [6 empty] | 30m Monopole | 5.8+3.5
4719A | Pulau Aman (Penang Bridge 2) | Northern |  | Remote MOCN | Modernization->Modernization(MOCN)->Remote MOCN | 2024 Q1_496 |  | GTSB | 14.2 Drop (Done Survey) |  | 2023-12-07 | 2023-09-21 |  |  |  | To be Submitted |  |  |  |  | N/A - site move to BAU | DU00002559072 | [5 empty] | Tower | 45m 3 Legged Tower | 77
3746A | Jalan PJS 10_11 | Central |  | Modernization |  | 2024 Q1_496 | AI | Ascentrack | 4.6 TSSR Approved |  | 2023-08-29 | 2023-09-04 |  | 2023-09-07 |  | Closed | 2023-09-07 | 2023-09-07 | E//Kok Keen | 2023-09-07 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230901 | DU00002559073 |  |  | 2023-12-20 | 2023-12-19 |  | In-Building System | 3m Bipod (RT) | 6.4 | Add R9264M M1821 x3,Dismantle R8892E M1821(BAA) x3
1934B | Pusat Tuisyen Sri Setia | Central |  | Modernization |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-09-06 | 2023-09-07 |  | 2023-09-11 |  | Closed | 2023-09-12 | 2023-10-02 | E//Kok Keen | 2023-09-13 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230823 | DU00002559074 |  |  | 2023-10-04 | 2023-10-04 |  | In-Building System | 3m Boom (RT) | 6.1 | Add R9264M M1821 x3,Dismantle R8882 S1800B(B6B) x3
2610B | Surau Al-Muttaqun USJ 12 | Central |  | Modernization |  | 2024 Q1_496 | AI | Ascentrack | 4.6 TSSR Approved |  | 2023-08-29 | 2023-09-04 |  | 2023-09-06 |  | Closed | 2023-09-07 | 2023-10-01 | E//Kok Keen | 2023-09-21 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230901 | DU00002559075 |  |  | 2023-10-19 | 2023-10-16 |  | Lampole | 24m Lampole | 20m | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3
9145B | SMI Industrial Park | Sarawak |  | Modernization |  | 2024 Q1_496 | SH | AllStar | 4.6 TSSR Approved |  | 2023-08-07 | 2023-08-15 |  | 2023-08-23 |  | Closed | 2023-08-24 | 2023-09-08 | E//Hannah | 2023-09-08 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230807 | DU00002559076 |  |  | 2023-10-28 | 2023-10-21 |  | Monopole | Tower | 30 | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8882-GUL1812 x2+R8882 S1800(B) x1+R8862A S2100(A6A) x3 | 3
9147B | Sejingkat Industrial | Sarawak |  | Modernization |  | 2024 Q1_496 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-08-11 | 2023-08-21 |  | 2023-08-23 |  | Closed | 2023-08-23 | 2023-10-18 | E//Hannah | 2023-09-25 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230815 | DU00002559077 |  |  | 2023-10-03 | 2023-09-21 |  |  | Tower | 45 | Add R8852E S9000 x3+R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3
3191B | Subang Andaman (REL) | Central |  | Modernization |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-09-05 | 2023-09-08 |  | 2023-09-13 |  | Closed | 2023-09-21 | 2023-10-27 | E//Kok Keen | 2023-09-21 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230907 | DU00002559078 |  |  | 2023-09-28 | 2023-09-28 |  | In-Building System | 6m Unipole RT | 6 | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8882 S1800(B) x2+R8882 S1800B(B6B) x1+R8862A S2100(A6A) x3 | 3 | 0
3283A | TMN_IND_UEP1 | Central |  | Modernization |  | 2024 Q1_496 | MA | YPTT | 4.6 TSSR Approved | 21/01 Change RRU Solution | 2023-08-24 | 2023-10-09 |  | 2024-01-19 |  | Closed | 2024-01-21 | 2024-01-23 | E//Razif | 2024-01-22 | CelcomDigi_RAN_YPTT_TSS_Central_20230829 | DU00002559079 |  |  | 2024-05-24 | 2024-05-21 |  | Wall mount boom | 3m Boom (RT) | 3M | Add R9264H M901821 x1+A9732 M1821 x2,Dismantle R8862A S9000(A6A) x1+R8894E M1821(A8A) x3 | 23 | 0
9151B | TM Demak Laut (REL) | Sarawak |  | Modernization |  | 2024 Q1_496 | SH | Trintel | 4.6 TSSR Approved |  | 2023-08-21 | 2023-09-26 |  | 2023-10-01 |  | Closed | 2023-10-02 | 2023-10-06 | E//Hannah | 2023-10-05 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230823 | DU00002559080 |  |  | 2024-02-29 | 2024-01-31 |  | Tower | Tower | 65m | Add A9732 M1821 x3,Dismantle R8882 S1800B(B6B) x3+R8862A S1800(B6A) x1+R8862A S2100(A6A) x4+R8862A S2601(A6A) x1 | 123 | 0
3254B | Jln Jaya Setia (REL) | Central |  | Remote MOCN |  | 2024 Q1_496 | CR | YPTT | 14.3 Drop (Done Survey + TSSR) |  | 2023-08-23 | 2023-08-29 |  | 2023-09-01 |  | Closed | 2023-09-04 | 2023-09-06 | E//Razif |  | CelcomDigi_RAN_YPTT_TSS_Central_20230824 | DU00002559081 | [5 empty] | In-Building System | 3m Boom (RT) | 5m
3323B | KDU Glenmarie RT | Central |  | Decomm | TBD->Decomm | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-09-04 | 2023-09-11 |  | 2024-02-15 | 2024-02-15 | Under Approval | 2024-02-16 | 2025-07-29 | E//Razif | 2024-02-20 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230905 | DU00002559082 |  |  |  |  | 2024-08-26 | In-Building System | 3m Boom (RT) | 4
3433A | SUBANG_INDAH | Central |  | Modernization |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-09-02 | 2023-09-06 |  | 2023-09-10 |  | Closed | 2023-09-12 | 2023-09-13 | E//Kok Keen | 2023-09-13 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230904 | DU00002559083 |  |  | 2023-12-27 | 2023-12-24 |  | In-Building System | 3m Bipod (RT) | 5.9 | Add R8852E S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 12 | 0
9160B | Demak Laut Ind 2 | Sarawak |  | Modernization |  | 2024 Q1_496 | SH | Datasco | 4.6 TSSR Approved |  | 2023-08-29 | 2023-09-14 |  | 2023-09-18 |  | Closed | 2023-09-18 | 2023-10-01 | E//Hannah | 2023-09-25 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230830 | DU00002559084 |  |  | 2023-11-08 | 2023-10-31 |  | Monopole | Monopole | 24 | Add R9264M M1821 x2+R9264H M901821 x3+R8862A S2601 x1,Dismantle R8882 S1800B(B6B) x3+R8862A S1800(B6A) x1+R8862A S2100(A6A) x4 |  | 12
3531B | Masjid Taman Subang Mewah USJ1 | Central |  | Decomm | Modernization->On Hold->Decomm->On Hold->Decomm | 2024 Q1_496 | HW | Ascentrack | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦Space constraint need to 3531B proposal change anchor | 2023-08-29 | 2023-09-05 |  |  | 2025-02-06 |  | 2025-02-18 | 2025-06-04 | E//Sumitra | 2025-02-20 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230901 | DU00002559085 | BAU_S1_Change MM to BI_Space constraint_XAIR NETWORK |  |  |  | 2025-04-29 | Lampole | 24m Lampole | 20 |  |  | 2
3621A | Monfort Boys Town (REL) | Central |  | Modernization |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-08-31 | 2023-09-04 |  | 2023-09-07 |  | Closed | 2023-09-07 | 2023-12-04 | E//Razif | 2023-12-01 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230901 | DU00002559086 |  |  | 2024-02-06 | 2024-02-06 |  | H-bracket pole | 3m Boom (RT) | 8.7m | Add R8852E S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R9224E M1821(AAB) x3 | 13
3612B | Taman Subang Mas | Central |  | Remote MOCN |  | 2024 Q1_496 | MA | YPTT | 14.3 Drop (Done Survey + TSSR) | AAU Cannot Install-Change MM to BI¦AAU can not install | 2023-08-23 | 2023-09-01 |  | 2023-09-07 |  | Closed |  |  |  |  | CelcomDigi_RAN_YPTT_TSS_Central_20230824 | DU00002559087 | BAU_S2_Change MM to BI_Space constraint_Digi OB |  |  |  |  | Unipole | 6m Unipole RT | 6M |  | 0 | 13
4305C | Paya Keladi (REL) | Northern |  | Modernization |  | 2024 Q1_496 | BY | Ascentrack | 4.6 TSSR Approved |  | 2023-08-17 | 2023-10-13 |  | 2023-10-18 |  | Closed | 2023-10-19 | 2023-10-27 | E//Hazida | 2023-10-24 | Celcom Digi_RAN-Ascentrack-TSS-Northern-20230824-0001 | DU00002559088 |  |  | 2024-01-23 | 2024-01-05 |  | Tower | 45m 3 Legged Tower | 45M | Add R8852E S9000 x4+R8894E M1821 x4,Dismantle R8882 S1800(B) x1+R8882 S1800B(B6B) x3+R8881 S2100 x4
9116B | Plaza Merdeka Outdoor | Sarawak |  | Modernization |  | 2024 Q1_496 | SH | AllStar | 4.6 TSSR Approved |  | 2023-08-09 | 2023-08-15 |  | 2023-08-25 |  | Closed | 2023-08-25 | 2023-09-13 | E//Hannah | 2023-09-12 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230808 | DU00002559089 |  |  | 2023-09-27 | 2023-09-22 |  | In-Building System | 3m RT (Wall Mounted Pole) | 4 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3+R8882 S1800B(B6B) x3+R8854D S2100(A4A) x3
4349D | Persiaran Bertam Perdana RT | Northern |  | Modernization |  | 2024 Q1_496 | SM | Ascentrack | 4.6 TSSR Approved |  | 2023-08-16 | 2023-08-21 |  | 2023-08-23 |  | Rectificating | 2023-08-23 | 2023-09-06 | E//Hazida | 2023-09-05 | Celcom Digi_RAN-Ascentrack-TSS-Northern-20230824-0001 | DU00002559090 |  |  | 2024-01-09 | 2024-01-05 |  | Portables BTS | 3m Boom (RT) | 9m | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x4
4386C | Taman Alma | Northern |  | Modernization |  | 2024 Q1_496 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-09-13 | 2023-09-16 |  | 2023-09-21 |  | Closed | 2023-09-22 | 2023-10-27 | E//Hazida | 2023-10-24 | Celcom Digi_RAN-GCI-TSS-Northern-20230913-0049 | DU00002559091 |  |  | 2023-10-21 | 2023-09-26 |  | Guide mast | 3m Bipod (RT) | 12 | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
4665C | Kg Udang (REL) | Northern |  | Modernization |  | 2024 Q1_496 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-09-01 | 2023-09-04 |  | 2023-09-08 |  | Closed | 2023-09-11 | 2023-10-02 | E//Hazida | 2023-10-01 | Celcom Digi_RAN-GTSB-TSS-Northern-20230904-0032 | DU00002559092 |  |  | 2023-11-17 | 2023-11-02 |  | Tower | 60m 4 Legged Tower | 61 | Add R9264M M1821 x1+R9264H M901821 x3+R8862A S2601 x4,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 1
9616A | Lee Sing Demak Laut (REL) | Sarawak |  | Modernization |  | 2024 Q1_496 | SH | Datasco | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦sacofa lampole not allow to add AAU | 2023-08-19 | 2023-08-25 |  | 2023-09-08 |  | Closed | 2023-09-08 | 2023-10-01 | E//Hannah | 2023-09-25 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230821 | DU00002559093 | NIC_S2_Change MM to BI_owner reject_SACOFA SDN BHD |  | 2023-11-01 | 2023-10-25 |  |  | 30m Rapole | 31 | Add R9264M M1821 x2+R9264H M901821 x3+R8862A S2600(A4A) x2,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 |  | 13
3762B | Masjid Al-Husna | Central |  | Modernization |  | 2024 Q1_496 | CR | Ascentrack | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦Space issue AAU can not install | 2023-08-28 | 2023-09-04 |  | 2023-09-18 |  | Closed | 2023-09-19 | 2024-07-10 | E//Sumitra | 2023-11-07 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230829 | DU00002559094 | NIC_S2_Change MM to BI_Space constraint_SBC KJS |  | 2023-10-21 | 2023-10-12 |  | Lampole | 24m Lampole | 25 | Add R9264M M1821 x6+R8862A S2601 x2,Dismantle R8892E M1821(BAA) x4 |  | 13
9099B | Jln Pelabuhan | Sarawak |  | Remote MOCN |  | 2024 Q1_496 | ZB |  | 14.3 Drop (Done Survey + TSSR) | AAU Cannot Install-Change MM to BI¦sacofa lampole not allow to add AAU | 2023-08-21 | 2023-08-24 |  | 2023-08-28 |  | Closed | 2023-08-28 | 2023-09-20 | E//Hannah |  | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230823 | DU00002559095 | NIC_S1_Change MM to BI_owner reject_SACOFA SDN BHD |  |  |  |  | Monopole | Rapole | 30 |  |  | 3
3091B | Masjid Al-Munawwarah | Central |  | Modernization | Modernization->Site Out->Modernization | 2024 Q1_496 | IE | Magicell | 4.6 TSSR Approved |  | 2023-08-24 | 2023-09-08 |  | 2023-09-13 |  | Closed | 2023-09-15 | 2023-09-21 | E//Razif | 2023-09-21 | CelcomDigi_RAN_Magicell_TSS_Central_20230825 | DU00002559096 |  |  | 2025-09-11 | 2025-08-21 |  | Minaret | 30m Minaret | 30m | Add R8894E M1821x3+R8862A S2601x3,Dismantle R8882 S1800B(B6B) x3++R8881 S2100 x3+ | 0 | 0
4528C | Bkt Tengah (REL) | Northern |  | Modernization |  | 2024 Q1_496 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-09-08 | 2023-09-16 |  | 2023-09-19 |  | Closed | 2023-09-20 | 2023-10-30 | E//Hazida | 2023-10-27 | Celcom Digi_RAN-GCI-TSS-Northern-20230911-0047 | DU00002559097 |  |  | 2024-02-02 | 2023-11-16 |  | Monopole | 30m Monopole | 30 | Add R9264M M1821 x1+R9264H M901821 x3+R8862A S2601 x4,Dismantle R8882 S1800B(B6B) x3++R8881 S2100 x3+ |  | 3
4532C | Pmtg Sintok (REL) | Northern |  | Modernization |  | 2024 Q1_496 | BY | Ascentrack | 4.6 TSSR Approved |  | 2023-09-06 | 2023-10-16 |  | 2023-10-20 |  | Closed | 2023-10-30 | 2023-11-06 | E//Ajay | 2023-11-03 | Celcom Digi_RAN-Ascentrack-TSS-Northern-20230907-0008 | DU00002559098 |  |  | 2024-01-14 | 2024-01-09 |  | Tower | 45M Tower | 45 | Add R9264M M1821 x2+R9264H M901821 x3+R8854 S2600 x3,Dismantle R8894E M1821(A8A) x3 |  | 13
4478C | Tmn Bertam Pedana | Northern |  | Modernization |  | 2024 Q1_496 | BY | Ascentrack | 4.6 TSSR Approved |  | 2023-08-18 | 2023-08-21 |  | 2023-08-23 |  | Closed | 2023-08-29 | 2023-10-31 | E//Hazida | 2023-10-31 | Celcom Digi_RAN-Ascentrack-TSS-Northern-20230824-0001 | DU00002559099 |  |  | 2024-01-12 | 2024-01-10 |  | Lampole | 24m Lampole | 30m | Add R8852E S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8892N M1821(BAB) x3 | 12
4231B | Kg Wellesley | Northern |  | Modernization |  | 2024 Q1_496 | HQ 1 | Ascentrack | 4.6 TSSR Approved |  | 2023-09-01 | 2023-09-15 |  | 2023-09-21 |  | Closed | 2023-09-22 | 2023-10-30 | E//Hazida | 2023-10-27 | Celcom Digi_RAN-Ascentrack-TSS-Northern-20230904-0006 | DU00002559100 |  |  | 2023-11-11 | 2023-10-16 |  | Tower | Tower | 46m | Add R9264M M1821 x1+R9264H M901821 x3,Dismantle R9224E M1821(AAB) x3 |  | 3
4574C | Tingkat Selamat 3 | Northern |  | Remote MOCN | Modernization->Modernization(MOCN)->Remote MOCN | 2024 Q1_496 |  | CCSMY | 14.1 Drop (No Survey) |  |  | 2023-09-13 |  |  |  | To be Submitted |  |  |  |  | N/A - site move to BAU | DU00002559101 | [5 empty] | Tower | Tower | 45m |  | 13
4575C | Bandar Tasik Mutiara | Northern |  | Remote MOCN |  | 2024 Q1_496 | SM | GTSB | 14.2 Drop (Done Survey) |  | 2023-12-07 | 2023-08-16 |  |  |  | To be Submitted |  |  | E//Hazida |  | N/A - site move to BAU | DU00002559102 | [5 empty] | Tower | 25m pBTS | 31 |  | 1
4373C | Batu Kawan Cassia | Northern |  | Modernization |  | 2024 Q1_496 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-09-21 | 2023-10-02 |  | 2023-10-06 |  | Closed | 2023-10-09 | 2023-10-27 | E//Hazida | 2023-10-26 | Celcom Digi_RAN-GTSB-TSS-Northern-20230922-0040 | DU00002559103 |  |  | 2023-10-25 | 2023-10-23 |  | Monopole | 30m Monopole | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
4581C | Sg Bakap (REL) | Northern |  | Modernization |  | 2024 Q1_496 | SM | GTSB | 4.6 TSSR Approved |  | 2023-08-27 | 2023-09-01 |  | 2023-09-06 |  | Rectificating | 2023-09-07 | 2023-10-02 | E//Hazida | 2023-10-01 | Celcom Digi_RAN-GTSB-TSS-Northern-20230828-0031 | DU00002559104 |  |  | 2023-10-27 | 2023-10-26 |  | Tower | 30m Monopole | 60 | Add R8852E S9000 x3+A9732 M1821 x3,Dismantle R8892E M1821(BAA) x3 | 123 | 0
4634C | SMK Dato Hj Ahmad Badaw | Northern |  | Decomm | Modernization->On hold->Decomm | 2024 Q1_496 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-08-23 | 2023-08-25 |  | 2023-08-30 |  | Closed | 2023-08-31 | 2023-09-15 | E//Hazida | 2024-06-28 | Celcom Digi_RAN-CCSMY-Standard PR TSS-Northern-20230824-0035 (Special case- TSS Ran is for Modernization due to subcon already done survey for SOW Modernization)/0612Northern-CCSMY-BOQ Template (template)/Celcom Digi_RAN-CCSMY-TSS-Northern-20241017_New Contract | DU00002559105 |  |  |  |  | 2024-04-05 | Lampole | Tower | 30
9320B | The Isthmus Kuching (REL) | Sarawak |  | Modernization |  | 2024 Q1_496 | SH | Datasco | 4.6 TSSR Approved |  | 2023-08-28 | 2023-08-30 |  | 2023-09-04 |  | Closed | 2023-09-04 | 2023-09-08 | E//Hannah | 2023-09-08 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230830 | DU00002559106 |  |  | 2023-09-14 | 2023-09-12 |  | Monopole | 30m Rapole | 30 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
3373C | Sunway PJS7 (REL) | Central |  | Modernization |  | 2024 Q1_496 | XH | Ascentrack | 4.6 TSSR Approved |  | 2023-08-30 | 2023-09-13 |  | 2023-09-16 |  | Closed | 2023-09-19 | 2023-09-21 | E//Sumitra | 2023-09-20 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230901 | DU00002559107 |  |  | 2023-10-21 | 2023-10-18 |  | Unipole | 6m Unipole RT | 6.6m | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
4652C | Bandar Cassia RT | Northern |  | Modernization |  | 2024 Q1_496 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-10-20 | 2023-10-16 |  | 2023-10-23 |  | Closed | 2023-10-24 | 2023-10-27 | E//Hazida | 2023-10-27 | Celcom Digi_RAN-GTSB-TSS-Northern-20231022-0054 | DU00002559108 |  |  | 2023-12-14 | 2023-12-13 |  | Pole | 24m Lampole | 38m | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 1
3468C | SS19 Billboard (REL) | Central |  | Modernization |  | 2024 Q1_496 | XH | GTSB | 4.6 TSSR Approved |  | 2023-08-28 | 2023-09-04 |  | 2023-09-07 |  | Closed | 2023-09-07 | 2023-10-20 | E//Kok Keen | 2023-10-20 | CelcomDigi_RAN_GTSB_TSS_Central_20230829 | DU00002559109 |  |  | 2023-10-05 | 2023-10-02 |  |  | Billboard | 30m | Add R9264M M1821 x4,Dismantle R8862A S1800(B6A) x4+R8862A S2100(A6A) x4
3739C | LDP Cable Bridge Laguna BB (REL) | Central |  | Modernization |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-09-18 | 2023-09-21 |  | 2023-09-25 |  | Closed | 2023-09-25 | 2023-10-02 | E//Sumitra | 2023-09-27 | Celcom Digi_RAN-Ascentrack-TSS-Central-20230919 | DU00002559110 |  |  | 2023-10-16 | 2023-10-07 |  | BillBoard | Billboard | 6 | Add R8852E S9000 x3+A9732 M1821 x3,Dismantle R8854 S2600(A4A) x3+R8894E M1821(A8A) x6 | 123
4668C | Honda Batu Kawan | Northern |  | Remote MOCN | Modernization->Modernization(MOCN)->Remote MOCN | 2024 Q1_496 | ZA | Ascentrack | 14.1 Drop (No Survey) |  |  | 2023-09-01 |  |  |  | To be Submitted |  |  | E//Hazida |  | N/A - site move to BAU | DU00002559111 | [5 empty] | Pole | 30m Monopole | 37m |  | 123
4793C | Sungai Dua Exit UM (REL) | Northern |  | Remote MOCN | Modernization->Modernization(MOCN)->Remote MOCN | 2024 Q1_496 | ZA | GCI | 14.1 Drop (No Survey) | AAU Cannot Install-S23 MM change to BI¦TP rejected due to loading issue |  | 2023-08-21 |  |  |  | To be Submitted |  |  | E//Hazida |  | N/A - site move to BAU | DU00002559112 | [5 empty] | Monopole | 30m Monopole | 30 |  | 23
4964C | Taman Seri Bistari | Northern |  | Modernization |  | 2024 Q1_496 |  | GCI | 4.6 TSSR Approved |  | 2023-09-06 | 2023-10-30 |  | 2023-11-08 |  | Closed | 2023-11-08 | 2023-11-14 | E//Hazida | 2023-11-10 | Celcom Digi_RAN-GCI-TSS-Northern-20230907-0046 | DU00002559113 |  |  | 2023-12-13 | 2023-12-12 |  | In-Building System | 3m Boom (RT) | 9m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
3719C | Taipan (REL) | Central |  | Modernization |  | 2024 Q1_496 | AI | GTSB | 4.6 TSSR Approved |  | 2023-08-24 | 2023-08-28 |  | 2023-08-31 |  | Closed | 2023-09-01 | 2023-09-01 | E//Razif | 2023-09-01 | CelcomDigi_RAN_GTSB_TSS_Central_20230825 | DU00002559114 |  |  | 2023-12-19 | 2023-12-07 |  | Portables BTS | 3m Boom (RT) | 6M | Add R9264M M1821 x5+R8862A S2601 x2,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 13
3730C | Subang HiTech Shoplot (REL) | Central |  | Modernization |  | 2024 Q1_496 | AI | GTSB | 4.6 TSSR Approved |  | 2023-08-23 | 2023-08-25 |  | 2023-08-30 |  | Closed | 2023-08-30 | 2023-09-01 | E//Razif | 2023-09-01 | CelcomDigi_RAN_GTSB_TSS_Central_20230824 | DU00002559115 |  |  | 2023-12-09 | 2023-12-09 |  | In-Building System | 3m Boom (RT) | 6M | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
3314A6 | pBTS Taman Industri Subang | Central |  | Modernization |  | 2024 Q1_496 | AI | GTSB | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦pBTS loading issue,AAU cannot install | 2023-08-22 | 2023-08-24 |  | 2023-08-30 |  | Closed | 2023-09-21 | 2023-10-19 | E//Kok Keen | 2023-10-19 | CelcomDigi_RAN_GTSB_TSS_Central_20230823 | DU00002559116 | NIC_S1_Change MM to BI_loading issue_Digi OB |  | 2023-09-30 | 2023-09-28 |  | Tower | 25m pBTS | 24m | Add R9264M M1821 x1+R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 1
4087D | Kg Changkat Jawi (REL) | Northern |  | Modernization |  | 2024 Q1_496 | BY | Ascentrack | 4.6 TSSR Approved |  | 2023-08-22 | 2023-08-24 |  | 2023-08-29 |  | Closed | 2023-08-30 | 2023-10-02 | E//Hazida | 2023-10-01 | Celcom Digi_RAN-Ascentrack-TSS-Northern-20230824-0002 | DU00002559117 |  |  | 2024-01-02 | 2023-10-31 |  | Tower | 76m 4 Legged Tower | 60m | Add R9264H M901821 x4,Dismantle R8882 S1800B(B6B) x4+R8862A S2100(A6A) x4
9464A | Sg Bako | Sarawak |  | Modernization |  | 2024 Q1_496 | SH | Datasco | 4.6 TSSR Approved |  | 2023-08-08 | 2023-08-08 |  | 2023-08-10 |  | Closed | 2023-08-10 | 2023-09-01 | E//Hannah | 2023-09-01 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230808 | DU00002559118 |  |  | 2023-09-11 | 2023-09-07 |  |  | 45m 3 Legged Tower | 76 | Add R8854E S1800 x3+R9224E M1821 x3,Dismantle R8894E M1821(A8A) x3
1214C | Taipan | Central |  | Remote MOCN |  | 2024 Q1_496 |  | GTSB | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559119 | [6 empty] | 3m Boom (RT) |  |  | 1
1216C | Subang Alam | Central |  | Modernization |  | 2024 Q1_496 | SS | Magicell | 4.6 TSSR Approved |  | 2023-10-10 | 2023-10-11 |  | 2023-10-13 |  | Closed | 2023-10-16 | 2023-11-29 | E//Razif | 2023-11-27 | CelcomDigi_RAN_Magicell_TSS_Central_20231011 | DU00002559120 |  |  | 2024-01-26 | 2024-01-10 |  | Monopole | landside | 30M | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x4
4237D | Design Village Outlet Mall PDC (REL) | Northern |  | Remote MOCN | Modernization->Modernization(MOCN)->Remote MOCN | 2024 Q1_496 |  | GTSB | 14.2 Drop (Done Survey) |  | 2023-12-07 | 2023-09-04 |  |  |  | To be Submitted |  |  |  |  | N/A - site move to BAU | DU00002559121 | [5 empty] | Monople Tree | 36m Monopole | 37 |  | 1
9976A | Kenyalang Park | Sarawak |  | Modernization |  | 2024 Q1_496 | SH | Datasco | 4.6 TSSR Approved |  | 2023-11-29 | 2023-11-30 |  | 2023-12-12 |  | Closed | 2023-12-13 | 2024-01-16 | E//Hannah | 2024-01-16 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231206 | DU00002559122 |  |  | 2024-01-17 | 2023-12-29 |  | In-Building System | 3m Boom (RT) | 6 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
4388D | Taman Gua Perahu | Northern |  | Modernization |  | 2024 Q1_496 | SM | YPTT | 4.6 TSSR Approved |  | 2023-09-02 | 2023-09-12 |  | 2023-09-15 |  | Rectificating | 2023-09-19 | 2023-10-27 | E//Hazida | 2023-10-26 | Celcom Digi_RAN-YPTT-TSS-Northern-20230904-0032 | DU00002559123 |  |  | 2023-09-29 | 2023-09-25 |  | Tower | 45m Tower | 50m | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 13(S1 -> S3,S2->S1,S3->S2,,need rename sector ID,FDD MM@NEW S1S3)
1572C | LRT Subang Jaya | Central |  | Remote MOCN | Modernization->Modernization(MOCN)->Remote MOCN | 2024 Q1_496 |  | GTSB | 14.2 Drop (Done Survey) |  | 2023-10-26 |  |  |  |  | To be Submitted | [5 empty] | DU00002559124 | [6 empty] | landside |  |  | 3
4409D | Hulubalang | Northern |  | Remote MOCN |  | 2024 Q1_496 | BY | CCSMY | 14.1 Drop (No Survey) |  |  | 2023-09-01 |  |  |  | To be Submitted |  |  | E//Hazida |  | N/A - site move to BAU | DU00002559125 | [5 empty] | Monopole | 60M Tower | 30m
4588D | PMTG Sintok 2 (REL) | Northern |  | Modernization |  | 2024 Q1_496 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-08-20 | 2023-08-23 |  | 2023-08-26 |  | Closed | 2023-08-28 | 2023-09-20 | E//Hazida | 2023-09-19 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230821-0032 | DU00002559126 |  |  | 2024-01-10 | 2024-01-08 |  | Pole | landside | 8 | Add R8852E S9000 x3+R8854E S1800 x3
4596D | Jarak Atas | Northern |  | Remote MOCN | Modernization->Modernization(MOCN)->Remote MOCN | 2024 Q1_496 |  | YPTT | 14.1 Drop (No Survey) |  |  | 2023-09-08 |  |  |  | To be Submitted |  |  |  |  | N/A - site move to BAU | DU00002559127 | [5 empty] | Tower | 60M Tower | 46 |  | 23
4598D | Sg Duri | Northern |  | Modernization |  | 2024 Q1_496 | BY | GTSB | 4.6 TSSR Approved |  | 2023-08-13 | 2023-08-21 |  | 2023-08-25 |  | Closed | 2023-08-28 | 2023-10-03 | E//Hazida | 2023-10-03 | Celcom Digi_RAN-GTSB-TSS-Northern-20230817-0025 | DU00002559128 |  |  | 2023-11-13 | 2023-10-28 |  | Monople Tree | landside | 45 | Add R8852E S9000 x1+R9264H M901821 x2+R8862A S2601 x3+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 2 | 0
4631D | Taman Kuala Muda Edotco Tower (REL) | Northern |  | Modernization |  | 2024 Q1_496 | SM | YPTT | 4.6 TSSR Approved |  | 2023-11-16 | 2023-11-07 |  | 2023-11-16 |  | Rectificating | 2023-11-17 | 2023-11-22 | E//Hazida | 2023-11-21 | Celcom Digi_RAN-YPTT-TSS-Northern-20231118-0043 | DU00002559129 |  |  | 2024-01-15 | 2024-01-10 |  |  | TBC | 45 | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R9224E M1821(AAB) x3 | 13
B02808 | B061I_B02808OD_LRT_USJ7 | Central |  | Decomm |  | 2024 Q1_496 | AI | DATASCO | 4.6 TSSR Approved |  | 2024-05-20 |  |  |  | 2024-05-20 |  | 2024-05-24 | 2024-07-19 | CD//Sapian | 2024-06-10 | CelcomDigi_RAN_Datasco_TSS_Central_20240528 | DU00002559130 |  |  |  |  | 2024-11-30 |  | BOOM
P00600 | P034B_P00600OD_MASJIDABDULLAHFAHIM | Northern |  | Decomm |  | 2024 Q1_496 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-09-27 |  |  |  | 2023-10-07 |  | 2023-10-09 | 2023-10-27 | CD//Affendi | 2023-10-17 | Celcom Digi_RAN-GTSB-TSS-Northern-20231002-0042 | DU00002559131 |  |  |  |  | 2023-11-29 |  | BOOM
P00112 | P034B_P00112OD_BERTAMEXIT | Northern |  | Decomm |  | 2024 Q1_496 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-09-27 |  |  |  | 2023-10-07 |  | 2023-10-09 | 2023-10-27 | CD//Affendi | 2023-10-17 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20240208-0092/Celcom Digi_RAN-GTSB-TSS-Northern-20231002-0042 | DU00002559132 |  |  |  |  | 2024-01-31 |  | BOOM
P00460 | P032A_P00460OD_TAMAN_TASEK_MUTIARA | Northern |  | Decomm |  | 2024 Q1_496 | BY | YPTT | 4.6 TSSR Approved |  | 2023-11-08 |  |  |  | 2024-01-22 |  | 2024-01-23 | 2024-03-12 | CD//Affendi | 2024-01-30 | Celcom Digi_RAN-YPTT-TSS-Northern-20231122-0044 | DU00002559133 |  |  |  |  | 2023-11-08 |  | MONOPOLE
B02575 | B061I_B02575OD_LRTWAWASAN | Central |  | Decomm |  | 2024 Q1_496 | BY | GCI | 4.6 TSSR Approved |  | 2024-07-02 |  |  |  | 2024-07-10 |  | 2024-07-11 | 2025-03-11 | CD//Ali Akaram | 2024-07-25 | PR raised | DU00002559134 |  |  |  |  | 2024-08-26 |  | UNIPOLE
P00095 | P034B_P00095OD_TMNBERTAM | Northern |  | Decomm |  | 2024 Q1_496 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-09-27 |  |  |  | 2023-10-13 |  | 2023-10-24 | 2023-11-23 | CD//Affendi | 2023-10-27 | Celcom Digi_RAN-GTSB-TSS-Northern-20231002-0042 | DU00002559135 |  |  |  |  | 2024-01-30 |  | TOWER
B00787 | B061H_B00787OD_SS12SBJ | Central |  | Decomm |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-01-29 |  |  |  | 2024-02-01 |  | 2024-02-02 | 2024-02-23 | CD//Ali Akaram | 2024-02-15 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240202 | DU00002559136 |  |  |  |  | 2024-01-26 |  | TRIPOD
B02683 | B061H_B02683OD_INDAH_VILLA_TS | Central |  | Decomm |  | 2024 Q1_496 | IE | DATASCO | 4.6 TSSR Approved |  | 2023-10-16 |  |  |  | 2024-04-04 |  | 2023-12-18 | 2024-07-12 | CD//Norhaliza | 2024-01-02 | CelcomDigi_RAN_Datasco_TSS_Central_20231213 | DU00002559137 |  |  |  |  | 2023-12-27 |  | BOOM
B02673 | B061H_B02673OD_JLN19_SHOPLOT_TS | Central |  | Decomm |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-08-18 |  |  |  | 2024-03-20 |  | 2023-12-18 | 2024-04-24 | CD//Ali Akaram | 2024-01-09 | CelcomDigi_RAN_Datasco_TSS_Central_20231213 | DU00002559138 |  |  |  |  | 2023-10-27 |  | BOOM
B02672 | B061H_B02672OD_FAVELLAFAVCO_TS | Central |  | Decomm |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-10-06 |  |  |  | 2024-03-13 |  | 2023-12-20 | 2024-05-27 | CD//Ali Akaram | 2024-01-02 | CelcomDigi_RAN_Datasco_TSS_Central_20231213 | DU00002559139 |  |  |  |  | 2023-10-26 |  | BOOM
B02457 | B061I_B02457OD_JLNPUTRAMURNI | Central |  | Decomm |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-11-01 |  |  |  | 2024-03-12 |  | 2024-01-11 | 2024-04-24 | CD//Norhaliza | 2024-02-06 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240110 | DU00002559140 |  |  |  |  | 2023-11-01 |  | UNIPOLE
B00356 | B061H_B00356OD_SEK19USJ | Central |  | Decomm |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-10-31 |  |  |  | 2024-03-15 |  | 2024-01-11 | 2024-05-27 | CD//Ali akaram | 2024-01-18 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240108 | DU00002559141 |  |  |  |  | 2023-10-30 |  | BOOM
B01456 | B061E_B01456OD_SEK28S2SHLM | Central |  | Decomm |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-10-26 |  |  |  | 2024-03-07 |  | 2023-12-21 | 2024-05-31 | CD//Sapian | 2023-12-27 | CelcomDigi_RAN_Datasco_TSS_Central_20231213 | DU00002559142 |  |  |  |  | 2023-10-26 |  | LAMP_POLE
B01242 | B061H_B01242OD_TMSBGJAYA | Central |  | Decomm |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-01-08 |  |  |  | 2024-03-20 |  | 2024-01-29 | 2024-05-27 | CD//Norhaliza | 2024-02-06 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240115 | DU00002559143 |  |  |  |  | 2023-12-26 |  | BOOM
B00085 | B061E_B00085OD_PSNKUALASGOR | Central |  | Decomm |  | 2024 Q1_496 | SHA | GTSB | 4.6 TSSR Approved |  | 2024-07-25 |  | 2024-07-30 |  | 2024-08-01 |  | 2024-08-06 | 2024-08-20 | CD//Sapian | 2024-08-12 | 0730CD-Central-GTSB-BOQ Template(new contract) | DU00002559144 |  |  |  |  | 2024-08-27 |  | BOOM
B00397 | B061B_B00397OD_PSNKERJAYA | Central |  | Decomm |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-05-03 |  |  |  | 2024-05-06 |  | 2024-05-08 | 2024-08-20 | CD//Sapian | 2024-05-19 | CelcomDigi_RAN_Datasco_TSS_Central_20240513 | DU00002559145 |  |  |  |  | 2024-06-28 |  | BOOM
B00389 | B061I_B00389OD_USJ21 | Central |  | Decomm |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-10-26 |  |  |  | 2023-12-21 |  | 2024-01-11 | 2024-02-15 | CD//Norhaliza | 2024-02-06 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240108 | DU00002559146 |  |  |  |  | 2023-10-25 |  | MINI STRUCTURE
B00750 | B061H_B00750OD_PJS7SUNWAY | Central |  | Decomm |  | 2024 Q1_496 | SH | DATASCO | 4.6 TSSR Approved |  | 2024-04-26 |  |  |  | 2024-06-28 |  | 2024-04-29 |  | CD//Norhaliza | 2024-08-23 | CelcomDigi_RAN_Datasco_TSS_Central_20240513 | DU00002559147 |  | TX Part Rejected; TSSR not amend based on previous rejection comment. 1) Pls provide digi cabinet photo 2) antenna tx photo at NE & FE part (DISMANTLE DIGI MICROWAVE LINK 1404B-1196A) |  |  | 2024-04-04 |  | TRIPOD
B01983 | B061I_B01983OD_USJ4_TS | Central |  | Decomm |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-08-18 |  |  |  | 2024-04-22 |  | 2023-12-20 | 2024-09-26 | CD//Sapian | 2023-12-26 | CelcomDigi_RAN_Datasco_TSS_Central_20231213 | DU00002559148 |  |  |  |  | 2023-10-24 |  | LAMP_POLE
B01125 | B061B_B01125OD_PR_SEKU2TTDIJAYA | Central |  | Decomm |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-10-25 |  |  |  | 2023-12-15 |  | 2023-12-20 |  | CD//Norhaliza | 2024-01-02 | CelcomDigi_RAN_Datasco_TSS_Central_20231213 | DU00002559149 |  | Please provide label photo for each IDU |  |  | 2024-02-27 |  | TOWER
B02340 | B061E_B02340OD_JLNKAPAR27SHLM | Central |  | Decomm |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-10-31 |  |  |  | 2024-03-07 |  | 2024-01-26 | 2024-04-24 | CD//Ali akaram | 2024-01-31 | CelcomDigi_RAN_Datasco_TSS_Central_20231213 | DU00002559150 |  |  |  |  | 2023-10-31 |  | LAMP_POLE
P00117 | P034B_P00117OD_PMTGBENDAHARI | Northern |  | Decomm |  | 2024 Q1_496 | SM | GTSB | 4.6 TSSR Approved |  | 2023-12-18 |  |  |  | 2023-12-20 |  | 2023-12-21 | 2025-10-01 | CD//Affendi | 2023-12-22 | Celcom Digi_RAN-GTSB-TSS-Northern-20231219-0078 | DU00002559151 |  |  |  |  | 2023-11-30 |  | LAMP_POLE
B02031 | B061L_B02031OD_KM10.2ELITEHWAY | Central |  | Decomm |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-10-13 |  |  |  | 2023-12-15 |  | 2023-12-20 | 2025-03-21 | CD//Ali Akaram | 2024-01-02 | CelcomDigi_RAN_Datasco_TSS_Central_20231213 | DU00002559152 |  |  |  |  | 2023-12-21 |  | AESTHETIC MONOPOLE
B00012 | B061H_B00012OD_TMNDESARIA | Central |  | Decomm |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-08-19 |  |  |  | 2024-04-16 |  | 2024-01-11 | 2024-04-24 | CD//Ali akaram | 2024-01-18 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240108 | DU00002559153 |  |  |  |  | 2023-11-04 |  | BOOM
B01838 | B061I_B01838OD_USJ7 | Central |  | Decomm |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-08-21 |  |  |  | 2024-03-20 |  | 2024-01-15 | 2024-05-31 | CD//Sapian | 2024-01-21 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240110 | DU00002559154 |  |  |  |  | 2023-10-25 |  | Lampole
P00513 | P034B_P00513OD_BERTAMINDAH | Northern |  | Decomm |  | 2024 Q1_496 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-09-27 |  |  |  | 2023-10-12 |  | 2023-10-13 | 2023-12-18 | CD//Affendi | 2023-10-18 | Celcom Digi_RAN-GTSB-TSS-Northern-20231002-0042 | DU00002559155 |  | missing other TX Equipment Photo, In TSSR only Cisco Router Photo |  |  | 2024-01-31 |  | LAMP_POLE
P00326 | P034C_P00326OD_KG_AMAN | Northern |  | Decomm |  | 2024 Q1_496 | SM | GTSB | 4.6 TSSR Approved |  | 2023-12-18 |  |  |  | 2023-12-20 |  | 2023-12-21 | 2024-03-22 | CD//Affendi | 2023-12-22 | Celcom Digi_RAN-GTSB-TSS-Northern-20231219-0078 | DU00002559156 |  |  |  |  | 2023-11-30 |  | TOWER
B01318 | B061I_B01318OD_USJ92 | Central |  | Decomm |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-08-18 |  |  |  | 2024-03-15 |  | 2024-01-11 | 2024-05-27 | CD//Sapian | 2024-01-19 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240108 | DU00002559157 |  |  |  |  | 2023-10-23 |  | BOOM
B00691 | B061B_B00691OD_PR_KM12GLNMARIE | Central |  | Decomm |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-10-10 |  |  |  | 2023-12-15 |  | 2023-12-20 |  | CD//Sapian | 2023-12-26 | CelcomDigi_RAN_Datasco_TSS_Central_20231213 | DU00002559158 |  | 1) Please provide hw idu with clear label 2) Missing FE part |  |  | 2024-02-27 |  | AESTHETIC MONOPOLE
P00170 | P032A_P00170OD_BKTTAMBUNSLTN | Northern |  | Decomm |  | 2024 Q1_496 | ZA | GCI | 4.6 TSSR Approved |  | 2023-09-13 |  |  |  | 2023-10-23 |  | 2023-10-25 | 2023-11-23 | CD//Affendi | 2023-10-27 | Celcom Digi_RAN-GCI-TSS-Northern-20230913-0049 | DU00002559159 |  |  |  |  | 2023-11-16 |  | TOWER
B00674 | B061B_B00674OD_PR_GLENMARIE | Central |  | Decomm | Decomm->Site Out | 2024 Q1_496 |  | YPTT | 14.1 TSSR Not Required (Decomm by CD) | [6 empty] | To be Submitted | [5 empty] | DU00002559160 |  |  |  |  | 2025-04-29 |  | TOWER
B02206 | B061I_B02206OD_PR_PERSIARANSUBANGDAMAI | Central |  | Decomm |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-10-27 |  |  |  | 2024-08-22 |  | 2024-01-11 | 2025-03-14 | CD//Norhaliza | 2024-02-06 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240108 | DU00002559161 |  |  |  |  | 2023-10-27 |  | RAPOLE
B01470 | B061D_B01470OD_SEK21SHLM | Central |  | Decomm |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-01-17 |  |  |  | 2024-07-17 |  | 2024-01-18 | 2025-03-21 | CD//Norhaliza | 2024-02-06 | CelcomDigi_RAN_DATASCO_TSS_Central_20240124 | DU00002559162 |  |  |  |  | 2024-01-26 |  | MONOPOLE
B00395 | B061I_B00395OD_TMBKTGUGUP | Central |  | Decomm |  | 2024 Q1_496 | SH | DATASCO | 4.6 TSSR Approved |  | 2024-04-26 |  |  |  | 2024-05-02 |  | 2024-04-30 |  | CD//Norhaliza | 2024-08-23 | CelcomDigi_RAN_Datasco_TSS_Central_20240513 | DU00002559163 |  | Missing antenna tx photo at NE & FE part |  |  | 2024-04-05 |  | BOOM
B02034 | B061I_B02034OD_JLNPUTRABISTARI | Central |  | Decomm |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-10-23 |  |  |  | 2023-10-25 |  | 2023-10-26 | 2025-03-27 | CD//Norhaliza | 2023-11-17 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231025 | DU00002559164 |  |  |  |  | 2023-10-23 |  | AESTHETIC MONOPOLE
B00394 | B061E_B00394OD_TMSAGA | Central |  | Decomm |  | 2024 Q1_496 | AD | Ascentrack | 4.6 TSSR Approved |  | 2024-01-09 |  |  |  | 2024-02-09 |  | 2024-02-14 | 2025-03-14 | CD//Sapian | 2024-06-07 | 0920CD-Central-Ascentrack-BOQ Template (old contract) | DU00002559165 |  |  |  |  | 2024-04-18 | Tower | 4 Legged Tower
B02477 | B061I_B02477OD_WTPUTRABAHAGIAPUTRAHEIGHT | Central |  | Decomm |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-10-05 |  |  |  | 2024-03-27 |  | 2024-01-11 | 2024-05-27 | CD//Sapian | 2024-01-19 | CelcomDigi_RAN_Datasco_TSS_Central_20231213 | DU00002559166 |  |  |  |  | 2023-10-31 |  | AESTHETIC MONOPOLE
P00103 | P033A_P00103OD_BERAPIT | Northern |  | Decomm |  | 2024 Q1_496 | ZA | GTSB | 4.6 TSSR Approved | ¦ 0129 - Pending Access for TSS 0220 - tssr submitted | 2024-01-29 |  |  |  | 2024-02-16 |  | 2024-02-20 | 2024-02-27 | CD//Affendi | 2024-02-26 | Celcom Digi_RAN-GTSB-TSS-Northern-20240202-0090 | DU00002559167 |  |  |  |  | 2024-06-06 |  | TOWER
B02744 | B061D_B02744OD_JLNTP75TMNPERINDUSTRIANSUBANGJAYA | Central |  | Decomm |  | 2024 Q1_496 | MA | GCI | 4.6 TSSR Approved |  | 2024-01-11 |  |  |  | 2024-01-22 |  | 2023-10-13 | 2024-02-15 | CD//Sapian | 2023-10-25 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240115/Celcom Digi_RAN-GCI-Standard PR TSS-Central-20241016 | DU00002559168 |  |  |  |  | 2023-09-29 |  | LAMP_POLE
B01268 | B061D_B01268OD_TMNPINGIRANUSJ | Central |  | Decomm |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-09-09 |  |  |  | 2023-10-13 |  | 2023-10-13 |  | CD//Norhaliza | 2023-11-07 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230911 | DU00002559169 |  | 1) Missing antenna TX photo at NE 2) Missing FE part |  |  | 2023-09-28 |  | TOWER
B00160 | B061H_B00160OD_PJS11SUNWAY2 | Central |  | Decomm |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-08-21 |  |  |  | 2023-12-22 |  | 2023-12-26 | 2024-04-29 | CD//Ali akaram | 2024-01-08 | CelcomDigi_RAN_Datasco_TSS_Central_20231213 | DU00002559170 |  |  |  |  | 2023-11-02 |  | BOOM
B01563 | B061I_B01563OD_SEK8PUTRAHIGHT | Central |  | Decomm |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-09-24 |  |  |  | 2024-01-29 |  | 2024-01-31 | 2025-10-01 | CD//Sapian | 2024-02-07 | Celcom Digi_RAN-Ascentrack-TSS-Central-20230925 | DU00002559171 |  |  |  |  | 2023-10-22 |  | LAMP_POLE
B00060 | B061I_B00060OD_PUTRAHEIGHT2 | Central |  | Decomm |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-09-24 |  |  |  | 2023-10-10 |  | 2023-10-11 | 2023-12-18 | CD//Sapian | 2023-10-20 | Celcom Digi_RAN-Ascentrack-TSS-Central-20230925 | DU00002559172 |  |  |  |  | 2023-10-23 |  | TOWER
B00105 | B061H_B00105OD_PJS11SNWY | Central |  | Decomm |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-11-06 |  |  |  | 2023-12-26 |  | 2024-01-11 |  | CD//Norhaliza | 2024-02-06 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240108 | DU00002559173 |  | 1) Please provide antenna TX photo at NE 2) Missing FE part |  |  | 2023-11-06 |  | TRIPOD
P00714 | P032A_P00714OD_KAW_IND_VALDOR | Northern |  | Decomm |  | 2024 Q1_496 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-10-23 |  |  |  | 2023-10-31 |  | 2023-11-01 | 2023-12-18 | CD//Affendi | 2023-11-01 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231025-0061/Celcom Digi_RAN-CCSMY-TSS Decomm-Northern-20240131-0091 | DU00002559174 |  |  |  |  | 2023-11-06 |  | TOWER
P00360 | P032A_P00360OD_TMSGBAKAP | Northern |  | Decomm |  | 2024 Q1_496 | ZA | GCI | 4.6 TSSR Approved |  | 2024-01-12 |  |  |  | 2024-01-31 |  | 2024-02-02 |  | CD//Affendi | 2024-02-06 | Celcom Digi_RAN-GCI-TSS-Northern-20240124-0090/0612Northern-GCI-BOQ Template (template) | DU00002559175 |  | TSSR reject. TX SOW not tally with network topology to remain & upgrade BW TMLL. |  |  | 2024-02-23 |  | TOWER
P00144 | P034C_P00144OD_TMTASEKGELUGOR | Northern |  | Decomm |  | 2024 Q1_496 | ZA | GCI | 4.6 TSSR Approved |  | 2023-09-13 |  |  |  | 2023-09-19 |  | 2023-10-09 | 2023-10-27 | CD//Affendi | 2023-10-17 | Celcom Digi_RAN-GCI-TSS-Northern-20230914-0050 | DU00002559176 |  |  |  |  | 2024-04-30 |  | TOWER
P00467 | P032A_P00467OD_BKTPANCHOR | Northern |  | Decomm |  | 2024 Q1_496 | SM | GCI | 4.6 TSSR Approved |  | 2024-01-02 |  |  |  | 2024-01-11 |  | 2024-01-17 | 2024-01-22 | CD//Affendi | 2024-01-18 | Celcom Digi_RAN-GCI-TSS-Northern-20240108-0088 | DU00002559177 |  |  |  |  | 2024-02-21 |  | TOWER
P00129 | P034B_P00129OD_PMTGLANGSAT | Northern |  | Decomm |  | 2024 Q1_496 | ZA | GCI | 4.6 TSSR Approved |  | 2023-09-05 |  |  |  | 2023-10-18 |  | 2023-10-19 | 2024-06-19 | CD//Affendi | 2023-10-19 | Celcom Digi_RAN-GCI-TSS-Northern-20230912-0048/GCI Northern TX TSS | DU00002559178 |  | No Antenna photo 3) No FE info and Photo |  |  | 2024-03-19 |  | TOWER
B02297 | B061H_B02297OD_SUBANG_SS14_SCT | Central |  | Decomm |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-10-21 |  |  |  | 2024-02-05 |  | 2024-02-07 |  | CD//Sapian | 2024-02-13 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231021 | DU00002559179 |  | 1) Pls provide digi cabinet/rack photo 2) Please reconfirm antenna TX photo at NE is (DIGI MICROWAVE LINK 2926A-1184A) 3) Missing FE part |  |  | 2023-10-26 |  | BOOM
B02491 | B061D_B02491OD_KGBARUHICOM | Central |  | Decomm |  | 2024 Q1_496 | AI | GTSB | 4.6 TSSR Approved |  | 2023-08-18 |  |  |  | 2023-10-06 |  | 2023-10-06 | 2024-04-29 | CD//Ali akaram | 2023-10-17 | CelcomDigi_RAN_GTSB_TSS_Central_20230819 | DU00002559180 |  |  |  |  | 2023-10-18 |  | UNIPOLE
B00427 | B061L_B00427OD_TMNINDPCHG | Central |  | Decomm |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-09-24 |  |  |  | 2024-01-19 |  | 2024-01-21 |  | CD//Ali akaram | 2024-01-31 | Celcom Digi_RAN-Ascentrack-TSS-Central-20230925 | DU00002559181 |  | Missing FE Part |  |  | 2023-10-18 |  | BOOM
P00337 | P034B_P00337OD_KG_TOKBEDU | Northern |  | Decomm |  | 2024 Q1_496 | ZA | GCI | 4.6 TSSR Approved |  | 2023-09-29 |  |  |  | 2023-10-18 |  | 2023-10-19 | 2023-10-27 | CD//Affendi | 2023-10-19 | Celcom Digi_RAN-GCI-TSS-Northern-20231002-0055/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240529-0109 | DU00002559182 |  | Need amend drawing |  |  | 2024-02-15 |  | TOWER
P00124 | P033C_P00124OD_LIMAUMANIS | Northern |  | Decomm |  | 2024 Q1_496 | SM | GCI | 4.6 TSSR Approved |  | 2023-11-24 |  |  |  | 2023-11-28 |  | 2023-12-27 | 2024-01-22 | CD//Affendi | 2023-12-27 | Celcom Digi_RAN-GCI-TSS-Northern-20231127-0076 | DU00002559183 |  |  |  |  | 2023-11-21 |  | TOWER
P00499 | P033B_P00499OD_JLNTEMBIKAI | Northern |  | Decomm |  | 2024 Q1_496 | ZA | GCI | 4.6 TSSR Approved |  | 2023-10-02 |  |  |  | 2023-11-28 |  | 2023-11-29 | 2024-07-19 | CD//Affendi | 2023-12-05 | Celcom Digi_RAN-GCI-TSS-Northern-20231130-0077/GCI Northern TX TSS | DU00002559184 |  |  |  |  | 2023-10-02 |  | LAMP_POLE
P00160 | P033B_P00160OD_TAMANBAKTI | Northern |  | Decomm |  | 2024 Q1_496 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-11-01 |  |  |  | 2023-11-06 |  | 2023-11-07 | 2023-11-23 | CD//Affendi | 2023-11-10 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231102-0066 | DU00002559185 |  |  |  |  | 2023-12-16 |  | MINI MONOPOLE
P00254 | P032A_P00254OD_JLNPABOI | Northern |  | Decomm |  | 2024 Q1_496 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-10-26 |  |  |  | 2023-10-31 |  | 2023-11-01 | 2023-11-23 | CD//Affendi | 2023-11-10 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231028-0063 | DU00002559186 |  |  |  |  | 2023-11-07 |  | TOWER
P00149 | P033A_P00149OD_FIBERAILBM | Northern |  | Decomm |  | 2024 Q1_496 | BY | CCSMY | 4.6 TSSR Approved | ¦ 0129 - Plan submit TSSR today | 2024-01-26 |  |  |  | 2024-01-29 |  | 2024-01-30 | 2024-02-15 | CD//Affendi | 2024-02-07 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240124-0090 | DU00002559187 |  |  |  |  | 2024-06-28 |  | TOWER
P00172 | P032A_P00172OD_VALDOR | Northern |  | Decomm |  | 2024 Q1_496 | ZA | YPTT | 4.6 TSSR Approved |  | 2023-11-07 |  |  |  | 2023-11-22 |  | 2023-11-23 | 2024-03-22 | CD//Affendi | 2023-12-05 | Celcom Digi_RAN-YPTT-TSS-Northern-20231026-0039 | DU00002559188 |  | Missing xD cabinet for relocation Celcom Equipment 7/2 : TSSR resubmit without amend. Missing few photo in cabinet, Equipment ID not Clear, which one xD and xC cabinet |  |  | 2023-11-07 |  | TOWER
P00009 | P033B_P00009OD_PERDA | Northern |  | Decomm |  | 2024 Q1_496 | ZA | GCI | 4.6 TSSR Approved |  | 2023-09-29 |  |  |  | 2023-10-18 |  | 2023-10-19 | 2024-05-24 | CD//Affendi | 2023-10-27 | Celcom Digi_RAN-GCI-TSS-Northern-20231002-0055 | DU00002559189 |  |  |  |  | 2023-11-14 |  | TRIPOD
P00319 | P033A_P00319OD_BKERNR | Northern |  | Decomm |  | 2024 Q1_496 | BY | GTSB | 4.6 TSSR Approved |  | 2023-11-14 |  |  |  | 2023-11-20 |  | 2023-11-21 | 2023-12-18 | CD//Affendi | 2023-11-30 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20231218-0078/Celcom Digi_RAN-GTSB-TSS-Northern-20231115-0065 | DU00002559190 |  |  |  |  | 2023-11-28 |  | TOWER
P00012 | P033B_P00012OD_TAMANARA | Northern |  | Decomm |  | 2024 Q1_496 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-09-27 |  |  |  | 2023-10-11 |  | 2023-10-12 | 2024-03-22 | CD//Affendi | 2023-10-17 | Celcom Digi_RAN-GTSB-TSS-Northern-20231002-0042 | DU00002559191 |  | 1) No Digi Cabinet 2) Please include clear photo ID Label for each Equipemnt 3) Please put properly TX equipment Photo and Info |  |  | 2023-10-17 |  | TOWER
P00530 | SGLEMBU2 | Northern |  | Decomm |  | 2024 Q1_496 | BY | GTSB | 4.6 TSSR Approved |  | 2023-11-09 |  |  |  | 2023-11-09 |  | 2023-11-14 | 2024-02-15 | CD//Affendi | 2023-11-16 | Celcom Digi_RAN-GTSB-TSS-Northern-20231115-0065 | DU00002559192 |  |  |  |  | 2023-11-28 |  | TOWER
P00105 | P034A_P00105OD_BGNLEBAITAHIR | Northern |  | Decomm |  | 2024 Q1_496 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-10-25 |  |  |  | 2023-10-27 |  | 2023-10-30 | 2023-11-23 | CD//Affendi | 2023-10-31 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231026-0062 | DU00002559193 |  |  |  |  | 2023-10-27 |  | BOOM
P00332 | P034A_P00332OD_TKAIRTAWAR2 | Northern |  | Decomm |  | 2024 Q1_496 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-10-24 |  |  |  | 2023-10-27 |  | 2023-10-30 | 2023-12-18 | CD//Affendi | 2023-11-16 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231025-0061 | DU00002559194 |  |  |  |  | 2023-10-27 |  | TOWER
P00065 | P034A_P00065OD_PEKANDARAT | Northern |  | Decomm |  | 2024 Q1_496 |  | CCSMY | 4.6 TSSR Approved |  | 2023-11-07 |  |  |  | 2023-11-08 |  | 2023-11-09 | 2023-11-23 | CD//Affendi | 2023-11-16 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231108-0069/Celcom Digi_RAN-CCSMY-TSS Decomm-Northern-20240131-0091 | DU00002559195 |  |  |  |  | 2024-01-02 |  | TOWER
P00357 | P034A_P00357OD_TUDMBWORTH | Northern |  | Decomm |  | 2024 Q1_496 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-10-02 |  |  |  | 2023-10-12 |  | 2023-10-13 | 2024-02-15 | CD//Affendi | 2023-10-18 | Celcom Digi_RAN-GTSB-TSS-Northern-20231003-0043 | DU00002559196 |  | Missing TM LL Celcom Photo |  |  | 2023-10-17 |  | LAMP_POLE
P00143 | P034B_P00143OD_TMKEPALABATAS | Northern | 4622K | Swap | Decomm->TBD->Swap | 2024 Q1_496 | WP | GCI | 4.6 TSSR Approved | ¦ 0725 - to use TSSR approval under CRwE to close TSSR ¦ 0515 - GCI:Need resurvey | 2023-09-14 | 2024-06-19 |  |  | 2023-09-27 |  | 2023-10-02 | 2024-07-25 | CD//Rohizam | 2024-07-16 | 0619Northen-GCI-BOQ Template (template) | DU00002559197 |  |  | 2024-08-22 | 2024-07-16 |  | Tower | TOWER | 62 | Add R8852E S9000 x1+R9264H M901821 x2+R8862A S2601 x3+A9732 M1821 x1,Dismantle | 3 | 0
P00120 | P032A_P00120OD_JUNJONG | Northern |  | Decomm |  | 2024 Q1_496 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-09-26 |  |  |  | 2023-10-03 |  | 2023-10-09 | 2023-10-27 | CD//Affendi | 2023-10-17 | Celcom Digi_RAN-GTSB-TSS-Northern-20230926-0041 | DU00002559198 |  |  |  |  | 2023-11-03 |  | TOWER
P00171 | P032A_P00171OD_TMNIBONGTEBAL | Northern |  | Decomm |  | 2024 Q1_496 | BY | YPTT | 4.6 TSSR Approved |  | 2023-12-20 |  |  |  | 2024-01-22 |  | 2024-01-23 | 2024-04-16 | CD//Rohizam | 2024-01-24 | Celcom Digi_RAN-YPTT-TSS-Northern-20240108-0051 | DU00002559199 |  |  |  |  | 2023-12-18 |  | MINI STRUCTURE
P00019 | P032A_P00019OD_KGSGKECHIL | Northern |  | Decomm |  | 2024 Q1_496 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-11-24 |  |  |  | 2023-11-24 |  | 2023-11-27 | 2024-02-15 | CD//Rohizam | 2023-11-27 | Celcom Digi_RAN-GTSB-TSS-Northern-20231127-0068 | DU00002559200 |  | Need Amend Drawing for location Digi Cabinet |  |  | 2023-11-29 |  | TOWER
P00024 | P032A_P00024OD_USMTRANSKRIAN | Northern |  | Decomm |  | 2024 Q1_496 | SM | GTSB | 4.6 TSSR Approved |  | 2023-11-30 |  |  |  | 2023-12-04 |  | 2023-12-12 | 2024-01-22 | CD//Rohizam | 2023-12-22 | Celcom Digi_RAN-GTSB-TSS-Northern-20231201-0070 | DU00002559201 |  |  |  |  | 2024-07-22 |  | UNIPOLE
P00613 | P032A_P00613OD_SGBAKAPTOWN | Northern |  | Decomm |  | 2024 Q1_496 | ZA | YPTT | 4.6 TSSR Approved |  | 2023-11-20 |  |  |  | 2023-11-23 |  | 2023-11-24 | 2024-02-15 | CD//Rohizam | 2023-11-24 | Celcom Digi_RAN-YPTT-TSS-Northern-20231122-0044 | DU00002559202 |  |  |  |  | 2023-11-06 |  | BOOM
P00371 | P032A_P00371OD_LIMAKONGSI | Northern |  | Decomm |  | 2024 Q1_496 | SM | GTSB | 4.6 TSSR Approved |  | 2023-12-18 |  |  |  | 2023-12-20 |  | 2023-12-26 | 2024-01-22 | CD//Rohizam | 2023-12-26 | Celcom Digi_RAN-GTSB-TSS-Northern-20231219-0078 | DU00002559203 |  |  |  |  | 2024-01-05 |  | TOWER
P00116 | P032A_P00116OD_TSKCEMPEDAK | Northern |  | Decomm |  | 2024 Q1_496 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-09-27 |  |  |  | 2023-10-11 |  | 2023-10-12 | 2024-02-15 | CD//Rohizam | 2023-10-13 | Celcom Digi_RAN-GTSB-TSS-Northern-20231002-0042 | DU00002559204 |  | Please include Other TX equipment in Cabinet |  |  | 2023-11-16 |  | TOWER
P00338 | P032A_P00338OD_LDGCHANGKAT | Northern |  | Decomm |  | 2024 Q1_496 | ZA | GCI | 4.6 TSSR Approved |  | 2023-10-17 |  |  |  | 2023-10-19 |  | 2023-10-20 | 2024-07-05 | CD//Rohizam | 2023-10-20 | Celcom Digi_RAN-GCI-TSS-Northern-20231018-0061/GCI Northern TX TSS | DU00002559205 |  | Missing FE Photo and info |  |  | 2024-01-11 |  | TOWER
P00111 | P033C_P00111OD_BKTTENGAHDELL | Northern |  | Decomm |  | 2024 Q1_496 | ZA | GCI | 4.6 TSSR Approved |  | 2023-09-06 |  |  |  | 2023-10-19 |  | 2023-10-20 | 2024-07-05 | CD//Rohizam | 2023-10-20 | Celcom Digi_RAN-GCI-TSS-Northern-20230907-0046 | DU00002559206 |  |  |  |  | 2023-11-15 |  | TOWER
B00348 | B061B_B00348OD_PR_SEKU8SHLM | Central |  | Decomm |  | 2024 Q1_496 | IE | Magicell | 4.6 TSSR Approved |  | 2023-09-11 |  |  |  | 2023-09-12 |  | 2023-09-13 | 2023-12-18 | CD//Sapian | 2023-10-06 | CelcomDigi_RAN_Magicell_TSS_Central_20230912 | DU00002559207 |  |  |  |  | 2024-03-06 |  | BOOM
P00449 | P034B_P00449OD_BUMBUNGLIMA | Northern |  | Decomm |  | 2024 Q1_496 | ZA | GCI | 4.6 TSSR Approved |  | 2023-09-03 |  |  |  | 2023-10-20 |  | 2023-10-23 | 2024-03-12 | CD//Rohizam | 2023-10-23 | Celcom Digi_RAN-GCI-TSS-Northern-20240520-0108/0612Northern-GCI-BOQ Template (template) | DU00002559208 |  | Missing NE antenna Photo, FE Photo and info 1) Please fill NE info Equipment, 2) Missing FE info |  |  | 2024-01-23 |  | TOWER
P00262 | P034B_P00262OD_PMTGBERAH | Northern |  | Decomm |  | 2024 Q1_496 | WP | GCI | 4.6 TSSR Approved |  | 2023-09-02 |  |  |  | 2023-09-08 |  | 2023-10-02 | 2024-06-07 | CD//Rohizam | 2023-10-09 | Celcom Digi_RAN-GCI-TSS Decomm-Northern-20230904-0045/Celcom Digi_RAN-GCI-TSS-Northern-20230904-0044_V2 | DU00002559209 |  |  |  |  | 2024-01-23 |  | TOWER
P00633 | P034C_P00633OD_TMNDESASENA_KPLBATAS | Northern | 4606K | Swap | Decomm->Swap | 2024 Q1_496 |  | GTSB | 4.6 TSSR Approved |  | 2023-12-29 | 2024-01-02 |  | 2024-01-09 |  | Closed | 2024-01-11 | 2024-01-12 | CD//Rohizam | 2024-01-12 | Celcom Digi_RAN-GTSB-TSS-Northern-20240508-0107 | DU00002559210 |  |  | 2024-02-29 | 2024-02-01 |  | Minaret | MINARET | 30M | Add R8862A S9000 x3+R8894E M1821 x3+R8862A S2601 x3,Dismantle | 0 | 0
B00428 | B061E_B00428OD_SEK28SA | Central |  | Decomm |  | 2024 Q1_496 | AI | GTSB | 4.6 TSSR Approved |  | 2023-08-17 |  |  |  | 2023-10-06 |  | 2023-10-07 | 2023-12-18 | CD//Sapian | 2023-10-13 | CelcomDigi_RAN_GTSB_TSS_Central_20230818 | DU00002559211 |  |  |  |  | 2023-10-20 |  | TRIPOD
P00715 | P033A_P00715OD_KG_MENGKUANG_GPERAHU | Northern |  | Decomm |  | 2024 Q1_496 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-09-26 |  |  |  | 2023-10-09 |  | 2023-10-19 | 2023-10-27 | CD//Rohizam | 2023-10-19 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20231218-0078/Celcom Digi_RAN-GTSB-TSS-Northern-20230926-0041 | DU00002559212 |  |  |  |  | 2023-10-17 |  | TOWER
P00114 | P034C_P00114OD_KAMPUNGSELAMAT | Northern |  | Decomm |  | 2024 Q1_496 | BY | YPTT | 4.6 TSSR Approved |  | 2024-01-17 |  |  |  | 2024-01-23 |  | 2024-01-30 | 2024-03-26 | CD//Rohizam | 2024-01-30 | Celcom Digi_RAN-YPTT-TSS-Northern-20240124-0056 | DU00002559213 |  |  |  |  | 2024-01-22 |  | TOWER
P00139 | P034B_P00139OD_PONGSUSERIBU | Northern |  | Decomm |  | 2024 Q1_496 | BY | GTSB | 4.6 TSSR Approved |  | 2023-10-02 |  |  |  | 2023-11-01 |  | 2023-11-02 | 2024-03-22 | CD//Rohizam | 2023-11-02 | Celcom Digi_RAN-GTSB-TSS-Northern-20231003-0043 | DU00002559214 |  | Please update drawing to show xD and xC location |  |  | 2023-11-17 |  | TOWER
P00057 | P034B_P00057OD_PAYAKELADI | Northern |  | Decomm |  | 2024 Q1_496 | ZA | YPTT | 4.6 TSSR Approved | 0202 - pending subcon revise ¦ 0129 - TSSR plan submit 30/1 | 2024-01-26 |  |  |  | 2024-01-31 |  | 2024-02-05 | 2024-03-26 | CD//Rohizam | 2024-02-05 | Celcom Digi_RAN-YPTT-TSS-Northern-20240124-0057 | DU00002559215 |  | All Photo Messy, missing Photo with ID label, wrong cabinet |  |  | 2024-01-23 |  | TOWER
P00141 | P034C_P00141OD_PDGMENORA | Northern |  | Decomm |  | 2024 Q1_496 | SM | GTSB | 4.6 TSSR Approved |  | 2023-09-26 |  |  |  | 2023-11-02 |  | 2023-11-08 | 2024-01-22 | CD//Rohizam | 2023-11-08 | Celcom Digi_RAN-GTSB-TSS-Northern-20231002-0042 | DU00002559216 |  |  |  |  | 2023-12-22 |  | TOWER
P00680 | P034B_P00680OD_PENAGA2 | Northern |  | Decomm |  | 2024 Q1_496 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-09-27 |  |  |  | 2023-10-09 |  | 2023-10-23 | 2023-10-27 | CD//Rohizam | 2023-10-23 | Celcom Digi_RAN-GTSB-TSS-Northern-20231002-0042 | DU00002559217 |  |  |  |  | 2023-10-19 |  | TOWER
P00132 | P034C_P00132OD_KBGMENERONG2 | Northern |  | Decomm |  | 2024 Q1_496 | BY | YPTT | 4.6 TSSR Approved | ¦ 0129 - submitted today, pending ZTE review | 2024-01-24 |  |  |  | 2024-01-29 |  | 2024-01-30 | 2024-02-16 | CD//Rohizam | 2024-01-30 | Celcom Digi_RAN-YPTT-TSS-Northern-20240124-0056 | DU00002559218 |  |  |  |  | 2024-04-18 |  | TOWER
P00582 | P034B_P00582OD_ILPKEPALABATAS | Northern |  | Decomm |  | 2024 Q1_496 | BY | CCSMY | 4.6 TSSR Approved | ¦ 0129 - YPTT: Site canceled | 2024-03-22 |  |  |  | 2024-03-22 |  | 2024-03-25 | 2024-04-16 | CD//Rohizam | 2024-03-26 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240325-0101 | DU00002559219 |  |  |  |  | 2024-03-22 |  | TOWER
B00404 | B061I_B00404OD_USJ9 | Central |  | Decomm |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-10-23 |  |  |  | 2023-10-25 |  | 2023-10-26 | 2025-03-21 | CD//Ali akaram | 2023-11-15 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231025 | DU00002559220 |  |  |  |  | 2023-10-23 |  | MINI MONOPOLE
P00031 | P034C_P00031OD_TOHALANG | Northern |  | Decomm |  | 2024 Q1_496 | ZA | GCI | 4.6 TSSR Approved |  | 2023-09-08 |  |  |  | 2023-11-24 |  | 2023-11-27 | 2023-12-18 | CD//Rohizam | 2023-11-28 | Celcom Digi_RAN-GCI-TSS-Northern-20230911-0047 | DU00002559221 |  |  |  |  | 2023-11-27 |  | TOWER
P00082 | P032A_P00082OD_SUNGAIUDANG | Northern |  | Decomm |  | 2024 Q1_496 | BY | GTSB | 4.6 TSSR Approved |  | 2023-11-16 |  |  |  | 2023-11-20 |  | 2023-11-21 | 2024-02-27 | CD//Rohizam | 2023-11-21 | Celcom Digi_RAN-GTSB-TSS-Northern-20231118-0066 | DU00002559222 |  |  |  |  | 2023-11-23 |  | TOWER
B02777 | B061H_B02777OD_JLNPJS8_12A_BDRSUNWAY_PJ | Central |  | Decomm |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-11-03 |  |  |  | 2024-03-12 |  | 2024-01-12 | 2024-04-29 | CD//Ali akaram | 2024-01-19 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240110 | DU00002559223 |  |  |  |  | 2023-11-02 |  | WALL MOUNTED BOOM
B02233 | B061H_B02233OD_PJS10TMNDATOHORMATPJ | Central |  | Decomm |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-11-06 |  |  |  | 2024-03-13 |  | 2024-01-15 | 2024-04-29 | CD//Ali akaram | 2024-01-23 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240110 | DU00002559224 |  |  |  |  | 2023-11-06 |  | LAMP_POLE
B00570 | B061H_B00570OD_SS13SBJ | Central |  | Decomm |  | 2024 Q1_496 | SY1 | Ascentrack | 4.6 TSSR Approved |  | 2024-02-16 |  |  |  | 2024-02-19 |  | 2024-10-07 |  | CD//Sapian | 2024-10-17 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240217 | DU00002559225 |  | No cisco router on site |  |  | 2024-05-09 |  | MINI STRUCTURE
B02585 | B061H_B02585OD_KGLINDUNGAN_SGWAY | Central |  | Decomm |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-03 |  |  |  | 2023-11-16 |  | 2024-02-19 | 2024-04-29 | CD//Norhaliza | 2024-02-23 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231104 | DU00002559226 |  |  |  |  | 2023-11-02 |  | LAMP_POLE
B02560 | B061B_B02560OD_JLNPENGATURCARAU1 | Central |  | Decomm |  | 2024 Q1_496 | AI | GTSB | 4.6 TSSR Approved |  | 2023-08-21 |  |  |  | 2023-10-11 |  | 2023-10-12 | 2023-12-18 | CD//Ali Akaram | 2023-10-19 | CelcomDigi_RAN_GTSB_TSS_Central_20230823 | DU00002559227 |  |  |  |  | 2024-03-04 |  | AESTHETIC MONOPOLE
P00512 | P033A_P00512OD_JLNABDKADIR | Northern |  | Decomm |  | 2024 Q1_496 | WP | GCI | 4.6 TSSR Approved |  | 2023-09-20 |  |  |  | 2023-09-29 |  | 2023-10-02 | 2023-10-27 | CD//Rohizam | 2023-10-10 | Celcom Digi_RAN-GCI-TSS-Northern-20230921-0053 | DU00002559228 |  |  |  |  | 2023-10-17 |  | LAMP_POLE
B00758 | B061I_B00758OD_USJ14 | Central |  | Decomm |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-10-19 |  |  |  | 2024-01-18 |  | 2024-01-19 | 2025-01-14 | CD//Sapian | 2024-01-27 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231020 | DU00002559229 |  |  |  |  | 2023-10-19 |  | TRIPOD
P00641 | P033B_P00641OD_KAW_INDUSTRI_RAWA_BM | Northern |  | Decomm |  | 2024 Q1_496 | ZA | GCI | 4.6 TSSR Approved |  | 2023-09-06 |  |  |  | 2023-10-20 |  | 2023-10-23 | 2023-12-18 | CD//Rohizam | 2023-10-23 | Celcom Digi_RAN-GCI-TSS-Northern-20230907-0046/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240529-0109 | DU00002559230 |  | Missing TX info and Photo |  |  | 2023-11-27 |  | UNIPOLE
P00598 | P032A_P00598OD_PULAUAMAN | Northern |  | Decomm |  | 2024 Q1_496 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-09-13 |  |  |  | 2023-10-07 |  | 2023-10-09 | 2023-10-27 | CD//Rohizam | 2023-10-16 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20231218-0078/Celcom Digi_RAN-GTSB-TSS-Northern-20230914-0037 | DU00002559231 |  |  |  |  | 2023-11-30 |  | TOWER
B00106 | B061H_B00106OD_TMNSRISBG | Central |  | Decomm |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-01-18 |  |  |  | 2024-02-18 |  | 2024-02-20 | 2025-01-14 | CD//Ali Akaram | 2024-03-04 | CelcomDigi_RAN_Ascentrack_TSS_Central_20240124 | DU00002559232 |  |  |  |  | 2024-05-14 |  | TRIPOD
B00357 | B061I_B00357OD_SEK4USJ | Central |  | Decomm |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-10-21 |  |  |  | 2023-10-24 |  | 2023-10-25 | 2023-12-18 | CD//Ali akaram | 2023-11-07 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231022 | DU00002559233 |  |  |  |  | 2023-10-20 |  | BOOM
B00793 | B061I_B00793OD_USJ12 | Central |  | Decomm |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-09-09 |  |  |  | 2023-10-12 |  | 2023-10-13 | 2023-11-20 | CD//Norhaliza | 2023-11-15 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230911 | DU00002559234 |  |  |  |  | 2023-10-25 |  | LAMP_POLE
B02254 | B061D_B02254OD_JLNJUBLIPERAKSHLM | Central |  | Decomm |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-12-04 |  |  |  | 2024-01-22 |  | 2024-01-24 |  | CD//Norhaliza | 2024-02-08 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231208 | DU00002559235 |  | 1) Pls provide digi cabinet/rack photo 2) Missing FE part |  |  | 2023-10-25 |  | UNIPOLE
B00752 | B061I_B00752OD_TMNINDUEP | Central |  | Decomm |  | 2024 Q1_496 | MA | YPTT | 4.6 TSSR Approved |  | 2024-05-28 |  |  |  | 2024-05-28 |  | 2024-05-29 | 2024-09-26 | CD//Norhaliza | 2024-08-09 | CelcomDigi_RAN_YPTT_TSS_Central_20240528 | DU00002559236 |  |  |  |  | 2024-06-05 |  | BOOM
B02510 | B061D_B02510OD_PSNTGKAMPUAN2SEK26 | Central |  | Decomm |  | 2024 Q1_496 | SS | YPTT | 4.6 TSSR Approved |  | 2023-10-04 |  |  |  | 2023-10-13 |  | 2023-10-13 |  | CD//Ali Akaram | 2023-11-02 | CelcomDigi_RAN_YPTT_TSS_Central_20231005 | DU00002559237 |  | Missing FE part |  |  | 2023-10-04 |  | BOOM
B01523 | B061B_B01523OD_KDUGLENMARIE | Central | 1835K | Swap | TBD->Swap | 2024 Q1_496 | YZ | Ascentrack | 4.6 TSSR Approved |  | 2024-02-15 | 2024-02-20 |  | 2024-02-27 | 2024-02-26 | Under Approval | 2024-02-27 | 2024-07-23 | CD//Norhaliza | 2024-07-23 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240217 | DU00002559238 |  |  | 2024-05-23 | 2024-05-11 |  | Unipole | RAPOLE | 3 | Add R8852E S9000 x2+R9264H M901821 x1+R8862A S2601 x3+A9732 M1821 x2,Dismantle | 23 | 0
B00384 | B061H_B00384OD_SUBANGINDAH | Central |  | Decomm |  | 2024 Q1_496 | BY | Ascentrack | 4.6 TSSR Approved |  | 2024-02-15 |  |  |  | 2024-02-20 |  | 2024-02-21 |  | CD//Sapian | 2024-02-27 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240217 | DU00002559239 |  | MISSING FE PART |  |  | 2024-03-07 |  | BOOM
B01504 | B061I_B01504OD_MASJIDALIRSYADUSJ1 | Central | 1836K | Swap | On Hold->Swap | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-09-19 | 2023-12-27 |  | 2024-01-04 |  | Closed | 2024-01-10 | 2024-01-17 | CD//Sapian | 2024-01-16 | 0626Central-Ascentrack-BOQ Template (template) | DU00002559240 |  |  | 2024-03-03 | 2024-03-01 |  | Monopole | LAMP_POLE | 24m | Add R9264M M1821 x1+R9264H M901821 x3+R8862A S2601 x2+R8854 S2600 x1,Dismantle
B02779 | B061B_B02779OD_PLAZAGLENMARIEU1SA | Central |  | Decomm |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-02-20 |  |  |  | 2024-02-21 |  | 2024-02-22 | 2024-12-31 | CD//Sapian | 2024-03-06 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240225 | DU00002559241 |  |  |  |  | 2024-05-18 |  | WALL MOUNTED BOOM
B02401 | B061D_B02401OD_TMNSUBANGMAS | Central |  | Decomm |  | 2024 Q1_496 | SS | YPTT | 4.6 TSSR Approved |  | 2023-10-25 |  |  |  | 2023-10-25 |  | 2023-10-13 |  | CD//Norhaliza | 2023-10-31 | CelcomDigi_RAN_YPTT_TSS_Central_20231028 | DU00002559242 |  | Missing FE part |  |  | 2023-10-06 |  | BOOM
P00601 | P034B_P00601OD_LAHARIKANMATI | Northern |  | Decomm |  | 2024 Q1_496 | BY | GCI | 4.6 TSSR Approved |  | 2023-12-18 |  |  |  | 2023-12-20 |  | 2024-01-17 | 2024-03-22 | CD//Rohizam | 2024-01-18 | Celcom Digi_RAN-GCI-TSS-Northern-20231225-0085/Celcom Digi_RAN-GCI-TSS-Northern-20240130-0092 | DU00002559243 |  |  |  |  | 2024-03-05 |  | TOWER
P00776 | P034B_P00776OD_SHAHBANDARBERTAM | Northern |  | Decomm |  | 2024 Q1_496 | BY | GCI | 4.6 TSSR Approved |  | 2023-12-18 |  |  |  | 2024-01-04 |  | 2024-01-05 | 2024-05-10 | CD//Rohizam | 2024-01-05 | Celcom Digi_RAN-GCI-TSS-Northern-20231225-0085/Celcom Digi_RAN-GCI-TSS-Northern-20240130-0092 | DU00002559244 |  | 1) Please include TM LL equipment for dismantle, 2) Missing TX dismantle Equipment, 3) Missing FE info |  |  | 2024-01-30 |  | UNIPOLE
P00154 | P033C_P00154OD_WISMAKWSIEW | Northern |  | Decomm |  | 2024 Q1_496 | ZA | GCI | 4.6 TSSR Approved |  | 2023-09-13 |  |  | 2023-09-14 | 2023-10-18 | Under Approval | 2023-09-15 | 2024-07-11 | CD//Rohizam | 2023-09-29 | Celcom Digi_RAN-GCI-TSS-Northern-20230913-0049/GCI Northern TX TSS | DU00002559245 |  | FE info not Complete |  |  | 2023-11-15 |  | MINI STRUCTURE
P00299 | P032A_P00299OD_PKNSGUDANG | Northern |  | Decomm |  | 2024 Q1_496 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-09-27 |  |  |  | 2023-10-11 |  | 2023-10-19 | 2023-10-27 | CD//Rohizam | 2023-10-24 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20231218-0078/Celcom Digi_RAN-GTSB-TSS-Northern-20231002-0042 | DU00002559246 |  | Please include Other TX equipment in Rack |  |  | 2023-11-29 |  | TOWER
B01211 | B061H_B01211OD_MASJIDSUNWAY | Central |  | Decomm |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-08 |  |  |  | 2024-01-18 |  | 2024-01-19 | 2025-03-21 | CD//Norhaliza | 2024-02-06 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231113 | DU00002559247 |  |  |  |  | 2023-11-08 |  | SHARING STRC OTHERS MINARATE
B00791 | B061E_B00791OD_SEK27SHLM | Central |  | Decomm | Decomm->On Hold->Decomm | 2024 Q1_496 | MA | Magicell | 4.6 TSSR Approved |  | 2023-09-06 |  |  |  | 2023-09-06 |  | 2023-09-08 | 2024-03-22 | CD//Sapian | 2023-10-16 | CelcomDigi_RAN_Magicell_TSS_Central_20230825/Celcom Digi_RAN-Magicell-Standard PR TSS-Central-20241016 | DU00002559248 |  |  |  |  | 2025-10-07 |  | BOOM
P00098 | P033C_P00098OD_JLNBKTTENGAH | Northern |  | Decomm |  | 2024 Q1_496 | ZA | GCI | 4.6 TSSR Approved |  | 2023-09-02 |  |  |  | 2023-09-27 |  | 2023-11-06 | 2023-11-23 | CD//Rohizam | 2023-11-10 | Celcom Digi_RAN-GCI-TSS-Northern-20230904-0044_V2 | DU00002559249 |  |  |  |  | 2024-02-23 |  | LAMP_POLE
P00679 | P034B_P00679OD_MARKETKEPALABATAS | Northern |  | Decomm |  | 2024 Q1_496 | SM | GCI | 4.6 TSSR Approved |  | 2023-12-19 |  |  |  | 2023-12-22 |  | 2023-12-27 | 2024-04-23 | CD//Rohizam | 2024-01-02 | Celcom Digi_RAN-GCI-TSS-Northern-20231225-0085/Celcom Digi_RAN-GCI-TSS-Northern-20240130-0092 | DU00002559250 |  |  |  |  | 2024-01-29 |  | TOWER
P00464 | P034B_P00464OD_BERTAMPERDANA3 | Northern |  | Decomm | Decomm->On Hold->Decomm | 2024 Q1_496 | SM | CCSMY | 4.6 TSSR Approved | ¦ 0620 - CD Rohizam: TSSR reviewed and approved to DECOM. to retain existing coverage and capacity will be replaced with NIC NNS 4005L Lorong Bentana @ 5.5321474°100.4725406°. ¦ 0402 - Li Jie fup to Izzat, pending revert¦ ¦ 15/3- LiJie to check with Izat ¦¦ 231120 - CD Rohizam: Proposed change paired to unpair site with 4478C and change SOW for site P00464 P034B_P00464OD_BERTAMPERDANA3 to SWAP. | 2023-11-06 |  |  |  | 2023-11-07 |  | 2023-11-08 | 2024-07-05 | CD//Rohizam | 2024-06-20 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231106-0068 | DU00002559251 |  |  |  |  | 2024-01-24 |  | LAMP_POLE
P00648 | P032A_P00648OD_KG_WELLESLEY | Northern |  | Decomm |  | 2024 Q1_496 | BY | GTSB | 4.6 TSSR Approved |  | 2023-11-23 |  |  |  | 2023-11-24 |  | 2023-11-27 | 2024-02-15 | CD//Rohizam | 2023-11-27 | Celcom Digi_RAN-GTSB-TSS-Northern-20231127-0068 | DU00002559252 |  | Missing FE Info and Photo |  |  | 2023-11-29 |  | TOWER
P00649 | P034C_P00649OD_PARIT_CINA | Northern |  | Decomm |  | 2024 Q1_496 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-10-10 |  |  |  | 2023-10-26 |  | 2023-10-27 | 2023-11-23 | CD//Rohizam | 2023-10-27 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231011-0052 | DU00002559253 |  |  |  |  | 2023-11-27 |  | TOWER
P00005 | P032A_P00005OD_SIMPANG4TASEK | Northern |  | Decomm |  | 2024 Q1_496 | SM | GTSB | 4.6 TSSR Approved |  | 2023-11-14 |  |  |  | 2023-11-17 |  | 2023-11-20 | 2023-11-29 | CD//Rohizam | 2023-11-24 | Celcom Digi_RAN-GTSB-TSS-Northern-20231115-0065 | DU00002559254 |  |  |  |  | 2023-11-21 |  | TOWER
P00606 | P032A_P00606OD_BDRCASSIA | Northern |  | Decomm |  | 2024 Q1_496 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-09-26 |  |  |  | 2023-10-11 |  | 2023-10-17 | 2024-02-15 | CD//Rohizam | 2023-10-18 | Celcom Digi_RAN-GTSB-TSS-Northern-20231002-0042 | DU00002559255 |  | Please include Other TX equipment in Cabinet 1/2: include another 1x IDU with label ID |  |  | 2023-11-29 |  | MONOPOLE
P00110 | P032A_P00110OD_JAWI | Northern |  | Decomm |  | 2024 Q1_496 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-10-03 |  |  |  | 2023-10-07 |  | 2023-10-12 | 2024-02-29 | CD//Rohizam | 2023-10-10 | Celcom Digi_RAN-GTSB-TSS-Northern-20231004-0044 | DU00002559256 |  |  |  |  | 2023-11-07 |  | TOWER
P00050 | P034B_P00050OD_KEPALABATAS | Northern | 4604K | Swap | Decomm->On hold->Swap | 2024 Q1_496 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-10-15 | 2024-01-09 |  | 2024-01-10 | 2023-10-26 | Closed | 2023-10-27 | 2024-01-16 | CD//Rohizam | 2024-01-15 | 0626Northen-CCSMY-BOQ Template (template) | DU00002559257 |  |  | 2024-02-08 | 2024-01-19 |  | Tower | TOWER | 48m | Add R8862A S9000 x3+R9264H M901821 x1+R8862A S2601 x4+A9732 M1821 x3,Dismantle | 124 | 0
B02432 | B061H_B02432OD_BDR SUNWAY 2 | Central |  | Decomm |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-08 |  |  |  | 2023-12-14 |  | 2023-12-22 |  | CD//Norhaliza | 2024-01-17 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231113 | DU00002559258 |  | Missing FE part |  |  | 2023-12-28 |  | TRIPOD
P00713 | P032A_P00713OD_TJGVILLA_BT_KAWAN | Northern |  | Decomm |  | 2024 Q1_496 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-10-27 |  |  |  | 2023-10-31 |  | 2023-11-01 | 2023-11-23 | CD//Rohizam | 2023-11-01 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231028-0063/Celcom Digi_RAN-CCSMY-TSS Decomm-Northern-20240131-0091 | DU00002559259 |  |  |  |  | 2024-01-23 |  | MONOPOLE
B00115 | B061H_B00115OD_PR_SS17SBJ | Central |  | Decomm |  | 2024 Q1_496 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-07 |  |  |  | 2024-01-11 |  | 2024-01-15 | 2024-02-15 | CD//Norhaliza | 2024-02-06 | CelcomDigi_RAN_GTSB_TSS_Central_20231113 | DU00002559260 |  |  |  |  | 2023-10-27 |  | BOOM
B02611 | B061H_B02611OD_FEDHWYLDPITC2_BILLBOARD | Central |  | Decomm |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-12-08 |  |  |  | 2023-12-12 |  | 2023-12-22 | 2025-07-04 | CD//Ali akaram | 2024-01-08 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231213 | DU00002559261 |  |  |  |  | 2023-12-31 |  | BILLBOARD
P00675 | P032A_P00675OD_BTKAWANINDPARK | Northern |  | Decomm |  | 2024 Q1_496 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-10-26 |  |  |  | 2023-11-02 |  | 2023-11-06 | 2024-05-24 | CD//Rohizam | 2023-11-16 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231028-0063/Celcom Digi_RAN-CCSMY-TSS Decomm-Northern-20240131-0091 | DU00002559262 |  |  |  |  | 2023-12-15 |  | MONOPOLE
P00140 | P034C_P00140OD_SUNGAIDUAEXIT | Northern |  | Decomm |  | 2024 Q1_496 | ZA | GCI | 4.6 TSSR Approved |  | 2023-09-13 |  |  |  | 2023-10-11 |  | 2023-10-12 | 2023-10-27 | CD//Rohizam | 2023-10-13 | Celcom Digi_RAN-GCI-TSS-Northern-20230913-0049 | DU00002559263 |  |  |  |  | 2023-10-18 |  | TOWER
P00378 | P032A_P00378OD_TMNSERIBISTARI | Northern |  | Decomm |  | 2024 Q1_496 | ZA | GCI | 4.6 TSSR Approved |  | 2023-11-09 |  |  |  | 2023-11-07 |  | 2023-11-16 | 2023-12-18 | CD//Rohizam | 2023-11-16 | Celcom Digi_RAN-GCI-TSS-Northern-20230907-0046 | DU00002559264 |  |  |  |  | 2024-01-03 |  | BOOM
B00519 | B061I_B00519OD_PR_USJ10 | Central |  | Decomm |  | 2024 Q1_496 | AI | GTSB | 4.6 TSSR Approved |  | 2023-10-31 |  |  |  | 2024-01-18 |  | 2024-01-19 | 2024-03-26 | CD//Ali akaram | 2024-03-22 | CelcomDigi_RAN_GTSB_TSS_Central_20231101 | DU00002559265 |  |  |  |  | 2024-03-05 |  | BOOM
B02217 | B061I_B02217OD_JLNNILAMSBGHITECH | Central |  | Decomm |  | 2024 Q1_496 | AI | GTSB | 4.6 TSSR Approved |  | 2023-08-23 |  |  |  | 2023-10-12 |  | 2023-10-13 |  | CD//Ali Akaram | 2023-10-26 | CelcomDigi_RAN_GTSB_TSS_Central_20230824 | DU00002559266 |  | Missing FE part |  |  | 2023-12-20 |  | UNIPOLE
B00799 | B061I_B00799OD_TMNINDSBJ | Central |  | Decomm |  | 2024 Q1_496 | IE | GTSB | 4.6 TSSR Approved |  | 2023-11-20 |  |  |  | 2024-01-05 |  | 2024-01-12 | 2024-02-15 | CD//Norhaliza | 2024-01-30 | CelcomDigi_RAN_GTSB_TSS_Central_20231113 | DU00002559267 |  |  |  |  | 2023-10-20 |  | TRIPOD
P00631 | P032A_P00631OD_KGCHANGKATJAWI | Northern |  | Decomm |  | 2024 Q1_496 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-11-02 |  |  |  | 2023-11-08 |  | 2023-11-09 | 2023-11-23 | CD//Rohizam | 2023-11-10 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231103-0067 | DU00002559268 |  |  |  |  | 2024-01-09 |  | TOWER
B02802 | B061I_B02802OD_LRTTAIPAN | Central |  | Decomm |  | 2024 Q1_496 | AI | GTSB | 4.6 TSSR Approved |  | 2024-02-16 |  |  |  | 2024-02-17 |  | 2024-02-19 | 2024-05-27 | CD//Norhaliza | 2024-05-13 | CelcomDigi_RAN_GTSB_TSS_Central_20240509 | DU00002559269 |  |  |  |  | 2024-08-26 |  | MINIMAST
B02835 | B061E_B02835OD_LRTSUBANGALAM | Central |  | Decomm |  | 2024 Q1_496 | SS | Magicell | 4.6 TSSR Approved |  | 2023-10-10 |  |  |  | 2023-10-28 |  | 2023-11-02 | 2024-07-26 | CD//Norhaliza | 2023-11-15 | CelcomDigi_RAN_Magicell_TSS_Central_20231011 | DU00002559270 |  | . |  |  | 2024-04-18 |  | RAPOLE
P00761 | P032A_P00761OD_DESIGN_VILLAGE | Northern |  | Decomm |  | 2024 Q1_496 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-09-27 |  |  |  | 2023-10-11 |  | 2023-10-17 | 2023-10-27 | CD//Rohizam | 2023-10-17 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20231218-0078/Celcom Digi_RAN-GTSB-TSS-Northern-20231002-0042 | DU00002559271 |  |  |  |  | 2023-11-20 |  | MONOPOLE
P00115 | P033A_P00115OD_GUARPERAHU | Northern |  | Decomm |  | 2024 Q1_496 | SM | YPTT | 4.6 TSSR Approved |  | 2023-10-23 |  |  |  | 2023-10-26 |  | 2023-10-27 | 2024-03-26 | CD//Rohizam | 2023-10-30 | Celcom Digi_RAN-YPTT-TSS-Northern-20231026-0039 | DU00002559272 |  | Missing antenna photo, FE info and Photo |  |  | 2023-10-28 |  | TOWER
B02606 | B061H_B02606OD_LRT_SUBANGJAYA | Central |  | Decomm |  | 2024 Q1_496 | AI | GTSB | 4.6 TSSR Approved |  | 2024-02-20 |  |  |  | 2024-02-21 |  | 2024-02-22 | 2024-07-19 | CD//Norhaliza | 2024-05-31 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240225 | DU00002559273 |  |  |  |  | 2025-01-27 |  | WALL MOUNTED BOOM
P00704 | P034B_P00704OD_BERTAM_PERDANA4 | Northern |  | Decomm |  | 2024 Q1_496 | BY | CCSMY | 4.6 TSSR Approved | ¦ 0130 - Smart lock Issue, pending reTSS ¦ 0129 - Pending re-TSS, plan tssr submit 30/1 | 2023-11-22 |  |  |  | 2024-01-31 |  | 2024-02-01 | 2024-02-15 | CD//Rohizam | 2024-02-01 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231127-0073 | DU00002559274 |  |  |  |  | 2024-04-03 |  | LAMP_POLE
P00780 | P034B_P00780OD_PEKANPMTGSINTOK | Northern |  | Decomm |  | 2024 Q1_496 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-10-13 |  |  |  | 2023-10-27 |  | 2023-10-30 | 2023-12-18 | CD//Rohizam | 2023-10-30 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231016-0055 | DU00002559275 |  |  |  |  | 2024-01-24 |  | landside
B02000 | B061I_B02000OD_PUTRAHEIGHTBC | Central |  | Decomm |  | 2024 Q1_496 | SS | YPTT | 4.6 TSSR Approved |  | 2023-12-02 |  |  |  | 2023-12-04 |  | 2023-12-06 | 2024-01-22 | CD//Norhaliza | 2023-12-26 | CelcomDigi_RAN_YPTT_TSS_Central_202031203 | DU00002559276 |  |  |  |  | 2023-11-30 |  | CONCRETE POLE
P00697 | P034C_P00697OD_JARAK_ATAS | Northern |  | Decomm |  | 2024 Q1_496 | SM | YPTT | 4.6 TSSR Approved |  | 2023-11-09 |  |  |  | 2024-01-19 |  | 2024-01-23 | 2024-03-12 | CD//Rohizam | 2024-01-23 | Celcom Digi_RAN-YPTT-TSS-Northern-20231122-0044 | DU00002559277 |  |  |  |  | 2023-11-09 |  | TOWER
P00121 | P032A_P00121OD_SGDURI2 | Northern |  | Decomm |  | 2024 Q1_496 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-11-17 |  |  |  | 2023-11-17 |  | 2023-11-20 | 2023-11-23 | CD//Rohizam | 2023-11-20 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20231218-0078/Celcom Digi_RAN-GTSB-TSS-Northern-20231118-0066 | DU00002559278 |  |  |  |  | 2023-11-22 |  | TOWER
P00698 | P034B_P00698OD_DESA_KUALAMUDA_PNG | Northern |  | Decomm |  | 2024 Q1_496 | ZA | CCSMY | 4.6 TSSR Approved | ¦ 0129 - YPTT Remarks, site Cencled by PM | 2024-02-23 |  |  |  | 2024-02-27 |  | 2024-02-29 | 2024-03-05 | CD//Rohizam | 2024-02-29 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240226-0096 | DU00002559279 |  |  |  |  | 2024-04-03 |  | TOWER
1212C | SS 15 | Central |  | Modernization |  | 2024 Q1_496 | SS | Magicell | 4.6 TSSR Approved |  | 2023-11-29 | 2023-12-04 |  | 2023-12-08 |  | Closed | 2023-12-08 | 2023-12-14 | E//Kok Keen | 2023-12-12 | CelcomDigi_RAN_Magicell_TSS_Central_20231201 | DU00002559280 |  |  | 2024-02-28 | 2024-01-29 |  | In-Building System | 3m Boom (RT) | 6M | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
4372D | East BKIP | Northern |  | Modernization |  | 2024 Q1_496 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-09-04 | 2023-09-06 |  | 2023-09-11 |  | Closed | 2023-09-13 | 2023-10-31 | E//Hazida | 2023-10-30 | Celcom Digi_RAN-GCI-TSS-Northern-20230904-0044 | DU00002559281 |  |  | 2023-10-20 | 2023-10-14 |  | Monopole | 36M Monopole | 35 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3
1222C | Mentari Court | Central |  | Remote MOCN |  | 2024 Q1_496 |  | DATASCO | 14.2 Drop (Done Survey) |  | 2023-10-26 |  |  |  |  | To be Submitted | 2023-11-20 |  |  |  |  | DU00002559282 | [6 empty] | 6m Unipole RT |  |  | 3
1223C | Sunway Lagoon | Central |  | Modernization |  | 2024 Q1_496 | SS | GCI | 4.6 TSSR Approved |  | 2024-02-20 | 2024-02-26 |  | 2024-02-28 |  | Closed | 2024-02-28 | 2024-03-13 | E//Kok Keen | 2024-03-12 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240225 | DU00002559283 |  |  | 2024-03-27 | 2024-03-18 |  | Portables BTS | 6m Unipole RT | 9 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1225C | Sun-U Monash | Central |  | Remote MOCN |  | 2024 Q1_496 |  | DATASCO | 14.2 Drop (Done Survey) |  | 2023-11-23 |  |  |  |  | To be Submitted | [5 empty] | DU00002559284 | [6 empty] | 6m Unipole RT |  |  | 3
1224C | BRT Sunway Medical | Central |  | Remote MOCN |  | 2024 Q1_496 |  | DATASCO | 14.2 Drop (Done Survey) |  | 2023-12-04 |  |  |  |  | To be Submitted | [5 empty] | DU00002559285 | [6 empty] | 6m Unipole RT |  |  | 2
3537B | BRT USJ 1 | Central |  | Remote MOCN |  | 2024 Q1_496 |  | DATASCO | 14.2 Drop (Done Survey) |  | 2023-10-30 |  |  |  |  | To be Submitted | [5 empty] | DU00002559286 | [6 empty] | 6m Unipole RT
4346D | Tmn Seri Rupawan | Northern |  | Modernization |  | 2024 Q1_496 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-08-19 | 2023-08-22 |  | 2023-08-25 |  | Closed | 2023-08-28 | 2023-09-20 | E//Hazida | 2023-09-19 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230821-0032 | DU00002559287 |  |  | 2024-01-12 | 2024-01-10 |  | Lampole | 24M Rapole | 31M | Add R8852E S9000 x3+R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
1388A | Pernia Subang | Central |  | Modernization |  | 2024 Q1_496 | IE | Datasco | 4.6 TSSR Approved |  | 2023-09-06 | 2023-09-14 |  | 2023-09-17 |  | Closed | 2023-09-19 | 2023-09-20 | E//Kok Keen | 2023-09-20 | CelcomDigi_RAN_Datasco_TSS_Central_20230907 | DU00002559288 |  |  | 2023-10-13 | 2023-09-29 |  | Minimast | 5m RT (Minimast) | 9 | Add R9264M M1821 x3+A9732 M1821 x1,Dismantle R8854E S1800(A6A) x4+R8862A S2100(A6A) x4 | 1 | 0
1682B | Seksyen 26 | Central |  | Remote MOCN |  | 2024 Q1_496 | IE | DATASCO | 14.3 Drop (Done Survey + TSSR) |  | 2023-09-01 | 2023-09-05 |  | 2023-09-07 |  | Closed | 2024-07-18 |  |  |  | CelcomDigi_RAN_Datasco_TSS_Central_20230901 | DU00002559289 | [5 empty] | In-Building System | 3m Boom (RT) | 6m |  | 2
1179A | Indera Subang | Central |  | Remote MOCN |  | 2024 Q1_496 | CR | Datasco | 14.2 Drop (Done Survey) |  | 2023-09-06 | 2023-10-03 |  |  |  | To be Submitted |  |  |  |  | CelcomDigi_RAN_Datasco_TSS_Central_20230907 | DU00002559290 | [5 empty] | In-Building System | 3m Boom (RT) | SECTOR 1-6m, SECTOR 2-3m, SECTOR 3-3m, SECTOR 4-3.5m |  | 4
1215A | USJ 4 Teen | Central |  | Modernization |  | 2024 Q1_496 | XH | DATASCO | 4.6 TSSR Approved |  | 2023-08-29 | 2023-09-05 |  | 2023-09-07 |  | Closed | 2023-09-07 | 2023-09-08 | E//Razif | 2023-09-08 | CelcomDigi_RAN_Datasco_TSS_Central_20230901 | DU00002559291 |  |  | 2023-09-26 | 2023-09-26 |  | Pole | 3m Boom (RT) | 5 | Add R8894E M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8840-U216 x3++
1220A | Puchopshop | Central |  | Modernization |  | 2024 Q1_496 | IE | DATASCO | 4.6 TSSR Approved |  | 2023-08-22 | 2023-09-01 |  | 2023-09-05 |  | Closed | 2023-09-06 | 2023-12-20 | E//Razif | 2023-12-19 | CelcomDigi_RAN_Datasco_TSS_Central_20230823 | DU00002559292 |  |  | 2023-09-21 | 2023-09-21 |  | Minimast | 6m RT (Minimast) | 13 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3+R8882 S1800(B) x2+R8840-U216 x4++
1221A | Mentari Plaza | Central |  | Modernization |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-09-22 | 2023-09-20 |  | 2023-09-22 |  | Closed | 2023-09-25 | 2023-10-02 | E//Sumitra | 2023-09-27 | CelcomDigi_RAN_Datasco_TSS_Central_20230901 | DU00002559293 |  |  | 2023-10-28 | 2023-10-28 |  | In-Building System | 6m RT (Boom) | 6 | Add R9264M M1821 x4,Dismantle R8882 S1800B(B6B) x4+R8854D S2100(A4A) x4
1233B | TTDI Jaya Shoplot | Central |  | Remote MOCN |  | 2024 Q1_496 |  | DATASCO | 14.2 Drop (Done Survey) |  | 2023-08-22 | 2023-09-13 | [6 empty] | E//Kok Keen |  | CelcomDigi_RAN_Datasco_TSS_Central_20230823 | DU00002559294 | [5 empty] | In-Building System | 6m RT (Boom) | 5 |  | 3
1250B | Sek 27 Shah Alam | Central |  | Modernization |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-08-29 | 2023-09-26 |  | 2023-09-29 |  | Closed | 2023-10-02 | 2024-01-16 | E//Razif | 2024-01-16 | CelcomDigi_RAN_Datasco_TSS_Central_20230901 | DU00002559295 |  |  | 2023-10-10 | 2023-10-07 |  | Lampole | 20m Lampole | 30 | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8862A S2601(A6A) x1+R8894E M1821(A8A) x4 | 3 | 0
4211A | Spg Empat | Northern |  | Remote MOCN |  | 2024 Q1_496 | BY | CCSMY | 14.1 Drop (No Survey) |  |  | 2023-09-04 |  |  |  | To be Submitted |  |  | E//Ajay |  | N/A - site move to BAU | DU00002559296 | [5 empty] | Monopole | 40m Monopole | 40 |  | 23
1306B | Tmn Subang Mewah | Central |  | Modernization |  | 2024 Q1_496 | XH | DATASCO | 4.6 TSSR Approved |  | 2023-08-29 | 2023-10-05 |  | 2023-10-09 |  | Closed | 2023-10-18 | 2023-10-19 | E//Sumitra | 2023-10-19 | CelcomDigi_RAN_Datasco_TSS_Central_20230901 | DU00002559297 |  |  | 2023-10-27 | 2023-10-25 |  |  | 6m RT (Boom) | 7 | Add R9264M M1821 x4,Dismantle R8862A S1800(B6A) x1+R8894E M1821(A8A) x4
1314B | USJ 11 | Central |  | Modernization |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-09-03 | 2023-09-15 |  | 2023-09-19 |  | Closed | 2023-09-21 | 2023-10-01 | E//Kok Keen | 2023-09-21 | CelcomDigi_RAN_Datasco_TSS_Central_20230901 | DU00002559298 |  |  | 2023-09-29 | 2023-09-28 |  | In-Building System | 3m RT (Minimast) | 4m | Add R8894E M1821 x4,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x2+R8840-U216 x3++R8862A S2100(A6A) x1
1324B | Batu Tiga | Central |  | Modernization |  | 2024 Q1_496 | IE | DATASCO | 4.6 TSSR Approved |  | 2023-08-29 | 2023-09-20 |  | 2023-09-21 |  | Closed | 2023-09-21 | 2023-10-01 | E//Razif | 2023-09-22 | CelcomDigi_RAN_Datasco_TSS_Central_20230901 | DU00002559299 |  |  | 2023-09-26 | 2023-09-25 |  | Minaret | 3m Bipod (RT) | 6 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3
1348B | SS 18 Shoplot(ZED) | Central |  | Modernization |  | 2024 Q1_496 | IE | DATASCO | 4.6 TSSR Approved |  | 2023-08-22 | 2023-09-05 |  | 2023-09-08 |  | Closed | 2023-09-15 | 2023-09-21 | E//Razif | 2023-09-21 | CelcomDigi_RAN_Datasco_TSS_Central_20230823 | DU00002559300 |  |  | 2023-09-27 | 2023-09-26 |  | Minimast | 6m RT (Minimast) | 8 | Add R8894E M1821 x4,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8840-U216 x3++R8862A S2100(A6A) x1
1354B | Tmn Industri Sg Penaga | Central |  | Modernization |  | 2024 Q1_496 | IE | DATASCO | 4.6 TSSR Approved |  | 2023-08-22 | 2023-09-01 |  | 2023-09-05 |  | Closed | 2023-09-06 | 2023-09-07 | E//Razif | 2023-09-07 | CelcomDigi_RAN_Datasco_TSS_Central_20230823 | DU00002559301 |  |  | 2023-09-23 | 2023-09-21 |  | In-Building System | 3m Bipod (RT) | 3M | Add R9264M M1821 x3+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x4 | 3 | 0
1369A | Sek U 1 Shah Alam | Central |  | Modernization |  | 2024 Q1_496 | XH | DATASCO | 4.6 TSSR Approved |  | 2023-09-01 | 2023-09-05 |  | 2023-09-07 |  | Closed | 2023-09-11 | 2023-09-12 | E//Razif | 2023-09-22 | CelcomDigi_RAN_Datasco_TSS_Central_20230901 | DU00002559302 |  |  | 2023-09-25 | 2023-09-22 |  | In-Building System | 5.5m RT (Boom) | 5.5 | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 23 | 0
1391A | USJ 8 | Central |  | Modernization |  | 2024 Q1_496 | IE | DATASCO | 4.6 TSSR Approved |  | 2023-09-01 | 2023-09-12 |  | 2023-09-14 |  | Closed | 2023-09-15 | 2023-09-15 | E//Kok Keen | 2023-09-15 | CelcomDigi_RAN_Datasco_TSS_Central_20230901 | DU00002559303 |  |  | 2023-09-25 | 2023-09-23 |  | Minimast | 6m RT (Minimast) | 6 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
1397B | USJ21 Shoplot | Central |  | Modernization |  | 2024 Q1_496 | SS | Datasco | 4.6 TSSR Approved |  | 2023-09-22 | 2023-09-19 |  | 2023-10-06 |  | Closed | 2023-09-29 | 2023-10-03 | E//Kok Keen | 2023-10-03 | Celcom Digi_RAN-Datasco-TSS-Central-20230925 | DU00002559304 |  |  | 2023-10-25 | 2023-10-19 |  | Pole | 3m Boom (RT) | 7 | Add R9264H M901821 x4,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8862A S2100(A6A) x4
1405A | UNZA | Central |  | Modernization |  | 2024 Q1_496 | SS | DATASCO | 4.6 TSSR Approved |  | 2023-09-03 | 2023-09-15 |  | 2023-09-18 |  | Closed | 2023-09-19 | 2023-09-21 | E//Kok Keen | 2023-09-20 | CelcomDigi_RAN_Datasco_TSS_Central_20230825 | DU00002559305 |  |  | 2023-09-29 | 2023-09-29 |  | H-bracket pole | 3m Bipod (RT) | 6 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
1409B | Kesas Subang(ZED) | Central |  | Modernization |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-10-09 | 2023-10-16 |  | 2023-10-19 |  | Closed | 2023-10-19 | 2023-10-24 | E//Kok Keen | 2023-10-20 | CelcomDigi_RAN_Datasco_TSS_Central_20231011 | DU00002559306 |  |  | 2023-11-24 | 2023-11-10 |  | Wall mount boom | 3m Bipod (RT) | 2 | Add R8894E M1821 x2,Dismantle R8882-GUL1812 x2+R8840-U216 x2++
1412B | Kesas Seafield (ZED) | Central |  | Remote MOCN |  | 2024 Q1_496 |  | Datasco | 14.2 Drop (Done Survey) |  | 2023-09-29 | 2023-09-14 | [8 empty] | CelcomDigi_RAN_Datasco_TSS_Central_20230905 | DU00002559307 | [5 empty] | Monopole | 30m Monopole | 30
1424B | SS19Shoplot | Central |  | Modernization |  | 2024 Q1_496 | IE | Datasco | 4.6 TSSR Approved |  | 2023-09-06 | 2023-09-13 |  | 2023-09-15 |  | Closed | 2023-09-18 | 2023-09-21 | E//Razif | 2023-09-21 | CelcomDigi_RAN_Datasco_TSS_Central_20230901 | DU00002559308 |  |  | 2023-09-30 | 2023-09-26 |  | In-Building System | 6.5m RT (Boom) | 6.5 | Add R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3++
1432B | Batu 3 Toll | Central |  | Remote MOCN |  | 2024 Q1_496 | MA | Ascentrack | 14.3 Drop (Done Survey + TSSR) | AAU Cannot Install-Change MM to BI¦Space issue AAU can not install | 2023-08-28 | 2023-09-05 |  | 2023-09-08 |  | Closed |  |  |  |  | CelcomDigi_RAN_Ascentrack_TSS_Central_20230829 | DU00002559309 | NIC_S1_Change MM to BI_Space constraint_Digi OB |  |  |  |  | In-Building System | 6m RT (Boom) | 7 |  |  | 3
1703B | Seksyen 27 no 2 | Central |  | Modernization |  | 2024 Q1_496 | XH | DATASCO | 4.6 TSSR Approved |  | 2023-08-22 | 2023-08-24 |  | 2023-08-28 |  | Closed | 2023-08-29 | 2023-10-01 | E//Kok Keen | 2023-09-21 | CelcomDigi_RAN_Datasco_TSS_Central_20230823 | DU00002559310 |  |  | 2023-10-16 | 2023-10-14 |  |  | 3m RT (Minimast) | 8 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3
1708B | Central Sugar Junction | Central |  | Modernization |  | 2024 Q1_496 | CR | Datasco | 4.6 TSSR Approved |  | 2023-10-04 | 2023-10-11 |  | 2023-10-13 |  | Closed | 2023-10-16 | 2023-10-18 | E//Kok Keen | 2023-10-17 | CelcomDigi_RAN_Datasco_TSS_Central_20231005 | DU00002559311 |  |  | 2023-11-08 | 2023-10-24 |  |  | 3m Boom (RT) | 3 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
1792A | Section 27 ShahAlam | Central |  | Modernization |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-09-03 | 2023-09-12 |  | 2023-10-13 |  | Closed | 2023-09-27 | 2023-10-02 | E//Razif | 2023-09-29 | CelcomDigi_RAN_Datasco_TSS_Central_20230901 | DU00002559312 |  |  | 2023-10-14 | 2023-10-14 |  | In-Building System | 3m Bipod (RT) | 6 | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 3
1801A | Subang Parade | Central |  | Modernization |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-09-25 | 2023-10-03 |  | 2023-10-05 |  | Closed | 2023-10-07 | 2023-10-11 | E//Kok Keen | 2023-10-10 | Celcom Digi_RAN-Datasco-TSS-Central-20230925 | DU00002559313 |  |  | 2023-10-21 | 2023-10-17 |  | Pole | 3m Bipod (RT) | 6m | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
2028B | Taman Perindustrian USJ1 | Central |  | Modernization |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-08-23 | 2023-09-01 |  | 2023-09-05 |  | Closed | 2023-09-06 | 2023-09-07 | E//Sumitra | 2023-09-07 | CelcomDigi_RAN_Datasco_TSS_Central_20230824 | DU00002559314 |  |  | 2023-09-22 | 2023-09-21 |  | In-Building System | 3m Bipod (RT) | 6m | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x4 |  | 3
2071B | SEK U1 GLENMARIE | Central |  | Site Out (Modernization) | Modernization->Site Out->Replacement, Site Out (Modernization) | 2024 Q1_496 |  | YPTT | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2025-07-16 |  | 2025-07-14 |  |  | To be Submitted |  |  |  |  | SQ202506140184 | DU00002559315 |  |  |  |  | 2025-08-05 |  | 3m Bipod (RT)
2075B | Putra Height Shoplot (REL) | Central |  | Modernization |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-09-22 | 2023-09-21 |  | 2023-09-26 |  | Closed | 2023-09-27 | 2023-10-02 | E//Razif | 2023-09-29 | CelcomDigi_RAN_Datasco_TSS_Central_20230901 | DU00002559316 |  |  | 2023-10-07 | 2023-10-07 |  | In-Building System | 3m RT (Wall Mounted Pole) | 7m | Add R8852E S9000 x4+R8894E M1821 x4,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x2
2083A | Jaya Square SS17 | Central |  | Modernization |  | 2024 Q1_496 | SS | Datasco | 4.6 TSSR Approved |  | 2023-09-24 | 2023-09-26 |  | 2023-09-27 |  | Closed | 2023-09-29 | 2023-10-03 | E//Kok Keen | 2023-10-03 | CelcomDigi_RAN_Datasco_TSS_Central_20230907 | DU00002559317 |  |  | 2023-10-11 | 2023-10-09 |  | Pole | 3m Bipod (RT) | 3m & 6m | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3
4348C | Taman Rathna (REL) | Northern |  | Modernization |  | 2024 Q1_496 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-08-21 | 2023-08-25 |  | 2023-08-30 |  | Closed | 2023-08-31 | 2023-09-20 | E//Hazida | 2023-09-19 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230822-0033 | DU00002559318 |  |  | 2023-09-22 | 2023-09-22 |  | In-Building System | Rooftop 3m boom | 4m | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3+++R8862A S2100(A6A) x3
4332C | Politeknik Seb. Prai (REL) | Northern |  | Remote MOCN |  | 2024 Q1_496 |  | Ascentrack | 14.1 Drop (No Survey) | AAU Cannot Install-Change MM to BI¦Space issue cant install AAU |  | 2023-09-18 |  |  |  | To be Submitted |  |  |  |  | N/A - site move to BAU | DU00002559319 | BAU_S2_Change MM to BI_Space constraint_Digi OB |  |  |  |  | Minimast | 3m Bipod (RT) | 3m |  | 0 | 12
2347A | USJ 11F | Central |  | Modernization |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-08-23 | 2023-08-25 |  | 2023-08-29 |  | Closed | 2023-08-29 | 2023-09-01 | E//Kok Keen | 2023-09-01 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230824 | DU00002559320 |  |  | 2023-09-13 | 2023-09-12 |  | In-Building System | 3m Boom (RT) | 7 | Add R9264M M1821 x4,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+++R8862A S2100(A6A) x1
2545A | Warehouse Sg Penaga | Central |  | Modernization |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-08-23 | 2023-09-01 |  | 2023-09-05 |  | Closed | 2023-09-06 | 2023-09-07 | E//Kok Keen | 2023-09-07 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230824 | DU00002559321 |  |  | 2023-09-24 | 2024-11-22 |  | In-Building System | 6m RT (Boom) | 6 | Add R8852E S9000 x3+R8894E M1821 x3,Dismantle R8882-GUL1812 x5+R8840-U216 x3++
2599B | Persiaran Selangor | Central |  | Modernization |  | 2024 Q1_496 | IE | DATASCO | 4.6 TSSR Approved |  | 2023-09-01 | 2023-09-20 |  | 2023-09-21 |  | Closed | 2023-09-21 | 2023-10-01 | E//Razif | 2023-09-22 | CelcomDigi_RAN_Datasco_TSS_Central_20230901 | DU00002559322 |  |  | 2023-09-26 | 2023-09-25 |  | Unipole | 3m Bipod (RT) | 7 | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 3 | 0
2608B | SIME UEP Industrial | Central |  | Modernization |  | 2024 Q1_496 | XH | DATASCO | 4.6 TSSR Approved |  | 2023-08-29 | 2023-09-05 |  | 2023-09-07 |  | Closed | 2023-09-11 | 2023-09-12 | E//Razif | 2023-09-12 | CelcomDigi_RAN_Datasco_TSS_Central_20230901 | DU00002559323 |  |  | 2023-09-22 | 2023-09-21 |  | In-Building System | 3m Bipod (RT) | 7 | Add R8852E S9000 x3+R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3++
2622B | Putra Permai (Maxis) | Central |  | Modernization |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-08-23 | 2023-09-04 |  | 2023-09-08 |  | Closed | 2023-09-15 | 2023-10-17 | E//Razif | 2023-10-11 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230824 | DU00002559324 |  |  | 2023-10-18 | 2023-10-18 |  | Unipole | Tower | 8 | Add R9264H M901821 x3,Dismantle R8882 S1800(B) x3
2624B | IDS Kesas | Central |  | Remote MOCN |  | 2024 Q1_496 | CR | Ascentrack | 14.3 Drop (Done Survey + TSSR) |  | 2023-08-31 | 2023-09-04 |  | 2023-09-07 |  | Closed | 2023-09-07 | 2023-09-20 | E//Kok Keen |  | CelcomDigi_RAN_Ascentrack_TSS_Central_20230901 | DU00002559325 | [5 empty] | H-bracket pole | 3m Boom (RT) | 5 |  | 123
2662A6 | pBTS USJ16 | Central |  | Modernization |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-08-23 | 2023-08-28 |  | 2023-09-01 |  | Closed | 2023-09-05 | 2023-09-06 | E//Kok Keen | 2023-09-18 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230824 | DU00002559326 |  |  | 2023-09-22 | 2023-09-22 |  | Watertank | 25m pBTS | 32 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
4232A | Tmn Jawi Jaya | Northern |  | Modernization |  | 2024 Q1_496 | BY | GTSB | 4.6 TSSR Approved |  | 2023-08-30 | 2023-09-07 |  | 2023-09-13 |  | Closed | 2023-09-13 | 2023-10-27 | E//Hazida | 2023-10-24 | Celcom Digi_RAN-GTSB-TSS-Northern-20230904-0032 | DU00002559327 |  |  | 2023-10-09 | 2023-10-07 |  | In-Building System | 6m Unipole RT | 6m | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x2+R8840-U216 x3
4275A | Tasek Gelugor 2 | Northern |  | Modernization |  | 2024 Q1_496 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-08-22 | 2023-08-24 |  | 2023-08-28 |  | Closed | 2023-08-29 | 2023-09-20 | E//Hazida | 2023-09-19 | Celcom Digi_RAN-GTSB-TSS-Northern-20230823-0028 | DU00002559328 |  |  | 2024-01-12 | 2024-01-08 |  | Tower | 60m 3 Legged Tower | 60 | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 1
2751B | Temasya Industrial Park (REL) | Central |  | Modernization |  | 2024 Q1_496 | MA | YPTT | 4.6 TSSR Approved |  | 2023-08-30 | 2023-09-15 |  | 2023-09-20 |  | Closed | 2023-09-20 | 2023-09-22 | E//Kok Keen | 2023-09-22 | CelcomDigi_RAN_YPTT_TSS_Central_20230829 | DU00002559329 |  |  | 2023-09-29 | 2023-09-29 |  | Wall mount boom | 3m Bipod (RT) | 4M | Add R8852E S9000 x3+R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3
2798A | Giant Putra Height | Central |  | Modernization |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-08-28 | 2023-09-01 |  | 2023-09-05 |  | Closed | 2023-09-06 | 2023-09-12 | E//Razif | 2023-09-12 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230829 | DU00002559330 |  |  | 2023-10-02 | 2023-09-27 |  | BillBoard | 3m Bipod (RT) | 28 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
2827A | SHT Tunnel | Central |  | Modernization |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-08-29 | 2023-09-14 |  | 2023-09-17 |  | Closed | 2023-09-18 | 2024-01-16 | E//Razif | 2024-01-16 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230901 | DU00002559331 |  |  | 2023-09-26 | 2023-09-26 |  | Lampole | Tower | 16 | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8860E-GU908 x1+R8894E M1821(A8A) x3 | 3 | 0
2937A | Alam Indah | Central |  | Remote MOCN |  | 2024 Q1_496 | MA | Ascentrack | 14.2 Drop (Done Survey) |  | 2023-09-06 | 2023-09-08 |  |  |  | To be Submitted |  |  |  |  | CelcomDigi_RAN_Ascentrack_TSS_Central_20230907 | DU00002559332 | [5 empty] | Lampole | 24m Lampole | 20
3287A | LDP Puchong (REL) | Central |  | Modernization |  | 2024 Q1_496 | XH | Ascentrack | 4.6 TSSR Approved |  | 2023-08-30 | 2023-09-06 |  | 2023-09-09 |  | Closed | 2023-09-11 | 2023-10-03 | E//Razif | 2023-10-03 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230901 | DU00002559333 |  |  | 2023-10-07 | 2023-09-22 |  | Lampole | 30m Lampole | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
3650A1 | pBTS Persiaran Sabak Bernam (KM) | Central |  | Remote MOCN |  | 2024 Q1_496 | CR | Ascentrack | 14.3 Drop (Done Survey + TSSR) |  | 2023-08-24 | 2023-09-05 |  | 2023-09-09 |  | Closed |  |  |  |  | CelcomDigi_RAN_Ascentrack_TSS_Central_20230824 | DU00002559334 | [6 empty] | 25m pBTS | 25 |  |  | 12
4126A | Kg Baharu | Northern |  | Modernization |  | 2024 Q1_496 | SM | YPTT | 4.6 TSSR Approved |  | 2023-08-28 | 2023-09-27 |  | 2023-10-02 |  | Rectificating | 2023-10-03 | 2023-10-27 | E//Hazida | 2023-10-25 | Celcom Digi_RAN-YPTT-TSS-Northern-20230829-0030 | DU00002559335 |  |  | 2024-01-04 | 2023-12-13 |  | Tower | 45m 4 Legged Tower | 60 | Add R8852E S9000 x3+R8894E M1821 x3,Dismantle R8860E-GU908 x1+R8862A S1800(B6A) x3
4061B10 | pBTS Nippon Electric Shah Alam (C) | Central |  | Modernization |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-08-29 | 2023-09-01 |  | 2023-09-05 |  | Closed | 2023-09-05 | 2023-09-06 | E//Razif | 2023-09-06 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230901 | DU00002559336 |  |  | 2023-09-22 | 2023-09-22 |  | Watertank | 25m pBTS | 24 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
4100B | Taman Bukit Kechil | Northern |  | Remote MOCN |  | 2024 Q1_496 | HQ 1 | Ascentrack | 14.1 Drop (No Survey) |  |  | 2023-08-30 |  |  |  | To be Submitted |  |  | E//Hazida |  | N/A - site move to BAU | DU00002559337 | [5 empty] | Tower | 60m 3 Legged Tower | 61m
4102A | MCA Bkt Mertajam | Northern |  | Modernization |  | 2024 Q1_496 | HQ 1 | Ascentrack | 4.6 TSSR Approved |  | 2023-09-10 | 2023-09-29 |  | 2023-10-09 |  | Closed | 2023-10-10 | 2023-10-25 | E//Hazida | 2023-10-24 | Celcom Digi_RAN-Ascentrack-TSS-Northern-20230921-0010 | DU00002559338 |  |  | 2023-12-27 | 2023-12-27 |  | H-bracket pole | 3m Boom (RT) | 4m | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R9224E M1821(AAB) x3 | 1 | 0
4110B | Taman Bukit Indah (Maxis) | Northern |  | Modernization |  | 2024 Q1_496 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-08-26 | 2023-10-20 |  | 2023-10-24 |  | Closed | 2023-10-25 | 2023-10-27 | E//Hazida | 2023-10-27 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230828-0036 | DU00002559339 |  |  | 2024-01-04 | 2024-01-04 |  | Monopole | 45m Monopole | 30 | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8882-GUL1812 x3+R8840-U216 x3 | 3 | 0
4114A | Summit BM | Northern |  | Remote MOCN |  | 2024 Q1_496 |  | GCI | 14.1 Drop (No Survey) |  |  | 2023-09-16 |  |  |  | To be Submitted |  |  |  |  | N/A - site move to BAU | DU00002559340 | [5 empty] | In-Building System | 3m Boom (RT) | 6 |  | 12
4181A | Penanti | Northern |  | Remote MOCN |  | 2024 Q1_496 | HQ 1 | GCI | 14.1 Drop (No Survey) | ¦ Approved under NIC 12/9/2023 |  | 2023-08-25 |  |  |  | To be Submitted |  |  | E//Hazida |  | N/A - site move to BAU | DU00002559341 | [5 empty] | Tower | 45m 3 Legged Tower | 50 |  | 12
4182A | Mengkuang | Northern |  | Modernization |  | 2024 Q1_496 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-08-23 | 2023-08-25 |  | 2023-08-30 |  | Closed | 2023-08-31 | 2023-10-02 | E//Hazida | 2023-09-13 | Celcom Digi_RAN-GCI-TSS-Northern-20230824-0041 | DU00002559342 |  |  | 2023-09-21 | 2023-09-21 |  | Tower | 30m 3-legged tower | 45 | Add R9264H M901821 x3,Dismantle R9224E M1821(AAB) x3
4193A | Sg Puyu2 | Northern |  | Remote MOCN |  | 2024 Q1_496 |  | CCSMY | 14.1 Drop (No Survey) |  |  | 2023-09-07 |  |  |  | To be Submitted |  |  |  |  | N/A - site move to BAU | DU00002559343 | [5 empty] | Tower | 45m slim tower | 48 |  | 23
4196B | KG PERMATANG CHETAK | Northern |  | Modernization |  | 2024 Q1_496 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-08-21 | 2023-08-28 |  | 2023-08-30 |  | Closed | 2023-08-31 | 2023-09-20 | E//Hazida | 2023-09-19 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230822-0033 | DU00002559344 |  |  | 2023-09-20 | 2023-09-19 |  | Monopole | 30m PBTS | 32 | Add R8852E S9000 x3+R8894E M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1
4221A | Nibong Tebal | Northern |  | Modernization |  | 2024 Q1_496 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-10-12 | 2023-10-19 |  | 2023-10-24 |  | Closed | 2023-10-25 | 2023-10-27 | E//Hazida | 2023-10-27 | Celcom Digi_RAN-YPTT-TSS-Northern-20230904-0032 | DU00002559345 |  |  | 2023-12-29 | 2023-12-17 |  | In-Building System | 3m Bipod (RT) | 4M | Add R9264M M1821 x4,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x2+R8862A S2100(A6A) x4
4273A | Kepala Batas 2 | Northern |  | Remote MOCN |  | 2024 Q1_496 | BY | GTSB | 14.2 Drop (Done Survey) |  | 2023-12-07 | 2023-08-17 | [6 empty] | E//Hazida |  | N/A - site move to BAU | DU00002559346 | [5 empty] | Tower | 200ft 3 legged tower | 55M |  | 3
4276A | Sungai Dua 2 | Northern |  | Modernization |  | 2024 Q1_496 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-08-19 | 2023-09-04 |  | 2023-09-06 |  | Closed | 2023-09-07 | 2023-09-20 | E//Hazida | 2023-09-19 | Celcom Digi_RAN-GCI-TSS-Northern-20230819-0038 | DU00002559347 |  |  | 2023-10-18 | 2023-10-10 |  | Tower | 60m 4 Legged Tower | 61 | Add R9264M M1821 x2+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x4 | 23 | 0
2728A | Batu 3 KTM | Central |  | Modernization |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-08-22 | 2023-08-25 |  | 2023-08-30 |  | Closed | 2023-09-01 | 2023-09-08 | E//Kok Keen | 2023-09-06 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230823 | DU00002559348 |  |  | 2023-09-09 | 2023-09-09 |  | In-Building System | 6m Unipole RT | 5 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3
3890B | Shell USJ 9 Subang Jaya (REL) | Central |  | Modernization |  | 2024 Q1_496 | XH | Ascentrack | 4.6 TSSR Approved |  | 2023-09-07 | 2023-09-13 |  | 2023-09-16 |  | Closed | 2023-09-19 | 2023-09-20 | E//Kok Keen | 2023-09-19 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230911 | DU00002559349 |  |  | 2023-11-16 | 2023-10-27 |  | Petronas Pylon | 24m Pylon | 25 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
4716A | Batu Kawan (REL) | Northern |  | Modernization |  | 2024 Q1_496 | SM | Ascentrack | 4.6 TSSR Approved |  | 2023-08-09 | 2023-08-16 |  | 2023-08-18 |  | Rectificating | 2023-08-22 | 2023-09-06 | E//Hazida | 2023-09-06 | Celcom Digi_RAN-Ascentrack-TSS-Northern-20230824-0001 | DU00002559350 |  |  | 2023-11-06 | 2023-11-03 |  | Tower | 45m 3 Legged Tower | 60m | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 1 | 0
4195A | Kg Nyior | Northern |  | Remote MOCN |  | 2024 Q1_496 |  | GCI | 14.1 Drop (No Survey) |  |  | 2023-09-30 |  |  |  | To be Submitted | [5 empty] | DU00002559351 | [5 empty] | Tower | 45m 3 Legged Tower | 60 |  |  | 12
4185A | Tasek Mutiara | Northern |  | Remote MOCN |  | 2024 Q1_496 | BY | Ascentrack | 14.1 Drop (No Survey) |  |  | 2023-09-04 |  |  |  | To be Submitted |  |  | E//Hazida |  | N/A - site move to BAU | DU00002559352 | [5 empty] | Tower | 45m 3 Legged Tower | 49m |  | 12
2647A | PJS 6 | Central |  | Modernization | Modernization->Site Out->Modernization | 2024 Q1_496 | AI | YPTT | 4.6 TSSR Approved |  | 2025-07-09 | 2025-07-23 |  | 2025-07-28 |  | Closed | 2025-07-29 | 2025-09-18 | E//Ali | 2025-08-01 | SQ202506140184 | DU00002559353 |  |  | 2025-08-23 | 2025-08-15 |  | BillBoard | Billboard | 3m | Add A9732 M1821x2+R8894E M1821x1, Dismantle R8862A S1800(B6A)x5+R8862A S2100(A6A)x3+R8862A S2601(A6A)x2 | 23 | 0
9311A | JLN Bako | Sarawak |  | Modernization |  | 2024 Q1_496 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-12-20 | 2024-01-09 |  | 2024-01-15 |  | Closed | 2024-01-17 | 2024-01-19 | E//Hannah | 2024-01-19 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230821 | DU00002559354 |  | 1601: 1. Existing Radio info Sector 1, 2 & 3 not tally with ML, please check 2. Missing dimension for cabinet location, compounding and cable ladder in Top View Construction Drawing. And also, missing horizontal cable ladder from RRU ground to tower 3. 3. Missing dropdown list for pager Sector 1, 2 & 3, please check your excel 4. Please fill up key type at page 1 and padlock photo is missing 5. missing RRU reuse | 2024-04-20 | 2024-01-23 |  | Tower | Tower | 68 | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8860E-GU908 x2+R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 1 | 0
2555B | Jln Subang Permai | Central |  | Modernization |  | 2024 Q1_496 | CR | Ascentrack | 4.6 TSSR Approved |  | 2023-08-31 | 2023-09-04 |  | 2023-09-07 |  | Closed | 2023-09-07 | 2023-10-02 | E//Razif | 2023-09-29 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230901 | DU00002559355 |  |  | 2023-10-13 | 2023-10-12 |  | Lampole | 24m Lampole | 24m | Add R9264M M1821 x3,Dismantle R8882 S1800(B) x2+R8882 S1800B(B6B) x1+R8862A S2100(A6A) x3
4189B | Taman Seri Mengkuang | Northern |  | Modernization |  | 2024 Q1_496 | SM | GCI | 4.6 TSSR Approved |  | 2023-08-23 | 2023-08-30 |  | 2023-09-04 |  | Rectificating | 2023-09-07 | 2023-10-02 | E//Hazida | 2023-09-14 | Celcom Digi_RAN-GCI-TSS-Northern-20230824-0041 | DU00002559356 |  |  | 2023-09-21 | 2023-09-21 |  | In-Building System | 3m Bipod (RT) | 8 | Add R8852E S9000 x3+R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8881 S2100 x3
2607B | USJ 3B | Central |  | Modernization |  | 2024 Q1_496 | XH | Ascentrack | 4.6 TSSR Approved |  | 2023-08-23 | 2023-08-30 |  | 2023-09-03 |  | Closed | 2023-09-05 | 2023-09-06 | E//Kok Keen | 2023-09-06 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230824 | DU00002559357 |  |  | 2023-09-23 | 2023-09-22 |  |  | 24m Lampole | 7 | Add R8894E M1821 x3,Dismantle R8882 S1800B(B6B) x3++R8881 S2100 x3+
4102B | Taman Alma Kijang 2 | Northern |  | Modernization |  | 2024 Q1_496 | ZA | GCI | 4.6 TSSR Approved |  | 2023-08-24 | 2023-08-24 |  | 2023-08-28 |  | Closed | 2023-08-29 | 2023-10-02 | E//Hazida | 2023-10-12 | Celcom Digi_RAN-GCI-TSS-Northern-20230825-0042 | DU00002559358 |  |  | 2023-09-29 | 2023-09-29 |  | In-Building System | 3m RT (Wall Mounted Pole) | 6 | Add R8852E S9000 x1+R9264M M1821 x2+A9732 M1821 x2,Dismantle R8854E S1800(A6A) x4+R8862A S2100(A6A) x1+R8854D S2100(A4A) x3 | 12 | 0
9091B | Kenyalang MP | Sarawak |  | Modernization |  | 2024 Q1_496 | SH | Trintel | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦sacofa lampole not allow to add AAU | 2023-08-17 | 2023-09-12 |  | 2023-09-15 |  | Closed | 2023-09-15 | 2023-10-01 | E//Hannah | 2023-09-25 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230823 | DU00002559359 | NIC_S1_Change MM to BI_owner reject_SACOFA SDN BHD |  | 2023-10-31 | 2023-10-26 |  | Pole | 24m Lampole | 30m | Add R9264M M1821 x4+R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 3
2619B | Tmn Alam Megah MP | Central |  | Remote MOCN |  | 2024 Q1_496 |  | Ascentrack | 14.2 Drop (Done Survey) |  | 2023-08-28 | 2023-09-05 | [8 empty] | CelcomDigi_RAN_Ascentrack_TSS_Central_20230829 | DU00002559360 | [5 empty] | Monople Tree | 45m Monopole Tree | 45 |  | 12
2611B | Persiaran Klang Hicom | Central |  | Remote MOCN |  | 2024 Q1_496 |  | Ascentrack | 14.2 Drop (Done Survey) | AAU Cannot Install-S2 MM change to normal sector¦Space constraint,need to change to normal sector | 2023-10-27 |  |  |  |  | To be Submitted | [5 empty] | DU00002559361 | [6 empty] | 24m Pylon
3738A | Sekolah Agama Rendah Anggur | Central |  | Modernization |  | 2024 Q1_496 | CR | Datasco | 4.6 TSSR Approved |  | 2023-09-04 | 2023-10-09 |  | 2023-10-11 |  | Closed | 2023-10-12 | 2023-10-17 | E//Kok Keen | 2023-10-13 | CelcomDigi_RAN_Datasco_TSS_Central_20230905 | DU00002559362 |  |  | 2023-10-21 | 2023-10-18 |  | Lampole | 24m Lampole | 30 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
4800A | Sunshine Bertam RT | Northern |  | Remote MOCN |  | 2024 Q1_496 |  | Ascentrack | 14.1 Drop (No Survey) |  |  | 2023-09-26 |  |  |  | To be Submitted |  |  |  |  | N/A - site move to BAU | DU00002559363 | [5 empty] | Unipole | 3m Boom (RT) | 10m
2605B | Kesas Billboard USJ 3 | Central |  | Modernization |  | 2024 Q1_496 | IE | Ascentrack | 4.6 TSSR Approved |  | 2023-08-24 | 2023-09-04 |  | 2023-09-06 |  | Closed | 2023-09-07 | 2023-09-08 | E//Razif | 2023-09-08 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230825 | DU00002559364 |  |  | 2023-12-16 | 2023-10-10 |  | BillBoard | Billboard | 27 | Add R9264H M901821 x3,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3
2613B | Surau Addin Seksyen 27 | Central |  | Remote MOCN |  | 2024 Q1_496 | AI | GTSB | 14.3 Drop (Done Survey + TSSR) |  | 2023-08-23 | 2023-08-25 |  | 2023-08-30 |  | Closed | 2023-08-30 | 2023-09-04 | E//Razif |  | CelcomDigi_RAN_GTSB_TSS_Central_20230824 | DU00002559365 | [5 empty] | Lampole | 24m Lampole | 25m
4192B | Jalan Bukit Tengah | Northern |  | Modernization |  | 2024 Q1_496 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-09-27 | 2023-10-05 |  | 2023-10-10 |  | Closed | 2023-10-11 | 2023-10-27 | E//Hazida | 2023-10-24 | Celcom Digi_RAN-GCI-TSS-Northern-20231002-0055 | DU00002559366 |  |  | 2023-10-22 | 2023-10-20 |  | Monopole | 30m Monopole | 85 | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 | 12 | 0
1960B | Taylor Lakeside Campus | Central |  | Modernization |  | 2024 Q1_496 | SS | DATASCO | 4.6 TSSR Approved |  | 2023-09-03 | 2023-09-15 |  | 2023-09-18 |  | Closed | 2023-09-19 | 2023-10-02 | E//Sumitra | 2023-09-27 | CelcomDigi_RAN_Datasco_TSS_Central_20230901 | DU00002559367 |  |  | 2023-10-20 | 2023-10-17 |  | In-Building System | 3m Boom (RT) | 6m | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 12 | 0
3314B | KM14 FED HWY | Central |  | Modernization |  | 2024 Q1_496 | CR | Ascentrack | 4.6 TSSR Approved |  | 2023-09-02 | 2023-09-14 |  | 2023-09-18 |  | Closed | 2023-09-19 | 2023-10-01 | E//Razif | 2023-09-27 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230821 | DU00002559368 |  |  | 2023-10-04 | 2023-10-04 |  | BillBoard | 3m Bipod (RT) | 43.6 | Add R9264M M1821 x3+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x4 | 1 | 0
3127B | USJ6 (HSR) | Central |  | Modernization |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-08-28 | 2023-09-01 |  | 2023-09-05 |  | Closed | 2023-09-06 | 2023-09-07 | E//Kok Keen | 2023-09-07 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230829 | DU00002559369 |  |  | 2023-09-21 | 2023-09-21 |  | In-Building System | 3m RT (Wall Mounted Pole) | 4 | Add R9264M M1821 x3,Dismantle R8882 S1800B(B6B) x3+R8854D S2100(A4A) x3
3667A | Subang Hi-Tech Lot 43 (REL) | Central |  | Modernization |  | 2024 Q1_496 | AI | Magicell | 4.6 TSSR Approved |  | 2023-10-17 | 2023-10-17 |  | 2023-10-18 |  | Rectificating | 2023-10-18 | 2023-10-19 | E//Kok Keen | 2023-10-19 | CelcomDigi_RAN_Magicell_TSS_Central_20231018 | DU00002559370 |  |  | 2023-11-16 | 2023-10-23 |  | Tower | 4 Legged Tower | 90M | Add R8894E M1821 x3,Dismantle R8882 S1800B(B6B) x3
4243B | kg Selamat (REL) | Northern |  | Remote MOCN |  | 2024 Q1_496 | HQ 1 | Ascentrack | 14.1 Drop (No Survey) |  |  | 2023-10-11 |  |  |  | To be Submitted |  |  | E//Hazida |  | N/A - site move to BAU | DU00002559371 | [5 empty] | Tower | 45m 3 Legged Tower | 40M |  | 13
4128A | Tmn Kota Permai (REL) | Northern |  | Modernization |  | 2024 Q1_496 | SM | GCI | 4.6 TSSR Approved |  | 2023-09-12 | 2023-09-20 |  | 2023-09-22 |  | Rectificating | 2023-09-25 | 2023-10-26 | E//Hazida | 2023-10-24 | Celcom Digi_RAN-GCI-TSS-Northern-20230914-0050 | DU00002559372 |  |  | 2023-10-09 | 2023-10-07 |  | In-Building System | 3m Boom (RT) | 6 | Add R8894E M1821 x3,Dismantle R8882 S1800(B) x3++R8881 S2100 x3+
3290B | Federal HW (Free Scale) | Central |  | Modernization |  | 2024 Q1_496 | XH | Ascentrack | 4.6 TSSR Approved |  | 2023-10-12 | 2023-10-17 |  | 2023-10-20 |  | Closed | 2023-10-23 | 2023-10-25 | E//Sumitra | 2023-10-24 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231013 | DU00002559373 |  |  | 2023-11-20 | 2023-11-01 |  | BillBoard | Billboard | structure height antenna boom= 4m | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R8882 S1800B(B6B) x3+R8894E M1821(A8A) x3 | 1
3396B | LDP-Kesas Interchange | Central |  | Modernization |  | 2024 Q1_496 | SS | Ascentrack | 4.6 TSSR Approved |  | 2023-08-20 | 2023-08-25 |  | 2023-09-01 |  | Closed | 2023-09-05 | 2023-11-29 | E//Razif | 2023-11-28 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230821 | DU00002559374 |  |  | 2024-02-24 | 2024-01-16 |  | BillBoard | Billboard | 30 | Add R8852E S9000 x2+R9264H M901821 x2+A9732 M1821 x2,Dismantle R8854 S2600(A4A) x1+R9224E M1821(AAB) x5 | 13 | 0
3676B | Taipan Carpark | Central |  | Modernization |  | 2024 Q1_496 | AI | GTSB | 4.6 TSSR Approved |  | 2023-09-13 | 2023-09-18 |  | 2023-09-21 |  | Closed | 2023-10-02 | 2023-11-15 | E//Kok Keen | 2023-11-14 | CelcomDigi_RAN_GTSB_TSS_Central_20230914 | DU00002559375 |  |  | 2023-11-23 | 2023-10-11 |  |  | 3m RT (Wall Mounted Pole) | 5 | Add R8852E S9000 x3+R8894E M1821 x3,Dismantle R8882 S1800B(B6B) x1+R8862A S1800(B6A) x2
3991B | AEON Big Subang Jaya Outdoor | Central |  | Remote MOCN |  | 2024 Q1_496 | AI | GTSB | 14.2 Drop (Done Survey) |  | 2023-09-08 |  |  |  |  | To be Submitted | [5 empty] | DU00002559376 | [6 empty] | 3m Boom (RT) |  |  | 1
3757B | Subang Square | Central |  | Modernization |  | 2024 Q1_496 | AI | GTSB | 4.6 TSSR Approved |  | 2023-09-01 | 2023-09-05 |  | 2023-09-08 |  | Closed | 2023-09-08 | 2023-09-12 | E//Kok Keen | 2023-09-12 | CelcomDigi_RAN_GTSB_TSS_Central_20230904 | DU00002559377 |  |  | 2023-10-07 | 2023-10-07 |  |  | 3m Boom (RT) | 2m | Add R9264H M901821 x3,Dismantle R9224E M1821(AAB) x3
3759B | Courtyard SS15 Outdoor | Central |  | Modernization |  | 2024 Q1_496 | AI | GTSB | 4.6 TSSR Approved |  | 2023-09-13 | 2023-09-14 |  | 2023-09-19 |  | Closed | 2023-10-04 | 2023-10-18 | E//Kok Keen | 2023-10-05 | CelcomDigi_RAN_GTSB_TSS_Central_20230914 | DU00002559378 |  |  | 2023-10-13 | 2023-10-09 |  |  | 3m Bipod (RT) | 3m | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x4
1411B | Wisma Kesas (ZED) | Central |  | Modernization |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-09-07 | 2023-09-13 |  | 2023-09-18 |  | Closed | 2023-10-20 | 2023-10-23 | E//Sumitra | 2023-10-23 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230911 | DU00002559379 |  |  | 2023-10-10 | 2023-09-27 |  | In-Building System | 6m RT (Minimast) | 8.6 | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R8854E S1800(A6A) x3+R8862A S2100(A6A) x3 | 1 | 0
3959B5 | pBTS Metropark (Subang Hi-Tech) | Central |  | Modernization |  | 2024 Q1_496 | AI | GTSB | 4.6 TSSR Approved |  | 2023-08-29 | 2023-09-04 |  | 2023-09-08 |  | Closed | 2023-09-11 | 2023-09-12 | E//Kok Keen | 2023-09-12 | CelcomDigi_RAN_GTSB_TSS_Central_20230901 | DU00002559380 |  |  | 2023-09-28 | 2023-09-27 |  | Monopole | 25m pBTS | 25 | Add R9264H M901821 x3,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3
4512C | Mukim Sg Bakap (REL) | Northern |  | Remote MOCN |  | 2024 Q1_496 | SM | Ascentrack | 14.1 Drop (No Survey) |  |  | 2023-08-30 |  |  |  | To be Submitted |  |  | E//Hazida |  | N/A - site move to BAU | DU00002559381 | [5 empty] | Monopole | 30m Monopole | 41m |  | 24
4290C | Tmn Merak | Northern |  | Remote MOCN |  | 2024 Q1_496 |  | CCSMY | 14.1 Drop (No Survey) |  |  | 2023-09-01 |  |  |  | To be Submitted |  |  |  |  | N/A - site move to BAU | DU00002559382 | [5 empty] | Lampole | 30m RDS | 30m |  | 123
4484C | Kota Permai | Northern |  | Modernization |  | 2024 Q1_496 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-09-11 | 2023-09-13 |  | 2023-09-19 |  | Closed | 2023-09-20 | 2023-10-31 | E//Hazida | 2023-10-31 | Celcom Digi_RAN-GCI-TSS-Northern-20230912-0048 | DU00002559383 |  |  | 2023-09-29 | 2023-09-29 |  | Lampole | 30m Monopole | 24 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
4105C | Kg Jawi Sempit | Northern |  | Remote MOCN |  | 2024 Q1_496 |  | GTSB | 14.2 Drop (Done Survey) |  | 2023-12-07 | 2023-09-13 |  |  |  | To be Submitted |  |  |  |  | N/A - site move to BAU | DU00002559384 | [5 empty] | Monopole | Tower | 30m
4578C | Taman Sg Bakap | Northern |  | Modernization |  | 2024 Q1_496 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-09-01 | 2023-09-06 |  | 2023-09-12 |  | Closed | 2023-09-13 | 2023-10-27 | E//Hazida | 2023-10-26 | Celcom Digi_RAN-GTSB-TSS-Northern-20230904-0032 | DU00002559385 |  |  | 2023-10-25 | 2023-10-22 |  | Tower | Tower | 45 | Add R8852E S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8862A S1800(B6A) x4+R8862A S2100(A6A) x4+R8862A S2601(A6A) x1 | 12 | 0
2943A | Seksyen 22 Shah Alam | Central |  | Modernization |  | 2024 Q1_496 | AI | GTSB | 4.6 TSSR Approved |  | 2023-08-24 | 2023-08-29 |  | 2023-09-04 |  | Closed | 2023-09-06 | 2023-09-12 | E//Razif | 2023-09-12 | CelcomDigi_RAN_GTSB_TSS_Central_20230825 | DU00002559386 |  |  | 2023-09-15 | 2023-09-15 |  | Monopole | landside | 20m | Add R9264H M901821 x4,Dismantle R8894E M1821(A8A) x4
4626C | Taman Industri Bukit Panchor | Northern |  | Modernization |  | 2024 Q1_496 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-08-29 | 2023-09-04 |  | 2023-09-08 |  | Closed | 2023-09-11 | 2024-05-15 | E//Hazida | 2023-10-01 | Celcom Digi_RAN-YPTT-TSS-Northern-20230830-0031 | DU00002559387 |  |  | 2023-12-08 | 2023-12-06 |  | Watertank | TBC | 35 | Add R8854E S1800 x3+R9224E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3
4612C | SMK Bandar Baru Tasek Mutiara | Northern |  | Modernization |  | 2024 Q1_496 | SM | GTSB | 4.6 TSSR Approved |  | 2023-09-19 | 2023-09-21 |  | 2023-09-29 |  | Rectificating | 2023-10-02 | 2023-10-27 | E//Hazida | 2023-10-24 | Celcom Digi_RAN-GTSB-TSS-Northern-20230920-0039 | DU00002559388 |  |  | 2023-11-09 | 2023-10-23 |  | In-Building System | 30m Monopole | 5 | Add R9264H M901821 x4,Dismantle R8862A S1800(B6A) x4
1242B | PJS5 Surau | Central |  | Modernization |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-09-02 | 2023-09-06 |  | 2023-09-10 |  | Closed | 2023-09-12 | 2023-09-21 | E//Sumitra | 2023-09-20 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230904 | DU00002559389 |  |  | 2023-09-22 | 2023-09-22 |  | Lampole | 20m Lampole | 21 | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 3 | 0
4661C | Medicare Specialist (REL) | Northern |  | Modernization |  | 2024 Q1_496 | BY | GTSB | 4.6 TSSR Approved |  | 2023-08-24 | 2023-08-29 |  | 2023-09-02 |  | Closed | 2023-09-05 | 2023-10-02 | E//Hazida | 2023-09-14 | Celcom Digi_RAN-GTSB-TSS-Northern-20230825-0030 | DU00002559390 |  |  | 2023-09-26 | 2023-09-26 |  | In-Building System | 3m Boom (RT) | 8 | Add R9264M M1821 x4,Dismantle R8862A S1800(B6A) x4+R8854D S2100(A4A) x4
3423C | Surau Al Mardhiah (REL) | Central |  | Remote MOCN |  | 2024 Q1_496 | AI | GTSB | 14.3 Drop (Done Survey + TSSR) |  | 2023-09-04 | 2023-08-23 |  | 2023-09-04 |  | Under Approval | 2023-09-06 | 2023-09-13 | E//Kok Keen |  | CelcomDigi_RAN_GTSB_TSS_Central_20230905 | DU00002559391 | [5 empty] | Monopole | 24m Lampole | 30 |  | 1
9271B3 | pBTS YKGI Holdings Demak Laut | Sarawak |  | Modernization |  | 2024 Q1_496 | SH | AllStar | 4.6 TSSR Approved |  | 2023-08-10 | 2023-08-11 |  | 2023-08-22 |  | Closed | 2023-08-22 | 2023-08-24 | E//Hannah | 2023-08-24 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230807 | DU00002559392 |  |  | 2023-09-15 | 2023-09-12 |  | Watertank | 25m pBTS | 25 | Add R8852E S9000 x3+R8854E S1800 x3+R9224E M1821 x3,Dismantle R8882 S1800(B) x3
3508C | Digi Lot 10 Recreational Park | Central |  | Modernization |  | 2024 Q1_496 | AI | GTSB | 4.6 TSSR Approved |  | 2023-08-30 | 2023-09-07 |  | 2023-09-12 |  | Closed | 2023-09-12 | 2023-09-13 | E//Kok Keen | 2023-09-13 | CelcomDigi_RAN_GTSB_TSS_Central_20230901 | DU00002559393 |  |  | 2023-09-30 | 2023-09-22 |  | Minimast | Tower | 20m | Add R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
3740C | FEDERAL HW – GAB (REL) | Central |  | Modernization |  | 2024 Q1_496 | IE | Ascentrack | 4.6 TSSR Approved |  | 2023-09-01 | 2023-09-04 |  | 2023-09-07 |  | Closed | 2023-09-11 | 2023-09-12 | E//Kok Keen | 2023-09-08 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230904 | DU00002559394 |  |  | 2023-10-31 | 2023-10-26 |  | BillBoard | landside | 26.3m | Add R8852E S9000 x3+R8854E S1800 x3+R9224E M1821 x3,Dismantle R8894E M1821(A8A) x3
4989C | Gemilang Business Centre | Northern |  | Modernization |  | 2024 Q1_496 | SM | GTSB | 4.6 TSSR Approved |  | 2023-08-27 | 2023-08-29 |  | 2023-09-01 |  | Rectificating | 2023-09-04 | 2023-10-02 | E//Hazida | 2023-09-13 | Celcom Digi_RAN-GTSB-TSS-Northern-20230828-0031 | DU00002559395 |  |  | 2023-09-26 | 2023-09-26 |  | In-Building System | 3m Boom (RT) | 6 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
4125D | Kampung Valdor | Northern |  | Modernization |  | 2024 Q1_496 | BY | GTSB | 4.6 TSSR Approved |  | 2023-08-13 | 2023-08-16 |  | 2023-08-19 |  | Closed | 2023-08-24 | 2023-08-24 | E//Hazida | 2023-08-24 | Celcom Digi_RAN-GTSB-TSS-Northern-20230817-0025 | DU00002559396 |  |  | 2023-10-21 | 2023-10-21 |  | Monopole | 30m Monopole | 30 | Add R8852E S9000 x3+R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
3471C2 | pBTS Perindustrian Subang Utama | Central |  | Modernization |  | 2024 Q1_496 | SS | YPTT | 4.6 TSSR Approved |  | 2023-08-24 | 2023-10-02 |  | 2023-10-04 |  | Closed | 2023-10-06 | 2023-11-22 | E//Razif | 2023-11-21 | CelcomDigi_RAN_YPTT_TSS_Central_20230825 | DU00002559397 |  |  | 2023-10-18 | 2023-10-17 |  | Watertank | 25m pBTS | 20 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
4339D | Penaga Town 2 (Celcom) | Northern |  | Modernization |  | 2024 Q1_496 | BY | Ascentrack | 4.6 TSSR Approved |  | 2023-08-15 | 2023-08-23 |  | 2023-08-28 |  | Closed | 2023-08-29 | 2023-10-02 | E//Hazida | 2023-09-12 | Celcom Digi_RAN-Ascentrack-TSS-Northern-20230824-0001 | DU00002559398 |  |  | 2023-10-06 | 2023-09-30 |  | Monopole | 30M RDS | 30m | Add R8852E S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 12 | 0
4403D | West BKIP | Northern |  | Remote MOCN |  | 2024 Q1_496 |  | GCI | 14.1 Drop (No Survey) |  |  | 2023-11-30 |  |  |  | To be Submitted | [5 empty] | DU00002559399 | [5 empty] | Monopole | 36M Monopole | 39 |  | 23
4404D | Penang 2nd Bridge | Northern |  | Remote MOCN |  | 2024 Q1_496 |  | GCI | 14.1 Drop (No Survey) |  |  | 2023-09-18 |  |  |  | To be Submitted |  |  |  |  | N/A - site move to BAU | DU00002559400 | [5 empty] | Tower | 45m Tower | 60 |  | 1
1655C | Goodyear Court | Central |  | Modernization |  | 2024 Q1_496 | AI | GTSB | 4.6 TSSR Approved |  | 2023-08-23 | 2023-08-28 |  | 2023-08-31 |  | Closed | 2023-09-01 | 2023-09-01 | E//Razif | 2023-09-01 | CelcomDigi_RAN_GTSB_TSS_Central_20230824 | DU00002559401 |  |  | 2023-10-10 | 2023-10-10 |  | Monopole | landside | 24m | Add R8852E S9000 x3+R8854E S1800 x3+R9224E M1821 x3,Dismantle R8894E M1821(A8A) x3
4434D | Mermok | Northern |  | Modernization |  | 2024 Q1_496 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-09-06 | 2023-09-12 |  | 2023-09-14 |  | Closed | 2023-09-15 | 2023-10-18 | E//Hazida | 2023-10-15 | Celcom Digi_RAN-YPTT-TSS-Northern-20230907-0034 | DU00002559402 |  |  | 2023-10-12 | 2023-10-09 |  | Lampole | 30M Lampole | 30 | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R9224E M1821(AAB) x3 | 3 | 0
4441D | Taman Sepadu | Northern |  | Modernization |  | 2024 Q1_496 | WP | GTSB | 4.6 TSSR Approved |  | 2023-12-19 | 2023-12-21 |  | 2024-01-04 |  | Closed | 2024-01-08 | 2024-01-11 | E//Hazida | 2024-01-10 | Celcom Digi_RAN-GTSB-TSS-Northern-20231225-0080 | DU00002559403 |  |  | 2024-02-10 | 2024-01-13 |  | Tower | 45m Tower | 46M | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1746C | Surau Al Mahdaniah (REL) | Central |  | Modernization |  | 2024 Q1_496 | AI | GTSB | 4.6 TSSR Approved |  | 2023-08-30 | 2023-09-06 |  | 2023-09-11 |  | Closed | 2023-09-12 | 2023-09-12 | E//Kok Keen | 2023-09-12 | CelcomDigi_RAN_GTSB_TSS_Central_20230901 | DU00002559404 |  |  | 2023-10-14 | 2023-10-12 |  | Lampole | 20M LP | 21M | Add R8894E M1821 x3,Dismantle R8882-GUL1812 x3
1763C | Seksyen 23 Shah Alam Industrial | Central |  | Modernization |  | 2024 Q1_496 | SS | YPTT | 4.6 TSSR Approved |  | 2023-08-23 | 2023-09-06 |  | 2023-09-11 |  | Closed | 2023-09-13 | 2023-10-01 | E//Razif | 2023-09-21 | CelcomDigi_RAN_YPTT_TSS_Central_20230824 | DU00002559405 |  |  | 2023-09-22 | 2023-09-22 |  | Monopole | 30m monopole | 24M | Add R9264H M901821 x4,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x1
3050C8 | pBTS Lahar Tiang | Northern |  | Modernization |  | 2024 Q1_496 | BY | YPTT | 4.6 TSSR Approved |  | 2023-08-22 | 2023-08-28 |  | 2023-08-30 |  | Closed | 2023-08-30 | 2023-09-20 | E//Hazida | 2023-09-19 | Celcom Digi_RAN-YPTT-TSS-Northern-20230823-0028 | DU00002559406 |  |  | 2023-10-28 | 2023-10-19 |  | Watertank | 25m pBTS | 25 | Add R8852E S9000 x3+R8854E S1800 x3+R9224E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
2681C | Jalan PJS 6_G | Central |  | Modernization |  | 2024 Q1_496 | XH | Ascentrack | 4.6 TSSR Approved | AAU Cannot Install-S23 MM change to normal sector¦Loading issue,site owner rejected AAU and bisecotr solution.Need to chage to normal sector.There is no space in the fence,Site owner rejected to add new RRU cage outside the fence | 2023-09-01 | 2023-09-04 |  | 2023-10-18 |  | Closed | 2023-10-18 | 2023-11-30 | E//Sumitra | 2023-11-29 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230904 | DU00002559407 | NIC_S2_Change MM to BI_loading issue_SBC KJS |  | 2023-12-22 | 2023-12-22 |  | Lampole | landside | 25m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 23
1637C | NXP (REL) | Central |  | Remote MOCN |  | 2024 Q1_496 | MA | Ascentrack | 14.3 Drop (Done Survey + TSSR) |  | 2023-08-30 | 2023-09-01 |  | 2023-09-05 |  | Closed | 2023-09-07 | 2023-09-08 | E//Sumitra |  | CelcomDigi_RAN_Ascentrack_TSS_Central_20230901 | DU00002559408 | [5 empty] | BillBoard | landside |  |  | 2
4399D | Sekolah Rendah Kebangsaan Hashim Awang | Northern |  | Modernization |  | 2024 Q1_496 | SM | GCI | 4.6 TSSR Approved |  | 2023-08-19 | 2023-08-28 |  | 2023-09-02 |  | Rectificating | 2023-09-05 | 2023-10-02 | E//Hazida | 2023-09-13 | Celcom Digi_RAN-GCI-TSS-Northern-20230819-0038 | DU00002559409 |  |  | 2023-10-26 | 2023-10-21 |  | Minaret | landside | 32 | Add R9264M M1821 x5,Dismantle R8894E M1821(A8A) x3 |  | 12
4597D | Kg Tok Hamid | Northern |  | Modernization |  | 2024 Q1_496 | BY | YPTT | 4.6 TSSR Approved |  | 2023-08-21 | 2023-08-28 |  | 2023-08-30 |  | Closed | 2023-08-30 | 2023-10-02 | E//Hazida | 2023-09-12 | Celcom Digi_RAN-YPTT-TSS-Northern-20230822-0027 | DU00002559410 |  |  | 2023-09-22 | 2023-09-22 |  | Monopole | landside | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
4595D | Taman Halaman Indah | Northern |  | Modernization |  | 2024 Q1_496 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-09-04 | 2023-09-12 |  | 2023-09-17 |  | Closed | 2023-09-18 | 2023-10-17 | E//Hazida | 2023-10-15 | Celcom Digi_RAN-GTSB-TSS-Northern-20230905-0033 | DU00002559411 |  |  | 2023-10-30 | 2023-10-30 |  | Monople Tree | landside | 30 | Add R8852E S9000 x3+R8854E S1800 x3+R9224E M1821 x3,Dismantle R8894E M1821(A8A) x3
4558D | Taman Binjai Pg | Northern |  | Modernization |  | 2024 Q1_496 | SM | GTSB | 4.6 TSSR Approved |  | 2023-08-25 | 2023-08-28 |  | 2023-09-01 |  | Closed | 2023-09-04 | 2023-09-20 | E//Hazida | 2023-09-19 | Celcom Digi_RAN-GTSB-TSS-Northern-20230825-0030 | DU00002559412 |  |  | 2023-10-28 | 2023-10-28 |  | In-Building System | landside | 9 | Add R8852E S9000 x3+R8854E S1800 x3+R9224E M1821 x3,Dismantle R8894E M1821(A8A) x3
2601B | Jalan Jurunilai | Central |  | Modernization |  | 2024 Q1_496 | XH | Magicell | 4.6 TSSR Approved |  | 2023-08-24 | 2023-09-01 |  | 2023-09-05 |  | Closed | 2023-09-06 | 2023-09-12 | E//Razif | 2023-09-12 | CelcomDigi_RAN_Magicell_TSS_Central_20230825 | DU00002559413 |  |  | 2023-09-27 | 2023-09-27 |  | Lampole | landside | 18 | Add R8852E S9000 x3+R8854E S1800 x3
4266H | 99 Speedmart PG Pusat Perniagaan Serdang | Northern |  | MOCN As-Is |  | 2024 Q1_496 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559414 | [6 empty] | Small Cell
4269H | 99 Speedmart PG Kws Perniagaan Tmn Merak | Northern |  | MOCN As-Is |  | 2024 Q1_496 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559415 | [6 empty] | Small Cell
4271H | 99 Speedmart PG Tmn Gelugor Indah | Northern |  | MOCN As-Is |  | 2024 Q1_496 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559416 | [6 empty] | Small Cell
4102H | TSK FATT TRADING | Northern |  | MOCN As-Is |  | 2024 Q1_496 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559417 | [6 empty] | Small Cell
4138H | UWV Industrial Batu Kawan | Northern |  | MOCN As-Is |  | 2024 Q1_496 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559418 | [6 empty] | Small Cell
1372H | 99 Speedmart USJ Avenue | Central |  | MOCN As-Is |  | 2024 Q1_496 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559419 | [6 empty] | Small Cell
1199H | 99 Speedmart SUBANG JAYA SS 19 | Central |  | MOCN As-Is |  | 2024 Q1_496 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559420 | [6 empty] | Small Cell
1210H | 99 Speedmart SUBANG JAYA SS 15 (1) | Central |  | MOCN As-Is |  | 2024 Q1_496 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559421 | [6 empty] | Small Cell
1214H | 99 Speedmart DESA MENTARI 2 | Central |  | MOCN As-Is |  | 2024 Q1_496 |  | GTSB | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559422 | [6 empty] | iMacro
1280H | 99 Speedmart SUNWAY PJS 9 | Central |  | MOCN As-Is |  | 2024 Q1_496 |  | GTSB | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559423 | [6 empty] | Small Cell
1282H | 99 Speedmart DATARAN MENTARI | Central |  | MOCN As-Is |  | 2024 Q1_496 |  | GTSB | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559424 | [6 empty] | Small Cell
1314H | 99 Speedmart TTDI JAYA | Central |  | MOCN As-Is |  | 2024 Q1_496 |  | GTSB | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559425 | [6 empty] | Small Cell
1389H | 99 Speedmart SHAH ALAM SEK 27 | Central |  | MOCN As-Is |  | 2024 Q1_496 |  | YPTT | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559426 | [6 empty] | Small Cell
1398H | 99 Speedmart TMN SUBANG INDAH | Central |  | MOCN As-Is |  | 2024 Q1_496 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559427 | [6 empty] | iMacro
1354H | LRT SS18 | Central |  | MOCN As-Is |  | 2024 Q1_496 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559428 | [6 empty] | Small Cell
1586H | 99 Speedmart SHAH ALAM SEK 26 (1) | Central |  | MOCN As-Is |  | 2024 Q1_496 |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559429 | [6 empty] | Small Cell
1356H | LRT Alam Megah | Central |  | MOCN As-Is |  | 2024 Q1_496 |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559430 | [6 empty] | landside
1602H | 99 Speedmart USJ 1 (2) | Central |  | MOCN As-Is |  | 2024 Q1_496 |  | YPTT | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559431 | [6 empty] | Small Cell
4265H | 99 Speedmart PG Tmn Camar Jaya | Northern |  | MOCN As-Is |  | 2024 Q1_496 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559432 | [6 empty] | Small Cell
4268H | 99 Speedmart PG Tmn Merak | Northern |  | MOCN As-Is |  | 2024 Q1_496 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559433 | [6 empty] | iMacro
4270H | 99 Speedmart PG Tmn Seri Berapit | Northern |  | MOCN As-Is |  | 2024 Q1_496 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559434 | [6 empty] | iMacro
4272H | 99 Speedmart PG Pp Valdor Jaya | Northern |  | MOCN As-Is |  | 2024 Q1_496 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559435 | [6 empty] | Small Cell
4273H | 99 Speedmart Pg Tmn Bayu Aman | Northern |  | MOCN As-Is |  | 2024 Q1_496 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559436 | [6 empty] | iMacro
4283H | 99 Speedmart PG Tmn Bunga | Northern |  | MOCN As-Is |  | 2024 Q1_496 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559437 | [6 empty] | Small Cell
4288H | 99 Speedmart PG Tmn Sri | Northern |  | MOCN As-Is |  | 2024 Q1_496 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559438 | [6 empty] | Small Cell
1746H | 99 Speedmart Sunway Metro | Central |  | MOCN As-Is |  | 2024 Q1_496 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559439 | [6 empty] | Small Cell
4326H | 99 Speedmart PG Tmn Halaman Indah | Northern |  | MOCN As-Is |  | 2024 Q1_496 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559440 | [6 empty] | iMacro
4323H | 99 Speedmart PG Bdr Tasek Mutiara | Northern |  | MOCN As-Is |  | 2024 Q1_496 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559441 | [6 empty] | iMacro
4287H | 99 Speedmart PG Tmn Seri Indah | Northern |  | MOCN As-Is |  | 2024 Q1_496 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559442 | [6 empty] | Small Cell
4285H | 99 Speedmart PG Bdr Perda | Northern |  | MOCN As-Is |  | 2024 Q1_496 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559443 | [6 empty] | Small Cell
4284H | 99 Speedmart PG Pp Seri Tambun | Northern |  | MOCN As-Is |  | 2024 Q1_496 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559444 | [6 empty] | Small Cell
1563H | Jalan USJ 3A_2 | Central |  | MOCN As-Is |  | 2024 Q1_496 |  | YPTT | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559445 | [6 empty] | iMacro
1805H | USJ Sri Bayu Condominium | Central |  | MOCN As-Is |  | 2024 Q1_496 |  | YPTT | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559446 | [6 empty] | iMacro
4343H | Passion Paradise Hostel | Northern |  | MOCN As-Is |  | 2024 Q1_496 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559447 | [6 empty] | Small Cell
1882H | IWK Shah Alam | Central |  | MOCN As-Is |  | 2024 Q1_496 |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559448 | [6 empty] | iMacro
4348H | 99 Speedmart PG Tmn Seruling Emas | Northern |  | MOCN As-Is |  | 2024 Q1_496 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559449 | [6 empty] | iMacro
4355H | 99 Speedmart PG Tmn Desa Ara Permai | Northern |  | MOCN As-Is |  | 2024 Q1_496 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559450 | [6 empty] | iMacro
4353H | 99 SM PG TMN PERKASA | Northern |  | MOCN As-Is |  | 2024 Q1_496 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559451 | [6 empty] | iMacro
3015M | Jalan SS 15_4c | Central |  | MOCN As-Is |  | 2024 Q1_496 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559452 | [6 empty] | Micro Cell
3018M | Sunway Mentari | Central |  | MOCN As-Is |  | 2024 Q1_496 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559453 | [6 empty] | Micro Cell
3035M | DS Sunway Pyramid Micro | Central |  | MOCN As-Is |  | 2024 Q1_496 |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559454 | [6 empty] | Micro Cell
1002Q | Courtyard SS15 (Q-Cell) | Central |  | MOCN As-Is |  | 2024 Q1_496 |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559826 | [6 empty] | Qcell
1006Q | ZTE Office Lot 8 | Central |  | MOCN As-Is |  | 2024 Q1_496 |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559827 | [6 empty] | landside
B00019 | B061H_B00019OD_SS19SBJ | Central | 1236K | Swap |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-10-07 | 2023-10-13 |  | 2023-10-17 |  | Closed | 2023-10-18 | 2024-03-13 | CD//Norhaliza | 2024-03-12 | CelcomDigi_RAN_Datasco_TI_Central_20231007 | DU00002559828 |  |  | 2023-10-24 | 2023-10-20 |  | Wall mount boom | LAMP_POLE | 4 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle
B00034 | B061I_B00034OD_USJ17 | Central | 1237K | Swap |  | 2024 Q1_496 | IE | Datasco | 4.6 TSSR Approved |  | 2023-09-04 | 2023-09-08 |  | 2023-09-12 |  | Closed | 2023-09-12 | 2023-09-20 | CD//Norhaliza | 2023-09-19 | CelcomDigi_RAN_Datasco_TSS_Central_20230905 | DU00002559829 |  |  | 2023-10-18 | 2023-10-17 |  | Monopole | MINI STRUCTURE | 10m | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle
B00321 | B061B_B00321OD_PR_SEKU2SHLM | Central | 1241K | Swap |  | 2024 Q1_496 | IE | Datasco | 4.6 TSSR Approved |  | 2023-09-05 | 2023-09-12 |  | 2023-09-13 |  | Closed | 2024-03-26 | 2024-03-27 | CD//Ali Akaram | 2024-03-27 | CelcomDigi_RAN_Datasco_TSS_Central_20230907 | DU00002559830 |  |  | 2024-02-22 | 2024-02-20 |  |  | MONOPOLE | 7 | Add R9264M M1821 x1+R9264H M901821 x3 |  | 3
B00391 | B061I_B00391OD_SUBANGPERMAI | Central | 1246K | Swap |  | 2024 Q1_496 | CR | Datasco | 4.6 TSSR Approved |  | 2023-09-04 | 2023-09-27 |  | 2023-10-04 |  | Closed | 2023-10-06 | 2023-11-22 | CD//Norhaliza | 2023-11-21 | CelcomDigi_RAN_Datasco_TSS_Central_20230905 | DU00002559831 |  |  | 2023-12-15 | 2023-12-11 |  | Pole | BOOM | S1 & S2 (10m) & S3 (7m) | Add R8852E S9000 x1+R9264H M901821 x2+R8862A S2601 x3+A9732 M1821 x1,Dismantle | 1 | 0
B00413 | B061B_B00413OD_SEKU1SA2 | Central | 1247K | Swap |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-09-19 | 2023-09-22 |  | 2023-09-25 |  | Closed | 2023-09-26 | 2023-10-03 | CD//Sapian | 2023-10-03 | CelcomDigi_RAN_Datasco_TSS_Central_20230920 | DU00002559832 |  |  | 2024-02-24 | 2024-02-20 |  | In-Building System | MINI STRUCTURE | 7 | Add R9264M M1821 x1+R9264H M901821 x3+R8862A S2601 x4,Dismantle |  | 3
B00454 | B061H_B00454OD_PJS9SNWY | Central | 1249K | Swap |  | 2024 Q1_496 | CR | Datasco | 4.6 TSSR Approved |  | 2023-09-06 | 2023-09-26 |  | 2023-09-27 |  | Closed | 2023-10-03 | 2024-02-16 | CD//Ali akaram | 2024-02-15 | CelcomDigi_RAN_Datasco_TSS_Central_20230907 | DU00002559833 |  |  | 2023-12-19 | 2023-12-11 |  | Unipole | TRIPOD | 10 | Add R9264M M1821 x2+R9264H M901821 x3+R8862A S2601 x5,Dismantle |  | 12
B00508 | B061B_B00508OD_BT3SHLM | Central | 1251K | Swap |  | 2024 Q1_496 | SS | Datasco | 4.6 TSSR Approved |  | 2023-09-05 | 2023-09-18 |  | 2023-09-20 |  | Closed | 2023-10-02 | 2023-10-06 | CD//Sapian | 2023-09-25 | CelcomDigi_RAN_Datasco_TSS_Central_20230907 | DU00002559834 |  |  | 2024-02-22 | 2024-02-20 |  | In-Building System | BOOM | 6 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle
B00577 | B061I_B00577OD_SBGHITECH | Central | 1254K | Swap |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-09-25 | 2023-09-25 |  | 2023-09-27 |  | Closed | 2023-10-03 | 2023-10-11 | CD//Sapian | 2023-10-10 | Celcom Digi_RAN-Datasco-TSS-Central-20230925 | DU00002559835 |  |  | 2023-12-29 | 2023-11-27 |  | Tower | TOWER | 70 | Add R9264M M1821 x1+R9264H M901821 x3+R8862A S2601 x4,Dismantle |  | 2
B00578 | B061D_B00578OD_SEK23SA | Central | 1255K | Swap |  | 2024 Q1_496 | IE | Datasco | 4.6 TSSR Approved |  |  | 2023-09-25 |  |  |  |  | 2023-09-29 | 2023-10-06 | CD//Sapian | 2023-10-05 | CelcomDigi_RAN_Datasco_TSS_Central_20230907 | DU00002559836 |  |  | 2024-01-17 | 2023-11-27 |  | In-Building System | TRIPOD | 9m | Add R8852E S9000 x2+R9264H M901821 x1+R8862A S2601 x3+A9732 M1821 x2,Dismantle | 23
B00660 | B061H_B00660OD_SS15SBJ | Central | 1259K | Swap |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-09-08 | 2023-09-12 |  | 2023-09-19 |  | Closed | 2023-09-20 | 2023-10-17 | CD//Ali Akaram | 2023-10-12 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230911 | DU00002559837 |  |  | 2024-02-04 | 2024-02-01 |  | In-Building System | BOOM | 7.5 | Add R8852E S9000 x1+R9264H M901821 x2+R8862A S2601 x3+A9732 M1821 x1,Dismantle | 1 | 0
B00738 | B061H_B00738OD_PR_JLNKEMAJUAN | Central | 1260K | Swap |  | 2024 Q1_496 | CR | Ascentrack | 4.6 TSSR Approved |  | 2023-09-09 | 2023-09-14 |  | 2023-09-17 |  | Closed | 2023-09-19 | 2023-10-18 | CD//Sapian | 2023-09-23 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230911 | DU00002559838 |  |  | 2023-12-28 | 2023-12-27 |  | In-Building System | TRIPOD | 15 | Add R9264H M901821 x3+R8854 S2600 x3,Dismantle
B00751 | B061E_B00751OD_SEK26SHLM | Central | 1261K | Swap |  | 2024 Q1_496 | IE | Datasco | 4.6 TSSR Approved |  | 2023-09-04 | 2023-09-16 |  | 2023-09-19 |  | Closed | 2023-09-22 | 2023-10-01 | CD//Sapian | 2023-09-26 | CelcomDigi_RAN_Datasco_TSS_Central_20230905 | DU00002559839 |  |  | 2023-12-14 | 2023-12-11 |  | Pole | TRIPOD | 14 | Add R8852E S9000 x3+R8854E S1800 x3+R9224E M1821 x3,Dismantle
B00839 | B061P_B00839SL_SS9SGWAYSL | Central | 1262K | Swap |  | 2024 Q1_496 | CR | Datasco | 4.6 TSSR Approved |  | 2023-09-24 | 2023-09-26 |  | 2023-09-29 |  | Closed | 2023-10-02 | 2023-10-06 | CD//Sapian | 2023-10-06 | CelcomDigi_RAN_Datasco_TSS_Central_20230907 | DU00002559840 |  |  | 2023-12-20 | 2023-12-11 |  | BillBoard | BOOM | Billboard Height : 17m & Antenna Pole Height : 6m | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle
B01031 | B061I_B01031OD_TMUSJTAIPAN | Central | 1263K | Swap |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-10-25 | 2023-10-30 |  | 2023-11-01 |  | Closed | 2023-11-07 | 2024-05-30 | CD//Norhaliza | 2024-05-30 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231028 | DU00002559841 |  |  | 2024-03-08 | 2024-02-13 |  | In-Building System | SHARING STRC TELEKOM | 4.10 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle
B01560 | B061D_B01560OD_SEK22SHLM | Central | 1273K | Swap |  | 2024 Q1_496 | SS | Ascentrack | 4.6 TSSR Approved |  | 2023-09-15 | 2023-09-18 |  | 2023-09-20 |  | Closed | 2023-09-21 | 2024-02-19 | CD//Norhaliza | 2024-02-16 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230918 | DU00002559842 |  |  | 2023-12-29 | 2023-11-15 |  |  | RAPOLE | 18 | Add R9264M M1821 x2+R9264H M901821 x3+R8862A S2601 x5,Dismantle |  | 12
B01593 | B061H_B01593OD_MENTARICOURTPJ | Central | 1274K | Swap |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-09-03 | 2023-09-16 |  | 2023-09-20 |  | Closed | 2023-09-25 | 2023-10-03 | CD//Sapian | 2023-10-03 | Celcom Digi_RAN-Datasco-TSS-Central-20230919 | DU00002559843 |  |  | 2023-12-23 | 2023-12-11 |  | Pole | UNIPOLE | 4m & 6m | Add R8852E S9000 x3+R8862A S2601 x3+A9732 M1821 x3,Dismantle | 123
B01679 | B061H_B01679OD_MENTARICOURT2 | Central | 1276K | Swap |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-08-29 | 2023-09-04 |  | 2023-09-08 |  | Closed | 2023-09-12 | 2023-10-17 | CD//Ali Akaram | 2023-10-12 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230901 | DU00002559844 |  |  | 2023-11-28 | 2023-11-28 |  | Minimast | TRIPOD | 6.2m | Add R8852E S9000 x1+R9264H M901821 x2+R8862A S2601 x3+A9732 M1821 x1,Dismantle | 2 | 0
B01721 | B061I_B01721OD_PT235 | Central | 1277K | Swap |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦Space issue AAU can not install | 2023-10-05 | 2023-10-12 |  | 2023-10-16 |  | Closed | 2023-10-23 | 2024-03-15 | CD//Norhaliza | 2024-03-14 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231005 | DU00002559845 | NIC_S1_Change MM to BI_Space constraint_STEALTH |  | 2023-11-07 | 2023-10-24 |  | Monopole | LAMP_POLE | 31 | Add R9264M M1821 x1+R9264H M901821 x3+R8862A S2601 x4,Dismantle | 0 | 2
B01963 | B061H_B01963OD_KM26FEDHWY | Central | 1282K | Swap |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-08-29 | 2023-09-04 |  | 2023-09-08 |  | Closed | 2023-09-08 | 2023-10-18 | CD//Sapian | 2023-10-16 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230901 | DU00002559846 |  |  | 2023-12-27 | 2023-11-15 |  | BillBoard | BILLBOARD | 32m | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle
B02067 | B061B_B02067OD_HICOMINDPARK | Central | 1285K | Swap |  | 2024 Q1_496 | SS | Ascentrack | 4.6 TSSR Approved |  | 2023-10-12 | 2023-10-16 |  | 2023-10-23 |  | Closed | 2023-10-24 | 2023-11-15 | CD//Ali akaram | 2023-11-08 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231013 | DU00002559847 |  |  | 2024-02-22 | 2024-02-20 |  | In-Building System | BOOM | 7 | Add R8852E S9000 x3+R8894E M1821 x3+R8862A S2601 x3,Dismantle
B02169 | B061E_B02169OD_JLNSERENDAH26SEK26SHLM | Central | 1287K | Swap |  | 2024 Q1_496 | AI | GTSB | 4.6 TSSR Approved |  | 2023-09-13 | 2023-09-08 |  | 2023-09-14 |  | Closed | 2023-11-30 | 2024-02-16 | CD//Norhaliza | 2024-02-16 | CelcomDigi_RAN_GTSB_TSS_Central_20230914 | DU00002559848 |  |  | 2023-12-21 | 2023-12-11 |  | Monopole | RAPOLE | 8 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle
B02261 | B061B_B02261OD_JLNPELUKIS GLENMARIE | Central | 1290K | Swap |  | 2024 Q1_496 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-09-04 | 2023-09-06 |  | 2023-09-10 |  | Closed | 2023-09-15 | 2023-10-18 | CD//Sapian | 2023-09-23 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230905 | DU00002559849 |  |  | 2024-02-22 | 2024-02-20 |  | In-Building System | BOOM | 4.2 | Add R8852E S9000 x3+R8894E M1821 x3+R8862A S2601 x3,Dismantle
B02294 | B061H_B02294OD_KM18_FEDERAL_HWY | Central | 1291K | Swap |  | 2024 Q1_496 | AI | GTSB | 4.6 TSSR Approved |  | 2023-09-06 | 2023-09-12 |  | 2023-09-15 |  | Closed | 2023-12-01 | 2024-03-15 | CD//Norhaliza | 2024-03-14 | CelcomDigi_RAN_GTSB_TSS_Central_20230907 | DU00002559850 |  |  | 2023-12-21 | 2023-12-09 |  | BillBoard | BILLBOARD | 31 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle
B02412 | B061B_B02412OD_SEKU2TTDIJAYAJLNOPERA | Central | 1295K | Swap |  | 2024 Q1_496 | AI | GTSB | 4.6 TSSR Approved |  | 2023-09-12 | 2023-09-16 |  | 2023-09-21 |  | Closed | 2023-09-22 | 2024-02-19 | CD//Norhaliza | 2024-02-16 | CelcomDigi_RAN_GTSB_TSS_Central_20230913 | DU00002559851 |  |  | 2024-02-22 | 2024-02-19 |  |  | UNIPOLE | 7m | Add R9264M M1821 x1+R9264H M901821 x3,Dismantle |  | 1
B02531 | B061I_B02531OD_KM8ELITEHW | Central | 1302K | Swap |  | 2024 Q1_496 | SS | YPTT | 4.6 TSSR Approved |  | 2023-10-04 | 2023-10-17 |  | 2023-10-22 |  | Closed | 2023-11-23 | 2024-03-14 | CD//Norhaliza | 2024-03-12 | CelcomDigi_RAN_YPTT_TSS_Central_20231005 | DU00002559852 |  |  | 2024-03-21 | 2024-03-21 |  | BillBoard | LAMP_POLE | 37 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle
B02690 | B061I_B02690OD_KGKENANGAN | Central | 1307K | Swap |  | 2024 Q1_496 | AI | GTSB | 4.6 TSSR Approved |  | 2023-08-30 | 2023-09-04 |  | 2023-09-08 |  | Closed | 2023-09-20 | 2023-09-21 | CD//Sapian | 2023-09-16 | CelcomDigi_RAN_GTSB_TSS_Central_20230901 | DU00002559853 |  |  | 2023-10-19 | 2023-10-12 |  | Monopole | LAMP_POLE | 24 | Add R8852E S9000 x3+R8854E S1800 x3+R9224E M1821 x3,Dismantle
B02725 | BB1_SEK33SHLM2 | Central | 1311K | Swap |  | 2024 Q1_496 | IE | Magicell | 4.6 TSSR Approved |  | 2023-09-16 | 2023-09-20 |  | 2023-09-22 |  | Closed | 2023-09-25 | 2023-10-18 | CD//Sapian | 2023-10-17 | CelcomDigi_RAN_Magicell_TSS_Central_20230918 | DU00002559854 |  |  | 2023-10-18 | 2023-10-12 |  | Lampole | LAMP_POLE | 25M | Add R8852E S9000 x3+R8854E S1800 x3+R9224E M1821 x3,Dismantle
B02960 | B061B_B02960OD_MESINNIAGAPOTS | Central | 1318K | Swap |  | 2024 Q1_496 | SS | YPTT | 4.6 TSSR Approved |  | 2023-10-08 | 2023-10-12 |  | 2023-10-16 |  | Closed | 2023-10-17 | 2024-03-06 | CD//Ali akaram | 2024-03-04 | CelcomDigi_RAN_YPTT_TSS_Central_20231011 | DU00002559855 |  |  | 2024-02-22 | 2024-02-17 |  | Watertank | Lampole | 30 | Add R8852E S9000 x3+R8894E M1821 x3,Dismantle
P00006 | P034C_P00006OD_POKOKMACHANG | Northern | 4361K | Remote MOCN |  | 2024 Q1_496 | HQ 1 | GTSB | 14.2 Drop (Done Survey) |  | 2023-12-07 | 2023-08-30 |  |  |  | To be Submitted |  |  | CD//Zulakmar |  | N/A - site move to BAU | DU00002559856 | [5 empty] | Monopole | TOWER | 40 |  | 12
P00007 | P032A_P00007OD_BTBATUKAWAN | Northern | 4362K | Remote MOCN |  | 2024 Q1_496 | ZA | GTSB | 14.2 Drop (Done Survey) |  | 2023-12-07 | 2023-08-25 |  |  |  | To be Submitted |  |  | CD//Zulakmar |  | N/A - site move to BAU | DU00002559857 | [5 empty] | Tower | TOWER | 60M |  | 12
P00029 | P034C_P00029OD_SGDUA | Northern | 4363K | Swap |  | 2024 Q1_496 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-08-24 | 2023-08-30 |  | 2023-09-05 |  | Closed | 2023-09-07 | 2023-09-08 | CD//Rohizam | 2023-09-08 | Celcom Digi_RAN-GTSB-TSS-Northern-20230825-0030 | DU00002559858 |  |  | 2024-01-02 | 2023-12-29 |  | Tower | TOWER | 47 | Add R9264M M1821 x3+R9264H M901821 x3+R8854 S2600 x3,Dismantle |  | 123
P00043 | P033A_P00043OD_BMHILL1 | Northern | 4364K | Swap |  | 2024 Q1_496 | HQ 1 | Ascentrack | 4.6 TSSR Approved |  | 2023-08-26 | 2023-10-09 |  | 2023-10-14 |  | Closed | 2023-10-17 | 2023-10-19 | CD//Affendi | 2023-10-18 | Celcom Digi_RAN-Ascentrack-TSS-Northern-20230828-0004 | DU00002559859 |  |  | 2023-11-07 | 2023-11-01 |  | Tower | TOWER | 46m | Add R8852E S9000 x1+R9264H M901821 x2+R8862A S2601 x3+A9732 M1821 x1,Dismantle | 2 | 0
P00047 | P033B_P00047OD_JALANKEBUNSIREH | Northern | 4365K | Swap |  | 2024 Q1_496 | WP | Ascentrack | 4.6 TSSR Approved |  | 2023-08-28 | 2023-09-15 |  | 2023-09-22 |  | Closed | 2023-09-22 | 2023-10-02 | CD//Rohizam | 2023-09-26 | Celcom Digi_RAN-Ascentrack-TSS-Northern-20230829-0005 | DU00002559860 |  |  | 2023-11-02 | 2023-09-27 |  | Pole | BOOM | 3m | Add R8852E S9000 x3+R8862A S2601 x3+A9732 M1821 x3,Dismantle | 123
P00058 | P033C_P00058OD_KOTAPERMAI | Northern | 4366K | Swap |  | 2024 Q1_496 | ZA | Ascentrack | 4.6 TSSR Approved |  | 2023-08-25 | 2023-09-01 |  | 2023-09-06 |  | Closed | 2023-09-07 | 2023-09-08 | CD//Rohizam | 2023-09-08 | Celcom Digi_RAN-Ascentrack-TSS-Northern-20230825-0003 | DU00002559861 |  |  | 2023-11-01 | 2023-11-01 |  | Pole | BOOM | 4m | Add R9264M M1821 x1+R9264H M901821 x3+R8862A S2601 x4,Dismantle |  | 3
P00063 | P033A_P00063OD_BMHILL2 | Northern | 4367K | Swap |  | 2024 Q1_496 |  | GCI | 4.6 TSSR Approved |  | 2023-12-06 | 2023-12-14 |  | 2023-12-19 |  | Closed | 2023-12-19 | 2023-12-21 | CD//Affendi | 2023-12-20 | Celcom Digi_RAN-GCI-TSS-Northern-20231206-0080 | DU00002559862 |  |  | 2024-01-17 | 2024-01-10 |  | Tower | TOWER | 75 | Add R8852E S9000 x2+R9264H M901821 x1+R8862A S2601 x3+A9732 M1821 x2,Dismantle | 23
P00088 | P034A_P00088OD_ROBINAPARK | Northern | 4368K | Swap |  | 2024 Q1_496 | SM | GTSB | 4.6 TSSR Approved |  | 2023-08-26 | 2023-08-29 |  | 2023-09-01 |  | Rectificating | 2023-09-06 | 2023-10-02 | CD//Rohizam | 2023-09-26 | Celcom Digi_RAN-GTSB-TSS-Northern-20230828-0031 | DU00002559863 |  |  | 2023-09-22 | 2023-09-21 |  | Rooftop | MINI STRUCTURE | 20 | Add R8852E S9000 x2+R9264H M901821 x1+R8862A S2601 x3+A9732 M1821 x2,Dismantle | 12 | 0
P00106 | P034A_P00106OD_SGPUYU2 | Northern | 4369K | Swap |  | 2024 Q1_496 | HQ 1 | Ascentrack | 4.6 TSSR Approved |  | 2023-08-24 | 2023-09-06 |  | 2023-09-11 |  | Closed | 2023-09-12 | 2023-09-15 | CD//Rohizam | 2023-09-14 | Celcom Digi_RAN-Ascentrack-TSS-Northern-20230825-0003 | DU00002559864 |  |  | 2023-09-29 | 2023-09-25 |  | A-bracket pole | TRIPOD | 5m | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle
P00118 | P032A_P00118OD_TMSIMPANG4 | Northern | 4370K | Remote MOCN |  | 2024 Q1_496 |  | CCSMY | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002559865 | [6 empty] | BOOM |  |  | 123
P00145 | P033A_P00145OD_TANAHLIAT | Northern | 4371K | Swap |  | 2024 Q1_496 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-08-24 | 2023-08-29 |  | 2023-09-04 |  | Closed | 2023-09-05 | 2023-09-07 | CD//Rohizam | 2023-09-06 | Celcom Digi_RAN-GTSB-TSS-Northern-20230825-0030 | DU00002559866 |  |  | 2023-09-28 | 2023-09-26 |  | In-Building System | BOOM | 9M | Add R8852E S9000 x1+R9264H M901821 x2+R8862A S2601 x3+A9732 M1821 x1,Dismantle | 1 | 0
P00152 | P033A_P00152OD_BMTOWN | Northern | 4372K | Swap |  | 2024 Q1_496 | BY | GCI | 4.6 TSSR Approved | //0227 - Subcon survey wrong info sector 3. Add new Antenna & New RRU Power Cable | 2023-09-12 | 2023-09-22 |  | 2023-09-25 |  | Closed | 2023-09-29 | 2023-11-16 | CD//Affendi | 2023-11-16 | Celcom Digi_RAN-GCI-TSS-Northern-20230919-0051 | DU00002559867 |  |  | 2024-02-29 | 2023-11-16 |  | In-Building System | BOOM | 5 | Add R8852E S9000 x3+R8894E M1821 x3+R8862A S2601 x3,Dismantle
P00153 | P033A_P00153OD_KUBANGSEMANG | Northern | 4373K | Swap |  | 2024 Q1_496 | HQ 1 | Ascentrack | 4.6 TSSR Approved |  | 2023-08-24 | 2023-09-08 |  | 2023-09-13 |  | Closed | 2023-09-14 | 2023-10-11 | CD//Rohizam | 2023-10-10 | Celcom Digi_RAN-Ascentrack-TSS-Northern-20230825-0003 | DU00002559868 |  |  | 2023-09-28 | 2023-09-28 |  | Tower | TOWER | 46m | Add R8852E S9000 x1+R9264H M901821 x2+R8862A S2601 x3+A9732 M1821 x1,Dismantle | 1(S1 -> S2,S2->S3,S3->S1,,need rename sector ID,FDD MM@NEW S1)
P00167 | P033B_P00167OD_POLITEKNIKPRAI | Northern | 4374K | Swap |  | 2024 Q1_496 | HQ 1 | GTSB | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦pBTS site,can not install AAU on site | 2023-08-25 | 2023-08-28 |  | 2023-09-14 |  | Closed | 2023-09-15 | 2023-10-27 | CD//Rohizam | 2023-10-27 | Celcom Digi_RAN-GTSB-TSS-Northern-20230825-0030 | DU00002559869 | NIC_S3_Change MM to BI_loading issue_EDOTCO (M) - NONE CSU |  | 2024-02-20 | 2024-02-09 |  | Tower | MINI STRUCTURE |  | Add R9264M M1821 x3+R9264H M901821 x3+R8862A S2601 x6,Dismantle | 1 | 0
P00333 | P033A_P00333OD_PENANTI | Northern | 4375K | Swap |  | 2024 Q1_496 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-09-09 | 2023-09-16 |  | 2023-09-21 |  | Closed | 2023-09-22 | 2023-10-11 | CD//Rohizam | 2023-10-10 | Celcom Digi_RAN-YPTT-TSS-Northern-20230911-0035 | DU00002559870 |  |  | 2023-10-13 | 2023-09-27 |  | Monopole | LAMP_POLE | 45 | Add R8852E S9000 x3+R8862A S2601 x3+A9732 M1821 x3,Dismantle | 123 | 0
P00334 | P033A_P00334OD_KUBANGULU | Northern | 4376K | Swap |  | 2024 Q1_496 | SM | GCI | 4.6 TSSR Approved |  | 2023-09-10 | 2023-09-19 |  | 2023-09-22 |  | Rectificating | 2023-09-25 | 2023-10-03 | CD//Affendi | 2023-10-03 | Celcom Digi_RAN-GCI-TSS-Northern-20230911-0047 | DU00002559871 |  |  | 2024-01-03 | 2023-12-22 |  | Tower | TOWER | 60 | Add R8852E S9000 x3+R8862A S2601 x3+A9732 M1821 x3,Dismantle | 123
P00462 | P034B_P00462OD_TMNSERISERDANG | Northern | 4377K | Swap |  | 2024 Q1_496 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-08-21 | 2023-08-23 |  | 2023-08-26 |  | Closed | 2023-08-29 | 2023-08-30 | CD//Rohizam | 2023-08-30 | Celcom Digi_RAN-GTSB-TSS-Northern-20230821-0027 | DU00002559872 |  |  | 2024-01-18 | 2024-01-13 |  | Rooftop | BOOM | 14 | Add R9264M M1821 x1+R9264H M901821 x3+R8854 S2600 x3,Dismantle |  | 1
P00469 | P033B_P00469OD_PSP1 | Northern | 4378K | Remote MOCN |  | 2024 Q1_496 | ZA | GTSB | 14.2 Drop (Done Survey) |  | 2023-12-07 | 2023-08-25 |  |  |  | To be Submitted |  |  | CD//Zulakmar |  | N/A - site move to BAU | DU00002559873 | [5 empty] | In-Building System | LAMP_POLE | 3 |  | 123
P00494 | P034B_P00494OD_PGRBERTAM | Northern | 4379K | Remote MOCN |  | 2024 Q1_496 | SM | GTSB | 14.2 Drop (Done Survey) |  | 2023-12-07 | 2023-08-25 |  |  |  | To be Submitted |  |  |  |  | N/A - site move to BAU | DU00002559874 | [5 empty] | Lampole | LAMP_POLE | 24
P00509 | P034C_P00509OD_PMTGSGDUA | Northern | 4380K | Remote MOCN |  | 2024 Q1_496 | HQ 1 | GCI | 14.1 Drop (No Survey) |  |  | 2023-09-04 |  |  |  | To be Submitted |  |  | CD//Zulakmar |  | N/A - site move to BAU | DU00002559875 | [5 empty] | Pole | LAMP_POLE | 15
P00510 | P034B_P00510OD_PGRBERTAM2 | Northern | 4381K | Swap |  | 2024 Q1_496 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-09-02 | 2023-09-07 |  | 2023-09-09 |  | Closed | 2023-09-11 | 2023-09-12 | CD//Rohizam | 2023-09-12 | Celcom Digi_RAN-GCI-TSS-Northern-20230904-0044 | DU00002559876 |  |  | 2024-01-23 | 2024-01-10 |  | Lampole | LAMP_POLE | 30 | Add R8852E S9000 x3+R8854E S1800 x3+R9224E M1821 x3,Dismantle
P00678 | P034A_P00678OD_TMNBAYUAMAN | Northern | 4382K | Swap |  | 2024 Q1_496 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-08-24 | 2023-08-28 |  | 2023-09-01 |  | Closed | 2023-09-05 | 2023-09-14 | CD//Rohizam | 2023-09-08 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230825-0036 | DU00002559877 |  |  | 2023-09-22 | 2023-09-20 |  |  | UNIPOLE | 6m | Add R8852E S9000 x1+R9264H M901821 x2+R8862A S2601 x3+A9732 M1821 x1,Dismantle | 3 | 0
P00681 | P032A_P00681OD_KOMP_PENJARA_JAWI | Northern | 4383K | Swap |  | 2024 Q1_496 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-09-04 | 2023-09-13 |  | 2023-09-16 |  | Closed | 2023-09-18 | 2023-10-11 | CD//Rohizam | 2023-10-10 | Celcom Digi_RAN-GTSB-TSS-Northern-20230905-0033 | DU00002559878 |  |  | 2023-11-03 | 2023-11-02 |  | In-Building System | TOWER | 6 | Add R8852E S9000 x1+R9264H M901821 x2+R8862A S2601 x3+A9732 M1821 x1,Dismantle | 3 | 0
P00696 | P034B_P00696OD_LAHAR_MINYAK | Northern | 4384K | Swap |  | 2024 Q1_496 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-09-07 | 2023-09-13 |  | 2023-09-15 |  | Closed | 2023-09-18 | 2023-09-21 | CD//Rohizam | 2023-09-20 | Celcom Digi_RAN-GCI-TSS-Northern-20230911-0047 | DU00002559879 |  |  | 2023-10-03 | 2023-09-25 |  | Tower | TOWER | 46m | Add R9264M M1821 x1+R9264H M901821 x3+R8862A S2601 x4,Dismantle |  | 2
P00712 | P032A_P00712OD_CRESCENTIA_PARK | Northern | 4385K | Swap |  | 2024 Q1_496 | SM | Ascentrack | 4.6 TSSR Approved |  | 2023-08-28 | 2023-09-18 |  | 2023-09-22 |  | Closed | 2023-09-25 | 2023-10-11 | CD//Rohizam | 2023-10-10 | Celcom Digi_RAN-Ascentrack-TSS-Northern-20230829-0005 | DU00002559880 |  |  | 2023-10-26 | 2023-10-26 |  | Monopole | MONOPOLE | 34m | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle | 2
P00716 | P034B_P00716OD_LAHAR_KEPAR | Northern | 4386K | Swap |  | 2024 Q1_496 | BY | YPTT | 4.6 TSSR Approved |  | 2023-09-02 | 2023-09-05 |  | 2023-09-07 |  | Closed | 2023-09-08 | 2023-09-12 | CD//Rohizam | 2023-09-11 | Celcom Digi_RAN-YPTT-TSS-Northern-20230904-0032 | DU00002559881 |  |  | 2023-09-29 | 2023-09-28 |  | Tower | TOWER | 47 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle
P00762 | P032A_P00762OD_TMNTAMBUNJAYA | Northern | 4387K | Swap |  | 2024 Q1_496 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-10-12 | 2023-10-16 |  | 2023-10-20 |  | Closed | 2023-10-23 | 2023-10-27 | CD//Rohizam | 2023-10-26 | Celcom Digi_RAN-GCI-TSS-Northern-20231013-0058 | DU00002559882 |  |  | 2023-10-28 | 2023-10-26 |  | Lampole | STREET POLE | 12m | Add R8852E S9000 x3+R8854E S1800 x3+R9224E M1821 x3,Dismantle
P00777 | P0033A_P00777_KUALAMENGKUANG | Northern | 4388K | Swap |  | 2024 Q1_496 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-08-14 | 2023-08-30 |  | 2023-09-04 |  | Closed | 2023-09-05 | 2023-09-07 | CD//Rohizam | 2023-09-06 | Celcom Digi_RAN-GTSB-TSS-Northern-20230817-0025 | DU00002559883 |  |  | 2023-10-09 | 2023-09-27 |  | Monopole | MONOPOLE | 45 | Add R8852E S9000 x3+R8854E S1800 x3+R9224E M1821 x3,Dismantle
Q00002 | Q124B_Q00002OD_TMJLNWERE | Sarawak | 9145K | Swap |  | 2024 Q1_496 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-09-20 | 2023-10-06 |  | 2023-10-10 |  | Closed | 2023-10-11 | 2023-10-17 |  | 2023-10-12 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230921 | DU00002559884 |  |  | 2024-02-29 | 2024-02-20 |  | Portables BTS | BOOM | 6 | Add R8852E S9000 x2+R9264H M901821 x1+R8862A S2601 x3+A9732 M1821 x2,Dismantle | 12
Q00005 | Q124F_Q00005OD_CB_SENARIPORT | Sarawak | 9146K | Swap |  | 2024 Q1_496 | SH | Datasco | 4.6 TSSR Approved |  | 2023-08-16 | 2023-08-22 |  | 2023-08-25 |  | Closed | 2023-08-25 | 2023-08-28 | CD//John | 2023-08-28 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230818 | DU00002559885 |  |  | 2024-01-26 | 2023-12-05 |  | Tower | BOOM | 60 | Add R8852E S9000 x3+R8854E S1800 x3+R9224E M1821 x3,Dismantle
Q00062 | Q124A_Q00062OD_TMSPG3 | Sarawak | 9149K | Swap |  | 2024 Q1_496 | SH | Trintel | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦exisitng S3 antenna pole have 2 pcs antrnna, can not add AAU | 2023-08-17 | 2023-10-12 |  | 2023-10-12 |  | Closed | 2024-01-25 | 2024-01-29 | CD//John | 2024-01-26 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230818 | DU00002559886 | NIC_S1_Change MM to BI_Space constraint_TELEKOM (M) |  | 2024-03-06 | 2024-02-27 |  | In-Building System | BOOM | 6m | Add R9264H M901821 x3+R8862A S2601 x2+R8854 S2600 x1,Dismantle |  | 3
Q00151 | Q124B_Q00151OD_LRGCARPENTER | Sarawak | 9156K | Swap |  | 2024 Q1_496 | ZB | AllStar | 4.6 TSSR Approved |  | 2023-08-17 | 2023-09-08 |  | 2023-09-12 |  | Closed | 2023-09-13 | 2023-09-15 | CD//John | 2023-09-13 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230807 | DU00002559887 |  |  | 2023-11-23 | 2023-11-15 |  | In-Building System | BOOM | 8 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle
Q00425 | Q124A_Q00425OD_TMNTHREEHILL | Sarawak | 9173K | Swap |  | 2024 Q1_496 | SH | Datasco | 4.6 TSSR Approved |  | 2023-08-24 | 2023-08-29 |  | 2023-09-04 |  | Closed | 2023-09-05 | 2023-09-14 | CD//John | 2023-09-06 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230830 | DU00002559888 |  |  | 2023-11-30 | 2023-11-14 |  | Monopole | TOWER | 24 | Add R8852E S9000 x3+R8854E S1800 x3+R9224E M1821 x3,Dismantle
Q00880 | Q124F_Q00880OD_KDRMSEJINGKAT | Sarawak | 9185K | Swap |  | 2024 Q1_496 | SH | Datasco | 4.6 TSSR Approved |  | 2023-08-08 | 2023-08-09 |  | 2023-08-13 |  | Closed | 2023-08-14 | 2023-08-15 | CD//John | 2023-08-15 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230808 | DU00002559889 |  |  | 2023-11-30 | 2023-10-30 |  | Monopole | BOOM | 24 | Add R8852E S9000 x3+R8854E S1800 x3+R9224E M1821 x3,Dismantle
Q01028 | Q124A_Q01028OD_JLNBANHOCK | Sarawak | 9195K | Swap |  | 2024 Q1_496 | ZB | AllStar | 4.6 TSSR Approved |  | 2023-08-22 | 2023-08-29 |  | 2023-09-01 |  | Closed | 2023-09-04 | 2023-09-06 | CD//John | 2023-09-05 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230823 | DU00002559890 |  |  | 2023-11-23 | 2023-11-14 |  | In-Building System | BOOM | 6 & 3 | Add R8852E S9000 x3+R8854E S1800 x3+R9224E M1821 x3,Dismantle
Q01394 | Q124B_Q01394OD_LRGHJTAHA | Sarawak | 9228K | Swap |  | 2024 Q1_496 | SH | Datasco | 4.6 TSSR Approved |  | 2023-08-08 | 2023-08-21 |  | 2023-08-23 |  | Closed | 2023-08-24 | 2023-08-25 | CD//John | 2023-08-25 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230808 | DU00002559891 |  |  | 2023-11-07 | 2023-11-06 |  | In-Building System | TBC | 6 | Add R8852E S9000 x1+R9264H M901821 x2+R8862A S2601 x3+A9732 M1821 x1,Dismantle | 2(S1->S3,S2->S1,S1->S3,Rename sectorID ,FDD MM@ NEW S1) | 0
Q01669 | Q124F_Q01669OD_KGSEJINGKAT | Sarawak | 9235K | Swap |  | 2024 Q1_496 | SH | Trintel | 4.6 TSSR Approved |  | 2023-08-17 | 2023-09-04 |  | 2023-09-06 |  | Closed | 2023-09-06 | 2023-09-12 | CD//John | 2023-09-08 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230818 | DU00002559892 |  |  | 2024-01-22 | 2024-01-17 |  | Tower | RAPOLE | 45m | Add R9264M M1821 x1+R9264H M901821 x3,Dismantle |  | 2
Q01750 | Q124F_Q01750OD_DEMAKLAUTIND3 | Sarawak | 9238K | Swap |  | 2024 Q1_496 | SH | Datasco | 4.6 TSSR Approved |  | 2023-08-10 | 2023-08-16 |  | 2023-08-25 |  | Closed | 2023-08-28 | 2023-08-28 | CD//John | 2023-08-28 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230811 | DU00002559893 |  |  | 2023-10-26 | 2023-10-18 |  | Monopole | RAPOLE | 30 | Add R8852E S9000 x3+R8894E M1821 x3,Dismantle
1261B_QW | Sunway Hospital IB | Central |  | Modernization |  | 2024 Q1_496 | AI | GTSB | 4.6 TSSR Approved |  | 2023-12-17 | 2023-12-26 |  | 2024-01-04 |  | Closed | 2024-01-04 | 2024-01-08 | E//Nazrul | 2024-01-05 | CelcomDigi_RAN_GTSB_TSS_Central_20231224 | DU00002559894 |  |  | 2024-06-24 | 2024-02-22 |  | Portables BTS | In-building system |  | Add R8852E S9000 x7+R8862A S2100 x3,dimantle R8882-GUL1812 x1+R8862A S1800(B6A) x2+R8840-U216 x1+R8881 S2100 x2 | 0 | 0
1262B | SJMC IB | Central |  | Modernization |  | 2024 Q1_496 | AI | GTSB | 4.6 TSSR Approved |  | 2023-09-13 | 2023-09-16 |  | 2023-09-21 |  | Closed | 2023-09-22 | 2023-10-01 | E//Nazrul | 2023-09-25 | CelcomDigi_RAN_GTSB_TSS_Central_20230914 | DU00002559895 |  |  | 2023-10-13 | 2023-10-12 |  | In-Building System | In-building system |  | Reuse existing R8862A S2600(A4A) x2+R8892E M1821(BAA) x1,dismantle R8882-GUL1812 x1+R8840-U216 x1(Need to Reconnect R8892E)
1723B | Empire Subang IB | Central |  | Modernization |  | 2024 Q1_496 | CR | GCI | 4.6 TSSR Approved |  | 2023-11-25 | 2023-11-29 |  | 2023-12-08 |  | Closed | 2023-12-13 | 2023-12-26 | E//Nazrul | 2023-12-09 | CelcomDigi_RAN_GCI_TSS_Central_20231126 | DU00002559896 |  |  | 2024-02-05 | 2024-01-31 |  | Portables BTS | In-building system |  | Add R8852E S9000 x3+R8862A S2100 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3
1836A | Sunway Micro 1 | Central |  | Site Out (Modernization) | Modernization->Site Out->Site Out (Modernization) | 2024 Q1_496 | AI | GTSB | 4.6 TSSR Approved |  | 2023-09-12 | 2023-09-21 | 2025-08-06 | 2023-09-28 |  | Under Approval | 2023-10-02 | 2024-09-09 | E//Nazrul | 2023-10-03 | CelcomDigi_RAN_GTSB_TSS_Central_20230913 | DU00002559897 | [6 empty] | In-building system
1856A | Sheraton Subang | Central |  | Modernization |  | 2024 Q1_496 | AI | GTSB | 4.6 TSSR Approved |  | 2023-09-18 | 2023-09-22 |  | 2023-10-02 |  | Closed | 2023-10-04 | 2023-10-06 | E//Nazrul | 2023-10-05 | Celcom Digi_RAN-GTSB-TSS-Central-20230919 | DU00002559898 |  |  | 2023-10-21 | 2023-10-21 |  |  | In-building system |  | Add R8862A S1800 x1,Dismantle R8882-GUL1812 x1
1866A | The Summit | Central |  | Modernization |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-10-10 | 2023-10-16 |  | 2023-12-14 |  | Closed | 2023-12-18 | 2024-03-27 | E//Nazrul | 2024-03-26 | CelcomDigi_RAN_Datasco_TSS_Central_20231005 | DU00002559899 |  |  | 2025-03-06 | 2025-02-28 |  | In-Building System | In-building system |  | Add R8852E S9000 x3+R8862A S2100 x2+R8862A S2601 x3,Dismantle R8882-GUL1812 x1 | 0 | 0
1872A | Carrefour Subang Jaya | Central |  | Modernization |  | 2024 Q1_496 | CR | GCI | 4.6 TSSR Approved |  | 2023-09-03 | 2023-09-16 |  | 2023-09-20 |  | Closed | 2023-09-21 | 2023-10-01 | E//Nazrul | 2023-09-22 | Celcom Digi_RAN-GCI-TSS-Central-20230919 | DU00002559900 |  |  | 2023-10-21 | 2023-10-07 |  | Portables BTS | In-building system | IBC | Add R8852E S9000 x2+R8892E M1821 x2,Dismantle R8882 S1800B(B6B) x1+R8862A S1800 x1++R8881 S2100 x1+
2500A | Mydin Subang Jaya | Central |  | Modernization |  | 2024 Q1_496 | SS | YPTT | 4.6 TSSR Approved |  | 2023-09-02 | 2023-09-06 |  | 2023-09-10 |  | Closed | 2023-09-13 | 2023-09-13 | E//Nazrul | 2023-09-13 | CelcomDigi_RAN_YPTT_TSS_Central_20230904 | DU00002559901 |  |  | 2023-10-19 | 2023-10-10 |  | Portables BTS | In-building system | N/A | Add R8862A S2100 x1+R8862A S1800 x1,Dismantle R8882-GUL1812 x1+R8840-U216 x1
2730A | Wisma Consplant IB | Central |  | Modernization | Modernization->On Hold->Decomm->Modernization | 2024 Q1_496 | SY1 | GCI | 4.6 TSSR Approved |  | 2024-07-29 | 2024-08-02 |  | 2024-08-14 | 2023-11-10 | Closed | 2024-08-15 | 2024-09-12 | E//Kok Keen | 2024-09-12 | 0619Central-GCI-BOQ Template (template) | DU00002559902 |  | NO TX INFO | 2024-09-20 | 2024-09-02 |  | Portables BTS | In-building system | N/A | Add R8862A S2100 x3+R8862A S1800 x3 +R8894E M1821x1,Dismantle R8882-GUL1812 x3 | 0 | 0
2731A | Menara Sunway (HQ) IB | Central |  | Modernization | Modernization->On Hold->Decomm->Modernization | 2024 Q1_496 | BY | GCI | 4.6 TSSR Approved |  | 2024-04-02 | 2024-06-18 |  | 2024-07-04 | 2024-04-09 | Under Approval | 2024-07-10 | 2024-07-10 |  | 2024-07-10 | 0626Central-GCI-BOQ Template (template) | DU00002559903 |  | MISSING FE PART | 2024-11-25 | 2024-10-26 |  | Portables BTS | In-building system |  | Add R8862A S2100 x3+R8862A S2601 x3+R8862A S1800 x3,Dismantle R8882-GUL1812 x1+R8840 U216x1 | 0 | 0
2732A | Sunway Pyramid New Wing IB | Central |  | Site Out (Modernization) | Modernization->Site Out->Site Out (Modernization) | 2024 Q1_496 |  | GCI | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2025-06-21 | 2025-07-10 | [8 empty] | SQ202506140192 | DU00002559904 | [6 empty] | In-building system
2985B | Sunway Pyramid Tower | Central |  | Modernization | Modernization->On Hold->Decomm->Modernization | 2024 Q1_496 | CR | GCI | 4.6 TSSR Approved |  | 2024-04-02 | 2024-06-18 |  | 2024-07-03 | 2024-04-19 | Rectificating | 2024-07-12 | 2024-07-23 | E//Nazrul | 2024-07-23 | 0626Central-GCI-BOQ Template (template) | DU00002559905 |  |  | 2024-11-05 | 2024-10-26 |  | Portables BTS | In-building system |  | Add R8862A S2100 x2+R8862A S2601 x1+R8894E M1821 x2+R8862A S1800 x2,Dismantle R8882-GUL1812 x1+R8840-U216 x1+R8892E M1821(BAA) x2
1598B | SUBANG PARADE CAR IB Subang Selangor | Central |  | Modernization |  | 2024 Q1_496 | CR | Magicell | 4.6 TSSR Approved |  | 2023-09-22 | 2023-09-25 |  | 2023-10-02 |  | Closed | 2023-10-12 | 2023-10-18 | E//Nazrul | 2023-10-12 | Celcom Digi_RAN-Magicell-TSS-Central-20230925 | DU00002559906 |  |  | 2023-12-06 | 2023-11-25 |  | In-Building System | In-building system |  | Add R8862A S2100 x2+R8862A S2601 x1+R8862A S1800 x2,Dismantle R8882-GUL1812 x1+R8840-U216 x1 | 0 | 0
1592B | TAYLOR UNI COLLEGE IB | Central |  | Modernization | Modernization->On Hold->Decomm->Modernization | 2024 Q1_496 | CR | Magicell | 4.6 TSSR Approved |  | 2023-10-19 | 2023-10-23 |  | 2024-06-13 | 2024-03-15 | Under Approval | 2024-06-14 | 2024-06-20 | E//Nazrul | 2024-06-14 | 0626Central-Magicell-BOQ Template (template) | DU00002559907 |  | Missing NE & FE | 2024-09-24 | 2024-09-23 |  |  | In-building system |  | Add R8852E S9000 x1+R8862A S2100 x1+R8862A S1800 x1,Dismantle R8882-GUL1812 x1 | 0 | 0
4815A | BM Plaza | Northern |  | Modernization |  | 2024 Q1_496 | WP | GTSB | 4.6 TSSR Approved |  | 2023-08-24 | 2023-08-25 |  | 2023-08-31 |  | Closed | 2023-09-01 | 2023-09-04 | E//Nazrul | 2023-09-03 | Celcom Digi_RAN-GTSB-TSS-Northern-20230825-0030 | DU00002559908 |  |  | 2023-10-01 | 2023-09-25 |  | Portables BTS | In-building system |  | Add R8862A S2100 x1+R8862A S2601 x1+R8862A S1800 x1,Dismantle R8882-GUL1812 x1
9811A | Crown Square Indoor | Sarawak |  | Modernization |  | 2024 Q1_496 | SH | Datasco | 4.6 TSSR Approved |  | 2023-08-30 | 2023-09-06 |  | 2023-09-11 |  | Closed | 2023-09-12 | 2023-10-03 | E//Hannah | 2023-10-03 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230901 | DU00002559909 |  |  | 2023-10-18 | 2023-10-13 |  | Portables BTS | In-building system |  | Add R8862A S2100 x1+R8862A S1800 x1,Dismantle R8882-GUL1812 x1
9847A | Spring Mall IB | Sarawak |  | Modernization |  | 2024 Q1_496 | SH | Datasco | 4.6 TSSR Approved |  | 2023-09-16 | 2023-09-22 |  | 2023-09-29 |  | Closed | 2023-09-30 | 2023-10-02 | E//Nazrul | 2023-10-02 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230919 | DU00002559910 |  |  | 2023-12-08 | 2023-12-04 |  |  | In-building system |  | Add R8862A S1800 x3,Dismantle R8882-GUL1812 x3
9866A | Borneo Convention Centre IB | Sarawak |  | Modernization |  | 2024 Q1_496 | SH | Datasco | 4.6 TSSR Approved |  | 2023-09-19 | 2023-09-27 |  | 2023-10-04 |  | Closed | 2023-12-14 | 2024-01-16 | E//Nazrul | 2024-01-16 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230921 | DU00002559911 |  |  | 2024-02-02 | 2024-01-25 |  |  | In-building system |  | Add R8862A S2601 x3+R8862A S1800 x2,Dismantle R8882 S1800B(B6B) x2 | 0 | 0
3143B | SJMC Old Wing IB | Central |  | Modernization |  | 2024 Q1_496 | CR | GCI | 4.6 TSSR Approved |  | 2023-09-27 | 2023-09-22 |  | 2023-09-27 |  | Closed | 2023-09-29 | 2023-10-03 | E//Nazrul | 2023-10-03 | CelcomDigi_RAN_GCI_TSS_Central_20231003 | DU00002559912 |  |  | 2023-08-30 | 2023-08-30 |  | In-Building System | In-building system | 41 | Reuse existing RRU
3259B | Main Place USJ20 | Central |  | Modernization |  | 2024 Q1_496 | XH | Magicell | 4.6 TSSR Approved |  | 2023-08-30 | 2023-09-01 |  | 2023-09-05 |  | Closed | 2023-09-06 | 2023-10-11 | E//Nazrul | 2023-10-11 | CelcomDigi_RAN_Magicell_TSS_Central_20230901 | DU00002559913 |  |  | 2023-08-30 | 2023-08-30 |  |  | In-building system |  | Reuse existing RRU
3267B | Sunway Pyramid Phase 3 | Central |  | Modernization |  | 2024 Q1_496 | SS | Magicell | 4.6 TSSR Approved |  | 2023-11-09 | 2023-10-19 |  | 2023-11-15 |  | Closed | 2023-11-20 | 2023-11-22 |  | 2023-11-20 | CelcomDigi_RAN_Magicell_TSS_Central_20231019 | DU00002559914 |  |  | 2023-12-08 | 2023-12-08 |  | Portables BTS | In-building system | NA | Add R8862A S2100 x3+R8862A S2601 x2+R8862A S1800 x2
2946B | Sunway Hotel | Central |  | Decomm | Modernization->On Hold->Decomm->Modernization->Decomm | 2024 Q1_496 | CR | Magicell | 15.4 Decomm Done without TSSR Approval |  | 2023-10-19 | 2023-10-23 |  |  | 2024-03-18 |  | 2024-03-18 |  | E//Nazrul |  | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240311 | DU00002559915 |  | Missing NE & FE |  |  | 2025-08-26 | Portables BTS | In-building system
3261B | One City Putra Height | Central |  | Modernization | Modernization->On Hold->Modernization | 2024 Q1_496 | AI | Magicell | 4.6 TSSR Approved |  | 2023-09-07 | 2023-09-14 |  | 2024-02-20 |  | Closed | 2024-02-20 | 2024-02-28 | E//Nazrul | 2024-02-28 | CelcomDigi_RAN_Magicell_TSS_Central_20230915 | DU00002559916 |  |  | 2024-01-15 | 2024-01-11 |  | Portables BTS | In-building system |  | Add R8862A S2100 x8+R8862A S1800 x8+R8862A S2601(A6A) x5,Dismantle R8882 S1800B(B6B) x3 | 0 | 0
9149B | Wisma Sarawak Energy | Sarawak |  | Modernization |  | 2024 Q1_496 | SH | AllStar | 4.6 TSSR Approved |  | 2023-08-22 | 2023-08-23 |  | 2023-08-25 |  | Closed | 2023-08-28 | 2023-09-14 | E//Hannah | 2023-09-08 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230823 | DU00002559917 |  |  | 2023-12-08 | 2023-11-28 |  | Portables BTS | In-building system |  | Add R8862A S2100 x3,Dismantle
3474B | Sunway Pinnacle IB | Central |  | Modernization | Modernization->On hold->Modernization | 2024 Q1_496 | CR | Magicell | 4.6 TSSR Approved |  | 2023-10-03 | 2023-10-05 |  | 2024-02-28 |  | Rectificating | 2024-03-07 | 2024-03-07 | E//Nazrul | 2024-03-07 | CelcomDigi_RAN_Magicell_TSS_Central_20231005 | DU00002559918 |  |  | 2024-04-02 | 2024-03-29 |  | Portables BTS | In-building system |  | Add R8862A S2601 x1 + R8862A S1800 x1 + R8862A S2100 x1,Reonnect R8892N
9103B | Plaza Merdeka Indoor | Sarawak |  | Modernization |  | 2024 Q1_496 | SH | AllStar | 4.6 TSSR Approved |  | 2023-08-09 | 2023-08-18 |  | 2023-08-23 |  | Closed | 2023-08-24 | 2023-09-14 | E//Hannah | 2023-09-08 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230807 | DU00002559919 |  |  | 2023-09-30 | 2023-09-17 |  | Portables BTS | In-building system |  | Add R8862A S2100 x3+R8862A S1800 x3,Dismantle
3575B | Da Men Shopping Mall IB | Central |  | Modernization |  | 2024 Q1_496 | SS | Magicell | 4.6 TSSR Approved |  | 2023-12-20 | 2023-12-27 |  | 2024-01-02 |  | Closed | 2024-01-03 | 2024-02-15 | E//NAZRUL | 2024-02-15 | CelcomDigi_RAN_Magicell_TSS_Central_20231224 | DU00002559920 |  |  | 2024-02-01 | 2024-01-30 |  | Portables BTS | In-building system |  | Add R8862A S2100 x3+R8862A S1800 x3,Dismantle R8882 S1800B(B6B) x3
4101D | IKEA Batu Kawan IB | Northern |  | Modernization |  | 2024 Q1_496 | WP | GCI | 4.6 TSSR Approved |  | 2023-08-30 | 2023-09-16 |  | 2023-09-14 |  | Closed | 2023-09-16 | 2023-09-26 | E//Hazida | 2023-09-22 | Celcom Digi_RAN-GCI-TSS-Northern-20230904-0044 | DU00002559921 |  |  | 2023-08-30 | 2023-08-30 |  | Portables BTS | In-building system | IBC | Reuse existing RRU
1600C | Nippon Express (HQ) IB | Central |  | Modernization |  | 2024 Q1_496 | MA | Magicell | 4.6 TSSR Approved |  | 2023-10-02 | 2023-10-03 |  | 2023-10-05 |  | Closed | 2023-10-06 | 2023-11-29 | E//Nazrul | 2023-11-27 | CelcomDigi_RAN_Magicell_TSS_Central_20231003 | DU00002559922 |  |  | 2023-12-10 | 2023-11-15 |  |  | In-building system |  | Add R8862A S2100 x2,Dismantle
1596B | USJ Nineteen IB | Central |  | Modernization |  | 2024 Q1_496 | XH | Magicell | 4.6 TSSR Approved |  | 2023-08-30 | 2023-09-01 |  | 2023-09-05 |  | Closed | 2023-09-06 | 2023-09-07 | E//Nazrul | 2023-09-06 | CelcomDigi_RAN_Magicell_TSS_Central_20230901 | DU00002559923 |  |  | 2023-09-23 | 2023-09-22 |  |  | In-building system |  | Add R8862A S2100 x1+R8862A S1800 x1,Dismantle R8882-GUL1812 x1
1593B | LEISURE COMMERCE SQUARE (BALI) IB | Central |  | Modernization |  | 2024 Q1_496 | SS | Magicell | 4.6 TSSR Approved |  | 2023-10-31 | 2023-11-01 |  | 2023-11-08 |  | Closed | 2023-11-09 | 2023-11-14 | E//Nazrul | 2023-11-09 | CelcomDigi_RAN_Magicell_TSS_Central_20231101 | DU00002559924 |  |  | 2023-12-20 | 2023-12-18 |  | Portables BTS | In-building system |  | Add R8862A S2100 x1,Dismantle
9809A | Kuching Hiliton | Sarawak |  | Modernization |  | 2024 Q1_496 | ZB | AllStar | 4.6 TSSR Approved |  | 2023-08-14 | 2023-08-15 |  | 2023-08-17 |  | Closed | 2023-08-21 | 2023-09-04 | E//Nazrul | 2023-09-03 | Celcom Digi_RAN-AllStar-TSS-Sarawak-20230815 | DU00002559925 |  |  | 2023-09-23 | 2023-09-20 |  | Watertank | In-building system |  | Add R8862A S2100 x1+R8862A S1800 x1,Dismantle R8882-GUL1812 x1
4182C | Sunshine Bertam Mall IBC | Northern |  | Modernization |  | 2024 Q1_496 | WP | GCI | 4.6 TSSR Approved |  | 2023-09-02 | 2023-09-04 |  | 2023-09-05 |  | Closed | 2023-09-07 | 2023-09-08 | E//Nazrul | 2023-09-07 | Celcom Digi_RAN-GCI-TSS-Northern-20230904-0044 | DU00002559926 |  |  | 2023-10-27 | 2023-10-27 |  |  | In-building system |  | Add R8862A S1800 x1,Dismantle R8882 S1800(B) x1
1660B | Sunway Hospital New Wing IB | Central |  | Modernization |  | 2024 Q1_496 | XH | Magicell | 4.6 TSSR Approved |  | 2023-08-29 | 2023-09-01 |  | 2023-09-05 |  | Closed | 2023-09-06 | 2023-09-07 | E//Nazrul | 2023-09-06 | CelcomDigi_RAN_Magicell_TSS_Central_20230901 | DU00002559927 |  |  | 2023-10-16 | 2023-10-07 |  | In-Building System | In-building system | NA | Add R8862A S2100 x1+R8862A S1800 x1,Dismantle R8882-GUL1812 x1
3374C | Sunway Pyramid Convention Centre IB | Central |  | Site Out (Modernization) | Modernization->Site Out->Site Out(Modernization) | 2024 Q1_496 | CR | YPTT | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2025-03-07 | 2025-10-21 | [8 empty] | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240510 | DU00002559928 | [5 empty] | Portables BTS | In-building system |  | Add R8892N M1821 x5,Dismantle R8892E M1821(BAA) x5 | 0 | 0
2021B | DiGi TOC (Lot 43) | Central |  | Modernization |  | 2024 Q1_496 | IE | Magicell | 4.6 TSSR Approved |  | 2023-09-11 | 2023-09-14 |  | 2023-09-18 |  | Closed | 2023-09-21 | 2023-10-01 | E//Nazrul | 2023-09-22 | CelcomDigi_RAN_Magicell_TSS_Central_20230912 | DU00002559929 |  |  | 2023-10-25 | 2023-09-27 |  | Portables BTS | In-building system |  | Add R8862A S2100 x1+R8862A S1800 x1+R8862A S2601 x1,Dismantle R8882 S1800B(B6B) x1+R8882-L268 x1
B00881 | B061H_B00881IB_SNWYCOLLEGE | Central | 1330K | Swap |  | 2024 Q1_496 | AI | GTSB | 4.6 TSSR Approved |  | 2023-09-29 | 2023-10-03 |  | 2023-10-06 |  | Closed | 2023-10-17 | 2023-10-25 | CD//Sofiah | 2023-10-23 | CelcomDigi_RAN_GTSB_TSS_Central_20231003 | DU00002559930 |  |  | 2024-01-09 | 2023-12-11 |  | Portables BTS | BOOM |  | Add R8852E S9000 x1+R8862A S2100 x1,Dismantle
B01387 | B061I_B01387IB_MHTECHVILAGE1 | Central | 1334K | Swap |  | 2024 Q1_496 | SS | Magicell | 4.6 TSSR Approved |  | 2023-12-15 | 2023-12-20 |  | 2024-01-02 |  | Closed | 2024-01-03 | 2024-02-13 | CD//Sofiah | 2024-02-13 | CelcomDigi_RAN_Magicell_TSS_Central_20231224 | DU00002559931 |  |  | 2024-03-20 | 2024-03-12 |  | Portables BTS | BOOM |  | Add R8862A S2100 x3+R8862A S1800 x3,Dismantle
B01398 | B061B_B01398IB_MENARAHEITECH | Central | 1335K | Swap |  | 2024 Q1_496 | SS | Magicell | 4.6 TSSR Approved |  | 2023-12-15 | 2023-12-20 |  | 2024-01-02 |  | Closed | 2024-01-03 | 2024-02-13 | CD//Sofiah | 2024-02-13 | CelcomDigi_RAN_Magicell_TSS_Central_20231224 | DU00002559932 |  |  | 2024-03-12 | 2024-03-07 |  | Portables BTS | BOOM |  | Add R8862A S2100 x1+R8862A S1800 x1,Dismantle
B01715 | B061H_B01715IB_THEICONIC | Central | 1337K | Site Out (Swap) | Swap->On Hold->Site out->Site Out (Swap) | 2024 Q1_496 | AI | GCI | [SiteOut]- 4.5 Pending TSSR Review - Customer |  | 2023-12-28 | 2024-01-11 |  | 2024-01-12 |  | Closed | 2024-01-12 |  | CD//Sofiah |  | CelcomDigi_RAN_GCI_TSS_Central_20231230 | DU00002559933 | [5 empty] | Portables BTS | Lampole | NA
B02530 | B061H_B02530IB_Sunway_GEO_CP4_Ready | Central | 1342K | Swap |  | 2024 Q1_496 | CR | Magicell | 4.6 TSSR Approved |  | 2023-10-10 | 2023-10-11 |  | 2023-10-16 |  | Closed | 2023-10-17 | 2023-11-17 | CD//Sapian | 2023-11-15 | CelcomDigi_RAN_Magicell_TSS_Central_20231011 | DU00002559934 |  |  | 2023-12-01 | 2023-11-08 |  | Portables BTS | IN-BUILDING |  | Add R8862A S2100 x3+R8862A S2601 x3+R8862A S1800 x3,Dismantle
B02753 | B061L_B02753IB_DHLTHEPLACECITYMALL | Central | 1344K | Swap |  | 2024 Q1_496 | AI | Magicell | 4.6 TSSR Approved |  | 2023-10-05 | 2023-10-13 |  | 2023-10-16 |  | Closed | 2023-10-16 | 2023-10-24 | CD//Sofiah | 2023-10-23 | CelcomDigi_RAN_Magicell_TSS_Central_20231006 | DU00002559935 |  |  | 2023-12-09 | 2023-11-15 |  | In-Building System | IN-BUILDING |  | Add R8862A S2100 x3+R8862A S2601 x3+R8862A S1800 x3,Dismantle
Q00075 | Q124B_Q00075IB_MERDEKAPALACE | Sarawak | 9270K | Swap |  | 2024 Q1_496 | SH | AllStar | 4.6 TSSR Approved |  | 2023-08-22 | 2023-08-25 |  | 2023-08-28 |  | Closed | 2023-08-29 | 2023-09-14 | CD//John | 2023-08-30 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230808 | DU00002559936 |  |  | 2024-02-26 | 2024-02-06 |  | Portables BTS | BOOM |  | Add R8862A S2100 x2+R8862A S2601 x2+R8862A S1800 x2,Dismantle
B01331 | B061H_B01331IB_SUNWAYMEDICAL | Central |  | Decomm |  | 2024 Q1_496 | AI | YPTT | 15.3 Decomm Done without TSSR | [6 empty] | To be Submitted |  |  | CD//Sapian |  | SQ202502180555 | DU00002559937 |  |  |  |  | 2025-11-28 |  | SHARING STRC MAXIS
B01377 | B061H_B01377IB_SUBANG_JAYA_MEDICALCENTRE | Central |  | Decomm |  | 2024 Q1_496 | IE | GTSB | 4.6 TSSR Approved |  | 2023-12-25 |  |  |  | 2024-01-11 |  | 2024-01-12 | 2024-07-12 | CD//Sofiah | 2024-03-27 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240110 | DU00002559938 |  | To maintain OB fiber as its colo. Relo to xD cabinet |  |  | 2023-12-23 |  | TRIPOD
B01571 | B061H_B01571IB_EMPIREGALLERY | Central |  | Decomm |  | 2024 Q1_496 | AD | GCI | 4.6 TSSR Approved |  | 2023-12-08 |  |  |  | 2024-01-15 |  | 2024-01-17 | 2025-03-21 | CD//Sapian -CD//Sofiiah | 2024-01-23 | CelcomDigi_RAN_GCI_TSS_Central_20231214 | DU00002559939 |  |  |  |  | 2024-08-26 |  | BOOM
B00874 | B061H_B00874IB_SNWYPYRAMID | Central |  | Site Out (Decomm) | Decomm->Site Out->Site Out (Decomm) | 2024 Q1_496 |  | GTSB | 15.3 Decomm Done without TSSR | [6 empty] | To be Submitted |  |  |  |  | SQ202506170074 | DU00002559940 |  |  |  |  | 2025-06-26 |  | BOOM
B00861 | B061H_B00861IB_SHERATONSBG | Central |  | Decomm |  | 2024 Q1_496 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-20 |  |  |  | 2023-11-21 |  | 2023-11-22 | 2024-05-27 | CD//Sofiah | 2023-11-30 | CelcomDigi_RAN_GTSB_TSS_Central_20231126 | DU00002559941 |  |  |  |  | 2023-12-21 |  | IN-BUILDING
B00705 | B061I_B00705OD_SUMMITUSJ | Central |  | Decomm |  | 2024 Q1_496 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-10-12 |  |  |  | 2024-08-22 |  | 2023-12-18 | 2024-01-22 | CD//Sapian | 2023-12-26 | CelcomDigi_RAN_Datasco_TSS_Central_20231213 | DU00002559942 |  |  |  |  | 2024-05-29 |  | BOOM
B00882 | B061H_B00882IB_CARREFOURSBJ | Central |  | Decomm |  | 2024 Q1_496 | CR | GCI | 4.6 TSSR Approved |  | 2023-09-12 |  |  |  | 2023-12-01 |  | 2023-12-05 | 2024-05-27 | CD//Norhaliza | 2024-01-02 | CelcomDigi_RAN_GCI_TSS_Central_20231201/Celcom Digi_RAN-GCI-Standard PR TSS-Central-20241016 | DU00002559943 |  |  |  |  | 2023-12-15 |  | BOOM
B01156 | B061I_B01156IB_MYDEENSJ | Central |  | Decomm |  | 2024 Q1_496 | MA | YPTT | 4.6 TSSR Approved |  | 2023-09-02 |  |  |  | 2023-09-07 |  | 2023-09-07 | 2023-12-18 | CD//Sofiah | 2023-09-12 | CelcomDigi_RAN_YPTT_TSS_Central_20230905_Decom | DU00002559944 |  |  |  |  | 2023-10-24 |  | SHARING STRC DIGI
B01503 | B061H_B01503IB_WCONSPLANT1 | Central |  | Decomm | Decomm->On Hold->Swap->Decomm | 2024 Q1_496 | SHA | GCI | 4.6 TSSR Approved |  | 2024-03-31 | 2023-10-11 |  | 2024-04-17 | 2024-07-19 | Rectificating | 2024-08-14 | 2024-08-22 | CD//Sofiah | 2024-08-15 | 0626Central-GCI-BOQ Template (template) | DU00002559945 |  |  |  |  | 2024-09-06 | Portables BTS | BOOM | INBULDING
B00844 | B061H_B00844IB_MENARASUNWAY | Central |  | Decomm | Decomm->On Hold->Swap->Decomm | 2024 Q1_496 | SHA | GCI | 4.6 TSSR Approved |  | 2024-03-31 | 2024-04-04 |  | 2024-04-08 | 2024-07-18 | Under Approval | 2024-07-22 | 2025-03-21 | CD//Sofiah | 2024-07-24 | 0626Central-GCI-BOQ Template (template) | DU00002559946 |  |  |  |  | 2024-11-29 | Portables BTS | BOOM
B01157 | B061H_B01157IB_SUNWAYPYRAMID2 | Central |  | Site Out (Decomm) | Decomm->Site Out->Site Out (Decomm) | 2024 Q1_496 |  | GCI | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2025-06-21 |  | 2025-07-14 | [7 empty] | SQ202506140192 | DU00002559947 |  |  |  |  | 2025-06-26 |  | BOOM
B00843 | B061H_B00843IB_PYRAMIDTOWER | Central |  | Decomm | Decomm->On Hold->Swap->Decomm | 2024 Q1_496 | BY | GCI | 4.6 TSSR Approved |  | 2024-03-31 | 2024-04-23 |  | 2024-04-25 | 2024-07-19 | Rectificating | 2024-07-22 | 2025-03-21 | CD//Sofiah | 2024-07-24 | 0626Central-GCI-BOQ Template (template) | DU00002559948 |  |  |  |  | 2024-10-30 | Portables BTS | BOOM
B00877 | B061H_B00877IB_SBGPARADE | Central |  | Decomm |  | 2024 Q1_496 | SS | Magicell | 4.6 TSSR Approved |  | 2023-09-22 |  |  |  | 2023-09-28 |  | 2023-09-29 | 2024-07-10 | CD//Sofiah | 2023-10-30 | Celcom Digi_RAN-Magicell-TSS-Central-20230925 | DU00002559949 |  |  |  |  | 2023-12-21 |  | BOOM
B00857 | B061H_B00857IB_TAYLORCOLLEGE | Central |  | Decomm | Decomm->On Hold->Swap->Decomm | 2024 Q1_496 | SHA | Magicell | 4.6 TSSR Approved |  | 2023-10-19 | 2024-03-15 |  | 2024-03-18 | 2024-07-12 | Under Approval | 2024-07-18 | 2024-10-29 | CD//Sofiah | 2024-07-24 | 0626Central-Magicell-BOQ Template (template) | DU00002559950 |  |  |  |  | 2024-09-30 |  | BOOM
P00162 | P033A_P00162IB_SUMMIT | Northern |  | Decomm |  | 2024 Q1_496 | BY | GTSB | 4.6 TSSR Approved |  | 2023-11-10 |  |  |  | 2023-11-10 |  | 2023-11-14 | 2023-11-23 | CD//Rohizam | 2023-11-21 | Celcom Digi_RAN-GTSB-TSS-Northern-20231115-0065 | DU00002559951 |  |  |  |  | 2023-11-30 |  | BOOM
B02471 | B061H_B02471IB_SIMEDARBY_MEDICALCENTRE_NORTHTWR | Central |  | Decomm |  | 2024 Q1_496 | CR | YPTT | 4.6 TSSR Approved |  | 2023-11-29 |  |  |  | 2023-11-29 |  | 2023-11-30 |  | CD//Sofiah | 2023-12-14 | CelcomDigi_RAN_YPTT_TSS_Central_20231126 | DU00002559952 |  | Missing FE part |  |  | 2023-11-24 |  | IN-BUILDING
B02501 | B061I_B02501OD_MAINPLACE | Central |  | Decomm |  | 2024 Q1_496 | IE | Magicell | 4.6 TSSR Approved |  | 2023-09-04 |  |  |  | 2023-09-15 |  | 2023-09-18 | 2024-07-10 | CD//Sofiah | 2023-12-05 | CelcomDigi_RAN_Magicell_TSS_Central_20230905_Decom | DU00002559953 |  |  |  |  | 2023-10-02 |  | IN-BUILDING
B02342 | B061H_B02342IB_SUNWAYPYRAMID3 | Central |  | Decomm |  | 2024 Q1_496 | SS | Magicell | 4.6 TSSR Approved |  | 2023-10-18 |  |  |  | 2023-10-20 |  | 2023-12-06 | 2024-02-23 | CD//Sofiah | 2024-02-15 | CelcomDigi_RAN_Magicell_TSS_Central_20231019 | DU00002559954 |  |  |  |  | 2023-12-09 |  | IN-BUILDING
B00850 | B061H_B00850IB_SUNWAYRESORT | Central | 2946B | Swap | On Hold->Swap | 2024 Q1_496 | AI | Magicell | 4.6 TSSR Approved |  | 2023-10-20 | 2024-03-27 |  | 2024-03-18 |  | Closed | 2024-07-15 | 2024-07-18 | CD//Sofiah | 2024-07-18 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240311 | DU00002559955 |  |  | 2024-05-31 | 2024-05-20 |  | Portables BTS | BOOM |  | Add R8892N M1821 x4+R8862A S2601 x4,Dismantle
B02290 | B061L_B02290IB_SKYPARKONECITYMALL | Central | 1821K | Decomm | Decomm->Swap->Decomm->Swap->Decomm | 2024 Q1_496 | AI | Magicell | 4.6 TSSR Approved |  | 2023-09-21 | 2023-09-26 |  |  | 2024-02-21 |  | 2024-01-29 | 2024-03-22 | CD//Sofiah | 2024-03-18 | CelcomDigi_RAN_Magicell_TSS_Central_20230922 | DU00002559956 |  |  |  |  | 2024-05-28 | Portables BTS | IN-BUILDING
B02032 | B061H_B02032IB_FNISUNWAYPINNACLE | Central |  | Decomm | Decomm->Swap->On hold->Decomm | 2024 Q1_496 | MS | Magicell | 4.6 TSSR Approved |  | 2023-10-03 | 2023-10-13 |  | 2023-10-17 | 2024-02-26 | Rectificating | 2024-02-27 |  | CD//Sofiah | 2024-07-18 | 0704CD-Central-Magicell-BOQ Template (template) | DU00002559957 |  | Suggest to maintain OB fiber and relo to xD cabinet |  |  | 2024-05-31 |  | IN-BUILDING
B02553 | B061I_B02553IB_DA_MEN_MALL | Central |  | Decomm |  | 2024 Q1_496 | SS | Magicell | 4.6 TSSR Approved |  | 2023-12-20 |  |  |  | 2024-01-03 |  | 2024-01-09 | 2024-05-14 | CD//Sofiah | 2024-02-20 | CelcomDigi_RAN_Magicell_TSS_Central_20231224 | DU00002559958 |  |  |  |  | 2025-05-22 |  | IN-BUILDING
P00751 | P032A_P00751IB_IKEA_BATU_KAWAN | Northern |  | Decomm |  | 2024 Q1_496 | ZA | GCI | 4.6 TSSR Approved |  | 2023-09-18 |  |  |  | 2023-10-05 |  | 2023-10-09 | 2023-10-27 | CD//Rohizam | 2023-10-10 | Celcom Digi_RAN-GCI-TSS-Northern-20230919-0051/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240529-0109 | DU00002559959 |  | No TX Info |  |  | 2023-10-30 |  | INBUILDING
B02918 | B058E_B02918_TM_BKT_CHANGGANG | Central | 1908K | Swap | Swap | 2026 | AI | GCI | 1.1 Pending Survey - Subcon | [6 empty] | To be Submitted | [5 empty] | DU00006569413 | [8 empty] | Add R8862A S9000x3+R8894E M1821x3+R8862A S2601x3
A01295 | A045A_A01295OD_KGKUAKLUAR | Northern | 4665K | Swap | Swap | 2026 | AI | GCI | 4.5 Pending TSSR Review - Customer |  | 2026-04-14 | 2026-05-07 |  | 2026-05-12 |  | Closed | 2026-05-14 |  |  |  |  | DU00006569414 | [7 empty] | 30m | Add R8862A S9000x3+R8894E M1821x3+R8862A S2601x3
W02260 | W066Z_W00152OD_TMNPERTAMA | Central | 1934K | Swap | Swap | 2026 | AI | GTSB | 4.6 TSSR Approved |  | 2026-03-12 | 2026-04-02 |  | 2026-04-07 |  | Under Approval | 2026-04-16 |  |  | 2026-05-08 | SQ202603120577 | DU00006569415 | [5 empty] | In-Building System |  | 6m | Add R8862A S9000x3+R8894E M1821x3+R8862A S2601x3
P00580_Smallcell | P035A_P00580OD_ALLSEASONPLACE | Northern | 4152K | Swap |  | 2023Q3 |  | GTSB | 4.6 TSSR Approved |  | 2023-09-13 | 2023-09-30 |  | 2023-10-04 |  | Closed | 2023-11-20 | 2023-11-20 | CD//Rohizam | 2023-09-29 | Celcom Digi_RAN-GTSB-TSS-Northern-20230914-0037 | DU00002754242 |  |  | 2023-09-21 | 2023-08-21 |  | Portables BTS | TBC |  | Add BS8932 x1,Dismantle Celcom small cell
B01305_1 | B061C_B01305OD_PR_MRBSSEK312SHLM | Central | 1833K | Swap |  | 2023Q3 | MA | CCSMY | 4.6 TSSR Approved |  | 2024-03-27 | 2024-04-01 |  | 2024-05-06 |  | Closed | 2023-12-03 | 2024-03-27 | CD//Sapian | 2024-03-27 | BOQ CelcomDigi_RAN_CCSMY_Standard PR TSS_Central_20240329 | DU00003202615 |  |  | 2023-12-09 | 2023-12-05 |  |  |  | 24 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle | 0 | 0
B00528_1 | B057C_B00528OD_TMNGBK | Central | 1818K | Swap |  | 2023Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2023-12-08 |  |  | 2023-12-08 |  | Closed | 2024-03-26 | 2024-03-27 | CD//Ali Akaram | 2024-03-27 | CelcomDigi_RAN_AllStar_TSS_Central_20240513 | DU00003211319 |  |  | 2023-12-22 | 2023-12-11 |  |  |  |  | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1+R8862A S2601 x3 | 12
A00283 | A040A_A00283OD_TMBERCHAM | Northern | 4015K | Swap |  | 2023Q2 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-03-27 | 2023-04-06 |  | 2023-03-30 |  | Closed | 2023-04-18 | 2023-04-27 | CD//Shamsul | 2023-04-26 | Celcom Digi_RAN-GTSB-TSS-Northern-20230327-0003 | DU00001866489 |  |  | 2023-05-25 | 2023-05-09 |  | Tower | BOOM | 50 | Add R8852E S9000 x3 + R8894E M1821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
4240D | Kuil Sungai Wangi Sitiawan (REL) | Northern |  | Modernization |  | 2023Q2 | IE | GCI | 4.6 TSSR Approved |  | 2023-03-14 | 2023-04-03 |  | 2023-03-30 | 2023-04-02 | Closed | 2023-04-04 | 2023-04-18 | CD//Quah | 2023-04-02 | Celcom Digi_RAN-GCI-TSS-20230316-0001 | DU00001866490 |  |  | 2023-04-17 | 2023-04-16 |  | Lampole | 24m Lampole | 30M | Add R9264H M901821 x3,Dismantle R8862A S2100(A6A) x3
3431A_1 | DESA_MELAWATI1 | Central | [6 empty] | 3.4 SOW/Solution On Hold | [6 empty] | To be Submitted | [5 empty] | DU00006271591
1455A_IBC | Wisma HLA | Central |  | Modernization |  | 2024 Q2 | AD | GTSB | 4.6 TSSR Approved |  | 2023-10-20 | 2023-10-24 |  | 2024-01-23 |  | Under Approval | 2024-01-24 | 2024-07-30 | E//Nazrul | 2024-07-29 | CelcomDigi_RAN_GTSB_TSS_Central_20231021 | DU00002764567 |  |  | 2024-07-18 | 2024-07-16 |  | Portables BTS | IBS |  | Add R8862A S2100 x1+R8862A S2601 x1+R8862A S1800 x1,Dismantle R8882-GUL1812 x1
7813A_IBC | Tg Aru Resort | Sabah |  | Modernization |  | 2024 Q2 | AD | Futong | 4.6 TSSR Approved |  | 2023-10-06 | 2023-10-09 |  | 2023-10-13 |  | Closed | 2023-12-05 | 2023-12-07 | E//Nazrul | 2023-12-06 | Celcom Digi_RAN-Futong-TSS-Sabah-20231009 | DU00002764568 |  |  | 2024-03-13 | 2024-03-09 |  | Portables BTS | In-building system |  | Add R8862A S2601 x3+R8892N M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S2100(A6A) x2 | 0 | 0
2878A_IBC | Mont Kiara | Central |  | Modernization | Modernization->On hold->Modernization | 2024 Q2 | CR | Datasco | 4.6 TSSR Approved |  | 2024-01-30 | 2024-04-16 |  | 2024-04-19 |  | Closed | 2024-04-23 | 2024-05-30 | E//Nazrul | 2024-05-30 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240311 | DU00002764569 |  |  | 2024-05-04 | 2024-04-25 |  |  | 6.5m RT (Boom) + IBS |  | Add R8862A S2100 x2+R8862A S1800 x2,Dismantle R8882-GUL1812 x2
K00008_IBC | K005B_K00008OD_SPPLAZAOUTDOOR | Northern |  | Decomm | Decomm->On hold->Decomm | 2024 Q1 | SM | GTSB | 4.6 TSSR Approved |  | 2023-10-02 |  |  |  | 2023-10-12 |  | 2023-10-17 | 2024-04-23 | CD//Rohizam | 2023-10-18 | Celcom Digi_RAN-GTSB-TSS-Northern-20231003-0043 | DU00002764570 |  |  |  |  | 2024-07-29 |  | BOOM
7223A_IBC | Likas Square | Sabah |  | Modernization |  | 2024 Q2 | AD | Futong | 4.6 TSSR Approved |  | 2023-10-06 | 2023-10-26 |  | 2023-11-01 |  | Closed | 2023-12-05 | 2023-12-07 | E//Nazrul | 2023-12-06 | Celcom Digi_RAN-Futong-TSS-Sabah-20231009 | DU00002764571 |  |  | 2024-02-29 | 2024-02-22 |  | Portables BTS | 3m RT (Wall Mounted Pole) |  | Add R8892N M1821 x1,Dismantle R8862A S2100(A6A) x1 | 0 | 0
Q00081_IBC | Q124A_Q00081OD_RIVERSIDE | Sarawak |  | Decomm | Decomm->On hold->Decomm | 2024 Q1 | ZB | Trintel | 4.6 TSSR Approved |  | 2024-04-01 |  |  |  | 2024-04-02 |  | 2024-04-02 | 2024-04-24 | CD//John | 2024-04-02 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240406 | DU00002764572 |  |  |  |  | 2025-01-17 |  | BOOM
S00537_IBC | S093C_S00537OD_CITYMALLLUYANG | Sabah |  | Decomm |  | 2024 Q2 | MS | NR services | 4.6 TSSR Approved |  | 2023-11-26 |  |  |  | 2023-11-28 |  | 2023-11-28 | 2024-02-15 | CD//Mohidi Jaan | 2023-11-28 | Celcom Digi_RAN-NR Services-TSS-Sabah-20231206 | DU00002764573 |  |  |  |  | 2024-06-24 |  | BOOM
S00122_IBC | S093F_S00122OD_STARKKID | Sabah |  | Decomm |  | 2024 Q2 | MS | Futong | 4.6 TSSR Approved |  | 2023-12-18 |  |  |  | 2023-12-19 |  | 2023-12-21 | 2024-02-15 | CD//Mohidi Jaan | 2023-12-21 | Celcom Digi_RAN-Futong-TSS-Sabah-20231220 | DU00002764574 |  |  |  |  | 2024-06-12 |  | BOOM
W00189_IBC | W066K_W00189OD_PWTC | Central | 1940B | Swap | Decomm->On hold->Swap->Decomm->On Hold->Decomm->Swap | 2024 Q2 | AI | YPTT | 4.5 Pending TSSR Review - Customer |  | 2025-06-09 |  |  | 2025-06-09 |  | Under Approval | 2025-06-10 |  | E// Nazrul |  | SQ202506110242 | DU00002764575 |  |  | 2025-06-28 | 2025-06-11 |  |  | BOOM |  | Add R8862A S9000x2+R8862A S2100x8+R8862A S2601x3+R8862A S1800x11, Dismantle
W01022_IBC | W066F_W01022OD_PLAZADAMAS | Central |  | Decomm |  | 2024 Q2 | CR | Datasco | 4.6 TSSR Approved |  | 2023-10-25 | 2023-12-04 |  | 2024-05-23 | 2024-02-29 | Under Approval | 2024-03-11 | 2024-07-12 | CD//Sofiah | 2024-06-24 | CelcomDigi_RAN_Datasco_TSS_Central_20231213 | DU00002764576 |  |  |  |  | 2024-05-27 | Portables BTS | TOWER
S00538_IBC | S093F_S00538OD_TGARUPLAZA | Sabah |  | Decomm | Decomm->TBD->TBD->Swap->On Hold->Swap->On Hold->Decomm | 2024 Q2 | AD | YPTT | 4.6 TSSR Approved |  | 2024-04-17 | 2024-04-22 | 2024-09-18 | 2024-04-23 |  | Closed | 2024-04-24 | 2024-11-15 | CD//Mohidi Jaan | 2024-09-13 | Celcom Digi_RAN-YPTT-Standard PR TSS-Sabah-20240420/0813CD-Sabah-YPTT-BOQ Template(new contract). | DU00002764577 |  |  |  |  | 2024-11-12 | Portables BTS | In Building
W00029_IBC | W066F_W00029OD_BANKNEGARA | Central | 1219K | Swap |  | 2024 Q2 | BY | GCI | 4.6 TSSR Approved |  | 2024-04-03 | 2024-04-20 |  | 2024-05-07 |  | Under Approval | 2024-05-16 | 2024-06-24 | CD//Sofiah | 2024-06-24 | CelcomDigi_RAN_GCI_TSS_Central_20231113 | DU00002764578 |  |  | 2024-07-21 | 2024-07-09 |  | Portables BTS | BOOM | IBC | Add R8862A S9000 x4+R8862A S2100 x4+R8862A S2601 x4,Dismantle
3824C_IBC | Plaza Arkadia | Central |  | Modernization |  | 2024 Q1 | MA | GTSB | 4.6 TSSR Approved |  | 2023-09-21 | 2023-09-25 |  | 2023-12-07 |  | Closed | 2023-10-23 | 2024-05-13 | E//Nazrul | 2024-05-13 | CelcomDigi_RAN_GTSB_TSS_Central_20230922 | DU00002764579 |  |  | 2024-05-24 | 2023-12-13 |  |  | IBC + Rooftop |  | Add R8894E M1821 x5+R8862A S2601 x2,Dismantle R8862A S2100(A6A) x3
7828A_IBC | Servay Hypermarket Penampang | Sabah |  | Modernization |  | 2024 Q1 | AD | Futong | 4.6 TSSR Approved |  | 2023-09-27 | 2023-09-29 |  | 2023-10-03 |  | Closed | 2023-10-04 | 2023-10-27 | E//Nazrul | 2023-10-05 | Celcom Digi_RAN-Futong-TSS-Sabah-20230930 | DU00002764580 |  |  | 2023-10-16 | 2023-10-10 |  | Portables BTS | IBS + 4m RT (Wall Mounted Pole) |  | Add R8862A S1800 x1,Dismantle R8882-GUL1812 x1
Q00732_IBC | Q139A_Q00732OD_BOULEVARDKCH | Sarawak |  | Decomm |  | 2024 Q1 | SH | South Pacific | 4.6 TSSR Approved |  | 2023-11-14 |  |  |  | 2023-11-16 |  | 2023-11-16 | 2023-12-08 | CD//John | 2023-11-16 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20231119 | DU00002764581 |  |  |  |  | 2025-10-09 |  | LAMP_POLE
Q00079_IBC | Q124A_Q00079OD_MARGHERITA | Sarawak | 9379K | Swap |  | 2024 Q1 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-10-07 | 2023-10-27 |  | 2023-12-27 |  | Closed | 2024-01-24 | 2024-02-28 | CD//John | 2024-02-28 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231009 | DU00002764582 |  |  | 2024-05-03 | 2024-04-29 |  | Portables BTS | BOOM |  | Add R8862A S2100 x3+R8862A S1800 x3,Dismantle
S01351_IBC | S093B_S01351OD_WATERFRONTKKSC | Sabah | 7069K | Decomm |  | 2024 Q2 | AD | Futong | 4.6 TSSR Approved |  | 2023-11-17 |  |  |  | 2023-11-17 |  | 2023-11-21 | 2024-02-09 | CD//Mohidi Jaan | 2023-11-22 | Celcom Digi_RAN-Futong-TSS-Sabah-20231119 | DU00002764583 |  |  |  |  | 2024-07-15 |  | INBUILDING
S00065_IBC | RL10097_KKPLAZA | Sabah |  | Decomm | Decomm->On hold->Decomm | 2024 Q2 | MS | NR services | 4.6 TSSR Approved |  | 2024-03-26 |  |  | 2024-03-27 |  | Under Approval | 2024-03-28 | 2024-04-24 | CD//Mohidi Jaan | 2024-03-28 | Celcom Digi_RAN-NR Services-TSS-Sabah-20240329 | DU00002764584 |  |  |  |  | 2024-05-06 |  | BOOM
9808A_IBC | Riverside Complex | Sarawak |  | Modernization | Modernization->On hold->Modernization | 2024 Q1 | ZB | AllStar | 4.6 TSSR Approved |  | 2023-09-28 | 2023-10-03 |  | 2023-10-10 |  | Closed | 2024-03-25 | 2024-03-25 |  | 2024-03-25 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230930 | DU00002764585 |  |  | 2024-04-27 | 2024-04-20 |  |  | IBS + RT (Boom) |  | Add R8894E M1821 x1,Dismantle R8882-GUL1812 x1+R8862A S2100(A6A) x1
7840A_IBC | City Mall | Sabah |  | Modernization |  | 2024 Q2 | AD | Futong | 4.6 TSSR Approved |  | 2023-10-05 | 2023-10-10 |  | 2023-10-14 |  | Closed | 2023-10-16 | 2023-10-27 | E//Nazrul | 2023-10-18 | Celcom Digi_RAN-Futong-TSS-Sabah-20231006 | DU00002764586 |  |  | 2024-02-28 | 2024-02-23 |  | Portables BTS | IBS + 3m RT (Boom) |  | Add R8862A S2100 x2+R8862A S1800 x1,Dismantle R8882 S1800(B) x1 | 0 | 0
2087A_IBC | Cineleisure Mutiara Dsara IB | Central |  | Site Out (Modernization) | Modernization->On hold->Site Out->Site Out (Modernization) | 2024 Q2 |  | YPTT | [SiteOut]- 1.0 Pending Survey - Subcon | [6 empty] | To be Submitted |  |  |  |  | SQ202506140184 | DU00002764587 | [6 empty] | 6m RT (Boom) + IBS
W00100_IBC | W066L_W00100OD_SOGO | Central | 1220K | Decomm |  | 2024 Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-02-23 |  |  |  | 2024-02-27 |  | 2024-02-28 | 2024-04-24 | CD//Sapian | 2024-03-06 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240225 | DU00002764588 |  |  |  |  | 2024-11-28 |  | SHARING STRC MAXIS
7808A_IBC | Karamunsing Complex | Sabah |  | Modernization | Modernization->On hold->Modernization | 2024 Q2 | AD | Futong | 4.6 TSSR Approved |  | 2023-10-06 | 2023-10-09 |  | 2023-10-13 |  | Closed | 2024-04-03 | 2024-04-04 | E//Nazrul | 2024-04-04 | Celcom Digi_RAN-Futong-TSS-Sabah-20231009 | DU00002764589 |  |  | 2024-04-22 | 2024-04-17 |  | Portables BTS | IBS + RT (Boom) |  | Add R8894E M1821 x3+R8862A S2601 x3,Dismantle R8862A S1800(B6A) x2+R8862A S2100(A6A) x2 | 0 | 0
4640A_IBC | SP Plaza | Northern |  | Modernization | Modernization->On hold->Modernization | 2024 Q1 | WP | GTSB | 4.6 TSSR Approved |  | 2023-09-13 | 2023-09-25 |  | 2023-10-02 |  | Closed | 2023-10-04 | 2023-10-09 | E//Nazrul | 2023-10-13 | Celcom Digi_RAN-GTSB-TSS-Northern-20230914-0037 | DU00002764590 |  |  | 2024-02-05 | 2024-02-01 |  | Portables BTS | IBS + RT (Boom) |  | Add R8862A S2100 x1+R8862A S1800 x1,Dismantle R8882-GUL1812 x1 | 0 | 0
S00050_IBC | S093B_S00050OD_PACIFICSUTERA | Sabah |  | Decomm | Decomm->On hold->Decomm | 2024 Q2 | AD | NR services | 4.6 TSSR Approved |  | 2024-03-29 |  |  |  | 2024-03-29 |  | 2024-03-29 | 2024-05-14 | CD//Mohidi Jaan | 2024-04-04 | Celcom Digi_RAN-NR Services-Standard PR TSS-Sabah-20240406 | DU00002764591 |  |  |  |  | 2024-06-14 |  | TOWER
4515C_IBC | First Solar Kulim Hi-Tech | Northern |  | Modernization |  | 2024 Q1 |  | GTSB | 4.6 TSSR Approved |  | 2024-01-04 | 2024-01-05 |  | 2024-01-08 |  | Rectificating | 2024-01-10 | 2024-01-11 |  | 2024-01-10 | Celcom Digi_RAN-GTSB-TSS-Northern-20240108-0083 | DU00002764592 |  |  | 2024-03-25 | 2024-03-21 |  | Portables BTS | IBS + RT (Boom) |  | Add R8862A S2100 x2+R8862A S2601 x2+R8862A S1800 x2,Dismantle R8882-GUL1812 x2++R8881 S2100 x2+
W00196_IBC | W066W_W00196OD_RHB1 | Central |  | Decomm | Decomm->On hold->Decomm | 2024 Q2 | SS | AllStar | 4.6 TSSR Approved |  | 2023-12-15 |  |  |  | 2024-01-03 |  | 2024-01-09 | 2024-02-15 | CD//Sapian | 2024-01-11 | BOQ CelcomDigi_RAN_AllStar_Standard PR TSS_Central_20240108 | DU00002764593 |  |  |  |  | 2024-08-26 |  | BOOM
W00031_IBC | W066L_W00031OD_SEMUAHOUSEOD | Central | 1228K | Swap |  | 2024 Q2 | SS | Magicell | 4.6 TSSR Approved |  | 2023-09-27 | 2023-09-29 |  | 2023-10-03 |  | Closed | 2024-05-06 | 2024-07-12 | CD//Sofiah | 2024-07-12 | CelcomDigi_RAN_Magicell_TSS_Central_20231003 | DU00002764594 |  |  | 2024-09-25 | 2024-09-13 |  | Portables BTS | BOOM |  | Add R8862A S9000 x1+R8862A S2100 x1,Dismantle
W00363_IBC | W066D_W00363OD_KOMPLEKSMUTIARA | Central | 1223K | Decomm | Decomm->On hold->Decomm | 2024 Q1 | SY1 | YPTT | 4.6 TSSR Approved |  | 2024-06-05 |  |  |  | 2024-06-14 |  | 2024-06-19 | 2025-01-14 | CD//Sofiah | 2024-12-16 | 0607Central-YPTT-BOQ Template | DU00002764595 |  |  |  |  | 2024-08-27 |  | BOOM
W00379_IBC | W066F_W00379OD_MENARAHPDSARAOD | Central | 1229K | Swap |  | 2024 Q2 | AI | Datasco | 4.6 TSSR Approved |  | 2024-01-30 | 2024-02-01 |  | 2024-02-20 |  | Under Approval | 2024-07-03 | 2024-07-15 | CD//Sofiah | 2024-07-15 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240202 | DU00002764596 |  |  | 2024-07-24 | 2024-06-29 |  | In-Building System | IN-BUILDING | IBC | Add R8862A S2100 x2+R8862A S2601 x2+R8862A S1800 x2,Dismantle
S00051_IBC | S093E_S00051OD_HYATT | Sabah |  | Decomm | Decomm->On hold->Decomm | 2024 Q2 | AD | Futong | 4.6 TSSR Approved |  | 2024-05-10 |  |  |  | 2024-05-10 |  | 2024-05-15 | 2024-06-28 | CD//Mohidi Jaan | 2024-05-29 | CelcomDigi_RAN_Futong_TSS_Sabah_20240513 | DU00002764597 |  |  |  |  | 2024-06-12 |  | BOOM
B00705_IBC | B061I_B00705OD_SUMMITUSJ | Central |  | Decomm |  | 2024 Q1_496 | CR | Datasco | 4.6 TSSR Approved |  | 2023-11-21 |  |  |  | 2024-04-03 |  | 2024-04-04 | 2024-04-24 | CD//Sofiah | 2024-04-05 | CelcomDigi_RAN_Datasco_TSS_Central_20231213 | DU00002764598 |  |  |  |  | 2025-03-13 |  | BOOM
W00462_IBC | W066F_W00462OD_AMANAHRAYAOD | Central | 1230K | Swap |  | 2024 Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2024-03-01 | 2024-03-15 |  | 2024-05-03 |  | Closed | 2024-05-06 | 2024-07-10 | CD//Sofiah | 2024-07-10 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240303 | DU00002764599 |  |  | 2024-07-01 | 2024-06-30 |  | Portables BTS | BOOM |  | Add R8862A S9000 x1+R8862A S2100 x1,Dismantle
7822A_IBC | Promenade Hotel | Sabah |  | Modernization | Modernization->On hold->Modernization | 2024 Q2 | AD | Futong | 4.6 TSSR Approved |  | 2023-10-04 | 2023-11-06 |  | 2023-12-05 |  | Closed | 2024-04-02 | 2024-04-03 | E//Nazrul | 2024-04-03 | Celcom Digi_RAN-Futong-TSS-Sabah-20231006 | DU00002764600 |  |  | 2024-04-22 | 2024-04-17 |  | Portables BTS | IBS + 2m RT (Boom) |  | Add R8894E M1821 x1,Dismantle R8882-GUL1812 x1+R8862A S2100(A6A) x1 | 0 | 0
7827A_IBC | Servay Hypermarket Likas | Sabah |  | Modernization | Modernization->On hold->Modernization | 2024 Q2 | AD | Futong | 4.6 TSSR Approved |  | 2024-04-05 | 2024-04-22 |  | 2024-04-08 |  | Closed | 2024-04-24 | 2024-05-10 | E//Hannah | 2024-05-10 | Celcom Digi_RAN-Futong-Standard PR TSS-Sabah-20240406 | DU00002764601 |  |  | 2024-04-30 | 2024-04-15 |  | Portables BTS | IBS + 9m RT (Boom) |  | Add R8894E M1821 x1,Dismantle R8882-GUL1812 x1+R8862A S2100(A6A) x1
S00960_IBC | S101A_S00960OD_SERVAYPENAMPANG | Sabah |  | Decomm |  | 2024 Q1 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2023-10-30 |  |  |  | 2023-11-16 |  | 2023-11-17 | 2024-02-09 | CD//Mohidi Jaan | 2023-11-20 | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231101 | DU00002764602 |  |  |  |  | 2024-01-25 |  | BOOM
S00055_IBC | S093B_S00055OD_CPSCOMPLEX | Sabah |  | Decomm | Decomm->On hold->Decomm | 2024 Q2 | MS | NR services | 4.6 TSSR Approved |  | 2023-12-28 |  |  |  | 2024-01-02 |  | 2024-01-02 | 2024-03-21 | CD//Mohidi Jaan | 2024-01-02 | Celcom Digi_RAN-NR Services-TSS-Sabah-20231231 | DU00002764603 |  |  |  |  | 2024-08-15 |  | BOOM
2872B_IBC | Jaya Jusco Kepong | Central |  | Modernization | Modernization->On hold->Modernization | 2024 Q1 | CR | GTSB | 4.6 TSSR Approved |  | 2023-12-21 | 2024-01-10 |  | 2024-01-16 |  | Closed | 2024-01-17 | 2024-04-18 | E//Nazrul | 2024-04-18 | CelcomDigi_RAN_GTSB_TSS_Central_20231224 | DU00002764604 |  |  | 2024-05-28 | 2024-05-27 |  | Portables BTS | 6m RT (Boom) + IBS |  | Add R8892N M1821 x1,Dismantle R8882-GUL1812 x1+R8862A S2100(A6A) x1
B00870_IBC | W066B_B00870OD_KOMPLEKDESA_KEPONG | Central | 1218K | Swap |  | 2024 Q1 | XH | GTSB | 4.6 TSSR Approved |  | 2023-11-29 | 2023-12-04 |  | 2023-12-07 |  | Closed | 2024-05-24 | 2024-05-28 | CD//Sofiah | 2024-05-28 | CelcomDigi_RAN_GTSB_TSS_Central_20231201 | DU00002764605 |  |  | 2024-04-29 | 2024-04-24 |  | Portables BTS | BOOM | NA | Add R8862A S2100 x1+R8862A S1800 x1,Dismantle
W01292_IBC | W066K_W01292IB_WISMAPERKESO | Central | 1231K | Swap |  | 2024 Q2 | AI | Datasco | 4.6 TSSR Approved |  | 2024-01-20 | 2024-02-08 |  | 2024-02-21 |  | Closed | 2024-02-23 | 2024-04-04 | CD//Sofiah | 2024-04-04 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240128 | DU00002764606 |  |  | 2024-06-22 | 2024-06-19 |  | Portables BTS | IN-BUILDING | 3 | Add R8862A S2100 x3+R8862A S2601 x3+R8862A S1800 x3,Dismantle
W01433_IBC | W066D_W01433OD_PLAZA_ARKADIA_OD | Central |  | Decomm |  | 2024 Q1 | BY | GTSB | 4.6 TSSR Approved |  | 2024-05-23 |  |  |  | 2024-06-26 |  | 2024-07-02 | 2025-01-14 | CD//Sofiah | 2024-12-31 | CelcomDigi_RAN_GTSB_TSS_Central_20240423 | DU00002764607 |  |  |  |  | 2024-08-19 |  | IN-BUILDING
Q00155_IBC | Q124D_Q00155OD_WISMASABERKAS | Sarawak |  | Decomm | Decomm->On hold->Swap->On hold->Decomm | 2024 Q1 | ZB | Magicell | 4.6 TSSR Approved |  | 2024-03-06 | 2024-06-21 |  | 2024-05-07 |  | Under Approval | 2024-09-24 | 2024-09-26 | CD//Sofiah | 2024-09-25 | 0903CD-Sarawak-Magicell-BOQ Template(new contract) | DU00002764608 |  |  |  |  | 2024-10-09 | In-Building System | BOOM
B02582_IBC | B061M_B02582OD_THOMSON_HOSPITAL_KDSARA | Central |  | Decomm | Decomm->On hold->Decomm | 2024 Q2 | AD | GTSB | 4.6 TSSR Approved |  | 2024-04-16 |  |  |  | 2024-04-18 |  | 2024-05-07 | 2024-07-12 | CD//Sapian | 2024-05-20 | CelcomDigi_RAN_GTSB_TSS_Central_20240509 | DU00002764609 |  |  |  |  | 2024-05-25 |  | WALL MOUNTED BOOM
W00392_IBC | W066N_W00392OD_TMKLTOWER | Central | 1224K | Decomm | Decomm->On hold->Decomm | 2024 Q2 | BY | Datasco | 4.6 TSSR Approved |  | 2023-10-24 | 2023-11-07 |  |  | 2024-07-02 |  | 2024-07-04 | 2026-01-21 | CD//Sofiah | 2026-03-31 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240110 | DU00002764610 |  |  |  |  | 2024-10-28 |  | BOOM
W00101_IBC | W066N_W00101OD_WISMASELDREDGOD | Central |  | Decomm | Decomm->On hold->Decomm | 2024 Q2 | SHA | GCI | 4.6 TSSR Approved |  | 2024-07-02 |  | 2024-07-04 |  | 2024-07-11 |  | 2024-07-16 |  | CD//Sofiah | 2024-07-23 | PR raised | DU00002764611 |  | Please provide photo for SOW (DISMANTLE CELCOM MICROWAVE LINK W00101_IBC-W00353) due to SOW Changed |  |  | 2024-09-06 |  | BOOM
S00053_IBC | S093B_S00053OD_PROMENADE | Sabah |  | Decomm | Decomm->On hold->Decomm | 2024 Q2 | MS | Seri Pancar | 4.6 TSSR Approved |  | 2024-04-05 |  |  |  | 2024-04-13 |  | 2024-04-17 | 2024-07-19 | CD//Mohidi Jaan | 2024-04-17 | Celcom Digi_RAN-Seri Pancar-Standard PR TSS-Sabah-20240406 | DU00002764612 |  |  |  |  | 2024-06-04 |  | BOOM
7837A_IBC | Asia City KK IB | Sabah |  | Modernization | Modernization->On hold->Modernization | 2024 Q2 | MS | Futong | 4.6 TSSR Approved |  | 2023-10-05 | 2024-04-30 |  | 2023-11-09 |  | Closed | 2024-03-05 | 2024-03-06 | E//Hannah | 2024-03-06 | Celcom Digi_RAN-Futong-TSS-Sabah-20231006 | DU00002764613 |  |  | 2024-03-22 | 2024-03-19 |  | Portables BTS | IBS + 6m RT (Boom) |  | Add R8894E M1821 x1+R8862A S2600 x1,Dismantle R8882-GUL1812 x1+R8862A S2100(A6A) x1
S00058_IBC | RL10014_KARAMUNSING | Sabah |  | Decomm | Decomm->On hold->Decomm | 2024 Q2 | MS | Seri Pancar | 4.6 TSSR Approved |  | 2024-04-05 |  |  |  | 2024-04-09 |  | 2024-04-19 | 2024-08-02 | CD//Mohidi Jaan | 2024-04-22 | Celcom Digi_RAN-Seri Pancar-Standard PR TSS-Sabah-20240406 | DU00002764614 |  |  |  |  | 2024-06-13 |  | In Building
1176A_IBC | Tropicana1 | Central |  | Modernization |  | 2024 Q2 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-11-02 | 2023-11-08 |  | 2024-01-24 |  | Closed | 2024-01-30 | 2024-01-31 | E//Nazrul | 2024-01-31 | CelcomDigi_RAN_CCSMY_TSS_Central_20231113 | DU00002764615 |  |  | 2024-03-15 | 2024-03-12 |  | Portables BTS | 6m RT (Boom) + IBS | NA | Add R8862A S2100 x1+R8862A S2601 x1+R8862A S1800 x1,Dismantle R8882-GUL1812 x1
S00464_IBC | S093F_S00464OD_CENTRALPLAZA | Sabah | 7071K | Swap |  | 2024 Q1 | MS | Futong | 4.6 TSSR Approved |  | 2023-10-10 | 2023-10-11 |  | 2023-10-12 |  | Closed | 2023-10-12 | 2023-10-27 | CD//Mohidi Jaan | 2023-10-13 | Celcom Digi_RAN-Futong-TSS-Sabah-20231013 | DU00002764616 |  |  | 2023-10-31 | 2023-10-31 |  | Portables BTS | TRIPOD |  | Add R8862A S2100 x1+R8862A S1800 x1,Dismantle
S00476_IBC | S093B_S00476OD_BEVERLYHOTEL | Sabah | 7076K | Swap |  | 2024 Q2 | MS | Futong | 4.6 TSSR Approved |  | 2023-10-10 | 2023-10-13 |  | 2023-10-16 |  | Closed | 2023-10-17 | 2023-10-18 | CD//Mohidi Jaan | 2023-10-17 | Celcom Digi_RAN-Futong-TSS-Sabah-20231013 | DU00002764617 |  |  | 2024-09-25 | 2024-04-18 |  | Portables BTS | BOOM |  | Add R8862A S2100 x2+R8862A S2601 x2+R8862A S1800 x2,Dismantle | 0 | 0
W00159_IBC | W066N_W00159OD_CONCORDHOTEL | Central |  | Decomm | Decomm->On hold->Decomm | 2024 Q2 | AI | GCI | 4.6 TSSR Approved |  | 2025-05-07 |  | 2025-05-21 | 2025-06-17 | 2025-06-17 | Rectificating | 2025-09-10 |  | CD//Sofiah | 2025-10-22 | SQ202506210248 | DU00002764618 |  |  |  |  | 2025-08-15 |  | BOOM
7801A_IBC | Centre Point | Sabah |  | Modernization |  | 2024 Q2 | MS | Futong | 4.6 TSSR Approved |  | 2023-10-09 | 2023-10-10 |  | 2023-10-13 |  | Closed | 2023-10-16 | 2023-10-18 | E//Nazrul | 2023-10-16 | Celcom Digi_RAN-Futong-TSS-Sabah-20231009 | DU00002764619 |  |  | 2024-03-12 | 2024-03-07 |  | Portables BTS | In-building system |  | Add R8862A S2100 x1+R8862A S1800 x1 | 0 | 0
K00226_IBC | K005A_K00226OD_PARKAVENUE | Northern | 4165K | Swap |  | 2024 Q1 | WP | CCSMY | 4.6 TSSR Approved |  | 2023-09-18 | 2023-10-13 |  | 2023-10-20 |  | Closed | 2023-10-24 | 2023-10-27 | CD//Rohizam | 2023-10-26 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230919-0042 | DU00002764620 |  |  | 2023-12-27 | 2023-12-18 |  | In-Building System | BOOM | NA | Add R8862A S2100 x1+R8862A S1800 x1,Dismantle
B02881_IBC | B061M_B02881OD_TROPICANAMALL_KDSARA_OD | Central | 1217K | Decomm |  | 2024 Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-19 |  |  |  | 2024-01-23 |  | 2024-01-23 | 2024-04-24 | CD//Sofiah | 2024-03-11 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240128 | DU00002764621 |  |  |  |  | 2024-05-30 |  | IN-BUILDING
W00690_IBC | W066N_W00690OD_KENANGAINTOD | Central | 1226K | Decomm | Decomm->On hold->Decomm | 2024 Q2 | HW | GCI | 4.6 TSSR Approved |  | 2024-08-23 |  | 2025-01-23 |  | 2025-03-17 |  | 2025-03-21 | 2025-10-01 | CD//Sapian | 2025-05-08 | 0821CD-GCI-Central-BOQ Template(new contract) | DU00002764622 |  |  |  |  | 2024-12-06 |  | BOOM
K00293_IBC | K005B_K00293OD_CENTRALSQUARESP | Northern | 4166K | Decomm | Decomm->On hold->Decomm | 2024 Q1 | BY | GCI | 4.6 TSSR Approved |  | 2024-06-27 |  |  |  | 2024-07-15 |  | 2024-07-17 | 2024-10-01 | CD//Sofiah | 2024-08-13 | Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240924_New Contract | DU00002764623 |  |  |  |  | 2024-08-14 |  | BOOM
S00067_IBC | S093B_S00067OD_BERJAYAPALACE | Sabah | 7068K | Swap |  | 2024 Q2 | MS | Futong | 4.6 TSSR Approved |  | 2023-10-13 | 2023-10-16 |  | 2023-10-19 |  | Closed | 2023-10-24 | 2023-10-25 | CD//Mohidi Jaan | 2023-10-19 | Celcom Digi_RAN-Futong-TSS-Sabah-20231016 | DU00002764624 |  |  | 2024-05-03 | 2024-04-15 |  | Portables BTS | IN-BUILDING |  | Add R8862A S2100 x1+R8862A S1800 x1,Dismantle | 0 | 0
S00076_IBC | S093B_S00076OD_WISMAMUIS | Sabah | 7070K | Swap |  | 2024 Q2 | MS | Futong | 4.6 TSSR Approved |  | 2023-10-11 | 2023-10-12 |  | 2023-10-16 |  | Closed | 2023-12-11 | 2023-12-12 | CD//Mohidi Jaan | 2023-12-11 | Celcom Digi_RAN-Futong-TSS-Sabah-20231013 | DU00002764625 |  |  | 2024-05-02 | 2024-04-18 |  | Portables BTS | BOOM |  | Add R8862A S9000 x3+R8862A S2100 x3+R8862A S2601 x3,Dismantle | 0 | 0
9846A_IBC | Boulevard Kuching IB | Sarawak |  | Modernization |  | 2024 Q1 | ZB | South Pacific | 4.6 TSSR Approved |  | 2023-09-27 | 2023-10-12 |  | 2023-10-24 |  | Closed | 2023-12-27 | 2023-10-30 |  | 2023-10-30 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20231009 | DU00002764626 |  | 2510 Missing photo cable route Missing Photo rectifier full view , battery full view for Rectifier 1 and 2 Missing AC Power voltage and Current data, please attached photo as well Wrong slot for VBe3p, and make a remarks "+VBPe3p (if can resue Macro site v9200)" Existing antenna Schematic using hybrid coupler or Splitter? please check S1, S2, S3 and S4. Please redo your existing and proposal schematic Missing photo triplexer Sector 4 Radio proposal not following from RF parameter file, please check for all sector page CPRI, Power cable, jumper proposal missing in every sector page | 2024-03-18 | 2024-03-01 |  | Portables BTS | In-building system |  | Add R8862A S2100 x3+R8862A S1800 x3,Dismantle R8882-GUL1812 x3 | 0 | 0
7809A_IBC | Plaza Wawasan | Sabah |  | Modernization | Modernization->On hold->Modernization | 2024 Q2 | MS | Futong | 4.6 TSSR Approved |  | 2023-10-09 | 2023-10-10 |  | 2023-10-13 |  | Closed | 2024-03-05 | 2024-03-06 | E//Hannah | 2024-03-05 | Celcom Digi_RAN-Futong-TSS-Sabah-20231009 | DU00002764627 |  |  | 2024-03-22 | 2024-03-14 |  | Portables BTS | IBS + RT (Boom) |  | Add R8894E M1821 x1+R8862A S2601 x1,Dismantle R8882-GUL1812 x1+R8862A S2100(A6A) x1
S00044_IBC | S093C_S00044OD_SURVEYLIKAS | Sabah |  | Decomm | Decomm->On hold->Decomm | 2024 Q2 | AD | Futong | 4.6 TSSR Approved |  | 2024-04-05 |  |  |  | 2024-04-08 |  | 2024-04-08 | 2024-07-12 | CD//Mohidi Jaan | 2024-04-15 | Celcom Digi_RAN-Futong-Standard PR TSS-Sabah-20240406 | DU00002764628 |  |  |  |  | 2024-06-21 |  | IN-BUILDING
W00219_IBC | W066N_W00219OD_JLNPRAMLEE | Central | 1222K | Decomm | Decomm->On hold->Decomm | 2024 Q2 | BY | Datasco | 4.6 TSSR Approved |  | 2024-07-15 |  | 2024-07-19 |  | 2024-07-19 |  | 2024-07-22 | 2024-12-09 | CD//Sofiah | 2024-08-19 | 0719Central-Datasco-BOQ Template | DU00002764629 |  |  |  |  | 2024-09-21 |  | BOOM
7812A_IBC | Magellan Sutera Harbour | Sabah |  | Modernization | Modernization->On hold->Modernization | 2024 Q2 | MS | Futong | 4.6 TSSR Approved |  | 2023-10-05 | 2023-10-06 |  | 2023-10-10 |  | Closed | 2024-03-05 | 2024-03-06 | E//Hannah | 2024-03-05 | Celcom Digi_RAN-Futong-TSS-Sabah-20231006 | DU00002764630 |  |  | 2024-03-14 | 2024-03-07 |  | Portables BTS | IBS + 2m RT (Boom) |  | Add R8894E M1821 x2,Dismantle R8882-GUL1812 x2+R8862A S2100(A6A) x2
9421A | Krokong | Sarawak |  | Decomm |  | 2024 Q2 |  | Magicell | 4.6 TSSR Approved |  | 2025-11-13 |  |  |  |  | To be Submitted | 2025-08-12 |  |  | 2025-09-09 | SQ202511130094 - Magicell | DU00005746242 |  |  |  |  | 2025-07-04 |  | #N/A
1138A | Kanchung Laut | Central |  | Modernization |  | 2023Q2 | IE | Magicell | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-10 |  | 2023-05-12 |  | Closed | 2023-05-19 | 2023-06-03 | E//Kok Keen | 2023-05-23 | CelcomDigi_RAN_Magicell_TSS_Central_20230428_0005 | DU00002008063 |  |  | 2023-06-03 | 2023-06-02 |  | Tower | 45m 4 Legged Tower | 45M | Add R8862A S9000 x3 + R8894E M1821 x3,Dismantle R8882-GUL1812 x1+R8882 S1800B(B6B) x3+R8862A S1800(B6A) x1+R8840-U216 x3
1004Z | PULAU INDAH SEL | Central |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q2 | IE | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008064 | [6 empty] | Land site
4174H | 99 Speedmart PK KG MANJOI | Northern |  | MOCN As-Is |  | 2023Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008065 | [6 empty] | Small Cell
1936B | Sijangkang Batu 9 (Celcom) | Central |  | Modernization |  | 2023Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-15 |  | 2023-04-17 |  | Closed | 2023-05-03 | 2023-06-03 | CD//Tee | 2023-05-11 | CelcomDigi_RAN_AllStar_TSS_Central_20230404_0005 / CelcomDigi_RAN_Allstar_TSS_Central_20230721_ClearLoan | DU00002008066 |  |  | 2023-05-26 | 2023-05-17 |  |  | Tower | 60 | Add A9732 M1821 x3 + R9264M M1821 x1,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x5+R9224E M1821(AAB) x1 | 134
1789A | Tmn Sri Berembang | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-11 | 2023-04-14 |  | 2023-04-17 |  | Closed | 2023-04-20 | 2023-05-21 | CD//Norhaliza | 2023-05-12 | CelcomDigi_RAN_Datasco_TSS_Central_20230413_0011 | DU00002008067 |  |  | 2023-05-24 | 2023-05-23 |  | Unipole | 6m Tripod (RT) | 6 | Add R9264H M901821 x2 + R9264M M1821 x4,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x2 |  | 123
1648B11 | pBTS Menggatal Town 2 | Sabah |  | Modernization |  | 2023Q2 | HQ 8 | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-11 |  | 2023-04-14 |  | Closed | 2023-04-18 | 2023-04-24 | CD//Mohidi Jaan | 2023-04-18 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002008068 |  |  | 2023-05-27 | 2023-05-25 |  |  | 25m pBTS | 24m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
2936A | Lorong Kapor Pandamaran | Central |  | Modernization |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-04-28 | 2023-05-06 |  | 2023-05-11 |  | Closed | 2023-05-11 | 2023-06-05 | CD//Syafiq | 2023-05-18 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230428_0015 | DU00002008069 |  |  | 2023-06-16 | 2023-06-14 |  | Minaret | 3m Boom (RT) | 2 | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 |  | 2
2642B | Kg Sg Udang | Central |  | Modernization |  | 2023Q3 | HQ 6 | Futong | 4.6 TSSR Approved |  | 2023-05-29 | 2023-05-29 |  | 2023-06-02 |  | Closed | 2023-06-05 | 2023-06-19 | CD//Nik Ashraf | 2023-06-19 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002008070 |  |  | 2023-06-24 | 2023-06-22 |  | Lampole | 30m Monopole | 20 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x3+R9224E M1821(AAB) x2 | 23
1205B | Jln Kg Delek 2 | Central |  | Modernization |  | 2023Q3 | SS | Futong | 4.6 TSSR Approved |  | 2023-05-24 | 2023-05-29 |  | 2023-06-02 |  | Closed | 2023-06-20 | 2023-06-28 | E//Razif | 2023-06-28 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002008071 |  |  | 2023-07-15 | 2023-06-28 |  | Tower | 60m 4 Legged Tower | 62 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
3295A1 | pBTS Kg Telok Gong (M) | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI,L2600 change to 40M¦3295A1 is a pBTS site,can not install AAU on site | 2023-04-12 | 2023-04-10 |  | 2023-04-12 |  | Closed | 2023-04-14 | 2023-07-12 | E//Razif | 2023-07-11 | CelcomDigi_RAN_Datasco_TSS_Central_20230413_0011 / CelcomDigi_RAN_Datasco_TSS_Central_20230721_ClearLoan | DU00002008072 | NIC_S2_Change MM to BI,L2600 change to 40M_loading issue_Digi OB |  | 2023-07-04 | 2023-05-15 |  | Guide mast | 25m pBTS | 31 | Add R9264M M1821 x2+R9264H M901821 x3+R8862A S2601 x1,Dismantle R8894E M1821(A8A) x4 |  | 12
1078A | Aik Hin Hardware | Central |  | Modernization |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-04-08 | 2023-05-06 |  | 2023-05-09 |  | Closed | 2023-05-09 | 2023-05-27 | E//Razif | 2023-05-26 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230410_0010 | DU00002008073 |  |  | 2023-05-26 | 2023-05-22 |  | Pole | 45m 3 Legged Tower | 6m | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x6 | 123
3333B | Jalan Sungai (REL) | Central |  | Decomm | Modernization->Decomm | 2023Q3 | MA | Futong | 4.6 TSSR Approved |  | 2023-10-02 | 2023-06-02 |  | 2023-06-08 | 2023-10-09 | Closed | 2023-10-10 |  | xD Site (MSP) | 2024-02-27 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002008074 |  | Pending TX part SOW Details (5 Sept- Found that anchor has change to B02822 Dismantle Digi Microwave 3333B-2646A) |  |  | 2023-11-17 | Lampole | 18m Lampole | 25
3515A7 | pBTS Industrial Port Klang (C) | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-10 |  | 2023-04-12 |  | Closed | 2023-04-15 | 2023-05-05 | CD//Sapian | 2023-05-03 | CelcomDigi_RAN_Datasco_TSS_Central_20230413_0011 | DU00002008075 |  |  | 2023-05-14 | 2023-05-10 |  | Tower | 25m pBTS | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1114A | Jln Tepi Sungai | Central |  | Modernization |  | 2023Q3 | HQ 6 | Futong | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-13 |  | 2023-05-16 |  | Closed | 2023-05-18 | 2023-06-27 | E//Razif | 2023-06-20 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002008076 |  |  | 2023-06-17 | 2023-06-13 |  | Pole | 6m Tripod (RT) | 7 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
1649H | 99 Speedmart TMN SERI DAGANG | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008077 | [6 empty] | Small Cell
1786A | Kop. Kopema Bhdh | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-11 | 2023-04-12 |  | 2023-04-13 |  | Closed | 2023-04-14 | 2023-05-25 | CD//Syafiq | 2023-05-02 | CelcomDigi_RAN_Datasco_TSS_Central_20230412_0010 | DU00002008078 |  |  | 2023-05-24 | 2023-05-22 |  | Pole | 6m Tripod (RT) | 7 | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x4 |  | 2
3366B | Giant Hypermarket Banting Outdoor | Central |  | Modernization |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-05 |  |  | 2023-04-15 |  | Closed | 2023-05-08 | 2023-06-06 | E//Razif | 2023-05-26 | CelcomDigi_RAN_GTSB_Central_20230406_0011 | DU00002008079 |  |  | 2023-06-22 | 2023-06-19 |  | Tower | 45m 3 Legged Tower | 46m | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 1
1104A | Surau Al-Amin | Central |  | Modernization |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-05-04 | 2023-05-17 |  | 2023-05-20 |  | Closed | 2023-05-20 | 2023-06-13 | E//Razif | 2023-06-13 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230505_0016 | DU00002008080 |  |  | 2023-06-10 | 2023-06-08 |  | Monopole | 30m Monopole | 46 | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8882-GUL1812 x5+R8862A S2100(A6A) x5 |  | 1
1987A | Tmn Bayu Perdana | Central |  | Modernization |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-04-05 |  |  | 2023-04-14 |  | Closed | 2023-04-15 | 2023-05-25 | CD//Syafiq | 2023-05-02 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230406_0008 | DU00002008081 |  |  | 2023-05-26 | 2023-05-22 |  | Pole | 3m Bipod (RT) | 6m | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8862A S2600(A4A) x1+R8894E M1821(A8A) x4 | 23
3971B | Taman Seri Jaromas | Central |  | Modernization |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-04 | 2023-04-13 |  | 2023-04-12 |  | Closed | 2023-04-15 | 2023-06-03 | CD//Sapian | 2023-05-11 | CelcomDigi_RAN_GTSB_TSS_Central_20230405_0010 | DU00002008082 |  |  | 2023-05-09 | 2023-05-09 |  | H-bracket pole | 3m Bipod (RT) | 6m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1644B | Berkeley 2 | Central |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-05-06 | 2023-05-11 |  | 2023-05-15 |  | Closed | 2023-05-18 | 2023-07-24 | E//Razif | 2023-07-24 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002008083 |  |  | 2023-06-16 | 2023-06-13 |  | H-bracket pole | 3m Boom (RT) | N/A | Add R9264H M901821 x1 + R9264M M1821 x4,Dismantle R8862A S1800(B6A) x7+R8862A S2100(A6A) x1+R8854D S2100(A4A) x3 |  | 3
3114A | Indah Residence | Central |  | Modernization |  | 2023Q3 | HQ 1 | Futong | 4.6 TSSR Approved |  | 2023-05-18 | 2023-06-02 |  | 2023-06-08 |  | Closed | 2023-06-10 | 2023-06-21 | CD//Nik Ashraf | 2023-06-21 | CelcomDigi_RANMW_Futong_TSS_Central_20230508_0001 | DU00002008084 |  |  | 2023-08-17 | 2023-08-16 |  | Pole | 3m Boom (RT) | 6.2m | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
2725C | Teluk Mengkuang (REL) | Central |  | Modernization |  | 2023Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-14 |  | 2023-04-16 |  | Closed | 2023-04-18 | 2023-06-03 | CD//Syafiq | 2023-04-19 | CelcomDigi_RAN_AllStar_TSS_Central_20230404_0005 / CelcomDigi_RAN_Allstar_TSS_Central_20230721_ClearLoan | DU00002008085 |  |  | 2023-05-26 | 2023-05-26 |  | Tower | Land site | 45 | Add R9264H M901821 x3,Dismantle R9224E M1821(AAB) x3
2688B | Jln Bkt Kemuning | Central |  | Modernization |  | 2023Q3 | SS | Futong | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-16 |  | 2023-05-19 |  | Closed | 2023-05-23 | 2023-06-24 | CD//Norhaliza | 2023-06-23 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002008086 |  |  | 2023-07-05 | 2023-06-28 |  | Wall mount boom | 3m Bipod (RT) | 4 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882-GUL1812 x3
4118B | Bagan Lalang RT | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-20 |  | 2023-05-27 |  | Closed | 2023-06-01 | 2023-06-08 | E//Hazida | 2023-06-09 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0016 | DU00002008087 |  |  | 2023-06-16 | 2023-06-15 |  | Lampole | 3m Boom (RT) | 8M | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8882-GUL1812 x3+R8882 S1800B(B6B) x3+R8840-U216 x3 |  | 1
1582B8 | pBTS Kaw Perindustrian TPG | Central |  | Modernization |  | 2023Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-18 |  | 2023-04-19 |  | Closed | 2023-04-27 | 2023-06-03 | CD//Sapian | 2023-05-04 | CelcomDigi_RAN_AllStar_TSS_Central_20230404_0005 / CelcomDigi_RAN_Allstar_TSS_Central_20230721_ClearLoan | DU00002008088 |  |  | 2023-05-14 | 2023-05-09 |  | Minimast | 25m pBTS | 30 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3
1610B | Kampung Delek(ZED) | Central |  | Modernization |  | 2023Q3 | HQ 6 | Futong | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-17 |  | 2023-05-22 |  | Closed | 2023-05-23 | 2023-06-13 | E//Razif | 2023-06-13 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002008089 |  |  | 2023-06-23 | 2023-06-22 |  | Tower | 45m 3 Legged Tower | 48 | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x2+R8854 S2600(A4A) x2 | 12
1084A | Bt 5 3 | Central |  | Modernization |  | 2023Q3 | YZ | CCSMY | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-16 |  | 2023-05-19 |  | Closed | 2023-05-20 | 2023-07-12 | E//Razif | 2023-07-12 | CelcomDigi_RAN_CCSMY_TSS_Central_20230428_0001 | DU00002008090 |  |  | 2023-07-05 | 2023-06-28 |  | Monopole | 30m Monopole | 45m | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x4 | 123
1595H | 99 Speedmart TAMAN MELAVIS | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008091 | [6 empty] | Small Cell
3412B | Dewan Grace | Central |  | Modernization |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-13 |  | 2023-04-14 |  | Closed | 2023-04-15 | 2023-05-22 | CD//Norhaliza | 2023-08-18 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230413_0011 | DU00002008092 |  |  | 2023-05-11 | 2023-05-11 |  | Wall mount boom | 3m Bipod (RT) | 3m | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8881 S2100 x3
1121A | Bkt Changgang | Central |  | Modernization |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-05 | 2023-04-10 |  | 2023-04-13 |  | Closed | 2023-04-14 | 2023-06-17 | CD//Tee | 2023-06-15 | CelcomDigi_RAN_GTSB_Central_20230406_0011 | DU00002008093 |  |  | 2023-05-12 | 2023-05-10 |  | Monopole | 30m Monopole | 45m | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x3 | 23
3440B8 | pBTS Angkasa Apartment (C) | Sabah |  | Modernization | Modernization->On Hold->Modernization->Site Out->Modernization | 2023Q2 | HQ 7 | Futong | 4.6 TSSR Approved | TI issue. Single phase power issue (Meter Application WIP) | 2023-04-08 | 2023-04-25 |  | 2023-04-28 |  | Closed | 2023-05-03 | 2023-05-25 | CD//Mohidi Jaan | 2026-04-17 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002008094 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed | 2025-11-25 | 2025-11-21 |  |  | 25m pBTS | 24 | Add R8854E S1800x4, Dismantle R8882 S1800B(B6B)x3+R8862A S1800(B6A)x1 | 0 | 0
2722B | Surau Baitul Ukhrawi | Central |  | Modernization |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-14 |  | 2023-04-17 |  | Closed | 2023-04-17 | 2023-05-22 | CD//Norhaliza | 2023-08-18 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230410_0010 | DU00002008095 |  |  | 2023-05-12 | 2023-05-11 |  | Lampole | 24m Lampole | 24m | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
1497H | 99 Speedmart TMN CEMPAKA BANTING | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008096 | [6 empty] | Small Cell
2078B | Jalan Haji Sirat (Celcom) (REL) | Central |  | Modernization |  | 2023Q3 | HQ 6 | Datasco | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-11 |  | 2023-05-13 |  | Closed | 2023-05-16 | 2023-07-31 | E//Razif | 2023-07-31 | CelcomDigi_RANMW_Datasco_TSS_Central_20230505_0002 | DU00002008097 |  |  | 2023-07-17 | 2023-07-17 |  | Tower | Tower | 50 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
4170A | Puspakom Mak Mandin | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-19 |  | 2023-05-23 |  | Closed | 2023-05-25 | 2023-06-10 | E//Hazida | 2023-06-10 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0016 | DU00002008098 |  |  | 2023-06-20 | 2023-06-19 |  | BillBoard | 45m Monopole | 27 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
1425H | 99 Speedmart BDR BOTANIK 2 | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008099 | [6 empty] | Small Cell
1633H | 99 Speedmart Sg Jati | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008100 | [6 empty] | Small Cell
1126A | Sijangkang | Central |  | Modernization |  | 2023Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2023-04-03 | 2023-05-05 |  | 2023-05-08 |  | Closed | 2023-05-09 | 2023-05-27 | E//Razif | 2023-05-26 | CelcomDigi_RAN_AllStar_TSS_Central_20230404_0005 / CelcomDigi_RAN_Allstar_TSS_Central_20230721_ClearLoan | DU00002008101 |  |  | 2023-05-19 | 2023-05-17 |  | Monopole | 30m Monopole | 30M | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
4166A | Pearl View Hotel | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-15 |  | 2023-05-18 |  | Closed | 2023-05-22 | 2023-06-27 | E//Hazida | 2023-06-27 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0016 | DU00002008102 |  |  | 2023-06-24 | 2023-06-24 |  |  | 3m Boom (RT) |  | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
1150E | Westport T2 (CT 4-1) | Central |  | Remote MOCN | Modernization->Remote MOCN | 2026 | AI | GTSB | 4.6 TSSR Approved |  | 2025-05-26 | 2025-05-23 |  | 2025-05-27 |  | Under Approval | 2025-05-27 | 2025-05-27 | E//Razif | 2025-05-27 | CelcomDigi_RAN_Datasco_TSS_Central_20230428_0018 | DU00002008103 | [5 empty] | Tower | Lampole | 30m | Reuse Existing RRU | 0 | 0
1573B2 | pBTS Klang Perdana | Central |  | Modernization | Modernization->Site Out->Modernization | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-26 | 2023-04-29 |  | 2023-05-05 |  | Closed | 2023-05-07 | 2023-07-07 | E//Razif | 2023-07-07 | CelcomDigi_RAN_Datasco_TSS_Central_20230428_0018 | DU00002008104 |  |  | 2023-07-03 | 2023-06-28 |  | Tower | 25m pBTS | 32 | Add R9264H M901821 x2 + R9264M M1821 x2,Dismantle R8894E M1821(A8A) x4 |  | 1
1619H | 99 Speedmart Bdr Parklands 2 | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008105 | [6 empty] | Small Cell
2665C | Westport Tower IB | Central |  | Modernization | Modernization->Remote MOCN->Modernization | 2026 | AI | GTSB | 4.6 TSSR Approved |  | 2025-05-27 | 2025-06-06 |  | 2025-06-11 |  | Closed | 2025-06-16 | 2025-07-25 | E//Nazrul | 2025-06-23 | CelcomDigi_RAN_Datasco_TSS_Central_20230428_0018 | DU00002008106 |  |  | 2026-01-26 | 2026-01-26 |  | Portables BTS | Lampole |  | Add R9224E M1821x3+R8862A S2600x3, Dismantle R8862A S1800 x3+R8862A S2100 x3
2638B | Sg Kapar Indah Industrial | Central |  | Modernization |  | 2023Q3 | AI | CCSMY | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-13 |  | 2023-05-16 |  | Closed | 2023-05-16 | 2023-07-13 | E//Razif | 2023-07-12 | CelcomDigi_RANMW_CCSMY_TSS_Central_20230508_0001 | DU00002008107 |  |  | 2023-06-28 | 2023-06-27 |  | Lampole | 24m Lampole | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1485H | 99 Speedmart JLN MERU 2 | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008108 | [6 empty] | Small Cell
2724B | Jln Seruling Tmn Klang Jaya | Central |  | Modernization |  | 2023Q3 | XH | Ascentrack | 4.6 TSSR Approved |  | 2023-05-16 | 2023-05-18 |  | 2023-05-20 |  | Closed | 2023-05-20 | 2023-06-13 | E//Razif | 2023-06-13 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230517_0019 | DU00002008109 |  |  | 2023-06-19 | 2023-06-19 |  | Lampole | 30m Lampole | 30m | Add R9264M M1821 x3,Dismantle R8854E S1800(A6A) x3+R8862A S2100(A6A) x3
4140C | Juru 3 | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-11 |  | 2023-05-19 |  | Closed | 2023-05-23 | 2023-06-01 | E//Hazida | 2023-06-01 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0016 | DU00002008110 |  |  | 2023-06-15 | 2023-06-13 |  | Wall mount boom | 3m Bipod (RT) |  | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8881 S2100 x3
1011C | Surau Darul Hikmah | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-14 | 2023-04-27 |  | 2023-04-28 |  | Closed | 2023-05-01 | 2023-05-05 | CD//Ali akaram | 2023-05-18 | CelcomDigi_RAN_Datasco_TSS_Central_20230417_0012 | DU00002008111 |  |  | 2023-05-16 | 2023-05-17 |  | Lampole | Tower | 25 | Add R9264M M1821 x6,Dismantle R8894E M1821(A8A) x3 |  | 123
1500H | 99 Speedmart TG SEPAT 1 | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008112 | [6 empty] | Small Cell
3282A | VL Sg Rambai | Central |  | Modernization |  | 2023Q2 | HQ 6 | GTSB | 4.6 TSSR Approved |  | 2023-04-16 | 2023-05-04 |  | 2023-05-06 |  | Closed | 2023-05-10 | 2023-06-06 | E//Razif | 2023-05-26 | CelcomDigi_RAN_GTSB_TSS_Central_20230417_0017 | DU00002008113 |  |  | 2023-06-13 | 2023-06-02 |  | Tower | 30m Monopole | 46 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3
1264H | 99 Speedmart SRI ANDALAS 3 | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008114 | [6 empty] | Small Cell
1831H | PEDi Taman Harmoni | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008115 | [6 empty] | Rooftop
3961A | Jusco Bukit Tinggi Outdoor | Central |  | Modernization |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-04-17 | 2023-04-27 |  | 2023-05-04 |  | Rectificating | 2023-06-03 | 2023-06-07 | E//Razif | 2023-06-06 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230417_0012 | DU00002008116 |  |  | 2023-09-10 | 2023-06-14 |  | Unipole | 3m Bipod (RT) |  | Add R9264M M1821 x6 + R8862A S2601 x3,Dismantle R8894E M1821(A8A) x3 |  | 123
3368B | Jalan Bayu Tinggi 2b | Central |  | Modernization |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-04-07 | 2023-04-12 |  | 2023-04-15 |  | Closed | 2023-04-16 | 2023-06-01 | CD//Norhaliza | 2023-08-18 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230407_0009 | DU00002008117 |  |  | 2023-05-23 | 2023-05-23 |  | Pole | 3m Boom (RT) | 5m | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x3 |  | 3
1012C | Masjid Al-Islah | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦Space limitation | 2023-04-19 | 2023-04-27 |  | 2023-04-28 |  | Closed | 2023-04-29 | 2023-05-05 | CD//Syafiq | 2023-05-05 | CelcomDigi_RAN_Datasco_TSS_Central_20230419_0014 | DU00002008118 | NIC_S3_Change MM to BI_Space constraint_EDOTCO (M) - NONE CSU |  | 2023-05-19 | 2023-05-17 |  | Lampole | Tower | 25 | Add R9264M M1821 x6,Dismantle R8894E M1821(A8A) x3 |  | 123
1103A | Shaw Centrepoint | Central |  | Modernization |  | 2023Q3 | HQ 6 | Datasco | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-10 |  | 2023-05-12 |  | Closed | 2023-05-16 | 2023-06-17 | E//Razif | 2023-06-15 | CelcomDigi_RAN_Datasco_TSS_20230505_0019 | DU00002008119 |  |  | 2023-06-16 | 2023-06-13 |  | Minimast | 6m RT (Minimast) | 9m | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8882-GUL1812 x4+R8854D S2100(A4A) x3 |  | 3
1018E | West Port CT4-2 Pole | Central |  | Modernization | MOCN As-Is->Modernization | 2026 | AI | GTSB | 4.6 TSSR Approved |  | 2025-05-26 | 2025-05-27 |  | 2025-05-29 |  | Closed | 2025-06-03 | 2025-06-10 | E//Razif | 2025-06-10 | SQ202502170746 | DU00002008120 |  |  | 2026-03-10 | 2026-03-09 |  | Tower | Small Cell | 36m | Add A8612 M1821 x2+R8894E M1821 x1, Dismantle A8602 M1821x3
2706A | Jln Batu Unjur 2 | Central |  | Modernization |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦S3 can install AAU，S1 not sure.It's RT sites,If add another Y bracket or RRU bracket,need CelcomDigi PE to check the structure can support or not.If use RRU bracket,a few part of the AAU will be blocked by existing Antenna 1,need to shift down existing S1 antenna. | 2023-04-12 | 2023-04-27 |  | 2023-04-30 |  | Closed | 2023-05-15 | 2023-05-25 | E//Razif | 2023-05-26 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230413_0011 | DU00002008121 | NIC_S2_Change MM to BI_loading issue_Digi OB |  | 2023-05-23 | 2023-05-23 |  | Unipole | 6m Unipole RT | 7m | Add R9264M M1821 x5,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 |  | 13
4051C | Jln Tawas Baru | Northern |  | Modernization |  | 2023Q2 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-04-13 | 2023-04-20 |  | 2023-04-26 |  | Closed | 2023-04-27 | 2023-05-25 | CD//Affendi | 2023-05-03 | Celcom Digi_RAN-GTSB-TSS-Northern-20230414-0010 | DU00002008122 |  |  | 2023-06-12 | 2023-06-11 |  | Minimast | 3m Bipod (RT) | 11 | Add R8894E M1821 x3,Dismantle R8882 S1800(B) x3+R8881 S2100 x3
1399H | 99 Speedmart KG PENDAMAR | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008123 | [6 empty] | Small Cell
1610H | 99 Speedmart Bukit Raja 3 | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008124 | [6 empty] | Small Cell
4165A | Tmn Inderawasih | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-04-29 | 2023-05-03 |  | 2023-05-09 |  | Closed | 2023-05-10 | 2023-05-25 | CD//Heng | 2023-05-15 | Celcom Digi_RAN-GCI-TSS-Northern-20230502-0011 | DU00002008125 |  |  | 2023-06-07 | 2023-06-07 |  | Unipole | 6m Tripod (RT) | 6 | Add A9732 M1821 x1 + R9264M M1821 x2,Dismantle R8894E M1821(A8A) x3 | 3
3723B | Jalan Chan Ah Choo Pandamaran | Central |  | Modernization |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-04-28 | 2023-05-02 |  | 2023-05-04 |  | Closed | 2023-05-04 | 2023-05-25 | E//Razif | 2023-05-26 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230428_0015 | DU00002008126 |  |  | 2023-05-26 | 2023-05-22 |  | Lampole | Land site | 25 | Add R9264H M901821 x3,Dismantle R9224E M1821(AAB) x3 | 0 | 0
3379A | NKVE1 | Central |  | Modernization |  | 2023Q3 | YZ | Datasco | 4.6 TSSR Approved |  | 2023-05-16 | 2023-05-25 |  | 2023-05-27 |  | Closed | 2023-05-29 | 2023-06-21 | CD//Tee | 2023-06-21 | CelcomDigi_RAN_Datasco_TSS_Central_20230508_0020 | DU00002008127 |  |  | 2023-06-26 | 2023-06-22 |  | BillBoard | Billboard | 25m | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882 S1800(B) x2+R8862A S1800(B6A) x1++R8881 S2100 x3+
1434B | Sek 16 Suria Apt | Central |  | Modernization |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-08-17 | 2023-09-05 |  | 2023-08-21 |  | Closed | 2023-08-22 | 2023-08-23 | E//Razif | 2023-08-23 | CelcomDigi_RAN_Asccentrack_TSS_Central_20230818 | DU00002008128 |  |  | 2023-08-29 | 2023-08-24 |  | H-bracket pole | 6m RT (Boom) | 6.5m | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 23
1478H | 99 Speedmart SULTAN SULEIMAN 2 | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008129 | [6 empty] | Rooftop
4075C | Anderson Ipoh | Northern |  | Modernization |  | 2023Q2 | WP | GTSB | 4.6 TSSR Approved |  | 2023-04-12 | 2023-05-02 |  | 2023-05-03 |  | Closed | 2023-05-04 | 2023-05-17 | CD//Shamsul | 2023-05-11 | Celcom Digi_RAN-GTSB-TSS-Northern-20230413-0009 | DU00002008130 |  |  | 2023-05-24 | 2023-05-24 |  | Wall mount boom | 30m Monopole | 6 | Add R9264H M901821 x3,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3
3652A3 | pBTS Pandamaran Industrial Estate (KM) | Central |  | Modernization |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦pBTS loading issue,AAU cannot install | 2023-04-17 | 2023-04-27 |  | 2023-04-29 |  | Closed | 2023-04-29 | 2023-07-17 | CD//Tee | 2023-07-13 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230417_0012 | DU00002008131 | NIC_S3_Change MM to BI_loading issue_Digi OB |  | 2023-06-25 | 2023-05-22 |  | Guide mast | 25m pBTS | 30 | Add R9264H M901821 x3 + R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x2 |  | 123
1929B | Sungai Buaya Banting(KJS) | Central |  | Modernization |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-05 | 2023-04-08 |  | 2023-04-06 |  | Closed | 2023-04-11 | 2023-05-25 | CD//Tee | 2023-04-18 | CelcomDigi_RAN_GTSB_TSS_Central_20230405_0010 | DU00002008132 |  |  | 2023-05-12 | 2023-05-10 |  | Tower | Tower | 60 | Add R9264M M1821 x5 + R8862A S2601 x2,Dismantle R8892E M1821(BAA) x3 |  | 13
4166H | 99 Speedmart PK TMN TASEK JAYA | Northern |  | MOCN As-Is |  | 2023Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008133 | [6 empty] | Small Cell
1208B | Jln Batu Nilam 2 | Central |  | Modernization |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-04-08 |  |  | 2023-04-19 |  | Closed | 2023-04-19 | 2023-05-22 | CD//Sapian | 2023-05-12 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230410_0010 | DU00002008134 |  |  | 2023-05-24 | 2023-05-22 |  | H-bracket pole | 3m RT (Wall Mounted Pole) | 6m/6m/6.5m | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3
4030C | Teluk Senangin | Northern |  | Modernization |  | 2023Q2 | WP | GTSB | 4.6 TSSR Approved |  | 2023-04-11 | 2023-04-14 |  | 2023-04-14 |  | Closed | 2023-04-14 | 2023-04-19 | CD//Heng | 2023-04-18 | Celcom Digi_RAN-GTSB-TSS-Northern-20230411-0008 | DU00002008135 |  |  | 2023-05-17 | 2023-05-15 |  | Tower | 4 Legged Tower | 60 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882 S1800B(B6B) x3+R8881 S2100 x3
4033C | Tmn Bintang | Northern |  | Modernization |  | 2023Q2 | ZA | GCI | 4.6 TSSR Approved |  | 2023-04-17 | 2023-04-18 |  | 2023-04-19 |  | Closed | 2023-04-23 | 2023-05-15 | CD//Shamsul | 2023-05-05 | Celcom Digi_RAN-GCI-TSS-Northern-20230418-0007 | DU00002008136 |  |  | 2023-05-20 | 2023-05-17 |  | Rooftop | 3m Bipod (RT) | 19 | Add R9264H M901821 x3,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3
3051C8 | pBTS Jalan Sungai Jati ( C ) | Central |  | Modernization |  | 2023Q3 | HQ 6 | Ascentrack | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-09 |  | 2023-05-12 |  | Closed | 2023-05-12 | 2023-06-13 | E//Razif | 2023-06-13 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230508_0017 | DU00002008137 |  |  | 2023-06-15 | 2023-06-14 |  | Minimast | 25m pBTS | 24 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
3166B5 | pBTS MFE Formwork (EB) | Central |  | Modernization |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-26 | 2023-05-03 |  | 2023-05-07 |  | Closed | 2023-05-09 | 2023-06-26 | CD//Tee | 2023-06-26 | CelcomDigi_RAN_Datasco_TSS_Central_20230428_0018 | DU00002008138 |  |  | 2023-06-17 | 2023-06-17 |  | Guide mast | 24m PBTS | 25m | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
2536A | Centro IB | Central |  | Modernization |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-06-13 | 2023-06-13 |  | 2023-06-19 |  | Closed | 2023-06-23 | 2023-07-07 | E//Nazrul | 2023-07-04 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002008139 |  |  | 2023-07-27 | 2023-07-22 |  | Portables BTS | In-building system |  | Add R8862A S1800 x3 + R8862A S2100 x3,Dismantle R8882-GUL1812 x1+R8882 S1800B x1+R8882 S1800B(B6B) x1+R8840-U216 x1+R8881 S2100 x2
3578C | Jln Bukit Kuda (REL) | Central |  | Modernization |  | 2023Q3 | SS | YPTT | 4.6 TSSR Approved |  | 2023-05-07 | 2023-05-11 |  | 2023-05-19 |  | Closed | 2023-05-25 | 2023-05-25 | E//Sumitra | 2023-05-25 | CelcomDigi_RANMW_YPTT_TSS_Central_20230508_0002 | DU00002008140 |  |  | 2023-06-24 | 2023-06-22 |  | Wall mount boom | 3m Boom (RT) | 6m | Add A9732 M1821 x1 + R9264M M1821 x2,Dismantle R8882 S2600(B4A) x1+R9224E M1821(AAB) x4 | 2
1620H | 99 Speedmart Banting Sg Emas | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008141 | [6 empty] | Small Cell
3811A | Jalan Bunga Pekan (Banting) | Central |  | Modernization |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-04 | 2023-04-08 |  | 2023-04-10 |  | Closed | 2023-04-11 | 2023-06-06 | CD//Tee | 2023-04-17 | CelcomDigi_RAN_GTSB_TSS_Central_20230405_0010 | DU00002008142 |  |  | 2023-11-29 | 2023-11-16 |  | Wall mount boom | 3m Bipod (RT) | 7m | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
1666C | Kg Sijangkang | Central |  | Modernization |  | 2023Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2023-04-05 | 2023-04-15 |  | 2023-04-17 |  | Closed | 2023-04-20 | 2023-06-09 | E//Razif | 2023-06-09 | CelcomDigi_RAN_AllStar_TSS_Central_20230404_0005 / CelcomDigi_RAN_Allstar_TSS_Central_20230721_ClearLoan | DU00002008143 |  |  | 2023-05-15 | 2023-05-11 |  | Monopole | 30m Lampole | 27.1 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1437C | Kg. Sijangkang | Central |  | Modernization |  | 2023Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2023-04-04 |  |  | 2023-04-14 |  | Closed | 2023-04-27 | 2023-05-29 | CD//Tee | 2023-05-28 | CelcomDigi_RAN_AllStar_TSS_Central_20230404_0005 / CelcomDigi_RAN_Allstar_TSS_Central_20230721_ClearLoan | DU00002008144 |  |  | 2023-05-21 | 2023-05-11 |  | Lampole | 24m Lampole | 25 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
4086B | Jln Usaha Maju 1 (Maxis) | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-04 | 2023-05-06 |  | 2023-05-10 |  | Closed | 2023-05-10 | 2023-05-26 | CD//Affendi | 2023-05-15 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0016 | DU00002008145 |  |  | 2023-06-14 | 2023-06-13 |  | Monopole | 20m Monopole | 30 | Add R9264H M901821 x2,Dismantle R8882 S1800B(B6B) x1+R8862A S1800(B6A) x1+R8854D S2100(A4A) x2 | 0
3313C | Jalan Sidang | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-10 | 2023-04-20 |  | 2023-04-28 |  | Closed | 2023-04-29 | 2023-06-03 | CD//Ali akaram | 2023-05-26 | CelcomDigi_RAN_Datasco_TSS_Central_20230411_0009 | DU00002008146 |  |  | 2023-09-17 | 2023-09-17 |  | Monopole | 30m Monopole | 45 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x3+R9224E M1821(AAB) x2 | 23
2814A_IBC | Klang Parade | Central |  | Modernization |  | 2023Q3 | CR | Datasco | 4.6 TSSR Approved |  | 2023-11-21 | 2023-11-29 |  | 2024-01-16 |  | Closed | 2023-07-18 | 2024-01-16 | E//Nazrul | 2023-07-20 | CelcomDigi_RAN_Datasco_TSS_Central_20231126 | DU00002008147 |  |  | 2023-12-12 | 2023-12-05 |  | Portables BTS | 6m RT (Boom) + IBS | N/A | Add R8862A S1800 x2+R8862A S2100(A6A) x2,dismantle R8882 S1800(B) x2+R8881 S2100 x2
1604H | 99 Speedmart Taman Meru Indah | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008148 | [6 empty] | Rooftop
1127E | West Port CT9 Pole | Central |  | Modernization | MOCN As-Is->Modernization | 2026 | AI | GTSB | 4.6 TSSR Approved |  | 2025-05-26 | 2025-05-27 |  | 2025-05-29 |  | Under Approval | 2025-06-04 | 2025-07-25 | E//Razif | 2025-06-29 | SQ202502170746 | DU00002008149 |  |  | 2026-03-12 | 2026-03-11 |  | Tower | Small Cell | 42 | Add A8612 M1821 x3, Dismantle A8602 M1821x3
1622B | EconSave Kapar Setia | Central |  | Modernization |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-28 | 2023-05-13 |  | 2023-05-16 |  | Closed | 2023-05-19 | 2023-07-12 | E//Razif | 2023-07-12 | CelcomDigi_RAN_Datasco_TSS_Central_20230609_0025 | DU00002008150 |  |  | 2023-07-02 | 2023-06-28 |  | BillBoard | 30m Monopole | 20m | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 23
1473H | 99 Speedmart PANDAMARAN | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008151 | [6 empty] | Small Cell
3499A2 | pBTS Shin Yang Wood System | Sarawak |  | Modernization | Modernization->Site Out->Modernization->On Hold->Modernization | 2026 | MA | AllStar | 4.6 TSSR Approved | Solution changed add L26 in 2026 | 2023-04-19 | 2023-04-25 |  | 2023-05-02 |  | Closed | 2023-05-04 | 2023-05-19 | CD//John | 2023-05-04 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230403-0003 | DU00002008152 | [5 empty] | Minimast | 25m pBTS | 24.2 | Add R8862A S9000x3+R9264M M1821x3, Dismantle R8862A S1800(B6A)x3R8862A S2100(A6A)x3
2065A | Taman Botanic Klang | Central |  | Modernization |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-28 |  | 2023-05-04 |  | Closed | 2023-05-10 | 2023-05-22 | CD//Syafiq | 2023-05-18 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230413_0011 | DU00002008153 |  |  | 2023-05-21 | 2023-05-20 |  | Monopole | 30m Monopole | 30 | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x4 |  | 1
2080A | ING KLANG IB | Central |  | Modernization |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-16 | 2023-05-23 |  | 2023-06-08 |  | Closed | 2023-06-22 | 2023-06-24 | E//Nazrul | 2023-06-23 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002008154 |  |  | 2023-09-14 | 2023-08-04 |  |  | In-building system | IBC SITE | Add R8852E S9000 x1 ,Dismantle R8882-GUL1812 x1
1016C | Stadium Jugra | Central |  | Modernization |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-13 | 2023-04-25 |  | 2023-04-27 |  | Closed | 2023-05-05 | 2023-06-06 | E//Razif | 2023-05-30 | CelcomDigi_RAN_GTSB_TSS_Central_20230413_0016 | DU00002008155 |  |  | 2023-06-05 | 2023-06-03 |  | Lampole | Tower | 30 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
1440B | Kg Belia Datuk Harun | Central |  | Modernization |  | 2023Q2 | MA | GTSB | 4.6 TSSR Approved |  | 2023-04-07 | 2023-04-12 |  | 2023-04-14 |  | Closed | 2023-04-14 | 2023-05-08 | CD//Tee | 2023-05-08 | CelcomDigi_RAN_GTSB_Central_20230407_0012 | DU00002008156 |  |  | 2023-05-11 | 2023-05-10 |  | Tower | 24m Monopole | 25m | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 12
1171C | Billboard Tol Sungai Rasau | Central |  | Modernization |  | 2023Q3 | XH | Ascentrack | 4.6 TSSR Approved |  | 2023-05-12 | 2023-05-18 |  | 2023-05-20 |  | Closed | 2023-05-20 | 2023-06-30 | E//Razif | 2023-06-30 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230511_0018 | DU00002008157 |  |  | 2023-06-13 | 2023-06-13 |  | Lampole | 24m Lampole | 26m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
2615A3 | pBTS Kg Getisan | Sabah |  | Modernization |  | 2023Q2 | HQ 2 | Futong | 4.6 TSSR Approved | AAU Cannot Install-Change MM to normal sector¦pbts cant install AAU | 2023-04-08 | 2023-04-10 |  | 2023-04-15 |  | Rectificating | 2023-04-25 | 2023-05-10 | CD//Ray Amos | 2023-05-10 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002008158 | NIC_S2_Change MM to normal sector_loading issue_Digi OB |  | 2023-05-27 | 2023-05-25 |  |  | 25m pBTS | 29 | Add R9264H M901821 x3,Dismantle R9224E M1821(AAB) x3
1343A | Assam Jawa | Central |  | Modernization |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-05-12 | 2023-05-17 |  | 2023-05-19 |  | Closed | 2023-05-19 | 2023-06-28 | E//Sumitra | 2023-06-28 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230511_0018 | DU00002008159 |  |  | 2023-06-13 | 2023-06-13 |  | H-bracket pole | 3m RT (Wall Mounted Pole) | 6.5m | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x2+R8862A S2100(A6A) x4
1119A | Tmn Andalas Jaya | Central |  | Modernization |  | 2023Q3 | HQ 6 | Ascentrack | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-19 |  | 2023-05-24 |  | Closed | 2023-05-25 | 2023-06-13 | E//Razif | 2023-06-13 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230511_0018 | DU00002008160 |  |  | 2023-06-10 | 2023-06-10 |  | Minimast | 3m RT (Minimast) | 9 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3
1782A | Tmn Bunga Melor | Central |  | Modernization |  | 2023Q3 | YZ | Datasco | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-12 |  | 2023-05-15 |  | Closed | 2023-10-20 | 2023-10-25 | E//Razif | 2023-06-15 | CelcomDigi_RAN_Datasco_TSS_Central_20230508_0020 | DU00002008161 |  |  | 2023-06-11 | 2023-06-11 |  | Minimast | 3m Bipod (RT) | 9 | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x4
1765H | 99 Speedmart Bkt Tinggi 4 | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008162 | [6 empty] | Rooftop
3557B | Surau Ar-Rahman Presint Inang | Central |  | Modernization |  | 2023Q3 | HQ 6 | Datasco | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-12 |  | 2023-05-15 |  | Closed | 2023-05-17 | 2023-06-14 | CD//Sapian | 2023-06-15 | CelcomDigi_RANMW_Datasco_TSS_Central_20230505_0002 | DU00002008163 |  |  | 2023-06-13 | 2023-06-12 |  | Lampole | 45m 3 Legged Tower | 25 | Add R9264M M1821 x5,Dismantle R8894E M1821(A8A) x3 |  | 23
4168A | SbJaya (TMTouch MSC) | Northern |  | Modernization |  | 2023Q3 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-05-22 | 2023-05-24 |  | 2023-05-26 |  | Closed | 2023-06-01 | 2023-06-28 | CD//Quah | 2023-06-21 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0009 | DU00002008164 |  |  | 2023-07-13 | 2023-07-04 |  | Tower | Tower | 46M | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
3058C6 | pBTS Suang Parai Village Housing (KM) | Sabah |  | Modernization |  | 2023Q3 | HQ 1 | AllStar | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-25 |  | 2023-05-04 |  | Closed | 2023-05-05 | 2023-05-08 | CD//Mohidi Jaan | 2023-05-08 | Celcom Digi_RAN-Allstar-TSS-Sabah-20230407-0002 | DU00002008165 |  |  | 2023-07-10 | 2023-07-06 |  | Guide mast | 25m pBTS | 25m | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8862A S2600(A4A) x1+R8894E M1821(A8A) x4 | 23
1611H | 99 Speedmart Pendamar Indah | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008166 | [6 empty] | Small Cell
4083B | UITM Mara | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-02 | 2023-05-20 |  | 2023-05-23 |  | Closed | 2023-05-26 | 2023-06-01 | E//Hazida | 2023-05-31 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230502-0013 | DU00002008167 |  |  | 2023-06-27 | 2023-06-26 |  | Tower | Tower | 60 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2,Dismantle R8892E M1821(BAA) x3 | 3
3774A | LABOHAN DAGANG 1 | Central |  | Modernization |  | 2023Q2 | MA | GTSB | 4.6 TSSR Approved |  | 2023-04-05 |  |  | 2023-04-13 |  | Closed | 2023-04-17 | 2023-05-02 | CD//Tee | 2023-04-25 | CelcomDigi_RAN_GTSB_Central_20230406_0011 | DU00002008168 |  |  | 2023-05-18 | 2023-05-13 |  | Tower | Tower | 70m | Add A9732 M1821 x3,Dismantle R8882 S1800B(B6B) x3+R8854D S2100(A4A) x3 | 123
1107A | Bukit Kemuning | Central |  | Modernization |  | 2023Q3 | SS | Futong | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-15 |  | 2023-05-18 |  | Closed | 2023-05-24 | 2023-06-24 | CD//Norhaliza | 2023-06-23 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002008169 |  |  | 2023-07-22 | 2023-07-22 |  | Minimast | 3m RT (Minimast) | 10 | Add R9264M M1821 x5 + R8862A S2601 x2,Dismantle R8894E M1821(A8A) x3 |  | 13
4085B | Bkt Tengah 2 | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-10 | 2023-06-12 |  | 2023-06-14 |  | Closed | 2023-06-16 | 2023-06-22 | E//Hazida | 2023-06-22 | Celcom Digi_RAN-GTSB-TSS-Northern-20230511-0018 | DU00002008170 |  |  | 2023-07-05 | 2023-07-04 |  | Tower | Tower | 60 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
1401H | 99 Speedmart BDR SG CHANDONG | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008171 | [6 empty] | Small Cell
1446B | Batu Laut (KJS) | Central |  | Modernization |  | 2023Q2 | IE | Magicell | 4.6 TSSR Approved |  | 2023-04-07 | 2023-04-13 |  | 2023-04-14 |  | Closed | 2023-04-17 | 2023-05-11 | CD//Tee | 2023-05-11 | CelcomDigi_RAN_Magicell_TSS_Central_20230411_0002/CelcomDigi_RAN_Magicell_TSS_Central_20230722 | DU00002008172 |  |  | 2023-05-12 | 2023-05-10 |  | Tower | Tower | 61m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1922B | Kg Seri Cheedings | Central |  | Modernization |  | 2023Q2 | SS | GTSB | 4.6 TSSR Approved |  | 2023-04-03 | 2023-04-12 |  | 2023-05-16 |  | Closed | 2023-05-18 | 2023-05-23 | E//Razif | 2023-05-19 | CelcomDigi_RAN_GTSB_TSS_Central_20230404_0009 | DU00002008173 |  |  | 2023-05-11 | 2023-05-09 |  | Tower | 45m 3 Legged Tower | 50 | Add R9264M M1821 x5,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 |  | 12
2537A | Kg Kanchong Tengah | Central |  | Modernization |  | 2023Q2 | IE | Magicell | 4.6 TSSR Approved |  | 2023-04-13 | 2023-04-25 |  | 2023-04-28 |  | Closed | 2023-04-29 | 2023-05-08 | CD//Tee | 2023-05-08 | CelcomDigi_RAN_Magicell_TSS_Central_20230417_0003 | DU00002008174 |  |  | 2023-05-29 | 2023-05-27 |  | Tower | 60m 4 Legged Tower | 62 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 |  | 2
1089A | Klang Shoplot | Central |  | Modernization |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-05-26 | 2023-06-30 |  | 2023-07-03 |  | Closed | 2023-07-04 | 2023-07-05 | E//Razif | 2023-07-05 | CelcomDigi_RAN_Datasco_TSS_Central_20230428_0018 | DU00002008175 |  |  | 2023-07-17 | 2023-07-17 |  | Pole | 24m Monopole | 6 | Add R9264M M1821 x4,Dismantle R8854 S1800(A4A) x3+R8840-U216 x3++ |  | 3
4054B9 | pBTS KKIP KTC Creamos (REL) | Sabah |  | Modernization |  | 2023Q2 | AD | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-25 |  | 2023-04-28 |  | Closed | 2023-05-04 | 2023-05-25 | CD//Ray Amos | 2023-05-10 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002008176 |  |  | 2023-06-14 | 2023-06-08 |  |  | 25m pBTS | 20 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3 | 0
1257C | Jln Batu Nilam (REL) | Central |  | Modernization |  | 2023Q3 | IE | Ascentrack | 4.6 TSSR Approved |  | 2023-05-12 | 2023-05-19 |  | 2023-05-23 |  | Closed | 2023-05-23 | 2023-06-30 | E//Razif | 2023-06-30 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230511_0018 | DU00002008177 |  |  | 2023-06-09 | 2023-06-08 |  | H-bracket pole | Lampole | 6 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8894E M1821(A8A) x3 |  | 2
3656B | Taman Mulia | Central |  | Modernization |  | 2023Q3 | HQ 6 | Futong | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-12 |  | 2023-05-14 |  | Closed | 2023-05-16 | 2023-06-28 | CD//Norhaliza | 2023-06-22 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002008178 |  |  | 2023-06-11 | 2023-06-11 |  | Unipole | 3m Bipod (RT) | 24 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1579H | 99 Speedmart Ken Rimba | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008179 | [6 empty] | Rooftop
3637B | Jalan Tengku Badar | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-17 | 2023-04-28 |  | 2023-05-03 |  | Closed | 2023-05-04 | 2023-05-22 | CD//Ali akaram | 2023-05-18 | CelcomDigi_RAN_Datasco_TSS_Central_20230418_0013 | DU00002008180 |  |  | 2023-05-22 | 2023-05-15 |  | Wall mount boom | 3m Bipod (RT) | 5m | Add A9732 M1821 x2 + R9264M M1821 x1 + R8862A S2601 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 12
3546A40 | mBTS Bukit Bantayan | Sabah |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-08 |  | 2023-04-13 |  | Closed | 2023-04-25 | 2023-05-25 | CD//Ray Amos | 2023-05-10 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230407-0002 | DU00002008181 |  |  | 2023-06-17 | 2023-06-13 |  | Minimast | Portable BTS | 10.2m | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle R8882 S1800(B) x3+R8862A S1800(B6A) x2+R8862A S2100(A6A) x5+R8862A S2600(A4A) x1 |  | 3
2094A | Kg Sg Lang Baru (Celcom) | Central |  | Modernization |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-03 | 2023-04-04 |  | 2023-04-06 |  | Closed | 2023-04-10 | 2023-04-17 | CD//Tee | 2023-04-17 | CelcomDigi_RAN_GTSB_TSS_Central_20230404_0009 | DU00002008182 |  |  | 2023-05-20 | 2023-05-18 |  |  | 45m 4 Legged Tower | 46 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
2633B | Jalan Mohd Yamin Klang | Central |  | Modernization |  | 2023Q3 | AI | Futong | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-10 |  | 2023-05-12 |  | Closed | 2023-05-17 | 2023-06-30 | E//Razif | 2023-06-30 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002008183 |  |  | 2023-06-25 | 2023-06-22 |  | Monople Tree | 30m Monopole | 32 | Add A9732 M1821 x2 + R9264M M1821 x2,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x3+R9224E M1821(AAB) x2 | 23
3121B | Lorong Nuri (HSR) | Central |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-05-06 | 2023-05-08 |  | 2023-05-10 |  | Closed | 2023-05-12 | 2023-07-05 | CD//Syafiq | 2023-07-05 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002008184 |  |  | 2023-06-13 | 2023-06-13 |  | Unipole | 3m Bipod (RT) | 3M | Add R8894E M1821 x3,Dismantle R8882 S1800B(B6B) x6+R8881 S2100 x3
1404C | Lebuh Damar Merah | Central |  | Modernization |  | 2023Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-15 |  | 2023-04-16 |  | Closed | 2023-04-17 | 2023-05-17 | CD//Ali akaram | 2023-04-27 | CelcomDigi_RAN_AllStar_TSS_Central_20230404_0005 / CelcomDigi_RAN_Allstar_TSS_Central_20230721_ClearLoan | DU00002008185 |  |  | 2023-05-12 | 2023-05-11 |  | Lampole | 30m Lampole | 31 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1125A | Kg Bt Laut | Central |  | Modernization |  | 2023Q2 | IE | Magicell | 4.6 TSSR Approved |  | 2023-04-13 | 2023-04-14 |  | 2023-04-18 |  | Closed | 2023-04-18 | 2023-05-10 | CD//Tee | 2023-04-19 | CelcomDigi_RAN_Magicell_TSS_Central_20230417_0003 | DU00002008186 |  |  | 2023-05-10 | 2023-05-10 |  | Monopole | 30m Monopole | 45m | Add R9264H M901821 x3,Dismantle R8882 S1800B(B6B) x3
3628B | Jalan Klang Banting | Central |  | Modernization |  | 2023Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2023-05-02 | 2023-05-08 |  | 2023-05-10 |  | Closed | 2023-05-11 | 2023-05-29 | E//Razif | 2023-05-29 | CelcomDigi_RAN_AllStar_TSS_Central_20230404_0005 / CelcomDigi_RAN_Allstar_TSS_Central_20230721_ClearLoan | DU00002008187 |  |  | 2023-05-22 | 2023-05-17 |  | Monopole | 3m Boom (RT) | 31 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
1178B | Jln Temoh | Central |  | Modernization |  | 2023Q3 | MA | Datasco | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-08 |  | 2023-05-10 |  | Closed | 2023-05-12 | 2023-06-17 | E//Razif | 2023-06-15 | CelcomDigi_RAN_Datasco_TSS_20230505_0019 | DU00002008188 |  |  | 2023-07-20 | 2023-07-13 |  | Unipole | 3m Bipod (RT) | 9 | Add R9264M M1821 x3,Dismantle R8862 S1800(B6A) x3+R8862A S2100(A6A) x2+R8862 S2100(A6A) x1
2801C | Pandamaran Industrial Estate (EB) | Central |  | Modernization |  | 2023Q2 | YZ | Ascentrack | 4.6 TSSR Approved |  | 2023-04-17 | 2023-04-29 |  | 2023-04-30 |  | Closed | 2023-05-02 | 2023-05-17 | CD//Sapian | 2023-05-17 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230417_0012 | DU00002008189 |  |  | 2023-05-15 | 2023-05-13 |  | Pole | Land site | 6m | Add R9264H M901821 x4,Dismantle R9224E M1821(AAB) x4
1633B | Bandar Armada Putra | Central |  | Modernization |  | 2023Q2 | AI | Datasco | 4.6 TSSR Approved |  | 2023-04-19 | 2023-04-20 |  | 2023-04-26 |  | Closed | 2023-04-28 | 2023-05-25 | CD//Tee | 2023-04-28 | CelcomDigi_RAN_Datasco_TSS_Central_20230412_0010 | DU00002008190 |  |  | 2023-05-31 | 2023-05-30 |  | Monopole | 30m Monopole | 30 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
3054C5 | pBTS BCCM Kolombong (KM) | Sabah |  | Modernization |  | 2023Q3 | HQ 8 | YPTT | 4.6 TSSR Approved | Single Phase Power Site. Site require upgrade to 3phase incoming | 2023-04-08 | 2023-04-10 |  | 2023-04-14 |  | Closed | 2023-04-18 | 2023-05-25 | CD//Mohidi Jaan | 2023-05-10 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230407-0002 | DU00002008191 |  |  | 2023-06-24 | 2023-06-12 |  | Guide mast | 25m pBTS | 25 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
3773A | MEGA STEEL | Central |  | Modernization |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-13 | 2023-04-29 |  | 2023-05-02 |  | Closed | 2023-05-08 | 2023-06-27 | CD//Tee | 2023-06-27 | CelcomDigi_RAN_GTSB_TSS_Central_20230413_0016 | DU00002008192 |  |  | 2023-06-24 | 2023-06-23 |  | Monopole | 24m Pylon | 30 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8881 S2100 x3
1006Z | KG PULAU CAREY | Central |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q2 |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Tee |  |  | DU00002008193 | [6 empty] | Land site
3458C | Botanic Business Gateway (REL) | Central |  | Modernization |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-04-05 | 2023-04-08 |  | 2023-04-11 |  | Closed | 2023-04-12 | 2023-05-25 | CD//Sapian | 2023-05-05 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230405_0007 | DU00002008194 |  |  | 2023-05-11 | 2023-05-10 |  | H-bracket pole | 3m Boom (RT) | 6m | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
3747C2 | pBTS Nexus Karambunai (C ) | Sabah |  | Remote MOCN | Modernization->On Hold->Remote MOCN | 2023Q2 | AD | Futong | 4.6 TSSR Approved | Single Phase Power Site. Site require upgrade to 3phase incoming | 2023-04-08 | 2023-04-25 |  | 2023-04-28 |  | Closed | 2023-05-02 | 2023-06-27 | CD//Mohidi Jaan | 2023-05-05 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002008195 | [6 empty] | 25m pBTS | 30
2631A | Samarinda | Central |  | Modernization |  | 2023Q3 | MA | Futong | 4.6 TSSR Approved |  | 2023-05-15 | 2023-05-29 |  | 2023-06-02 |  | Closed | 2023-06-03 | 2023-06-21 | CD//Nik Ashraf | 2023-06-21 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002008196 |  |  | 2023-07-04 | 2023-07-03 |  | Tower | 45m 3 Legged Tower | 46m | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x4 | 12
3310C | Desa Alam Seksyen U12 Shah Alam | Central |  | Modernization |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-17 |  | 2023-05-19 |  | Closed | 2023-05-19 | 2023-06-28 | CD//Tee | 2023-06-19 | CelcomDigi_RAN_Datasco_TSS_Central_20230508_0020 | DU00002008197 |  |  | 2023-07-04 | 2023-06-28 |  | Monople Tree | 30m Monopole | 30 | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x3+R8894E M1821(A8A) x3+R9224E M1821(AAB) x3 | 123
2728C | Kg. Jenjarom 2 | Central |  | Modernization |  | 2023Q2 | YZ | GTSB | 4.6 TSSR Approved |  | 2023-04-03 | 2023-04-04 |  | 2023-04-15 |  | Closed | 2023-05-04 | 2023-05-17 | CD//Syafiq | 2023-05-17 | CelcomDigi_RAN_GTSB_TSS_Central_20230404_0009 | DU00002008198 |  |  | 2023-05-17 | 2023-05-15 |  | Tower | Land site | 60m | Add R9264H M901821 x3 + R9264M M1821 x3 + R8862A S2601 x6,Dismantle R8894E M1821(A8A) x3 |  | 123
3638B | Manipal Hospitals Klang | Central |  | Modernization |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-16 |  | 2023-05-18 |  | Closed | 2023-05-19 | 2023-06-05 | E//Razif | 2023-05-24 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230428_0015 | DU00002008199 |  |  | 2023-06-25 | 2023-06-22 |  | Rooftop | 3m Bipod (RT) | 40 | Add R9264M M1821 x5,Dismantle R8854E S1800(A6A) x3+R8854D S2100(A4A) x3 |  | 12
2953A | Kampung Lenang | Central |  | Modernization |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-04 | 2023-04-07 |  | 2023-04-11 |  | Closed | 2023-04-12 | 2023-06-08 | CD//Tee | 2023-06-01 | CelcomDigi_RAN_GTSB_TSS_Central_20230405_0010 | DU00002008200 |  |  | 2023-05-17 | 2023-05-15 |  | Tower | Tower | 60 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 12
1416H | 99 Speedmart Sri Andalas 2 | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008201 | [6 empty] | Rooftop
1652H | 99 Speedmart Pulau Indah | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008202 | [6 empty] | Small Cell
3751A | Masjid Riyadh-us-Solihin | Central |  | Modernization |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-05-17 | 2023-05-23 |  | 2023-05-26 |  | Closed | 2023-05-27 | 2023-06-28 | E//Sumitra | 2023-06-28 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230523_0020 | DU00002008203 |  |  | 2023-07-05 | 2023-07-04 |  | Lampole | 20m Lampole | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1438B | Jln Dengkil Banting | Central |  | Modernization |  | 2023Q2 | MA | GTSB | 4.6 TSSR Approved |  | 2023-04-05 | 2023-04-14 |  | 2023-04-16 |  | Closed | 2023-04-17 | 2023-05-25 | CD//Sapian | 2023-04-28 | CelcomDigi_RAN_GTSB_TSS_Central_20230405_0010 | DU00002008204 |  |  | 2023-05-12 | 2023-05-10 |  | Tower | 60m 3 Legged Tower | 60m | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 23
1641B | Jln Kampung Delek | Central |  | Modernization |  | 2023Q3 | YZ | Futong | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-16 |  | 2023-05-19 |  | Closed | 2023-05-20 | 2023-08-01 | E//Razif | 2023-08-01 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002008205 |  |  | 2023-07-02 | 2023-06-28 |  | Monople Tree | 30m Monopole Tree | 32 | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x3+R8894E M1821(A8A) x3+R9224E M1821(AAB) x3 | 123
3472C3 | pBTS Masjid Nurul Jannah ( C ) | Central |  | Modernization |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-26 | 2023-04-28 |  | 2023-05-05 |  | Closed | 2023-05-09 | 2023-06-28 | E//Razif | 2023-06-26 | CelcomDigi_RAN_Datasco_TSS_Central_20230428_0018 | DU00002008206 |  |  | 2023-06-10 | 2023-06-10 |  | Tower | 25m pBTS | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
4154A | Bagan Shoplot | Northern |  | Modernization |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-05-04 | 2023-05-06 |  | 2023-05-12 |  | Closed | 2023-05-16 | 2023-06-10 | E//Hazida | 2023-06-10 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0015 | DU00002008207 |  |  | 2023-06-19 | 2023-06-14 |  | H-bracket pole | 3m Boom (RT) | 6 | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8882-GUL1812 x3+R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 |  | 1
4174A | LBSB Factory | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-19 |  | 2023-05-25 |  | Closed | 2023-06-01 | 2023-06-21 | CD//Affendi | 2023-06-21 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0016 | DU00002008208 |  |  | 2023-06-21 | 2023-06-15 |  | Wall mount boom | 2m RT (Boom) | 3 | Add R9264H M901821 x1 + R9264M M1821 x5,Dismantle R8894E M1821(A8A) x4 |  | 24
1008R | BB1_B058E_B00119OD_PULAUCAREY2 | Central |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2023Q2 | AI | GCI | 4.6 TSSR Approved |  | 2025-07-08 |  | 2025-07-16 |  | 2025-10-15 |  | 2025-10-22 | 2025-11-03 | CD//Tee | 2025-10-23 | SQ202506110093 | DU00002008209 |  |  |  |  | 2025-08-05 |  | Land site
2463A | Kg Titib | Central |  | Modernization |  | 2023Q2 | HQ 6 | Magicell | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-09 |  | 2023-05-11 |  | Closed | 2023-05-12 | 2023-05-25 | E//Razif | 2023-05-25 | CelcomDigi_RAN MW_Magicell_TSS_Central_20230428_0001 | DU00002008210 |  |  | 2023-05-24 | 2023-05-23 |  | Tower | 60m 4 Legged Tower | 60M | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x2+R8862A S2100(A6A) x2
1108A | PNSB Acmar | Central |  | Modernization |  | 2023Q3 | SS | Datasco | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-12 |  | 2023-05-15 |  | Closed | 2023-05-17 | 2023-06-05 | E//Razif | 2023-05-22 | CelcomDigi_RANMW_Datasco_TSS_Central_20230505_0002 | DU00002008211 |  |  | 2023-06-22 | 2023-06-19 |  | Pole | 6m Unipole RT | 6m | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8862A S1800(B6A) x3+R8854E S1800(A6A) x3+R8854D S2100(A4A) x3 | 12
2796A | Jenjarum Temple | Central |  | Modernization |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-05 |  |  | 2023-04-11 |  | Closed | 2023-04-14 | 2023-05-25 | CD//Ali akaram | 2023-05-03 | CelcomDigi_RAN_GTSB_Central_20230406_0011 | DU00002008212 |  |  | 2023-05-21 | 2023-05-09 |  | Unipole | 60m 4 Legged Tower | 6m | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 |  | 3
1128A | OLAK LEMPIK | Central |  | Modernization |  | 2023Q2 | YZ | GTSB | 4.6 TSSR Approved |  | 2023-04-07 | 2023-04-15 |  | 2023-04-18 |  | Closed | 2023-04-19 | 2023-05-05 | CD//Tee | 2023-05-05 | CelcomDigi_RAN_GTSB_Central_20230407_0012 | DU00002008213 |  |  | 2023-05-21 | 2023-05-09 |  | Tower | 76m Tower | 40m | Add A9732 M1821 x3,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8854D S2100(A4A) x4+R8854 S2600(A4A) x1 | 123
4183B | Jalan Siram | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-13 | 2023-05-31 |  | 2023-06-02 |  | Closed | 2023-06-06 | 2023-06-20 | CD//Shukri | 2023-06-20 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0016 | DU00002008214 |  |  | 2023-06-21 | 2023-06-19 |  | Minimast | Tower | 4 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
2804C | Bandar Sultan Suleiman 2 (EB) | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-17 | 2023-04-20 |  | 2023-04-20 |  | Closed | 2023-04-20 | 2023-05-12 | CD//Sapian | 2023-05-12 | CelcomDigi_RAN_Datasco_TSS_Central_20230418_0013 | DU00002008215 |  |  | 2023-05-12 | 2023-05-11 |  | Lampole | Land site | 30 | Add R9264H M901821 x3,Dismantle R9224E M1821(AAB) x3
3615B | Lorong Bakong Tlk Pulai | Central |  | Modernization |  | 2023Q3 | HQ 6 | Futong | 4.6 TSSR Approved |  | 2023-05-20 | 2023-05-22 |  | 2023-05-25 |  | Closed | 2023-05-26 | 2023-06-20 | E//Sumitra | 2023-06-20 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002008216 |  |  | 2023-06-15 | 2023-06-12 |  | Pole | 3m Bipod (RT) | 7 | Add R9264M M1821 x4,Dismantle R8862A S1800(B6A) x4+R8862A S2100(A6A) x4
2646A | Teluk Pulai 2 | Central |  | Modernization |  | 2023Q3 | HQ 6 | Futong | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦Structure is critical and require off loading, so that can not install | 2023-05-17 | 2023-05-18 |  | 2023-05-22 |  | Closed | 2023-05-24 | 2023-08-10 | E//Razif | 2023-06-20 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002008217 | NIC_S3_Change MM to BI_loading issue_UMOBILE |  | 2024-05-24 | 2024-05-15 |  | Monopole | 30m Monopole | 35 | Add A9732 M1821 x3,Dismantle R8862A S9000(A6A) x3+R8894E M1821(A8A) x3+R8854 S2600(A4A) x3 | 123 | 0
3771A | PO Teluk Panglima Garang | Central |  | Modernization |  | 2023Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-27 |  | 2023-04-28 |  | Closed | 2023-05-01 | 2023-06-06 | CD//Tee | 2023-05-08 | CelcomDigi_RAN_AllStar_TSS_Central_20230404_0005 / CelcomDigi_RAN_Allstar_TSS_Central_20230721_ClearLoan | DU00002008218 |  |  | 2023-06-10 | 2023-06-08 |  | Wall mount boom | 30m Monopole |  | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 12
3087B | Lebuh Samudera | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-14 | 2023-05-03 |  | 2023-05-06 |  | Closed | 2023-05-08 | 2023-05-30 | E//Razif | 2023-05-26 | CelcomDigi_RAN_Datasco_TSS_Central_20230417_0012 | DU00002008219 |  |  | 2023-05-27 | 2023-05-27 |  | Lampole | 24m Lampole | 20 | Add R9264H M901821 x3,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3
4161Z | Telaga Nenas | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Zulakmar |  |  | DU00002008220 | [6 empty] | Land site
2658B | Aman Perdana | Central |  | Modernization |  | 2023Q3 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-05-17 | 2023-05-27 |  | 2023-05-31 |  | Closed | 2023-06-22 | 2023-07-25 | E//Razif | 2023-07-20 | CelcomDigi_RAN_CCSMY_TSS_Central_20230508_0002 | DU00002008221 |  |  | 2023-08-07 | 2023-08-02 |  | Monopole | 30m Monopole | 30 | Add R9264H M901821 x1 + A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x4+R9224E M1821(AAB) x1 | 23
2635B | Jln Raja Lumu | Central |  | Modernization |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-18 |  | 2023-04-18 |  | Closed | 2023-04-19 | 2023-05-25 | CD//Norhaliza | 2023-08-18 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230410_0010 | DU00002008222 |  |  | 2023-05-24 | 2023-05-24 |  | Unipole | 3m Bipod (RT) | 6.70m | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
1988A | Tmn Klang Jaya | Central |  | Modernization |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-05-15 | 2023-05-18 |  | 2023-05-22 |  | Closed | 2023-05-23 | 2023-06-26 | E//Razif | 2023-06-26 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230511_0018 | DU00002008223 |  |  | 2023-06-10 | 2023-06-08 |  | H-bracket pole | 5m RT (Boom) | 3 | Add R8894E M1821 x3,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x1+R8840-U216 x3+
4117B | BGM Development Sdn Bhd (REL) | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-15 | 2023-05-26 |  | 2023-06-01 |  | Closed | 2023-06-02 | 2023-06-20 | CD//Shukri | 2023-06-20 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0016 | DU00002008224 |  |  | 2023-06-23 | 2023-06-21 |  | Wall mount boom | 6m Unipole RT | 5M | Add R9264H M901821 x4 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8882-GUL1812 x3+R8882 S1800B(B6B) x3+R8862A S1800(B6A) x2+R8840-U216 x3+R8862A S2100(A6A) x1 |  | 1
2662B | Kg Batu Empat (Maxis) | Central |  | Modernization |  | 2023Q3 | SS | CCSMY | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦Maxis reject add AAU | 2023-05-22 | 2023-06-02 |  | 2024-01-16 |  | Closed | 2024-01-16 | 2024-01-30 | E//Razif | 2024-01-19 | CelcomDigi_RAN_CCSMY_TSS_Central_20230508_0002 | DU00002008225 | NIC_S3_Change MM to BI_owner reject_MAXIS |  | 2024-01-29 | 2024-01-22 |  | Tower | 45m 3 Legged Tower | 45 | Add R9264H M901821 x3,Dismantle R8862A S9000(A6A) x3+R8854E S1800(A6A) x3+R8854D S2100(A4A) x3 |  | 12
1087A | Rantau Panjang | Central |  | Modernization |  | 2023Q3 | YZ | Datasco | 4.6 TSSR Approved |  | 2023-04-28 | 2023-05-06 |  | 2023-05-09 |  | Closed | 2023-05-13 | 2023-06-13 | CD//Tee | 2023-06-13 | CelcomDigi_RAN_Datasco_TSS_Central_20230502_0019 | DU00002008226 |  |  | 2023-06-15 | 2023-06-13 |  | Tower | 45m 4 Legged Tower | 50 | Add R9264M M1821 x6,Dismantle R8894E M1821(A8A) x4 |  | 123
2772A | Jln Sg Keramat | Central |  | Modernization |  | 2023Q3 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-05-17 | 2023-05-27 |  | 2023-05-31 |  | Closed | 2023-06-06 | 2023-07-13 | E//Razif | 2023-07-12 | CelcomDigi_RAN_CCSMY_TSS_Central_20230508_0002 | DU00002008227 |  |  | 2023-07-06 | 2023-06-28 |  | Monopole | 30m Monopole | 31 | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x3+R9224E M1821(AAB) x2 | 123
1581C | Kg Batu Enam (REL) | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-06-14 | 2023-06-15 |  | 2023-06-16 |  | Closed | 2023-06-18 | 2023-06-28 | E//Razif | 2023-06-22 | CelcomDigi_RAN MW_Datasco_TSS_Central_20230428_0001 | DU00002008228 |  |  | 2023-09-25 | 2023-09-18 |  | Tower | 60m 4 Legged Tower | 50m | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 3
4153A | Zheng De Mai | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-12 | 2023-05-18 |  | 2023-05-26 |  | Closed | 2023-06-01 | 2023-06-20 | CD//Shukri | 2023-06-20 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0016 | DU00002008229 |  |  | 2023-06-20 | 2023-06-19 |  | Pole | 3m Boom (RT) | 3 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
3633B | Kampung Idaman | Central |  | Modernization |  | 2023Q2 | YZ | Ascentrack | 4.6 TSSR Approved |  | 2023-04-17 | 2023-05-05 |  | 2023-05-08 |  | Closed | 2023-05-09 | 2023-06-20 | E//Razif | 2023-06-20 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230417_0012 | DU00002008230 |  |  | 2023-05-25 | 2023-05-20 |  | Lampole | 24m Lampole | 20 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
2661C | Kawasan Perindustrian Olak Lempit | Central |  | Modernization |  | 2023Q2 | YZ | GTSB | 4.6 TSSR Approved |  | 2023-04-18 | 2023-04-27 |  | 2023-04-28 |  | Closed | 2023-05-01 | 2023-05-10 | CD//Syafiq | 2023-05-10 | CelcomDigi_RAN_GTSB_TSS_Central_20230419_0019 | DU00002008231 |  |  | 2023-05-10 | 2023-05-09 |  | Tower | Land site | 45m | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8894E M1821(A8A) x3 |  | 12
1132C | Jalan Khamis | Central |  | Modernization |  | 2023Q3 | YZ | CCSMY | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-26 |  | 2023-05-29 |  | Closed | 2023-05-30 | 2023-07-13 | E//Razif | 2023-07-12 | CelcomDigi_RANMW_CCSMY_TSS_Central_20230508_0001 | DU00002008232 |  |  | 2023-07-07 | 2023-06-28 |  | Lampole | 30m Lampole | 23.7m | Add R9264H M901821 x1 + R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 |  | 1
1073A | KTM Padang Jawa | Central |  | Modernization |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-05-11 | 2023-07-21 |  | 2023-07-25 |  | Closed | 2023-07-26 | 2023-07-28 | E//Razif | 2023-07-27 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230511_0018 | DU00002008233 |  |  | 2023-10-10 | 2023-08-10 |  | Tower | 45m 3 Legged Tower | 92 | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x5 | 123
3557A | GM Klang (REL) | Central |  | Modernization |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦wall mount pole was rejected by owner due to loading issue,AAU cannot install | 2023-04-17 | 2023-05-06 |  | 2023-05-15 |  | Closed | 2023-05-18 | 2023-06-05 | E//Razif | 2023-05-30 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230417_0012 | DU00002008234 | NIC_S2_Change MM to BI_loading issue_Digi OB |  | 2023-09-05 | 2023-06-08 |  | Pole | 3m Boom (RT) | 3 | Add R9264M M1821 x5 + R8862A S2601 x2,Dismantle R8894E M1821(A8A) x3 |  | 23
2720A | TPG Kuala Langat | Central |  | Modernization |  | 2023Q2 | IE | AllStar | 4.6 TSSR Approved |  | 2023-04-17 | 2023-04-20 |  | 2023-04-27 |  | Closed | 2023-04-28 | 2023-05-09 | CD//Ali akaram | 2023-05-09 | CelcomDigi_RAN_AllStar_TSS_Central_20230404_0005 / CelcomDigi_RAN_Allstar_TSS_Central_20230721_ClearLoan | DU00002008235 |  |  | 2023-05-18 | 2023-05-15 |  | Tower | 60m 4 Legged Tower | 61 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x3+R9224E M1821(AAB) x2 | 12
3200C | Kg Jenjarom | Central |  | Modernization |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-04 | 2023-04-08 |  | 2023-04-12 |  | Closed | 2023-04-13 | 2023-06-06 | CD//Sapian | 2023-05-11 | CelcomDigi_RAN_GTSB_TSS_Central_20230405_0010 | DU00002008236 |  |  | 2023-12-21 | 2023-12-11 |  | Lampole | Land site | 31 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1122A | Jenjarum | Central |  | Modernization |  | 2023Q2 | IE | GTSB | 4.6 TSSR Approved |  | 2023-04-04 | 2023-04-07 |  | 2023-04-12 |  | Closed | 2023-05-12 | 2023-05-25 | CD//Tee | 2023-05-24 | CelcomDigi_RAN_GTSB_TSS_Central_20230405_0010 | DU00002008237 |  |  | 2023-05-17 | 2023-05-15 |  | Tower | 76m Tower | 50 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8860E-GU908 x3+R8894E M1821(A8A) x3 | 23
3027C | Sg Kapar Industrial (REL) | Central |  | Modernization |  | 2023Q3 | HQ 6 | CCSMY | 4.6 TSSR Approved |  | 2023-07-18 | 2023-07-21 |  | 2023-07-26 |  | Closed | 2023-07-27 | 2023-07-28 | E//Razif | 2023-07-28 | CelcomDigi_RAN_CCSMY_TSS_Central_20230428_0001 | DU00002008238 |  |  | 2023-08-06 | 2023-08-02 |  | Lampole | 24m Lampole | 25m | Add R9264M M1821 x5,Dismantle R8894E M1821(A8A) x5 |  | 4
4157A | Halaman Tenggiri | Northern |  | Modernization |  | 2023Q3 | MH | GCI | 4.6 TSSR Approved |  | 2023-05-06 | 2023-05-09 |  | 2023-05-13 |  | Closed | 2023-05-15 | 2023-07-06 | E//Hazida | 2023-07-05 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0015 | DU00002008239 |  |  | 2023-06-27 | 2023-06-14 |  | Pole | 3m Boom (RT) | N/A | Add A9732 M1821 x1 + R9264M M1821 x3,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x5 | 3(MM @190°)
3888B | Shell Tmn Meru Jaya | Central |  | Modernization |  | 2023Q3 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-05-16 | 2023-05-30 |  | 2023-06-03 |  | Closed | 2023-06-19 | 2023-07-14 | E//Razif | 2023-07-14 | CelcomDigi_RAN_CCSMY_TSS_Central_20230508_0002 | DU00002008240 |  |  | 2023-07-08 | 2023-07-04 |  | Monopole | 30m Lampole | 30 | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 |  | 1
4000A | MSC Prai | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-17 | 2023-05-19 |  | 2023-05-27 |  | Closed | 2023-06-01 | 2023-06-28 | CD//Quah | 2023-06-21 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0016 | DU00002008241 |  |  | 2023-06-22 | 2023-06-19 |  | Tower | 70m 4 Legged Tower | 77 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
1483H | 99 Speedmart MEDAN SERI PEKAN BANTING | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008242 | [6 empty] | Small Cell
3044C | Jalan Haji Othman Lama | Central |  | Modernization |  | 2023Q3 | HQ 6 | Datasco | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-12 |  | 2023-05-15 |  | Closed | 2023-05-17 | 2023-06-28 | CD//Tee | 2023-06-15 | CelcomDigi_RAN_Datasco_TSS_Central_20230508_0020 | DU00002008243 |  |  | 2023-06-14 | 2023-06-13 |  | Lampole | 24m Lampole | 32m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1088A | Bkt Naga | Central |  | Modernization |  | 2023Q3 | MA | Futong | 4.6 TSSR Approved |  | 2023-05-12 | 2023-05-13 |  | 2023-05-17 |  | Closed | 2023-05-20 | 2023-06-05 | E//Sumitra | 2023-06-01 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002008244 |  | 1. TSSR not complete 2. many info missing 3. wrong schematic diagram for all sec | 2023-07-03 | 2023-06-28 |  | Monopole | 24m Monopole | 31 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
4139C | Perusahaan Pelangi | Northern |  | Modernization |  | 2023Q3 | MH | GCI | 4.6 TSSR Approved |  | 2023-04-28 | 2023-05-08 |  | 2023-05-13 |  | Closed | 2023-05-15 | 2023-05-30 | E//Hazida | 2023-05-30 | Celcom Digi_RAN-GCI-TSS-Northern-20230502-0011 | DU00002008245 |  |  | 2023-06-13 | 2023-06-12 |  | Pole | 3m Bipod (RT) | 4 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882 S1800B(B6B) x3+R8881 S2100 x3
3952B5 | pBTS Zedtee Plywood | Sarawak |  | Modernization |  | 2023Q3 | HQ 2 | Magicell | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-03 |  | 2023-05-05 |  | Closed | 2023-05-09 | 2023-05-15 | CD//John | 2023-05-13 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230505-0005 | DU00002008246 |  |  | 2023-06-12 | 2023-06-08 |  | Guide mast | 25m pBTS | 24m | Add R9264M M1821 x3,Dismantle R8882 S1800(B) x2+R8882 S1800B(B6B) x1+R8862A S2100(A6A) x3 | 0
2931A | Pangsapuri Meru Ehsan | Central |  | Modernization |  | 2023Q3 | HQ 6 | CCSMY | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-18 |  | 2023-05-22 |  | Closed | 2023-05-24 | 2023-07-04 | E//Razif | 2023-07-04 | CelcomDigi_RAN_CCSMY_TSS_Central_20230508_0002 | DU00002008247 |  |  | 2023-07-05 | 2023-06-28 |  | H-bracket pole | 3m Boom (RT) | 6m | Add R9264M M1821 x5,Dismantle R8882 S1800(B) x3+R8862A S1800(B6A) x2+R8862A S2100(A6A) x5 |  | 13
3744A | Lorong Batu Nilam 20A | Central |  | Modernization |  | 2023Q2 | YZ | Ascentrack | 4.6 TSSR Approved |  | 2023-04-17 | 2023-04-28 |  | 2023-04-29 |  | Closed | 2023-05-02 | 2023-05-30 | CD//Norhaliza | 2023-05-29 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230417_0012 | DU00002008248 |  |  | 2023-05-12 | 2023-05-11 |  | Pole | 3m RT (Wall Mounted Pole) | 5 | Add R8894E M1821 x3,Dismantle R8882 S1800B(B6B) x3+R8881 S2100 x3
3605B | Gold Course Hotel | Central |  | Modernization |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-06-20 | 2023-07-04 |  | 2023-07-06 |  | Closed | 2023-07-15 | 2023-07-18 | E//Razif | 2023-07-18 | CelcomDigi_RANMW_Datasco_TSS_Central_20230622_0006 | DU00002008249 |  |  | 2024-01-31 | 2024-01-26 |  | Pole | 3m Boom (RT) | 7m | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
1486H | 99 Speedmart KG DELEK | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008250 | [6 empty] | Small Cell
1151E | Westport T3 (CT 7-1) | Central |  | Remote MOCN | Modernization->Remote MOCN | 2026 | AI | GTSB | 4.6 TSSR Approved |  | 2025-05-26 | 2025-05-27 |  | 2025-05-29 |  | Closed | 2025-05-29 | 2025-07-25 | E// Razif | 2025-05-30 | CelcomDigi_RAN_Datasco_TSS_Central_20230428_0018 | DU00002008251 | [5 empty] | Lampole | Lampole | 35 | Reuse Existing RRU
3630B | Jalan Sungai Bertih | Central |  | Modernization |  | 2023Q3 | HQ 6 | Futong | 4.6 TSSR Approved |  | 2023-05-15 | 2023-05-19 |  | 2023-05-24 |  | Closed | 2023-06-06 | 2023-06-28 | CD//Nik Ashraf | 2023-06-19 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002008252 |  |  | 2023-06-21 | 2023-06-19 |  | Unipole | 3m Bipod (RT) | 5 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8881 S2100 x3+
2697A | Aman Perdana | Central |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-19 | 2023-05-30 |  | 2023-06-06 |  | Closed | 2023-06-12 | 2023-07-14 | E//Razif | 2023-07-14 | CelcomDigi_RAN_CCSMY_TSS_Central_20230508_0002 | DU00002008253 |  |  | 2023-08-14 | 2023-08-10 |  | Pole | 45m Monopole | 35 | Add R9264H M901821 x1 + R9264M M1821 x5,Dismantle R8894E M1821(A8A) x4 |  | 23
1076A | W Binakom | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-18 |  | 2023-04-26 |  | Closed | 2023-04-29 | 2023-05-25 | CD//Tee | 2023-05-12 | CelcomDigi_RAN_Datasco_TSS_Central_20230413_0011 | DU00002008254 |  |  | 2023-05-14 | 2023-05-11 |  | Pole | 30m Monopole | 6m | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 |  | 3
2814A | Klang Parade | Central |  | Modernization |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-05-26 | 2023-07-10 |  | 2023-07-13 |  | Closed | 2023-07-18 | 2023-07-21 | E//Nazrul | 2023-07-20 | CelcomDigi_RANMW_Datasco_TSS_Central_20230529_0004 | DU00002008255 |  |  | 2023-12-05 | 2023-07-26 |  | Pole | 6m RT (Boom) + IBS | Sector 1&2 - 6.5m & Sector 3 - 5m | Add A9732 M1821 x2 + R9264M M1821 x1 ,Dismantle R8854E S1800(A6A) x3+R8854D S2100(A4A) x3 | 13
3627B | Teluk Gong | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-17 | 2023-04-20 |  | 2023-04-20 |  | Closed | 2023-04-20 | 2023-05-12 | CD//Sapian | 2023-05-12 | CelcomDigi_RAN_Datasco_TSS_Central_20230418_0013 | DU00002008256 |  |  | 2023-05-14 | 2023-05-11 |  | Lampole | 30 RDS | 25 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
4042D | Jln Raja Uda (REL) | Northern |  | Modernization |  | 2023Q3 | MH | GCI | 4.6 TSSR Approved |  | 2023-05-01 | 2023-05-03 |  | 2023-05-06 |  | Closed | 2023-05-08 | 2023-05-13 | CD//Quah | 2023-05-13 | Celcom Digi_RAN-GCI-TSS-Northern-20230502-0011 | DU00002008257 |  |  | 2023-06-09 | 2023-06-08 |  | Pole | Land site | 6.1 | Add R9264H M901821 x4,Dismantle R8894E M1821(A8A) x4
1293C | Jalan Kebun Baru | Central |  | Modernization |  | 2023Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-17 |  | 2023-04-19 |  | Closed | 2023-05-05 | 2023-08-22 | E//Razif | 2023-08-22 | CelcomDigi_RAN_AllStar_TSS_Central_20230404_0005 / CelcomDigi_RAN_Allstar_TSS_Central_20230721_ClearLoan | DU00002008258 |  |  | 2023-05-22 | 2023-05-17 |  | Monopole | 24m Lampole | 24M | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
3423B7 | pBTS UIE | Northern |  | Modernization |  | 2023Q2 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-04-18 | 2023-05-02 |  | 2023-05-03 |  | Closed | 2023-05-05 | 2023-05-18 | CD//Shamsul | 2023-05-09 | Celcom Digi_RAN-GCI-TSS-Northern-20230418-0007 | DU00002008259 |  |  | 2023-05-23 | 2023-05-23 |  | Tower | 25m pBTS | 24m | Add R8894E M1821 x3,Dismantle R8882 S1800(B) x3+R8862A S2100(A6A) x3
3935B | Jalan Pandamaran Jaya | Central |  | Modernization |  | 2023Q2 | HQ 6 | Ascentrack | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦a few part of the AAU will be blocked by existing Antenna,and have loadig issue | 2023-04-26 | 2023-05-02 |  | 2023-05-06 |  | Closed | 2023-05-11 | 2023-07-25 | E//Razif | 2023-07-25 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230428_0015 | DU00002008260 | NIC_S2_Change MM to BI_loading issue_Digi OB |  | 2023-05-24 | 2023-05-22 |  |  | 3m Bipod (RT) | 6m | Add R9264M M1821 x5,Dismantle R8894E M1821(A8A) x3 |  | 13
2770A | Surau Tmn Menara Maju | Central |  | Modernization |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-05-16 | 2023-05-17 |  | 2023-05-19 |  | Closed | 2023-05-22 | 2023-06-23 | E//Razif | 2023-06-22 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230517_0019 | DU00002008261 |  |  | 2023-06-10 | 2023-06-10 |  | Lampole | 20m Lampole | 20 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
3312C | Pulau Indah MP | Central |  | Modernization | Modernization->On Hold->Modernization | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-11 | 2023-04-20 |  | 2023-04-15 |  | Closed | 2023-04-19 | 2023-05-08 | CD//Syafiq | 2023-05-03 | CelcomDigi_RAN_Datasco_TSS_Central_20230412_0010 | DU00002008262 |  |  | 2023-05-27 | 2023-05-27 |  | Monopole | 30m Monopole | 45 | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x3+R8894E M1821(A8A) x3+R9224E M1821(AAB) x3 | 123
1780A | Tmn Mewah Baru | Central |  | Modernization |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-27 | 2023-05-17 |  | 2023-05-19 |  | Closed | 2023-05-19 | 2023-07-13 | E//Razif | 2023-07-12 | CelcomDigi_RAN_Datasco_TSS_Central_20230609_0025 | DU00002008263 |  |  | 2023-07-03 | 2023-06-28 |  | Minimast | 3m Bipod (RT) | 13 | Add A9732 M1821 x3,Dismantle R8854E S1800(A6A) x3+R8854D S2100(A4A) x3 | 123
1571B4 | pBTS SMK Dtk Hj Ahmad Said (KM) | Northern |  | Decomm | Modernization->Site out->Replacement, Site Out (Modernization) | 2023Q3 |  | CCSMY | 15.3 Decomm Done without TSSR |  | 2025-07-02 |  |  |  |  | To be Submitted |  |  |  |  | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0016 | DU00002008264 |  |  |  |  | 2025-08-05 |  | 25m pBTS
1432H | 99 Speedmart JENJAROM | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008265 | [6 empty] | Small Cell
4171A | Megamall Prai | Northern |  | Modernization |  | 2023Q3 | MH | GTSB | 4.6 TSSR Approved |  | 2023-04-29 | 2023-05-09 |  | 2023-05-14 |  | Closed | 2023-05-17 | 2023-06-12 | E//Hazida | 2023-06-12 | Celcom Digi_RAN-GTSB-TSS-Northern-20230502-0012 | DU00002008266 |  |  | 2023-06-19 | 2023-06-16 |  |  | 2m RT (Boom) | 2M | Add A9732 M1821 x3,Dismantle R8882 S2600(B4A) x2+R8894E M1821(A8A) x5 | 123
1118A | Perabut Sri Intan | Central |  | Modernization |  | 2023Q3 | SS | Futong | 4.6 TSSR Approved |  | 2023-05-11 | 2023-05-13 |  | 2023-05-16 |  | Closed | 2023-05-24 | 2023-06-19 | E//Razif | 2023-06-19 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002008267 |  |  | 2023-06-10 | 2023-06-10 |  | Minimast | 3m RT (Minimast) | 9 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3
4150C | Sun Media (REL) | Northern |  | Modernization |  | 2023Q3 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-05-02 | 2023-05-10 |  | 2023-05-12 |  | Closed | 2023-05-16 | 2023-05-22 | CD//Affendi | 2023-05-17 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0016 | DU00002008268 |  |  | 2023-06-19 | 2023-06-19 |  | Monople Tree | 3m Bipod (RT) | 45 | Add R8852E S9000 x3 + A9732 M1821 x3 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x4 | 123
1441B | PULAU CAREY | Central |  | Modernization |  | 2023Q2 | IE | Magicell | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-12 |  | 2023-04-14 |  | Closed | 2023-04-14 | 2023-06-03 | CD//Tee | 2023-04-18 | CelcomDigi_RAN_Magicell_TSS_Central_20230411_0002/CelcomDigi_RAN_Magicell_TSS_Central_20230722 | DU00002008269 |  |  | 2023-06-07 | 2023-06-07 |  | Tower | 60m 4 Legged Tower | 60 | Add R9264H M901821 x1 + R9264M M1821 x2,Dismantle R8894E M1821(A8A) x3
1636H | 99 Speedmart Batu Belah | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008270 | [6 empty] | Small Cell
3860B | SYABAS Sijangkang | Central |  | Modernization |  | 2023Q2 | YZ | AllStar | 4.6 TSSR Approved |  | 2023-04-04 | 2023-04-29 |  | 2023-05-03 |  | Closed | 2023-05-04 | 2023-05-22 | CD//Ali akaram | 2023-05-18 | CelcomDigi_RAN_AllStar_TSS_Central_20230404_0005 / CelcomDigi_RAN_Allstar_TSS_Central_20230721_ClearLoan | DU00002008271 |  |  | 2023-05-14 | 2023-05-09 |  | Pole | 3m Boom (RT) | 4 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
3520B | Jalan Kebun Bt4 | Central |  | Modernization |  | 2023Q3 | SS | Futong | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-15 |  | 2023-05-19 |  | Closed | 2023-06-13 | 2023-06-28 | E//Razif | 2023-06-27 | CelcomDigi_RANMW_Futong_TSS_Central_20230508_0001 | DU00002008272 |  |  | 2023-07-09 | 2023-07-08 |  | BillBoard | 3m RT (Minimast) | 18 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 | 23
1768H | 99 Speedmart Rantau Panjang 2 | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008273 | [6 empty] | Rooftop
3970B | Jln Permata 2 | Central |  | Modernization |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-09 | 2023-04-17 |  | 2023-04-19 |  | Closed | 2023-04-27 | 2023-06-21 | CD//Sapian | 2023-06-20 | CelcomDigi_RAN_GTSB_TSS_Central_20230410_0013 | DU00002008274 |  |  | 2023-05-26 | 2023-05-24 |  | Pole | 3m Bipod (RT) | 3m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1863A | JJusco Bkt.Raja | Central |  | Modernization |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-05-26 | 2023-06-08 |  | 2023-06-11 |  | Closed | 2023-06-14 | 2023-09-07 | E//Nazrul | 2023-09-07 | CelcomDigi_RANMW_Datasco_TSS_Central_20230529_0004 | DU00002008275 |  |  | 2023-07-14 | 2023-07-04 |  |  | In-building system |  | Add R8852E S9000 x1 + R8862A S1800 x1 + R8862A S2100 x1,Dismantle R8882-GUL1812 x1
2930A | Jalan Bakti | Central |  | Modernization |  | 2023Q3 | HQ 6 | Datasco | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-09 |  | 2023-05-11 |  | Closed | 2023-05-12 | 2023-06-28 | CD//Tee | 2023-06-28 | CelcomDigi_RAN_Datasco_TSS_20230505_0019 | DU00002008276 |  |  | 2023-06-11 | 2023-06-11 |  | Lampole | 30m Monopole | 20 | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x1
4032C | Taman Desa Pantai | Northern |  | Modernization |  | 2023Q2 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-04-17 | 2023-04-20 |  | 2023-04-19 |  | Closed | 2023-04-26 | 2023-05-18 | CD//Shamsul | 2023-05-05 | Celcom Digi_RAN-GCI-TSS-Northern-20230418-0007 | DU00002008277 |  |  | 2023-05-23 | 2023-05-23 |  | Unipole | 3m Bipod (RT) | 7 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
3420B6 | pBTS Kampung Perigi Nanas | Central |  | Modernization |  | 2026 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-20 |  | 2023-04-20 |  | Closed | 2023-04-27 | 2023-06-03 | CD//Sapian | 2023-05-05 | CelcomDigi_RAN_Datasco_TSS_Central_20230413_0011 | DU00002008278 |  |  | 2023-06-04 | 2023-05-27 |  | Guide mast | 25m pBTS | 24 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
3511A9 | pBTS Rugarding Commercial Center (KM) | Sabah |  | Modernization |  | 2023Q2 | HQ 3 | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-06 |  | 2023-04-26 |  | Closed | 2023-04-28 | 2023-05-10 | CD//Ray Amos | 2023-05-10 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002008279 |  |  | 2023-05-27 | 2023-05-26 |  | Tower | 25m pBTS | 24m | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
1865H | 99 Speedmart Bdr Mahkota Banting | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008280 | [6 empty] | Rooftop
2628B | Jln Mat Raji (REL) | Central |  | Modernization |  | 2023Q3 | YZ | Ascentrack | 4.6 TSSR Approved |  | 2023-05-16 | 2023-05-17 |  | 2023-05-21 |  | Closed | 2023-05-22 | 2023-06-30 | E//Razif | 2023-06-30 | CelcomDigi_RANMW_Ascentrack_TSS_Central_20230517_0002 | DU00002008281 |  |  | 2023-06-12 | 2023-06-12 |  | Lampole | 24m Lampole | 25 | Add R9264H M901821 x3,Dismantle R9224E M1821(AAB) x3 | 0 | 0
1739C | Bulatan Tun Teja | Central |  | Modernization |  | 2023Q3 | SS | Futong | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-15 |  | 2023-05-18 |  | Closed | 2023-05-25 | 2023-06-21 | CD//Norhaliza | 2023-06-21 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002008282 |  |  | 2023-06-25 | 2023-06-13 |  | Monopole | 24m Lampole | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
4088D | ACM Prai | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-15 |  | 2023-05-17 |  | Closed | 2023-05-19 | 2023-06-21 | E//Hazida | 2023-06-21 | Celcom Digi_RAN-GCI-TSS-Northern-20230524-0020 | DU00002008283 |  |  | 2023-06-22 | 2023-06-17 |  | H-bracket pole | 30m Monopole | 6 | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 3
1634H | 99 Speedmart Bdr Bkt Raja 1 | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008284 | [6 empty] | Small Cell
3793A | Masjid Bukit Lipat | Central |  | Modernization |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-05-16 | 2023-05-18 |  | 2023-05-21 |  | Closed | 2023-05-23 | 2023-06-17 | CD//Sapian | 2023-06-16 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230517_0019 | DU00002008285 |  |  | 2023-06-10 | 2023-06-10 |  | Lampole | 24m Lampole | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
4156A | Emc Logistic | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-13 |  | 2023-05-16 |  | Closed | 2023-05-19 | 2023-06-27 | E//Hazida | 2023-06-20 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0016 | DU00002008286 |  |  | 2023-06-16 | 2023-06-14 |  | H-bracket pole | 3m Boom (RT) |  | Add A9732 M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8894E M1821(A8A) x3 | 123
4078C | Fair Park | Northern |  | Modernization |  | 2023Q2 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-13 |  | 2023-04-14 |  | Closed | 2023-04-18 | 2023-05-01 | CD//Heng | 2023-04-26 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230413-0006 | DU00002008287 |  |  | 2023-05-17 | 2023-05-15 |  | Unipole | 3m Bipod (RT) | 6 | Add R9264H M901821 x3 + R9264M M1821 x3 + R8862A S2601 x3,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 |  | 123
2639B | Mutiara Bkt Raja LP 2 | Central |  | Modernization |  | 2023Q3 | HQ 6 | Datasco | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-10 |  | 2023-05-12 |  | Closed | 2023-05-16 | 2023-06-21 | CD//Tee | 2023-06-21 | CelcomDigi_RAN_Datasco_TSS_20230505_0019 | DU00002008288 |  |  | 2023-06-12 | 2023-06-12 |  | Wall mount boom | 3m Bipod (RT) | 4 | Add R9264M M1821 x3,Dismantle R8882 S1800(B) x3+R8881 S2100 x3
1607B | Bandar Bukit Tinggi | Central |  | Modernization |  | 2023Q2 | AI | Ascentrack | 4.6 TSSR Approved |  | 2023-04-17 | 2023-04-25 |  | 2023-04-27 |  | Closed | 2023-05-02 | 2023-05-16 | CD//Tee | 2023-05-11 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230417_0012 | DU00002008289 |  |  | 2023-05-14 | 2023-05-11 |  | Minimast | 6m Unipole RT | 10m | Add R9264M M1821 x5 + R8862A S2601 x2,Dismantle R8894E M1821(A8A) x3 |  | 12
3649B | Jln Sri Sarawak | Central |  | Modernization |  | 2023Q3 | HQ 6 | Ascentrack | 4.6 TSSR Approved |  | 2023-05-06 | 2023-05-09 |  | 2023-05-12 |  | Closed | 2023-05-12 | 2023-06-14 | E//Razif | 2023-06-14 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230508_0017 | DU00002008290 |  |  | 2023-06-14 | 2023-06-13 |  | Lampole | 30m Monopole | 28 | Add R9264M M1821 x4,Dismantle R8862A S1800(B6A) x4+R8854D S2100(A4A) x4
1092A | Swee Leong | Central |  | Modernization |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-05-06 | 2023-05-17 |  | 2023-05-19 |  | Closed | 2023-05-20 | 2023-06-30 | E//Sumitra | 2023-06-30 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230508_0017 | DU00002008291 |  |  | 2023-06-10 | 2023-06-08 |  | Wall mount boom | 3m RT (Wall Mounted Pole) | 6 | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8894E M1821(A8A) x3 |  | 2
3245A | TM_JENJAROM | Central |  | Modernization |  | 2023Q2 | HQ 6 | GTSB | 4.6 TSSR Approved |  | 2023-05-17 | 2023-05-24 |  | 2023-05-31 |  | Closed | 2023-05-31 | 2023-06-06 | E//Razif | 2023-06-01 | CelcomDigi_RAN_GTSB_TSS_Central_20230428_0022 | DU00002008292 |  |  | 2023-08-06 | 2023-06-13 |  | Monopole | 30m Monopole | 46m | Add R8852E S9000 x3 + A9732 M1821 x3 + R9264H M901821 x1,Dismantle R8862A S1800(B6A) x1+R8854E S1800(A6A) x3+R8862A S2100(A6A) x1+R8854D S2100(A4A) x3 | 123
1487H | 99 Speedmart TMN BKT KUDA | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008293 | [6 empty] | Small Cell
1593H | 99 Speedmart KAPAR INDAH | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008294 | [6 empty] | Small Cell
3447B8 | pBTS Kampung Baru 9 Kebun Baru | Central |  | Modernization |  | 2023Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-20 |  | 2023-04-20 |  | Closed | 2023-04-28 | 2023-05-17 | CD//Sapian | 2023-05-05 | CelcomDigi_RAN_AllStar_TSS_Central_20230404_0005 / CelcomDigi_RAN_Allstar_TSS_Central_20230721_ClearLoan | DU00002008295 |  |  | 2023-05-14 | 2023-05-09 |  | Tower | 25m pBTS | 24.4m | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 |  | 3
2805C | Bandar Sultan Suleiman 3 (EB) | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-17 | 2023-04-20 |  | 2023-04-20 |  | Closed | 2023-04-26 | 2023-05-25 | E//Razif | 2023-05-25 | CelcomDigi_RAN_Datasco_TSS_Central_20230418_0013 | DU00002008296 |  |  | 2023-05-12 | 2023-05-11 |  | Lampole | Land site | 30 | Add R9264H M901821 x3,Dismantle R9224E M1821(AAB) x3
4180C | Pantai Remis (REL) | Northern |  | Modernization |  | 2023Q2 | MH | GCI | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-08 |  | 2023-04-15 |  | Closed | 2023-04-17 | 2023-04-27 | CD//Heng | 2023-04-26 | Celcom Digi_RAN-GCI-TSS-Northern-20230414-0005 | DU00002008297 |  |  | 2023-05-16 | 2023-05-15 |  | Monopole | 30m Lampole | 30 | Add R9264H M901821 x3,Dismantle R8882 S1800(B) x3 | 0 | 0
1028C | Bukit Rimau | Central |  | Modernization |  | 2023Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-25 |  | 2023-05-29 |  | Closed | 2023-05-29 | 2023-07-06 | E//Razif | 2023-07-04 | CelcomDigi_RAN_Allstar_TSS_Central_20230511_0007 | DU00002008298 |  |  | 2023-06-17 | 2023-06-13 |  | Lampole | 30m Monopole | 30 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2600 x2,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 13
1318H | 99 Speedmart TMN BANTING BARU | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008299 | [6 empty] | Small Cell
1632H | 99 Speedmart Jln Tepi Sungai | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008300 | [6 empty] | Small Cell
1866H | 99 Speedmart Tmn Intan | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008301 | [6 empty] | Rooftop
1635B | Jalan Batu Nilam | Central |  | Modernization |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-04-17 | 2023-04-27 |  | 2023-04-28 |  | Closed | 2023-05-10 | 2023-05-30 | E//Razif | 2023-05-30 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230417_0012 | DU00002008302 |  |  | 2023-05-20 | 2023-05-20 |  | Pole | 3m RT (Minimast) | 10 | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8882-GUL1812 x4+R8862A S2100(A6A) x3 |  | 3
3982B | Kuil Sri Purvaneshwari Amman | Central |  | Modernization |  | 2023Q3 | IE | Ascentrack | 4.6 TSSR Approved |  | 2023-05-17 | 2023-05-19 |  | 2023-05-23 |  | Closed | 2023-05-23 | 2023-06-29 | E//Razif | 2023-06-28 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230523_0020 | DU00002008303 |  |  | 2023-06-12 | 2023-06-12 |  | Lampole | 24m Lampole | 30 | Add R9264H M901821 x3,Dismantle R8892E M1821(BAA) x3 | 0 | 0
1124A | Bt 15 Banting | Central |  | Modernization |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-05 | 2023-04-13 |  | 2023-04-14 |  | Closed | 2023-04-17 | 2023-05-05 | CD//Ali akaram | 2023-04-28 | CelcomDigi_RAN_GTSB_Central_20230406_0011 | DU00002008304 |  |  | 2023-05-21 | 2023-05-09 |  | Guide mast | 3m RT (Minimast) | 6m | Add R9264M M1821 x5 + R8862A S2601 x2,Dismantle R8882-GUL1812 x4+R8862A S2100(A6A) x5 |  | 13
3901B | Taman Yakin | Central |  | Modernization |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-05-11 | 2023-05-17 |  | 2023-05-21 |  | Closed | 2023-05-22 | 2023-06-13 | E//Razif | 2023-06-13 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230511_0018 | DU00002008305 |  |  | 2023-06-13 | 2023-06-08 |  | H-bracket pole | 3m Boom (RT) | 3 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
3294C | Tlk Panglima Garang (REL) | Central |  | Modernization |  | 2023Q2 | HQ 6 | AllStar | 4.6 TSSR Approved |  | 2023-05-02 | 2023-05-09 |  | 2023-05-12 |  | Closed | 2023-05-15 | 2023-06-06 | E//Razif | 2023-05-31 | CelcomDigi_RAN_AllStar_TSS_Central_20230404_0005 / CelcomDigi_RAN_Allstar_TSS_Central_20230721_ClearLoan | DU00002008306 |  |  | 2023-06-10 | 2023-06-08 |  | Tower | 24m Lampole | 45m | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 |  | 3
1962B | Taman Klang Perdana | Central |  | Modernization |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-27 | 2023-05-18 |  | 2023-06-12 |  | Closed | 2023-06-21 | 2024-12-06 | E//Razif | 2024-12-06 | CelcomDigi_RAN_Datasco_TSS_Central_20230609_0025 | DU00002008307 |  |  | 2023-07-05 | 2023-07-04 |  | Minimast | 3m Boom (RT) | 7 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 12
1653C | Flat Sri Perantau | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-14 | 2023-05-02 |  | 2023-05-03 |  | Closed | 2023-05-05 | 2023-06-06 | E//Razif | 2023-05-31 | CelcomDigi_RAN_Datasco_TSS_Central_20230412_0010 | DU00002008308 |  |  | 2023-05-20 | 2023-05-17 |  | Unipole | Land site | 5 | Add R9264H M901821 x4,Dismantle R8894E M1821(A8A) x4
4037B | Jln Perusahaan Maju 5 | Northern |  | Modernization |  | 2023Q3 | SM | YPTT | 4.6 TSSR Approved |  | 2023-05-02 | 2023-05-11 |  | 2023-05-14 |  | Closed | 2023-05-22 | 2023-05-29 | E//Hazida | 2023-05-28 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0009 | DU00002008309 |  |  | 2023-06-28 | 2023-06-25 |  | Tower | Tower | 60 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
1437H | 99 Speedmart BDR BOTANIK 5 | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008310 | [6 empty] | Small Cell
2045B | KLIA Expressway | Central |  | Modernization |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-04 | 2023-04-05 |  | 2023-04-12 |  | Closed | 2023-04-13 | 2023-05-06 | CD//Sapian | 2023-05-06 | CelcomDigi_RAN_GTSB_TSS_Central_20230405_0010 | DU00002008311 |  |  | 2023-05-14 | 2023-05-09 |  | BillBoard | 4m RT (Billboard) | 25 | Add R9264H M901821 x4,Dismantle R8881 S9000 x1+R8894E M1821(A8A) x4
3211B | SKVE KM 112 (REL) | Central |  | Modernization |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-17 | 2023-05-02 |  | 2023-05-03 |  | Closed | 2023-05-05 | 2023-06-23 | CD//Tee | 2023-06-22 | CelcomDigi_RAN_GTSB_TSS_Central_20230418_0018 / CelcomDigi_TX_GTSB_TSS_Decom_Central_20230717 | DU00002008312 |  |  | 2023-05-27 | 2023-05-15 |  | Monople Tree | 30m Monopole | 45m | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
3355B | Alam Avenue | Central |  | Modernization |  | 2023Q3 | HQ 6 | Ascentrack | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-25 |  | 2023-05-30 |  | Closed | 2023-05-31 | 2023-06-27 | E//Razif | 2023-06-27 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230511_0018 | DU00002008313 |  |  | 2023-06-24 | 2023-06-24 |  | Pole | 3m Bipod (RT) | 4 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R9224E M1821(AAB) x3 |  | 1
1582H | 99 Speedmart Tmn Sentosa Perdana | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008314 | [6 empty] | Small Cell
4158D | Penang Sentral IB | Northern |  | Modernization |  | 2023Q3 | WP | GCI | 4.6 TSSR Approved |  | 2023-06-14 | 2023-06-20 |  | 2023-06-15 |  | Closed | 2023-06-22 | 2023-07-07 | E//Nazrul | 2023-07-03 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0015 | DU00002008315 |  |  | 2023-06-24 | 2023-06-22 |  | Portables BTS | In-building system |  | Add R8862A S1800 x3
3406A | Teluk Datuk (REL) | Central |  | Modernization |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-11 | 2023-04-28 |  | 2023-04-29 |  | Closed | 2023-05-03 | 2023-05-17 | CD//Syafiq | 2023-05-17 | CelcomDigi_RAN_GTSB_TSS_Central_20230412_0015 | DU00002008316 |  |  | 2023-05-17 | 2023-05-13 |  | Tower | Tower | 60m | Add A9732 M1821 x3 + R9264M M1821 x1,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x6 | 123
3433B1 | pBTS Finisar Klebang (M ) | Northern |  | Modernization |  | 2023Q2 | ZA | GCI | 4.6 TSSR Approved |  | 2023-04-18 | 2023-04-26 |  | 2023-04-28 |  | Closed | 2023-05-01 | 2023-05-26 | CD//Shamsul | 2023-05-10 | Celcom Digi_RAN-GCI-TSS-Northern-20230418-0007 | DU00002008317 |  |  | 2023-06-06 | 2023-06-06 |  | Minimast | 25m pBTS | 18 | Add R9264H M901821 x3,Dismantle R8882 S1800(B) x3+R8862A S2100(A6A) x3
1469H | 99 Speedmart TELOK PANGLIMA GARANG 1 | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008318 | [6 empty] | Small Cell
4163A | Raja Uda | Northern |  | Modernization |  | 2023Q3 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-08 |  | 2023-05-10 |  | Closed | 2023-05-11 | 2023-05-25 | CD//Heng | 2023-05-15 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0009 | DU00002008319 |  |  | 2023-06-15 | 2023-06-15 |  |  | 6m Tripod (RT) | 6 | Add A9732 M1821 x3 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x4 | 123
1096A | Klang Perdana | Central |  | Modernization |  | 2023Q3 | XH | Datasco | 4.6 TSSR Approved |  | 2023-04-27 | 2023-05-30 |  | 2023-06-01 |  | Closed | 2023-06-04 | 2023-07-13 | E//Razif | 2023-07-13 | CelcomDigi_RAN_Datasco_TSS_Central_20230609_0025 | DU00002008320 |  |  | 2023-07-19 | 2023-07-18 |  | Tower | 5m RT (Boom) | 30 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x4 | 12
2718A | Sijangkang 2 | Central |  | Modernization |  | 2023Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-12 |  | 2023-04-13 |  | Closed | 2023-04-13 | 2023-05-25 | CD//Sapian | 2023-05-11 | CelcomDigi_RAN_AllStar_TSS_Central_20230404_0005 / CelcomDigi_RAN_Allstar_TSS_Central_20230721_ClearLoan | DU00002008321 |  |  | 2023-05-17 | 2023-05-15 |  | Tower | 60m 4 Legged Tower | 65m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
4054C | Mydin Manjoi | Northern |  | Modernization |  | 2023Q2 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-04-09 |  |  | 2023-04-15 |  | Closed | 2023-04-27 | 2023-05-25 | CD//Quah | 2023-04-28 | Celcom Digi_RAN-GTSB-TSS-Northern-20230410-0007 | DU00002008322 |  |  | 2023-06-06 | 2023-06-03 |  | Unipole | 3m Bipod (RT) | 6.5 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle R8882 S1800(B) x3+R8862A S2100(A6A) x3
2032B | Pandamaran | Central |  | Modernization |  | 2023Q2 | YZ | Datasco | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-29 |  | 2023-05-03 |  | Closed | 2023-05-03 | 2023-06-05 | CD//Ali akaram | 2023-05-15 | CelcomDigi_RAN_Datasco_TSS_Central_20230413_0011 | DU00002008323 |  |  | 2023-06-10 | 2023-05-15 |  | Monopole | 45m Monopole | 45 | Add A9732 M1821 x3,Dismantle R8854E S1800(A6A) x3+R8854D S2100(A4A) x3 | 123
3122B | Jalan Bukit Kuda (HSR) | Central |  | Modernization |  | 2023Q3 | AI | YPTT | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-05 |  | 2023-05-08 |  | Closed | 2023-05-18 | 2023-07-21 | CD//Syafiq | 2023-07-21 | CelcomDigi_RAN_YPTT_TSS_20230505_0002 | DU00002008324 |  |  | 2023-06-16 | 2023-06-14 |  | Unipole | 3m Boom (RT) | 6m | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882 S1800(B) x3
3039M | Klang DS Micro | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008325 | [6 empty] | Micro Cell
4180A | Butterworth Town | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-07 | 2023-06-08 |  | 2023-06-10 |  | Closed | 2023-06-13 | 2023-06-24 | E//Hazida | 2023-06-23 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0016 | DU00002008326 |  |  | 2023-06-25 | 2023-06-19 |  | Pole | 76m Tower | 4 | Add A9732 M1821 x3,Dismantle R8862A S9000(A6A) x1+R8854 S2600(A4A) x1+R8894E M1821(A8A) x4 | 123
1600H | 99 Speedmart RANTAU PANJANG | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008327 | [6 empty] | Small Cell
1590H | 99 Speedmart Jln Ehsan Pandamaran | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008328 | [6 empty] | Small Cell
3435B12 | pBTS Taman Sentosa Kapar (C ) | Central |  | Modernization |  | 2023Q3 | XH | CCSMY | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦pBTS loading issue,AAU cannot install | 2023-08-22 | 2023-08-23 |  | 2023-09-05 |  | Closed | 2023-09-11 | 2023-09-12 | E//Razif | 2023-09-12 | CelcomDigi_RAN_Datasco_TSS_Central_20230426_0017 | DU00002008329 | NIC_S3_Change MM to BI_loading issue_Digi OB |  | 2023-10-06 | 2023-09-23 |  |  | 25m pBTS | 30m | Add R9264M M1821 x3+R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 |  | 123
2475A | Kg Perepat | Central |  | Modernization |  | 2023Q3 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-05-22 | 2023-06-07 |  | 2023-06-10 |  | Closed | 2023-06-13 | 2023-07-13 | E//Razif | 2023-07-13 | CelcomDigi_RANMW_CCSMY_TSS_Central_20230508_0001 | DU00002008330 |  |  | 2023-12-13 | 2023-12-11 |  | Tower | 45m Tower | 45M | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8862A S2600(A4A) x2+R8894E M1821(A8A) x5 | 13
2774A | Pandamaran Indah 2 | Central |  | Modernization |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-04-17 | 2023-04-20 |  | 2023-04-25 |  | Closed | 2023-04-27 | 2023-05-25 | CD//Norhaliza | 2023-06-15 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230417_0012 | DU00002008331 |  |  | 2023-05-12 | 2023-05-11 |  | Pole | 6m RT (Boom) | 3.5m/3m/6m | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
3813A | Taman Seri Putra | Central |  | Modernization |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-05 | 2023-04-29 |  | 2023-04-12 |  | Closed | 2023-05-03 | 2023-05-10 | CD//Sapian | 2023-05-09 | CelcomDigi_RAN_GTSB_TSS_Central_20230405_0010 | DU00002008332 |  |  | 2023-05-17 | 2023-05-15 |  | Pole | 3m Boom (RT) | 4 | Add R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
3255B | Jln Haji Abdul Manan (REL) | Central |  | Modernization |  | 2023Q3 | SS | CCSMY | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI,L2600 change to 40M¦TP rejected by owner as unable to cater additional load. There are 6 telcos sharing the site currently. | 2023-06-16 | 2023-06-21 |  | 2023-06-23 |  | Closed | 2023-06-28 | 2023-07-14 | E//Razif | 2023-07-13 | CelcomDigi_RANMW_CCSMY_TSS_Central_20230508_0001 | DU00002008333 | NIC_S2_Change MM to BI,L2600 change to 40M_loading issue_MAXIS |  | 2023-11-22 | 2023-11-10 |  | Tower | 45m Tower | 46m | Add R9264M M1821 x2+R9264H M901821 x3,Dismantle R8894E M1821(A8A) x4 | 0 | 13
2031B | Bdr Armada Putra 2 | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-11 | 2023-05-17 |  | 2023-05-20 |  | Closed | 2023-05-20 | 2023-06-03 | E//Razif | 2023-05-26 | CelcomDigi_RAN_Datasco_TSS_Central_20230412_0010 | DU00002008334 |  |  | 2023-06-08 | 2023-06-08 |  | Monople Tree | 45m Monopole Tree | 46m | Add A9732 M1821 x1 + R9264M M1821 x2,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x4 | 2
4079C | Greentown Ipoh | Northern |  | Modernization |  | 2023Q2 | WP | GCI | 4.6 TSSR Approved |  | 2023-04-17 | 2023-04-25 |  | 2023-04-27 |  | Closed | 2023-04-26 | 2023-05-12 | CD//Heng | 2023-05-02 | Celcom Digi_RAN-GCI-TSS-Northern-20230418-0007 | DU00002008335 |  |  | 2023-05-29 | 2023-05-27 |  | Minaret | 24m Lampole | 30m | Add R9264M M1821 x3,Dismantle R8882 S1800B(B6B) x3+R8881 S2100 x3
1093A | Kian Hoe Huat | Central |  | Modernization |  | 2023Q2 | YZ | Datasco | 4.6 TSSR Approved |  | 2023-04-11 | 2023-04-20 |  | 2023-04-26 |  | Closed | 2023-04-28 | 2023-05-25 | E//Razif | 2023-05-25 | CelcomDigi_RAN_Datasco_TSS_Central_20230412_0010 | DU00002008336 |  |  | 2023-05-12 | 2023-05-11 |  | Pole | 60m 3 Legged Tower | 4 | Add R9264M M1821 x6,Dismantle R8894E M1821(A8A) x3 |  | 123
4107B | Bukit Minyak (UM) | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-02 | 2023-05-11 |  | 2023-05-16 |  | Closed | 2023-05-19 | 2023-06-20 | E//Hazida | 2023-06-20 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230502-0013 | DU00002008337 |  |  | 2023-07-08 | 2023-07-06 |  | Tower | 76m 4 Legged Tower | 85M | Add A9732 M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8854D S2100(A4A) x3 | 123
1601H | 99 Speedmart SHAH ALAM SEK 34 | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008338 | [6 empty] | Small Cell
3936A | KLIA Expressway 3 (REL) | Central |  | Modernization |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-04 | 2023-04-08 |  | 2023-04-13 |  | Closed | 2023-04-14 | 2023-06-24 | CD//Sapian | 2023-06-23 | CelcomDigi_RAN_GTSB_TSS_Central_20230405_0010 / CelcomDigi_RAN_GTSB_TSS_Central_20230721_ClearLoan | DU00002008339 |  |  | 2023-05-11 | 2023-05-09 |  | BillBoard | Billboard | 24 | Add R8852E S9000 x2 + R8894E M1821 x2,Dismantle R8882 S1800B(B6B) x2+R8881 S2100 x2 | 0 | 0
2949A | Surau Al-Hijrah | Central |  | Modernization |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-05-12 | 2023-05-15 |  | 2023-05-18 |  | Closed | 2023-05-19 | 2023-06-28 | E//Sumitra | 2023-06-28 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230517_0019 | DU00002008340 |  |  | 2023-06-13 | 2023-06-13 |  | Lampole | 24m Lampole | 30 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
1179B | Bkt Raja Ind Park Apartment | Central |  | Modernization |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-06-14 | 2023-06-15 |  | 2023-06-17 |  | Closed | 2023-06-19 | 2023-07-06 | E//Razif | 2023-07-04 | CelcomDigi_RAN_Datasco_TSS_Central_20230616_0026 | DU00002008341 |  |  | 2023-07-05 | 2023-07-03 |  | Lampole | 24m Lampole | 25 | Add R9264M M1821 x3,Dismantle R8882 S1800(B) x3+R8881 S2100 x3 | 0 | 0
3814A | Masjid At-Taqwa Banting (REL) | Central |  | Modernization |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-05 | 2023-04-08 |  | 2023-04-10 |  | Closed | 2023-04-12 | 2023-05-05 | CD//Sapian | 2023-05-02 | CelcomDigi_RAN_GTSB_TSS_Central_20230405_0010 | DU00002008342 |  |  | 2023-05-11 | 2023-05-10 |  | Lampole | 24m Lampole | 25 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
1646B | Kg Sg Pandan | Central |  | Modernization |  | 2023Q2 | YZ | Datasco | 4.6 TSSR Approved |  | 2023-04-14 | 2023-05-09 |  | 2023-05-11 |  | Closed | 2023-05-12 | 2023-06-03 | E//Razif | 2023-05-26 | CelcomDigi_RAN_Datasco_TSS_Central_20230417_0012 | DU00002008343 |  |  | 2023-06-10 | 2023-06-08 |  | Tower | 60m 4 Legged Tower | 80 | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x3+R9224E M1821(AAB) x2 | 123
4053C | TM Jelapang | Northern |  | Modernization |  | 2023Q2 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-23 | 2023-05-22 |  | 2023-05-24 |  | Closed | 2023-05-26 | 2023-06-01 | E//Hazida | 2023-06-01 | Celcom Digi_RAN-GCI-TSS-Northern-20230505-0012 | DU00002008344 |  |  | 2024-02-02 | 2023-08-11 |  | Pole | 3m Bipod (RT) | 3 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
4071D | Taman Perindustrian Beringin | Northern |  | Modernization |  | 2023Q3 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-05-16 | 2023-05-22 |  | 2023-05-24 |  | Closed | 2023-05-26 | 2023-06-20 | E//Hazida | 2023-06-20 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0009 | DU00002008345 |  |  | 2023-07-01 | 2023-06-25 |  | Tower | 30m Lampole | 61M | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2,Dismantle R8894E M1821(A8A) x3 | 1 | 0
1411H | 99 Speedmart BDR PARKLANDS 1 | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008346 | [6 empty] | Small Cell
1631H | 99 Speedmart Taman Sementa Utama | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008347 | [6 empty] | Small Cell
1384H | 99 Speedmart JLN KIM CHUAN | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008348 | [6 empty] | Small Cell
4172H | 99 Speedmart PK TMN MERU 2B | Northern |  | MOCN As-Is |  | 2023Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008349 | [6 empty] | Small Cell
4110R | Kg Gelung Pepuyu | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Zulakmar |  |  | DU00002008350 | [6 empty] | Land site
1781A | Jln Kim Chuan | Central |  | Modernization |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-04-07 |  |  | 2023-04-13 |  | Closed | 2023-04-14 | 2023-05-25 | E//Razif | 2023-05-16 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230407_0009 | DU00002008351 |  |  | 2023-05-23 | 2023-05-23 |  | Unipole | 3m Bipod (RT) | 6m/5m | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
1136A | Tmn Medan Indah | Central |  | Modernization |  | 2023Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-14 |  | 2023-04-17 |  | Closed | 2023-04-18 | 2023-05-25 | CD//Ali akaram | 2023-04-28 | CelcomDigi_RAN_AllStar_TSS_Central_20230404_0005 / CelcomDigi_RAN_Allstar_TSS_Central_20230721_ClearLoan | DU00002008352 |  |  | 2023-05-12 | 2023-05-09 |  | Minimast | 3m Bipod (RT) | 14 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3
2948A | Shell Alam Impian | Central |  | Modernization |  | 2023Q3 | HQ 1 | Futong | 4.6 TSSR Approved |  | 2023-05-25 | 2023-05-29 |  | 2023-06-01 |  | Closed | 2023-06-04 | 2023-06-19 | CD//Nik Ashraf | 2023-06-19 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002008353 |  |  | 2023-06-26 | 2023-06-26 |  | Monopole | 30M RDS | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1105A | Kpg Raja Uda | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-11 |  |  | 2023-04-12 |  | Closed | 2023-04-12 | 2023-05-25 | CD//Tee | 2023-04-28 | CelcomDigi_RAN_Datasco_TSS_Central_20230412_0010 | DU00002008354 |  |  | 2023-05-29 | 2023-05-22 |  | Pole | 3m Boom (RT) | 6 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3
1634B | Bukit Tinggi 2 | Central |  | Modernization |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-04-05 |  |  | 2023-04-06 |  | Closed | 2023-04-18 | 2023-05-25 | CD//Syafiq | 2023-04-19 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230406_0008 | DU00002008355 |  |  | 2023-05-14 | 2023-05-11 |  | Pole | 3m Bipod (RT) | 6 | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x4 |  | 1
1009C | Kampung Telok Gong | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-15 | 2023-04-20 |  | 2023-04-27 |  | Closed | 2023-04-28 | 2023-05-05 | CD//Syafiq | 2023-05-05 | CelcomDigi_RAN_Datasco_TSS_Central_20230417_0012 | DU00002008356 |  |  | 2023-05-23 | 2023-05-17 |  | Tower | 24m Lampole | 50 | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
2726C | Taman Bunga Raya (REL) | Central |  | Modernization |  | 2023Q3 | SS | Futong | 4.6 TSSR Approved |  | 2023-06-16 | 2023-06-09 |  | 2023-06-21 |  | Closed | 2023-06-22 | 2023-07-11 | E//Razif | 2023-07-11 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002008357 |  |  | 2023-07-07 | 2023-07-06 |  | Lampole | Land site | 30 | Add R9264H M901821 x3,Dismantle R9224E M1821(AAB) x3
1538H | 99 Speedmart Jln Kapar Bt 2 | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008358 | [6 empty] | Small Cell
1140A | Celcom Tanjung Sepat | Central |  | Modernization |  | 2023Q2 | HQ 6 | Magicell | 4.6 TSSR Approved |  | 2023-04-17 | 2023-04-20 |  | 2023-04-26 |  | Closed | 2023-04-27 | 2023-06-10 | CD//Tee | 2023-06-01 | CelcomDigi_RAN_Magicell_TSS_Central_20230417_0003 | DU00002008359 |  |  | 2023-05-18 | 2023-05-15 |  | Tower | Tower | 60 | Add R9264M M1821 x6 + R8862A S2601 x3,Dismantle R8894E M1821(A8A) x3 |  | 123
3404A | Telok Gong (REL) | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-11 | 2023-05-10 |  | 2023-05-11 |  | Closed | 2023-05-11 | 2023-06-12 | E//Sumitra | 2023-06-07 | CelcomDigi_RAN_Datasco_TSS_Central_20230412_0010 | DU00002008360 |  |  | 2023-05-17 | 2023-05-15 |  | Monopole | 45m 4 Legged Tower | 45 | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x3+R9224E M1821(AAB) x2 | 123
3297C | Sapura Kemuning (REL) | Central |  | Modernization |  | 2023Q3 | HQ 6 | Futong | 4.6 TSSR Approved |  | 2023-05-19 | 2023-05-22 |  | 2023-05-24 |  | Closed | 2023-05-26 | 2023-06-21 | CD//Norhaliza | 2023-06-21 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002008361 |  |  | 2023-06-25 | 2023-06-24 |  | Unipole | 3m Bipod (RT) | 9 | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 |  | 3
4183H | VR Star | Northern |  | MOCN As-Is |  | 2023Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008362 | [6 empty] | Small Cell
3380A | Bkt Raja Industrial Selatan | Central |  | Modernization |  | 2023Q3 | HQ 1 | Datasco | 4.6 TSSR Approved |  | 2023-05-08 | 2023-06-22 |  | 2023-06-26 |  | Closed | 2023-06-28 | 2023-07-06 | E//Razif | 2023-07-04 | CelcomDigi_RAN_Datasco_TSS_Central_20230508_0020 | DU00002008363 |  |  | 2023-07-20 | 2023-07-18 |  | Lampole | 24m Lampole | 25 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3
1986A | Klang Utara(TMTouch) | Central |  | Modernization |  | 2023Q2 | HQ 1 | Datasco | 4.6 TSSR Approved |  | 2023-05-17 | 2023-05-19 |  | 2023-05-25 |  | Closed | 2023-05-26 | 2023-06-03 | E//Razif | 2023-06-01 | CelcomDigi_RAN_Datasco_TSS_Central_20230428_0018 | DU00002008364 |  |  | 2023-07-15 | 2023-06-13 |  | Tower | Tower | 47m | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 |  | 1
2683C | Olak Lempit | Central |  | Modernization |  | 2023Q2 | MA | GTSB | 4.6 TSSR Approved |  | 2023-04-10 | 2023-04-12 |  | 2023-04-14 |  | Closed | 2023-04-14 | 2023-05-10 | CD//Sapian | 2023-05-10 | CelcomDigi_RAN_GTSB_TSS_Central_20230411_0014 | DU00002008365 |  |  | 2023-05-12 | 2023-05-11 |  | Lampole | Land site | 25m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1002Z | LDG WEST (MN_PCAREYTGH) | Central |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q2 |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Tee |  |  | DU00002008366 | [6 empty] | Land site
4066R | 2220_YLEntpMiniPet_UPTWM1_7 | Northern |  | Decomm | Maintain USP MOCN(Dismantle Passive)->On Hold->Maintain USP MOCN(Dismantle Passive) | 2023Q2 |  | NR services | 15.3 Decomm Done without TSSR |  | 2025-11-03 |  |  |  |  | To be Submitted |  |  | CD//Zulakmar |  | SQ202504230465-NR services | DU00002008367 |  |  |  |  | 2025-08-05 |  | TBC
1561B6 | pBTS Tmn Kapar Setia (C ) | Central |  | Modernization |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-26 | 2023-04-28 |  | 2023-05-05 |  | Closed | 2023-05-09 | 2023-07-17 | E//Razif | 2023-07-14 | CelcomDigi_RAN_Datasco_TSS_Central_20230428_0018 | DU00002008368 |  |  | 2023-07-06 | 2023-06-28 |  | Guide mast | 25m pBTS | 25 | Add R9264H M901821 x3 + R9264M M1821 x2,Dismantle R8894E M1821(A8A) x5 |  | 13(S2->S3,S3->S2,rename sectorID,Bisector @new S1/S3)
4050Z | KGKEDAH | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Zulakmar |  |  | DU00002008369 | [6 empty] | Land site
3294B | Jln Sungai Batu | Central |  | Modernization |  | 2023Q3 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-05-06 | 2023-05-23 |  | 2023-05-29 |  | Closed | 2023-05-29 | 2023-07-17 | E//Razif | 2023-07-14 | CelcomDigi_RAN_CCSMY_TSS_Central_20230428_0001 | DU00002008370 |  |  | 2023-07-06 | 2023-07-04 |  | Wall mount boom | 3m RT (Wall Mounted Pole) | 3 | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 |  | 1
1645B | Port Klang | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-11 | 2023-04-17 |  | 2023-04-18 |  | Closed | 2023-04-19 | 2023-06-22 | E//Razif | 2023-06-21 | CelcomDigi_RAN_Datasco_TSS_Central_20230413_0011 | DU00002008371 |  |  | 2023-05-21 | 2023-05-11 |  | Pole | 5m RT (Wall Mounted Pole) | 7m | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3
1474H | 99 Speedmart TMN RAJA UDA | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008372 | [6 empty] | Small Cell
3141C | Manipal Hospital IB | Central |  | Modernization |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-18 |  | 2023-05-19 |  | Closed | 2023-05-19 | 2023-06-12 | E//Nazrul | 2023-06-12 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230428_0015 | DU00002008373 |  |  | 2023-06-12 | 2023-06-12 |  |  | In-building system |  | Reuse existing RRU
1437B | Jenjarum 2 | Central |  | Modernization |  | 2023Q2 | MA | GTSB | 4.6 TSSR Approved |  | 2023-04-07 | 2023-04-12 |  | 2023-04-17 |  | Closed | 2023-04-18 | 2023-05-25 | CD//Sapian | 2023-05-06 | CelcomDigi_RAN_GTSB_TSS_Central_20230410_0013 | DU00002008374 |  |  | 2023-05-21 | 2023-05-09 |  | Tower | 60m 3 Legged Tower | 45m | Add R9264M M1821 x5 + R8862A S2601 x2,Dismantle R8894E M1821(A8A) x3 |  | 12
3292E | Family Mart Bukit Tinggi 2 | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008375 | [6 empty] | Small Cell
1007Z | BUSUT BARU | Central |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q2 |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Tee |  |  | DU00002008376 | [6 empty] | Land site
2067A | Jusco Bukit Tinggi IB | Central |  | Modernization |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-04-17 | 2023-05-03 |  | 2023-05-06 |  | Closed | 2023-05-16 | 2024-01-11 | E//Razif | 2024-01-11 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230417_0012 | DU00002008377 |  |  | 2023-09-25 | 2023-09-01 |  |  | In-building system |  | Add R8862A S1800 x4 + R8862A S2100 x6 + R8862A S2601 x2,Dismantle R8882 S1800(B) x2+R8840-U216 x2+R8881 S2100 x2
1117A | Sport ToTo | Central |  | Modernization |  | 2023Q3 | YZ | Futong | 4.6 TSSR Approved |  | 2023-05-11 | 2023-05-16 |  | 2023-05-19 |  | Closed | 2023-05-20 | 2023-06-19 | E//Razif | 2023-06-19 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002008378 |  |  | 2023-06-15 | 2023-06-13 |  | Unipole | 3m Boom (RT) | 4 | Add R9264M M1821 x4 + R8862A S2600 x1,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 |  | 2
1627B | Pulau Indah Highway(ZED) | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-06-12 | 2023-06-16 |  | 2023-06-17 |  | Closed | 2023-06-18 | 2023-07-04 | E//Razif | 2023-06-23 | CelcomDigi_RAN_Datasco_TSS_Central_20230428_0018 | DU00002008379 |  |  | 2023-06-27 | 2023-06-26 |  | Tower | 60m 3 Legged Tower | 62 | Add R9264M M1821 x4,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8854D S2100(A4A) x4 |  | 2
1086A | Klang Utama | Central |  | Modernization |  | 2023Q3 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-05-04 | 2023-05-27 |  | 2023-05-30 |  | Closed | 2023-06-02 | 2023-07-14 | E//Razif | 2023-07-14 | CelcomDigi_RAN_CCSMY_TSS_Central_20230428_0001 | DU00002008380 |  |  | 2023-07-03 | 2023-06-28 |  | Rooftop | 24m Monopole | 14M | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x4
1740C | Tmn Cempaka Sari | Central |  | Modernization |  | 2023Q3 | YZ | CCSMY | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-18 |  | 2023-05-22 |  | Closed | 2023-05-23 | 2023-07-07 | E//Razif | 2023-07-06 | CelcomDigi_RAN_CCSMY_TSS_Central_20230508_0002 | DU00002008381 |  |  | 2023-07-06 | 2023-07-04 |  | Lampole | 24M lampole | 30m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1654H | 99 Speedmart Tmn Chodoi Bestari | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008382 | [6 empty] | Rooftop
3876C | Taman Klang Utama | Central |  | Modernization |  | 2023Q3 | HQ 6 | CCSMY | 4.6 TSSR Approved |  | 2023-05-11 | 2023-06-06 |  | 2023-06-09 |  | Closed | 2023-06-14 | 2023-07-13 | E//Razif | 2023-07-13 | CelcomDigi_RAN_CCSMY_TSS_Central_20230428_0001 | DU00002008383 |  |  | 2023-07-06 | 2023-07-04 |  | Lampole | 24m Lampole | 24m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
1460H | 99 Speedmart KLANG SENTRAL | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008384 | [6 empty] | Small Cell
2794A | Pantai Kelanang | Central |  | Modernization |  | 2023Q2 | IE | Magicell | 4.6 TSSR Approved |  | 2023-04-07 |  |  | 2023-04-28 |  | Closed | 2023-05-02 | 2023-05-10 | CD//Tee | 2023-05-02 | CelcomDigi_RAN_Magicell_TSS_Central_20230411_0002/CelcomDigi_RAN_Magicell_TSS_Central_20230722 | DU00002008385 |  |  | 2023-05-27 | 2023-05-27 |  | Tower | 60m 4 Legged Tower | 65 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8882-GUL1812 x1+R8882 S1800B(B6B) x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3 |  | 1
3247C | Ambang Botanic 2 (REL) | Central |  | Modernization |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-17 |  | 2023-05-20 |  | Closed | 2023-05-22 | 2023-06-12 | E//Razif | 2023-06-12 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230511_0018 | DU00002008386 |  |  | 2023-06-11 | 2023-06-08 |  | Lampole | Land site | 25 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
3650B | Bandar Botanic 2 | Central |  | Modernization |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-04-05 |  |  | 2023-04-19 |  | Closed | 2023-04-19 | 2023-05-25 | CD//Norhaliza | 2023-05-16 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230405_0007 | DU00002008387 |  |  | 2023-05-14 | 2023-05-11 |  | Pole | 3m Bipod (RT) | 6m | Add R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8881 S2100 x3
3357A11 | pBTS FO GUANG SHAH DONG CNY 2023 | Central |  | Site Out (Modernization) | Modernization->MOCN Decomm->Site Out->Site Out (Modernization) | 2023Q2 |  | GTSB | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2025-07-15 |  | 2025-07-02 |  |  | To be Submitted |  |  |  |  | SQ202506170074 | DU00002008388 | [6 empty] | PBTS
3957B5 | pBTS Jalan Sidang | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-10 | 2023-04-26 |  | 2023-04-14 |  | Closed | 2023-04-15 | 2023-05-06 | CD//Sapian | 2023-05-07 | CelcomDigi_RAN_Datasco_TSS_Central_20230411_0009 | DU00002008389 |  |  | 2023-06-01 | 2023-05-27 |  | Minimast | 25m pBTS | 25 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1127A | Kg. Morib | Central |  | Modernization |  | 2023Q2 | XH | Magicell | 4.6 TSSR Approved |  | 2023-05-26 | 2023-05-30 |  | 2023-06-02 |  | Closed | 2023-06-06 | 2023-06-13 | E//Razif | 2023-06-13 | CelcomDigi_RAN_Magicell_TSS_Central_20230428_0005 | DU00002008390 |  |  | 2023-06-23 | 2023-06-22 |  | Tower | 30m 4 Legged Tower | 46M | Add R9264M M1821 x6 + R8862A S2601 x3,Dismantle R8894E M1821(A8A) x3 |  | 123
2823A | Shaw Center Point | Central |  | Modernization |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-05-26 | 2023-06-08 |  | 2023-06-13 |  | Closed | 2023-06-20 | 2023-06-20 | E//Razif | 2023-06-20 | CelcomDigi_RAN_Datasco_TSS_Central_20230529_0023 | DU00002008391 |  |  | 2023-07-15 | 2023-06-28 |  |  | In-building system |  | Add R8862A S1800 x1 + R8862A S2100 x1,Dismantle R8882-GUL1812 x1
1793A | Sek 17 Shah Alam | Central |  | Modernization |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-24 |  | 2023-05-26 |  | Closed | 2023-05-29 | 2023-06-27 | E//Sumitra | 2023-06-27 | CelcomDigi_RANMW_Ascentrack_TSS_Central_20230511_0001 | DU00002008392 |  |  | 2023-08-29 | 2023-06-28 |  | Unipole | 6m Tripod (RT) | 6.1 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8882-GUL1812 x3+R8840-U216 x3++ |  | 2
2677C | Tmn Kemuning Banting | Central |  | Modernization |  | 2023Q2 | MA | GTSB | 4.6 TSSR Approved |  | 2023-04-07 | 2023-04-17 |  | 2023-04-13 |  | Closed | 2023-04-20 | 2023-05-25 | CD//Sapian | 2023-05-10 | CelcomDigi_RAN_GTSB_TSS_Central_20230410_0013 | DU00002008393 |  |  | 2023-05-12 | 2023-05-11 |  | Lampole | Land site | 24M | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
2033B | Kampung Sg Kandis | Central |  | Modernization |  | 2023Q3 | HQ 6 | Futong | 4.6 TSSR Approved |  | 2023-05-16 | 2023-05-19 |  | 2023-05-24 |  | Closed | 2023-05-25 | 2023-06-12 | E//Razif | 2023-06-12 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002008394 |  |  | 2023-06-14 | 2023-06-13 |  | Monopole | Tower | 31 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
3006A4 | pBTS Inanam Capital (KM) | Sabah |  | Modernization |  | 2023Q3 | MS | YPTT | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦Limitted space to install AAU,Space is ouccuped by cable and limitted space to install new AAU. | 2023-04-08 | 2023-04-29 |  | 2023-06-30 |  | Closed | 2023-05-26 | 2023-06-12 | E//Hannah | 2023-06-12 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230407-0002 | DU00002008395 | NIC_S2_Change MM to BI_Space constraint_Digi OB |  | 2023-07-12 | 2023-07-08 |  | Minimast | 25m pBTS | 24.5 | Add R9264H M901821 x3 + R9264M M1821 x2,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x2 |  | 12
1375H | 99 Speedmart Bdr Botanik 4 | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008396 | [6 empty] | Rooftop
1787A | P.Indah Industrial Park | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-11 | 2023-04-14 |  | 2023-04-17 |  | Closed | 2023-04-18 | 2023-07-28 | E//Razif | 2023-07-28 | CelcomDigi_RAN_Datasco_TSS_Central_20230413_0011 / CelcomDigi_RAN_Datasco_TSS_Central_20230721_ClearLoan | DU00002008397 |  |  | 2023-06-10 | 2023-06-08 |  | Rooftop | 3m Bipod (RT) | 6 | Add R8862A S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
1090A | Hin Hua | Central |  | Modernization |  | 2023Q3 | YZ | Futong | 4.6 TSSR Approved |  | 2023-05-12 | 2023-05-24 |  | 2023-05-27 |  | Closed | 2023-05-30 | 2023-06-24 | CD//Ali akaram | 2023-06-23 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002008398 |  |  | 2023-07-05 | 2023-06-28 |  | Pole | 3m Boom (RT) | 4 | Add R9264M M1821 x5,Dismantle R8854E S1800(A6A) x3+R8854D S2100(A4A) x3 |  | 13
4085C | Lang Indah | Northern |  | Modernization |  | 2023Q2 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-04-13 | 2023-04-20 |  | 2023-04-18 |  | Closed | 2023-04-25 | 2023-05-11 | CD//Heng | 2023-04-27 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230414-0007 | DU00002008399 |  |  | 2023-05-29 | 2023-05-27 |  | Lampole | 30m Monopole | 30 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8862A S1800(B6A) x3 |  | 12
3511B | Wetland Park | Central |  | Modernization |  | 2023Q2 | AI | AllStar | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦Limitted space to install AAU,Space is ouccuped by cable and limitted space to install new AAU. | 2023-04-03 | 2023-04-28 |  | 2023-05-02 |  | Closed | 2023-05-03 | 2023-05-18 | CD//Sapian | 2023-05-18 | CelcomDigi_RAN_AllStar_TSS_Central_20230404_0005 / CelcomDigi_RAN_Allstar_TSS_Central_20230721_ClearLoan | DU00002008400 | NIC_S1_Change MM to BI_Space constraint_OCK TELCO INFRA |  | 2023-05-29 | 2023-05-17 |  | Monopole | 30m Monopole | 30 | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 |  | 3
1651C | Matrikulasi banting | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-14 | 2023-04-17 |  | 2023-04-18 |  | Closed | 2023-04-26 | 2023-05-14 | CD//Sapian | 2023-05-14 | CelcomDigi_RAN_Datasco_TSS_Central_20230417_0012 | DU00002008401 |  |  | 2023-05-24 | 2023-05-22 |  | Lampole | 30m Lampole | 30m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1470B | Surau Al-Raudhah Bkt Naga | Central |  | Modernization |  | 2023Q3 | SS | Futong | 4.6 TSSR Approved |  | 2023-05-29 | 2023-05-29 |  | 2023-06-01 |  | Closed | 2023-06-20 | 2023-07-11 | E//Razif | 2023-07-11 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002008402 |  |  | 2023-07-10 | 2023-07-07 |  | Lampole | 20m Lampole | 20 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x2+R8862A S2100(A6A) x3
3533B | Pulau Indah Billboard | Central |  | Modernization |  | 2023Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2023-04-03 |  |  | 2023-04-13 |  | Closed | 2023-04-14 | 2023-05-22 | CD//Syafiq | 2023-04-18 | CelcomDigi_RAN_AllStar_TSS_Central_20230404_0005 / CelcomDigi_RAN_Allstar_TSS_Central_20230721_ClearLoan | DU00002008403 |  |  | 2023-05-15 | 2023-05-09 |  | BillBoard | Billboard | 20M | Add R9264M M1821 x4,Dismantle R8882 S1800B(B6B) x2+R8862A S1800(B6A) x2+R8854D S2100(A4A) x4
4183A | Bukit Minyak | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-15 |  | 2023-05-18 |  | Closed | 2023-05-19 | 2023-06-20 | E//Hazida | 2023-06-20 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0016 | DU00002008404 |  |  | 2023-06-17 | 2023-06-16 |  | Wall mount boom | 6m RT (Boom) | 7 | Add A9732 M1821 x3,Dismantle R9224E M1821(AAB) x3 | 123
1112A | Restoran 999 | Central |  | Modernization |  | 2023Q3 | MA | Futong | 4.6 TSSR Approved |  | 2023-05-11 | 2023-05-13 |  | 2023-05-16 |  | Closed | 2023-05-18 | 2023-06-12 | E//Razif | 2023-06-12 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002008405 |  |  | 2023-07-07 | 2023-07-07 |  | Pole | 6m Tripod (RT) | 7/9 | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3 |  | 3
1008C | Bandar Bestari | Central |  | Modernization |  | 2023Q2 | MA | AllStar | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-10 |  | 2023-04-12 |  | Closed | 2023-04-12 | 2023-04-20 | CD//Syafiq | 2023-04-20 | CelcomDigi_RAN_AllStar_TSS_Central_20230404_0005 / CelcomDigi_RAN_Allstar_TSS_Central_20230721_ClearLoan | DU00002008406 |  |  | 2023-05-14 | 2023-05-11 |  | Monopole | 30m Monopole |  | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
4106B | Taman Alma Jaya | Northern |  | Modernization |  | 2023Q3 | MH | GCI | 4.6 TSSR Approved |  | 2023-05-06 | 2023-05-08 |  | 2023-05-12 |  | Closed | 2023-05-16 | 2023-06-20 | E//Hazida | 2023-06-20 | Celcom Digi_RAN-GCI-TSS-Northern-20230502-0011 | DU00002008407 |  |  | 2023-06-20 | 2023-06-16 |  | Pole | 6m RT (Boom) | 5 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 |  | 1
2771A | Tmn Bendahara | Central |  | Modernization |  | 2023Q3 | MA | Futong | 4.6 TSSR Approved |  | 2023-05-19 | 2023-05-23 |  | 2023-05-26 |  | Closed | 2023-05-30 | 2023-06-28 | CD//Norhaliza | 2023-06-26 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002008408 |  |  | 2023-07-03 | 2023-06-28 |  | Pole | 3m RT (Wall Mounted Pole) | 6 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
2631B | Perepat MP | Central |  | Modernization |  | 2023Q3 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-05-13 | 2023-05-24 |  | 2023-05-27 |  | Closed | 2023-05-29 | 2023-07-14 | E//Razif | 2023-07-14 | CelcomDigi_RAN_CCSMY_TSS_Central_20230508_0002 | DU00002008409 |  |  | 2023-07-01 | 2023-06-28 |  | Monopole | 30m Monopole Tree | 35m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
3592B4 | pBTS Jalan Kebun Baru Batu 9 | Central |  | Modernization |  | 2023Q2 | HQ 6 | AllStar | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-28 |  | 2023-05-03 |  | Closed | 2023-05-05 | 2023-07-18 | E//Sumitra | 2023-07-17 | CelcomDigi_RAN_AllStar_TSS_Central_20230404_0005 / CelcomDigi_RAN_Allstar_TSS_Central_20230721_ClearLoan | DU00002008410 |  |  | 2023-05-19 | 2023-05-17 |  | Tower | 25m pBTS | 25 | Add R9264H M901821 x3 + R9264M M1821 x2,Dismantle R8854E S1800(A6A) x3+R8854D S2100(A4A) x3+R9224E M1821(AAB) x2 |  | 13
3180B2 | pBTS McD Kingfisher Sulaman (M) | Sabah |  | Modernization |  | 2023Q3 | HQ 3 | GTSB | 4.6 TSSR Approved |  | 2023-04-04 | 2023-04-20 |  | 2023-04-26 |  | Closed | 2023-04-28 | 2023-05-10 | CD//Ray Amos | 2023-05-10 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230407-0002 | DU00002008411 |  |  | 2023-06-11 | 2023-06-09 |  | Guide mast | 25m pBTS | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1181B | Tmn Sri Pinang | Central |  | Modernization |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-10 |  | 2023-05-30 |  | Closed | 2023-05-20 | 2023-06-03 | E//Sumitra | 2023-05-23 | CelcomDigi_RAN_Datasco_TSS_20230505_0019 | DU00002008412 |  |  | 2023-07-17 | 2023-07-15 |  | Tower | 45m 4 Legged Tower | 55m | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
3997B | Maahad Tahfiz Alam Impian | Central |  | Modernization |  | 2023Q3 | MA | Futong | 4.6 TSSR Approved |  | 2023-05-20 | 2023-05-30 |  | 2023-06-02 |  | Closed | 2023-06-03 | 2023-06-28 | CD//Nik Ashraf | 2023-06-20 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002008413 |  |  | 2023-07-10 | 2023-07-10 |  | Monople Tree | 45m Monopole | 44 | Add R9264H M901821 x1 + R9264M M1821 x1 + A9732 M1821 x2,Dismantle R8862A S1800(B6A) x4+R8862A S2100(A6A) x4 | 12
1642H | 99 Speedmart Alam Impian | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008414 | [6 empty] | Small Cell
1617H | 99 Speedmart Tmn Sejati | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008415 | [6 empty] | Small Cell
2492A | Tmn Pandamaran Indah 2 | Central |  | Modernization |  | 2023Q2 | AI | CCSMY | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦Maxis reject add AAU | 2023-06-07 | 2023-06-09 |  | 2023-06-10 |  | Closed | 2023-06-28 | 2023-09-08 | E//Razif | 2023-09-08 | CelcomDigi_RAN_AllStar_TSS_Central_20230404_0005 / CelcomDigi_RAN_Allstar_TSS_Central_20230721_ClearLoan | DU00002008416 | NIC_S1_Change MM to BI_Space constraint_MAXIS |  | 2023-11-24 | 2023-10-26 |  | Tower | 60m 3 Legged Tower | 60m | Add R9264M M1821 x4+R8862A S2601 x1,Dismantle R8894E M1821(A8A) x3 | 0 | 3
3041C | Idaman Sentosa (REL) | Central |  | Modernization |  | 2023Q3 | SS | Futong | 4.6 TSSR Approved |  | 2023-05-16 | 2023-05-18 |  | 2023-05-22 |  | Closed | 2023-05-24 | 2023-06-20 | E//Sumitra | 2023-06-20 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002008417 |  |  | 2023-07-06 | 2023-06-28 |  | Pole | 3m Boom (RT) | 6 | Add R9264H M901821 x3 + R9264M M1821 x2,Dismantle R8894E M1821(A8A) x5 |  | 23
2634B | Jalan Keretapi Lama | Central |  | Modernization |  | 2023Q3 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-05-29 | 2023-06-08 |  | 2023-06-10 |  | Closed | 2023-06-12 | 2023-07-14 | E//Razif | 2023-07-14 | CelcomDigi_RAN_CCSMY_TSS_Central_20230508_0002 | DU00002008418 |  |  | 2023-07-01 | 2023-06-28 |  | Tower | 45m Tower | 30m + 30m = 60m | Add R9264H M901821 x4,Dismantle R8894E M1821(A8A) x4
1100A | Chop Lee Heng | Central |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-05-06 | 2023-05-12 |  | 2023-05-15 |  | Closed | 2023-05-18 | 2023-06-27 | E//Sumitra | 2023-06-27 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002008419 |  |  | 2023-06-14 | 2023-06-13 |  | Minimast | 3m RT (Minimast) | 15m | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3+R8882 S1800(B) x1+R8862A S2100(A6A) x3
4159H | 99 Speedmart PK TMN TASEK DAMAI | Northern |  | MOCN As-Is |  | 2023Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008420 | [6 empty] | Small Cell
1636B | Sri Andalas | Central |  | Modernization |  | 2023Q3 | HQ 6 | Ascentrack | 4.6 TSSR Approved |  | 2023-05-11 | 2023-05-13 |  | 2023-05-16 |  | Closed | 2023-05-18 | 2023-06-05 | E//Sumitra | 2023-05-24 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230511_0018 | DU00002008421 |  |  | 2023-06-19 | 2023-06-19 |  | Minimast | 3m RT (Minimast) | 12m | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
4042B | Bagan Lalang (REL) | Northern |  | Modernization |  | 2023Q3 | MH | GCI | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-11 |  | 2023-05-11 |  | Closed | 2023-05-15 | 2023-06-21 | E//Hazida | 2023-06-14 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0015 | DU00002008422 |  |  | 2023-06-19 | 2023-06-17 |  | Minimast | 6m Unipole RT | 6.3 | Add R8894E M1821 x3,Dismantle R8882 S1800B(B6B) x3+R8881 S2100 x3
1080A | WIT | Central |  | Modernization |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-04-17 | 2023-04-20 |  | 2023-04-25 |  | Closed | 2023-04-26 | 2023-05-22 | CD//Tee | 2023-05-09 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230417_0012 | DU00002008423 |  |  | 2023-05-29 | 2023-05-22 |  | Pole | 3m RT (Wall Mounted Pole) | 6m | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3
2040A | Sg Kandis | Central |  | Modernization |  | 2023Q3 | HQ 6 | Futong | 4.6 TSSR Approved |  | 2023-05-19 | 2023-05-26 |  | 2023-05-30 |  | Closed | 2023-06-01 | 2023-06-28 | CD//Nik Ashraf | 2023-06-20 | CelcomDigi_RANMW_Futong_TSS_Central_20230508_0001 | DU00002008424 |  |  | 2023-11-29 | 2023-11-10 |  | Tower | 45m Tower | 46 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x2
1133A | Tlk Panglima Garang | Central |  | Site Out (Modernization) | Modernization->Site out->Replacement, Site Out (Modernization) | 2023Q2 | AI | GCI | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-20 |  | 2023-04-28 |  | Closed | 2023-05-01 | 2023-06-06 | CD//Ali akaram | 2023-05-08 | CelcomDigi_RAN_AllStar_TSS_Central_20230404_0005 / CelcomDigi_RAN_Allstar_TSS_Central_20230721_ClearLoan | DU00002008425 | [5 empty] | Tower | 45m 4 Legged Tower | 60
1014C | Desa Alam | Central |  | Modernization |  | 2023Q3 | HQ 6 | Datasco | 4.6 TSSR Approved |  | 2023-05-05 | 2023-06-07 |  | 2023-06-09 |  | Closed | 2023-06-14 | 2023-07-06 | E//Razif | 2023-07-05 | CelcomDigi_RANMW_Datasco_TSS_Central_20230508_0003 | DU00002008426 |  |  | 2023-07-05 | 2023-06-28 |  | Lampole | Tower | 20 | Add R9264H M901821 x1 + R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8894E M1821(A8A) x4 |  | 4(S1->S2,S2->S3,S3->S1,rename Sector ID,,Bisector@New S4)
2646B | TM Jln Kebun | Central |  | Modernization |  | 2023Q3 | XH | Futong | 4.6 TSSR Approved |  | 2023-05-31 | 2023-06-02 |  | 2023-06-08 |  | Closed | 2023-06-15 | 2023-06-27 | E//Razif | 2023-06-27 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002008427 |  |  | 2024-01-14 | 2024-01-11 |  | Tower | 30m Monopole | 60 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
4027C | Bt 10 Lekir | Northern |  | Modernization |  | 2023Q2 | MH | GTSB | 4.6 TSSR Approved |  | 2023-04-19 | 2023-04-26 |  | 2023-04-27 |  | Closed | 2023-04-28 | 2023-05-25 | CD//Quah | 2023-05-11 | Celcom Digi_RAN-GTSB-TSS-Northern-20230425-0012 | DU00002008428 |  |  | 2023-06-06 | 2023-06-06 |  | Tower | 4 Legged Tower | 120m | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
4129C | Tong Guan Knitting | Northern |  | Modernization |  | 2023Q2 | WP | GCI | 4.6 TSSR Approved |  | 2023-04-18 | 2023-04-20 |  | 2023-04-18 |  | Closed | 2023-04-24 | 2023-05-15 | CD//Shamsul | 2023-05-05 | Celcom Digi_RAN-GCI-TSS-Northern-20230419-0008 | DU00002008429 |  |  | 2023-05-22 | 2023-05-20 |  | H-bracket pole | 3m RT (Wall Mounted Pole) | 6m | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882 S1800B(B6B) x3+R8881 S2100 x3
2678C | Tmn Pendamaran Indah 1 | Central |  | Modernization |  | 2023Q2 | YZ | Ascentrack | 4.6 TSSR Approved |  | 2023-04-17 | 2023-04-29 |  | 2023-05-02 |  | Closed | 2023-05-04 | 2023-05-31 | E//Sumitra | 2023-05-31 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230417_0012 | DU00002008430 |  |  | 2023-05-15 | 2023-05-13 |  | Lampole | Land site | 25 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1495H | 99 Speedmart PORT KLANG 2 | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008431 | [6 empty] | Small Cell
1930B | Tanjung Dua Belas (Celcom) | Central |  | Modernization |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-03 | 2023-04-06 |  | 2023-04-06 |  | Closed | 2023-04-11 | 2023-06-27 | CD//Tee | 2023-06-27 | CelcomDigi_RAN_GTSB_TSS_Central_20230404_0009 / CelcomDigi_RAN_GTSB_TSS_Central_20230721_ClearLoan | DU00002008432 |  |  | 2023-05-20 | 2023-05-17 |  | Tower | 45m 4 Legged Tower | 46 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8894E M1821(A8A) x3 |  | 13
3170B3 | pBTS Kg Labohan Dagang | Central |  | Modernization |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-09 | 2023-04-20 |  | 2023-04-14 |  | Closed | 2023-04-20 | 2023-05-10 | CD//Sapian | 2023-05-10 | CelcomDigi_RAN_GTSB_TSS_Central_20230410_0013 | DU00002008433 |  |  | 2023-05-12 | 2023-05-11 |  | Guide mast | Land site | 26m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1013C | Tmn Banting Baru | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-16 | 2023-04-20 |  | 2023-04-26 |  | Closed | 2023-04-29 | 2023-05-10 | CD//Sapian | 2023-05-10 | CelcomDigi_RAN_Datasco_TSS_Central_20230417_0012 | DU00002008434 |  |  | 2023-05-16 | 2023-05-11 |  | Lampole | Tower | 30 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
1019E | West Port CT6-1 Pole | Central |  | Modernization | MOCN As-Is->Modernization | 2026 | AI | GTSB | 4.6 TSSR Approved |  | 2025-05-26 | 2025-05-23 |  | 2025-05-28 |  | Under Approval | 2025-05-28 | 2025-07-25 | E// Razif | 2025-05-30 | SQ202502170746 | DU00002008435 |  |  | 2026-03-10 | 2026-03-10 |  | Tower | Small Cell | 36m | Add A8612 M1821 x2+R8894E M1821 x1, Dismantle A8602 M1821x3
1149E | Westport T1 (CT 9-2) | Central |  | Remote MOCN | Modernization->Remote MOCN | 2026 | AI | GTSB | 4.6 TSSR Approved |  | 2025-05-26 | 2025-05-27 |  | 2025-05-28 |  | Closed | 2025-06-03 | 2025-07-25 | E//Razif | 2025-06-04 | CelcomDigi_RAN_Datasco_TSS_Central_20230428_0018 | DU00002008436 | [5 empty] | Lampole | Lampole | 43m | Reuse Existing RRU
1923B | Kg Sijangkang(KJS) | Central |  | Modernization |  | 2023Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2023-04-05 |  |  | 2023-04-28 |  | Closed | 2023-05-03 | 2023-05-12 | CD//Tee | 2023-05-12 | CelcomDigi_RAN_AllStar_TSS_Central_20230404_0005 / CelcomDigi_RAN_Allstar_TSS_Central_20230721_ClearLoan | DU00002008437 |  |  | 2023-05-17 | 2023-05-15 |  | Tower | Tower | 60m | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
4122D | Taman Anjung Tawas Sinaran | Northern |  | Modernization |  | 2023Q2 | MH | GTSB | 4.6 TSSR Approved |  | 2023-04-13 | 2023-04-20 |  | 2023-04-26 |  | Closed | 2023-04-27 | 2023-05-25 | CD//Shamsul | 2023-05-10 | Celcom Digi_RAN-GTSB-TSS-Northern-20230414-0010 | DU00002008438 |  |  | 2023-06-06 | 2023-06-02 |  | Minimast | 3m Boom (RT) | 8 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
1924B | Bdr Seri Ehsan | Central |  | Modernization |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-29 | 2023-05-04 |  | 2023-05-06 |  | Closed | 2023-05-09 | 2023-05-31 | E//Razif | 2023-10-18 | CelcomDigi_RAN_GTSB_TSS_Central_20230428_0022 | DU00002008439 |  |  | 2023-05-13 | 2023-05-11 |  | Tower | 45m Tower | 48 | Add R8852E S9000 x2 + R8894E M1821 x3,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x2+R8840-U216 x3
3634B | Tmn Pendamar Indah | Central |  | Modernization |  | 2023Q2 | YZ | Ascentrack | 4.6 TSSR Approved |  | 2023-04-17 | 2023-04-27 |  | 2023-04-29 |  | Closed | 2023-05-02 | 2023-06-07 | E//Sumitra | 2023-06-06 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230417_0012 | DU00002008440 |  |  | 2023-05-16 | 2023-05-15 |  | Lampole | 24m Lampole | 26m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
2610A3 | pBTS Hospital Likas | Sabah |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-04-07 | 2023-04-25 |  | 2023-04-27 |  | Closed | 2023-04-28 | 2023-05-22 | CD//Ray Amos | 2023-05-03 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230407-0002 | DU00002008441 |  |  | 2023-06-19 | 2023-06-09 |  | Guide mast | 25m pBTS | 30m | Add R9264H M901821 x3,Dismantle R8854E S1800(A6A) x3+R8862A S2100(A6A) x6
1623H | 99 Speedmart TMN PINANG RAJA | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008442 | [6 empty] | Small Cell
1640B | Permatang Pasir (Maxis) | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-06 |  | 2023-05-09 |  | Closed | 2023-05-12 | 2023-06-03 | E//Razif | 2023-05-30 | CelcomDigi_RAN_Datasco_TSS_Central_20230428_0018 | DU00002008443 |  |  | 2023-06-17 | 2023-06-17 |  | Tower | Tower | 60 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3
1957B | Teluk Gong Seafood | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-11 | 2023-04-29 |  | 2023-05-03 |  | Closed | 2023-05-04 | 2023-06-03 | E//Sumitra | 2023-06-02 | CelcomDigi_RAN_Datasco_TSS_Central_20230412_0010 | DU00002008444 |  |  | 2023-05-22 | 2023-05-15 |  | Monopole | 30m Monopole | 30m | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x5 | 13
4182B | Butterworth Outer Hw 1 | Northern |  | Modernization |  | 2023Q3 | MH | GTSB | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-11 |  | 2023-05-14 |  | Closed | 2023-05-16 | 2023-05-22 | CD//Affendi | 2023-05-17 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0016 | DU00002008445 |  |  | 2023-06-07 | 2023-06-07 |  | Wall mount boom | 3m Boom (RT) |  | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
2664B | JLN SG PINANG | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-16 | 2023-04-20 |  | 2023-04-28 |  | Closed | 2023-05-03 | 2023-06-03 | CD//Norhaliza | 2023-05-17 | CelcomDigi_RAN_Datasco_TSS_Central_20230417_0012 | DU00002008446 |  |  | 2023-06-24 | 2023-06-13 |  | Lampole | 30m Lampole | 30 | Add R9264M M1821 x5,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x2 |  | 23
3573A | GM KLANG WHOLESALE CITY IB | Central |  | Modernization |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-04-17 | 2023-06-14 |  | 2023-06-14 |  | Closed | 2023-06-15 | 2023-06-17 | E//Nazrul | 2023-06-15 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230417_0012 | DU00002008447 |  |  | 2023-09-25 | 2023-09-18 |  |  | In-building system | 3 | Add R8862A S1800 x3 + R8862A S2100 x3 + R8862A S2601 x2,Dismantle R8882 S1800(B) x1+R8882 S1800B(B6B) x2
4173A | Taman Kelasah | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-11 | 2023-05-25 |  | 2023-05-27 |  | Closed | 2023-06-01 | 2023-06-21 | CD//Quah | 2023-06-21 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0016 | DU00002008448 |  |  | 2023-06-16 | 2023-06-16 |  | Pole | 2m RT (Boom) | 6m | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3
3920B | Surau Baitul Rahman | Central |  | Modernization |  | 2023Q2 | IE | Magicell | 4.6 TSSR Approved |  | 2023-04-10 | 2023-04-13 |  | 2023-04-15 |  | Closed | 2023-04-28 | 2023-06-09 | E//Razif | 2023-06-09 | CelcomDigi_RAN_Magicell_TSS_Central_20230411_0002/CelcomDigi_RAN_Magicell_TSS_Central_20230722 | DU00002008449 |  |  | 2023-05-15 | 2023-05-16 |  | Lampole | 24m Lampole | 30m | Add R9264H M901821 x3,Dismantle R8882 S1800B(B6B) x3+R8854D S2100(A4A) x3 | 0 | 0
1005Z | KG BARU TLK GONG | Central |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q2 | IE | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Tee |  |  | DU00002008450 | [6 empty] | Land site
1039C | Uji Niaga Akademy | Central |  | Modernization |  | 2023Q2 | AI | Ascentrack | 4.6 TSSR Approved |  | 2023-04-26 | 2023-05-02 |  | 2023-05-03 |  | Closed | 2023-05-04 | 2023-05-31 | E//Razif | 2023-05-30 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230417_0012 | DU00002008451 |  |  | 2023-05-25 | 2023-05-22 |  | Lampole | 30m Lampole | 35 | Add R9264H M901821 x3 + R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x3 |  | 123
4076C | Panglima Bukit Gantang | Northern |  | Modernization |  | 2023Q2 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-14 |  | 2023-04-15 |  | Closed | 2023-04-17 | 2023-04-28 | CD//Heng | 2023-04-18 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230413-0006 | DU00002008452 |  |  | 2023-05-17 | 2023-05-15 |  | H-bracket pole | 3m Boom (RT) | 7 | Add R8852E S9000 x3 + R8894E M1821 x3 + R8862A S2601 x3,Dismantle R8882 S1800(B) x1+R8882 S1800B(B6B) x2+R8881 S2100 x3
1072A | Dunlop Shoplot | Central |  | Modernization |  | 2023Q3 | YZ | Datasco | 4.6 TSSR Approved |  | 2023-04-26 | 2023-05-18 |  | 2023-05-21 |  | Closed | 2023-05-22 | 2023-06-28 | CD//Tee | 2023-06-19 | CelcomDigi_RAN_Datasco_TSS_Central_20230428_0018 | DU00002008453 |  |  | 2023-07-12 | 2023-07-12 |  | Wall mount boom | 60m 3 Legged Tower | 6 | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8894E M1821(A8A) x3 |  | 1
1476H | 99 Speedmart PUSAT BDR LATANIA | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008454 | [6 empty] | Small Cell
1137A | Lian Hup Jenjarum | Central |  | Modernization |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-07 | 2023-04-14 |  | 2023-04-11 |  | Closed | 2023-04-18 | 2023-05-17 | CD//Ali akaram | 2023-05-03 | CelcomDigi_RAN_GTSB_Central_20230407_0012 | DU00002008455 |  |  | 2023-05-25 | 2023-05-23 |  | A-bracket pole | 3m Bipod (RT) | 6m | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x4 |  | 3
2640B | Mutiara Bkt Raja LP 1 | Central |  | Modernization |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-04 |  | 2023-05-08 |  | Closed | 2023-05-10 | 2023-06-03 | CD//Syafiq | 2023-05-18 | CelcomDigi_RANMW_Datasco_TSS_Central_20230505_0002 | DU00002008456 |  |  | 2023-06-17 | 2023-06-13 |  | Unipole | 3m Boom (RT) | 7M | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8854D S2100(A4A) x3 |  | 3
2011B | West Port Building | Central |  | Modernization | Modernization | 2026 | SHA | Datasco | 4.6 TSSR Approved |  | 2023-04-11 | 2023-04-14 |  | 2023-04-17 |  | Closed | 2023-04-18 | 2024-12-02 | CD//Norhaliza | 2024-12-02 | CelcomDigi_RAN_Datasco_TSS_Central_20230412_0010 | DU00002008457 |  |  | 2026-02-02 | 2026-02-02 |  | Pole | 3m Bipod (RT) | 10 | R9264H M901821(AIA)x3, Dismantle R8862A S9000(A6A) x3+R8894E M1821(A8A) x3 | 0 | 123
1921B | Jugra Banting(Smart) | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-15 | 2023-04-27 |  | 2023-04-28 |  | Closed | 2023-04-29 | 2023-05-09 | CD//Tee | 2023-05-09 | CelcomDigi_RAN_Datasco_TSS_Central_20230417_0012 | DU00002008458 |  |  | 2023-05-29 | 2023-05-15 |  | Tower | 60m 4 Legged Tower | 60m | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
3874C_IBC | Wisma 99 Speedmart | Central |  | Remote MOCN |  | 2023Q3 |  | Datasco | 14.2 Drop (Done Survey) |  | 2023-10-23 | 2023-12-01 |  |  |  | To be Submitted | [5 empty] | DU00002008459 | [5 empty] | Portables BTS | IBC + Rooftop | NA
1376H | 99 Speedmart BAYU PERDANA 1 | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008460 | [6 empty] | Small Cell
3724C | Jalan Tiara 5 Bkt Raja (REL) | Central |  | Modernization |  | 2023Q3 | CR | Datasco | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-10 |  | 2024-01-15 |  | Closed | 2024-01-18 | 2024-01-23 | E//Razif | 2024-01-22 | CelcomDigi_RANMW_Datasco_TSS_Central_20230508_0003 | DU00002008461 |  |  | 2024-01-31 | 2024-01-26 |  | H-bracket pole | 3m Boom (RT) |  | Add R9264H M901821 x3+R8854 S2600 x1,Dismantle R8862A S2600(A4A) x1+R8894E M1821(A8A) x3 |  | 3
4172A | Sunway Prai | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-11 |  | 2023-05-17 |  | Closed | 2023-05-18 | 2023-06-21 | E//Hazida | 2023-06-21 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0016 | DU00002008462 |  |  | 2023-06-19 | 2023-06-16 |  | Pole | 3m Boom (RT) | 5m | Add A9732 M1821 x3,Dismantle R8882-GUL1812 x3+R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 | 123
3735B | Jalan Tengku Badri Shah | Central |  | Modernization |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-05-15 | 2023-05-18 |  | 2023-05-20 |  | Closed | 2023-05-22 | 2023-06-13 | E//Razif | 2023-06-13 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230511_0018 | DU00002008463 |  |  | 2023-06-22 | 2023-06-21 |  | Pole | 3m Bipod (RT) | 6m | Add R9264M M1821 x5,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 |  | 12
2641B | Desa Alam | Central |  | Modernization |  | 2023Q3 | SS | Datasco | 4.6 TSSR Approved |  | 2023-05-02 | 2023-05-19 |  | 2023-05-27 |  | Closed | 2023-05-31 | 2023-06-28 | CD//Tee | 2023-06-19 | CelcomDigi_RANMW_Datasco_TSS_Central_20230505_0002 | DU00002008464 |  |  | 2023-07-10 | 2023-06-28 |  | Monople Tree | 30m Monopole | 32 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x3,Dismantle R8882 S1800(B) x2+R8882 S1800B(B6B) x1+R8862A S1800(B6A) x2+R8862A S2100(A6A) x5+R8862A S2600(A4A) x1 | 3
1784A | Bdr Sultan Suleiman | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-11 | 2023-04-12 |  | 2023-04-14 |  | Closed | 2023-04-19 | 2023-05-25 | CD//Tee | 2023-05-05 | CelcomDigi_RAN_Datasco_TSS_Central_20230412_0010 | DU00002008465 |  |  | 2023-05-29 | 2023-05-22 |  | Minimast | 3m RT (Minimast) | 11m | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x5 | 13
1206B | Jln Kastam | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-14 | 2023-05-03 |  | 2023-05-06 |  | Closed | 2023-05-08 | 2023-06-03 | E//Sumitra | 2023-06-02 | CelcomDigi_RAN_Datasco_TSS_Central_20230417_0012 | DU00002008466 |  |  | 2023-05-13 | 2023-05-11 |  | Minimast | 3m RT (Minimast) | 12 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3
1627H | 99 Speedmart TG SEPAT 2 | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008467 | [6 empty] | Small Cell
4087C | Seri desa Tnh Hitam | Northern |  | Modernization |  | 2023Q2 | ZA | YPTT | 4.6 TSSR Approved |  | 2023-04-12 | 2023-05-09 |  | 2023-04-14 |  | Closed | 2023-04-18 | 2023-05-07 | CD//Shamsul | 2023-05-05 | Celcom Digi_RAN-YPTT-TSS-Northern-20230413-0004 | DU00002008468 |  |  | 2023-05-20 | 2023-05-24 |  | Unipole | 3m Bipod (RT) | 5 | Add R9264H M901821 x3,Dismantle R9224E M1821(AAB) x3
3816A | Jln Cendana 44 | Central |  | Modernization |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-02 | 2023-04-03 |  | 2023-04-14 |  | Closed | 2023-04-15 | 2023-05-25 | CD//Sapian | 2023-05-09 | CelcomDigi_RAN_GTSB_TSS_Central_20230403_0008 | DU00002008469 |  |  | 2023-05-24 | 2023-05-24 |  | Pole | 3m Boom (RT) | 4m | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
1406H | 99 Speedmart BAYU TINGGI | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008470 | [6 empty] | Small Cell
2952A | Taman Kota Sungai Rambai | Central |  | Modernization |  | 2023Q2 | IE | GTSB | 4.6 TSSR Approved |  | 2023-04-05 | 2023-04-08 |  | 2023-04-13 |  | Closed | 2023-04-15 | 2023-05-09 | CD//Sapian | 2023-05-08 | CelcomDigi_RAN_GTSB_TSS_Central_20230405_0010 | DU00002008471 |  |  | 2023-05-10 | 2023-05-09 |  | Lampole | 30m Monopole | 21 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3
4076D | Taman Dedap (REL) | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-13 | 2023-05-19 |  | 2023-05-30 |  | Closed | 2023-06-01 | 2023-06-10 | CD//Shamsul | 2023-06-10 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0016 | DU00002008472 |  |  | 2023-06-19 | 2023-06-19 |  | Wall mount boom | 3m Boom (RT) | 4m | Add R8852E S9000 x4 + R8894E M1821 x4,Dismantle R8862A S1800(B6A) x4+R8862A S2100(A6A) x4
1079A | Harpsoon | Central |  | Modernization |  | 2023Q3 | YZ | Datasco | 4.6 TSSR Approved |  | 2023-04-26 | 2023-05-10 |  | 2023-05-12 |  | Closed | 2023-05-18 | 2023-06-17 | CD//Tee | 2023-06-16 | CelcomDigi_RAN_Datasco_TSS_Central_20230428_0018 | DU00002008473 |  |  | 2023-07-08 | 2023-06-28 |  | Pole | 60m 4 Legged Tower | 7m | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8854 S1800(A4A) x3+R8854D S2100(A4A) x3 | 23
3491C | Jalan Nangka Sijangkang KJS (REL) | Central |  | Modernization |  | 2023Q2 | YZ | AllStar | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-28 |  | 2023-05-02 |  | Closed | 2023-05-03 | 2023-06-08 | CD//Syafiq | 2023-05-17 | CelcomDigi_RAN_AllStar_TSS_Central_20230404_0005 / CelcomDigi_RAN_Allstar_TSS_Central_20230721_ClearLoan | DU00002008474 |  |  | 2023-05-17 | 2023-05-17 |  | Lampole | 24m Lampole | 30M | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
2720C | Sg. Lang Tengah | Central |  | Modernization |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-04 | 2023-04-05 |  | 2023-04-07 |  | Closed | 2023-04-10 | 2023-05-02 | CD//Syafiq | 2023-05-02 | CelcomDigi_RAN_GTSB_TSS_Central_20230405_0010 | DU00002008475 |  |  | 2023-05-25 | 2023-05-24 |  | Monople Tree | Lampole | 45m | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle R9224E M1821(AAB) x3 |  | 1
1433H | 99 Speedmart TMN TELOK GEDUNG INDAH | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008476 | [6 empty] | Small Cell
1496H | 99 Speedmart TMN LANGAT UTAMA | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008477 | [6 empty] | Rooftop
3532A | Taman Seleguri (REL) | Central |  | Modernization |  | 2023Q2 | HQ 6 | Ascentrack | 4.6 TSSR Approved |  | 2023-04-12 | 2023-05-11 |  | 2023-05-14 |  | Closed | 2023-05-16 | 2023-06-05 | E//Razif | 2023-05-24 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230413_0011 | DU00002008478 |  |  | 2023-06-22 | 2023-06-22 |  | Pole | 6M RT (Boom) | 6 | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8894E M1821(A8A) x3 |  | 2
2950A | Persiaran Batu Nilam | Central |  | Modernization |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-04-05 |  |  | 2023-04-15 |  | Closed | 2023-04-16 | 2023-05-25 | CD//Syafiq | 2023-05-02 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230405_0007 / CelcomDigi_TX_Ascentrack_TSS_Decom_Central_20230717 | DU00002008479 |  |  | 2023-05-11 | 2023-05-10 |  | H-bracket pole | 3m Bipod (RT) |  | Add R9264M M1821 x5 + R8862A S2601 x2,Dismantle R8894E M1821(A8A) x3 |  | 23
1436B | Teluk Panglima Garang 2 | Central |  | Modernization |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-07 | 2023-04-15 |  | 2023-04-17 |  | Closed | 2023-05-03 | 2023-05-17 | CD//Sapian | 2023-05-17 | CelcomDigi_RAN_GTSB_TSS_Central_20230410_0013 | DU00002008480 |  |  | 2023-05-09 | 2023-05-09 |  | Tower | 45m 3 Legged Tower | 45m | Add R9264M M1821 x3,Dismantle R8854E S1800(A6A) x3+R8854D S2100(A4A) x3
3645B | Tmn Klang Utama 2 | Central |  | Modernization |  | 2023Q3 | YZ | CCSMY | 4.6 TSSR Approved |  | 2023-05-15 | 2023-05-26 |  | 2023-05-30 |  | Closed | 2023-05-31 | 2023-07-28 | E//Razif | 2023-07-28 | CelcomDigi_RANMW_CCSMY_TSS_Central_20230508_0001 | DU00002008481 |  |  | 2023-07-07 | 2023-07-04 |  | Wall mount boom | 3m Bipod (RT) | 4m | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 2
2672A11 | pBTS Ambang Botanic | Central |  | Modernization |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-04-05 | 2023-04-25 |  | 2023-04-28 |  | Closed | 2023-04-29 | 2023-05-30 | E//Razif | 2023-05-30 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230406_0008 | DU00002008482 |  |  | 2023-05-15 | 2023-05-13 |  | Guide mast | 25m pBTS | 30m | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8882 S1800B(B6B) x3+R8840-U216 x3
2038B | North Klang Industrial (Celcom) | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-14 | 2023-04-29 |  | 2023-05-03 |  | Closed | 2023-05-05 | 2023-07-15 | CD//Tee | 2023-06-27 | CelcomDigi_RAN_Datasco_TSS_Central_20230417_0012 | DU00002008483 |  |  | 2023-06-04 | 2023-05-22 |  | Tower | 50m Tower | 45 | Add R9264H M901821 x1 + A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8854E S1800(A6A) x3+R8854D S2100(A4A) x3+R8894E M1821(A8A) x1 | 12
2679A14 | pBTS Kg Sijangkang | Central |  | Modernization |  | 2023Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2023-04-05 | 2023-04-18 |  | 2023-04-19 |  | Closed | 2023-04-27 | 2023-06-01 | E//Razif | 2023-06-01 | CelcomDigi_RAN_AllStar_TSS_Central_20230404_0005 / CelcomDigi_RAN_Allstar_TSS_Central_20230721_ClearLoan | DU00002008484 |  |  | 2023-05-21 | 2023-05-09 |  | Minimast | Portable BTS | 26 | Add R9264H M901821 x3,Dismantle R8882 S1800(B) x3+R8862A S2100(A6A) x3
1442B | Pulau Indah Telekom | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-19 | 2023-04-27 |  | 2023-04-28 |  | Closed | 2023-04-29 | 2023-06-03 | CD//Tee | 2023-05-09 | CelcomDigi_RAN_Datasco_TSS_Central_20230420_0015 | DU00002008485 |  |  | 2023-06-22 | 2023-06-13 |  | Tower | Tower | 70m | Add R9264H M901821 x1 + R9264M M1821 x2 + R8862A S2601 x1,Dismantle R8882-GUL1812 x1
1974B | Jalan Kg Bukit Kemuning (REL) | Central |  | Modernization |  | 2023Q3 | YZ | Futong | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-11 |  | 2023-05-14 |  | Closed | 2023-05-16 | 2023-06-20 | CD//Norhaliza | 2023-06-20 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002008486 |  |  | 2023-07-10 | 2023-07-10 |  | Pole | 3m Boom (RT) | 15 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3 |  | 12
2797A | Sek 17 Mosque | Central |  | Modernization |  | 2023Q3 | HQ 1 | Ascentrack | 4.6 TSSR Approved |  | 2023-05-18 | 2023-09-22 |  | 2023-06-01 |  | Closed | 2023-06-04 | 2023-06-28 | E//Sumitra | 2023-06-27 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230523_0020 | DU00002008487 |  |  | 2023-06-24 | 2023-06-24 |  | Lampole | 20m Lampole | 30 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3
4055C | Bkt Meru Kinta | Northern |  | Modernization |  | 2023Q2 | SM | YPTT | 4.6 TSSR Approved |  | 2023-04-13 | 2023-04-25 |  | 2023-04-18 |  | Rectificating | 2023-04-28 | 2023-05-25 | CD//Heng | 2023-05-02 | Celcom Digi_RAN-YPTT-TSS-Northern-20230414-0005 | DU00002008488 |  |  | 2023-06-07 | 2023-06-03 |  | Unipole | 3m Bipod (RT) | 8M | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 |  | 2
1020E | West Port CT8-1 Pole | Central |  | Modernization | MOCN As-Is->Modernization | 2026 | AI | GTSB | 4.6 TSSR Approved |  | 2025-05-26 | 2025-05-27 |  | 2025-05-29 |  | Closed | 2025-06-03 | 2025-06-10 | E//Razif | 2025-06-10 | SQ202502170746 | DU00002008489 |  |  | 2026-03-11 | 2026-03-11 |  | Tower | Small Cell | 40m | Add A8612 M1821 x3, Dismantle A8602 M1821x3
1620B | Jalan Batai Laut Klang(ZED) | Central |  | Modernization |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-16 | 2023-05-25 |  | 2023-05-29 |  | Closed | 2023-05-31 | 2023-06-17 | CD//Nik Ashraf | 2023-06-16 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002008490 |  |  | 2023-06-15 | 2023-06-13 |  | Minimast | 6m RT (Minimast) | 10m | Add R9264M M1821 x5 + R8862A S2600 x2,Dismantle R8894E M1821(A8A) x3 |  | 12
1091A | Berkeley | Central |  | Modernization |  | 2023Q3 | YZ | Datasco | 4.6 TSSR Approved |  | 2023-04-28 | 2023-05-12 |  | 2023-05-16 |  | Closed | 2023-05-17 | 2023-06-17 | CD//Tee | 2023-06-16 | CelcomDigi_RAN_Datasco_TSS_Central_20230502_0019 | DU00002008491 |  |  | 2023-06-16 | 2023-06-13 |  | Wall mount boom | 6m Unipole RT | 8 | Add R9264M M1821 x3,Dismantle R8854 S1800(A4A) x3+R8854D S2100(A4A) x3
1010Z | KG TBK DARAT | Central |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q2 |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Tee |  |  | DU00002008492 | [6 empty] | Land site
2640A | Sek16 Industry Area | Central |  | Modernization |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-09-16 | 2023-08-25 |  | 2023-08-15 |  | Closed | 2023-08-25 | 2023-09-14 | E//Razif | 2023-09-12 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230824 | DU00002008493 |  |  | 2023-09-01 | 2023-08-30 |  | Monople Tree | 30m Monopole | 30m | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 |  | 1
3363C | Taman Muthu 3 (REL) | Central |  | Modernization |  | 2023Q3 | MA | Futong | 4.6 TSSR Approved |  | 2023-05-20 | 2023-05-22 |  | 2023-05-26 |  | Closed | 2023-05-27 | 2023-06-22 | CD//Ali akaram | 2023-06-22 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002008494 |  |  | 2023-06-14 | 2023-06-13 |  | Lampole | 24m Lampole | 25 | Add R9264H M901821 x3,Dismantle R8892E M1821(BAA) x3
1756H | 99 Speedmart Tmn Mulia | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008495 | [6 empty] | Rooftop
1585H | 99 Speedmart Tmn Raja Nong | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008496 | [6 empty] | Small Cell
3716C | Jln Delima Parkland (REL) | Central |  | Modernization |  | 2023Q2 | YZ | AllStar | 4.6 TSSR Approved |  | 2023-04-05 | 2023-04-28 |  | 2023-05-02 |  | Closed | 2023-05-03 | 2023-05-25 | CD//Syafiq | 2023-05-17 | CelcomDigi_RAN_AllStar_TSS_Central_20230404_0005 / CelcomDigi_RAN_Allstar_TSS_Central_20230721_ClearLoan | DU00002008497 |  |  | 2023-05-09 | 2023-05-08 |  | Pole | 3m Boom (RT) | 13 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
2689B | Desa Latania | Central |  | Modernization |  | 2023Q3 | IE | Futong | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-19 |  | 2023-05-23 |  | Closed | 2023-05-23 | 2023-07-27 | CD//Syafiq | 2023-07-27 | CelcomDigi_RANMW_Futong_TSS_Central_20230508_0001 | DU00002008498 |  |  | 2023-07-05 | 2023-07-04 |  | Monople Tree | 45m Monopole | 45 | Add A9732 M1821 x3,Dismantle R8862A S2600(A4A) x3+R8894E M1821(A8A) x6 | 123
4132A | KG TANJUNG PUTUS | Northern |  | Modernization |  | 2023Q3 | SM | YPTT | 4.6 TSSR Approved |  | 2023-05-04 | 2023-05-12 |  | 2023-05-14 |  | Closed | 2023-05-23 | 2023-06-27 | E//Hazida | 2023-06-27 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0009 | DU00002008499 |  |  | 2023-07-10 | 2023-07-04 |  | Tower | 45m 4 Legged Tower | 45 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3 | 23
3560A | PKFZ (REL) | Central |  | Modernization |  | 2026 | SY1 | Datasco | 4.6 TSSR Approved |  | 2023-06-27 | 2023-07-17 |  | 2023-07-20 |  | Closed | 2023-07-22 | 2024-12-17 | E//Razif | 2024-12-17 | CelcomDigi_RAN_Datasco_TSS_Central_20230428_0018 | DU00002008500 |  |  | 2025-05-14 | 2025-04-24 |  | Monopole | 6m Unipole RT | 36 | Add R8862A S9000x3+A9732 M1821x1 | 3 | 1
1082A | West Port Lot 5692 | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-14 |  | 2023-04-17 |  | Closed | 2023-04-18 | 2023-06-03 | CD//Tee | 2023-04-28 | CelcomDigi_RAN_Datasco_TSS_Central_20230413_0011 | DU00002008501 |  |  | 2023-06-10 | 2023-06-08 |  | Tower | 45m 3 Legged Tower | 48 | Add R8862A S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
3345B | Lorong Batu Nilam (REL) | Central |  | Site Out (Modernization) | Modernization->MOCN Decomm->Site Out->Replacement, Site Out (Modernization) | 2023Q2 | AI | GCI | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-25 |  | 2023-04-27 |  | Closed | 2023-04-29 | 2023-06-06 | CD//Ali akaram | 2023-05-05 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230413_0011 | DU00002008502 | [5 empty] | Pole | 3m Boom (RT) | 5m
1763H | 99 Speedmart Tmn Jaya Utama | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008503 | [6 empty] | Rooftop
1017E | West Port CT3-1 Pole | Central |  | Modernization | MOCN As-Is->Modernization | 2026 | AI | GTSB | 4.6 TSSR Approved |  | 2025-05-26 | 2025-05-23 |  | 2025-05-27 |  | Under Approval | 2025-05-28 | 2025-07-25 | E// Razif | 2025-06-04 | SQ202502170746 | DU00002008504 |  |  | 2026-03-06 | 2026-03-03 |  | Tower | Small Cell | 36 | Add A8612 M1821 x2+R8894E M1821 x1, Dismantle A8602 M1821x3
2632B | Perepat Housing LP | Central |  | Modernization |  | 2023Q3 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-05-16 | 2023-05-25 |  | 2023-05-28 |  | Closed | 2023-05-29 | 2023-07-21 | E//Razif | 2023-07-21 | CelcomDigi_RAN_CCSMY_TSS_Central_20230508_0002 | DU00002008505 |  |  | 2023-06-28 | 2023-06-27 |  | Pole | 24m Lampole | 30M | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
4004D | Ampang Baru Ipoh | Northern |  | Decomm | Modernization->Decomm | 2023Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2023-04-09 | 2023-04-08 |  | 2023-04-13 |  | Closed | 2023-04-17 | 2023-05-08 | CD//Heng | 2023-04-28 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230720-0023/Celcom Digi_RAN-GTSB-TSS-Northern-20230410-0007 | DU00002008506 |  |  |  |  | 2023-12-19 | Minaret | 30m Monopole | 30
3874C | Wisma 99 Speedmart | Central |  | Remote MOCN | Modernization->Remote MOCN | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-17 |  | 2023-06-09 |  | Closed | 2023-06-14 | 2023-06-27 | E//Razif | 2023-06-27 | CelcomDigi_RAN_Datasco_TSS_20230505_0019 | DU00002008507 | [5 empty] | Wall mount boom | IBC + Rooftop | 1 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8892N M1821(BAB) x3
1480H | 99 Speedmart TMN SRI SENTOSA JAYA 1 | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008508 | [6 empty] | Small Cell
1274H | 99 Speedmart JLN PEKAN BARU MERU | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008509 | [6 empty] | Small Cell
2181A3 | pBTS Saujana Putra (C) | Central |  | Modernization |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-04 | 2023-05-06 |  | 2023-04-11 |  | Closed | 2023-05-11 | 2023-05-31 | E//Razif | 2023-05-30 | CelcomDigi_RAN_GTSB_TSS_Central_20230405_0010 | DU00002008510 |  |  | 2023-05-20 | 2023-05-18 |  | Guide mast | 25m pBTS | 20 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3
2187A7 | pBTS Kampung Sepakat Jaya ( C ) | Sabah |  | Modernization |  | 2023Q2 | HQ 6 | Futong | 4.6 TSSR Approved | Single Phase Power Site. Site require upgrade to 3phase incoming | 2023-04-08 | 2023-04-04 |  | 2025-02-06 |  | Under Approval | 2023-04-28 | 2023-06-13 | CD//Ray Amos | 2023-05-10 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002008511 |  |  | 2023-06-14 | 2023-06-08 |  | Tower | 25m pBTS | 25m | Remain existing RRU
2719A | TPG industry | Central |  | Modernization |  | 2023Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2023-06-07 | 2023-06-08 |  | 2023-06-09 |  | Closed | 2023-06-09 | 2023-06-13 | E//Razif | 2023-06-13 | CelcomDigi_RAN_AllStar_TSS_Central_20230404_0005 / CelcomDigi_RAN_Allstar_TSS_Central_20230721_ClearLoan | DU00002008512 |  |  | 2023-09-15 | 2023-08-21 |  | Tower | Tower | 60 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x3 | 23
2777C | JBA Bukit Lipat TX Relocation | Central |  | Modernization |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-05-09 | 2023-06-20 |  | 2023-06-22 |  | Closed | 2023-06-23 | 2023-06-26 | E//Razif | 2023-06-26 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230511_0018 | DU00002008513 |  |  | 2023-07-13 | 2023-07-13 |  | Tower | Land site | 78 | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x1+R9224E M1821(AAB) x4 | 123
1203H | 99 Speedmart KG SG LANG | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008514 | [6 empty] | Small Cell
1130A | Kanchong Darat | Central |  | Modernization |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-04 |  |  | 2023-04-19 |  | Closed | 2023-04-27 | 2023-05-25 | CD//Tee | 2023-05-03 | CelcomDigi_RAN_GTSB_TSS_Central_20230405_0010 | DU00002008515 |  |  | 2023-05-15 | 2023-05-13 |  | Tower | 60m 4 Legged Tower | 47m | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 13
1459H | 99 Speedmart SG JAROM | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008516 | [6 empty] | Small Cell
3606B | Lorong Stesen Bas (Klang) | Central |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-05-17 | 2023-05-22 |  | 2023-05-24 |  | Closed | 2023-05-25 | 2023-06-05 | E//Sumitra | 2023-05-26 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002008517 |  |  | 2023-06-16 | 2023-06-14 |  | Pole | 3m Bipod (RT) | 4 | Add R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
1637B | Simpang Morib | Central |  | Modernization |  | 2023Q2 | HQ 6 | Magicell | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-12 |  | 2023-05-15 |  | Closed | 2023-05-17 | 2023-06-05 | CD//Tee | 2023-05-24 | CelcomDigi_RAN MW_Magicell_TSS_Central_20230428_0001 | DU00002008518 |  |  | 2023-06-03 | 2023-06-02 |  | Tower | Tower | 45 | Add R9264H M901821 x3 + R8862A S2601 x1,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x1+R8862A S2100(A6A) x2
3346A8 | pBTS Taman Bukit Jati | Central |  | Modernization |  | 2023Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-10 |  | 2023-05-12 |  | Closed | 2023-05-18 | 2023-06-27 | E//Razif | 2023-06-27 | CelcomDigi_RAN_YPTT_TSS_20230505_0002 | DU00002008519 |  | Major Rejection 1. Wrong RRU and antenna for diagram and connection 2. sector view and pano not same 3. wrong azimuth 4. many info missing 5. not follow RF para 6. drawing and schematic wrong | 2023-06-11 | 2023-06-10 |  | Monopole | 25m pBTS | 25m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1566B10 | pBTS Lorong Batu Nilam (R ) | Central |  | Modernization |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-04-03 | 2023-04-10 |  | 2023-04-13 |  | Closed | 2023-04-13 | 2023-05-25 | CD//Sapian | 2023-05-11 | SQ202411080525 | DU00002008520 |  |  | 2023-06-01 | 2023-05-22 |  | Guide mast | 25m pBTS | 30m | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
4102C | Tmn Seri Murni | Northern |  | Modernization |  | 2023Q3 | WP | CCSMY | 4.6 TSSR Approved |  | 2023-05-02 | 2023-05-05 |  | 2023-05-08 |  | Closed | 2023-05-10 | 2023-05-25 | CD//Affendi | 2023-05-11 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230502-0013 | DU00002008521 |  |  | 2023-06-10 | 2023-06-07 |  |  | 3m Bipod (RT) | 4 | Add R9264H M901821 x3,Dismantle R8892E M1821(BAA) x3
2050B | ELITE HW KM25.8 | Central |  | Modernization |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-04 | 2023-04-05 |  | 2023-04-19 |  | Closed | 2023-05-22 | 2023-07-24 | E//Sumitra | 2023-07-21 | CelcomDigi_RAN_GTSB_TSS_Central_20230405_0010 / CelcomDigi_RAN_GTSB_TSS_Central_20230721_ClearLoan | DU00002008522 |  |  | 2023-06-02 | 2023-05-30 |  | BillBoard | Billboard | 26 | Add R9264H M901821 x4,Dismantle R8882 S1800(B) x2+R8892E M1821(BAA) x6
4162A | Arowana | Northern |  | Modernization |  | 2023Q3 | MH | GTSB | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-09 |  | 2023-05-14 |  | Closed | 2023-05-17 | 2023-05-23 | CD//Affendi | 2023-05-18 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0016 | DU00002008523 |  |  | 2023-06-08 | 2023-06-08 |  | Minimast | 6m Tripod (RT) | 7 | Add R9264M M1821 x4,Dismantle R8882 S1800B(B6B) x2+R8862A S1800(B6A) x2+R8854D S2100(A4A) x4
4104C | Bkt Juru | Northern |  | Modernization |  | 2023Q3 | MH | GTSB | 4.6 TSSR Approved |  | 2023-05-02 | 2023-05-16 |  | 2023-05-18 |  | Closed | 2023-05-19 | 2023-05-29 | E//Hazida | 2023-05-28 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0016 | DU00002008524 |  |  | 2023-06-25 | 2023-06-23 |  | Monopole | Micro Cell | 30 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 123
1131A | Hakka Banting | Central |  | Modernization |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-07 | 2023-05-08 |  | 2023-05-11 |  | Closed | 2023-05-19 | 2023-05-19 | E//Razif | 2023-05-19 | CelcomDigi_RAN_GTSB_Central_20230407_0012 | DU00002008525 |  |  | 2023-05-26 | 2023-05-24 |  | Pole | 3m Bipod (RT) | 6 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 13
2773A | Batu Belah | Central |  | Modernization |  | 2023Q3 | YZ | Datasco | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-11 |  | 2023-05-16 |  | Closed | 2023-05-17 | 2023-06-17 | CD//Tee | 2023-06-15 | CelcomDigi_RANMW_Datasco_TSS_Central_20230505_0002 | DU00002008526 |  |  | 2023-07-04 | 2023-06-28 |  | Monopole | 30m Monopole | 30m | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x3+R9224E M1821(AAB) x2 | 123
1378H | 99 Speedmart TELOK PANGLIMA GARANG 2 | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008527 | [6 empty] | Small Cell
4077C | Bulatan canning | Northern |  | Modernization |  | 2023Q2 | ZA | YPTT | 4.6 TSSR Approved |  | 2023-04-12 | 2023-05-08 |  | 2023-04-14 |  | Closed | 2023-04-18 | 2023-05-07 | CD//Shamsul | 2023-05-04 | Celcom Digi_RAN-YPTT-TSS-Northern-20230413-0004 | DU00002008528 |  |  | 2023-05-16 | 2023-05-15 |  | Unipole | 6m Unipole RT | 6m | Add R8894E M1821 x3,Dismantle R8882 S1800B(B6B) x3+R8881 S2100 x3
3331A | TMN_SRI_MEWAH1 | Central |  | Modernization |  | 2023Q3 | HQ 6 | Futong | 4.6 TSSR Approved |  | 2023-05-16 | 2023-05-19 |  | 2023-05-24 |  | Closed | 2023-05-27 | 2023-07-05 | CD//Syafiq | 2023-07-05 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002008529 |  |  | 2023-06-12 | 2023-06-12 |  | Pole | 30m Monopole | 6 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3
2725A | Bukit Naga 2 | Central |  | Modernization |  | 2023Q3 | SS | Futong | 4.6 TSSR Approved |  | 2023-05-31 | 2023-06-07 |  | 2023-06-10 |  | Closed | 2023-06-12 | 2023-06-28 | E//Razif | 2023-06-27 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002008530 |  |  | 2023-07-22 | 2023-07-22 |  | Monople Tree | 30m Monopole | 32 | Add R9264H M901821 x4 + R9264M M1821 x2 + R8862A S2601 x3,Dismantle R8862A S1800(B6A) x1+R8862A S2100(A6A) x1+R8892E M1821(BAA) x3 |  | 13
3815A | Jln Delima | Central |  | Modernization |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-05 | 2023-04-08 |  | 2023-04-10 |  | Closed | 2023-04-12 | 2023-06-06 | CD//Ali akaram | 2023-04-27 | CelcomDigi_RAN_GTSB_Central_20230406_0011 | DU00002008531 |  |  | 2023-06-04 | 2023-05-30 |  | Wall mount boom | 3m Boom (RT) | 4m | Add R8862A S9000 x3 + R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
1113A | Pulau Ketam | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-19 | 2023-04-27 |  | 2023-05-03 |  | Closed | 2023-05-05 | 2023-05-25 | CD//Tee | 2023-05-18 | CelcomDigi_RAN_Datasco_TSS_Central_20230419_0014 | DU00002008532 |  |  | 2023-05-12 | 2023-05-09 |  | Minimast | 45m 3 Legged Tower | 16 | Add R9264H M901821 x3 + R9264M M1821 x3 + R8862A S2601 x3,Dismantle R8894E M1821(A8A) x3 |  | 123
1102A | Teluk Pulai | Central |  | Modernization |  | 2023Q3 | MA | Futong | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦Structure,unable to install 36 pcs antenna on this unipole | 2023-05-23 | 2023-05-27 |  | 2023-05-31 |  | Closed | 2023-06-16 | 2023-06-28 | E//Razif | 2023-06-26 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002008533 | NIC_S3_Change MM to BI_loading issue_Digi OB |  | 2023-07-10 | 2023-06-28 |  | Unipole | 3m Boom (RT) | 9 | Add R9264M M1821 x7 + R8862A S2601 x3,Dismantle R8894E M1821(A8A) x4 |  | 123
1439B | Jln Dengkil Banting 2 | Central |  | Modernization |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-05 | 2023-04-04 |  | 2023-04-14 |  | Closed | 2023-04-17 | 2023-05-25 | CD//Sapian | 2023-05-02 | CelcomDigi_RAN_GTSB_TSS_Central_20230405_0010 | DU00002008534 |  |  | 2023-05-13 | 2023-05-09 |  | Tower | 45m 3 Legged Tower | 50m | Add R9264M M1821 x5 + R8862A S2601 x2,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3 |  | 13
3610B | Kota Bayu Emas | Central |  | Modernization |  | 2023Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2023-04-03 | 2023-04-13 |  | 2023-04-15 |  | Closed | 2023-05-08 | 2023-06-20 | E//Razif | 2023-06-20 | CelcomDigi_RAN_AllStar_TSS_Central_20230404_0005 / CelcomDigi_RAN_Allstar_TSS_Central_20230721_ClearLoan | DU00002008535 |  |  | 2023-05-14 | 2023-05-11 |  |  | 3m Bipod (RT) | 14 | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3+R8881 S2100 x3
1283C | Paya Indah (REL) | Central |  | Modernization |  | 2023Q2 | MA | GTSB | 4.6 TSSR Approved |  | 2023-04-10 | 2023-04-14 |  | 2023-04-16 |  | Closed | 2023-04-18 | 2023-05-25 | CD//Syafiq | 2023-04-19 | CelcomDigi_RAN_GTSB_TSS_Central_20230411_0014 | DU00002008536 |  |  | 2023-05-31 | 2023-05-30 |  | Tower | 60m 4 Legged Tower | 60 | Add R8862A S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2,Dismantle R8894E M1821(A8A) x3 | 1
3585B1 | pBTS Taman Klang Ria (KM) | Central |  | Modernization |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-08 |  | 2023-05-10 |  | Closed | 2023-05-12 | 2023-06-13 | E//Sumitra | 2023-06-13 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230505_0016 | DU00002008537 |  |  | 2023-06-12 | 2023-06-12 |  | Guide mast | 25m pBTS | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1377C | Jln Hj Abdul Manan 1 (REL) | Central |  | Modernization |  | 2023Q3 | HQ 6 | CCSMY | 4.6 TSSR Approved |  | 2023-05-11 | 2023-06-01 |  | 2023-06-08 |  | Closed | 2023-06-12 | 2023-07-14 | E//Razif | 2023-07-14 | CelcomDigi_RAN_CCSMY_TSS_Central_20230508_0002 | DU00002008538 |  |  | 2023-07-03 | 2023-06-28 |  | Lampole | Land site | 24m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1626H | 99 Speedmart KLANG UTAMA 1 | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008539 | [6 empty] | Small Cell
2637B | Jalan Bakti 2 | Central |  | Modernization |  | 2023Q3 | HQ 6 | Datasco | 4.6 TSSR Approved |  | 2023-05-03 | 2023-06-13 |  | 2023-06-15 |  | Closed | 2023-06-17 | 2023-07-06 | E//Razif | 2023-07-05 | CelcomDigi_RAN_Datasco_TSS_20230505_0019 | DU00002008540 |  |  | 2023-07-03 | 2023-06-28 |  | Lampole | 20m Lampole | 20m | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
2789C | Tmn Perindustrian Bandar Sultan Suleiman (REL) | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-17 | 2023-04-20 |  | 2023-04-28 |  | Closed | 2023-04-28 | 2023-05-15 | CD//Sapian | 2023-05-15 | CelcomDigi_RAN_Datasco_TSS_Central_20230418_0013 | DU00002008541 |  |  | 2023-05-20 | 2023-05-17 |  | Lampole | Land site | 25 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1202B | Lbh Sg Puloh | Central |  | Modernization |  | 2023Q3 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-05-19 | 2023-05-25 |  | 2023-05-28 |  | Closed | 2023-05-31 | 2023-07-25 | E//Razif | 2023-07-20 | CelcomDigi_RAN_CCSMY_TSS_Central_20230508_0002 | DU00002008542 |  |  | 2023-07-07 | 2023-07-04 |  | Monopole | 45m Monopole | 35M | Add A9732 M1821 x1 + R9264M M1821 x2,Dismantle R8894E M1821(A8A) x3 | 2
3418B3 | pBTS KKIP Timur | Sabah |  | Modernization |  | 2023Q2 | HQ 6 | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-05 |  | 2023-04-26 |  | Closed | 2023-04-28 | 2023-05-10 | CD//Ray Amos | 2023-05-10 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002008543 |  |  | 2023-05-27 | 2023-05-26 |  |  | 25m pBTS | 31m | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
2663A13 | pBTS Sri Sedeli Andalas [C] | Central |  | Modernization |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-12 |  | 2023-05-14 |  | Closed | 2023-05-16 | 2023-06-24 | E//Sumitra | 2023-06-13 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230511_0018 | DU00002008544 |  |  | 2023-06-16 | 2023-06-14 |  | Guide mast | 25m pBTS | 25 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3
3298A1 | pBTS Bandar Botanic (M) | Central |  | Modernization |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦pBTS loading issue,AAU cannot install | 2023-04-12 | 2023-04-26 |  | 2023-05-01 |  | Closed | 2023-05-15 | 2023-06-16 | E//Razif | 2023-06-15 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230413_0011 | DU00002008545 | NIC_S3_Change MM to BI_loading issue_Digi OB |  | 2023-05-20 | 2023-05-20 |  | Guide mast | 25m pBTS | 30 | Add R9264H M901821 x3 + R9264M M1821 x3,Dismantle R8854E S1800(A6A) x3+R8854D S2100(A4A) x3 |  | 123
1010C | Surau Al-Faizin | Central |  | Modernization |  | 2023Q3 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-29 |  | 2023-05-31 |  | Closed | 2023-06-13 | 2023-07-04 | E//Razif | 2023-07-04 | CelcomDigi_RANMW_CCSMY_TSS_Central_20230508_0001 | DU00002008546 |  |  | 2023-07-03 | 2023-07-03 |  | Lampole | Tower | 20m | Add A9732 M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 123
3661B | Jalan Demang 5 | Central |  | Modernization |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-05-11 | 2023-05-13 |  | 2023-05-17 |  | Closed | 2023-05-17 | 2023-06-22 | E//Sumitra | 2023-06-22 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230511_0018 | DU00002008547 |  |  | 2023-06-13 | 2023-06-13 |  | Pole | 3m Boom (RT) | 5 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1003Z | LDG EAST (MN_KGKOKOH) | Central |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q2 |  | Magicell | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Tee |  |  | DU00002008548 | [6 empty] | Land site
1129H | SNH Communications | Central |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008549 | [6 empty] | Small Cell
1990A | Senior Citizen Club | Central |  | Modernization |  | 2023Q3 | HQ 1 | Futong | 4.6 TSSR Approved |  | 2023-05-17 | 2023-05-19 |  | 2023-05-24 |  | Closed | 2023-05-25 | 2023-06-05 | E//Sumitra | 2023-05-26 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002008550 |  |  | 2023-06-12 | 2023-06-12 |  | Pole | 3m Bipod (RT) | 6 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3
1506H | 99 Speedmart TMN KAPAR RIA | Central |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008551 | [6 empty] | Small Cell
2674C | Kg Rantau Panjang | Central |  | Modernization |  | 2023Q3 | YZ | Datasco | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-12 |  | 2023-05-15 |  | Closed | 2023-05-16 | 2023-06-03 | E//Razif | 2023-05-22 | CelcomDigi_RAN_Datasco_TSS_20230505_0019 | DU00002008552 |  |  | 2023-06-11 | 2023-06-11 |  | Lampole | Land site | 32 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
1639B | Bandar Palace | Central |  | Modernization |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-05 |  |  | 2023-04-26 |  | Closed | 2023-04-28 | 2023-05-05 | CD//Tee | 2023-05-03 | CelcomDigi_RAN_Datasco_TSS_Central_20230405_0008 | DU00002008553 |  |  | 2023-05-11 | 2023-05-09 |  | Tower | 60m 3 Legged Tower | 60 | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 | 123
1626B | Tmn Seri Rantau(ZED) | Central |  | Modernization |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-16 |  | 2023-05-19 |  | Closed | 2023-05-19 | 2023-06-21 | E//Razif | 2023-06-21 | CelcomDigi_RAN_Datasco_TSS_Central_20230428_0018 | DU00002008554 |  |  | 2023-06-19 | 2023-06-18 |  | Tower | Tower | 45 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x5 | 12
4119B | Mak Mandin Industry | Northern |  | Modernization |  | 2023Q3 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-09 |  | 2023-05-11 |  | Closed | 2023-05-12 | 2023-05-25 | CD//Affendi | 2023-05-16 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0016 | DU00002008555 |  |  | 2023-06-10 | 2023-06-10 |  | Monopole | 6m Unipole RT | 25 | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x3 |  | 1
1249B | Bandar Parklands | Central |  | Modernization |  | 2023Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2023-05-14 | 2023-05-09 |  | 2023-05-12 |  | Closed | 2023-05-18 | 2023-06-07 | E//Sumitra | 2023-06-07 | CelcomDigi_RAN_AllStar_TSS_Central_20230404_0005 / CelcomDigi_RAN_Allstar_TSS_Central_20230721_ClearLoan | DU00002008556 |  |  | 2023-06-07 | 2023-06-03 |  | Lampole | 24m Lampole | 25 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
1613B | SG KAPAR INDAH | Central |  | Modernization |  | 2023Q3 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-15 |  | 2023-05-18 |  | Closed | 2023-05-20 | 2023-07-25 | E//Razif | 2023-07-18 | CelcomDigi_RAN_CCSMY_TSS_Central_20230428_0001 | DU00002008557 |  |  | 2023-07-07 | 2023-07-04 |  | Minaret | 3m Boom (RT) | 4M | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 |  | 2
1509C | Batu 22 1_2 Kanchong Darat Banting | Central |  | Modernization |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-07 | 2023-04-11 |  | 2023-04-12 |  | Closed | 2023-04-17 | 2023-05-25 | CD//Sapian | 2023-05-08 | CelcomDigi_RAN_GTSB_Central_20230407_0012 | DU00002008558 |  |  | 2023-05-12 | 2023-05-11 |  | Lampole | Lampole | 30m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
3622C | Ulu Tinggi | Central |  | Modernization |  | 2023Q3 | IE | Magicell | 4.6 TSSR Approved |  | 2023-05-19 | 2023-05-24 |  | 2023-05-26 |  | Closed | 2023-05-30 | 2023-06-10 | E//Kok Keen | 2023-06-08 | CelcomDigi_RAN_Magicell_TSS_Central_20230523_0009 | DU00002008559 |  |  | 2023-09-15 | 2023-08-10 |  | Tower | 60M 3L Tower | 77M | Add A9732 M1821 x2 + R9264M M1821 x1 + R8862A S2601 x3,Dismantle R8894E M1821(A8A) x3 | 13
3475C1 | pBTS D_Sri Gayang (KM) | Sabah |  | Modernization |  | 2023Q2 | AD | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-10 |  | 2023-04-17 |  | Closed | 2023-04-28 | 2023-05-10 | CD//Mohidi Jaan | 2023-05-10 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002008560 |  |  | 2023-05-27 | 2023-05-25 |  |  | 25m pBTS | 30 | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
B00396 | B061C_B00396OD_TMKEMUNING | Central | 1019K | Swap |  | 2023Q3 | HQ 6 | Futong | 4.6 TSSR Approved |  | 2023-05-25 | 2023-05-29 |  | 2023-06-01 |  | Closed | 2023-06-04 | 2023-06-09 | CD//Sapian | 2023-06-09 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002007075 |  |  | 2023-10-06 | 2023-09-22 |  | Tower | TOWER | 46 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 1
B00421 | B058E_B00421OD_PR_KGSIJANGKANG | Central |  | Decomm |  | 2023Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2023-04-05 | 2023-06-26 |  | 2023-04-18 | 2024-01-22 | Closed | 2023-07-21 | 2025-07-29 | CD//Ali Akaram | 2023-08-26 | CelcomDigi_RAN_AllStar_TSS_Central_20230626_decom reraise | DU00002007076 |  |  |  |  | 2023-07-13 | Tower | TOWER
B00405 | B058E_B00405OD_VLSGRAMBAI | Central |  | Decomm |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-16 | 2023-06-26 |  |  | 2023-08-03 |  | 2023-06-12 | 2023-09-01 | CD//Norhaliza | 2023-06-13 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002007077 |  | EXTRA IDU-CT09080 |  |  | 2023-09-22 | Tower | TOWER | 46
B00398 | B061D_B00398OD_TMBENGKEL | Central | 1020K | Swap |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-02-14 | 2024-02-16 |  | 2024-02-17 |  | Closed | 2024-02-19 | 2024-03-05 | CD//Ali Akaram | 2024-03-05 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240217 | DU00002007078 |  |  | 2024-04-24 | 2024-03-29 |  | Monopole | MONOPOLE | 45 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 12
B00380 | B058B_B00380OD_TMNKLGUTAMA | Central | 1018K | Swap |  | 2023Q3 | HQ 6 | CCSMY | 4.6 TSSR Approved |  | 2023-05-12 | 2023-05-18 |  | 2023-05-22 |  | Closed | 2023-05-24 | 2023-07-07 | CD//Ali akaram | 2023-07-06 | CelcomDigi_RAN_CCSMY_TSS_Central_20230508_0002 | DU00002007079 |  |  | 2023-09-01 | 2023-08-21 |  | In-Building System | BOOM | 9 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
B00417 | B059A_B00417OD_KGSGBUAYA | Central |  | Decomm |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-05 | 2023-04-10 |  |  | 2023-08-02 |  | 2023-07-18 | 2023-09-01 | CD//Ali Akaram | 2023-08-27 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002007080 |  |  |  |  | 2023-07-19 | Tower | LAMP_POLE | 60m
B00410 | B058D_B00410OD_TMPULAUKETAM | Central |  | Decomm |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-21 |  |  | 2023-06-08 | 2023-06-21 | Closed | 2023-08-09 | 2025-10-01 | CD//Syafiq | 2023-07-25 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002007081 |  |  |  |  | 2023-11-20 |  | TOWER
B00416 | B059A_B00416OD_KGSRIKLANANG | Central |  | Decomm |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-15 | 2023-06-26 |  |  | 2023-07-26 |  | 2023-06-12 | 2023-06-28 | CD//Norhaliza | 2023-06-13 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002007082 |  |  |  |  | 2023-07-09 | Tower | TOWER | 60
B00407 | B058D_B00407OD_TMPULAUINDAH | Central |  | Decomm |  | 2023Q2 | MA | Datasco | 4.6 TSSR Approved |  | 2023-04-19 | 2023-06-26 |  |  | 2023-06-19 |  | 2023-06-19 |  | CD//Norhaliza | 2023-09-25 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002007083 |  |  |  |  | 2023-11-20 | Tower | TOWER
B00414 | B059A_B00414OD_KGENDAH | Central | 1021K | Swap |  | 2023Q2 | IE | Magicell | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-14 |  | 2023-04-18 |  | Closed | 2023-04-20 | 2023-07-07 | CD//Sapian | 2023-06-26 | CelcomDigi_RAN_Magicell_TSS_Central_20230417_0003 | DU00002007084 |  |  | 2023-06-27 | 2023-06-22 |  | Tower | TOWER | 50m | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x5,Dismantle Celcom all RRU&BBU |  | 13
B00403 | B058D_B00403OD_PORTKLGIP | Central |  | Decomm |  | 2023Q2 | MA | Datasco | 4.6 TSSR Approved |  | 2023-04-14 | 2023-06-26 |  |  | 2023-06-19 |  | 2023-06-19 | 2024-07-12 | CD//Norhaliza | 2023-10-09 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002007085 |  |  |  |  | 2023-08-16 | Tower | TOWER | 45m
S00415 | S093G_S00415OD_SULAMANROAD | Sabah |  | Decomm |  | 2023Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-04-19 | 2023-06-26 |  |  | 2023-06-07 |  | 2023-06-12 | 2023-07-27 | CD//Mohidi Jaan | 2023-06-13 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230608-0007 | DU00002007086 |  |  |  |  | 2023-10-02 | Lampole | SHARING STRC SBC | 19
Q01120 | Q144A_Q01120OD_T3_KEMGABONG | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007087 | [6 empty] | Land site
Q00961 | Q118B_Q00961OD_KEMENAIND2 | Sarawak |  | Decomm |  | 2023Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2023-04-18 |  |  |  | 2023-08-08 |  | 2023-08-08 | 2023-09-23 | CD//John | 2023-08-09 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230613-0009 | DU00002007088 |  |  |  |  | 2023-08-30 |  | MONOPOLE
Q00471 | Q144A_Q00471OD_CB_LDGWOODMAN | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007089 | [6 empty] | TOWER
B02208 | B058E_B02208OD_TMNJAYAUTAMATLKPGARANG | Central |  | Decomm |  | 2023Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2023-04-12 | 2023-06-26 |  | 2023-04-20 | 2023-06-14 | Closed | 2023-06-26 | 2023-12-20 | CD//Sapian | 2023-07-06 | CelcomDigi_RAN_AllStar_TSS_Central_20230626_decom reraise | DU00002007090 |  |  |  |  | 2023-07-13 | Pole | BOOM | 21
P00322 | P033C_P00322OD_BUKITMINYAKIND | Northern | 4045K | Swap |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-17 | 2023-06-05 |  | 2023-06-08 |  | Closed | 2023-06-14 | 2023-06-27 | CD//Affendi | 2023-06-27 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0016 | DU00002007091 |  |  | 2023-07-12 | 2023-07-12 |  | Monople Tree | MONOPOLE | 30 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x5,Dismantle Celcom all RRU&BBU |  | 13
Q01494 | Q140B_Q01494OD_BKTAUPSBW | Sarawak | 9039K | Swap |  | 2023Q2 | HQ 2 | AllStar | 4.6 TSSR Approved |  | 2023-04-14 | 2023-05-02 |  | 2023-05-09 |  | Closed | 2023-05-15 | 2023-05-16 | CD//John | 2023-05-16 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230403-0003 | DU00002007092 |  |  | 2023-07-21 | 2023-07-06 |  | Minimast | RAMO | 30m | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
Q01268 | Q140C_Q01268OD_KGSENTOSA | Sarawak |  | Decomm |  | 2023Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-07-04 |  |  |  | 2023-07-25 |  | 2023-07-25 | 2023-08-08 | CD//John | 2023-08-08 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230613-0009/Celcom Digi_RAN-Trintel-TSS DECOMM-Sarawak-20231130 | DU00002007093 |  |  |  |  | 2023-11-21 |  | UNIPOLE
Q02132 | Kg Tanjung Bekakap | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | N/A - no need PR for MOCN Decomm | DU00002007094 | [6 empty] | TOWER
Q00565 | Q140C_Q00565OD_JLNWONGKINHUO | Sarawak |  | Decomm |  | 2023Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-06-20 |  |  |  | 2023-07-28 |  | 2023-07-31 | 2023-08-14 | CD//John | 2023-08-01 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230613-0009/Celcom Digi_RAN-Trintel-TSS DECOMM-Sarawak-20231130 | DU00002007095 |  | 20230807: all tx info & photos are wrong |  |  | 2023-12-31 |  | TOWER
S01765 | S109A_S01765OD_GILING2 | Sabah |  | Decomm |  | 2023Q2 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-20 |  |  |  | 2023-07-13 |  | 2023-07-13 | 2023-07-21 | CD//Ray Amos | 2023-07-13 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009/0612Sabah-Futong-BOQ Template (template) | DU00002007096 |  |  |  |  | 2023-07-20 |  | TOWER
P00764 | P033B_P00764IB_SUNWAY_CARNIVAL_MALL_SEBERANGJAYA | Northern | 4061K | Swap |  | 2023Q3 | WP | CCSMY | 4.6 TSSR Approved |  | 2023-06-15 | 2023-06-09 |  | 2023-06-15 |  | Closed | 2023-07-06 | 2023-07-12 | CD//Shamsul | 2023-07-11 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0016 | DU00002007097 |  |  | 2023-07-14 | 2023-07-13 |  | Portables BTS | INBUILDING |  | Add R8852E S9000 x3 + R8862A S1800 x3 + R8862A S2100 x3,Dismantle all celcom BBU&RRU
B02729 | B058D_B02729OD_TMNPERINDUSTRIANPULAUINDAH | Central |  | Decomm | Decomm->On Hold->Decomm | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-11 | 2023-06-26 |  |  | 2023-07-26 |  | 2023-06-15 | 2023-08-18 | CD//Sapian | 2023-07-04 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002007098 | [5 empty] | Monopole | MONOPOLE | 45
Q00668 | Q140A_Q00668OD_LRGINDAH | Sarawak |  | Decomm |  | 2023Q2 | SH | Datasco | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-26 |  | 2023-06-19 |  | Closed | 2023-06-20 | 2023-10-06 | CD//John | 2023-06-21 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009 | DU00002007099 |  | 17/8 - TSSR Reject Picture not complete |  |  | 2024-01-24 | Monopole | TOWER | 40m
S01888 | S093G_S01888IB_PPNS | Sabah |  | Decomm |  | 2023Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-06-15 |  |  |  | 2023-06-23 |  | 2023-06-15 | 2023-09-11 | CD//Ray Amos | 2023-06-15 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0008/0612Sabah-YPTT-BOQ Template (template) | DU00002007100 |  | 2023-07-14 missing tx photos and info |  |  | 2024-05-27 |  | INBUILDING
Q01795 | Q140B_Q01795OD_TMNTINE2 | Sarawak |  | Decomm |  | 2023Q2 | BY | Trintel | 4.6 TSSR Approved |  | 2023-06-16 |  |  |  | 2023-06-27 |  | 2023-06-07 | 2023-07-21 | CD//John | 2023-06-10 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230613-0009/Celcom Digi_RAN-Trintel-TSS DECOMM-Sarawak-20231130 | DU00002007101 |  |  |  |  | 2023-08-25 |  | TOWER
Q00915 | Q140B_Q00915OD_JLNBAWANGASSAN | Sarawak |  | Decomm |  | 2023Q2 | SH | CCSMY | 4.6 TSSR Approved |  | 2023-04-13 |  |  | 2023-06-14 |  | Closed | 2023-06-14 | 2023-08-08 | CD//John | 2023-06-14 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230613-0007/0612Sarawak-CCSMY-BOQ Template (template) | DU00002007102 |  | 20230712: missing TX photos and info |  |  | 2023-08-10 |  | TOWER
B01254 | B058E_B01254OD_PR_PLKNPAYAINDAH | Central |  | Decomm |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-10 | 2023-06-26 |  |  | 2024-05-29 |  | 2023-06-22 | 2024-07-16 | CD//Sapian | 2023-07-06 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002007103 |  |  |  |  | 2023-07-18 | Tower | MINI STRUCTURE | 60
P00454 | P033B_P00454OD_JLNSIAKAP | Northern |  | Decomm |  | 2023Q3 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-05-24 |  |  |  | 2023-06-16 |  | 2023-06-16 | 2023-07-21 | CD//Quah | 2023-07-06 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230720-0023/Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2 | DU00002007104 |  |  |  |  | 2023-08-16 |  | LAMP_POLE
Q00716 | Q140C_Q00716OD_TANAHWANG | Sarawak |  | Decomm |  | 2023Q2 | BY | Trintel | 4.6 TSSR Approved |  | 2023-04-20 | 2023-06-26 |  | 2023-07-08 |  | Closed | 2023-07-12 | 2023-07-28 | CD//John | 2023-07-13 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230613-0009 | DU00002007105 |  |  |  |  | 2023-12-28 | Monopole | TOWER | 30m
P00038 | P033B_P00038OD_EMC | Northern |  | Decomm |  | 2023Q3 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-05-05 |  |  |  | 2023-09-06 |  | 2023-08-15 | 2023-09-25 | CD//Shamsul | 2023-08-20 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1/Celcom Digi_RAN-CCSMY-TSS Decomm-Northern-20240131-0091 | DU00002007106 |  | 19/9: Need amend Drawing, dismantle list and FE Info |  |  | 2023-08-18 |  | MINI STRUCTURE
B02479 | B058D_B02479OD_SURAUDHIKMAH | Central |  | Decomm |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-14 |  |  |  | 2023-10-10 |  | 2023-06-12 | 2023-12-20 | CD//Ali akaram | 2023-06-13 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002007107 |  |  |  |  | 2023-07-18 | Lampole | LAMP_POLE | 25m
B02040 | B058D_B02040OD_MN_PULAUINDAH | Central | 1004P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007108 | [6 empty] | TOWER
Q01622 | QS50248_9_0-RHUNJI | Sarawak | 9008K | Swap |  | 2023Q3 | SH | Magicell | 4.6 TSSR Approved |  | 2023-04-17 | 2023-05-02 |  | 2023-05-10 |  | Closed | 2023-05-12 | 2023-05-15 | CD//John | 2023-05-13 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230419-0002 | DU00002007109 |  |  | 2023-10-24 | 2023-10-17 |  | Tower | TOWER | 31 | Add R9264H M901821 x2 + R9264M M1821 x1
S00791 | S109A_S00791OD_APARTMENTTUARAN | Sabah |  | Decomm |  | 2023Q2 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-26 |  |  | 2023-06-12 |  | 2023-06-14 | 2024-06-26 | CD//Ray Amos | 2023-06-15 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009/0612Sabah-Futong-BOQ Template (template) | DU00002007110 |  |  |  |  | 2023-09-29 | Pole | SHARING STRC OTHERS WATER TANK | 21
B00446 | B058D_B00446OD_PENDAMARINDAH | Central |  | Decomm |  | 2023Q2 | IE | Ascentrack | 4.6 TSSR Approved |  | 2023-04-26 | 2023-06-26 |  | 2023-06-03 | 2024-10-21 | Closed | 2023-06-06 | 2023-10-18 | CD//Norhaliza | 2023-06-08 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230626_decom reraise | DU00002007111 |  |  |  |  | 2023-07-17 | Unipole | TRIPOD | 8m
P00048 | P033C_P00048OD_TMNPELANGI | Northern |  | Decomm |  | 2023Q3 | SM | YPTT | 4.6 TSSR Approved |  | 2023-06-17 |  |  |  | 2023-07-03 |  | 2023-07-04 | 2023-09-21 | CD//Affendi | 2023-07-04 | Celcom Digi_RAN-YPTT-TSS-Northern-20230609-0018 | DU00002007112 |  | Missing Info and Photo for link NT03294 |  |  | 2023-07-19 |  | TOWER
Q00718 | Q140C_Q00718OD_TMNSEDUAN | Sarawak |  | Decomm |  | 2023Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-04-17 | 2023-06-26 |  | 2023-06-23 |  | Under Approval | 2023-07-11 | 2023-09-23 | CD//John | 2023-07-12 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230613-0009 | DU00002007113 |  |  |  |  | 2023-07-28 | Monopole | BOOM | 30m
B02461 | B058D_B02461OD_KGTELOKGONG | Central |  | Decomm |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-15 |  |  |  | 2023-05-31 |  | 2023-06-12 | 2023-08-09 | CD//Sapian | 2023-06-14 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002007114 |  |  |  |  | 2023-07-18 |  | TOWER
B02605 | B059A_B02605OD_JLNMJDLAMABANTING | Central |  | Decomm |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-04 | 2023-04-05 |  |  | 2023-06-22 |  | 2023-06-22 | 2023-08-09 | CD//Sapian | 2023-07-06 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise / CelcomDigi_TX_GTSB_TSS_Decom_Central_20230714 | DU00002007115 |  |  |  |  | 2023-07-14 | Monople Tree | MONOPOLE | 45m
Q01747 | Q140C_Q01747OD_JLNJEWITTIMUR | Sarawak |  | Decomm |  | 2023Q2 | ZB | AllStar | 4.6 TSSR Approved |  | 2023-04-25 | 2023-06-26 |  | 2023-07-07 |  | Closed | 2023-07-11 | 2024-02-15 | CD//John | 2023-07-12 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230613-0007/0612Sarawak-AllStar-BOQ Template (template).xls | DU00002007116 |  | 2023-07-16 Missing TX photos and info |  |  | 2023-12-09 |  | RAPOLE | 30
S00580 | RL10137_INDAHPERMAI2 | Sabah |  | Decomm |  | 2023Q2 | SH | Datasco | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-26 |  |  | 2023-05-18 |  | 2023-06-12 | 2023-10-13 | CD//Mohidi Jaan | 2023-06-13 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006 | DU00002007117 |  |  |  |  | 2023-10-20 | Minimast | BOOM
P00099 | P034A_P00099OD_BAGANLALANG | Northern |  | Decomm |  | 2023Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-05-23 |  |  |  | 2023-07-03 |  | 2023-07-03 | 2023-08-08 | CD//Shamsul | 2023-07-06 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V2 | DU00002007118 |  |  |  |  | 2023-10-24 |  | TRIPOD
P00709 | P034A_P00709IB_PENANG_CENTRAL | Northern |  | Decomm |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-06-14 |  |  |  | 2023-06-19 |  | 2023-06-20 | 2024-07-22 | CD//Quah | 2023-07-06 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002007119 |  |  |  |  | 2023-10-13 |  | IN-BUILDING
B00484 | B058B_B00484OD_BT6SEMENTA | Central | 1023K | Swap |  | 2023Q3 | HQ 6 | CCSMY | 4.6 TSSR Approved |  | 2023-05-15 | 2023-06-02 |  | 2023-06-08 |  | Closed | 2023-06-19 | 2023-07-07 | CD//Norhaliza | 2023-07-06 | CelcomDigi_RAN_CCSMY_TSS_Central_20230508_0002 | DU00002007120 |  |  | 2023-12-18 | 2023-12-09 |  | Tower | TOWER | 45 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 1
P00349 | P034A_P00349OD_BGNDALAM | Northern | 4046K | Swap |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-15 | 2023-05-23 |  | 2023-05-26 |  | Closed | 2023-06-01 | 2023-06-11 | E//Hazida | 2023-06-11 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0015 | DU00002007121 |  |  | 2023-06-27 | 2023-06-22 |  | Monopole | LAMP_POLE | 25 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 12
S01148 | S093G_S01148OD_KINGFISHERRAJAUDANG | Sabah |  | Decomm |  | 2023Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-06-15 |  |  |  | 2023-04-30 |  | 2023-06-15 | 2023-09-01 | CD//Mohidi Jaan | 2023-06-15 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0008/0612Sabah-YPTT-BOQ Template (template) | DU00002007122 |  | 2023-07-20 missing tx photos and info |  |  | 2023-10-16 |  | LAMP_POLE
B01476 | B058D_B01476OD_PR_LAGUNAPARK | Central |  | Decomm |  | 2023Q2 | MA | Datasco | 4.6 TSSR Approved |  | 2023-04-15 |  |  |  | 2023-07-26 |  | 2023-06-26 | 2023-10-18 | CD//Sapian | 2023-07-07 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002007123 |  |  |  |  | 2023-09-23 | Lampole | AESTHETIC MONOPOLE | 20m
B01952 | B058D_B01952OD_TELOKGONGIND | Central |  | Decomm |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-11 |  |  |  | 2023-07-26 |  | 2023-06-13 | 2023-08-09 | CD//Sapian | 2023-07-04 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002007124 |  |  |  |  | 2023-07-19 |  | MONOPOLE
B02212 | B058E_B02212OD_JLNSEGENTINGBNTG | Central | 1040K | Swap |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-07 | 2023-05-08 |  | 2023-04-14 |  | Closed | 2023-05-11 | 2023-06-06 | CD//Sapian | 2023-05-19 | CelcomDigi_RAN_GTSB_Central_20230407_0012 | DU00002007125 |  |  | 2023-06-13 | 2023-06-08 |  | Monople Tree | MONOPOLE | 45 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
B00502 | B058D_B00502OD_PR_PULAUKETAM | Central | 1024K | Swap |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-19 | 2023-04-28 |  | 2023-05-03 |  | Closed | 2023-05-12 | 2023-05-22 | CD//Norhaliza | 2023-05-22 | CelcomDigi_RAN_Datasco_TSS_Central_20230419_0014 | DU00002007126 |  |  | 2023-05-31 | 2023-05-27 |  | Minimast | MINI STRUCTURE | 9 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
P00367 | P033B_P00367OD_PENANGBRIDGE | Northern |  | Decomm |  | 2023Q3 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-07-20 |  |  |  | 2023-07-26 |  | 2023-07-27 | 2023-08-08 | CD//Affendi | 2023-07-31 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1 | DU00002007127 |  |  |  |  | 2023-08-30 | BillBoard | LAMP_POLE | 35m
P00070 | P034A_P00070OD_CHAINFERRY | Northern |  | Decomm |  | 2023Q3 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-05-25 |  |  |  | 2023-06-22 |  | 2023-06-23 | 2023-09-25 | CD//Shamsul | 2023-07-04 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002007128 |  | 21/8:Please include all TX equipment Photo |  |  | 2023-08-23 |  | TRIPOD
P00597 | P033B_P00597OD_LIGHTHOTEL | Northern | 4055K | Swap |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-13 | 2023-06-15 |  | 2023-06-15 |  | Closed | 2023-06-16 | 2023-06-22 | CD//Shamsul | 2023-06-22 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0015 | DU00002007129 |  |  | 2023-07-15 | 2023-07-14 |  | In-Building System | BOOM | No structure, got antenna boom wall mount only at site | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
S01324 | S093A_S01324OD_SOUTHKKIP | Sabah |  | Decomm |  | 2023Q2 | MS | Datasco | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-26 |  |  | 2023-06-23 |  | 2023-06-20 | 2023-07-21 | CD//Ray Amos | 2023-06-21 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006 | DU00002007130 |  |  |  |  | 2023-10-03 | Lampole | RAPOLE | 30 meter
P00163 | P033B_P00163OD_TMSBRGJAYA2 | Northern |  | Decomm |  | 2023Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-06-17 |  |  |  | 2023-08-16 |  | 2023-06-26 | 2023-08-28 | CD//Shamsul | 2023-07-04 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002007131 |  | No TX Info, Photo not enough |  |  | 2023-09-28 |  | TOWER
B02716 | B058E_B02716OD_VLJLNNANGKASIJANGKANG | Central |  | Decomm |  | 2023Q2 | CR | AllStar | 4.6 TSSR Approved |  | 2023-04-12 |  |  |  | 2023-10-26 |  | 2023-08-17 | 2023-11-29 | CD//Sapian | 2023-08-23 | CelcomDigi_RAN_AllStar_TSS_Central_20230626_decom reraise | DU00002007132 |  |  |  |  | 2023-07-22 |  | LAMP_POLE
P00166_IBC | P034A_P00166OD_NBTOWER | Northern | 4060K | Swap |  | 2023Q3 | WP | GCI | 4.6 TSSR Approved |  | 2023-10-04 |  |  | 2024-04-24 |  | Closed | 2023-10-04 | 2023-10-19 | CD//Affendi | 2023-06-22 | Celcom Digi_RAN-GCI-TSS-Northern-20231108-0073 | DU00002007133 |  |  | 2023-10-12 | 2023-06-22 |  |  | BOOM |  | R8862A S2100 x1+R8862A S1800 x1,Dismantle all celcom BBU&RRU
B01708 | B058D_ B01708IB_WESTPORT | Central |  | Decomm |  | 2023Q2 | SY1 | GCI | 4.6 TSSR Approved |  | 2024-10-04 |  | 2024-10-16 |  | 2024-10-16 | To be Submitted | 2024-10-17 |  | CD//Sofiah | 2024-11-07 | 0924CD-Central-GCI-BOQ Template(new contract) | DU00002007134 |  | Pls provide FE part |  |  |  |  | BOOM
Q02084 | Q144A_Q02084OD_T3_SGANNAU | Sarawak | 9446P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN->Swap | 2023Q3 |  | Trintel | 1.1 Pending Survey - Subcon | [6 empty] | To be Submitted |  |  |  |  | SQ202601300355 - Trintel | DU00002007135 | [6 empty] | TOWER |  | Add R8852E S9000 x6+R9264M M1821 x4 |  | 3
B01960 | B058D_B01960OD_PLBHBARAT | Central |  | Decomm |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-11 | 2023-06-26 |  |  | 2023-06-15 |  | 2023-06-15 | 2026-04-20 | CD//Norhaliza | 2023-07-05 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002007136 |  | For NE, Please check existing IDU for CT09421 (B01960-B01069). SM AGS20. should have 2 run IF cable. IDU shown in photo probably belongs different link. FE: wrong antenna, existing antenna freq should be 13G. ODU should have 2 pcs. |  |  | 2026-04-23 | Unipole | UNIPOLE | 10
Q01834 | Q140A_Q01834OD_NANGSANG | Sarawak |  | Decomm |  | 2023Q2 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-04-12 |  |  | 2023-06-16 |  | Closed | 2023-06-16 | 2023-08-30 | CD//John | 2023-06-16 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230613-0007/Celcom Digi_RAN-CCSMY-TSS DECOMM-Sarawak-20230823 | DU00002007137 |  | 20230727: missing tx photos and info |  |  | 2024-02-15 |  | TOWER
Q00215 | Q140C_Q00215OD_TMSBW | Sarawak | 9017K | Swap |  | 2023Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-04-28 | 2023-05-04 |  | 2023-05-08 |  | Closed | 2023-05-15 | 2023-05-15 | CD//John | 2023-05-15 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230403-0003 | DU00002007138 |  |  | 2023-08-30 | 2023-07-14 |  | Tower | TOWER | 100 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2600 x4,Dismantle Celcom all RRU&BBU |  | 2
B00492 | B058C_B00492OD_TMNRADZI | Central |  | Decomm |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-05-16 |  |  |  | 2023-06-21 |  | 2023-06-23 | 2023-10-18 | CD//Norhaliza | 2023-10-09 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230626_decom reraise | DU00002007139 |  |  |  |  | 2023-07-11 |  | TOWER
Q01748 | Q140B_Q01748OD_JLNOYASBW | Sarawak |  | Decomm |  | 2023Q2 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-04-14 |  |  | 2023-06-16 |  | Closed | 2023-06-16 | 2023-08-14 | CD//John | 2023-06-16 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230613-0007/Celcom Digi_RAN-CCSMY-TSS DECOMM-Sarawak-20230809 | DU00002007140 |  | 20230731 : Missing TX info |  |  | 2023-10-06 |  | RAPOLE
S00032 | S109A_S00032OD_MIMPIANJADI | Sabah |  | Decomm |  | 2023Q2 | MS | Futong | 4.6 TSSR Approved |  | 2023-06-22 |  |  |  | 2023-06-22 |  | 2023-06-19 | 2023-09-29 | CD//Ray Amos | 2023-06-19 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009 | DU00002007141 |  | 2023-07-06 missing tx photos and info |  |  | 2023-10-09 |  | TOWER
S00571 | S093D_S00571OD_CB_KGKOBUNI | Sabah |  | Decomm |  | 2023Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2023-04-20 | 2023-06-26 |  |  | 2023-06-23 |  | 2023-06-13 | 2023-07-21 | CD//Mohidi Jaan | 2023-06-13 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230608-0008 | DU00002007142 |  |  |  |  | 2023-10-19 | Tower | TOWER | 60
B00745 | B063A_B00745OD_TMTGSEPAT | Central |  | Decomm |  | 2023Q2 | IE | Magicell | 4.6 TSSR Approved |  | 2023-04-19 | 2023-06-26 |  | 2023-04-21 | 2023-08-18 | Rectificating | 2023-07-24 | 2023-08-24 | CD//Sapian | 2023-09-23 | CelcomDigi_RAN_Magicell_TSS_Central_20230626_decom reraise / CelcomDigi_TX-RAN_Magicell_TSS_Central_20230818 | DU00002007143 |  |  |  |  | 2023-10-27 | Tower | BOOM | 47
Q00237 | Q140C_Q00237OD_SMCSBW | Sarawak |  | Decomm |  | 2023Q2 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-08-10 |  |  | 2023-08-25 |  | Closed | 2023-08-25 | 2023-09-01 | CD//John | 2023-08-28 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009/0612Sarawak-Datasco-BOQ Template (template) | DU00002007144 |  |  |  |  | 2023-10-11 |  | BOOM
Q00205 | Q140C_Q00205ODA_JLNSALIM | Sarawak |  | Decomm |  | 2023Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-06-22 |  |  |  | 2023-07-20 |  | 2023-07-20 | 2024-01-18 | CD//John | 2023-08-08 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230613-0009 | DU00002007145 |  | 28/8: All tx info are mssing |  |  | 2023-12-31 |  | BOOM
B00686 | B058D_B00686OD_PULAUINDAH | Central |  | Decomm |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-14 |  |  |  | 2023-07-27 |  | 2023-07-27 | 2023-12-21 | CD//Sapian | 2023-08-15 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002007146 |  |  |  |  | 2023-09-30 |  | TOWER
Q02082 | Q144A_Q02082OD_T3_JLNTATAUSANGAN | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | N/A | DU00002007147 | [6 empty] | TOWER
P00634 | P033C_P00634OD_TMNBKTJURU | Northern |  | Decomm |  | 2023Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-06-08 |  |  |  | 2023-07-05 |  | 2023-06-15 | 2023-10-27 | CD//Quah | 2023-07-07 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1 | DU00002007148 |  | No TX Info, Photo not enough |  |  | 2023-07-22 | Monopole | MONOPOLE | 26m
Q01688 | Q140C_Q01688OD_CB_RHKANYAN | Sarawak |  | Decomm |  | 2023Q2 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-06-28 |  |  | 2023-07-04 |  | Under Approval | 2023-07-11 | 2024-06-19 | CD//John | 2023-07-12 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009/0612Sarawak-Datasco-BOQ Template (template) | DU00002007149 |  |  |  |  | 2024-01-17 |  | TOWER
S01962 | S093D_S01962OD_TMNNELLYPH9 | Sabah | 7016K | Swap |  | 2023Q3 | MS | Datasco | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-28 |  | 2023-05-11 |  | Closed | 2023-05-13 | 2023-05-15 | CD//Mohidi Jaan | 2023-05-15 | Celcom Digi_RAN-Datasco- TSS-Sabah-20230407-0002 | DU00002007150 |  |  | 2023-07-13 | 2023-07-06 |  | Tower | TOWER | 30m | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
Q01790 | Q140C_Q01790OD_LEMBAGAAIRSBW | Sarawak |  | Decomm |  | 2023Q2 | ZB | AllStar | 4.6 TSSR Approved |  | 2023-04-13 | 2023-06-26 |  | 2023-07-07 |  | Under Approval | 2023-07-12 | 2023-09-23 | CD//John | 2023-07-13 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230613-0007/0612Sarawak-AllStar-BOQ Template (template).xls | DU00002007151 |  | 2023-07-16 Missing TX photos and info |  |  | 2023-12-08 | Monopole | RAPOLE | 30
P00136 | P034A_P00136OD_JLNONGYIIHOW | Northern | 4171K | Decomm |  | 2023Q3 | MH | YPTT | 4.6 TSSR Approved |  | 2023-05-18 |  |  |  | 2023-06-17 |  | 2023-06-19 | 2023-08-08 | CD//Shamsul | 2023-07-04 | Celcom Digi_RAN-YPTT-TSS-Northern-20230609-0018 | DU00002007152 |  | No TX Info, Photo not enough |  |  | 2023-07-21 |  | MINI STRUCTURE
P00156 | P034A_P00156OD_RAJAUDA | Northern |  | Decomm |  | 2023Q3 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-05-23 |  |  |  | 2023-06-16 |  | 2023-06-16 | 2023-09-06 | CD//Quah | 2023-07-06 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1 | DU00002007153 |  | 11/7: No TX Info, Photo not enough 7/8: Pending TX solution, Have E1&IDU |  |  | 2023-07-24 |  | BOOM
P00234 | P034A_P00234OD_TMBUTTERWORTH | Northern |  | Decomm |  | 2023Q3 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-06-17 |  |  |  | 2023-07-27 |  | 2023-07-23 | 2023-08-08 | CD//Shamsul | 2023-07-26 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002007154 |  |  |  |  | 2023-08-17 |  | BOOM
Q01335 | Q118B_Q01335OD_KGJEPAK | Sarawak |  | Site Out (Decomm) | Decomm->On Hold->Site Out->Replacement, Site Out (Decomm) | 2023Q3 |  | Trintel | 15.3 Decomm Done without TSSR |  | 2025-09-20 |  |  |  |  | To be Submitted |  |  | CD//John |  | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230613-0009 | DU00002007155 |  |  |  |  | 2025-06-26 |  | RAPOLE
B02005 | B058D_B02005OD_TMPORTKLG | Central | 1036K | Swap |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-19 | 2023-04-29 |  | 2023-05-06 |  | Closed | 2023-05-11 | 2023-06-03 | CD//Sapian | 2023-05-19 | CelcomDigi_RAN_Datasco_TSS_Central_20230419_0014 | DU00002007156 |  |  | 2023-09-08 | 2023-06-13 |  | Pole | BOOM | 6 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x5,Dismantle Celcom all RRU&BBU |  | 12
Q00682 | Q118A_Q00682OD_SHAHIDACOMM | Sarawak |  | Decomm |  | 2023Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2023-04-17 | 2023-06-26 |  | 2023-06-12 |  | Closed | 2023-06-12 | 2023-11-16 | CD//John | 2023-06-12 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230613-0009 | DU00002007157 |  | 2023-06-26 Missing TX photos and info |  |  | 2023-11-08 | Monopole | LAMP_POLE | 24m
S01740 | Kg Pangalan | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q2 | MS | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Ray Amos |  | N/A | DU00002007158 | [6 empty] | TOWER
S00806 | S109A_S00806OD_PEKANTAMPARULI | Sabah |  | Decomm |  | 2023Q2 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-20 | 2023-06-26 |  |  | 2023-06-22 |  | 2023-06-14 | 2023-07-27 | CD//Ray Amos | 2023-06-15 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009 | DU00002007159 |  |  |  |  | 2023-09-29 | Unipole | BOOM | 13
X00045 | S093G_X00045OD_RAMOKINGFISHER | Sabah |  | Decomm |  | 2023Q3 | MS | GTSB | 4.6 TSSR Approved |  | 2023-08-17 |  |  |  | 2023-11-03 |  | 2023-11-06 | 2024-05-14 | CD//Ray Amos | 2023-11-07 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230818/Celcom Digi_RAN-GTSB-TSS DECOMM MW-Sabah-20240419 | DU00002007160 |  |  |  |  | 2024-02-23 |  | TBC
Q01867 | Q122A_Q01867OD_CB_RHJELINGAI | Sarawak | 9047K | Swap |  | 2023Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-04-13 | 2023-05-05 |  | 2023-05-10 |  | Closed | 2023-05-11 | 2023-05-11 | CD//John | 2023-05-11 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230403-0003 | DU00002007161 |  |  | 2023-07-22 | 2023-07-05 |  |  | TOWER | 45 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
P00430 | P033B_P00430OD_PERMATANGTOKKANDU | Northern | 4048K | Swap | Swap->On Hold->Swap | 2023Q3 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-05-25 | 2023-06-23 |  | 2024-06-11 |  | Rectificating | 2023-06-27 | 2024-06-21 | CD//Affendi | 2024-06-21 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0016 | DU00002007162 |  |  | 2024-08-01 | 2023-07-25 |  | Monopole | LAMP_POLE | 20m | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
P00458 | P033B_P00458OD_PAUHINDAH | Northern | 4050K | Swap |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-13 | 2023-05-20 |  | 2023-05-30 |  | Closed | 2023-06-06 | 2023-06-13 | CD//Affendi | 2023-06-13 | Celcom Digi_RAN-GTSB-TSS-Northern-20230509-0017 | DU00002007163 |  |  | 2023-07-13 | 2023-07-06 |  | Unipole | LAMP_POLE | 3M | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 2
P00041 | P033B_P00041OD_SEBERANGJAYA | Northern | 4038K | Swap |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-17 | 2023-05-23 |  | 2023-06-02 |  | Closed | 2023-06-06 | 2023-06-14 | CD//Heng | 2023-06-14 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0016 | DU00002007164 |  |  | 2023-07-13 | 2023-07-13 |  | Minimast | BOOM | 5 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x5,Dismantle Celcom all RRU&BBU |  | 12
S00420 | RT10219_ONEBORNEOHYPERMALL | Sabah |  | Decomm |  | 2023Q3 | MS | GTSB | 4.6 TSSR Approved |  | 2023-08-15 |  |  |  | 2023-08-16 |  | 2023-09-11 | 2023-09-16 | CD//Ray Amos | 2023-08-21 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230816 | DU00002007165 |  |  |  |  | 2023-11-18 |  | BOOM
S00701 | S093A_S00701OD_PEKANTELIPOK | Sabah |  | Decomm |  | 2023Q2 | MS | Datasco | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-26 |  |  | 2023-05-13 |  | 2023-07-10 | 2023-07-21 | CD//Mohidi Jaan | 2023-07-10 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006 | DU00002007166 |  |  |  |  | 2023-08-07 | Minimast | TOWER | 60m
B02204 | B058C_B02204OD_AMBANGBOTANICKLG | Central |  | Decomm |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-04-17 |  |  |  | 2023-08-02 |  | 2023-08-08 | 2023-10-25 | CD//Sapian | 2023-08-17 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230626_decom reraise | DU00002007167 |  |  |  |  | 2024-07-31 |  | BOOM
P00166 | P034A_P00166OD_NBTOWER | Northern | 4060K | Decomm |  | 2023Q3 | WP | GCI | 4.6 TSSR Approved |  | 2023-06-15 | 2023-06-21 |  | 2023-06-16 | 2023-07-05 | Closed | 2023-06-20 | 2023-06-22 | CD//Quah | 2023-06-22 | 0626Northen-GCI-BOQ Template (template) | DU00002007168 |  |  |  |  | 2023-07-24 |  | BOOM
Q00787 | Q140A_Q00787OD_BKTKEMUYANG | Sarawak |  | Decomm |  | 2023Q2 | ZB | CCSMY | 4.6 TSSR Approved |  | 2023-04-17 |  |  |  | 2023-06-26 |  | 2023-07-20 | 2023-09-08 | CD//John | 2023-07-20 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230613-0007 | DU00002007169 |  | 22/8: Uncompleted info & photos |  |  | 2023-08-03 |  | TOWER
Q01257 | Q140A_Q01257OD_ULUSGMERAHCOMM | Sarawak |  | Decomm |  | 2023Q2 | SH | CCSMY | 4.6 TSSR Approved |  | 2023-06-19 |  |  | 2023-06-26 |  | Closed | 2023-08-28 | 2023-09-01 | CD//John | 2023-08-28 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230613-0007/Celcom Digi_RAN-CCSMY-TSS DECOMM-Sarawak-20230825 | DU00002007170 |  |  |  |  | 2024-02-27 |  | LAMP_POLE
Q00650 | Q125A_Q00650OD_SPGJEPAK | Sarawak |  | Decomm |  | 2023Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2023-08-22 |  |  | 2023-08-24 |  | Closed | 2023-08-24 | 2023-09-19 | CD//John | 2023-08-25 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230613-0009/Celcom Digi_RAN-Trintel-TSS DECOMM-Sarawak-20231216 | DU00002007171 |  | 25/8: Uncompleted info & photos |  |  | 2023-09-07 |  | TOWER
Q00663 | Q140A_Q00663OD_SGMERAH2 | Sarawak |  | Decomm |  | 2023Q2 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-06-27 |  |  | 2023-07-18 |  | Closed | 2023-07-18 | 2023-09-08 | CD//John | 2023-07-19 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009 | DU00002007172 |  |  |  |  | 2023-07-31 |  | TOWER
B02243 | B058B_B02243OD_JLNGAMELANKLGUTAMA | Central | 1041K | Swap |  | 2023Q3 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-05-12 | 2023-06-14 |  | 2023-06-19 |  | Rectificating | 2023-06-23 | 2023-08-16 | CD//Sapian | 2023-08-16 | CelcomDigi_RAN_CCSMY_TSS_Central_20230508_0002 | DU00002007173 |  |  | 2023-08-11 | 2023-08-04 |  | Tower | RAPOLE | 25 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 23
B00475 | B058D_B00475OD_LBHSULTANMOHD | Central | 1022K | Swap |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-19 | 2023-05-12 |  | 2023-05-16 |  | Closed | 2023-05-19 | 2023-06-03 | CD//Norhaliza | 2023-05-29 | CelcomDigi_RAN_Datasco_TSS_Central_20230417_0012 | DU00002007174 |  |  | 2023-07-13 | 2023-06-19 |  | Unipole | TRIPOD | 8m | Add R8852E S9000 x3 + A9732 M1821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 123
S01849 | T3_0092 - PULAU GAYA | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q2 | MS | Datasco | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  | N/A | DU00002007175 | [6 empty] | TOWER
B01183 | B058D_B01183OD_KGNELAYAN | Central |  | Decomm |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-15 |  |  | 2023-10-10 | 2023-05-19 | Under Approval | 2023-06-13 | 2023-11-29 | CD//Sapian | 2023-07-04 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002007176 |  |  |  |  | 2023-07-14 |  | MINARATE
B02844 | B063A_B02844OD_CB_KGBATULAUT2 | Central |  | Decomm |  | 2023Q2 | MA | Magicell | 4.6 TSSR Approved |  | 2023-04-15 | 2023-06-26 |  | 2023-04-18 | 2023-06-13 | Rectificating | 2023-06-16 | 2023-08-09 | CD//Norhaliza | 2023-07-06 | CelcomDigi_RAN_Magicell_TSS_Central_20230626_decom reraise / CelcomDigi_TX_Magicell_TSS_Decom_Central_20230714 | DU00002007177 |  |  |  |  | 2023-07-03 | Monople Tree | MONOPOLE | 45M
S00447 | S109A_S00447OD_FOHLIM | Sabah |  | Decomm |  | 2023Q2 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-20 |  |  |  | 2023-07-12 |  | 2023-07-13 | 2023-07-21 | CD//Ray Amos | 2023-07-13 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009/0612Sabah-Futong-BOQ Template (template) | DU00002007178 |  |  |  |  | 2023-07-24 |  | TOWER
S00923 | RL10566_UMSMASJID2 | Sabah |  | Decomm |  | 2023Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-04-21 | 2023-06-26 |  |  | 2023-06-08 |  | 2023-06-13 | 2023-07-21 | CD//Mohidi Jaan | 2023-06-13 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230608-0007 | DU00002007179 |  |  |  |  | 2023-09-11 | Lampole | MINARET | 25
B02806 | B058E_B02806OD_KOTABAYUEMASKLANG | Central |  | Decomm |  | 2023Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2023-04-12 | 2023-06-26 |  |  | 2023-12-13 |  | 2023-06-15 | 2023-12-20 | CD//Norhaliza | 2023-07-05 | CelcomDigi_RAN_AllStar_TSS_Central_20230626_decom reraise | DU00002007180 |  |  |  |  | 2023-07-12 | Pole | WALL MOUNTED BOOM | 15
P00151 | P033B_P00151OD_JALANBARU | Northern | 4042K | Swap |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-12 | 2023-06-02 |  | 2023-06-08 |  | Closed | 2023-06-12 | 2023-06-21 | CD//Affendi | 2023-06-21 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0016/Celcom Digi_CD CONSOLIDATION-GTSB-TI-Northern-20240920_Old Contract | DU00002007181 |  |  | 2023-07-11 | 2023-07-06 |  | In-Building System | BOOM | 16M | Add R8852E S9000 x3 + A9732 M1821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 123
Q01943 | Q140A_Q01943OD_KGBAHAGIAJAYA | Sarawak |  | Decomm |  | 2023Q2 | SH | CCSMY | 4.6 TSSR Approved |  | 2023-04-13 |  |  | 2023-06-22 |  | Closed | 2023-07-26 | 2023-08-24 | CD//John | 2023-07-27 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230613-0007/Celcom Digi_RAN-CCSMY-TSS DECOMM-Sarawak-20230811 | DU00002007182 |  |  |  |  | 2024-02-19 |  | RAPOLE
Q01117 | Q118B_Q01117OD_CB_RHRANGGA | Sarawak | 9031K | Swap |  | 2023Q3 | MA | Trintel | 4.6 TSSR Approved |  | 2023-04-13 | 2023-04-20 |  | 2023-04-28 |  | Closed | 2023-05-02 | 2023-05-04 | CD//John | 2023-05-04 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230403-0003 | DU00002007183 |  |  | 2023-07-27 | 2023-07-06 |  | Tower | Land site | 70 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
B02613 | B058C_B02613OD_JLNIMPIAN3BDRBOTANIKKLG | Central | 1052K | Swap |  | 2023Q2 | IE | Ascentrack | 4.6 TSSR Approved |  | 2023-04-28 | 2023-05-02 |  | 2023-05-04 |  | Closed | 2023-05-05 | 2023-06-05 | CD//Tee | 2023-05-18 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230428_0015 | DU00002007184 |  |  | 2023-06-22 | 2023-06-21 |  | Lampole | LAMP_POLE | 24 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
B00840 | B058D_B00840IB_GLENNCRUISE | Central | 1062K | Swap |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-06-22 | 2023-06-26 |  | 2023-07-08 |  | Closed | 2023-07-20 | 2023-08-29 | CD//Sofiah | 2023-08-29 | CelcomDigi_RAN_Datasco_TSS_Central_20230417_0012 | DU00002007185 |  |  | 2023-12-28 | 2023-09-18 |  |  | BOOM |  | Add R8852E S9000 x1 + R8862A S2100 x1,Dismantle all celcom BBU&RRU
Q00169 | Q140C_Q00169OD_PDRMSBW | Sarawak | 9011K | Swap |  | 2023Q2 | MA | Trintel | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-25 |  | 2023-04-28 |  | Rectificating | 2023-04-29 | 2023-05-04 | CD//John | 2023-05-04 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230403-0003 | DU00002007186 |  |  | 2023-07-26 | 2023-07-14 |  | Tower | TOWER | 90m | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2600 x4,Dismantle Celcom all RRU&BBU |  | 1
B02458 | B058E_B02458OD_PULAUINDAHBOTANIC | Central |  | Decomm |  | 2023Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-15 |  | 2023-04-14 | 2023-06-14 | Under Approval | 2023-06-15 | 2023-12-21 | CD//Sapian | 2023-07-04 | CelcomDigi_RAN_AllStar_TSS_Central_20230626_decom reraise | DU00002007187 |  |  |  |  | 2023-07-11 | BillBoard | BILLBOARD
P00113 | P033C_P00113OD_KUALAJURU | Northern |  | Decomm |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-05-31 |  |  |  | 2023-07-06 |  | 2023-07-06 | 2023-09-06 | CD//Shamsul | 2023-07-12 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1 | DU00002007188 |  | No TX Info, Photo not enough |  |  | 2023-09-20 |  | TOWER
P00610 | P033B_P00610OD_PENANGBRIDGEITC | Northern |  | Decomm |  | 2023Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-05-19 |  |  |  | 2023-07-28 |  | 2023-08-02 | 2023-08-28 | CD//Rohizam | 2023-08-02 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002007189 |  |  |  |  | 2023-07-28 |  | TOWER
B00826 | B058D_B00826OD_JLNTGBADAR | Central |  | Decomm |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-17 | 2023-06-26 |  |  | 2024-03-19 |  | 2023-06-13 | 2024-05-31 | CD//Norhaliza | 2023-11-16 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002007190 |  |  |  |  | 2023-07-13 | Minimast | BOOM | 6
P00133 | P033B_P00133OD_BANDARSUNWAY | Northern |  | Decomm |  | 2023Q3 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-06-19 |  |  |  | 2023-07-11 |  | 2023-07-12 | 2023-09-06 | CD//Shamsul | 2023-07-12 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1 | DU00002007191 |  | No TX Info, Photo not enough |  |  | 2023-10-02 |  | BOOM
B02547 | B058B_B02547OD_TMNKEMBARAKLG | Central | 1048K | Swap |  | 2023Q3 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-05-06 | 2023-05-19 |  | 2023-05-24 |  | Closed | 2023-06-16 | 2023-11-16 | CD//Ali akaram | 2023-08-16 | CelcomDigi_RAN_CCSMY_TSS_Central_20230508_0002 | DU00002007192 |  |  | 2023-09-24 | 2023-08-04 |  | Monopole | LAMP_POLE | 30M | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 13
B00531 | B058D_B00531OD_PKLANGUTARA | Central |  | Decomm |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2024-07-30 |  | 2024-08-01 |  | 2024-08-12 |  | 2024-08-15 | 2024-09-26 | CD//Sapian | 2024-08-20 | 0731CD-Central-GTSB-BOQ Template(new contract) | DU00002007193 |  |  |  |  | 2024-11-14 |  | BOOM
B00784 | B058B_B00784OD_TMNENGANN | Central | 1031K | Site Out (Swap) | Swap->Site out->Replacement, Site Out (Swap) | 2023Q3 | MA | YPTT | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2025-07-16 |  | 2025-07-10 |  |  | To be Submitted |  |  |  |  | SQ202506140184 | DU00002007194 | [6 empty] | TRIPOD
S00924 | S093G_S00924OD_KINGFISHERSULAMAN | Sabah |  | Decomm |  | 2023Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-04-21 | 2023-06-26 |  |  | 2023-06-30 |  | 2023-06-13 | 2023-07-27 | CD//Ray Amos | 2023-06-13 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230608-0007 | DU00002007195 |  |  |  |  | 2023-09-20 | Pole | BOOM | 3
S01100 | S093D_S01100OD_KIANYAP | Sabah |  | Decomm |  | 2023Q3 | AD | Magicell | 4.6 TSSR Approved |  | 2023-05-05 |  |  |  | 2023-06-14 |  | 2023-06-19 | 2023-07-21 | CD//Mohidi Jaan | 2023-06-18 | Celcom Digi_RAN-Magicell-TSS-Sabah-20230608-0003 | DU00002007196 |  |  |  |  | 2023-09-11 |  | BOOM
S00702 | S093G_S00702OD_POLITEKNIKK | Sabah |  | Decomm |  | 2023Q2 | MS | Datasco | 4.6 TSSR Approved |  | 2023-08-15 |  |  |  | 2023-08-18 |  | 2023-08-23 | 2023-09-16 | CD//Ray Amos | 2023-08-24 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006/0612Sabah-Datasco-BOQ Template (template) | DU00002007197 |  |  |  |  | 2023-12-14 |  | LAMP_POLE
S00926 | S093G_S00926OD_RAMOAPARTMENTUNIVERSITI | Sabah |  | Decomm |  | 2023Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-06-14 |  |  |  | 2023-06-16 |  | 2023-06-19 | 2023-07-21 | CD//Jahganathan | 2023-06-20 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0008/0612Sabah-YPTT-BOQ Template (template) | DU00002007198 |  |  |  |  | 2023-09-15 |  | RAMO
Q00813 | Q140C_Q00813OD_JLNTEMPLE | Sarawak |  | Decomm |  | 2023Q2 | SH | Datasco | 4.6 TSSR Approved |  | 2023-04-13 | 2023-06-26 |  | 2023-06-19 |  | Rectificating | 2023-06-21 | 2023-08-24 | CD//John | 2023-06-21 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009/0612Sarawak-Datasco-BOQ Template (template) | DU00002007199 |  | 2023-07-16 Missing TX photos and info |  |  | 2023-10-16 | Monopole | LAMP_POLE
Q00258 | Q118B_Q00258OD_CB_RHCHABI | Sarawak | 9025X | Decomm |  | 2023Q3 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-04-28 | 2023-06-26 |  |  | 2023-07-20 |  | 2023-07-24 | 2023-09-23 | CD//John | 2023-07-28 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230613-0014/Celcom Digi_RAN-Magicell-TSS DECOMM-Sarawak-20230818 | DU00002007200 |  | 20230808: Decom RAN only |  |  | 2023-08-11 | Tower | TOWER | 61
B00566 | B058E_B00566OD_JENJAROM | Central |  | Decomm |  | 2023Q2 | SS | GTSB | 4.6 TSSR Approved |  | 2023-04-10 | 2023-06-26 |  |  | 2023-07-12 |  | 2023-07-12 | 2023-10-18 | CD//Sapian | 2023-07-20 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002007201 |  | CD Yusri-Since this site is Non-Colo, please check back scope Dismantle Celcom OB Fiber B00566. This site need to maintain fiber since have AGGB and DWDM equipment. Tq |  |  | 2023-07-19 | Tower | TOWER | 60m
Q00645 | Q126A_Q00645OD_SGSELAT | Sarawak |  | Decomm |  | 2023Q3 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-04-27 | 2023-06-26 |  |  | 2023-08-02 |  | 2023-08-04 | 2023-08-14 | CD//John | 2023-08-08 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230613-0014/Celcom Digi_RAN-Magicell-TSS DECOMM-Sarawak-20230818 | DU00002007202 |  |  |  |  | 2023-08-12 |  | TOWER | 60M
B02738 | B058D_B02738OD_BDRSULTANSULEIMANSCT | Central |  | Decomm |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-11 | 2023-04-15 |  |  | 2023-06-21 |  | 2023-06-21 | 2023-09-07 | CD//Norhaliza | 2023-08-03 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002007203 |  |  |  |  | 2023-06-22 | Minimast | MINI STRUCTURE | 11m
P00150 | P033B_P00150OD_INDERAWASIHIND | Northern |  | Decomm |  | 2023Q3 | MH | GCI | 4.6 TSSR Approved |  | 2023-06-02 |  |  |  | 2023-07-29 |  | 2023-06-19 | 2023-07-21 | CD//Shamsul | 2023-06-27 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1 | DU00002007204 |  |  |  |  | 2023-08-08 |  | MINI STRUCTURE
Q00224 | Q140C_Q00224OD_RHSAGRING | Sarawak |  | Decomm |  | 2023Q2 | SH | Datasco | 4.6 TSSR Approved |  | 2023-06-21 |  |  | 2023-06-22 |  | Closed | 2023-06-23 | 2023-11-22 | CD//John | 2023-06-25 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009/0612Sarawak-Datasco-BOQ Template (template) | DU00002007205 |  | 2023-07-18 Missing TX photos and info |  |  | 2023-12-07 |  | TOWER
Q00176 | Q140B_Q00176OD_CB_TGKUNYIT | Sarawak |  | Decomm |  | 2023Q2 | SH | CCSMY | 4.6 TSSR Approved |  | 2023-04-14 |  |  | 2023-06-15 |  | Closed | 2023-06-15 | 2023-08-14 | CD//John | 2023-06-16 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230613-0007 | DU00002007206 |  | 20230731 : Missing TX info |  |  | 2023-08-08 |  | TOWER
Q00512 | Q116A_Q00512OD_BELAGA | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2023Q3 | BY | AllStar | 4.6 TSSR Approved |  | 2023-05-04 | 2023-06-26 |  | 2023-07-10 |  | Under Approval | 2023-07-12 | 2023-08-18 | CD//John | 2023-07-13 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230613-0007 | DU00002007207 |  |  |  |  | 2025-08-05 | Tower | TOWER | 76m
S00024 | CBTMTAMPARULI | Sabah |  | Decomm |  | 2023Q2 | MS | Futong | 4.6 TSSR Approved |  | 2024-02-23 |  |  |  | 2024-02-23 |  | 2024-02-26 | 2024-03-21 | CD//Ray Amos | 2024-02-27 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009/0612Sabah-Futong-BOQ Template (template) | DU00002007208 |  |  |  |  | 2024-02-29 |  | TOWER
Q02126 | SUNGAI TUAH | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | N/A - no need PR for MOCN Decomm | DU00002007209 | [6 empty] | TOWER
B01475 | B058D_B01475OD_WESTPORTCT4 | Central |  | Decomm |  | 2023Q2 | SY1 | GCI | 4.6 TSSR Approved |  | 2024-10-04 |  | 2024-10-15 |  | 2024-10-14 |  | 2024-10-15 | 2025-03-24 | CD//Sapian | 2024-12-06 | 0924CD-Central-GCI-BOQ Template(new contract) | DU00002007210 | [6 empty] | TRIPOD
B00711 | B058D_B00711OD_BDRARMADAPUTRA | Central |  | Decomm |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-15 | 2023-06-26 |  |  | 2023-07-26 |  | 2023-07-07 | 2023-10-18 | CD//Ali akaram | 2023-08-16 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002007211 |  |  |  |  | 2023-09-24 | Monopole | SHARING STRC SBC | 30
S01165 | S093D_S01165OD_KIANSAMBARU | Sabah |  | Decomm |  | 2023Q3 | AD | Trintel | 4.6 TSSR Approved |  | 2023-06-28 |  |  |  | 2023-07-11 |  | 2023-07-12 | 2023-07-21 | CD//Jahganathan | 2023-07-13 | Celcom Digi_RAN-Trintel-TSS-Sabah-20230608-0003 | DU00002007212 |  |  |  |  | 2023-10-02 |  | LAMP_POLE
S00015 | S093G_S00015OD_KGMELAWA | Sabah |  | Decomm |  | 2023Q2 | MS | Datasco | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-26 |  |  | 2023-05-18 |  | 2023-06-19 | 2023-08-30 | CD//Mohidi Jaan | 2023-06-14 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006 | DU00002007213 |  |  |  |  | 2023-08-07 | Tower | TOWER | 45
Q01121 | Q144A_Q01121OD_CB_KUALAANAU | Sarawak | 9033K | Swap |  | 2023Q3 | MA | Magicell | 4.6 TSSR Approved |  | 2023-04-19 | 2023-04-27 |  | 2023-05-02 |  | Closed | 2023-05-05 | 2023-05-08 | CD//John | 2023-05-08 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230425-0003 | DU00002007214 |  |  | 2023-07-26 | 2023-07-07 |  | Tower | Land site | 65m | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
Q01115 | Q118B_Q01115OD_ULUSEGAN | Sarawak |  | Decomm |  | 2023Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2023-04-19 |  |  |  | 2023-08-24 |  | 2023-08-24 | 2024-02-15 | CD//John | 2023-08-28 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230613-0009/Celcom Digi_RAN-Trintel-TSS DECOMM-Sarawak-20231130 | DU00002007215 |  | 25/8: uncompleted info & photos Wrong proposal |  |  | 2023-12-13 |  | TOWER
Q00715 | Q140C_Q00715OD_TMNHARMONI | Sarawak |  | Decomm |  | 2023Q2 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-06-16 |  |  | 2023-06-28 |  | Under Approval | 2023-07-14 | 2023-09-19 | CD//John | 2023-07-15 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009 | DU00002007216 |  | 2023-07-17 Missing TX photos and info |  |  | 2023-08-03 |  | MONOPOLE
Q00207 | Q140C_Q00207OD_KINGWOOD | Sarawak |  | Decomm |  | 2023Q2 | SH | Datasco | 4.6 TSSR Approved |  | 2023-04-17 | 2023-06-26 |  | 2023-06-17 |  | Closed | 2023-06-19 | 2024-03-21 | CD//John | 2023-06-22 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009/Celcom Digi_RAN-Datasco-TSS DECOMM-Sarawak-20230818 | DU00002007217 |  | 20230802: all tx info & photos are missing |  |  | 2024-07-15 | Pole | BOOM
Q02161 | Q140B_Q02161OD_SIBUJAYA2 | Sarawak |  | Decomm |  | 2023Q2 | SH | Datasco | 4.6 TSSR Approved |  | 2023-08-19 |  |  |  | 2023-08-28 |  | 2023-08-28 | 2023-09-29 | CD//John | 2023-08-28 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009/0612Sarawak-Datasco-BOQ Template (template) | DU00002007218 |  |  |  |  | 2024-02-20 |  | RAPOLE
Q01627 | QS50242_9_0-RHBAYAN | Sarawak | 9010K | Swap |  | 2023Q3 | BY | Trintel | 4.6 TSSR Approved |  | 2023-04-12 | 2023-05-03 |  | 2023-05-12 |  | Closed | 2023-05-17 | 2023-05-17 | CD//John | 2023-05-17 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230403-0003 | DU00002007219 |  |  | 2023-11-11 | 2023-10-26 |  | Tower | TOWER | 30 | Add R9264M M1821 x3,Dismantle R8852E S1800(A8A) x3
S00052 | S109A_S00052_TENGILAN | Sabah |  | Decomm |  | 2023Q2 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-20 |  |  | 2023-06-22 |  | Closed | 2023-06-23 | 2023-07-27 | CD//Ray Amos | 2023-06-26 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009 | DU00002007220 |  |  |  |  | 2023-09-30 |  | MONOPOLE
S01019 | S093D_S01019OD_CB_KGBANTAYAN | Sabah |  | Decomm |  | 2023Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2023-04-20 | 2023-06-26 |  |  | 2023-06-23 |  | 2023-06-13 | 2023-07-21 | CD//Mohidi Jaan | 2023-06-13 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230608-0008/0612Sabah-GTSB-BOQ Template (template) | DU00002007221 |  |  |  |  | 2023-07-28 | Monople Tree | AESTHETIC MONOPOLE | 45
B01322 | B058E_B01322OD_MSJDSIJANGKANG | Central |  | Decomm |  | 2023Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2023-06-16 |  |  |  | 2023-06-19 |  | 2023-06-21 | 2024-01-22 | CD//Norhaliza | 2023-07-12 | CelcomDigi_RAN_AllStar_TSS_Central_20230626_decom reraise | DU00002007222 |  |  |  |  | 2023-06-28 |  | TRIPOD
Q00211 | Q140A_Q00211OD_JLNTEKU | Sarawak |  | Decomm |  | 2023Q2 | SH | Satellite | 4.6 TSSR Approved |  | 2023-04-17 |  |  | 2023-06-21 |  | Closed | 2023-06-22 | 2024-07-19 | CD//John | 2023-06-23 | Celcom Digi_RAN-Satellite-TSS-Sarawak-20231009 | DU00002007223 |  |  |  |  | 2024-02-21 |  | TOWER
Q01258 | Q140B_Q01258OD_PERMAITIMUR | Sarawak |  | Decomm |  | 2023Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-06-12 |  |  |  | 2023-07-15 |  | 2023-07-17 | 2023-08-08 | CD//John | 2023-08-08 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230613-0009/Celcom Digi_RAN-Trintel-TSS DECOMM-Sarawak-20231130 | DU00002007224 |  |  |  |  | 2023-09-08 |  | LAMP_POLE
P00235 | P033B_P00235OD | Northern | 4044K | Swap |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-31 | 2023-06-07 |  | 2023-06-09 |  | Closed | 2023-06-10 | 2023-06-21 | CD//Affendi | 2023-06-21 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0015 | DU00002007225 |  |  | 2023-07-15 | 2023-07-14 |  | Guide mast | MINI STRUCTURE | 46 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 2
B01834 | B058C_B01834OD_TMNBAYUPDANA | Central |  | Decomm |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-04-12 | 2023-06-26 |  |  | 2023-07-22 |  | 2023-07-25 | 2023-08-09 | CD//Sapian | 2023-08-06 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230626_decom reraise | DU00002007226 |  |  |  |  | 2023-07-11 | Pole | Rooftop | 6m
Q01154 | Q122A_Q01154OD_T3_NGTADA | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007227 | [6 empty] | TOWER
B02041 | B058D_B02041OD_MN_KGBARUTLKGONG | Central | 1005P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Syafiq |  |  | DU00002007228 | [6 empty] | TOWER
P00476 | P033C_P00476OD_PMTGTINGGI | Northern |  | Decomm |  | 2023Q3 | ZA | YPTT | 4.6 TSSR Approved |  | 2023-06-17 |  |  |  | 2023-08-07 |  | 2023-08-08 | 2023-11-23 | CD//Rohizam | 2023-08-15 | Celcom Digi_RAN-YPTT-TSS-Northern-20230609-0018 | DU00002007229 |  |  |  |  | 2023-10-06 |  | LAMP_POLE
Q00220 | Q140C_Q00220OD_JLNKGDATU | Sarawak | 9018K | Swap |  | 2023Q2 | HQ 2 | Trintel | 4.6 TSSR Approved |  | 2023-04-12 | 2023-05-03 |  | 2023-05-06 |  | Closed | 2023-05-09 | 2023-05-10 | CD//John | 2023-05-10 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230403-0003 | DU00002007230 |  |  | 2023-08-15 | 2023-07-24 |  | Unipole | MINI MONOPOLE | 9 | Add R8852E S9000 x3 + R8894E M1821 x3 + R8862A S2600 x3,Dismantle Celcom all RRU&BBU
Q00264 | QC10147_BTUAIRPORT | Sarawak |  | Decomm |  | 2023Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2023-04-17 |  |  | 2023-07-14 |  | Closed | 2023-07-24 | 2023-07-28 | CD//John | 2023-07-26 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230613-0009 | DU00002007231 |  |  |  |  | 2023-08-01 |  | LAMP_POLE
S00018 | S109A_S00018OD_KGROUN | Sabah |  | Decomm |  | 2023Q2 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-09 |  |  |  | 2023-06-22 |  | 2023-06-12 | 2023-07-21 | CD//Ray Amos | 2023-06-13 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009 | DU00002007232 |  |  |  |  | 2023-09-11 |  | TOWER
B00781 | B061D_B00781OD_SEK16SHLM | Central | 1030K | Swap |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI,L2600 change to 40M¦Maxis reject add AAU | 2023-06-02 | 2023-06-08 |  | 2023-06-12 |  | Closed | 2023-06-16 | 2023-07-06 | CD//Norhaliza | 2023-07-04 | Celcomdigi_RAN_Ascentrack_TSS_Central_20230606_0021 | DU00002007233 | NIC_S1_Change MM to BI,L2600 change to 40M_owner reject_MAXIS |  | 2023-09-24 | 2023-08-23 |  | Tower | TOWER | 46 | Add R9264M M1821 x1+R9264H M901821 x3+R8862A S2600 x4,Dismantle |  | 2
B00693 | B063A_B00693OD_BTLAUT | Central |  | Decomm |  | 2023Q2 | IE | Magicell | 4.6 TSSR Approved |  | 2023-06-13 |  |  |  | 2023-07-22 |  | 2023-07-22 | 2023-10-18 | CD//Ali akaram | 2023-08-01 | CelcomDigi_RAN_Magicell_TSS_Central_20230626_decom reraise | DU00002007234 |  |  |  |  | 2023-08-24 |  | TOWER
S01092 | S093A_S01092OD_RAPOLEPUTERAJAYA | Sabah | 7012K | Swap |  | 2023Q2 | MS | Datasco | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-10 |  | 2023-06-11 |  | Closed | 2023-06-12 | 2023-06-13 | CD//Mohidi Jaan | 2023-06-13 | Celcom Digi_RAN-Datasco- TSS-Sabah-20230407-0002 | DU00002007235 |  |  | 2023-06-30 | 2023-06-20 |  | Lampole | RAPOLE | 20m | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 3
S01074 | S109A_S01074OD_TELIPOKRIA | Sabah |  | Decomm |  | 2023Q2 | AD | Futong | 4.6 TSSR Approved |  | 2023-07-10 |  |  |  | 2023-08-01 |  | 2023-07-26 | 2023-08-23 | CD//Jahganathan | 2023-08-01 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009/0612Sabah-Futong-BOQ Template (template) | DU00002007236 |  | 20230807: cisco router missing |  |  | 2023-09-29 |  | WATERTANK
Q00713 | Q140C_Q00713OD_BUNGATERATAI | Sarawak |  | Decomm |  | 2023Q2 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-06-27 |  |  | 2023-06-29 |  | Closed | 2023-07-14 | 2023-09-29 | CD//John | 2023-07-15 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009 | DU00002007237 |  | 2023-07-17 Missing TX photos and info |  |  | 2023-08-04 |  | TOWER
S00438 | S093G_S00438OD_TMNBKTSEPANGGAR | Sabah |  | Decomm |  | 2023Q2 | MS | Datasco | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-26 |  |  | 2023-05-15 |  | 2023-07-28 | 2023-07-28 | CD//Ray Amos | 2023-07-25 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006 | DU00002007238 |  |  |  |  | 2023-10-10 | Guide mast | TOWER | 18
Q01929 | Q140A_Q01929OD_ULUSGMERAH2 | Sarawak |  | Decomm |  | 2023Q2 | SH | CCSMY | 4.6 TSSR Approved |  | 2023-04-14 |  |  | 2023-06-19 |  | Closed | 2023-06-21 | 2023-09-01 | CD//John | 2023-07-28 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230613-0007/Celcom Digi_RAN-CCSMY-TSS DECOMM-Sarawak-20230822 | DU00002007239 |  | 24/8: Uncompleted info + photos FE info & photos are missing |  |  | 2024-05-14 |  | RAPOLE
Q00690 | Q144A_Q00690OD_CB_KUALASANGAN | Sarawak | 9027K | Swap |  | 2023Q3 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-06-28 | 2023-07-03 |  | 2023-07-05 |  | Closed | 2023-07-07 | 2023-07-18 | CD//John | 2023-07-24 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230426-0003 | DU00002007240 |  | This site propose to decom and relocate to existing xD Site, 9595C | 2023-10-16 | 2023-10-05 |  | Tower | BOOM | 47m | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
Q00171 | QE10127_BLUECUBE_SIBU | Sarawak | 9003K | Swap |  | 2023Q2 | BY | Datasco | 4.6 TSSR Approved |  | 2023-04-28 | 2023-05-02 |  | 2023-05-15 |  | Closed | 2023-05-18 | 2023-05-19 | CD//John | 2023-05-18 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002007241 |  |  | 2023-09-14 | 2023-09-04 |  | Wall mount boom | BOOM |  | Add BS8932 x1,Dismantle Celcom small cell
B01265 | B058C_B01265IB_AEONBKTTINGGI | Central |  | Decomm |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-05-04 |  |  |  | 2023-08-10 |  | 2023-08-11 | 2023-09-07 | CD//Sofiah | 2023-08-29 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230626_decom reraise | DU00002007242 |  | Extra equipment |  |  | 2023-09-26 |  | SHARING STRC MAXIS
P00039 | P033B_P00039OD_CHAILENGPARK | Northern |  | Decomm |  | 2023Q3 | MH | GTSB | 4.6 TSSR Approved |  | 2023-05-10 |  |  |  | 2023-06-02 |  | 2023-06-07 | 2023-07-21 | CD//Shamsul | 2023-06-21 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1 | DU00002007243 |  |  |  |  | 2023-07-21 |  | BOOM
P00355 | P033B_P00355IB_SUNWAYCARNIVAL | Northern |  | Decomm |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-06-07 |  |  |  | 2023-10-21 |  | 2023-10-23 | 2024-01-22 | CD//Quah | 2023-07-06 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1 | DU00002007244 |  | TX info not complete 5/12: missing Digi Cabinet |  |  | 2023-10-13 |  | SHARING STRC MAXIS
P00079 | P033B_P00079OD_MEGAMALLOD | Northern |  | Decomm |  | 2023Q3 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-05-23 |  |  |  | 2023-07-03 |  | 2023-07-10 | 2024-03-13 | CD//Rohizam | 2023-11-21 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1 | DU00002007245 |  |  |  |  | 2023-10-13 |  | BOOM
Q00559 | Q140B_Q00559OD_JLNPERMAI | Sarawak |  | Decomm |  | 2023Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-04-18 |  |  | 2023-07-08 |  | Closed | 2023-07-12 | 2023-07-28 | CD//John | 2023-07-13 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230613-0009 | DU00002007246 |  |  |  |  | 2023-07-25 |  | TOWER
Q01473 | Q118B_Q01473OD_KEMENAIND3 | Sarawak |  | Decomm |  | 2023Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2023-04-19 |  |  | 2023-06-17 |  | Closed | 2023-06-19 | 2023-07-21 | CD//John | 2023-06-22 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230613-0009/Celcom Digi_RAN-Trintel-TSS DECOMM-Sarawak-20231130 | DU00002007247 |  |  |  |  | 2023-08-03 |  | RAPOLE
B00654 | B058B_B00654OD_RANTAUPJG | Central | 1029K | Swap |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-13 | 2023-05-19 |  | 2023-05-25 |  | Closed | 2023-05-26 | 2023-07-06 | CD//Sapian | 2023-07-04 | CelcomDigi_RAN_CCSMY_TSS_Central_20230508_0002 | DU00002007248 |  |  | 2023-08-08 | 2023-08-02 |  | Tower | TOWER | 70M | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 23
P00525 | P033B_P00525OD_KGTELUK | Northern |  | Site Out (Swap) | Swap->TBD->Swap->Site Out->Replacement, Site Out (Swap) | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved | ¦ 0227 - Site relocate to new location using same config, use TP provided by CD | 2023-05-12 | 2023-05-19 |  | 2023-05-25 |  | Under Approval | 2023-05-29 | 2023-06-12 | CD//Shamsul | 2023-06-12 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0016 | DU00002007249 | [5 empty] | Guide mast | LAMP_POLE | 15
S00707 | S093D_S00707OD_RAMOTMNNELLY | Sabah |  | Decomm |  | 2023Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2023-04-20 | 2023-06-26 |  |  | 2023-06-23 |  | 2023-06-13 | 2023-07-21 | CD//Ray Amos | 2023-06-14 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230608-0008 | DU00002007250 |  |  |  |  | 2023-10-10 | Guide mast | AESTHETIC MONOPOLE | 25
S00459 | S109A_S00459OD_KGKAPA | Sabah |  | Decomm |  | 2023Q2 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-21 |  |  |  | 2023-06-23 |  | 2023-06-24 | 2023-07-21 | CD//Ray Amos | 2023-06-26 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009/0612Sabah-Futong-BOQ Template (template) | DU00002007251 |  |  |  |  | 2023-07-20 |  | TOWER
S01497 | S093A_S01497OD_KKIPZONE2 | Sabah |  | Decomm |  | 2023Q2 | MS | Datasco | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-26 |  |  | 2023-06-06 |  | 2023-06-13 | 2023-08-30 | CD//Mohidi Jaan | 2023-06-13 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006/0612Sabah-Datasco-BOQ Template (template) | DU00002007252 |  |  |  |  | 2023-10-27 | Lampole | LAMP_POLE | 30
B01933 | B058B_B01933IB_GIANTKLGSENTRAL | Central | 1063K | Site Out (Swap) | Swap->Site out->Site Out (Swap) | 2023Q3 | SS | YPTT | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2025-07-16 |  | 2025-07-14 |  |  | To be Submitted |  |  |  |  | SQ202506140184 | DU00002007253 | [6 empty] | IN-BUILDING
Q01746 | Q140C_Q01746OD_LANANGIND2 | Sarawak | 9041K | Swap |  | 2023Q2 | HQ 2 | AllStar | 4.6 TSSR Approved |  | 2023-04-17 | 2023-05-02 |  | 2023-05-08 |  | Closed | 2023-05-15 | 2023-05-15 | CD//John | 2023-05-15 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230403-0003 | DU00002007254 |  |  | 2023-07-24 | 2023-07-10 |  | Monopole | RAPOLE | 30 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
S01113 | S093A_S01113OD_KGSINOMPUROUCA2 | Sabah |  | Decomm |  | 2023Q2 | MS | Datasco | 4.6 TSSR Approved |  | 2023-06-09 |  |  |  | 2023-06-07 |  | 2023-06-13 | 2023-09-11 | CD//Ray Amos | 2023-06-13 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006/0612Sabah-Datasco-BOQ Template (template) | DU00002007255 |  |  |  |  | 2023-10-10 |  | MONOPOLE
P00155 | P033B_P00155OD_PRAIINDAREA4 | Northern | 4043K | Swap |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-26 | 2023-05-29 |  | 2023-06-03 |  | Closed | 2023-06-07 | 2023-06-21 | CD//Affendi | 2023-06-21 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0016 | DU00002007256 |  |  | 2023-07-11 | 2023-07-05 |  | Tower | TOWER | 30 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
S01661 | S109A_S01661OD_KGBAWANG | Sabah |  | Decomm |  | 2023Q2 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-26 |  |  | 2023-06-10 |  | 2023-06-14 | 2024-07-05 | CD//Ray Amos | 2023-06-15 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009/0612Sabah-Futong-BOQ Template (template) | DU00002007257 |  | 2023-07-06 missing tx photos and info |  |  | 2023-10-09 | Tower | TOWER | 60
S00534 | S093G_S00534IB_DUNSABAH | Sabah | 7017K | Swap |  | 2023Q3 | MS | Datasco | 4.6 TSSR Approved |  | 2023-07-04 | 2023-07-07 |  | 2023-07-10 |  | Rectificating | 2023-07-11 | 2023-07-15 | CD//Mohidi Jaan | 2023-07-15 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230626 | DU00002007258 |  |  | 2023-07-28 | 2023-07-25 |  | Portables BTS | TRIPOD |  | Add R8862A S1800 x1 + R8862A S2100 x1,Dismantle all celcom BBU&RRU
B00557 | B058E_B00557OD_TLKPGARANG | Central |  | Decomm |  | 2023Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2023-04-14 | 2023-06-26 |  |  | 2024-01-23 |  | 2023-06-17 | 2024-02-23 | CD//Norhaliza | 2023-07-06 | CelcomDigi_RAN_AllStar_TSS_Central_20230626_decom reraise | DU00002007259 |  |  |  |  | 2023-07-13 | Tower | TOWER | 45
S00014 | S093G_S00014OD_KINGFISHER | Sabah |  | Decomm |  | 2023Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-04-21 | 2023-06-26 |  |  | 2023-06-30 |  | 2023-06-13 | 2023-07-27 | CD//Mohidi Jaan | 2023-06-13 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230608-0007 | DU00002007260 |  |  |  |  | 2023-09-19 | Pole | TRIPOD
Q00533 | Q140C_Q00533OD_JLNMANTIS | Sarawak |  | Decomm |  | 2023Q2 | BY | Datasco | 4.6 TSSR Approved |  | 2023-06-16 |  |  | 2023-06-16 |  | Closed | 2023-06-16 | 2023-08-30 | CD//John | 2023-06-16 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009 | DU00002007261 |  |  |  |  | 2023-07-25 |  | TOWER
Q00676 | Q118B_Q00676OD_CB_LDGSILAS | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007262 | [6 empty] | TOWER
P00394 | P033B_P00394OD_JLNTENGGIRI | Northern |  | Decomm |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-06-16 |  |  |  | 2023-07-07 |  | 2023-06-22 | 2023-07-21 | CD//Shamsul | 2023-07-03 | Celcom Digi_RAN-GCI-TSS-Northern-20230801-0037 | DU00002007263 |  |  |  |  | 2023-07-20 |  | LAMP_POLE
Q00196 | Q140C_Q00196OD_SPGDURIN | Sarawak |  | Decomm |  | 2023Q2 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-06-21 |  |  | 2023-06-24 |  | Closed | 2023-07-18 | 2024-01-18 | CD//John | 2023-07-19 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009 | DU00002007264 |  |  |  |  | 2024-04-19 |  | TOWER
S01134 | S093D_S01134OD_BORNEODEVCORP | Sabah |  | Decomm |  | 2023Q3 | AD | AllStar | 4.6 TSSR Approved |  | 2023-05-18 |  |  |  | 2023-05-22 |  | 2023-06-02 | 2023-07-27 | CD//Mohidi Jaan | 2023-06-02 | Celcom Digi_RAN-Allstar-TSS-Sabah-20230608-0004 | DU00002007265 |  |  |  |  | 2023-10-19 |  | TOWER
S00026 | S109A_S00026OD_CB_RASARIA | Sabah |  | Decomm |  | 2023Q2 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-09 |  |  | 2023-06-14 |  | Closed | 2023-06-16 | 2023-07-21 | CD//Ray Amos | 2023-06-17 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009 | DU00002007266 |  |  |  |  | 2023-10-03 |  | BOOM
S00040 | S093G_S00040OD_CB_KGBATANGANBARU | Sabah |  | Decomm |  | 2023Q2 | MS | Datasco | 4.6 TSSR Approved |  | 2023-04-17 | 2023-06-26 |  |  | 2023-06-01 |  | 2023-06-06 | 2023-10-13 | CD//Mohidi Jaan | 2023-06-09 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006 | DU00002007267 |  | 16/8 - TSSR Reject TX Picture not complete 2023-07-14 missing tx photos and info |  |  | 2023-09-15 | Tower | TOWER | 79
Q00613 | Q140B_Q00613OD_CB_RASCOM | Sarawak | 9026K | Swap |  | 2023Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-04-20 | 2023-05-09 |  | 2023-05-12 |  | Closed | 2023-05-16 | 2023-05-16 | CD//John | 2023-05-16 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230403-0003 | DU00002007268 |  |  | 2023-08-16 | 2023-07-27 |  | Tower | BOOM | 36m | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 2
B01141 | B058E_B01141OD_BT9SIJANGKANG | Central |  | Decomm |  | 2023Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2023-04-12 | 2023-06-26 |  | 2023-04-18 | 2023-06-14 | Under Approval | 2023-06-15 | 2024-01-30 | CD//Sapian | 2023-06-27 | CelcomDigi_RAN_AllStar_TSS_Central_20230626_decom reraise | DU00002007269 |  |  |  |  | 2023-06-26 | Tower | TOWER
Q00792 | Q144A_Q00792OD_CB_KUALATATAU | Sarawak | 9459P | Swap | Swap->Maintain USP MOCN->On Hold->Maintain USP MOCN->On Hold->Swap | 2023Q3 | BY | Magicell | 4.6 TSSR Approved |  | 2023-04-18 | 2023-05-12 |  | 2023-05-15 |  | Closed | 2023-05-24 | 2023-05-24 | CD//John | 2023-05-24 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230419-0002 | DU00002007270 |  |  | 2025-09-27 | 2025-09-25 |  | Tower | TOWER | 76M | Add R8852E S9000x3+R8894E M1821x6, Dismantle | 0 | 0
Q00179 | Q140C_Q00179OD_JLNEKDEE | Sarawak |  | Decomm |  | 2023Q2 | SH | Datasco | 4.6 TSSR Approved |  | 2023-04-17 | 2023-06-26 |  | 2023-06-19 |  | Closed | 2023-06-21 | 2023-09-19 | CD//John | 2023-06-21 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009 | DU00002007271 |  | 2023-07-16 Missing TX photos and info |  |  | 2024-01-08 | Pole | BOOM
Q01169 | Q140B_Q01169OD_CB_TGBEKAKAP | Sarawak | 9035K | Swap |  | 2023Q2 | MA | Datasco | 4.6 TSSR Approved |  | 2023-04-17 | 2023-05-03 |  | 2023-05-05 |  | Closed | 2023-05-09 | 2023-05-10 | CD//John | 2023-05-10 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002007272 |  |  | 2023-07-20 | 2023-07-13 |  | Tower | TOWER | 76m | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2600 x4,Dismantle Celcom all RRU&BBU |  | 2
B00630 | B058E_B00630OD_PULAUCAREY3 | Central | 1027K | Swap |  | 2023Q2 | YZ | Magicell | 4.6 TSSR Approved |  | 2023-04-13 | 2023-04-23 |  | 2023-04-26 |  | Closed | 2023-04-27 | 2023-06-03 | CD//Sapian | 2023-05-14 | CelcomDigi_RAN_Magicell_TSS_Central_20230417_0003 | DU00002007273 |  |  | 2023-07-15 | 2023-07-14 |  | Monople Tree | TOWER | 45 | Add R9264H M901821 x4 + R8862A S2600 x4,Dismantle Celcom all RRU&BBU
Q00216_IBC | Q140C_Q00216OD_WISMASANYAN | Sarawak |  | Decomm |  | 2023Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-10-19 |  |  |  | 2023-10-18 |  | 2023-10-19 | 2023-10-27 | CD//John | 2023-10-21 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231016/Celcom Digi_RAN-Trintel-TSS DECOMM-Sarawak-20231130 | DU00002007274 |  |  |  |  | 2024-03-14 |  | BOOM
B02576 | B058C_B02576OD_BATUNILAM_KLANG | Central |  | Decomm |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-04-17 | 2023-06-26 |  |  | 2023-07-17 |  | 2023-07-18 | 2023-09-07 | CD//Ali Akaram | 2023-08-27 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230626_decom reraise | DU00002007275 |  | NE: 1. IDU & label photo blurry. Please provide clear photo. Also please remove other equipment not related to TX at page 9. 2. Please provide close up antenna photo, ODU photo & ODU label photo FE: 1. IDU photo ok 2. Wrong antenna. IDU use SM IDU, antenna also should be SM antenna, not HUAWEI antenna. |  |  | 2023-08-14 | Pole | WALL MOUNTED BOOM | 4m
Q00234 | Q140C_Q00234OD_JLNMERDEKA | Sarawak | 9019K | Swap |  | 2023Q2 | SH | Datasco | 4.6 TSSR Approved |  | 2023-04-17 | 2023-04-20 |  | 2023-04-25 |  | Closed | 2023-05-10 | 2023-05-10 | CD//John | 2023-05-10 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002007276 |  |  | 2023-09-18 | 2023-08-28 |  | Pole | BOOM | 13 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
Q01597 | QS50224_4_1-BOMBATATAU | Sarawak | 9005K | Swap |  | 2023Q3 | SH | Magicell | 4.6 TSSR Approved |  | 2023-04-18 | 2023-05-04 |  | 2023-05-10 |  | Closed | 2023-05-11 | 2023-05-11 | CD//John | 2023-05-11 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230419-0002 | DU00002007277 |  |  | 2023-10-16 | 2023-10-13 |  | Tower | TOWER | 31M | Add R9264H M901821 x2 + R9264M M1821 x1,Dismantle R8862A S1800(B6A) x1
P00165 | P034A_P00165OD_JALANNEWFERRY | Northern |  | Decomm |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-06-02 |  |  |  | 2023-06-20 |  | 2023-06-20 | 2023-10-27 | CD//Shamsul | 2023-06-27 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1 | DU00002007278 |  |  |  |  | 2023-07-20 |  | BOOM
S00690 | S093D_S00690OD_KGLEMBAGAPADI | Sabah |  | Decomm |  | 2023Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2023-04-20 | 2023-06-26 |  |  | 2023-06-23 |  | 2023-06-13 | 2023-07-27 | CD//Ray Amos | 2023-06-14 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230608-0008 | DU00002007279 |  |  |  |  | 2023-10-09 | A-bracket pole | TRIPOD | 20m
B01087 | B058D_B01087OD_KOTAPENDAMAR | Central |  | Decomm |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-21 |  |  |  | 2023-07-24 |  | 2023-07-25 | 2023-10-18 | CD//Sapian | 2023-08-04 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002007280 |  |  |  |  | 2023-07-21 |  | LAMP_POLE
B02329 | B058D_B02329OD_PORTKLANG2 | Central | 1044K | Swap |  | 2023Q2 | AI | Ascentrack | 4.6 TSSR Approved |  | 2023-04-26 | 2023-04-29 |  | 2023-05-03 |  | Closed | 2023-05-04 | 2023-06-06 | CD//Sapian | 2023-05-19 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230428_0015 | DU00002007281 |  |  | 2023-06-23 | 2023-06-23 |  | Monopole | MONOPOLE | 30 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 2
Q00197 | Q138A_Q00197OD_CB_SEKUAU | Sarawak | 9285P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN->Swap | 2023Q2 | HW | Trintel | 4.6 TSSR Approved |  | 2025-03-17 | 2025-04-07 |  | 2025-04-16 |  | Under Approval | 2025-04-17 | 2025-05-19 | CD//John | 2025-05-09 | SQ202503240175-Trintel | DU00002007282 |  |  | 2025-06-14 | 2025-06-05 |  | Tower | TOWER | 76 | Add R8852E S9000x3+R8854E S1800x3+R8894E M1821x4, Dismantle | 0 | 3
P00079_IBC | P033B_P00079OD_MEGAMALLOD | Northern |  | Decomm |  | 2023Q3 | BY | GTSB | 4.6 TSSR Approved | ¦ 0129 - Pending TSSR submission, no RRU photo as already decomm | 2024-01-31 |  |  |  | 2024-02-07 |  | 2024-02-08 | 2024-04-23 | CD//Rohizam | 2024-02-09 | Celcom Digi_RAN-GTSB-TSS-Northern-20240202-0090 | DU00002007283 |  |  |  |  | 2024-08-02 |  | BOOM
Q01928 | Q118B_Q01928OD_SOPSEBAUH | Sarawak | 9050K | Swap |  | 2023Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2023-04-27 | 2023-05-11 |  | 2023-05-13 |  | Closed | 2023-05-19 | 2023-08-29 | CD//John | 2023-05-19 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230403-0003 | DU00002007284 |  |  | 2023-07-25 | 2023-07-06 |  | Tower | TOWER | 63m | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
Q01152 | Q122A_Q01152OD_T3_BAWANTGH | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007285 | [6 empty] | TOWER
P00159 | P034A_P00159OD_PUSPAKOMMANDIN | Northern |  | Decomm |  | 2023Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-05-09 |  |  |  | 2023-07-27 |  | 2023-06-06 | 2023-07-21 | CD//Shamsul | 2023-06-22 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1/Celcom Digi_CD CONSOLIDATION-GTSB-TI-Northern-20240920_Old Contract | DU00002007286 |  |  |  |  | 2023-09-11 |  | WATER TANK
Q00213 | Q140B_Q00213OD_RTMOYA | Sarawak |  | Decomm |  | 2023Q2 | ZB | CCSMY | 4.6 TSSR Approved |  | 2023-04-12 | 2023-06-26 |  | 2023-05-03 | 2023-07-05 | Rectificating | 2023-07-20 | 2024-09-13 | CD//John | 2023-07-20 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230613-0007 | DU00002007287 |  | 1/9: uncompleted photos & info |  |  | 2023-09-29 | Tower | TOWER | 45
Q00261 | Q144A_Q00261OD_TMBKTSETIAM | Sarawak |  | Decomm |  | 2023Q3 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-05-05 |  |  |  | 2023-08-23 |  | 2023-08-23 | 2023-08-30 | CD//John | 2023-08-23 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230613-0014/0612Sarawak-Magicell-BOQ Template (template) | DU00002007288 |  | 24/8: uncompleted info FE wrong idu photo |  |  | 2024-04-15 |  | TOWER
S01901 | S093D_S01901OD_EMOSBUKITBANTAYANRESIDENCE | Sabah | 7015K | Site Out (Swap) | Swap->MOCN Decomm->Decomm->Site Out->Site Out (Swap) | 2023Q3 | MS | Datasco | 4.6 TSSR Approved |  | 2023-05-25 | 2023-06-19 |  |  | 2023-12-19 |  | 2023-06-23 | 2023-11-17 | CD//Mohidi Jaan | 2023-12-20 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230626 | DU00002007289 | [5 empty] | Watertank | EMOS | 17m
Q00198 | Q138A_Q00198OD_CB_BKTSINGALANG | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007290 | [6 empty] | TOWER
Q00269 | Q142A_Q00269OD_RH_DINGON | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007291 | [6 empty] | TOWER
Q00177 | Q140C_Q00177OD_BKTLAN | Sarawak | 9014K | Swap |  | 2023Q2 | MA | Datasco | 4.6 TSSR Approved |  | 2023-04-16 | 2023-05-02 |  | 2023-05-04 |  | Rectificating | 2023-05-07 | 2023-05-08 | CD//John | 2023-05-08 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002007292 |  |  | 2023-07-18 | 2023-07-14 |  | Tower | GUYED MAST | 45 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
Q00209 | Q140C_Q00209OD_REJANGPARK | Sarawak |  | Decomm |  | 2023Q2 | SH | Datasco | 4.6 TSSR Approved |  | 2023-08-10 |  |  | 2023-08-10 |  | Closed | 2023-08-14 | 2023-08-24 | CD//John | 2023-08-15 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009 | DU00002007293 |  |  |  |  | 2023-09-26 |  | GUYED MAST
P00386 | P033C_P00386OD_IKSBKTMINYAK | Northern |  | Decomm |  | 2023Q3 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-07-21 |  |  |  | 2023-08-03 |  | 2023-07-28 | 2023-09-25 | CD//Shamsul | 2023-08-06 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1/Celcom Digi_RAN-CCSMY-TSS Decomm-Northern-20240131-0091 | DU00002007294 |  | 21/8: Please Celcom Cabinet and Zoom in photo TX |  |  | 2023-07-29 |  | TOWER
Q02123 | RANTAU DILANG | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | N/A - no need PR for MOCN Decomm | DU00002007295 | [6 empty] | TOWER
B02173 | B058E_B02173OD_MEGASTEELBTG | Central |  | Decomm |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-13 | 2023-06-26 |  |  | 2023-06-13 |  | 2023-06-13 | 2023-06-28 | CD//Sapian | 2023-06-27 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002007296 |  |  |  |  | 2023-07-26 | Monopole | Lampole | 33.5m
B00530 | B063A_B00530OD_TGSEPAT | Central |  | Decomm |  | 2023Q2 | MA | Magicell | 4.6 TSSR Approved |  | 2023-04-17 | 2023-06-26 |  | 2023-04-20 | 2023-07-17 | Rectificating | 2023-07-21 | 2024-01-30 | CD//Norhaliza | 2023-09-25 | CelcomDigi_RAN_Magicell_TSS_Central_20230626_decom reraise / CelcomDigi_TX_Magicell_TSS_Decom_Central_20230714 | DU00002007297 |  |  |  |  | 2023-08-29 | Tower | TOWER | 60
Q01151 | Q122A_Q01151OD_CB_ULUJIH | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007298 | [6 empty] | TOWER
Q01421 | Q140B_Q01421OD_RAMOJLNRANTAUPJGSBW | Sarawak | 9038K | Swap |  | 2023Q2 | BY | AllStar | 4.6 TSSR Approved |  | 2023-04-25 | 2023-04-26 |  | 2023-04-27 |  | Closed | 2023-05-01 | 2023-05-03 | CD//John | 2023-05-02 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230403-0003 | DU00002007299 |  |  | 2023-07-21 | 2023-07-10 |  | Guide mast | RAMO | 30 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
Q00527 | Q116A_Q00527OD_TMBKTTUNEONG | Sarawak | 9470P | Swap |  | 2023Q3 | SH | Datasco | 4.6 TSSR Approved |  | 2023-08-10 | 2023-08-16 |  | 2023-08-17 |  | Closed | 2023-08-17 | 2023-08-18 | CD//John | 2023-08-17 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230913 | DU00002007300 |  |  | 2023-10-17 | 2023-09-20 |  |  | TOWER | 93 | Add R9264H M901821 x3 + R9264M M1821 x3,Dismantle Celcom all RRU&BBU |  | 123
P00125 | P033C_P00125OD_JURU2 | Northern |  | Decomm |  | 2023Q3 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-07-25 |  |  |  | 2023-07-25 |  | 2023-07-25 | 2023-11-23 | CD//Affendi | 2023-07-26 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V1 | DU00002007301 |  | 1)Please include Zoom in photo IDU with Label ID |  |  | 2023-07-25 |  | TOWER
S01088 | S093G_S01088OD_KKIPMILL | Sabah | 7011K | Swap |  | 2023Q2 | MS | Datasco | 4.6 TSSR Approved |  | 2023-05-26 | 2023-05-25 |  | 2023-06-03 |  | Closed | 2023-06-06 | 2023-06-13 | CD//Mohidi Jaan | 2023-06-13 | Celcom Digi_RAN-Datasco- TSS-Sabah-20230407-0002 | DU00002007302 |  |  | 2023-06-28 | 2023-06-20 |  | Pole | TRIPOD |  | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
B01441 | B058E_B01441OD_BT14JENJAROM | Central |  | Decomm |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-03 | 2023-04-05 |  |  | 2023-07-21 |  | 2023-07-21 | 2023-09-01 | CD//Ali akaram | 2023-08-01 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002007303 |  |  |  |  | 2023-07-19 | Tower | TOWER | 60m
B02543 | B058D_B02543OD_JLNPLBHUTARA | Central |  | Decomm |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-14 | 2023-06-26 |  |  | 2023-06-13 |  | 2023-06-13 | 2023-11-15 | CD//Sapian | 2023-06-27 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002007304 |  |  |  |  | 2023-07-12 | Pole | BOOM | 6
B02916 | B058E_B02916OD_PEDI_LABOHAN_DAGANG | Central | 1060K | Swap |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-07 | 2023-04-10 |  | 2023-04-13 |  | Closed | 2023-05-06 | 2023-06-27 | CD//Norhaliza | 2023-06-26 | CelcomDigi_RAN_GTSB_Central_20230407_0012 / CelcomDigi_RAN_GTSB_TSS_Central_20230721_ClearLoan | DU00002007305 |  |  | 2023-06-08 | 2023-06-04 |  |  | POTS |  | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
S00577 | S093D_S00577OD_KGSUKANG | Sabah |  | Decomm |  | 2023Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2023-04-20 | 2023-06-26 |  |  | 2023-06-23 |  | 2023-06-13 | 2023-07-21 | CD//Mohidi Jaan | 2023-06-13 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230608-0008 | DU00002007306 |  |  |  |  | 2023-09-18 |  | TOWER | 40
P00532 | P033B_P00532OD_SOUTHERNSTEEL | Northern | 4054K | Swap |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-15 | 2023-05-17 |  | 2023-05-22 |  | Closed | 2023-05-25 | 2023-06-12 | CD//Shamsul | 2023-06-12 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0015 | DU00002007307 |  |  | 2023-07-12 | 2023-07-12 |  | Wall mount boom | Land site | 4m | Add R8852E S9000 x3 + R8894E M1821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
Q01527 | Q140C_Q01527OD_JLNTEKAMSBW | Sarawak |  | Decomm |  | 2023Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-04-25 | 2023-06-26 |  |  | 2023-07-29 |  | 2023-07-31 | 2023-08-18 | CD//John | 2023-08-01 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230613-0009/Celcom Digi_RAN-Trintel-TSS DECOMM-Sarawak-20231130 | DU00002007308 |  |  |  |  | 2023-12-18 | Monopole | BOOM | 30
S00407 | S093G_S00407OD_FEDERALGOVBUILDING | Sabah |  | Decomm |  | 2023Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-04-21 | 2023-06-26 |  |  | 2023-06-07 |  | 2023-06-13 | 2023-10-13 | CD//Mohidi Jaan | 2023-08-03 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230612-0008/0612Sabah-YPTT-BOQ Template (template) | DU00002007309 |  | 2/8: all tx info missing (NE & FE ) |  |  | 2023-11-07 |  | BOOM | 45
Q01483 | Q144A_Q01483OD_ZEDTEETATAU | Sarawak |  | Decomm |  | 2023Q3 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-08-19 |  |  |  | 2023-08-21 |  | 2023-08-22 | 2023-08-30 | CD//John | 2023-08-28 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230613-0014/0612Sarawak-Magicell-BOQ Template (template) | DU00002007310 |  |  |  |  | 2023-09-09 |  | RAMO
S01151 | S093D_S01151OD_KIANSAM3GDEN | Sabah |  | Decomm |  | 2023Q3 | AD | Trintel | 4.6 TSSR Approved |  | 2023-06-27 |  |  |  | 2023-07-11 |  | 2023-07-12 | 2023-07-21 | CD//Mohidi Jaan | 2023-07-13 | Celcom Digi_RAN-Trintel-TSS-Sabah-20230608-0003 | DU00002007311 |  |  |  |  | 2023-07-28 |  | MONOPOLE
S00039 | S109A_S00039OD_TUARANTOWN | Sabah |  | Decomm |  | 2023Q2 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-26 |  |  | 2023-06-22 |  | 2023-06-14 | 2023-07-21 | CD//Ray Amos | 2023-06-16 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009 | DU00002007312 |  |  |  |  | 2023-09-04 | Pole | BOOM
S00965 | S093G_S00965OD_UITMADMINHILL | Sabah | 7009K | Swap |  | 2023Q2 | MS | Datasco | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-28 |  | 2023-05-10 |  | Closed | 2023-05-13 | 2023-05-16 | CD//Ray Amos | 2023-05-16 | Celcom Digi_RAN-Datasco- TSS-Sabah-20230407-0002 | DU00002007313 |  |  | 2023-06-28 | 2023-06-21 |  | Monopole | LAMP_POLE | 30 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
S01557 | S109A_S01557OD_CB_KGTOPOKON | Sabah |  | Decomm |  | 2023Q2 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-26 |  |  | 2023-06-22 |  | 2023-06-15 | 2023-07-21 | CD//Ray Amos | 2023-06-16 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009/0612Sabah-Futong-BOQ Template (template) | DU00002007314 |  |  |  |  | 2023-09-29 | Tower | TOWER | 75
S00664 | S109A_S00664OD_SYAHBANDARHO | Sabah |  | Decomm |  | 2023Q2 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-02 | 2023-06-26 |  |  | 2023-06-22 |  | 2023-06-15 | 2023-07-21 | CD//Ray Amos | 2023-06-16 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009 | DU00002007315 |  |  |  |  | 2023-11-07 | Tower | TOWER | 61
B01185 | B058B_B01185OD_BDRBARUKLG | Central | 1009K | Decomm |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-05-08 |  |  |  | 2023-07-24 |  | 2023-07-24 | 2023-12-20 | CD//Norhaliza | 2023-10-09 | 0626Central-Datasco-BOQ Template (template) | DU00002007316 |  |  |  |  | 2023-10-10 |  | BOOM
Q01167 | Q140A_Q01167OD_T3_JLNTEKUPASAI | Sarawak | 9228P | Swap | Swap->Maintain USP MOCN->On Hold->Swap | 2023Q2 | SH | CCSMY | 4.6 TSSR Approved |  | 2023-04-17 | 2023-05-13 |  | 2023-05-19 |  | Closed | 2023-05-26 | 2023-05-27 | CD//John | 2025-04-07 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230403-0003 | DU00002007318 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed | 2025-04-23 | 2025-04-10 |  | Tower | TOWER | 78 | Add R8852E S9000x3+R8854E S1800x3+R8894E M1821x4, Dismantle | 0 | 1
B02911 | B058E_B02911OD_SDPAPULAUCAREY | Central | 1059K | Swap |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-14 | 2023-04-20 |  | 2023-04-27 |  | Closed | 2023-04-28 | 2023-06-03 | CD//Syafiq | 2023-05-05 | CelcomDigi_RAN_Datasco_TSS_Central_20230417_0012 | DU00002007319 |  |  | 2023-09-12 | 2023-09-07 |  | Lampole | LAMP_POLE | 30 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
B01349 | B058B_B01349OD_JLNRAJANONG | Central | 1033K | Site Out (Swap) | Swap->MOCN Decomm->Site Out->Replacement, Site Out (Swap) | 2023Q3 |  | YPTT | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2025-07-16 |  | 2025-07-14 |  |  | To be Submitted |  |  |  |  | SQ202506140184 | DU00002007320 | [6 empty] | TRIPOD
S00002 | S093A_S00002OD_LAWAMANDAU | Sabah | 7001K | Swap |  | 2023Q2 | MS | Datasco | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-19 |  | 2023-06-03 |  | Closed | 2023-06-13 | 2023-06-13 | CD//Mohidi Jaan | 2023-06-13 | Celcom Digi_RAN-Datasco- TSS-Sabah-20230407-0002 | DU00002007321 |  |  | 2023-07-07 | 2023-07-06 |  | Tower | TOWER | 76 | Add R8852E S9000 x2 + R8894E M1821 x2,Dismantle Celcom all RRU&BBU | 0
S00687 | S093G_S00687OD_RAMOINTANKK | Sabah | 7005K | Swap |  | 2023Q2 | MS | Datasco | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-02 |  | 2023-07-05 |  | Closed | 2023-06-13 | 2023-08-30 | CD//Ray Amos | 2023-08-25 | Celcom Digi_RAN-Datasco- TSS-Sabah-20230407-0002 | DU00002007322 |  |  | 2023-06-27 | 2023-06-26 |  | Lampole | GUYED MAST | 30m | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
B02270 | B058E_B02270OD_TLKDATOKBANTING | Central |  | Decomm |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-11 | 2023-06-26 |  |  | 2023-07-25 |  | 2023-07-25 | 2023-08-08 | CD//Sapian | 2023-08-04 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002007323 |  |  |  |  | 2023-07-20 | Tower | TOWER | 60m
B01677 | B063C_B01677OD_PR_KM2KLIA | Central | 1034K | Swap |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-14 | 2023-04-15 |  | 2023-04-17 |  | Closed | 2023-04-18 | 2023-06-06 | CD//Sapian | 2023-05-12 | CelcomDigi_RAN_GTSB_TSS_Central_20230417_0017 | DU00002007324 |  |  | 2023-06-27 | 2023-06-04 |  | BillBoard | BILLBOARD | 23m | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
Q00542 | Q140A_Q00542OD_JLNPASAISIONG | Sarawak | 9024K | Swap |  | 2023Q2 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-04-18 | 2023-05-10 |  | 2023-05-14 |  | Closed | 2023-05-27 | 2023-06-29 | CD//John | 2023-06-02 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230403-0003 | DU00002007325 |  |  | 2023-11-11 | 2023-09-07 |  | Guide mast | GUYED MAST | 55 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
S00003 | S093D_S00003OD_EVERIGHT | Sabah |  | Decomm |  | 2023Q3 | AD | AllStar | 4.6 TSSR Approved |  | 2023-05-18 |  |  |  | 2023-05-22 |  | 2023-06-09 | 2023-07-21 | CD//Mohidi Jaan | 2023-06-10 | Celcom Digi_RAN-Allstar-TSS-Sabah-20230608-0004 | DU00002007326 |  |  |  |  | 2023-10-09 |  | BOOM
Q01837 | Q118B_Q01837OD_LDGBUMIALMA | Sarawak | 9045K | Swap |  | 2023Q3 | SH | Datasco | 4.6 TSSR Approved |  | 2023-05-30 | 2023-05-30 |  | 2023-06-07 |  | Closed | 2023-06-09 | 2023-06-10 | CD//John | 2023-06-10 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002007327 |  |  | 2023-08-08 | 2023-07-10 |  | Tower | TOWER | 45 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
P00002 | P033C_P00002OD_JURU | Northern |  | Decomm |  | 2023Q3 | MH | YPTT | 4.6 TSSR Approved |  | 2023-05-16 |  |  |  | 2023-06-15 |  | 2023-06-16 | 2023-08-08 | CD//Quah | 2023-07-06 | Celcom Digi_RAN-YPTT-TSS-Northern-20230609-0018/Celcom Digi_RAN-YPTT-TSS Decomm-Northern-20240311-0048 | DU00002007328 |  |  |  |  | 2023-09-14 |  | TOWER
B02232 | B058D_B02232OD_PKFZPORTKLG | Central |  | Decomm |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-07-26 |  |  |  | 2023-07-27 |  | 2023-07-27 | 2023-12-21 | CD//Sapian | 2023-08-15 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002007329 | [6 empty] | MONOPOLE
B00529 | B059A_B00529OD_BANTING | Central |  | Decomm |  | 2023Q2 | SS | GTSB | 4.6 TSSR Approved |  | 2023-04-04 |  |  |  | 2023-08-03 |  | 2023-08-03 | 2023-11-20 | CD//Norhaliza | 2023-09-25 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002007330 |  |  |  |  | 2023-12-27 | Minimast | MINI STRUCTURE | 8m
Q01599 | Q140C_Q01599OD_KGNGBELALANG | Sarawak | 9006K | Swap |  | 2023Q2 | SH | AllStar | 4.6 TSSR Approved |  | 2023-04-18 | 2023-05-02 |  | 2023-05-11 |  | Closed | 2023-05-12 | 2023-05-15 | CD//John | 2023-05-13 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230403-0003 | DU00002007331 |  |  | 2024-02-06 | 2023-12-20 |  | Tower | TOWER | 30M | Add R9264H M901821 x2 + R9264M M1821 x1,Dismantle Celcom all BBU
S00463 | S109A_S00463OD_CB_KGBERUNGIS | Sabah |  | Decomm |  | 2023Q2 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-19 |  |  |  | 2023-06-20 |  | 2023-06-21 | 2023-07-21 | CD//Ray Amos | 2023-06-23 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0009 | DU00002007332 |  |  |  |  | 2023-07-24 |  | TOWER
S01155 | S093A_S01155OD_TMNFLAMINGO | Sabah |  | Decomm |  | 2023Q2 | MS | Datasco | 4.6 TSSR Approved |  | 2023-05-18 |  |  |  | 2023-05-19 |  | 2023-06-14 | 2023-08-06 | CD//Ray Amos | 2023-07-14 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006 | DU00002007333 |  | 20230728: TX photos & info missing |  |  | 2023-10-09 |  | LAMP_POLE
S00033 | S093D_S00033OD_KIANSOM | Sabah |  | Decomm |  | 2023Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2023-04-20 | 2023-06-26 |  |  | 2023-06-23 |  | 2023-06-13 | 2023-07-27 | CD//Mohidi Jaan | 2023-06-13 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230608-0008 | DU00002007334 |  |  |  |  | 2023-09-18 | Tower | TOWER | 60M
B02422 | B058E_B02422OD_KM24SKVE | Central |  | Decomm |  | 2023Q2 | SS | GTSB | 4.6 TSSR Approved |  | 2023-04-17 | 2023-06-26 |  |  | 2023-06-09 |  | 2023-06-15 | 2023-12-20 | CD//Ali Akaram | 2023-11-22 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002007335 |  |  |  |  | 2023-06-21 | Monople Tree | AESTHETIC MONOPOLE | 45m
P00169 | P033C_P00169OD_ASASJAYA | Northern |  | Decomm |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-06-09 |  |  |  | 2023-06-26 |  | 2023-07-12 | 2023-08-19 | CD//Shamsul | 2023-07-12 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1 | DU00002007336 |  | No TX Info, Photo not enough |  |  | 2023-08-09 |  | MINI STRUCTURE
B02542 | B058D_B02542OD_JLNPANDAMARANJAYA | Central |  | Decomm |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-05-03 |  |  |  | 2023-07-26 |  | 2023-07-27 | 2023-09-19 | CD//Norhaliza | 2023-09-15 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230626_decom reraise | DU00002007337 |  |  |  |  | 2023-07-09 |  | UNIPOLE
B00708 | B058E_B00708OD_KGSRICHEEDING | Central |  | Decomm |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-07 | 2023-06-26 |  |  | 2023-08-02 |  | 2023-07-28 | 2023-09-01 | CD//Ali Akaram | 2023-08-27 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002007338 |  |  |  |  | 2023-06-19 | Tower | TOWER | 50
Q01590 | QS50235_4_1-SPGSKULUSEGAN | Sarawak | 9004K | Swap |  | 2023Q3 | SH | Datasco | 4.6 TSSR Approved |  | 2023-04-17 | 2023-05-04 |  | 2023-05-12 |  | Closed | 2023-05-18 | 2023-05-18 | CD//John | 2023-05-18 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002007339 |  |  | 2024-03-17 | 2023-10-10 |  |  | TOWER | 30 | Add R9264H M901821 x2 + R9264M M1821 x1,Dismantle R8862A S1800(B6A) x1+R8862A S1800(B6A) x1
P00451 | P033B_P00451OD_PRAIINDAREA2 | Northern | 4049K | Swap |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-17 | 2023-06-01 |  | 2023-06-06 |  | Closed | 2023-06-12 | 2023-06-21 | CD//Affendi | 2023-06-21 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0016 | DU00002007340 |  |  | 2023-07-11 | 2023-07-10 |  | Monopole | BOOM | 30 | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 1
Q00218 | Q140C_Q00218OD_PBSMSBW | Sarawak |  | Decomm |  | 2023Q2 | SH | Datasco | 4.6 TSSR Approved |  | 2023-04-14 | 2023-06-26 |  | 2023-06-17 |  | Closed | 2023-06-21 | 2023-09-23 | CD//John | 2023-06-25 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009 | DU00002007341 |  | 20230731 : TX info and photos not completed |  |  | 2023-10-03 | Pole | BOOM
Q01422 | Q116A_Q01422OD_MN_UMALAHANAN | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007342 | [6 empty] | TOWER
Q00832 | Q118A_Q00832OD_JLNDAGANGBTU | Sarawak |  | Decomm |  | 2023Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2023-04-17 | 2023-06-26 |  | 2023-06-12 |  | Closed | 2023-06-13 | 2023-09-08 | CD//John | 2023-06-16 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230613-0009 | DU00002007343 |  | 2023-06-26 Missing TX photos and info |  |  | 2023-09-05 | Monopole | LAMP_POLE | 36
S01119 | S093G_S01119OD_SEPANGGAR | Sabah |  | Decomm |  | 2023Q2 | MS | Datasco | 4.6 TSSR Approved |  | 2023-04-19 | 2023-06-26 |  |  | 2023-05-12 |  | 2023-06-20 | 2024-03-21 | CD//Ray Amos | 2023-06-23 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006/0612Sabah-Datasco-BOQ Template (template) | DU00002007344 |  | 2023-07-06 missing tx photos and info |  |  | 2023-11-10 | Monopole | LAMP_POLE
S00001 | S093D_S00001OD_INANAMMTX | Sabah |  | Decomm |  | 2023Q3 | AD | Magicell | 4.6 TSSR Approved |  | 2023-05-05 |  |  |  | 2023-08-15 |  | 2023-06-19 | 2024-06-28 | CD//Mohidi Jaan | 2023-06-18 | Celcom Digi_RAN-Magicell-TSS-Sabah-20230608-0003 | DU00002007345 |  | 2023-07-20 missing tx photos and info |  |  | 2023-10-20 |  | TOWER
S00696 | S093D_S00696OD_KOLOMBONGSHOPLOT | Sabah |  | Decomm |  | 2023Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2023-05-02 | 2023-06-26 |  |  | 2023-05-19 |  | 2023-06-15 | 2023-07-27 | CD//Ray Amos | 2023-06-16 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230608-0008 | DU00002007346 |  |  |  |  | 2023-10-19 | Minimast | TRIPOD | 19m
S00954 | S093G_S00954OD_UMSKGE | Sabah |  | Decomm |  | 2023Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-04-21 | 2023-06-26 |  |  | 2023-06-12 |  | 2023-06-19 | 2023-07-27 | CD//Mohidi Jaan | 2023-06-19 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230608-0007 | DU00002007347 |  |  |  |  | 2023-08-15 | Lampole | BOOM | 25
S00034 | S093G_S00034OD_SALUT | Sabah |  | Decomm |  | 2023Q2 | MS | Datasco | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-26 |  |  | 2023-05-12 |  | 2023-06-21 | 2023-08-23 | CD//Mohidi Jaan | 2023-06-22 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006 | DU00002007348 |  | 20230716: missing tx photos and info |  |  | 2023-09-21 | Tower | TOWER | 46
B01987 | B058E_B01987OD_OLAKLEMPITIP | Central |  | Decomm |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-18 | 2023-06-26 |  |  | 2024-05-08 |  | 2023-06-17 | 2024-07-16 | CD//Sapian | 2023-06-28 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise / CelcomDigi_TX_GTSB_TSS_Decom_Central_20230714 | DU00002007349 |  |  |  |  | 2023-11-15 | Tower | TOWER | 45m
S00028 | S093D_S00028OD_TMINANAM | Sabah |  | Decomm |  | 2023Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2023-05-15 |  |  |  | 2023-06-02 |  | 2023-07-24 | 2023-07-27 | CD//Jahganathan | 2023-07-24 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230608-0008 | DU00002007350 |  |  |  |  | 2024-02-23 |  | MONOPOLE
B01438 | B058E_B01438OD_RTBBKTCHANGGANG | Central |  | Decomm |  | 2023Q2 | MA | GTSB | 4.6 TSSR Approved |  | 2023-04-09 |  |  | 2023-04-13 | 2023-08-02 | Closed | 2023-07-14 | 2023-08-04 | CD//Norhaliza | 2023-08-03 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002007351 |  |  |  |  | 2023-11-22 | Tower | TOWER | 40
B02481 | B058E_B02481OD_BDRSAUJANAPUTRAJENJAROM | Central |  | Decomm |  | 2023Q2 | SS | GTSB | 4.6 TSSR Approved |  | 2023-04-04 | 2023-06-26 |  |  | 2024-05-08 |  | 2023-06-15 | 2025-03-24 | CD//Sapian | 2023-07-03 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002007352 |  |  |  |  | 2023-06-22 | Guide mast | RAMO | 20
S00873 | S093A_S00873OD_PSSBDRPUTERA | Sabah |  | Decomm |  | 2023Q2 | MS | Futong | 4.6 TSSR Approved |  | 2023-06-09 |  |  |  | 2023-09-09 |  | 2023-09-11 | 2023-09-29 | CD//Mohidi Jaan | 2023-09-12 | Celcom Digi_RAN-Futong-TSS-Sabah-20230913 | DU00002007353 |  |  |  |  | 2024-07-10 |  | PSS PYLON
Q00181 | Q140C_Q00181ODA_CENTERPOINT | Sarawak | 9015K | Swap |  | 2023Q2 | MA | Datasco | 4.6 TSSR Approved |  | 2023-04-16 | 2023-05-02 |  | 2023-05-03 |  | Closed | 2023-05-06 | 2024-11-22 | CD//John | 2023-05-08 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002007354 |  |  | 2023-09-25 | 2023-07-26 |  |  | BOOM | 33 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2600 x3,Dismantle Celcom all RRU&BBU | 13
X00050 | MBTSMBRESIDENCE_4G | Northern | 4057K | Swap |  | 2023Q2 | WP | GCI | 4.6 TSSR Approved |  | 2023-05-09 | 2023-06-21 |  | 2023-06-21 |  | Closed | 2023-06-28 | 2023-07-05 | CD//Shamsul | 2023-07-05 | Celcom Digi_RAN-GCI-TSS-Northern-20230425-0009 | DU00002007355 |  |  | 2023-06-14 | 2023-06-13 |  | Monopole | MBTS | 25M | Add R9264M M1821 x3,Dismantle Celcom all RRU&BBU
B00473 | B059A_B00473OD_SGLANG | Central |  | Decomm |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-03 |  |  |  | 2023-08-03 |  | 2023-08-09 | 2023-10-18 | CD//Sapian | 2023-07-03 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002007356 |  |  |  |  | 2023-07-21 | Tower | TOWER | 46m
Q01516 | Q140A_Q01516OD_UCTSSBW | Sarawak |  | Decomm |  | 2023Q2 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-06-27 |  |  | 2023-06-30 |  | Closed | 2023-07-12 | 2024-06-26 | CD//John | 2023-07-13 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009/0612Sarawak-Datasco-BOQ Template (template) | DU00002007357 |  | 2023-07-18 Missing TX photos and info |  |  | 2024-02-14 |  | RAMO
Q01884 | Q118B_Q01884OD_SAMARAKANNURSERY | Sarawak | 9048K | Swap |  | 2023Q3 | HQ 1 | Magicell | 4.6 TSSR Approved |  | 2023-04-27 | 2023-05-09 |  | 2023-05-11 |  | Closed | 2023-05-15 | 2023-05-16 | CD//John | 2023-05-16 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230502-0004 | DU00002007358 |  |  | 2023-07-29 | 2023-07-06 |  | Tower | TOWER | 65m | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
Q02133 | Kg Hulu Nanga | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | N/A - no need PR for MOCN Decomm | DU00002007359 | [6 empty] | TOWER
Q01543 | Q142A_Q01543OD_MN_RHJARAU | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007360 | [6 empty] | TOWER
B02266 | B058A_B02266OD_LORONGABDMANANMERU | Central | 1042K | Swap |  | 2023Q3 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-05-15 | 2023-05-22 |  | 2023-05-26 |  | Closed | 2023-06-02 | 2023-08-24 | E//Razif | 2023-08-24 | CelcomDigi_RANMW_CCSMY_TSS_Central_20230508_0001 | DU00002007361 |  |  | 2023-08-13 | 2023-08-04 |  | Monopole | TOWER | 30M | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x5,Dismantle Celcom all RRU&BBU |  | 12
S00010 | S093A_S00010OD_MENGGATALTOWN | Sabah |  | Decomm |  | 2023Q2 | MS | Datasco | 4.6 TSSR Approved |  | 2023-04-20 | 2023-06-26 |  |  | 2023-05-12 |  | 2023-06-23 | 2023-07-27 | CD//Ray Amos | 2023-06-26 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006 | DU00002007362 |  |  |  |  | 2023-10-13 | Wall mount boom | BOOM | 30
Q01512 | Q132B_Q01512OD_CB_TMNTEKUSBW | Sarawak |  | Decomm |  | 2023Q2 | SH | CCSMY | 4.6 TSSR Approved |  | 2023-04-13 |  |  | 2023-06-21 |  | Closed | 2023-07-21 | 2023-08-30 | CD//John | 2023-07-23 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230613-0007/Celcom Digi_RAN-CCSMY-TSS DECOMM-Sarawak-20230822 | DU00002007363 |  | 23/8: uncompleted photos & info NE & FE |  |  | 2024-02-16 |  | RAMO
Q00598 | Q118A_Q00598IB_KEMENAPLAZAID | Sarawak | 9052K | Swap |  | 2023Q3 | BY | Trintel | 4.6 TSSR Approved |  | 2023-04-26 | 2023-05-10 |  | 2023-05-15 |  | Closed | 2023-05-19 | 2023-08-24 | CD//John | 2023-05-19 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230403-0003 | DU00002007364 |  | 0408 Required resurvey due to missing RRU | 2024-01-15 | 2023-11-25 |  |  | BOOM |  | Add R8862A S1800 x1 + R8862A S2100 x1,Dismantle all celcom BBU&RRU
B02313 | B058E_B02313OD_MEGASTEELFACTBANTING | Central | 1043K | Swap |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-28 | 2023-05-03 |  | 2023-05-04 |  | Closed | 2023-05-05 | 2023-06-06 | CD//Sapian | 2023-05-30 | CelcomDigi_RAN_GTSB_TSS_Central_20230428_0022 | DU00002007365 |  |  | 2023-06-08 | 2023-06-08 |  | Monopole | RAPOLE | 30 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
Q01858 | Q140B_Q01858OD_JLNWAWASAN | Sarawak | 9046K | Swap |  | 2023Q2 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-04-17 | 2023-05-08 |  | 2023-05-10 |  | Closed | 2023-05-11 | 2023-05-11 | CD//John | 2023-05-11 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230403-0003 | DU00002007366 |  |  | 2023-07-19 | 2023-07-12 |  | Tower | TOWER | 48 | Add R9264H M901821 x3 + R8862A S2600 x3,Dismantle Celcom all RRU&BBU
Q01114 | Q118B_Q01114OD_SGSEMANOK | Sarawak | 9030K | Swap |  | 2023Q3 | BY | Magicell | 4.6 TSSR Approved |  | 2023-06-19 | 2023-06-21 |  | 2023-06-23 |  | Rectificating | 2023-06-26 | 2023-06-27 | CD//John | 2023-06-27 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230426-0003 | DU00002007367 |  |  | 2023-07-25 | 2023-07-07 |  | Tower | Land site | 76 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
B02038 | B058E_B02038OD_MN_LDGWEST | Central | 1008P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Syafiq |  |  | DU00002007368 | [6 empty] | TOWER
S00414 | S093D_S00414OD_RAMOMILE7JLN | Sabah |  | Decomm |  | 2023Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2023-04-20 | 2023-06-26 |  |  | 2023-06-23 |  | 2023-06-13 | 2023-07-21 | CD//Ray Amos | 2023-06-14 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230608-0008/0612Sabah-GTSB-BOQ Template (template) | DU00002007369 |  |  |  |  | 2024-02-06 |  | RAPOLE | 30
P00488 | P033C_P00488OD_TMNDUKU | Northern |  | Decomm |  | 2023Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-05-12 |  |  |  | 2023-08-03 |  | 2023-08-02 | 2023-08-28 | CD//Rohizam | 2023-08-02 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V2 | DU00002007370 |  | 1) Please include Celcom TX cabinet |  |  | 2023-07-29 | Lampole | MONOPOLE | 30m
Q01087 | Q140B_Q01087OD_KGHIJRAH | Sarawak | 9029K | Swap |  | 2023Q2 | BY | Trintel | 4.6 TSSR Approved |  | 2023-04-19 | 2023-05-05 |  | 2023-05-10 |  | Closed | 2023-05-16 | 2023-05-16 | CD//John | 2023-05-16 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230403-0003 | DU00002007371 |  |  | 2023-08-30 | 2023-08-23 |  | Minaret | SHARING STRC SBC |  | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
S01152 | S093D_S01152OD_TMNBDCKOLOMBONG | Sabah |  | Decomm |  | 2023Q3 | AD | AllStar | 4.6 TSSR Approved |  | 2023-05-18 |  |  |  | 2023-05-22 |  | 2023-06-02 | 2023-07-27 | CD//Jahganathan | 2023-06-10 | Celcom Digi_RAN-Allstar-TSS-Sabah-20230608-0004 | DU00002007372 |  |  |  |  | 2023-10-02 |  | MONOPOLE
S00794 | S093G_S00794OD_UMSCHANSELLORY2 | Sabah |  | Decomm |  | 2023Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-04-18 | 2023-06-26 |  |  | 2023-06-30 |  | 2023-06-09 | 2023-10-27 | CD//Mohidi Jaan | 2023-06-10 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230608-0007 | DU00002007373 |  |  |  |  | 2023-07-28 | BillBoard | BOOM | 18
B02952 | B058B_B02952OD_JLNRAJANONG2 | Central | 1061K | Swap |  | 2023Q3 | HQ 1 | Ascentrack | 4.6 TSSR Approved |  | 2023-05-19 | 2023-05-25 |  | 2023-05-27 |  | Closed | 2023-05-29 | 2023-06-07 | CD//Ali akaram | 2023-06-06 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230523_0020 | DU00002007374 |  |  | 2023-06-29 | 2023-06-22 |  | H-bracket pole | Land site | 6 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
Q00270 | CITYPOINTID | Sarawak | 9051K | Site Out (Swap) | Swap->MOCN Decomm->Site Out->Site Out (Swap) | 2023Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2023-04-26 | 2023-05-10 |  | 2023-05-13 |  | Closed | 2023-05-24 | 2023-05-24 | CD//John | 2023-05-24 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230403-0003 | DU00002007375 | [6 empty] | IN-BUILDING
P00137 | P033B_P00137OD_TAMANAROWANA | Northern | 4041K | Swap |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-17 | 2023-06-06 |  | 2023-06-08 |  | Closed | 2023-06-12 | 2023-06-21 | CD//Affendi | 2023-06-21 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0016 | DU00002007376 |  |  | 2023-07-13 | 2023-07-06 |  | In-Building System | BOOM | 6M | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 3
B02811 | B058E_B02811OD_TMNSRIJAROMJENJAROM | Central | 1056K | Swap |  | 2023Q2 | YZ | GTSB | 4.6 TSSR Approved |  | 2023-04-07 | 2023-04-28 |  | 2023-04-29 |  | Closed | 2023-05-04 | 2023-06-06 | CD//Sapian | 2023-05-22 | CelcomDigi_RAN_GTSB_Central_20230407_0012 | DU00002007377 |  |  | 2023-06-13 | 2023-06-08 |  | Wall mount boom | UNIPOLE | 6 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
P00085 | P033B_P00085OD_TMNINDERAWASIH | Northern |  | Decomm |  | 2023Q3 | MH | GCI | 4.6 TSSR Approved |  | 2023-05-11 |  |  |  | 2023-06-19 |  | 2023-06-19 | 2023-10-27 | CD//Heng | 2023-07-03 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240529-0109 | DU00002007378 |  |  |  |  | 2023-07-26 |  | TOWER
B02043 | B058E_B02043OD_MN_BUSUTBARU | Central | 1006P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Syafiq |  |  | DU00002007379 | [6 empty] | Tower
P00501 | P033C_P00501OD_LRGPERMAJU6 | Northern | 4051K | Swap |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-31 | 2023-06-06 |  | 2023-06-06 |  | Closed | 2023-06-12 | 2023-06-21 | CD//Shamsul | 2023-06-21 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0015 | DU00002007380 |  |  | 2023-07-13 | 2023-07-12 |  | Lampole | LAMP_POLE | 24m | Add R8852E S9000 x3 + R8894E M1821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
B02046 | B063A_B02046OD_MN_KGTBKDARAT | Central | 1001P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN->Swap | 2026 | AI | GTSB | 4.6 TSSR Approved |  | 2025-11-12 | 2025-11-26 |  | 2025-11-27 |  | Under Approval | 2025-12-01 | 2026-01-22 | E//Ali | 2025-12-08 | SQ202512090181 | DU00002007381 |  |  | 2026-05-02 | 2026-05-02 |  | Tower | TOWER | 76m | Add R8852E S9000 x6+R9264M M1821 x4 |  | 3
B02948 | B058E_B02948OD_JLNSIMPANGTELUKPANGLIMAGARANG | Central |  | Decomm |  | 2023Q2 | MS | GCI | 14.1 TSSR Not Required (Decomm by CD) | [6 empty] | To be Submitted |  |  | CD//Ali akaram |  | 0925CD-Central-GCI-BOQ Template(new contract) | DU00002007382 |  |  |  |  | 2024-11-25 |  | Land site
B01857 | B061F_B01857OD_LATAR3 | Central |  | Decomm |  | 2023Q2 | MA | MTK | 4.6 TSSR Approved |  | 2023-04-10 | 2023-06-26 |  |  | 2023-05-30 |  | 2023-07-29 | 2023-11-28 | CD//Norhaliza | 2023-10-09 | CelcomDigi_RAN_MTK_TSS_Central_20230626_decom reraise | DU00002007383 |  |  |  |  | 2023-08-17 | Tower | TOWER | 45
Q00504 | Q140B_Q00504OD_RPRSBWJAYA | Sarawak |  | Decomm |  | 2023Q2 | SH | Datasco | 4.6 TSSR Approved |  | 2023-07-19 |  |  | 2023-07-24 |  | Closed | 2023-07-24 | 2024-01-22 | CD//John | 2023-07-25 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009/0612Sarawak-Datasco-BOQ Template (template) | DU00002007384 |  | 22/8: uncompleted info & photos FE info & photos are missing |  |  | 2024-01-08 |  | BOOM
B00563 | B059A_B00563OD_BT6BANTING | Central |  | Decomm |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-06-14 |  |  |  | 2024-04-17 |  | 2023-06-19 | 2024-05-29 | CD//Sapian | 2023-07-04 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002007385 |  | 1) Please provide clear photo for all existing TX equipment (zoom in photo) with clear labelling, including existing IDU. 2) Missing Antenna TX part at NE & FE page. Please provide photo with clear label. |  |  | 2023-09-21 |  | TOWER
Q00202 | Q140C_Q00202OD_TMBKT5 | Sarawak |  | Decomm |  | 2023Q2 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-12-14 |  |  |  | 2024-02-28 |  | 2024-03-01 | 2024-03-21 | CD//John | 2024-03-04 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009/0612Sarawak-Datasco-BOQ Template (template) | DU00002007386 |  |  |  |  | 2024-04-22 |  | TOWER
Q00707 | Q140C_Q00707OD_FORTUNECOMM | Sarawak |  | Decomm |  | 2023Q2 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-06-27 |  |  | 2023-07-04 |  | Under Approval | 2023-07-13 | 2023-09-29 | CD//John | 2023-07-13 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009 | DU00002007387 |  |  |  |  | 2023-08-05 |  | TOWER
P00695 | P033C_P00695_KGBARUALMA | Northern | 4056K | Swap |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-17 | 2023-05-27 |  | 2023-05-31 |  | Closed | 2023-06-07 | 2023-06-21 | CD//Shamsul | 2023-06-21 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0016 | DU00002007388 |  |  | 2023-07-11 | 2023-07-05 |  | Tower | MONOPOLE | 47 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
B02794 | B058D_B02794OD_LRGORKID1AKS04PORTKLANG | Central | 1055K | Swap |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-17 | 2023-05-10 |  | 2023-05-12 |  | Closed | 2023-05-17 | 2023-06-03 | CD//Tee | 2023-05-19 | CelcomDigi_RAN_Datasco_TSS_Central_20230418_0013 | DU00002007389 |  |  | 2023-06-21 | 2023-06-13 |  | Rooftop | UNIPOLE | 8m | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x5,Dismantle Celcom all RRU&BBU |  | 23
Q01173 | Q138A_Q01173OD_T3_NGTANYIT | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007390 | [6 empty] | TOWER
B02587 | B059A_B02587OD_JLNDAHLIAKGSGKELAMBU | Central | 1049K | Swap |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-07 | 2023-04-12 |  | 2023-04-18 |  | Closed | 2023-04-20 | 2023-06-06 | CD//Norhaliza | 2023-05-08 | CelcomDigi_RAN_GTSB_Central_20230407_0012 | DU00002007391 |  |  | 2023-06-08 | 2023-06-08 |  | Monople Tree | MONOPOLE | 45 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
Q00173 | Q140B_Q00173OD_CB_KKNJUNACO | Sarawak |  | Decomm |  | 2023Q2 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-06-23 |  |  | 2023-07-07 |  | Closed | 2023-07-21 | 2023-10-06 | CD//John | 2023-07-28 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009 | DU00002007392 |  |  |  |  | 2024-02-22 |  | TOWER
Q00724 | Q140C_Q00724OD_JLNNEWLANANG | Sarawak |  | Decomm |  | 2023Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-04-20 |  |  | 2023-06-15 |  | Closed | 2023-06-15 | 2023-07-28 | CD//John | 2023-06-17 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230613-0009 | DU00002007393 |  |  |  |  | 2023-12-09 |  | TOWER
B00579 | B058E_B00579OD_PR_KM5KLIA | Central | 1025K | Site Out (Swap) | Swap->MOCN Decomm->Site Out->Replacement, Site Out (Swap) | 2023Q2 | YZ | GTSB | 4.6 TSSR Approved |  | 2023-04-14 | 2023-04-17 | 2025-07-03 | 2023-04-19 |  | Closed | 2023-04-29 | 2023-05-15 | CD//Sapian | 2023-05-15 | CelcomDigi_RAN_GTSB_TSS_Central_20230417_0017 | DU00002007394 | [5 empty] | BillBoard | BILLBOARD | 32m
Q00184 | Q140C_Q00184OD_CB_JLNSBWDURIN | Sarawak | 9016K | Swap |  | 2023Q2 | MA | Datasco | 4.6 TSSR Approved |  | 2023-04-14 | 2023-04-26 |  | 2023-04-27 |  | Closed | 2023-05-03 | 2023-05-03 | CD//John | 2023-05-03 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002007395 |  |  | 2023-12-15 | 2023-11-27 |  | Tower | TOWER | 44 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
Q01119 | Q133A_Q01119OD_T3_KUALASERUPAI | Sarawak | 9032K | Swap |  | 2023Q3 | HQ 2 | Trintel | 4.6 TSSR Approved |  | 2023-04-13 | 2023-04-26 |  | 2023-05-09 |  | Closed | 2023-05-15 | 2023-05-16 | CD//John | 2023-05-16 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230403-0003 | DU00002007396 |  |  | 2023-08-02 | 2023-07-05 |  | Tower | TOWER | 45m | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
B00608 | B058E_B00608OD_PULAUCAREY | Central | 1026K | Swap |  | 2023Q2 | IE | Magicell | 4.6 TSSR Approved |  | 2023-04-15 | 2023-04-27 |  | 2023-05-02 |  | Closed | 2023-05-04 | 2023-06-05 | CD//Ali akaram | 2023-05-19 | CelcomDigi_RAN_Magicell_TSS_Central_20230417_0003 | DU00002007397 |  |  | 2023-07-14 | 2023-06-14 |  | Monople Tree | MONOPOLE | 45m | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
P00037 | P033B_P00037OD_NMXPRAI | Northern |  | Decomm |  | 2023Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-05-18 |  |  |  | 2023-07-27 |  | 2023-06-09 | 2024-05-10 | CD//Affendi | 2023-06-14 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1 | DU00002007398 |  | No TX Info, Photo not enough |  |  | 2023-07-25 |  | TOWER
S00953 | S093G_S00953OD_UMSKGC | Sabah |  | Decomm |  | 2023Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-05-02 | 2023-06-26 |  |  | 2023-06-12 |  | 2023-06-19 | 2023-07-27 | CD//Mohidi Jaan | 2023-06-19 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230608-0007 | DU00002007399 |  |  |  |  | 2023-07-28 | Lampole | BOOM | 25
S01077 | S093G_S01077OD_NAVALBASE2 | Sabah | 7010K | Swap |  | 2023Q2 | AD | Datasco | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-25 |  | 2023-04-30 |  | Closed | 2023-05-18 | 2023-06-13 | CD//Mohidi Jaan | 2023-06-13 | Celcom Digi_RAN-Datasco- TSS-Sabah-20230407-0002 | DU00002007400 |  |  | 2023-06-28 | 2023-06-22 |  | Lampole | RAPOLE | 30 | Add R9264M M1821 x3+R9264H M901821 x4+R8862A S2601 x7,Dismantle all celcom BBU&RRU |  | (S1->S2,S2->S3,S3->S4,S4->S1,Bisector@New S2/S3/S4)
B01921 | B061F_B01921OD_LATAR4 | Central |  | Decomm |  | 2023Q2 | MA | MTK | 4.6 TSSR Approved |  | 2023-04-11 | 2023-06-26 |  |  | 2023-05-31 |  | 2023-07-25 | 2023-11-28 | CD//Ali akaram | 2023-08-06 | CelcomDigi_RAN_MTK_TSS_Central_20230626_decom reraise | DU00002007401 |  |  |  |  | 2023-09-04 | Tower | TOWER | 45
Q00892 | Q140C_Q00892OD_LANANGIND | Sarawak |  | Decomm |  | 2023Q2 | ZB | AllStar | 4.6 TSSR Approved |  | 2023-04-19 | 2023-06-26 |  | 2023-06-30 |  | Closed | 2023-07-13 | 2023-09-01 | CD//John | 2023-07-13 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230613-0007 | DU00002007402 |  |  |  |  | 2023-07-28 | Monopole | TOWER | 30
Q01832 | Q138A_Q01832OD_SKTAMIN2 | Sarawak | 9043K | Swap |  | 2023Q2 | HQ 1 | Trintel | 4.6 TSSR Approved |  | 2023-04-14 | 2023-05-05 |  | 2023-05-11 |  | Closed | 2023-05-15 | 2023-05-15 | CD//John | 2023-05-15 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230403-0003 | DU00002007403 |  |  | 2023-09-15 | 2023-07-05 |  | Tower | TOWER | 60m | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
P00071 | P033B_P00071OD_PMTGNIBONG | Northern |  | Decomm |  | 2023Q3 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-05-19 |  |  |  | 2023-06-15 |  | 2023-06-16 | 2024-02-15 | CD//Shamsul | 2023-06-27 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V2 | DU00002007404 |  | CD request to maintain Celcom TM LL and change to Dismantle Digi link 2/2: Missing xC equipment for relocation |  |  | 2023-08-03 |  | TOWER
P00013 | P034A_P00013OD_SUNGAIPUYU | Northern |  | Decomm |  | 2023Q3 | ZA | YPTT | 4.6 TSSR Approved |  | 2023-07-13 |  |  |  | 2023-07-26 |  | 2023-07-27 | 2023-08-30 | CD//Shamsul | 2023-08-06 | Celcom Digi_RAN-YPTT-TSS-Northern-20230609-0018 | DU00002007405 |  | On Hold, waiting DC share missing Photo |  |  | 2023-07-22 |  | TOWER
Q02023 | Punan Ba (old - Nanga Ibun) | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007406 | [6 empty] | TOWER
Q00194 | Q140C_Q00194OD_JLNSTABAU | Sarawak |  | Decomm |  | 2023Q2 | ZB | AllStar | 4.6 TSSR Approved |  | 2023-04-25 | 2023-06-26 |  | 2023-07-11 |  | Closed | 2023-07-21 | 2023-08-14 | CD//John | 2023-07-21 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230613-0007 | DU00002007407 |  | 20230801: All TX info are missing (NE & FE ) |  |  | 2023-08-19 | Tower | TOWER
B02427 | B058B_B02427OD_KGSGKANDIS | Central | 1045K | Swap |  | 2023Q3 | HQ 6 | Futong | 4.6 TSSR Approved |  | 2023-05-24 | 2023-06-07 |  | 2023-06-12 |  | Closed | 2023-06-17 | 2023-07-06 | CD//Ali akaram | 2023-07-04 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002007408 |  |  | 2023-07-27 | 2023-07-22 |  | Monopole | RAPOLE | 30 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
Q00658 | Q118B_Q00658OD_CB_PKNSEBAUH | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2023Q3 | HW | Magicell | 4.6 TSSR Approved |  | 2025-06-17 |  | 2025-06-18 |  | 2025-08-01 |  | 2025-09-12 | 2026-01-20 | E//John | 2025-09-12 | SQ202506110081-Magicell/SQ202507140221-Magicell | DU00002007409 |  |  |  |  | 2025-11-18 |  | TOWER
Q00285 | Q118A_Q00285OD_JLNKEPPEL | Sarawak |  | Decomm |  | 2023Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2023-06-19 |  |  | 2023-09-06 |  | Closed | 2023-09-06 | 2023-09-12 | CD//John | 2023-09-08 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230613-0009/Celcom Digi_RAN-Trintel-TSS DECOMM-Sarawak-20231130 | DU00002007410 |  |  |  |  | 2023-12-07 |  | BOOM
Q01375 | Q140B_Q01375OD_KGJERIAH | Sarawak |  | Decomm |  | 2023Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-06-09 |  |  |  | 2023-07-27 |  | 2023-07-27 | 2023-08-06 | CD//John | 2023-07-28 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230613-0009/Celcom Digi_RAN-Trintel-TSS DECOMM-Sarawak-20231130 | DU00002007411 |  |  |  |  | 2023-10-13 |  | RAPOLE
Q00172 | Q140B_Q00172OD_JLNOYA | Sarawak | 9013K | Swap |  | 2023Q2 | BY | Datasco | 4.6 TSSR Approved |  | 2023-04-17 | 2023-04-26 |  | 2023-04-28 |  | Closed | 2023-04-28 | 2023-05-03 | CD//John | 2023-04-28 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002007412 |  |  | 2023-11-25 | 2023-11-18 |  | Tower | TOWER | 30 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
S00037 | S093D_S00037OD_INANAMBUSINESSCENTRE | Sabah |  | Decomm |  | 2023Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2023-04-20 | 2023-06-26 |  |  | 2023-06-23 |  | 2023-06-14 | 2023-07-27 | CD//Mohidi Jaan | 2023-06-14 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230608-0008 | DU00002007413 |  |  |  |  | 2023-09-18 | Unipole | BOOM | 15
Q01831 | Q138A_Q01831OD_RHAGAN2 | Sarawak | 9042K | Swap |  | 2023Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-04-17 | 2023-05-09 |  | 2023-05-12 |  | Closed | 2023-05-17 | 2023-05-17 | CD//John | 2023-05-17 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230419-0004 | DU00002007414 |  |  | 2023-08-02 | 2023-07-14 |  | Tower | TOWER | 65m | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
B02677 | B058E_B02677OD_BDRBESTARIKLG | Central |  | Decomm |  | 2023Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2023-04-17 | 2023-06-26 |  | 2023-04-20 | 2023-06-15 | Rectificating | 2023-06-16 | 2023-07-17 | CD//Ali akaram | 2023-07-06 | CelcomDigi_RAN_AllStar_TSS_Central_20230626_decom reraise | DU00002007415 |  |  |  |  | 2023-06-26 | Monopole | LAMP_POLE | 25
S01549 | S093D_S01549OD_PURIWARISAN | Sabah |  | Decomm |  | 2023Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2023-04-20 | 2023-06-26 |  |  | 2023-06-23 |  | 2023-06-14 | 2023-07-21 | CD//Ray Amos | 2023-06-26 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230608-0008/0612Sabah-GTSB-BOQ Template (template) | DU00002007416 |  |  |  |  | 2023-09-12 | Monopole | RAPOLE | 30
S00952 | S093G_S00952OD_UMSKGA | Sabah |  | Decomm |  | 2023Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-04-18 | 2023-06-26 |  |  | 2023-06-30 |  | 2023-06-09 | 2023-07-27 | CD//Mohidi Jaan | 2023-06-09 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230608-0007 | DU00002007417 |  |  |  |  | 2023-08-15 | BillBoard | BOOM | 25
S00042 | S093A_S00042OD_BUKITKOKOL | Sabah |  | Decomm |  | 2023Q2 | MS | Datasco | 4.6 TSSR Approved |  | 2023-05-18 | 2023-06-26 |  |  | 2023-05-13 |  | 2023-07-26 | 2023-10-13 | CD//Ray Amos | 2023-07-27 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006 | DU00002007418 |  | 20230727: FE photos & info missing |  |  | 2023-10-27 | Monopole | TOWER | 106m
P00711 | P033C_P00711OD_PENANG_SCIENCE_PARK | Northern |  | Decomm |  | 2023Q3 | MH | GTSB | 4.6 TSSR Approved |  | 2023-06-02 |  |  |  | 2023-06-16 |  | 2023-06-18 | 2024-04-23 | CD//Quah | 2023-07-06 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1/Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20240305-0096 | DU00002007419 |  |  |  |  | 2023-08-22 |  | MONOPOLE
Q01269 | Q140C_Q01269OD_JLNPOHYEW | Sarawak | 9036K | Swap |  | 2023Q2 | HQ 2 | AllStar | 4.6 TSSR Approved |  | 2023-04-17 | 2023-05-03 |  | 2023-05-09 |  | Closed | 2023-05-15 | 2023-05-15 | CD//John | 2023-05-15 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230403-0003 | DU00002007420 |  |  | 2023-11-17 | 2023-10-23 |  | Wall mount boom | BOOM | 3 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
P00108 | P033B_P00108IB_SOLECTRON1 | Northern | 4059K | Swap |  | 2023Q3 | WP | GTSB | 4.6 TSSR Approved |  | 2023-06-13 | 2023-06-14 |  | 2023-06-15 |  | Closed | 2023-06-23 | 2023-07-07 | CD//Shamsul | 2023-07-03 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0016 | DU00002007421 |  |  | 2023-07-13 | 2023-07-13 |  | Portables BTS | BOOM |  | Add R8852E S9000 x1 + R8862A S1800 x1 + R8862A S2100 x1,Dismantle all celcom BBU&RRU
Y00057 | B058E_Y00057OD_DEWAN_SERI_JUGRABANTING | Central |  | Decomm |  | 2023Q2 | AI | GTSB | 14.1 TSSR Not Required (Decomm by CD) | [6 empty] | To be Submitted |  |  | CD//Ali akaram |  | 0925CD-Central-GTSB-BOQ Template(new contract) | DU00002007422 |  |  |  |  | 2024-11-25 |  | TOWER
P00097 | P034A_P00097OD_DESAMURNI | Northern | 4040K | Swap |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-06-06 | 2023-06-06 |  | 2023-06-09 |  | Closed | 2023-06-10 | 2023-06-21 | CD//Affendi | 2023-06-21 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0016 | DU00002007423 |  |  | 2023-06-27 | 2023-06-24 |  | Tower | TOWER | 60 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 13
S00516 | S109A_S00516OD_KIULU | Sabah |  | Decomm |  | 2023Q2 | AD | Futong | 4.6 TSSR Approved |  | 2023-07-08 |  |  |  | 2023-07-11 |  | 2023-07-12 | 2023-08-30 | CD//Ray Amos | 2023-07-14 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0010 | DU00002007424 |  |  |  |  | 2023-11-07 |  | TOWER
B01979 | B058E_B01979OD_BDRSRIEHSAN2 | Central | 1035K | Swap |  | 2023Q2 | XH | GTSB | 4.6 TSSR Approved |  | 2023-04-24 | 2023-05-03 |  | 2023-05-04 |  | Closed | 2023-05-06 | 2023-06-06 | CD//Ali akaram | 2023-05-20 | CelcomDigi_RAN_GTSB_TSS_Central_20230425_0020 | DU00002007425 |  |  | 2023-06-08 | 2023-06-06 |  | Lampole | LAMP_POLE | 20 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 3
B02204_IBC | B058C_B02204OD_AMBANGBOTANICKLG | Central |  | Decomm |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-01-19 |  |  |  | 2024-02-02 |  | 2024-02-05 | 2024-02-23 | CD//Sapian | 2024-02-20 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240128 | DU00002007426 |  |  |  |  | 2024-07-31 |  | BOOM
S00736 | S093A_S00736OD_TMNSERIPULUT | Sabah |  | Decomm |  | 2023Q2 | MS | Datasco | 4.6 TSSR Approved |  | 2023-06-09 |  |  |  | 2023-05-19 |  | 2023-06-14 | 2023-07-21 | CD//Ray Amos | 2023-06-19 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006 | DU00002007427 |  |  |  |  | 2023-09-15 |  | TOWER
B01307 | B059A_B01307OD_PANTAIKLANANG | Central |  | Decomm |  | 2023Q2 | MA | Magicell | 4.6 TSSR Approved |  | 2023-04-07 |  |  | 2023-04-11 | 2023-06-14 | Closed | 2023-06-19 | 2023-07-17 | CD//Ali akaram | 2023-07-04 | CelcomDigi_RAN_Magicell_TSS_Central_20230626_decom reraise / CelcomDigi_TX_Magicell_TSS_Decom_Central_20230714 | DU00002007428 |  | 1606 TSSR reject. No mMCME info & photo |  |  | 2023-07-20 | Tower | TOWER | 62
B02607 | B058B_B02607OD_GALERIEMPIREKLG | Central | 1051K | Swap |  | 2023Q3 | SS | YPTT | 4.6 TSSR Approved |  | 2023-07-05 | 2023-06-28 |  | 2023-07-05 |  | Closed | 2023-07-06 | 2023-10-27 | CD//Sapian | 2023-07-15 | CelcomDigi_RANMW_YPTT_TSS_Central_20230508_0002 | DU00002007429 |  |  | 2023-07-25 | 2023-07-22 |  | Pole | POLE | 4m | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
B02042 | B058E_B02042OD_MN_KGPULAUCAREY | Central | 1010P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Syafiq |  |  | DU00002007430 | [6 empty] | Tower
S01135 | S093D_S01135OD_KGMABPAI2 | Sabah |  | Decomm |  | 2023Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2023-05-02 | 2023-06-26 |  |  | 2023-05-18 |  | 2023-07-24 | 2023-10-06 | CD//Mohidi Jaan | 2023-07-24 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230608-0008/0612Sabah-GTSB-BOQ Template (template) | DU00002007431 |  |  |  |  | 2023-10-11 | Monopole | MONOPOLE | NO SPACE TO STEP FOR MEASURING HEIGHT
S00019 | S093A_S00019OD_TMKARATONG | Sabah | 7004K | Swap |  | 2023Q2 | AD | Datasco | 4.6 TSSR Approved |  | 2023-06-24 | 2023-09-08 |  | 2023-09-12 |  | Closed | 2023-09-12 | 2023-09-15 | CD//Mohidi Jaan | 2023-09-13 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230626 | DU00002007432 |  |  | 2024-02-14 | 2024-01-16 |  | Tower | TOWER | 100 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
S00027 | S093D_S00027OD_KOLOMBONG | Sabah |  | Decomm |  | 2023Q3 | AD | AllStar | 4.6 TSSR Approved |  | 2023-05-18 |  |  |  | 2023-05-18 |  | 2023-06-12 | 2023-07-21 | CD//Mohidi Jaan | 2023-06-13 | Celcom Digi_RAN-Allstar-TSS-Sabah-20230608-0004 | DU00002007433 |  |  |  |  | 2023-09-15 |  | LAMP_POLE
B02578 | B058C_B02578OD_PANGSAPURIKASUARINAKLG | Central |  | Decomm |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-04-17 | 2023-06-26 |  |  | 2024-05-20 |  | 2023-08-02 | 2023-10-18 | CD//Norhaliza | 2023-10-09 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230626_decom reraise | DU00002007434 |  |  |  |  | 2023-09-08 | H-bracket pole | WALL MOUNTED BOOM | 6.7m
P00516 | P033B_P00516OD_KGMASJIDTIMAH | Northern | 4052K | Swap |  | 2023Q3 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-05-07 | 2023-05-19 |  | 2023-05-24 | 2023-05-24 | Closed | 2023-05-29 | 2023-06-12 | CD//Shamsul | 2023-06-12 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0009 | DU00002007435 |  |  | 2023-07-13 | 2023-07-06 |  | Lampole | LAMP_POLE | 17M | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x5,Dismantle Celcom all RRU&BBU |  | 12
Q00585 | Q140B_Q00585OD_RANTAUPJG | Sarawak |  | Decomm |  | 2023Q2 | ZB | AllStar | 4.6 TSSR Approved |  | 2023-04-20 | 2023-06-26 |  | 2023-07-11 |  | Closed | 2023-07-21 | 2023-09-01 | CD//John | 2023-07-28 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230613-0007 | DU00002007436 |  | 26/8: UNCOMPLETED INFO 16/8: Uncompleted info & photos |  |  | 2023-08-04 | Tower | TOWER | 60
Q00480 | Q140A_Q00480OD_TMNAPOLLO | Sarawak |  | Decomm |  | 2023Q2 | SH | Datasco | 4.6 TSSR Approved |  | 2023-07-18 |  |  | 2023-07-24 |  | Closed | 2023-07-24 | 2023-08-24 | CD//John | 2023-07-25 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009 | DU00002007437 |  |  |  |  | 2024-01-26 |  | TOWER
B02499 | B058E_B02499OD_JLNSKLHKGJENJAROM | Central | 1046K | Swap |  | 2023Q2 | YZ | GTSB | 4.6 TSSR Approved |  | 2023-04-07 | 2023-04-17 |  | 2023-04-19 |  | Closed | 2023-05-03 | 2023-05-17 | CD//Sapian | 2023-05-17 | CelcomDigi_RAN_GTSB_Central_20230407_0012 | DU00002007438 |  |  | 2023-06-15 | 2023-06-13 |  | Unipole | MONOPOLE | 45 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 3
B00559 | B061F_B00559OD_BKTTADUN | Central |  | Decomm |  | 2023Q2 | MA | MTK | 4.6 TSSR Approved |  | 2023-04-11 | 2023-06-26 |  |  | 2023-07-06 |  | 2023-07-29 | 2023-11-22 | CD//Ali Akaram | 2023-09-19 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002007439 |  |  |  |  | 2023-09-28 | Tower | TOWER | 76
Q00662 | Q140C_Q00662OD_LRGTUNKUOSMAN | Sarawak |  | Decomm |  | 2023Q2 | BY | Datasco | 4.6 TSSR Approved |  | 2023-06-15 |  |  | 2023-06-19 |  | Closed | 2023-06-20 | 2024-07-30 | CD//John | 2023-06-22 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009 | DU00002007440 |  | 20230731 : Missing TX info |  |  | 2023-08-02 |  | LAMP_POLE
B02058 | B059A_B02058OD_TMNSRIPUTRABANTING | Central | 1038K | Swap |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-07 | 2023-04-13 |  | 2023-04-14 |  | Closed | 2023-05-02 | 2023-06-06 | CD//Sapian | 2023-05-16 | CelcomDigi_RAN_GTSB_Central_20230407_0012 | DU00002007441 |  |  | 2023-06-29 | 2023-06-06 |  | Monopole | MONOPOLE | 45 | Add R9264H M901821 x3 + R9264M M1821 x3 + R8862A S2601 x6,Dismantle Celcom all RRU&BBU |  | 123
S00678 | S093G_S00678OD_UMSWATERTANK | Sabah |  | Decomm |  | 2023Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-05-02 | 2023-06-26 |  |  | 2023-07-05 |  | 2023-06-13 | 2023-10-13 | CD//Mohidi Jaan | 2023-06-13 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230608-0007 | DU00002007442 |  | 2023-07-06 missing tx photos and info |  |  | 2023-09-11 |  | BOOM | 45
S00021 | S109A_S00021OD_TMTUARAN | Sabah |  | Decomm |  | 2023Q2 | AD | Futong | 4.6 TSSR Approved |  | 2023-08-24 |  |  |  | 2023-08-24 |  | 2023-08-30 | 2023-09-29 | CD//Ray Amos | 2023-09-01 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0010/0612Sabah-Futong-BOQ Template (template) | DU00002007443 |  |  |  |  | 2024-01-31 |  | TOWER
B01078 | B059A_B01078OD_KANCHONGTENGAH | Central |  | Decomm |  | 2023Q2 | IE | Magicell | 4.6 TSSR Approved |  | 2023-04-13 | 2023-06-26 |  | 2023-04-19 | 2023-08-11 | Rectificating | 2023-07-24 | 2024-01-26 | CD//Ali akaram | 2023-08-02 | CelcomDigi_RAN_Magicell_TSS_Central_20230626_decom reraise/CelcomDigi_TX_Magicell_TSS_Central_20230807 | DU00002007444 |  |  |  |  | 2023-08-29 | Tower | TOWER | 62M
Q00644 | Q140C_Q00644OD_JAMBATANDURIN | Sarawak |  | Decomm |  | 2023Q2 | SH | Datasco | 4.6 TSSR Approved |  | 2023-07-15 |  |  | 2023-07-29 |  | Closed | 2023-07-31 | 2023-09-29 | CD//John | 2023-08-01 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009 | DU00002007445 |  | 22/8: uncompleted info & photos |  |  | 2023-12-12 |  | TOWER
Q00612 | Q144A_Q00612OD_KEMSEKAWIE | Sarawak | 9025K | Swap |  | 2023Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2023-06-20 | 2023-06-22 |  | 2023-06-26 |  | Closed | 2023-06-30 | 2023-07-07 | CD//John | 2023-07-06 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230626 | DU00002007446 |  |  | 2023-12-11 | 2023-09-18 |  | Tower | GUYED MAST | 54m | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
Q00584 | Q138A_Q00584OD_CB_STAPANG | Sarawak | 9001K | MOCN By Other Vendor | Swap->Maintain USP MOCN->On Hold->Maintain USP MOCN->On Hold->MOCN By Other Vendor | 2023Q2 | HQ 2 | Trintel | 4.6 TSSR Approved |  | 2023-04-19 | 2023-05-03 |  | 2023-05-09 |  | Closed | 2023-05-15 | 2023-05-16 | CD//John | 2023-05-16 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230425-0005 | DU00002007447 | [5 empty] | Pole | TOWER | 75
Q01902 | Q140A_Q01902OD_ULUSGMERAH3 | Sarawak | 9049K | Swap |  | 2023Q2 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-06-12 | 2023-06-28 |  | 2023-07-03 |  | Closed | 2023-07-04 | 2023-07-05 | CD//John | 2023-07-04 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230626 | DU00002007448 |  |  | 2024-01-26 | 2024-01-22 |  |  | RAPOLE | 31 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
S00036 | S093D_S00036OD_KALANSANAN | Sabah |  | Decomm |  | 2023Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2023-04-20 | 2023-06-26 |  |  | 2023-06-23 |  | 2023-06-14 | 2023-07-27 | CD//Mohidi Jaan | 2023-06-14 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230608-0008 | DU00002007449 |  |  |  |  | 2023-09-12 | Pole | BOOM | 6
B02505 | B058B_B02505OD_JLNSGPINANGKLG | Central | 1047K | Swap |  | 2023Q3 | HQ 6 | Datasco | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-09 |  | 2023-05-11 |  | Closed | 2023-05-18 | 2023-06-10 | CD//Tee | 2023-06-01 | CelcomDigi_RAN_Datasco_TSS_20230505_0019 | DU00002007450 |  |  | 2023-07-25 | 2023-07-22 |  | Lampole | LAMP_POLE | 27 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x5,Dismantle Celcom all RRU&BBU |  | 13
Q01835 | Q140B_Q01835OD_YMCA | Sarawak | 9044K | Swap |  | 2023Q2 | HQ 2 | Datasco | 4.6 TSSR Approved |  | 2023-04-14 | 2023-05-03 |  | 2023-05-06 |  | Closed | 2023-05-08 | 2023-05-10 | CD//John | 2023-05-10 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002007451 |  |  | 2023-12-07 | 2023-11-24 |  | Tower | TOWER | 61 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
Q00193 | Q140B_Q00193OD_SEBINTEK | Sarawak |  | Decomm |  | 2023Q2 | BY | Datasco | 4.6 TSSR Approved |  | 2023-04-17 | 2023-06-26 |  | 2023-06-19 |  | Closed | 2023-06-20 | 2024-02-15 | CD//John | 2023-06-21 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009/0612Sarawak-Datasco-BOQ Template (template) | DU00002007452 |  | 17/8 - TSSR Reject Picture not complete |  |  | 2023-12-11 | Tower | TOWER | 60
B00590 | B059A_B00590OD_KGKURAUBDR | Central |  | Decomm |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-11 | 2023-04-15 |  |  | 2023-07-31 |  | 2023-06-14 | 2023-12-20 | CD//Ali akaram | 2023-07-05 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise / CelcomDigi_TX_Datasco_TSS_Decom_Central_20230714 | DU00002007453 |  |  |  |  | 2023-07-09 | Tower | TOWER | 60
Q01122 | Q144A_Q01122OD_T3_RHMANDAU | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007454 | [6 empty] | Land site
Q00240 | Q140A_Q00240OD_ULUSGMERAH | Sarawak |  | Decomm |  | 2023Q2 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-06-24 |  |  | 2023-07-03 |  | Closed | 2023-07-20 | 2023-10-21 | CD//John | 2023-08-08 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009 | DU00002007455 |  |  |  |  | 2024-02-01 |  | BOOM
B02588 | B058D_B02588OD_TGINDUSTRIALPARKKL | Central | 1050K | Swap |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-11 | 2023-04-23 |  | 2023-04-27 |  | Closed | 2023-04-27 | 2023-06-03 | CD//Sapian | 2023-05-15 | CelcomDigi_RAN_Datasco_TSS_Central_20230413_0011 | DU00002007456 |  |  | 2023-06-27 | 2023-06-26 |  | Pole | WALL MOUNTED BOOM | 7m | Add R9264H M901821 x3 + R8862A S2600 x3,Dismantle Celcom all RRU&BBU
B00526 | B059A_B00526OD_PR_MORIB | Central |  | Decomm |  | 2023Q2 | MA | Magicell | 4.6 TSSR Approved |  | 2023-04-17 | 2023-06-26 |  | 2023-04-20 | 2023-06-16 | Rectificating | 2023-06-16 | 2023-07-22 | CD//Ali akaram | 2023-07-12 | CelcomDigi_RAN_Magicell_TSS_Central_20230626_decom reraise/CelcomDigi_RAN-TX_Magicell_TSS_Central_20230816_Decom | DU00002007457 |  |  |  |  | 2023-07-18 | Tower | TOWER | 60m
B02490 | B058C_B02490OD_BOTANICAVENUEKLG | Central |  | Decomm |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-04-12 |  |  |  | 2023-10-05 |  | 2023-10-06 |  | CD//Sapian | 2023-10-13 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230626_decom reraise | DU00002007458 |  | Wrong FE |  |  | 2023-10-10 |  | TRIPOD
B02164 | B061C_B02164OD_SEK34SHLM | Central | 1039K | Swap |  | 2023Q3 | YZ | Futong | 4.6 TSSR Approved |  | 2023-05-25 | 2023-05-26 |  | 2023-05-30 |  | Closed | 2023-05-31 | 2023-10-18 | CD//Ali akaram | 2023-08-02 | CelcomDigi_RANMW_Futong_TSS_Central_20230508_0001 | DU00002007459 |  |  | 2023-07-27 | 2023-07-22 |  | Pole | UNIPOLE | 6 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
P00278 | P033C_P00278OD_AUTOCITY | Northern |  | Decomm |  | 2023Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-05-23 |  |  |  | 2023-07-07 |  | 2023-06-08 | 2023-07-21 | CD//Shamsul | 2023-06-22 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1 | DU00002007460 |  |  |  |  | 2023-08-23 |  | LAMP_POLE
Q01761 | Q140B_Q01761OD_TMNPERMAISBW | Sarawak |  | Decomm |  | 2023Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-04-17 | 2023-06-26 |  | 2023-06-12 |  | Closed | 2023-06-12 | 2023-07-21 | CD//John | 2023-06-12 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230613-0009/Celcom Digi_RAN-Trintel-TSS DECOMM-Sarawak-20231130 | DU00002007461 |  |  |  |  | 2023-07-31 | Lampole | RAPOLE | 30
Q00170 | Q140C_Q00170OD_JLNLANANG | Sarawak | 9012K | Swap |  | 2023Q2 | SH | Datasco | 4.6 TSSR Approved |  | 2023-04-17 | 2023-05-09 |  | 2023-05-10 |  | Closed | 2023-05-12 | 2023-05-12 | CD//John | 2023-05-12 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002007462 |  |  | 2023-08-29 | 2023-07-26 |  | Pole | BOOM |  | Add R9264H M901821 x3 + R8862A S2600 x3,Dismantle Celcom all RRU&BBU
S00517 | S109A_S00517OD_CB_KGSGDAMIT | Sabah |  | Decomm |  | 2023Q2 | AD | Futong | 4.6 TSSR Approved |  | 2023-05-18 | 2023-06-26 |  |  | 2023-06-06 |  | 2023-06-12 | 2023-07-21 | CD//Ray Amos | 2023-06-13 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0010 | DU00002007463 |  |  |  |  | 2023-09-30 | Tower | TOWER
S00023 | S093G_S00023OD_UITM | Sabah |  | Decomm |  | 2023Q2 | MS | Datasco | 4.6 TSSR Approved |  | 2023-05-18 | 2023-06-26 |  |  | 2023-05-18 |  | 2023-06-21 | 2023-10-27 | CD//Mohidi Jaan | 2023-06-22 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006 | DU00002007464 |  |  |  |  | 2023-10-19 | Tower | TOWER | 45
Q00916 | Q140C_Q00916OD_JLNSGASSAN | Sarawak |  | Decomm |  | 2023Q2 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-06-11 |  |  | 2023-07-13 |  | Under Approval | 2023-07-13 | 2023-08-24 | CD//John | 2023-07-13 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009/0612Sarawak-Datasco-BOQ Template (template) | DU00002007465 |  |  |  |  | 2023-08-23 |  | TOWER
S00606 | S109A_S00606OD_KGPANANDAWAN | Sabah |  | Decomm |  | 2023Q2 | AD | Futong | 4.6 TSSR Approved |  | 2023-07-08 |  |  |  | 2023-08-18 |  | 2023-08-23 | 2023-10-06 | CD//Ray Amos | 2023-08-24 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0010 | DU00002007466 |  |  |  |  | 2023-11-07 |  | TOWER
P00381 | P033B_P00381OD_TMNSEMBILANG | Northern | 4047K | Swap |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-19 |  | 2023-05-29 |  | Closed | 2023-06-01 | 2023-06-11 | CD//Affendi | 2023-06-11 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0016 | DU00002007467 |  |  | 2023-07-13 | 2023-07-13 |  | Minaret | LAMP_POLE | NA | Add R9264H M901821 x3 + R9264M M1821 x3 + R8862A S2601 x6,Dismantle Celcom all RRU&BBU |  | 123
S01122 | S093G_S01122OD_UITMTMNJAYADIRI | Sabah |  | Decomm |  | 2023Q2 | MS | Datasco | 4.6 TSSR Approved |  | 2023-06-09 |  |  |  | 2023-05-12 |  | 2023-06-21 | 2023-09-16 | CD//Mohidi Jaan | 2023-06-22 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0006/0612Sabah-Datasco-BOQ Template (template) | DU00002007468 |  | 20230807: all tx info & photos are wrong, 2023-07-20 missing tx photos and info |  |  | 2024-02-07 | Lampole | LAMP_POLE
Q00597 | Q140C_Q00597IB_PREMIERID | Sarawak |  | Decomm |  | 2023Q2 | SH | Datasco | 4.6 TSSR Approved |  | 2023-08-10 |  |  | 2023-08-16 |  | Closed | 2023-08-16 | 2023-10-06 | CD//John | 2023-08-21 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009 | DU00002007469 |  |  |  |  | 2023-10-16 |  | BOOM
B02069 | B058C_B02069OD_PSRNPEGAGAKLG | Central |  | Decomm |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-04-17 |  |  |  | 2023-08-07 |  | 2023-07-21 | 2023-08-09 | CD//Sapian | 2023-07-29 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230626_decom reraise | DU00002007470 |  |  |  |  | 2023-08-22 |  | BOOM
Q01922 | Q140A_Q01922OD_TMNWAWASAN | Sarawak |  | Decomm |  | 2023Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-04-17 | 2023-06-26 |  | 2023-07-10 |  | Closed | 2023-07-12 | 2023-07-21 | CD//John | 2023-07-13 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230613-0009/Celcom Digi_RAN-Trintel-TSS DECOMM-Sarawak-20231130 | DU00002007471 |  |  |  |  | 2023-08-05 | Monopole | RAPOLE | 30
Q00180 | Q140C_Q00180OD_PARADOM | Sarawak |  | Decomm |  | 2023Q2 | BY | Datasco | 4.6 TSSR Approved |  | 2023-06-20 |  |  | 2023-06-23 |  | Under Approval | 2023-07-13 | 2024-06-21 | CD//John | 2023-07-13 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009 | DU00002007472 |  | 16/8: Uncompleted info & photos |  |  | 2023-07-26 |  | TOWER
B00448 | B058E_B00448OD_PR_BT8SIJANGKANG | Central |  | Decomm |  | 2023Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2023-04-12 | 2023-06-26 |  |  | 2023-06-14 |  | 2023-06-15 | 2023-12-20 | CD//Ali akaram | 2023-08-16 | CelcomDigi_RAN_AllStar_TSS_Central_20230626_decom reraise | DU00002007473 |  |  |  |  | 2023-07-11 | Tower | TOWER | 60
Q02020 | Pekan Nanga Merit | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007474 | [6 empty] | TOWER
Q00926 | Q140B_Q00926OD_KEMRENJER | Sarawak |  | Decomm |  | 2023Q2 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-06-27 |  |  | 2023-06-30 |  | Rectificating | 2023-07-12 | 2023-08-23 | CD//John | 2023-07-13 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009 | DU00002007475 |  | 2023-07-18 Missing TX photos and info |  |  | 2023-12-11 |  | TOWER
B00809 | B058D_B00809OD_PDMARANJAYA | Central |  | Decomm |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-05-03 | 2023-06-26 |  | 2023-06-04 | 2024-10-21 | Closed | 2023-06-09 | 2023-07-17 | CD//Norhaliza | 2023-06-09 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230626_decom reraise | DU00002007476 |  |  |  |  | 2023-07-17 | Minaret | TOWER | 2m
B02039 | B058E_B02039OD_MN_LDGEAST | Central | 1009P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Syafiq |  |  | DU00002007477 | [6 empty] | TOWER
S00029 | S093G_S00029OD_CB_NEXUSKARAMBUNAI | Sabah |  | Decomm |  | 2023Q2 | MS | Datasco | 4.6 TSSR Approved |  | 2023-06-22 |  |  |  | 2023-06-14 |  | 2023-06-15 | 2023-09-08 | CD//Mohidi Jaan | 2023-06-15 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007/0612Sabah-Datasco-BOQ Template (template) | DU00002007478 |  | 2023-07-21 missing tx photos and info |  |  | 2024-01-08 |  | TRIPOD
Q00620 | Q140B_Q00620OD_JLNULUOYA | Sarawak | 9430K | Swap | TBD->Swap | 2023Q2 | ZB | Trintel | 4.6 TSSR Approved |  | 2024-01-18 | 2024-01-18 |  | 2024-01-19 |  | Closed | 2024-03-04 | 2024-03-04 | CD//John | 2024-03-04 | 0626Sarawak-Trintel-BOQ Template (template) | DU00002007479 |  | 1/19 : 1. RRU not proposed at ground for all Sector 2. Y Bracket Angle leg with 2*2m boom for Antenna not H Bracket | 2024-04-06 | 2024-02-23 |  | Tower | TOWER | 76m | Add R8852E S9000 x3+R8862A S2601 x3+A9732 M1821 x3,Dismantle | 123 | 0
P00052 | P034A_P00052OD_WISMAPELADANG | Northern |  | Decomm |  | 2023Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-05-10 |  |  |  | 2023-06-02 |  | 2023-06-07 | 2023-07-21 | CD//Shamsul | 2023-06-13 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1 | DU00002007480 |  |  |  |  | 2023-07-25 |  | BOOM
P00033 | P034A_P00033OD_WISMAUMNO | Northern | 4037K | Swap |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-06-07 | 2023-06-08 |  | 2023-06-09 |  | Closed | 2023-06-10 | 2023-06-27 | CD//Heng | 2023-06-26 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0015 | DU00002007481 |  |  | 2023-06-27 | 2023-06-20 |  | In-Building System | BOOM | 3 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 3(S1->S3,S2->S1,S3->S2,rename Sector ID,Bisector@New s2)
Q01155 | Q122A_Q01155OD_T3_RHEROK | Sarawak | 9034K | Swap |  | 2023Q2 | MA | Trintel | 4.6 TSSR Approved |  | 2023-04-13 | 2023-04-26 |  | 2023-05-01 |  | Closed | 2023-05-05 | 2023-05-05 | CD//John | 2023-05-05 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230403-0003 | DU00002007482 |  |  | 2023-10-19 | 2023-07-11 |  | Tower | TOWER | 60 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
Q00230 | Q140B_Q00230OD_SBWAIRPORT | Sarawak |  | Decomm |  | 2023Q2 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-06-22 |  |  | 2023-06-28 |  | Under Approval | 2023-07-12 | 2023-10-06 | CD//John | 2023-07-13 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009 | DU00002007483 |  | 2023-07-18 Missing TX photos and info |  |  | 2023-12-09 |  | MONOPOLE
P00226 | CARREFOURSBJ_4G | Northern |  | Decomm |  | 2023Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-05-25 |  |  |  | 2023-08-03 |  | 2023-08-04 | 2023-09-21 | CD//Quah | 2023-08-22 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V2/Celcom Digi_RAN-CCSMY-TSS Decomm-Northern-20240131-0091 | DU00002007484 |  | 1) Please include Celcom cabinet and TX equipment inside 15/9: Please state in drawing location cabinet Celcom Digi |  |  | 2023-08-28 |  | BOOM
Q01541 | Q140B_Q01541OD_DESASATRIA | Sarawak |  | Decomm |  | 2023Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-04-17 |  |  | 2023-07-17 |  | Closed | 2023-07-21 | 2023-07-28 | CD//John | 2023-07-23 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230613-0009/Celcom Digi_RAN-Trintel-TSS DECOMM-Sarawak-20231130 | DU00002007485 |  |  |  |  | 2023-08-18 |  | RAPOLE
P00068 | P034A_P00068OD_MAKMANDIN | Northern |  | Decomm |  | 2023Q3 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-05-07 |  |  | 2023-06-09 |  | Closed | 2023-07-28 | 2023-08-08 | CD//Quah | 2023-08-02 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V2 | DU00002007486 |  |  |  |  | 2023-11-09 |  | BOOM
S01153 | S093D_S01153OD_CITYAPARTMENT | Sabah |  | Site Out (Decomm) | Decomm->TBD->On hold->Site out->Site Out (Decomm) | 2023Q3 | AD | YPTT | 15.3 Decomm Done without TSSR | [6 empty] | To be Submitted |  |  | CD//Ray Amos |  | SQ202506160238 - YPTT | DU00002007487 |  |  |  |  | 2025-06-26 |  | LAMP_POLE
P00348 | P033B_P00348OD_MALAYAWATA | Northern |  | Decomm |  | 2023Q3 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-05-25 |  |  |  | 2023-06-22 |  | 2023-06-23 | 2023-08-08 | CD//Shamsul | 2023-07-04 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V2 | DU00002007488 |  |  |  |  | 2023-08-17 |  | AESTHETIC MONOPOLE
P00056 | P034A_P00056OD_BGAJAM | Northern | 4039K | Swap |  | 2023Q3 | YZ | CCSMY | 4.6 TSSR Approved |  | 2023-05-24 | 2023-06-15 |  | 2023-06-16 |  | Closed | 2023-06-19 | 2023-06-27 | CD//Heng | 2023-06-26 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0016 | DU00002007489 |  |  | 2023-06-27 | 2023-06-25 |  | Pole | TRIPOD | 8m | Add R8852E S9000 x3 + A9732 M1821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 123
B01237 | B058B_B01237OD_BT3JLNKAPAR | Central | 1032K | Swap |  | 2023Q3 | HQ 6 | Datasco | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-10 |  | 2023-05-12 |  | Closed | 2023-05-17 | 2023-06-03 | CD//Norhaliza | 2023-05-22 | CelcomDigi_RANMW_Datasco_TSS_Central_20230505_0002 | DU00002007490 |  |  | 2023-07-25 | 2023-07-22 |  | Lampole | LAMP_POLE | 23 | Add R9264H M901821 x3 + R9264M M1821 x3 + R8862A S2601 x6,Dismantle Celcom all RRU&BBU |  | 123
S00608 | S093G_S00608OD_SABAHPORT | Sabah |  | Decomm |  | 2023Q2 | MS | Datasco | 4.6 TSSR Approved |  | 2023-05-18 |  |  |  | 2023-05-22 |  | 2023-06-14 | 2023-07-27 | CD//Mohidi Jaan | 2023-06-14 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007 | DU00002007491 |  |  |  |  | 2023-09-19 |  | BOOM
P00158 | P033B_P00158OD_ACMPRAI | Northern |  | Decomm |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-05-09 |  |  |  | 2023-06-14 |  | 2023-06-15 | 2023-10-27 | CD//Quah | 2023-07-06 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240529-0109 | DU00002007492 |  | Need Include xC Cabinet |  |  | 2023-09-25 |  | BOOM
S00665 | S093G_S00665OD_TMNINDAHPERMAI | Sabah |  | Decomm |  | 2023Q2 | MS | Datasco | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-26 |  |  | 2023-05-15 |  | 2023-06-20 | 2023-08-30 | CD//Mohidi Jaan | 2023-06-21 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007 | DU00002007493 |  |  |  |  | 2023-09-26 | Monople Tree | TOWER | 45
Q01606 | QS50213_4_1-SKTAMIN | Sarawak | 9007K | Swap |  | 2023Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-04-18 | 2023-05-08 |  | 2023-05-13 |  | Closed | 2023-05-20 | 2023-07-29 | CD//John | 2023-05-20 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230419-0004 | DU00002007494 |  |  | 2023-10-16 | 2023-09-30 |  | Tower | TOWER | 30 | Add R8892E M1821 x1,Dismantle R8862A S1800(B6A) x1
P00054 | P033C_P00054OD_BKTMINYAKIND2 | Northern |  | Decomm |  | 2023Q3 | MH | GTSB | 4.6 TSSR Approved |  | 2023-06-02 |  |  |  | 2023-06-07 |  | 2023-06-08 | 2023-08-10 | CD//Shamsul | 2023-06-21 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20231226-0079/Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1 | DU00002007495 |  |  |  |  | 2023-08-04 |  | TOWER
B02821 | B058B_B02821OD_KLGTMNINDUSTRIOFFJLNSGPULOH | Central | 1057K | Swap |  | 2023Q3 | YZ | CCSMY | 4.6 TSSR Approved |  | 2023-05-15 | 2023-05-29 |  | 2023-05-31 |  | Closed | 2023-06-01 | 2023-06-12 | CD//Sapian | 2023-06-12 | CelcomDigi_RANMW_CCSMY_TSS_Central_20230508_0001 | DU00002007496 |  |  | 2023-08-14 | 2023-08-04 |  | Lampole | LAMP_POLE | 24m | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
P00570 | P033B_P00570OD_KGTANJUNGPUTUS | Northern |  | Decomm |  | 2023Q3 | SM | YPTT | 4.6 TSSR Approved |  | 2023-06-19 |  |  |  | 2023-07-04 |  | 2023-07-07 |  | CD//Shamsul | 2023-07-12 | Celcom Digi_RAN-YPTT-TSS-Northern-20230609-0018 | DU00002007497 |  | Please include Zoom in Photo of ODF in another cabinet |  |  | 2023-08-30 |  | TOWER
S01742 | Kg Sinarut | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q2 | MS | Datasco | 14.2 Drop (Done Survey) |  | 2023-05-18 |  |  |  |  | To be Submitted |  |  | CD//Ray Amos |  | N/A | DU00002007498 | [6 empty] | TOWER
Q00283 | Q118A_Q00283OD_TMBTUEX | Sarawak | 9022K | Swap |  | 2023Q3 | HQ 2 | AllStar | 4.6 TSSR Approved |  | 2023-04-18 | 2023-05-02 |  | 2023-05-08 |  | Closed | 2023-05-11 | 2023-05-11 | CD//John | 2023-05-11 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230403-0003 | DU00002007499 |  |  | 2023-11-09 | 2023-10-17 |  | Unipole | BOOM | 7m | Add R8852E S9000 x3 + R8894E M1821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
Q01123 | Q144A_Q01123OD_T3_KEMKELABU | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007500 | [6 empty] | TOWER
B02617 | B058C_B02617OD_JLNSERUNAISMKRAJAMAHADI | Central | 1053K | Swap |  | 2023Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-05-19 | 2023-05-26 |  | 2023-05-28 |  | Closed | 2023-05-30 | 2023-06-20 | CD//Sapian | 2023-06-20 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230523_0020 | DU00002007501 |  |  | 2023-06-27 | 2023-06-23 |  | Lampole | LAMP_POLE | 24 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
Q01881 | Q140C_Q01881OD_LRGSUKUN2 | Sarawak |  | Decomm |  | 2023Q2 | ZB | AllStar | 4.6 TSSR Approved |  | 2023-04-25 | 2023-06-26 |  | 2023-07-14 |  | Closed | 2023-07-24 | 2023-08-08 | CD//John | 2023-07-28 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230613-0007/0612Sarawak-AllStar-BOQ Template (template).xls | DU00002007502 |  | 20230801: idu label missing, ne & fe info are missing, ne & fe photo are missing |  |  | 2023-08-10 |  | RAPOLE | 30
P00027 | P034A_P00027OD_TAMANSELAT | Northern |  | Decomm |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-06-15 |  |  |  | 2023-06-22 |  | 2023-06-22 | 2023-09-06 | CD//Shamsul | 2023-07-03 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1 | DU00002007503 |  |  |  |  | 2023-07-19 |  | BOOM
B01772 | B058C_B01772OD_BDRBOTANICKLG2 | Central |  | Decomm |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-04-17 | 2023-06-26 |  | 2023-06-11 | 2024-10-18 | Closed | 2023-06-27 | 2023-09-19 | CD//Norhaliza | 2023-09-15 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230626_decom reraise | DU00002007504 |  |  |  |  | 2023-07-09 | Minimast | BOOM | 10
B02535 | B058D_B02535OD_KGTLKNIPAHPULAUINDAH | Central |  | Decomm |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-15 |  |  | 2023-05-28 | 2023-08-16 | Closed | 2023-05-31 | 2023-09-01 | CD//Norhaliza | 2023-06-09 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002007505 |  |  |  |  | 2023-09-30 |  | MONOPOLE
B00717 | B058D_B00717OD_TMNIDAMAN | Central |  | Decomm |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-04-17 |  |  |  | 2023-07-21 |  | 2023-07-22 | 2024-09-26 | CD//Sapian | 2023-08-14 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230626_decom reraise | DU00002007506 |  |  |  |  | 2023-08-15 |  | MINARATE
Q01109 | Q140C_Q01109OD_JLNBKT5 | Sarawak |  | Decomm |  | 2023Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-07-10 |  |  |  | 2023-07-26 |  | 2023-07-26 | 2023-08-06 | CD//John | 2023-07-27 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230613-0009/Celcom Digi_RAN-Trintel-TSS DECOMM-Sarawak-20231130 | DU00002007507 |  |  |  |  | 2023-11-21 |  | MONOPOLE
Q00259 | Q144A_Q00259OD_TATAU | Sarawak |  | Decomm |  | 2023Q3 | BY | Magicell | 4.6 TSSR Approved |  | 2023-04-27 | 2023-06-26 |  |  | 2023-05-31 |  | 2023-06-02 | 2023-07-28 | CD//John | 2023-06-11 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230613-0014/Celcom Digi_RAN-Magicell-TSS DECOMM-Sarawak-20230818 | DU00002007508 |  |  |  |  | 2023-08-10 | Tower | GUYED MAST | 46m
Q01689 | Q140C_Q01689OD_CB_SGSADIT | Sarawak |  | Decomm |  | 2023Q2 | SH | Datasco | 4.6 TSSR Approved |  | 2023-06-12 | 2023-06-26 |  | 2023-06-13 |  | Closed | 2023-06-14 | 2024-05-14 | CD//John | 2023-07-04 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009/Celcom Digi_RAN-Datasco-TSS DECOMM MW-Sarawak-20240419 | DU00002007509 |  |  |  |  | 2023-07-28 | Tower | TOWER | 44
S00466 | S109A_S00466OD_CB_KGGUAKON | Sabah |  | Decomm |  | 2023Q2 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-02 | 2023-06-26 |  |  | 2023-06-12 |  | 2023-06-15 | 2024-05-14 | CD//Ray Amos | 2023-06-16 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0010/Celcom Digi_RAN-Futong-TSS DECOMM MW-Sabah-20240419 | DU00002007510 |  | 2023-07-06 missing tx photos and info |  |  | 2023-09-04 | Tower | TOWER | 60
B00794 | B059A_B00794OD_SGKELAMBU | Central |  | Decomm |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-03 | 2023-06-26 |  |  | 2024-02-22 |  | 2023-06-06 | 2024-05-29 | CD//Sapian | 2023-06-09 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise / CelcomDigi_TX_GTSB_TSS_Decom_Central_20230714 | DU00002007511 |  |  |  |  | 2023-07-16 | Tower | TOWER | 46
S01669 | S093D_S01669OD_SMAINANAM | Sabah |  | Decomm |  | 2023Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2023-04-20 |  |  |  | 2023-06-23 |  | 2023-06-15 | 2023-07-21 | CD//Ray Amos | 2023-06-16 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230608-0008/0612Sabah-GTSB-BOQ Template (template) | DU00002007512 |  |  |  |  | 2023-09-19 | Lampole | LAMP_POLE | 32
B02007 | B058E_B02007OD_KM28.3SKVE4 | Central | 1037K | Swap |  | 2023Q2 | YZ | AllStar | 4.6 TSSR Approved |  | 2023-04-17 | 2023-04-25 |  | 2023-04-27 |  | Closed | 2023-05-06 | 2023-06-06 | CD//Sapian | 2023-05-20 | CelcomDigi_RAN_AllStar_TSS_Central_20230404_0005 / CelcomDigi_RAN_Allstar_TSS_Central_20230721_ClearLoan | DU00002007513 |  |  | 2023-06-17 | 2023-06-08 |  | Tower | RAPOLE | 50 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 3
Q00884 | Q140C_Q00884OD_LRGPAHLAWAN | Sarawak |  | Decomm |  | 2023Q2 | SH | CCSMY | 4.6 TSSR Approved |  | 2023-04-14 |  |  | 2023-06-21 |  | Closed | 2023-06-22 | 2023-08-18 | CD//John | 2023-06-23 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230613-0007 | DU00002007514 |  |  |  |  | 2023-08-01 |  | BOOM
Q00226 | Q144A_Q00226OD_BT12SBW | Sarawak |  | Decomm |  | 2023Q2 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-06-27 |  |  | 2023-07-03 |  | Closed | 2023-07-12 | 2023-09-23 | CD//John | 2023-07-13 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009/0612Sarawak-Datasco-BOQ Template (template) | DU00002007515 |  | 2023-07-18 Missing TX photos and info |  |  | 2024-01-05 |  | TOWER
S01117 | S093A_S01117OD_KGKARMILAN | Sabah |  | Decomm |  | 2023Q2 | AD | Datasco | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-26 |  |  | 2023-05-15 |  | 2023-08-10 | 2023-09-29 | CD//Ray Amos | 2023-08-11 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007/0612Sabah-Datasco-BOQ Template (template) | DU00002007516 |  | 18/8: All tx info are missing |  |  | 2023-09-22 | Lampole | LAMP_POLE | 31
Q02008 | T3E_0303_Durin-Kanaowit Road | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | N/A - no need PR for MOCN Decomm | DU00002007517 | [6 empty] | TOWER
S00043 | S093D_S00043OD_CB_KIANSOMHEIGH | Sabah |  | Decomm |  | 2023Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2023-04-20 | 2023-06-26 |  |  | 2023-06-23 |  | 2023-06-16 | 2023-07-21 | CD//Mohidi Jaan | 2023-06-16 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230608-0008 | DU00002007518 |  |  |  |  | 2023-07-24 | Tower | TOWER | 45
Q01768 | Q118B_Q01768OD_TMNCHINLEE | Sarawak |  | Decomm |  | 2023Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2023-04-17 | 2023-06-26 |  | 2023-06-12 |  | Under Approval | 2023-06-12 | 2023-07-21 | CD//John | 2023-06-12 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230613-0009/Celcom Digi_RAN-Trintel-TSS DECOMM-Sarawak-20231130 | DU00002007519 |  |  |  |  | 2023-12-28 | Monopole | RAPOLE | 31
Q01083 | Q140B_Q01083OD_BOUGENVILLA | Sarawak | 9028K | Swap |  | 2023Q2 | HQ 2 | Trintel | 4.6 TSSR Approved |  | 2023-04-18 | 2023-05-03 |  | 2023-05-08 |  | Closed | 2023-05-11 | 2023-05-11 | CD//John | 2023-05-11 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230403-0003 | DU00002007520 |  |  | 2023-08-12 | 2023-08-03 |  | Minaret | BOOM | 17 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
P00138 | P034A_P00138OD_MAKMANDININD | Northern |  | Decomm |  | 2023Q3 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-05-24 |  |  |  | 2023-07-01 |  | 2023-07-10 | 2023-08-08 | CD//Shamsul | 2023-07-12 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230720-0023/Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1 | DU00002007521 |  |  |  |  | 2023-10-27 |  | MINI STRUCTURE
Q00248 | Q118A_Q00248OD_ABGGALAU | Sarawak | 9021K | Swap |  | 2023Q3 | HQ 1 | AllStar | 4.6 TSSR Approved |  | 2023-04-20 | 2023-05-03 |  | 2023-05-09 |  | Closed | 2023-05-15 | 2023-05-15 | CD//John | 2023-05-15 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230403-0003 | DU00002007522 |  |  | 2023-11-22 | 2023-10-19 |  | Wall mount boom | BOOM | 5 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 1
Q01475 | Q140B_Q01475OD_SGBIDUT | Sarawak |  | Decomm |  | 2023Q2 | ZB | AllStar | 4.6 TSSR Approved |  | 2023-04-19 | 2023-06-26 |  | 2023-07-14 |  | Closed | 2023-07-24 | 2023-08-08 | CD//John | 2023-07-28 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230613-0007/0612Sarawak-AllStar-BOQ Template (template).xls | DU00002007523 |  | 20230801: all tx info & photos are missing |  |  | 2023-08-09 | Monopole | RAPOLE | 30
Q00546 | Q140A_Q00546OD_SGIGAN | Sarawak |  | Decomm |  | 2023Q2 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-06-21 |  |  | 2023-07-03 |  | Rectificating | 2023-07-11 | 2023-09-29 | CD//John | 2023-07-12 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009 | DU00002007524 |  | 2023-07-18 Missing TX photos and info |  |  | 2024-02-13 |  | TOWER
B00641 | B058B_B00641OD_HWSELATKLG | Central | 1028K | Swap |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-05-03 | 2023-06-07 |  | 2023-06-10 |  | Closed | 2023-06-11 | 2023-06-14 | CD//Sapian | 2023-06-14 | CelcomDigi_RAN_Datasco_TSS_20230505_0019 | DU00002007525 |  |  | 2023-07-27 | 2023-07-22 |  | Tower | TOWER | 60m | Add R8852E S9000 x3 + A9732 M1821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 123
P00087 | P033B_P00087OD_NAGASARI | Northern |  | Decomm |  | 2023Q3 | MH | GCI | 4.6 TSSR Approved |  | 2023-06-07 |  |  |  | 2023-06-16 |  | 2023-06-16 | 2023-09-07 | CD//Quah | 2023-07-06 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1 | DU00002007526 |  | No TX Info |  |  | 2023-07-21 |  | BOOM
B02577 | B059A_B02577OD_HAKKABANTING | Central |  | Decomm |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-07 | 2023-06-26 |  |  | 2023-08-02 |  | 2023-06-22 | 2023-08-09 | CD//Sapian | 2023-07-06 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002007527 |  |  |  |  | 2023-06-24 | Pole | POLE | 2
S00722 | S093A_S00722OD_BDRSIERRA | Sabah |  | Decomm |  | 2023Q2 | MS | Datasco | 4.6 TSSR Approved |  | 2023-04-19 | 2023-06-26 |  |  | 2023-05-13 |  | 2023-06-23 | 2023-07-21 | CD//Mohidi Jaan | 2023-06-23 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007 | DU00002007528 |  |  |  |  | 2023-09-15 | Tower | TOWER | 45
P00217 | P033B_P00217IB_SONY | Northern |  | Decomm | Decomm->On Hold->Decomm | 2023Q3 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-05-11 |  |  |  | 2023-07-03 |  | 2023-07-05 | 2023-09-18 | CD//Shamsul | 2023-10-05 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1/Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230726-0024 | DU00002007529 |  | No TX Info, Photo not enough |  |  | 2024-11-13 |  | TOWER
Q00288 | Q118B_Q00288OD_SGNYIGU | Sarawak |  | Decomm |  | 2023Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2023-04-17 | 2023-06-26 |  | 2023-06-17 |  | Closed | 2023-06-19 | 2023-08-08 | CD//John | 2023-06-22 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230613-0009 | DU00002007530 |  | 2023-08-04 : decom RAN only 2023-07-24 Missing TX photos and info |  |  | 2023-08-10 | Tower | TOWER
B00580 | B058C_B00580OD_BDRBOTANICKLG | Central |  | Decomm |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-04-08 | 2023-06-26 |  |  | 2024-05-20 |  | 2023-08-02 | 2023-08-19 | CD//Ali akaram | 2023-08-15 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230626_decom reraise | DU00002007531 |  |  |  |  | 2023-07-09 | Monopole | TOWER | 30
S01499 | S093G_S01499OD_TLKSEPANGGAR | Sabah | 7013K | Swap |  | 2023Q2 | AD | Datasco | 4.6 TSSR Approved |  | 2023-04-08 |  |  | 2023-05-12 |  | Closed | 2023-05-16 | 2023-05-17 | CD//Mohidi Jaan | 2023-05-16 | Celcom Digi_RAN-Datasco- TSS-Sabah-20230407-0002 | DU00002007532 |  |  | 2023-06-28 | 2023-06-22 |  | Monopole | LAMP_POLE | 30 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
S00837 | S109A_S00837OD_KGLABUAYA | Sabah |  | Decomm |  | 2023Q2 | AD | Futong | 4.6 TSSR Approved |  | 2023-07-06 |  |  |  | 2023-07-07 |  | 2023-07-11 | 2023-07-21 | CD//Ray Amos | 2023-07-12 | Celcom Digi_RAN-Futong-TSS-Sabah-20230608-0010/0612Sabah-Futong-BOQ Template (template) | DU00002007533 |  |  |  |  | 2023-09-30 |  | TOWER
B02836 | B058D_B02836OD_KM51.6SKVETOLLPULAUINDAH | Central | 1058K | Swap |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-16 | 2023-04-27 |  | 2023-05-02 |  | Closed | 2023-05-02 | 2023-06-03 | CD//Tee | 2023-05-12 | CelcomDigi_RAN_Datasco_TSS_Central_20230417_0012 | DU00002007534 |  |  | 2023-09-12 | 2023-09-07 |  | Monople Tree | MONOPOLE | 75 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
Q00673 | Q140B_Q00673OD_SBWJAYACOMM | Sarawak |  | Decomm |  | 2023Q2 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-06-28 |  |  | 2023-06-30 |  | Under Approval | 2023-07-18 | 2023-10-06 | CD//John | 2023-07-18 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009 | DU00002007535 |  | 1. Please delete blank page 2. counter check return whare house item tally with photo and page 1 3. Missing radio 900 4. Missing drawing |  |  | 2024-01-15 |  | TOWER
S01496 | S093A_S01496OD_KGDARAUKK | Sabah |  | Decomm |  | 2023Q2 | MS | Datasco | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-26 |  |  | 2023-05-12 |  | 2023-06-20 | 2023-08-06 | CD//Ray Amos | 2023-06-21 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007/0612Sabah-Datasco-BOQ Template (template) | DU00002007536 |  |  |  |  | 2023-09-27 | Monopole | LAMP_POLE | 32
S00824 | S093G_S00824OD_UMSSPORTCOMPLEX | Sabah | 7008K | Swap |  | 2023Q3 | MS | Datasco | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-28 |  | 2023-05-10 |  | Closed | 2023-05-13 | 2023-05-15 | CD//Ray Amos | 2023-05-15 | Celcom Digi_RAN-Datasco- TSS-Sabah-20230407-0002 | DU00002007537 |  |  | 2023-07-16 | 2023-07-07 |  | BillBoard | BOOM | 25 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 2
B02061 | B058E_B02061OD_BDRPARKLANDKLG | Central |  | Decomm |  | 2023Q2 | CR | AllStar | 4.6 TSSR Approved |  | 2023-04-12 |  |  |  | 2023-07-31 |  | 2023-07-31 | 2023-08-18 | CD//Ali Akaram | 2023-08-15 | CelcomDigi_RAN_AllStar_TSS_Central_20230626_decom reraise | DU00002007538 |  |  |  |  | 2023-09-11 | Pole | UNIPOLE | 3M
Q01933 | Q118B_Q01933OD_KGBARUBTU2 | Sarawak |  | Decomm |  | 2023Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2023-04-17 | 2023-06-26 |  | 2023-06-12 |  | Closed | 2023-06-12 | 2023-07-21 | CD//John | 2023-06-16 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230613-0009/Celcom Digi_RAN-Trintel-TSS DECOMM-Sarawak-20231130 | DU00002007539 |  |  |  |  | 2023-11-27 | Monopole | RAPOLE | 33
S00724 | S093A_S00724OD_KGRAMPAYAN | Sabah |  | Decomm |  | 2023Q2 | MS | Datasco | 4.6 TSSR Approved |  | 2023-04-19 | 2023-06-26 |  |  | 2023-05-13 |  | 2023-08-02 | 2023-09-29 | CD//Ray Amos | 2023-08-10 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007 | DU00002007540 |  | 2023-07-21 missing tx photos and info |  |  | 2023-09-18 | Tower | TOWER | 48
B00440 | B058D_B00440OD_KGPENDAMARKLG | Central |  | Decomm |  | 2023Q2 | SS | AllStar | 4.6 TSSR Approved |  | 2023-11-22 |  |  |  | 2023-11-30 |  | 2023-12-27 | 2024-09-26 | CD//Ali akaram | 2024-01-08 | CelcomDigi_RAN_AllStar_TSS_Central_20230626_decom reraise | DU00002007541 |  |  |  |  | 2023-11-24 | Tower | TOWER
P00053 | P033B_P00053OD_TMSBJ | Northern |  | Decomm |  | 2023Q3 | MH | YPTT | 4.6 TSSR Approved |  | 2023-05-22 |  |  |  | 2023-06-17 |  | 2023-06-19 | 2023-09-25 | CD//Shamsul | 2023-07-04 | Celcom Digi_RAN-YPTT-TSS Decomm-Northern-20230810-0027/Celcom Digi_RAN-YPTT-TSS-Northern-20230609-0018 | DU00002007542 |  | 11082023: No AggA Cisco ASR 9010 Router picture 27072023: Need Info&Photo Celcom Cabinet Colo |  |  | 2023-10-02 |  | TOWER
S00041 | S093A_S00041OD_KGSINOMPURO | Sabah |  | Decomm |  | 2023Q2 | MS | Datasco | 4.6 TSSR Approved |  | 2023-08-30 |  |  |  | 2023-09-08 |  | 2023-09-11 | 2023-09-29 | CD//Ray Amos | 2023-09-13 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007 | DU00002007543 |  |  |  |  | 2023-11-18 |  | TOWER
Q00633 | Q144A_Q00633OD_PKNTATAU | Sarawak |  | Decomm |  | 2023Q3 | BY | Magicell | 4.6 TSSR Approved |  | 2023-04-26 | 2023-06-26 |  | 2023-04-28 |  | Rectificating | 2023-05-30 | 2023-07-21 | CD//John | 2023-06-07 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230613-0014 | DU00002007544 |  |  |  |  | 2023-08-17 | Tower | TOWER | 62M
Q01027 | Q140A_Q01027OD_JLNGETAH | Sarawak |  | Decomm |  | 2023Q2 | SH | Datasco | 4.6 TSSR Approved |  | 2023-04-27 |  |  | 2023-07-25 |  | Closed | 2023-07-25 | 2023-08-08 | CD//John | 2023-07-25 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009/0612Sarawak-Datasco-BOQ Template (template) | DU00002007545 |  | 3/8: fe info & photos missing |  |  | 2023-10-16 |  | RAMO
Q01270 | Q140C_Q01270OD_JLNTAZA | Sarawak | 9037K | Swap |  | 2023Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-06-20 | 2023-06-28 |  | 2023-07-04 |  | Closed | 2023-07-06 | 2023-07-08 | CD//John | 2023-07-08 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230626 | DU00002007546 |  |  | 2023-11-04 | 2023-10-23 |  | Pole | RAPOLE | 15 | Add R8852E S9000x3 + R8894E M1821x3,Dismantle Celcom all RRU&BBU
P00274 | P034A_P00274OD_JLNSIRAM | Northern |  | Decomm |  | 2023Q3 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-05-19 |  |  |  | 2023-08-02 |  | 2023-08-01 | 2023-08-30 | CD//Rohizam | 2023-08-15 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V2 | DU00002007547 |  |  |  |  | 2023-07-25 |  | TOWER
Q00238 | Q140C_Q00238OD_JLNCAUSEWAY | Sarawak | 9020K | Swap |  | 2023Q2 | MA | Datasco | 4.6 TSSR Approved |  | 2023-04-16 | 2023-05-02 |  | 2023-05-05 |  | Closed | 2023-05-06 | 2023-05-08 | CD//John | 2023-05-08 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002007548 |  |  | 2023-08-18 | 2023-08-02 |  | H-bracket pole | BOOM |  | Add R8852E S9000 x2 + R8894E M1821 x2 + R8862A S2601 x2,Dismantle Celcom all RRU&BBU | 0
S00714 | S093G_S00714OD_UITMSEPANGGAR | Sabah | 7007K | Swap |  | 2023Q2 | MS | Datasco | 4.6 TSSR Approved |  | 2023-05-25 | 2023-06-10 |  | 2023-06-11 |  | Closed | 2023-06-12 | 2023-06-13 | CD//Ray Amos | 2023-06-13 | Celcom Digi_RAN-Datasco- TSS-Sabah-20230407-0002 | DU00002007549 |  |  | 2023-06-28 | 2023-06-21 |  | Lampole | MONOPOLE | 26m | Add R9264H M901821 x2,Dismantle Celcom all RRU&BBU | 0
Q00216 | Q140C_Q00216OD_WISMASANYAN | Sarawak |  | Decomm |  | 2023Q2 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-05-12 |  |  | 2023-07-13 |  | Under Approval | 2023-07-13 | 2024-01-18 | CD//John | 2023-07-13 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009/0612Sarawak-Datasco-BOQ Template (template) | DU00002007550 |  |  |  |  | 2024-08-22 |  | BOOM
B01069 | B058D_B01069OD_PULAUINDAHHWY | Central |  | Decomm |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-06-21 |  |  |  | 2023-08-02 |  | 2023-07-25 | 2023-08-19 | CD//Sapian | 2023-08-04 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002007551 |  | Please include link CT09421 & CT07743 in TSSR. |  |  | 2023-07-11 |  | TOWER
Q02083 | Q118B_Q02083OD_T3_ULUSEGAN2 | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007552 | [6 empty] | TOWER
Q01259 | Q140C_Q01259OD_JLNLANANGBARAT | Sarawak |  | Decomm |  | 2023Q2 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-06-24 |  |  | 2023-08-10 |  | Rectificating | 2023-08-10 | 2024-06-27 | CD//John | 2023-08-11 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009/0612Sarawak-Datasco-BOQ Template (template) | DU00002007553 |  |  |  |  | 2023-08-16 |  | LAMP_POLE
Q01283 | Q140C_Q01283OD_JLNDELTA | Sarawak |  | Decomm |  | 2023Q2 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-07-19 |  |  |  | 2023-09-19 |  | 2023-08-02 | 2023-08-08 | CD//John | 2023-08-02 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230613-0009/0612Sarawak-Datasco-BOQ Template (template) | DU00002007554 |  | 20230802: no FE info |  |  | 2023-08-10 |  | LAMP_POLE
S01494 | S093A_S01494OD_JLNGUDON | Sabah |  | Decomm |  | 2023Q2 | MS | Datasco | 4.6 TSSR Approved |  | 2023-06-09 | 2023-06-26 |  |  | 2023-06-01 |  | 2023-08-09 | 2023-09-29 | CD//Ray Amos | 2023-06-28 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230608-0007/0612Sabah-Datasco-BOQ Template (template) | DU00002007555 |  | 2023-07-20 missing tx photos and info |  |  | 2023-10-19 | Lampole | LAMP_POLE | 30
S00796 | S093G_S00796OD_UMSFAKULTIBUILDING | Sabah |  | Decomm |  | 2023Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-04-18 | 2023-06-26 |  |  | 2023-06-30 |  | 2023-06-09 | 2023-07-27 | CD//Mohidi Jaan | 2023-06-09 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230608-0007 | DU00002007556 |  |  |  |  | 2023-07-28 | BillBoard | BOOM | 25
B01039 | B058E_B01039OD_BDRSRIEHSAN | Central |  | Decomm |  | 2023Q2 | SS | GTSB | 4.6 TSSR Approved |  | 2023-04-16 | 2023-06-26 |  |  | 2024-05-08 |  | 2023-06-15 | 2023-11-15 | CD//Ali akaram | 2023-07-05 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002007557 |  |  |  |  | 2023-07-12 |  | TOWER | 39
B02670 | B058E_B02670OD_BDRMAHKOTABNTG | Central | 1054K | Swap |  | 2023Q2 | IE | GTSB | 4.6 TSSR Approved |  | 2023-04-07 | 2023-04-12 |  | 2023-04-18 |  | Closed | 2023-04-29 | 2023-06-08 | CD//Nik Ashraf | 2023-05-26 | CelcomDigi_RAN_GTSB_Central_20230407_0012 | DU00002007558 |  |  | 2023-06-08 | 2023-06-06 |  | Monopole | LAMP_POLE | 30 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
S00404 | S093G_S00404OD_ALAMMESRA | Sabah |  | Decomm |  | 2023Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-04-18 | 2023-06-26 |  |  | 2023-06-30 |  | 2023-06-09 | 2023-07-21 | CD//Mohidi Jaan | 2023-06-10 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230608-0007 | DU00002007559 |  |  |  |  | 2023-10-02 | Unipole | TRIPOD | 13
Q01626 | QS50243_4_1-RHGEMAT | Sarawak | 9009K | Swap |  | 2023Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2023-04-12 | 2023-05-12 |  | 2023-05-16 |  | Closed | 2023-05-18 | 2023-05-19 | CD//John | 2023-05-19 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230403-0003 | DU00002007560 |  |  | 2023-11-11 | 2023-10-11 |  | Tower | TOWER | 40M | Add R9264H M901821 x2 + R9264M M1821 x1,Dismantle R8862A S1800(B6A) x1
Q02003 | T3E_0304_Rumah Lambai Rumah Minda Ladang Mapai | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | N/A - no need PR for MOCN Decomm | DU00002007561 | [6 empty] | TOWER
Q02005 | T3E_0312_Tg. Penasu Batu Burak | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | N/A - no need PR for MOCN Decomm | DU00002007562 | [6 empty] | TOWER
Q02004 | T3E_0306_Nanga Dap Rumah Jelan Rumah Michael Ru | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | N/A - no need PR for MOCN Decomm | DU00002007563 | [6 empty] | TOWER
4191A | Taman Indrawasih 2 | Northern |  | Modernization |  | 2023Q3 | MH | GTSB | 4.6 TSSR Approved |  | 2023-05-01 | 2023-05-03 |  | 2023-05-06 |  | Closed | 2023-05-09 | 2023-05-11 | CD//Shamsul | 2023-05-11 | Celcom Digi_RAN-GTSB-TSS-Northern-20230502-0012 | DU00002007564 |  |  | 2023-06-14 | 2023-06-13 |  |  | 30m Monopole | 6 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882 S1800B(B6B) x3+R8881 S2100 x3
4187B | Medan Kikik | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-11 | 2023-05-15 |  | 2023-05-17 |  | Closed | 2023-05-22 | 2023-06-27 | E//Hazida | 2023-06-27 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0015 | DU00002007565 |  |  | 2023-07-15 | 2023-07-06 |  | Minimast | Guyed Mast | 21 | Add R8852E S9000 x3 + A9732 M1821 x3 + R8862A S2601 x3,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 | 123
4186B | Jln Assumption | Northern |  | Modernization |  | 2023Q3 | MH | YPTT | 4.6 TSSR Approved |  | 2023-04-29 | 2023-05-02 |  | 2023-05-05 |  | Rectificating | 2023-05-05 | 2023-06-17 | E//Hazida | 2023-06-15 | Celcom Digi_RAN-YPTT-TSS-Northern-20230505-0007 | DU00002007566 |  |  | 2023-06-15 | 2023-06-15 |  | Unipole | Watertank Structure | 4 | Add R9264M M1821 x3,Dismantle R9224E M1821(AAB) x3 | 0 | 0
4187D | Vnion Bk Minyak (REL) | Northern |  | Modernization |  | 2023Q3 | MH | GTSB | 4.6 TSSR Approved |  | 2023-05-11 | 2023-05-13 |  | 2023-05-17 |  | Closed | 2023-05-22 | 2023-06-22 | E//Hazida | 2023-06-22 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0016 | DU00002007567 |  |  | 2023-06-15 | 2023-06-15 |  | Monopole | 30m Monopole | 30 | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
4188B | Tingkat Perusahaan 2 | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-20 | 2023-06-05 |  | 2023-06-08 |  | Closed | 2023-06-09 | 2023-06-14 | CD//Affendi | 2023-06-14 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0016 | DU00002007568 |  |  | 2023-07-13 | 2023-07-07 |  | Monopole | Land site | 30m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
7310H | IMacro KK MSC | Sabah |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007569 | [6 empty] | Rooftop
9281B | Rantau Panjang Sibu | Sarawak |  | Modernization |  | 2023Q2 | SH | CCSMY | 4.6 TSSR Approved |  | 2023-04-06 | 2023-05-10 |  | 2023-05-12 |  | Closed | 2023-05-17 | 2023-05-17 | CD//John | 2023-05-17 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230403-0003 | DU00002007570 |  |  | 2023-06-29 | 2023-06-21 |  | Pole | 30m Rapole | 30 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
9720B | Jalan Sentosa Timur | Sarawak |  | Modernization |  | 2023Q2 | BY | AllStar | 4.6 TSSR Approved |  | 2023-04-10 | 2023-04-12 |  | 2023-04-14 |  | Closed | 2023-04-18 | 2023-05-10 | CD//John | 2023-04-19 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230403-0003 | DU00002007571 |  |  | 2023-06-10 | 2023-06-08 |  |  | Land site | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
7647A | Kg Bambangan | Sabah |  | Modernization |  | 2023Q3 | HQ 5 | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-06 |  | 2023-04-19 |  | Closed | 2023-04-23 | 2023-05-03 | CD//Ray Amos | 2023-05-03 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002007572 |  |  | 2023-07-07 | 2023-07-04 |  | Monople Tree | 45m 4 Legged Tower | 46 | Add R9264H M901821 x1 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x4 | 234
4557B | Chemor Tanah Hitam RCC | Northern |  | Modernization |  | 2023Q2 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-06 | 2023-05-09 |  | 2023-05-10 |  | Closed | 2023-05-11 | 2023-06-08 | E//Hazida | 2023-06-09 | Celcom Digi_RAN-GCI-TSS-Northern-20230505-0012 | DU00002007573 |  |  | 2023-06-16 | 2023-06-14 |  | Tower | Tower | 60m | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x3+R9224E M1821(AAB) x2 | 13
9595C | Kuala Sangan 2 | Sarawak |  | Modernization |  | 2023Q3 | SH | Magicell | 4.6 TSSR Approved |  | 2023-04-26 | 2023-04-28 |  | 2023-05-03 |  | Closed | 2023-05-05 | 2023-05-07 | CD//John | 2023-05-05 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230426-0003 | DU00002007574 |  |  | 2023-06-10 | 2023-06-08 |  | Tower | Tower | 46m | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x3 |  | 1
7043A | University Utama | Sabah |  | Modernization |  | 2023Q2 | HQ 6 | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-12 |  | 2023-04-15 |  | Rectificating | 2023-04-25 | 2023-05-10 | CD//Ray Amos | 2023-05-10 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002007575 |  |  | 2023-06-10 | 2023-06-08 |  | Monopole | Land site | 30m | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle R8862A S1800(B6A) x2+R8862A S2100(A6A) x2+R8894E M1821(A8A) x2 | 0 | 3
A00581 | A040C_A00581OD_WISMAKPK | Northern |  | Decomm |  | 2023Q2 | MH | GCI | 4.6 TSSR Approved |  | 2023-05-02 |  |  |  | 2023-07-12 |  | 2023-06-13 | 2023-08-30 | CD//Affendi | 2023-06-21 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002007576 |  |  |  |  | 2023-07-06 |  | BOOM
4817A | Megamall Prai | Northern |  | Modernization |  | 2023Q3 | WP | CCSMY | 4.6 TSSR Approved |  | 2023-05-13 | 2023-06-08 |  | 2023-06-12 |  | Closed | 2023-06-23 | 2023-06-28 | E//Hazida | 2023-06-28 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0016 | DU00002007577 |  |  | 2023-07-17 | 2023-07-13 |  | Wall mount boom | In-building system |  | Add R8862A S1800 x2 + R8862A S2100 x2,Dismantle R8882-GUL1812 x1
4527D | Klebang Ria 2 (REL) | Northern |  | Modernization |  | 2023Q2 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-04-18 | 2023-05-02 |  | 2023-05-03 |  | Closed | 2023-05-04 | 2023-05-18 | CD//Shamsul | 2023-05-10 | Celcom Digi_RAN-GCI-TSS-Northern-20230425-0009 | DU00002007578 |  |  | 2023-06-01 | 2023-05-31 |  | Minaret | Land site | 30m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
9149A | Jalan Teku Sibu | Sarawak |  | Modernization |  | 2023Q2 | SH | Datasco | 4.6 TSSR Approved |  | 2023-04-21 | 2023-05-05 |  | 2023-05-08 |  | Closed | 2023-05-09 | 2023-05-09 | CD//John | 2023-05-09 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002007579 |  |  | 2023-06-30 | 2023-06-14 |  |  | 3m RT (Minimast) | 2 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2600 x1,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8854D S2100(A4A) x3 |  | 3
B00198 | B058E_B00198OD_PR_LBHNDAGANG | Central |  | Decomm |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-07 |  |  |  | 2023-06-22 |  | 2023-06-22 | 2023-08-19 | CD//Sapian | 2023-07-06 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise / CelcomDigi_TX_GTSB_TSS_Decom_Central_20230714 | DU00002007580 |  |  |  |  | 2023-06-26 | Tower | TOWER | 70m
9014Z | RH JARAU | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | N/A - no need PR for MOCN Decomm | DU00002007581 | [6 empty] | Land site
9619B | Lorong Ding | Sarawak |  | Modernization |  | 2023Q2 | MA | Trintel | 4.6 TSSR Approved |  | 2023-04-11 | 2023-04-25 |  | 2023-04-26 |  | Rectificating | 2023-05-02 | 2023-05-10 | CD//John | 2023-05-02 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230403-0003 | DU00002007582 |  |  | 2023-05-27 | 2023-05-24 |  | Lampole | 30m Rapole | 30 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
7282C | Pusat Pentadbiran Negeri Sabah | Sabah |  | Remote MOCN |  | 2023Q3 | AD | AllStar | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-10 |  | 2023-05-19 |  | Rectificating | 2023-06-12 | 2023-06-19 | E//Hannah | 2023-06-19 | Celcom Digi_RAN-Allstar-TSS-Sabah-20230626 | DU00002007583 | [6 empty] | Land site |  | Reuse existing RRU
9360B | Kuala Tatau | Sarawak |  | Decomm | Decomm->On Hold->Decomm->On Hold->Decomm | 2023Q3 | BY | Magicell | 4.6 TSSR Approved |  | 2023-04-18 | 2023-06-26 |  | 2023-04-19 |  | Closed | 2023-05-30 | 2024-02-15 | E//Hannah | 2023-07-20 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230613-0014/Celcom Digi_RAN-Magicell-TSS DECOMM-Sarawak-20230818 | DU00002007584 |  | 2023-07-24 Missing TX photos and info |  |  | 2025-10-16 | Tower | 45m 3 Legged Tower | 76m
7300A7 | pBTS Suria Inanam | Sabah |  | Modernization |  | 2023Q3 | HQ 8 | YPTT | 4.6 TSSR Approved |  | 2023-04-08 | 2023-05-09 |  | 2023-04-14 |  | Closed | 2023-04-18 | 2023-05-10 | CD//Mohidi Jaan | 2023-05-10 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230407-0002 | DU00002007585 |  |  | 2023-06-17 | 2023-06-08 |  | Tower | 24m PBTS | 25m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 | 0
A00171 | A040C_A00171OD_KLEBANGINDUSTRI | Northern |  | Decomm |  | 2023Q2 | MH | GTSB | 4.6 TSSR Approved |  | 2023-04-12 | 2023-06-26 |  |  | 2023-06-17 |  | 2023-06-20 | 2023-09-07 | CD//Affendi | 2023-06-20 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1/Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230726-0024 | DU00002007586 |  |  |  |  | 2023-07-21 | Monopole | TOWER | 90
4261C | Jln Perusahaan (REL) | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-11 | 2023-05-19 |  | 2023-05-23 |  | Closed | 2023-05-26 | 2023-06-20 | E//Hazida | 2023-06-20 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0016 | DU00002007587 |  |  | 2023-07-12 | 2023-06-28 |  | Tower | 76M Tower | 80 | Add A9732 M1821 x3,Dismantle R8862A S2600(A4A) x2+R9224E M1821(AAB) x5 | 123
9715B | Sungai Merah Dua | Sarawak |  | Modernization |  | 2023Q2 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-04-06 | 2023-04-12 |  | 2023-04-17 |  | Rectificating | 2023-04-20 | 2023-05-10 | CD//John | 2023-04-28 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230403-0003 | DU00002007588 |  |  | 2023-06-15 | 2023-06-12 |  | Monopole | Land site | 31 | Add R9264H M901821 x4,Dismantle R8894E M1821(A8A) x4
7169A | UMWINANAM | Sabah |  | Modernization |  | 2023Q3 | AD | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-25 |  | 2023-04-28 |  | Closed | 2023-05-04 | 2023-05-09 | CD//Jahganathan | 2023-05-09 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002007589 |  |  | 2023-07-06 | 2023-06-24 |  | Pole | 3m Boom (RT) |  | Add A9732 M1821 x3 + R9264M M1821 x1,Dismantle R8882-L268 x2+R9224E M1821(AAB) x6 | 234
7270B | Kg Rampayan | Sabah |  | Modernization |  | 2023Q2 | HQ 6 | Futong | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-17 |  | 2023-04-26 |  | Closed | 2023-04-28 | 2023-05-10 | CD//Ray Amos | 2023-05-10 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002007590 |  |  | 2023-06-12 | 2023-06-08 |  | Monopole | 30m RDS | 30m | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x4 |  | 2
7544B | KKIP Timur | Sabah |  | Modernization |  | 2023Q2 | HQ 1 | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-11 |  | 2023-05-05 |  | Closed | 2023-05-06 | 2023-05-10 | CD//Ray Amos | 2023-05-08 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002007591 |  |  | 2023-06-21 | 2023-06-12 |  | Monopole | 30m Monopole | 32 | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x3+R8894E M1821(A8A) x6 | 123
A01124 | A040C_A01124OD_TMN_BERTUAH_CHEMOR | Northern | 4032K | Swap |  | 2023Q2 | ZA | YPTT | 4.6 TSSR Approved |  | 2023-04-13 | 2023-04-17 |  | 2023-04-14 |  | Closed | 2023-04-27 | 2023-05-02 | CD//Nik Ashraf | 2023-05-02 | Celcom Digi_RAN-YPTT-TSS-Northern-20230414-0005 | DU00002007592 |  |  | 2023-06-22 | 2023-06-22 |  | Monopole | MINARET | 30 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
4407B | Kg Baharu Manjung NS Camp-100Q4 | Northern |  | Modernization |  | 2023Q2 | MH | GTSB | 4.6 TSSR Approved |  | 2023-04-13 | 2023-04-28 |  | 2023-04-29 |  | Closed | 2023-05-02 | 2023-05-17 | CD//Affendi | 2023-05-03 | Celcom Digi_RAN-GTSB-TSS-Northern-20230414-0010 | DU00002007593 |  |  | 2023-05-24 | 2023-05-24 |  | Tower | 60m 3 Legged Tower | 63 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3
7303A | One Borneo Temporary | Sabah |  | Modernization |  | 2023Q3 | AD | AllStar | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-04 |  | 2023-08-04 |  | Closed | 2023-08-08 | 2023-08-08 | CD//Mohidi Jaan | 2023-08-08 | Celcom Digi_RAN-Allstar-TSS-Sabah-20230626 | DU00002007594 |  |  | 2023-08-03 | 2023-08-03 |  |  | In-building system |  | Add R8862A S1800 x1 + R8862A S2100 x1,Dismantle R8882-GUL1812 x1
7087B | UMS MP | Sabah |  | Modernization |  | 2023Q3 | HQ 5 | GTSB | 4.6 TSSR Approved |  | 2023-04-05 |  |  | 2023-04-20 |  | Closed | 2023-04-25 | 2023-06-13 | CD//Jahganathan | 2023-06-13 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230407-0002 | DU00002007595 |  |  | 2023-07-13 | 2023-07-06 |  | Monople Tree | 30m Monopole | 58 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
4229D | UITM Permatang Pauh | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-16 |  | 2023-05-22 |  | Closed | 2023-05-24 | 2023-06-11 | E//Hazida | 2023-06-11 | Celcom Digi_RAN-GCI-TSS-Northern-20230502-0011 | DU00002007596 |  |  | 2023-06-21 | 2023-06-17 |  | Monopole | 30M Unipole | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
7257A | Inanam Laut(JBA) | Sabah |  | Modernization |  | 2023Q3 | HQ 6 | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-14 |  | 2023-04-26 |  | Closed | 2023-04-28 | 2023-05-05 | CD//Jahganathan | 2023-04-28 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002007597 |  |  | 2023-07-03 | 2023-06-12 |  | Pole | 4m RT (Wall Mounted Pole) | 20 | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3 |  | 2
9374A | Stapang | Sarawak |  | Decomm, MOCN By Other Vendor | Decomm->On Hold->Decomm->On Hold->Decomm | 2023Q2 | ZB | Trintel | 4.6 TSSR Approved |  | 2023-04-19 |  |  |  | 2023-07-27 |  | 2023-07-27 | 2025-05-02 | E//Hannah | 2023-08-02 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230613-0009 | DU00002007598 |  | 22/8: Need to confirm LL EQ |  |  | 2025-12-04 |  | 45m 3 Legged Tower
A00038 | A042D_A00038OD_LDGHUNTLY_RDD | Northern |  | Decomm |  | 2023Q2 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-04-13 |  |  |  | 2023-06-20 |  | 2023-06-21 | 2024-02-29 | CD//Affendi | 2023-06-28 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V2 | DU00002007599 |  | 21/8: Please include all TX equipment Photo |  |  | 2023-07-02 |  | TOWER
9290B | Sungai Bidut 2 | Sarawak |  | Modernization |  | 2023Q2 | HQ 1 | AllStar | 4.6 TSSR Approved |  | 2023-04-05 |  |  | 2023-05-05 |  | Closed | 2023-05-06 | 2023-05-10 | CD//John | 2023-05-10 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230403-0003 | DU00002007600 |  |  | 2023-07-22 | 2023-07-13 |  |  | Tower | 30m | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882 S1800B(B6B) x3
4603C | Desa Rasi | Northern |  | Modernization |  | 2023Q2 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-04-14 | 2023-04-17 |  | 2023-04-17 |  | Closed | 2023-04-19 | 2023-05-12 | CD//Quah | 2023-05-06 | Celcom Digi_RAN-GCI-TSS-Northern-20230417-0006 | DU00002007601 |  |  | 2023-05-23 | 2023-05-20 |  | Tower | Tower | 60m | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
A01164 | A040C_A01164OD_MERUIMPIAN_BUSINESS_CTR | Northern | 4034K | Swap |  | 2023Q2 | ZA | GCI | 4.6 TSSR Approved |  | 2023-04-19 | 2023-04-28 |  | 2023-04-25 |  | Closed | 2023-05-03 | 2023-05-15 | CD//Quah | 2023-05-12 | Celcom Digi_RAN-GCI-TSS-Northern-20230425-0009 | DU00002007602 |  |  | 2023-06-22 | 2023-06-16 |  | Pole | UNIPOLE | 10.3 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
4811A | Carrefour Seberang Jaya Prai | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-25 | 2023-06-13 |  | 2023-06-22 |  | Closed | 2023-06-26 | 2023-06-28 | E//Hazida | 2023-06-28 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0016 | DU00002007603 |  |  | 2023-07-17 | 2023-07-17 |  | Minimast | IBS + RT (Boom) | 11m | Add R9264H M901821 x2 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8894E M1821(A8A) x2 |  | 1
A00044_IBC | A040C_A00044OD_BGNPKNP | Northern | 4058K | Swap |  | 2023Q2 | WP | GCI | 4.6 TSSR Approved |  | 2023-10-04 |  |  | 2024-04-24 |  | Closed | 2023-10-04 | 2023-10-19 | CD//Affendi | 2023-06-11 | Celcom Digi_RAN-GCI-TSS-Northern-20231108-0073 | DU00002007604 |  |  | 2023-09-21 | 2023-06-13 |  |  | BOOM |  | R8852E S9000 x1+R8862A S2100 x1+R8862A S1800 x1,Dismantle all celcom BBU&RRU
7215B | INANAM MTX | Sabah |  | Modernization |  | 2023Q3 | HQ 5 | YPTT | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-25 |  | 2023-04-18 |  | Closed | 2023-05-06 | 2023-05-10 | CD//Mohidi Jaan | 2023-05-08 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230407-0002 | DU00002007605 |  |  | 2023-06-23 | 2023-06-15 |  | Unipole | 3m Bipod (RT) | 10.7m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
B00059 | B058E_B00059OD_PULAUCAREY4 | Central |  | Decomm |  | 2023Q2 | MA | Magicell | 4.6 TSSR Approved |  | 2023-04-12 | 2023-06-26 |  | 2023-04-17 | 2023-05-31 | Closed | 2023-07-20 | 2023-12-05 | CD//Norhaliza | 2023-09-25 | CelcomDigi_RAN_Magicell_TSS_Central_20230626_decom reraise / CelcomDigi_TX_Magicell_TSS_Decom_Central_20230714 | DU00002007606 |  | CD Yusri - TSSR rejected. Currently existing MOCN site already riding on fiber OB. Im already notify ZTE planner to change the topology and scope of work, please refer attached email. CD Siti-In far end (1929B) can rewrite the detail jobscope to be done there in the decomm strategy plan box same as summary “1. to re-engineer TDC LL patching from IDU…..” then only “2. Dismantle Digi Microwave 1441B-1929B”. |  |  | 2023-07-21 | Tower | TOWER | 60M
7059R | T3_0092 - PULAU GAYA | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007607 | [6 empty] | TOWER
7270C | Taman Cerah | Sabah |  | Modernization |  | 2023Q3 | HQ 2 | AllStar | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-14 |  | 2023-04-26 |  | Closed | 2023-04-28 | 2023-05-10 | CD//Ray Amos | 2023-05-10 | Celcom Digi_RAN-Allstar-TSS-Sabah-20230407-0002 | DU00002007608 |  |  | 2023-06-14 | 2023-06-09 |  | Monopole | 30M Monopole | 30m | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8894E M1821(A8A) x3 |  | 1
4345A | Kg Khantan | Northern |  | Modernization |  | 2023Q2 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-13 |  | 2023-04-17 |  | Closed | 2023-04-24 | 2023-05-12 | CD//Affendi | 2023-05-03 | Celcom Digi_RAN-YPTT-TSS-Northern-20230413-0004 | DU00002007609 |  |  | 2023-06-16 | 2023-06-14 |  |  | 60m 4 Legged Tower | 61M | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2,Dismantle R8894E M1821(A8A) x3 | 1
7014C | Kalansanan Village | Sabah |  | Modernization |  | 2023Q3 | HQ 1 | YPTT | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦Limitted space to install AAU,Space is ouccuped by cable and limitted space to install new AAU. | 2023-04-08 | 2023-09-22 |  | 2023-04-17 |  | Closed | 2023-05-05 | 2023-05-08 | CD//Ray Amos | 2023-05-08 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230407-0002 | DU00002007610 | NIC_S3_Change MM to BI_Space constraint_STEALTH |  | 2023-06-21 | 2023-06-15 |  | Lampole | 30m Monopole | 31M | Add R9264H M901821 x3 + R9264M M1821 x3,Dismantle R8854 S2600(A4A) x3+R8894E M1821(A8A) x3+R9224E M1821(AAB) x3 |  | 123
A00707 | A040B_A00707IB_GREENTOWNMALL | Northern |  | Decomm |  | 2023Q2 | SM | YPTT | 4.6 TSSR Approved |  | 2023-05-05 | 2023-06-26 |  |  | 2023-07-25 |  | 2023-07-25 | 2023-08-08 | CD//Shamsul | 2023-08-01 | Celcom Digi_RAN-YPTT-TSS-Northern-20230609-0018/Celcom Digi_RAN-YPTT-TSS Decomm-Northern-20240311-0048 | DU00002007611 |  |  |  |  | 2023-07-21 |  | BOOM
9695B | Kem PLKN Bumimas (REL) | Sarawak |  | Modernization |  | 2023Q2 | HQ 2 | Datasco | 4.6 TSSR Approved |  | 2023-04-13 | 2023-04-29 |  | 2023-05-12 |  | Closed | 2023-05-05 | 2023-05-13 | CD//John | 2023-05-13 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230419-0003 | DU00002007612 |  |  | 2023-06-30 | 2023-06-20 |  | Monopole | 30M Rapole | 30m | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x4 | 0 | 0
7282B | Taman Satria | Sabah |  | Modernization |  | 2023Q2 | HQ 8 | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-13 |  | 2023-04-19 |  | Closed | 2023-04-25 | 2023-05-22 | CD//Jahganathan | 2023-05-22 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002007613 |  |  | 2023-06-20 | 2023-06-12 |  | Monopole | 30m Monopole | 30 | Add A9732 M1821 x3,Dismantle R9224E M1821(AAB) x3 | 123
4267C | Ipoh Parade RT | Northern |  | Modernization |  | 2023Q2 | ZA | GCI | 4.6 TSSR Approved |  | 2023-04-17 | 2023-04-20 |  | 2023-05-02 |  | Closed | 2023-05-06 | 2023-05-25 | E//Hazida | 2023-05-25 | Celcom Digi_RAN-GCI-TSS-Northern-20230418-0007 | DU00002007614 |  |  | 2023-05-26 | 2023-05-24 |  | Pole | 3m Bipod (RT) | S1,S2=3m S3=5m | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8882 S1800B(B6B) x3+R8881 S2100 x3 |  | 1
7132B | PETRONAS-BANDARPUTRA | Sabah |  | Modernization |  | 2023Q2 | AD | Futong | 4.6 TSSR Approved | AAU Cannot Install ¦Pylon site Space constraint | 2023-05-06 | 2023-05-24 |  | 2023-06-11 |  | Closed | 2023-06-12 | 2023-06-13 | E//Hannah | 2023-06-17 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002007615 | NIC_S3_Change MM to BI_Space constraint_STEALTH |  | 2023-09-08 | 2023-07-28 |  | BillBoard | 24m Pylon | 26 | Add R9264M M1821 x1+R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 |  | 2
4490A | Kg Merbau | Northern |  | Modernization |  | 2023Q2 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-27 |  | 2023-04-17 |  | Closed | 2023-05-02 | 2023-05-17 | CD//Affendi | 2023-05-03 | Celcom Digi_RAN-GTSB-TSS-Northern-20230413-0009 | DU00002007616 |  |  | 2023-05-26 | 2023-05-24 |  |  | 3m Boom (RT) | 60 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3
7297A | Kiansam(Celcom) | Sabah |  | Modernization |  | 2023Q3 | HQ 8 | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-12 |  | 2023-04-18 |  | Closed | 2023-04-23 | 2023-06-10 | CD//Jahganathan | 2023-06-08 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002007617 |  |  | 2023-08-07 | 2023-06-27 |  | Tower | 60m 4 Legged Tower | 62m | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
7114H | 99 Speedmart KG BATANGAN | Sabah |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007618 | [6 empty] | Small Cell
4299C | Klebang Restu | Northern |  | Modernization |  | 2023Q2 | MH | GTSB | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-13 |  | 2023-04-19 |  | Closed | 2023-04-20 | 2023-05-12 | CD//Shamsul | 2023-05-03 | Celcom Digi_RAN-GTSB-TSS-Northern-20230413-0009 | DU00002007619 |  |  | 2023-05-20 | 2023-05-20 |  | Minimast | 3m Bipod (RT) | 3 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
7095B | Inanam Baru RT | Sabah |  | Modernization |  | 2023Q3 | HQ 3 | AllStar | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-14 |  | 2023-04-19 |  | Closed | 2023-04-25 | 2023-05-05 | CD//Ray Amos | 2023-05-05 | Celcom Digi_RAN-Allstar-TSS-Sabah-20230407-0002 | DU00002007620 |  |  | 2023-07-07 | 2023-07-03 |  | Unipole | 3m RT (Wall Mounted Pole) | 12m | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x3+R9224E M1821(AAB) x2 | 123
9733B | Lorong Sentosa (REL) | Sarawak |  | Modernization |  | 2023Q2 | BY | Trintel | 4.6 TSSR Approved |  | 2023-04-06 | 2023-05-11 |  | 2023-05-15 |  | Closed | 2023-05-19 | 2023-05-24 | E//Hannah | 2023-05-24 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230403-0003 | DU00002007621 |  |  | 2023-06-21 | 2023-06-19 |  | Pole | TOWER | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
4820C | Tmn Kledang Jaya | Northern |  | Modernization |  | 2023Q2 | ZA | GCI | 4.6 TSSR Approved |  | 2023-04-19 | 2023-04-29 |  | 2023-05-02 |  | Closed | 2023-05-07 | 2023-05-25 | CD//Shamsul | 2023-05-10 | Celcom Digi_RAN-GCI-TSS-Northern-20230425-0009 | DU00002007622 |  |  | 2023-06-06 | 2023-05-31 |  | Unipole | 6m Unipole RT | 5 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3
7113B | Tuaran | Sabah |  | Modernization |  | 2023Q2 | HQ 3 | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-05 |  | 2023-04-13 |  | Closed | 2023-04-26 | 2023-05-10 | CD//Mohidi Jaan | 2023-05-10 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002007623 |  |  | 2023-06-24 | 2023-06-16 |  |  | 30m Monopole | 40m | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
9341B | Kemena Industrial (Shin Yang) | Sarawak |  | Modernization |  | 2023Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2023-04-05 | 2023-04-26 |  | 2023-05-02 |  | Closed | 2023-05-03 | 2023-05-05 | CD//John | 2023-05-03 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230403-0003 | DU00002007624 |  |  | 2023-07-12 | 2023-07-01 |  | Tower | 30m Monopole | 31m | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R8862A S2600(A4A) x2+R8894E M1821(A8A) x2 | 13
4874A | Finisar Indoor | Northern |  | Modernization |  | 2023Q2 | WP | GCI | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-12 |  | 2023-05-22 |  | Closed | 2023-05-25 | 2023-06-11 | E//Nazrul | 2023-06-11 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0015 | DU00002007625 |  |  | 2023-06-14 | 2023-06-13 |  |  | In-building system |  | Add R8862A S1800 x1 + R8862A S2100 x1,Dismantle R8882-GUL1812 x1+R8840-U216 x1
7156B | Seri Indah Apartment | Sabah |  | Modernization |  | 2023Q3 | AD | Futong | 4.6 TSSR Approved |  | 2023-05-18 | 2023-05-06 |  | 2023-05-25 |  | Closed | 2023-05-18 | 2023-05-21 | CD//Ray Amos | 2023-05-22 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002007626 |  |  | 2023-07-11 | 2023-07-08 |  | Lampole | 25m Lamp pole | 25 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8882 S2600(B4A) x1+R8862A S2600(A4A) x1+R8894E M1821(A8A) x5 | 23
9700B | Jalan Au Yoong Selatan | Sarawak |  | Modernization |  | 2023Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-04-05 | 2023-05-04 |  | 2023-05-09 |  | Closed | 2023-05-10 | 2023-05-10 | CD//John | 2023-05-10 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230403-0003 | DU00002007627 |  |  | 2023-06-19 | 2023-06-12 |  | Pole | 30M Rapole | 31m | Add R8894E M1821 x4,Dismantle R8862A S1800(B6A) x4
7224B | Taman View Point (Water Tank) | Sabah |  | Modernization |  | 2023Q3 | HQ 8 | YPTT | 4.6 TSSR Approved |  | 2023-04-06 | 2023-04-25 |  | 2023-04-14 |  | Closed | 2023-05-11 | 2023-05-14 | CD//Mohidi Jaan | 2023-05-14 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230407-0002 | DU00002007628 |  |  | 2023-07-07 | 2023-07-04 |  | Monopole | Tower | 30m | Add A9732 M1821 x1 + R9264M M1821 x2,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 2
A01093 | A040C_A01093OD_KOLEJSAINSKESIHATAN | Northern |  | Decomm |  | 2023Q2 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-06-26 |  |  |  | 2023-06-26 |  | 2023-06-27 | 2023-08-19 | CD//Affendi | 2023-07-03 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V2/Celcom Digi_RAN-CCSMY-TSS Decomm-Northern-20240131-0091 | DU00002007629 |  |  |  |  | 2023-07-22 |  | LAMP_POLE | 32
4981C | Surau Al-Ridzuaniah | Northern |  | Modernization |  | 2023Q2 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-07 | 2023-05-08 |  | 2023-05-10 |  | Closed | 2023-05-11 | 2023-05-25 | CD//Shamsul | 2023-05-15 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0016 | DU00002007630 |  |  | 2023-06-12 | 2023-06-09 |  | Minaret | 22m Minaret | 30 | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8894E M1821(A8A) x3 |  | 1
4545C | Icon City | Northern |  | Modernization |  | 2023Q3 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-06-01 | 2023-06-08 |  | 2023-06-10 |  | Closed | 2023-06-13 | 2023-06-17 | E//Hazida | 2023-06-15 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0009 | DU00002007631 |  |  | 2023-06-26 | 2023-06-25 |  |  | 3m Boom (RT) | 7m | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8894E M1821(A8A) x3 |  | 1
A00744 | A040B_A00744OD_HERITAGEHOTEL_RDD | Northern |  | Decomm |  | 2023Q2 | ZA | GCI | 4.6 TSSR Approved |  | 2023-05-02 |  |  |  | 2023-06-22 |  | 2023-06-23 | 2023-08-08 | CD//Rohizam | 2023-08-02 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002007632 |  |  |  |  | 2023-06-30 |  | SHARING STRC DIGI
4241A | Juru Tower | Northern |  | Modernization |  | 2023Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-10 |  | 2023-05-15 |  | Closed | 2023-05-18 | 2023-05-31 | E//Hazida | 2023-05-31 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0016 | DU00002007633 |  |  | 2023-07-05 | 2023-07-05 |  | Tower | 60m 4 Legged Tower | 37 | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x5 | 123
9364A | Ulu Sg Merah (SACOFA) | Sarawak |  | Modernization |  | 2023Q2 | BY | Datasco | 4.6 TSSR Approved |  | 2023-04-13 | 2023-04-13 |  | 2023-04-15 |  | Closed | 2023-04-19 | 2023-04-25 | CD//John | 2023-04-25 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002007634 |  |  | 2023-07-14 | 2023-07-06 |  | Tower | Tower | 63m | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
7199B | KK Taman Flamingo | Sabah |  | Modernization |  | 2023Q2 | AD | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-06 |  | 2023-04-28 |  | Closed | 2023-05-04 | 2023-05-05 | CD//Ray Amos | 2023-05-05 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002007635 |  |  | 2023-06-16 | 2023-06-12 |  | Monopole | 30m Monopole | 30m | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x3+R9224E M1821(AAB) x2 | 23
4936C | Taman Mak Mandin Jaya | Northern |  | Modernization |  | 2023Q3 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-05-02 | 2023-05-08 |  | 2023-05-11 |  | Closed | 2023-05-13 | 2023-05-25 | CD//Shamsul | 2023-05-20 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0009 | DU00002007636 |  |  | 2023-06-07 | 2023-06-07 |  | A-bracket pole | 3m Boom (RT) | N/A | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
B00269 | B058E_B00269OD_PR_KGKUBANGBERAS | Central | 1403X | Decomm |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-04 | 2023-04-14 |  |  | 2023-08-03 |  | 2023-08-03 | 2025-03-13 | CD//Ali akaram | 2023-08-15 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002007637 |  |  |  |  | 2023-07-14 | Tower | TOWER | 60
B00126 | B061F_B00126OD_KUNDANG | Central |  | Decomm |  | 2023Q2 | CR | MTK | 4.6 TSSR Approved |  | 2023-04-10 | 2023-06-26 |  |  | 2023-07-03 |  | 2023-07-31 | 2023-10-18 | CD//Sapian | 2023-08-15 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002007638 |  |  |  |  | 2023-08-23 | Monopole | TOWER | 45
A00602 | A042D_A00602OD_UIEM | Northern |  | Decomm |  | 2023Q2 | ZA | GCI | 4.6 TSSR Approved |  | 2023-04-14 | 2023-06-26 |  |  | 2023-06-13 |  | 2023-06-14 | 2023-06-28 | CD//Affendi | 2023-06-26 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002007639 |  |  |  |  | 2023-06-26 | Minaret | TOWER | 2
7055A | Inanam Baru | Sabah |  | Modernization |  | 2023Q3 | HQ 5 | YPTT | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-25 |  | 2023-04-15 |  | Closed | 2023-05-11 | 2023-05-14 | CD//Mohidi Jaan | 2023-05-14 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230407-0002 | DU00002007640 |  |  | 2023-07-06 | 2023-07-04 |  | Wall mount boom | 3m Bipod (RT) | S1 6.25, S26.14, S3 6.18 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8882 S2600(B4A) x2+R8894E M1821(A8A) x5 | 23
A00288 | A040C_A00288OD_KLEBANGJAYA | Northern |  | Decomm |  | 2023Q2 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-09-05 |  |  |  | 2023-09-05 |  | 2023-08-16 | 2024-03-06 | CD//Shamsul | 2023-08-20 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V2 | DU00002007641 |  |  |  |  | 2023-10-07 |  | TOWER
B00349 | B058D_B00349OD_WITKLG | Central |  | Decomm |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-04-12 | 2023-06-26 |  | 2023-06-02 | 2023-07-14 | Closed | 2023-07-18 | 2023-08-10 | CD//Sapian | 2023-07-25 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230626_decom reraise | DU00002007642 |  | CD Yusri - please include link id for both IDU as per below. Tq |  |  | 2023-09-13 | Pole | BOOM | 5m
4400B | Kg Raja Hitam RDC | Northern |  | Modernization |  | 2023Q2 | MH | GTSB | 4.6 TSSR Approved |  | 2023-04-14 | 2023-04-25 |  | 2023-04-28 |  | Closed | 2023-04-28 | 2023-05-17 | CD//Quah | 2023-05-09 | Celcom Digi_RAN-GTSB-TSS-Northern-20230417-0011 | DU00002007643 |  |  | 2023-05-24 | 2023-05-23 |  |  | 60m 3 Legged Tower | 60 | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle R8860E-GU908 x3+R8882-GUL1812 x1+R8882 S1800B(B6B) x3+R8840-U216 x3 |  | 2
9015Z | UMA LAHANAN | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | N/A - no need PR for MOCN Decomm | DU00002007644 | [6 empty] | Land site
4212B | Kg Lahar Yooi | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-02 | 2023-05-03 |  | 2023-05-05 |  | Closed | 2023-05-08 | 2023-05-25 | CD//Affendi | 2023-05-09 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230502-0013 | DU00002007645 |  |  | 2023-06-11 | 2023-06-11 |  | Monopole | 30m Monopole | 30 | Add R9264M M1821 x3,Dismantle R8882 S1800(B) x3+R8881 S2100 x3
4194A | Bdr Perai Jaya | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-06-16 | 2023-06-15 |  | 2023-06-16 |  | Closed | 2023-06-17 | 2023-06-28 | E//Hazida | 2023-06-27 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0017 | DU00002007646 |  |  | 2023-09-12 | 2023-09-12 |  | Tower | Tower | 125 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R9224E M1821(AAB) x3 | 123
9147R | SEKUAU | Sarawak |  | Decomm | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2023Q2 | HW | Trintel | 4.6 TSSR Approved |  | 2025-07-29 |  | 2025-08-11 |  | 2025-08-12 |  | 2025-09-10 | 2025-12-08 | E//John | 2025-09-11 | SQ202508190236-Trintel | DU00002007647 |  |  |  |  | 2025-10-01 |  | Land site
A00862 | A040C_A00862OD_MERUPERMAI | Northern |  | Decomm |  | 2023Q2 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-04-09 | 2023-06-26 |  |  | 2023-07-26 |  | 2023-06-20 | 2024-06-19 | CD//Rohizam | 2023-08-15 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230720-0023/Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1 | DU00002007648 |  |  |  |  | 2023-07-18 | Minimast | BOOM | 11
9138R | LDGWOODMAN | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2023Q3 | AD | Magicell | 4.6 TSSR Approved |  | 2025-06-18 |  | 2025-06-30 |  | 2025-07-10 |  | 2025-08-07 | 2025-10-31 | E//John | 2025-08-11 | SQ202506110081-Magicell/SQ202507140221-Magicell | DU00002007649 |  |  |  |  | 2025-09-17 |  | Land site
9395B | Jln Apollo Timur MP | Sarawak |  | Modernization |  | 2023Q2 | BY | Datasco | 4.6 TSSR Approved |  | 2023-04-06 | 2023-04-12 |  | 2023-04-15 |  | Closed | 2023-04-18 | 2023-04-25 | CD//John | 2023-04-25 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002007650 |  |  | 2023-06-30 | 2023-06-26 |  | Monopole | 30m Monopole | 34m | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
9036R | KG. HULU NANGA | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007651 | [6 empty] | Land site
7092B | Kian Yap Industry | Sabah |  | Modernization |  | 2023Q3 | HQ 5 | Futong | 4.6 TSSR Approved |  | 2023-04-12 | 2023-05-08 |  | 2023-04-14 |  | Closed | 2023-04-20 | 2023-05-30 | CD//Jahganathan | 2023-05-29 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002007652 |  |  | 2023-07-06 | 2023-06-12 |  | Unipole | 3m Boom (RT) |  | Add R9264H M901821 x1 + R9264M M1821 x5 + R8862A S2601 x2,Dismantle R9224E M1821(AAB) x4 |  | 12
7059D | Taman Inanam Villa (REL) | Sabah |  | Modernization |  | 2023Q3 | HQ 3 | YPTT | 4.6 TSSR Approved | 22/2: Confirmed by Thien, site already upgrade to 3-Phase Power// Single Phase Power Site. Site require upgrade to 3phase incoming | 2023-04-08 | 2023-04-05 |  | 2023-04-13 |  | Closed | 2023-04-14 | 2023-04-20 | CD//Mohidi Jaan | 2023-04-18 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230407-0002 | DU00002007653 |  |  | 2023-06-22 | 2023-06-15 |  | Monopole | Land site | 30 | Add R9264M M1821 x5,Dismantle R9224E M1821(AAB) x4 |  | 1
4192A | Bagan Ajam | Northern |  | Modernization |  | 2023Q3 | MH | GCI | 4.6 TSSR Approved |  | 2023-04-28 | 2023-05-04 |  | 2023-05-06 |  | Closed | 2023-05-08 | 2023-06-10 | E//Hazida | 2023-06-15 | Celcom Digi_RAN-GCI-TSS-Northern-20230502-0011 | DU00002007654 |  |  | 2023-06-20 | 2023-06-13 |  | Unipole | 3m Boom (RT) | 6 | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R9224E M1821(AAB) x3 |  | 2
7268A | Kg Mabpai | Sabah |  | Modernization |  | 2023Q3 | HQ 8 | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-08 |  | 2023-04-15 |  | Closed | 2023-04-14 | 2023-04-28 | CD//Mohidi Jaan | 2023-04-18 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002007655 |  |  | 2023-06-28 | 2023-06-24 |  | Monopole | 24m Monopole | 25m | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3
7279B | Bandar Sierra | Sabah |  | Modernization |  | 2023Q2 | HQ 2 | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-03 |  | 2023-04-26 |  | Closed | 2023-04-28 | 2023-05-05 | CD//Mohidi Jaan | 2023-05-05 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002007656 |  |  | 2023-06-03 | 2023-06-02 |  | Pole | 30m Monopole | 4 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
A00956 | A040C_A00956OD_DESALANGINDAH | Northern |  | Decomm |  | 2023Q2 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-04-13 |  |  |  | 2023-06-17 |  | 2023-06-19 | 2024-10-16 | CD//Heng | 2023-07-03 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V2 | DU00002007657 |  |  |  |  | 2023-06-30 |  | TOWER
7280B | Taman Bukit Sepanggar | Sabah |  | Modernization |  | 2023Q2 | AD | Futong | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦Limitted space to install AAU,Space is ouccuped by cable and limitted space to install new AAU. | 2023-04-08 | 2023-05-08 |  | 2023-04-15 |  | Closed | 2023-04-18 | 2023-05-17 | CD//Ray Amos | 2023-05-17 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002007658 | NIC_S2_Change MM to BI_Space constraint_VALSER TELCO SDN BHD |  | 2023-06-10 | 2023-06-09 |  | Monopole | 30m Monopole | 30 | Add R9264H M901821 x3 + R9264M M1821 x2,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 |  | 12
A00679 | A040C_A00679OD_JLNLABROOY_RDD | Northern |  | Decomm |  | 2023Q2 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-04-13 |  |  |  | 2023-06-19 |  | 2023-06-21 | 2024-02-27 | CD//Rohizam | 2023-08-02 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V2 | DU00002007659 |  |  |  |  | 2023-07-11 |  | UNIPOLE
B00360 | B058D_B00360OD_TMTLKGONG | Central | 1013K | Swap |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-19 | 2023-04-25 |  | 2023-04-28 |  | Closed | 2023-05-03 | 2023-06-03 | CD//Sapian | 2023-05-21 | CelcomDigi_RAN_Datasco_TSS_Central_20230419_0014 | DU00002007660 |  |  | 2023-08-29 | 2023-08-24 |  | Guide mast | BOOM | 20 | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
B00104 | B059A_B00104OD_KELANANG | Central |  | Decomm |  | 2023Q2 | MA | Magicell | 4.6 TSSR Approved |  | 2023-05-03 |  |  |  | 2023-06-14 |  | 2023-06-19 | 2023-07-17 | CD//Sapian | 2023-07-03 | CelcomDigi_RAN_Magicell_TSS_Central_20230626_decom reraise / CelcomDigi_TX_Magicell_TSS_Decom_Central_20230714 | DU00002007661 |  | 1706 TSSR reject. No mMCME info & photo |  |  | 2023-07-19 |  | TOWER
7271A | Inanam Commercial Center | Sabah |  | Modernization |  | 2023Q3 | AD | Futong | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦Limitted space to install AAU,Space is ouccuped by cable and limitted space to install new AAU. | 2023-04-08 | 2023-04-11 |  | 2023-04-17 |  | Closed | 2023-04-23 | 2023-05-25 | CD//Jahganathan | 2023-05-18 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002007662 | NIC_S2_Change MM to BI_Space constraint_Digi OB |  | 2023-07-10 | 2023-07-06 |  | Pole | 3m RT (Wall Mounted Pole) |  | Add R9264M M1821 x6,Dismantle R8894E M1821(A8A) x6 |  | 23
A00276 | A040C_A00276OD_TMNPERMAI | Northern | 4025K | Swap |  | 2023Q2 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-04-28 | 2023-04-29 |  | 2023-04-29 |  | Closed | 2023-05-03 | 2023-05-11 | CD//Shamsul | 2023-05-11 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230428-0011 | DU00002007663 |  |  | 2023-06-16 | 2023-06-13 |  | Unipole | MINI MONOPOLE | 9 | Add R8852E S9000 x3 + R8894E M1821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
7035C | Ujana Kingfisher | Sabah |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-04-07 | 2023-04-25 |  | 2023-04-13 |  | Closed | 2023-04-28 | 2023-05-05 | CD//Mohidi Jaan | 2023-05-05 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230407-0002 | DU00002007664 |  |  | 2023-07-07 | 2023-06-09 |  | Monopole | 30m RDS | 30 | Add R9264H M901821 x4 + R9264M M1821 x2,Dismantle R8894E M1821(A8A) x4 |  | 23
9369A | SMK Luar Bandar | Sarawak |  | Modernization |  | 2023Q2 | SH | Datasco | 4.6 TSSR Approved |  | 2023-04-18 | 2023-04-27 |  | 2023-05-02 |  | Closed | 2023-05-03 | 2023-05-17 | CD//John | 2023-05-03 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230419-0003 | DU00002007665 |  |  | 2023-06-19 | 2023-06-16 |  | Tower | 45m 3 Legged Tower | 60 | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x3 |  | 2
4937C | Taman Bayu Segar (REL) | Northern |  | Modernization |  | 2023Q3 | MH | GTSB | 4.6 TSSR Approved |  | 2023-05-09 | 2023-05-11 |  | 2023-05-16 |  | Closed | 2023-05-19 | 2023-06-27 | E//Hazida | 2023-06-27 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0016 | DU00002007666 |  |  | 2023-06-17 | 2023-06-17 |  | Minimast | 3m Boom (RT) | 3 | Add R8852E S9000 x4 + R8894E M1821 x4,Dismantle R8862A S1800(B6A) x4+R8862A S2100(A6A) x4
B00245 | B058E_B00245OD_BKTCHANGGANG | Central |  | Decomm |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-09 |  |  | 2023-04-13 | 2023-08-02 | Closed | 2023-07-20 | 2023-12-21 | CD//Ali Akaram | 2023-10-23 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002007667 |  | CD Yusri - 1.I can see MOCN traffic at this IPRAN for site B02916. Please verify. 2. From topology seem one site left out from topology and ZTE plan that is currently on air B02918_TM BKT CHANGGANG. Please include this site in the topology coz I cannot find the site from ZTE plan. |  |  | 2023-07-26 |  | TOWER | 55
7256A | Tmn Kingfisher | Sabah |  | Modernization |  | 2023Q3 | HQ 2 | GTSB | 4.6 TSSR Approved |  | 2023-04-04 | 2023-04-20 |  | 2023-04-26 |  | Closed | 2023-04-28 | 2023-05-01 | CD//Jahganathan | 2023-04-29 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230407-0002 | DU00002007668 |  |  | 2023-06-12 | 2023-06-02 |  | Wall mount boom | 6m RT (Wall Mounted Pole) | 5m | Add R9264H M901821 x3 + R9264M M1821 x2,Dismantle R8894E M1821(A8A) x3 |  | 12
9041Z | Durin-Kanaowitroad | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007669 | [6 empty] | 45m 3 Legged Tower
4962C | Taman Bukit Minyak | Northern |  | Modernization |  | 2023Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-05-02 | 2023-05-09 |  | 2023-05-09 |  | Closed | 2023-05-12 | 2023-05-25 | CD//Shamsul | 2023-05-17 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230502-0013 | DU00002007670 |  |  | 2023-06-19 | 2023-06-13 |  | Unipole | 24m Lampole | 7.35 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
7288A | Kg Kobuni Inanam | Sabah |  | Modernization |  | 2023Q3 | AD | Datasco | 4.6 TSSR Approved |  | 2023-07-17 | 2023-08-01 |  | 2023-08-08 |  | Closed | 2023-08-08 | 2023-08-16 | E//Hannah | 2023-08-16 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230626 | DU00002007671 |  |  | 2023-08-22 | 2023-08-20 |  | Tower | Tower | 61 | Add R9264H M901821 x3,Dismantle R8892E M1821(BAA) x3
A00983 | A040C_A00983OD_TASEKIND2IPH | Northern |  | Decomm |  | 2023Q2 | MH | GTSB | 4.6 TSSR Approved |  | 2023-04-05 | 2023-04-25 |  |  | 2023-06-17 |  | 2023-06-18 | 2023-08-08 | CD//Affendi | 2023-06-27 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1/Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230726-0024 | DU00002007672 |  |  |  |  | 2023-07-15 | Tower | TOWER | 60
A00561 | A042D_A00561OD_CB_PREMISTOWN | Northern |  | Decomm |  | 2023Q2 | ZA | GCI | 4.6 TSSR Approved |  | 2023-04-14 | 2023-06-26 |  |  | 2023-06-13 |  | 2023-06-14 | 2023-06-28 | CD//Affendi | 2023-06-26 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002007673 |  |  |  |  | 2023-06-26 | Minaret | TOWER | 31
A00399 | A040C_A00399OD_MASJIDMANJOI | Northern |  | Decomm |  | 2023Q2 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-04-13 |  |  |  | 2023-07-28 |  | 2023-08-01 | 2023-08-28 | CD//Affendi | 2023-08-01 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V2 | DU00002007674 |  |  |  |  | 2023-07-29 |  | MINARET
A00251 | A043B_A00251OD_TMAIRTAWAR | Northern |  | Decomm |  | 2023Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2023-04-29 |  |  |  | 2023-06-16 |  | 2023-06-18 | 2023-07-21 | CD//Heng | 2023-07-03 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230717-0022/Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1 | DU00002007675 |  |  |  |  | 2024-03-26 | Tower | TOWER | 45
A00404 | A043B_A00404OD_KGBAHARU | Northern |  | Decomm |  | 2023Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2023-04-15 |  |  |  | 2023-06-20 |  | 2023-06-20 |  | CD//Affendi | 2023-06-21 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1 | DU00002007676 |  | 21/8: Please Include all TX Equipment in page. Still have missing Equipment 4/6: still pending tssr report |  |  | 2023-07-10 |  | TOWER
4714B | Kg Tengah (Maxis) RDD | Northern |  | Modernization | Modernization->Decomm->Modernization->On Hold->Modernization | 2023Q2 | SM | GCI | 4.6 TSSR Approved |  | 2023-04-19 | 2023-05-11 |  | 2023-05-04 |  | Rectificating | 2023-05-15 | 2023-05-25 | CD//Quah | 2023-05-19 | Celcom Digi_RAN-GCI-TSS-Northern-20230425-0009 | DU00002007677 |  |  | 2023-05-28 | 2023-05-24 |  | Tower | 60m 3 Legged Tower | 45 | Add R9264H M901821 x3,Dismantle R8860E-GU908 x3+R8862A S1800(B6A) x3+R8881 S2100 x3
A00547 | A042D_A00547OD_CB_LUMUTPOWERPLANT | Northern |  | Decomm | Decomm->Site Out->Decomm | 2023Q2 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-04-13 |  |  |  | 2023-06-16 |  | 2023-06-22 |  | CD//Affendi | 2023-06-28 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V2 | DU00002007678 |  |  |  |  | 2025-06-26 |  | TOWER
A00799 | A043B_A00799OD_MN_KGKEDAH | Northern | 4133P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Heng |  |  | DU00002007679 | [6 empty] | TOWER
7117B | ILP Sepanggar 2 | Sabah |  | Modernization |  | 2023Q2 | AD | South Pacific | 4.6 TSSR Approved | AAU Cannot Install-Change MM to normal sector¦PTS sites remove MM | 2023-06-22 | 2023-06-23 |  | 2023-06-24 |  | Closed | 2023-06-24 | 2023-06-27 | E//Hannah | 2023-06-28 | Celcom Digi_RAN-South Pacific-TSS-Sabah-20230626 | DU00002007680 | NIC_S3_Change MM to normal sector_loading issue_EDOTCO (M) - NONE CSU |  | 2023-06-28 | 2023-06-27 |  | Monopole | 25m pBTS | 31 | Add R9264M M1821 x3,Dismantle R9224E M1821(AAB) x3 | 0
A00048 | A043B_A00048OD_CB_KAYAN | Northern |  | Decomm |  | 2023Q2 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-04-13 |  |  |  | 2023-06-17 |  | 2023-06-20 | 2023-06-28 | CD//Affendi | 2023-06-21 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V2 | DU00002007681 |  |  |  |  | 2023-06-27 |  | TOWER
4825A | Ipoh Parade | Northern |  | Modernization |  | 2023Q2 | WP | GCI | 4.6 TSSR Approved |  | 2023-04-17 | 2023-04-27 |  | 2023-05-06 |  | Closed | 2023-05-08 | 2023-05-25 | CD//Shamsul | 2023-05-10 | Celcom Digi_RAN-GCI-TSS-Northern-20230418-0007 | DU00002007682 |  |  | 2023-05-27 | 2023-05-24 |  |  | In-building system |  | Add R8852E S9000 x3 + R8862A S1800 x3 + R8862A S2100 x3,Dismantle R8882 S1800B(B6B) x3
A00046 | A043B_A00046OD_CB_KGRAJAHITAM_RDC | Northern |  | Decomm |  | 2023Q2 | MH | GTSB | 4.6 TSSR Approved |  | 2023-04-14 | 2023-06-26 |  |  | 2023-06-15 |  | 2023-06-16 | 2023-07-04 | CD//Heng | 2023-07-03 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230717-0022/Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1 | DU00002007683 |  |  |  |  | 2023-06-24 | Tower | TOWER | 60
A01084 | A040C_A01084OD_TMN_CHEPOR_IMPIAN | Northern | 4030K | Swap |  | 2023Q2 | MH | GTSB | 4.6 TSSR Approved |  | 2023-04-09 |  |  | 2023-04-15 |  | Closed | 2023-04-20 | 2023-05-06 | CD//Shamsul | 2023-05-06 | Celcom Digi_RAN-GTSB-TSS-Northern-20230410-0007 | DU00002007684 |  |  | 2023-06-22 | 2023-06-16 |  | Minaret | MINARET | 30 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 2
7263A | Kiansam Heights | Sabah |  | Modernization |  | 2023Q3 | HQ 1 | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-12 |  | 2023-04-17 |  | Closed | 2023-04-25 | 2023-06-08 | CD//Jahganathan | 2023-06-09 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002007685 |  |  | 2023-06-28 | 2023-06-26 |  | Tower | 60m 3 Legged Tower | 60 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
4529C | Kampung Baru Alma (REL) | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-09 |  | 2023-05-10 |  | Closed | 2023-05-11 | 2023-05-25 | CD//Shamsul | 2023-05-15 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0015 | DU00002007686 |  |  | 2023-06-19 | 2023-06-16 |  | Lampole | Tower | 30 | Add R9264M M1821 x5 + R8862A S2601 x1,Dismantle R8894E M1821(A8A) x4 |  | 4
4523D | Chepor Impian (REL) | Northern |  | Modernization |  | 2023Q2 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-04-19 | 2023-04-28 |  | 2023-04-28 |  | Closed | 2023-05-02 | 2023-05-25 | CD//Shamsul | 2023-05-10 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230419-0009 | DU00002007687 |  |  | 2023-06-05 | 2023-06-03 |  | Lampole | Land site | 32 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
7051A | Wisma Everight | Sabah |  | Modernization |  | 2023Q3 | HQ 1 | Futong | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-12 |  | 2023-04-17 |  | Closed | 2023-04-28 | 2023-06-10 | CD//Jahganathan | 2023-06-08 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002007688 |  |  | 2023-07-07 | 2023-06-30 |  | Minimast | 3m Boom (RT) | 10 | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x4 | 123
A00139 | A040C_A00139OD_MERUHEIGHT | Northern |  | Decomm |  | 2023Q2 | MH | YPTT | 4.6 TSSR Approved |  | 2023-04-26 | 2023-06-26 |  |  | 2023-06-16 |  | 2023-06-18 | 2024-03-26 | CD//Affendi | 2023-06-27 | Celcom Digi_RAN-YPTT-TSS-Northern-20230609-0018 | DU00002007689 |  | 11/9:No Photo, No info, nothing for TX part |  |  | 2023-07-13 | Tower | TOWER | 30M
4567A | Medan Klebang Restu | Northern |  | Modernization |  | 2023Q2 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-04-18 | 2023-05-18 |  | 2023-05-23 |  | Closed | 2023-05-26 | 2023-06-02 | E//Hazida | 2023-06-02 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230418-0008 | DU00002007690 |  |  | 2023-06-11 | 2023-06-10 |  | Tower | 60m 3 Legged Tower | 60m | Add A9732 M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R8894E M1821(A8A) x2 | 123
A00280 | A040C_A00280OD_TMJELAPANG | Northern |  | Decomm |  | 2023Q2 | ZA | GCI | 4.6 TSSR Approved |  | 2023-06-07 |  |  |  | 2023-06-22 |  | 2023-06-22 | 2023-09-21 | CD//Affendi | 2023-06-28 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1 | DU00002007691 |  |  |  |  | 2024-05-09 |  | MINI STRUCTURE
4522A | MERU1 | Northern |  | Modernization |  | 2023Q2 | MH | GTSB | 4.6 TSSR Approved |  | 2023-04-13 | 2023-04-17 |  | 2023-04-19 |  | Closed | 2023-04-20 | 2023-05-11 | CD//Affendi | 2023-05-03 | Celcom Digi_RAN-GTSB-TSS-Northern-20230414-0010 | DU00002007692 |  |  | 2023-05-20 | 2023-05-20 |  | Tower | 30m Monopole | 30 | Add R9264M M1821 x6,Dismantle R8894E M1821(A8A) x4 |  | 23
7000A | K.K. MSC | Sabah |  | Modernization |  | 2023Q3 | AD | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-05-08 |  | 2023-04-17 |  | Rectificating | 2023-05-05 | 2023-06-12 | CD//Jahganathan | 2023-06-13 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002007693 |  |  | 2023-07-13 | 2023-07-01 |  | Tower | 76m 4 Legged Tower | 76 | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x3+R9224E M1821(AAB) x6 | 123
7112B | Kg Moronon | Sabah |  | Modernization |  | 2023Q2 | AD | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-04 |  | 2023-04-13 |  | Rectificating | 2023-04-18 | 2023-05-10 | CD//Mohidi Jaan | 2023-05-10 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002007694 |  |  | 2023-06-21 | 2023-06-12 |  | Tower | Tower | 45 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8882 S2600(B4A) x1+R8862A S2600(A4A) x1+R8894E M1821(A8A) x5 | 13
9113A | Kg Jepak (SACOFA) | Sarawak |  | Modernization |  | 2023Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2023-04-05 | 2023-04-07 |  | 2023-04-13 |  | Closed | 2023-05-16 | 2023-05-19 | CD//John | 2023-05-16 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230403-0003 | DU00002007695 |  |  | 2023-06-23 | 2023-06-20 |  |  | Tower | 31m | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3
4363C | Mydin Meru (REL) | Northern |  | Modernization |  | 2023Q2 | WP | GTSB | 4.6 TSSR Approved |  | 2023-04-11 | 2023-04-14 |  | 2023-04-15 |  | Closed | 2023-04-19 | 2023-05-09 | CD//Heng | 2023-05-03 | Celcom Digi_RAN-GTSB-TSS-Northern-20230411-0008 | DU00002007696 |  |  | 2023-05-21 | 2023-05-20 |  |  | 6m Unipole RT | 7 | Add A9732 M1821 x2 + R9264M M1821 x2,Dismantle R8894E M1821(A8A) x4 | 13(S2->S3,S3->S4,S4->S2,Rename sector;FDD MM @ S1/S4)
A00126 | A042D_A00126OD_BERUAS | Northern | 4024K | Swap |  | 2023Q2 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-10 |  | 2023-05-12 |  | Closed | 2023-05-17 | 2023-05-23 | CD//Shamsul | 2023-05-23 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230428-0011 | DU00002007697 |  |  | 2023-06-13 | 2023-05-27 |  | Tower | TOWER | 70m | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
7317A | Pulutan SBC | Sabah |  | Modernization |  | 2023Q2 | HQ 5 | Futong | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-29 |  | 2023-05-03 |  | Closed | 2023-05-05 | 2023-05-11 | CD//Jahganathan | 2023-05-11 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002007698 |  |  | 2023-06-14 | 2023-06-08 |  | Monopole | 30m Monopole | 45 | Add R9264H M901821 x3,Dismantle R9224E M1821(AAB) x3
7814M | Kingfisher Plaza | Sabah |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007699 | [6 empty] | Micro Cell
A00665 | A040C_A00665OD_KGMANDAILING_RDD | Northern |  | Decomm |  | 2023Q2 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-04-17 |  |  |  | 2023-08-08 |  | 2023-08-09 | 2023-08-19 | CD//Shamsul | 2023-08-10 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V2 | DU00002007700 |  |  |  |  | 2023-07-27 |  | TOWER
7225A | Borneo Development Corp. | Sabah |  | Modernization |  | 2023Q3 | HQ 2 | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-27 |  | 2023-05-05 |  | Closed | 2023-05-06 | 2023-06-07 | CD//Jahganathan | 2023-06-07 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002007701 |  |  | 2023-07-05 | 2023-06-26 |  | Pole | 3m RT (Wall Mounted Pole) |  | Add A9732 M1821 x1 + R9264M M1821 x2,Dismantle R8894E M1821(A8A) x3 | 3
9368A | Salim Road Sacofa | Sarawak |  | Modernization |  | 2023Q2 | SH | Trintel | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI,L2600 change to 40M¦Sacofa lampole not allow to add antenna | 2023-04-11 | 2023-05-03 |  | 2023-05-05 |  | Closed | 2023-05-22 | 2023-09-08 | E//Hannah | 2023-09-08 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230626 | DU00002007702 | NIC_S3_Change MM to BI,L2600 change to 40M_owner reject_SACOFA SDN BHD |  | 2023-12-27 | 2023-08-15 |  | Tower | Tower | 90 | Add R9264H M901821 x3 + R9264M M1821 x3,Dismantle R8894E M1821(A8A) x6 |  | 123
4889A | SUNWAY CARNIVAL | Northern |  | Modernization |  | 2023Q3 | WP | GCI | 4.6 TSSR Approved |  | 2023-05-13 | 2023-05-15 |  | 2023-06-09 |  | Closed | 2023-06-13 | 2023-06-22 | E//Nazrul | 2023-06-22 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0015 | DU00002007703 |  |  | 2023-07-11 | 2023-07-07 |  |  | In-building system |  | Add + R8862A S1800 x3 + R8862A S2100 x3 + R8862A S2601 x3,Dismantle R8882-GUL1812 x1+R8882 S1800(B) x1 | 0 | 0
7056H | 99 Speedmart TMN CANGGIH | Sabah |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007704 | [6 empty] | Small Cell
4726C | Jln Sg Nyior (REL) | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-11 | 2023-05-13 |  | 2023-05-19 |  | Closed | 2023-05-29 | 2023-06-21 | CD//Shukri | 2023-06-21 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0015 | DU00002007705 |  |  | 2023-06-24 | 2023-06-17 |  | Minimast | 3m Boom (RT) | 11 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x3+R9224E M1821(AAB) x2 | 12
A00093 | A042D_A00093OD_CB_BTHAMPAR_RDD | Northern |  | Decomm |  | 2023Q2 | SM | YPTT | 4.6 TSSR Approved |  | 2023-04-12 | 2023-06-26 |  |  | 2023-07-25 |  | 2023-07-03 | 2023-07-21 | CD//Affendi | 2023-07-04 | Celcom Digi_RAN-YPTT-TSS-Northern-20230609-0018/Celcom Digi_RAN-YPTT-TSS Decomm-Northern-20240311-0048 | DU00002007706 |  |  |  |  | 2023-07-05 | Tower | TOWER | 60M
A00044 | A040C_A00044OD_BGNPKNP | Northern | 4058K | Decomm |  | 2023Q2 | BY | GCI | 4.6 TSSR Approved |  | 2023-10-04 | 2023-06-08 |  |  | 2024-02-29 |  | 2024-03-25 | 2024-10-07 | IBC Pic | 2024-03-25 | 0626Northen-GCI-BOQ Template (template)/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002007707 |  | 0602// Pending revise - need resurvey due to solution changed |  |  | 2023-07-25 |  | BOOM | NA
4546A | KWSP Ipoh RDD | Northern |  | Modernization |  | 2023Q2 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-04-13 | 2023-04-20 |  | 2023-04-17 |  | Closed | 2023-04-19 | 2023-05-15 | CD//Quah | 2023-05-06 | Celcom Digi_RAN-YPTT-TSS-Northern-20230414-0005 | DU00002007708 |  |  | 2023-05-29 | 2023-05-27 |  | H-bracket pole | 60m 4 Legged Tower | 4 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
7030H | NAC BRILLIANCE GROUP SDN.BHD | Sabah |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007709 | [6 empty] | Small Cell
A00316 | A040A_A00316OD_TOLIPOHSELATAN_RCC | Northern |  | Decomm |  | 2023Q2 | MH | GTSB | 4.6 TSSR Approved |  | 2023-04-09 | 2023-04-25 |  |  | 2023-06-07 |  | 2023-06-08 | 2023-07-21 | CD//Affendi | 2023-06-13 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230717-0022/Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1 | DU00002007710 |  |  |  |  | 2023-07-02 | Tower | TOWER | 60
A00289 | A040B_A00289OD_PUSATISLAMIPOH | Northern |  | Decomm |  | 2023Q2 | ZA | YPTT | 4.6 TSSR Approved |  | 2023-04-26 | 2023-06-26 |  |  | 2023-06-21 |  | 2023-06-23 | 2025-09-24 | CD//Affendi | 2023-06-28 | Celcom Digi_RAN-YPTT-TSS-Northern-20230609-0018 | DU00002007711 |  |  |  |  | 2023-07-18 | Pole | BOOM | 3M
4543B | Zon Perdagangan Bebas Jelapang | Northern |  | Modernization |  | 2023Q2 | MH | GTSB | 4.6 TSSR Approved |  | 2023-04-09 |  |  | 2023-04-14 |  | Closed | 2023-04-17 | 2023-05-18 | CD//Quah | 2023-05-05 | Celcom Digi_RAN-GTSB-TSS-Northern-20230410-0007 | DU00002007712 |  |  | 2023-06-06 | 2023-06-03 |  | Tower | 60m 3 Legged Tower | 45 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x2+R8854D S2100(A4A) x3
4324H | 99 Speedmart PG Tmn Seri Delima | Northern |  | MOCN As-Is |  | 2023Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007713 | [6 empty] | Rooftop
A01384 | Kg Gelung Pepuyu | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Heng |  |  | DU00002007714 | [6 empty] | TOWER
9239B | Celcom Jln Teku | Sarawak |  | Modernization |  | 2023Q2 | HQ 2 | CCSMY | 4.6 TSSR Approved |  | 2023-04-04 | 2023-04-08 |  | 2023-05-05 |  | Closed | 2023-05-07 | 2023-05-10 | CD//John | 2023-05-10 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230403-0003 | DU00002007715 |  |  | 2023-09-08 | 2023-06-26 |  | Tower | Tower | 46 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R9224E M1821(AAB) x3 | 123
9005M | Sibu Medan Mall DS Micro | Sarawak |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007716 | [6 empty] | Micro Cell
9686C | Lorong Sibu Jaya | Sarawak |  | Modernization |  | 2023Q2 | BY | AllStar | 4.6 TSSR Approved |  | 2023-04-13 | 2023-04-17 |  | 2023-04-18 |  | Closed | 2023-04-20 | 2023-04-25 | CD//John | 2023-04-25 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230403-0003 | DU00002007717 |  |  | 2023-06-15 | 2023-06-12 |  |  | Land site | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
9356A | Durin Ferry | Sarawak |  | Modernization |  | 2023Q2 | SH | Datasco | 4.6 TSSR Approved |  | 2023-04-11 | 2023-05-15 |  | 2023-05-18 |  | Closed | 2023-05-24 | 2023-06-20 | E//Hannah | 2023-06-20 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230626 | DU00002007718 |  |  | 2023-08-17 | 2023-07-21 |  | Tower | Tower | 76M | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2600 x1,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3 |  | 2
7126B | UMS Bngn Canselori | Sabah |  | Modernization |  | 2023Q3 | HQ 6 | GTSB | 4.6 TSSR Approved |  | 2023-04-05 |  |  | 2023-04-13 |  | Closed | 2023-04-26 | 2023-06-11 | CD//Jahganathan | 2023-06-11 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230407-0002 | DU00002007719 |  |  | 2023-07-13 | 2023-07-13 |  | BillBoard | 3m RT (Minimast) | 18m | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8882 S1800B(B6B) x2+R8862A S1800(B6A) x1+R8840-U216 x2
9699B | TK Materials | Sarawak |  | Modernization |  | 2023Q2 | MA | AllStar | 4.6 TSSR Approved |  | 2023-04-11 | 2023-04-25 |  | 2023-04-26 |  | Closed | 2023-05-04 | 2023-05-04 | CD//John | 2023-05-04 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230403-0003 | DU00002007720 |  |  | 2023-06-12 | 2023-06-08 |  |  | 30M Rapole | 30 | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3
9806A | Wisma Sanyan | Sarawak |  | Modernization |  | 2023Q2 | SH | Datasco | 4.6 TSSR Approved |  | 2023-04-20 | 2023-05-15 |  | 2023-05-16 |  | Closed | 2023-05-18 | 2023-06-17 | CD//John | 2023-05-18 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002007721 |  |  | 2023-07-18 | 2023-07-04 |  | Monopole | In-building system | 3.1 | Add R8862A S1800 x1 + R8862A S2100 x1,Dismantle R8882 S1800(B) x1
A00571 | A040C_A00571OD_CB_KGULUKUANG_RCD | Northern |  | Decomm |  | 2023Q2 | MH | YPTT | 4.6 TSSR Approved |  | 2023-04-13 | 2023-06-26 |  |  | 2023-06-24 |  | 2023-06-26 | 2023-07-21 | CD//Shamsul | 2023-07-04 | Celcom Digi_RAN-YPTT-TSS-Northern-20230609-0018/Celcom Digi_RAN-YPTT-TSS Decomm-Northern-20240311-0048 | DU00002007722 |  |  |  |  | 2023-07-17 | Tower | TOWER | 60M
B00185 | B057B_B00185OD_KANCHINGBARU | Central |  | Decomm |  | 2023Q2 | IE | MTK | 4.6 TSSR Approved |  | 2023-04-12 | 2023-06-26 |  |  | 2023-05-30 |  | 2023-07-12 | 2024-05-31 | CD//Sapian | 2023-07-20 | CelcomDigi_RAN_MTK_TSS_Central_20230626_decom reraise / CelcomDigi_TX_MTK_TSS_Decom_Central_20230714 | DU00002007723 |  |  |  |  | 2023-10-12 | Tower | TOWER | 60
A00250 | A042D_A00250OD_CB_TMPREMIS | Northern |  | Decomm |  | 2023Q2 | SM | GCI | 4.6 TSSR Approved |  | 2023-06-13 |  |  |  | 2023-06-19 |  | 2023-06-22 | 2023-08-08 | CD//Rohizam | 2023-08-02 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002007724 |  |  |  |  | 2023-07-03 |  | TOWER
4458C | Pantai Remis Hotel | Northern |  | Modernization |  | 2023Q2 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-04-13 | 2023-04-14 |  | 2023-04-18 |  | Closed | 2023-04-19 | 2023-05-09 | CD//Heng | 2023-04-28 | Celcom Digi_RAN-GCI-TSS-Northern-20230414-0005 | DU00002007725 |  |  | 2023-05-16 | 2023-05-15 |  | Pole | 3m Bipod (RT) | 4 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 | 13
4275C | Klebang Ria 2 | Northern |  | Modernization |  | 2023Q2 | MH | CCSMY | 4.6 TSSR Approved |  | 2023-04-17 | 2023-05-03 |  | 2023-04-20 |  | Closed | 2023-05-04 | 2023-05-25 | CD//Affendi | 2023-05-08 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230418-0008 | DU00002007726 |  |  | 2023-06-10 | 2023-06-09 |  | Minaret | 30m RDS | 30M | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
4346A | Chemor | Northern |  | Modernization |  | 2023Q2 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-04-17 | 2023-04-28 |  | 2023-04-28 |  | Closed | 2023-05-02 | 2023-05-25 | CD//Heng | 2023-05-03 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230418-0008 | DU00002007727 |  |  | 2023-06-22 | 2023-06-22 |  | Tower | Tower | 61.7 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
4470A | Beruas(Maxis) | Northern |  | Modernization |  | 2023Q2 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-17 |  | 2023-04-17 |  | Closed | 2023-04-18 | 2023-05-09 | CD//Quah | 2023-05-05 | Celcom Digi_RAN-YPTT-TSS-Northern-20230413-0004 | DU00002007728 |  |  | 2023-05-31 | 2023-05-29 |  | Tower | 60m 3 Legged Tower | 75 | Add R9264M M1821 x4,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x3+R8840-U216 x3 |  | 2
B00376 | B058D_B00376OD_PLBHBARAT2 | Central |  | Decomm |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-14 |  |  |  | 2023-10-10 |  | 2023-06-15 | 2024-02-23 | CD//Ali akaram | 2023-07-18 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002007729 |  |  |  |  | 2023-09-24 |  | TOWER
7150B | Alam Mesra 2 | Sabah |  | Modernization |  | 2023Q3 | HQ 5 | GTSB | 4.6 TSSR Approved |  | 2023-04-04 | 2023-04-10 |  | 2023-04-15 |  | Closed | 2023-04-18 | 2024-01-02 | CD//Mohidi Jaan | 2023-12-29 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230407-0002 | DU00002007730 |  |  | 2023-06-14 | 2023-06-09 |  | Unipole | 3m Unipole (RT) | 3 | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle R8882 S1800(B) x3+R8862A S1800(B6A) x1+R8854D S2100(A4A) x4 |  | 1
7605B | Grand Merdeka Mall (RT) | Sabah |  | Modernization |  | 2023Q2 | HQ 5 | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-04 |  | 2023-04-13 |  | Rectificating | 2023-04-23 | 2023-05-05 | CD//Mohidi Jaan | 2023-05-05 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002007731 |  |  | 2023-06-24 | 2023-06-12 |  | Pole | 3m Boom (RT) |  | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x3 | 23
A01171 | A040C_A01171OD_TMN_SILIBIN_IPH | Northern | 4035K | Swap |  | 2023Q2 | MH | GTSB | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-17 |  | 2023-04-19 |  | Closed | 2023-04-20 | 2023-05-08 | CD//Shamsul | 2023-05-08 | Celcom Digi_RAN-GTSB-TSS-Northern-20230413-0009 | DU00002007732 |  |  | 2023-06-13 | 2023-06-10 |  | Pole | BOOM | 12 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
4577B | Khantan Industry RDD | Northern |  | Modernization |  | 2023Q2 | MH | YPTT | 4.6 TSSR Approved |  | 2023-04-13 | 2023-04-25 |  | 2023-04-18 |  | Closed | 2023-04-26 | 2023-06-02 | CD//Quah | 2023-06-02 | Celcom Digi_RAN-YPTT-TSS-Northern-20230414-0005 | DU00002007733 |  |  | 2023-06-16 | 2023-06-16 |  | Tower | 60m 3 Legged Tower | 60 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8860E-GU908 x1+R8882-GUL1812 x4+R8840-U216 x3 |  | 2
7283A | Kg Bandulan | Sabah |  | Modernization |  | 2023Q2 | HQ 3 | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-11 |  | 2023-04-19 |  | Closed | 2023-04-25 | 2023-05-09 | CD//Jahganathan | 2023-05-09 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002007734 |  |  | 2023-06-20 | 2023-06-16 |  | Monople Tree | 30m Monopole | 45 | Add A9732 M1821 x3 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 | 123
7245A | Kiansam Baru | Sabah |  | Modernization |  | 2023Q3 | HQ 3 | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-06 |  | 2023-04-13 |  | Closed | 2023-04-14 | 2023-05-10 | CD//Jahganathan | 2023-05-10 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002007735 |  |  | 2023-07-10 | 2023-07-08 |  | Tower | 30m 3-legged tower | 24 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 13
7707B | Kionsom Lama | Sabah |  | Modernization |  | 2023Q3 | AD | Datasco | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-08 |  | 2023-04-17 |  | Rectificating | 2023-04-18 | 2023-05-10 | CD//Mohidi Jaan | 2023-05-10 | Celcom Digi_RAN-Datasco- TSS-Sabah-20230407-0002 | DU00002007736 |  |  | 2023-06-24 | 2023-06-13 |  | Tower | Tower | 60m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
4535B | Ipoh (S) Tol (KJS) RCC | Northern |  | Modernization |  | 2023Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2023-04-09 | 2023-04-08 |  | 2023-04-14 |  | Closed | 2023-04-14 | 2023-05-11 | CD//Quah | 2023-05-05 | Celcom Digi_RAN-GTSB-TSS-Northern-20230410-0007 | DU00002007737 |  |  | 2023-05-16 | 2023-05-15 |  | Tower | 60m 4 Legged Tower | 60 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
7080B | Inanam Point RT | Sabah |  | Modernization |  | 2023Q3 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-04-10 | 2024-09-12 |  | 2023-04-18 |  | Closed | 2023-04-28 | 2024-07-10 | CD//Mohidi Jaan | 2023-05-05 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230407-0002 | DU00002007738 |  |  | 2023-07-10 | 2023-07-07 |  | Pole | 6m RT (Boom) | 26 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
9103C | Jalan Bahagia Selatan | Sarawak |  | Modernization |  | 2023Q2 | SH | CCSMY | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI,L2600 change to 40M¦9103C tower owner Sacofa reject our TP of adding AAU. | 2023-04-04 | 2023-05-10 |  | 2023-05-02 |  | Closed | 2023-05-18 | 2023-05-18 | CD//Norhaliza | 2023-05-18 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230403-0003 | DU00002007739 | NIC_S3_Change MM to BI,L2600 change to 40M_owner reject_SACOFA SDN BHD |  | 2023-09-01 | 2023-08-16 |  | Monopole | 30m Monopole | 32 | Add R9264H M901821 x3 + R9264M M1821 x3 + R8862A S2601 x3,Dismantle R8894E M1821(A8A) x3 |  | 123
4503B | Gunung Lang | Northern |  | Modernization |  | 2023Q2 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-04-13 | 2023-04-20 |  | 2023-04-19 |  | Rectificating | 2023-05-01 | 2023-05-18 | CD//Quah | 2023-05-11 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230414-0007 | DU00002007740 |  |  | 2023-06-19 | 2023-06-13 |  | Tower | 60m 3 Legged Tower | 60 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3
A00205 | A042D_A00205OD_CB_PINTUGERBANGBERUAS_RDD | Northern |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2023Q2 | ZA | NR services | 4.6 TSSR Approved |  | 2023-06-15 |  |  |  | 2023-08-08 |  | 2023-08-18 | 2023-08-21 | CD//Heng | 2023-08-18 | SQ202504230470-YPTT | DU00002007741 |  |  |  |  | 2023-07-04 |  | TOWER
7028C | Bukit Damaisari Menggatal | Sabah |  | Modernization |  | 2023Q2 | AD | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-07 |  | 2023-04-13 |  | Rectificating | 2023-04-18 | 2023-04-28 | CD//Mohidi Jaan | 2023-04-20 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002007742 |  |  | 2023-06-10 | 2023-06-08 |  | Monopole | 30m Lampole | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
4245A | Titi Panjang | Northern |  | Modernization |  | 2023Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-05-16 | 2023-05-11 |  | 2023-05-16 |  | Closed | 2023-05-18 | 2023-06-17 | E//Hazida | 2023-06-16 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0017 | DU00002007743 |  |  | 2023-07-05 | 2023-07-03 |  | Tower | 60m 3 Legged Tower | 62m | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8882 S1800B(B6B) x3+R8862A S1800(B6A) x1+R8854D S2100(A4A) x4+R8882 S2600(B4A) x1 | 13
9134A | Isti Jaya | Sarawak |  | Modernization |  | 2023Q2 | SH | Datasco | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦Limitted space to install AAU,Space is ouccuped by cable and limitted space to install new AAU. | 2023-04-06 |  |  | 2023-04-26 |  | Closed | 2023-05-02 | 2023-05-03 | CD//John | 2023-05-03 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002007744 | NIC_S3_Change MM to BI_Space constraint_Digi OB |  | 2023-06-30 | 2023-06-22 |  |  | 3m RT (Wall Mounted Pole) |  | Add R9264H M901821 x3 + R9264M M1821 x3 + R8862A S2600 x3,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3 |  | 123
A01128 | A040C_A01128OD_KG_SGTAPAH_IPH | Northern |  | Decomm |  | 2023Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2023-04-11 |  |  |  | 2023-06-09 |  | 2023-06-11 | 2024-05-10 | CD//Affendi | 2023-06-12 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230720-0023/Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1 | DU00002007745 |  |  |  |  | 2023-07-19 | Minaret | MINARET | 27
9035R | KG. TG BEKAKAP | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Norhaliza |  |  | DU00002007746 | [6 empty] | Land site
4220B | Persiaran Kerapu | Northern |  | Modernization |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-04-29 | 2023-05-03 |  | 2023-04-29 |  | Closed | 2023-05-06 | 2023-05-30 | E//Hazida | 2023-05-29 | Celcom Digi_RAN-GCI-TSS-Northern-20230502-0011 | DU00002007747 |  |  | 2023-06-07 | 2023-06-07 |  | Wall mount boom | 4 Legged Tower | 6 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
B00370 | B058E_B00370OD_TMTPGARANG | Central |  | Decomm |  | 2023Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2023-06-06 |  |  | 2023-06-12 | 2023-06-14 | Closed | 2023-06-15 | 2024-01-30 | CD//Ali akaram | 2023-07-18 | CelcomDigi_RAN_AllStar_TSS_Central_20230626_decom reraise | DU00002007748 |  |  |  |  | 2023-10-12 |  | BOOM
9384B | Sibu Jaya MP | Sarawak |  | Modernization |  | 2023Q2 | HQ 2 | Datasco | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦Limitted space to install AAU,Space is ouccuped by cable and limitted space to install new AAU. | 2023-04-04 |  |  | 2023-05-08 |  | Closed | 2023-05-13 | 2023-05-15 | CD//John | 2023-05-15 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002007749 | NIC_S2_Change MM to BI_Space constraint_SACOFA SDN BHD |  | 2023-06-26 | 2023-06-22 |  |  | 30m Monopole | 36m | Add R9264H M901821 x4 + R9264M M1821 x2,Dismantle R8862A S1800(B6A) x1+R8854E S1800(A6A) x3+R8862A S2100(A6A) x1+R8854D S2100(A4A) x3 |  | 23
A00101 | A040B_A00101OD_IPOHRAYA | Northern |  | Decomm |  | 2023Q2 | MH | CCSMY | 4.6 TSSR Approved |  | 2023-04-13 |  |  |  | 2023-06-17 |  | 2023-06-18 | 2024-02-27 | CD//Affendi | 2023-06-27 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V2/Celcom Digi_RAN-CCSMY-TSS Decomm-Northern-20240131-0091 | DU00002007750 |  | 10/8:Wrong SOW, suppose dismantle link Celcom |  |  | 2023-07-12 |  | BOOM
4536A | Tasek Industrial RDD | Northern |  | Modernization |  | 2023Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2023-04-09 |  |  | 2023-04-14 |  | Closed | 2023-04-27 | 2023-05-25 | CD//Quah | 2023-05-08 | Celcom Digi_RAN-GTSB-TSS-Northern-20230410-0007 | DU00002007751 |  |  | 2023-06-06 | 2023-06-03 |  | Monopole | 30m Monopole | 40 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 23
9286B | UCTS Sibu | Sarawak |  | Modernization |  | 2023Q2 | SH | Datasco | 4.6 TSSR Approved |  | 2023-04-10 |  |  | 2023-05-02 |  | Closed | 2023-05-04 | 2023-05-05 | CD//John | 2023-05-05 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002007752 |  |  | 2023-08-03 | 2023-07-21 |  |  | 30m Monopole | 30 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
4971C | Kilang Papan Kampung Kanthan | Northern |  | Modernization |  | 2023Q2 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-04-19 | 2023-05-04 |  | 2023-05-05 |  | Closed | 2023-05-08 | 2023-06-01 | E//Hazida | 2023-06-01 | Celcom Digi_RAN-GCI-TSS-Northern-20230425-0009 | DU00002007753 |  |  | 2023-06-07 | 2023-06-07 |  | Monopole | 30m Monopole | 30 | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
4998C | Jelapang Jaya | Northern |  | Modernization |  | 2023Q2 | ZA | YPTT | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-13 |  | 2023-04-26 |  | Closed | 2023-04-27 | 2023-05-25 | CD//Shamsul | 2023-05-08 | Celcom Digi_RAN-YPTT-TSS-Northern-20230413-0004 | DU00002007754 |  |  | 2023-06-12 | 2023-06-10 |  | Tower | Tower | 47m | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
4539B | Jelapang Ria | Northern |  | Modernization |  | 2023Q2 | WP | CCSMY | 4.6 TSSR Approved |  | 2023-04-19 | 2023-04-20 |  | 2023-04-19 |  | Closed | 2023-04-25 | 2023-05-16 | CD//Shamsul | 2023-05-09 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230419-0009 | DU00002007755 |  |  | 2023-05-23 | 2023-05-23 |  | Lampole | 30m Minaret | 30m | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8881 S2100 x3
4301A | Wisma Ban Nam | Northern |  | Modernization |  | 2023Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2023-04-05 | 2023-04-13 |  | 2023-04-14 |  | Closed | 2023-04-14 | 2023-04-27 | CD//Quah | 2023-04-26 | Celcom Digi_RAN-GTSB-TSS-Northern-20230410-0007 | DU00002007756 | Interim to 12port Hybrid |  | 2023-05-16 | 2023-05-15 |  |  | 6m RT (Boom) | 5 | Add R9264M M1821 x8 + R8862A S2601 x4,Dismantle R8894E M1821(A8A) x4 |  | 1234
B00128 | B058C_B00128OD_BKTTINGGIKLG2 | Central |  | Decomm |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-04-17 | 2023-06-26 |  | 2023-06-10 | 2023-06-27 | Closed | 2023-06-27 | 2023-09-01 | CD//Ali Akaram | 2023-08-27 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230626_decom reraise | DU00002007757 |  |  |  |  | 2023-07-18 | Unipole | BOOM | 12m
7845A | One Borneo IB | Sabah |  | Modernization |  | 2023Q3 | AD | AllStar | 4.6 TSSR Approved |  | 2023-04-08 | 2023-05-08 |  | 2023-05-08 |  | Closed | 2023-05-11 | 2023-05-25 | CD//Mohidi Jaan | 2023-05-14 | Celcom Digi_RAN-Allstar-TSS-Sabah-20230407-0002 | DU00002007758 |  |  | 2023-06-28 | 2023-06-28 |  |  | In-building system |  | Add R8862A S1800 x4,Dismantle R8882-GUL1812 x3+R8882 S1800(B) x1
4267H | 99 Speedmart PG Tmn Merbau Indah | Northern |  | MOCN As-Is |  | 2023Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007759 | [6 empty] | Small Cell
9279B | Lorong Salim | Sarawak |  | Modernization |  | 2023Q2 | HQ 1 | AllStar | 4.6 TSSR Approved |  | 2023-04-11 | 2023-05-03 |  | 2023-05-06 |  | Closed | 2023-05-08 | 2023-05-10 | CD//John | 2023-05-10 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230403-0003 | DU00002007760 |  |  | 2023-06-14 | 2023-06-12 |  | Monopole | 30m Rapole | 30 | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
9384A | Jalan Wong Kin Huo | Sarawak |  | Modernization |  | 2023Q2 | BY | Trintel | 4.6 TSSR Approved |  | 2023-04-04 | 2023-04-07 |  | 2023-04-17 |  | Rectificating | 2023-04-18 | 2023-04-25 | CD//John | 2023-04-25 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230403-0003 | DU00002007761 |  |  | 2023-06-26 | 2023-06-22 |  | Monopole | Tower | 39m | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
4406B | Batu 11 Segari | Northern |  | Modernization |  | 2023Q2 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-13 |  | 2023-04-15 |  | Closed | 2023-04-19 | 2023-05-06 | CD//Quah | 2023-05-06 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230413-0006 | DU00002007762 |  |  | 2023-06-08 | 2023-05-24 |  | Tower | 60m 3 Legged Tower | 65 | Add R9264H M901821 x3,Dismantle R8860E-GU908 x1+R8862A S1800(B6A) x3+R8840-U216 x3
4431C | Jelapang 1 | Northern |  | Modernization |  | 2023Q2 | MH | YPTT | 4.6 TSSR Approved |  | 2023-04-14 | 2023-04-28 |  | 2023-04-19 |  | Closed | 2023-05-01 | 2023-05-25 | CD//Heng | 2023-05-03 | Celcom Digi_RAN-YPTT-TSS-Northern-20230414-0005 | DU00002007763 |  |  | 2023-06-01 | 2023-06-01 |  | Tower | 45m 3 Legged Tower | 45 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 12
A00285 | A040C_A00285OD_TMNSRIDESA | Northern | 4026K | Swap |  | 2023Q2 | MH | GTSB | 4.6 TSSR Approved |  | 2023-04-09 |  |  | 2023-04-15 |  | Closed | 2023-04-19 | 2023-05-06 | CD//Quah | 2023-05-06 | Celcom Digi_RAN-GTSB-TSS-Northern-20230410-0007 | DU00002007764 |  |  | 2023-06-22 | 2023-06-15 |  | Wall mount boom | MINI STRUCTURE | 8 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle Celcom all RRU&BBU
9115A | Bukit Setiam (Celcom) | Sarawak |  | Modernization |  | 2023Q3 | HQ 1 | Magicell | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-08 |  | 2023-05-11 |  | Closed | 2023-05-30 | 2023-06-08 | E//Hannah | 2023-06-09 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230508-0006 | DU00002007765 |  |  | 2023-07-17 | 2023-07-07 |  | Tower | Tower | 100M | Add R9264M M1821 x4,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 3
4500B | Kg Tawas | Northern |  | Modernization |  | 2023Q2 | WP | GTSB | 4.6 TSSR Approved |  | 2023-04-05 | 2023-04-15 |  | 2023-04-14 |  | Closed | 2023-04-28 | 2023-05-07 | CD//Heng | 2023-05-05 | Celcom Digi_RAN-GTSB-TSS-Northern-20230410-0007 | DU00002007766 |  |  | 2023-05-20 | 2023-05-20 |  | Tower | 45m 3 Legged Tower | 60 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
4745B | Batu 15 Lekir | Northern |  | Modernization |  | 2023Q2 | MH | GTSB | 4.6 TSSR Approved |  | 2023-04-05 | 2023-04-14 |  | 2023-04-06 |  | Closed | 2023-04-15 | 2023-05-10 | CD//Quah | 2023-05-10 | Celcom Digi_RAN-GTSB-TSS-Northern-20230410-0007 | DU00002007767 |  |  | 2023-05-17 | 2023-05-15 |  |  | Tower | 60 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3
B00352 | B058E_B00352OD_SGMANGGIS | Central |  | Decomm |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-07 |  |  |  | 2023-08-02 |  | 2023-08-02 | 2023-10-18 | CD//Sapian | 2023-08-17 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002007768 |  | EXTRA IDU |  |  | 2023-07-20 | Tower | TOWER | 46M
4345C | Meru Permai | Northern |  | Modernization |  | 2023Q2 | WP | GTSB | 4.6 TSSR Approved |  | 2023-04-11 | 2023-04-15 |  | 2023-04-15 |  | Closed | 2023-04-28 | 2023-05-25 | CD//Quah | 2023-05-11 | Celcom Digi_RAN-GTSB-TSS-Northern-20230411-0008 | DU00002007769 |  |  | 2023-06-08 | 2023-06-03 |  |  | 3m Bipod (RT) | 2 | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3 |  | 3
9045R | SEBAUH | Sarawak |  | Maintain USP MOCN(Dismantle Passive) | Maintain USP MOCN(Dismantle Passive)->On Hold->Maintain USP MOCN(Dismantle Passive) | 2023Q3 | HW | Magicell | 4.6 TSSR Approved |  | 2025-06-18 |  | 2025-06-18 |  | 2025-07-17 |  | 2025-08-08 | 2026-01-20 | E//John | 2025-08-11 | SQ202506110081-Magicell/SQ202507140221-Magicell | DU00002007770 |  |  |  |  | 2025-11-20 |  | Land site
7637A | Tomher Industrial | Sabah |  | Modernization |  | 2023Q2 | HQ 5 | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-14 |  | 2023-04-18 |  | Closed | 2023-04-23 | 2023-06-08 | CD//Jahganathan | 2023-06-09 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002007771 |  |  | 2023-06-24 | 2023-06-12 |  | Tower | 60m 3 Legged Tower | 60 | Add A9732 M1821 x3,Dismantle R8862A S2600(A4A) x2+R9224E M1821(AAB) x5 | 123
4538B | Ulu Kuang RDD | Northern |  | Modernization |  | 2023Q2 | SM | YPTT | 4.6 TSSR Approved |  | 2023-04-13 | 2023-04-17 |  | 2023-04-19 |  | Closed | 2023-04-26 | 2023-05-25 | CD//Heng | 2023-05-03 | Celcom Digi_RAN-YPTT-TSS-Northern-20230414-0005 | DU00002007772 |  |  | 2023-06-22 | 2023-06-03 |  | Tower | Tower | 60 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x3 | 12
9375B | Rantau Panjang | Sarawak |  | Modernization |  | 2023Q2 | HQ 1 | AllStar | 4.6 TSSR Approved |  | 2023-04-06 | 2023-04-12 |  | 2023-04-14 |  | Closed | 2023-05-11 | 2023-05-18 | CD//John | 2023-05-11 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230403-0003 | DU00002007773 |  |  | 2023-08-08 | 2023-07-14 |  | Tower | 60m 3 Legged Tower | 60 | Add A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8882 S1800B(B6B) x3+R8854D S2100(A4A) x3 | 13
9584B | Sg Mawar Sibu | Sarawak |  | Modernization |  | 2023Q2 | SH | CCSMY | 4.6 TSSR Approved |  | 2023-04-03 | 2023-04-20 |  | 2023-04-29 |  | Closed | 2023-05-02 | 2023-05-03 | CD//John | 2023-05-03 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230403-0003 | DU00002007774 |  |  | 2023-05-29 | 2023-05-22 |  | Tower | Tower | 47m | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3
4552B | Sek Men Izzuddin Shah | Northern |  | Modernization |  | 2023Q2 | ZA | GTSB | 4.6 TSSR Approved | AAU Cannot Install-Change MM to normal sector¦pbts cant install AAU | 2023-04-11 | 2023-04-13 |  | 2023-04-14 |  | Closed | 2023-04-14 | 2023-05-25 | CD//Quah | 2023-05-10 | Celcom Digi_RAN-GTSB-TSS-Northern-20230411-0008 | DU00002007775 | NIC_S2_Change MM to normal sector_loading issue_PROSONTECH SDN BHD |  | 2023-05-30 | 2023-05-27 |  | Minaret | 25m pBTS | 30 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3 | 0
A01133 | A040C_A01133OD_TMN_MERU2B_IPH | Northern | 4033K | Swap |  | 2023Q2 | MH | GTSB | 4.6 TSSR Approved |  | 2023-04-13 | 2023-04-20 |  | 2023-04-26 |  | Closed | 2023-04-28 | 2023-05-09 | CD//Shamsul | 2023-05-09 | Celcom Digi_RAN-GTSB-TSS-Northern-20230414-0010 | DU00002007776 |  |  | 2023-06-13 | 2023-06-09 |  | Minaret | MINARET | 21 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
7226B | Harmony Industrial Park | Sabah |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-05 |  | 2023-04-13 |  | Closed | 2023-04-14 | 2023-04-28 | CD//Mohidi Jaan | 2023-04-18 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230407-0002 | DU00002007777 |  |  | 2023-07-12 | 2023-07-07 |  |  | Tower | 31 | Add R9264H M901821 x3 + R9264M M1821 x2,Dismantle R8894E M1821(A8A) x3 |  | 13
9233B_IBC | RH HQ IB | Sarawak |  | Modernization |  | 2023Q2 |  | Datasco | 4.6 TSSR Approved |  | 2023-11-02 |  |  | 2023-11-02 |  | Closed | 2023-11-01 | 2023-11-15 |  | 2023-06-10 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231107 | DU00002007778 |  |  | 2023-10-05 | 2023-09-20 |  |  | In-building system |  | Add R8862A S1800 x2,dismantle R8882 S1800B(B6B) x2
9148R | BKTSINGALANG | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2023Q2 | HW | Trintel | 4.6 TSSR Approved |  | 2025-07-29 |  | 2025-08-08 |  | 2025-09-09 |  | 2025-09-12 | 2025-12-08 | E//John | 2025-09-12 | SQ202508190236-Trintel | DU00002007779 |  |  |  |  | 2025-10-09 |  | Land site
9829B | Rh. Sagring | Sarawak |  | Modernization |  | 2023Q2 | BY | Datasco | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦ owner Sacofa reject our TP of adding AAU. | 2023-04-04 | 2023-04-06 |  | 2023-04-14 |  | Rectificating | 2023-04-13 | 2023-06-27 | CD//John | 2023-04-25 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002007780 | NIC_S1_Change MM to BI_owner reject_SACOFA SDN BHD |  | 2023-07-28 | 2023-07-05 |  | Tower | TOWER | 46 | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x3 |  | 3
A00687 | A040C_A00687OD_V_POINT | Northern | 4029K | Swap |  | 2023Q2 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-04-27 | 2023-05-02 |  | 2023-05-03 |  | Closed | 2023-05-05 | 2023-05-10 | CD//Shamsul | 2023-05-10 | Celcom Digi_RAN-GCI-TSS-Northern-20230428-0010 | DU00002007781 |  |  | 2023-06-26 | 2023-06-08 |  | Pole | TRIPOD | 3.8 | Add R9264H M901821 x2,Dismantle Celcom all RRU&BBU
7222B | Taman inanam laut ph2 | Sabah |  | Modernization |  | 2023Q3 | HQ 5 | YPTT | 4.6 TSSR Approved |  | 2023-04-13 | 2024-09-12 |  | 2023-04-13 |  | Closed | 2023-04-28 | 2023-06-13 | CD//Mohidi Jaan | 2023-06-13 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230407-0002 | DU00002007782 |  |  | 2023-07-12 | 2023-07-08 |  | Monopole | 3m Bipod (RT) | 30 | Add R9264M M1821 x5,Dismantle R8894E M1821(A8A) x5 |  | 13
9383B | Taman Harmoni MP | Sarawak |  | Modernization |  | 2023Q2 | HQ 2 | Datasco | 4.6 TSSR Approved |  | 2023-04-05 | 2023-05-05 |  | 2023-05-06 |  | Closed | 2023-05-11 | 2023-05-13 | CD//John | 2023-05-13 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002007783 |  |  | 2023-07-09 | 2023-07-04 |  |  | 30m Monopole | 30 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
9390A | Bukit Lima Timur(TMB-Sacofa) | Sarawak |  | Modernization |  | 2023Q2 | HQ 1 | Datasco | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦sacofa Reject to install AAU | 2023-06-17 | 2023-07-11 |  | 2023-07-13 |  | Rectificating | 2023-07-20 | 2023-07-26 | E//Hannah | 2023-09-29 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230508-0005 | DU00002007784 | NIC_S3_Change MM to BI_owner reject_SACOFA SDN BHD |  | 2024-02-01 | 2023-11-06 |  | Tower | 60m 4 Legged Tower | THE STRUCTURE IS TOO DANGEROUS FOR TEAM TO TAKE THE STRUCTURE HEIGHT BUT IF WE FOLLOW OLD TSSR THE TOWER HEIGHT IS ABOUT 120M | Add R9264M M1821 x3+R9264H M901821 x3+R8862A S2600 x2,Dismantle R8882-GUL1812 x4+R8862A S1800(B6A) x1+R8862A S2100(A6A) x4 |  | 123
7272A | Kolej Ibu Kota | Sabah |  | Modernization |  | 2023Q2 | AD | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-05-08 |  | 2023-04-18 |  | Closed | 2023-04-28 | 2023-05-30 | CD//Jahganathan | 2023-05-29 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002007785 |  |  | 2023-06-11 | 2023-06-08 |  | Tower | Tower | 45 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3
4459B | Kg Bakar Bata | Northern |  | Modernization |  | 2023Q2 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-15 |  | 2023-04-17 |  | Closed | 2023-04-18 | 2023-05-09 | CD//Quah | 2023-05-05 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230413-0006 | DU00002007786 |  |  | 2023-05-16 | 2023-05-15 |  | Tower | 60m 3 Legged Tower | 60 | Add R9264M M1821 x4,Dismantle R8862A S1800(B6A) x3+R8881 S2100 x3 |  | 3
B00374 | B059A_B00374OD_TMJUGRA | Central |  | Decomm |  | 2023Q2 | CR | Datasco | 4.6 TSSR Approved |  | 2023-05-03 |  |  |  | 2024-03-15 |  | 2023-06-15 | 2024-05-31 | CD//Ali akaram | 2023-07-18 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002007787 |  |  |  |  | 2023-11-16 |  | BOOM
B00119 | B058E_B00119OD_CB_PULAUCAREY2 | Central | 1007P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Syafiq |  |  | DU00002007788 | [6 empty] | AESTHETIC MONOPOLE
7475A | Taman Seri Indah (REL) | Sabah |  | Modernization |  | 2023Q3 | HQ 8 | GTSB | 4.6 TSSR Approved |  | 2023-04-04 | 2023-04-20 |  | 2023-04-26 |  | Closed | 2023-04-28 | 2023-05-10 | CD//Ray Amos | 2023-05-10 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230407-0002 | DU00002007789 |  |  | 2023-07-11 | 2023-07-06 |  | Monopole | 3m Boom (RT) | 35 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
9063C | Klinik Kesihatan Sibujaya | Sarawak |  | Modernization |  | 2023Q2 | MA | AllStar | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-26 |  | 2023-04-28 |  | Closed | 2023-05-01 | 2023-05-04 | CD//John | 2023-05-04 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230403-0003 | DU00002007790 |  |  | 2023-06-20 | 2023-06-12 |  | Monopole | 30M Rapole | 30 | Add R9264H M901821 x4,Dismantle R8894E M1821(A8A) x4 | 0 | 0
9387B | Sg Igan Industrial | Sarawak |  | Modernization |  | 2023Q2 | BY | Datasco | 4.6 TSSR Approved |  | 2023-04-13 | 2023-04-13 |  | 2023-04-15 |  | Closed | 2023-04-18 | 2023-04-25 | CD//John | 2023-04-25 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002007791 |  |  | 2023-07-25 | 2023-07-10 |  | Tower | Tower | 77 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
A00459 | A043B_A00459OD_CB_BT15LEKIR | Northern |  | Decomm |  | 2023Q2 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-04-05 | 2023-04-05 |  |  | 2023-06-16 |  | 2023-06-20 | 2023-07-21 | CD//Affendi | 2023-06-21 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230717-0022/Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1 | DU00002007792 |  |  |  |  | 2023-06-25 | Tower | TOWER | 60
7208B | Kolombong Industrial | Sabah |  | Modernization |  | 2023Q3 | HQ 3 | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-04 |  | 2023-04-13 |  | Closed | 2023-04-26 | 2023-04-28 | CD//Mohidi Jaan | 2023-04-18 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002007793 |  |  | 2023-07-10 | 2023-07-08 |  | Unipole | 3m Bipod (RT) | 2m | Add R9264M M1821 x5 + R8862A S2601 x2,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 |  | 23
4657C | Tmn Kledang Raya | Northern |  | Modernization |  | 2023Q2 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-04-13 | 2023-04-15 |  | 2023-04-18 |  | Closed | 2023-04-19 | 2023-05-09 | CD//Quah | 2023-05-06 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230414-0007 | DU00002007794 |  |  | 2023-05-26 | 2023-05-26 |  | Lampole | 24m Lampole | 30 | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
7128B | UMS Kg. C | Sabah |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-04-07 | 2023-04-20 |  | 2023-04-19 |  | Closed | 2023-04-28 | 2023-06-13 | CD//Jahganathan | 2023-06-13 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230407-0002 | DU00002007795 |  |  | 2023-07-14 | 2023-07-07 |  | Lampole | 30m Lampole | 25m | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3
7076H | 99 Speedmart UNIVERSITI PLAZA | Sabah |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007796 | [6 empty] | Small Cell
4246C | Tiger lane (REL) | Northern |  | Modernization |  | 2023Q2 | MH | GTSB | 4.6 TSSR Approved |  | 2023-04-11 | 2023-04-15 |  | 2023-04-14 |  | Closed | 2023-04-17 | 2023-05-18 | CD//Shamsul | 2023-05-09 | Celcom Digi_RAN-GTSB-TSS-Northern-20230411-0008 | DU00002007797 |  |  | 2023-05-21 | 2023-05-21 |  | Lampole | 24m Lampole | 30M | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882 S1800B(B6B) x3
9337B | Belaga | Sarawak |  | Modernization | Modernization->Maintain USP MOCN->Modernization->On Hold->Modernization | 2023Q3 | HQ 1 | AllStar | 4.6 TSSR Approved |  | 2023-04-17 | 2023-05-05 |  | 2023-05-11 |  | Closed | 2023-05-15 | 2023-05-19 | CD//John | 2023-05-15 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230403-0003 | DU00002007798 |  |  | 2023-06-26 | 2023-06-22 |  |  | Tower | 76 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
9136B | Kg Jepak | Sarawak |  | Site Out (Modernization) | Modernization->MOCN Decomm->Site Out->Replacement, Site Out (Modernization) | 2023Q3 |  | Magicell | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2025-07-31 |  | 2025-08-12 |  |  | To be Submitted |  |  |  |  | SQ202507160538-Magicell | DU00002007799 | [6 empty] | 30m Rapole
4496A | LAP Tasek 1&2 | Northern |  | Modernization |  | 2023Q2 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-04-05 | 2023-04-06 |  | 2023-04-06 |  | Closed | 2023-04-13 | 2023-05-05 | CD//Heng | 2023-04-28 | Celcom Digi_RAN-GTSB-TSS-Northern-20230410-0007 | DU00002007800 |  |  | 2023-05-23 | 2023-05-23 |  |  | 60m 4 Legged Tower | 40 | Add A9732 M1821 x3 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x4 | 123
7635A | Menggatal Town | Sabah |  | Modernization |  | 2023Q2 | HQ 6 | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-05-08 |  | 2023-05-05 |  | Rectificating | 2023-05-05 | 2023-05-11 | CD//Jahganathan | 2023-05-11 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002007801 |  |  | 2023-06-06 | 2023-06-02 |  | Pole | 3m RT (Wall Mounted Pole) |  | Add R9264M M1821 x6 + R8862A S2601 x2,Dismantle R8894E M1821(A8A) x4 |  | 23
9686A | Kemena Industrial 2 | Sarawak |  | Modernization |  | 2023Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2023-04-04 | 2023-04-26 |  | 2023-05-01 |  | Closed | 2023-05-03 | 2023-05-03 | CD//John | 2023-05-03 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230403-0003 | DU00002007802 |  |  | 2023-07-27 | 2023-07-21 |  |  | 30m Rapole | 31m | Add R9264H M901821 x3,Dismantle R8882 S1800B(B6B) x3 | 0 | 0
9836A | Premier Dept. Store | Sarawak |  | Modernization |  | 2023Q2 | SH | Datasco | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-20 |  | 2023-05-01 |  | Closed | 2023-05-03 | 2023-05-10 | CD//John | 2023-05-10 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002007803 |  |  | 2023-07-11 | 2023-06-22 |  |  | In-building system |  | Add R8862A S1800 x1 + R8862A S2100 x1,Dismantle R8882-GUL1812 x1
7125B | UMS Sains Teknologi | Sabah |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-04-05 |  |  | 2023-04-15 |  | Rectificating | 2023-04-23 | 2023-06-08 | CD//Jahganathan | 2023-06-09 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230407-0002 | DU00002007804 |  |  | 2023-07-13 | 2023-07-12 |  | BillBoard | 3m RT (Minimast) | 26 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3
A00406 | A042D_A00406OD_CB_PKLNBARU | Northern | 4027K | Swap |  | 2023Q2 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-04-09 | 2023-04-12 |  | 2023-04-18 |  | Closed | 2023-04-19 | 2023-05-05 | CD//Shamsul | 2023-05-05 | Celcom Digi_RAN-GTSB-TSS-Northern-20230410-0007 | DU00002007805 |  |  | 2023-06-13 | 2023-05-25 |  |  | TOWER | 60 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 3
A00058 | A042D_A00058OD_KGKEDAH | Northern | 4023K | Swap |  | 2023Q2 | ZA | GCI | 4.6 TSSR Approved |  | 2023-04-20 | 2023-05-04 |  | 2023-05-06 |  | Closed | 2023-05-08 | 2023-05-10 | CD//Shamsul | 2023-05-10 | Celcom Digi_RAN-GCI-TSS-Northern-20230425-0009 | DU00002007806 |  |  | 2023-06-06 | 2023-05-27 |  | Tower | TOWER | 60m | Add R9264H M901821 x3,Dismantle Celcom all RRU&BBU
4376C | Tmn Pauh Indah | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-12 |  | 2023-05-18 |  | Closed | 2023-05-22 | 2023-05-31 | E//Hazida | 2023-05-31 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0016 | DU00002007807 |  |  | 2023-06-10 | 2023-06-08 |  | Pole | 30m Monopole | 8M | Add R9264H M901821 x3 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 |  | 3
A00035 | A042D_A00035OD_CB_KGCHEPUTEH_RCC | Northern |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2023Q2 |  | NR services | 15.3 Decomm Done without TSSR | [6 empty] | To be Submitted |  |  | CD//Heng |  | SQ202504230465-NR services | DU00002007808 |  |  |  |  | 2025-09-22 | Tower | TOWER | 64
7632A | Nexus Karabunai Resort | Sabah |  | Modernization |  | 2023Q2 | AD | Datasco | 4.6 TSSR Approved |  | 2023-07-05 | 2023-09-07 |  | 2023-09-12 |  | Closed | 2023-09-12 | 2023-09-13 | E//Hannah | 2023-09-13 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230626 | DU00002007809 |  |  | 2023-09-27 | 2023-09-19 |  | Wall mount boom | IBS + RT (Boom) | 26 | Add R8852E S9000 x3 + R8894E M1821 x3 ,Dismantle R8882-GUL1812 x3+R8840-U216 x3++ | 0
A00287 | A040C_A00287OD_CHEMOR_RCC | Northern |  | Decomm |  | 2023Q2 | ZA | GCI | 4.6 TSSR Approved |  | 2023-05-15 |  |  |  | 2023-06-13 |  | 2023-06-14 | 2023-09-21 | CD//Shamsul | 2023-06-27 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002007810 |  | 18/8: Please Confirm suppose Celcom rack have few IDU due this is CP site |  |  | 2023-07-20 |  | TOWER
7155Z | Kg Sinorut | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  |  | DU00002007811 | [6 empty] | TOWER
B00324 | B058D_B00324OD_PANDAMARAN | Central |  | Decomm |  | 2023Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-04-12 |  |  | 2023-05-30 | 2024-10-21 | Closed | 2023-07-17 | 2023-10-02 | CD//Norhaliza | 2023-09-26 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230626_decom reraise | DU00002007812 |  |  |  |  | 2023-08-15 |  | BOOM
9393B | Long Tunku Osman MP | Sarawak |  | Modernization |  | 2023Q2 | BY | Datasco | 4.6 TSSR Approved |  | 2023-04-04 | 2023-04-10 |  | 2023-04-14 |  | Closed | 2023-04-18 | 2023-04-25 | CD//John | 2023-04-25 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002007813 |  |  | 2023-07-13 | 2023-07-01 |  | Monopole | Tower | 25m | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
7093B | Puri Wawasan Wtk | Sabah |  | Modernization |  | 2023Q3 | MS | Datasco | 4.6 TSSR Approved |  | 2023-04-08 | 2023-05-18 |  | 2023-06-02 |  | Closed | 2023-06-06 | 2023-06-13 | E//Hannah | 2023-06-13 | Celcom Digi_RAN-Datasco- TSS-Sabah-20230407-0002 | DU00002007814 |  |  | 2023-06-28 | 2023-06-24 |  | Pole | 3m Bipod (RT) | 19m | Add R9264M M1821 x5,Dismantle R8894E M1821(A8A) x4 |  | 2
4383B | Batu 8 Segari | Northern |  | Modernization |  | 2023Q2 | WP | GTSB | 4.6 TSSR Approved |  | 2023-04-17 | 2023-05-03 |  | 2023-05-05 |  | Closed | 2023-05-05 | 2023-05-18 | CD//Affendi | 2023-05-09 | Celcom Digi_RAN-GTSB-TSS-Northern-20230417-0011 | DU00002007815 |  |  | 2023-05-24 | 2023-05-24 |  | Tower | 4 Legged Tower | 60 | Add R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3
9136R | RHDINGON | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2023Q3 | AD | Magicell | 4.6 TSSR Approved |  | 2025-06-18 |  | 2025-06-30 |  | 2025-07-15 |  | 2025-08-07 | 2025-10-31 | E//John | 2025-08-11 | SQ202506110081-Magicell/SQ202507140221-Magicell | DU00002007816 |  |  |  |  | 2025-09-19 |  | Land site
7241A | Taman Indah Permai | Sabah |  | Modernization |  | 2023Q2 | HQ 5 | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-12 |  | 2023-04-17 |  | Closed | 2023-04-26 | 2023-05-08 | CD//Jahganathan | 2023-04-27 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002007817 |  |  | 2023-06-03 | 2023-06-02 |  | Unipole | 3m RT (Minimast) |  | Add R9264M M1821 x5,Dismantle R8894E M1821(A8A) x3 |  | 23
4298C | Bandar baru Sri Klebang | Northern |  | Modernization |  | 2023Q2 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-04-17 | 2023-04-29 |  | 2023-04-27 |  | Closed | 2023-05-03 | 2023-05-25 | CD//Heng | 2023-05-09 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230419-0009 | DU00002007818 |  |  | 2023-06-06 | 2023-06-03 |  | Unipole | 3m Bipod (RT) | 3.8 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle R8862A S1800(B6A) x3+R8881 S2100 x3 |  | 3
4933C | Taman Chemor | Northern |  | Modernization |  | 2023Q2 | MH | CCSMY | 4.6 TSSR Approved |  | 2023-04-27 | 2023-05-03 |  | 2023-04-29 |  | Closed | 2023-05-05 | 2023-05-25 | CD//Shamsul | 2023-05-11 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230427-0010 | DU00002007819 |  |  | 2023-06-06 | 2023-06-03 |  | Monopole | 30m Monopole | 32 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 3
7107B | University Apartment | Sabah |  | Modernization |  | 2023Q3 | AD | YPTT | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦Limitted space to install AAU,Space is ouccuped by cable and limitted space to install new AAU. | 2023-04-08 | 2024-09-12 |  | 2023-04-13 |  | Closed | 2023-04-25 | 2023-05-19 | CD//Jahganathan | 2023-05-17 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230407-0002 | DU00002007820 | NIC_S3_Change MM to BI_Space constraint_Digi OB |  | 2023-06-09 | 2023-06-06 |  | Lampole | 24m 3 Legged Tower | 24 | Add R9264H M901821 x3 + R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3 |  | 123
9258B | Sing Kwong | Sarawak |  | Modernization |  | 2023Q2 | HQ 1 | Trintel | 4.6 TSSR Approved |  | 2023-04-05 | 2023-05-02 |  | 2023-05-05 |  | Closed | 2023-05-08 | 2023-05-15 | CD//John | 2023-05-15 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230403-0003 | DU00002007821 |  |  | 2023-06-27 | 2023-06-24 |  | Monopole | 30m Rapole | 30m | Add R9264M M1821 x5,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x2 |  | 23
4374H | 99 Speedmart PK Tmn Klebang Ria | Northern |  | MOCN As-Is |  | 2023Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007822 | [6 empty] | Rooftop
B00363 | B061C_B00363OD_TMJLNKEBUN | Central | 1014K | Swap |  | 2023Q3 | YZ | Futong | 4.6 TSSR Approved |  | 2023-05-24 | 2023-05-29 |  | 2023-06-01 |  | Closed | 2023-06-02 | 2023-06-12 | CD//Sapian | 2023-06-12 | CelcomDigi_RAN_Futong_TSS_Central_20230508_0001 | DU00002007823 |  |  | 2023-10-12 | 2023-09-22 |  | Monopole | MONOPOLE | 45 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 2
4724C | Penang Porth North Butterworth (REL) | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-06 | 2023-05-11 |  | 2023-05-17 |  | Closed | 2023-06-01 | 2023-06-13 | CD//Shamsul | 2023-06-13 | Celcom Digi_RAN-GTSB-TSS-Northern-20230502-0012 | DU00002007824 |  |  | 2023-06-21 | 2023-06-19 |  | Minimast | 3m Boom (RT) | 8 | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
4526A | LAP Pekan Rezeki RCC | Northern |  | Modernization |  | 2023Q2 | MH | GTSB | 4.6 TSSR Approved |  | 2023-04-09 |  |  | 2023-04-14 |  | Closed | 2023-04-17 | 2023-05-07 | CD//Quah | 2023-05-05 | Celcom Digi_RAN-GTSB-TSS-Northern-20230410-0007 | DU00002007825 |  |  | 2023-05-16 | 2023-05-15 |  |  | Watertank Structure | 18 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
A01121 | A042D_A01121OD_KG_BAKAR_BATA | Northern |  | Decomm |  | 2023Q2 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-04-13 |  |  |  | 2023-06-20 |  | 2023-06-22 | 2023-07-21 | CD//Heng | 2023-07-13 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V2 | DU00002007826 |  |  |  |  | 2023-07-05 |  | TOWER
9197B | Lehdo Enterprise (REL) | Sarawak |  | Modernization |  | 2023Q2 | HQ 1 | Datasco | 4.6 TSSR Approved |  | 2023-04-12 | 2023-05-08 |  | 2023-05-10 |  | Closed | 2023-05-16 | 2023-05-16 | CD//Norhaliza | 2023-05-16 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230419-0003 | DU00002007827 |  |  | 2023-07-12 | 2023-06-26 |  |  | 3m RT (Wall Mounted Pole) |  | Add A9732 M1821 x3,Dismantle R8882 S2600(B4A) x3+R8894E M1821(A8A) x6 | 123
4385B | Batu 5 Segari RDC | Northern |  | Modernization |  | 2023Q2 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-04-05 | 2023-04-14 |  | 2023-04-18 |  | Closed | 2023-04-18 | 2023-05-10 | CD//Quah | 2023-05-03 | Celcom Digi_RAN-GTSB-TSS-Northern-20230410-0007 | DU00002007828 |  |  | 2023-05-16 | 2023-05-15 |  | Tower | 60m 4 Legged Tower | 50 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8860E-GU908 x1+R8882-GUL1812 x2+R8862A S1800(B6A) x3+R8840-U216 x2
4709B | Manjung Parade | Northern |  | Modernization |  | 2023Q2 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-04-13 | 2023-04-15 |  | 2023-04-17 |  | Closed | 2023-04-25 | 2023-05-18 | CD//Quah | 2023-05-11 | Celcom Digi_RAN-GTSB-TSS-Northern-20230417-0011 | DU00002007829 |  |  | 2023-05-28 | 2023-05-26 |  | Lampole | 60m 4 Legged Tower | 30M | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8840-U216 x3
7060A | Putera Jaya | Sabah |  | Modernization |  | 2023Q2 | HQ 2 | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-03 |  | 2023-04-15 |  | Closed | 2023-04-14 | 2023-04-28 | CD//Mohidi Jaan | 2023-04-18 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002007830 |  |  | 2023-06-06 | 2023-06-02 |  | Minimast | 25m Guyed Mast | 27 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
7222H | 99 Speedmart Telipok Town | Sabah |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007831 | [6 empty] | Rooftop
A00133 | PREMISRCC | Northern |  | Decomm |  | 2023Q2 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-04-17 |  |  |  | 2023-06-16 |  | 2023-06-21 | 2024-03-26 | CD//Heng | 2023-07-13 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V2/Celcom Digi_RAN-CCSMY-TSS Decomm-Northern-20240131-0091 | DU00002007832 |  | Wrong TX info compare with TX solution 21/2: Please Include all Equipment in Celcom Rack |  |  | 2023-07-21 |  | TOWER
B00378 | B058C_B00378OD_TMSRIANDALAS | Central | 1016K | Swap |  | 2023Q2 | YZ | Ascentrack | 4.6 TSSR Approved |  | 2023-04-18 | 2023-04-28 |  | 2023-04-29 |  | Closed | 2023-05-02 | 2023-06-05 | CD//Ali akaram | 2023-05-11 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230419_0013 | DU00002007833 |  |  | 2023-08-30 | 2023-08-29 |  | Tower | BOOM | 45 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 12
4630D | Desa Cemara Seberang Jaya (REL) | Northern |  | Modernization |  | 2023Q3 | YZ | CCSMY | 4.6 TSSR Approved |  | 2023-05-07 | 2023-05-16 |  | 2023-05-18 |  | Closed | 2023-05-23 | 2023-06-11 | E//Hazida | 2023-06-11 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0017 | DU00002007834 |  |  | 2023-06-19 | 2023-06-17 |  | Pole | Land site | 6 | Add R9264M M1821 x3,Dismantle R9224E M1821(AAB) x3
A01104 | A040C_A01104OD_CB_BT11_JLN_JELAPANG | Northern |  | Decomm |  | 2023Q2 | SM | GCI | 4.6 TSSR Approved |  | 2023-05-02 |  |  |  | 2023-06-19 |  | 2023-06-21 | 2023-08-08 | CD//Rohizam | 2023-08-02 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V1/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002007835 |  |  |  |  | 2023-07-17 |  | TOWER
4707B | Ladang Huntly (Maxis) RDD | Northern |  | Modernization |  | 2023Q2 | MH | CCSMY | 4.6 TSSR Approved |  | 2023-04-13 | 2023-04-28 |  | 2023-04-28 |  | Closed | 2023-05-01 | 2023-05-25 | CD//Quah | 2023-05-10 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230414-0007 | DU00002007836 |  |  | 2023-05-29 | 2023-05-24 |  | Tower | 60m 3 Legged Tower | 60M | Add R9264H M901821 x3,Dismantle R8860E-GU908 x3+R8882-GUL1812 x3+R8840-U216 x3
A00671 | A040C_A00671OD_TASEKINDUSTRIAL_RDD | Northern |  | Decomm |  | 2023Q2 | MH | GTSB | 4.6 TSSR Approved |  | 2023-04-09 | 2023-04-10 |  |  | 2023-06-17 |  | 2023-06-19 | 2023-08-08 | CD//Shamsul | 2023-06-27 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1/Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230726-0024 | DU00002007837 |  |  |  |  | 2023-07-17 |  | SHARING STRC DIGI | 40
9151A | Chin Soon | Sarawak |  | Modernization |  | 2023Q2 | MA | Datasco | 4.6 TSSR Approved |  | 2023-04-10 |  |  | 2023-04-28 |  | Closed | 2023-05-02 | 2023-05-04 | CD//John | 2023-05-04 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002007838 |  |  | 2023-06-18 | 2023-06-12 |  | Tower | Tower | 46 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2600 x2,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 |  | 12
A00963 | A043B_A00963OD_T3_TELAGANENAS | Northern | 4214P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Heng |  |  | DU00002007839 | [6 empty] | TOWER
9275B | Jalan Upi | Sarawak |  | Modernization |  | 2023Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-04-06 | 2023-04-13 |  | 2023-04-20 |  | Closed | 2023-05-02 | 2023-05-03 | CD//John | 2023-05-03 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230403-0003 | DU00002007840 |  |  | 2023-06-15 | 2023-06-12 |  | Tower | 30m Monopole | 30m | Add R9264M M1821 x5 + R8862A S2601 x2,Dismantle R8894E M1821(A8A) x3 |  | 12
4459C | UIE | Northern |  | Modernization |  | 2023Q2 | ZA | GCI | 4.6 TSSR Approved |  | 2023-04-13 | 2023-04-14 |  | 2023-04-19 |  | Closed | 2023-04-23 | 2023-05-11 | CD//Heng | 2023-04-27 | Celcom Digi_RAN-GCI-TSS-Northern-20230414-0005 | DU00002007841 |  |  | 2023-06-01 | 2023-05-26 |  | Minaret | 30m Monopole | 37M | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 |  | 12
A01043 | A040C_A01043OD_TMNJATI_IPH | Northern |  | Decomm |  | 2023Q2 | MH | YPTT | 4.6 TSSR Approved |  | 2023-04-13 | 2023-06-26 |  |  | 2023-06-23 |  | 2023-06-26 | 2023-09-07 | CD//Affendi | 2023-07-03 | Celcom Digi_RAN-YPTT-TSS-Northern-20230609-0018/Celcom Digi_RAN-YPTT-TSS Decomm-Northern-20240311-0048 | DU00002007842 |  |  |  |  | 2023-07-03 | Minaret | MINARET | 230M
9365A | Mile 16 Jalan Oya | Sarawak |  | Modernization |  | 2023Q2 | HQ 1 | Datasco | 4.6 TSSR Approved |  | 2023-04-16 | 2023-05-05 |  | 2023-05-06 |  | Closed | 2023-05-08 | 2023-05-10 | CD//John | 2023-05-10 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230419-0003 | DU00002007843 |  |  | 2023-06-15 | 2023-06-12 |  | Tower | Tower | 50m | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x3 |  | 1
4245H | 99 Speedmart PK Tmn Seri Indah | Northern |  | MOCN As-Is |  | 2023Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007844 | [6 empty] | Small Cell
9043C | Kolej Vokasional Sibu | Sarawak |  | Modernization |  | 2023Q2 | BY | Datasco | 4.6 TSSR Approved |  | 2023-04-11 | 2023-04-12 |  | 2023-04-15 |  | Closed | 2023-04-18 | 2023-04-25 | CD//John | 2023-04-25 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002007845 |  |  | 2023-06-21 | 2023-06-16 |  |  | 30m Rapole | 30 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
7072C | University Apartment 2 | Sabah |  | Modernization |  | 2023Q3 | HQ 6 | AllStar | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-14 |  | 2023-04-20 |  | Closed | 2023-04-26 | 2023-05-10 | CD//Mohidi Jaan | 2023-05-10 | Celcom Digi_RAN-Allstar-TSS-Sabah-20230407-0002 | DU00002007846 |  |  | 2023-06-11 | 2023-06-09 |  | Monopole | 30m Monopole | 30m | Add R9264H M901821 x3 + R9264M M1821 x2,Dismantle R9224E M1821(AAB) x3 |  | 13
A00538 | A040C_A00538OD_KHANTANIND_W900 | Northern |  | Decomm |  | 2023Q2 | MH | YPTT | 4.6 TSSR Approved |  | 2023-04-13 |  |  |  | 2023-06-24 |  | 2023-06-26 |  | CD//Shamsul | 2023-07-05 | Celcom Digi_RAN-YPTT-TSS-Northern-20230609-0018 | DU00002007847 |  | Need include full photo for UNUSED Equiment |  |  | 2023-07-22 |  | TOWER
A00523 | A043B_A00523OD_CB_TLKSENANGIN | Northern |  | Decomm |  | 2023Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2023-04-11 | 2023-06-26 |  |  | 2023-06-19 |  | 2023-06-20 | 2023-06-28 | CD//Affendi | 2023-06-21 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230717-0022/Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1 | DU00002007848 |  |  |  |  | 2023-07-04 | Tower | TOWER | 60
7110B | UMS Kg. E | Sabah |  | Modernization |  | 2023Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2023-07-08 | 2023-07-10 |  | 2023-07-12 |  | Closed | 2023-07-13 | 2023-07-17 | E//Hannah | 2023-07-17 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230626 | DU00002007849 |  |  | 2023-07-30 | 2023-07-30 |  | Lampole | 30m Lampole | 25 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3
9241Z | T3E_0798 Rantau Dilang | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007850 | [6 empty] | Tower
4295A | Tabung Haji Prai | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-16 |  | 2023-05-18 |  | Closed | 2023-05-23 | 2023-06-27 | E//Hazida | 2023-06-27 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0017 | DU00002007851 |  |  | 2023-06-26 | 2023-06-19 |  | Lampole | 3m Boom (RT) | 27m | Add A9732 M1821 x3,Dismantle R8882-GUL1812 x3+R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 | 123
7120B | Kiansam 3GDen | Sabah |  | Modernization |  | 2023Q3 | HQ 3 | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-05-08 |  | 2023-04-19 |  | Closed | 2023-04-25 | 2023-06-01 | CD//Jahganathan | 2023-05-30 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002007852 |  |  | 2023-07-03 | 2023-06-26 |  | Monopole | 30m Monopole | 45 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3
B00028 | B058D_B00028OD_STNSULAIMAN | Central | 1011K | Swap |  | 2023Q2 | MA | Datasco | 4.6 TSSR Approved |  | 2023-04-14 | 2023-05-04 |  | 2023-05-07 |  | Closed | 2023-05-10 | 2023-06-05 | CD//Ali akaram | 2023-05-22 | CelcomDigi_RAN_Datasco_TSS_Central_20230417_0012 | DU00002007853 |  |  | 2023-06-22 | 2023-06-19 |  | Minaret | MINI STRUCTURE | 44m | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU | 13
9036C | Jalan Ruby | Sarawak |  | Modernization |  | 2023Q2 | BY | Trintel | 4.6 TSSR Approved |  | 2023-04-11 | 2023-04-12 |  | 2023-04-13 |  | Rectificating | 2023-04-18 | 2023-05-09 | CD//John | 2023-04-25 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230403-0003 | DU00002007854 |  |  | 2023-05-25 | 2023-05-24 |  | Pole | 3m Boom (RT) |  | Add R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
9238B | Ulu Sg Merah Commercial | Sarawak |  | Modernization |  | 2023Q2 | ZB | CCSMY | 4.6 TSSR Approved |  | 2023-06-16 | 2023-07-13 |  | 2023-07-18 |  | Closed | 2023-07-21 | 2023-07-26 | CD//Norhaliza | 2023-07-25 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230626 | DU00002007855 |  |  | 2023-08-14 | 2023-08-10 |  | Monopole | 30m Monopole | 15.32m | Add R9264H M901821 x3,Dismantle R8882 S1800B(B6B) x3
7179B | Wismas | Sabah |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-18 |  | 2023-04-14 |  | Closed | 2023-04-25 | 2023-05-05 | CD//Ray Amos | 2023-05-05 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230407-0002 | DU00002007856 |  |  | 2023-07-07 | 2023-06-09 |  | Pole | 3m Bipod (RT) | 2 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8882 S1800B(B6B) x3+R8881 S2100 x3 |  | 1
9280B | Nang Sang | Sarawak |  | Modernization |  | 2023Q2 | SH | CCSMY | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦9280B reject by site Owner Sacofa. Site owner don't allow DIGI add antenna on tower. | 2023-04-06 | 2023-05-09 |  | 2023-05-14 |  | Closed | 2023-06-28 | 2023-05-25 | E//Hannah | 2023-05-26 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230403-0003 | DU00002007857 | NIC_S2_Change MM to BI_owner reject_SACOFA SDN BHD |  | 2023-08-04 | 2023-07-25 |  | Monopole | 30m Monopole | 30 | Add R9264M M1821 x5 + R8862A S2600 x2,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 |  | 12
4349A | Ipoh Tunnel IB (Inside tunnel) | Northern |  | Modernization |  | 2023Q2 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-06-19 | 2023-06-19 |  | 2023-06-19 |  | Closed | 2023-06-22 | 2024-06-28 | CD//Shamsul | 2023-07-04 | Celcom Digi_RAN-GCI-TSS-Northern-20230425-0009 | DU00002007858 | Remarks: Solution TSSR/BOM Changed |  | 2023-07-08 | 2023-06-22 |  | Lampole | 3m Bipod (RT) | 33 | Add R8852E S9000 x2 + R8894E M1821 x2,Dismantle R8882 S1800(B) x1+R8882 S1800B(B6B) x1++R8881 S2100 x2+ | 0
4996C | Klebang Bayu | Northern |  | Modernization |  | 2023Q2 | MH | GTSB | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-20 |  | 2023-04-27 |  | Closed | 2023-04-28 | 2023-05-25 | CD//Quah | 2023-05-08 | Celcom Digi_RAN-GTSB-TSS-Northern-20230413-0009 | DU00002007859 |  |  | 2023-06-10 | 2023-06-09 |  | Minaret | Tower | 30 | Add R9264M M1821 x4 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 3
7221H | 99 Speedmart Inanam Point | Sabah |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007860 | [6 empty] | Rooftop
4194B | Bagan Dalam | Northern |  | Modernization |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-04-28 | 2023-05-02 |  | 2023-05-07 |  | Closed | 2023-05-08 | 2023-06-13 | CD//Heng | 2023-06-07 | Celcom Digi_RAN-GCI-TSS-Northern-20230502-0011 | DU00002007861 |  |  | 2023-06-13 | 2023-06-12 |  | H-bracket pole | 6m RT (Boom) | 6m | Add R9264M M1821 x5+R9264H M901821 x1,Dismantle R8894E M1821(A8A) x5 |  | (S1->S2,S2->S3，S3->S4,new sector is S1,,rename sector ID,Bisector@New S2/S3)
7267C | UCA 2 | Sabah |  | Modernization |  | 2023Q2 | HQ 3 | Futong | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-14 |  | 2023-04-18 |  | Closed | 2023-04-23 | 2023-05-05 | CD//Mohidi Jaan | 2023-05-05 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002007862 |  |  | 2023-06-09 | 2023-06-09 |  | Monopole | 30M Monopole | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
9038C | Sibujaya 4 | Sarawak |  | Modernization |  | 2023Q2 | HQ 1 | Datasco | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI,L2600 change to 40M¦ Sacofa lamppoe not allow to add antenna on tower | 2023-04-04 | 2023-05-05 |  | 2023-05-08 |  | Closed | 2023-06-28 | 2023-05-11 | CD//John | 2023-07-04 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002007863 | NIC_S3_Change MM to BI,L2600 change to 40M_owner reject_SACOFA SDN BHD |  | 2024-01-25 | 2023-12-16 |  | Pole | 30m Monopole | 30 | Add R9264H M901821 x3 + R9264M M1821 x3,Dismantle R8894E M1821(A8A) x5 |  | 123
7130B | UMS Masjid Besar | Sabah |  | Modernization |  | 2023Q3 | HQ 2 | GTSB | 4.6 TSSR Approved |  | 2023-04-10 | 2023-04-25 |  | 2023-04-28 |  | Closed | 2023-05-06 | 2023-05-25 | CD//Jahganathan | 2023-05-11 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230407-0002 | DU00002007864 |  |  | 2023-07-03 | 2023-06-09 |  | Monopole | 30m Lampole | 26 | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3
7213H | 99 Speedmart Inanam Town | Sabah |  | MOCN As-Is |  | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007865 | [6 empty] | Rooftop
4887A | Sony Prai | Northern |  | Modernization |  | 2023Q3 | WP | GTSB | 4.6 TSSR Approved |  | 2023-05-11 | 2023-05-13 |  | 2023-05-18 |  | Rectificating | 2023-06-20 | 2023-06-27 | E//Hazida | 2023-06-21 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0014 | DU00002007866 |  |  | 2023-07-14 | 2023-07-12 |  | Wall mount boom | In-building system | 7M | Add + R8862A S1800 x2 + R8862A S2100 x2 + R8862A S2601 x2,Dismantle R8882-GUL1812 x1
4225H | 99 Speedmart PK Chepor Indah | Northern |  | MOCN As-Is |  | 2023Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007867 | [6 empty] | Small Cell
4310A | Kg Matang Acheh-100Q4(Digi Trunk)_REL | Northern |  | Modernization |  | 2023Q2 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-04-12 | 2023-05-09 |  | 2023-04-17 |  | Closed | 2023-04-18 | 2023-05-10 | CD//Affendi | 2023-04-28 | Celcom Digi_RAN-YPTT-TSS-Northern-20230413-0004 | DU00002007868 |  |  | 2023-05-16 | 2023-05-15 |  | Tower | 35m Tower | 61M | Add R9264M M1821 x3,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3
4359B | Klebang Ind RCC | Northern |  | Modernization |  | 2023Q2 | WP | GTSB | 4.6 TSSR Approved |  | 2023-04-12 | 2023-05-03 |  | 2023-05-05 |  | Closed | 2023-05-07 | 2023-06-12 | CD//Heng | 2023-06-12 | Celcom Digi_RAN-GTSB-TSS-Northern-20230413-0009 | DU00002007869 |  |  | 2023-06-19 | 2023-06-03 |  |  | 60m 3 Legged Tower | 90 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 13(MM@New S1/S2)
7263C | Nountun Apartment | Sabah |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-06 |  | 2023-04-13 |  | Closed | 2023-04-16 | 2023-04-25 | CD//Mohidi Jaan | 2023-04-21 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230407-0002 | DU00002007870 |  |  | 2023-07-07 | 2023-07-04 |  | Tower | Land site | 46m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
4553A | PKNP(ZED) RCC | Northern |  | Modernization |  | 2023Q2 | ZA | GCI | 4.6 TSSR Approved |  | 2023-05-03 | 2023-04-17 |  | 2023-05-05 |  | Closed | 2023-05-11 | 2023-06-08 | E//Hazida | 2023-06-09 | Celcom Digi_RAN-GCI-TSS-Northern-20230417-0006 | DU00002007871 |  |  | 2023-06-13 | 2023-06-12 |  | Wall mount boom | 3m Boom (RT) | 6m | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8862A S2601(A6A) x1+R8894E M1821(A8A) x3+R9224E M1821(AAB) x1+ R8882-GUL1812 x2 | 23
4489A | Changkat Kruing RDD | Northern |  | Modernization |  | 2023Q2 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-04-13 | 2023-05-09 |  | 2023-04-27 |  | Closed | 2023-05-12 | 2023-05-25 | CD//Quah | 2023-05-17 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230414-0007 | DU00002007872 |  |  | 2023-05-26 | 2023-05-24 |  | Tower | 60m 3 Legged Tower | 65 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8860E-GU908 x2+R8882-GUL1812 x3+R8854D S2100(A4A) x3 |  | 12
7286A | Alam Mesra | Sabah |  | Modernization |  | 2023Q3 | HQ 5 | GTSB | 4.6 TSSR Approved |  | 2023-04-04 |  |  | 2023-04-20 |  | Closed | 2023-04-25 | 2023-05-09 | CD//Jahganathan | 2023-05-09 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230407-0002 | DU00002007873 |  |  | 2023-07-11 | 2023-07-07 |  | Minimast | 3m RT (Minimast) | 8 | Add A9732 M1821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 123
4474C | Akademi Badminton Perak | Northern |  | Modernization |  | 2023Q2 | WP | GTSB | 4.6 TSSR Approved |  | 2023-04-13 | 2023-05-02 |  | 2023-05-03 |  | Closed | 2023-05-04 | 2023-05-25 | CD//Quah | 2023-05-15 | Celcom Digi_RAN-GTSB-TSS-Northern-20230414-0010 | DU00002007874 |  |  | 2023-06-01 | 2023-06-01 |  | Monopole | 24m Lampole | 30 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8881 S2100 x3 | 0 | 0
9008M | Sibu Mission Road DS Micro | Sarawak |  | MOCN As-Is |  | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007875 | [6 empty] | Micro Cell
4280C | DiGi Green Town Office | Northern |  | Modernization |  | 2023Q2 | SM | YPTT | 4.6 TSSR Approved |  | 2023-04-13 | 2023-04-17 |  | 2023-04-19 |  | Closed | 2023-04-20 | 2023-05-12 | CD//Heng | 2023-04-26 | Celcom Digi_RAN-YPTT-TSS-Northern-20230414-0005 | DU00002007876 |  |  | 2023-05-16 | 2023-05-15 |  | Pole | 3m Bipod (RT) | 2M | Add R8894E M1821 x3 + R8862A S2601 x3,Dismantle R8882 S1800B(B6B) x3+R8881 S2100 x3
7165A | ITM Sepangar | Sabah |  | Modernization |  | 2023Q2 | AD | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-05-08 |  | 2023-05-19 |  | Closed | 2023-05-26 | 2023-06-17 | E//Hannah | 2023-06-15 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002007877 |  |  | 2023-06-28 | 2023-06-21 |  | Tower | Tower | 30 | Add A9732 M1821 x3,Dismantle R8882 S1800B(B6B) x3+R8854D S2100(A4A) x3 | 123
4217D | Taman Nagasari (REL) | Northern |  | Modernization |  | 2023Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-04-29 | 2023-05-04 |  | 2023-05-07 |  | Closed | 2023-05-09 | 2023-05-25 | CD//Affendi | 2023-05-09 | Celcom Digi_RAN-GCI-TSS-Northern-20230502-0011 | DU00002007878 |  |  | 2023-06-16 | 2023-06-14 |  | Wall mount boom | 6m RT (Boom) | 6 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R9224E M1821(AAB) x3 | 123
A00040 | A042D_A00040OD_CB_KGTENGAH_RCD | Northern |  | Decomm | Swap->Decomm->On Hold->Decomm | 2023Q2 | MH | YPTT | 4.6 TSSR Approved |  | 2023-05-10 |  |  |  | 2023-06-14 |  | 2023-06-16 | 2023-09-18 | CD//Affendi | 2023-06-27 | Celcom Digi_RAN-YPTT-TSS-Northern-20230919-0036 | DU00002007879 |  | 11/9: Antenna NE & FE same photo |  |  | 2023-06-23 |  | TOWER
4581B | Kayan (Maxis) | Northern |  | Modernization |  | 2023Q2 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-04-13 | 2023-04-19 |  | 2023-04-15 |  | Closed | 2023-04-20 | 2023-05-12 | CD//Quah | 2023-05-06 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230413-0006 | DU00002007880 |  |  | 2023-05-23 | 2023-05-23 |  | Tower | 60m 3 Legged Tower | 66 | Add R9264H M901821 x3,Dismantle R8860E-GU908 x3+R8862A S1800(B6A) x3+R8840-U216 x3
9114A | Tatau Bazaar | Sarawak |  | Modernization |  | 2023Q3 | SH | Magicell | 4.6 TSSR Approved |  | 2023-04-19 | 2023-04-27 |  | 2023-05-02 |  | Closed | 2023-05-05 | 2023-05-07 | CD//John | 2023-05-04 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230425-0003 | DU00002007881 |  |  | 2023-07-06 | 2023-07-04 |  | Tower | Tower | 62M | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
9131A | Kingwood Hotel | Sarawak |  | Modernization |  | 2023Q2 | SH | Datasco | 4.6 TSSR Approved |  | 2023-04-15 | 2023-05-03 |  | 2023-05-06 |  | Closed | 2023-05-08 | 2023-05-09 | CD//John | 2023-05-09 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230419-0003 | DU00002007882 |  |  | 2023-07-31 | 2023-07-10 |  | Pole | 3m RT (Wall Mounted Pole) |  | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
A00045 | A043B_A00045OD_KGJERING_RDD | Northern |  | Decomm |  | 2023Q2 | MH | GTSB | 4.6 TSSR Approved |  | 2023-04-12 | 2023-06-26 |  |  | 2023-06-15 |  | 2023-06-16 | 2023-06-21 | CD//Heng | 2023-07-03 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230717-0022/Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1 | DU00002007883 |  |  |  |  | 2023-06-21 | Tower | TOWER | 90
A00673 | A043B_A00673OD_CB_BT5SEGARI_RDC | Northern |  | Decomm |  | 2023Q2 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-04-05 | 2023-06-26 |  |  | 2023-06-17 |  | 2023-06-26 | 2023-08-28 | CD//Shamsul | 2023-08-21 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230717-0022/Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1 | DU00002007884 |  |  |  |  | 2023-06-21 |  | UNIPOLE | 50
4495B | Jln Labrooy RDD | Northern |  | Modernization |  | 2023Q2 | MH | CCSMY | 4.6 TSSR Approved |  | 2023-04-13 | 2023-05-09 |  | 2023-04-27 |  | Closed | 2023-05-11 | 2023-06-02 | E//Hazida | 2023-06-02 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230414-0007 | DU00002007885 |  |  | 2023-06-11 | 2023-06-10 |  | Minimast | 3m RT (Minimast) | 6m | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3
7650A | Taman Rampainan | Sabah |  | Modernization |  | 2023Q2 | HQ 5 | Futong | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-14 |  | 2023-04-20 |  | Closed | 2023-04-26 | 2023-05-10 | CD//Jahganathan | 2023-04-28 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0002 | DU00002007886 |  |  | 2023-06-03 | 2023-06-02 |  | Unipole | 3m Bipod (RT) | 4 | Add R9264M M1821 x5 + R8862A S2601 x2,Dismantle R8882 S1800B(B6B) x3 |  | 13
4491B | Chepor RDC | Northern |  | Modernization |  | 2023Q2 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-05-24 | 2023-05-25 |  | 2023-05-26 |  | Closed | 2023-05-27 | 2023-06-08 | E//Hazida | 2023-06-09 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0017 | DU00002007887 |  |  | 2023-06-18 | 2023-06-14 |  |  | 60m 3 Legged Tower | 62m | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
4801C | Kampung Kastam | Northern |  | Modernization |  | 2023Q3 | MH | YPTT | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-10 |  | 2023-05-12 |  | Closed | 2023-05-14 | 2023-05-25 | CD//Shamsul | 2023-05-17 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0009 | DU00002007888 |  |  | 2023-06-15 | 2023-06-15 |  |  | Tower | 2M | Add R9264M M1821 x4,Dismantle R9224E M1821(AAB) x4
4383A | PREMISRCC | Northern |  | Modernization |  | 2023Q2 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-04-13 | 2023-05-09 |  | 2023-04-17 |  | Closed | 2023-05-12 | 2023-05-25 | CD//Quah | 2023-05-22 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230413-0006 | DU00002007889 |  |  | 2023-05-27 | 2023-05-26 |  | Tower | 3m Bipod (RT) | 47 | Add R9264H M901821 x2 + R9264M M1821 x4 + R8862A S2601 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8854D S2100(A4A) x3 |  | 123
A01145 | A040C_A01145OD_BB_SRIKLEBANG_IPH | Northern |  | Decomm |  | 2023Q2 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-07-05 |  |  |  | 2023-08-07 |  | 2023-07-26 | 2023-08-28 | CD//Affendi | 2023-07-26 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V2 | DU00002007890 |  |  |  |  | 2023-07-24 |  | MINARET
4328H | 99 Speedmart PG Kg Benggali | Northern |  | MOCN As-Is |  | 2023Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007891 | [6 empty] | Rooftop
9097R | NANGATANYIT | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | N/A - no need PR for MOCN Decomm | DU00002007892 | [6 empty] | Land site
4970C | Kuala Kuang | Northern |  | Modernization |  | 2023Q2 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-16 |  | 2023-05-19 |  | Closed | 2023-05-23 | 2023-06-07 | E//Hazida | 2023-06-06 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230509-0018 | DU00002007893 |  |  | 2023-06-10 | 2023-06-09 |  | Minaret | Tower | 30M | Add R9264M M1821 x3,Dismantle R9224E M1821(AAB) x3
7118B | KKIP KK | Sabah |  | Modernization |  | 2023Q2 | HQ 8 | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-05-08 |  | 2023-04-18 |  | Closed | 2023-04-25 | 2023-05-10 | CD//Ray Amos | 2023-05-10 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0003 | DU00002007894 |  |  | 2023-05-27 | 2023-05-24 |  | Unipole | 3m Bipod (RT) | 4m | Add R9264M M1821 x5 + R8862A S2601 x2,Dismantle R8894E M1821(A8A) x3 |  | 13
A00864 | A040C_A00864OD_MERU_RAYA | Northern |  | Decomm |  | 2023Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2023-04-09 |  |  |  | 2023-07-07 |  | 2023-06-15 | 2023-07-21 | CD//Affendi | 2023-06-27 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1 | DU00002007895 |  |  |  |  | 2023-07-18 |  | UNIPOLE | 5
A00987 | A040C_A00987IB_AEONKLEBANGIPOH | Northern |  | Decomm |  | 2023Q2 | ZA | GCI | 4.6 TSSR Approved |  | 2023-04-14 |  |  |  | 2023-10-20 |  | 2023-06-14 | 2023-10-27 | CD//Quah | 2023-07-06 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V2/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002007896 |  |  |  |  | 2023-07-27 |  | IN-BUILDING
A00951 | A040C_A00951OD_MERUIMPIAN_IPH | Northern |  | Decomm |  | 2023Q2 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-04-13 | 2023-06-26 |  |  | 2023-06-19 |  | 2023-06-22 | 2023-08-19 | CD//Quah | 2023-06-22 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1/Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20240305-0096 | DU00002007897 |  |  |  |  | 2023-07-17 | Monopole | LAMP_POLE | 30
A00192 | A042D_A00192OD_CB_CKTKERUING_RDD | Northern |  | Decomm |  | 2023Q2 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-04-13 |  |  |  | 2023-06-17 |  | 2023-06-19 | 2023-08-28 | CD//Heng | 2023-07-13 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V2/Celcom Digi_RAN-CCSMY-TSS Decomm-Northern-20240131-0091 | DU00002007898 |  | 21/8: Please include all TX equipment Photo |  |  | 2023-06-21 |  | TOWER
B00064 | B058B_B00064OD_KGBKTKUDA | Central | 1012K | Swap |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-06-15 | 2023-06-13 |  | 2023-06-15 |  | Closed | 2023-06-17 | 2023-07-18 | CD//Ali akaram | 2023-07-18 | CelcomDigi_RAN_YPTT_TSS_Central_20230508_0003 | DU00002007899 |  |  | 2023-09-25 | 2023-09-11 |  | Monopole | TOWER | 36 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
4522B | Gugusan Manjoi | Northern |  | Modernization |  | 2023Q2 | MH | CCSMY | 4.6 TSSR Approved |  | 2023-04-13 | 2023-04-29 |  | 2023-04-27 |  | Closed | 2023-05-02 | 2023-05-25 | CD//Quah | 2023-05-12 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230414-0007 | DU00002007900 |  |  | 2023-06-10 | 2023-06-03 |  | Monopole | 24m Lampole | 27m | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8840-U216 x3
4811A_IBC | Carrefour Seberang Jaya Prai | Northern |  | Modernization |  | 2023Q3 | WP | CCSMY | 4.6 TSSR Approved |  | 2023-09-05 | [5 empty] | 2023-10-04 | 2023-10-19 |  | 2023-06-28 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230906-0038 | DU00002007901 |  |  | 2023-09-19 | 2023-07-17 |  |  | IBS + RT (Boom) |  | Add R8862A S1800 x2+R8862A S2100 x1+R8862A S2600 x1,Dismantle R8882-GUL1812 x1
7221B | Canggih Park | Sabah |  | Modernization |  | 2023Q3 | HQ 5 | YPTT | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-25 |  | 2023-04-13 |  | Closed | 2023-05-06 | 2023-05-08 | CD//Ray Amos | 2023-05-08 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230407-0002 | DU00002007902 |  |  | 2023-07-26 | 2023-06-24 |  | Monopole | 30m Monopole | 30 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 13
4292C | Juru Tol | Northern |  | Modernization |  | 2023Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-04-28 | 2023-05-04 |  | 2023-05-05 |  | Closed | 2023-05-10 | 2023-05-25 | CD//Shamsul | 2023-05-16 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230502-0012 | DU00002007903 |  |  | 2023-06-07 | 2023-06-07 |  | Unipole | 3m Bipod (RT) | 5.4 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3
A00303_IBC | A040B_A00303OD_IPOHPARADE | Northern |  | Decomm |  | 2023Q2 | ZA | GCI | 4.6 TSSR Approved |  | 2023-10-19 |  |  |  | 2023-10-19 |  | 2023-10-04 | 2023-10-19 | CD//Shamsul | 2023-06-26 | Celcom Digi_RAN-GCI-TSS-Northern-20231020-0063/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002007904 |  | Missing All TX information and Photo |  |  | 2023-12-22 |  | BOOM
9357A | Sibu-Durin | Sarawak |  | Modernization |  | 2023Q2 | HQ 2 | Datasco | 4.6 TSSR Approved |  | 2023-04-11 | 2023-04-12 |  | 2023-05-08 |  | Closed | 2023-05-12 | 2023-05-13 | CD//John | 2023-05-13 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002007905 |  |  | 2023-06-26 | 2023-06-20 |  |  | Tower | 61.5 | Add R9264H M901821 x1 + R9264M M1821 x2 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x2
A00121 | A040B_A00121OD_FAIRPARK | Northern |  | Decomm |  | 2023Q2 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-04-13 |  |  |  | 2023-06-20 |  | 2023-06-23 | 2023-08-08 | CD//Affendi | 2023-06-28 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V2 | DU00002007906 |  | Need Include all TX Photo |  |  | 2023-07-11 |  | MINI STRUCTURE
A00104 | A040C_A00104OD_TASEKW9 | Northern |  | Decomm |  | 2023Q2 | MH | GTSB | 4.6 TSSR Approved |  | 2023-04-13 | 2023-06-26 |  |  | 2023-06-20 |  | 2023-06-20 | 2025-10-28 | CD//Affendi | 2023-06-21 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1/Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230726-0024 | DU00002007907 |  | 21/8: Please include all TX equipment Photo |  |  | 2023-07-20 | Monopole | GUYED MAST | 35
7061H | 99 Speedmart TMN INDAH PERMAI | Sabah |  | MOCN As-Is |  | 2023Q2 | AD |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007908 | [6 empty] | Small Cell
4502A | Kin Mee Shoplot | Northern |  | Modernization |  | 2023Q2 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-04-17 | 2023-05-11 |  | 2023-04-19 |  | Closed | 2023-05-16 | 2023-05-31 | E//Hazida | 2023-05-22 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230418-0008 | DU00002007909 |  |  | 2023-05-26 | 2023-05-24 |  | Pole | 3m Boom (RT) | 6 | Add R8894E M1821 x3,Dismantle R8882-GUL1812 x3
9262B | Jalan Delta | Sarawak |  | Modernization |  | 2023Q2 | SH | Datasco | 4.6 TSSR Approved |  | 2023-04-21 | 2023-04-26 |  | 2023-05-02 |  | Closed | 2023-05-04 | 2023-05-04 | CD//John | 2023-05-04 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002007910 |  |  | 2023-06-11 | 2023-06-08 |  | Pole | Rapole | 12 | Add R9264M M1821 x3,Dismantle R8882 S1800B(B6B) x3
B00371 | B058E_B00371OD_TMJENJAROM | Central |  | Decomm |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-05-17 |  |  |  | 2023-06-07 |  | 2023-06-14 | 2024-01-26 | CD//Ali akaram | 2023-07-18 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002007911 |  |  |  |  | 2023-08-16 |  | TOWER
7313A | Tmn Nelly Kolombong | Sabah |  | Modernization |  | 2023Q3 | HQ 3 | YPTT | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-13 |  | 2023-04-18 |  | Closed | 2023-04-23 | 2023-05-05 | CD//Mohidi Jaan | 2023-05-05 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230407-0002 | DU00002007912 |  |  | 2023-06-27 | 2023-06-24 |  | Pole | 6m Unipole RT | 10 | Add R9264M M1821 x4,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8854D S2100(A4A) x4
4357C | Kg Jering New (REL) | Northern |  | Modernization |  | 2023Q2 | WP | GTSB | 4.6 TSSR Approved |  | 2023-04-05 | 2023-05-04 |  | 2023-04-14 |  | Closed | 2023-04-21 | 2023-05-18 | CD//Shamsul | 2023-05-05 | Celcom Digi_RAN-GTSB-TSS-Northern-20230410-0007 | DU00002007913 |  |  | 2023-05-23 | 2023-05-23 |  | Monopole | 45m Monopole | 46 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
7123B | One Borneo RT | Sabah |  | Modernization |  | 2023Q3 | MS | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-05-08 |  | 2023-05-13 |  | Closed | 2023-05-16 | 2023-07-03 | CD//Jahganathan | 2023-05-22 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0003 | DU00002007914 |  |  | 2023-07-11 | 2023-07-07 |  | Pole | 3m RT (Wall Mounted Pole) |  | Add R9264M M1821 x5 + R8862A S2601 x2,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3 |  | (S4->S2,S2->S3,S3->S4,Rename sectorID,Bisector@new S3/S4)
9242Z | T3E_0799_Sungai Tuah | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007915 | [6 empty] | 60m 4 Legged Tower
7082H | 99 Speedmart TMN SRI RUGADING | Sabah |  | MOCN As-Is |  | 2023Q2 | AD |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007916 | [6 empty] | Small Cell
9381B | Jalan Gambir MP | Sarawak |  | Modernization |  | 2023Q2 | BY | Trintel | 4.6 TSSR Approved |  | 2023-04-05 | 2023-04-14 |  | 2023-04-18 |  | Closed | 2023-04-26 | 2023-04-26 | CD//John | 2023-04-25 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230403-0003 | DU00002007917 |  |  | 2023-06-10 | 2023-06-08 |  | Monopole | 30m Monopole | 30 | Add R9264M M1821 x6 + R8862A S2601 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8840-U216 x3 |  | 123
9132A | Sibu Airport | Sarawak |  | Modernization |  | 2023Q2 | BY | Datasco | 4.6 TSSR Approved |  | 2023-04-06 | 2023-04-06 |  | 2023-04-14 |  | Rectificating | 2023-04-13 | 2023-05-08 | CD//John | 2023-04-17 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002007918 |  |  | 2023-07-04 | 2023-06-26 |  | Monopole | Tower | 26m | Add R8852E S9000 x1 + A9732 M1821 x1 + R9264H M901821 x2 + R8862A S2601 x1,Dismantle R8882-GUL1812 x2 | 1
7126H | 99 Speedmart KKIP Warehouse | Sabah |  | MOCN As-Is |  | 2023Q2 | AD |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007919 | [6 empty] | Small Cell
9373A | Durin Town | Sarawak |  | Modernization |  | 2023Q2 | SH | Datasco | 4.6 TSSR Approved |  | 2023-04-13 | 2023-05-05 |  | 2023-05-08 |  | Closed | 2023-05-09 | 2023-05-09 | CD//John | 2023-05-09 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002007920 |  |  | 2023-06-15 | 2023-06-12 |  | Tower | 45m 3 Legged Tower | 76 | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x3 |  | 3
A00221 | A040C_A00221OD_LAPTANAHHITAM_RDD | Northern |  | Decomm |  | 2023Q2 | MH | GCI | 4.6 TSSR Approved |  | 2023-05-08 |  |  |  | 2023-06-08 |  | 2023-06-09 | 2023-08-08 | CD//Shamsul | 2023-06-14 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V2/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002007921 |  |  |  |  | 2023-07-18 |  | TOWER
A00866 | A040C_A00866OD_KGKEPAYANGIPH2 | Northern |  | Decomm |  | 2023Q2 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-04-13 |  |  |  | 2023-06-23 |  | 2023-06-26 | 2023-10-27 | CD//Affendi | 2023-07-03 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V2 | DU00002007922 |  |  |  |  | 2023-07-16 |  | LAMP_POLE
9171A | Wisma Sanyan RT | Sarawak |  | Modernization |  | 2023Q2 | MA | Datasco | 4.6 TSSR Approved |  | 2023-04-20 | 2023-04-27 |  | 2023-04-30 |  | Rectificating | 2023-05-03 | 2023-05-03 | CD//John | 2023-05-03 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002007923 |  |  | 2024-05-23 | 2024-04-19 |  |  | Rooftop |  | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
7156Z | Kg Pangalan | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q2 | AD |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Jahganathan |  |  | DU00002007924 | [6 empty] | TOWER
4322H | 99 Speedmart PK Tmn Meru Perdana | Northern |  | MOCN As-Is |  | 2023Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007925 | [6 empty] | Rooftop
4783C | Jln Raja Uda Klinik Bersatu (REL) | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-20 | 2023-05-23 |  | 2023-06-01 |  | Closed | 2023-06-06 | 2023-06-24 | E//Hazida | 2023-06-23 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0014 | DU00002007926 |  |  | 2023-06-20 | 2023-06-19 |  | Wall mount boom | 3m Bipod (RT) | 3 | Add R9264H M901821 x2 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8862A S1800(B6A) x2 |  | 2
7033C | Taman Saga | Sabah |  | Modernization |  | 2023Q3 | HQ 5 | YPTT | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-10 |  | 2023-04-15 |  | Closed | 2023-04-18 | 2023-05-10 | CD//Ray Amos | 2023-05-10 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230407-0002 | DU00002007927 |  |  | 2023-07-03 | 2023-07-01 |  | Wall mount boom | 30m Monopole |  | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
9370A | Tg. Kunyit | Sarawak |  | Modernization |  | 2023Q2 | SH | CCSMY | 4.6 TSSR Approved |  | 2023-04-12 | 2023-05-03 |  | 2023-05-07 |  | Closed | 2023-05-09 | 2023-05-09 | CD//John | 2023-05-09 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230403-0003 | DU00002007928 |  |  | 2023-05-29 | 2023-05-23 |  | Tower | 45m 3 Legged Tower | 80m | Add R9264M M1821 x5 + R8862A S2600 x2,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x2+R8854D S2100(A4A) x3 |  | 13
4233D | Bagan Specialist (REL) | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-15 | 2023-05-23 |  | 2023-05-26 |  | Closed | 2023-06-01 | 2023-06-10 | E//Hazida | 2023-06-10 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0017 | DU00002007929 |  |  | 2023-06-30 | 2023-06-19 |  | Minimast | Rooftop | 10 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R9224E M1821(AAB) x3 | 13
A00648 | A040B_A00648OD_TMNIPOH | Northern | 4028K | Swap |  | 2023Q2 | ZA | GCI | 4.6 TSSR Approved |  | 2023-04-20 | 2023-04-28 |  | 2023-05-03 |  | Closed | 2023-05-06 | 2023-05-16 | CD//Shamsul | 2023-05-15 | Celcom Digi_RAN-GCI-TSS-Northern-20230425-0009 | DU00002007930 |  |  | 2023-06-13 | 2023-05-27 |  | Monopole | LAMP_POLE | 27m | Add R8852E S9000 x3 + R8894E M1821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
4293A | Jln Chain Ferry | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-04-28 | 2023-05-02 |  | 2023-05-03 |  | Closed | 2023-05-04 | 2023-05-25 | CD//Heng | 2023-05-11 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230502-0012 | DU00002007931 |  |  | 2023-06-08 | 2023-06-07 |  | Unipole | 6m Unipole RT | 6 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle R8882-GUL1812 x3+R8882 S1800B(B6B) x3+R8840-U216 x3
7261A | Kg. Salut (Celcom) | Sabah |  | Modernization |  | 2023Q2 | HQ 3 | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-12 |  | 2023-04-18 |  | Closed | 2023-04-23 | 2023-05-30 | CD//Jahganathan | 2023-05-29 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0003 | DU00002007932 |  |  | 2023-06-24 | 2023-06-16 |  |  | 60m 4 Legged Tower | 50 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
4197A | Sg Lokan | Northern |  | Modernization |  | 2023Q3 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-05-11 | 2023-05-22 |  | 2023-05-25 |  | Closed | 2023-06-01 | 2023-06-21 | CD//Quah | 2023-06-21 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0009 | DU00002007933 |  |  | 2023-06-20 | 2023-06-19 |  | Tower | 60m 3 Legged Tower | 75 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
9133A | Kin-Orient Plaza | Sarawak |  | Modernization |  | 2023Q2 | BY | Datasco | 4.6 TSSR Approved |  | 2023-04-05 | 2023-04-12 |  | 2023-04-17 |  | Closed | 2023-04-18 | 2023-05-10 | CD//John | 2023-04-19 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002007934 |  |  | 2023-06-25 | 2023-06-22 |  |  | 3m RT (Wall Mounted Pole) |  | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
4236C | Meru Perdana Perak | Northern |  | Modernization |  | 2023Q2 | SM | CCSMY | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦NO space | 2023-04-17 | 2023-04-25 |  | 2023-04-20 |  | Rectificating | 2023-05-16 | 2023-07-15 | E//Hazida | 2023-07-14 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230418-0008 | DU00002007935 | NIC_S2_Change MM to BI_Space constraint_PROSONTECH SDN BHD |  | 2023-06-15 | 2023-06-12 |  | Minaret | 3m RT (Minimast) | 30m | Add R9264M M1821 x6,Dismantle R8894E M1821(A8A) x3 |  | 123
9039C | Jalan Jewit Timur | Sarawak |  | Modernization |  | 2023Q2 | MA | AllStar | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦ owner Sacofa reject our TP of adding AAU. | 2023-04-10 | 2023-04-28 |  | 2023-05-02 |  | Closed | 2023-05-04 | 2023-08-16 | CD//John | 2023-08-16 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230403-0003 | DU00002007936 | NIC_S3_Change MM to BI_owner reject_SACOFA SDN BHD |  | 2023-07-13 | 2023-07-06 |  | Monopole | Tower | 30 | Add R9264M M1821 x3 + R9264H M901821 x3 + R8862A S2601 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 123
7357C | KKIP zone 2 | Sabah |  | Modernization |  | 2023Q2 | MS | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-11 |  | 2023-05-12 |  | Closed | 2023-05-16 | 2023-05-17 | CD//Ray Amos | 2023-05-17 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0003 | DU00002007937 |  |  | 2023-06-11 | 2023-06-08 |  | Lampole | 30M Lampole | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
4536B | LAP Tanah Hitam RDD | Northern |  | Modernization |  | 2023Q2 | ZA | GCI | 4.6 TSSR Approved |  | 2023-04-19 | 2023-04-25 |  | 2023-04-27 |  | Closed | 2023-04-28 | 2023-10-13 | CD//Quah | 2023-05-09 | Celcom Digi_RAN-GCI-TSS-Northern-20230425-0009 | DU00002007938 |  |  | 2023-06-10 | 2023-06-06 |  | Tower | Tower | 60m | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R9224E M1821(AAB) x3 |  | 13(S1->S3,S2->S1,S3->S2,rename Sector ID,Bisector@New S2/S3)
7549B | KG KARMILAN 2 | Sabah |  | Modernization |  | 2023Q2 | HQ 3 | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-05-08 |  | 2023-04-18 |  | Closed | 2023-04-23 | 2023-05-25 | CD//Jahganathan | 2023-05-25 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0003 | DU00002007939 |  |  | 2023-06-22 | 2023-06-16 |  | Monopole | 24m Lampole | 30 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
4451D | Taman Siakap | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-04 | 2023-05-19 |  | 2023-05-29 |  | Closed | 2023-06-01 | 2023-06-22 | CD//Quah | 2023-06-22 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0015 | DU00002007940 |  |  | 2023-06-17 | 2023-06-16 |  | Monopole | Land site | 30M | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
4366D | Surau An-Nur (REL) | Northern |  | Modernization |  | 2023Q2 | WP | GTSB | 4.6 TSSR Approved |  | 2023-04-09 | 2023-04-12 |  | 2023-04-14 |  | Closed | 2023-04-17 | 2023-05-05 | CD//Heng | 2023-05-03 | Celcom Digi_RAN-GTSB-TSS-Northern-20230410-0007 | DU00002007941 |  |  | 2023-06-14 | 2023-06-14 |  | Minaret | 22m Minaret | 27 | Add R8852E S9000 x3 + A9732 M1821 x3 + R8862A S2601 x1,Dismantle R8894E M1821(A8A) x3 | 123
4828A | Green Town Mall | Northern |  | Modernization |  | 2023Q2 | WP | YPTT | 4.6 TSSR Approved |  | 2023-04-14 | 2023-04-20 |  | 2023-05-02 |  | Closed | 2023-05-05 | 2023-05-18 | CD//Shamsul | 2023-05-12 | Celcom Digi_RAN-YPTT-TSS-Northern-20230417-0006 | DU00002007942 |  |  | 2023-05-25 | 2023-05-24 |  |  | In-building system | N/A | Add R8852E S9000 x1 + R8862A S1800 x1 + R8862A S2100 x1,Dismantle R8882-GUL1812 x1
4489B | Heritage Hotel RDD | Northern |  | Modernization |  | 2023Q2 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-04-20 | 2023-05-03 |  | 2023-05-05 |  | Closed | 2023-05-07 | 2023-05-25 | CD//Quah | 2023-05-12 | Celcom Digi_RAN-GCI-TSS-Northern-20230425-0009 | DU00002007943 |  |  | 2023-05-26 | 2023-05-24 |  | Pole | 3m Boom (RT) | 3.6 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 13
B00353 | B059A_B00353OD_KANCHUNGDARAT | Central |  | Decomm |  | 2023Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-04-10 | 2023-06-26 |  |  | 2023-07-18 |  | 2023-07-18 | 2023-10-02 | CD//Sapian | 2023-07-24 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002007944 |  |  |  |  | 2023-07-20 | Tower | TOWER | 40
9037C | Lorong Apollo Sungai Merah | Sarawak |  | Modernization |  | 2023Q2 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-04-05 | 2023-05-10 |  | 2023-04-18 |  | Closed | 2023-05-18 | 2023-05-18 | CD//John | 2023-05-18 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230403-0003 | DU00002007945 |  |  | 2023-06-24 | 2023-06-20 |  | Monopole | 30m Rapole | 31 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 | 0 | 0
9178B | Tatau Timber | Sarawak |  | Modernization |  | 2023Q3 | SH | Magicell | 4.6 TSSR Approved |  | 2023-04-27 | 2023-04-29 |  | 2023-05-05 |  | Closed | 2023-05-08 | 2023-05-09 | CD//John | 2023-05-09 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230428-0003 | DU00002007946 |  |  | 2023-06-19 | 2023-06-14 |  | Tower | Guyed Mast | 46m | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
7201B | KK Kg Sinompuro - UCA | Sabah |  | Modernization |  | 2023Q2 | HQ 7 | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-05-08 |  | 2023-04-29 |  | Closed | 2023-05-04 | 2023-05-09 | CD//Jahganathan | 2023-05-09 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0003 | DU00002007947 |  |  | 2023-07-03 | 2023-06-09 |  | Monopole | 30m Monopole | 30 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x1,Dismantle R9224E M1821(AAB) x5 |  | 13
4248A | Kuala Juru | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-05-31 | 2023-06-07 |  | 2023-06-08 |  | Closed | 2023-06-12 | 2023-06-27 | E//Hazida | 2023-06-27 | Celcom Digi_RAN-GCI-TSS-Northern-20230508-0015 | DU00002007948 |  |  | 2023-06-26 | 2023-06-20 |  | Tower | 60m 3 Legged Tower | 60 | Add R8852E S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle | 12 | 0
B00379 | B058B_B00379OD_TMBKTRAJA | Central | 1017K | Swap |  | 2023Q3 | IE | Datasco | 4.6 TSSR Approved |  | 2023-06-19 | 2023-06-27 |  | 2023-06-30 |  | Closed | 2023-07-04 | 2023-12-12 | CD//Norhaliza | 2023-12-10 | CelcomDigi_RAN_Datasco_TSS_Central_20230620_0027 | DU00002007949 |  |  | 2023-08-30 | 2023-08-24 |  | Pole | TRIPOD | 4 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x5,Dismantle Celcom all RRU&BBU |  | 13
B00372 | B059A_B00372OD_TMBANTING | Central | 1015K | Swap |  | 2023Q2 | YZ | GTSB | 4.6 TSSR Approved |  | 2023-04-10 | 2023-04-17 |  | 2023-04-19 |  | Closed | 2023-05-02 | 2023-06-06 | CD//Sapian | 2023-05-16 | CelcomDigi_RAN_GTSB_TSS_Central_20230411_0014 | DU00002007950 |  |  | 2023-07-03 | 2023-06-06 |  | Tower | BOOM | 100m | Add R9264H M901821 x3 + R9264M M1821 x3 + R8862A S2601 x6,Dismantle Celcom all RRU&BBU |  | 123
A00245 | A042D_A00245OD_CB_TMBERUAS | Northern |  | Decomm |  | 2023Q2 | MH | YPTT | 4.6 TSSR Approved |  | 2023-04-12 | 2023-06-26 |  |  | 2023-06-15 |  | 2023-06-16 | 2023-07-04 | CD//Heng | 2023-07-03 | Celcom Digi_RAN-YPTT-TSS-Northern-20230609-0018//Celcom Digi_RAN-YPTT-TSS Decomm-Northern-20240311-0048 | DU00002007951 |  |  |  |  | 2023-07-07 | Tower | TOWER | 45
7098H | Masjid Al-Falah Imacro | Sabah |  | MOCN As-Is |  | 2023Q2 | AD | YPTT | 14.1 Drop (No Survey) |  | 2025-07-17 | 2025-07-14 |  |  |  | To be Submitted | [5 empty] | DU00002007952 | [5 empty] | Wall mount boom | Small Cell
9135A | Zeninth Minth Cinema | Sarawak |  | Modernization |  | 2023Q2 | BY | Datasco | 4.6 TSSR Approved |  | 2023-04-15 | 2023-05-08 |  | 2023-05-10 |  | Closed | 2023-05-11 | 2023-05-11 | CD//John | 2023-05-11 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002007953 |  |  | 2023-07-28 | 2023-06-28 |  | Monopole | 9m RT (Wall Mounted Pole) | 6 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
4196A | Kg Pertama | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-03 | 2023-05-06 |  | 2023-05-09 |  | Closed | 2023-05-10 | 2023-05-25 | CD//Affendi | 2023-05-11 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0015 | DU00002007954 |  |  | 2023-06-07 | 2023-06-07 |  | Tower | 30m 3-legged tower | 45m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
9412B | Wong Ting Hock Lane | Sarawak |  | Modernization |  | 2023Q2 | BY | Datasco | 4.6 TSSR Approved |  | 2023-04-11 | 2023-04-13 |  | 2023-04-15 |  | Closed | 2023-04-18 | 2023-04-25 | CD//John | 2023-04-25 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002007955 |  |  | 2023-07-10 | 2023-07-04 |  | Monopole | 30m Monopole | 32M | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
9155A | Delta | Sarawak |  | Modernization |  | 2023Q2 | SH | Datasco | 4.6 TSSR Approved |  | 2023-04-25 | 2023-05-04 |  | 2023-05-05 |  | Closed | 2023-05-09 | 2023-05-09 | CD//John | 2023-05-09 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002007956 |  |  | 2023-05-27 | 2023-05-25 |  |  | 3m RT (Minimast) |  | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
9035C | Kampung Datu Sibu | Sarawak |  | Modernization |  | 2023Q2 | BY | Trintel | 4.6 TSSR Approved |  | 2023-04-06 | 2023-04-06 |  | 2023-04-14 |  | Closed | 2023-04-18 | 2023-04-25 | CD//John | 2023-04-25 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230403-0003 | DU00002007957 |  |  | 2023-05-27 | 2023-05-24 |  | Monopole | 30m Rapole | 31.8m | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 | 0 | 0
4329H | 99 Speedmart PG Tmn Seri Juru | Northern |  | MOCN As-Is |  | 2023Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007958 | [6 empty] | Rooftop
9124A | Sg Selat | Sarawak |  | Modernization |  | 2023Q3 | SH | Magicell | 4.6 TSSR Approved |  | 2023-04-27 | 2023-04-29 |  | 2023-05-04 |  | Closed | 2023-05-05 | 2023-05-07 | CD//John | 2023-05-05 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230428-0003 | DU00002007959 |  |  | 2023-06-13 | 2023-06-08 |  | Tower | 45m 3 Legged Tower | 60M | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
7231H | 99 Speedmart Tuaran Town | Sabah |  | MOCN As-Is |  | 2023Q2 | AD |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007960 | [6 empty] | Rooftop
4235C | Persiaran Tawas | Northern |  | Modernization |  | 2023Q2 | MH | GTSB | 4.6 TSSR Approved |  | 2023-04-05 | 2023-04-04 |  | 2023-04-12 |  | Closed | 2023-04-12 | 2023-05-11 | CD//Quah | 2023-05-11 | Celcom Digi_RAN-GTSB-TSS-Northern-20230410-0007 | DU00002007961 |  |  | 2023-05-20 | 2023-05-20 |  | Minimast | 3m Bipod (RT) | 11 | Add R9264M M1821 x3,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3
9413B | Jln Bawang Assan | Sarawak |  | Modernization |  | 2023Q2 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-04-03 | 2023-04-07 |  | 2023-04-18 |  | Closed | 2023-04-20 | 2023-05-04 | CD//John | 2023-05-04 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230403-0003 | DU00002007962 |  |  | 2023-05-31 | 2023-05-26 |  | Tower | 30m Monopole | 62m | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3
A00585 | A040B_A00585OD_SMAIZUDDIN | Northern |  | Decomm |  | 2023Q2 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-04-11 | 2023-06-26 |  |  | 2023-05-29 |  | 2023-05-30 | 2023-06-28 | CD//Heng | 2023-06-07 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230717-0022/Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1 | DU00002007963 |  |  |  |  | 2023-07-01 | Lampole | LAMP_POLE | 30
A00738 | A040C_A00738OD_JELAPANGTOWN_RDD | Northern |  | Decomm |  | 2023Q2 | MH | YPTT | 4.6 TSSR Approved |  | 2023-04-13 |  |  |  | 2023-06-23 |  | 2023-06-26 | 2023-08-08 | CD//Rohizam | 2023-08-02 | Celcom Digi_RAN-YPTT-TSS-Northern-20230609-0018//Celcom Digi_RAN-YPTT-TSS Decomm-Northern-20240311-0048 | DU00002007964 |  |  |  |  | 2023-07-12 |  | BOOM
7282A | KG. NUMBAK | Sabah |  | Modernization |  | 2023Q2 | HQ 3 | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-11 |  | 2023-04-19 |  | Closed | 2023-04-25 | 2023-05-22 | CD//Jahganathan | 2023-05-22 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0003 | DU00002007965 |  |  | 2023-06-20 | 2023-06-16 |  | Monople Tree | 30m Monopole | 45m | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
4232H | 99 Speedmart PK Tmn Permai | Northern |  | MOCN As-Is |  | 2023Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007966 | [6 empty] | Small Cell
A00594 | A040C_A00594OD_JELAPANGMAJU | Northern |  | Decomm |  | 2023Q2 | MH | GTSB | 4.6 TSSR Approved |  | 2023-04-09 |  |  |  | 2023-06-09 |  | 2023-06-10 | 2023-07-21 | CD//Affendi | 2023-06-14 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1 | DU00002007967 |  |  |  |  | 2023-06-29 | Lampole | LAMP_POLE | 30
9585B | Jalan Teku Pasai | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2023Q2 | ZB | CCSMY | 4.6 TSSR Approved |  | 2023-04-12 |  |  |  | 2023-06-28 |  | 2023-07-24 | 2024-02-15 | E//Hannah | 2023-07-27 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230613-0007 | DU00002007968 |  |  |  |  | 2025-03-26 |  | Tower
4404A | Kg Jering Tower Manjung RDD | Northern |  | Modernization |  | 2023Q2 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-14 |  | 2023-04-17 |  | Closed | 2023-04-18 | 2023-05-08 | CD//Quah | 2023-05-05 | Celcom Digi_RAN-GTSB-TSS-Northern-20230413-0009 | DU00002007969 |  |  | 2023-05-18 | 2023-05-15 |  | Tower | 60m 4 Legged Tower | 90 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 123
A00149 | A040B_A00149OD_PKNRAZAKI | Northern |  | Decomm |  | 2023Q2 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-04-12 | 2023-06-26 |  |  | 2023-06-17 |  | 2023-06-19 | 2023-06-28 | CD//Affendi | 2023-06-21 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1 | DU00002007970 |  |  |  |  | 2023-07-11 | Wall mount boom | SHARING STRC SBC | 40
A01294 | A040C_A01294OD_KG_SRI_KLEBANG | Northern | 4036K | Swap |  | 2023Q2 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-04-28 | 2023-05-02 |  | 2023-05-03 |  | Closed | 2023-05-04 | 2023-05-15 | CD//Quah | 2023-05-15 | Celcom Digi_RAN-GCI-TSS-Northern-20230425-0009 | DU00002007971 |  |  | 2023-06-22 | 2023-06-13 |  | Lampole | LAMP_POLE | 25M | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 3
4375C | Kg Tersusun | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-11 | 2023-06-02 |  | 2023-06-08 |  | Closed | 2023-06-12 | 2023-06-27 | E//Hazida | 2023-06-27 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0017 | DU00002007972 |  |  | 2023-07-07 | 2023-06-25 |  | Pole | 3m Bipod (RT) | 8M | Add R8852E S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8882 S1800B(B6B) x3+R8854D S2100(A4A) x3 | 13 | 0
7025C | Jalan Puri Warisan | Sabah |  | Modernization |  | 2023Q3 | HQ 6 | YPTT | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-06 |  | 2023-04-13 |  | Closed | 2023-04-23 | 2023-05-05 | CD//Mohidi Jaan | 2023-05-05 | Celcom Digi_RAN-YPTT-TSS-Sabah-20230407-0002 | DU00002007973 |  |  | 2023-07-06 | 2023-07-01 |  | Lampole | 30m Lampole | 30m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
7246C | Wismas (REL) | Sabah |  | Modernization |  | 2023Q3 | HQ 7 | Datasco | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-25 |  | 2023-04-30 |  | Closed | 2023-05-04 | 2023-05-05 | CD//Mohidi Jaan | 2023-05-05 | Celcom Digi_RAN-Datasco- TSS-Sabah-20230407-0002 | DU00002007974 |  |  | 2023-07-11 | 2023-07-06 |  | Pole | Land site | 6m | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8854 S2600(A4A) x1+R9224E M1821(AAB) x4 | 12
9382B | Jalan Pedada MP | Sarawak |  | Modernization |  | 2023Q2 | BY | Trintel | 4.6 TSSR Approved |  | 2023-04-06 | 2023-05-03 |  | 2023-05-08 |  | Closed | 2023-05-13 | 2023-05-15 | CD//John | 2023-05-15 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230403-0003 | DU00002007975 |  |  | 2023-07-03 | 2023-06-26 |  | Monopole | 30m Monopole | 30m | Add R8852E S9000 x3 + A9732 M1821 x3 + R9264H M901821 x1,Dismantle R8882-GUL1812 x4+R8862A S1800(B6A) x1+R8862A S2100(A6A) x1+R8854D S2100(A4A) x3 | 123
7316A | Federal Government Buidling KK | Sabah |  | Modernization |  | 2023Q3 | HH | GTSB | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦Limitted space to install AAU,Space is ouccuped by cable and limitted space to install new AAU. | 2023-04-07 | 2023-04-28 |  | 2023-05-02 |  | Closed | 2023-05-08 | 2023-06-08 | CD//Jahganathan | 2023-06-09 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230407-0002 | DU00002007976 | NIC_S2_Change MM to BI_Space constraint_COMMON TOWER TECH |  | 2023-07-16 | 2023-07-07 |  | Monopole | 30m Monopole | 45m | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 |  | 12
A01109 | A040C_A01109OD_CB_KG_TENGKU_HUSIN_IPH | Northern |  | Decomm |  | 2023Q2 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-04-13 |  |  |  | 2023-08-07 |  | 2023-08-08 | 2023-08-19 | CD//Rohizam | 2023-08-08 | Celcom Digi_RAN-CCSMY- TSS Decomm-Northern-20230829-0037/Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V2 | DU00002007977 |  |  |  |  | 2023-08-30 |  | LAMP_POLE
9394B | Lorong Upper Lanang Lane 1 | Sarawak |  | Modernization |  | 2023Q2 | MA | Trintel | 4.6 TSSR Approved |  | 2023-04-04 | 2023-04-28 |  | 2023-05-02 |  | Closed | 2023-05-04 | 2023-05-05 | CD//John | 2023-05-05 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230403-0003 | DU00002007978 |  |  | 2023-06-27 | 2023-06-25 |  | Monopole | 30m Monopole | 36 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R9224E M1821(AAB) x3 | 123
4307A | LAP Air Tawar RCC | Northern |  | Modernization |  | 2023Q2 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-04-12 | 2023-05-03 |  | 2023-04-17 |  | Closed | 2023-05-05 | 2023-05-18 | CD//Quah | 2023-05-09 | Celcom Digi_RAN-GTSB-TSS-Northern-20230413-0009 | DU00002007979 |  |  | 2023-05-30 | 2023-05-24 |  | Tower | Tower | 60 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
4334D | Taman Perai Indah | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-05 | 2023-05-15 |  | 2023-05-18 |  | Closed | 2023-05-22 | 2023-05-31 | E//Hazida | 2023-05-31 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0017 | DU00002007980 |  |  | 2023-06-21 | 2023-06-19 |  | Pole | 3m Boom (RT) | 6 | Add R9264M M1821 x5,Dismantle R8894E M1821(A8A) x5 |  | 13
7547B | KKIP Barat | Sabah |  | Modernization |  | 2023Q2 | HQ 1 | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-08 |  | 2023-04-13 |  | Closed | 2023-04-27 | 2023-05-10 | CD//Mohidi Jaan | 2023-05-10 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0003 | DU00002007981 |  |  | 2023-05-29 | 2023-05-26 |  | Pole | 3m Bipod (RT) | 6 | Add R9264M M1821 x3,Dismantle R8882 S1800(B) x1+R8882 S1800B(B6B) x2+R8862A S2100(A6A) x3
7078H | 99 Speedmart MENGGATAL PLAZA | Sabah |  | MOCN As-Is |  | 2023Q2 | AD |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007982 | [6 empty] | Small Cell
A00303 | A040B_A00303OD_IPOHPARADE | Northern |  | Decomm |  | 2023Q2 | ZA | GCI | 4.6 TSSR Approved |  | 2023-05-02 |  |  |  | 2023-06-12 |  | 2023-06-14 | 2023-07-21 | CD//Affendi | 2023-06-26 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V2/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002007983 |  |  |  |  | 2023-06-30 |  | BOOM
B00344 | B058D_B00344ODA_ZALIDENT | Central |  | Decomm |  | 2023Q2 | IE | Datasco | 4.6 TSSR Approved |  | 2023-04-17 | 2023-06-26 |  |  | 2024-06-28 |  | 2023-06-15 | 2024-07-19 | CD//Ali akaram | 2023-07-18 | CelcomDigi_RAN_Datasco_TSS_Central_20230626_decom reraise | DU00002007984 |  |  |  |  | 2023-08-15 | Pole | TRIPOD | 6m
4383H | 99 SM PK TMN SELAMAT | Northern |  | MOCN As-Is |  | 2023Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002007985 | [6 empty] | Rooftop
4929A | Taman Perwira REL | Northern |  | Modernization |  | 2023Q3 | HQ 1 | YPTT | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-17 |  | 2023-05-20 |  | Closed | 2023-05-29 | 2023-06-27 | E//Hazida | 2023-06-27 | Celcom Digi_RAN-YPTT-TSS-Northern-20230508-0009 | DU00002007986 |  |  | 2023-07-05 | 2023-07-05 |  | Monopole | 30m Lampole | 25 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3 | 0 | 0
9967A | City Hotel Sibu Market | Sarawak |  | Modernization |  | 2023Q2 | HQ 2 | Datasco | 4.6 TSSR Approved |  | 2023-04-21 | 2023-05-03 |  | 2023-05-05 |  | Closed | 2023-05-07 | 2023-05-10 | CD//John | 2023-05-10 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002007987 |  |  | 2023-07-18 | 2023-07-12 |  | Pole | 3m Boom (RT) | 9m | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8894E M1821(A8A) x3 |  | 23
9569B | Kampung Pandan | Sarawak |  | Modernization |  | 2023Q3 | BY | Trintel | 4.6 TSSR Approved |  | 2023-04-05 | 2023-04-05 |  | 2023-04-13 |  | Rectificating | 2023-04-23 | 2023-05-10 | CD//John | 2023-04-28 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230403-0003 | DU00002007988 |  |  | 2023-08-01 | 2023-07-10 |  | Tower | Tower | 61m | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R9224E M1821(AAB) x3 | 123
9274B | Jalan Tekam | Sarawak |  | Modernization |  | 2023Q2 | BY | Trintel | 4.6 TSSR Approved |  | 2023-04-11 | 2023-04-13 |  | 2023-04-15 |  | Rectificating | 2023-04-18 | 2023-04-25 | CD//John | 2023-04-25 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230403-0003 | DU00002007989 |  |  | 2023-05-28 | 2023-05-26 |  | Monopole | Tower | 30m | Add R9264M M1821 x4,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 |  | 1
A00353 | IPOHBRANCH_4G | Northern |  | Decomm |  | 2023Q2 | ZA | YPTT | 4.6 TSSR Approved |  | 2023-04-25 |  |  |  | 2023-06-20 |  | 2023-06-22 | 2023-10-27 | CD//Affendi | 2023-06-28 | Celcom Digi_RAN-YPTT-TSS-Northern-20230609-0018//Celcom Digi_RAN-YPTT-TSS Decomm-Northern-20240311-0048 | DU00002007990 |  |  |  |  | 2023-08-01 |  | BOOM
7253A | KOL 2 | Sabah |  | Modernization |  | 2023Q3 | HQ 5 | Futong | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-13 |  | 2023-04-20 |  | Closed | 2023-04-25 | 2023-06-09 | CD//Jahganathan | 2023-06-09 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0003 | DU00002007991 |  |  | 2023-07-14 | 2023-06-30 |  | Tower | 30m 3-legged tower | 33 | Add A9732 M1821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 123
7318C4 | DUN SABAH | Sabah |  | Site Out (Modernization) | Modernization->Site out->Site Out (Modernization) | 2023Q3 | AD | AllStar | 4.6 TSSR Approved |  | 2023-06-12 | 2023-07-11 |  | 2023-10-17 |  | Closed | 2023-11-10 | 2023-11-28 | E//Hannah | 2023-11-28 | Celcom Digi_RAN-Allstar-TSS-Sabah-20230626 | DU00002007992 | [5 empty] | In-Building System | Land site | 2M
4501A | Foong Yit & Son | Northern |  | Modernization |  | 2023Q2 | MH | GTSB | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-15 |  | 2023-04-19 |  | Closed | 2023-04-20 | 2023-05-25 | CD//Affendi | 2023-05-03 | Celcom Digi_RAN-GTSB-TSS-Northern-20230413-0009 | DU00002007993 |  |  | 2023-06-12 | 2023-06-10 |  | Pole | 3m Boom (RT) | 6 | Add R8852E S9000 x2 + R8894E M1821 x2,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x1+R8840-U216 x2 | 0
7152B | Alam Mesra 1 | Sabah |  | Modernization |  | 2023Q3 | HQ 6 | GTSB | 4.6 TSSR Approved |  | 2023-04-04 | 2023-04-10 |  | 2023-04-13 |  | Closed | 2023-04-14 | 2023-05-01 | CD//Mohidi Jaan | 2023-04-18 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230407-0002 | DU00002007994 |  |  | 2023-06-06 | 2023-06-02 |  | Unipole | 24m Lampole | 10m | Add R8852E S9000 x3 + R8894E M1821 x3,Dismantle R8882 S1800(B) x3+R8881 S2100 x3
7315A | Kg Sukang | Sabah |  | Modernization |  | 2023Q3 | HQ 7 | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-29 |  | 2023-05-03 |  | Closed | 2023-05-05 | 2023-05-10 | CD//Jahganathan | 2023-05-10 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0003 | DU00002007995 |  |  | 2023-07-14 | 2023-06-30 |  | Monople Tree | 30m Monopole Tree | 31 | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3
A01082 | A042D_A01082OD_KG_SG_BATU_PREMIS | Northern |  | Decomm |  | 2023Q2 | SM | GCI | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-10 |  |  | 2023-06-19 |  | 2023-06-21 | 2023-06-28 | CD//Affendi | 2023-06-22 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V2/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002007996 |  |  |  |  | 2023-06-22 | Tower | LAMP_POLE | 30
B00025 | B063A_B00025OD_PACHITAN | Central |  | Decomm |  | 2023Q2 | IE | Magicell | 4.6 TSSR Approved |  | 2023-04-07 | 2023-06-26 |  | 2023-04-13 | 2023-07-17 | Closed | 2023-07-20 | 2023-07-31 | CD//Sapian | 2023-07-26 | CelcomDigi_RAN_Magicell_TSS_Central_20230626_decom reraise | DU00002007997 |  |  |  |  | 2023-07-25 | Tower | TOWER | 61m
7230A | Kampung Rampayan | Sabah |  | Modernization |  | 2023Q2 | HQ 8 | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-18 |  | 2023-04-26 |  | Closed | 2023-04-28 | 2023-05-22 | CD//Jahganathan | 2023-05-22 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0003 | DU00002007998 |  |  | 2023-06-26 | 2023-06-12 |  | Tower | 45m 3 Legged Tower | 35 | Add A9732 M1821 x3 + R9264M M1821 x1,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x6 | 124
A00246 | A043B_A00246OD_TMLEKIR | Northern |  | Decomm |  | 2023Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2023-04-29 |  |  |  | 2023-06-19 |  | 2023-06-20 | 2023-12-19 | CD//Heng | 2023-07-13 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230717-0022/Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1 | DU00002007999 |  |  |  |  | 2023-07-24 | Tower | TOWER | 100
4381B | Lumut Power Plant | Northern |  | Modernization | Modernization->Site Out->Modernization->On Hold->Modernization | 2023Q2 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-04-13 | 2023-04-29 |  | 2023-04-19 |  | Closed | 2023-05-02 | 2023-05-25 | CD//Quah | 2023-05-10 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230414-0007 | DU00002008000 |  |  | 2023-05-29 | 2023-05-24 |  | Tower | 60m 3 Legged Tower | 60M | Add R8852E S9000x3 + R8894E M1821x3,Dismantle R8860E-GU908 x1+R8862A S1800(B6A) x3+R8840-U216 x3
4327H | 99 Speedmart PG Tmn Sutera | Northern |  | MOCN As-Is |  | 2023Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008001 | [6 empty] | Rooftop
A00037 | A040C_A00037OD_CHEPOR_RDC | Northern |  | Decomm |  | 2023Q2 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-07-27 |  |  |  | 2023-08-10 |  | 2023-08-02 | 2024-04-23 | CD//Affendi | 2023-08-07 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V2 | DU00002008002 |  | 21/8: Please include all TX equipment Photo |  |  | 2023-07-26 |  | TOWER
7645A | Kg Batangan | Sabah |  | Modernization |  | 2023Q2 | HQ 8 | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-18 |  | 2023-04-26 |  | Closed | 2023-04-28 | 2023-11-20 | CD//Ray Amos | 2023-05-03 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0003 | DU00002008003 |  |  | 2023-07-18 | 2023-06-16 |  | Tower | Tower | 76 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x2,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x4+R9224E M1821(AAB) x1 | 12
A01110 | A040C_A01110OD_CB_KG_TERSUSUN_TANAH_HITAM | Northern | 4031K | Swap |  | 2023Q2 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-05-08 | 2023-05-11 |  | 2023-05-17 |  | Closed | 2023-05-22 | 2023-06-12 | CD//Quah | 2023-06-02 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0017 | DU00002008004 |  |  | 2023-06-22 | 2023-06-11 |  | Lampole | LAMP_POLE | 30M | Add R9264H M901821 x3 + R9264H M901821 x1+R8862A S2601 x4,Dismantle Celcom all RRU&BBU |  | 1
9380B | Teku Commercial Centre MP | Sarawak |  | Modernization |  | 2023Q2 | MA | Datasco | 4.6 TSSR Approved |  | 2023-04-04 |  |  | 2023-04-18 |  | Closed | 2023-04-25 | 2023-05-16 | CD//John | 2023-05-16 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002008005 |  |  | 2023-08-01 | 2023-07-21 |  | Monopole | 30m Monopole | 36 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x2,Dismantle R8860E-GU908 x1+R8882-GUL1812 x2+R8862A S1800(B6A) x2+R8862A S2100(A6A) x4 | 34
9182B | Bukit Kemuyang | Sarawak |  | Modernization |  | 2023Q2 | HQ 2 | CCSMY | 4.6 TSSR Approved |  | 2023-04-05 | 2023-05-05 |  | 2023-05-08 |  | Closed | 2023-05-12 | 2023-05-12 | CD//John | 2023-05-12 | Celcom Digi_RAN-CCSMY-TSS-Sarawak-20230403-0003 | DU00002008006 |  |  | 2023-07-09 | 2023-07-04 |  | Tower | 45m 3 Legged Tower | 62 | Add A9732 M1821 x1 + R9264M M1821 x2,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 1
A00120 | A040C_A00120OD_KGMANJOI | Northern |  | Decomm |  | 2023Q2 | MH | GTSB | 4.6 TSSR Approved |  | 2023-04-11 | 2023-04-25 |  |  | 2023-06-08 |  | 2023-06-09 | 2023-08-08 | CD//Affendi | 2023-06-14 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1/Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230726-0024 | DU00002008007 |  |  |  |  | 2023-07-10 |  | TRIPOD | 4
7111B | Sepanggar | Sabah |  | Modernization |  | 2023Q2 | HQ 6 | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-03 |  | 2023-04-13 |  | Rectificating | 2023-04-25 | 2023-05-11 | CD//Jahganathan | 2023-05-11 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0003 | DU00002008008 |  |  | 2023-06-06 | 2023-06-02 |  | H-bracket pole | Watertank Structure | 3m | Add R9264M M1821 x5,Dismantle R8894E M1821(A8A) x5 | 0 | 23
9080B | Fortune Commercial Centre | Sarawak |  | Modernization |  | 2023Q2 | SH | Datasco | 4.6 TSSR Approved |  | 2023-04-04 |  |  | 2023-05-06 |  | Closed | 2023-05-08 | 2023-05-09 | CD//John | 2023-05-09 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002008009 |  |  | 2023-07-26 | 2023-07-04 |  | Monopole | 30m Monopole | 35 | Add R8852E S9000 x3 + A9732 M1821 x3 + R9264H M901821 x1,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x6 | 234
7109B | Kg Karmilan | Sabah |  | Modernization |  | 2023Q2 | AD | Futong | 4.6 TSSR Approved |  | 2023-06-12 | 2023-06-12 |  | 2023-06-14 |  | Closed | 2023-06-14 | 2023-06-15 | CD//Mohidi Jaan | 2023-06-15 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0003 | DU00002008010 |  |  | 2023-06-26 | 2023-06-21 |  | Lampole | 24m Lampole | 20 | Add R9264H M901821 x3,Dismantle R8882 S1800(B) x3+R8862A S2100(A6A) x3
A00726 | A040C_A00726OD_TMKGTAWAS | Northern |  | Decomm |  | 2023Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2023-04-29 |  |  |  | 2023-07-26 |  | 2023-06-20 | 2023-09-07 | CD//Affendi | 2023-06-21 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1 | DU00002008011 |  |  |  |  | 2023-09-08 | Minimast | BOOM | 5
A00193 | A040B_A00193OD_GREENTOWN | Northern |  | Decomm |  | 2023Q2 | MH | GCI | 4.6 TSSR Approved |  | 2023-05-02 |  |  |  | 2023-06-08 |  | 2023-06-09 |  | CD//Affendi | 2023-06-14 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V2 | DU00002008012 |  |  |  |  | 2023-06-28 |  | BOOM
4303A | Pekan Ayer Tawar | Northern |  | Modernization |  | 2023Q2 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-04-13 | 2023-04-14 |  | 2023-04-18 |  | Closed | 2023-04-18 | 2023-05-10 | CD//Affendi | 2023-04-28 | Celcom Digi_RAN-GTSB-TSS-Northern-20230414-0010 | DU00002008013 |  |  | 2023-05-18 | 2023-05-15 |  | Tower | 60m 3 Legged Tower | 60 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
7127B | UMS Kg. A | Sabah |  | Modernization |  | 2023Q3 | HQ 5 | GTSB | 4.6 TSSR Approved |  | 2023-04-07 | 2023-04-12 |  | 2023-04-26 |  | Closed | 2023-04-28 | 2023-05-10 | CD//Jahganathan | 2023-04-29 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230407-0002 | DU00002008014 |  |  | 2023-07-13 | 2023-07-06 |  | BillBoard | 3m RT (Minimast) | 26m | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x3 | 12
9667C | Jalan Sibu Jaya (SJDH) | Sarawak |  | Modernization |  | 2023Q2 | SH | AllStar | 4.6 TSSR Approved |  | 2023-04-14 | 2023-04-28 |  | 2023-05-04 |  | Closed | 2023-05-05 | 2023-05-06 | CD//John | 2023-05-05 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230403-0003 | DU00002008015 |  |  | 2023-06-19 | 2023-06-12 |  | Monopole | Land site | 30 | Add R9264H M901821 x4,Dismantle R8894E M1821(A8A) x4
A01063 | A040C_A01063OD_KG_KANTHAN | Northern |  | Decomm |  | 2023Q2 | ZA | GCI | 4.6 TSSR Approved |  | 2023-06-20 |  |  |  | 2023-08-11 |  | 2023-08-16 | 2023-08-24 | CD//Quah | 2023-08-22 | Celcom Digi_RAN-GCI-TSS-Northern-20230609-0025_V2/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240130-0093_V1 | DU00002008016 |  |  |  |  | 2023-07-15 | Monopole | MONOPOLE | 30
9358A | Sibu Airport Road (Maxis) | Sarawak |  | Modernization |  | 2023Q2 | SH | AllStar | 4.6 TSSR Approved |  | 2023-05-13 | 2023-05-13 |  | 2023-05-16 |  | Closed | 2023-05-18 | 2023-05-20 | CD//John | 2023-05-18 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230403-0003 | DU00002008017 |  |  | 2023-06-25 | 2023-06-12 |  | Tower | Tower | 47 | Add R9264H M901821 x3,Dismantle R8860E-GU908 x1+R8894E M1821(A8A) x3
7113H | 99 Speedmart BERUNGIS COMMERCIAL CENTRE | Sabah |  | MOCN As-Is |  | 2023Q2 | AD |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008018 | [6 empty] | Small Cell
9102R | RUMAHMANDAU | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2023Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | N/A - no need PR for MOCN Decomm | DU00002008019 | [6 empty] | Land site
4497A | Jelapang RDD | Northern |  | Modernization |  | 2023Q2 | MH | YPTT | 4.6 TSSR Approved |  | 2023-04-13 | 2023-05-02 |  | 2023-04-17 |  | Closed | 2023-05-03 | 2023-05-25 | CD//Quah | 2023-05-15 | Celcom Digi_RAN-YPTT-TSS-Northern-20230414-0005 | DU00002008020 |  |  | 2023-06-05 | 2023-06-03 |  | Minimast | 3m RT (Minimast) | 10 | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8840-U216 x1 |  | 1
4535A | Kompleks Islam RCC | Northern |  | Modernization |  | 2023Q2 | MH | YPTT | 4.6 TSSR Approved |  | 2023-04-14 | 2023-04-25 |  | 2023-04-19 |  | Closed | 2023-04-27 | 2023-05-18 | CD//Quah | 2023-05-08 | Celcom Digi_RAN-YPTT-TSS-Northern-20230417-0006 | DU00002008021 |  |  | 2023-05-31 | 2023-05-27 |  | H-bracket pole | 3m Boom (RT) | 3 | Add R8852E S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x3 | 23
4319D | Penang Science Park | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-01 | 2023-05-08 |  | 2023-05-10 |  | Closed | 2023-05-11 | 2023-05-25 | CD//Affendi | 2023-05-16 | Celcom Digi_RAN-GTSB-TSS-Northern-20230502-0012 | DU00002008022 |  |  | 2023-07-04 | 2023-06-19 |  | Monopole | 45m Monopole | 45 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x2,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 |  | 13
4610C | Hup Heng Motors (REL) | Northern |  | Modernization |  | 2023Q2 | ZA | GCI | 4.6 TSSR Approved |  | 2023-04-13 | 2023-04-15 |  | 2023-04-19 |  | Closed | 2023-04-23 | 2023-05-11 | CD//Heng | 2023-05-03 | Celcom Digi_RAN-GCI-TSS-Northern-20230414-0005 | DU00002008023 |  |  | 2023-06-01 | 2023-05-31 |  | Pole | 3m Bipod (RT) | 6 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
B00017 | B058C_B00017OD_PR_TMNPTLGKLG | Central | 1010K | Swap |  | 2023Q2 | YZ | Ascentrack | 4.6 TSSR Approved |  | 2023-04-17 | 2023-04-28 |  | 2023-04-29 |  | Closed | 2023-05-02 | 2023-06-05 | CD//Ali akaram | 2023-05-16 | CelcomDigi_RAN_Ascentrack_TSS_Central_20230417_0012 | DU00002008024 |  |  | 2023-06-22 | 2023-06-21 |  | Unipole | BOOM | 9 | Add R9264H M901821 x3 + R8862A S2601 x3,Dismantle Celcom all RRU&BBU
4710B | Batu Hampar RDD | Northern |  | Modernization |  | 2023Q2 | WP | YPTT | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-20 |  | 2023-04-18 |  | Closed | 2023-04-24 | 2023-05-11 | CD//Quah | 2023-04-25 | Celcom Digi_RAN-YPTT-TSS-Northern-20230413-0004 | DU00002008025 |  |  | 2023-05-16 | 2023-05-15 |  | Tower | 60m 3 Legged Tower | 60 | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3+R8881 S2100 x3
4711B | Pintu Gerbang Beruas RDD | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Zulakmar |  |  | DU00002008026 | [6 empty] | 60m 3 Legged Tower
9415B | Jln Bkt Lima | Sarawak |  | Modernization |  | 2023Q2 | MA | Trintel | 4.6 TSSR Approved |  | 2023-04-04 | 2023-04-25 |  | 2023-04-27 |  | Closed | 2023-04-29 | 2023-04-29 | CD//John | 2023-04-29 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230403-0003 | DU00002008027 |  |  | 2023-07-28 | 2023-07-25 |  | Monopole | 30m Monopole | 31m | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R9224E M1821(AAB) x3 | 123
4338B | IGB Umobile (REL) | Northern |  | Modernization |  | 2023Q2 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-04-13 | 2023-04-20 |  | 2023-04-26 |  | Closed | 2023-04-27 | 2023-05-25 | CD//Heng | 2023-05-02 | Celcom Digi_RAN-GTSB-TSS-Northern-20230414-0010 | DU00002008028 |  |  | 2023-06-02 | 2023-06-02 |  | Lampole | 24m Lampole | 35 | Add R9264H M901821 x3,Dismantle R8882 S1800(B) x1+R8862A S1800(B6A) x2+R8881 S2100 x2 | 0 | 0
9143A | 12th Mile Oya | Sarawak |  | Modernization |  | 2023Q2 | BY | Datasco | 4.6 TSSR Approved |  | 2023-04-05 | 2023-04-12 |  | 2023-04-17 |  | Closed | 2023-04-23 | 2023-05-02 | CD//John | 2023-04-28 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002008029 |  |  | 2023-05-29 | 2023-05-26 |  | Tower | 30m 4 Legged Tower | 47m | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8840 U216 x3+R8840-U216 x3
A00110 | A043B_A00110OD_LAPAIRTAWAR_RCC | Northern |  | Decomm |  | 2023Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2023-04-12 | 2023-06-26 |  |  | 2023-06-17 |  | 2023-06-20 | 2023-07-21 | CD//Heng | 2023-07-13 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20230717-0022/Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1 | DU00002008030 |  |  |  |  | 2023-07-08 | Tower | TOWER | 60
4627C | Masjid Batu Kg Pertama | Northern |  | Modernization |  | 2023Q3 | HQ 1 | CCSMY | 4.6 TSSR Approved |  | 2023-06-06 | 2023-06-02 |  | 2023-06-07 |  | Closed | 2023-06-12 | 2023-06-21 | E//Hazida | 2023-06-21 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230508-0017 | DU00002008031 |  |  | 2023-07-04 | 2023-06-19 |  | Monopole | 30m Monopole | 30 | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
4235H | 99 Speedmart PK Tmn Alkaff | Northern |  | MOCN As-Is |  | 2023Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008032 | [6 empty] | Small Cell
7281B | UCA 2 | Sabah |  | Modernization |  | 2023Q2 | HQ 7 | Futong | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-27 |  | 2023-04-29 |  | Closed | 2023-05-04 | 2023-05-05 | CD//Mohidi Jaan | 2023-05-05 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0003 | DU00002008033 |  |  | 2023-06-24 | 2023-06-16 |  | Monopole | 30m Monopole | 30 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x5 | 23
4264H | 99 Speedmart PK Tmn Bertuah | Northern |  | MOCN As-Is |  | 2023Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008034 | [6 empty] | Small Cell
9373B | Hock Peng MP | Sarawak |  | Modernization |  | 2023Q2 | BY | Datasco | 4.6 TSSR Approved |  | 2023-04-06 | 2023-04-13 |  | 2023-04-16 |  | Rectificating | 2023-04-20 | 2023-04-25 | CD//John | 2023-04-25 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230403-0002 | DU00002008035 |  |  | 2023-07-07 | 2023-06-30 |  | Monopole | Tower | 30m | Add A9732 M1821 x3 + R9264M M1821 x1,Dismantle R9224E M1821(AAB) x4 | 123
B00243 | B058E_B00243OD_OLAKLEMPIT | Central |  | Decomm |  | 2023Q2 | CR | GTSB | 4.6 TSSR Approved |  | 2023-04-09 |  |  | 2023-04-13 | 2023-08-03 | Closed | 2023-08-04 | 2025-03-24 | CD//Norhaliza | 2023-09-15 | CelcomDigi_RAN_GTSB_TSS_Central_20230626_decom reraise | DU00002008036 |  |  |  |  | 2023-06-19 | Tower | TOWER | 40m
7417B | Grand Merdeka IB | Sabah |  | Modernization |  | 2023Q2 | AD | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-04 |  | 2023-04-28 |  | Closed | 2023-05-04 | 2023-05-05 | CD//Mohidi Jaan | 2023-05-05 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0003 | DU00002008037 |  |  | 2023-06-09 | 2023-06-09 |  | Wall mount boom | In-building system |  | Reuse existing RRU
4485A | Pantai Remis Town | Northern |  | Modernization |  | 2023Q2 | MH | GCI | 4.6 TSSR Approved |  | 2023-04-12 | 2023-04-23 |  | 2023-04-15 |  | Closed | 2023-04-26 | 2023-05-18 | CD//Quah | 2023-05-08 | Celcom Digi_RAN-GCI-TSS-Northern-20230414-0005 | DU00002008038 |  |  | 2023-05-27 | 2023-05-27 |  |  | 6m RT (Boom) | S1S3S4 : 7m S2: 4m | Add R8852E S9000 x3 + A9732 M1821 x3 + R9264H M901821 x1,Dismantle R8894E M1821(A8A) x4 | 124
7085B1 | pBTS Kingfisher | Sabah |  | Modernization |  | 2023Q3 | HQ 2 | GTSB | 4.6 TSSR Approved |  | 2023-04-04 | 2023-04-05 |  | 2023-04-14 |  | Closed | 2023-04-18 | 2023-06-01 | CD//Mohidi Jaan | 2023-06-01 | Celcom Digi_RAN-GTSB-TSS-Sabah-20230407-0002 | DU00002008039 |  |  | 2023-06-16 | 2023-06-09 |  | Guide mast | 25m pBTS | 31 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 | 0
7345B | Bukit Kokol | Sabah |  | Modernization |  | 2023Q2 | HQ 6 | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-08 |  | 2023-04-14 |  | Closed | 2023-04-27 | 2023-04-28 | CD//Jahganathan | 2023-04-28 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0003 | DU00002008040 |  |  | 2023-06-10 | 2023-06-07 |  | Tower | 45m 3 Legged Tower | 76 | Add R9264H M901821 x3 + R9264M M1821 x3 + R8862A S2601 x3,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 |  | 123
9125A | Bkt Tunggong | Sarawak |  | Modernization |  | 2023Q3 | HQ 2 | Magicell | 4.6 TSSR Approved |  | 2023-04-27 | 2023-05-04 |  | 2023-05-08 |  | Closed | 2023-05-12 | 2023-05-15 | CD//John | 2023-05-12 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20230502-0004 | DU00002008041 |  |  | 2023-06-21 | 2023-06-16 |  | Tower | 45m 3 Legged Tower | 61 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
7632A_IBC | Nexus Karabunai Resort | Sabah |  | Modernization |  | 2023Q2 | AD | Datasco | 4.6 TSSR Approved |  | 2023-09-11 | 2023-09-19 |  | 2023-09-21 |  | Closed | 2023-09-21 | 2023-10-31 | E//Hannah | 2023-09-27 | Celcom Digi_RAN-Datasco-TSS-Sabah-20230913 | DU00002008042 |  |  | 2023-10-09 | 2023-09-30 |  | Portables BTS | IBS + RT (Boom) |  | Add R8862A S2100 x1+R8862A S1800 x1,Dismantle R8840-U216 x1+R8882-GUL1812 x1
7227A | Kampung Malawa | Sabah |  | Modernization |  | 2023Q2 | HQ 7 | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-04-14 |  | 2023-04-20 |  | Closed | 2023-04-25 | 2023-05-02 | CD//Jahganathan | 2023-04-29 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0003 | DU00002008043 |  |  | 2023-06-28 | 2023-06-12 |  | Tower | 20m 4 Legged Tower | 35 | Add R8852E S9000 x3 + A9732 M1821 x3,Dismantle R8894E M1821(A8A) x4 | 123
4200A | TMN LEAN FUNG | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-05-10 | 2023-05-13 |  | 2023-05-17 |  | Closed | 2023-05-22 | 2023-06-01 | E//Hazida | 2023-05-31 | Celcom Digi_RAN-GTSB-TSS-Northern-20230508-0015 | DU00002008044 |  |  | 2023-06-18 | 2023-06-17 |  |  | 6m RT (Boom) | 7 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
7072H | 99 Speedmart MENGGATAL TOWN | Sabah |  | MOCN As-Is |  | 2023Q2 | AD |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008045 | [6 empty] | Small Cell
7106B | Kg Bangka Bangka | Sabah |  | Modernization |  | 2023Q3 | HQ 5 | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-05-08 |  | 2023-04-26 |  | Closed | 2023-04-28 | 2023-05-03 | CD//Ray Amos | 2023-05-03 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0003 | DU00002008046 |  |  | 2023-07-03 | 2023-06-26 |  | Unipole | 24m Lampole | 11m | Add R9264M M1821 x3,Dismantle R8882 S1800(B) x2+R8882 S1800B(B6B) x1+R8854D S2100(A4A) x3 | 0 | 0
7321H | Restoran Sedap | Sabah |  | MOCN As-Is |  | 2023Q2 | AD |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008047 | [6 empty] | Rooftop
4513B | Bukit Kinding | Northern |  | Modernization |  | 2023Q2 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-04-17 | 2023-04-28 |  | 2023-04-28 |  | Closed | 2023-05-05 | 2023-05-25 | CD//Heng | 2023-05-09 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230418-0008 | DU00002008048 |  |  | 2023-06-06 | 2023-06-03 |  | Tower | 60m 3 Legged Tower | 60 | Add R9264M M1821 x6 + R8862A S2601 x3,Dismantle R8894E M1821(A8A) x3 |  | 123
9981A | Sibujaya 6 | Sarawak |  | Modernization |  | 2023Q2 | BY | AllStar | 4.6 TSSR Approved |  | 2023-04-11 | 2023-04-13 |  | 2023-04-14 |  | Closed | 2023-04-20 | 2023-05-10 | CD//John | 2023-05-02 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20230403-0003 | DU00002008049 |  |  | 2023-06-14 | 2023-06-08 |  |  | 30m Lampole | 30 | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x4
A00856 | A040C_A00856OD_TMNMERUPERDANACHEMOR | Northern |  | Decomm |  | 2023Q2 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-04-13 |  |  |  | 2023-08-02 |  | 2023-08-01 | 2024-02-22 | CD//Rohizam | 2023-08-15 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V2 | DU00002008050 |  | xD cabinet no space for relocation xC, propose new cabinet |  |  | 2023-08-02 | Minaret | MINARET | 35m
B00154 | B061F_B00154OD_KM447SGSERAI | Central |  | Decomm |  | 2023Q2 | IE | MTK | 4.6 TSSR Approved |  | 2023-04-13 | 2023-06-26 |  |  | 2023-06-08 |  | 2023-07-12 | 2023-11-28 | CD//Norhaliza | 2023-11-16 | CelcomDigi_RAN_MTK_TSS_Central_20230626_decom reraise | DU00002008051 |  |  |  |  | 2023-10-30 | Tower | TOWER | 60
9110A | Bintulu New Airport (SACOFA) | Sarawak |  | Modernization |  | 2023Q3 | MA | Trintel | 4.6 TSSR Approved |  | 2023-04-05 | 2023-05-10 |  | 2023-04-29 |  | Closed | 2023-05-03 | 2023-05-18 | CD//John | 2023-05-03 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20230403-0003 | DU00002008052 |  |  | 2023-06-18 | 2023-06-12 |  | Tower | Tower | 18m | Add R9264H M901821 x3 + R9264M M1821 x1 + R8862A S2601 x1,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1 |  | 3
A00016 | A042D_A00016OD_SEGARIBT10 | Northern |  | Decomm |  | 2023Q2 | ZA | CCSMY | 4.6 TSSR Approved |  | 2023-04-13 |  |  |  | 2023-06-21 |  | 2023-06-23 | 2023-07-21 | CD//Heng | 2023-07-13 | Celcom Digi_RAN-CCSMY-TSS-Northern-20230609-0023_V2 | DU00002008053 |  |  |  |  | 2023-06-26 |  | TOWER
A00495 | A040B_A00495OD_MASJIDSAS | Northern | 4170K | Swap | Decomm->Swap | 2023Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2023-04-09 |  |  | 2023-05-31 | 2023-06-14 | Closed | 2023-06-07 | 2023-08-17 | CD//Affendi | 2023-08-17 | Celcom Digi_RAN-GTSB-TSS-Northern-20230609-0021_V1 | DU00002008054 |  |  | 2023-08-25 | 2023-08-25 |  | Minaret | SHARING STRC OTHERS MINARATE | 26 | Add R8852E S9000 x2+R9264H M901821 x1+R8862A S2601 x3+A9732 M1821 x2,Dismantle | 13
A00395 | A040B_A00395OD_KWSPIPOH_RCD | Northern |  | Decomm |  | 2023Q2 | ZA | YPTT | 4.6 TSSR Approved |  | 2023-04-25 |  |  |  | 2023-06-17 |  | 2023-06-19 | 2024-03-26 | CD//Affendi | 2023-06-21 | Celcom Digi_RAN-YPTT-TSS-Northern-20230609-0018 | DU00002008055 |  | 21/8 Missing IDU Label Photo Need Include all TX Photo 11/9: No TX photo for xC Dismantle 27/2: Missing Label TX equipment, Missing xD Cabinet |  |  | 2023-07-20 |  | BOOM
4333C | Penang Bridge Tol (REL) | Northern |  | Modernization |  | 2023Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-04-29 | 2023-05-04 |  | 2023-05-08 |  | Closed | 2023-05-09 | 2023-05-25 | CD//Heng | 2023-05-13 | Celcom Digi_RAN-GTSB-TSS-Northern-20230502-0012 | DU00002008056 |  |  | 2023-06-10 | 2023-06-07 |  | Tower | 60m 4 Legged Tower | 60 | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x3+R8894E M1821(A8A) x3+R9224E M1821(AAB) x3 | 123
7154A | Menggatal | Sabah |  | Modernization |  | 2023Q2 | HQ 7 | Futong | 4.6 TSSR Approved |  | 2023-04-08 | 2023-05-08 |  | 2023-04-20 |  | Closed | 2023-04-25 | 2023-05-02 | CD//Jahganathan | 2023-05-02 | Celcom Digi_RAN-Futong-TSS-Sabah-20230407-0003 | DU00002008057 |  |  | 2023-06-24 | 2023-06-12 |  | Tower | 30m 4 Legged Tower | 33 | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x3+R8894E M1821(A8A) x6 | 123
9049Z | Tg.PenasuBatuBurak | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q2 |  |  | 14.1 Drop (No Survey) |  | 2025-11-28 |  |  |  |  | To be Submitted |  |  | CD//Norhaliza |  |  | DU00002008058 | [6 empty] | 45m 3 Legged Tower
4222C | AEON Klebang Ipoh | Northern |  | Modernization |  | 2023Q2 | WP | GCI | 4.6 TSSR Approved |  | 2023-04-14 | 2023-04-15 |  | 2023-05-09 |  | Closed | 2023-05-11 | 2023-05-25 | CD//Shamsul | 2023-05-13 | Celcom Digi_RAN-GCI-TSS-Northern-20230417-0006 | DU00002008059 |  |  | 2023-06-08 | 2023-06-06 |  |  | In-building system |  | Add R8862A S2100 x3
4772C | Klebang Restu Ipoh (KBDM) | Northern |  | Modernization |  | 2023Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2023-04-11 | 2023-04-15 |  | 2023-04-15 |  | Closed | 2023-04-19 | 2023-05-09 | CD//Quah | 2023-05-05 | Celcom Digi_RAN-GTSB-TSS-Northern-20230411-0008 | DU00002008060 |  |  | 2023-05-21 | 2023-05-21 |  | Monopole | 24m Lampole | 30M | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
9043Z | NangaDapRumahJelanRumahMichaelRumahBantin | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008061 | [6 empty] | 45m 3 Legged Tower
9042Z | RumahLambaiRumahMindaLadangMapai | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2023Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002008062 | [6 empty] | 45m 3 Legged Tower
3833A | LATAR08 | Central |  | Modernization |  | 2023Q2 | IE | MTK | 4.6 TSSR Approved |  | 2023-04-10 | 2023-04-12 |  | 2023-05-02 |  | Closed | 2023-05-06 | 2023-06-08 | E//Kok Keen | 2023-06-06 | CelcomDigi_RANMW_MTK_TSS_Central_20230609_0002 | DU00002013107 |  |  | 2023-07-11 | 2023-07-11 |  | Tower | 45m Tower | 45 | Add R9264H M901821 x3,Dismantle R8882 S1800(B) x3+R8882 S2100 x3+R8881 S2100 x3
2773B | LATAR HW Tmn Rimba Templer | Central |  | Modernization |  | 2023Q2 | YZ | MTK | 4.6 TSSR Approved |  | 2023-04-11 | 2023-04-25 |  | 2023-05-16 |  | Closed | 2023-05-25 | 2023-06-06 | E//Kok Keen | 2023-06-01 | CelcomDigi_RANMW_MTK_TSS_Central_20230609_0002 | DU00002013108 |  |  | 2023-06-15 | 2023-06-13 |  | Tower | Tower | 45 | Add R9264H M901821 x3,Dismantle R8882 S1800(B) x2
2476A | Sg Serai (Maxis) | Central | 2476A | Modernization |  | 2023Q2 | IE | MTK | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦loading issue,AAU cannot install | 2023-04-13 | 2023-05-05 |  | 2023-05-15 |  | Closed | 2023-05-25 | 2023-08-23 | E//Kok Keen | 2023-06-06 | CelcomDigi_RAN_MTK_TSS_Central_20230417_0002 | DU00002013109 | NIC_S2_Change MM to BI_loading issue_MAXIS |  | 2023-10-26 | 2023-10-23 |  | Tower | 45m 3 Legged Tower | 60.3m | Add R9264H M901821 x3+ R9264M M1821 x3 + R8862A S2601 x3,Dismantle R8882 S1800(B) x3+R8862A S2100(A6A) x3 |  | 123
2432A | Kundang (KJS) | Central |  | Modernization |  | 2023Q2 | IE | MTK | 4.6 TSSR Approved |  | 2023-04-10 | 2023-05-11 |  | 2023-05-27 |  | Closed | 2023-06-01 | 2023-07-07 | E//Kok Keen | 2023-07-07 | CelcomDigi_RAN_MTK_TSS_Central_20230609_0004 | DU00002013110 |  |  | 2023-07-17 | 2023-07-17 |  | Monopole | 45m Monopole | 45 | Add A9732 M1821 x2 + R9264M M1821 x1,Dismantle R8894E M1821(A8A) x3 | 23
1766B | Ladang Sg Tua(Maxis) | Central |  | Modernization |  | 2023Q2 | MA | MTK | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI,L2600 change to 40M¦Maxis rejected,Only allow 3*RRU+3*Antenna on tower top.If change MM to Bi-sector,need to add new cable ladder for new feeders. | 2023-04-12 | 2023-04-17 |  | 2023-05-10 |  | Closed | 2023-05-11 | 2023-07-13 | E//Kok Keen | 2023-09-20 | CelcomDigi_RAN MW_MTK_TSS_Central_20230413_0001 / CelcomDigi_RAN_MTK_Central_20230721_ClearLoan | DU00002013111 | NIC_S2_Change MM to BI,L2600 change to 40M_owner reject_MAXIS |  | 2023-09-30 | 2023-09-26 |  | Tower | 60m 3 Legged Tower | 60 | Add R9264H M901821 x3 + R9264M M1821 x2 + R8862A S2601 x3,Dismantle R8894E M1821(A8A) x2+R8862A S9000(A6A) x2 | 0 | 12(S1->S2,S2->S3，S3->S1,rename sector ID,Bisector@ new S2/S3)
1412A | Bkt Tadun | Central |  | Modernization |  | 2023Q2 | IE | MTK | 4.6 TSSR Approved |  | 2023-04-11 | 2023-04-14 |  | 2023-05-12 |  | Closed | 2023-05-18 | 2023-06-01 | E//Kok Keen | 2023-06-01 | CelcomDigi_RAN_MTK_TSS_Central_20230609_0004 | DU00002013112 |  |  | 2023-05-29 | 2023-05-27 |  | Tower | 60m 4 Legged Tower | 76 | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x4 | 123
4809A | JJusco Kinta | Northern |  | Modernization |  | 2023Q2 | ZA | GCI | 4.6 TSSR Approved |  | 2023-03-31 | 2023-04-06 |  | 2023-04-14 |  | Closed | 2023-04-14 | 2023-04-27 | CD//Shamsul | 2023-04-27 | Celcom Digi_RAN-GCI-TSS-Northern-20230331-0004 | DU00001867803 |  |  | 2023-05-23 | 2023-05-17 |  |  | In-building system | IBC SITE | Add R8862A S1800 x1，dismantle R8882-GUL1812 x1
A00186_IBC | JJusco Kinta | Northern |  | Decomm |  | 2023Q2 | ZA | GCI | 4.6 TSSR Approved |  | 2023-03-31 |  |  |  | 2023-10-19 |  | 2023-11-17 | 2024-02-27 | CD//Shamsul | 2023-11-22 | Celcom Digi_RAN-GCI-TSS-Northern-20240512-0106 | DU00001879061 |  |  |  |  | 2023-10-07 |  | BOOM
7041D | PEKAN TELUPID | Sabah |  | Remote MOCN |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00003438325 | [10 empty] | 13
7323C | KGPOPOK | Sabah |  | Modernization |  | 2024 Q3(single site MOCN) | MS | Futong | 14.0 TSSR Not Required (Reuse Existing BBU/RRU) |  | 2025-09-29 |  |  |  |  | To be Submitted |  |  |  |  | 0809CD-Sabah-Futong-BOQ Template(new contract) | DU00003515122 |  |  | 2024-04-07 | 2024-03-13 |  |  | TOWER |  | Reuse existing RRU
B00902 | B063B_B00902IB_AMCKLIASEPANG | Central |  | Decomm | Swap->On Hold->Decomm | 2024 Additional | SHA | CCSMY | 4.6 TSSR Approved |  | 2024-04-30 | 2024-05-24 |  | 2024-05-31 | 2024-10-07 | Closed | 2024-12-15 | 2025-03-21 | CD//Sofiah | 2024-12-16 | 0813CD-Central-CCSMY-BOQ Template(new contract) | DU00003515123 | [5 empty] | Portables BTS
7324C | KAMPUNGTOMPINATAU | Sabah |  | Modernization |  | 2024 Q3(single site MOCN) | MS | Futong | 14.0 TSSR Not Required (Reuse Existing BBU/RRU) | [6 empty] | To be Submitted |  |  |  |  | 0809CD-Sabah-Futong-BOQ Template(new contract) | DU00003515124 |  |  | 2024-04-07 | 2024-03-13 |  |  |  |  | Reuse existing RRU
1382C | AMC KLIA SEPANG IB | Central |  | Modernization | Decomm->On Hold->Modernization | 2024 Additional | AI | CCSMY | 4.6 TSSR Approved |  | 2024-05-03 | 2024-09-30 |  | 2024-10-01 | 2024-05-08 | Under Approval | 2024-10-04 | 2024-10-14 | E//Nazrul | 2024-10-02 | 0813CD-Central-CCSMY-BOQ Template(new contract) | DU00003515125 |  | TOPO show digi ON, Celcom OFF | 2025-02-25 | 2025-02-20 |  | Portables BTS |  |  | Add R8852E S9000 x1+R8894E M1821 x1,Dismantle R8892E M1821(BAA) x1 | 0 | 0
W01573 | W066Q_W01573OD_SALAKSELATANNEWVILLAGE3 | Central | 1904K | Swap |  | 2025 | AI | GTSB | 4.6 TSSR Approved |  | 2025-03-18 | 2025-03-21 |  | 2025-03-24 |  | Under Approval | 2025-03-25 | 2025-10-06 | CD//Sapian | 2025-10-06 | SQ202505080070 | DU00005190638 |  |  | 2025-04-21 | 2025-04-10 |  | Lampole |  | 20M | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
1649C | PUTRA MAHKOTA (REL) | Central |  | Remote MOCN |  | 2024 Q1_496 |  | YPTT | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002561865 | [6 empty] | Lampole
4109B | Simpang Empat RT | Northern |  | Remote MOCN |  | 2024 Q1_496 | ZA | CCSMY | 14.1 Drop (No Survey) |  |  | 2023-09-04 |  |  |  | To be Submitted |  |  | E//Hazida |  | N/A - site move to BAU | DU00002561866 | [5 empty] | In-Building System | 60m 4 Legged Tower | 12
9432A | Jalan Sekama 2 | Sarawak |  | Remote MOCN |  | 2024 Q1_496 |  | Datasco | 14.2 Drop (Done Survey) |  | 2023-08-29 | 2023-10-31 |  |  |  | To be Submitted |  |  |  |  | Celcom Digi_RAN-Datasco-TSS-Sarawak-20230830 | DU00002561867 | [6 empty] | 30m Monopole | 30 |  | 3
4190B | Jalan Abd Kadir | Northern |  | Remote MOCN |  | 2024 Q1_496 | HQ 1 | GCI | 14.1 Drop (No Survey) |  |  | 2023-09-04 |  |  |  | To be Submitted |  |  | E//Hazida |  | N/A - site move to BAU | DU00002561868 | [5 empty] | In-Building System | 3m Bipod (RT) | 2m
4236A | Dua Kongsi (Celcom) | Northern |  | Remote MOCN |  | 2024 Q1_496 | HQ 1 | GTSB | 14.2 Drop (Done Survey) |  | 2023-12-07 | 2023-08-21 |  |  |  | To be Submitted |  |  | E//Hazida |  | N/A - site move to BAU | DU00002561869 | [5 empty] | Tower | 60m 4 Legged Tower | 55 |  | 13
1559B4 | pBTS Teluk Air Tawar (REL) | Northern |  | Remote MOCN |  | 2024 Q1_496 | BY | YPTT | 14.1 Drop (No Survey) |  |  | 2023-08-28 |  |  |  | To be Submitted |  |  | E//Hazida |  | N/A - site move to BAU | DU00002561870 | [5 empty] | Watertank | 25m pBTS | 31
2977B | DiGi HQ (Lot 10) | Central |  | Remote MOCN |  | 2024 Q1_496 | IE | In-House | 4.6 TSSR Approved |  | 2023-09-11 | 2023-09-14 |  | 2023-09-18 |  | Closed | 2023-09-19 | 2023-09-20 | E//Nazrul | 2023-09-19 | CelcomDigi_RAN_Magicell_TSS_Central_20230912 | DU00002561871 | [5 empty] | Portables BTS | In-building system |  | Reuse existing RRU
K00119_1 | K009A_K00119OD_JKRKUALANERANG | Northern | 4640K | Swap | Decomm->On Hold->Decomm->Swap | 2024 Q3 | [9 empty] | To be Submitted | [5 empty] | DU00006778501 | [8 empty] | Add R8862A S9000x3+R9264M M1821x1+A9732 M1821x2+R8854 S2600x3 | 23
4999A_1 | Kuala Nerang | Northern |  | Modernization | Modernization->Remote MOCN>Modernization | [10 empty] | To be Submitted | [5 empty] | DU00006778502 | [8 empty] | Add R9264M M1821x2, Dismantle A9732 M1821x2 | 0 | 0
8037Z | Brook | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002859978 | [6 empty] | 76m 4 Legged Tower
4442B | Kuala Terla | Northern |  | Modernization | Modernization->On Hold->Modernization | 2024 Q4(single site MOCN)-L26 SSM | SM | GCI | 4.6 TSSR Approved | ¦ 1126 - Emailed rollout on PE required | 2024-11-18 | 2024-11-19 |  | 2024-11-25 |  | Rectificating | 2024-11-26 | 2024-12-16 | E//Hazida | 2024-12-15 | SQ202411060531 | DU00002859979 |  |  | 2024-12-06 | 2024-12-06 |  | In-Building System | 3m Boom (RT) | S1&S3=7, S2=8 | Add R8894E M1821x2+A9732 M1821 x1,Dismantle R8854E S1800(A6A)x3+R8854D S2100(A4A)x3 | 1 | 0
4107R | 4834_BohTea_BOHTM1_22 | Northern |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2025 Q3 | HW | GCI | 4.6 TSSR Approved |  | 2025-10-15 |  | 2025-10-22 |  | 2025-10-24 |  | 2026-02-16 | 2026-02-16 |  | 2026-04-17 | SQ202504230429-GCI | DU00002859980 |  |  |  |  | 2026-01-30
4900B | Puncak Arabella | Northern |  | Modernization | Modernization->On Hold->Modernization | 2024 Q3(single site MOCN) | SM | GTSB | 4.6 TSSR Approved |  | 2024-04-30 | 2024-05-02 |  | 2024-05-04 |  | Rectificating | 2024-05-10 | 2024-05-13 | E//Hazida | 2024-05-13 | Celcom Digi_RAN-GTSB-TSS-Northern-20240502-0106 | DU00002859981 |  |  | 2024-06-18 | 2024-05-27 |  | Tower | Tower | 76m | Add R8862A S9000 x3+R9224E M1821 x2+A9732 M1821 x1,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3 | 3 | 0
2297B | Inti College Nilai | Southern |  | Site Out (Modernization) | Modernization->Site Out->Site Out (Modernization) | 2025 Q3 |  | CCSMY | [SiteOut]- 1.0 Pending Survey - Subcon | [6 empty] | To be Submitted | [5 empty] | DU00002859982 | [6 empty] | 60m 3 Legged Tower
4572A | Tringkap | Northern |  | Modernization | Modernization->On Hold->Modernization | 154 single site MOCN | SM | GCI | 4.6 TSSR Approved | ¦ 0923 - E//Hazida: Suggest to restudy anchor site proposal, xC site is having higher antenna and located at higher elevation and high possibility having better coverage area. Since this location is hilly with surrounding blockage, suggest to change anchor/unpair. | 2024-08-21 | 2024-08-25 |  | 2024-08-30 |  | Rectificating | 2024-09-02 | 2024-09-23 | E//Hazida | 2024-09-23 | 0809CD-Northern-GCI-BOQ Template(new contract) | DU00002859983 |  |  | 2024-09-17 | 2024-09-07 |  | Floor Mount Boom | 60m 4 Legged Tower | 6 | Add R8894E M1821 x5+R8854 S2600 x2,Dismantle R8862A S1800(B6A) x3+R8862A S2600(A4A) x2 | 0 | 13
4204C | Ulu Ringlet | Northern |  | Modernization | Modernization->On Hold->Modernization | 154 single site MOCN | SM | GTSB | 4.6 TSSR Approved |  | 2024-08-29 | 2024-09-05 |  | 2024-09-10 |  | Rectificating | 2024-09-11 | 2024-09-26 | E//Hazida | 2024-09-25 | 0809CD-Northern-GTSB-BOQ Template(new contract) | DU00002859984 |  |  | 2024-09-27 | 2024-09-20 |  | Tower | 15m Mini Structure | 15 | Add R8862A S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882 S1800B(B6B) x3+R8881 S2100 x3+R8862A S2600(A4A) x1 | 0 | 2
4618D | Taman Ringlet | Northern |  | Modernization | Modernization->On Hold->Modernization | 131 single site mocn | SHA | CCSMY | 4.6 TSSR Approved |  | 2024-08-29 | 2024-09-02 |  | 2024-09-07 |  | Under Approval | 2024-09-09 | 2024-09-25 | E//Ajay | 2024-09-25 | 0809CD-Northern-CCSMY-BOQ Template(new contract) | DU00002859985 |  |  | 2024-09-30 | 2024-09-30 |  | Tower | 60M Tower | 70m | Add R8862A S9000 x4+R8862A S2601 x2+A9732 M1821 x2,Dismantle R9224E M1821(AAB) x2 | 12 | 0
D00443 | Brook_T3_0269_RAN SHARING | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002859986 | [6 empty] | #N/A
4103D | Cosa Rossa | Northern |  | Modernization | Modernization->On Hold->Modernization | 154 single site MOCN | SHA | GCI | 4.6 TSSR Approved |  | 2024-08-22 | 2024-08-25 |  | 2024-08-29 |  | Under Approval | 2024-08-30 | 2024-09-11 | E//Ajay | 2024-09-10 | 0809CD-Northern-GCI-BOQ Template(new contract) | DU00002859987 |  |  | 2024-09-30 | 2024-09-05 |  | Monopole | Tower | 30 | Add R8894E M1821 x5+R8854 S2600 x2,Dismantle R8862A S2600(A4A) x2+R8892E M1821(BAA) x3 | 0 | 12
C00031 | C048A_C00031OD_CB_KUALATERLA | Northern |  | Decomm |  | 2024 | HW | GCI | 4.6 TSSR Approved |  | 2025-01-21 |  | 2025-01-09 |  | 2024-12-20 |  | 2025-06-17 | 2025-10-01 | E//Hazida | 2025-07-15 | SQ202504180288-GCI/SQ202505160598 | DU00002859988 |  | Missing FE Tx Part |  |  | 2024-12-24 |  | BOOM
C00537 | C048A_C00537OD_CD_BOHPLANTATION | Northern | 4240P | Swap | Swap->On Hold->Swap | 2025 Q3 | AI | CCSMY | 4.6 TSSR Approved |  | 2024-02-16 | 2024-03-12 |  | 2025-02-18 |  | Closed | 2025-04-11 | 2025-05-02 | CD//Zulakmar | 2025-04-30 | SQ202501030318 - CCSMY | DU00002859989 |  |  | 2025-08-10 | 2025-08-09 |  | Monopole | TOWER | 45m | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
4108R | Pos Lemoi | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q1 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002859990
4109R | Kg Telimau | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q1 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002859991
4607C | Kg Raja New Township | Northern |  | Remote MOCN | Modernization->On Hold->Modernization->Remote MOCN | 2025 Q3 | SM | CCSMY | 4.4 Pending TSSR Review - Design Team |  | 2025-01-22 | 2025-02-05 |  | 2025-02-14 |  | Under Approval |  |  |  |  | SQ202501030037 - CCSMY | DU00002859992 | [5 empty] | In-Building System | 3m Bipod (RT) | 7m | Reuse Existing RRU | 0 | 0
3053C7 | pBTS Masjid Keputeraan Lojing (M) | Northern |  | Modernization | On Hold->Modernization->On Hold->Modernization | 2025 Q3 | HW | CCSMY | 4.6 TSSR Approved |  | 2025-01-22 | 2025-01-31 |  | 2025-02-12 |  | Under Approval | 2025-03-26 | 2025-09-26 | E//Hazida | 2025-05-13 | SQ202504220316 | DU00002859993 |  |  | 2025-04-18 | 2025-04-12 |  | Watertank | 25m pBTS | 25m | Add R8894E M1821x3, Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3 | 0 | 0
N00380 | N073D_N00380OD_INTIKOLEJ | Southern |  | Decomm |  | 2025 Q3 |  | GCI | 14.1 TSSR Not Required (Decomm by CD) |  | 2025-07-08 |  | 2025-07-16 |  |  | To be Submitted |  |  | CD//Sapian |  |  | DU00002859994 | [6 empty] | TOWER
C00033 | C048A_C00033OD_BRIJCOURT | Northern |  | Decomm |  | 2024 Q3(single site MOCN) | BY | GTSB | 4.6 TSSR Approved |  | 2024-07-10 |  | 2024-07-07 |  | 2024-07-10 |  | 2024-07-12 | 2024-10-01 | CD//Zulakmar | 2024-07-12 | 0919CD-Northern-GTSB-BOQ Template (old contract)/0919MW-Northern-GTSB-BOQ Template (old contract) | DU00002859995 |  |  |  |  | 2024-08-16 |  | MINI STRUCTURE
C00032 | C048A_C00032OD_LDGTEHBHARAT | Northern |  | Decomm |  | 2025 Q3 | HW | CCSMY | 4.6 TSSR Approved |  | 2025-02-06 |  | 2025-02-07 |  | 2025-02-18 |  | 2025-02-27 | 2026-01-23 | CD//Hazwan | 2025-02-28 | SQ202501060201 - CCSMY | DU00002859996 |  |  |  |  | 2025-11-28 |  | TOWER
C00577 | C048A_C00577OD_CB_BLUEVALLEY | Northern |  | Decomm |  | 2024 Q3(single site MOCN) | SM | GTSB | 4.6 TSSR Approved |  | 2024-07-22 |  | 2024-07-07 |  | 2024-07-23 |  | 2024-08-01 | 2024-10-01 | CD//Zulakmar | 2024-08-02 | 0725Northern-GTSB-BOQ Template(new contract)/0725Northen-GTSB-BOQ Template(new contract) | DU00002859997 |  |  |  |  | 2024-08-19 |  | TOWER
C00029 | C048A_C00029OD_KGRAJA | Northern |  | Decomm |  | 2024 Q4 | SM | GCI | 4.6 TSSR Approved |  | 2024-10-10 |  | 2024-10-17 |  | 2024-10-21 |  | 2024-11-11 | 2025-05-27 | CD//Zulakmar | 2024-11-15 | 0927CD-Northern-GCI-BOQ Template(new contract)/0927MW-Northern-GCI-BOQ Template(new contract) | DU00002859998 |  |  |  |  | 2024-11-08 |  | 60m 3 Legged Tower
C01085 | C048A_C01085OD_CB_TMN_TRIANGKAP2 | Northern | 4625K | Swap | Decomm->On Hold->Swap | 2024 Q4 | SHA | GTSB | 4.6 TSSR Approved | ¦ 1003 - CD Zul: PRopose change anchor from 4572A to C01085. Not agree to decom. | 2024-02-06 | 2024-11-25 |  | 2024-11-28 | 2024-02-08 | Under Approval | 2024-12-02 | 2024-12-06 | CD//Zulakmar | 2024-12-05 | Celcom Digi_RAN-GTSB-TSS-Northern-20240207-0091 | DU00002859999 |  |  | 2025-02-04 | 2025-01-27 |  | Tower | TOWER | 50m | Add R8852E S9000x3+R8894E M1821 x3, Dismantle | 0 | 0
C00359 | C048A_C00359OD_GNGBRINCHANG | Northern |  | Decomm |  | 2024 Q3(single site MOCN) | BY | GTSB | 4.6 TSSR Approved | ¦ 0703 - GTSB: Resurvey today, Pending photos | 2024-06-18 |  | 2024-08-12 |  | 2024-07-23 |  | 2024-07-24 | 2025-10-01 | CD//Zulakmar | 2024-07-24 | 0919CD-Northern-GTSB-BOQ Template (old contract) | DU00002860000 |  |  |  |  | 2024-08-16 |  | TOWER
C00023 | C048A_C00023OD_EQUATORIALHOTEL_CH | Northern |  | Decomm | Decomm->On hold->Decomm | 2024 Q4 | SM | GCI | 4.6 TSSR Approved |  | 2024-10-09 |  | 2024-10-23 |  | 2024-10-28 |  | 2024-11-14 | 2025-05-27 | CD//Zulakmar | 2024-11-18 | 0927CD-Northern-GCI-BOQ Template(new contract)/0927MW-Northern-GCI-BOQ Template(new contract) | DU00002860001 |  | Missing TX Info |  |  | 2024-11-07 |  | BOOM
C00030 | C048A_C00030OD_BRINCHANGTOWN | Northern |  | Decomm |  | 2024 Q3(single site MOCN) | SM | GCI | 4.6 TSSR Approved |  | 2024-07-12 |  | 2024-07-24 |  | 2024-07-26 |  | 2024-07-30 | 2025-10-01 | CD//Zulakmar | 2024-07-30 | 0725Northern-GCI-BOQ Template(new contract)/0725MW-Northern-GCI-BOQ Template(new contract) | DU00002860002 |  |  |  |  | 2024-08-16 |  | BOOM
C00582 | C048A_C00582OD_PUNCAKARABELA | Northern |  | Decomm |  | 2024 Q3(single site MOCN) | BY | GCI | 4.6 TSSR Approved |  | 2024-07-08 |  | 2024-07-20 |  | 2024-07-24 |  | 2024-07-25 |  | CD//Zulakmar | 2024-07-25 | 0918MW-Northern-GCI-BOQ Template (old contract) | DU00002860003 |  |  |  |  | 2024-08-14 |  | AESTHETIC MONOPOLE
C00027 | C048A_C00027OD_CB_ULURINGLET | Northern |  | Decomm |  | 2024 Q4 | SHA | CCSMY | 4.6 TSSR Approved |  | 2024-02-05 |  |  |  | 2024-02-07 |  | 2024-09-27 | 2024-10-01 | CD//Zulakmar | 2024-09-30 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240207-0092 | DU00002860004 |  |  |  |  | 2024-11-12 |  | MINI STRUCTURE
C01069 | C048A_C01069OD_GOLDEN_HILLS_CH | Northern |  | Decomm |  | 2024 Q4 | SM | GCI | 4.6 TSSR Approved |  | 2024-10-15 |  | 2024-10-18 |  | 2024-10-24 |  | 2024-11-12 | 2025-07-29 | CD//Zulakmar | 2024-11-15 | 0927CD-Northern-GCI-BOQ Template(new contract)/0927MW-Northern-GCI-BOQ Template(new contract) | DU00002860005 |  | Missing TX Info |  |  | 2024-10-29 |  | TOWER
C01026 | C048A_C01026OD_TMNRINGLET_CH | Northern |  | Decomm |  | 2024 Q4 |  | CCSMY | 4.6 TSSR Approved |  | 2024-10-23 |  | 2024-09-27 |  | 2024-10-28 |  | 2024-11-26 | 2025-07-29 | CD//Zulakmar | 2024-11-27 | 0927CD-Northern-CCSMY-BOQ Template(new contract)/0927MW-Northern-CCSMY-BOQ Template(new contract) | DU00002860006 |  |  |  |  | 2024-09-26 |  | TOWER
4446B | Strawberry Park Cameron | Northern |  | Modernization | Modernization->On Hold->Modernization | 2024 Additional | SM | GTSB | 4.6 TSSR Approved |  | 2024-12-19 | 2024-12-24 |  | 2024-12-30 |  | Rectificating | 2024-12-31 | 2025-01-14 | E//Hazida | 2025-01-14 | 1911CD-Northern-TSS-BOQ Template(new contract)_GTSB_V2 | DU00002860007 |  |  | 2025-01-13 | 2025-01-13 |  |  | 6m RT (Boom) | 3M | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8860E-GU908x2+R8882-GUL1812x1+R8840-U216x3 | 0 | 0
4127H | Flower Farm | Northern |  | MOCN As-Is |  | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860008 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
C00536 | C048A_C00536OD_TMTANAHRATA | Northern | 4511K | Swap | Swap->On Hold->Swap | 2025 Q3 | AI | CCSMY | 4.6 TSSR Approved |  | 2025-03-07 | 2025-03-12 |  | 2025-03-19 |  | Closed | 2025-03-20 | 2025-05-02 | CD//Zulakmar | 2025-04-30 | SQ202501030037 - CCSMY | DU00002860009 |  |  | 2025-06-24 | 2025-06-03 |  | In-Building System | BOOM | 7m | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
C01196 | C048A_C01196OD_CB_CARNATION_PARK_CH | Northern | 4513K | Swap | Swap->On Hold->Swap | 131 single site mocn | SM | GCI | 4.6 TSSR Approved | ¦ 0913 - CD Zul: Propose change azimuth: 20/90/160 Emailed planner | 2024-09-09 | 2024-09-10 |  | 2024-09-11 |  | Rectificating | 2024-09-11 | 2024-09-26 | CD//Zulakmar | 2024-09-26 | 0809CD-Northern-GCI-BOQ Template(new contract) | DU00002860010 |  |  | 2024-10-11 | 2024-10-03 |  | Tower | 45m 3 Legged Tower | 45 | Add R8852E S9000 x3+R8894E M1821 x5+R8862A S2601 x1+R8854 S2600 x2,Dismantle | 0 | 23
4441B | Habu (Celcom) | Northern |  | Site Out (Modernization) | Modernization->On Hold->Modernization->Site Out->Replacement, Site Out (Modernization) | 2025 Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2025-02-05 | 2025-02-14 |  | 2025-02-21 |  | Rectificating | 2025-03-12 | 2025-03-17 | E//Hazida | 2025-03-13 | SQ202501030037 - CCSMY | DU00002860011 | Remarks: Solution TSSR/BOM Changed |  |  |  |  | Tower | 45m 4 Legged Tower | 45m | Add R8852E S9000x3+R8894E M1821x4+R8862A S2601x2+R8854 S2600x1, Dismantle R8860E-GU908x3+R8882-GUL1812x2+R8862A S1800(B6A)x1+R8840-U216x3 | 0 | 3
4104R | LEMPURHULU_RCC | Northern |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 | HW | GCI | 4.6 TSSR Approved |  | 2025-07-12 |  | 2025-07-23 |  | 2025-09-19 |  | 2025-09-29 | 2026-01-22 | E//Hazida | 2025-10-03 | SQ202504230429-GCI | DU00002860012 |  |  |  |  | 2025-10-15
4718B | Rantau Panjang Selama RDD | Northern |  | Modernization | Modernization->On Hold->Modernization | 2025 Q1 | AI | YPTT | 4.6 TSSR Approved |  | 2024-01-15 | 2024-01-11 |  | 2025-01-20 |  | Under Approval | 2025-01-21 | 2025-10-14 | E//Hazida | 2025-10-10 | Celcom Digi_RAN-YPTT-TSS-Northern-20240116-0054 | DU00002860013 | Remarks: Solution TSSR/BOM Changed |  | 2025-03-15 | 2025-02-05 |  | Tower | 60m 4 Legged Tower | 50+10=60 | Add R8894E M1821x1 | 0 | 3
9095R | KGSELEPONG | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 | AI | Trintel | 4.6 TSSR Approved |  | 2025-06-25 |  | 2025-06-30 |  | 2025-07-09 |  | 2025-09-25 | 2025-10-03 |  | 2025-09-25 | SQ202506060240-Trintel | DU00002860014 |  |  |  |  | 2025-10-26 |  | #N/A
9062R | Bentong Junction | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2025 Q3 | AI | Trintel | 4.6 TSSR Approved |  | 2025-06-25 |  | 2025-06-30 |  | 2025-07-09 |  | 2025-09-22 | 2025-10-31 | E//John | 2025-09-22 | SQ202506060240-Trintel | DU00002860015 |  |  |  |  | 2025-10-17 |  | #N/A
9150R | SGRUSA | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 | HW | Trintel | 4.6 TSSR Approved |  | 2025-06-23 |  | 2025-06-24 |  | 2025-07-01 |  | 2025-09-10 | 2025-09-25 | E//John | 2025-09-11 | SQ202506060240-Trintel | DU00002860016 |  |  |  |  | 2025-11-14 |  | #N/A
9043R | TANJUNG MANIS | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2025 Q1 | HW | Trintel | 4.6 TSSR Approved |  | 2025-06-23 |  | 2025-06-30 |  | 2025-07-09 |  | 2025-08-08 | 2025-09-25 | E//John | 2025-09-09 | SQ202506060240-Trintel | DU00002860017 |  |  |  |  | 2025-09-19 |  | #N/A
9151R | KGSESSANG | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2025 Q3 | HW | Trintel | 4.6 TSSR Approved |  | 2025-06-18 |  | 2025-06-20 |  | 2025-06-23 |  | 2025-09-10 | 2025-09-25 | E//John | 2025-09-11 | SQ202506060240-Trintel | DU00002860018 |  |  |  |  | 2025-09-25 |  | #N/A
9044R | BUKIT SABAN | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2025 Q3 | HW | Trintel | 4.6 TSSR Approved |  | 2025-06-23 |  | 2025-06-26 |  | 2025-06-30 |  | 2025-08-08 | 2025-09-25 | E//John | 2025-08-11 | SQ202506060240-Trintel | DU00002860019 |  |  |  |  | 2025-09-26 |  | #N/A
9140R | KGALIT | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 | HW | Trintel | 4.6 TSSR Approved |  | 2025-06-18 |  | 2025-06-18 |  | 2025-06-23 |  | 2025-09-09 | 2025-09-25 | E//John | 2025-09-10 | SQ202506060240-Trintel | DU00002860020 |  |  |  |  | 2025-09-25 |  | #N/A
9154R | KGAPING | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 | AD | Trintel | 4.6 TSSR Approved |  | 2025-06-23 |  | 2025-06-26 |  | 2025-06-30 |  | 2025-09-26 | 2025-10-31 | E//John | 2025-09-26 | SQ202506060240-Trintel | DU00002860021 |  |  |  |  | 2025-10-26 |  | #N/A
9054R | BULAT | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2025 Q2 | HW | Trintel | 4.6 TSSR Approved |  | 2025-06-23 |  | 2025-06-24 |  | 2025-06-30 |  | 2025-08-12 | 2025-09-25 | E//John | 2025-08-25 | SQ202506060240-Trintel | DU00002860022 |  |  |  |  | 2025-09-23 |  | #N/A
9143R | KGBTLINTANG | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 | HW | Trintel | 4.6 TSSR Approved |  | 2025-06-25 |  | 2025-07-03 |  | 2025-07-11 |  | 2025-09-09 | 2025-09-25 | E//John | 2025-09-10 | SQ202506060240-Trintel | DU00002860023 |  |  |  |  | 2025-09-24 |  | #N/A
9155R | SGPAOH | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2025 Q2 | AD | Trintel | 4.6 TSSR Approved |  | 2025-06-23 |  | 2025-06-30 |  | 2025-07-09 |  | 2025-09-26 | 2025-10-31 | E//John | 2025-10-29 | SQ202506060240-Trintel | DU00002860024 |  |  |  |  | 2025-10-28 |  | #N/A
9101R | SIMPANG JAONG | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 | HW | Trintel | 4.6 TSSR Approved |  | 2025-06-23 |  | 2025-07-09 |  | 2025-08-13 |  | 2025-09-12 | 2025-09-25 | E//John | 2025-09-12 | SQ202506060240-Trintel | DU00002860025 |  |  |  |  | 2025-09-24 |  | #N/A
9119R | PANGGIL | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 | HW | Trintel | 4.6 TSSR Approved |  | 2025-06-23 |  | 2025-06-26 |  | 2025-06-30 |  | 2025-10-01 | 2025-12-08 | E//John | 2025-10-01 | SQ202506060240-Trintel | DU00002860026 |  |  |  |  | 2025-10-24 |  | #N/A
9126R | NANGALIPUS | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2025 Q3 | HW | Trintel | 4.6 TSSR Approved |  | 2025-06-27 |  | 2025-07-03 |  | 2025-07-11 |  | 2025-08-27 | 2025-09-25 | E//John | 2025-08-29 | SQ202506060240-Trintel | DU00002860027 |  |  |  |  | 2025-09-25 |  | #N/A
9108R | KAMPUNG PERPAT | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2025 Q3 | AI | Trintel | 4.6 TSSR Approved |  | 2025-06-27 |  | 2025-06-30 |  | 2025-07-07 |  | 2025-09-25 | 2025-10-31 | E//John | 2025-09-25 | SQ202506060240-Trintel | DU00002860028 |  |  |  |  | 2025-10-28 |  | #N/A
9109R | SUNGAI SEBELAK | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 | AI | Trintel | 4.6 TSSR Approved |  | 2025-06-18 |  | 2025-06-24 |  | 2025-07-03 |  | 2025-08-07 | 2025-09-23 | E//John | 2025-08-08 | SQ202506060240-Trintel | DU00002860029 |  |  |  |  | 2025-09-25 |  | #N/A
9110R | SUNGAI BURUI | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 | AI | Trintel | 4.6 TSSR Approved |  | 2025-06-23 |  | 2025-06-24 |  | 2025-07-04 |  | 2025-08-07 | 2025-09-23 | E//John | 2025-08-08 | SQ202506060240-Trintel | DU00002860030 |  |  |  |  | 2025-09-26 |  | #N/A
9111R | KAMPUNG JERIJEH | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 | AI | Trintel | 4.6 TSSR Approved |  | 2025-06-25 |  | 2025-06-30 |  | 2025-07-11 |  | 2025-09-26 | 2025-10-31 | E//Zamri | 2025-09-26 | SQ202506060240-Trintel | DU00002860031 |  |  |  |  | 2025-10-28 |  | #N/A
9134R | KAMPUNG BUKIT KINYAU | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2025 Q1 | AD | Trintel | 4.6 TSSR Approved |  | 2025-12-03 |  | 2025-12-05 |  | 2025-12-05 |  | 2025-12-17 | 2026-01-13 | E//Zamri | 2025-12-18 | SQ202506060240-Trintel | DU00002860032 |  |  |  |  | 2025-12-04 |  | #N/A
9130R | SUNGAI MADOR | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 | HW | Trintel | 4.6 TSSR Approved |  | 2025-06-23 |  | 2025-06-24 |  | 2025-07-14 |  | 2025-08-27 | 2025-09-25 | E//John | 2025-09-02 | SQ202506060240-Trintel | DU00002860033 |  |  |  |  | 2025-09-26 |  | #N/A
9113R | SUNGAI STRASS | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 | AI | Trintel | 4.6 TSSR Approved |  | 2025-06-23 |  | 2025-06-24 |  | 2025-07-09 |  | 2025-09-26 | 2025-09-29 | E//John | 2025-09-26 | SQ202506060240-Trintel | DU00002860034 |  |  |  |  | 2025-10-28 |  | #N/A
9156R | BB1_Q136A_Q01710OD_CB_SKBRAYANG | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 | AD | Trintel | 4.6 TSSR Approved |  | 2025-06-23 |  | 2025-06-24 |  | 2025-07-11 |  | 2025-09-26 | 2025-10-31 | E//John | 2025-09-26 | SQ202506060240-Trintel | DU00002860035 |  |  |  |  | 2025-10-17 |  | #N/A
9055R | KELAMPIR | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 | HW | Trintel | 4.6 TSSR Approved |  | 2025-06-18 |  | 2025-06-20 |  | 2025-06-24 |  | 2025-08-12 | 2025-09-25 | E//John | 2025-08-13 | SQ202506060240-Trintel | DU00002860036 |  |  |  |  | 2025-09-25 |  | #N/A
7055R | SIMPANG SUKAU KINABATANGAN SANDAKAN | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2025-07-18 |  | 2025-07-29 |  | 2025-07-22 |  | 2025-08-06 | 2025-10-31 | E//Hannah | 2025-09-17 | SQ202506100849 - GTSB / SQ202507010442 - GTSB | DU00002860037 |  |  |  |  | 2025-09-26 |  | #N/A
7053R | Sukau Town | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2025-07-19 |  | 2025-07-22 |  | 2025-07-23 |  | 2025-08-04 | 2025-10-31 |  | 2026-04-17 | SQ202506100849 - GTSB / SQ202507010442 - GTSB | DU00002860038 |  |  |  |  | 2025-09-26 |  | #N/A
7086R | KGSINARJAYA | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2025-07-18 |  | 2025-07-21 |  | 2025-07-22 |  | 2025-08-08 | 2025-10-31 | E//Hannah | 2025-09-16 | SQ202506100849 - GTSB / SQ202507010442 - GTSB | DU00002860039 |  |  |  |  | 2025-11-30 |  | #N/A
7089R | BB1_S091A_S01600OD_KGBERJAYA1 | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 | HW | GTSB | 4.6 TSSR Approved |  | 2025-07-19 |  | 2025-07-22 |  | 2025-07-22 |  | 2025-10-06 | 2026-01-20 | E//Faiz | 2025-10-30 | SQ202506100849 - GTSB / SQ202507010442 - GTSB | DU00002860040 |  |  |  |  | 2025-11-30 |  | #N/A
9214A | Sungai Selidap | Sarawak |  | Decomm, MOCN By Other Vendor | Decomm->On Hold->Decomm->On Hold->Decomm | 2025 | SH | Trintel | 4.6 TSSR Approved |  | 2023-12-19 |  |  |  | 2024-01-05 |  | 2024-01-26 | 2025-10-29 | E//Hannah | 2025-10-23 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231218 | DU00002860041 |  |  |  |  | 2025-12-04 |  | Tower
9641B | Roban Town | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q3 | NA | Trintel | 4.6 TSSR Approved |  | 2025-05-07 |  | 2025-05-16 |  | 2025-05-19 | To be Submitted | 2025-05-21 |  | E//John | 2025-05-27 | SQ202505150459-Trintel | DU00002860042 |  |  |  |  | 2025-10-29 |  | Tower
9229A | Melugu | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2024-01-05 |  |  |  | 2024-01-16 |  | 2024-01-26 | 2025-05-02 |  | 2025-04-21 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240109 | DU00002860043 |  |  |  |  | 2025-08-21 |  | 45m 3 Legged Tower
9230A | Bayai | Sarawak |  | Decomm, MOCN By Other Vendor | Decomm->On Hold->Decomm->On Hold->Decomm | 2025 | SH | Trintel | 4.6 TSSR Approved |  | 2024-01-16 |  |  |  | 2024-01-25 |  | 2024-01-26 | 2025-10-31 | E//Hannah | 2025-10-23 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240116 | DU00002860044 |  |  |  |  | 2025-11-19 |  | 45m 3 Legged Tower
9207A | Repuk Road | Sarawak |  | Decomm | Decomm->On Hold->Decomm->On Hold->Decomm | 2025 | SH | Trintel | 4.6 TSSR Approved |  | 2023-12-26 |  |  |  | 2023-12-29 |  | 2024-01-26 | 2025-10-29 | E//Hannah | 2025-10-23 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231231 | DU00002860045 |  |  |  |  | 2025-10-24 |  | Tower
9215A | Jln Meradong Pasi | Sarawak |  | Decomm, MOCN By Other Vendor | Decomm->On Hold->Decomm->On Hold->Decomm | 2025 | SH | Trintel | 4.6 TSSR Approved |  | 2023-12-14 |  |  |  | 2024-01-15 |  | 2024-01-26 | 2025-10-31 | E//Hannah | 2025-10-23 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231214 | DU00002860046 |  |  |  |  | 2025-11-19 |  | Tower
9226A | Lubok Antu Town | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2024-01-18 |  |  |  | 2024-01-25 |  | 2024-02-16 | 2025-10-29 | E//Hannah | 2025-10-23 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20240124 | DU00002860047 |  |  |  |  | 2025-10-23 |  | Tower
9271A | Lachau Kara Road | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2024-01-05 |  |  |  | 2024-01-16 |  | 2024-02-16 |  | E//Hannah | 2025-02-24 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240109 | DU00002860048 |  |  |  |  | 2025-10-26 |  | 4 Legged Tower
9562B | Kampung Triso | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q3 | NA | Trintel | 4.6 TSSR Approved |  | 2025-05-05 |  | 2025-05-08 |  | 2025-05-13 |  | 2025-05-21 | 2025-12-15 | E//John | 2025-05-27 | SQ202505150459-Trintel | DU00002860049 |  |  |  |  | 2025-10-21 |  | Tower
9535B | Sungai Besai Asal | Sarawak |  | Decomm | Decomm->On Hold->Decomm->On Hold->Decomm | 2025 | HW | Trintel | 4.6 TSSR Approved |  | 2024-01-05 |  |  |  | 2024-01-17 |  | 2025-02-28 | 2025-10-31 | E//Hannah | 2025-10-23 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240109 | DU00002860050 |  |  |  |  | 2025-11-12 |  | Tower
9511B | Kampung Bakong | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2024-01-22 |  |  |  | 2024-02-06 |  | 2024-02-07 | 2025-10-29 | E//Hannah | 2025-10-15 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20240124 | DU00002860051 |  |  |  |  | 2025-10-29 |  | Tower
9586B | San Kemantan_San Deman | Sarawak |  | Decomm, MOCN By Other Vendor | Decomm->On Hold->Decomm->On Hold->Decomm | 2025 | HW | Trintel | 4.6 TSSR Approved |  | 2024-01-18 |  |  |  | 2024-01-18 |  | 2025-02-28 | 2025-10-31 | E//John | 2025-10-23 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20240124 | DU00002860052 |  |  |  |  | 2025-11-19 |  | Tower
9589B | Nanga Budu | Sarawak |  | Decomm, MOCN By Other Vendor | Decomm->On Hold->Decomm->On Hold->Decomm | 2025 | AD | Trintel | 4.6 TSSR Approved |  | 2025-05-05 |  | 2025-05-08 |  | 2025-05-13 |  | 2025-05-16 | 2025-10-17 | E//John | 2025-05-27 | SQ202505150459-Trintel | DU00002860053 |  |  |  |  | 2025-12-04 |  | Tower
9590B | Wong Besi | Sarawak |  | Decomm, MOCN By Other Vendor | Decomm->On Hold->Decomm->On Hold->Decomm | 2025 | NA | Trintel | 4.6 TSSR Approved |  | 2025-05-05 |  | 2025-05-16 |  | 2025-05-19 |  | 2025-05-21 | 2025-10-17 | E//John | 2025-05-27 | SQ202505150459-Trintel | DU00002860054 |  |  |  |  | 2025-11-22 |  | Tower
9765B | Lata Iskandar _ Kg Tua Ulu Kerian | Sarawak |  | Decomm, MOCN By Other Vendor | Decomm->On Hold->Decomm->On Hold->Decomm | 2025 | HW | Trintel | 4.6 TSSR Approved |  | 2024-01-18 |  |  |  | 2024-01-31 |  | 2025-02-28 | 2025-10-31 | E//John | 2025-10-23 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20240124 | DU00002860055 |  | Please provide clear label and drawing. |  |  | 2025-12-04 |  | In-Building System
A00009 | Kg. Seri Kampar _ Kg Redang Ponggor | Northern |  | Decomm | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 | AI | GTSB | 15.3 Decomm Done without TSSR | [6 empty] | To be Submitted |  |  |  |  | SQ202504230446-GTSB | DU00002860056 |  |  |  |  | 2025-08-05 |  | TOWER
A00519 | Pos Keding _ Pos Tibang | Northern |  | Decomm | Decomm->On Hold->Decomm | 2025 Q3 | HW | CCSMY | 4.6 TSSR Approved |  | 2023-11-22 |  |  |  | 2023-12-06 |  | 2025-02-27 | 2025-07-29 | CD//Zulakmar | 2025-03-10 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231127-0073 | DU00002860057 |  |  |  |  | 2025-08-28 |  | TOWER
A00786 | UiTMBlueW_Tank | Northern |  | Decomm | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 |  | GTSB | 15.3 Decomm Done without TSSR | [6 empty] | To be Submitted |  |  |  |  | SQ202504230446-GTSB | DU00002860058 |  |  |  |  | 2025-08-05 |  | TOWER
K00462 | Kg. Ayer Merah _ Kg. Ayer Kepal | Northern |  | Decomm | Decomm->On Hold->Decomm | 2024 Q3 | HW | GTSB | 4.6 TSSR Approved |  | 2024-01-21 |  |  |  | 2024-01-22 |  | 2025-02-18 | 2025-07-29 | CD//Hazwan | 2025-02-28 | Celcom Digi_RAN-GTSB-TSS-Northern-20240124-0088/Celcom Digi_RAN-GTSB-TSS-Northern-20241030_New Contract | DU00002860059 |  | CD Hazwan reviewed but Hold wait for upg tssr ready first |  |  | 2025-08-25 |  | TOWER
Q00117 | PAIS | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 | AD | Trintel | 4.6 TSSR Approved |  | 2025-06-30 |  | 2025-07-09 |  | 2025-07-15 |  | 2025-09-26 | 2025-10-31 | E//John | 2025-09-26 | SQ202506060240-Trintel | DU00002860060 |  |  |  |  | 2025-10-22 |  | TOWER
Q00120 | SPG BATANG AI | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q3 | AI | Trintel | 4.6 TSSR Approved |  | 2025-06-25 |  | 2025-06-30 |  | 2025-07-07 |  | 2025-07-08 | 2026-04-28 | E//John | 2025-07-10 | SQ202505150459-Trintel | DU00002860061 |  |  |  |  | 2025-08-23 |  | TOWER
Q00183 | Jln 52_4 PJ | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | ZB | Trintel | 4.6 TSSR Approved |  | 2023-12-28 |  |  |  | 2024-01-02 |  | 2024-01-25 | 2025-05-02 | CD//John | 2024-01-26 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231231 | DU00002860062 |  |  |  |  | 2025-08-11 |  | TOWER
Q00272 | ULU KRIAN | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q3 | AD | Trintel | 4.6 TSSR Approved |  | 2025-05-05 |  | 2025-05-08 |  | 2025-05-13 | To be Submitted | 2025-05-16 |  | E//John | 2025-05-27 | SQ202505150459-Trintel | DU00002860063 |  |  |  |  | 2025-10-15 |  | TOWER
Q00396 | Jalan 3_93 Cheras | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | ZB | Trintel | 4.6 TSSR Approved |  | 2023-12-14 |  |  |  | 2023-12-19 |  | 2024-02-16 |  | CD//John | 2024-02-19 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231214 | DU00002860064 |  |  |  |  | 2025-10-24 |  | TOWER
Q00516 | MALUDAM | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q3 | HW | Trintel | 4.6 TSSR Approved |  | 2025-05-13 |  | 2025-05-14 |  | 2025-05-16 |  | 2025-05-16 | 2026-01-12 | CD//John | 2025-05-27 | SQ202505150459-Trintel | DU00002860065 |  |  |  |  | 2025-07-23 |  | TOWER
Q00871 | Kg. Seri Kampar _ Kg Redang Ponggor | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q3 | NA | Trintel | 4.6 TSSR Approved |  | 2024-01-18 |  |  |  | 2024-01-31 | To be Submitted | 2025-05-02 |  | CD//John | 2025-05-27 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20240124 | DU00002860066 |  |  |  |  | 2025-08-23 |  | TOWER
Q01648 | Kg. Tebing Rebak_ Kg. Sg. Dulang Dalam | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | ZB | Trintel | 4.6 TSSR Approved |  | 2024-01-02 |  |  |  | 2024-01-02 |  | 2024-01-26 | 2025-10-29 | CD//John | 2025-10-28 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240109 | DU00002860067 |  |  |  |  | 2025-10-24 |  | TOWER
Q01713 | STIDC 4 | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 | HW | Trintel | 4.6 TSSR Approved |  | 2025-06-23 |  | 2025-06-30 |  | 2025-07-08 |  | 2025-09-26 | 2026-01-19 | E//John | 2025-09-26 | SQ202506060240-Trintel | DU00002860068 |  |  |  |  | 2025-10-24 |  | MONOPOLE
Q01717 | STIDC 3 | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 | HW | Trintel | 4.6 TSSR Approved |  | 2025-06-25 |  | 2025-07-14 |  | 2025-07-21 |  | 2025-09-26 | 2026-01-20 | E//John | 2025-09-26 | SQ202506060240-Trintel | DU00002860069 |  | No FE Drawing |  |  | 2025-10-24 |  | MONOPOLE
S00311 | Jalan Mile 14 _ Jalil Alip | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | AD | YPTT | 4.6 TSSR Approved | 8/8 - NE settled, pending FE site TM wait permit. // 6/8 - Team plan wk33 | 2025-08-13 |  | 2025-08-11 |  |  | To be Submitted | 2025-08-21 |  | E//Hannah | 2025-09-26 | SQ202504140301 - YPTT | DU00002860070 |  |  |  |  | 2025-10-29 |  | TOWER
S00426 | Jln SS 2_4a | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 |  | GCI | 15.3 Decomm Done without TSSR | 12/8 BOC Cannot open, stuck/loose // 8/8 - Bush too high, team will escalate email today. // 6/8 - Team plan wk33 | 2026-01-19 |  |  |  |  | To be Submitted |  |  | CD//Mohidi Jaan |  | SQ202602040163 - GCI | DU00002860071 |  |  |  |  | 2025-11-30 |  | TOWER
S01566 | Jln Sg Long 7_5 | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4 | MNO | GTSB | 4.6 TSSR Approved |  | 2025-07-09 |  | 2025-07-10 |  | 2025-07-14 | To be Submitted | 2025-07-17 |  | E//Saiful | 2025-10-06 | SQ202508120138 - GTSB | DU00002860072 |  |  |  |  | 2025-10-31 |  | TOWER
S01572 | Jln Utama 2_26 | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4 | MNO | GTSB | 4.6 TSSR Approved |  | 2025-07-07 |  | 2025-07-09 |  | 2025-07-10 | To be Submitted | 2025-07-14 |  | E//Haliza | 2025-11-10 | SQ202508120138 - GTSB | DU00002860073 |  |  |  |  | 2025-10-31 |  | TOWER
S01584 | Jln 6_14 | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4 | MNO | GTSB | 4.6 TSSR Approved |  | 2025-07-07 |  | 2025-07-09 |  | 2025-07-10 | To be Submitted | 2025-07-14 |  | CD//Mohidi Jaan | 2025-09-23 | SQ202508120138 - GTSB | DU00002860074 |  |  |  |  | 2025-08-27 |  | TOWER
B00977 | B061R_B00977OD_TMSGWAY | Central |  | Decomm |  | 2024 Q1 | CR | GCI | 4.6 TSSR Approved |  | 2024-04-25 |  |  |  | 2024-05-06 |  | 2024-05-08 | 2024-10-29 | CD//Ali Akaram | 2024-05-17 | CelcomDigi_RAN_GCI_TSS_Central_20240513 | DU00002860075 |  |  |  |  | 2024-05-14 |  | MINI STRUCTURE
B00543 | B061R_B00543OD_SS5KLJ | Central |  | Decomm |  | 2024 Q1 | BY | DATASCO | 4.6 TSSR Approved |  | 2024-06-05 |  | 2024-06-20 |  | 2024-07-19 |  | 2024-07-22 |  | CD//Norhaliza | 2024-09-09 | 0607Central-DATASCO-BOQ Template | DU00002860076 |  |  |  |  | 2024-08-19 |  | TRIPOD
B00385 | B061P_B00385OD_SGWAY | Central |  | Decomm |  | 2024 Q1 | MS | Magicell | 4.6 TSSR Approved |  | 2024-02-29 |  |  |  | 2024-03-06 |  | 2024-03-14 | 2024-09-25 | CD//Ali Akaram | 2024-07-17 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240303 | DU00002860077 |  |  |  |  | 2024-05-15 |  | BOOM
B02682 | B061R_B02682OD_STELLAR_TS_DIGI | Central |  | Decomm |  | 2024 Q1 | MS | Magicell | 4.6 TSSR Approved |  | 2024-01-27 |  |  |  | 2024-02-14 |  | 2024-02-15 | 2024-03-22 | CD//Sapian | 2024-02-26 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240202 | DU00002860078 |  |  |  |  | 2024-04-30 |  | BOOM
B00406 | B061R_B00406OD_KGTUNKUPJ | Central |  | Decomm |  | 2024 Q1 | SS | Magicell | 4.6 TSSR Approved |  | 2024-02-29 |  |  |  | 2024-05-02 |  | 2024-03-05 | 2024-07-12 | CD//Norhaliza | 2024-06-10 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240303 | DU00002860079 |  |  |  |  | 2024-05-16 |  | MINI MONOPOLE
B02177 | B061G_B02177OD_DAMANSARAIDAMAN | Central |  | Decomm |  | 2024 Q1 | SS | Magicell | 4.6 TSSR Approved |  | 2024-03-18 |  |  |  | 2024-03-20 |  | 2024-03-22 | 2024-07-10 | CD//Ali Akaram | 2024-04-01 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240323 | DU00002860080 |  |  |  |  | 2024-05-21 |  | TRIPOD
B00797 | B061G_B00797OD_PR_PTRSBGDEPOH | Central |  | Decomm |  | 2024 Q1 | SH | GTSB | 4.6 TSSR Approved |  | 2024-05-20 |  |  |  | 2024-05-21 |  | 2024-05-23 | 2024-09-25 | CD//Norhaliza | 2024-09-09 | CelcomDigi_RAN_GTSB_TSS_Central_20240423 | DU00002860081 |  |  |  |  | 2024-08-22 |  | BOOM
B02311 | B061P_B02311OD_KELANACENTREPOINT | Central |  | Decomm |  | 2024 Q1 | SHA | GTSB | 4.6 TSSR Approved |  | 2024-07-23 |  | 2024-08-01 |  | 2024-08-06 |  | 2024-08-07 | 2025-01-14 | CD//Sapian | 2024-08-13 | 0725Central-GTSB-BOQ Template(new contract) | DU00002860082 |  |  |  |  | 2024-09-24 |  | TRIPOD
B01842 | B061R_B01842OD_SS6PJ | Central |  | Decomm |  | 2024 Q1 | SM | DATASCO | 4.6 TSSR Approved |  | 2024-01-24 |  |  |  | 2024-07-05 |  | 2024-02-23 | 2024-09-25 | CD//Sapian | 2024-04-21 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240202 | DU00002860083 |  |  |  |  | 2024-04-25 |  | UNIPOLE
B01962 | B061R_B01962OD_SS1PJ | Central |  | Decomm |  | 2024 Q1 | SM | Magicell | 4.6 TSSR Approved |  | 2023-11-23 |  |  |  | 2023-12-17 |  | 2024-01-17 |  | CD//Sapian | 2024-01-24 | CelcomDigi_RAN_Magicell_TSS_Central_20231126 | DU00002860084 |  | Missing FE part |  |  | 2024-05-08 |  | UNIPOLE
B00618 | B061R_B00618OD_SS3PJ2 | Central |  | Decomm |  | 2024 Q1 | SS | Magicell | 4.6 TSSR Approved |  | 2023-12-05 |  |  |  | 2023-12-07 |  | 2023-12-08 | 2024-02-23 | CD//Ali Akaram | 2024-02-20 | CelcomDigi_RAN_Magicell_TSS_Central_20231208 | DU00002860085 |  |  |  |  | 2024-04-29 |  | BOOM
Q00382 | Q136A_Q00382OD_PKNSARATOK | Sarawak |  | Decomm |  | 2025 Q3 | ZB | Trintel | 4.6 TSSR Approved |  | 2024-02-19 |  |  |  | 2024-02-21 |  | 2024-02-22 | 2024-08-01 | CD//John | 2024-02-23 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240220 | DU00002860086 |  |  |  |  | 2025-08-14 |  | TOWER
B00176 | B061B_B00176OD_PR_TOLSUBANG | Central |  | Decomm |  | 2024 Q1 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-17 |  |  |  | 2024-01-30 |  | 2024-02-02 | 2024-04-24 | CD//Sapian | 2024-02-23 | CelcomDigi_RAN_GTSB_TSS_Central_20240124 | DU00002860087 |  |  |  |  | 2024-05-14 |  | LAMP_POLE
B00581 | B061G_B00581OD_ARADAMANSARA | Central | 1831K | Swap | Decomm->On hold->Swap | 2024 Q1 | AI | GTSB | 4.6 TSSR Approved |  | 2024-02-27 | 2024-05-03 |  | 2024-05-27 | 2024-03-04 | Closed | 2024-05-27 | 2024-06-20 | CD//Ali akaram | 2024-06-14 | 0619Central-GTSB-BOQ Template (template) | DU00002860088 |  |  | 2024-08-01 | 2024-07-30 |  | Wall mount boom | BOOM | 10m | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle | 0 | 0
K00122 | K006A_K00122OD_KAMPUNGRAWA | Northern |  | Decomm |  | 2024 Q3 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-12-07 |  |  |  | 2023-12-20 |  | 2023-12-21 | 2024-01-22 | CD//Rohizam | 2023-12-21 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231208-0079 | DU00002860089 |  |  |  |  | 2024-06-10 |  | TOWER
K00404 | K006A_K00404OD_KOLEJGUTHRIE | Northern |  | Decomm |  | 2024 Q3 | BY | GCI | 4.6 TSSR Approved |  | 2024-02-24 |  |  |  | 2024-03-07 |  | 2024-03-20 | 2024-04-16 | CD//Rohizam | 2024-04-02 | Celcom Digi_RAN-GCI-TSS-Northern-20240310-0100/0612Northern-GCI-BOQ Template (template) | DU00002860090 |  |  |  |  | 2024-05-25 |  | TOWER
K00176 | K006A_K00176OD_BUKITKACHI | Northern |  | Decomm |  | 2024 Q3 | SM | GCI | 4.6 TSSR Approved |  | 2023-12-11 |  |  |  | 2023-12-26 |  | 2023-12-28 | 2024-01-22 | CD//Rohizam | 2024-01-02 | Celcom Digi_RAN-GCI-TSS-Northern-20231212-0082/0612Northern-GCI-BOQ Template (template) | DU00002860091 |  |  |  |  | 2024-05-27 |  | TOWER
Q00122 | Q117A_Q00122OD_CB_TMSPAOH | Sarawak |  | Decomm |  | 2025 Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2024-01-22 |  |  |  | 2024-02-13 |  | 2024-02-14 | 2024-03-05 | CD//John | 2024-03-01 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20240124 | DU00002860092 |  |  |  |  | 2025-10-10 |  | TOWER
4049R | Kg Budi | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860093 | [6 empty] | 60M Tower
B02175 | B061G_B02175OD_DATARANARADSARA | Central |  | Decomm |  | 2024 Q1 | BY | GTSB | 4.6 TSSR Approved |  | 2024-02-27 |  |  |  | 2024-03-04 |  | 2024-03-13 | 2024-04-24 | CD//Sapian | 2024-03-26 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240303 | DU00002860094 |  |  |  |  | 2024-05-13 |  | UNIPOLE
4053R | Kg Belida | Northern |  | Modernization | Maintain USP MOCN->On Hold->Maintain USP MOCN->Modernization | 2025 Q2 | AI | CCSMY | 4.6 TSSR Approved |  | 2025-04-30 | 2025-05-14 |  | 2025-05-16 |  | Under Approval | 2025-05-19 | 2025-05-27 | E//Hazida | 2025-05-23 | SQ202501030318 - CCSMY | DU00002860095 |  |  | 2025-06-30 | 2025-06-18 |  | Tower | 75M 4 Legged Tower | 76m | Add R8894E M1821x1 | 0 | 1
4057R | Kg Bukit Pak Kuning | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860096 | [6 empty] | 75M 4 Legged Tower
B00642 | B061P_B00642OD_PR_TMNMAYANG | Central |  | Decomm |  | 2024 Q1 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-05-09 |  |  |  | 2024-05-09 |  | 2024-05-10 |  | CD//Norhaliza | 2024-08-23 | CelcomDigi_RAN_Datasco_TSS_Central_20240513 | DU00002860097 |  | Missing FE part |  |  | 2024-05-17 |  | BOOM
K00049 | K006B_K00049OD_BUKITNAPOH | Northern |  | Decomm |  | 2024 Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-10-12 |  |  |  | 2023-10-18 |  | 2023-10-23 | 2024-05-10 | CD//Rohizam | 2023-11-21 | Celcom Digi_RAN-GCI-TSS-Northern-20231015-0059/0612Northern-GCI-BOQ Template (template) | DU00002860098 |  | missing NE antenna Photo, Fe antenna photo |  |  | 2024-06-11 |  | TOWER
K00461 | K006B_K00461OD_KKBDA | Northern |  | Decomm |  | 2024 Q3 | SM | GCI | 4.6 TSSR Approved |  | 2023-10-12 |  |  |  | 2023-10-20 |  | 2023-10-24 | 2024-03-26 | CD//Rohizam | 2023-10-25 | Celcom Digi_RAN-GCI-TSS-Northern-20231015-0059/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240529-0109 | DU00002860099 |  | Missing TX info and Photo |  |  | 2024-05-23 |  | BOOM
9333B | Rh James | Sarawak |  | Remote MOCN | Modernization->On Hold->Maintain USP MOCN->Modernization->Remote MOCN | 2025 Q2 |  |  | 14.0 TSSR Not Required (Reuse Existing BBU/RRU) | [6 empty] | To be Submitted | [5 empty] | DU00002860100 | [6 empty] | 45m 3 Legged Tower |  | Reuse Existing RRU | 0 | 0
A00266 | A040D_A00266OD_BATAMAS_RDD | Northern |  | Decomm |  | 2024 Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2023-12-02 |  |  |  | 2023-12-06 |  | 2023-12-12 | 2024-04-23 | CD//Rohizam | 2024-01-30 | Celcom Digi_RAN-GTSB-TSS-Northern-20231204-0071 | DU00002860101 |  |  |  |  | 2024-04-17 |  | TOWER
9352A | Hilltop Kapit | Sarawak |  | Modernization | Modernization->On Hold->Modernization | 2025 Q3 | AI | Trintel | 4.6 TSSR Approved |  | 2025-03-17 | 2025-04-04 |  | 2025-04-10 |  | Closed | 2025-04-21 | 2025-05-21 | E//Hannah | 2025-05-18 | SQ202503030411-Trintel | DU00002860102 |  |  | 2025-07-06 | 2025-05-28 |  | Tower | 60m 4 Legged Tower | 90m | Add R8894E M1821x2, Dismantal R8854E S1800(A6A)x3 | 0 | 13
9543A | Sg Niah | Sarawak |  | Modernization | Modernization->On Hold->Modernization | 2025 Q2 | AI | Magicell | 4.6 TSSR Approved |  | 2025-02-05 | 2025-02-27 |  | 2025-03-07 |  | Closed | 2025-04-07 | 2025-05-27 | E//Hannah | 2025-04-21 | SQ202501070146-Magicell | DU00002860103 |  |  | 2025-09-18 | 2025-09-10 |  | Tower | Tower | 76 | Add R8894E M1821x1, Dismantle R8854E S1800(A6A)x3 | 0 | 1
9403B | SPAD Mukah Satu | Sarawak |  | Remote MOCN | Modernization->On Hold->Modernization->Remote MOCN | 2025 Q2 | AI | Trintel | 4.6 TSSR Approved |  | 2025-02-05 | 2025-02-05 |  | 2025-02-26 |  | Closed | 2025-03-11 | 2025-07-17 | E//Hannah | 2025-03-20 | SQ202501070293-Trintel | DU00002860104 | [5 empty] | Tower | 45m 3 Legged Tower | 76 | Reuse Existing RRU | 0 | 0
A00067 | A041A_A00067OD_SALAK_RDD | Northern |  | Decomm |  | 2024 Q4 | SHA | YPTT | 4.6 TSSR Approved |  | 2024-01-16 |  |  |  | 2024-01-23 |  | 2024-09-27 |  | CD//Zulakmar | 2024-10-01 | Celcom Digi_RAN-YPTT-TSS-Northern-20240124-0056 | DU00002860105 |  |  |  |  | 2024-10-25 |  | TOWER
A00162 | A041A_A00162OD_CB_LUBUKMERBAUKK_RDD | Northern |  | Decomm |  | 2024 Q4 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-11-23 |  |  |  | 2023-12-08 |  | 2023-12-12 | 2024-02-15 | CD//Rohizam | 2024-01-30 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231127-0073 | DU00002860106 |  |  |  |  | 2024-09-24 |  | TOWER
9407B | Sungai Kut | Sarawak |  | Remote MOCN | Modernization->On Hold->Modernization->Remote MOCN | 2025 Q2 | AD | Trintel | 14.0 TSSR Not Required (Reuse Existing BBU/RRU) |  | 2025-03-11 | 2025-03-27 |  | 2025-04-14 |  | Under Approval | 2025-04-16 | 2025-10-03 | E//John | 2025-09-29 | SQ202501070293-Trintel | DU00002860107 | [5 empty] | Tower | Tower | 76 | Reuse Existing RRU | 0 | 0
9469A | Lundu Ferry | Sarawak |  | Modernization | Modernization->On Hold->Modernization | 2024 Q2 | AD | Magicell | 4.6 TSSR Approved |  | 2025-03-06 | 2025-03-25 |  | 2025-04-04 |  | Under Approval | 2025-04-16 | 2025-05-27 | E//John | 2025-05-26 | SQ202503170571-Magicell | DU00002860108 | Remarks: Solution TSSR/BOM Changed |  | 2025-07-06 | 2025-06-28 |  | Tower | 45m 3 Legged Tower | 75 | Add R8894E M1821x2, Dismantal R8854E S1800(A6A)x3 | 0 | 23
A00272 | A041A_A00272OD_KATI_RCD | Northern |  | Decomm |  | 2024 Q4 | SHA | YPTT | 4.6 TSSR Approved |  | 2024-02-14 |  |  |  | 2024-02-14 |  | 2024-09-27 | 2024-10-07 | CD//Zulakmar | 2024-10-03 | Celcom Digi_RAN-YPTT-TSS-Northern-20240215-0060_reraise 21/6 | DU00002860109 |  | messy photo arrangement, Wrong IDU NE&FE |  |  | 2024-12-06 |  | TOWER
A00462 | A041A_A00462OD_CB_KGPERIANG | Northern |  | Decomm |  | 2024 Q4 | SM | GTSB | 4.6 TSSR Approved |  | 2023-12-28 |  |  |  | 2023-12-28 |  | 2024-01-02 | 2024-01-22 | CD//Rohizam | 2024-01-02 | Celcom Digi_RAN-GTSB-TSS-Northern-20231229-0081 | DU00002860110 |  |  |  |  | 2024-09-25 |  | TOWER
A00516 | A041A_A00516OD_CB_PERLOP | Northern |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2025 Q3 | HW | GCI | 4.6 TSSR Approved |  | 2025-07-12 |  | 2025-07-22 |  | 2025-09-11 |  | 2025-09-29 | 2026-01-22 | E//Hazida | 2025-10-03 | SQ202504230429-GCI | DU00002860111 |  |  |  |  | 2025-10-14 |  | TOWER
A00282 | A041A_A00282OD_TMSGSIPUTOLD | Northern |  | Decomm |  | 2024 Q4 | HW | CCSMY | 4.6 TSSR Approved | 20/8- PTW approved, 18/8 - Team will share WNL by today// 14/8 - long aging SA to check // 8/8 - team retract, Rollout to reassign // 6/8 - TM site, access pending, raise up to SA to prioritize | 2025-09-10 |  | 2025-09-09 |  | 2025-09-10 | To be Submitted | 2025-09-26 |  | CD//Zulakmar | 2025-09-25 | SQ202509290447 - CCSMY | DU00002860112 |  |  |  |  | 2025-11-16 |  | TOWER
A00496 | A041A_A00496OD_CB_BT3LINTANG_RCD | Northern |  | Decomm |  | 2024 Q4 | SM | GTSB | 4.6 TSSR Approved |  | 2023-12-21 |  |  |  | 2023-12-28 |  | 2024-01-02 | 2025-07-29 | CD//Rohizam | 2024-01-02 | Celcom Digi_RAN-GTSB-TSS-Northern-20231225-0080 | DU00002860113 |  | have 6x IDU |  |  | 2024-09-30 |  | TOWER
A00464 | A041A_A00464OD_CB_BKTKRUDA_RCC | Northern |  | Decomm |  | 2024 Q4 | SHA | GTSB | 15.4 Decomm Done without TSSR Approval |  | 2024-12-16 |  | 2024-10-16 |  | 2024-12-16 | To be Submitted | 2024-12-19 |  | CD//Zulakmar |  | 0927CD-Northern-GTSB-BOQ Template(new contract)/0927MW-Northern-GTSB-BOQ Template(new contract) | DU00002860114 |  |  |  |  | 2025-01-27 |  | TOWER
A00714 | A042C_A00714OD_POKOKASSAM | Northern |  | Decomm |  | 2024 Q2 | SM | YPTT | 4.6 TSSR Approved | ¦ 0425 - CD Rohizam: TSSR RAN_A00714 A042C_A00714OD_POKOKASSAM_Decomm_V1, Reviewed and approved. ¦ 0425 - Replied to Rohizam with RF justification ¦ 0412 - Fup done, pending Li Jie revert ¦ 15-3 - ZTE planner to study and revert ¦ 0206 - fup done to Izzat/Khai ¦ 0131 - Fwd email to planning regarding CD RF Rohizam: TSSR RAN_A00714 A042C_A00714OD_POKOKASSAM_Decomm_V1, reviewed and pending to approved due to pair site 4451B is about 377m away with site A00714. we concerns coverage will degraded at red circle below. Please share the coverage plot for 3 scenario: Scenario1: Digi site 4451B as Anchor, Celcom site A00714 decom Scenario2: Celcom site A00714 as Anchor, Digi site 4451B decom Scenario3: site A00714 and site 4451B both maintain | 2024-01-26 |  |  |  | 2024-01-29 |  | 2024-01-30 | 2024-05-06 | CD//Rohizam | 2024-04-25 | Celcom Digi_RAN-YPTT-TSS-Northern-20240124-0057 | DU00002860115 |  |  |  |  | 2024-06-20 |  | BOOM
A01096 | A042B_A01096OD_HOTEL_PERDANA_TAIPING | Northern |  | Decomm |  | 2024 Q2 | SM | GCI | 4.6 TSSR Approved |  | 2023-12-24 |  |  |  | 2024-01-08 |  | 2024-01-19 | 2024-02-15 | CD//Rohizam | 2024-01-30 | Celcom Digi_RAN-GCI-TSS-Northern-20231225-0085/Celcom Digi_RAN-GCI-TSS-Northern-20240130-0092 | DU00002860116 |  |  |  |  | 2024-06-01 |  | UNIPOLE
A00535 | A041A_A00535OD_CB_TALANGTENGAH_RCD | Northern |  | Decomm |  | 2024 Q4 | SM | GTSB | 4.6 TSSR Approved |  | 2023-12-28 |  |  |  | 2023-12-29 |  | 2024-01-02 | 2024-01-22 | CD//Rohizam | 2024-01-03 | Celcom Digi_RAN-GTSB-TSS-Northern-20231229-0081 | DU00002860117 |  |  |  |  | 2024-10-03 |  | TOWER
A00291 | A040C_A00291OD_BPOLISBUNTONG | Northern |  | Decomm |  | 2024 Q2 | ZA | YPTT | 4.6 TSSR Approved |  | 2024-01-22 |  |  |  | 2024-01-24 |  | 2024-01-30 | 2024-02-23 | CD//Rohizam | 2024-01-30 | Celcom Digi_RAN-YPTT-TSS-Northern-20240124-0056 | DU00002860118 |  |  |  |  | 2024-06-28 |  | BOOM
A01056 | A040D_A01056OD_CB_KGSERDANGPERMAI | Northern |  | Decomm |  | 2024 Q2 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-11-24 |  |  |  | 2023-12-06 |  | 2023-12-13 | 2024-02-15 | CD//Rohizam | 2024-01-30 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231127-0073 | DU00002860119 |  |  |  |  | 2024-05-31 |  | TOWER
A00024 | A040D_A00024OD_CB_KELLIESCASTLE_RDD | Northern |  | Decomm |  | 2024 Q2 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-11-23 |  |  |  | 2023-11-29 |  | 2023-12-01 | 2023-12-18 | CD//Rohizam | 2023-12-01 | Celcom Digi_RAN-GTSB-TSS-Northern-20231127-0068 | DU00002860120 |  |  |  |  | 2024-04-16 |  | TOWER
R00079 | R001A_R00079OD_CB_JLNCHUPING | Northern |  | Decomm |  | 2024 Q4 | BY | GTSB | 4.6 TSSR Approved |  | 2023-12-12 |  |  |  | 2023-12-19 |  | 2023-12-21 | 2024-01-22 | CD//Rohizam | 2023-12-21 | Celcom Digi_RAN-GTSB-TSS-Northern-20231213-0076 | DU00002860121 |  |  |  |  | 2024-10-20 |  | TOWER
R00097 | R001B_R00097OD_TMN_SRIPILIHAN_KGR | Northern |  | Decomm |  | 2024 Q4 | ZA | GCI | 4.6 TSSR Approved |  | 2024-03-22 |  |  |  | 2024-03-28 |  | 2024-04-18 | 2024-04-23 | CD//Rohizam | 2024-04-19 | Celcom Digi_RAN-GCI-TSS-Northern-20240329-0104 | DU00002860122 |  |  |  |  | 2024-06-11 |  | LAMP_POLE
9572B | Ulu Kapit | Sarawak |  | Modernization | Modernization->On Hold->Modernization | 2025 Q3 | HW | Trintel | 4.6 TSSR Approved |  | 2025-03-17 | 2025-04-04 |  | 2025-04-12 |  | Under Approval | 2025-04-14 | 2025-04-24 | E//Hannah | 2025-04-21 | SQ202503030411-Trintel | DU00002860123 |  |  | 2025-07-06 | 2025-05-28 |  | Tower | 60m 4 Legged Tower | 60m | Add R8894E M1821x2, Dismantal R8854E S1800(A6A)x3 | 0 | 23
K00387 | K006B_K00387OD_DARULAMANIND | Northern |  | Decomm |  | 2024 Q3 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-12-07 |  |  |  | 2023-12-20 |  | 2023-12-21 | 2024-01-22 | CD//Rohizam | 2023-12-21 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231208-0079 | DU00002860124 |  |  |  |  | 2024-05-21 |  | TOWER
K00125 | K006A_K00125OD_JKRSINTOK | Northern |  | Decomm |  | 2024 Q3 | SM | GCI | 4.6 TSSR Approved |  | 2023-10-12 |  |  |  | 2023-10-20 |  | 2023-10-25 |  | CD//Rohizam | 2023-10-26 | Celcom Digi_RAN-GCI-TSS-Northern-20231015-0059 | DU00002860125 |  | Missing TX info and Photo |  |  | 2024-05-10 |  | TOWER
K00212 | K006A_K00212OD_BKHITAMBORDER | Northern |  | Decomm |  | 2024 Q3 | BY | GTSB | 4.6 TSSR Approved |  | 2024-03-03 |  |  |  | 2024-03-05 |  | 2024-03-20 | 2024-04-23 | CD//Rohizam | 2024-03-21 | Celcom Digi_RAN-GTSB-TSS-Northern-20240303-0095 | DU00002860126 |  |  |  |  | 2024-06-26 |  | TOWER
K00178 | K006A_K00178OD_KOLEJALBUKHARY | Northern |  | Decomm |  | 2024 Q3 | BY | GTSB | 4.6 TSSR Approved |  | 2024-02-25 |  |  |  | 2024-02-27 |  | 2024-03-21 | 2024-03-26 | CD//Rohizam | 2024-03-22 | Celcom Digi_RAN-GTSB-TSS-Northern-20240226-0094 | DU00002860127 |  |  |  |  | 2024-05-29 |  | BOOM
K00266 | K006A_K00266OD_WANGPERAH | Northern |  | Decomm | MOCN Decomm(Dismantle Passive)->On Hold->Decomm | 2024 Q3 | HW | CCSMY | 4.6 TSSR Approved |  | 2024-12-14 |  | 2025-02-03 |  | 2025-02-12 |  | 2025-02-20 | 2025-07-25 | CD//Hazwan | 2025-02-26 | Celcom Digi_RAN-CCSMY-TSS-Northern-20241112_New Contract | DU00002860128 |  |  |  |  | 2025-02-28 |  | TOWER
K00175 | K006A_K00175OD_BKAYUHITAM | Northern |  | Decomm |  | 2024 Q3 | SM | GCI | 4.6 TSSR Approved |  | 2023-10-12 |  |  |  | 2023-10-20 |  | 2023-10-26 | 2024-05-24 | CD//Rohizam | 2023-10-27 | Celcom Digi_RAN-GCI-TSS-Northern-20231015-0059/0612Northern-GCI-BOQ Template (template) | DU00002860129 |  | Missing TX info and Photo |  |  | 2024-06-26 |  | TOWER
K00602 | K006A_K00602OD_CHANGLOONTOWN | Northern |  | Decomm |  | 2024 Q3 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-12-06 |  |  |  | 2023-12-20 |  | 2023-12-21 | 2024-01-22 | CD//Rohizam | 2023-12-22 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231207-0078 | DU00002860130 |  |  |  |  | 2024-06-07 |  | UNIPOLE
K00104 | K006A_K00104OD_SANGLANG | Northern |  | Decomm |  | 2024 Q3 |  | CCSMY | 4.6 TSSR Approved |  | 2024-02-28 |  |  |  | 2024-03-11 |  | 2024-03-22 | 2024-03-26 | CD//Rohizam | 2024-03-22 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240229-0097 | DU00002860131 |  |  |  |  | 2024-07-12 |  | TOWER
K00386 | K006B_K00386OD_SUNGAIKOROK | Northern |  | Decomm |  | 2024 Q3 | BY | GTSB | 4.6 TSSR Approved |  | 2023-12-07 |  |  |  | 2023-12-19 |  | 2023-12-27 | 2024-01-22 | CD//Rohizam | 2024-01-02 | Celcom Digi_RAN-GTSB-TSS-Northern-20231207-0073 | DU00002860132 |  |  |  |  | 2024-05-31 |  | TOWER
K00391 | K006A_K00391OD_LAKATEMINSLTN | Northern |  | Decomm |  | 2024 Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-12-15 |  |  |  | 2023-12-15 |  | 2023-12-19 | 2024-01-22 | CD//Rohizam | 2023-12-19 | Celcom Digi_RAN-GTSB-TSS-Northern-20231214-0077 | DU00002860133 |  |  |  |  | 2024-05-29 |  | TOWER
A00255 | A042D_A00255OD_BGNPANCHOR | Northern |  | Decomm |  | 2024 Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2023-12-22 |  |  |  | 2024-01-12 |  | 2024-01-19 | 2024-02-15 | CD//Rohizam | 2024-01-22 | Celcom Digi_RAN-GTSB-TSS-Northern-202401114-0085 | DU00002860134 |  |  |  |  | 2024-07-24 |  | TOWER
K00181 | K006B_K00181OD_CB_TUALANGPALAS | Northern |  | Decomm |  | 2024 Q3 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-12-05 |  |  |  | 2023-12-19 |  | 2023-12-28 | 2024-06-07 | CD//Rohizam | 2024-01-02 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231206-0077 | DU00002860135 |  |  |  |  | 2024-06-11 |  | TOWER
K00033 | K006B_K00033OD_TUNKUSARINA | Northern |  | Decomm |  | 2024 Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-12-06 |  |  |  | 2023-12-20 |  | 2023-12-27 | 2024-01-22 | CD//Rohizam | 2024-01-02 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231207-0078/0612Northern-CCSMY-BOQ Template (template) | DU00002860136 |  | 1) Please include 1xIDU 2) Please include Digi NE Cabinet & IDU to decom 3) Please mention in drawing location Celcom Cabinet and Digi Cabinet |  |  | 2024-05-21 |  | TOWER
K00540 | K006A_K00540OD_TMNSERICHANGLOON | Northern |  | Decomm |  | 2024 Q3 | BY | GCI | 4.6 TSSR Approved |  | 2023-12-28 |  |  |  | 2024-01-10 |  | 2024-02-27 | 2024-02-29 | CD//Rohizam | 2024-02-27 | Celcom Digi_RAN-GCI-TSS-Northern-20240108-0088 | DU00002860137 |  |  |  |  | 2024-06-05 |  | TOWER
K00275 | K006B_K00275OD_KGNAGA | Northern |  | Decomm |  | 2024 Q3 | SM | GCI | 4.6 TSSR Approved |  | 2024-05-03 |  |  |  | 2024-05-06 |  | 2024-05-07 | 2024-05-10 | CD//Rohizam | 2024-05-07 | Celcom Digi_RAN-GCI-TSS-Northern-20240512-0106 | DU00002860138 |  |  |  |  | 2024-05-21 |  | TOWER
R00139 | R001A_R00139OD_CB_KOKKLANG | Northern |  | Decomm |  | 2024 Q4 | SHA | GTSB | 4.6 TSSR Approved |  | 2023-12-28 |  |  |  | 2024-01-02 |  | 2024-12-15 | 2025-09-18 | CD//Zulakmar | 2024-12-30 | Celcom Digi_RAN-GTSB-TSS-Northern-20231229-0081 | DU00002860139 |  |  |  |  | 2024-11-13 |  | TOWER
A01074 | A041A_A01074OD_SG_SIPUT_IND | Northern |  | Decomm |  | 2024 Q4 | SHA | GCI | 4.6 TSSR Approved |  | 2023-12-19 |  |  |  | 2024-01-11 |  | 2024-09-27 | 2024-10-07 | CD//Zulakmar | 2024-10-03 | Celcom Digi_RAN-GCI-TSS-Northern-20231225-0085/Celcom Digi_RAN-GCI-TSS-Northern-20240130-0092 | DU00002860140 |  |  |  |  | 2024-10-10 |  | TOWER
S00524 | S091A_S00524OD_SUANLAMBAESTATE | Sabah |  | Decomm |  | 2024 Q4 | MS | NR services | 4.6 TSSR Approved |  | 2024-07-22 |  | 2024-08-16 |  | 2024-08-19 |  | 2024-08-20 | 2024-11-29 | CD//Mohidi Jaan | 2024-08-26 | 0725Sabah-NR-BOQ Template(new contract)/0725MW-Sabah-NR-BOQ Template(new contract) | DU00002860141 |  |  |  |  | 2025-02-12 | Tower | TOWER | 76
K00214 | K006B_K00214OD_BDRWAWASAN | Northern |  | Decomm |  | 2024 Q3 | SM | GCI | 4.6 TSSR Approved |  | 2023-12-11 |  |  |  | 2023-12-29 |  | 2024-01-02 | 2024-01-22 | CD//Rohizam | 2024-01-02 | Celcom Digi_RAN-GCI-TSS-Northern-20231212-0082/0612Northern-GCI-BOQ Template (template) | DU00002860142 |  |  |  |  | 2024-06-06 |  | TOWER
K00208 | K006A_K00208OD_CB_FELDABKTTANGGA | Northern |  | Decomm |  | 2024 Q3 |  | GTSB | 4.6 TSSR Approved |  | 2024-02-25 |  |  |  | 2024-02-29 |  | 2024-03-22 | 2024-03-26 | CD//Rohizam | 2024-03-22 | Celcom Digi_RAN-GTSB-TSS-Northern-20240226-0094 | DU00002860143 |  |  |  |  | 2024-05-29 |  | TOWER
K00261 | K006A_K00261OD_FELDABT8 | Northern |  | Decomm |  | 2024 Q3 |  | GTSB | 4.6 TSSR Approved |  | 2024-03-03 |  |  |  | 2024-03-05 |  | 2024-03-22 | 2024-03-26 | CD//Rohizam | 2024-03-22 | Celcom Digi_RAN-GTSB-TSS-Northern-20240303-0095 | DU00002860144 |  |  |  |  | 2024-06-26 |  | TOWER
K00117 | K006B_K00117OD_KGJERLUN | Northern |  | Decomm |  | 2024 Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-12-07 |  |  |  | 2023-12-30 |  | 2024-01-03 | 2024-01-22 | CD//Rohizam | 2024-01-03 | Celcom Digi_RAN-GTSB-TSS-Northern-20231207-0073 | DU00002860145 |  |  |  |  | 2024-06-10 |  | TOWER
K00447 | K006B_K00447OD_LEMBAHABU | Northern |  | Decomm |  | 2024 Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-12-18 |  |  |  | 2023-12-18 |  | 2023-12-19 | 2024-01-22 | CD//Rohizam | 2023-12-20 | Celcom Digi_RAN-GTSB-TSS-Northern-20231219-0078 | DU00002860146 |  |  |  |  | 2024-06-21 |  | TOWER
K00123 | K006A_K00123OD_TUNJANGTOWN | Northern |  | Decomm |  | 2024 Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-12-18 |  |  |  | 2023-12-18 |  | 2023-12-20 | 2024-01-22 | CD//Rohizam | 2023-12-20 | Celcom Digi_RAN-GTSB-TSS-Northern-20231219-0078 | DU00002860147 |  |  |  |  | 2024-06-13 |  | TOWER
9012R | KG. DURAS | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q1 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860148 | [6 empty] | 76M 3 Legged Tower |  | Dismantle R8854E S1800(A6A)x3 | 0 | 0
K00579 | K006B_K00579_BANDAR_DARUL_AMAN | Northern |  | Decomm |  | 2024 Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-12-05 |  |  |  | 2023-12-21 |  | 2023-12-27 | 2024-01-22 | CD//Rohizam | 2024-01-02 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231206-0077 | DU00002860149 |  |  |  |  | 2024-05-14 |  | TOWER
K00578 | K006A_K00578OD_KODIANG_RDC | Northern |  | Decomm |  | 2024 Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-12-08 |  |  |  | 2023-12-15 |  | 2023-12-19 | 2024-01-22 | CD//Rohizam | 2023-12-20 | Celcom Digi_RAN-GTSB-TSS-Northern-20231212-0075 | DU00002860150 |  |  |  |  | 2024-06-12 |  | LAMP_POLE
K00217 | K006A_K00217OD_KM7CHANGLUN | Northern |  | Decomm |  | 2024 Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-10-13 |  |  |  | 2023-10-23 |  | 2023-10-25 | 2024-05-10 | CD//Rohizam | 2023-10-26 | Celcom Digi_RAN-GCI-TSS-Northern-20231017-00600612/Northern-GCI-BOQ Template (template) | DU00002860151 |  | Missing TX info and photo |  |  | 2024-06-06 |  | TOWER
K00040 | K006B_K00040OD_CB_TMAIRHITAM | Northern |  | Decomm |  | 2024 Q3 | BY | CCSMY | 4.6 TSSR Approved | ¦ 0425 - CD Rohizam: TSSR RAN_K00040 K006B_K00040OD_CB_TMAIRHITAM_Decomm_V1.1, reviewed and approved. ¦ 0425 - Replied with RF justification ¦ 0402 - Li Jie fup to Izzat, pending revert¦ 15-3- ZTE planner to start study ¦ 0301 - CD ROhizam: Before proceed to decom site K00040, pls provide coverage prediction before and after NIC with 3 scenario below. Decom K00040, Anchor 4998A Decom A998A, Anchor K00040 Remain K00040 and 4998A | 2024-01-07 |  |  |  | 2024-01-16 |  | 2024-02-27 | 2024-05-06 | CD//Rohizam | 2024-04-25 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240108-0084 | DU00002860152 |  |  |  |  | 2024-12-31 |  | TOWER
9039Z | KampungMedongHilir MedongHulu | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860153 | [6 empty] | 45m 3 Legged Tower
9046Z | KampungSekai | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860154 | [6 empty] | 45m 3 Legged Tower
9047Z | Mukah-Selangauroad | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860155 | [6 empty] | 45m 3 Legged Tower |  | Dismantle R8854E S1800(A6A)x3 | 0 | 0
9044Z | RumahSandin RumahJanin RumahLili RumahTelajan | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | Under Approval | [5 empty] | DU00002860156 | [6 empty] | 45m 3 Legged Tower |  | Dismantle R8854E S1800(A6A)x3 | 0 | 0
Q00374 | Q137A_Q00374OD_CB_SEBANGKOI | Sarawak |  | Decomm |  | 2025 Q2 | ZB | Trintel | 4.6 TSSR Approved |  | 2023-12-16 |  |  |  | 2023-12-21 |  | 2024-01-26 | 2024-07-19 | CD//John | 2024-01-29 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231214 | DU00002860157 |  |  |  |  | 2025-08-25 |  | TOWER
S00079 | S101A_S00079OD_PENAMPANG | Sabah |  | Site Out (Decomm) | On Hold->On Hold->Site Out->Site Out (Decomm) | 2024 Q3 | AD | YPTT | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2025-06-17 |  | 2025-06-18 | [5 empty] | CD//Mohidi Jaan |  | SQ202506160238 - YPTT | DU00002860158 |  |  |  |  | 2025-04-30 |  | TOWER
S00213 | S105A_S00213OD_BDRNAMTUNG | Sabah |  | Decomm | Decomm-On Hold->Decomm | 2024 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2024-04-26 |  |  |  | 2024-05-02 |  | 2024-05-03 | 2024-05-24 | CD//Mohidi Jaan | 2024-05-06 | Celcom Digi_RAN-YPTT-Standard PR TSS-Sabah-20240503 | DU00002860159 |  |  |  |  | 2025-11-14 |  | BOOM
7501A | Jeroco | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-03-14 | 2025-03-19 |  | 2025-03-21 |  | Under Approval | 2025-03-26 | 2025-05-20 | E//Hannah | 2025-04-02 | SQ202503270453 - Futong | DU00002860160 |  |  | 2025-07-06 | 2025-05-13 |  | Tower | Tower | 60m | Add R8894E M1821x2, Dismantal R8854E S1800(A6A)x3 | 0 | 12
7105A | Silabukan | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2024 Q3(single site MOCN) | AD | Futong | 4.6 TSSR Approved |  | 2025-02-28 | 2025-03-04 |  | 2025-03-06 |  | Under Approval | 2025-03-26 | 2025-05-19 | E//Hannah | 2025-04-02 | SQ202504080091 - Futong | DU00002860161 | Remarks: Solution TSSR/BOM Changed |  | 2025-07-06 | 2025-05-09 |  | Tower | Tower | 60m | Add R8852E S9000x1+R8854E S1800x1+R9264M M1821x4,Dismantle R8894E M1821(A8A) x3 | 0 | 124
S00195 | S105A_S00195OD_GRANDVIEW | Sabah |  | Decomm |  | 2024 Q3 | BY | GTSB | 4.6 TSSR Approved |  | 2024-03-13 |  |  |  | 2024-03-20 |  | 2024-04-03 | 2024-07-12 | CD//Mohidi Jaan | 2024-04-03 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240313 | DU00002860162 |  |  |  |  | 2024-08-09 |  | BOOM
S00188 | S105B_S00188OD_TMNINDAH | Sabah |  | Decomm |  | 2024 Q3 | BY | GTSB | 4.6 TSSR Approved |  | 2024-03-19 |  |  |  | 2024-03-20 |  | 2024-04-03 | 2024-07-12 | CD//Mohidi Jaan | 2024-04-03 | Celcom Digi_RAN-GTSB-TSS-Sabah-20240324 | DU00002860163 |  |  |  |  | 2024-08-20 |  | MINI STRUCTURE
S00171 | S105B_S00171OD_MILE11 | Sabah |  | Decomm |  | 2025 Q2 | MS | GTSB | 4.6 TSSR Approved |  | 2024-07-09 |  | 2024-07-15 |  | 2024-08-05 |  | 2024-08-09 | 2025-10-28 | CD//Mohidi Jaan | 2024-08-09 | SQ202501020455 - GTSB | DU00002860164 |  |  |  |  | 2024-08-14 |  | GUYED MAST
7391B | TAMANMAJU | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-03-10 | 2025-03-16 |  | 2025-03-20 |  | Under Approval | 2025-03-24 | 2025-05-21 | E//Hannah | 2025-04-02 | SQ202503270453 - Futong | DU00002860165 |  |  | 2025-07-06 | 2025-05-13 |  | Tower | 45m 3 Legged Tower | 76m | Add A9732 M1821 x2,Dismantle R8894E M1821(A8A) x2 | 13 | 0
S00462 | S101A_S00462OD_RAMAYAH | Sabah |  | Decomm |  | 2024 Q3 | MS | NR services | 4.6 TSSR Approved |  | 2024-03-25 |  |  |  | 2024-03-25 |  | 2024-03-26 | 2024-06-21 | CD//Mohidi Jaan | 2024-03-26 | Celcom Digi_RAN-NR Services-TSS-Sabah-20240329 | DU00002860166 |  |  |  |  | 2024-10-28 |  | TOWER
7674A | USP Tomani | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2025 Q2 | AD | YPTT | 4.6 TSSR Approved |  | 2025-01-06 | 2025-03-07 |  | 2025-03-19 |  | Under Approval | 2025-03-24 | 2025-05-21 | E//Hannah | 2025-04-02 | SQ202501020336 - YPTT | DU00002860167 |  |  | 2025-04-23 | 2025-04-19 |  | Tower | 70m 4 Legged Tower | 60 | Add R8894E M1821x1 | 0 | 2
7334A | Segangan | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-03-07 | 2025-03-12 |  | 2025-03-14 |  | Under Approval | 2025-03-22 | 2025-05-21 | E//Hannah | 2025-05-07 | SQ202503270453 - Futong | DU00002860168 | Remarks: Solution TSSR/BOM Changed |  | 2025-04-26 | 2025-04-11 |  | Tower | Tower | 76m | Add A9732 M1821x2,Dismantle R8894E M1821(A8A)x1 | 23 | 1
7109A | Telisai | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-03-17 | 2025-03-20 |  | 2025-03-25 |  | Under Approval | 2025-03-26 | 2025-04-11 | E//Hannah | 2025-04-02 | SQ202503270453 - Futong | DU00002860169 |  |  | 2025-04-10 | 2025-04-09 |  | Tower | Tower | 60m | Add A9732 M1821 x2,Dismantle R8894E M1821(A8A) x2 | 13 | 0
S00111 | S101A_S00111OD_DONGGONGAN | Sabah |  | Decomm |  | 2024 Q3 | MS | Seri Pancar | 4.6 TSSR Approved |  | 2024-01-10 |  |  |  | 2024-01-18 |  | 2024-03-21 | 2024-04-24 | CD//Mohidi Jaan | 2024-03-21 | Celcom Digi_RAN-Seri Pancar-Standard PR TSS-Sabah-20240116 | DU00002860170 |  |  |  |  | 2024-11-27 |  | TRIPOD
7690B | KG.BUMIPUTERA | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-03-12 | 2025-03-16 |  | 2025-03-20 |  | Under Approval | 2025-03-24 | 2025-05-19 | E//Hannah | 2025-05-18 | SQ202503270453 - Futong | DU00002860171 |  |  | 2025-07-06 | 2025-05-09 |  | Tower | 45m 3 Legged Tower | 60m | Add A9732 M1821x1 | 2 | 1
S00124 | S101A_S00124OD_INOBONG | Sabah |  | Decomm |  | 2024 Q3 | MS | Seri Pancar | 4.6 TSSR Approved |  | 2024-01-10 |  |  |  | 2024-03-21 |  | 2024-03-28 | 2024-12-13 | CD//Mohidi Jaan | 2024-03-28 | Celcom Digi_RAN-Seri Pancar-Standard PR TSS-Sabah-20240116 | DU00002860172 |  |  |  |  | 2024-06-07 |  | TOWER
7490B | Sg Koyah | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860173 | [6 empty] | 60m 3 Legged Tower
S00125 | S101A_S00125OD_BABAGON | Sabah |  | Decomm |  | 2024 Q3 | MS | Seri Pancar | 4.6 TSSR Approved |  | 2024-01-10 |  |  |  | 2024-03-21 |  | 2024-03-25 | 2025-05-02 | CD//Mohidi Jaan | 2024-03-26 | Celcom Digi_RAN-Seri Pancar-Standard PR TSS-Sabah-20240116 | DU00002860174 |  |  |  |  | 2024-08-05 |  | TOWER
S00789 | S101A_S00789OD_KGKASIGUI | Sabah |  | Decomm |  | 2024 Q3 | MS | Seri Pancar | 4.6 TSSR Approved |  | 2024-01-10 |  |  |  | 2024-03-21 |  | 2024-03-26 | 2024-06-21 | CD//Mohidi Jaan | 2024-03-26 | Celcom Digi_RAN-Seri Pancar-Standard PR TSS-Sabah-20240116 | DU00002860175 |  |  |  |  | 2024-06-12 |  | TOWER
S00120 | S101A_S00120OD_NAMPASAN | Sabah |  | Decomm |  | 2024 Q3 | MS | Seri Pancar | 4.6 TSSR Approved |  | 2024-01-10 |  |  |  | 2024-03-21 |  | 2024-03-28 | 2024-06-21 | CD//Mohidi Jaan | 2024-03-28 | Celcom Digi_RAN-Seri Pancar-Standard PR TSS-Sabah-20240116 | DU00002860176 |  |  |  |  | 2024-05-24 |  | TOWER
S00838 | S108A_S00838OD_KGSANDAPAK | Sabah |  | Decomm |  | 2025 Q2 | HW | YPTT | 4.6 TSSR Approved |  | 2025-01-15 |  | 2025-01-22 | 2025-01-24 | 2025-02-17 | Under Approval | 2025-02-23 | 2025-05-02 | CD//Sharidah | 2025-02-26 | SQ202501030034 - YPTT | DU00002860177 |  |  |  |  | 2025-07-23 |  | TOWER
S00308 | S108A_S00308OD_CB_NAMBAYAN | Sabah |  | Decomm |  | 2024 Q3(single site MOCN) | MS | Seri Pancar | 4.6 TSSR Approved |  | 2024-06-18 |  |  |  | 2024-07-04 |  | 2024-07-09 | 2024-09-13 | CD//Mohidi Jaan | 2024-07-10 | Celcom Digi_RAN-Seri Pancar-Standard PR TSS-Sabah-20240621 | DU00002860178 |  |  |  |  | 2024-10-11 |  | TOWER
S00811 | S108A_S00811OD_SMKTAMBUNAN | Sabah |  | Decomm |  | 2024 | SHA | Datasco | 4.6 TSSR Approved |  | 2024-11-19 |  | 2024-12-06 |  | 2024-12-26 |  | 2024-12-31 |  | CD//Sharidah | 2025-01-02 | Celcom Digi_RAN-Datasco-Standard PR TSS-Sabah-20241030 | DU00002860179 |  | IDU LABE MISSING |  |  | 2025-02-12 |  | BOOM
S00307 | S109A_S00307OD_CB_GNGALAB | Sabah |  | Decomm |  | 2024 Q3(single site MOCN) | MS | Seri Pancar | 4.6 TSSR Approved |  | 2024-08-12 |  | 2024-08-15 |  | 2024-08-21 |  | 2024-08-22 | 2024-09-30 | CD//Mohidi Jaan | 2024-08-22 | 0809MW-Sabah-Seri Pancar-BOQ Template(new contract)/0809CD-Sabah-Seri Pancar-BOQ Template(new contract) | DU00002860180 |  |  |  |  | 2024-11-06 |  | TOWER
S00443 | S092A_S00443OD_RTMKOTABELUD | Sabah |  | Decomm |  | 2024 Q3 | MS | GTSB | 4.6 TSSR Approved |  | 2024-01-24 |  |  |  | 2024-01-29 |  | 2024-03-21 | 2024-11-15 | CD//Mohidi Jaan | 2024-03-23 | Celcom Digi_RAN-GTSB-TSS-Sabah-20240204 | DU00002860181 |  |  |  |  | 2024-07-01 |  | TOWER
S00161 | S092A_S00161OD_KGKINOTA | Sabah |  | Decomm |  | 2024 Q3 | AD | Futong | 4.6 TSSR Approved |  | 2024-01-27 |  |  |  | 2024-01-29 |  | 2024-03-21 | 2024-10-02 | CD//Mohidi Jaan | 2024-03-21 | Celcom Digi_RAN-Futong-TSS-Sabah-20240204 | DU00002860182 |  |  |  |  | 2024-06-10 |  | TOWER
S00151 | S092A_S00151OD_KASAPANG | Sabah |  | Decomm |  | 2024 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2024-01-19 |  |  |  | 2024-01-25 |  | 2024-03-22 | 2024-11-15 | CD//Mohidi Jaan | 2024-03-24 | Celcom Digi_RAN-YPTT-TSS-Sabah-20240124 | DU00002860183 |  |  |  |  | 2024-08-08 |  | TOWER
S00149 | S092A_S00149OD_RANGALAU | Sabah |  | Decomm |  | 2024 Q3 | AD | Futong | 4.6 TSSR Approved |  | 2024-02-03 |  |  |  | 2024-03-21 |  | 2024-03-21 | 2024-05-14 | CD//Mohidi Jaan | 2024-03-21 | Celcom Digi_RAN-Futong-Standard PR TSS-Sabah-20240213 | DU00002860184 |  |  |  |  | 2024-06-18 |  | TOWER
S00138 | S092A_S00138OD_ULUKUKUT | Sabah |  | Decomm |  | 2024 Q3 | AD | Futong | 4.6 TSSR Approved |  | 2024-01-11 |  |  |  | 2024-01-11 |  | 2024-03-21 | 2024-11-15 | CD//Mohidi Jaan | 2024-03-21 | Celcom Digi_RAN-Futong-Standard PR TSS-Sabah-20240116 | DU00002860185 |  |  |  |  | 2024-07-01 |  | TOWER
S00162 | S092A_S00162OD_KULAMBAI | Sabah |  | Decomm |  | 2024 Q3 | AD | Futong | 4.6 TSSR Approved |  | 2024-02-07 |  |  |  | 2024-03-21 |  | 2024-03-21 | 2025-10-28 | CD//Mohidi Jaan | 2024-03-21 | Celcom Digi_RAN-Futong-Standard PR TSS-Sabah-20240213 | DU00002860186 |  |  |  |  | 2024-06-19 |  | TOWER
S01166 | S092A_S01166OD_USPKGBANGKAHAK | Sabah |  | Decomm |  | 2024 Q3 | AD | Futong | 4.6 TSSR Approved |  | 2024-01-29 |  |  |  | 2024-01-30 |  | 2024-03-21 | 2025-10-28 | CD//Mohidi Jaan | 2024-03-23 | Celcom Digi_RAN-Futong-TSS-Sabah-20240204/0612Sabah-Futong-BOQ Template (template) | DU00002860187 |  |  |  |  | 2024-07-05 |  | TOWER
S00446 | S091A_S00446OD_TMSUKAU | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2025-07-23 |  | 2025-07-29 |  | 2025-07-29 |  | 2025-09-09 | 2025-09-20 | E//Hannah | 2025-09-16 | SQ202508130660 - Seri Pancar | DU00002860188 |  |  |  |  | 2025-09-29 |  | BOOM
S00662 | S105B_S00662OD_SUNGAIMANILA | Sabah |  | Decomm |  | 2025 Q2 | ZB | Futong | 4.6 TSSR Approved |  | 2024-03-25 |  |  |  | 2024-03-26 |  | 2024-04-04 | 2024-07-19 | CD//Mohidi Jaan | 2024-04-04 | Celcom Digi_RAN-Futong-TSS-Sabah-20240329 / SQ202501020444 - Futong | DU00002860189 |  |  |  |  | 2024-07-16 |  | BOOM
S00911 | S105B_S00911OD_CB_TGPISAU | Sabah |  | Decomm |  | 2025 Q2 | AD | Futong | 4.6 TSSR Approved |  | 2024-04-20 |  |  |  | 2024-04-23 |  | 2024-04-24 | 2024-07-24 | CD//Mohidi Jaan | 2024-04-30 | Celcom Digi_RAN-Futong-Standard PR TSS-Sabah-20240503 / SQ202501020444 - Futong / SQ202501070242 - Futong | DU00002860190 |  |  |  |  | 2024-07-29 |  | BOOM
S00473 | S089A_S00473OD_MILE32SDK | Sabah |  | Decomm |  | 2024 Q4 | MS | NR services | 4.6 TSSR Approved |  | 2024-08-09 |  | 2024-08-15 |  | 2024-08-18 |  | 2024-08-19 | 2024-09-30 | CD//Sharidah | 2024-08-20 | 0809CD-Sabah-NR Servieces-BOQ Template(new contract) | DU00002860191 |  |  |  |  | 2024-12-05 |  | TOWER
S00527 | S091A_S00527OD_BUKITGARAM | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 | HW | GTSB | 4.6 TSSR Approved |  | 2025-07-07 |  | 2025-07-10 |  | 2025-07-11 |  | 2025-09-10 | 2026-01-20 | E//Hannah | 2025-09-17 | SQ202506100849 - GTSB / SQ202507010442 - GTSB | DU00002860192 |  |  |  |  | 2025-10-31 |  | TOWER
S00655 | S105B_S00655OD_MILE9SDK | Sabah |  | Decomm |  | 2025 Q2 | SH | Futong | 4.6 TSSR Approved |  | 2024-03-26 |  |  |  | 2024-04-01 |  | 2024-04-04 | 2024-07-12 | CD//Mohidi Jaan | 2024-04-04 | Celcom Digi_RAN-Futong-Standard PR TSS-Sabah-20240406 / SQ202501020444 - Futong / SQ202501070242 - Futong | DU00002860193 |  |  |  |  | 2024-07-24 |  | TOWER
S00484 | S091A_S00484OD_BTTULUG | Sabah |  | Decomm |  | 2024 Q4 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2024-07-22 |  | 2024-07-26 |  | 2024-07-29 |  | 2024-07-30 | 2024-10-25 | CD//Mohidi Jaan | 2024-07-30 | 0725Sabah-Seri Pancar-BOQ Template(new contract)/0725MW-Sabah-Seri Pancar-BOQ Template(new contract) | DU00002860194 |  |  |  |  | 2024-11-27 |  | TOWER
S00526 | S105B_S00526OD_SEPILOK | Sabah |  | Decomm |  | 2025 Q2 | ZB | Futong | 4.6 TSSR Approved |  | 2024-03-27 |  |  |  | 2024-03-28 |  | 2024-04-04 | 2024-09-26 | CD//Mohidi Jaan | 2024-04-04 | Celcom Digi_RAN-Futong-TSS-Sabah-20240329 / SQ202501020444 - Futong | DU00002860195 |  |  |  |  | 2024-07-22 |  | TOWER
S00182 | S091A_S00182OD_SENTOSAJAYA | Sabah |  | Decomm |  | 2024 Q4 | MS | Seri Pancar | 4.6 TSSR Approved |  | 2024-07-23 |  | 2024-07-26 |  | 2024-08-01 |  | 2024-08-02 | 2024-09-13 | CD//Mohidi Jaan | 2024-08-06 | 0725Sabah-Seri Pancar-BOQ Template(new contract)/0725MW-Sabah-Seri Pancar-BOQ Template(new contract) | DU00002860196 |  |  |  |  | 2024-11-27 |  | TOWER
S01582 | S089A_S01582OD_CB_BT30SDK | Sabah |  | Decomm |  | 2025 Q2 | AD | Futong | 4.6 TSSR Approved |  | 2024-05-02 |  |  |  | 2024-05-02 |  | 2024-05-10 | 2024-06-21 | CD//Mohidi Jaan | 2024-06-05 | Celcom Digi_RAN-Futong-Standard PR TSS-Sabah-20240503 / SQ202501020444 - Futong / SQ202501070242 - Futong | DU00002860197 |  |  |  |  | 2024-07-19 |  | TOWER
S01562 | S091A_S01562OD_CB_TRUSJAYASUKAU | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 | HW | GTSB | 4.6 TSSR Approved |  | 2025-07-09 |  | 2025-07-10 |  | 2025-07-11 |  | 2025-09-10 | 2026-01-20 | E//Hannah | 2025-09-17 | SQ202506100849 - GTSB / SQ202507010442 - GTSB | DU00002860198 |  |  |  |  | 2025-10-31 |  | TOWER
7106Z | T3E_0699_Kg Botition | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860199 | [6 empty] | 76m 4 Legged Tower
7078Z | SabangMill | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860200 | [6 empty] | 76m 4 Legged Tower
7105Z | T3E_0698_IOI Bimbingan 2 Plantation | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860201 | [6 empty] | 76m 4 Legged Tower
7388A | Masjid Sipitang | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860202 | [6 empty] | 24m Lampole
Q00609 | Q117A_Q00609OD_PKNBETONG | Sarawak |  | Decomm |  | 2024 | ZB | Magicell | 4.6 TSSR Approved |  | 2024-04-20 |  |  |  | 2024-04-25 |  | 2024-05-06 | 2024-08-29 | CD//John | 2024-05-06 | Celcom Digi_RAN-Magicell-Standard PR TSS-Sarawak-20240221 | DU00002860203 |  |  |  |  | 2024-12-06 |  | TOWER
Q00586 | Q117A_Q00586OD_DESARIA | Sarawak |  | Decomm |  | 2025 Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2024-02-14 |  |  |  | 2024-02-20 |  | 2024-02-20 | 2024-07-29 | CD//John | 2024-02-21 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240220 | DU00002860204 |  |  |  |  | 2025-08-15 |  | TOWER
Q00655 | Q117A_Q00655OD_PKNSPAOH | Sarawak |  | Decomm |  | 2025 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2025-03-11 |  | 2025-05-06 |  | 2025-05-20 |  | 2025-05-22 | 2025-09-20 | E//John | 2025-05-23 | SQ202502270773-YPTT | DU00002860205 |  |  |  |  | 2025-09-26 |  | TOWER
Q00383 | Q117A_Q00383OD_CB_SPGDEBAK | Sarawak |  | Decomm |  | 2025 Q3 | ZB | Trintel | 4.6 TSSR Approved |  | 2024-02-16 |  |  |  | 2024-02-21 |  | 2024-02-22 | 2024-06-21 | CD//John | 2024-02-23 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240220 | DU00002860206 |  |  |  |  | 2025-11-11 |  | TOWER
Q00416 | Q136A_Q00416OD_TMSARATOK | Sarawak |  | Decomm |  | 2025 Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2024-02-19 |  |  |  | 2024-02-22 |  | 2024-02-22 | 2024-08-01 | CD//John | 2024-03-01 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240220 | DU00002860207 |  |  |  |  | 2025-10-13 |  | TOWER
Q00514 | Q136A_Q00514OD_PKNKABONG | Sarawak |  | Decomm |  | 2024 | SH | Trintel | 4.6 TSSR Approved |  | 2024-02-21 |  |  |  | 2024-02-22 |  | 2024-02-22 | 2024-10-25 | CD//John | 2024-03-01 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240223/Celcom Digi_RAN-Trintel-Standard PR TSS DECOMM-Sarawak-20240314 | DU00002860208 |  |  |  |  | 2024-12-27 |  | TOWER
Q00888 | Q129A_Q00888OD_JLNBAKONG | Sarawak |  | Decomm |  | 2025 Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-12-06 |  |  |  | 2023-12-07 |  | 2023-12-13 | 2024-04-24 | CD//John | 2023-12-13 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231207 | DU00002860209 |  |  |  |  | 2025-05-27 |  | TOWER
Q00404 | Q143A_Q00404OD_CB_BKTTEMUDUK | Sarawak |  | Decomm |  | 2025 Q3 | SH | Magicell | 4.6 TSSR Approved |  | 2023-11-24 |  |  |  | 2023-12-01 |  | 2023-12-01 | 2024-03-21 | CD//John | 2023-12-01 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231126 | DU00002860210 |  |  |  |  | 2025-07-14 |  | TOWER
Q00418 | Q143A_Q00418OD_SESCOSRIAMAN | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q3 | ZB | Trintel | 4.6 TSSR Approved |  | 2024-01-19 |  |  |  | 2024-02-08 |  | 2024-02-14 | 2024-02-16 | CD//John | 2024-02-15 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20240124 | DU00002860211 |  |  |  |  | 2025-08-26 |  | BOOM
Q00123 | Q143A_Q00123OD_SMKSRIAMAN | Sarawak |  | Decomm |  | 2024 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-11-30 |  |  |  | 2023-12-04 |  | 2023-12-04 | 2023-12-16 | CD//John | 2023-12-05 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231206 | DU00002860212 |  |  |  |  | 2024-12-06 |  | BOOM
Q00686 | Q143A_Q00686OD_KGHILIR | Sarawak |  | Decomm |  | 2025 Q3 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-11-28 |  |  |  | 2023-12-05 |  | 2023-12-08 | 2023-12-16 | CD//John | 2023-12-08 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231206 | DU00002860213 |  |  |  |  | 2025-04-29 |  | TOWER
Q01705 | Q129A_Q01705OD_CB_IPGBINTANGOR | Sarawak |  | Decomm |  | 2025 Q2 | ZB | Trintel | 4.6 TSSR Approved |  | 2023-12-15 |  |  |  | 2023-12-22 |  | 2024-01-26 | 2024-02-15 | CD//John | 2024-01-29 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231214 | DU00002860214 |  |  |  |  | 2025-05-27 |  | TOWER
2238A | Desa Petaling 2 | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 | 2023-10-25 |  |  |  | To be Submitted | [5 empty] | DU00002860215 | [5 empty] | Monople Tree | 20m Minaret | 3 |  | 12
1210A | SS 2 | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-10-23 | 2023-10-25 |  | 2024-04-16 |  | Closed | 2024-04-17 | 2024-04-18 | E//Kok Keen | 2024-04-18 | CelcomDigi_RAN_GTSB_TSS_Central_20231025 | DU00002860216 |  |  | 2024-05-30 | 2024-05-18 |  | Minimast | 3m Boom (RT) | 8m | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 12 | 0
Q00698 | Q117A_Q00698OD_CB_SAKA | Sarawak |  | Decomm |  | 2025 Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2024-02-16 |  |  |  | 2024-02-22 |  | 2024-02-22 | 2024-03-21 | CD//John | 2024-03-01 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240220 | DU00002860217 |  |  |  |  | 2025-08-18 |  | TOWER
Q00955 | Q117A_Q00955OD_KGSEPINANG | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2025 Q3 | HW | Trintel | 4.6 TSSR Approved |  | 2025-06-27 |  | 2025-06-30 |  | 2025-07-08 |  | 2025-09-26 | 2026-01-20 | E//John | 2025-09-26 | SQ202506060240-Trintel | DU00002860218 |  | No FE Drawing |  |  | 2025-10-17 |  | TOWER
3599C | Jalan Bukit Pantai | Central |  | Modernization |  | 2024 Q2 | AI | Ascentrack | 4.6 TSSR Approved |  | 2023-11-22 | 2023-11-27 |  | 2024-03-03 |  | Closed | 2024-03-05 | 2024-03-05 | E//Kok Keen | 2024-03-05 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231126 | DU00002860219 |  |  | 2024-05-08 | 2024-04-30 |  | Lampole | 18m Lampole | 18 | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 3 | 0
3212B | IOI Mall Outdoor | Central |  | Modernization |  | 2024 Q3 | CR | Magicell | 4.6 TSSR Approved |  | 2024-05-28 | 2024-06-05 |  | 2024-06-10 |  | Under Approval | 2024-06-14 | 2024-06-20 | E//Sumitra | 2024-06-20 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240510 | DU00002860220 |  |  | 2024-10-29 | 2024-10-22 |  | In-Building System | 3m Tripod (RT) | 3M | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle R8862A S2600(A4A) x1 | 0 | 2
7596B | Haxan Light Industrial (REL) | Sabah |  | Modernization |  | 2024 Q3(single site MOCN) | SH | Seri Pancar | 4.6 TSSR Approved |  | 2024-07-11 | 2024-07-31 |  | 2024-08-08 |  | Under Approval | 2024-08-13 | 2024-08-22 | E//Norsyahriani | 2024-08-22 | 0719Sabah-Seri Pancar-BOQ Template | DU00002860221 |  |  | 2024-10-04 | 2024-09-09 |  | Tower | 45m Tower | 45 | Add R8862A S9000 x4+A9732 M1821 x3,Dismantle R8862A S2601(A6A) x2+R8894E M1821(A8A) x5 | 134 | 0
3237D | Medan Idaman (REL) | Central |  | Modernization |  | 2024 Q1 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-12-02 | 2023-12-05 |  | 2024-01-03 |  | Closed | 2024-01-04 | 2024-01-05 | E//Kok Keen | 2024-01-04 | CelcomDigi_RAN_Datasco_TSS_Central_20231208 | DU00002860222 |  |  | 2024-04-26 | 2024-04-24 |  | Lampole | 18m Lampole | 18 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
3239D | JPJ Semenyih (REL) | Central |  | Modernization | Modernization->On Hold->Modernization | 2024 Q4 | AI | YPTT | 4.6 TSSR Approved |  | 2024-07-26 | 2024-08-10 |  | 2024-12-05 |  | Closed | 2024-12-06 | 2024-12-10 | E//Sumitra | 2024-12-10 | BOQ_Celcom Digi_RAN-YPTT-Standard PR TSS-20240407 | DU00002860223 |  |  | 2025-03-04 | 2025-02-28 |  | Tower | 60m 4 Legged Tower | 60 | Add R8894E M1821 x5+R8854 S2600x1,Dismantle R8862A S1800(B6A) x4+R8862A S2100(A6A) x4+R8862A S2601(A6A)x1 | 0 | 2
Q00838 | Q117A_Q00838OD_PKNDEBAK | Sarawak |  | Decomm |  | 2024 | ZB | Magicell | 4.6 TSSR Approved |  | 2024-04-22 |  |  |  | 2024-04-24 |  | 2024-04-26 | 2024-05-16 | CD//John | 2024-05-13 | Celcom Digi_RAN-Magicell-Standard PR TSS-Sarawak-20240503 | DU00002860224 |  |  |  |  | 2024-12-06 |  | TOWER
3817C | Jalan Tandang PJ | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002860225 | [6 empty] | 3m Boom (RT) |  |  |  | 23
3418C | MAYBANKSALAKSTH (REL) | Central |  | Modernization |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-04-06 | 2024-04-21 |  | 2024-04-25 |  | Closed | 2024-05-02 | 2024-05-27 | E//Sumitra | 2024-05-27 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240407 | DU00002860226 |  |  | 2024-06-15 | 2024-06-14 |  | Tower | 45m Tower | 45 | Add R8894E M1821 x1,Dismantle | 0 | 1
4288C | ISKANDAR PERDANA (REL) | Northern |  | Modernization |  | 2024 Q2 | BY | CCSMY | 4.6 TSSR Approved | ¦ 0228 - Listed for solution change, pending confirmed solution | 2024-01-10 | 2024-01-16 |  | 2024-01-19 |  | Closed | 2024-03-04 | 2024-03-05 | E//Hazida | 2024-03-05 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240114-0086 | DU00002860227 |  |  | 2024-04-08 | 2024-03-29 |  | Lampole | 30m Lampole | 30m | Add R8852E S9000 x4+R8894E M1821 x7+R8854 S2600 x3,Dismantle R8862A S1800(B6A) x4+R8862A S2100(A6A) x4+R8862A S2600(A4A) x3 | 0 | 124
3634C | Permai Prima | Central |  | Modernization |  | 2024 Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2023-12-26 | 2024-02-08 |  | 2024-05-14 |  | Closed | 2024-05-14 | 2024-05-21 | E//Sumitra | 2024-05-21 | CelcomDigi_RAN_AllStar_TSS_Central_20231230 | DU00002860228 |  |  | 2024-07-26 | 2024-07-26 |  | In-Building System | 3m Boom (RT) | 6 | Add R8862A S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 | 2 | 0
3844C | Kajang Utama (REL) | Central |  | Modernization |  | 2024 Q4 | SY1 | YPTT | 4.6 TSSR Approved |  | 2024-04-16 | 2024-06-12 |  | 2024-06-20 |  | Closed | 2024-06-21 | 2024-07-02 | E//Sumitra | 2024-07-02 | CelcomDigi_RAN_YPTT_TSS_Central_20240513 | DU00002860229 |  |  | 2024-08-20 | 2024-08-15 |  | Pole | 3m Boom (RT) | 6 | Add R8852E S9000 x3+R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
4815C | Jln Langgar Pokok Sena (REL) | Northern |  | Modernization |  | 2024 Q3(single site MOCN) | BY | CCSMY | 4.6 TSSR Approved |  | 2024-01-12 | 2024-01-15 |  | 2024-04-24 |  | Closed | 2024-04-26 | 2024-05-03 |  | 2024-05-02 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240114-0086 | DU00002860230 |  |  | 2024-06-24 | 2024-06-15 |  | Tower | 45m 3 Legged Tower | 50m | Add R8862A S9000 x3+A9732 M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 123 | 0
1370C | Tmn Srankai (REL) | Central |  | Modernization |  | 2024 Q3 | AI | AllStar | 4.6 TSSR Approved | ¦ 0307 : All RRUs to be installed inside cabinet. Required cooling/fan system upgrade. Owner not allowed install RRU at top. | 2023-12-01 | 2023-12-05 |  | 2023-12-13 |  | Closed | 2023-12-14 | 2024-04-24 | E//Sumitra | 2024-04-24 | CelcomDigi_RAN_Allstar_TSS_Central_20231203 | DU00002860231 |  |  | 2024-04-07 | 2024-04-02 |  |  | 18m Lampole | 18 | Add R8862A S9000 x3+R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
S00728 | S092A_S00728OD_KGBONGALIU | Sabah |  | Decomm |  | 2024 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2024-01-19 |  |  |  | 2024-01-23 |  | 2024-03-22 | 2024-04-24 | CD//Mohidi Jaan | 2024-03-24 | Celcom Digi_RAN-YPTT-TSS-Sabah-20240124 | DU00002860232 |  |  |  |  | 2024-06-06 |  | TOWER
1001A | SINGERMELAWATI | Central |  | Modernization |  | 2024 Q1 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-10 | 2023-11-22 |  | 2023-12-30 |  | Closed | 2024-01-02 | 2024-01-05 | E//Sumitra | 2024-01-05 | CelcomDigi_RAN_GTSB_TSS_Central_20231113 | DU00002860233 |  |  | 2024-03-07 | 2024-03-04 |  | Unipole | 6m RT (Wall Mounted Pole) | 6 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882-GUL1812 x3
1012B | Bandar Tun Razak | Central |  | Modernization |  | 2024 Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-11-17 | 2023-11-23 |  | 2024-03-25 |  | Closed | 2024-03-25 | 2024-04-01 | E//Sumitra | 2024-04-01 | CelcomDigi_RAN_AllStar_TSS_Central_20231119 | DU00002860234 |  |  | 2024-06-06 | 2024-06-01 |  | Wall mount boom | 5m RT (Wall Mounted Pole) | 3 | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3 | 23 | 0
1019B | LRT Station Wangsa Maju(ZED) | Central |  | Modernization |  | 2024 Q1 | CR | GCI | 4.6 TSSR Approved |  | 2024-04-03 | 2024-04-08 |  | 2024-04-16 |  | Closed | 2024-04-18 | 2024-04-19 | E//Kok Keen | 2024-04-18 | CelcomDigi_RAN_GCI_TSS_Central_20240513 | DU00002860235 |  |  | 2024-05-24 | 2024-05-18 |  | In-Building System | 3m RT (Wall Mounted Pole) | 3 (Sector 1, 3 & 4) , 6 (Sector 2)=9M | Add R9264H M901821 x4,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x1
S01021 | S092A_S01021OD_KGJAWIJAWI | Sabah |  | Decomm |  | 2024 Q3 | AD | Futong | 4.6 TSSR Approved |  | 2024-01-17 |  |  |  | 2024-01-18 |  | 2024-03-22 | 2024-05-14 | CD//Mohidi Jaan | 2024-03-24 | Celcom Digi_RAN-Futong-TSS-Sabah-20240124/0612Sabah-Futong-BOQ Template (template) | DU00002860236 |  |  |  |  | 2024-07-01 |  | LAMP_POLE
A01146 | A042B_A01146OD_KG_ASAM_KUMBANG | Northern |  | Decomm |  | 2024 Q2 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-11-26 |  |  |  | 2023-12-06 |  | 2023-12-13 | 2024-02-15 | CD//Rohizam | 2024-01-30 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231127-0073 | DU00002860237 |  |  |  |  | 2024-06-12 |  | UNIPOLE
1033A | Suntex | Central |  | Modernization |  | 2024 Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-10-22 | 2023-11-06 |  | 2024-05-20 |  | Closed | 2024-05-21 | 2024-05-29 | E//Sumitra | 2024-05-29 | CelcomDigi_RAN_GTSB_TSS_Central_20231201 | DU00002860238 |  |  | 2024-06-13 | 2024-06-12 |  | H-bracket pole | 5m RT (Wall Mounted Pole) | 3 | Add R9264M M1821 x3+A9732 M1821 x1,Dismantle R8862A S2600(A4A) x1+R8894E M1821(A8A) x5 | 1 | 0
1037B | JALAN SEMARAK | Central |  | Modernization |  | 2024 Q1 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-14 | 2023-11-23 |  | 2023-12-28 |  | Closed | 2023-12-29 | 2024-01-05 | E//Sumitra | 2024-01-05 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231116 | DU00002860239 |  |  | 2024-02-06 | 2024-01-11 |  | In-Building System | 3m Bipod (RT) | 3.8 | Add R8894E M1821 x4,Dismantle R8882 S1800(B) x3+R8862A S1800(B6A) x1+R8854D S2100(A4A) x4 |  | 1
1042A | Tmn Indah Kajang | Central |  | Modernization |  | 2024 Q4 | SM | GTSB | 4.6 TSSR Approved |  | 2024-01-15 | 2024-02-22 |  | 2024-05-31 |  | Under Approval | 2024-06-05 | 2024-06-13 | E//Sumitra | 2024-06-13 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240116 | DU00002860240 |  |  | 2024-09-09 | 2024-09-06 |  |  | 3m RT (Minimast) | 12 | Add R9264M M1821 x2+R8862A S2601 x3+A9732 M1821 x2,Dismantle R8882-L268 x3+R8894E M1821(A8A) x4 | 34 | 0
1044B | Bandar Tun Hussein Onn 2 | Central |  | Modernization |  | 2024 Q4 | MA | Solusi | 4.6 TSSR Approved |  | 2024-03-28 | 2024-02-20 |  | 2024-05-21 |  | Closed | 2024-05-29 | 2024-06-06 | E//Sumitra | 2024-06-06 | BOQ CelcomDigi_RAN_Solusi_Standard PR TSS_Central_20240329 | DU00002860241 |  |  | 2024-06-15 | 2024-06-15 |  | Monople Tree | 30m Monopole | 24 | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R8862A S2601(A6A) x1+R9224E M1821(AAB) x4 | 3 | 0
1050A | Tmn Uniindah | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002860242 | [6 empty] | 45m 3 Legged Tower |  |  | 12
1051A | ILPM | Central |  | Modernization |  | 2024 Q3 | SY1 | YPTT | 4.6 TSSR Approved |  | 2024-05-15 | 2024-05-08 |  | 2024-05-15 |  | Closed | 2024-05-17 | 2024-07-11 | E//Sumitra | 2024-07-11 | CelcomDigi_RAN_YPTT_TSS_Central_20240517 | DU00002860243 |  |  | 2024-06-26 | 2024-06-26 |  |  | 3m RT (Wall Mounted Pole) | 20 | Add R8894E M1821 x4,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8840-U216 x3+R8862A S2100 x1 | 0 | 0
A01134 | A040D_A01134OD_TMN_KLEDANGSURIA_IPH | Northern |  | Decomm | Decomm->On Hold->Decomm | 2024 Q2 | SM | GCI | 4.6 TSSR Approved | ¦ 0222 - Replied to Rohizam with simulation justification. Rohizam reverted agreed. ¦ 0208 - Li Jie reverted for IZzat to do case Study to change anchor or add sector at NB ¦ 0206 - fup done to Izzat/Khai ¦ 0119 - CD Rohizam Rejected and Proposed change anchor to site A01134, email fwdd to Duan/RF | 2023-12-22 |  |  |  | 2024-01-05 |  | 2024-01-19 |  | CD//Rohizam | 2024-02-22 | 0628Northern-GCI-BOQ Template (template) | DU00002860244 |  |  |  |  | 2024-07-12 |  | LAMP_POLE
1073B | Kg Cheras Baru | Central |  | Modernization |  | 2024 Q3 | HQ 1 | AllStar | 4.6 TSSR Approved |  | 2023-11-17 | 2023-11-24 |  | 2024-04-08 |  | Closed | 2024-04-15 | 2024-04-18 | E//Sumitra | 2024-04-18 | CelcomDigi_RAN_AllStar_TSS_Central_20231119 | DU00002860245 |  |  | 2024-06-07 | 2024-06-01 |  | Minimast | 3m Boom (RT) | 5 | Add R9264M M1821 x3+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x4 | 2 | 0
1075B | Tmn Pandan Mewah | Central |  | Modernization |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-10-28 | 2023-11-06 |  | 2023-11-27 |  | Closed | 2024-07-05 | 2024-07-10 | E//Sumitra | 2024-07-10 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231101 | DU00002860246 |  |  | 2024-06-06 | 2024-06-04 |  | Monopole | 60m 3 Legged Tower | 20 | Add R9264M M1821 x1+A9732 M1821 x3,Dismantle R8894E M1821(A8A) x4 | 123 | 0
1085B | Sri Rampai 2 | Central |  | Modernization |  | 2024 Q1 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-03 | 2023-11-08 |  | 2023-11-21 |  | Closed | 2023-12-27 | 2023-12-28 | E//Kok Keen | 2023-12-27 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231104 | DU00002860247 |  |  | 2024-01-09 | 2024-01-09 |  | Monopole | 60m 3 Legged Tower | 24 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1121B | Desa Petaling | Central |  | Modernization |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-15 | 2023-11-21 |  | 2023-11-30 |  | Closed | 2024-07-05 | 2024-07-10 | E//Sumitra | 2024-07-10 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231116 | DU00002860248 |  |  | 2024-06-06 | 2024-06-04 |  | In-Building System | 3m Boom (RT) | 3 | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8854D S2100(A4A) x4+R8862A S2600(A4A) x1 | 13 | 0
1137B | JBA Puchong Jaya (AS) | Central |  | Modernization |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-11-08 | 2023-12-21 |  | 2024-04-23 |  | Closed | 2024-04-27 | 2024-04-30 | E//Sumitra | 2024-04-30 | CelcomDigi_RAN_Datasco_TSS_Central_20231214 | DU00002860249 |  |  | 2024-05-15 | 2024-05-07 |  | Monople Tree | 30m Monopole | 30 | Add R8894E M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8840-U216 x3++ | 0 | 0
1145B | UKM Fakulti Pendidikan (JBA) | Central |  | Modernization |  | 2024 Additional | SHA | YPTT | 4.6 TSSR Approved |  | 2024-04-19 | 2024-05-07 |  | 2024-11-24 |  | Closed | 2024-12-04 | 2024-12-10 | E//Sumitra | 2024-12-10 | CelcomDigi_RAN_YPTT_TSS_Central_20240513 | DU00002860250 | Remarks: Solution TSSR/BOM Changed |  | 2024-12-19 | 2024-12-16 |  | Monople Tree | 30m Monopole Tree | 30 | Add R8852E S9000 x4+R8894E M1821 x4+R8862A S2601 x3,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8862A S2100(A6A) x4+R8882 S2600(B4A) x3 | 0 | 0
1157B | Putra Perdana 6 | Central |  | Modernization | Modernization-On Hold-Modernization | 2024 Q3 | AD | Magicell | 4.6 TSSR Approved |  | 2024-05-03 | 2024-05-21 |  | 2024-11-25 |  | Under Approval | 2024-11-26 | 2024-12-03 | E//Razif | 2024-11-27 | CelcomDigi_RAN_Magicell_TSS_Central_20240424 | DU00002860251 |  |  | 2024-12-06 | 2024-12-03 |  | Monopole | 20m Lampole | 20M | Add R8894E M1821x3+R8862A S2601x3,Dismantle R8882-GUL1812x3+R8882 S2600(B4A)x3 | 0 | 0
1180A | Wisma IJM | Central |  | Modernization |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-12-20 | 2024-01-18 |  | 2024-03-27 |  | Closed | 2024-03-29 | 2024-04-01 | E//Kok Keen | 2024-04-01 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231224 | DU00002860252 |  |  | 2024-06-04 | 2024-05-31 |  | In-Building System | 3m Boom (RT) | 6 | Add R9264H M901821 x4,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x2+R8862A S2100(A6A) x4
1190A | Tmn Megah | Central |  | Modernization |  | 2024 Q3 | SH | GTSB | 4.6 TSSR Approved |  | 2023-11-07 | 2023-11-10 |  | 2024-03-25 |  | Closed | 2024-03-26 | 2024-03-27 | E//Kok Keen | 2024-03-27 | CelcomDigi_RAN_GTSB_TSS_Central_20231113 | DU00002860253 |  |  | 2024-05-03 | 2024-04-30 |  | Pole | 3m Boom (RT) | 6m | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3 | 0 | 0
S01466 | S092A_S01466OD_CB_PULAUMANTANANI | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2024 Q3 | MS | Seri Pancar | 4.6 TSSR Approved |  | 2024-04-05 |  |  |  | 2024-04-08 |  | 2024-04-17 | 2024-08-09 | CD//Mohidi Jaan | 2024-04-17 | Celcom Digi_RAN-Seri Pancar-Standard PR TSS-Sabah-20240406 | DU00002860254 |  |  |  |  | 2025-11-30 |  | TOWER
K00230 | K006A_K00230OD_TMCHANGLUN | Northern |  | Decomm |  | 2024 Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2024-03-03 |  |  |  | 2024-03-05 |  | 2024-03-21 | 2024-04-23 | CD//Rohizam | 2024-03-21 | Celcom Digi_RAN-GTSB-TSS-Northern-20240303-0095/0612Northern-GTSB-BOQ Template (template) | DU00002860255 |  |  |  |  | 2024-11-26 |  | TOWER
1193A | University Hosp | Central |  | Modernization |  | 2024 Q3 | AI | YPTT | 4.6 TSSR Approved |  | 2024-04-30 | 2024-05-08 |  | 2024-05-09 |  | Closed | 2024-05-10 | 2024-05-10 | E//Sumitra | 2024-05-10 | CelcomDigi_RAN_YPTT_TSS_Central_20240513 | DU00002860256 |  |  | 2024-09-20 | 2024-06-08 |  | In-Building System | 3m Boom (RT) | 2m | Add R8862A S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R8882-L268 x1+R8862A S2600(A4A) x1+R8894E M1821(A8A) x2 | 13 | 0
K00026 | K006B_K00026OD_BBDARULAMAN2 | Northern |  | Decomm |  | 2024 Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-10-12 |  |  |  | 2023-10-23 |  | 2023-10-25 | 2023-12-18 | CD//Rohizam | 2023-10-26 | Celcom Digi_RAN-GCI-TSS-Northern-20231015-0059 | DU00002860257 |  | Missing TX info and photo |  |  | 2024-05-08 |  | BOOM
K00392 | K006A_K00392OD_CB_BT5KODIANG | Northern |  | Decomm |  | 2024 Q3 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-12-28 |  |  |  | 2024-01-22 |  | 2024-02-29 | 2024-03-05 | CD//Rohizam | 2024-02-29 | Celcom Digi_RAN-GTSB-TSS-Northern-20231229-0081/0612Northern-GTSB-BOQ Template (template) | DU00002860258 |  |  |  |  | 2024-07-01 |  | TOWER
K00220 | K006A_K00220OD_PADANGSERA | Northern |  | Decomm |  | 2024 Q3 | SM | GCI | 4.6 TSSR Approved |  | 2024-04-24 |  | 2025-07-03 |  | 2024-04-30 |  | 2024-05-06 | 2025-10-01 | CD//Rohizam | 2024-05-07 | Celcom Digi_RAN-GCI-TSS-Northern-20240512-0106 | DU00002860259 |  |  |  |  | 2025-03-20 |  | TOWER
K00505 | K006B_K00505OD_HOSPITALJITRA | Northern |  | Decomm |  | 2024 Q3 | SM | GCI | 4.6 TSSR Approved |  | 2023-12-20 |  |  |  | 2024-01-03 |  | 2024-01-05 | 2024-01-22 | CD//Rohizam | 2024-01-05 | Celcom Digi_RAN-GCI-TSS-Northern-20231225-0085/Celcom Digi_RAN-GCI-TSS-Northern-20240130-0092 | DU00002860260 |  |  |  |  | 2024-05-10 | Lampole | SHARING STRC OTHERS 3RD PARTY | 30
1205A | S17PJ | Central |  | Modernization | Modernization->Decomm->On Hold->Decomm | 2024 Q3 | SH | DATASCO | 4.6 TSSR Approved |  | 2023-10-28 | 2023-11-02 | 2024-09-09 | 2023-11-08 | 2024-09-18 | Under Approval | 2024-09-20 | 2024-04-01 | E//Kok Keen | 2024-09-20 | 0823CD-Central-Datasco-BOQ Template(new contract) | DU00002860261 |  |  | 2024-04-29 | 2024-04-25 | 2024-09-24 | In-Building System | 3m Tripod (RT) | S1&3 - 5M S2-3M
1209A | Puchong Permai | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-04 | 2024-01-15 |  | 2024-04-29 |  | Closed | 2024-04-29 | 2024-05-06 | E//Razif | 2024-05-06 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240108 | DU00002860262 |  |  | 2024-06-05 | 2024-06-01 |  | Wall mount boom | 3m Boom (RT) | 6 | Add R9264M M1821 x2+A9732 M1821 x2,Dismantle R9224E M1821(AAB) x4 | 12 | 0
1211A | KDU | Central |  | Modernization |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-04-25 | 2024-05-21 |  | 2024-05-23 |  | Closed | 2024-05-23 | 2024-05-23 |  | 2024-05-23 | CelcomDigi_RAN_Datasco_TSS_Central_20240513 | DU00002860263 |  |  | 2024-05-28 | 2024-05-28 |  | In-Building System | 3m Boom (RT) | 3m | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3 | 0 | 0
1212B | Tmn Bukit Pantai | Central |  | Modernization |  | 2024 Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2023-12-22 | 2024-01-05 |  | 2024-01-10 |  | Closed | 2024-01-15 | 2024-01-16 | E//Kok Keen | 2024-01-15 | BOQ CelcomDigi_RAN_AllStar_Standard PR TSS_Central_20240108 | DU00002860264 |  |  | 2024-06-14 | 2024-05-30 |  | Wall mount boom | 3m Boom (RT) | 3 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3
1229A | Bandar Puchong Utama | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002860265 | [6 empty] | 6m RT (Minimast) |  |  | 23
1236A | Labu Lanjut | Central |  | Modernization |  | 154 single site MOCN | CR | GCI | 4.6 TSSR Approved |  | 2024-02-07 | 2024-03-20 |  | 2024-06-12 |  | Under Approval | 2024-06-20 | 2024-07-19 | E//Razif | 2024-07-18 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240212 | DU00002860266 |  |  | 2024-09-27 | 2024-09-12 |  | Tower | Tower | 40 | Add R8862A S9000 x3+R9264H M901821 x1+A9732 M1821 x3+R8862A S2601(A6A) x1,Dismantle R8881 S9000 x1+R8894E M1821(A8A) x3 | 124 | 0
1238B | Seksyen 13 Industrial Park | Central |  | Modernization |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-04-06 | 2024-04-08 |  | 2024-04-15 |  | Closed | 2024-04-17 | 2024-04-23 | E//Kok Keen | 2024-04-17 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240311 | DU00002860267 |  |  | 2024-05-01 | 2024-05-01 |  | Wall mount boom | 6m RT (Boom) | 7m | Add R8862A S9000 x3+R9224E M1821 x4+R8854 S2600 x1,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8862A S2600(A4A) x1+R8840-U216 x3++ | 0 | 3
1245A | GemilangApart | Central |  | Modernization |  | 2024 Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-11-30 | 2023-12-28 |  | 2024-03-29 |  | Closed | 2024-03-29 | 2024-04-03 | E//Sumitra | 2024-04-03 | CelcomDigi_RAN_Allstar_TSS_Central_20231203 | DU00002860268 |  |  | 2024-07-23 | 2024-05-13 |  | In-Building System | 5m RT (Boom) | 7 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x4+R8862A S2100(A6A) x3 | 0 | 0
1250A | Goldenbright | Central |  | Modernization |  | 2024 Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-12-05 | 2023-12-15 |  | 2024-04-01 |  | Closed | 2024-04-01 | 2024-04-05 | E//Sumitra | 2024-04-05 | CelcomDigi_RAN_Allstar_TSS_Central_20231208 | DU00002860269 |  |  | 2024-04-26 | 2024-04-24 |  |  | 3m Tripod (RT) | 6 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8840-U216 x3 | 0 | 0
1265B | Tmn Sinara | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-10-20 | 2023-10-30 |  | 2023-11-02 |  | Closed | 2024-05-30 | 2024-06-07 | E//Sumitra | 2024-06-07 | CelcomDigi_RAN_GTSB_TSS_Central_20231021 | DU00002860270 |  |  | 2024-06-22 | 2024-06-22 |  | Pole | 3m Boom (RT) | 3 | Reuse exisiting RRU | 0 | 0
1266A | Sucasa | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q1 |  |  | 14.1 Drop (No Survey) |  |  | 2023-12-19 |  |  |  | Under Approval | [5 empty] | DU00002860271 | [5 empty] | In-Building System | 3m Boom (RT) | 6 |  | 2
1267B | Saujana Impian Resort | Central |  | Modernization |  | 2024 Q4 | SY1 | YPTT | 4.6 TSSR Approved |  | 2024-04-30 | 2024-05-03 |  | 2024-05-15 |  | Closed | 2024-05-17 | 2024-10-11 | E//Sumitra | 2024-10-11 | CelcomDigi_RAN_YPTT_TSS_Central_20240513 | DU00002860272 |  |  | 2024-09-24 | 2024-09-24 |  | Monople Tree | 45m Monopole | 45 | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 1 | 0
1271A | Risda Ampang | Central |  | Modernization |  | 2024 Q1 | CR | GCI | 4.6 TSSR Approved | 22/01/24 - Reject to Subcon - TSSR Quality | 2023-12-08 | 2023-12-18 |  | 2024-01-05 |  | Rectificating | 2024-01-24 | 2024-01-31 | E//Sumitra | 2024-01-30 | CelcomDigi_RAN_GCI_TSS_Central_20231214 | DU00002860273 |  |  | 2024-04-19 | 2024-04-16 |  | In-Building System | 3m Boom (RT) | 4 | Add R9224E M1821 x1+R8854 S2600 x1,Dismantle R8882-L268 x1 |  | 13
1276B | Damai Impian | Central |  | Modernization |  | 2024 Q4 | SY1 | GTSB | 4.6 TSSR Approved |  | 2024-08-23 | 2024-08-26 |  | 2024-08-28 |  | Closed | 2024-09-27 | 2024-09-30 | E//Sumitra | 2024-09-30 | 0809CD-Central-GTSB-BOQ Template(new contract) | DU00002860274 |  |  | 2024-09-28 | 2024-09-27 |  | Monople Tree | 24m Pylon | 31m | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 1 | 0
1279B | Shamelin Perkasa | Central |  | Decomm | Modernization-On Hold->Decomm | 2024 Q3 | MA | CCSMY | 4.6 TSSR Approved |  | 2023-11-08 | 2023-11-24 | 2025-10-22 | 2023-11-30 |  | Rectificating | 2024-07-25 | 2025-10-31 | E//Sumitra | 2025-10-23 | SQ202512220044 - CCS | DU00002860275 | [5 empty] | In-Building System | 3m Bipod (RT) | 8 | Add R8862A S9000x1+R8894E M1821x3+A9732 M1821x2, Dismantle R8882-GUL1812x3+R8862A S1800(B6A)x2+R8862A S2100(A6A)x5+R8882 S2600(B4A)x1 | 12 | 4
1305B | Jalan Penchala | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-22 | 2023-11-24 |  | 2024-04-03 |  | Closed | 2024-04-03 | 2024-04-04 | E//Kok Keen | 2024-04-03 | CelcomDigi_RAN_GTSB_TSS_Central_20231126 | DU00002860276 |  |  | 2024-05-03 | 2024-04-30 |  | H-bracket pole | 3m Boom (RT) | 4m | Add R8862A S9000 x3+R8894E M1821 x1+R8854 S2600 x1,Dismantle R8862A S2600(A4A) x1 | 0 | 2
S00902 | S092A_S00902OD_KGAMBONG | Sabah |  | Decomm |  | 2024 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2024-01-22 |  |  |  | 2024-01-29 |  | 2024-03-22 | 2024-11-29 | CD//Mohidi Jaan | 2024-03-24 | Celcom Digi_RAN-YPTT-TSS-Sabah-20240124/0612Sabah-YPTT-BOQ Template (template) | DU00002860277 |  |  |  |  | 2024-06-06 |  | TOWER
S00565 | S092A_S00565OD_KGSEMBIRAI | Sabah |  | Decomm |  | 2024 Q3 | MS | GTSB | 4.6 TSSR Approved |  | 2024-01-24 |  |  |  | 2024-01-30 |  | 2024-03-21 | 2024-08-16 | CD//Mohidi Jaan | 2024-03-21 | Celcom Digi_RAN-GTSB-TSS-Sabah-20240204/0612Sabah-GTSB-BOQ Template (template) | DU00002860278 |  |  |  |  | 2024-07-29 |  | TOWER
1313B | Sg Rasau | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002860279 | [6 empty] | 76m 4 Legged Tower |  |  | 34
1315A | Kien Heng Motor | Central |  | Modernization |  | 2024 Q1 | YZ | Ascentrack | 4.6 TSSR Approved |  | 2023-11-11 | 2024-01-15 |  | 2024-01-21 |  | Closed | 2024-01-23 | 2024-01-29 | E//Kok Keen | 2024-01-26 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231113 | DU00002860280 |  |  | 2024-06-05 | 2024-06-04 |  | In-Building System | 3m Boom (RT) | 3 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3
4447A | Langkap(Celcom) | Northern |  | Modernization |  | 2024 Q3(single site MOCN) | SM | GTSB | 4.6 TSSR Approved | ¦ 0506 - SA Adila: will change anchor | 2024-01-11 | 2024-02-15 |  | 2024-04-16 |  | Rectificating | 2024-04-17 | 2024-04-22 | E//Hazida | 2024-04-19 | Celcom Digi_RAN-GTSB-TSS-Northern-202401114-0085 | DU00002860281 |  |  | 2024-06-26 | 2024-06-15 |  | Tower | Tower | 60m | Add R8862A S9000 x2+R9264H M901821 x1+A9732 M1821 x3,Dismantle R8860E-GU908 x2+R8854E S1800(A6A) x3+R8854D S2100(A4A) x3+R8894E M1821(A8A) x1 | 134 | 0
4482A | University MARA (AsiaSpace) RCC | Northern |  | Modernization |  | 2024 Q2 | BY | YPTT | 4.6 TSSR Approved | ¦ 0304 - Need revise TSSR due to 900 RRU model not available ¦ 0202 - ETSS rejected, pending Colo Info, need re-TSS | 2024-01-28 | 2024-02-06 |  | 2024-02-19 |  | Closed | 2024-02-19 | 2024-02-20 | E//Hazida | 2024-02-20 | Celcom Digi_RAN-YPTT-TSS-Northern-20240202-0058 | DU00002860282 |  |  | 2024-04-04 | 2024-03-20 |  | Tower | 60m 4 Legged Tower | 55 | Add R8862A S9000 x3+A9732 M1821 x3,Dismantle R8860E-GU908 x1+R8854E S1800(A6A) x3+R8862A S2100(A6A) x4 | 123
1340B | OUG Kesas (Lamp pole) | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-04 | 2023-11-07 |  | 2024-03-30 |  | Closed | 2024-04-01 | 2024-04-05 | E//Sumitra | 2024-04-05 | CelcomDigi_RAN_GTSB_TSS_Central_20231113 | DU00002860283 |  |  | 2024-09-25 | 2024-06-01 |  | Monople Tree | 24m Lampole | 25M | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3++ | 0 | 0
1346B | Jalan Mayang Emas | Central |  | Modernization |  | 2024 Q3 | IE | GTSB | 4.6 TSSR Approved |  | 2023-10-23 | 2023-10-30 |  | 2024-03-21 |  | Closed | 2024-03-25 | 2024-03-26 | E//Kok Keen | 2024-03-26 | CelcomDigi_RAN_GTSB_TSS_Central_20231025 | DU00002860284 |  |  | 2024-05-01 | 2024-05-01 |  | H-bracket pole | 6m RT (Boom) | 6m | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
1353B | Putra Permai | Central |  | Modernization |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-10-25 | 2024-02-07 |  | 2024-05-02 |  | Closed | 2024-05-16 | 2024-05-27 | E//Sumitra | 2024-05-24 | CelcomDigi_RAN_Datasco_TSS_Central_20231214 | DU00002860285 |  |  | 2024-06-27 | 2024-06-27 |  | In-Building System | 6m RT (Minimast) | 4m + 6m = 10m | Add R8894E M1821 x6+R8854 S2600 x2,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8862A S2100(A6A) x4+R8862A S2600(A4A) x2 | 0 | 13
1357B | Tmn Seri Sentosa | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-09 | 2023-11-14 |  | 2024-04-26 |  | Closed | 2024-04-29 | 2024-05-03 | E//Sumitra | 2024-05-03 | CelcomDigi_RAN_GTSB_TSS_Central_20231113 | DU00002860286 |  |  | 2024-04-15 | 2024-04-03 |  | H-bracket pole | 3m Boom (RT) | 6m | Add R9264M M1821 x3+R8854 S2600 x1,Dismantle R8894E M1821(A8A) x3+ R8882 S2600(B4A) x1 | 0 | 3
B02350 | B061G_B02350OD_ARADAMANSARABERKLEY | Central |  | Decomm |  | 2024 Q1 | MS | GTSB | 4.6 TSSR Approved |  | 2024-02-14 |  |  |  | 2024-02-26 |  | 2024-02-27 | 2024-04-24 | CD//Sapian | 2024-03-13 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240217 | DU00002860287 |  |  |  |  | 2024-05-30 |  | AESTHETIC MONOPOLE
B00513 | B061R_B00513OD_SS3PJ | Central |  | Decomm |  | 2024 Q1 | SS | Magicell | 4.6 TSSR Approved |  | 2024-02-21 |  |  |  | 2024-02-29 |  | 2024-03-01 | 2025-03-14 | CD//Ali Akaram | 2024-03-19 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240225 | DU00002860288 |  |  |  |  | 2024-05-15 |  | TOWER
B02188 | B061G_B02188OD_OASISARADAMANSARA | Central |  | Decomm |  | 2024 Q1 | AI | GTSB | 4.6 TSSR Approved |  | 2024-05-15 |  |  |  | 2024-05-24 |  | 2024-05-28 | 2024-07-12 | CD//Ali akaram | 2024-06-14 | CelcomDigi_RAN_GTSB_TSS_Central_20240423 | DU00002860289 |  |  |  |  | 2024-05-30 |  | BOOM
1369B | Tmn Puchong Intan(ZED) | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-05 | 2024-01-09 |  | 2024-04-22 |  | Closed | 2024-04-23 | 2024-04-26 | E//Razif | 2024-04-25 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240108 | DU00002860290 |  |  | 2024-06-24 | 2024-06-24 |  | In-Building System | 3m Bipod (RT) | 6M | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle R8862A S2601(A6A) x1 | 0 | 3
A01148 | A041A_A01148OD_CB_KG_SENGGANG_KK | Northern |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2025 Q3 | HW | GCI | 4.6 TSSR Approved |  | 2025-07-12 |  | 2025-08-12 |  | 2025-09-10 |  | 2025-09-29 | 2026-01-22 | E//Hazida | 2025-10-03 | SQ202504230429-GCI | DU00002860291 |  |  |  |  | 2025-10-13 |  | TOWER
B00449 | B061P_B00449OD_SS9PJ | Central |  | Decomm |  | 2024 Q1 | SS | Magicell | 4.6 TSSR Approved |  | 2024-01-18 |  |  |  | 2024-01-19 |  | 2024-08-13 | 2025-01-14 | CD//Ali akaram | 2024-08-15 | CelcomDigi_RAN_MAGICELL_TSS_Central_20240124 | DU00002860292 |  |  |  |  | 2025-03-24 |  | BOOM
1408A | Puchong Jaya | Central |  | Modernization |  | 2024 Q3 | CR | Magicell | 4.6 TSSR Approved |  | 2023-10-30 | 2023-11-01 |  | 2024-04-25 |  | Closed | 2024-04-29 | 2024-05-02 | E//Sumitra | 2024-05-02 | CelcomDigi_RAN_Magicell_TSS_Central_20231214 | DU00002860293 |  |  | 2024-07-02 | 2024-06-26 |  | Guide mast | 3m RT (Minimast) | 10M | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8862A S2601(A6A) x1+R8894E M1821(A8A) x4+R9224E M1821(AAB) x1 | 12 | 0
1420B | PUAS BK5 (KJS) | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002860294 | [6 empty] | 30m Monopole |  |  | 13
W01401 | W066G_W01401OD_JLNDANAUSAUJANA_DANAUKOTA | Central |  | Decomm |  | 2024 Q1 | BY | GTSB | 4.6 TSSR Approved |  | 2024-06-12 | 2024-07-03 |  |  | 2024-07-09 |  | 2024-07-11 | 2024-09-25 | CD//Sapian | 2024-07-24 | 0618Central-GTSB-BOQ Template (template) | DU00002860295 |  |  |  |  | 2024-07-17 | Lampole | LAMP_POLE | 18M
1442A | Desa Pandan | Central |  | Modernization |  | 2024 Q2 | YZ | GTSB | 4.6 TSSR Approved |  | 2023-11-21 | 2023-11-24 |  | 2024-03-05 |  | Closed | 2024-03-07 | 2024-03-13 | E//Sumitra | 2024-03-12 | CelcomDigi_RAN_GTSB_TSS_Central_20231126 | DU00002860296 |  |  | 2024-04-18 | 2024-04-18 |  | In-Building System | 3m Boom (RT) | 6 | Add R9264M M1821 x1+A9732 M1821 x3,Dismantle R8862A S2601(A6A) x1+R8894E M1821(A8A) x4+R9224E M1821(AAB) x1 | 123 | 0
S01010 | S092A_S01010OD_KGTENGKURUS | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2025-07-31 |  | 2025-08-04 |  | 2025-08-07 |  | 2025-09-09 | 2025-09-20 | E//Hannah | 2025-09-17 | SQ202506100836 - YPTT / SQ202507010450 - YPTT | DU00002860297 |  |  |  |  | 2025-09-18 |  | TOWER
Q01366 | Q143A_Q01366OD_RAMOJLNMUHIBBAH | Sarawak |  | Decomm |  | 2025 Q3 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-12-15 |  |  |  | 2023-12-19 |  | 2024-01-25 | 2024-02-09 | CD//John | 2024-01-25 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231218 | DU00002860298 |  |  |  |  | 2025-11-26 |  | RAPOLE
Q00600 | Q137A_Q00600OD_TMSELALANG | Sarawak |  | Decomm |  | 2025 Q1 | AI | Trintel | 4.6 TSSR Approved |  | 2025-04-16 |  | 2025-07-04 |  | 2025-07-08 | To be Submitted | 2025-07-09 |  | CD//John | 2025-10-17 | SQ202503030411-Trintel | DU00002860299 |  |  |  |  | 2025-10-24 |  | TOWER
Q00405 | Q127A_Q00405OD_ENGKELILI | Sarawak |  | Decomm |  | 2025 Q3 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-12-14 |  |  |  | 2023-12-22 |  | 2024-01-25 | 2024-02-09 | CD//John | 2024-01-25 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231215 | DU00002860300 |  |  |  |  | 2025-06-11 |  | GUYED MAST
S00198 | S091A_S00198OD_CB_TMKINABATANGAN | Sabah |  | Decomm |  | 2024 Q4(single site MOCN)-L2126 SSM | AD | Seri Pancar | 4.6 TSSR Approved |  | 2024-08-09 |  | 2024-08-15 |  | 2024-08-19 |  | 2024-08-20 | 2024-09-30 | CD//Sharidah | 2024-08-20 | 0809MW-Sabah-Seri Pancar-BOQ Template(new contract)/0809CD-Sabah-Seri Pancar-BOQ Template(new contract) | DU00002860301 |  |  |  |  | 2025-01-28 |  | TOWER
B02813 | B061G_B02813OD_LRT_LEMBAH_SUBANG | Central |  | Decomm |  | 2024 Q1 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-25 |  |  |  | 2024-02-08 |  | 2024-02-13 | 2024-09-25 | CD//Norhaliza | 2024-08-05 | CelcomDigi_RAN_GTSB_TSS_Central_20231126 | DU00002860302 |  |  |  |  | 2024-07-29 |  | RAPOLE
S01764 | S092A_S01764OD_CB_RAMOSMKARSHAD | Sabah | 7287K | Swap | Decomm->On Hold-Swap | 2024 Q3 | AD | GTSB | 4.6 TSSR Approved | Change anchor study | 2024-01-24 | 2024-11-25 |  | 2024-12-06 | 2024-01-29 | Under Approval | 2024-03-21 | 2024-12-17 | CD//Sharidah | 2024-12-17 | Celcom Digi_RAN-GTSB-TSS-Sabah-20240204/0821CD-Sabah-GTSBBOQ Template(new contract) | DU00002860303 |  |  | 2025-02-13 | 2025-02-06 |  | Tower | RAMO | 60 | Add R8862A S9000 x3+R8894E M1821 x4+R8862A S2601 x2+R8854 S2600 x1,Dismantle | 0 | 1
1703A | Jenderam Hampar Tenang | Central |  | Modernization |  | 154 single site MOCN | BY | GTSB | 4.6 TSSR Approved |  | 2024-01-10 | 2024-01-16 |  | 2024-05-09 |  | Closed | 2024-05-13 | 2024-05-15 | E//Razif | 2024-05-15 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240115 | DU00002860304 |  |  | 2024-06-06 | 2024-05-31 |  | Tower | Tower | 32m | Add R8862A S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x2+R8862A S2100(A6A) x3 | 13 | 0
1730A | Fak Perniagaan UM | Central |  | Modernization |  | 2024 Q3 | AI | YPTT | 4.6 TSSR Approved |  | 2023-12-04 | 2023-12-07 |  | 2024-04-05 |  | Closed | 2024-04-05 | 2024-04-15 | E//Kok Keen | 2024-04-15 | CelcomDigi_RAN_YPTT_TSS_Central_20231224 | DU00002860305 |  |  | 2024-07-06 | 2024-05-29 |  | In-Building System | 3m Boom (RT) | 6 | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 3 | 0
1732A | Tmn Billion | Central |  | Modernization |  | 2024 Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-11-14 | 2023-11-16 |  | 2024-04-16 |  | Closed | 2024-04-16 | 2024-04-23 | E//Sumitra | 2024-04-23 | CelcomDigi_RAN_AllStar_TSS_Central_20231116 | DU00002860306 |  |  | 2024-06-20 | 2024-06-15 |  | In-Building System | 3m Bipod (RT) | 6 | Add R8894E M1821 x2+R8854 S2600 x2,Dismantle R8882 S2600(B4A) x2 | 0 | 34
1742A | Desa Serdang | Central |  | Modernization |  | 2024 Q3 | SY1 | YPTT | 4.6 TSSR Approved |  | 2024-05-06 | 2024-05-13 |  | 2024-05-23 |  | Closed | 2024-05-24 | 2024-06-12 | E//Sumitra | 2024-06-10 | CelcomDigi_RAN_YPTT_TSS_Central_20240513 | DU00002860307 |  |  | 2024-08-13 | 2024-08-09 |  | In-Building System | 6m RT (Boom) | 6 | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle R8882 S2600(B4A) x1 | 0 | 2
1779B | Ukay Perdana 2 | Central |  | Modernization |  | 2024 Q1 | MA | GCI | 4.6 TSSR Approved |  | 2023-11-16 | 2023-11-20 |  | 2024-01-04 |  | Closed | 2024-01-04 | 2024-01-09 | E//Sumitra | 2024-01-09 | Celcom Digi_RAN-GCI-TSS-Central-20231119 | DU00002860308 |  |  | 2024-03-05 | 2024-02-24 |  | Lampole | 24m Lampole | 15 | Add R8862A S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R9224E M1821(AAB) x3 | 1
A00588 | A041A_A00588OD_KGJERLUNKKG9_RCC | Northern |  | Decomm |  | 2025 Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-10-16 |  |  |  | 2023-10-23 |  | 2023-10-25 | 2025-10-28 | CD//Rohizam | 2023-10-25 | Celcom Digi_RAN-GCI-TSS-Northern-20231018-0061/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240529-0109//SQ202501030261 - GCI | DU00002860309 |  |  |  |  | 2025-06-30 |  | TOWER
1819A | Mines Centre | Central |  | Modernization | Modernization->On Hold->Modernization | 2024 Q3 | CR | Magicell | 4.6 TSSR Approved |  | 2023-11-20 | 2024-01-04 |  | 2024-04-24 |  | Closed | 2024-04-29 | 2024-05-27 | E//Sumitra | 2024-05-27 | CelcomDigi_RAN_Magicell_TSS_Central_20231214 | DU00002860310 |  |  | 2025-03-12 | 2025-03-12 |  | In-Building System | 6m RT (Boom) + IBS | 6M | Add R8894E M1821x5+R8854 S2600x1, Dismantle R8882 S1800B(B6B)x2+R8862A S1800(B6A)x1+R8862A S2100(A6A)x4+R8862A S2600(A4A)x1 | 0 | 23
S01487 | S092A_S01487OD_CB_KGUSUKAN2 | Sabah |  | Decomm |  | 2024 Q3 | AD | Futong | 4.6 TSSR Approved |  | 2024-01-27 |  |  |  | 2024-03-21 |  | 2024-03-22 | 2024-04-24 | CD//Mohidi Jaan | 2024-03-24 | Celcom Digi_RAN-Futong-TSS-Sabah-20240204/0612Sabah-Futong-BOQ Template (template) | DU00002860311 |  |  |  |  | 2024-07-10 |  | TOWER
1840B | Putrajaya Marriott | Central |  | Decomm | Modernization->Decomm | 2024 Q3 | SY1 | Solusi | 4.6 TSSR Approved |  | 2024-01-10 | 2024-01-18 |  |  | 2024-09-18 |  | 2024-09-20 | 2025-03-07 | E//Sumitra | 2024-09-20 | BOQ CelcomDigi_RAN_Solusi_Standard PR TSS_Central_20240117 | DU00002860312 |  |  |  |  | 2025-01-23 | In-Building System | 3m RT (Boom) + IBS | 3.3
1847B | Putra Perdana 1 | Central |  | Modernization |  | 2024 Q3 | SH | Magicell | 4.6 TSSR Approved |  | 2024-01-09 | 2024-01-15 |  | 2024-04-29 |  | Closed | 2024-05-07 | 2024-05-08 | E//Razif | 2024-05-08 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240115 | DU00002860313 |  |  | 2024-06-19 | 2024-06-19 |  | Minimast | 3m RT (Minimast) | 6 | Add R9264M M1821 x1+A9732 M1821 x3,Dismantle R8894E M1821(A8A) x4 | 134 | 0
1849B | UPM1 (Celcom) | Central |  | Modernization |  | 2024 Q3 | SM | YPTT | 4.6 TSSR Approved |  | 2024-05-13 | 2024-05-16 |  | 2024-06-13 |  | Rectificating | 2024-06-24 | 2024-07-03 | E//Sumitra | 2024-07-03 | CelcomDigi_RAN_YPTT_TSS_Central_20240528 | DU00002860314 |  |  | 2024-10-10 | 2024-08-15 |  | Tower | Tower | 60M | Add R9264M M1821 x1+A9732 M1821 x3,Dismantle R8894E M1821(A8A) x4 | 123 | 0
Q00241 | Q129A_Q00241OD_KGSEMOP | Sarawak |  | Decomm |  | 2025 Q1 | SH | Magicell | 4.6 TSSR Approved |  | 2024-01-31 |  |  |  | 2024-02-17 |  | 2024-02-19 | 2024-03-21 | CD//John | 2024-03-01 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20240204 | DU00002860315 |  |  |  |  | 2025-10-24 |  | TOWER
1869B | KJS Kg Semarang(KJS) | Central |  | Modernization |  | 131 single site mocn | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-15 | 2024-01-16 |  | 2024-05-17 |  | Closed | 2024-05-21 | 2024-05-27 | E//Razif | 2024-05-27 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240116 | DU00002860316 |  |  | 2024-06-12 | 2024-06-12 |  | Tower | 60m 4 Legged Tower | 62M | Add R8862A S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3 | 2 | 0
1871B | Putrajaya MOF OD(AsiaSpace) | Central |  | Modernization |  | 2024 Q3 | CR | GTSB | 4.6 TSSR Approved |  | 2024-06-28 | 2024-07-03 |  | 2024-07-05 |  | Under Approval | 2024-07-09 | 2024-11-27 | E//Razif | 2024-11-27 | 0701Central-GTSB-BOQ Template (template) | DU00002860317 |  |  | 2024-08-12 | 2024-07-29 |  | Pole | 3m Bipod (RT) | 4m | Add R8862A S9000 x3+R8894E M1821 x1+R8862A S2601 x2+R8854 S2600 x1,Dismantle R8862A S2600(A4A) x3 | 0 | 3
1872B | UPM College | Central |  | Modernization |  | 2024 Q3 | SY1 | YPTT | 4.6 TSSR Approved |  | 2024-06-12 | 2024-06-13 |  | 2024-06-20 |  | Closed | 2024-06-24 | 2024-11-27 | E//Sumitra | 2024-11-27 | 0618Central-YPTT-BOQ Template (template) | DU00002860318 |  |  | 2024-08-01 | 2024-07-30 |  | Monople Tree | 45m Monopole Tree | 45 | Add R8862A S9000 x2+R9264H M901821 x1+R8862A S2601 x2+A9732 M1821 x2,Dismantle R8882 S2600(B4A) x2+R8894E M1821(A8A) x3 | 13 | 0
1874B | Fakulti Pendidikan UPM | Central |  | Modernization |  | 2024 Q3 | SY1 | YPTT | 4.6 TSSR Approved |  | 2024-06-12 | 2024-06-14 |  | 2024-06-24 |  | Closed | 2024-06-25 | 2024-07-03 | E//Sumitra | 2024-07-03 | 0618Central-YPTT-BOQ Template (template) | DU00002860319 |  |  | 2024-08-01 | 2024-07-30 |  | Monople Tree | 45m Monopole Tree | 45 | Add R9264M M1821 x1+R8862A S2601 x1+A9732 M1821 x2,Dismantle R8882 S2600(B4A) x1+R8894E M1821(A8A) x3 | 12 | 0
1896B | BEHRANG2020 | Northern |  | Modernization |  | 2024 Additional | AI | YPTT | 4.6 TSSR Approved |  | 2023-12-27 | 2023-12-27 |  | 2024-12-10 |  | Under Approval | 2024-12-16 | 2024-12-17 | E//Hazida | 2024-12-17 | Celcom Digi_RAN-YPTT-TSS-Northern-20231229-0049 | DU00002860320 |  |  | 2024-12-25 | 2024-12-25 |  | Tower | 45m 3 Legged Tower | 45m | Add R8852E S9000 x3+R8894E M1821 x1+R8854 S2600x1,Dismantle R8862A S2600(A4A)x1 | 0 | 3
1900B | Sunway Semenyih (KJS) | Central |  | Decomm | Modernization->On Hold->Decomm | 154 single site MOCN | SHA | YPTT | 4.6 TSSR Approved |  | 2024-01-30 | 2024-02-02 |  | 2024-06-12 |  | Under Approval | 2024-10-08 | 2024-12-18 | E//Sumitra | 2024-10-10 | SQ202411140060 | DU00002860321 |  |  |  |  | 2025-01-27 | Lampole | 20m Lampole | 20 | Add R8862A S9000x3+R8894E M1821x4+R8862A S2601x2,Dismantle R8882 S1800(B)x1+R8882 S1800B(B6B)x1+R8882 S2600(B4A)x2 | 0 | 2
1902B | Bdr Sg Long 3 | Central |  | Modernization |  | 2024 Q4 | AI | YPTT | 4.6 TSSR Approved |  | 2024-01-18 | 2024-02-21 |  | 2024-06-06 |  | Closed | 2024-06-06 | 2024-06-13 | E//Sumitra | 2024-06-13 | BOQ_Celcom Digi_RAN-YPTT-Standard PR TSS-20240202 | DU00002860322 |  |  | 2024-06-15 | 2024-06-14 |  | Tower | 45m Tower | 45 | Add R8852E S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8862A S2601(A6A) x1+R8894E M1821(A8A) x3+R9224E M1821(AAB) x1 | 23 | 0
1908B | Diamond Complex Bangi | Central |  | Modernization |  | 2024 Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2024-04-19 | 2024-04-22 |  | 2024-05-07 |  | Closed | 2024-05-13 | 2024-05-15 | E//Sumitra | 2024-05-15 | CelcomDigi_RAN_YPTT_TSS_Central_20240513 | DU00002860323 |  |  | 2024-06-26 | 2024-06-26 |  | H-bracket pole | 3m Bipod (RT) | 6 | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 13 | 0
1909B | Sek3 Tambahan Bangi | Central |  | Site Out (Modernization) | On hold->Decomm->Site Out->Site Out (Modernization) | 2024 Q3 | CR | GTSB | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2025-07-15 |  | 2025-07-02 |  |  | To be Submitted |  |  |  |  | SQ202506170074 | DU00002860324 |  |  |  |  | 2025-08-05 |  | 20m Monopole
A00842 | A041A_A00842OD_TMNLERISTA | Northern |  | Decomm |  | 2025 Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-12-20 |  |  |  | 2023-12-28 |  | 2024-01-03 | 2024-01-22 | CD//Rohizam | 2024-01-03 | Celcom Digi_RAN-GTSB-TSS-Northern-20231225-0080//SQ202501030229-gtsb | DU00002860325 |  |  |  |  | 2025-05-22 |  | MONOPOLE
S00099 | S101A_S00099OD_BABAH | Sabah |  | Decomm |  | 2024 Q3 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2023-11-07 |  |  |  | 2023-12-05 |  | 2024-03-23 | 2024-05-14 | CD//Mohidi Jaan | 2024-03-23 | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231206 | DU00002860326 |  |  |  |  | 2024-06-18 |  | TOWER
1956B | Apt Fasa 8 Precint 9 | Central |  | Decomm | Modernization->Decomm | 2024 Q3 | MA | Magicell | 4.6 TSSR Approved |  | 2023-12-29 | 2024-01-05 |  | 2024-04-22 | 2024-06-05 | Under Approval | 2024-06-05 |  | E//Nazrul | 2024-06-06 | 0704CD-Central-Magicell-BOQ Template (template) | DU00002860327 |  |  |  |  | 2025-01-27 | In-Building System | 3m RT (Wall Mounted Pole) | 2.5
Q01520 | Q117A_Q01520OD_BETONGNTS | Sarawak |  | Decomm |  | 2025 Q3 | ZB | Trintel | 4.6 TSSR Approved |  | 2024-02-19 |  |  |  | 2024-02-23 |  | 2024-02-23 | 2024-03-21 | CD//John | 2024-02-24 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240220/Celcom Digi_RAN-Trintel-Standard PR TSS DECOMM-Sarawak-20240314 | DU00002860328 |  |  |  |  | 2025-08-23 |  | BOOM
1975B | KG KERINCHI (REL) | Central |  | Modernization |  | 2024 Q2 |  | AllStar | 4.6 TSSR Approved |  | 2023-12-27 | 2024-01-16 |  | 2024-03-06 |  | Closed | 2024-03-13 | 2024-03-14 | E//Kok Keen | 2024-03-13 | BOQ CelcomDigi_RAN_AllStar_Standard PR TSS_Central_20240108 | DU00002860329 |  |  | 2024-03-12 | 2024-03-09 |  | Wall mount boom | 30m Minaret | 2 | Add R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3+R8862A S2600(A4A) x1 | 0 | 2
W01465 | W066G_W01465OD_MADRASAHNRLMUTTAQIN_GBK_SETIA | Central |  | Decomm |  | 2024 Q1 | SM | AllStar | 4.6 TSSR Approved |  | 2023-11-16 |  |  |  | 2023-11-29 |  | 2024-01-16 | 2024-02-15 | CD//Ali akaram | 2024-01-23 | CelcomDigi_RAN_AllStar_TSS_Central_20231119 | DU00002860330 |  |  |  |  | 2024-04-30 |  | LAMP_POLE
1992A | Jalan Liku | Central |  | Modernization |  | 2024 Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2023-12-21 | 2024-01-11 |  | 2024-01-16 |  | Closed | 2024-01-22 | 2024-02-05 | E//Kok Keen | 2024-02-05 | CelcomDigi_RAN_AllStar_TSS_Central_20231224 | DU00002860331 |  |  | 2024-05-28 | 2024-05-20 |  | In-Building System | 3m Boom (RT) | 6 | Add R8894E M1821 x4,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8840-U216 x3++ |  | 2
S01468 | S092A_S01468OD_CB_PARADISECAMP | Sabah |  | Decomm |  | 2024 Q3 | MS | Futong | 4.6 TSSR Approved |  | 2024-01-27 |  |  |  | 2024-03-21 |  | 2024-03-25 | 2024-05-24 | CD//Mohidi Jaan | 2024-03-26 | Celcom Digi_RAN-Futong-TSS-Sabah-20240204/0612Sabah-Futong-BOQ Template (template) | DU00002860332 |  |  |  |  | 2024-07-29 |  | MONOPOLE
S01467 | S092A_S01467OD_CB_KGTAMBULIAN | Sabah |  | Decomm |  | 2024 Q3 | MS | Futong | 4.6 TSSR Approved |  | 2024-01-27 |  |  |  | 2024-03-21 |  | 2024-03-25 | 2024-05-24 | CD//Mohidi Jaan | 2024-03-26 | Celcom Digi_RAN-Futong-TSS-Sabah-20240204/0612Sabah-Futong-BOQ Template (template) | DU00002860333 |  |  |  |  | 2024-06-18 |  | MONOPOLE
S01008 | S092A_S01008OD_CB_KGNAHABA | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2025-07-10 |  | 2025-07-14 |  | 2025-07-16 |  | 2025-08-06 | 2025-09-20 | E//Hannah | 2025-09-16 | SQ202506100836 - YPTT / SQ202507010450 - YPTT | DU00002860334 |  |  |  |  | 2025-09-11 |  | TOWER
2016B | Dunham Bush 2 - Bkt Angkat Kajang (MP) | Central |  | Modernization |  | 2024 Q4 | SH | Magicell | 4.6 TSSR Approved |  | 2023-11-30 | 2023-12-22 |  | 2024-05-09 |  | Closed | 2024-09-27 | 2024-09-30 | E//Sumitra | 2024-09-30 | CelcomDigi_RAN_Magicell_TSS_Central_20231214 | DU00002860335 |  |  | 2024-09-28 | 2024-09-05 |  | Lampole | 24m Lampole | 30 | Add R8894E M1821 x3 | 0 | 123
2023A | Centerpoint BU | Central |  | Modernization |  | 2024 Q3 | CR | GCI | 4.6 TSSR Approved |  | 2024-01-10 | 2024-04-24 |  | 2024-04-26 |  | Closed | 2024-04-29 | 2024-04-30 | E//Kok Keen | 2024-04-29 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240115 | DU00002860336 |  |  | 2024-05-24 | 2024-05-18 |  | Portables BTS | 8m RT (Boom) + IBS |  | Add R9224E M1821 x4+R8854 S2600 x1,Dismantle R8882-GUL1812 x4+R8862A S2100(A6A) x1+R8854D S2100(A4A) x3+R8882-L268 x1 | 0 | 1
2024A | PUAS Bdr Mahkota Cheras | Central |  | Modernization |  | 2024 Q4 | SY1 | YPTT | 4.6 TSSR Approved |  | 2024-04-30 | 2024-05-06 |  | 2024-05-20 |  | Closed | 2024-05-21 | 2024-05-27 | E//Sumitra | 2024-05-27 | CelcomDigi_RAN_YPTT_TSS_Central_20240513 | DU00002860337 |  |  | 2024-06-11 | 2024-06-08 |  | Monopole | 30m Monopole | 30m | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 23 | 0
W01437 | W066H_W01437OD_WANGSAJAYA_WANGSAMAJU | Central |  | Decomm |  | 2024 Q1 | SS | YPTT | 4.6 TSSR Approved |  | 2023-12-07 |  |  |  | 2023-12-14 |  | 2024-01-05 | 2024-01-22 | CD//Sapian | 2024-01-10 | CelcomDigi_RAN_YPTT_TSS_Central_20231224 | DU00002860338 |  |  |  |  | 2024-07-29 |  | LAMP_POLE
2049B | Taman Mas Sepang(Celcom) | Central |  | Modernization |  | 2024 Q3 | MA | Magicell | 4.6 TSSR Approved |  | 2023-12-05 | 2023-12-18 |  | 2024-04-22 |  | Closed | 2024-04-26 | 2024-05-06 | E//Razif | 2024-05-06 | CelcomDigi_RAN_Magicell_TSS_Central_20231214 | DU00002860339 |  |  | 2024-06-12 | 2024-06-08 |  | Tower | Tower | 30m | Add R8894E M1821 x2,Dismantle | 0 | 13
2055A | Puchong Prima | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-09 | 2024-01-18 |  | 2024-04-29 |  | Closed | 2024-05-06 | 2024-05-07 | E//Razif | 2024-05-06 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240110 | DU00002860340 |  |  | 2024-06-25 | 2024-06-22 |  | H-bracket pole | 3m Boom (RT) | 6 | Add R8894E M1821 x1,Dismantle R8854 S2600(A4A) x1 | 0 | 23
2057A | LKW Cyberjaya (KJS) | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-13 | 2024-01-15 |  | 2024-04-22 |  | Closed | 2024-04-25 | 2024-04-29 | E//Razif | 2024-04-26 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240115 | DU00002860341 |  |  | 2024-07-05 | 2024-06-21 |  | Monople Tree | 30m Monopole Tree | 30M | Add R9264M M1821 x4,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x2 | 0 | 0
S00304 | S108A_S00304OD_CB_TMTAMBUNAN | Sabah | 7279K | Swap | Decomm->Swap | 131 single site mocn | MS | Seri Pancar | 4.6 TSSR Approved |  | 2024-10-04 | 2024-10-08 |  | 2024-10-10 |  | Under Approval | 2024-10-11 | 2024-10-11 | CD//Mohidi Jaan | 2024-10-11 | 0930CD-Sabah-SeriPancar-BOQ Template(new contract) | DU00002860342 |  |  | 2026-03-06 | 2025-12-15 |  | Tower | TOWER | 76 | Add R9264H M901821 x3+R8862A S2601 x2+R8854 S2600x1,Dismantle | 0 | 1
Q00380 | Q129A_Q00380OD_SPGKJD | Sarawak |  | Decomm |  | 2025 Q2 | ZB | Trintel | 4.6 TSSR Approved |  | 2023-12-15 |  |  |  | 2024-01-15 |  | 2024-01-26 | 2024-03-21 | CD//John | 2024-01-29 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231214 | DU00002860343 |  |  |  |  | 2025-05-27 |  | TOWER
Q01397 | Q137A_Q01397OD_JLNCENTURY | Sarawak |  | Decomm |  | 2024 Q4(single site MOCN)-L21 SSM | SH | Trintel | 4.6 TSSR Approved |  | 2023-12-07 |  |  |  | 2023-12-12 |  | 2023-12-13 | 2023-12-20 | CD//John | 2023-12-13 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231207 | DU00002860344 |  |  |  |  | 2024-12-06 |  | RAPOLE
2210A | Jln Stonor | Central |  | Modernization | Decomm->On Hold->Modernization | 2024 Q2 | SS | Magicell | 4.6 TSSR Approved |  | 2024-02-08 | 2024-02-16 |  | 2024-02-21 |  | Closed | 2024-02-22 | 2024-02-27 | E//Sumitra | 2024-02-27 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240218 | DU00002860345 |  |  | 2025-01-08 | 2025-01-06 |  | In-Building System | 3m Bipod (RT) | 3 | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x3+R9224E M1821(AAB) x1
2232A | Aked Esplanade Commercial | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-10-23 | 2023-10-27 |  | 2024-03-22 |  | Closed | 2024-03-25 | 2024-04-01 | E//Sumitra | 2024-04-01 | CelcomDigi_RAN_GTSB_TSS_Central_20231025 | DU00002860346 |  |  | 2024-06-30 | 2024-06-25 |  | Unipole | 3m Boom (RT) | 6m | Add R9264M M1821 x3,Dismantle R8882 S1800(B) x3++R8881 S2100 x3+ | 0 | 0
2248A | Alam Damai Cheras 1 | Central |  | Modernization |  | 2024 Q3 | AI | Magicell | 4.6 TSSR Approved |  | 2024-08-15 | 2024-08-20 |  | 2024-08-26 |  | Closed | 2024-12-05 | 2024-12-10 | E//Sumitra | 2024-12-09 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240510 | DU00002860347 |  |  | 2024-11-26 | 2024-11-25 |  | In-Building System | 3m Boom (RT) | S1 = 6m, S2 = 6m, S3 = 6m | Add R8862A S9000x4+R8862A S2601x1+R8894E M1821x3+A9732 M1821x2, Dismantle R8882-GUL1812x2+R8862A S1800(B6A)x1+R8854D S2100(A4A)x3+ | 14 | 3
Q00406 | Q117A_Q00406OD_BETONG | Sarawak |  | Decomm |  | 2025 Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2024-02-16 |  |  |  | 2024-02-23 |  | 2024-02-23 | 2024-12-13 | CD//John | 2024-04-03 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240220/Celcom Digi_RAN-Trintel-Standard PR TSS DECOMM-Sarawak-20240314 | DU00002860348 |  |  |  |  | 2025-08-25 |  | TOWER
Q00972 | Q117A_Q00972OD_T3_KGTGASSAM | Sarawak |  | Decomm |  | 2024 Q4(single site MOCN)-L21 SSM | ZB | Trintel | 4.6 TSSR Approved |  | 2024-01-22 |  |  |  | 2024-02-19 |  | 2024-02-22 | 2024-03-21 | CD//John | 2024-02-23 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20240124/Celcom Digi_RAN-Trintel-Standard PR TSS DECOMM-Sarawak-20240314 | DU00002860349 |  |  |  |  | 2024-12-06 |  | TOWER
2260A | Section 4 wangsa maju watertank | Central |  | Modernization |  | 2024 Q1 | IE | Ascentrack | 4.6 TSSR Approved |  | 2023-11-20 | 2023-11-24 |  | 2023-12-29 |  | Closed | 2024-01-03 | 2024-01-03 | E//Kok Keen | 2024-01-03 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231119 | DU00002860350 |  |  | 2024-03-01 | 2024-02-27 |  | Lampole | 24m Lampole | 23m | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle R8862A S2600(A4A) x1 |  | 3
Q00998 | Q143A_Q00998OD_T3_SKRANG | Sarawak |  | Decomm |  | 2025 Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2024-01-06 |  |  |  | 2024-01-19 |  | 2024-01-29 | 2024-02-09 | CD//John | 2024-01-29 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240109/Celcom Digi_RAN-Trintel-Standard PR TSS DECOMM-Sarawak-20240314 | DU00002860351 |  |  |  |  | 2025-09-26 |  | TOWER
Q00996 | CBKGSENGKUANG | Sarawak |  | Decomm |  | 2025 Q3 | SH | Magicell | 4.6 TSSR Approved |  | 2024-01-16 |  |  |  | 2024-01-17 |  | 2024-01-29 | 2024-09-05 | CD//John | 2024-01-29 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20240204/Celcom Digi_RAN-Magicell-Standard PR TSS-Sarawak-20240221 | DU00002860352 |  |  |  |  | 2025-10-24 |  | TOWER
Q00995 | Q143A_Q00995OD_CB_NGKLASSEN | Sarawak |  | Decomm |  | 2025 Q3 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-11-28 |  |  |  | 2023-12-05 |  | 2023-12-12 | 2023-12-20 | CD//John | 2023-12-13 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231206 | DU00002860353 |  |  |  |  | 2025-08-21 |  | TOWER
2268A | Bkt Mewah ShopLot Kajang | Central |  | Modernization |  | 2024 Q4 | BY | YPTT | 4.6 TSSR Approved |  | 2024-04-16 | 2024-06-05 |  | 2024-06-17 |  | Under Approval | 2024-06-25 | 2024-07-10 | E//Sumitra | 2024-07-10 | CelcomDigi_RAN_YPTT_TSS_Central_20240513 | DU00002860354 |  |  | 2024-09-13 | 2024-09-05 |  | In-Building System | 3m Bipod (RT) | 6 | Add R8852E S9000 x4+R8894E M1821 x6+R8862A S2601 x2+R8854 S2600 x2,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3+R8882 S2600(B4A) x3 | 0 | 12
2281A | Kg Balokong 2 | Central |  | Modernization |  | 2024 Q3 | MA | Magicell | 4.6 TSSR Approved |  | 2024-03-12 | 2024-03-20 |  | 2024-04-19 |  | Closed | 2024-04-25 | 2024-04-30 | E//Sumitra | 2024-04-30 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240316 | DU00002860355 |  |  | 2024-09-19 | 2024-07-27 |  | In-Building System | 3m RT (Minimast) | 5M | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882 S1800(B) x3+R8862A S2100(A6A) x3 | 0 | 0
S01667 | S101A_S01667OD_KGDUNGKAHANG | Sabah |  | Decomm |  | 2024 Q3 | MS | NR services | 4.6 TSSR Approved |  | 2024-03-25 |  |  |  | 2024-03-25 |  | 2024-03-26 | 2024-06-28 | CD//Mohidi Jaan | 2024-03-26 | Celcom Digi_RAN-NR Services-TSS-Sabah-20240329 | DU00002860356 |  |  |  |  | 2024-07-15 |  | TOWER
Q00697 | Q122A_Q00697OD_MACHAN | Sarawak |  | Decomm |  | 2025 Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2024-01-02 |  |  |  | 2024-01-05 |  | 2024-02-27 | 2024-08-01 | CD//John | 2024-04-03 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240109 | DU00002860357 |  |  |  |  | 2025-05-22 |  | TOWER
2316A | Jln AU 2A | Central |  | Modernization |  | 2024 Q1 | MA | GCI | 4.6 TSSR Approved |  | 2023-11-09 | 2023-11-16 |  | 2024-01-02 |  | Closed | 2024-01-03 | 2024-01-18 | E//Sumitra | 2024-01-17 | CelcomDigi_RAN_GCI_TSS_Central_20231113 | DU00002860358 |  |  | 2024-01-21 | 2024-01-11 |  | Lampole | 20m Lampole | 24 | Add R8862A S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882-GUL1812 x3+R8882-L268 x1 |  | 3
2317A | Kg Baru Ampang 2 | Central |  | Modernization |  | 2024 Q2 | SS | YPTT | 4.6 TSSR Approved |  | 2023-10-21 | 2023-10-27 |  | 2024-03-05 |  | Rectificating | 2024-03-06 | 2024-07-10 | E//Sumitra | 2024-07-10 | CelcomDigi_RAN_YPTT_TSS_Central_20231025 | DU00002860359 |  |  | 2024-04-18 | 2024-04-18 |  | In-Building System | 3m Boom (RT) | 4 | Add R9264M M1821 x1+A9732 M1821 x3,Dismantle R8882 S1800(B) x3+R8862A S1800(B6A) x3+R8854D S2100(A4A) x6+R8862A S2601(A6A) x2 | 134 | 0
2328A | Psiaran Impian Cheras | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-05 | 2024-01-18 |  | 2024-04-26 |  | Closed | 2024-04-30 | 2024-05-10 | E//Sumitra | 2024-05-09 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240108 | DU00002860360 |  |  | 2024-06-23 | 2024-06-23 |  | Wall mount boom | 3m Boom (RT) | 3 | Add R8894E M1821 x1,Dismantle | 0 | 2
2389A | BU 11 LP | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-15 | 2023-11-20 |  | 2024-03-21 |  | Closed | 2024-03-21 | 2024-03-26 | E//Kok Keen | 2024-03-25 | CelcomDigi_RAN_GTSB_TSS_Central_20231116 | DU00002860361 |  |  | 2024-05-02 | 2024-04-29 |  | Lampole | 24m Lampole | 24m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
2390A | Petronas F1 Billboard (REL) | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-04-26 | 2024-05-02 |  | 2024-05-06 |  | Closed | 2024-05-06 | 2024-05-07 | E//Kok Keen | 2024-05-07 | CelcomDigi_RAN_GTSB_TSS_Central_20240509 | DU00002860362 |  |  | 2024-05-22 | 2024-05-18 |  | BillBoard | Billboard | 35M | Add R9264H M901821 x4,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x2 | 0 | 0
2391A | BU 12 LP | Central |  | Modernization |  | 2024 Q3 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-11-16 | 2023-11-29 |  | 2024-04-08 |  | Closed | 2024-04-15 | 2024-04-16 | E//Kok Keen | 2024-04-15 | CelcomDigi_RAN_GTSB_TSS_20231119 | DU00002860363 |  |  | 2024-05-09 | 2024-05-07 |  | Lampole | 20m Lampole | 20 | Add R8862A S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8882-GUL1812 x2+R8862A S2100(A6A) x3 | 3 | 0
2416A | KJS Bukit Unggul | Central |  | Modernization |  | 2024 Additional | AI | GTSB | 4.6 TSSR Approved |  | 2024-04-23 | 2024-06-20 |  | 2024-06-28 |  | Closed | 2024-07-02 | 2024-07-19 | E//Razif | 2024-07-19 | CelcomDigi_RAN_GTSB_TSS_Central_20240509 | DU00002860364 |  |  | 2024-12-08 | 2024-12-05 |  | Tower | Tower | 60 | Add R8862A S9000 x1+R9264H M901821 x2+R8862A S2601 x3+A9732 M1821 x1,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3+R8882 S2600(B4A) x3 | 2 | 0
S01505 | S092A_S01505OD_CB_KGPIRASAN | Sabah |  | Decomm |  | 2024 Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2024-01-19 |  |  |  | 2024-01-29 |  | 2024-03-21 | 2024-08-09 | CD//Mohidi Jaan | 2024-03-21 | Celcom Digi_RAN-YPTT-TSS-Sabah-20240124/0612Sabah-YPTT-BOQ Template (template) | DU00002860365 |  |  |  |  | 2024-07-04 |  | TOWER
S01503 | S092A_S01503OD_CB_KGSUANGPUNGGUR | Sabah |  | Decomm |  | 2024 Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2024-01-19 |  |  |  | 2024-01-24 |  | 2024-03-21 | 2024-08-16 | CD//Mohidi Jaan | 2024-03-21 | Celcom Digi_RAN-YPTT-TSS-Sabah-20240124/0612Sabah-YPTT-BOQ Template (template) | DU00002860366 |  |  |  |  | 2024-07-11 |  | TOWER
S01476 | S092A_S01476OD_CB_SKKELAWAT | Sabah |  | Decomm |  | 2024 Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2024-01-19 |  |  |  | 2024-01-25 |  | 2024-03-22 | 2024-05-14 | CD//Mohidi Jaan | 2024-03-22 | Celcom Digi_RAN-YPTT-TSS-Sabah-20240124/0612Sabah-YPTT-BOQ Template (template) | DU00002860367 |  |  |  |  | 2024-06-24 |  | TOWER
S01477 | S092A_S01477OD_KUALAABAIUPPER | Sabah |  | Decomm |  | 2024 Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2024-01-19 |  |  |  | 2024-01-24 |  | 2024-03-22 | 2024-05-14 | CD//Mohidi Jaan | 2024-03-22 | Celcom Digi_RAN-YPTT-TSS-Sabah-20240124/0612Sabah-YPTT-BOQ Template (template) | DU00002860368 |  |  |  |  | 2024-06-20 |  | TOWER
S01481 | S092A_S01481OD_CB_KOMPLEXSUKANKB | Sabah |  | Decomm |  | 2024 Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2024-01-22 |  |  |  | 2024-01-29 |  | 2024-03-22 | 2024-05-14 | CD//Mohidi Jaan | 2024-03-22 | Celcom Digi_RAN-YPTT-TSS-Sabah-20240124/0612Sabah-YPTT-BOQ Template (template) | DU00002860369 |  |  |  |  | 2024-07-09 |  | TOWER
S01504 | S092A_S01504OD_CB_KGSIASAIKB | Sabah |  | Decomm |  | 2024 Q3 | MS | Futong | 4.6 TSSR Approved |  | 2024-02-05 |  |  |  | 2024-02-06 |  | 2024-03-22 | 2024-05-14 | CD//Mohidi Jaan | 2024-03-22 | Celcom Digi_RAN-Futong-Standard PR TSS-Sabah-20240213/0612Sabah-Futong-BOQ Template (template) | DU00002860370 |  |  |  |  | 2024-07-02 |  | RAPOLE
S00988 | S099A_S00988OD_KGMAMPISAS | Sabah |  | Decomm |  | 2025 Q2 | AD | YPTT | 4.6 TSSR Approved |  | 2025-01-15 |  | 2025-06-04 |  | 2025-06-05 |  | 2025-06-06 | 2025-10-13 | E//Hannah | 2025-09-23 | SQ202501030034 - YPTT / SQ202501070337 - YPTT | DU00002860371 |  |  |  |  | 2025-08-11 |  | TOWER
2441A | Kg Padang Balang (Asiaspace) | Central |  | Modernization |  | 2024 Q1 | SS | Magicell | 4.6 TSSR Approved |  | 2023-11-11 | 2023-11-20 |  | 2024-01-02 |  | Closed | 2024-01-03 | 2024-01-04 | E//Kok Keen | 2024-01-03 | CelcomDigi_RAN_Magicell_TSS_Central_20231113 | DU00002860372 |  |  | 2024-03-08 | 2024-02-24 |  | Monopole | 45m Monopole | 45 | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 13
S01589 | S108A_S01589OD_KGTIMBOU | Sabah |  | Decomm |  | 2025 Q2 | AD | YPTT | 4.6 TSSR Approved |  | 2025-01-15 |  | 2025-01-20 |  | 2025-02-12 | To be Submitted | 2025-02-22 |  | CD//Sharidah | 2025-02-24 | SQ202501030034 - YPTT / SQ202501070337 - YPTT | DU00002860373 |  |  |  |  | 2025-10-06 |  | TOWER
2462A | Barefield Semenyih(Celcom) | Central |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q1 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002860374 | [6 empty] | 60m 4 Legged Tower |  |  |  | 123
S00488 | S105B_S00488OD_RANCANGSGMANILA | Sabah |  | Decomm |  | 2025 Q2 | AD | Futong | 4.6 TSSR Approved |  | 2024-04-20 |  |  |  | 2024-04-25 |  | 2024-05-10 | 2024-09-26 | CD//Mohidi Jaan | 2024-05-10 | Celcom Digi_RAN-Futong-Standard PR TSS-Sabah-20240503 / SQ202501070242 - Futong | DU00002860375 |  |  |  |  | 2024-07-29 |  | TOWER
B00973 | B061R_B00973OD_PR_TMKELANAJAYA | Central |  | Decomm |  | 2024 Q1 | SHA | GCI | 4.6 TSSR Approved |  | 2024-07-08 |  | 2024-07-15 |  | 2024-07-17 |  | 2024-07-18 | 2024-09-03 | CD//Norhaliza | 2024-08-07 | 0918CD-Central-GCI-BOQ Template (old contract) | DU00002860376 |  |  |  |  | 2024-08-13 |  | BOOM
Q00562 | Q117A_Q00562OD_PKNPUSA | Sarawak |  | Decomm |  | 2024 | SH | Trintel | 4.6 TSSR Approved |  | 2024-02-19 |  |  |  | 2024-02-23 |  | 2024-02-23 | 2024-08-09 | CD//John | 2024-04-03 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240220 | DU00002860377 |  |  |  |  | 2024-12-27 |  | TOWER
Q01878 | Q143A_Q01878OD_TMNMAYFAIR2 | Sarawak |  | Decomm |  | 2025 Q3 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-12-05 |  |  |  | 2023-12-08 |  | 2023-12-11 | 2023-12-20 | CD//John | 2023-12-13 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231206 | DU00002860378 |  |  |  |  | 2025-05-28 |  | RAPOLE
S01207 | S101A_S01207OD_KGHUNGAB | Sabah |  | Decomm |  | 2024 Q3 | MS | NR services | 4.6 TSSR Approved |  | 2024-03-25 |  |  |  | 2024-03-25 |  | 2024-03-26 | 2024-06-28 | CD//Mohidi Jaan | 2024-03-26 | Celcom Digi_RAN-NR Services-TSS-Sabah-20240329 | DU00002860379 |  |  |  |  | 2024-06-12 |  | AESTHETIC MONOPOLE
W00048 | W066J_W00048OD_LRTDATOKERAMAT | Central |  | Decomm |  | 2024 Q1 | AD | GCI | 4.6 TSSR Approved |  | 2025-04-24 |  | 2025-06-10 |  | 2025-06-12 |  | 2025-06-23 | 2025-07-14 | E//Ali | 2025-06-24 | 0924CD-Central-CCSMY-BOQ Template(new contract) | DU00002860380 |  |  |  |  | 2025-05-21 |  | BOOM
7088A | Modular BTS Labuan Airport | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2025 Q1 | AD | Datasco | 4.6 TSSR Approved |  | 2024-05-23 | 2024-06-12 |  | 2025-01-15 |  | Under Approval | 2025-01-17 | 2025-02-18 | E//Hannah | 2025-05-20 | 0920CD-Sabah-Datasco-BOQ Template (old contract) | DU00002860381 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed | 2025-05-16 | 2025-05-03 |  | Tower | Tower | 35 | Add R8852E S9000x3+R9264M M1821x2+R8862A S2601x2+R8854 S2600x1+A9732 M1821x1, Dismantle R8882-GUL1812x3+R8882 S2600(B4A)x3+R8894E M1821(A8A)x3 | 1 | 3
7083A | Global Hotel | Sabah |  | Modernization |  | 2025 Q1 | AD | Datasco | 4.6 TSSR Approved |  | 2024-05-28 | 2024-06-06 |  | 2025-01-12 |  | Rectificating | 2025-01-13 | 2025-02-18 | E//Hannah | 2025-05-18 | 0920CD-Sabah-Datasco-BOQ Template (old contract) | DU00002860382 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed | 2025-05-11 | 2025-03-21 |  | Wall mount boom | 3m Boom (RT) | 3m, 5m | Add R8852E S9000x3+R9264M M1821x2+A9732 M1821x1, Dismantle R8894E M1821(A8A)x3 | 1 | 0
S00682 | S101A_S00682OD_BEVERLYPARK | Sabah |  | Decomm |  | 2024 Q3 | MS | NR services | 4.6 TSSR Approved |  | 2024-03-25 |  |  |  | 2024-03-25 |  | 2024-03-29 | 2024-06-28 | CD//Mohidi Jaan | 2024-04-15 | Celcom Digi_RAN-NR Services-TSS-Sabah-20240329 | DU00002860383 |  |  |  |  | 2024-06-24 |  | LAMP_POLE
2591A | Mutiara Barat | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002860384 | [6 empty] | 3m Bipod (RT) |  |  |  | 2
Q02094 | Q117A_Q02094OD_BELADIN2 | Sarawak |  | Decomm |  | 2024 Q4(single site MOCN)-L21 SSM | SH | Magicell | 4.6 TSSR Approved |  | 2024-06-12 |  | 2024-07-25 |  | 2024-07-03 |  | 2024-07-19 | 2024-09-05 | CD//John | 2024-07-24 | Celcom Digi_RAN-Magicell-Standard PR TSS-Sarawak-20240221 | DU00002860385 |  |  |  |  | 2024-12-06 |  | TOWER
4343D | Puncak Iskandar Seri Iskandar | Northern |  | Modernization |  | 2024 Q2 | BY | CCSMY | 4.6 TSSR Approved | ¦ 0306 - TSSR Approved ¦ 0228 - Listed for solution change, pending confirmed solution ¦ 0221 - RF Izzat: Please relo to higher location. ¦ 0206 - fup done to Izzat/Khai ¦ 0131 - BY followed up with RF ¦ 0126 - Li Jie fwd to Ariffin ¦ 0124 - RF Hazida: Based on TSSR, pair site antenna height at 27m compared to anchor site is 25m. suggest to relocate to 27m for better coverage as this is the only site serving Puncak Iskandar area. | 2024-01-07 | 2024-01-15 |  | 2024-01-19 |  | Closed | 2024-03-05 | 2024-03-06 | E//Hazida | 2024-03-06 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240108-0084 | DU00002860386 |  |  | 2024-04-03 | 2024-03-29 |  | Lampole | 30m Lampole | 31m | Add R8852E S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8862A S2600(A4A) x1+R8892N M1821(BAB) x3 | 0 | 3
W01485 | W066G_W01485OD_JLNGOMBAKSEJAHTERA | Central |  | Decomm |  | 2024 Q1 | CR | GCI | 4.6 TSSR Approved |  | 2023-11-10 |  |  |  | 2023-11-20 |  | 2023-11-20 | 2025-03-14 | CD//Sapian | 2023-11-28 | CelcomDigi_RAN_GCI_TSS_Central_20231113 | DU00002860387 |  |  |  |  | 2024-06-13 |  | LAMP_POLE
7053C | Taman Warisan LD | Sabah |  | Modernization |  | 2024 Q3(single site MOCN) | SHA | GTSB | 4.6 TSSR Approved |  | 2023-10-26 | 2023-10-25 |  | 2024-07-08 |  | Under Approval | 2024-07-10 | 2024-07-19 | E//Hannah | 2024-07-19 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231028 | DU00002860388 |  |  | 2024-10-08 | 2024-08-27 |  | Monopole | 30m Monopole | 30 | Add R8862A S9000 x3+A9732 M1821 x3,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x4 | 123 | 0
2657B | The Wharf RT | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002860389 | [6 empty] | 3m Boom (RT) |  |  |  | 123
2690A | IMU Bukit Jalil | Central |  | Modernization |  | 2024 Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2023-12-14 | 2023-12-20 |  | 2024-04-02 |  | Closed | 2024-04-03 | 2024-04-15 | E//Sumitra | 2024-04-09 | CelcomDigi_RAN_Magicell_TSS_Central_20231215 | DU00002860390 |  |  | 2024-06-25 | 2024-06-24 |  | BillBoard | 24m Lampole | 3 | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle R8882 S2600(B4A) x1 | 0 | 3
2719B | Tmn Sepakat BBB | Central |  | Modernization |  | 2024 Q4 | CR | Magicell | 4.6 TSSR Approved |  | 2023-12-28 | 2024-01-05 |  | 2024-04-16 |  | Closed | 2024-04-17 | 2024-05-27 | E//Sumitra | 2024-05-27 | CelcomDigi_RAN_Magicell_TSS_Central_20231230 | DU00002860391 |  |  | 2024-08-22 | 2024-08-19 |  | In-Building System | 3m Boom (RT) | 6 | Add R8852E S9000 x3+A9732 M1821 x3,Dismantle R8882 S1800(B) x3+R8862A S1800(B6A) x1+R8854D S2100(A4A) x4+R8862A S2600(A4A) x1 | 123 | 0
2726B | Kg Sri Aman Berkat MP | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002860392 | [6 empty] | 30m Monopole |  |  | 2
2741A | Tmn Cheras Mas | Central |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | CR | GCI | 4.6 TSSR Approved |  | 2024-01-16 | 2024-01-16 |  | 2024-05-15 |  | Under Approval | 2024-09-27 | 2024-09-30 | E//Sumitra | 2024-09-30 | CelcomDigi_RAN_GCI_TSS_Central_20240124 | DU00002860393 |  |  | 2024-11-18 | 2024-11-15 |  | Monopole | 30m Monopole | 30 | Add R8852E S9000 x3+A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123 | 0
K00555 | K006B_K00555OD_TMNSRIAMAN | Northern |  | Decomm |  | 2024 Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-12-06 |  |  |  | 2023-12-21 |  | 2023-12-27 | 2024-01-22 | CD//Rohizam | 2024-01-02 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231207-0078/0612Northern-CCSMY-BOQ Template (template) | DU00002860394 |  |  |  |  | 2024-05-14 |  | MINARET | 17m
2783A | PUASSalakSelatan(AsiaSpace) | Central |  | Modernization |  | 2024 Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2024-01-08 | 2024-02-19 |  | 2024-04-02 |  | Closed | 2024-04-02 | 2024-04-15 | E//Sumitra | 2024-04-09 | CelcomDigi_RAN_Allstar_TSS_Central_20240124 | DU00002860395 |  |  | 2024-04-30 | 2024-04-19 |  |  | 30m Monopole | 30 | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle R8882 S2600(B4A) x1 | 0 | 2
2786A | TM Tower Federal Highway | Central |  | Modernization |  | 2024 Q3 | CR | CCSMY | 4.6 TSSR Approved |  | 2024-05-08 | 2024-05-10 |  | 2024-05-11 |  | Closed | 2024-05-11 | 2024-05-13 | E//Kok Keen | 2024-05-13 | CelcomDigi_RAN_CCSMY_TSS_Central_20240513 | DU00002860396 |  |  | 2024-07-19 | 2024-07-16 |  | Tower | Tower | 62m | Add R8862A S9000 x3+R8894E M1821 x1+R8854 S2600 x1,Dismantle R8862A S2600(A4A) x1 | 0 | 1
2945A | JALAN 3_27A | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q1 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002860397 | [6 empty] | 3m Bipod (RT) |  |  | 123
R00089 | R001A_R00089OD_FELDA_CHUPING_2 | Northern |  | Decomm |  | 2025 Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-12-06 |  |  |  | 2023-12-21 |  | 2023-12-28 | 2024-01-22 | CD//Rohizam | 2024-01-02 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231207-0078//SQ202501030037 | DU00002860398 |  |  |  |  | 2025-05-19 |  | TOWER
4194C | Kg Mata Tok Embin | Northern |  | Modernization |  | 2024 Q2 | BY | CCSMY | 4.6 TSSR Approved | ¦ 0228 - Listed for solution change, pending confirmed solution | 2023-12-21 | 2023-12-22 |  | 2024-03-11 |  | Closed | 2024-03-05 | 2024-03-07 | E//Ajay | 2024-03-06 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231225-0082 | DU00002860399 |  |  | 2024-03-18 | 2024-03-13 |  | Monopole | 3m Bipod (RT) | 45m | Add R8852E S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 | 13 | 0
3020A | SEK 9 TMN LKS PKNS | Central |  | Modernization |  | 2024 Q3 | SH | YPTT | 4.6 TSSR Approved |  | 2024-04-19 | 2024-04-25 |  | 2024-05-03 |  | Closed | 2024-05-06 | 2024-05-14 | E//Kok Keen | 2024-05-14 | CelcomDigi_RAN_YPTT_TSS_Central_20240513 | DU00002860400 |  |  | 2024-09-11 | 2024-09-06 |  | In-Building System | 3m Boom (RT) | 6 | Add R8862A S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8854D S2100(A4A) x4+R8862A S2601(A6A) x1 | 1 | 0
3083A | Taman P.Ramlee (REL) | Central |  | Modernization |  | 2024 Q1 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-02-03 | 2024-02-21 |  | 2024-03-05 |  | Closed | 2024-03-07 | 2024-03-07 | E//Kok Keen | 2024-03-07 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240212 | DU00002860401 |  |  | 2024-04-21 | 2024-04-16 |  | Wall mount boom | 30m Minaret | 20m | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3
W00652 | W066U_W00652OD_1SENTRALOD | Central |  | Decomm | Decomm->On Hold->Decomm | 2024 Q2 | SS | YPTT | 4.6 TSSR Approved |  | 2024-02-29 |  |  |  | 2024-03-01 |  | 2024-03-05 | 2024-07-19 | CD//Norhaliza | 2024-06-10 | BOQ_Celcom Digi_RAN-YPTT-Standard PR TSS-20240303 | DU00002860402 |  |  |  |  | 2024-09-11 |  | BOOM
3240A | Lorong Ikan Emas | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002860403 | [6 empty] | Tower |  |  | 12
3249A | Cheras Perdana 2 | Central |  | Modernization |  | 2024 Q4 | MA | Solusi | 4.6 TSSR Approved |  | 2024-01-09 | 2024-01-16 |  | 2024-05-27 |  | Closed | 2024-06-05 | 2024-06-12 | E//Sumitra | 2024-06-11 | BOQ CelcomDigi_RAN_Solusi_Standard PR TSS_Central_20240110 | DU00002860404 |  |  | 2024-06-22 | 2024-06-22 |  | In-Building System | 3m Boom (RT) | 7M | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle R8882 S2600(B4A) x1 | 0 | 1
3262A | BGN_LALANG | Central |  | Modernization |  | 2024 Additional | SY1 | YPTT | 4.6 TSSR Approved |  | 2024-05-17 | 2024-05-20 |  | 2024-12-02 |  | Rectificating | 2024-12-04 | 2024-12-05 | E//Razif | 2024-12-05 | CelcomDigi_RAN_YPTT_TSS_Central_20240528 | DU00002860405 |  |  | 2024-12-16 | 2024-12-16 |  | Tower | Tower | 60 | Add R8852E S9000 x3+R8894E M1821x1+R8862A S2601x2+R8854 S2600 x1,Dismantle R8862A S9000(A6A) x3+R8862A S2600(A4A) x3 | 0 | 1
3264A | DESA_PANDAN21 | Central |  | Modernization | Modernization->Site Out->Modernization | 2024 Q2 | AI | GTSB | 4.6 TSSR Approved | AAU Cannot Install-S123 MM change to BI¦Space constraint | 2023-11-22 | 2023-11-24 |  | 2024-03-05 |  | Closed | 2024-03-14 | 2024-03-21 | E//Sumitra | 2025-07-16 | CelcomDigi_RAN_GTSB_TSS_Central_20231126 | DU00002860406 | Remarks: Solution TSSR/BOM Changed |  | 2025-08-28 | 2025-08-21 |  | H-bracket pole | 3m Bipod (RT) | 7m | Add R8862A S9000x3+R8894E M1821x6+R8854 S2600x3, Dismantle R8882-GUL1812x3+R8862A S1800(B6A)x1+R8862A S2100(A6A)x3+R8862A S2600(A4A)x3 | 0 | 0
3288A | Parcel E Outdoor | Central |  | Decomm | Modernization->Decomm | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2025-02-20 |  | 2025-04-18 |  | 2025-04-21 |  | 2025-04-28 | 2025-10-01 | E//Sumitra | 2025-04-29 | 0924CD-Central-Solusi-BOQ Template(new contract) | DU00002860407 |  |  |  |  | 2025-05-06 |  | 3m RT (Wall Mounted Pole)
W01169 | W066V_W01169IB_DTNMAYBANK | Central |  | Decomm | Decomm->On hold->Decomm | 2024 Q2 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-08-12 |  |  |  | 2024-01-17 |  | 2024-08-15 | 2024-08-23 | CD//Sofiah | 2024-08-22 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240128/Celcom Digi_RAN-Datasco-Standard PR TSS-Central-20241016 | DU00002860408 |  | 1) Missing antenna TX photo at NE 2) MIssing FE part |  |  | 2024-06-14 |  | IN-BUILDING
3326A | SS4B_10 Petronas | Central |  | Modernization |  | 2024 Q3 | CR | Magicell | 4.6 TSSR Approved |  | 2023-11-30 | 2023-12-13 |  | 2024-03-21 |  | Closed | 2024-03-22 | 2024-03-26 | E//Kok Keen | 2024-03-25 | CelcomDigi_RAN_Magicell_TSS_Central_20231203 | DU00002860409 |  |  | 2024-05-08 | 2024-05-07 |  | In-Building System | 3m Bipod (RT) | 6m | Add R9264M M1821 x3,Dismantle R8882 S1800(B) x3 | 0 | 0
B01807 | B061P_B01807IB_PARADIGMMALL | Central |  | Decomm |  | 2024 Q1 | CR | GCI | 4.6 TSSR Approved |  | 2023-11-29 |  |  |  | 2024-05-08 |  | 2024-05-09 | 2026-01-21 | CD//Sofiah | 2026-03-31 | CelcomDigi_RAN_GCI_TSS_Central_20231203 | DU00002860410 |  |  |  |  | 2024-06-13 |  | IBC + Rooftop
B00851 | B061R_B00851IB_GIANTKLJ | Central |  | Decomm | Decomm->TBD->Swap->Site out | 2024 Q1 |  | CCSMY | 14.1 TSSR Not Required (Decomm by CD) | [6 empty] | To be Submitted | [5 empty] | DU00002860411 |  |  |  |  | 2025-04-29 |  | BOOM
3392A | Putra-Cyber1 | Central |  | Modernization |  | 131 single site mocn | SM | GTSB | 4.6 TSSR Approved |  | 2024-01-19 | 2024-01-23 |  | 2024-05-23 |  | Under Approval | 2024-05-24 | 2024-05-28 | E//Kok Keen | 2024-05-28 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240128 | DU00002860412 |  |  | 2024-06-13 | 2024-06-13 |  | Tower | Tower | 62 | Add R8862A S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 23 | 0
W00452 | W066U_W00452IB_LEMERIDIEN | Central |  | Decomm | Decomm->On hold->Swap->Decomm | 2024 Q2 | SHA | DATASCO | 4.6 TSSR Approved |  | 2024-01-04 | 2024-03-20 |  | 2024-03-19 | 2024-01-08 | Under Approval | 2024-07-26 | 2024-08-21 | CD//Sofiah | 2024-08-02 | 0626Central-Datasco-BOQ Template (template) | DU00002860413 |  |  |  |  | 2024-09-26 | Portables BTS | LAMP_POLE | NA
3428A | TMNGASING_INDAH1 | Central |  | Modernization |  | 2024 Q2 | SS | Solusi | 4.6 TSSR Approved |  | 2023-11-21 | 2023-11-27 |  | 2024-03-06 |  | Closed | 2024-03-13 | 2024-03-14 | E//Kok Keen | 2024-03-13 | BOQ CelcomDigi_RAN_Solusi_Standard PR TSS_Central_20240115 | DU00002860414 |  |  | 2024-08-27 | 2024-08-24 |  | In-Building System | 3m Boom (RT) | 6.3 | Add R8852E S9000 x1+R9264H M901821 x3+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x4 | 1 | 0
3446A | TMN_MUTIARARAYA1 | Central |  | Modernization |  | 2024 Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-11-15 | 2023-12-01 |  | 2024-03-22 |  | Closed | 2024-03-25 | 2024-03-26 | E//Sumitra | 2024-03-26 | CelcomDigi_RAN_AllStar_TSS_Central_20231116 | DU00002860415 |  |  | 2024-08-14 | 2024-08-03 |  | In-Building System | 30m Monopole | 4 | Add R8862A S9000 x3+R8894E M1821 x1,Dismantle | 0 | 1
A01068 | A040B_A01068IB_Yik_Foong_Mall_IB | Northern |  | Decomm |  | 2024 Q2 | BY | Magicell | 4.6 TSSR Approved |  | 2023-10-30 |  |  |  | 2023-11-24 |  | 2023-11-27 | 2024-10-01 | CD//Rohizam | 2024-01-30 | Celcom Digi_RAN-Magicell-TSS-Northern-20231101-0002 | DU00002860416 |  |  |  |  | 2024-03-21 |  | IN-BUILDING
3692A | The Trillium (REL) | Central |  | Site Out (Modernization) | Modernization->Decomm->Site Out->Site Out (Modernization) | 2024 Q3 | BY | Magicell | [SiteOut]- 4.5 Pending TSSR Review - Customer |  | 2024-01-09 | 2024-01-22 |  |  | 2024-03-22 |  | 2024-03-26 |  | E//Sumitra |  | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240110 | DU00002860417 | [5 empty] | In-Building System | 3m Bipod (RT) | 9
4313A | Pekan Pasir Bidor | Northern |  | Modernization |  | 2024 Additional | BY | CCSMY | 4.6 TSSR Approved |  | 2023-11-21 | 2023-11-28 |  | 2023-12-05 |  | Closed | 2023-12-08 | 2023-12-20 | E//Hazida | 2023-12-15 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231122-0072 | DU00002860418 |  |  | 2024-12-02 | 2024-11-26 |  | Tower | 200ft 3 legged tower | 62M | Add R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3++ | 0 | 0
B01050 | B061G_B01050IB_CITTAMALLID | Central |  | Decomm | Decomm->On hold->Decomm | 2024 Q1 | BY | GTSB | 4.6 TSSR Approved |  | 2024-03-02 |  |  |  | 2024-06-28 |  | 2024-07-02 | 2024-07-19 | CD//Sofiah | 2024-07-10 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240311 | DU00002860419 |  |  |  |  | 2025-10-27 |  | INBUILDING
4176A | USM Prai | Northern |  | Modernization |  | 131 single site mocn | ZB | YPTT | 4.6 TSSR Approved |  | 2023-12-16 | 2023-12-19 |  | 2024-08-19 |  | Under Approval | 2024-08-23 | 2024-09-04 | E//Hazida | 2024-09-03 | Celcom Digi_RAN-YPTT-TSS-Northern-20231225-0047 | DU00002860420 |  |  | 2024-08-29 | 2024-08-26 |  | Tower | 48m 3 Legged Tower | 50 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
4239A | Sg Rambai | Northern |  | Modernization |  | 2025 Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-12-21 | 2023-12-22 |  | 2025-02-18 |  | Rectificating | 2025-03-12 | 2025-03-17 | E//Hazida | 2025-03-13 | Celcom Digi_RAN-GTSB-TSS-Northern-20231225-0080 | DU00002860421 |  |  | 2025-06-08 | 2025-05-31 |  | Tower | 60m 4 Legged Tower | 60 | Add R8862A S9000x3+R8894E M1821x4+R8854 S2600x1, Dismantle R8882-GUL1812x3+R8862A S2100(A6A)x3+R8862A S2600(A4A)x1 | 0 | 3
4271B | Tmn Syed Alwi | Northern |  | Modernization |  | 2024 Q4 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-10-17 | 2023-10-25 |  | 2024-04-19 |  | Closed | 2024-04-24 | 2024-04-26 | E//Hazida | 2024-04-25 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231018-0057 | DU00002860422 |  |  | 2024-05-16 | 2024-05-11 |  | Tower | Tower | 50M | Add R8862A S9000 x3+A9732 M1821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 123 | 0
W01556 | B057C_W01556IB_KLEASTMALL | Central |  | Decomm | Decomm->On hold->Decomm | 2024 Q1 | SH | GTSB | 4.6 TSSR Approved |  | 2024-06-10 |  |  |  | 2024-06-13 |  | 2024-12-18 | 2025-01-14 | CD//Sofiah | 2024-12-19 | CelcomDigi_RAN_GTSB_TSS_Central_20240423 | DU00002860423 |  |  |  |  | 2025-04-25 | Portables BTS | IN-BUILDING
4103R | 4037_Trolak_JTROM1_27 | Northern |  | Maintain USP MOCN(Dismantle Passive) | Maintain USP MOCN(Dismantle Passive)->On Hold->Maintain USP MOCN(Dismantle Passive) | 2024 Q4 |  | NR services | 15.3 Decomm Done without TSSR | [6 empty] | To be Submitted |  |  |  |  | SQ202504230465-NR services | DU00002860424 |  |  |  |  | 2025-11-28
4344B | W Pavaai RCC | Northern |  | Modernization |  | 2024 Q2 |  | GCI | 4.6 TSSR Approved |  | 2023-10-18 | 2023-10-27 |  | 2024-01-08 |  | Closed | 2024-01-09 | 2024-01-11 |  | 2024-01-10 | Celcom Digi_RAN-GCI-TSS-Northern-20231023-0064 | DU00002860425 |  |  | 2024-01-29 | 2024-01-26 |  | In-Building System | Tower | Wall mount boom S1/S2/S3=2.2m/3m/3m | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3
4076Z | KGAYERKUNING | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 Q1 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860426
4353B | Rapat Perdana RCC | Northern |  | Modernization |  | 2024 Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2023-10-11 | 2023-10-20 |  | 2024-01-05 |  | Closed | 2024-01-19 | 2024-01-22 | E//Hazida => E//Ajay | 2024-01-18 | Celcom Digi_RAN-GTSB-TSS-Northern-20231012-0047 | DU00002860427 |  |  | 2024-02-27 | 2024-02-19 |  | In-Building System | Tower | 10 | Add R8862A S9000 x3+R8894E M1821 x1+R8854 S2600 x1,Dismantle R8862A S2600(A4A) x1 |  | 3
4359A | Simpang Gua Tempurong RDC | Northern |  | Modernization |  | 2024 Additional | SM | GTSB | 4.6 TSSR Approved |  | 2024-11-22 | 2024-11-26 |  | 2024-11-30 |  | Rectificating | 2024-12-02 | 2024-12-06 | E//Hazida | 2024-12-06 | 1911CD-Northern-TSS-BOQ Template(new contract)_GTSB | DU00002860428 |  |  | 2025-01-05 | 2024-12-11 |  | Tower | 60m 3 Legged Tower | 65m | Add R8862A S9000x1+R8894E M1821x5+R8854 S2600x1, Dismantle R8882-GUL1812x2+R8862A S1800(B6A)x1 | 0 | 4
4065R | 3264_SgSumun_SMUNM1_13 | Northern |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Additional | HW | NR services | 4.6 TSSR Approved |  | 2025-10-07 |  | 2025-10-22 |  | 2025-10-22 |  | 2025-10-29 | 2026-01-22 | E//Hazida | 2025-11-04 | SQ202504230465-NR services | DU00002860429 |  |  |  |  | 2025-10-21
4360A | NS KM301 NB (Maxis) RDD | Northern |  | Modernization |  | 2024 Additional | SM | GCI | 4.6 TSSR Approved | 0204 - Emailed Rollout on Major CME required | 2025-01-09 | 2025-01-14 |  | 2025-02-03 |  | Rectificating | 2025-02-04 | 2025-02-19 | E//Hazida | 2025-02-19 | 1911CD-Northern-TSS-BOQ Template(new contract)_GCI | DU00002860430 |  |  | 2025-03-03 | 2025-02-24 |  | Tower | 76m 3 Legged Tower | 60m | Add R8852E S9000x1+R8862A S2601x1+R8894E M1821x4, Dismantle R8882-GUL1812x1+R8862A S1800(B6A)x2 | 0 | 0
4362B | UiTM Kg Gajah RDD | Northern |  | Modernization |  | 2024 Q2 | SM | GCI | 4.6 TSSR Approved | ¦ 0301 - Revised TSSR submitted n BOM revised ¦ 0228 - Listed for solution change, pending confirmed solution | 2023-10-20 | 2023-11-01 |  | 2024-01-15 |  | Rectificating | 2024-03-01 | 2024-03-06 | E//Hazida | 2024-03-01 | Celcom Digi_RAN-GCI-TSS-Northern-20231214-0084 | DU00002860431 |  |  | 2024-03-11 | 2024-03-07 |  |  | 60m 3 Legged Tower | 60m | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3 | 13 | 0
4095R | 6404_SBktBesout_BBESM1_22 | Northern |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2025 Q1 |  | NR services | 15.3 Decomm Done without TSSR |  | 2025-11-03 |  |  |  |  | To be Submitted |  |  |  |  | SQ202504230465-NR services | DU00002860432 |  |  |  |  | 2025-11-28
4057Z | KGSGDENDANG | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 Q1 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860433
4391B | Sg Gedung (Maxis) RDD | Northern |  | Modernization |  | 154 single site MOCN | AI | GTSB | 4.6 TSSR Approved |  | 2023-10-17 | 2023-10-23 |  | 2024-08-22 |  | Closed | 2024-09-10 | 2024-09-19 | E//Hazida | 2024-09-19 | Celcom Digi_RAN-GTSB-TSS-Northern-20231130-0069 | DU00002860434 |  |  | 2024-09-03 | 2024-08-26 |  | Tower | 60m 3 Legged Tower | 60 | Add R8852E S9000 x3+R9224E M1821 x2+R8854 S2600 x2,Dismantle R8862A S2600(A4A) x2 |  | 13
4064Z | FELCRACHANGKAT | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 Q1 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860435
4060Z | KGSGSAMAK | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860436
4054Z | KGSGBIL | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860437
4168Z | Tanjung Sari (Bagan Datoh) | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860438
4169Z | Kg Tanah Lalang Darat | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860439
4163Z | Sungai Tukang Sidin (chikus) | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860440
4170Z | Sungai Pergam | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860441
4167Z | Kg Teluk Bharu | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860442
4171Z | Bgn Sg Belukang | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860443
4411B | NS KM385 NB | Northern |  | Modernization | Modernization->On Hold | 2024 Additional | AI | YPTT | 4.6 TSSR Approved |  | 2023-12-11 | 2023-12-07 |  | 2025-02-17 |  | Closed | 2025-02-25 | 2025-02-27 | E//Hazida | 2025-02-27 | Celcom Digi_RAN-YPTT-TSS-Northern-20231225-0047 | DU00002860444 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed | 2025-08-30 | 2025-08-30 |  | Tower | 60m 3 Legged Tower | 61 | Add R8852E S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2600(A4A) x1 | 0 | 1
4414B | Sg Dara Tanjung Malim | Northern |  | Modernization |  | 131 single site mocn | SM | GTSB | 4.6 TSSR Approved |  | 2023-10-27 | 2023-10-30 |  | 2023-12-05 |  | Rectificating | 2024-08-16 | 2024-08-19 | E//Hazida | 2024-08-16 | Celcom Digi_RAN-GTSB-TSS-Northern-20231028-0057 | DU00002860445 |  |  | 2024-09-21 | 2024-08-21 |  | Tower | 60m 3 Legged Tower | 55 | Add R8894E M1821 x4+R8854 S2600 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2600(A4A) x1 | 0 | 2
4415A | Cold Stream | Northern |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | SM | GTSB | 4.6 TSSR Approved |  | 2023-11-21 | 2023-11-27 |  | 2023-12-02 |  | Rectificating | 2024-10-24 | 2024-10-29 | E//Hazida | 2024-10-27 | Celcom Digi_RAN-GTSB-TSS-Northern-20231122-0067 | DU00002860446 |  |  | 2024-11-20 | 2024-11-13 |  | Tower | 3m Bipod (RT) | 60 | Add R8862A S9000 x3+R8894E M1821 x4,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3 | 0 | 2
4166Z | Kg Sg Teras | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860447
4165Z | Kg Menderang | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 Q1 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860448
4164Z | RPS Jernang | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 Q1 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860449
4173Z | Jeram Mengkuang (Changkat Ramu) | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 Q1 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860450
4155Z | Lata Iskandar _ Kg Tua Ulu Kerian | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q1 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860451
4096Z | Kg Teluk Seribu | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860452
4099Z | Jln Gula | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860453
4154Z | Kg. Rasau Slim River | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860454
4158Z | Kg. Alor Setanggol | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860455
4151Z | Kg Poh Bidor | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860456
4430A | Kg Sg Protan RCC | Northern |  | Modernization |  | 2024 Q3(single site MOCN) | BY | Magicell | 4.6 TSSR Approved |  | 2024-01-04 | 2024-01-10 |  | 2024-04-17 |  | Closed | 2024-04-18 | 2024-04-22 | E//Hazida | 2024-04-19 | Celcom Digi_RAN-Magicell-TSS-Northern-20240108-0008 | DU00002860457 |  |  | 2024-06-21 | 2024-06-15 |  | Tower | Tower | 60 | Add A9732 M1821 x2,Dismantle R8894E M1821(A8A) x2 | 12 | 0
4152Z | Kg. Seri Kampar _ Kg Redang Ponggor | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860458
4150Z | Pos Keding _ Pos Tibang | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860459
4440B | Tapah Road | Northern |  | Modernization |  | 2025 Q1 | SM | GTSB | 4.6 TSSR Approved |  | 2025-01-15 | 2025-01-27 |  | 2025-02-05 |  | Rectificating | 2025-02-07 | 2025-02-19 | E//Hazida | 2025-02-19 | SQ202501030229 - gtsb | DU00002860460 |  |  | 2025-02-17 | 2025-02-11 |  | Tower | 60m 3 Legged Tower | 60M | Add R8894E M1821x3, Dismantle R8882-GUL1812x2+R8862A S1800(B6A)x1+R8854D S2100(A4A)x3 | 0 | 0
4446A | R&R Maxis | Northern |  | Modernization | Modernization->On Hold->Modernization | 2024 Additional | SM | GTSB | 4.6 TSSR Approved |  | 2023-10-27 | 2023-10-30 |  | 2023-12-02 |  | Rectificating | 2023-12-05 | 2023-12-26 | E//Hazida | 2023-12-23 | Celcom Digi_RAN-GTSB-TSS-Northern-20231028-0057 | DU00002860461 |  |  | 2025-05-19 | 2025-05-15 |  | Tower | 60m 4 Legged Tower | 55 | Add R8862A S9000 x3+R8894E M1821 x2+A9732 M1821 x1,Dismantle R8882-GUL1812 x3+R8840-U216 x3++ | 1 | 0
4005R | Parit 9 | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860462
4451B | Tupai Industrial Park | Northern |  | Modernization |  | 2024 Q2 |  | GCI | 4.6 TSSR Approved |  | 2023-10-09 | 2023-10-24 |  | 2024-01-11 |  | Closed | 2024-01-17 | 2024-01-30 | E//Hazida | 2024-01-23 | Celcom Digi_RAN-GCI-TSS-Northern-2023111-0057 | DU00002860463 |  |  | 2024-03-22 | 2024-03-07 |  | In-Building System | 6.5m RT (Boom) | 7 | Add R8894E M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8840-U216 x3++
4452B | Pasir Besar RCC | Northern |  | Modernization |  | 2024 Q2 | SM | GTSB | 4.6 TSSR Approved | ¦ 0228 - Listed for solution change, pending confirmed solution | 2023-10-17 | 2023-10-20 |  | 2024-01-05 |  | Rectificating | 2024-03-04 | 2024-03-05 | E//Hazida | 2024-03-05 | Celcom Digi_RAN-GTSB-TSS-Northern-20231018-0051 | DU00002860464 |  |  | 2024-04-05 | 2024-03-28 |  | Tower | 60m 4 Legged Tower | 60 | Add R8852E S9000 x1+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882-GUL1812 x2++R8881 S2100 x2+ | 0 | 2
4004R | Kg Parit 4 Sg Sumun | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860465
4454B | Kubu Gajah RDD | Northern |  | Modernization |  | 131 single site mocn | SM | GCI | 4.6 TSSR Approved |  | 2023-10-17 | 2023-10-18 |  | 2023-10-23 |  | Closed | 2024-08-19 | 2024-08-21 | E//Hazida | 2024-08-20 | Celcom Digi_RAN-GCI-TSS-Northern-20231018-0061 | DU00002860466 |  |  | 2024-09-13 | 2024-08-23 |  | Tower | 60m 3 Legged Tower | 62 | Add R8852E S9000 x3+R8894E M1821 x5+R8854 S2600 x2,Dismantle R8882-GUL1812 x3+R8862A S2600(A4A) x2 |  | 12
4003R | Kg Sg Batang | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860467
4002R | Kg Tebuk Imam Tasir | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860468
4006R | Parit 19 | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860469
4457B | KG HUJUNG MATANG RDD | Northern |  | Modernization |  | 2024 Q2 | HQ 1 | GTSB | 4.6 TSSR Approved | ¦ 0304 - Need revise TSSR due to 900 RRU model not available | 2023-10-13 | 2023-10-16 |  | 2024-01-08 |  | Closed | 2024-01-17 | 2024-01-29 | E//Hazida | 2024-01-23 | Celcom Digi_RAN-GTSB-TSS-Northern-20231015-0049 | DU00002860470 |  |  | 2024-04-06 | 2024-03-28 |  | Tower | 60m 3 Legged Tower | 60 | Add R8862A S9000 x1+R8894E M1821 x3,Dismantle R8882-GUL1812 x1+R8882 S1800B(B6B) x3
4068R | JALAN KAMPAR - CHANGKAT JONG | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860471
4460A | TAIPING HAWKER | Northern |  | Modernization |  | 2024 Q2 | BY | YPTT | 4.6 TSSR Approved | ¦ 0228 - Listed for solution change, pending confirmed solution | 2023-12-05 | 2023-11-06 |  | 2024-01-09 |  | Closed | 2024-03-05 | 2024-03-06 | E//Hazida | 2024-03-06 | Celcom Digi_RAN-YPTT-TSS-Northern-20231225-0047 | DU00002860472 |  |  | 2024-04-08 | 2024-04-04 |  |  | 60m 4 Legged Tower | 5 | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x4 | 13 | 0
4070R | KG SUNGAI KERAWAI | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860473
4071R | KG SENDI LIMA | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860474
4072R | RISDA CHANGKAT SULAIMAN | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860475
4074R | KG CHANGKAT SERUNAI | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860476
4075R | KG BULUH SERUAS | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860477
4076R | KG TITI IJOK | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860478
4077R | LANDASAN KERETAPI GUNUNG SEMANGGOL | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860479
4014R | Kg Sungai Baru | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860480
4013R | Matang Kunda | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860481
4468A | Selama RCC | Northern |  | Modernization |  | 2024 Q3(single site MOCN) | BY | YPTT | 4.6 TSSR Approved | ¦ 0507 - SA Adam: Site will change achor | 2023-12-16 | 2023-12-27 |  | 2024-04-19 |  | Closed | 2024-04-26 | 2024-04-30 |  | 2024-04-29 | Celcom Digi_RAN-YPTT-TSS-Northern-20231225-0047 | DU00002860482 |  |  | 2024-06-27 | 2024-06-15 |  | Tower | 60m 4 Legged Tower | 65m | Add R8862A S9000 x3+A9732 M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8854D S2100(A4A) x3 | 123 | 0
4473A | Hutan Melintang | Northern |  | Modernization |  | 154 single site MOCN | SH | CCSMY | 4.6 TSSR Approved |  | 2024-01-17 | 2024-01-19 |  | 2024-08-15 |  | Under Approval | 2024-08-16 | 2024-08-20 |  | 2024-08-19 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240124-0089 | DU00002860483 |  |  | 2024-08-26 | 2024-08-22 |  | Tower | 60m 4 Legged Tower | 47m | Add R8862A S9000 x2+R9264H M901821 x1+R8862A S2601 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x2 | 13 | 0
4515B | Pinji Mewah 2 RCC | Northern |  | Modernization |  | 2024 Q2 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-12-30 | 2024-02-26 |  | 2024-02-27 |  | Closed | 2024-02-28 | 2024-03-01 | E//Ajay | 2024-03-01 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240229-0097 | DU00002860484 |  |  | 2024-03-09 | 2024-03-05 |  | Tower | Tower | 61m | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
4516B | Ladang Pinji RDD | Northern |  | Modernization |  | 2024 Q2 | ZA | YPTT | 4.6 TSSR Approved | ¦ 0228 - TSSR rejected by Maxis due to limitation of RRU on top ¦ Listed for solution change, pending confirmed solution 19/2 - subcon plsn resurvey 20/2 for AC power reading | 2023-10-26 | 2024-02-06 |  | 2024-02-14 |  | Closed | 2024-03-05 | 2024-03-06 | E//Ajay | 2024-03-05 | Celcom Digi_RAN-YPTT-TSS-Northern-20231028-0040 | DU00002860485 |  |  | 2024-03-17 | 2024-03-07 |  | Tower | 60m 3 Legged Tower | 60 | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 3 | 0
4521A | Ipoh MSC | Northern |  | Modernization |  | 2024 Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2023-10-27 | 2024-01-09 |  | 2024-01-12 |  | Rectificating | 2024-01-17 | 2024-01-23 | E//Hazida | 2024-01-21 | Celcom Digi_RAN-GTSB-TSS-Northern-20231028-0057 | DU00002860486 |  |  | 2024-02-26 | 2024-02-14 |  | Tower | 60m 4 Legged Tower | 60 | Add R9264M M1821 x1+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R8882 S2600(B4A) x1+R8862A S2600(A4A) x2+R8894E M1821(A8A) x4 | 12
4524B | Silibin Industry | Northern |  | Modernization |  | 2024 Q2 |  | Magicell | 4.6 TSSR Approved |  | 2024-01-10 | 2024-01-15 |  | 2024-01-18 |  | Closed | 2024-01-23 | 2024-01-29 | E//Hazida | 2024-01-25 | Celcom Digi_RAN-Magicell-TSS-Northern-20240114-0010 | DU00002860487 |  |  | 2024-02-09 | 2024-02-05 |  | Monopole | 30m Monopole | 30M | Reuse existing RRU
4540A | RIMA Industry | Northern |  | Modernization |  | 2024 Q2 | BY | GCI | 4.6 TSSR Approved | ¦ 0304 - Need revise TSSR due to 900 RRU model not available | 2024-01-17 | 2024-01-18 |  | 2024-01-23 |  | Closed | 2024-01-26 | 2024-01-31 | E//Ajay | 2024-01-30 | Celcom Digi_RAN-GCI-TSS-Northern-20240124-0090 | DU00002860488 |  |  | 2024-03-15 | 2024-03-12 |  | Monopole | 30m Monopole | 30 | Add R8862A S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 12
4557A | Chenderong | Northern |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | SHA | CCSMY | 4.6 TSSR Approved |  | 2024-11-21 | 2024-12-02 |  | 2024-12-03 |  | Under Approval | 2024-12-03 | 2024-12-16 | E//Hazida | 2024-12-13 | 1911CD-Northern-TSS-BOQ Template(new contract)_CCSMY | DU00002860489 |  |  | 2025-01-09 | 2024-12-11 |  | Tower | 45m 4 Legged Tower | 60 | Add R8862A S9000x3+R8894E M1821x3, Dismantle R8860E-GU908x1+R8882-GUL1812x2+R8840-U216x3 | 0 | 0
4560A | Kg Seri Kinta | Northern |  | Modernization |  | 2024 Q2 | SM | GTSB | 4.6 TSSR Approved | ¦ 0119 - revised TSSR submitted | 2023-10-10 | 2023-10-12 |  | 2024-01-08 |  | Rectificating | 2024-01-11 | 2024-01-29 | E//Hazida | 2024-01-24 | Celcom Digi_RAN-GTSB-TSS-Northern-20231011-0046 | DU00002860490 |  |  | 2024-02-18 | 2024-02-14 |  | Tower | 45m 3 Legged Tower | 60 | Add R8894E M1821 x2+R8854 S2600 x2,Dismantle R8862A S2600(A4A) x2 |  | 23
4592B | Ulu Dedap | Northern |  | Modernization |  | 2024 Q2 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-10-22 | 2023-10-31 |  | 2024-01-10 |  | Closed | 2024-01-11 | 2024-01-19 | E//Ajay | 2024-01-19 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231214-0081 | DU00002860491 |  |  | 2024-04-01 | 2024-03-28 |  | Tower | 60m 3 Legged Tower | 61m | Add R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882-GUL1812 x3+R8862A S2601(A6A) x1 |  | 1
4594B | Kellie s Castle RDD | Northern |  | Modernization |  | 2024 Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2023-10-16 | 2023-10-20 |  | 2024-01-09 |  | Rectificating | 2024-01-11 | 2024-01-22 | E//Hazida => E//Ajay | 2024-01-19 | Celcom Digi_RAN-GTSB-TSS-Northern-20231017-0050 | DU00002860492 |  |  | 2024-02-27 | 2024-02-19 |  | Tower | 60m 3 Legged Tower | 60 | Add R8862A S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3+R8862A S2600(A4A) x1 |  | 1
4601A | Hotel Federal Kangar | Northern |  | Modernization |  | 2024 Q4 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-11-09 | 2023-11-14 |  | 2024-04-23 |  | Closed | 2024-04-29 | 2024-04-30 | E//Hazida | 2024-04-29 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231115-0070 | DU00002860493 |  |  | 2024-05-31 | 2024-05-16 |  | In-Building System | 3m Boom (RT) | 3m | Add R8862A S9000 x3+R8894E M1821 x5+R8854 S2600 x2,Dismantle R8882-GUL1812 x3+R8862A S2600(A4A) x2+R8840-U216 x3++ | 0 | 13
4609A | Klj Matrix Perlis | Northern |  | Modernization |  | 2024 Q4 | BY | YPTT | 4.6 TSSR Approved |  | 2023-10-26 | 2023-11-06 |  | 2024-04-19 |  | Closed | 2024-04-24 | 2024-05-15 | E//Hazida | 2024-04-25 | Celcom Digi_RAN-YPTT-TSS-Northern-20231028-0040 | DU00002860494 |  |  | 2024-05-25 | 2024-05-17 |  | Pole | Watertank Structure | 3 | Add R8862A S9000 x3+R8894E M1821 x2+A9732 M1821 x1,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 2 | 0
4610B | Titi Tengah | Northern |  | Modernization |  | 131 single site mocn | SM | GCI | 4.6 TSSR Approved |  | 2023-10-13 | 2023-10-18 |  | 2023-10-23 |  | Closed | 2024-08-19 | 2024-08-20 | E//Hazida | 2024-08-19 | Celcom Digi_RAN-GCI-TSS-Northern-20231017-0060 | DU00002860495 |  |  | 2024-08-28 | 2024-08-22 |  | Tower | 45m 4 Legged Tower | 50m | Add A9732 M1821 x2,Dismantle R8894E M1821(A8A) x2+R8854 S2600(A4A) x3 | 12 | 0
4613A | Berseri Perlis | Northern |  | Modernization |  | 2025 Q3 | SM | GCI | 4.6 TSSR Approved |  | 2023-10-14 | 2023-12-14 |  | 2025-04-18 |  | Under Approval | 2025-03-13 | 2025-05-27 | E//Hazida | 2025-03-20 | Celcom Digi_RAN-GCI-TSS-Northern-20231017-0060 | DU00002860496 |  |  | 2025-04-09 | 2025-03-24 |  | Tower | 60m 3 Legged Tower | 60 | Add R8852E S9000x3+R9264M M1821x2+A9732 M1821x1, Dismantle R8860E-GU908x3+R8882-GUL1812x3+R8862A S2100(A6A)x3 | 2 | 0
4617A | KWSP Kangar | Northern |  | Modernization |  | 2024 Q4 | BY | GCI | 4.6 TSSR Approved |  | 2024-02-29 | 2024-03-19 |  | 2024-04-25 |  | Closed | 2024-05-08 | 2024-05-10 | E//Hazida | 2024-05-09 | Celcom Digi_RAN-GCI-TSS-Northern-20240310-0100 | DU00002860497 |  |  | 2024-05-25 | 2024-05-17 |  | In-Building System | 60m 4 Legged Tower | 6M | Add R8862A S9000 x3+A9732 M1821 x3,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x3+R9224E M1821(AAB) x2 | 123 | 0
4686A | Relau | Northern |  | Modernization | Modernization->On Hold->Modernization | 2025 Q3 | SM | CCSMY | 4.6 TSSR Approved | 0317 - Emailed rollout on Major CME requirement | 2023-10-13 | 2023-10-27 |  | 2025-02-19 |  | Under Approval | 2025-03-14 | 2025-03-17 | E//Hazida | 2025-03-17 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231016-0055 | DU00002860498 | Remarks: Solution TSSR/BOM Changed |  | 2025-06-10 | 2025-06-10 |  | Tower | 60m 3 Legged Tower | 60 | Add R8852E S9000x4+R8894E M1821x4+R8862A S2601x1, Dismantle R8882-GUL1812x3 | 0 | 0
4722B | Pasir Putih (Vsat) | Northern |  | Modernization |  | 2025 Q3 | HW | GCI | 4.6 TSSR Approved |  | 2025-01-16 | 2025-03-07 |  | 2025-03-18 |  | Under Approval | 2025-03-24 | 2025-05-19 | E//Hazida | 2025-04-23 | SQ202501030261 - GCI | DU00002860499 |  |  | 2025-07-06 | 2025-06-19 |  | Tower | Tower | 60m | Add R8862AS9000x2+R8894E M1821x3, Dismantle R8862A S1800(B6A)x3 | 0 | 0
4771A | Bkt Besar (Trunk) | Northern |  | Modernization |  | 154 single site MOCN | AD | GTSB | 4.6 TSSR Approved |  | 2024-01-11 | 2024-01-16 |  | 2024-08-16 |  | Under Approval | 2024-08-19 | 2024-08-21 | E//Hazida | 2024-08-21 | Celcom Digi_RAN-GTSB-TSS-Northern-202401114-0085 | DU00002860500 |  |  | 2024-09-06 | 2024-08-27 |  | Tower | 75m 4 Legged Tower | 75M | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123 | 0
4773A | Bukit Sungai Kecil (Trunk) | Northern |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | SM | GCI | 4.6 TSSR Approved |  | 2023-10-13 | 2023-10-20 |  | 2024-11-04 |  | Rectificating | 2024-11-11 | 2024-11-14 | E//Hazida | 2024-11-12 | Celcom Digi_RAN-GCI-TSS-Northern-20231017-0060 | DU00002860501 |  |  | 2025-01-05 | 2024-11-26 |  | Tower | 70m 4 Legged Tower | 100m | Add R8862A S9000x3+R8894E M1821x4, Dismantle R8882-GUL1812x1+R8862A S1800(B6A)x2 | 0 | 3
4774B | Kg Kok Klang | Northern |  | Modernization |  | 154 single site MOCN | SM | GTSB | 4.6 TSSR Approved |  | 2023-10-13 | 2023-10-17 |  | 2023-10-24 |  | Closed | 2024-08-19 | 2024-08-20 | E//Hazida | 2024-08-19 | Celcom Digi_RAN-GTSB-TSS-Northern-20231015-0049 | DU00002860502 |  |  | 2024-08-26 | 2024-08-21 |  | Tower | Tower | 60M | Add R8852E S9000 x3+R8894E M1821 x4,Dismantle R8882-GUL1812 x3+R8862A S2601(A6A) x3 | 0 | 3
4778B | UiTMBlueW_Tank | Northern |  | Modernization |  | 2024 Q4 | BY | GTSB | 4.6 TSSR Approved |  | 2023-10-13 | 2023-10-20 |  | 2024-04-24 |  | Rectificating | 2024-05-07 | 2024-05-09 |  | 2024-05-08 | Celcom Digi_RAN-GTSB-TSS-Northern-20231015-0049 | DU00002860503 |  |  | 2024-05-20 | 2024-05-16 |  | Tower | Tower | 60 | Add R8862A S9000 x3+R8894E M1821 x5+R8854 S2600 x2,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3+R8862A S2600(A4A) x2 | 0 | 23
4781B | FELDABESOUT4 | Northern |  | Modernization |  | 2025 Q1 | HW | GTSB | 4.6 TSSR Approved |  | 2023-10-27 | 2023-11-07 |  | 2025-02-17 |  | Under Approval | 2023-12-12 | 2023-12-20 | E//Hazida | 2025-04-25 | Celcom Digi_RAN-GTSB-TSS-Northern-20231028-0057 | DU00002860504 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed | 2025-06-14 | 2025-05-14 |  | Tower | Tower | 60 | Add R8894E M1821x3+R8854 S2600x1+A9732 M1821x1, Dismantle R8882-GUL1812x2+R8862A S1800(B6A)x3+R8862A S2100(A6A)x4+R8862A S2601(A6A)x1 | 1 | 2
4794B | Kg Batu 2 | Northern |  | Modernization |  | 131 single site mocn | AD | GTSB | 4.6 TSSR Approved |  | 2023-11-29 | 2023-11-08 |  | 2024-08-16 |  | Under Approval | 2024-08-19 | 2024-08-22 | E//Hazida | 2024-08-21 | Celcom Digi_RAN-GTSB-TSS-Northern-20231214-0077 | DU00002860505 |  |  | 2024-09-10 | 2024-08-23 |  | Tower | Tower | 60 | Add R8852E S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 23 | 0
4853B | Kg Long Boh | Northern |  | Modernization |  | 2024 Q4 | BY | GTSB | 4.6 TSSR Approved |  | 2023-10-13 | 2023-10-20 |  | 2024-04-19 |  | Rectificating | 2024-04-24 | 2024-04-26 | E//Hazida | 2024-04-25 | Celcom Digi_RAN-GTSB-TSS-Northern-20231015-0049 | DU00002860506 |  |  | 2024-05-27 | 2024-05-16 |  | Tower | Tower | 60 | Add R8862A S9000 x3+R9224E M1821 x2+R8854 S2600 x2,Dismantle R8862A S2600(A4A) x2 | 0 | 12
7390A | Kundasang Town | Sabah |  | Modernization |  | 131 single site mocn | AD | Futong | 4.6 TSSR Approved |  | 2023-11-09 | 2023-11-10 |  | 2024-08-30 |  | Under Approval | 2024-09-02 | 2024-09-03 | E//Hannah | 2024-09-03 | Celcom Digi_RAN-Futong-TSS-Sabah-20231112 | DU00002860507 |  |  | 2024-10-04 | 2024-09-20 |  | Monopole | 30m Rapole | 30 | Add R8862A S9000 x3+A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123 | 0
4951B | Bandar Baharu HW | Northern |  | Modernization |  | 2025 Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-10-11 | 2023-11-10 |  | 2025-02-18 |  | Rectificating | 2025-02-27 | 2025-02-28 | E//Hazida | 2025-02-28 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231012-0053 | DU00002860508 |  |  | 2025-06-06 | 2025-06-03 |  | Tower | 60m 3 Legged Tower | 61 | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8882-GUL1812x2+R8862A S1800(B6A)x1+R8862A S2100(A6A)x1 | 0 | 0
4957B | Kg Hangus | Northern |  | Modernization |  | 2024 Q3(single site MOCN) | BY | GTSB | 4.6 TSSR Approved |  | 2023-10-18 | 2023-10-20 |  | 2024-04-18 |  | Closed | 2024-04-23 | 2024-04-25 |  | 2024-04-24 | Celcom Digi_RAN-GTSB-TSS-Northern-20231019-0052 | DU00002860509 |  |  | 2024-06-19 | 2024-06-15 |  | Tower | Tower | 60 | Add R9224E M1821 x1+A9732 M1821 x2,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 23 | 0
4963B | Ulu Sedim | Northern |  | Modernization |  | 131 single site mocn | SM | CCSMY | 4.6 TSSR Approved |  | 2024-08-29 | 2024-11-08 |  | 2024-11-12 |  | Rectificating | 2024-11-12 | 2024-11-29 | E//Hazida | 2024-11-29 | 0809CD-Northern-CCSMY-BOQ Template(new contract) | DU00002860510 |  |  | 2024-11-21 | 2024-11-21 |  | Tower | Tower | 75m | Add R8894E M1821x3+A9732 M1821x1, Dismantle R8862A S1800(B6A)x3 | 1 | 2
4970B | Jabi | Northern |  | Modernization |  | 2025 Q2 | SM | CCSMY | 4.6 TSSR Approved |  | 2025-01-07 | 2025-02-24 |  | 2025-03-04 |  | Rectificating | 2025-03-12 | 2025-03-17 | E//Hazida | 2025-03-13 | SQ202501030037 - CCSMY | DU00002860511 |  |  | 2025-07-24 | 2025-05-22 |  | Tower | 60m 4 Legged Tower | 60M | Add R8862A S9000x3+R8894E M1821x3, Dismantle R8860E-GU908x1+R8882-GUL1812x3+R8840-U216x3 | 0 | 0
4971B | Felcra Bukit Tampoi_Kg Kejai | Northern |  | Modernization |  | 2025 Q2 | SM | GCI | 4.6 TSSR Approved |  | 2025-01-17 | 2025-02-24 |  | 2025-03-04 |  | Rectificating | 2025-03-07 | 2025-03-17 | E//Hazida | 2025-03-17 | SQ202501030261 - GCI | DU00002860512 |  |  | 2025-09-14 | 2025-04-12 |  | Tower | Tower | 60m | Add R9264M M1821x2+A9732 M1821x1, Dismantle R8862A S1800(B6A)x3+R8854D S2100(A4A)x3 | 2 | 0
4981A | Kampung Tok Gula (KJS) | Northern |  | Modernization |  | 154 single site MOCN | SHA | GTSB | 4.6 TSSR Approved |  | 2023-10-17 | 2023-10-24 |  | 2024-08-26 |  | Under Approval | 2024-08-27 | 2024-09-11 | E//Ajay | 2024-09-10 | Celcom Digi_RAN-GTSB-TSS-Northern-20231018-0051 | DU00002860513 |  |  | 2024-09-16 | 2024-09-13 |  | Tower | 4 Legged Tower | 76 | Add R8852E S9000 x3+R9224E M1821 x2+R8854 S2600 x2,Dismantle R8862A S2600(A4A) x2 |  | 13
4986A | Binjul | Northern |  | Modernization |  | 2025 Q2 | AD | Magicell | 4.6 TSSR Approved |  | 2023-11-11 | 2023-11-17 |  | 2025-01-27 |  | Under Approval | 2025-02-14 | 2025-03-09 | E//Hazida | 2025-02-21 | Celcom Digi_RAN-Magicell-TSS-Northern-20231115-0003 | DU00002860514 |  |  | 2025-03-28 | 2025-02-20 |  | Tower | 60m 3 Legged Tower | 65m | Add R8894E M1821x3, Dismantle R8862A S1800(B6A)x5 | 0 | 0
4987B | Sg Tegas | Northern |  | Modernization |  | 2025 Q3 | SM | GCI | 4.6 TSSR Approved |  | 2023-10-14 | 2023-10-20 |  | 2025-02-25 |  | Rectificating | 2025-03-13 | 2025-03-19 | E//Hazida | 2025-03-19 | Celcom Digi_RAN-GCI-TSS-Northern-20231017-0060 | DU00002860515 |  |  | 2025-09-30 | 2025-06-18 |  | Tower | 60m 4 Legged Tower | 61 | Add R8852E S9000x3+R8894E M1821x4+R8854 S2600x1, Dismantle R8882-GUL1812x2+R8862A S1800(B6A)x1+R8862A S2100(A6A)x3+R8862A S2600(A4A)x1 | 0 | 2
4997B | Kg Tembak (Maxis) | Northern |  | Modernization |  | 154 single site MOCN | SH | GCI | 4.6 TSSR Approved |  | 2023-10-12 | 2023-10-23 |  | 2023-10-31 |  | Under Approval | 2024-09-13 | 2024-09-26 | E//Hazida | 2024-09-26 | Celcom Digi_RAN-GCI-TSS-Northern-20231013-0058 | DU00002860516 |  |  | 2024-08-28 | 2024-08-26 |  | Tower | 60m 3 Legged Tower | 62 | Add R8852E S9000 x1+R8894E M1821 x3,Dismantle R8892E M1821(BAA) x3
4626B | Pekan Bt5(Celcom) | Northern |  | Modernization | Modernization->On Hold->Modernization | 2024 Q3(single site MOCN) | AI | GCI | 4.6 TSSR Approved |  | 2025-01-09 | 2025-02-07 |  | 2025-02-25 |  | Closed | 2025-02-27 | 2025-03-10 | E//Hazida | 2025-03-28 | SQ202501030328 - GCI | DU00002860517 |  |  | 2025-06-18 | 2025-05-27 |  | Tower | 60m 4 Legged Tower | 60 | A9732 M1821 x1, Dismantle R8894E M1821(A8A)x1 | 3 | 0
4721B | Kg.Perik (Vsat) | Northern |  | MOCN As-Is | Maintain USP MOCN->On Hold->Maintain USP MOCN->MOCN As Is | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860518 | [6 empty] | Tower
4035Z | Telok Rambong _ Kg. Batu 8 | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860519
4038Z | Kg Teluk Temelah (Kg Legong) | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860520
4039Z | Kg Bukit Hijau (Kg Tawar Besar) | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860521
4034Z | Kg Kuala Kuang (Kg. Hulu Bakai) | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860522
4033Z | Kg. Ayer Merah _ Kg. Ayer Kepal | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860523
4179Z | KG SELARONG_KEJAI (Kg Batu 19) | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860524
4175Z | KG ULU BAKAI (Kg Batu 17) | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860525
4177Z | KG DALAM WANG (Kg Batu 14) | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860526
4202Z | KG KUALA KULI (Pos Musuh LZ) | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860527
4176Z | KG TIAK (Kg Batu 15) | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860528
4109Z | Kg Kuala Merah | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860529
4125Z | Kg Pinang Padang Terap | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860530
4103Z | Hutan Lipur Sungai Sedim | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860531
4104Z | Kg Kejai | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860532
4013Z | KGMACHANG | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860533
4138Z | Kg. KEDA Keledang | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860534
4132Z | Kg Bakong Asam Jawa | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860535
4136Z | Kg Charok Kapas | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860536
4110Z | Ayer Kepal | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860537
4111Z | Kg Kuala Nau | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860538
3973B | Bandar Tasik Kesuma Phase 2 | Central |  | Modernization |  | 131 single site mocn | SH | DATASCO | 4.6 TSSR Approved |  | 2023-12-13 | 2023-12-20 |  | 2024-04-25 |  | Closed | 2024-05-13 | 2024-05-21 | E//Sumitra | 2024-05-21 | CelcomDigi_RAN_Datasco_TSS_Central_20231224 | DU00002860539 |  |  | 2024-09-11 | 2024-09-06 |  | Pole | 3m Bipod (RT) | 6 | Add R8862A S9000 x2+R9264H M901821 x1+R8862A S2601 x3+A9732 M1821 x2,Dismantle R8854E S1800(A6A) x3+R8862A S2100(A6A) x3+R8862A S2600(A4A) x3 | 23 | 0
4108Z | Kg Ulu Seputeh | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860540
4139Z | Kg Sri Kelengga | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860541
4008R | Kg Lubuk Batu | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860542
4007R | Kg Teluk Sg Durian | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860543
4009R | Kg Padang Besar | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860544
4051R | Kg Bukit Sebelah | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860545 | [6 empty] | 75M 3 Legged Tower
4052R | Kg. Binjoi Luar | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860546 | [6 empty] | 75M 4 Legged Tower
4054R | Kg. Kuala Kijang | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860547 | [6 empty] | 75M 4 Legged Tower
4058R | Kg Kuala Darat | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860548 | [6 empty] | 75M 4 Legged Tower
4050R | Kg Terabak | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860549 | [6 empty] | 60M Tower
4011R | Kg Kuala Bakung | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860550
4010R | Ladang Kim Seng Batu 5 | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860551
9468A | Kem Putra Sentosa | Sarawak |  | Modernization | Modernization->On Hold->Modernization | 2024 Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2024-07-16 | 2024-02-21 |  | 2025-02-04 |  | Under Approval | 2025-03-10 | 2025-05-19 | E//Hannah | 2025-04-07 |  | DU00002860552 |  |  | 2025-05-24 | 2025-05-15 |  | Tower | 45m 3 Legged Tower | 76 | Add R8894E M1821x2, Dismantle R8854E S1800(A6A)x3 | 0 | 12
9418A | Pang Stungkor | Sarawak |  | Modernization | Modernization->On Hold->Modernization | 2024 Q2 | SM | GCI | 4.6 TSSR Approved |  | 2024-02-20 | 2024-02-19 |  | 2025-02-14 |  | Rectificating | 2025-02-20 | 2025-02-25 | E//Hannah | 2025-02-24 | SQ202505130354-GCI | DU00002860553 |  |  | 2025-04-17 | 2025-04-14 |  | Tower | 45m 3 Legged Tower | 76m | Add R8894E M1821 x2 | 0 | 13
9568B | TM Kuala Igan | Sarawak |  | Modernization | Modernization->On Hold->Modernization | 2025 Q2 |  | Trintel | 14.0 TSSR Not Required (Reuse Existing BBU/RRU) | [6 empty] | To be Submitted |  |  |  |  | SQ202501070293-Trintel | DU00002860554 |  |  | 2025-05-10 | 2025-05-08 |  |  | Tower |  | Reuse Existing RRU | 0 | 23
9059R | Kg Stinggang | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q2 | AI | Magicell | 4.6 TSSR Approved |  | 2025-06-19 |  | 2025-06-24 |  | 2025-07-07 |  | 2025-08-07 | 2025-10-31 | E//John | 2025-08-08 | SQ202506110081-Magicell/SQ202507140221-Magicell | DU00002860555 |  |  |  |  | 2025-09-06 |  | #N/A
9149R | TT844 | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 | AD | Magicell | 4.6 TSSR Approved |  | 2025-06-16 |  | 2025-06-18 |  | 2025-07-07 |  | 2025-08-07 | 2025-09-20 | E//John | 2025-09-17 | SQ202506110081-Magicell/SQ202507140221-Magicell | DU00002860556 |  |  |  |  | 2025-11-18 |  | #N/A
9289A | Siang Siang (TM-Sacofa) | Sarawak |  | Modernization | Modernization->On Hold->Modernization | 2025 Q2 | AD | CCSMY | 4.6 TSSR Approved |  | 2025-06-16 | 2025-06-26 |  | 2025-07-01 |  | Under Approval | 2025-07-07 | 2025-09-20 | E//John | 2025-07-08 | SQ202506060165-CCSMY | DU00002860557 |  |  | 2025-09-21 | 2025-09-04 |  | Tower | 60m 4 Legged Tower | 100m | Add R8894E M1821x1, Dismantle R8854E S1800(A6A)x4 | 0 | 2
9712A | Bkt Dabei (Celcom) | Sarawak |  | Remote MOCN | Modernization->On Hold->Maintain USP MOCN->Remote MOCN | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860558 | [6 empty] | Tower |  | Reuse Existing RRU | 0 | 0
9415A | Kg Pueh (Sacofa) | Sarawak |  | Modernization | Modernization->On Hold->Modernization | 2024 Q2 | AD | Magicell | 4.6 TSSR Approved |  | 2025-03-24 | 2025-03-26 |  | 2025-04-03 |  | Under Approval | 2025-04-18 | 2025-05-21 | E//Hannah | 2025-05-08 | SQ202503170571-Magicell | DU00002860559 | Remarks: Solution TSSR/BOM Changed |  | 2025-07-06 | 2025-06-28 |  |  | 45m 3 Legged Tower | 75 | Add R8894E M1821x1, Dismantle R8854E S1800(A6A)x3 | 0 | 3
9506A | Pakat | Sarawak |  | Remote MOCN | Modernization->On Hold->Maintain USP MOCN->Remote MOCN | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860560 | [6 empty] | Tower |  | Reuse Existing RRU | 0 | 0
9334B | Rh Mawa | Sarawak |  | Remote MOCN | Modernization->On Hold->Maintain USP MOCN->Remote MOCN | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860561 | [6 empty] | 45m 3 Legged Tower |  | Reuse Existing RRU | 0 | 0
9259Z | Kg Padang Pasir Bario | Sarawak |  | Remote MOCN | TBD->Site Out->On Hold->Maintain USP MOCN->Remote MOCN | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860562 | [6 empty] | 76M 3 Legged Tower |  | Reuse Existing RRU | 0 | 0
9402B | Kuala Igan | Sarawak |  | Remote MOCN | Modernization->On Hold->Maintain USP MOCN->Remote MOCN | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860563 | [6 empty] | 76m Tower |  | Reuse Existing RRU | 0 | 0
9378B | Matadeng | Sarawak |  | Remote MOCN | Modernization->On Hold->Maintain USP MOCN->Remote MOCN | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860564 | [6 empty] | Tower |  | Reuse Existing RRU | 0 | 0
7003A | Kuala Penyu 1 | Sabah |  | Modernization |  | 2025 Q1 | SM | Seri Pancar | 4.6 TSSR Approved |  | 2023-11-02 | 2023-11-06 |  | 2023-11-20 |  | Rectificating | 2025-01-09 | 2025-05-27 | CD//Sharidah | 2025-04-11 | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231221 | DU00002860565 | Remarks: Solution TSSR/BOM Changed |  | 2025-03-14 | 2025-03-06 |  | Tower | 45m 3 Legged Tower | 54 | Reuse Existing RRU | 0 | 0
9294A | Marudi | Sarawak |  | Remote MOCN | Modernization->On Hold->Maintain USP MOCN->Remote MOCN | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860566 | [6 empty] | Tower |  | Reuse Existing RRU | 0 | 0
7006A | Weston Town | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2025 Q2 | AD | DATASCO | 4.6 TSSR Approved |  | 2025-01-13 | 2025-03-21 |  | 2025-03-27 |  | Under Approval | 2025-03-27 | 2025-04-28 | E//Hannah | 2025-04-02 | SQ202501020331 - Datasco | DU00002860567 |  |  | 2025-05-04 | 2025-04-24 |  | Tower | Tower | 60 | Add R8852E S9000x2+R8894E M1821x4, Dismantle R8882-GUL1812x2+R8862A S1800(B6A)x1+R8854D S2100(A4A)x4+R8892N M1821(BAB)x1 | 0 | 0
7010A | Kg Kayul | Sabah |  | Modernization |  | 131 single site mocn | MS | Seri Pancar | 4.6 TSSR Approved |  | 2023-11-02 | 2023-11-06 |  | 2024-08-20 |  | Under Approval | 2024-08-22 | 2024-08-26 |  | 2024-08-26 | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231221 | DU00002860568 |  |  | 2024-09-25 | 2024-09-14 |  | Tower | Tower | 76 | Add R8894E M1821 x6+R8854 S2600 x2,Dismantle R8882 S1800(B) x1+R8882 S1800B(B6B) x1+R8862A S1800(B6A) x2+R8862A S2100(A6A) x4+R8862A S2601(A6A) x2 | 0 | 14
7012A | Pakka Choon | Sabah |  | Modernization |  | 131 single site mocn | SH | YPTT | 4.6 TSSR Approved |  | 2023-11-14 | 2023-11-20 |  | 2024-09-06 |  | Under Approval | 2024-09-10 | 2024-09-19 | E//Hannah | 2024-09-12 | Celcom Digi_RAN-YPTT-Standard PR TSS-Sabah-20240813 | DU00002860569 |  |  | 2024-09-30 | 2024-09-23 |  | Tower | 60m 3 Legged Tower | 60 | Add R8862A S9000 x3+R9264H M901821 x1+A9732 M1821 x3,Dismantle R8894E M1821(A8A) x4 | 234
7013A | TMNKUDAT | Sabah |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | MS | YPTT | 4.6 TSSR Approved |  | 2023-11-14 | 2023-11-16 |  | 2024-11-01 |  | Closed | 2024-11-04 | 2024-11-22 | E//Hannah | 2024-11-21 | Celcom Digi_RAN-YPTT-Standard PR TSS-Sabah-20240813 | DU00002860570 |  |  | 2024-12-27 | 2024-12-09 |  | Tower | 45m 3 Legged Tower | 45 | Add R8862A S9000x3+A9732 M1821 x3, Dismantle R8854 S2600(A4A)x2+R8894E M1821(A8A)x3+R9224E M1821(AAB)x2 | 123 | 0
7015A | Kg. Bangau | Sabah |  | Modernization |  | 2025 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2023-11-01 | 2023-11-10 |  | 2025-02-18 |  | Under Approval | 2025-04-16 | 2025-05-21 | E//Hannah | 2025-05-07 | Celcom Digi_RAN-YPTT-Standard PR TSS-Sabah-20240813 | DU00002860571 |  |  | 2025-04-30 | 2025-04-24 |  | Tower | 60m 3 Legged Tower | 60 | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8882-GUL1812x2+R8862A S1800(B6A)x1+R8862A S2100(A6A)x3 | 0 | 0
9362A | Oya | Sarawak |  | Modernization | Modernization->On Hold->Modernization | 2025 Q2 | AI | Trintel | 4.6 TSSR Approved |  | 2025-02-26 | 2025-03-20 |  | 2025-03-25 |  | Closed | 2025-04-23 | 2025-05-21 | E//Hannah | 2025-05-09 | SQ202501070293-Trintel | DU00002860572 |  |  | 2025-05-24 | 2025-05-21 |  | Tower | Tower | 60 | Add R8894E M1821x2, Dismantal R8854E S1800(A6A)x3 | 0 | 13
7017A | Tambuluran | Sabah |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | MS | YPTT | 4.6 TSSR Approved |  | 2023-11-01 | 2023-11-29 |  | 2024-11-01 |  | Under Approval | 2024-11-04 | 2024-12-05 | E//Hannah | 2024-12-05 | Celcom Digi_RAN-YPTT-Standard PR TSS-Sabah-20240813 | DU00002860573 |  |  | 2024-12-21 | 2024-11-29 |  | Tower | 60m 3 Legged Tower | 60 | Add R8862A S9000x3+R8894E M1821x2+R8854 S2600x2, Dismantle R8860E-GU908x3+R8862A S2600(A4Ax2 | 0 | Rename sector ID, Bisector @new S23
7022A | RTM Layang-Layang | Sabah |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | SHA | GTSB | 4.6 TSSR Approved |  | 2024-11-27 | 2024-12-12 |  | 2024-12-17 |  | Under Approval | 2024-12-23 | 2025-03-10 | E//Yanie | 2025-01-21 | Celcom Digi_RAN GTSB-Standard PR TSS-Sabah-20241126 | DU00002860574 |  |  | 2025-12-21 | 2025-12-15 |  |  | 30m 3-legged tower | 60m | Add R8862A S9000x3+R8894E M1821x3, Dismantle R8860E-GU908x1+R8882-GUL1812x1+R8882 S1800B(B6B)x1+R8862A S1800(B6A)x1+R8840-U216x2+R8881 S2100x1 | 0 | 0
9542A | Beluru Town | Sarawak |  | Modernization | Modernization->On Hold->Modernization | 2025 Q3 | AI | Trintel | 4.6 TSSR Approved | Solution changed to bisector as per Li Jie email | 2025-02-21 | 2025-03-14 |  | 2025-03-21 |  | Closed | 2025-03-24 | 2025-04-29 | E//Hannah | 2025-04-28 | SQ202501070293-Trintel | DU00002860575 | Remarks: Solution TSSR/BOM Changed |  | 2025-07-06 | 2025-05-29 |  | Tower | Tower | 60 | Add R8894E M1821x1 | 0 | 0
9645B | Trusan | Sarawak |  | Remote MOCN | Modernization->On Hold->Modernization->Remote MOCN | 2025 Q2 |  | DATASCO | 14.0 TSSR Not Required (Reuse Existing BBU/RRU) |  | 2025-02-10 | 2025-10-24 |  |  |  | To be Submitted |  |  |  |  | SQ202501070453-Datasco | DU00002860576 | [5 empty] | Tower | Tower | 76 | Reuse Existing RRU | 0 | 0
9030B | Rambungan | Sarawak |  | Modernization | Modernization->On Hold->Modernization | 2024 Q2 | ZB | Magicell | 4.6 TSSR Approved |  | 2024-09-03 | 2024-09-05 |  | 2024-09-10 |  | Under Approval | 2024-09-10 | 2024-09-12 | E//Hannah | 2024-09-12 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20240123 | DU00002860577 |  |  | 2024-10-01 | 2024-09-20 |  | Tower | Tower | 80 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
7075A | Lazenda Warehouse | Sabah |  | Modernization |  | 2025 Q1 | SM | Datasco | 4.6 TSSR Approved |  | 2024-05-23 | 2024-06-06 |  | 2025-01-14 |  | Under Approval | 2025-01-20 | 2025-02-07 | E//Hannah | 2025-02-07 | 0920CD-Sabah-Datasco-BOQ Template (old contract) | DU00002860578 |  |  | 2025-02-14 | 2025-02-07 |  | In-Building System | 6m RT (Boom) | 6m | Add R8852E S9000x4+R9264M M1821x4, Dismantle R8882-GUL1812x1+R8882 S1800B(B6B)x3+R8862A S1800(B6A)x3+R8854D S2100(A4A)x4 | 0 | 0
7076A | Wisma Kosan | Sabah |  | Modernization |  | 2025 Q1 | SM | Datasco | 4.6 TSSR Approved |  | 2024-05-23 | 2024-05-23 |  | 2024-06-10 |  | Under Approval | 2025-01-15 | 2025-01-21 | E//Hannah | 2025-01-21 | S1MY2021071001WBF1-5645 | DU00002860579 | Remarks: Solution TSSR/BOM Changed |  | 2025-03-17 | 2025-03-06 |  | Minimast | 3m RT (Minimast) | 14 | Add R8852E S9000x3+R8894E M1821x5+R8854 S2600x2, Dismantle R8882-GUL1812x3+R8882 S1800B(B6B)x3+R8854D S2100(A4A)x3+R8862A S2600(A4A)x2 | 0 | 13
7078A | Foo Chow Association | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2025 Q1 | AD | Datasco | 4.6 TSSR Approved |  | 2024-05-23 | 2024-05-30 |  | 2025-01-11 |  | Under Approval | 2025-01-13 | 2025-02-18 | E//Hannah | 2025-02-07 | S1MY2021071001WBF1-5645 | DU00002860580 |  |  | 2025-03-04 | 2025-02-21 |  | Minimast | 3m RT (Minimast) | 12 | Add R8852E S9000x3+R9264M M1821x3+R8862A S2601x3, Dismantle R8882 S1800B(B6B)x3+R8882 S2600(B4A)x3+R8894E M1821(A8A)x3 | 0 | 0
7079A | Taman Fulliwa | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2025 Q1 | AI | Datasco | 4.6 TSSR Approved |  | 2024-05-23 | 2024-05-24 |  | 2024-06-12 |  | Closed | 2025-03-14 | 2025-03-28 | E//Hannah | 2025-03-14 | 0920CD-Sabah-Datasco-BOQ Template (old contract) | DU00002860581 | Remarks: Solution TSSR/BOM Changed |  | 2025-04-19 | 2025-03-21 |  | Minimast | 3m RT (Minimast) | 15 | Add R8852E S9000x3+R8894E M1821x1+R8854 S2600x1, Dismantle R8882-GUL1812x3+R8862A S2600(A4A)x1 | 0 | 2
7095A | Tomaco-Jln Segama | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-03-12 |  | 2025-03-19 |  | 2025-03-27 |  | 2025-04-22 | 2025-10-28 | E//Hannah | 2025-07-14 | SQ202503270530 - Futong | DU00002860582 |  |  |  |  | 2025-08-27 |  | 12m MBTS |  | Add R8852E S9000x3+R8854E S1800x3+R8894E M1821x1, Dismantle R8862A S9000(A6A)x3+R8882 S1800(B)x1 | 0 | 12
9125R | SUNGAIPEKING | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860583 | [6 empty] | #N/A
9103R | LONGTERAWAN | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860584 | [6 empty] | #N/A
7100A | Muhibbah | Sabah |  | Modernization |  | 2024 Q3 | MS | GTSB | 4.6 TSSR Approved |  | 2023-10-18 | 2023-10-30 |  | 2023-11-03 |  | Closed | 2024-04-19 | 2024-05-29 | E//Hannah | 2024-05-29 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231019 | DU00002860585 |  |  | 2024-06-06 | 2024-05-25 |  | Tower | 30m 3-legged tower | 45 | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8862A S2600(A4A) x2+R9224E M1821(AAB) x5 | 12 | 0
7101A | Agaseh-100Q4 | Sabah |  | Modernization |  | 2024 Q3 |  | GTSB | 4.6 TSSR Approved |  | 2023-10-26 | 2023-10-24 |  | 2023-10-26 |  | Closed | 2024-04-16 | 2024-04-24 | E//Hannah | 2024-04-24 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231028 | DU00002860586 |  |  | 2024-06-15 | 2024-05-24 |  |  | 3m RT (Minimast) | 30 | Add R8894E M1821 x2,Dismantle | 0 | 12
9050R | SGSTAPANG | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860587 | [6 empty] | #N/A
7107A | Felda Sahabat (Maxis) | Sabah |  | Modernization |  | 2024 Q3(single site MOCN) | MS | GTSB | 4.6 TSSR Approved |  | 2023-10-26 | 2024-05-02 |  | 2024-07-04 |  | Under Approval | 2024-07-11 | 2024-08-07 | E//Hannah | 2024-08-05 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231028 | DU00002860588 |  |  | 2024-08-30 | 2024-08-20 |  | Tower | 90m 4 Legged Tower | 92 | Add R8894E M1821 x3,Dismantle | 0 | 123
7110A | Kg Melewar | Sabah |  | Modernization |  | 2024 Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-12-15 | 2024-01-09 |  | 2024-07-19 |  | Under Approval | 2024-07-23 | 2024-08-02 | E//Hannah | 2024-07-30 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231218 | DU00002860589 |  |  | 2024-10-12 | 2024-08-13 |  | Tower | Tower | 60 | Add R8894E M1821 x2+R8854 S2600 x2,Dismantle R8862A S2600(A4A) x2 | 0 | 12
7113A | Kimanis | Sabah |  | Modernization |  | 2025 Q2 | SM | Seri Pancar | 4.6 TSSR Approved |  | 2023-11-01 | 2023-11-08 |  | 2025-01-16 |  | Rectificating | 2025-03-10 | 2025-05-27 | E//Hannah | 2025-03-17 | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231221 | DU00002860590 |  |  | 2025-05-11 | 2025-04-11 |  | Tower | 45m 3 Legged Tower | 60m | Add R8852E S9000x3 | 0 | 23
9557A | Kg Bakong | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860591 | [6 empty] | 76m 3 Legged Tower
7124A | Trig Hill | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2024 Q3 | AD | Datasco | 4.6 TSSR Approved |  | 2024-04-21 | 2024-05-02 |  | 2024-05-07 |  | Under Approval | 2024-05-08 | 2024-07-23 | E//Hannah | 2024-07-19 | Celcom Digi_RAN-Datasco-Standard PR TSS-Sabah-20240503 | DU00002860592 |  |  | 2024-08-23 | 2024-08-02 |  | Tower | 76m 4 Legged Tower | 90 | Add R8862A S9000 x2+R9264H M901821 x2+R8862A S2601 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 12
7125A | Wisma Harbour | Sabah |  | Modernization |  | 2024 Q3 | MS | YPTT | 4.6 TSSR Approved | PE Analysis | 2024-03-15 | 2024-06-13 |  | 2024-06-19 |  | Under Approval | 2024-06-20 | 2024-07-04 | E//Hannah | 2024-07-04 | Celcom Digi_RAN-YPTT-TSS-Sabah-20240324 | DU00002860593 |  |  | 2024-12-26 | 2024-12-12 |  | In-Building System | 3m Boom (RT) | 3 | Add R8862A S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 23 | 0
7126A | Bandar Kim Fung | Sabah |  | Modernization |  | 2024 Q3 | AD | Datasco | 4.6 TSSR Approved |  | 2024-03-31 | 2024-04-05 |  | 2024-04-23 |  | Closed | 2024-05-02 | 2024-05-08 | E//Hannah | 2024-05-03 | Celcom Digi_RAN-Datasco-Standard PR TSS-Sabah-20240406 | DU00002860594 |  |  | 2024-06-23 | 2024-06-20 |  | Minimast | 3m RT (Minimast) | 12m | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R9224E M1821(AAB) x3 | 13 | 0
7145A | Taman Fajar Sandakan Airport(M | Sabah |  | Decomm | Modernization->On Hold->Modernization->Decomm | 2024 Q3 | AD | Datasco | 4.6 TSSR Approved | 2/5: Handing to prepare slides for solution downgrade proposal | 2024-04-18 | 2024-04-24 |  | 2024-05-28 | 2025-06-05 | Under Approval | 2025-06-06 | 2025-10-30 | E//Hannah | 2025-10-30 | Celcom Digi_RAN-Datasco-Standard PR TSS-Sabah-20240420 | DU00002860595 |  |  |  |  | 2025-11-14 | Tower | 60m 4 Legged Tower | 60 | Reuse RRU | 0 | 123
9567A | RH Sikun | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860596 | [6 empty] | 45m 3 Legged Tower
7146A | Masjid Sandakan | Sabah |  | Modernization |  | 2024 Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2024-03-14 | 2024-05-16 |  | 2024-05-20 |  | Closed | 2024-05-23 | 2024-05-30 | E//Hannah | 2024-05-30 | Celcom Digi_RAN-YPTT-TSS-Sabah-20240324 | DU00002860597 |  |  | 2024-07-04 | 2024-06-19 |  | In-Building System | 30m Minaret | 59 | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R9224E M1821(AAB) x2 | 1 | 0
9506B | Telok Melano | Sarawak |  | Modernization | Modernization->On Hold->Modernization | 2024 Q2 | AI | Magicell | 4.6 TSSR Approved |  | 2025-03-06 | 2025-03-13 |  | 2025-03-17 |  | Closed | 2025-03-19 | 2025-04-15 | E//Hannah | 2025-04-07 | SQ202503170571-Magicell | DU00002860598 | Remarks: Solution TSSR/BOM Changed |  | 2025-07-06 | 2025-06-09 |  | Tower | Tower | 45 | Add R8894E M1821x1, Dismantle R8854E S1800(A6A)x3 | 0 | 3
9569A | Bintulu Lumber Devlmpt (BLD) | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860599 | [6 empty] | 45m 3 Legged Tower
9075R | T3_0224 - KG JEGOI | Sarawak |  | Maintain USP MOCN(Dismantle Passive) | Maintain USP MOCN(Dismantle Passive)->On Hold->Maintain USP MOCN(Dismantle Passive) | 2024 Q2 | AD | GCI | 4.6 TSSR Approved |  | 2025-07-18 |  | 2025-10-13 |  | 2025-10-15 |  | 2025-10-17 | 2025-10-31 | E//John | 2025-10-21 | SQ202506110086&SQ202507140574-GCI | DU00002860600 |  |  |  |  | 2025-10-23 |  | #N/A
7183A | Tenom Town | Sabah |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | MS | Futong | 4.6 TSSR Approved |  | 2024-10-22 | 2024-10-23 |  | 2024-10-30 |  | Closed | 2024-11-04 | 2024-11-11 | E//Hannah | 2024-11-07 | S1MY2024071007WBF1-186 | DU00002860601 |  |  | 2024-11-22 | 2024-11-22 |  | In-Building System | 45m 3 Legged Tower | 6m | Add A9732 M1821x2, Dismantle R8894E M1821(A8A)x2 | 23 | 0
9558A | Kg Braya | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860602 | [6 empty] | 45m 3 Legged Tower
9561A | RH Ranggong | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860603 | [6 empty] | 45m 3 Legged Tower
9565A | Kg Iran | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860604 | [6 empty] | 45m 3 Legged Tower
9566A | Kg Baru | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860605 | [6 empty] | 45m 3 Legged Tower
9568A | RH Mat | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860606 | [6 empty] | 45m 3 Legged Tower
9570A | RH Kupang | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860607 | [6 empty] | 45m 3 Legged Tower
9571A | RH Suyong | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860608 | [6 empty] | 45m 3 Legged Tower
9572A | Kg Pelapi | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860609 | [6 empty] | 45m 3 Legged Tower
9573A | Kuala Sibuti | Sarawak |  | Remote MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN->Modernization->Remote MOCN | 2025 Q2 | AD | Trintel | 14.0 TSSR Not Required (Reuse Existing BBU/RRU) |  | 2025-02-28 | 2025-04-15 |  | 2025-04-19 |  | Under Approval | 2025-04-21 | 2025-10-03 | E//John | 2025-09-29 | SQ202501070293-Trintel | DU00002860610 | [5 empty] | Tower | 45m 3 Legged Tower | 60 | Reuse Existing RRU | 0 | 0
9574A | Kg Kejapil | Sarawak |  | Remote MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN->Modernization->Remote MOCN | 2025 Q2 |  | Trintel | 14.0 TSSR Not Required (Reuse Existing BBU/RRU) | [6 empty] | To be Submitted | [5 empty] | DU00002860611 | [6 empty] | 76m 3 Legged Tower |  | Reuse Existing RRU | 0 | 0
7213A | SFI Sipitang | Sabah |  | Decomm | Modernization->On Hold->Decomm | 2025 Q1 | MS | Seri Pancar | 4.6 TSSR Approved |  | 2023-10-27 | 2023-11-01 | 2024-08-08 | 2023-11-03 | 2024-08-26 | Under Approval | 2024-08-28 | 2024-11-29 | E//Hannah | 2024-11-29 | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231221 / SQ202501020446 - Seri Pancar | DU00002860612 |  |  |  |  | 2025-02-26 | Tower | 60m 3 Legged Tower | 60 | Add R8852E S9000x1+R8894E M1821x2+R8854 S2600x1 | 0 | 1
9559A | RH Undian | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860613 | [6 empty] | 76m 3 Legged Tower
9540A | Mile 38 Miri Niah Road | Sarawak |  | Remote MOCN | Modernization->On Hold->Maintain USP MOCN->Remote MOCN | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860614 | [6 empty] | Tower |  | Reuse Existing RRU | 0 | 0
7219A | Kg Merintaman | Sabah |  | Modernization |  | 2025 Q2 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2023-10-29 | 2023-11-01 |  | 2025-01-22 |  | Under Approval | 2025-02-17 | 2025-03-09 | E//Hannah | 2025-03-19 | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231221 | DU00002860615 | Remarks: Solution TSSR/BOM Changed |  | 2025-04-12 | 2025-03-25 |  | Tower | Tower | 60 | Add R8852E S9000x4+R8894E M1821x5+R8854 S2600x1, Dismantle R8882-GUL1812x1+R8862A S1800(B6A)x2+R8862A S2100(A6A)x3 | 0 | 4
9562A | Kg Lajong | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860616 | [6 empty] | 45m 3 Legged Tower
9299C | Kampung Pemindahan Marudi | Sarawak |  | Modernization | Modernization->On Hold->Modernization | 2025 Q2 | AI | Trintel | 4.6 TSSR Approved |  | 2025-02-26 | 2025-04-09 |  | 2025-04-14 |  | Under Approval | 2025-04-17 | 2025-05-27 | E//Hannah | 2025-10-03 | SQ202501070293-Trintel | DU00002860617 |  |  | 2025-07-06 | 2025-06-23 |  | Monopole | Tower | 30m | Add R8894E M1821x1, Dismantle R8854E S1800(A6A)x3 | 0 | 1
9048C | Jalan Daro Tebaan | Sarawak |  | Remote MOCN | Modernization->On Hold->Maintain USP MOCN->Remote MOCN | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860618 | [6 empty] | 30m Monopole |  | Reuse Existing RRU | 0 | 0
3450A | PANDANJAYA1 | Central |  | Modernization |  | 2024 Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-28 | 2023-12-01 |  | 2024-01-20 |  | Closed | 2024-01-30 | 2024-02-06 | E//Sumitra | 2024-02-06 | CelcomDigi_RAN_GTSB_TSS_Central_20231201 | DU00002860619 |  |  | 2024-05-08 | 2024-05-06 |  | Minimast | 3m Bipod (RT) | 9m | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
9160R | COASTAL HIGHWAY #5 | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860620 | [6 empty] | #N/A
9163R | RH. LINGU | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860621 | [6 empty] | #N/A
9162R | KG BUNGAI | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860622 | [6 empty] | #N/A
9088R | Kg Selanyau | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860623 | [6 empty] | #N/A
9161R | HIGHWAY BEKENU MIRI-LAMBIR | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860624 | [6 empty] | #N/A
9166R | RUMAH SERING | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860625 | [6 empty] | #N/A
7949A | Menggaris | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860626 | [6 empty] | Tower |  | Reuse Existing RRU | 0 | 0
7326A | Kg Matupang | Sabah |  | Site Out (Modernization) | Modernization->On Hold->Modernization->Site Out->Replacement, Site Out (Modernization) | 2024 Q4 | AD | Futong | [SiteOut]- 4.5 Pending TSSR Review - Customer |  | 2025-01-07 | 2025-01-13 |  | 2025-01-18 |  | Under Approval | 2025-01-20 |  |  |  | SQ202501020392 - Futong | DU00002860627 | Remarks: Solution TSSR/BOM Changed |  |  |  |  | Tower | Tower | 76m | Reuse Existing RRU | 0 | 0
7321A | Jln Marakau Ranau | Sabah |  | Modernization |  | 2024 Q3(single site MOCN) | AD | Futong | 4.6 TSSR Approved |  | 2024-02-14 | 2024-02-15 |  | 2024-06-21 |  | Under Approval | 2024-06-25 | 2024-07-04 | E//Hannah | 2024-07-04 | Celcom Digi_RAN-Futong-Standard PR TSS-Sabah-20240220 | DU00002860628 |  |  | 2024-07-22 | 2024-07-15 |  | Tower | Tower | 76 | Add A9732 M1821 x1,Dismantle R8894E M1821(A8A) x1 | 3 | 0
7120R | PONTIAN | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2025-07-12 |  | 2025-07-14 |  | 2025-07-15 |  | 2025-09-10 | 2025-09-20 | E//Hannah | 2025-09-16 | SQ202506100849 - GTSB / SQ202507010442 - GTSB | DU00002860629 |  |  |  |  | 2025-09-26 |  | #N/A
7189A | Simpangan | Sabah |  | Modernization | Modernization->On Hold->Maintain USP MOCN->Modernization | 2025 Q2 | AD | YPTT | 4.6 TSSR Approved |  | 2025-06-09 | 2025-06-09 |  | 2025-06-11 |  | Under Approval | 2025-06-13 | 2025-09-20 | E//Hannah | 2025-07-02 | SQ202506100756 - YPTT | DU00002860630 |  |  | 2025-07-06 | 2025-06-30 |  | Tower | 60m 3 Legged Tower | 60 | Add R8894E M1821x3 | 0 | 123
7524A | Kg. Lumat | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2025 Q2 | AD | DATASCO | 4.6 TSSR Approved |  | 2025-02-05 | 2025-03-13 |  | 2025-03-20 |  | Under Approval | 2025-03-22 | 2025-04-14 | E//Hannah | 2025-04-02 | SQ202501020331 - Datasco | DU00002860631 |  |  | 2025-04-14 | 2025-04-10 |  | Tower | Tower | 60 | Add R8894E M1821x1, Dismantle R8854E S1800(A6A)x3 | 0 | 3
7008A | Kota Klias | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2025 Q2 | AD | DATASCO | 4.6 TSSR Approved |  | 2025-01-13 | 2025-03-12 |  | 2025-03-18 |  | Under Approval | 2025-03-22 | 2025-04-16 | E//Hannah | 2025-04-07 | SQ202501020331 - Datasco | DU00002860632 |  |  | 2025-05-11 | 2025-04-10 |  | Tower | Tower | 60 | Add R8894E M1821x2, Dismantal R8854E S1800(A6A)x3 | 0 | 13
7697A | Sindumin (REL) | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2025 Q2 | AD | DATASCO | 4.6 TSSR Approved |  | 2025-01-17 | 2025-03-03 |  | 2025-03-07 |  | Under Approval | 2025-03-10 | 2025-03-28 | E//Hannah | 2025-03-19 | SQ202501020331 - Datasco | DU00002860633 |  |  | 2025-03-27 | 2025-03-21 |  | Tower | Tower | 60 | Add R8894E M1821x1 | 0 | 1
7363A | Kg Pimping | Sabah |  | Modernization |  | 2025 Q2 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2023-10-31 | 2024-05-27 |  | 2025-01-22 |  | Under Approval | 2025-03-03 | 2025-04-11 | E//Hannah | 2025-03-17 | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231221 | DU00002860634 |  |  | 2025-04-10 | 2025-04-08 |  | Tower | Tower | 60 | Add R8894E M1821x1 | 0 | 3
7043R | SILABUKAN | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2025-07-12 |  | 2025-07-16 |  | 2025-07-17 |  | 2025-09-10 | 2025-09-20 | E//Hannah | 2025-09-16 | SQ202506100849 - GTSB / SQ202507010442 - GTSB | DU00002860635 |  |  |  |  | 2025-10-31 |  | #N/A
7044R | KGPARIS | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2025-07-10 |  | 2025-07-14 |  | 2025-07-15 |  | 2025-09-10 | 2025-09-20 | E//Hannah | 2025-09-16 | SQ202506100849 - GTSB / SQ202507010442 - GTSB | DU00002860636 |  |  |  |  | 2025-10-31 |  | #N/A
7119R | KGNABUTAN | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2025 | AD | YPTT | 4.6 TSSR Approved |  | 2025-08-11 |  | 2025-08-13 |  | 2025-08-16 |  | 2025-09-09 | 2025-10-29 | E//Hannah | 2025-09-18 | SQ202506100836 - YPTT / SQ202507010450 - YPTT | DU00002860637 |  |  |  |  | 2025-09-26 |  | #N/A
7083R | TAKON | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2025-07-13 |  | 2025-07-14 |  | 2025-07-15 |  | 2025-10-06 | 2025-10-31 |  | 2025-10-22 | SQ202506100849 - GTSB / SQ202507010442 - GTSB | DU00002860638 |  |  |  |  | 2025-11-25 |  | #N/A
7380B | Kg Sharif (Celcom) | Sabah |  | Modernization |  | 2024 Q3 | MS | GTSB | 4.6 TSSR Approved |  | 2023-10-23 | 2023-10-30 |  | 2023-11-03 |  | Closed | 2024-04-15 | 2024-05-29 | E//Hannah | 2024-05-29 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231024 | DU00002860639 |  |  | 2024-06-07 | 2024-05-24 |  | Tower | 76m 3 Legged Tower | 60m | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123 | 0
7081R | S102A_S00118OD_KGKANIBONGAN | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2025 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2025-06-13 |  | 2025-06-18 |  | 2025-06-19 |  | 2025-10-29 | 2025-12-04 | E//Hannah | 2025-11-25 | SQ202506100836 - YPTT / SQ202507010450 - YPTT | DU00002860640 |  |  |  |  | 2025-10-30 |  | #N/A
7121R | TMPITAS | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2025 Q3 |  | GTSB | 15.3 Decomm Done without TSSR | [6 empty] | To be Submitted |  |  |  |  | SQ202509220684 -GTSB | DU00002860641 |  |  |  |  | 2025-11-30 |  | #N/A
7391A | Kg Nangka | Sabah |  | Modernization |  | 2025 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2023-11-01 | 2023-11-21 |  | 2025-02-18 |  | Under Approval | 2025-03-24 | 2025-05-21 | E//Hannah | 2025-04-16 | Celcom Digi_RAN-YPTT-Standard PR TSS-Sabah-20240813 | DU00002860642 |  |  | 2025-04-26 | 2025-04-12 |  | Tower | Tower | 60 | Add R8852E S9000x3+R8894E M1821x4+R8854 S2600x1, Dismantle R8882-GUL1812x3+R8862A S2100(A6A)x3+R8862A S2601(A6A)x1 | 0 | 1
7113R | JERAGANBISTARI | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2025-07-14 |  | 2025-07-14 |  | 2025-07-15 |  | 2025-08-08 | 2025-09-20 | E//Hannah | 2025-09-16 | SQ202506100849 - GTSB / SQ202507010442 - GTSB | DU00002860643 |  |  |  |  | 2025-11-25 |  | #N/A
7084R | TGLABIAN | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2025-07-14 |  | 2025-07-16 |  | 2025-07-17 |  | 2025-08-08 | 2025-10-31 | E//Hannah | 2025-09-24 | SQ202506100849 - GTSB / SQ202507010442 - GTSB | DU00002860644 |  |  |  |  | 2025-10-31 |  | #N/A
7985B | Kg Muruk | Sabah |  | Modernization | Modernization->On Hold->Maintain USP MOCN->Modernization | 2025 Q3 | AD | YPTT | 4.6 TSSR Approved | 12/8 - wrong site key, CD to check the right key // 8/8 - Monday 11/8 target close TSS // 5/8- New Assignment to subcon YPTT,Wk34 plan | 2025-09-12 | 2025-09-22 |  | 2025-09-24 |  | Under Approval | 2025-09-25 | 2025-10-13 | E//Hannah | 2025-09-30 | SQ202508040374 - YPTT | DU00002860645 |  |  | 2025-10-03 | 2025-09-30 |  | Tower | 30m Monopole | 76 | Dismantle R8862A S9000(A6A)x3+R8854E S1800(A6A)x3 | 0 | 0
7052R | T3_0879 - BUKIT KIMANDAU | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2025 Q3 | AD | GCI | 4.6 TSSR Approved |  | 2025-11-24 |  | 2025-12-04 |  | 2025-12-04 | To be Submitted | 2026-04-24 |  | E//Faiz | 2026-05-08 | SQ202602230361 - GCI | DU00002860646 |  |  |  |  | 2025-11-21 |  | #N/A
7407A | Kg.Taginambur | Sabah |  | Modernization |  | 2024 Q3(single site MOCN) | AD | Futong | 4.6 TSSR Approved |  | 2023-10-25 | 2023-11-01 |  | 2023-11-02 |  | Closed | 2024-05-03 | 2024-06-06 | E//Hannah | 2024-06-06 | Celcom Digi_RAN-Futong-TSS-Sabah-20231028 | DU00002860647 |  |  | 2024-07-11 | 2024-07-11 |  |  | 75m 3 Legged Tower | 70 | Add A9732 M1821 x1,Dismantle R8894E M1821(A8A) x1 | 2 | 0
7074R | T3_0878 - KG MERUNGIN | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860648 | [6 empty] | #N/A
7429B | Simpang Ladang Sandau | Sabah |  | Remote MOCN | Modernization->On Hold->Modernization->Remote MOCN | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-02-04 | 2025-02-07 |  | 2025-02-10 |  | Under Approval | 2025-02-18 | 2025-03-09 | E//Hannah | 2025-02-26 | SQ202501020392 - Futong | DU00002860649 | Remarks: Solution TSSR/BOM Changed |  |  |  |  | Tower | Tower | 65m | Reuse Existing RRU | 0 | 0
7123R | KGRUKOMLUYONG | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2025 Q3 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2025-05-13 |  | 2025-06-16 |  | 2025-10-17 |  | 2025-10-22 | 2025-10-27 | E//Hannah | 2025-10-23 | SQ202508130660 - Seri Pancar | DU00002860650 |  |  |  |  | 2025-10-31 |  | #N/A
7071R | T3_0076 - KG DUDAR (KG TABURAN) | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860651 | [6 empty] | #N/A
7079R | KG. RANGGAL | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860652 | [6 empty] | #N/A
7105R | KG. LAUT TANDAWAN | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860653 | [6 empty] | #N/A
7106R | KG. DELIMA | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2025 | AD | YPTT | 4.6 TSSR Approved |  | 2025-07-18 |  | 2025-07-21 |  | 2025-07-21 |  | 2025-09-09 | 2025-10-29 | E//Hannah | 2025-09-18 | SQ202506100836 - YPTT / SQ202507010450 - YPTT | DU00002860654 |  |  |  |  | 2025-10-10 |  | #N/A
7049R | LABAN RATA | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2025 Q3 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2025-12-22 |  |  |  | 2025-12-29 |  | 2025-12-31 | 2026-01-19 | E//Ali | 2026-01-08 |  | DU00002860655 |  |  |  |  | 2025-12-23 |  | #N/A
7117R | KGKIBBAS | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2025 | AD | YPTT | 4.6 TSSR Approved |  | 2025-08-11 |  | 2025-08-13 |  | 2025-08-19 |  | 2025-09-09 | 2025-10-29 | E//Hannah | 2025-09-18 | SQ202506100836 - YPTT / SQ202507010450 - YPTT | DU00002860656 |  |  |  |  | 2025-09-24 |  | #N/A
7139Z | Kg Taburan | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860657 | [6 empty] | #N/A
7091R | BUKIT IJAI | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2025 Q3 | AD | NR services | 4.6 TSSR Approved |  | 2025-10-02 |  | 2025-10-01 |  | 2025-10-02 |  | 2025-10-07 | 2025-10-29 | E//Hannah | 2025-10-21 | SQ202509220701 - NR Service | DU00002860658 |  |  |  |  | 2025-10-29 |  | #N/A
7101R | KG TALAMANSON | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2025 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2025-09-26 |  | 2025-10-03 |  | 2025-10-04 |  | 2025-10-22 | 2025-10-29 | E//Hannah | 2025-10-27 | SQ202506100836 - YPTT / SQ202507010450 - YPTT | DU00002860659 |  |  |  |  | 2025-10-28 |  | #N/A
7952A | USP Kg.Marakparak | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2025 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2025-01-23 | 2025-02-26 |  | 2025-03-21 |  | Under Approval | 2025-03-28 | 2025-05-21 | E//Hannah | 2025-04-18 | SQ202501020343 - GTSB | DU00002860660 |  |  | 2025-07-06 | 2025-05-22 |  | Tower | 60m 4 Legged Tower | 60 | Add R9224E M1821x1, Dismantle R8854E S1800(A6A)x3 | 0 | 1
7070R | T3_0094 - KG SAYAP | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860661 | [6 empty] | #N/A
7504B | Ladang Hassan | Sabah |  | Remote MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN->Modernization->Remote MOCN | 2024 Q4 |  |  | 14.0 TSSR Not Required (Reuse Existing BBU/RRU) | [6 empty] | To be Submitted | [5 empty] | DU00002860662 | [6 empty] | 76m Tower |  | Reuse Existing RRU | 0 | 0
7455B | Rancangan Sg. Manila (Celcom) | Sabah |  | Modernization |  | 2024 Q4 | MS | Futong | 4.6 TSSR Approved |  | 2024-03-14 | 2024-03-21 |  | 2024-04-04 |  | Closed | 2024-04-05 | 2024-06-21 | E//Hannah | 2024-06-06 | Celcom Digi_RAN-Futong-TSS-Sabah-20240324 | DU00002860663 |  |  | 2024-06-10 | 2024-06-04 |  | Tower | Tower | 60 | Add R8862A S9000 x3+R8894E M1821 x2+R8854 S2600 x2,Dismantle R8862A S2600(A4A) x2 | 0 | 13
7055Z | T3_Bulusbikang | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860664 | [6 empty] | #N/A
7486A | Kg Sg Lada-100Q4(TMTouch) | Sabah |  | Modernization |  | 2025 Q1 | AI | Datasco | 4.6 TSSR Approved |  | 2024-05-28 | 2024-06-06 |  | 2025-01-11 |  | Closed | 2025-01-21 | 2025-02-27 | E//Hannah | 2025-02-24 | 0920CD-Sabah-Datasco-BOQ Template (old contract) | DU00002860665 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed | 2025-03-30 | 2025-02-18 |  | Tower | 60m 4 Legged Tower | 60 | Add R8852E S9000x3+R8894E M1821x2+A9732 M1821x1, Dismantle R8860E-GU908x3+R8882 S1800B(B6B)x3+R8854D S2100(A4A)x3 | 3 | 0
7487A | Kompleks Kastam | Sabah |  | Modernization |  | 2025 Q1 | SM | Datasco | 4.6 TSSR Approved |  | 2024-05-23 | 2024-06-07 |  | 2025-01-11 |  | Under Approval | 2025-01-13 | 2025-02-07 | E//Hannah | 2025-02-07 | 0920CD-Sabah-Datasco-BOQ Template (old contract) | DU00002860666 |  |  | 2025-02-26 | 2025-02-18 |  | Tower | 45m 3 Legged Tower | 45 | Add R8852E S9000x3+R8894E M1821x2+R8854 S2600x2, Dismantle R8862A S2600(A4A)x2 | 0 | 23
7068Z | T3_Kg Ulu Dusun | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860667 | [6 empty] | #N/A
7062Z | T3_Silabukan Forest Reserve | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860668 | [6 empty] | #N/A
7070Z | Division 10 Tomaco | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860669 | [6 empty] | #N/A
7066Z | T3_Old Dam Road | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860670 | [6 empty] | #N/A
7061Z | T3_kg Jawa | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860671 | [6 empty] | #N/A
7073Z | T3_Kg Kadumu | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860672 | [6 empty] | #N/A
7071Z | T3_Kg Silam Lamak | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860673 | [6 empty] | #N/A
7072Z | T3_Ulu Segama | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860674 | [6 empty] | #N/A
7074Z | T3_Kg. Sri Putatan | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860675 | [6 empty] | #N/A
7506A | Ulu Sapi (Celcom) | Sabah |  | Modernization |  | 2024 Q3(single site MOCN) | AD | GTSB | 4.6 TSSR Approved | Solution changed MM>Bi | 2024-04-08 | 2024-04-25 |  | 2024-06-26 |  | Rectificating | 2024-07-01 | 2024-08-19 | E//Hannah | 2024-08-19 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240420 | DU00002860676 |  |  | 2024-09-09 | 2024-08-24 |  | Tower | 76m 4 Legged Tower | 75m | Add R8894E M1821 x3+R8854 S2600 x3,Dismantle | 0 | 123
7059Z | T3_Kg Segama | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860677 | [6 empty] | #N/A
7063Z | T3_Kg Pantai | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860678 | [6 empty] | #N/A
7058Z | T3_S. Tungku | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860679 | [6 empty] | #N/A
7511A | KEMBARA SAKTI(CELCOM) | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-03-16 |  | 2025-03-20 |  | 2025-03-27 | To be Submitted | 2025-04-22 | 2026-04-01 | E//Hannah | 2025-07-14 | SQ202503270530 - Futong | DU00002860680 |  |  |  |  | 2026-01-30 |  | 76m 4 Legged Tower
7065Z | T3_Division 11 Tomaco | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860681 | [6 empty] | #N/A
7513A | Taman Fajar | Sabah |  | Modernization |  | 2024 Q3 | MS | GTSB | 4.6 TSSR Approved |  | 2023-10-18 | 2023-10-30 |  | 2024-04-17 |  | Closed | 2024-04-25 | 2024-05-29 | E//Hannah | 2024-05-29 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231019 | DU00002860682 |  |  | 2024-06-04 | 2024-05-23 |  | In-Building System | 6m Unipole RT | 6M | Add R8862A S9000 x1+R8894E M1821 x3,Dismantle | 0 | 234
3430A | TMN_MAWAR1 | Central |  | Modernization |  | 2024 Q3 | AI | YPTT | 4.6 TSSR Approved |  | 2024-06-04 | 2024-06-14 |  | 2024-06-18 |  | Closed | 2024-07-02 | 2024-07-04 | E//Sumitra | 2024-07-04 | 0607Central-YPTT-BOQ Template | DU00002860683 |  |  | 2024-07-26 | 2024-07-26 |  | In-Building System | 30m Monopole | 6 | Add R8862A S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 23 | 0
7516A | Kg.Kokos | Sabah |  | Modernization |  | 2024 Q3(single site MOCN) | AD | GTSB | 4.6 TSSR Approved |  | 2023-10-23 | 2023-10-23 |  | 2024-06-21 |  | Under Approval | 2024-06-25 | 2024-07-04 | E//Hannah | 2024-07-04 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231024 | DU00002860684 |  |  | 2024-08-09 | 2024-07-15 |  | Tower | Tower | 75 | Add A9732 M1821 x2,Dismantle R8894E M1821(A8A) x2 | 23 | 0
7517A | Kg Wawasan (Celcom) | Sabah |  | Modernization |  | 2024 Q3(single site MOCN) | AD | GTSB | 4.6 TSSR Approved |  | 2023-10-23 | 2023-10-25 |  | 2024-07-09 |  | Under Approval | 2024-07-10 | 2024-07-19 | E//Hannah | 2024-07-19 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231024 | DU00002860685 |  |  | 2024-09-06 | 2024-08-22 |  | Tower | 60m 3 Legged Tower | 60M | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 12 | 0
7064Z | T3_Simpang Bakapit | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860686 | [6 empty] | #N/A
7056Z | T3_Ladang Timora | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860687 | [6 empty] | #N/A
7555A | Batu Sapi Bypass | Sabah |  | Modernization |  | 2024 Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2024-03-15 | 2024-04-20 |  | 2024-04-26 |  | Closed | 2024-04-26 | 2024-05-02 | E//Hannah | 2024-05-02 | Celcom Digi_RAN-YPTT-TSS-Sabah-20240324 | DU00002860688 |  |  | 2024-06-25 | 2024-06-18 |  | Tower | 60m 3 Legged Tower | 60 | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x5 | 123 | 0
7557A | Taman Merpati | Sabah |  | Modernization |  | 2024 Q3 | AD | Datasco | 4.6 TSSR Approved |  | 2024-04-19 | 2024-04-25 |  | 2024-05-01 |  | Closed | 2024-05-02 | 2024-05-13 | E//Hannah | 2024-05-13 | Celcom Digi_RAN-Datasco-Standard PR TSS-Sabah-20240420 | DU00002860689 |  |  | 2024-06-27 | 2024-06-18 |  | Tower | 45m 4 Legged Tower | 45m | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x3+R9224E M1821(AAB) x6 | 123 | 0
7567A | Taman Sibuga (Maxis) | Sabah |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | MS | Futong | 4.6 TSSR Approved | Solution downgrade. MM to Bisector study | 2024-03-23 | 2024-03-29 |  | 2024-04-22 |  | Closed | 2024-09-23 | 2024-12-05 | E//Hannah | 2024-12-05 | Celcom Digi_RAN-Futong-TSS-Sabah-20240329 | DU00002860690 |  |  | 2025-02-20 | 2025-01-25 |  | Tower | 60m 3 Legged Tower | 60 | Add R9264H M901821 x4+R8854 S2600x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x2+R8862A S2100(A6A) x4+R8862A S2600x3 | 0 | 234
7573A | KG Cecily | Sabah |  | Modernization |  | 2024 Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2024-03-14 | 2024-04-20 |  | 2024-04-25 |  | Closed | 2024-04-26 | 2024-10-04 | E//Hannah | 2024-10-04 | Celcom Digi_RAN-YPTT-TSS-Sabah-20240324 | DU00002860691 |  |  | 2024-06-25 | 2024-06-18 |  | Tower | Tower | 60 | Add R8862A S9000 x3+R9224E M1821 x5+R8862A S2601 x2,Dismantle R8882-GUL1812 x3+R8840-U216 x3++ | 0 | 13
7587A | Pamol | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-04-14 |  | 2025-04-15 |  | 2025-04-22 | To be Submitted | 2025-04-28 | 2026-04-01 | E//Hannah | 2025-07-14 | SQ202504100583 - Futong | DU00002860692 |  |  |  |  | 2025-11-21 |  | 76m 3 Legged Tower
7600A | KM 50 Ulu Dusun | Sabah |  | Modernization |  | 2024 Q4 | MS | Futong | 4.6 TSSR Approved |  | 2024-03-19 | 2024-03-21 |  | 2024-04-05 |  | Closed | 2024-04-15 | 2024-06-21 | E//Hannah | 2024-06-06 | 0610Sabah-Futong-BOQ Template (template) | DU00002860693 |  |  | 2024-06-25 | 2024-06-04 |  | Tower | 45m 3 Legged Tower | 60 | Add R8862A S9000 x1+R9224E M1821 x5+R8862A S2601 x1,Dismantle R8882-GUL1812 x3 | 0 | 4
7072R | T3_0105 - KG.SARANG (KG DUDAR) | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860694 | [6 empty] | #N/A
7067R | T3_0085 - KG MELANGKAP (KG PURAK OGIS) | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860695 | [6 empty] | #N/A
7482B | Kg Tenagang | Sabah |  | Remote MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN->Modernization->Remote MOCN | 2024 Q4 |  |  | 14.0 TSSR Not Required (Reuse Existing BBU/RRU) | [6 empty] | To be Submitted | [5 empty] | DU00002860696 | [6 empty] | 76m 3 Legged Tower |  | Reuse Existing RRU | 0 | 0
7491B | Tung Hup | Sabah |  | Remote MOCN | Modernization->On Hold->Modernization->Remote MOCN | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-02-05 | 2025-02-10 |  | 2025-02-12 |  | Under Approval | 2025-02-18 | 2025-03-09 | E//Hannah | 2025-02-26 | SQ202501020392 - Futong | DU00002860697 | Remarks: Solution TSSR/BOM Changed |  |  |  |  | Tower | 76m 3 Legged Tower | 76m | Add R9264M M1821x4, Dismantle R8894E M1821(A8A)x3 | 0 | 3
7495B | Kg Takala | Sabah |  | Modernization | Maintain USP MOCN->On Hold->Maintain USP MOCN->Modernization | 2024 Q4 | HW | NR services | 4.6 TSSR Approved |  | 2025-05-02 | 2025-05-20 |  | 2025-05-22 |  | Under Approval | 2025-05-23 | 2025-06-16 | E//Hannah | 2025-06-10 | SQ202504140266 - NR Service | DU00002860698 |  |  | 2025-07-06 | 2025-06-11 |  | Tower | 76m 3 Legged Tower | 76 | Add R8894E M1821x1 | 0 | 2
7485B | Ladang Morisem | Sabah |  | Modernization | Modernization->On Hold->Maintain USP MOCN->Modernization | 2024 Q4 | HW | NR services | 4.6 TSSR Approved |  | 2025-05-14 | 2025-05-19 |  | 2025-05-22 |  | Under Approval | 2025-05-23 | 2025-06-25 | E//Hannah | 2025-05-30 | SQ202504220498 - NR Service | DU00002860699 |  |  | 2025-07-06 | 2025-06-11 |  | Tower | 76m 3 Legged Tower | 76 | Add R8894E M1821x1 | 0 | 2
7007A | Kg Kebidang | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2025 Q2 | AD | DATASCO | 4.6 TSSR Approved |  | 2025-01-09 | 2025-03-04 |  | 2025-03-07 |  | Under Approval | 2025-03-10 | 2025-03-28 | E//Hannah | 2025-03-19 | SQ202501020331 - Datasco | DU00002860700 |  |  | 2025-04-12 | 2025-03-25 |  | Tower | Tower | 60 | Add R8894E M1821x2, Dismantal R8854E S1800(A6A)x3 | 0 | 12
7493B | Morisem 2 | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860701 | [6 empty] | 60m 3 Legged Tower
7087Z | LinddaleEstate | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860702 | [6 empty] | 76m 4 Legged Tower
7090Z | TundunBohangin | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860703 | [6 empty] | 76m 4 Legged Tower
7104Z | T3E_0697_IOI Unico Desa Plantation | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860704 | [6 empty] | 76m 4 Legged Tower
7705A | Labuan Trunk | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2024 Q3(single site MOCN) | MS | Datasco | 4.6 TSSR Approved |  | 2024-05-23 | 2024-05-30 |  | 2024-09-25 |  | Under Approval | 2024-11-18 | 2024-12-05 | E//Syahriani | 2024-12-05 | Celcom Digi_RAN-Datasco-Standard PR TSS-Sabah-20240528 | DU00002860705 |  |  | 2024-12-07 | 2024-11-22 |  | Tower | 76m 4 Legged Tower | 60m | Add R9264H M901821 x3+A9732 M1821 x1,Dismantle R8860E-GU908 x1+R8882-GUL1812 x2+R8882 S1800B(B6B) x3+R8862A S1800(B6A) x2+R8862A S2100(A6A) x4 | 2 | 0
7102Z | T3E_0695_KgUpakUluSegama | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860706 | [6 empty] | 76m 4 Legged Tower
7146Z | Kg Dandun Pusat | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860707 | [6 empty] | #N/A
7815A | Sabah Hotel Indoor | Sabah |  | Modernization |  | 2024 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2024-03-25 | 2024-03-29 |  | 2024-04-22 |  | Rectificating | 2024-05-10 | 2024-05-16 | E//Hannah | 2024-05-16 | Celcom Digi_RAN-GTSB-TSS-Sabah-20240329 | DU00002860708 |  |  | 2025-06-15 | 2025-06-11 |  | In-Building System | IBS + 2m RT (Wall Mounted Pole) | 2 | Add R8862A S9000 x3+R9224E M1821 x3+R8862A S2601 x1,Dismantle R8882-GUL1812 x2+R8862A S2100(A6A) x2 | 0 | 0
7149Z | Kg Pahu | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860709 | [6 empty] | #N/A
7151Z | SK Nampasan | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860710 | [6 empty] | #N/A
7147Z | Kg Narawang | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860711 | [6 empty] | #N/A
7832A | Centrepoint Lahad Datu | Sabah |  | Modernization |  | 2024 Q3 | MS | GTSB | 4.6 TSSR Approved |  | 2023-10-26 | 2023-11-08 |  | 2024-04-06 |  | Closed | 2024-04-16 | 2024-05-16 | E//Hannah | 2024-05-16 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231028 | DU00002860712 |  |  | 2024-06-04 | 2024-05-23 |  | In-Building System | IBS + 3m RT (Wall Mounted Pole) | 7M | Add R8862A S9000 x3+A9732 M1821 x3,Dismantle R8894E M1821(A8A) x4 | 123 | 0
7944A | Kg. Pingan Pingan | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2025 Q3 | AD | NR services | 4.6 TSSR Approved |  | 2025-02-04 |  | 2025-03-12 |  | 2025-03-19 |  | 2025-04-30 | 2025-10-28 | E//Hannah | 2025-07-14 | SQ202504100592 - NR Service | DU00002860713 |  |  |  |  | 2025-08-11 |  | Tower
7153Z | Tiong Ratau | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860714 | [6 empty] | #N/A
7152Z | Tomis | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860715 | [6 empty] | #N/A
7011R | Kg Rungus Nahaba | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860716 | [6 empty] | #N/A
7020R | Turong Puteh | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860717 | [6 empty] | #N/A
7009R | Kg Kebatasan (Jln Pitas - Kanibongan_1) | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860718 | [6 empty] | #N/A
7028R | Kg Mengkapon Pitas | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860719 | [6 empty] | #N/A
7062R | T3_0095 - KG PAKA | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860720 | [6 empty] | #N/A
7075R | T3_0897 - KINABALU PARK | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860721 | [6 empty] | #N/A
7076R | T3_0899 - KG TIBABAR | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860722 | [6 empty] | #N/A
7481B | Kg Sri Ganda | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860723 | [6 empty] | 76m 3 Legged Tower
7498B | SK Sangau | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860724 | [6 empty] | 45m 3 Legged Tower
7128R | Kg Sosop Bai | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860725 | [6 empty] | #N/A
7124R | Kg Bilangau Kecil | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860726 | [6 empty] | #N/A
7125R | Kg Salungkapit | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860727 | [6 empty] | #N/A
7127R | Kg Pandan Mandamai | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860728 | [6 empty] | #N/A
7126R | Kg Tutuwoon | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860729 | [6 empty] | #N/A
7136R | Kg Naruntung | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860730 | [6 empty] | #N/A
7134R | Kg Ampungai | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860731 | [6 empty] | #N/A
7135R | Kg Petani Baru | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860732 | [6 empty] | #N/A
7133R | Kg Pituru | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860733 | [6 empty] | #N/A
7146R | Kg Bawing | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860734 | [6 empty] | #N/A
7060Z | T3_Simpang Jeragan | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860735 | [6 empty] | #N/A
7057Z | T3_Mercu Puspita | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860736 | [6 empty] | #N/A
7069Z | T3_Tabin Wildlife Reserve Area | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860737 | [6 empty] | #N/A
1204A | Tivoli | Central |  | Modernization |  | 2024 Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-24 | 2023-11-29 |  | 2024-01-08 |  | Rectificating | 2024-01-09 | 2024-01-11 | E//Kok Keen | 2024-01-10 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231126 | DU00002860738 |  |  | 2024-06-08 | 2024-06-06 |  | In-Building System | 3m Boom (RT) | 3 | Add R9264M M1821 x3,Dismantle R8882 S1800(B) x1+R8882 S1800B(B6B) x2++R8881 S2100 x3+
7486B | Sungai Pin | Sabah |  | Modernization |  | 2024 Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-12-15 | 2024-01-09 |  | 2024-07-19 |  | Closed | 2024-07-23 | 2024-07-26 | E//Hannah | 2024-07-26 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231218 | DU00002860739 |  |  | 2024-08-31 | 2024-08-12 |  | Tower | 76m 3 Legged Tower | 75 | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle | 0 | 1
3741B | Taman Desa Business Park | Central |  | Modernization |  | 2024 Q3 | XH | AllStar | 4.6 TSSR Approved |  | 2023-11-28 | 2023-11-30 |  | 2023-12-05 |  | Closed | 2023-12-05 | 2023-12-07 | E//Sumitra | 2023-12-07 | CelcomDigi_RAN_Allstar_TSS_Central_20231101 | DU00002860740 |  |  | 2024-04-04 | 2024-04-04 |  | Lampole | 18m Lampole | 18 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
3643C | Masjid Batiu 14 | Central |  | Modernization |  | 2024 Additional | SY1 | GCI | 4.6 TSSR Approved |  | 2023-10-25 | 2023-11-01 |  | 2024-05-13 |  | Closed | 2024-05-14 | 2024-05-21 | E//Sumitra | 2024-05-21 | CelcomDigi_RAN_GCI_TSS_Central_20231214 | DU00002860741 |  |  | 2024-06-03 | 2024-05-28 |  | Monopole | 25m Monopole | 25 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
1186C | Jalan Manis 4 Cheras | Central |  | Modernization |  | 2024 Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-11-10 | 2023-11-20 |  | 2024-04-03 |  | Closed | 2024-04-03 | 2024-04-15 | E//Sumitra | 2024-04-09 | CelcomDigi_RAN_Allstar_TSS_Central_20231113 | DU00002860742 |  |  | 2024-07-11 | 2024-07-11 |  | Monopole | 18m Lampole | 18 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
1571C | LRT Taman Bahagia | Central |  | Modernization |  | 2024 Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2023-12-06 | 2023-12-13 |  | 2024-04-02 |  | Closed | 2024-04-03 | 2024-04-04 | E//Kok Keen | 2024-04-03 | CelcomDigi_RAN_Magicell_TSS_Central_20231208 | DU00002860743 |  |  | 2024-11-21 | 2024-11-19 |  | In-Building System | 6m RT (Minimast) | 6 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
1148C | Jalan Shamelin Niaga 1 | Central |  | Modernization |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-02 | 2023-12-01 |  | 2024-03-25 |  | Under Approval | 2024-07-25 | 2024-08-06 | E//Sumitra | 2024-08-06 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231104 | DU00002860744 |  |  | 2024-05-30 | 2024-05-28 |  | Lampole | 18m Lampole | 18 | Add R9264H M1821 x3+R8854 S2600 x1,Dismantle R8862A S2600(A4A) x1+R8862A S2601(A6A) x1+R8892N M1821(BAB) x4 | 0 | 2
3765B | Jalan Sri Permaisuri 6 | Central |  | Modernization |  | 2024 Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-11-08 | 2023-11-17 |  | 2024-03-21 |  | Closed | 2024-03-25 | 2024-04-03 | E//Sumitra | 2024-04-02 | CelcomDigi_RAN_Allstar_TSS_Central_20231113 | DU00002860745 |  |  | 2024-05-06 | 2024-05-02 |  | Lampole | 18m Lampole | 18 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
3639C | Eaton International School - Jade Hill | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-10 | 2024-01-15 |  | 2024-04-25 |  | Closed | 2024-04-30 | 2024-05-09 | E//Sumitra | 2024-05-09 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240115 | DU00002860746 |  |  | 2024-07-02 | 2024-06-26 |  | Tower | 45m 3 Legged Tower | 45m | Add R8862A S9000 x4+R8894E M1821 x4,Dismantle R8862A S1800(B6A) x4+R8862A S2100(A6A) x4 | 0 | 0
3598C | Jalan Mesra Ria (REL) | Central |  | Modernization |  | 2024 Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-12-07 | 2023-12-15 |  | 2024-04-02 |  | Closed | 2024-04-02 | 2024-04-15 | E//Sumitra | 2024-04-09 | CelcomDigi_RAN_Allstar_TSS_Central_20231208 | DU00002860747 |  |  | 2024-05-20 | 2024-05-17 |  | Lampole | 18m Lampole | 18 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3 | 0 | 0
2409A | Bt 21 Pangsun(AsiaSpace) | Central |  | Modernization |  | 154 single site MOCN | CR | GCI | 4.6 TSSR Approved |  | 2023-10-31 | 2023-11-22 |  | 2024-05-13 |  | Closed | 2024-05-20 | 2024-05-27 | E//Sumitra | 2024-05-27 | CelcomDigi_RAN_GCI_TSS_Central_20231101 | DU00002860748 |  |  | 2024-06-15 | 2024-06-08 |  | Tower | 45m 3 Legged Tower | 75 | Add R9264M M1821 x1+R8862A S2601 x2+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 12 | 0
1008A | JBA UK 2 | Central |  | Modernization |  | 2024 Q1 | AI | DATASCO | 4.6 TSSR Approved |  | 2023-12-01 | 2023-12-08 |  | 2024-01-02 |  | Closed | 2024-01-12 | 2024-01-17 | E//Sumitra | 2024-01-16 | CelcomDigi_RAN_Datasco_TSS_Central_20231203 | DU00002860749 |  |  | 2024-05-22 | 2024-05-17 |  | Minimast | 30m Monopole | 12 | Add R8862A S9000 x1+R8894E M1821 x3+R8862A S2601 x1,Dismantle R8882-GUL1812 x2
1024B | Tmn Bukit Setiawangsa | Central |  | Modernization |  | 2024 Q1 | SS | YPTT | 4.6 TSSR Approved |  | 2023-10-26 | 2023-11-01 |  | 2023-12-29 |  | Closed | 2024-01-03 | 2024-01-05 | E//Kok Keen | 2024-01-04 | CelcomDigi_RAN_YPTT_TSS_Central_20231028 | DU00002860750 |  |  | 2024-07-17 | 2024-06-28 |  |  | 3m RT (Wall Mounted Pole) | 3 | Add R8862A S9000 x3+R8894E M1821 x3+R8862A S2601 x2,Dismantle R8882-GUL1812 x1
1027B | Balai Polis Pantai | Central |  | Decomm | Modernization->On hold->Decomm | 2024 Q2 | SM | AllStar | 4.6 TSSR Approved |  | 2024-04-08 |  |  |  | 2024-05-03 |  | 2024-05-07 | 2025-07-01 | E//Kok Keen | 2024-05-07 | CelcomDigi_RAN_AllStar_TSS_Central_20240513 | DU00002860751 |  |  |  |  | 2024-10-28 |  | 3m Boom (RT)
1031A | Semenyih Shoplot | Central |  | Modernization |  | 131 single site mocn | SY1 | GTSB | 4.6 TSSR Approved |  | 2024-08-02 | 2024-08-09 |  | 2024-08-15 |  | Closed | 2024-08-20 | 2024-08-21 | E//Sumitra | 2024-08-21 | 0806CD-Central-GTSB-BOQ Template(new contract) | DU00002860752 |  |  | 2024-09-18 | 2024-09-18 |  | In-Building System | 3m RT (Wall Mounted Pole) | 7M | Add R8862A S2601 x3+A9732 M1821 x3,Dismantle R8860E-GU908 x1+R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3+R8882-L268 x3 | 123 | 0
1036A | JBA Bkt Mewah | Central |  | Modernization | Modernization->On Hold->Modernization | 2024 Q4 | SHA | GTSB | 4.6 TSSR Approved |  | 2024-01-17 | 2024-01-18 |  | 2024-05-21 |  | Closed | 2024-09-25 | 2025-08-29 | E//Sumitra | 2025-05-28 | CelcomDigi_RAN_GTSB_TSS_Central_20240124 | DU00002860753 |  |  | 2025-06-19 | 2025-06-19 |  | In-Building System | 3m Bipod (RT) | 2m | Add R8894E M1821x1+R8862A S2601x1 | 0 | 3
1036B | Taman Koperasi Polis 2 | Central |  | Modernization |  | 2024 Q1 | IE | Magicell | 4.6 TSSR Approved |  | 2023-11-06 | 2023-11-08 |  | 2023-12-29 |  | Closed | 2024-01-03 | 2024-01-03 |  | 2024-01-03 | CelcomDigi_RAN_Magicell_TSS_Central_20231113 | DU00002860754 |  |  | 2024-02-28 | 2024-02-24 |  | In-Building System | 6m RT (Minimast) | 7 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
1048B | Shoplot Jalan Telawi | Central |  | Modernization |  | 2024 Q2 | AI | Ascentrack | 4.6 TSSR Approved |  | 2023-11-21 | 2023-12-01 |  | 2024-03-02 |  | Closed | 2024-03-05 | 2024-05-30 | E//Kok Keen | 2024-05-30 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231126 | DU00002860755 |  |  | 2024-05-24 | 2024-05-23 |  | In-Building System | 3m RT (Wall Mounted Pole) | 4 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x2+R8840-U216 x2++ | 0 | 0
1052A | Putratower2 | Central |  | Modernization |  | 2024 Q3 | SHA | YPTT | 4.6 TSSR Approved |  | 2024-05-12 | 2024-05-23 |  | 2024-06-12 |  | Under Approval | 2024-06-13 | 2024-07-01 | E//Razif | 2024-06-25 | CelcomDigi_RAN_YPTT_TSS_Central_20240517 | DU00002860756 |  |  | 2024-08-12 | 2024-08-09 |  | Monople Tree | Tower | 45 | Add R8852E S9000 x2+R9264H M901821 x1+R8862A S2601 x3+A9732 M1821 x2,Dismantle R8862A S9000(A6A) x3+R8882 S2600(B4A) x3+R8894E M1821(A8A) x3 | 23 | 0
1054A | Alam Jaya Shop | Central |  | Modernization |  | 2024 Q4 | BY | GTSB | 4.6 TSSR Approved |  | 2024-01-10 | 2024-01-12 |  | 2024-08-09 |  | Under Approval | 2024-06-11 | 2024-06-14 | E//Sumitra | 2024-06-14 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240115 | DU00002860757 |  |  | 2024-07-19 | 2024-07-17 |  | In-Building System | 3m RT (Minimast) | 9M | Add R9264M M1821 x1+A9732 M1821 x3,Dismantle R8894E M1821(A8A) x4 | 123 | 0
1056A | CYBERJAYA | Central |  | Modernization |  | 2024 Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2024-05-16 | 2024-05-20 |  | 2024-05-29 |  | Under Approval | 2024-05-30 | 2024-05-31 |  | 2024-05-30 | CelcomDigi_RAN_GTSB_TSS_Central_20240528 | DU00002860758 |  |  | 2025-09-07 | 2025-08-27 |  | Tower | 65m Tower | 75m | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x2+R8862A S2600(A4A) x3 | 0 | 0
1060A | Sg Long Maxis | Central |  | Modernization | Modernization->On Hold->Modernization | 2024 Q4 | SHA | YPTT | 4.6 TSSR Approved |  | 2024-05-13 | 2024-05-14 |  | 2024-05-23 |  | Under Approval | 2024-10-09 | 2024-11-29 | E//Sumitra | 2024-11-29 | CelcomDigi_RAN_YPTT_TSS_Central_20240528 | DU00002860759 |  |  | 2025-01-13 | 2025-01-08 |  | Tower | 60m 4 Legged Tower | 18m | Add R8894E M1821 x1+R8854 S2600x1, Dismantle R8862A S2600(A4A)x1 | 0 | 13
1076B | Jalan Perak IKED | Central |  | Modernization |  | 2024 Q3 | AI | Magicell | 4.6 TSSR Approved |  | 2024-07-29 | 2024-07-31 |  | 2024-08-02 |  | Closed | 2024-08-05 | 2024-08-13 | E//Sumitra | 2024-08-13 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240510 | DU00002860760 |  |  | 2024-12-19 | 2024-12-16 |  | Monople Tree | 55m 3 Legged Tower | 22M | Add R9264M M1821 x1+R8862A S2601 x3+A9732 M1821 x2,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3+R8882 S2600(B4A) x3 | 23 | 0
4463B | Pengkalan Hulu(Celcom) | Northern |  | Modernization |  | 2024 Additional | MS | GTSB | 4.6 TSSR Approved |  | 2023-12-05 | 2023-12-08 |  | 2024-11-21 |  | Closed | 2024-11-22 | 2024-12-16 | E//Hazida | 2024-12-16 | Celcom Digi_RAN-GTSB-TSS-Northern-20231206-0072 | DU00002860761 |  |  | 2025-01-20 | 2025-01-13 |  | Tower | 76m 4 Legged Tower | 75 | Add R8852E S9000 x3+R8894E M1821x5, Dismantle R8860E-GU908x3+R8862A S1800(B6A)x3+R8862A S2100(A6A)x3 | 0 | 23
1082B | Tmn Melur Ampang | Central |  | Modernization |  | 2024 Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-24 | 2023-12-01 |  | 2024-05-21 |  | Closed | 2024-05-13 | 2024-05-15 | E//Sumitra | 2024-05-15 | CelcomDigi_RAN_GTSB_TSS_Central_20231126 | DU00002860762 |  |  | 2024-06-22 | 2024-06-22 |  | In-Building System | 45m 3 Legged Tower | 6m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
1099B | PLUS Salak Selatan | Central |  | Modernization |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-12-28 | 2024-01-23 |  | 2024-03-21 |  | Closed | 2024-03-22 | 2024-05-09 | E//Sumitra | 2024-03-26 | CelcomDigi_RAN_Ascentrak_TSS_Central_20231230 | DU00002860763 |  |  | 2024-05-30 | 2024-05-28 |  | Monopole | 30m Monopole | 30m | Add R8894E M1821 x1,Dismantle | 0 | 1
1135B | Putrajaya Precinct 9 | Central |  | Decomm | Modernization->Decomm | 2024 Q3 | MA | Magicell | 4.6 TSSR Approved |  | 2024-01-15 | 2024-01-24 | 2024-07-01 | 2024-04-23 | 2024-07-01 | Under Approval | 2024-07-02 | 2024-12-09 | E//Razif | 2024-07-16 | 0704CD-Central-Magicell-BOQ Template (template) | DU00002860764 |  |  |  |  | 2024-11-29 | Wall mount boom | 3m Bipod (RT)
1143B | Tmn Universiti Bangi (Maxis) | Central |  | Modernization | Modernization->On Hold->Modernization | 2024 Q4 | SY1 | YPTT | 4.6 TSSR Approved |  | 2024-04-17 | 2024-05-08 |  | 2024-05-20 |  | Closed | 2024-05-20 | 2024-05-27 | E//Sumitra | 2024-05-27 | CelcomDigi_RAN_YPTT_TSS_Central_20240513 | DU00002860765 |  |  | 2025-05-10 | 2025-05-07 |  | Monopole | 35m MonopoleTower | 35 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3 | 0 | 0
1144B | Tmn Mawar Puchong | Central |  | Modernization |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-11-18 | 2024-03-18 |  | 2024-04-19 |  | Closed | 2024-05-28 | 2024-06-04 | E//Sumitra | 2024-06-04 | CelcomDigi_RAN_Datasco_TSS_Central_20231214 | DU00002860766 |  |  | 2024-06-25 | 2024-06-25 |  | Minimast | Tower | 12 | Reuse exisiting RRU | 0 | 0
1148B | UKM Lestari (Maxis) | Central |  | Modernization |  | 2024 Additional | SY1 | YPTT | 4.6 TSSR Approved |  | 2024-04-17 | 2024-05-14 |  | 2024-05-23 |  | Closed | 2024-05-24 | 2024-06-07 | E//Sumitra | 2024-06-06 | CelcomDigi_RAN_YPTT_TSS_Central_20240513 | DU00002860767 |  |  | 2025-03-30 | 2025-03-20 |  | Monople Tree | 60m 3 Legged Tower | 30 | Add R9264H M901821 x3,Dismantle R8860E-GU908 x1+R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8840-U216 x3 | 0 | 0
1156B | Pinggiran Putra | Central |  | Modernization |  | 2024 Q3 | CR | GTSB | 4.6 TSSR Approved |  | 2024-06-07 | 2024-06-12 |  | 2024-06-18 |  | Under Approval | 2024-06-20 | 2024-07-24 | E//Sumitra | 2024-07-24 | 0610Central-GTSB-BOQ Template (template) | DU00002860768 |  |  | 2024-07-03 | 2024-06-29 |  | Monopole | 30m Monopole | 46m | Add R8862A S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3 | 3 | 0
1158B | Surau Muhajirin Kajang (KJS) | Central |  | Modernization |  | 2024 Q4 | AI | YPTT | 4.6 TSSR Approved |  | 2023-12-06 | 2023-12-18 |  | 2024-06-06 |  | Closed | 2024-06-07 | 2024-06-13 | E//Sumitra | 2024-06-13 | CelcomDigi_RAN_YPTT_TSS_Central_202031203 | DU00002860769 |  |  | 2024-06-15 | 2024-06-15 |  | Lampole | 24m Lampole | 20m | Add R8852E S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8862A S1800(B6A) x3+R8882 S2600(B4A) x1 | 0 | 1
1181A | PT Utama | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-09 | 2023-11-23 |  | 2023-12-18 |  | Closed | 2023-12-20 | 2024-01-03 | E//Sumitra | 2024-01-03 | CelcomDigi_RAN_GTSB_TSS_Central_20231113 | DU00002860770 |  |  | 2024-04-20 | 2024-04-03 |  | Minimast | 3m RT (Minimast) | 6m | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3++
1235B | SS23_15 | Central |  | Modernization |  | 2024 Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2023-11-07 | 2023-11-17 |  | 2024-04-02 |  | Closed | 2024-04-03 | 2024-04-04 | E//Kok Keen | 2024-04-03 | CelcomDigi_RAN_Magicell_TSS_Central_20231113 | DU00002860771 |  |  | 2024-04-27 | 2024-04-24 |  | Monopole | 3m RT (Unipole) | 10 | Add R9224E M1821 x5+R8854 S2600 x1,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8862A S2100(A6A) x4+R8882-L268 x1 | 0 | 1
1238A | KLIA (Sapura) | Central |  | Site Out (Modernization) | On Hold->Site Out->Site Out (Modernization) | 2026 | AI | GTSB | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002860772 | [6 empty] | Tower
1258B | Kg Ulu ChuChuh( CLM) | Central |  | Modernization |  | 131 single site mocn | SY1 | YPTT | 4.6 TSSR Approved |  | 2024-05-17 | 2024-05-23 |  | 2024-05-27 |  | Closed | 2024-05-29 | 2024-05-30 | E//Razif | 2024-05-30 | CelcomDigi_RAN_YPTT_TSS_Central_20240528 | DU00002860773 |  |  | 2024-07-05 | 2024-06-16 |  | Tower | Tower | 60 | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 23 | 0
1264A | Tmn Cheras | Central |  | Modernization |  | 2024 Q3 | SS | AllStar | 4.6 TSSR Approved |  | 2023-11-03 | 2023-11-10 |  | 2024-04-17 |  | Closed | 2024-04-17 | 2024-04-23 | E//Sumitra | 2024-04-23 | CelcomDigi_RAN_Allstar_TSS_Central_20231113 | DU00002860774 |  |  | 2024-06-20 | 2024-06-16 |  | In-Building System | 6m RT (Minimast) | 5 | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 12 | 0
1268B | Kantan Permai | Central |  | Modernization |  | 2024 Q4 | SY1 | YPTT | 4.6 TSSR Approved |  | 2024-05-05 | 2024-05-08 |  | 2024-05-16 |  | Rectificating | 2024-06-05 | 2024-06-10 | E//Sumitra | 2024-06-07 | CelcomDigi_RAN_YPTT_TSS_Central_20240513 | DU00002860775 |  |  | 2024-06-14 | 2024-06-14 |  |  | 20m Lampole | 20 | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8882-GUL1812 x3+R8840-U216 x3 | 3 | 0
1292A | Nor Market | Central |  | Modernization |  | 2024 Q3 | SH | AllStar | 4.6 TSSR Approved |  | 2023-11-09 | 2023-11-17 |  | 2024-03-25 |  | Closed | 2024-03-27 | 2024-04-05 | E//Kok Keen | 2024-04-05 | CelcomDigi_RAN_Allstar_TSS_Central_20231113 | DU00002860776 |  |  | 2024-06-20 | 2024-06-18 |  | In-Building System | 3m Boom (RT) | 6 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 0 | 0
1299A | Weng Zeng | Central |  | Modernization |  | 2024 Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-12-01 | 2023-12-05 |  | 2023-12-12 |  | Closed | 2023-12-13 | 2023-12-20 | E//Sumitra | 2023-12-19 | CelcomDigi_RAN_Allstar_TSS_Central_20231203 | DU00002860777 |  |  | 2024-04-22 | 2024-04-02 |  | Unipole | 3m Boom (RT) | 8 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
1301B | Plaza Hamodal Seksyen 13 | Central |  | Modernization |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-03-07 | 2024-04-03 |  | 2024-04-16 |  | Closed | 2024-04-23 | 2024-04-23 | E//Kok Keen | 2024-04-23 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240311 | DU00002860778 |  |  | 2024-06-15 | 2024-05-14 |  | Pole | 3m Boom (RT) | 6 | Add R9264H M901821 x4+R8862A S2601 x1,Dismantle R8882-GUL1812 x3+R8840-U216 x3++
1303B | Kg Cempaka RT | Central |  | Modernization |  | 2024 Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2023-11-04 | 2023-11-08 |  | 2024-03-22 |  | Closed | 2024-03-25 | 2024-03-26 |  | 2024-03-25 | CelcomDigi_RAN_Magicell_TSS_Central_20231113 | DU00002860779 |  |  | 2024-05-04 | 2024-05-03 |  | In-Building System | 3m Boom (RT) | 9 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
1308A | Wangsaria | Central |  | Modernization |  | 2024 Q2 | YZ | Ascentrack | 4.6 TSSR Approved |  | 2024-01-10 | 2024-01-16 |  | 2024-01-24 |  | Closed | 2024-01-26 | 2024-01-30 | E//Kok Keen | 2024-01-29 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240115 | DU00002860780 |  |  | 2024-06-07 | 2024-05-31 |  | In-Building System | 6m RT (Boom) | (S1/S2 =3.5M) (S3/S4 = 3M) | Add R9264M M1821 x3+R9264H M901821 x1,Dismantle R8882-GUL1812 x3+R8882 S1800B(B6B) x3+R8862A S1800(B6A) x1+R8862A S2100(A6A) x4
1313A | Rspring | Central |  | Modernization |  | 2024 Q1 | MA | DATASCO | 4.6 TSSR Approved | AAU Cannot Install-S12 MM change to BI¦All boom are wallmounted boom,S2 space constraint | 2023-11-02 | 2023-11-14 |  | 2023-12-28 |  | Closed | 2023-12-29 | 2024-01-02 | E//Kok Keen | 2024-01-02 | CelcomDigi_RAN_Datasco_TSS_Central_20231126 | DU00002860781 |  |  | 2024-03-21 | 2024-03-18 |  |  | 6m RT (Boom) | S1= 6m, S2&S3= 4m | Add R8894E M1821 x4,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x3+R8862A S2100(A6A) x5+R8882-L268 x1 |  | 1
1320B | Bandar Puteri 1 | Central |  | Modernization |  | 2024 Q3 | MA | Magicell | 4.6 TSSR Approved |  | 2024-01-09 | 2024-01-11 |  | 2024-04-19 |  | Closed | 2024-04-25 | 2024-04-30 | E//Sumitra | 2024-04-30 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240115 | DU00002860782 |  |  | 2024-06-21 | 2024-06-15 |  | In-Building System | 3m Boom (RT) | 9 | Add R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 0 | 0
1331A | Wisma AT | Central |  | Modernization |  | 2024 Q2 | XH | YPTT | 4.6 TSSR Approved |  | 2023-10-23 | 2023-11-10 |  | 2024-01-11 |  | Closed | 2024-01-17 | 2024-01-23 | E//Sumitra | 2024-01-23 | CelcomDigi_RAN_YPTT_TSS_Central_20231025 | DU00002860783 |  |  | 2024-05-11 | 2024-05-09 |  | In-Building System | 6m RT (Boom) | 6 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1377B | Institut Pengajian Siswazah(ZED | Central |  | Modernization |  | 2024 Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2024-04-26 | 2024-04-30 |  | 2024-04-30 |  | Closed | 2024-05-02 | 2024-05-21 | E//Kok Keen | 2024-05-21 | CelcomDigi_RAN_YPTT_TSS_Central_20240513 | DU00002860784 |  |  | 2024-05-30 | 2024-05-29 |  | In-Building System | 3m Boom (RT) | 9m | Add R9224E M1821 x1+R8854 S2600 x1,Dismantle R8862A S2600(A4A) x1 | 0 | 1
1392A | Jln Bukit | Central |  | Modernization |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-12-19 | 2024-02-09 |  | 2024-03-27 |  | Closed | 2024-03-29 | 2024-04-01 | E//Kok Keen | 2024-04-01 | CelcomDigi_RAN_Datasco_TSS_Central_20231224 | DU00002860785 |  |  | 2024-04-19 | 2024-04-16 |  | Pole | 3m Tripod (RT) | 5m & 6m | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3++ | 0 | 0
1396A | Jln Gasing | Central |  | Modernization |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-21 | 2023-12-12 |  | 2024-04-04 |  | Closed | 2024-04-05 | 2024-04-15 | E//Kok Keen | 2024-04-08 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231126 | DU00002860786 |  |  | 2024-04-15 | 2024-04-02 |  | In-Building System | 3m Bipod (RT) | 6.5 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x2+R8840-U216 x3++ | 0 | 0
1396B | Taman Aman PJ | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-09 | 2023-11-15 |  | 2023-11-29 |  | Closed | 2023-11-30 | 2023-12-04 | E//Kok Keen | 2023-12-01 | CelcomDigi_RAN_GTSB_TSS_Central_20231113 | DU00002860787 |  |  | 2024-04-04 | 2024-04-04 |  | H-bracket pole | 3m Boom (RT) | 6m | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x2+R8854D S2100(A4A) x2 | 0 | 0
1400B | Taman Putra Prima | Central |  | Modernization |  | 2024 Q3 | MA | Magicell | 4.6 TSSR Approved |  | 2024-02-08 | 2024-02-22 |  | 2024-04-23 |  | Closed | 2024-05-27 | 2024-05-28 | E//Razif | 2024-05-27 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240218 | DU00002860788 |  |  | 2024-06-11 | 2024-06-08 |  | In-Building System | 3m Bipod (RT) | 7M | Reuse exisiting RRU | 0 | 0
1401A | Bandar Kinrara | Central |  | Modernization | Modernization->On Hold->Modernization->On Hold->Modernization | 2024 Q3 | AI | DATASCO | 4.6 TSSR Approved |  | 2023-11-18 | 2023-11-23 |  | 2024-12-11 |  | Under Approval | 2024-12-06 | 2024-12-10 | E//Sumitra | 2024-12-10 | CelcomDigi_RAN_Datasco_TSS_Central_20231214 | DU00002860789 | Remarks: Solution TSSR/BOM Changed |  | 2024-12-18 | 2024-12-16 |  | In-Building System | 3m Boom (RT) | 6 | Add R8852E S9000x1+R8854 S2600x1+R8894E M1821 x5,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 0 | 2
1402A | Jln Industri Puchong | Central |  | Modernization |  | 2024 Q3 | MA | Magicell | 4.6 TSSR Approved |  | 2024-01-11 | 2024-01-18 |  | 2024-04-22 |  | Closed | 2024-04-25 | 2024-04-29 | E//Sumitra | 2024-04-26 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240115 | DU00002860790 |  |  | 2024-06-24 | 2024-06-19 |  | In-Building System | 6m RT (Minimast) | 12m | Add R8894E M1821 x4,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8862A S2100(A6A) x4 | 0 | 0
1437A | Deliq | Central |  | Modernization |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-10-30 | 2023-11-06 |  | 2023-11-22 |  | Closed | 2024-04-03 | 2024-04-15 | E//Sumitra | 2024-04-09 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231101 | DU00002860791 |  |  | 2024-08-21 | 2024-08-19 |  | In-Building System | 3m Boom (RT) | 6 | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle R8882-L268 x1 | 0 | 1
1439A | Zats | Central |  | Modernization |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-02 | 2023-11-08 |  | 2023-11-23 |  | Closed | 2024-04-01 | 2024-04-15 | E//Sumitra | 2024-04-09 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231101 | DU00002860792 |  |  | 2024-06-15 | 2024-06-15 |  | Minimast | 3m Boom (RT) | 8m | Add R9264H M901821 x3,Dismantle R8860E-GU908 x1+R8882-GUL1812 x3+R8840-U216 x2++ | 0 | 0
1448A | Dagangjaya | Central |  | Modernization |  | 2024 Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-23 | 2023-12-01 |  | 2024-05-21 |  | Closed | 2024-05-16 | 2024-06-06 | E//Sumitra | 2024-06-06 | CelcomDigi_RAN_GTSB_TSS_Central_20231126 | DU00002860793 |  |  | 2024-05-26 | 2024-05-26 |  | Unipole | 6m RT (Boom) | 5 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3 | 0 | 0
1449A | Tmn Ampang Indah | Central |  | Modernization |  | 2024 Q4 | BY | Ascentrack | 4.6 TSSR Approved |  | 2023-11-03 | 2023-11-09 |  | 2023-11-27 |  | Closed | 2024-05-31 | 2024-06-12 |  | 2024-06-11 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231104 | DU00002860794 |  |  | 2024-06-22 | 2024-06-21 |  | Minimast | 3m Boom (RT) | 10 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3++ | 0 | 0
1457A | Kyoto Garden | Central |  | Modernization |  | 2024 Q1 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-11-07 | 2023-11-14 |  | 2023-12-28 |  | Closed | 2023-12-30 | 2024-07-18 | E//Sumitra | 2024-07-18 | CelcomDigi_RAN_Datasco_TSS_Central_20231113 | DU00002860795 |  |  | 2024-07-24 | 2024-07-24 |  | In-Building System | 3m Bipod (RT) | S1 - 5M / S2 - 3M | Add R8862A S9000 x3+R8894E M1821 x3+R8862A S2601 x1,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x1
1460A | Tmn Desa | Central |  | Modernization |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-23 | 2023-11-27 |  | 2024-04-16 |  | Closed | 2024-04-03 | 2024-04-05 | E//Sumitra | 2024-04-05 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231126 | DU00002860796 |  |  | 2024-04-20 | 2024-04-05 |  | In-Building System | 3m Boom (RT) | 6 | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8840-U216 x3++ | 2 | 0
1463A | Tmn Danau Kota | Central |  | Modernization |  | 2024 Q1 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-10-31 | 2023-11-15 |  | 2023-12-29 |  | Closed | 2024-01-02 | 2024-01-03 | E//Kok Keen | 2024-01-02 | CelcomDigi_RAN_Datasco_TSS_Central_20231101 | DU00002860797 |  |  | 2024-02-26 | 2024-02-26 |  |  | 3m Boom (RT) | 6m | Resuse exsiting RRU |  | 13
1467A | OG Business Park | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-16 | 2023-11-21 |  | 2023-12-14 |  | Closed | 2023-12-13 | 2023-12-20 | E//Sumitra | 2023-12-19 | CelcomDigi_RAN_GTSB_TSS_20231119 | DU00002860798 |  |  | 2024-04-13 | 2024-04-05 |  | Minimast | 3m RT (Minimast) | 6m | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x4
1474A | Supertread | Central |  | Modernization |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-12-27 | 2024-05-16 |  | 2024-05-31 |  | Closed | 2024-06-07 | 2024-06-13 | E//Sumitra | 2024-06-13 | CelcomDigi_RAN_Datasco_TSS_Central_20231230 | DU00002860799 |  |  | 2024-06-30 | 2024-06-22 |  | In-Building System | 3m Bipod (RT) | 4.5m | Add R8862A S9000(A6A) x1+R8894E M1821 x1 | 0 | 1
1486A | Sepang Circuit | Central |  | Site Out (Modernization) | Modernization->Site Out->Replacement, Site Out (Modernization) | 2025 Q2 | BY | GTSB | 4.6 TSSR Approved |  | 2023-12-27 | 2024-01-03 | 2025-07-02 | 2024-05-29 |  | Under Approval | 2024-05-30 | 2024-09-06 | E//Razif | 2024-06-11 | SQ202411080530 | DU00002860800 | [6 empty] | 3m Boom (RT) | 6
1487A | Tmn Dahlia | Central |  | Modernization |  | 2024 Additional | CR | GCI | 4.6 TSSR Approved |  | 2023-10-27 | 2023-11-08 |  | 2024-05-13 |  | Closed | 2024-05-20 | 2024-05-29 | E//Razif | 2024-05-29 | CelcomDigi_RAN_GCI_TSS_Central_20231028 | DU00002860801 |  |  | 2024-12-11 | 2024-12-06 |  | In-Building System | 3m Boom (RT) | 8 | Add R8852E S9000 x3+R8894E M1821 x5,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 0 | 23
1491A | Bukit Bandaraya | Central |  | Modernization |  | 2024 Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-23 | 2023-12-07 |  | 2024-03-02 |  | Closed | 2024-03-04 | 2024-05-23 | E//Kok Keen | 2024-05-23 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231126 | DU00002860802 |  |  | 2024-04-30 | 2024-04-05 |  | In-Building System | 3m Boom (RT) | 5 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3++ | 0 | 0
3248A | Bdr Tun Hussein Onn | Central |  | Modernization |  | 2024 Q3 | CR | Magicell | 4.6 TSSR Approved |  | 2023-12-24 | 2024-01-23 |  | 2024-04-23 |  | Closed | 2024-04-27 | 2024-04-30 | E//Sumitra | 2024-04-30 | CelcomDigi_RAN_Magicell_TSS_Central_20231227 | DU00002860803 |  |  | 2024-06-22 | 2024-06-21 |  | In-Building System | 3m Bipod (RT) | S1,S2,S3=5m | Add R8894E M1821 x3,Dismantle R8882 S1800(B) x3++R8881 S2100 x3+ | 0 | 0
7546A | Bukit Kalam | Sabah |  | Modernization |  | 2025 Q1 | AD | Datasco | 4.6 TSSR Approved |  | 2024-05-23 | 2024-05-30 |  | 2025-01-14 |  | Under Approval | 2025-01-17 | 2025-02-18 | E//Yanie | 2025-01-31 | 0920CD-Sabah-Datasco-BOQ Template (old contract) | DU00002860804 |  |  | 2025-02-27 | 2025-02-21 |  | Monopole | 30m Monopole | 30 | Add R8852E S9000x3+R9264M M1821x3, Dismantle R8882 S1800(B)x3+R8862A S2100(A6A)x3 | 0 | 0
2465A | Bukit Puchong 2 | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-10 | 2024-01-18 |  | 2024-04-30 |  | Closed | 2024-05-03 | 2024-05-07 | E//Razif | 2024-05-06 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240115 | DU00002860805 |  |  | 2024-06-04 | 2024-05-31 |  | Monopole | 30m Monopole | 30M | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3 | 0 | 0
1776B | Tmn Selaseh | Central |  | Modernization |  | 2024 Q1 | SS | Magicell | 4.6 TSSR Approved |  | 2023-12-14 | 2023-12-18 |  | 2023-12-29 |  | Closed | 2024-01-02 | 2024-01-03 | E//Kok Keen | 2024-01-03 | CelcomDigi_RAN_Magicell_TSS_Central_20231215 | DU00002860806 |  |  | 2024-01-31 | 2024-01-25 |  | H-bracket pole | 3m Bipod (RT) | 3 | Add R8894E M1821 x3,Dismantle R8882-GUL1812 x3
1777A | Sek 4 Bdr Baru Bangi | Central |  | Modernization |  | 2024 Q3 | SY1 | Solusi | 4.6 TSSR Approved |  | 2023-10-25 | 2023-11-23 |  | 2024-05-20 |  | Closed | 2024-06-06 | 2024-07-11 | E//Sumitra | 2024-07-11 | CelcomDigi_RAN_Solusi_TSS_Central_20231101 | DU00002860807 |  |  | 2024-06-27 | 2024-06-23 |  | Portables BTS | 3m Boom (RT) | 7 | Add R8852E S9000 x3+R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3++ | 0 | 0
1790B | Tmn Melawati | Central |  | Modernization |  | 2024 Q1 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-14 | 2023-11-21 |  | 2023-12-30 |  | Closed | 2024-01-02 | 2024-01-05 | E//Sumitra | 2024-01-04 | CelcomDigi_RAN_GTSB_TSS_Central_20231116 | DU00002860808 |  |  | 2024-01-15 | 2024-01-11 |  | Monopole | 30m Monopole | 30 | Add R8862A S9000 x2+R8894E M1821 x2,Dismantle R8882 S1800(B) x2
1794B | Shoplot Tmn Melawati 2 | Central |  | Modernization |  | 2024 Q1 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-07 | 2023-11-16 |  | 2023-12-29 |  | Closed | 2023-12-29 | 2024-01-05 | E//Sumitra | 2024-01-05 | CelcomDigi_RAN_GTSB_TSS_Central_20231113 | DU00002860809 |  |  | 2024-03-21 | 2024-03-16 |  | In-Building System | 3m Boom (RT) | 6 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1
1801B | Kemensah Heights | Central |  | Modernization |  | 2024 Q1 | SHA | GCI | 4.6 TSSR Approved |  | 2024-05-16 | 2024-05-27 |  | 2024-06-13 |  | Under Approval | 2024-06-14 | 2024-06-25 | E//Sumitra | 2024-06-25 | CelcomDigi_RAN_GCI_TSS_Central_20240528 | DU00002860810 |  |  | 2024-07-24 | 2024-07-22 |  | Monople Tree | 30m Monopole Tree | 30 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x2+R8840-U216 x3++
1828B | Kajang Prima | Central |  | Modernization |  | 2024 Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-16 | 2024-02-14 |  | 2024-05-21 |  | Closed | 2024-05-23 | 2024-05-30 | E//Sumitra | 2024-05-30 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240117 | DU00002860811 |  |  | 2024-09-11 | 2024-09-07 |  | Wall mount boom | 3m Boom (RT) | 6 | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 3 | 0
1829B | Country Heights(Maxis _ ZED) | Central |  | Site Out (Modernization) | Modernization->On hold->Site out->Replacement, Site Out (Modernization) | 2024 Q3 |  | GTSB | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2025-07-15 |  | 2025-07-02 |  |  | To be Submitted |  |  |  |  | SQ202506170074 | DU00002860812 |  |  |  |  | 2025-08-05 |  | 76m 4 Legged Tower
1844B | Cyberjaya Cyberdail(AsiaSpace) | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-23 | 2024-02-21 |  | 2024-04-26 |  | Closed | 2024-05-03 | 2024-05-07 | E//Razif | 2024-05-06 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240128 | DU00002860813 |  |  | 2024-07-16 | 2024-06-26 |  | Monopole | 45m Monopole | 45 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3+R8882 S1800B(B6B) x3+R8840-U216 x2++ | 0 | 0
1865B | ERL Wetland(TMTouch) | Central |  | Modernization | Modernization->On Hold->Modernization | 2024 Q3 | SS | YPTT | 4.6 TSSR Approved |  | 2023-11-28 | 2023-12-29 |  | 2024-04-19 |  | Closed | 2024-04-19 | 2024-04-23 | E//Sumitra | 2024-04-23 | CelcomDigi_RAN_YPTT_TSS_Central_20231201 | DU00002860814 |  |  | 2024-11-22 | 2024-11-19 |  | Tower | 45m Tower | 75 | Add R8862A S9000 x4,Dismantle | 0 | 0
1868B | UNITEN (Residence Hotel) | Central |  | Modernization |  | 2024 Q3 | SY1 | YPTT | 4.6 TSSR Approved |  | 2024-05-06 | 2024-05-09 |  | 2024-05-20 |  | Closed | 2024-07-04 | 2024-07-10 | E//Sumitra | 2024-07-10 | CelcomDigi_RAN_YPTT_TSS_Central_20240513 | DU00002860815 |  |  | 2025-03-05 | 2025-02-10 |  | In-Building System | 13m Minimast (Rooftop) | 13 | Add R8862A S9000 x4+R8894E M1821 x4+R8862A S2601 x4,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x2+R8840-U216 x3+R8862A S2100(A6A) x1+R8862A S2600(A4A) x3+R8862A S2601(A6A) x1 | 0 | 0
1879B | Putrajaya Precinct 17 (AS) | Central |  | Modernization | Modernization->Decomm->Modernization | 2024 Q3 | AI | YPTT | 4.6 TSSR Approved |  | 2024-05-12 | 2024-07-05 |  | 2024-08-12 | 2024-07-29 | Under Approval | 2024-08-12 | 2024-12-24 | E//Razif | 2024-12-24 | 0813CD-Central-YPTT-BOQ Template(new contract) | DU00002860816 |  |  | 2024-10-19 | 2024-10-16 |  | Monople Tree | 45m Monopole | 46 | Add R9264M M1821 x2+A9732 M1821 x1+R8862A S2601 x3,Dismantle R8892E M1821(BAA) x3+R8882 S2600(B4A) x3 | 1 | 0
4962B | Yan Besar | Northern |  | Modernization |  | 131 single site mocn | SM | GCI | 4.6 TSSR Approved |  | 2024-08-15 | 2024-09-02 |  | 2024-09-04 |  | Rectificating | 2024-09-05 | 2024-09-30 | E//Hazida | 2024-09-28 | 0809CD-Northern-GCI-BOQ Template(new contract) | DU00002860817 |  |  | 2024-09-26 | 2024-09-26 |  | Tower | 60m 3 Legged Tower | 60 | Add R8862A S9000 x3+R8894E M1821 x2+A9732 M1821 x1,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 2
1903B | Taman Kemacahaya 2 | Central |  | Modernization |  | 2024 Additional | CR | GCI | 4.6 TSSR Approved |  | 2023-10-27 | 2023-10-30 |  | 2023-11-06 |  | Closed | 2024-05-28 | 2024-06-20 | E//Sumitra | 2024-06-20 | CelcomDigi_RAN_GCI_TSS_Central_20231028 | DU00002860818 |  |  | 2025-01-06 | 2025-01-02 |  |  | 3m Bipod (RT) | 6 | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x4 | 0 | 0
1910B | Menara Impian | Central |  | Modernization |  | 2024 Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-06 | 2024-04-22 |  | 2024-06-14 |  | Under Approval | 2024-07-25 | 2024-08-01 | E//Sumitra | 2024-08-01 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231113 | DU00002860819 |  |  | 2024-09-04 | 2024-08-30 |  | In-Building System | 3m Boom (RT) | 4 | Add R9264H M901821 x3+R8862A S2601 x1,Dismantle R8882-GUL1812 x2++R8881 S2100 x2+ | 0 | 0
1915B | Bandar Sri Permaisuri | Central |  | Modernization |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-03 | 2023-11-17 |  | 2023-12-03 |  | Rectificating | 2024-04-03 | 2024-04-15 | E//Sumitra | 2024-04-09 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231104 | DU00002860820 |  |  | 2024-07-26 | 2024-06-24 |  | In-Building System | 3m RT (Minimast) | 11 | Add A9732 M1821 x3,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8862A S2100(A6A) x5 | 123 | 0
1918A | Damansara Intan | Central |  | Modernization |  | 2024 Q3 | AI | DATASCO | 4.6 TSSR Approved |  | 2023-12-19 | 2023-12-29 |  | 2024-04-18 |  | Closed | 2024-04-19 | 2024-04-23 |  | 2024-04-23 | CelcomDigi_RAN_Datasco_TSS_Central_20231224 | DU00002860821 |  |  | 2025-01-05 | 2024-05-30 |  | In-Building System | 3m Bipod (RT) | 3.5M | Add R9264H M901821 x3+R8862A S2601 x2,Dismantle R8882-GUL1812 x1+R8840-U216 x1++ | 0 | 0
1956A | Seksyen 6 PJ (KJS) | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-18 | 2023-11-22 |  | 2023-12-18 |  | Closed | 2024-04-04 | 2024-04-05 | E//Kok Keen | 2024-04-04 | CelcomDigi_RAN_GTSB_TSS_20231119 | DU00002860822 |  |  | 2024-05-16 | 2024-05-15 |  | Lampole | 26m Lampole | 20m | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3++ | 0 | 0
1973A | tmn Bkt Serdang | Central |  | Modernization |  | 2024 Q3 | SH | DATASCO | 4.6 TSSR Approved |  | 2023-11-10 | 2023-11-20 |  | 2024-04-24 |  | Closed | 2024-05-03 | 2024-05-14 | E//Kok Keen | 2024-05-14 | CelcomDigi_RAN_Datasco_TSS_Central_20231214 | DU00002860823 |  |  | 2024-06-20 | 2024-06-20 |  |  | 3m Boom (RT) | 5.5 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8854D S2100(A4A) x3 | 0 | 0
1974A | Jln Sg Besi | Central |  | Modernization |  | 2024 Q3 | AI | Ascentrack | 4.6 TSSR Approved |  | 2023-11-06 | 2023-11-16 |  | 2023-11-23 |  | Closed | 2024-03-27 | 2024-04-05 | E//Sumitra | 2024-04-05 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231113 | DU00002860824 |  |  | 2024-06-20 | 2024-06-18 |  | In-Building System | 3m Bipod (RT) | 6.6 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 0 | 0
1975A | Selturf Club | Central |  | Modernization |  | 2024 Q3 | SH | Magicell | 4.6 TSSR Approved |  | 2024-01-03 | 2024-01-17 |  | 2024-04-22 |  | Closed | 2024-05-10 | 2024-05-16 | E//Kok Keen | 2024-05-15 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240108 | DU00002860825 |  |  | 2024-07-17 | 2024-06-15 |  | In-Building System | 30m Monopole | 3M | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8840-U216 x3++ | 0 | 0
1980B | TAMAN HIJAU (KJS) | Central |  | Modernization |  | 2024 Q4 | SY1 | Ascentrack | 4.6 TSSR Approved |  | 2024-01-03 | 2024-01-11 |  | 2024-05-13 |  | Rectificating | 2024-05-15 | 2024-05-21 | E//Sumitra | 2024-05-21 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240108 | DU00002860826 |  |  | 2024-05-25 | 2024-05-24 |  | Monopole | 30m Monopole | 30m | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3++ | 0 | 0
1984A | Bangsar Shopping Mall | Central |  | Modernization |  | 2024 Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-12-15 | 2023-12-28 |  | 2024-01-06 |  | Closed | 2024-01-24 | 2024-01-29 | E//Kok Keen | 2024-01-26 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231224 | DU00002860827 |  |  | 2024-06-21 | 2024-06-21 |  | H-bracket pole | 3m Boom (RT) | 3.5m/4.5m | Add R8862A S9000 x4+R8894E M1821 x5,Dismantle R8882-GUL1812 x2+R8882 S1800(B) x1+R8862A S1800(B6A) x2+R8862A S2100(A6A) x4 |  | 4
1996A | Taman Midah Cheras | Central |  | Modernization |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-10-30 | 2023-11-06 |  | 2023-11-27 |  | Closed | 2024-04-04 | 2024-04-16 | E//Sumitra | 2024-04-16 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231101 | DU00002860828 |  |  | 2024-06-19 | 2024-06-18 |  | H-bracket pole | 3m Bipod (RT) | 5.5 | Add R9264M M1821 x3+A9732 M1821 x1,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8854D S2100(A4A) x4 | 2 | 0
2011A | Tmn Sg Besi | Central |  | Modernization |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-10 | 2023-11-17 |  | 2024-03-21 |  | Closed | 2024-03-24 | 2024-03-26 | E//Sumitra | 2024-03-26 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231113 | DU00002860829 |  |  | 2024-06-21 | 2024-06-16 |  | In-Building System | 3m Boom (RT) | 11 | Add R9264M M1821 x4,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8862A S2100(A6A) x4 | 0 | 0
2018B | Saujana Kajang | Central |  | Modernization |  | 2024 Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-12 | 2024-01-15 |  | 2024-05-14 |  | Closed | 2024-05-15 | 2024-05-31 | E//Razif | 2024-05-31 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240115 | DU00002860830 |  |  | 2024-09-09 | 2024-09-06 |  | Unipole | 3m Boom (RT) | 6m | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 13 | 0
2020B | Sri Petaling 3 (REL) | Central |  | Modernization |  | 2024 Q3 | SH | Ascentrack | 4.6 TSSR Approved |  | 2024-01-12 | 2024-04-04 |  | 2024-04-03 |  | Closed | 2024-04-18 | 2024-04-23 | E//Kok Keen | 2024-04-23 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240115 | DU00002860831 |  |  | 2024-06-23 | 2024-06-21 |  | Unipole | 3m Boom (RT) | 6.5m | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x4 | 13 | 0
2055B | Sg Pelek 2 | Central |  | Modernization |  | 2024 Additional | SY1 | YPTT | 4.6 TSSR Approved |  | 2024-05-17 | 2024-05-20 |  | 2024-05-31 |  | Closed | 2024-07-04 | 2024-07-22 | E//Razif | 2024-07-18 | CelcomDigi_RAN_YPTT_TSS_Central_20240528 | DU00002860832 |  |  | 2024-12-11 | 2024-12-06 |  | Tower | 60m 3 Legged Tower | 60 | Add R8862A S9000 x3+R8894E M1821 x3+R8862A S2601 x3,Dismantle R8882-GUL1812 x2+R8882 S1800(B) x1+R8862A S2600(A4A) x3 | 0 | 0
2057B | KLIA KM10 | Central |  | Modernization |  | 2024 Additional | BY | GTSB | 4.6 TSSR Approved |  | 2023-11-14 | 2023-11-17 |  | 2024-05-09 |  | Closed | 2024-05-14 | 2024-05-27 | E//Razif | 2024-05-27 | CelcomDigi_RAN_GTSB_TSS_Central_20231116 | DU00002860833 |  |  | 2024-06-23 | 2024-06-23 |  | BillBoard | Billboard | 30m | Add R8862A S9000 x1+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882-GUL1812 x2+R8840-U216 x2++ | 0 | 2
7536A | Kolej Matrikulasi Labuan | Sabah |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | MS | Seri Pancar | 4.6 TSSR Approved |  | 2023-12-15 | 2024-06-13 |  | 2024-10-21 |  | Under Approval | 2024-10-25 | 2024-11-29 | E//Hannah | 2024-11-29 | Celcom Digi_RAN-Seri Pancar-Standard PR TSS-Sabah-20240109 | DU00002860834 |  |  | 2024-12-16 | 2024-12-16 |  | Monopole | 30m Monopole | 30 | Add R9264M M1821 x1+A9732 M1821 x3,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x5 | 134 | 0
2163A | BALAI ISLAM TMN PANDAN MEWAH | Central |  | Modernization |  | 2024 Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-12-06 | 2023-12-07 |  | 2024-05-09 |  | Closed | 2024-05-10 | 2024-05-21 | E//Sumitra | 2024-05-21 | CelcomDigi_RAN_GTSB_TSS_Central_20231208 | DU00002860835 |  |  | 2024-05-29 | 2024-05-29 |  | Minaret | 25m Minaret | 23m | Add R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3+R8882 S2600(B4A) x1 | 0 | 1
2165A | MASJID BKT INDAH | Central |  | Modernization |  | 2024 Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-30 | 2023-12-20 |  | 2024-04-22 |  | Closed | 2024-04-30 | 2024-07-11 | E//Sumitra | 2024-07-11 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231203 | DU00002860836 |  |  | 2024-06-06 | 2024-06-04 |  | Tower | 24m Lampole | 25 | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R8882-GUL1812 x3 | 1 | 0
2166A | SURAU UBUDIAH | Central |  | Modernization |  | 2024 Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-25 | 2023-12-12 |  | 2024-05-08 |  | Closed | 2024-06-01 | 2024-06-21 | E//Sumitra | 2024-06-04 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231126 | DU00002860837 |  |  | 2024-06-07 | 2024-06-06 |  |  | 20m Lampole | 20m | Add R9264M M1821 x2+R9264H M901821 x1+R8862A S2601 x1,Dismantle R8882-GUL1812 x2+R8840-U216 x2++ | 0 | 0
2170A | SURAU BKT MULIA | Central |  | Modernization |  | 2024 Q1 | AI | DATASCO | 4.6 TSSR Approved |  | 2023-11-27 | 2023-12-01 |  | 2024-01-02 |  | Closed | 2024-01-03 | 2024-01-11 | E//Sumitra | 2024-01-10 | CelcomDigi_RAN_Datasco_TSS_Central_20231201 | DU00002860838 |  |  | 2024-01-14 | 2024-01-11 |  | Monople Tree | 30m Monopole Tree | 30 | Add R8894E M1821 x3,Dismantle R8882 S1800(B) x3
2224A | Surau Taman Bunga Raya (REL) | Central |  | Modernization |  | 2024 Q1 | XH | Ascentrack | 4.6 TSSR Approved |  | 2023-11-18 | 2023-11-22 |  | 2023-12-28 |  | Closed | 2023-12-28 | 2023-12-29 | E//Kok Keen | 2023-12-29 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231119 | DU00002860839 |  |  | 2024-03-07 | 2024-02-27 |  | Lampole | 30m Lampole | 35 | Add R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x2+R8854D S2100(A4A) x3+R8862A S2600(A4A) x1 |  | 3
2255A | Jln Bukit Setiawangsa | Central |  | Modernization |  | 2024 Q1 | MA | GCI | 4.6 TSSR Approved |  | 2023-11-09 | 2023-11-10 |  | 2024-01-02 |  | Closed | 2024-01-04 | 2024-01-09 | E//Sumitra | 2024-01-09 | CelcomDigi_RAN_GCI_TSS_Central_20231113 | DU00002860840 |  |  | 2024-05-11 | 2024-05-09 |  | Lampole | 24m Lampole | 30 | Add R8862A S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882 S1800(B) x1+R8882 S1800B x1+R8882 S1800B(B6B) x1+R8862A S2100(A6A) x3+R8882 S2600(B4A) x1 |  | 3
2275A | Kg Sg Sekamat Kajang | Central |  | Modernization |  | 2024 Q4 | BY | YPTT | 4.6 TSSR Approved |  | 2023-10-22 | 2023-10-31 |  | 2024-06-16 |  | Under Approval | 2024-06-18 | 2024-06-25 | E//Sumitra | 2024-06-25 | CelcomDigi_RAN_YPTT_TSS_Central_20231224 | DU00002860841 |  |  | 2024-09-20 | 2024-09-06 |  | In-Building System | 3m Boom (RT) | 11-8 = 3 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8840-U216 x3++ | 0 | 0
2283A | Bkt Segar Jaya Cheras | Central |  | Modernization |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-07 | 2023-11-09 |  | 2023-11-29 |  | Closed | 2024-03-25 | 2024-04-02 | E//Sumitra | 2024-04-02 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231113 | DU00002860842 |  |  | 2024-06-19 | 2024-06-18 |  | In-Building System | 6m Unipole RT | 9 | Add R8894E M1821 x3,Dismantle R8882 S1800(B) x3+R8862A S2100(A6A) x3 | 0 | 0
2288A | Jln Linkaran Tengah2 | Central |  | Modernization |  | 2024 Q1 | MA | GCI | 4.6 TSSR Approved |  | 2023-10-23 | 2023-10-26 |  | 2024-01-02 |  | Closed | 2024-01-03 | 2024-01-09 | E//Sumitra | 2024-01-09 | CelcomDigi_RAN_GCI_TSS_Central_20231025 | DU00002860843 |  |  | 2024-05-08 | 2024-05-07 |  | In-Building System | 3m Boom (RT) | 6 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882-GUL1812 x3
2293A | Jln Kolam Ayer Ampang | Central |  | Modernization |  | 2024 Q4 | SY1 | Ascentrack | 4.6 TSSR Approved |  | 2023-11-10 | 2024-02-21 |  | 2024-06-14 |  | Closed | 2024-06-24 | 2024-07-03 | E//Sumitra | 2024-07-03 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231113 | DU00002860844 |  |  | 2024-09-09 | 2024-09-05 |  | In-Building System | 3m Boom (RT) | 3 | Add R9264H M901821 x3,Dismantle R8882 S1800(B) x3+R8881 S2100 x3 | 0 | 0
2296A | Tmn Melawati Fasa 1 | Central |  | Modernization |  | 2024 Q1 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-16 | 2023-11-22 |  | 2024-01-02 |  | Closed | 2024-01-02 | 2024-01-05 | E//Sumitra | 2024-01-05 | CelcomDigi_RAN_GTSB_TSS_20231119 | DU00002860845 |  |  | 2024-01-13 | 2024-01-11 |  | Lampole | 20m Lampole | 22m | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882-GUL1812 x3
2305A | Tmn Ramal Ros | Central |  | Modernization | Modernization->On Hold | 2024 Q4(single site MOCN)-L2126 SSM | AI | DATASCO | 4.6 TSSR Approved |  | 2024-10-03 | 2024-10-09 |  | 2024-12-24 |  | Under Approval | 2024-12-24 | 2025-02-07 | E//Sumitra | 2025-01-07 | CelcomDigi_RAN_Datasco_TSS_Central_20231214 | DU00002860846 |  |  | 2025-01-20 | 2025-01-20 |  | Pole | 3m Boom (RT) | 5.4m | Add R8852E S9000 x3+R9224E M1821 x4+R8854 S2600x1,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8882 S2600(B4A) x1 | 0 | 1
2311A | Wawasan Ampang | Central |  | Modernization | Modernization->On Hold->Modernization | 2024 Q4(single site MOCN)-L2126 SSM | AI | GCI | 4.6 TSSR Approved |  | 2023-11-18 | 2023-11-23 |  | 2024-05-08 |  | Closed | 2024-05-15 | 2024-05-20 | E//Sumitra | 2024-05-20 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231119 | DU00002860847 |  |  | 2025-10-17 | 2025-10-14 |  | In-Building System | 3m Bipod (RT) | 6 | Add R8862A S2601x3, Dismantle R8882 S2600(B4A) x3 | 0 | 0
2322A | Enville Golf Resort | Central |  | Modernization |  | 154 single site MOCN | BY | GTSB | 4.6 TSSR Approved |  | 2024-01-18 | 2024-03-15 |  | 2024-05-23 |  | Closed | 2024-05-28 | 2024-05-29 | E//Razif | 2024-05-29 | CelcomDigi_RAN_GTSB_TSS_Central_20240124 | DU00002860848 |  |  | 2024-06-19 | 2024-06-19 |  | Tower | 30m Monopole | 45M | Add R8862A S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3 | 2 | 0
2331A | Sek7 BBB | Central |  | Modernization |  | 2024 Q4 | SH | Magicell | 4.6 TSSR Approved |  | 2023-12-29 | 2024-01-05 |  | 2024-05-10 |  | Closed | 2024-05-13 | 2024-05-21 | E//Sumitra | 2024-05-21 | CelcomDigi_RAN_Magicell_TSS_Central_20231230 | DU00002860849 |  |  | 2024-06-21 | 2024-06-13 |  | In-Building System | 3m Boom (RT) | 3 | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8840-U216 x3++ | 1 | 0
2343A | Puchong Lake | Central |  | Modernization |  | 2024 Q3 | SH | Solusi | 4.6 TSSR Approved |  | 2024-01-18 | 2024-01-23 |  | 2024-04-30 |  | Closed | 2024-05-07 | 2024-05-14 | E//Kok Keen | 2024-05-14 | CelcomDigi_RAN_Solusi_TSS_Central_20240124 | DU00002860850 |  |  | 2024-06-07 | 2024-05-31 |  | Monopole | 30m Lampole | 30M | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle R8862A S2600(A4A) x1 | 0 | 3
2349A | SS 22a LP | Central |  | Modernization |  | 2024 Q3 | CR | Magicell | 4.6 TSSR Approved |  | 2023-12-29 | 2024-03-14 |  | 2024-03-21 |  | Closed | 2024-03-22 | 2024-03-26 | E//Kok Keen | 2024-03-25 | CelcomDigi_RAN_Magicell_TSS_Central_20231230 | DU00002860851 |  |  | 2024-04-27 | 2024-04-24 |  | In-Building System | 4m RT (Boom) | 4M | Add R9264H M901821 x3,Dismantle R8882 S1800(B) x3+R8862A S2100(A6A) x3 | 0 | 0
2410A | Bt 18 Sg Lui(AsiaSpace) | Central |  | Modernization |  | 154 single site MOCN | AI | GCI | 4.6 TSSR Approved |  | 2023-11-02 | 2023-11-16 |  | 2024-05-13 |  | Closed | 2024-05-13 | 2024-05-21 | E//Sumitra | 2024-05-20 | CelcomDigi_RAN_GCI_TSS_Central_20231104 | DU00002860852 |  |  | 2024-06-05 | 2024-05-28 |  | Tower | 45m 3 Legged Tower | 90 | Add R8852E S9000 x3+R8862A S2601 x3+A9732 M1821 x3,Dismantle R8860E-GU908 x1+R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 123 | 0
2413A | Kg Sg Kembung Hilir(ZED) | Central |  | Modernization |  | 2024 Additional | SY1 | YPTT | 4.6 TSSR Approved |  | 2024-04-18 | 2024-04-22 |  | 2024-05-20 |  | Closed | 2024-05-25 | 2024-07-11 | E//Sumitra | 2024-07-11 | CelcomDigi_RAN_YPTT_TSS_Central_20240513 | DU00002860853 |  |  | 2024-06-15 | 2024-06-15 |  | Tower | 60m 3 Legged Tower | 60 | Add R8852E S9000 x1+R9264H M901821 x3+A9732 M1821 x1,Dismantle R9224E M1821(AAB) x4 | 2 | 0
2414A | Bangi Seksyen 3 (Surau) | Central |  | Modernization |  | 2024 Q3 | SH | DATASCO | 4.6 TSSR Approved |  | 2023-11-12 | 2024-02-21 |  | 2024-04-30 |  | Closed | 2024-05-13 | 2024-05-21 | E//Sumitra | 2024-05-21 | CelcomDigi_RAN_Datasco_TSS_Central_20231214 | DU00002860854 |  |  | 2024-06-22 | 2024-06-22 |  | Monopole | 30m Monopole | 30m | Add R8862A S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882-GUL1812 x3+R8882 S2600(B4A) x1+R8840-U216 x3++ | 0 | 3
2417A | PUAS Precinct 19(AsiaSpace) | Central |  | Decomm | Modernization->Decomm | 2024 Q3 | AI | Magicell | 4.6 TSSR Approved |  | 2024-11-06 |  |  |  | 2024-12-05 |  | 2025-04-28 |  | E//Razif | 2025-04-29 | 0809CD-Central-Magicell-BOQ Template(new contract)/Celcom Digi_RAN-Magicell-Standard PR TSS-Central-20241016 | DU00002860855 |  |  |  |  | 2024-09-29 |  | 45m Monopole
2464A | Bkt Kuchai Puchong | Central |  | Modernization |  | 2024 Q3 | SHA | DATASCO | 4.6 TSSR Approved |  | 2024-07-15 | 2024-07-16 |  | 2024-07-18 |  | Under Approval | 2024-08-01 | 2024-11-28 | E//Sumitra | 2024-11-28 | CelcomDigi_RAN_Datasco_TSS_Central_20231126 | DU00002860856 |  |  | 2024-08-13 | 2024-08-13 |  | Pole | 6m RT (Boom) | 3.5m | Add R8894E M1821 x4+R8862A S2601 x1+R8854 S2600 x1,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8862A S2100(A6A) x4+R8882 S2600(B4A) x3 | 0 | 1
9707A | Semupoh | Sarawak |  | Modernization |  | 2025 Q3 | AD | Magicell | 4.6 TSSR Approved |  | 2024-03-05 | 2024-03-25 |  | 2025-02-19 |  | Under Approval | 2025-02-26 | 2025-04-29 | E//Hannah | 2025-03-09 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20240123 | DU00002860857 |  |  | 2025-05-17 | 2025-04-11 |  | Tower | Tower | 77m | Reuse Existing RRU | 0 | 0
2466A | Uni Nottingham (KJS) | Central |  | Modernization |  | 2024 Additional | SM | YPTT | 4.6 TSSR Approved |  | 2023-10-24 | 2023-11-10 |  | 2024-12-02 |  | Under Approval | 2024-12-04 | 2024-12-24 | E//Sumitra | 2024-12-12 | CelcomDigi_RAN_YPTT_TSS_Central_20231224 | DU00002860858 |  |  | 2024-12-20 | 2024-12-16 |  | Monopole | 45m Monopole | 45 | Add R8852E S9000 x3+R8894E M1821x4+R8854 S2600 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R8882 S2600(B4A) x1 | 0 | 3
2486A | Bt14 Hulu Langat | Central |  | Modernization |  | 131 single site mocn | CR | GCI | 4.6 TSSR Approved |  | 2023-11-10 | 2023-11-21 |  | 2024-05-14 |  | Under Approval | 2024-05-20 | 2024-07-24 | E//Sumitra | 2024-07-24 | CelcomDigi_RAN_GCI_TSS_Central_20231214 | DU00002860859 |  |  | 2024-06-13 | 2024-06-11 |  | Tower | 60m 4 Legged Tower | 60 | Add R8862A S9000 x3+R9264H M901821 x1+A9732 M1821 x3,Dismantle R8894E M1821(A8A) x4 | 123 | 0
2499A | JBA Bkt Mewah 9 (AS) | Central |  | Modernization |  | 2024 Additional | SHA | GCI | 4.6 TSSR Approved |  | 2023-11-27 | 2023-11-29 |  | 2024-11-25 |  | Under Approval | 2024-11-26 | 2024-11-27 | E//Sumitra | 2024-11-27 | CelcomDigi_RAN_GCI_TSS_Central_20231201 | DU00002860860 | Remarks: Solution TSSR/BOM Changed |  | 2024-12-13 | 2024-12-10 |  | Monopole | 45m Monopole | 45 | Add R8852E S9000 x3+R8894E M1821 x3+R8862A S2601 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3+R8882 S2600(B4A) x3 | 0 | 0
2503A | Tmn TYL | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-20 | 2023-11-27 |  | 2024-04-16 |  | Closed | 2024-04-23 | 2024-04-23 | E//Sumitra | 2024-04-23 | CelcomDigi_RAN_GTSB_TSS_Central_20231126 | DU00002860861 |  |  | 2024-04-08 | 2024-04-03 |  | Unipole | 3m Bipod (RT) | 6 | Add R9264M M1821 x4+R8854 S2600 x1,Dismantle R8894E M1821(A8A) x4+ R8882 S2600(B4A) x1 | 0 | 1
2513A | Tmn Desa (AsiaSpace) | Central |  | Modernization |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-12-15 | 2024-01-09 |  | 2024-01-16 |  | Closed | 2024-04-01 | 2024-04-15 | E//Sumitra | 2024-04-09 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231224 | DU00002860862 |  |  | 2024-04-24 | 2024-04-19 |  | Monople Tree | 30m Monopole | 30m | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x1+R8882 S1800(B) x1+R8862A S1800(B6A) x2+R8862A S2100(A6A) x5 | 0 | 0
2533A | Precinct 8B | Central |  | Decomm | Modernization->Decomm | 2024 Q3 | AI | Magicell | 4.6 TSSR Approved |  | 2023-12-07 | 2023-12-21 |  | 2024-04-23 | 2024-06-04 | Under Approval | 2024-06-05 | 2025-10-01 | E//Razif | 2024-06-05 | 0704CD-Central-Magicell-BOQ Template (template) | DU00002860863 |  |  |  |  | 2024-11-21 | In-Building System | 3m Bipod (RT) | 2
2534A | Ukay Perdana 3 | Central |  | Modernization |  | 2024 Q1 | XH | GCI | 4.6 TSSR Approved |  | 2023-11-14 | 2023-11-16 |  | 2024-01-02 |  | Closed | 2024-01-26 | 2024-01-31 | E//Sumitra | 2024-01-30 | CelcomDigi_RAN_GCI_TSS_Central_20231116 | DU00002860864 |  |  | 2024-03-18 | 2024-02-22 |  | Monopole | 30m Monopole | 30 | Add R8862A S9000 x3+R8894E M1821 x6+R8854 S2600 x3,Dismantle R8862A S2600(A4A) x3+R8892E M1821(BAA) x3 |  | 123
2557B | Jln 52_4 PJ | Central |  | Modernization |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-12-22 | 2023-12-22 |  | 2024-04-04 |  | Closed | 2024-03-29 | 2024-04-15 | E//Kok Keen | 2024-04-08 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231224 | DU00002860865 |  |  | 2024-04-19 | 2024-04-17 |  | Pole | 3m Boom (RT) | 3m | Add R9264H M901821 x3,Dismantle R8882 S1800(B) x3++R8881 S2100 x6+ | 0 | 0
2585A | Taman Bukit Seputeh (Maxis) | Central |  | Modernization |  | 2024 Q3 | SH | Ascentrack | 4.6 TSSR Approved |  | 2024-02-27 | 2024-03-01 |  | 2024-04-06 |  | Closed | 2024-04-16 | 2024-04-23 | E//Kok Keen | 2024-04-23 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240303 | DU00002860866 |  |  | 2025-02-14 | 2025-02-14 |  | Monopole | 24m Monopole | 22 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8840-U216 x2++ | 0 | 0
2589A | Raja Puchong | Central |  | Modernization |  | 2024 Q3 | CR | Magicell | 4.6 TSSR Approved |  | 2024-01-04 | 2024-01-10 |  | 2024-04-23 |  | Closed | 2024-04-27 | 2024-04-30 | E//Sumitra | 2024-04-30 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240108 | DU00002860867 |  |  | 2024-06-24 | 2024-06-23 |  | In-Building System | 3m Boom (RT) | 9M | Add R8894E M1821 x3,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x2+R8862A S2100(A6A) x3 | 0 | 0
2612AD | pBTS LCCT | Central |  | Modernization | Modernization->On Hold->Modernization | 2024 Additional | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-02 | 2024-01-10 |  | 2024-10-01 |  | Under Approval | 2024-10-09 | 2024-12-05 | E//Razif | 2024-12-05 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240108 | DU00002860868 |  |  | 2024-10-18 | 2024-10-12 |  | Tower | 25m pBTS | 24M | Add R8862A S9000 x3+R8894E M1821 x3+R8862A S2601 x3,Dismantle R8862A S1800(B6A)x2+R8882 S1800B(B6B)x1+R8882-L268x3 | 0 | 0
4990B | Kg Lalang | Northern |  | Modernization |  | 154 single site MOCN | AD | GTSB | 4.6 TSSR Approved |  | 2023-10-19 | 2023-10-23 |  | 2024-08-16 |  | Under Approval | 2024-08-19 | 2024-09-23 | E//Hazida | 2024-09-22 | Celcom Digi_RAN-GTSB-TSS-Northern-20231020-0053 | DU00002860869 |  |  | 2024-09-13 | 2024-09-03 |  | Tower | Tower | 60m | Add A9732 M1821 x3,Dismantle R8854D S2100(A4A) x3+R8892E M1821(BAA) x3 | 123 | 0
2717B | Jln Pandan Indah | Central |  | Modernization |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-22 | 2023-11-27 |  | 2024-04-03 |  | Closed | 2024-04-04 | 2024-04-16 | E//Sumitra | 2024-04-16 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231126 | DU00002860870 |  |  | 2024-06-05 | 2024-06-04 |  | Lampole | 20m Lampole | 20m | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3 | 1 | 0
2730B | Jln BBB | Central |  | Modernization |  | 2024 Q3 | SH | Solusi | 4.6 TSSR Approved |  | 2024-03-28 | 2024-02-21 |  | 2024-04-30 |  | Closed | 2024-05-06 | 2024-05-14 | E//Kok Keen | 2024-05-14 | BOQ CelcomDigi_RAN_Solusi_Standard PR TSS_Central_20240329 | DU00002860871 |  |  | 2024-06-15 | 2024-06-15 |  | Lampole | 20m Lampole | 22 | Add R8862A S9000 x3+A9732 M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3 | 123 | 0
2736A | Tmn Bukit Desa | Central |  | Modernization |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-12-11 | 2023-12-20 |  | 2024-01-22 |  | Closed | 2024-04-02 | 2024-04-15 | E//Sumitra | 2024-04-08 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231213 | DU00002860872 |  |  | 2024-04-25 | 2024-04-24 |  | H-bracket pole | 3m Boom (RT) | 6m | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x5++ | 0 | 0
2740A | Tmn Bkt Indah | Central |  | Modernization |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-01-15 | 2024-01-30 |  | 2024-02-16 |  | Closed | 2024-04-20 | 2024-04-23 | E//Sumitra | 2024-04-23 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240116 | DU00002860873 |  |  | 2024-04-25 | 2024-04-24 |  | In-Building System | 3m Bipod (RT) | 3 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3 | 0 | 0
4340A | Tmn Mewah Bagan Serai | Northern |  | Modernization |  | 154 single site MOCN | AI | GTSB | 4.6 TSSR Approved |  | 2023-10-10 | 2023-10-18 |  | 2024-08-29 |  | Under Approval | 2024-09-02 | 2024-09-20 | E//Hazida | 2024-09-20 | Celcom Digi_RAN-GTSB-TSS-Northern-20231011-0046 | DU00002860874 |  |  | 2024-09-10 | 2024-09-06 |  | Floor Mount Boom | 6m RT (Boom) | 6 | Add R8862A S9000 x4+R8894E M1821 x6+R8854 S2600 x2,Dismantle R8860E-GU908 x1+R8882-GUL1812 x1+R8862A S1800(B6A) x3+R8862A S2100(A6A) x4+R8862A S2600(A4A) x2 |  | 24
7504A | Dewata | Sabah |  | Modernization |  | 2024 Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-12-15 | 2024-04-30 |  | 2024-07-19 |  | Under Approval | 2024-07-22 | 2024-07-26 | E//Hannah | 2024-07-26 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231218 | DU00002860875 |  |  | 2024-08-31 | 2024-08-24 |  | Tower | Tower | 60 | Reuse exsiting RRU | 0 | 0
7514A | Simpang Ladang Bagahak II | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-03-09 |  | 2025-03-14 |  | 2025-03-24 |  | 2025-04-22 | 2025-09-10 | E//Hannah | 2025-07-14 | SQ202503270530 - Futong | DU00002860876 |  |  |  |  | 2025-11-25 |  | Tower
2924A | Alam Damai Cheras (REL) | Central |  | Modernization |  | 2024 Q3 | CR | Magicell | 4.6 TSSR Approved |  | 2024-02-15 | 2024-03-01 |  | 2024-03-21 |  | Closed | 2024-03-22 | 2024-03-26 | E//Sumitra | 2024-03-25 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240218 | DU00002860877 |  |  | 2024-05-31 | 2024-05-29 |  | In-Building System | 30m Minaret | 4M | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle R8882 S2600(B4A) x1 | 0 | 2
7331B | Kg Dalamason | Sabah |  | Modernization |  | 2024 Q3(single site MOCN) | AD | Seri Pancar | 4.6 TSSR Approved | Solution changed MM>Bi | 2024-06-13 | 2024-06-20 |  | 2024-06-26 |  | Under Approval | 2024-07-02 | 2024-08-19 | E//Hannah | 2024-08-19 | 0618Sabah-Seri Pancar-BOQ Template (template) | DU00002860878 |  |  | 2024-08-30 | 2024-08-24 |  | Tower | 45m 3 Legged Tower | 75 | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle | 0 | 3
1134B | Bt 22 Sg Lui | Central |  | Modernization |  | 2024 Additional | BY | GCI | 4.6 TSSR Approved |  | 2024-01-16 | 2024-01-18 |  | 2024-05-22 |  | Closed | 2024-05-24 | 2024-06-07 | E//Sumitra | 2024-06-07 | CelcomDigi_RAN_GCI_TSS_Central_20231214 | DU00002860879 |  |  | 2024-06-07 | 2024-06-06 |  | Tower | 45m 3 Legged Tower | 90 | Add R8862A S9000 x1+R8894E M1821 x1,Dismantle | 0 | 0
4100D | Gurun R&R Maxis (REL) | Northern |  | Modernization |  | 2025 Q3 | HW | GCI | 4.6 TSSR Approved |  | 2025-01-13 | 2025-03-03 |  | 2025-03-13 |  | Under Approval | 2025-04-18 | 2025-05-19 | E//Hazida | 2025-04-23 | SQ202501030261 - GCI | DU00002860880 |  |  | 2025-05-26 | 2025-05-26 |  | Tower | 4 Legged Tower | 60m | Add R8894E M1821x3, Dismantle R8892N M1821(BAB)x3 | 0 | 0
9708A | TMB Balong | Sarawak |  | Modernization |  | 2025 Q2 | AD | Trintel | 4.6 TSSR Approved |  | 2025-03-18 | 2025-04-03 |  | 2025-04-10 |  | Under Approval | 2025-04-11 | 2025-05-19 | E//Hannah | 2025-04-21 | SQ202503030116-Trintel | DU00002860881 |  |  | 2025-05-17 | 2025-05-16 |  | Tower | Tower | 76 | Reuse Existing RRU | 0 | 0
2983A | MEX HW KM13.8 | Central |  | Modernization |  | 2024 Q3 | CR | GTSB | 4.6 TSSR Approved |  | 2024-06-10 | 2024-06-26 |  | 2024-07-03 |  | Under Approval | 2024-07-04 | 2024-07-18 | E//Sumitra | 2024-07-18 | 0618Central-GTSB-BOQ Template (template) | DU00002860882 |  |  | 2024-07-20 | 2024-07-17 |  | Monople Tree | 30m Monopole | 30 | Add R8862A S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3+R8862A S2600(A4A) x1 | 0 | 1
3092A | Bkt Tampoi (REL) | Central |  | Modernization |  | 2024 Additional | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-03 | 2024-01-05 |  | 2024-05-17 |  | Closed | 2024-05-21 | 2024-05-24 | E//Razif | 2024-05-24 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240108 | DU00002860883 |  |  | 2024-06-13 | 2024-06-13 |  | Tower | Tower | 60 | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R8882 S1800(B) x4+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3 | 2 | 0
3100A | Pantai Hillpark | Central |  | Modernization |  | 2024 Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2023-12-21 | 2024-01-17 |  | 2024-01-23 |  | Closed | 2024-01-23 | 2024-01-29 | E//Kok Keen | 2024-01-26 | CelcomDigi_RAN_AllStar_TSS_Central_20231224 | DU00002860884 |  |  | 2024-05-31 | 2024-05-31 |  | Pole | 3m Boom (RT) | 3 | Add R9264M M1821 x3,Dismantle R8882 S1800(B) x3+R8862A S2100(A6A) x3
3220A | Jalan Ukay Perdana | Central |  | Modernization |  | 2024 Q1 | CR | GCI | 4.6 TSSR Approved |  | 2023-11-14 | 2023-11-20 |  | 2024-01-02 |  | Closed | 2024-01-03 | 2024-01-09 | E//Sumitra | 2024-01-09 | CelcomDigi_RAN_GCI_TSS_Central_20231116 | DU00002860885 |  |  | 2024-05-24 | 2024-05-18 |  | In-Building System | 30m Monopole | 7 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3
3221A | Jln Hijrah 10 | Central |  | Modernization |  | 2024 Q1 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-12-03 | 2023-12-12 |  | 2023-12-29 |  | Closed | 2024-01-02 | 2024-01-05 | E//Sumitra | 2024-01-04 | CelcomDigi_RAN_Datasco_TSS_Central_20231203 | DU00002860886 |  |  | 2024-01-24 | 2024-01-19 |  | Lampole | 24m Lampole | 25 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882 S1800(B) x3
3225A | Tmn Keramat 1 | Central |  | Modernization |  | 2024 Q1 | CR | GCI | 4.6 TSSR Approved |  | 2024-01-11 | 2024-01-24 |  | 2024-02-22 |  | Closed | 2024-02-27 | 2024-03-06 | E//Sumitra | 2024-03-06 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240115 | DU00002860887 |  |  | 2024-09-25 | 2024-09-23 |  | Tower | 45m 3 Legged Tower | 45 | Add R9264H M901821 x3,Dismantle R8882 S1800(B) x3
3229A | Jln Rahman Rashim | Central |  | Modernization |  | 2024 Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-25 | 2023-11-27 |  | 2024-05-08 |  | Closed | 2024-05-09 | 2024-05-15 | E//Sumitra | 2024-05-15 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231126 | DU00002860888 |  |  | 2024-06-06 | 2024-06-04 |  | Lampole | 20m Lampole | 20m | Add R9264M M1821 x3,Dismantle R8882 S1800(B) x3++R8881 S2100 x3+ | 0 | 0
3236A | Perumahan Seri Melaka | Central |  | Modernization |  | 2024 Q3 | AI | Ascentrack | 4.6 TSSR Approved |  | 2023-11-07 | 2023-11-10 |  | 2023-12-02 |  | Closed | 2024-03-20 | 2024-03-26 | E//Sumitra | 2024-03-25 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231113 | DU00002860889 |  |  | 2024-07-10 | 2024-07-10 |  | In-Building System | 3m Boom (RT) | 4 | Add R9264H M901821 x3,Dismantle R8882 S1800(B) x3+R8862A S2100(A6A) x3 | 0 | 0
3275A | TMN_MELAWATI21 | Central |  | Modernization |  | 2024 Q1 | BY | GCI | 4.6 TSSR Approved |  | 2023-11-06 | 2023-11-23 |  | 2024-03-07 |  | Closed | 2024-03-07 | 2024-03-13 | E//Sumitra | 2024-03-12 | CelcomDigi_RAN_GCI_TSS_Central_20231113 | DU00002860890 |  |  | 2024-09-19 | 2024-09-19 |  | In-Building System | 30m Monopole | 9 | Add R8862A S9000 x4+R8894E M1821 x1,Dismantle
3289A | LADANGKINRARA1 | Central |  | Modernization |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-11-18 | 2024-03-20 |  | 2024-04-22 |  | Closed | 2024-04-27 | 2024-04-30 | E//Sumitra | 2024-04-30 | CelcomDigi_RAN_Datasco_TSS_Central_20231214 | DU00002860891 |  |  | 2024-06-14 | 2024-06-14 |  | Pole | 3m Boom (RT) | 12 / 7 | Add R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 0 | 0
3328A | AU51 | Central |  | Modernization |  | 2024 Q1 | SS | YPTT | 4.6 TSSR Approved |  | 2023-11-27 | 2023-11-30 |  | 2023-12-29 |  | Closed | 2024-08-21 | 2024-08-21 | E//Sumitra | 2024-08-21 | CelcomDigi_RAN_YPTT_TSS_Central_20231201 | DU00002860892 |  |  | 2024-10-18 | 2024-10-11 |  | Tower | 38m Tower | 45 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3
3334A | SRDG_PERDANA1 | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-06-05 | 2024-06-12 |  | 2024-06-18 |  | Under Approval | 2024-12-05 | 2024-06-25 | E//Sumitra | 2026-04-17 | 0607Central-GTSB-BOQ Template | DU00002860893 |  |  | 2024-10-25 | 2024-10-24 |  | In-Building System | 3m Boom (RT) | 3 | Reuse exisiting RRU | 0 | 1
3339A | TMN JUARA JAYA1 | Central |  | Modernization |  | 2024 Q3 | MA | Magicell | 4.6 TSSR Approved |  | 2023-12-25 | 2023-12-28 |  | 2024-04-19 |  | Closed | 2024-04-26 | 2024-04-30 | E//Sumitra | 2024-04-30 | CelcomDigi_RAN_Magicell_TSS_Central_20231227 | DU00002860894 |  |  | 2024-06-15 | 2024-06-13 |  | In-Building System | 3m Bipod (RT) | 10 | Add R8862A S9000 x3,Dismantle | 0 | 0
3344A | BDR_PUTERIPCHG5 | Central |  | Modernization |  | 2024 Q3 | SH | Magicell | 4.6 TSSR Approved |  | 2024-01-08 | 2024-01-16 |  | 2024-04-22 |  | Closed | 2024-05-06 | 2024-05-07 | E//Kok Keen | 2024-05-07 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240110 | DU00002860895 |  |  | 2024-09-24 | 2024-09-23 |  | In-Building System | 30m Monopole | 6 | Add R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3++R8881 S2100 x3 | 0 | 0
3243B | Taman Puncak Jalil (REL) | Central |  | Modernization |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-07-15 | 2024-07-14 |  | 2024-07-16 |  | Under Approval | 2024-12-10 | 2024-12-10 | E//Sumitra | 2024-12-10 | 0712Central-DATASCO-BOQ Template | DU00002860896 |  |  | 2024-11-17 | 2024-09-13 |  | Monopole | 24m Lampole | 30m | Add A9732 M1821x1 | 2 | 3
3388A | Chr-Kjg | Central |  | Modernization |  | 2024 Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-16 | 2023-11-21 |  | 2024-05-15 |  | Closed | 2024-08-13 | 2024-09-25 | E//Sumitra | 2024-09-25 | CelcomDigi_RAN_GTSB_TSS_20231119 | DU00002860897 |  |  | 2024-09-10 | 2024-09-06 |  | Lampole | Tower | 25m | Add R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882 S1800(B) x2+R8882 S1800B x1+R8882-L268 x1+R8881 S2100 x3+ | 0 | 1
3431A | DESA_MELAWATI1 | Central |  | Modernization | On Hold->Site out->Modernization | 2024 Q1 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-14 | 2023-12-13 |  | 2024-01-02 |  | Closed | 2024-02-26 | 2024-02-27 | E//Sumitra | 2026-04-17 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231116 | DU00002860898 | Remarks: Solution TSSR/BOM Changed |  | 2025-09-15 | 2025-09-12 |  | In-Building System | 30m Monopole | 7 | Add R9264H M901821x3+R8862A S2601x3,Dismantle R8882-GUL1812x3+R8882 S2600(B4A)x3 | 0 | 0
3436A | BT2_JLN_CHRS1 | Central |  | Modernization |  | 2024 Q3 | SH | Ascentrack | 4.6 TSSR Approved |  | 2023-12-27 | 2024-01-22 |  | 2024-04-05 |  | Closed | 2024-04-16 | 2024-04-18 | E//Kok Keen | 2024-04-18 | CelcomDigi_RAN_Ascentrak_TSS_Central_20231230 | DU00002860899 |  |  | 2024-07-29 | 2024-07-29 |  | In-Building System | 30m Monopole | 6m | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 23 | 0
3454A | KUMPULANCHALK6 | Central |  | Modernization |  | 2024 Q2 | AD | CCSMY | 4.6 TSSR Approved |  | 2024-01-17 | 2024-01-23 |  | 2024-02-06 |  | Closed | 2024-02-07 | 2024-02-14 | E//Sumitra | 2024-02-14 | CelcomDigi_RAN_CCS_TSS_Central_20240124 | DU00002860900 |  |  | 2024-05-16 | 2024-04-29 |  | In-Building System | 3m Bipod (RT) | 3m & 7m | Add R9264M M1821 x3,Dismantle R8882 S1800(B) x3+R8862A S2100(A6A) x3
3455A | PUTRASULAIMAN1 | Central |  | Modernization |  | 2024 Q2 | SS | YPTT | 4.6 TSSR Approved |  | 2023-11-22 | 2023-11-28 |  | 2024-01-11 |  | Closed | 2024-01-15 | 2024-01-17 | E//Sumitra | 2024-01-16 | CelcomDigi_RAN_YPTT_TSS_Central_20231126 | DU00002860901 |  |  | 2024-07-20 | 2024-07-17 |  | Minimast | 3m Bipod (RT) | 15 | Add R9264H M901821 x3,Dismantle R8882 S1800B(B6B) x3++R8881 S2100 x3+
4058B6 | pBTS Sepang Goldcoast | Central |  | Modernization | Modernization->On Hold->Modernization | 2024 Additional | AI | YPTT | 4.6 TSSR Approved |  | 2025-02-22 | 2025-03-07 |  | 2025-03-18 |  | Closed | 2025-03-19 | 2025-04-15 | E//Razif | 2025-03-20 | SQ202411190429 | DU00002860902 |  |  | 2025-03-25 | 2025-03-25 |  | Watertank | 25m pBTS | 30 | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8882-GUL1812x1R8862A S1800(B6A)x1 | 0 | 0
4142A | KISAP | Northern |  | Modernization |  | 154 single site MOCN | SM | GTSB | 4.6 TSSR Approved |  | 2024-08-29 | 2024-09-07 |  | 2024-09-11 |  | Rectificating | 2024-09-12 | 2024-09-23 | E//Hazida | 2024-09-20 | 0809CD-Northern-GTSB-BOQ Template(new contract) | DU00002860903 |  |  | 2024-10-24 | 2024-10-19 |  | Tower | 45m 3 Legged Tower | 50M | Add R8894E M1821 x2+A9732 M1821 x1,Dismantle R8882-GUL1812 x3 | 1
4260B | KG NAWA | Northern |  | Modernization |  | 131 single site mocn | SHA | CCSMY | 4.6 TSSR Approved |  | 2024-08-19 | 2024-08-27 |  | 2024-08-29 |  | Under Approval | 2024-08-30 | 2024-09-11 | E//Ajay | 2024-09-11 | 0809CD-Northern-CCSMY-BOQ Template(new contract) | DU00002860904 |  |  | 2024-09-18 | 2024-09-06 |  | Tower | Tower | 50M | Add R8852E S9000 x3+R8894E M1821 x1+A9732 M1821 x2,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3 | 13 | 0
4280B | Lata Mengkuang Clm | Northern |  | Decomm | Decomm->On Hold->Decomm | 2025 Q3 | HW | NR services | 4.6 TSSR Approved |  | 2025-09-10 |  | 2025-09-03 |  | 2025-09-10 |  | 2025-09-19 | 2026-02-10 | E//Hazida | 2025-09-22 | SQ202502100379 | DU00002860905 |  |  |  |  | 2025-10-14 |  | Tower
4290B | Bukit Hantu Celcom | Northern |  | Modernization |  | 2024 Q3(single site MOCN) | SM | GTSB | 4.6 TSSR Approved |  | 2024-04-18 | 2024-04-23 |  | 2024-04-26 |  | Closed | 2024-05-10 | 2024-05-16 | E//Hazida | 2024-05-15 | Celcom Digi_RAN-GTSB-TSS-Northern-20240422-0104 | DU00002860906 |  |  | 2024-06-26 | 2024-06-18 |  | Tower | 60m 3 Legged Tower | 60M | Add R8862A S9000 x3+R9224E M1821 x1+R8862A S2600 x2+A9732 M1821 x2,Dismantle R8860E-GU908 x3+R8882 S1800(B) x1+R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 | 23 | 0
4291B | Bkt Penarak Maxis | Northern |  | Modernization |  | 2024 Q3(single site MOCN) | SM | GTSB | 4.6 TSSR Approved |  | 2023-10-17 | 2023-10-20 |  | 2024-04-16 |  | Rectificating | 2024-04-17 | 2024-04-22 | E//Hazida | 2024-04-19 | Celcom Digi_RAN-GTSB-TSS-Northern-20231018-0051 | DU00002860907 |  |  | 2024-07-02 | 2024-06-18 |  | Tower | 90m 4 Legged Tower | 85 | Add R8862A S9000 x3+A9732 M1821 x3,Dismantle R8882-GUL1812 x2+R8882 S1800B(B6B) x1+R8840-U216 x3++ | 123 | 0
4312A | Bidor (NS highwa | Northern |  | Modernization |  | 2024 Additional | SHA | CCSMY | 4.6 TSSR Approved |  | 2023-11-21 | 2023-11-20 |  | 2024-11-22 |  | Under Approval | 2024-11-26 | 2024-12-16 | E//Hazida | 2024-12-15 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231122-0072//2111CD-Northern-TSS-BOQ Template(new contract)_CCSMY | DU00002860908 | Remarks: Solution TSSR/BOM Changed |  | 2024-12-05 | 2024-12-05 |  | Tower | 6m Unipole RT | 60m | Add R8894E M1821x1+R8854 S2600x1, Dismantle R8862A S2600(A4A) x1 | 0 | 1
4321A | Batu Gajah | Northern |  | Modernization |  | 2024 Additional | SM | CCSMY | 4.6 TSSR Approved |  | 2024-11-19 | 2024-11-26 |  | 2024-11-27 |  | Rectificating | 2024-12-04 | 2024-12-16 | E//Hazida | 2024-12-15 | 1911CD-Northern-TSS-BOQ Template(new contract)_CCSMY_V2 | DU00002860909 |  |  | 2025-01-05 | 2024-12-11 |  | In-Building System | 6m RT (Boom) | 6 | Add R8852E S9000 x3 | 0 | 0
4324B | Layang RCC | Northern |  | Modernization |  | 2024 Q2 | SM | GTSB | 4.6 TSSR Approved | ¦ 0301 - Revised TSSR submitted n BOM revised ¦ 0228 - Listed for solution change, pending confirmed solution | 2024-01-08 | 2024-01-09 |  | 2024-01-15 |  | Rectificating | 2024-03-01 | 2024-03-06 | E//Hazida | 2024-03-01 | Celcom Digi_RAN-GTSB-TSS-Northern-20240110-0084 | DU00002860910 |  |  | 2024-03-18 | 2024-03-12 |  | Tower | Tower | 110m | Add R8852E S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 23 | 0
4325A | Changkat Cermin RCC | Northern |  | Modernization |  | 2024 Q2 | SM | GTSB | 4.6 TSSR Approved | ¦ 0228 - Listed for solution change, pending confirmed solution ¦ 0126 - Revised TSSR submitted ¦ 0123 - BOM uploaded | 2024-01-12 | 2024-01-15 |  | 2024-01-19 |  | Rectificating | 2024-03-06 | 2024-03-07 | E//Ajay | 2024-03-06 | Celcom Digi_RAN-GTSB-TSS-Northern-202401114-0085 | DU00002860911 |  |  | 2024-04-08 | 2024-04-02 |  | Tower | Tower | 60m | Add R8862A S9000 x2+R8894E M1821 x6+R8854 S2600 x3,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3+R8862A S2600(A4A) x3 | 0 | 123
4332B | Kg Keretapi RCC | Northern |  | Modernization |  | 2025 Q1 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-11-19 | 2023-11-21 |  | 2025-01-15 |  | Rectificating | 2025-01-16 | 2025-01-17 | E//Hazida | 2025-01-17 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231122-0072 | DU00002860912 |  |  | 2025-02-06 | 2025-01-22 |  | Tower | 45m 3 Legged Tower | 77M | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8860E-GU908x3+R8882-GUL1812x2+R8862A S1800(B6A)x1+R8854D S2100(A4A)x3 | 0 | 0
4335A | Kg Nelayan RCC | Northern |  | Modernization |  | 2024 Additional | SHA | CCSMY | 4.6 TSSR Approved |  | 2023-10-23 | 2023-11-30 |  | 2024-11-21 |  | Under Approval | 2024-12-04 | 2024-12-06 | E//Hazida | 2024-12-06 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231025-0061 | DU00002860913 |  |  | 2024-12-31 | 2024-12-11 |  | Tower | 76m 3 Legged Tower | 77 | Add R8852E S9000 x2+R8894E M1821x3 | 0 | 0
4363A | Mambang Diawan RDD | Northern |  | Modernization |  | 2024 Additional | SM | GTSB | 4.6 TSSR Approved |  | 2023-11-16 | 2023-12-22 |  | 2024-01-05 |  | Under Approval | 2024-11-21 | 2024-12-17 | E//Hazida | 2024-12-17 | Celcom Digi_RAN-GTSB-TSS-Northern-20231118-0066 | DU00002860914 |  |  | 2024-11-29 | 2024-11-25 |  |  | 60m 4 Legged Tower | 45 | Add R8852E S9000 x3+R8894E M1821x4+R8854 S2600x1, Dismantle R8860E-GU908x2+R8882-GUL1812x2+R8862A S1800(B6A)x1+R8854D S2100(A4A)x3+R8862A S2600(A4A)x1 | 0 | 2
4367A | Kg Gajah(Celcom) | Northern |  | Modernization |  | 2024 Q2 | SM | GCI | 4.6 TSSR Approved | ¦ 0228 - Listed for solution change, pending confirmed solution | 2023-12-22 | 2024-01-05 |  | 2024-01-15 |  | Rectificating | 2024-03-05 | 2024-03-06 | E//Hazida | 2024-03-06 | Celcom Digi_RAN-GCI-TSS-Northern-20231214-0084 | DU00002860915 |  |  | 2024-04-22 | 2024-03-15 |  | Tower | 60m 4 Legged Tower | 60 | Add A9732 M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 123 | 0
4367B | Utar Kampar RCC | Northern |  | Modernization |  | 2024 Q3(single site MOCN) | BY | CCSMY | 4.6 TSSR Approved |  | 2024-01-17 | 2024-01-19 |  | 2024-04-23 |  | Closed | 2024-05-09 | 2024-05-10 | E//Hazida | 2024-05-10 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240124-0089 | DU00002860916 |  |  | 2024-06-24 | 2024-06-15 |  | Tower | Tower | 60m | Add R8862A S9000 x3+A9732 M1821 x3,Dismantle R9224E M1821(AAB) x3 | 123 | 0
4370A | Tmn Kampar Perdana | Northern |  | Modernization |  | 2024 Additional | AI | CCSMY | 4.6 TSSR Approved |  | 2024-12-04 | 2024-12-17 |  | 2024-12-18 |  | Under Approval | 2024-12-20 | 2024-12-20 | E//Hazida | 2024-12-20 | 1911CD-Northern-TSS-BOQ Template(new contract)_CCSMY_V2 | DU00002860917 |  |  | 2025-01-19 | 2025-01-17 |  | Tower | 60m 3 Legged Tower | 60M | Add R8852E S9000 x3+R8894E M1821x3+R8862A S2601x3, Dismantle R8860E-GU908x1+R8882-GUL1812x3+R8882 S1800B(B6B)x2+R8862A S1800(B6A)x1+R8840-U216x3+R8882 S2600(B4A)x2+R8862A S2600(A4A)x1 | 0 | 0
4371B | Lubok Merbau KK RDD | Northern |  | Modernization |  | 154 single site MOCN | SHA | CCSMY | 4.6 TSSR Approved |  | 2023-10-28 | 2023-11-06 |  | 2024-08-16 |  | Under Approval | 2024-08-19 | 2024-08-22 | E//Ajay | 2024-08-21 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231028-0063 | DU00002860918 |  |  | 2024-08-28 | 2024-08-24 |  | Tower | 60m 3 Legged Tower | 62m | Add R8852E S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882-GUL1812 x3+R8862A S2600(A4A) x1 |  | 2
4373B | Sauk | Northern |  | Modernization | Modernization->On Hold->Modernization | 2025 Q3 | AI | GCI | 4.6 TSSR Approved |  | 2023-10-09 | 2023-12-29 |  | 2025-02-25 |  | Closed | 2025-03-11 | 2025-04-15 | E//Hazida | 2025-03-17 | Celcom Digi_RAN-GCI-TSS-Northern-2023111-0057 | DU00002860919 |  |  | 2025-05-27 | 2025-05-23 |  | Tower | 60m 3 Legged Tower | 76 | Add R8894E M1821 x3, Dismantle R8882-GUL1812x3 | 0 | 0
4401B | Kg Temerloh-100Q4 RDD | Northern |  | Decomm | Decomm->On Hold->Decomm | 2024 Q2 | HW | CCSMY | 4.6 TSSR Approved |  | 2024-01-02 |  |  |  | 2024-01-02 |  | 2025-02-27 | 2025-07-29 | E//Hazida | 2025-02-28 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240108-0084 | DU00002860920 |  | Not space for relocation, need check other cabinet |  |  | 2025-06-12 |  | 60m 3 Legged Tower
4411A | Slim River (Maxis) | Northern |  | Modernization |  | 2024 Q3(single site MOCN) | BY | YPTT | 4.6 TSSR Approved | SUBMI PENDING RF APPROVAL | 2023-12-22 | 2023-12-27 |  | 2025-02-06 |  | Under Approval | 2024-05-09 | 2024-06-12 | E//Hazida | 2024-06-12 | Celcom Digi_RAN-YPTT-TSS-Northern-20231225-0047 | DU00002860921 |  |  | 2024-06-30 | 2024-06-21 |  | Tower | 60m 4 Legged Tower | 60M | Add R8862A S9000 x2+A9732 M1821 x3+R8862A S2601 x1,Dismantle R8894E M1821(A8A) x3 | 234 | 0
4413B | Kuala Slim | Northern |  | Decomm | Decomm->On Hold->Decomm | 2024 Additional | SM | GTSB | 4.6 TSSR Approved |  | 2023-12-07 |  |  |  | 2023-12-12 | To be Submitted | 2025-02-07 |  | E//Hazida | 2025-03-03 | Celcom Digi_RAN-GTSB-TSS-Northern-20231207-0073/Celcom Digi_RAN-GTSB-TSS-Northern-20241030_New Contract | DU00002860922 |  | Wrong Link propose DECOM |  |  | 2025-05-14 |  | 60m 4 Legged Tower
4415B | SLIM VILLAGE | Northern |  | Modernization |  | 2024 Additional | BY | YPTT | 4.6 TSSR Approved |  | 2023-11-24 | 2023-11-30 |  | 2023-12-04 |  | Closed | 2023-12-07 | 2023-12-13 | E//Hazida | 2023-12-13 | Celcom Digi_RAN-YPTT-TSS-Northern-20231127-0045 | DU00002860923 |  |  | 2024-11-26 | 2024-11-26 |  | Guide mast | 60m 4 Legged Tower | 60 | Add R8862A S9000 x1+R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x1++
4416B | Sg Klah | Northern |  | Modernization |  | 2024 Additional |  | GTSB | 4.6 TSSR Approved |  | 2023-10-27 | 2023-12-12 |  | 2023-12-14 |  | Closed | 2023-12-15 | 2023-12-20 |  | 2023-12-17 | Celcom Digi_RAN-GTSB-TSS-Northern-20231028-0057 | DU00002860924 |  |  | 2024-11-28 | 2024-11-25 |  | Tower | 60m 4 Legged Tower | 60 | Add R8894E M1821x3, Dismantle R8862A S1800(B6A)x3 | 0 | 0
4422A | KJS Bukit Merah | Northern |  | Modernization |  | 2025 Q1 | AI | Magicell | 4.6 TSSR Approved |  | 2024-01-13 | 2024-01-19 |  | 2025-01-27 |  | Under Approval | 2025-01-28 | 2025-02-27 | E//Hazida | 2025-02-19 | SQ202501030105 - Magicell | DU00002860925 |  |  | 2025-03-15 | 2025-03-10 |  | Tower | 76m Tower | 76m | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8882-GUL1812x2+R8862A S1800(B6A)x1 | 0 | 0
4425A | Changkat Lobak RDD | Northern |  | Modernization |  | 2025 Q1 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-10-22 | 2023-11-30 |  | 2025-01-15 |  | Rectificating | 2025-01-16 | 2025-01-17 | E//Haizda | 2025-01-17 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231022-0060 | DU00002860926 |  |  | 2025-01-26 | 2025-01-26 |  | Tower | 60m 3 Legged Tower | 61 | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x1 | 0 | 0
4377B | Karai RDD | Northern |  | Modernization |  | 2025 Q3 | SM | Magicell | 4.6 TSSR Approved |  | 2023-10-30 | 2023-11-27 |  | 2025-01-27 |  | Under Approval | 2025-02-27 | 2025-02-28 | E//Hazida | 2025-02-28 | Celcom Digi_RAN-Magicell-TSS-Northern-20231101-0002 | DU00002860927 |  |  | 2025-04-19 | 2025-03-19 |  | Tower | 45m slim tower | 61 | Add R8894E M1821x3, Dismantle R8882-GUL1812x3+R8854D S2100(A4A)x3 | 0 | 0
4378A | Jerlun Tower | Northern |  | Modernization |  | 2025 Q3 | SM | GCI | 4.6 TSSR Approved |  | 2023-10-16 | 2023-10-26 |  | 2023-11-02 |  | Rectificating | 2025-01-13 | 2025-01-14 | E//Hazida | 2025-01-14 | Celcom Digi_RAN-GCI-TSS-Northern-20231018-0061 | DU00002860928 | Remarks: Solution TSSR/BOM Changed |  | 2025-02-22 | 2025-01-22 |  | Tower | 60m 4 Legged Tower | 60 | Add R8852E S9000x4+A9732 M1821 x1+R9264M M1821 x3, Dismantle R8882-GUL1812x2+R8862A S1800(B6A)x2 | 1 | 0
4380A | Kuala Kangsar Industry | Northern |  | Modernization |  | 154 single site MOCN | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-10-12 | 2023-10-16 |  | 2023-10-23 |  | Closed | 2024-08-16 | 2024-08-19 | E//Hazida | 2024-08-19 | Celcom Digi_RAN-GTSB-TSS-Northern-20231013-0048 | DU00002860929 |  |  | 2024-08-31 | 2024-08-21 |  | Monopole | 45m Monopole | 30 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8840-U216 x3 | 0 | 0
4430B | Perlop RDD | Northern |  | Modernization | Modernization->On Hold->Modernization | 2025 Q3 | HW | GCI | 4.6 TSSR Approved |  | 2023-10-31 | 2023-11-03 |  | 2025-03-11 |  | Under Approval | 2025-03-17 | 2025-05-19 | E//Hazida | 2025-03-20 | Celcom Digi_RAN-GCI-TSS-Northern-20231102-0070 | DU00002860930 |  |  | 2025-04-23 | 2025-04-16 |  | Tower | Tower | 61 | Add R8894E M1821x3, Dismantle R8862A S1800(B6A)x3+R8881 S2100x3 | 0 | 0
4445A | Chui Chak | Northern |  | Modernization |  | 2025 Q1 | AA | GTSB | 4.6 TSSR Approved |  | 2025-01-15 | 2025-01-27 |  | 2025-02-07 |  | Closed | 2025-02-13 | 2025-05-27 | E//Hazida | 2025-04-23 | SQ202501030229 - gtsb | DU00002860931 | Remarks: Solution TSSR/BOM Changed |  | 2025-04-14 | 2025-04-04 |  | Tower | 60m 3 Legged Tower | 60M | Add R8852E S9000x3+R8894E M1821x4+R8854 S2600x1, Dismantle R8860E-GU908x1+R8882-GUL1812x2+R8862A S1800(B6A)x1+R8854D S2100(A4A)x3+R8862A S2600(A4A)x1 | 0 | 2
4458B | Bukit Naga RCC | Northern |  | Decomm | Decomm->On Hold->Decomm | 2024 Q2 | HW | GTSB | 4.6 TSSR Approved |  | 2024-01-29 |  |  |  | 2024-02-07 |  | 2025-02-21 | 2025-07-29 | E//Hazida | 2025-02-27 | Celcom Digi_RAN-GTSB-TSS-Northern-20241030_New Contract | DU00002860932 |  |  |  |  | 2025-06-23 |  | 60m 4 Legged Tower
9022B | UiTM Samarahan | Sarawak |  | Modernization |  | 2024 Q2 | MS | AllStar | 4.6 TSSR Approved |  | 2023-10-11 | 2023-10-18 |  | 2023-10-20 |  | Closed | 2023-10-26 | 2023-11-14 | E//Hannah | 2023-11-08 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20231013 | DU00002860933 |  |  | 2023-12-16 | 2023-11-16 |  | Tower | 45m 3 Legged Tower | 75 | Add A9732 M1821 x3,Dismantle R9224E M1821(AAB) x5 | 123 | 0
4435A | Sg Siput Shoplot | Northern |  | Decomm | Modernization->On Hold->Decomm | 2025 Q3 | HW | GTSB | 4.6 TSSR Approved |  | 2023-10-21 | 2023-11-02 | 2025-06-18 |  | 2025-06-19 |  | 2025-06-23 |  | E//Haliza | 2025-07-02 | Celcom Digi_RAN-GTSB-TSS-Northern-20231022-0054 | DU00002860934 | SOW Changed from Mod to Decomm | SOW Changed from Mod to Decomm |  |  | 2025-09-26 | In-Building System | 5m RT (Boom) | 5
4470B | Bagan Pasir | Northern |  | Modernization | Modernization->On Hold->Modernization->On Hold->Modernization | 154 single site MOCN | SM | CCSMY | 4.6 TSSR Approved |  | 2024-01-16 | 2024-01-23 |  | 2024-11-04 |  | Rectificating | 2024-11-28 | 2024-12-17 | E//Hazida | 2024-12-17 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240117-0088 | DU00002860935 |  |  | 2024-11-17 | 2024-11-17 |  | Tower | 60m 4 Legged Tower | 62m | Add R8862A S9000x3+R8894E M1821x3+A9732 M1821x1, Dismantle R8882-GUL1812x2+R8862A S1800(B6A)x1+R8854D S2100(A4A)x3 | 2 | 1
4477B | Chenderong Balai | Northern |  | Modernization |  | 154 single site MOCN | SY1 | GCI | 4.6 TSSR Approved |  | 2024-02-19 | 2024-02-23 |  | 2024-08-20 |  | Closed | 2024-08-23 | 2024-09-03 | E//Hazida | 2024-09-02 | Celcom Digi_RAN-GCI-TSS-Northern-20240226-0098 | DU00002860936 |  |  | 2024-09-09 | 2024-08-26 |  | Tower | 60m 4 Legged Tower | 60 | Add R8862A S9000 x3+R8894E M1821 x1+R8854 S2600 x1,Dismantle R8862A S2601(A6A) x1 |  | 3
9029B | Kg Empila | Sarawak |  | Modernization |  | 2024 Q2 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-11-28 | 2023-11-30 |  | 2024-03-08 |  | Closed | 2024-03-05 | 2024-03-07 | E//Hannah | 2024-03-07 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231206 | DU00002860937 |  |  | 2024-05-20 | 2024-04-23 |  | Tower | Tower | 70 | Add R8852E S9000 x3+R8894E M1821 x3+R8854 S2600 x3,Dismantle R8862A S2600(A4A) x3 | 0 | 123
4484B | Temoh Station-100Q4 RDC | Northern |  | Modernization |  | 2024 Additional | AD | GTSB | 4.6 TSSR Approved |  | 2023-11-17 | 2023-12-26 |  | 2024-01-05 |  | Under Approval | 2024-11-20 | 2024-12-16 | E//Hazida | 2024-12-16 | Celcom Digi_RAN-GTSB-TSS-Northern-20231118-0066 | DU00002860938 |  |  | 2024-12-04 | 2024-12-01 |  | Tower | 60m 3 Legged Tower | 60 | Add R8862A S9000 x1+R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3
4506B | PosSlim 18 RDC | Northern |  | Modernization |  | 2024 Q3(single site MOCN) | BY | GCI | 4.6 TSSR Approved |  | 2024-04-22 | 2024-04-24 |  | 2024-05-09 |  | Closed | 2024-05-16 | 2024-05-30 |  | 2024-05-30 | Celcom Digi_RAN-GCI-TSS-Northern-20240512-0106 | DU00002860939 |  |  | 2024-06-24 | 2024-06-15 |  | Tower | 60m 3 Legged Tower | 60 | Add R8852E S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8854D S2100(A4A) x3+R8862A S2600(A4A) x1 | 0 | 2
4510B | Taman Ipoh Jaya | Northern |  | Modernization |  | 2024 Q2 | BY | Magicell | 4.6 TSSR Approved |  | 2023-11-04 | 2023-11-10 |  | 2024-01-08 |  | Rectificating | 2024-01-08 | 2024-01-11 | E//Ajay | 2024-01-10 | Celcom Digi_RAN-Magicell-TSS-Northern-20231115-0003 | DU00002860940 |  |  | 2024-01-19 | 2024-01-12 |  | In-Building System | 3m Boom (RT) | 6 | Add R8894E M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8854D S2100(A4A) x3
4523B | Taman Botani (Maxis) RCC | Northern |  | Modernization |  | 2024 Q2 |  | CCSMY | 4.6 TSSR Approved | ¦ 0207 - TP rejected, need to add in table existing RRU on top. | 2023-10-18 | 2023-10-23 |  | 2024-01-08 |  | Closed | 2024-01-09 | 2024-01-11 |  | 2024-01-11 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231019-0058 | DU00002860941 |  |  | 2024-02-27 | 2024-02-20 |  | Tower | 45m Monopole Tree | 40 | Add R8894E M1821 x4+R8854 S2600 x1,Dismantle R8860E-GU908 x1+R8882-GUL1812 x3+R8882 S2600(B4A) x1+R8840-U216 x3++ |  | 3
4551A | Kg Bali RDD | Northern |  | Modernization |  | 2024 Additional | AD | CCSMY | 4.6 TSSR Approved |  | 2024-11-19 | 2025-01-17 |  | 2025-01-22 |  | Under Approval | 2025-01-27 | 2025-03-09 | E//Hazida | 2025-02-19 | 1911CD-Northern-TSS-BOQ Template(new contract)_CCSMY_V2 | DU00002860942 |  |  | 2025-02-21 | 2025-02-21 |  | Tower | 60m 3 Legged Tower | 65m | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8860E-GU908x3+R8882-GUL1812x3+R8862A S2100(A6A)x3 | 0 | 0
4554A | Kg Jeram RDD | Northern |  | Modernization |  | 2024 Additional | SM | GTSB | 4.6 TSSR Approved |  | 2023-12-30 | 2025-01-15 |  | 2025-01-20 |  | Rectificating | 2025-01-21 | 2025-02-18 | E//Hazida | 2025-02-18 | 1911CD-Northern-TSS-BOQ Template(new contract)_GTSB | DU00002860943 | Remarks: Solution TSSR/BOM Changed |  | 2025-02-13 | 2025-02-05 |  |  | 60m 4 Legged Tower | 60M | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8860E-GU908x2+R8882-GUL1812x1+R8882 S1800B(B6B)x3+R8862A S2100(A6A)x3 | 0 | 0
9038B | Simunjan 2 | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 | NA | Magicell | 4.6 TSSR Approved |  | 2025-04-09 |  | 2025-04-09 |  | 2025-05-04 |  | 2025-05-05 | 2025-10-28 | E//John | 2025-05-22 | SQ202503170852-Magicell | DU00002860944 |  |  |  |  | 2025-08-29 |  | Tower
9039A | Sungai Jerenang | Sarawak |  | Modernization |  | 2024 Q2 | ZB | AllStar | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦sacofa not allow to add AAU | 2023-10-10 | 2023-10-16 |  | 2023-10-20 |  | Closed | 2023-12-14 | 2023-12-15 | E//Hannah | 2023-12-15 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20231013 | DU00002860945 |  |  | 2024-04-29 | 2024-04-22 |  | Tower | Tower | 45m | Add R8894E M1821 x3+R8854 S2600 x3,Dismantle R8862A S2600(A4A) x3 | 0 | 123
4575A | NS-KM322(KJS) | Northern |  | Modernization |  | 2024 Additional | ZA | GCI | 4.6 TSSR Approved |  | 2023-11-07 | 2023-11-23 |  | 2023-12-01 |  | Closed | 2023-12-04 | 2023-12-22 | E//Ajay | 2023-12-21 | Celcom Digi_RAN-GCI-TSS-Northern-20231115-0074 | DU00002860946 |  |  | 2024-11-26 | 2024-11-26 |  | Tower | 60m 4 Legged Tower | 62 | Add R8852E S9000x1+R8894E M1821x3+R8862A S2601x1, Dismantle R8882-GUL1812x2 | 0 | 0
4577A | NSKM319 NB(Maxis) | Northern |  | Modernization |  | 2024 Additional | ZA | GCI | 4.6 TSSR Approved | 1224 - Emailed Rollout on major CME required. | 2023-11-10 | 2023-11-17 |  | 2023-12-02 |  | Closed | 2023-12-07 | 2024-01-23 | E//Hazida | 2024-01-21 | Celcom Digi_RAN-GCI-TSS-Northern-20231122-0075 | DU00002860947 |  |  | 2025-06-23 | 2025-06-23 |  | Monopole | 24m Monopole | 47 | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8860E-GU908x3+R8882-GUL1812x3+R8862A S2100(A6A)x3 | 0 | 0
9044B | Kg Biawak USP | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2024 Q2 | NA | South Pacific | 4.6 TSSR Approved |  | 2024-01-23 |  |  |  | 2025-05-08 |  | 2025-05-17 | 2025-10-17 | E//Hannah | 2025-10-16 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20240124 | DU00002860948 |  |  |  |  | 2025-07-26 |  | Tower
4597B | Desa Sri Iskandar RDC | Northern |  | Modernization |  | 2024 Q2 | BY | GCI | 4.6 TSSR Approved | ¦ 0228 - Listed for solution change, pending confirmed solution | 2024-01-18 | 2024-01-30 |  | 2024-02-06 |  | Closed | 2024-02-29 | 2024-03-04 | E//Ajay | 2024-03-04 | Celcom Digi_RAN-GCI-TSS-Northern-20240124-0090 | DU00002860949 |  |  | 2024-03-11 | 2024-03-07 |  | Tower | 6m RT (Boom) | 60 | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 1 | 0
4599B | UTP Tronoh | Northern |  | Modernization |  | 2024 Q2 | BY | CCSMY | 4.6 TSSR Approved | ¦ 0228 - Listed for solution change, pending confirmed solution | 2024-01-07 | 2024-01-08 |  | 2024-01-15 |  | Closed | 2024-03-04 | 2024-03-04 | E//Hazida | 2024-03-04 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240108-0084 | DU00002860950 |  |  | 2024-03-18 | 2024-03-13 |  | Lampole | 30m Lampole | 31m | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8882-GUL1812 x3+R8840-U216 x3++ | 2 | 0
4600B | Sanglang (Mxs) | Northern |  | Modernization |  | 2024 Q4 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-10-19 | 2023-10-30 |  | 2024-04-18 |  | Closed | 2024-04-23 | 2024-05-15 | E//Hazida | 2024-05-13 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231020-0059 | DU00002860951 |  |  | 2024-05-29 | 2024-05-16 |  | Tower | 60m 3 Legged Tower | 70m | Add R8862A S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8860E-GU908 x3+R8882 S1800B(B6B) x3+R8854D S2100(A4A) x3+R8862A S2600(A4A) x1 | 0 | 2
4601B | Kaki Bukit | Northern |  | Modernization |  | 131 single site mocn | MS | GCI | 4.6 TSSR Approved |  | 2024-04-12 | 2024-04-21 |  | 2024-08-19 |  | Under Approval | 2024-08-23 | 2024-09-12 | E//Hazida | 2024-09-11 | Celcom Digi_RAN-GCI-TSS-Northern-20240512-0106 | DU00002860952 |  |  | 2024-09-09 | 2024-09-04 |  | Tower | 50m 3 Legged Tower | 50M | Add R8852E S9000 x2+R8894E M1821 x4,Dismantle R8862A S1800(B6A) x3+R8862A S2601(A6A) x3 | 0 | 2
9053A | Unimas 2(SACOFA) | Sarawak |  | Modernization |  | 2024 Q2 | SH | AllStar | 4.6 TSSR Approved |  | 2023-10-17 | 2023-11-23 |  | 2023-12-14 |  | Closed | 2024-03-04 | 2024-03-05 | E//Hannah | 2024-03-05 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20231019 | DU00002860953 |  |  | 2024-05-03 | 2024-03-16 |  | Tower | Tower | 60 | Add R9224E M1821 x3+R8854 S2600 x4,Dismantle R8862A S2600(A4A) x3+R8862A S2601(A6A) x1 | 0 | 1234
4602B | Bukit Kateri(Mxs) | Northern |  | Modernization |  | 131 single site mocn | AI | GTSB | 4.6 TSSR Approved |  | 2023-10-16 | 2023-10-20 |  | 2024-08-29 |  | Closed | 2024-09-25 | 2024-09-26 | E//Hazida | 2024-09-26 | Celcom Digi_RAN-GTSB-TSS-Northern-20231017-0050 | DU00002860954 |  |  | 2024-09-20 | 2024-09-13 |  | Tower | 76m 3 Legged Tower | 60 | Add R8852E S9000 x3+R8894E M1821 x1+A9732 M1821 x2,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 13 | 0
4614B | Kubang Triwer | Northern |  | Modernization |  | 154 single site MOCN | AI | GTSB | 4.6 TSSR Approved |  | 2023-10-18 | 2023-11-28 |  | 2024-08-20 |  | Under Approval | 2024-08-22 | 2024-08-30 | E//Hazida | 2024-08-30 | Celcom Digi_RAN-GTSB-TSS-Northern-20231019-0052 | DU00002860955 |  |  | 2024-08-29 | 2024-08-27 |  | Tower | 60m 3 Legged Tower | 60 | Add R8894E M1821 x5,Dismantle R8862A S1800(B6A) x4+R8862A S2100(A6A) x4+R8862A S2601(A6A) x4 | 0 | 2
4621B | Jeniang | Northern |  | Modernization |  | 131 single site mocn | SM | CCSMY | 4.6 TSSR Approved | ¦ 0923 - E//Hazzida: TSSR approved with comment; As per discussed with CD planner Zulakmar, propose to unpair 4621B and K00274 to ensure no degradation on existing coverage area. | 2024-08-25 | 2024-08-27 |  | 2024-08-30 |  | Rectificating | 2024-09-03 | 2024-09-23 | E//Hazida | 2024-09-23 | 0809CD-Northern-CCSMY-BOQ Template(new contract) | DU00002860956 |  |  | 2024-09-12 | 2024-09-06 |  | Tower | 60m 3 Legged Tower | 65M | Add R8862A S2601 x2+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x2 | 13
4622B | Sik Town | Northern |  | Modernization |  | 131 single site mocn | SHA | GCI | 4.6 TSSR Approved |  | 2024-08-18 | 2024-08-25 |  | 2024-08-29 |  | Under Approval | 2024-09-03 | 2024-09-20 | E//Hazida | 2024-09-20 | 0809CD-Northern-GCI-BOQ Template(new contract) | DU00002860957 |  |  | 2024-09-20 | 2024-09-07 |  | Tower | 60m 3 Legged Tower | 60 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123 | 0
9057A | Kg.Melayu | Sarawak |  | Modernization |  | 2024 Q2 | SH | Datasco | 4.6 TSSR Approved |  | 2023-10-12 | 2023-10-18 |  | 2023-10-23 |  | Closed | 2023-12-13 | 2024-01-19 | E//Hannah | 2024-01-18 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231016 | DU00002860958 |  |  | 2024-04-19 | 2024-04-04 |  | Tower | 45m 3 Legged Tower | 70 | Add R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3+R8862A S2600(A4A) x1 | 0 | 1
9058A | Tambirat | Sarawak |  | Modernization |  | 2024 Q2 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-10-21 | 2023-10-27 |  | 2023-12-13 |  | Closed | 2024-03-07 | 2024-03-18 | E//Hannah | 2024-03-15 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231024 | DU00002860959 |  | 2612 Different picture but same azimuth for sector 1. - Done revised | 2024-06-12 | 2024-06-07 |  | Tower | 45m 3 Legged Tower | 76 | Add R8862A S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x4 | 3 | 0
9058B | Riveria (Celcom) | Sarawak |  | Modernization |  | 2024 Q2 | AD | Magicell | 4.6 TSSR Approved |  | 2023-10-30 | 2023-11-02 |  | 2023-12-14 |  | Closed | 2024-01-16 | 2024-01-19 | E//Hannah | 2025-05-22 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231101 | DU00002860960 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed | 2025-09-27 | 2025-09-26 |  | Tower | 60m 4 Legged Tower | 47M | Add R8862A S9000x4+R8894E M1821x4+R8862A S2601x1, Dismantle R8882-GUL1812x3 | 0 | 0
9059A | Semera | Sarawak |  | Modernization |  | 2024 Q2 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-10-27 | 2023-11-21 |  | 2023-12-14 |  | Closed | 2024-03-07 | 2024-03-08 | E//Hannah | 2024-03-08 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231028 | DU00002860961 |  | 2612 1. Missing RRU location for sector 3. - Done Revised 2. Missing another UBR RRU for sector 3. -Done revised | 2024-04-16 | 2024-04-03 |  | Tower | 45m 3 Legged Tower | 60 | Add R8894E M1821 x3+R8854 S2600 x3,Dismantle R8862A S2600(A4A) x3 | 0 | 123
9059B | Desa Ilmu MP | Sarawak |  | Modernization |  | 2024 Q2 | SH | AllStar | 4.6 TSSR Approved |  | 2023-10-23 | 2023-10-27 |  | 2023-11-08 |  | Closed | 2024-03-04 | 2024-05-09 | E//Hannah | 2024-05-09 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20231024 | DU00002860962 |  |  | 2024-05-13 | 2024-05-07 |  | Monopole | 30m Monopole | 36 | Add A9732 M1821 x3,Dismantle R8882-GUL1812 x3+R8882 S1800B(B6B) x3+R8854D S2100(A4A) x3 | 123 | 0
4644A | Gunung Raya | Northern |  | Modernization |  | 2025 Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2025-01-27 | 2025-02-23 |  | 2025-02-28 |  | Rectificating | 2025-03-04 | 2025-03-19 | E//Hazida | 2025-03-19 | SQ202501030229 - gtsb | DU00002860963 |  |  | 2025-03-23 | 2025-03-13 |  | Tower | 75m 4 Legged Tower | 80m | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8882-GUL1812x3+R8881 S2100x2 | 0 | 0
4646A | Langkawi Airport | Northern |  | Modernization |  | 154 single site MOCN | SM | GTSB | 4.6 TSSR Approved |  | 2024-11-02 | 2024-11-11 |  | 2024-11-13 |  | Rectificating | 2024-11-13 | 2024-12-17 | E//Hazida | 2024-12-17 | 0809CD-Northern-GTSB-BOQ Template(new contract) | DU00002860964 |  |  | 2024-11-29 | 2024-11-25 |  |  | 2m RT (Boom) | NA | Add R8862A S9000x3+A9732 M1821x1, Dismantle R8894E M1821(A8A)x1 | 1 | 0
4647A | Kelebang | Northern |  | Modernization |  | 2024 Q3(single site MOCN) | BY | CCSMY | 4.6 TSSR Approved |  | 2023-10-18 | 2023-10-25 |  | 2023-11-02 |  | Closed | 2024-04-26 | 2024-05-13 |  | 2024-05-10 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231019-0058 | DU00002860965 |  |  | 2024-06-23 | 2024-06-18 |  | In-Building System | 6m RT (Boom) | 7m | Add R8862A S9000 x3+R9264H M901821 x1+R8862A S2601 x3+A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 134 | 0
4648A | Taman Berlian | Northern |  | Modernization | Modernization->On Hold | 2025 Q2 | AD | GTSB | 4.6 TSSR Approved |  | 2023-10-26 | 2023-10-20 |  | 2025-01-22 |  | Under Approval | 2025-02-14 | 2025-03-09 | E//Hazida | 2025-02-25 | Celcom Digi_RAN-GTSB-TSS-Northern-20231214-0077 | DU00002860966 |  |  | 2025-03-10 | 2025-03-03 |  | Minimast | 3m RT (Minimast) | 10m | Add R8852E S9000 x3+R9264M M1821 x3, Dismantle R8882-GUL1812x3 | 0 | 0
4662B | Padang Terap | Northern |  | Modernization |  | 131 single site mocn | SHA | GCI | 4.6 TSSR Approved |  | 2024-08-17 | 2024-08-20 |  | 2024-08-27 |  | Under Approval | 2024-08-28 | 2024-09-19 | E//Ajay | 2024-09-19 | 0809CD-Northern-GCI-BOQ Template(new contract) | DU00002860967 |  |  | 2024-10-28 | 2024-09-04 |  | Tower | Tower | 60 | Add R8852E S9000 x4+R8894E M1821 x4+R8862A S2601,Dismantle R8860E-GU908 x3 |  | 123
4702A | LAP Rapat Indah (REL) | Northern |  | Modernization |  | 2024 Q2 |  | YPTT | 4.6 TSSR Approved |  | 2023-12-26 | 2024-01-02 |  | 2024-01-11 |  | Closed | 2024-01-13 | 2024-01-17 | E//Hazida | 2024-01-16 | Celcom Digi_RAN-YPTT-TSS-Northern-20231226-0048 | DU00002860968 |  |  | 2024-03-24 | 2024-01-26 |  | Monopole | 30m Monopole | 30m | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882 S1800(B) x3+R8881 S2100 x3
4720B | Kg Tanjong | Northern |  | Modernization |  | 2025 Q3 | AD | GCI | 4.6 TSSR Approved |  | 2025-01-16 | 2025-02-05 |  | 2025-02-25 |  | Under Approval | 2025-04-11 | 2025-05-21 | E//Hazida | 2025-04-23 | SQ202501030261 - GCI | DU00002860969 |  |  | 2025-06-28 | 2025-04-19 |  | Tower | Tower | 60m | Add R8862A S9000x3+R8894E M1821x3+R8854 S2600x3, Dismantle R8862A S2600(A4A)x3 | 0 | 123
9085A | Holiday Park | Sarawak |  | Modernization |  | 2025 Q1 | AI | Trintel | 4.6 TSSR Approved |  | 2023-10-31 | 2023-11-14 |  | 2025-02-10 |  | Closed | 2025-03-27 | 2025-05-21 | E//Hannah | 2025-04-18 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231101 | DU00002860970 |  |  | 2025-10-23 | 2025-10-21 |  | Tower | 45m 4 Legged Tower | 48m | Add R8852E S9000x4+R9264M M1821x4, Dismantle R8882 S1800B(B6B)x3+R8862A S1800(B6A)x1+R8862A S2100(A6A)x4 | 0 | 0
4740B | TGBAYAN | Northern |  | Modernization |  | 154 single site MOCN | ZB | GTSB | 4.6 TSSR Approved |  | 2024-09-04 | 2024-09-06 |  | 2024-09-10 |  | Under Approval | 2024-09-10 | 2024-09-25 | E//Vijay | 2024-09-25 | 0809CD-Northern-GTSB-BOQ Template(new contract) | DU00002860971 |  |  | 2024-09-21 | 2024-09-16 |  | Tower | 60m 4 Legged Tower | 60M | Add R8862A S9000 x3+R8894E M1821 x1+R8854 S2600 x1,Dismantle R8860E-GU908 x3+R8862A S2600(A4A) x1 |  | 3
4741B | Sarang Tiong | Northern |  | Modernization |  | 2025 Q1 | SM | GCI | 4.6 TSSR Approved |  | 2025-01-09 | 2025-01-16 |  | 2025-02-06 |  | Rectificating | 2025-02-07 | 2025-02-19 | E//Hazida | 2025-02-19 | SQ202501030261 - GCI | DU00002860972 |  |  | 2025-02-22 | 2025-02-22 |  | Tower | Tower | 60m | Add R8894E M1821x3, Dismantle R8862A S1800(B6A)x3 | 0 | 0
4744B | Bagan Sg Burung | Northern |  | Modernization |  | 131 single site mocn | SHA | CCSMY | 4.6 TSSR Approved |  | 2024-08-28 | 2024-09-02 |  | 2024-09-07 |  | Under Approval | 2024-09-09 | 2024-09-25 | E//Ajay | 2024-09-25 | 0809CD-Northern-CCSMY-BOQ Template(new contract) | DU00002860973 |  |  | 2024-09-25 | 2024-09-25 |  | Tower | Tower | 53 | Add R8894E M1821 x2+R8854 S2600 x2,Dismantle | 0 | 12
9466A | Kg Kuap | Sarawak |  | Modernization |  | 2025 Q1 | AD | Magicell | 4.6 TSSR Approved |  | 2025-02-17 | 2025-02-26 |  | 2025-03-04 |  | Under Approval | 2025-03-07 | 2025-04-18 | E//Hannah | 2025-03-19 | SQ202502050300-Magicell | DU00002860974 | Remarks: Solution TSSR/BOM Changed |  | 2025-04-30 | 2025-04-10 |  |  | 45m 3 Legged Tower | 70 | Add R8852E S9000x2+R8894E M1821x1+R8854 S2600x1, Dismantle R8862A S1800(B6A)x3+R8862A S2600(A4A)x1 | 0 | 1
4750B | Sg Terap RCC | Northern |  | Modernization |  | 131 single site mocn | SHA | GCI | 4.6 TSSR Approved | ¦ 0822 - GCI: Need resurvey due to lack photo for additional sectore proposal | 2023-10-11 | 2023-11-03 |  | 2024-01-02 |  | Under Approval | 2024-08-29 | 2024-09-19 | E//Ajay | 2024-09-19 | Celcom Digi_RAN-GCI-TSS-Northern-20231013-0058 | DU00002860975 |  |  | 2024-08-28 | 2024-08-24 |  | Tower | Tower | 65 | Add R8852E S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882-GUL1812 x2+R8862A S2100(A6A) x2 | 0 | 3
9099A | Lambir (Celcom) | Sarawak |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | ZB | Magicell | 4.6 TSSR Approved |  | 2023-10-11 | 2023-10-16 |  | 2023-10-23 |  | Closed | 2023-10-25 | 2024-11-11 | E//Hannah | 2024-11-07 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231013 | DU00002860976 |  |  | 2024-11-06 | 2024-10-29 |  | Tower | Tower | 47M | Add A9732 M1821 x3, Dismantle R8894E M1821(A8A)x3 | 123 | 0
9100A | Sg Dalam | Sarawak |  | Modernization |  | 2025 Q1 | SM | Magicell | 4.6 TSSR Approved |  | 2023-10-09 | 2023-10-10 |  | 2023-10-13 |  | Closed | 2023-10-13 | 2023-10-27 | E//Hannah | 2025-02-28 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231009 | DU00002860977 |  | Remarks: Solution Changed | 2025-06-14 | 2025-04-05 |  | Tower | Tower | 46 | Add R8852E S9000x3+R8894E M1821x3+R8862A S2601x1, Dismantle R8882 S1800B(B6B)x2 | 0 | 0
4765B | BKTTEMBAGA | Northern |  | Modernization |  | 131 single site mocn | SHA | CCSMY | 4.6 TSSR Approved |  | 2024-09-03 | 2024-09-04 |  | 2024-09-07 |  | Under Approval | 2024-09-13 | 2024-09-24 | E//Ajay | 2024-09-24 | 0809CD-Northern-CCSMY-BOQ Template(new contract) | DU00002860978 |  |  | 2024-10-01 | 2024-10-01 |  | Tower | Tower | 55m | Add R8862A S9000 x1+R8862A S2601 x2+R8894E M1821 x1+A9732 M1821 x2,Dismantle R8862A S1800(B6A) x2+R8862A S2100(A6A) x2 | 23
4770B | Pdg Besar Town | Northern |  | Modernization |  | 2025 Q3 | BY | Magicell | 4.6 TSSR Approved |  | 2024-01-12 | 2024-01-18 |  | 2024-04-19 |  | Closed | 2024-04-22 | 2024-05-24 | E//Hazida | 2024-04-24 | Celcom Digi_RAN-Magicell-TSS-Northern-20240114-0010 | DU00002860979 |  |  | 2024-05-22 | 2024-04-24 |  | Monopole | 45m Monopole | 46 | Add R8852E S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882-GUL1812 x3+R8862A S2601(A6A) x1 | 0 | 3
4784B | Kg Ayer Hitam | Northern |  | Modernization |  | 131 single site mocn | ZB | GCI | 4.6 TSSR Approved |  | 2024-08-20 | 2024-08-25 |  | 2024-08-29 |  | Under Approval | 2024-09-02 | 2024-09-23 | E//Hazida | 2024-09-23 | 0809CD-Northern-GCI-BOQ Template(new contract) | DU00002860980 |  |  | 2024-09-18 | 2024-09-18 |  | Tower | Tower | 60 | Add R8852E S9000 x3+R8894E M1821 x5+R8854 S2600 x2,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3+R8862A S2601(A6A) x2 |  | 12
4852B | Kg Pdg Keria | Northern |  | Modernization |  | 2024 Q4 | BY | GCI | 4.6 TSSR Approved |  | 2023-11-15 | 2023-11-17 |  | 2024-04-22 |  | Closed | 2024-04-25 | 2024-04-26 |  | 2024-04-26 | Celcom Digi_RAN-GCI-TSS-Northern-20231122-0075 | DU00002860981 |  |  | 2024-05-14 | 2024-05-09 |  | Tower | Tower | 60 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3 | 0 | 0
4859B | Kuala Tekai (Celcom) | Northern |  | Modernization |  | 2025 Q3 | SM | GCI | 4.6 TSSR Approved |  | 2025-01-13 | 2025-01-27 |  | 2025-02-10 |  | Rectificating | 2025-03-13 | 2025-03-19 | E//Hazida | 2025-03-19 | SQ202501030261 - GCI | DU00002860982 |  |  | 2025-06-19 | 2025-06-09 |  | Tower | 45m 3 Legged Tower | 60m | Add R8894E M1821x2 | 0 | 13
4908B | Batu 2 Tapah (REL) | Northern |  | Modernization |  | 2024 Additional | SM | CCSMY | 4.6 TSSR Approved |  | 2023-11-19 | 2023-11-21 |  | 2024-11-22 |  | Rectificating | 2024-11-25 | 2024-12-16 | E//Hazida | 2024-12-16 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231122-0072//2111CD-Northern-TSS-BOQ Template(new contract)_CCSMY | DU00002860983 | Remarks: Solution TSSR/BOM Changed |  | 2024-12-05 | 2024-12-05 |  | Tower | Tower | 61 | Add R8852E S9000 x2 | 0 | 0
4909B | Air Kuning RCC | Northern |  | Modernization |  | 2024 Additional | SM | GTSB | 4.6 TSSR Approved |  | 2023-10-31 | 2023-11-02 |  | 2024-11-22 |  | Rectificating | 2024-11-25 | 2024-12-16 | E//Hazida | 2024-12-16 | Celcom Digi_RAN-GTSB-TSS-Northern-20231101-0060//2111CD-Northern-TSS-BOQ Template(new contract)_GTSB | DU00002860984 |  |  | 2024-12-12 | 2024-12-04 |  | Tower | 45m 3 Legged Tower | 75 | Add R8852E S9000 x3+R8894E M1821x4+R8854 S2600x1, Dismantle R8882-GUL1812x2+R8862A S1800(B6A)x1+R8854D S2100(A4A)x3+R8862A S2600(A4A)x1 | 0 | 3
4940B | Kg Iboi(Mxs) | Northern |  | Modernization |  | 131 single site mocn | SHA | YPTT | 4.6 TSSR Approved |  | 2023-12-21 | 2023-12-29 |  | 2024-08-21 |  | Under Approval | 2024-08-23 | 2024-09-04 | E//Ajay | 2024-09-04 | Celcom Digi_RAN-YPTT-TSS-Northern-20231225-0047 | DU00002860985 |  |  | 2024-08-28 | 2024-08-26 |  | Tower | 60m 3 Legged Tower | 60 | Add R8862A S2601 x2+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x2 | 23
4947B | Kg TokSenik | Northern |  | Modernization |  | 2025 Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2025-01-26 | 2025-02-12 |  | 2025-02-14 |  | Rectificating | 2025-02-19 | 2025-02-20 | E//Hazida | 2025-02-20 | SQ202501030229 - gtsb | DU00002860986 | Remarks: Solution TSSR/BOM Changed |  | 2025-03-21 | 2025-02-21 |  | Tower | Tower | 60m | Add R8852E S9000x1+R8894E M1821x3 | 0 | 14
4952B | Selama Kdh | Northern |  | Modernization |  | 154 single site MOCN | MS | GCI | 4.6 TSSR Approved |  | 2023-10-11 | 2023-11-01 |  | 2024-01-08 |  | Under Approval | 2024-08-23 | 2024-09-04 | E//Hazida | 2024-09-04 | Celcom Digi_RAN-GCI-TSS-Northern-20231013-0058 | DU00002860987 |  |  | 2024-08-31 | 2024-08-24 |  | Tower | Tower | 65 | Add R8894E M1821 x1+A9732 M1821 x2,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 12 | 0
4955B | Tawar | Northern |  | Modernization |  | 131 single site mocn | ZB | CCSMY | 4.6 TSSR Approved |  | 2023-10-31 | 2023-11-14 |  | 2024-08-15 |  | Under Approval | 2024-08-23 | 2024-09-04 | E//Hazida | 2024-09-03 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231031-0064 | DU00002860988 |  |  | 2024-09-04 | 2024-08-26 |  | Tower | Tower | 71M | Add R8852E S9000 x3+R8862A S2601 x3+A9732 M1821 x3,Dismantle R8860E-GU908 x3+R8862A S1800(B6A) x4+R8862A S2100(A6A) x3 | 123 | 0
4956B | Kuala Pegang | Northern |  | Modernization |  | 131 single site mocn | SH | YPTT | 4.6 TSSR Approved |  | 2023-12-22 | 2024-01-03 |  | 2024-08-19 |  | Under Approval | 2024-08-29 | 2024-09-03 | E//Hazida | 2024-08-30 | Celcom Digi_RAN-YPTT-TSS-Northern-20231225-0047 | DU00002860989 |  |  | 2024-10-24 | 2024-08-27 |  | Tower | Tower | 60 | Add A9732 M1821 x3,Dismantle R8862A S1800(B6A) x4 | 123
4974B | Pdg Durian | Northern |  | Modernization |  | 131 single site mocn | SM | GCI | 4.6 TSSR Approved |  | 2024-08-17 | 2024-08-25 |  | 2024-08-28 |  | Rectificating | 2024-08-29 | 2024-09-23 | E//Hazida | 2024-09-22 | 0809CD-Northern-GCI-BOQ Template(new contract) | DU00002860990 |  |  | 2024-11-16 | 2024-09-05 |  | Tower | Tower | 60 | Add R8862A S2601 x2+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x2 | 23 | 0
4976B | Paya Mat Isun | Northern |  | Modernization |  | 2025 Q2 | HW | GTSB | 4.6 TSSR Approved |  | 2025-02-21 | 2025-03-04 |  | 2025-03-21 |  | Under Approval | 2025-04-08 | 2025-05-19 | E//Hazida | 2025-04-23 | SQ202501030229 - gtsb | DU00002860991 |  |  | 2025-06-28 | 2025-05-31 |  | Tower | Tower | 60M | Add A9732 M1821x1, Dismantle R8894E M1821(A8A)x1 | 1 | 0
4979B | Naka | Northern |  | Modernization |  | 2024 Q3(single site MOCN) | BY | GCI | 4.6 TSSR Approved |  | 2024-05-14 | 2024-05-14 |  | 2024-06-05 |  | Closed | 2024-06-12 | 2024-06-13 |  | 2024-06-12 | Celcom Digi_RAN-GCI-TSS-Northern-20240519-0107 | DU00002860992 |  |  | 2024-06-30 | 2024-06-22 |  | Tower | Tower | 80M | Add A9732 M1821 x3,Dismantle R8862A S1800(B6A) x3 | 123 | 0
4985B | Jln Jeniang | Northern |  | Modernization |  | 131 single site mocn | SHA | GTSB | 4.6 TSSR Approved |  | 2024-09-06 | 2024-08-20 |  | 2024-09-09 |  | Under Approval | 2024-09-10 | 2024-09-25 | E//Ajay | 2024-09-25 | 0809CD-Northern-GTSB-BOQ Template(new contract) | DU00002860993 |  |  | 2024-09-21 | 2024-09-16 |  | Tower | Tower | 60M | Add R8862A S2601 x3+A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
4992B | Bdr Baharu Town RCC | Northern |  | Modernization |  | 154 single site MOCN | ZB | GTSB | 4.6 TSSR Approved |  | 2023-12-22 | 2023-12-26 |  | 2024-08-15 |  | Under Approval | 2024-08-26 | 2024-09-13 | E//Hazida | 2024-09-13 | Celcom Digi_RAN-GTSB-TSS-Northern-20231225-0080 | DU00002860994 |  | 2308_Wrong RRU location S2600 | 2024-09-13 | 2024-08-24 |  | Tower | 45m 4 Legged Tower | 45M | Add R8852E S9000 x3+A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123 | 0
9156A | Mukah(SACOFA) | Sarawak |  | Modernization |  | 2025 Q2 | AI | Magicell | 4.6 TSSR Approved |  | 2023-10-06 | 2023-10-13 |  | 2023-10-20 |  | Closed | 2023-10-26 | 2023-11-14 | E//Hannah | 2025-10-06 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231009 | DU00002860995 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed | 2025-04-04 | 2025-03-15 |  | Monopole | Tower | 76m | Add R8852E S9000x3+R8894E M1821x2, Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3+R8862A S2600(A4A)x2 | 0 | 1
9165A | Siburan 2 | Sarawak |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | SHA | Datasco | 4.6 TSSR Approved |  | 2023-10-24 | 2023-11-29 |  | 2024-04-18 |  | Under Approval | 2024-10-26 | 2024-10-30 | E//Syahriani | 2024-10-30 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231214 | DU00002860996 |  |  | 2024-12-16 | 2024-11-26 |  | Tower | Tower | 100 | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x1+R8894E M1821(A8A) x4 | 123 | 0
1181C | Jalan Bukit Angkasa | Central |  | Modernization |  | 2024 Q2 | AI | AllStar | 4.6 TSSR Approved | 29/01 RRU install inside cabinet, 3 RRU on top,have temperature alarm according to technical team | 2023-12-07 | 2023-12-19 |  | 2024-03-07 |  | Closed | 2024-03-07 | 2024-03-08 | E//Kok Keen | 2024-03-08 | CelcomDigi_RAN_Allstar_TSS_Central_20231208 | DU00002860997 |  |  | 2024-04-30 | 2024-04-30 |  | Lampole | 18m Lampole | 18 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3 | 0 | 0
9200B | Sebuyau (Sacofa) | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 | MNO | Magicell | 4.6 TSSR Approved |  | 2025-07-16 |  | 2025-07-03 |  | 2025-07-16 | To be Submitted | 2025-07-17 |  | E//John | 2025-07-18 | SQ202507250423-Magicell | DU00002860998 |  |  |  |  | 2025-11-13 |  | 60m 4 Legged Tower
9201B | Kota Samarahan 2 MP | Sarawak |  | Modernization |  | 2024 Q2 | ZB | Datasco | 4.6 TSSR Approved |  | 2023-10-06 | 2023-10-11 |  | 2023-10-23 |  | Rectificating | 2024-03-12 | 2024-03-13 | E//Hannah | 2024-03-13 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231016 | DU00002860999 |  | 2612 RF approved with comment Please change sector 3 to 350 degree as currently the sector is point 350 deg. -Done Revised | 2024-04-06 | 2024-04-04 |  | Tower | Tower | 45 | Add R8862A S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882-GUL1812 x3+R8862A S2600(A4A) x1 | 0 | 2
9204B | TM Jalan Muara Tuang | Sarawak |  | Modernization |  | 2024 Q2 | AD | Datasco | 4.6 TSSR Approved |  | 2024-04-01 | 2024-04-04 |  | 2024-04-06 |  | Closed | 2024-04-17 | 2024-04-25 | E//Hannah | 2025-03-17 | Celcom Digi_RAN-Datasco-Standard PR TSS-Sabah-20240406 | DU00002861000 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed | 2025-06-28 | 2025-06-06 |  | Tower | Tower | 60 | Add R8862A S9000x3+R8894E M1821x3, Dismantle R8882-GUL1812x3+R8840-U216x3 | 0 | 0
9457B | Dewan Unimas | Sarawak |  | Modernization |  | 2024 Q2 | SH | AllStar | 4.6 TSSR Approved |  | 2023-10-13 | 2023-10-25 |  | 2023-11-03 |  | Closed | 2024-03-07 | 2024-04-02 | E//Hannah | 2024-04-02 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20231016 | DU00002861001 |  |  | 2024-05-06 | 2024-05-03 |  | Monopole | 30M Rapole | 30 | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3 | 0 | 0
9284A | Bukit Mas | Sarawak |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | SHA | Datasco | 4.6 TSSR Approved |  | 2024-02-05 | 2024-04-24 |  | 2024-10-21 |  | Under Approval | 2024-10-26 | 2024-10-30 | E//Syahriani | 2024-10-30 | Celcom Digi_RAN-Datasco-Standard PR TSS-Sarawak-20240213 | DU00002861002 |  |  | 2025-07-06 | 2025-03-07 |  | Tower | Tower | 106 | Add R8862A S9000 x4+A9732 M1821 x2,Dismantle R8881 S9000 x2+R8882 S1800B(B6B) x2+R8854D S2100(A4A) x2 | 13 | 0
9288A | Tedungan(SACOFA) | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | AD | DATASCO | 4.6 TSSR Approved | TX Bulk approval | 2025-05-27 |  | 2025-05-28 |  | 2025-06-06 |  | 2025-06-12 | 2026-01-15 | E//John | 2025-06-13 | SQ202502050346-Datasco | DU00002861003 |  |  |  |  | 2025-11-17 |  | Tower
4161C | USP_ Ulu Melaka | Northern |  | Modernization |  | 131 single site mocn | SHA | GTSB | 4.6 TSSR Approved |  | 2024-08-29 | 2024-09-12 |  | 2024-09-11 |  | Under Approval | 2024-09-19 | 2024-09-23 | E//Ajay | 2024-09-23 | 0809CD-Northern-GTSB-BOQ Template(new contract) | DU00002861004 |  |  | 2024-10-13 | 2024-10-09 |  | Tower | 30m Monopole | 60M | Add R8862A S2601 x1+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x1 | 1
1233C | Pandan Jaya | Central |  | Modernization |  | 2024 Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-12-22 | 2023-12-28 |  | 2024-01-18 |  | Closed | 2024-01-22 | 2024-01-29 | E//Sumitra | 2024-01-26 | CelcomDigi_RAN_GTSB_TSS_Central_20231224 | DU00002861005 |  |  | 2024-08-08 | 2024-08-03 |  | Lampole | 30m Lampole | 30m | Add R8862A S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R8862A S2601(A6A) x2+R8894E M1821(A8A) x2 | 3
3911B | Jalan Gombak | Central |  | Modernization |  | 2024 Q1 | CR | DATASCO | 4.6 TSSR Approved | 21/02/24 - change RRU solution to UBRH, 06/02/24 - Email to SA regarding SO Cabinet and RRU Location | 2024-01-25 | 2024-01-29 |  | 2024-02-05 |  | Closed | 2024-02-21 | 2024-04-05 | E//Kok Keen | 2024-04-05 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240128 | DU00002861006 |  |  | 2024-05-21 | 2024-05-18 |  | Lampole | 24m Lampole | 19m | Add R9264H x 3+R8854 S2600 x1,DismantleR8862A S9000(A6A) x3+R8862A S2600(A4A) x1+R8894E M1821(A8A) x3 |  | 3
9342A | Institut Latihan Perindustrian | Sarawak |  | Modernization |  | 2024 Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-10-23 | 2023-10-27 |  | 2024-01-09 |  | Closed | 2024-03-05 | 2024-03-15 | E//Hannah | 2024-03-14 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231019 | DU00002861007 |  |  | 2024-03-07 | 2024-03-02 |  | Tower | Tower | 61m | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8882-GUL1812 x3 | 3 | 0
9353A | Song | Sarawak |  | Modernization |  | 2025 Q3 | SH | AllStar | 4.6 TSSR Approved |  | 2023-11-04 | 2023-11-20 |  | 2024-04-16 |  | Closed | 2024-04-18 | 2024-04-25 | E//Hannah | 2024-04-25 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20231214 | DU00002861008 |  |  | 2025-04-04 | 2025-03-11 |  | Tower | Tower | 106 | Add A9732 M1821 x2,Dismantle R8894E M1821(A8A) x2 | 12 | 0
9354A | Kanowit | Sarawak |  | Modernization |  | 2025 Q3 | AD | Trintel | 4.6 TSSR Approved |  | 2025-04-02 | 2025-04-15 |  | 2025-04-23 |  | Under Approval | 2025-04-24 | 2025-05-21 | E//Hannah | 2025-05-08 | SQ202503030411-Trintel | DU00002861009 |  |  | 2025-07-06 | 2025-05-29 |  | Tower | 60m 4 Legged Tower | 121 | Add R9264M M1821x2+A9732 M1821x1, Dismantle R8894E M1821(A8A)x3 | 1 | 3
9360A | Selangau(SACOFA) | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | AD | Trintel | 4.6 TSSR Approved |  | 2025-05-16 |  | 2025-05-30 |  | 2025-06-16 |  | 2025-06-16 | 2026-01-07 | E//John | 2025-06-17 | SQ202505020084-Trintel | DU00002861010 |  |  |  |  | 2025-11-25 |  | Tower
9229B | Sacofa Jangkar | Sarawak |  | Modernization |  | 2024 Q2 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-10-21 | 2023-10-24 |  | 2023-11-07 |  | Closed | 2024-01-08 | 2024-01-18 | E//Hannah | 2024-01-18 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231214 | DU00002861011 |  |  | 2024-02-21 | 2024-01-20 |  | Tower | 45m 3 Legged Tower | 76m | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882 S1800B(B6B) x3
9371A | Limbang Airport (SACOFA) | Sarawak |  | Modernization |  | 2025 Q2 | AD | Datasco | 4.6 TSSR Approved |  | 2024-02-26 | 2025-03-25 |  | 2025-04-14 |  | Under Approval | 2025-04-17 | 2025-05-21 | E//Hannah | 2025-05-07 | Celcom Digi_RAN-Datasco-Standard PR TSS-Sarawak-20240302 | DU00002861012 |  |  | 2025-06-30 | 2025-06-14 |  | Tower | 45m 3 Legged Tower | 30 | Add R8852E S9000x3+A9732 M1821x1+R9264M M1821x2, Dismantle R8894E M1821(A8A)x3 | 3 | 0
9382A | Kapit (SACOFA) | Sarawak |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | SHA | Magicell | 4.6 TSSR Approved |  | 2024-10-25 | 2024-11-08 |  | 2024-11-12 |  | Under Approval | 2024-11-12 | 2024-11-14 | E//Syahriani | 2025-03-06 | Celcom Digi_RAN-Magicell-Standard PR TSS-Sarawak-20240503 | DU00002861013 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed | 2025-07-06 | 2025-06-24 |  | Tower | 60m 4 Legged Tower | 120 | Add R8862A S9000x4+A9732 M1821x1+R8894E M1821x4, Dismantle R8860E-GU908x3+R8882-GUL1812x3+R8862A S1800(B6A)x3+R8862A S2100(A6A)x3+R8862A S2600(A4A)x1 | 1 | 4
7708B | Kg Nilasan | Sabah |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q3 | AD | NR services | 4.6 TSSR Approved |  | 2025-01-14 | 2025-02-10 |  | 2025-02-23 |  | Under Approval | 2025-03-03 | 2025-07-16 | E//Hannah | 2025-03-16 | SQ202501020451 - NR Service | DU00002861014 | [5 empty] | Tower | 45m 3 Legged Tower | 76 | Add R8862A S2601x3 | 0 | 0
7025A | BCCM Kundasang | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2025 Q3 | AD | NR services | 4.6 TSSR Approved |  | 2025-03-12 |  | 2025-03-05 |  | 2025-04-09 |  | 2025-04-30 | 2025-09-10 | E//Hannah | 2025-07-14 | SQ202504100592 - NR Service | DU00002861015 |  |  |  |  | 2025-06-20 |  | Tower
7073A | Wisma Wong Wo Lo | Sabah |  | Modernization |  | 2025 Q1 | AD | Datasco | 4.6 TSSR Approved |  | 2024-05-23 | 2024-06-07 |  | 2025-01-10 |  | Under Approval | 2025-01-17 | 2025-02-18 | E//Yanie | 2025-01-31 | 0920CD-Sabah-Datasco-BOQ Template (old contract) | DU00002861016 |  |  | 2025-02-17 | 2025-02-10 |  | In-Building System | 3m Boom (RT) | 6m | Add R9264M M1821x4, Dismantle R8882-GUL1812x3+R8894E M1821(A8A)x4 | 0 | 0
7135A | Grand View | Sabah |  | Modernization |  | 2024 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2024-03-25 | 2024-04-05 |  | 2024-04-22 |  | Closed | 2024-04-24 | 2024-06-12 | E//Hannah | 2024-06-11 | Celcom Digi_RAN-GTSB-TSS-Sabah-20240329 | DU00002861017 |  |  | 2024-06-15 | 2024-06-08 |  | Minimast | 3m RT (Minimast) | 13 | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle R8862A S2600(A4A) x1 | 0 | 2
7137A | Taman Indah Jaya | Sabah |  | Modernization |  | 2024 Q3 | AD | Datasco | 4.6 TSSR Approved |  | 2024-04-01 | 2024-05-03 |  | 2024-05-07 |  | Closed | 2024-06-05 | 2024-07-09 | E//Hannah | 2024-07-09 | Celcom Digi_RAN-Datasco-Standard PR TSS-Sabah-20240406 | DU00002861018 |  |  | 2024-07-22 | 2024-07-02 |  | In-Building System | 3m RT (Minimast) | 9M | Add R8862A S9000 x1+R9224E M1821 x5+R8862A S2601 x3+R8854 S2600 x1,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8882 S2600(B4A) x3+R8862A S2600(A4A) x1+R8862A S2100 x1 | 0 | 2
7141A | Taman Tshun Ngen | Sabah |  | Modernization |  | 2024 Q3 | AD | Datasco | 4.6 TSSR Approved |  | 2024-04-21 | 2024-04-26 |  | 2024-05-02 |  | Closed | 2024-05-03 | 2024-05-13 | E//Hannah | 2024-05-13 | Celcom Digi_RAN-Datasco-Standard PR TSS-Sabah-20240503 | DU00002861019 |  |  | 2024-07-05 | 2024-07-02 |  |  | 45m 4 Legged Tower | 6 | Add R9224E M1821 x3,Dismantle R8882-GUL1812 x3 | 0 | 0
7214A | Tunggol Tinggi | Sabah |  | Modernization |  | 2025 Q2 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2023-10-30 | 2023-11-08 |  | 2025-01-15 |  | Under Approval | 2025-01-17 | 2025-03-09 | E//Yanie | 2025-01-20 | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231101 | DU00002861020 |  |  | 2025-03-17 | 2025-03-13 |  | Tower | 106m 4 Legged Tower | 110M | Reuse Existing RRU | 0 | 0
9401B | Mukah NTS MP | Sarawak |  | Modernization |  | 2024 Q4(single site MOCN)-L21 SSM | ZB | Magicell | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦TP reject due to tower overstressed. only swap is allowed. | 2023-10-05 | 2023-10-16 |  | 2024-04-03 |  | Closed | 2024-04-04 | 2024-10-24 | E//Hannah | 2024-10-24 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231006 | DU00002861021 |  | 2612 Pending RRU Solution 3010 TP was rejected by Sacofa | 2024-11-16 | 2024-11-06 |  | Monopole | 30m Monopole | 30 | Add R8852E S9000 x1+R8894E M1821 x5,Dismantle R8862A S1800(B6A) x1+R8862A S2100(A6A) x1 | 0 | 1234
7218A | Tampalagus(Celcom) | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | AI | Datasco | 4.6 TSSR Approved |  | 2025-03-19 |  | 2025-04-24 |  | 2025-06-26 | To be Submitted | 2025-07-08 |  | E//Hannah | 2025-07-14 | SQ202504100595 - Datasco | DU00002861022 |  |  |  |  | 2025-09-04 |  | 76m 4 Legged Tower
7324A | Mile 8 Kg Taviu | Sabah |  | Modernization |  | 2024 Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2024-04-08 | 2024-04-20 |  | 2024-05-10 |  | Under Approval | 2024-05-14 | 2024-06-21 | E//Hannah | 2024-06-21 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240420 | DU00002861023 |  |  | 2024-07-16 | 2024-07-12 |  | Tower | Tower | 75m | R8894E M1821(A8A) x2+R8854 S2600 x2 |  | 23
7333A | Sabah Tea | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2025 Q3 | HW | NR services | 4.6 TSSR Approved |  | 2025-02-11 |  | 2025-02-18 |  | 2025-02-23 | To be Submitted | 2025-02-24 |  | E//Hannah | 2025-02-26 | SQ202504100592 - NR Service | DU00002861024 |  |  |  |  | 2025-07-22 |  | Tower
7348A | Kg.Tungou Ranau | Sabah |  | Decomm, MOCN By Other Vendor | Decomm->On Hold->Decomm->On Hold->Decomm | 2025 | AD | Datasco | 4.6 TSSR Approved |  | 2025-05-20 |  | 2025-05-19 |  | 2025-05-22 |  | 2025-05-23 | 2025-10-31 | E//Faiz | 2025-10-27 | SQ202504100595 - Datasco | DU00002861025 |  |  |  |  | 2025-11-29 |  | Tower
7364B | Kampung Katagadan SBC | Sabah |  | Modernization |  | 2024 Q3(single site MOCN) | AD | GTSB | 4.6 TSSR Approved |  | 2023-11-06 | 2023-11-09 |  | 2024-06-21 |  | Under Approval | 2024-07-01 | 2024-07-30 | E//Hannah | 2024-07-29 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231107 | DU00002861026 |  |  | 2024-08-19 | 2024-08-10 |  | Tower | Tower | 60 | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle | 0 | 2
7366B | Jalan Segama | Sabah |  | Modernization |  | 2024 Q3 | MS | GTSB | 4.6 TSSR Approved |  | 2023-10-23 | 2023-10-24 |  | 2023-10-26 |  | Rectificating | 2024-04-19 | 2024-06-12 | E//Hannah | 2024-06-11 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231024 | DU00002861027 |  |  | 2024-06-18 | 2024-06-04 |  | Tower | Tower | 60 | Add R8894E M1821 x1 | 0 | 13
7370A | Bandau | Sabah |  | Remote MOCN | Modernization->On Hold->Remote MOCN | 2025 Q2 |  | Seri Pancar | 14.2 Drop (Done Survey) |  | 2023-10-31 | 2023-11-22 |  | 2025-03-20 |  | Under Approval |  |  |  |  | Celcom Digi_RAN-Seri Pancar-Standard PR TSS-Sabah-20240116 | DU00002861028 | [5 empty] | Tower | Tower | 60M | Reuse Existing RRU | 0 | 0
9544A | Rumah Datu Anduh | Sarawak |  | Modernization |  | 2025 Q3 | AI | Datasco | 4.6 TSSR Approved |  | 2024-01-10 | 2024-03-27 |  | 2025-02-27 |  | Closed | 2025-02-28 | 2025-04-21 | E//Hannah | 2025-03-20 | Celcom Digi_RAN-Datasco-Standard PR TSS-Sarawak-20240116 | DU00002861029 |  |  | 2025-07-06 | 2025-04-05 |  | Tower | Tower | 76 | Add R8894E M1821x1 | 0 | 3
9422A | Kpg Daun | Sarawak |  | Modernization |  | 2024 Q2 | SH | Datasco | 4.6 TSSR Approved |  | 2023-10-19 | 2023-12-06 |  | 2024-01-08 |  | Closed | 2024-01-17 | 2024-01-19 | E//Hannah | 2024-01-19 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231020 | DU00002861030 |  |  | 2024-04-13 | 2024-04-01 |  | Tower | 45m 3 Legged Tower | 76 | Reuse existing RRU
7392A | Jln Kudat-K.Marudu | Sabah |  | Modernization |  | 2025 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2023-11-01 | 2023-11-21 |  | 2025-02-18 |  | Under Approval | 2025-02-24 | 2025-03-09 | E//Hannah | 2025-02-26 | Celcom Digi_RAN-YPTT-Standard PR TSS-Sabah-20240813 | DU00002861031 |  |  | 2025-03-27 | 2025-03-26 |  | Tower | 60m 3 Legged Tower | 60 | Add R8894E M1821x3, Dismantle R8882 S1800B(B6B)x3+R8854D S2100(A4A)x3 | 0 | 0
7396A | Bkt. Karakit | Sabah |  | Modernization |  | 2025 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2023-11-14 | 2023-12-22 |  | 2025-02-19 |  | Under Approval | 2025-02-24 | 2025-03-09 | E//Hannah | 2025-02-26 | Celcom Digi_RAN-YPTT-Standard PR TSS-Sabah-20240813 | DU00002861032 |  |  | 2025-09-30 | 2025-09-24 |  | Tower | Tower | 76m | Add R9264M M1821x1+A9732 M1821x2, Dismantle R8862A S1800(B6A)x3+R8854D S2100(A4A)x3 | 23 | 0
7409A | Kg Kelawat | Sabah |  | Modernization |  | 2025 Q3 | AD | Futong | 4.6 TSSR Approved |  | 2023-10-25 | 2023-10-27 |  | 2023-11-01 |  | Closed | 2024-01-31 | 2025-05-21 | E//Hannah | 2025-03-19 | Celcom Digi_RAN-Futong-TSS-Sabah-20231028 | DU00002861033 |  |  | 2025-04-04 | 2025-03-15 |  | Tower | Tower | 76 | Add R8894E M1821x3, Dismantle R8862A S1800(B6A)x3 | 0 | 0
7426B | Syarimol | Sabah |  | Modernization |  | 2024 Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-11-10 | 2023-11-22 |  | 2024-07-16 |  | Under Approval | 2024-07-17 | 2024-07-22 | E//Hannah | 2024-07-19 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231112 | DU00002861034 |  |  | 2024-08-31 | 2024-08-12 |  | Tower | 76m 3 Legged Tower | 76m | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle | 0 | 1
7365B | CBRICHARDLIND | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2024 Q3(single site MOCN) | AD | GTSB | 4.6 TSSR Approved |  | 2023-11-20 | 2023-11-24 |  | 2024-05-30 |  | Under Approval | 2024-10-14 | 2024-10-23 | E//Hannah | 2024-10-23 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231126 | DU00002861035 |  |  | 2024-11-15 | 2024-11-15 |  | Tower | 76m 3 Legged Tower | 60 | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle |  | 3
7438B | Mile 75 SBC | Sabah |  | Modernization |  | 2024 Q3(single site MOCN) | SHA | GTSB | 4.6 TSSR Approved |  | 2024-04-08 | 2024-04-25 |  | 2024-06-26 |  | Under Approval | 2024-07-05 | 2024-07-12 | E//Hannah | 2024-07-12 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240420 | DU00002861036 |  |  | 2024-08-23 | 2024-07-29 |  | Tower | Tower | 60m | Add R9224E M1821 x4+R8854 S2600 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2600(A4A) x1++R8881 S2100 x3+ | 0 | 1
7446B | Mile 14 Batu Sapi | Sabah |  | Modernization |  | 2024 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2024-03-15 | 2024-04-20 |  | 2024-04-25 |  | Closed | 2024-04-30 | 2024-05-16 | E//Hannah | 2024-05-15 | Celcom Digi_RAN-YPTT-TSS-Sabah-20240324 | DU00002861037 |  |  | 2024-06-18 | 2024-06-13 |  | Tower | Tower | 60 | Add R8862A S9000 x3+R9224E M1821 x3,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x2+R8862A S2100(A6A) x3 | 0 | 0
7452B | Tmn Megah SBC | Sabah |  | Modernization |  | 2024 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2024-03-19 | 2024-03-21 |  | 2024-04-05 |  | Closed | 2024-04-16 | 2024-06-10 | E//Hannah | 2024-06-10 | Celcom Digi_RAN-GTSB-TSS-Sabah-20240324 | DU00002861038 |  |  | 2024-06-21 | 2024-06-07 |  | Monople Tree | 45m 3 Legged Tower | 45m | Add R8862A S9000 x3+R9224E M1821 x4+R8862A S2601 x1,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 0 | 1
7458B | Tmn Sunny Estate SBC | Sabah |  | Modernization |  | 2024 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2024-03-11 | 2024-03-20 |  | 2024-04-05 |  | Closed | 2024-04-15 | 2024-04-18 | E//Hannah | 2024-04-18 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240313 | DU00002861039 |  |  | 2024-07-02 | 2024-06-18 |  | Tower | 76m Tower | 60m | Add R8862A S9000 x3+R9224E M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3 | 0 | 0
7495A | SMT Labuan Maxis | Sabah |  | Modernization |  | 2025 Q1 | AI | Datasco | 4.6 TSSR Approved |  | 2024-05-28 | 2024-06-07 |  | 2025-01-11 |  | Closed | 2025-01-24 | 2025-04-22 | E//Hannah | 2025-04-22 | 0920CD-Sabah-Datasco-BOQ Template (old contract) | DU00002861040 | Remarks: Solution TSSR/BOM Changed |  | 2025-06-14 | 2025-05-23 |  | Tower | 60m 3 Legged Tower | 60m | Add R8852E S9000x3+A9732 M1821x1, Dismantle R8854 S2600(A4A)x1+R8894E M1821(A8A)x1+R9224E M1821(AAB)x1 | 2 | 13
3230A | Kg Baru Ampang | Central |  | Modernization |  | 2024 Q2 | SS | YPTT | 4.6 TSSR Approved |  | 2023-10-30 | 2023-11-09 |  | 2024-01-09 |  | Closed | 2024-01-10 | 2024-01-17 | E//Sumitra | 2024-01-16 | CelcomDigi_RAN_YPTT_TSS_Central_20231101 | DU00002861041 |  |  | 2024-04-17 | 2024-04-15 |  | H-bracket pole | 3m Boom (RT) | 7 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
7569A | Mile 32 Checkpoint Sandakan | Sabah |  | Modernization |  | 2024 Q4 | SH | NR services | 4.6 TSSR Approved |  | 2024-07-22 | 2024-08-05 |  | 2024-08-08 |  | Under Approval | 2024-08-13 | 2024-08-16 | E//Syahriani | 2024-08-16 | 0725Sabah-NR-BOQ Template(new contract) | DU00002861042 |  |  | 2024-09-13 | 2024-09-07 |  | Monople Tree | 30m Monopole | 45 | Add R8862A S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3+R8862A S2600(A4A) x1 | 0 | 1
7499A | Hotel Victoria | Sabah |  | Modernization |  | 2025 Q1 | AD | Datasco | 4.6 TSSR Approved |  | 2024-05-28 | 2024-06-28 |  | 2025-01-15 |  | Under Approval | 2025-01-17 | 2025-03-09 | E//Yanie | 2025-01-20 | 0920CD-Sabah-Datasco-BOQ Template (old contract) | DU00002861043 |  |  | 2025-02-12 | 2025-02-07 |  | In-Building System | 4m RT (Wall Mounted Pole) | 4m | Add R8852E S9000x3+R9264M M1821x3, Dismantle R8882-GUL1812x3+R8882 S1800B(B6B)x3+R8862A S2100(A6A)x4 | 0 | 0
3534B | Prima Setapak | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q1 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002861044 | [6 empty] | 3m RT (Wall Mounted Pole) |  |  |  | 123
7503A | Embara Budi | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-03-15 |  | 2025-03-20 |  | 2025-03-27 | To be Submitted | 2025-04-25 | 2026-04-01 | E//Hannah | 2025-07-14 | SQ202503270530 - Futong | DU00002861045 |  |  |  |  | 2025-10-27 |  | 76m 3 Legged Tower
7509A | CBNANGOH | Sabah |  | Modernization |  | 131 single site mocn | AD | GTSB | 4.6 TSSR Approved |  | 2024-04-30 | 2024-05-06 |  | 2024-05-13 |  | Closed | 2024-05-15 | 2024-05-27 | E//Hannah | 2024-05-27 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240503 | DU00002861046 |  |  | 2024-06-27 | 2024-06-15 |  | Tower | 76m 4 Legged Tower | 75 | Add R8862A S2601 x1+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x1 | 3 | 0
7512A | Morisem | Sabah |  | Modernization |  | 2024 Q3(single site MOCN) | MS | GTSB | 4.6 TSSR Approved |  | 2023-11-20 | 2023-11-23 |  | 2024-05-30 |  | Under Approval | 2024-06-13 | 2024-06-20 | E//Hannah | 2024-06-20 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231126 | DU00002861047 |  |  | 2024-10-08 | 2024-10-03 |  |  | 76m 3 Legged Tower | 75 | Add R8894E M1821 x2,Dismantle | 0 | 23
7428B | Batu Tulog | Sabah |  | Modernization |  | 2024 Q4 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2024-07-22 | 2024-08-15 |  | 2024-08-26 |  | Under Approval | 2024-09-30 | 2024-09-30 | E//Hannah | 2024-09-30 | 0725Sabah-Seri Pancar-BOQ Template(new contract) | DU00002861048 |  |  | 2024-09-25 | 2024-09-14 |  | Tower | Tower | 60 | Add R8852E S9000 x1+R8894E M1821 x3+R8862A S2601x1,Dismantle R8862A S1800(B6A) x2 | 0 | 0
7570A | Kg. Garinono | Sabah |  | Modernization |  | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2024-04-24 | 2024-04-29 |  | 2024-05-10 |  | Closed | 2024-06-05 | 2024-06-12 | E//Hannah | 2024-06-11 | Celcom Digi_RAN-Futong-Standard PR TSS-Sabah-20240503 | DU00002861049 |  |  | 2024-06-25 | 2024-06-04 |  | Tower | 76m Tower | 76 | Add R8894E M1821 x5+R8854 S2600 x2,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 23
7581A | Kg Paris 2 | Sabah |  | Modernization |  | 2024 Q3(single site MOCN) | AD | GTSB | 4.6 TSSR Approved |  | 2023-11-15 | 2023-11-22 |  | 2024-05-30 |  | Under Approval | 2024-06-25 | 2024-07-04 | E//Hannah | 2024-07-04 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231119 | DU00002861050 |  |  | 2024-07-22 | 2024-07-15 |  | Tower | Tower | 60m | Add R9224E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 | 0 | 0
7568A | Bukit Sentosa Jaya | Sabah |  | Modernization |  | 2024 Q4 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2024-07-23 | 2024-07-26 |  | 2024-08-02 |  | Under Approval | 2024-08-05 | 2024-08-09 | E//Hannah | 2024-08-08 | 0725Sabah-Seri Pancar-BOQ Template(new contract) | DU00002861051 |  |  | 2024-08-30 | 2024-08-23 |  | Tower | Tower | 60 | Add R8862A S9000 x1+R8894E M1821 x3+R8862A S2601 x1,Dismantle R8862A S1800(B6A) x2 | 0 | 0
7584A | Kg Segaliud | Sabah |  | Modernization |  | 2024 Q4(single site MOCN)-L2126 SSM | MS | NR services | 4.6 TSSR Approved |  | 2024-07-22 | 2024-08-05 |  | 2024-08-10 |  | Closed | 2024-10-02 | 2024-08-30 | E//Hannah | 2024-08-30 | 0725Sabah-NR-BOQ Template(new contract) | DU00002861052 |  |  | 2024-11-06 | 2024-11-06 |  | Tower | Tower | 76 | Add R8852E S9000x1+R8894E M1821x5+R8854 S2600x1,Dismantle R8862A S1800(B6A) x3 | 0 | 1
7948A | Langkon K.Marudu SBC | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2025 Q3 | HW | NR services | 4.6 TSSR Approved |  | 2025-02-04 |  | 2025-02-24 |  | 2025-03-10 |  | 2025-03-11 | 2026-02-03 | CD//Hannah | 2026-03-31 | SQ202504100592 - NR Service | DU00002861053 |  |  |  |  | 2025-08-25 |  | Tower
7980B | Pekan Nabalu | Sabah |  | Modernization |  | 2025 Q3 | AD | Futong | 4.6 TSSR Approved |  | 2023-11-09 | 2023-11-10 |  | 2025-02-14 |  | Under Approval | 2025-02-24 | 2025-03-28 | E//Hannah | 2025-03-10 | Celcom Digi_RAN-Futong-TSS-Sabah-20231112 | DU00002861054 |  |  | 2025-03-27 | 2025-03-25 |  | Tower | Tower | 65 | Add R8894E M1821x3, Dismantle R8862A S1800(B6A)x3+R8854D S2100(A4A)x3 | 0 | 0
4646B | Teluk Ewa(Clm) | Northern |  | Modernization |  | 154 single site MOCN | SM | GTSB | 4.6 TSSR Approved |  | 2024-09-06 | 2024-09-06 |  | 2024-09-13 |  | Rectificating | 2024-09-13 | 2024-09-20 | E//Hazida | 2024-09-20 | 0809CD-Northern-GTSB-BOQ Template(new contract) | DU00002861055 |  |  | 2024-10-26 | 2024-10-05 |  | Tower | 50m 3 Legged Tower | 50M | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle | 0 | 2
9490A | Kg Serosat | Sarawak |  | Modernization |  | 2024 Q2 | SH | Datasco | 4.6 TSSR Approved |  | 2023-10-19 | 2023-11-02 |  | 2024-01-09 |  | Closed | 2024-01-17 | 2024-01-19 | E//Hannah | 2024-01-19 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231020 | DU00002861056 |  |  | 2024-04-21 | 2024-04-01 |  | Tower | 45m 3 Legged Tower | 75 | Add R8852E S9000 x3+R8894E M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1++R8881 S2100 x3+
9522A | Tukau | Sarawak |  | Modernization |  | 2025 Q1 | SH | Trintel | 4.6 TSSR Approved |  | 2023-10-06 | 2023-10-23 |  | 2023-10-27 |  | Closed | 2023-10-30 | 2023-11-07 | E//Hannah | 2023-11-07 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231006 | DU00002861057 |  |  | 2023-11-23 | 2023-11-06 |  | Monopole | 36m Monopole | 35m | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 2 | 0
9640A | Sundar | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | AD | DATASCO | 4.6 TSSR Approved |  | 2025-05-14 |  | 2025-05-28 |  | 2025-06-06 | To be Submitted | 2025-06-12 |  | E//John | 2025-06-17 | SQ202502050346-Datasco | DU00002861058 |  | Please provide FE drawing. |  |  | 2025-11-27 |  | Tower
1753B | Seri Kembangan (Serdang New Village) | Central |  | Modernization |  | 2024 Q3 | SY1 | DATASCO | 4.6 TSSR Approved |  | 2024-07-15 | 2024-07-16 |  | 2024-07-19 |  | Closed | 2024-12-16 | 2024-12-17 | E//Sumitra | 2024-12-17 | CelcomDigi_RAN_Datasco_TSS_Central_20231214 | DU00002861059 |  |  | 2024-11-18 | 2024-11-07 |  | Tower | 45m 3 Legged Tower | 24m | Add R8862A S9000x3+R8894E M1821x1+A9732 M1821x1 | 3 | 12
3270A | TMNSEGARPERDANA | Central |  | Modernization |  | 2024 Q4 | BY | GTSB | 4.6 TSSR Approved |  | 2024-01-08 | 2024-01-15 |  | 2024-05-23 |  | Closed | 2024-05-29 | 2024-06-12 |  | 2024-06-07 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240110 | DU00002861060 |  |  | 2024-12-10 | 2024-12-06 |  | Pole | 3m Bipod (RT) | 12m | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 1 | 0
3453A | JLN20SEK14PJ1 | Central |  | Modernization |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-04-06 | 2024-04-16 |  | 2024-04-19 |  | Closed | 2024-04-23 | 2024-04-23 | E//Kok Keen | 2024-04-23 | CelcomDigi_RAN_Datasco_TSS_Central_20231201 | DU00002861061 |  |  | 2024-05-20 | 2024-05-17 |  | In-Building System | 3m Bipod (RT) | 6 | Add R9264M M1821 x3,Dismantle R8882 S1800(B) x2+R8862A S1800(B6A) x1++R8881 S2100 x3+ | 0 | 0
9573B | Bukit Goram Kapit | Sarawak |  | Modernization |  | 2025 Q3 | AD | Trintel | 4.6 TSSR Approved |  | 2025-03-17 | 2025-03-20 |  | 2025-04-04 |  | Under Approval | 2025-04-07 | 2025-05-23 | E//Hannah | 2025-04-21 | SQ202503240175-Trintel | DU00002861062 |  |  | 2025-07-06 | 2025-05-28 |  | Lampole | Tower | 30m | Add R9264M M1821x2+A9732 M1821x1, Dismantle R8894E M1821(A8A)x3 | 3 | 0
9037B | 10th Mile Bazaar MP | Sarawak |  | Modernization |  | 2025 Q1 | SH | Magicell | 4.6 TSSR Approved |  | 2023-10-09 | 2023-10-10 |  | 2023-10-13 |  | Closed | 2023-10-13 | 2023-10-30 | E//Hannah | 2023-10-27 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231009 | DU00002861063 |  |  | 2023-11-10 | 2023-11-07 |  | Monopole | 30m Monopole | 30 | Add R8852E S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 13 | 0
9038A | Ayer Manis | Sarawak |  | Modernization |  | 2025 Q3 | AI | Magicell | 4.6 TSSR Approved | AAU Cannot Install-S3 MM change to BI¦rejected by Sacofa due to AAU not allowed to install at Sector 3 | 2023-10-13 | 2023-10-16 |  | 2023-10-20 |  | Closed | 2023-10-21 | 2023-11-03 | E//John | 2025-05-20 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231016 | DU00002861064 |  | Remarks: Solution Changed | 2025-03-22 | 2025-03-07 |  | Tower | Tower | 47M | Add R8894E M1821x1 | 0 | 3
9056A | Simunjan (Sacofa) | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 | HW | Magicell | 4.6 TSSR Approved |  | 2025-04-09 |  | 2025-04-08 |  | 2025-05-01 | To be Submitted | 2025-05-05 |  | E//Hannah | 2025-05-23 | SQ202503170852-Magicell | DU00002861065 |  |  |  |  | 2025-08-05 |  | 60m 4 Legged Tower
9077A | Luak Bay | Sarawak |  | Modernization |  | 2025 Q1 | SH | Trintel | 4.6 TSSR Approved |  | 2023-10-12 | 2023-10-19 |  | 2023-10-23 |  | Closed | 2023-10-23 | 2023-11-20 | E//Hannah | 2025-03-05 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231013 | DU00002861066 |  | Remarks: Solution Changed | 2025-04-12 | 2025-03-06 |  | Tower | 45m 4 Legged Tower | 31 | Add R8852E S9000x3+R9264M M1821x3, Dismantle R8882 S1800B(B6B)x3+R8854D S2100(A4A)x3 | 0 | 0
9094A | Niah Town | Sarawak |  | Modernization |  | 2025 Q2 | AI | Trintel | 4.6 TSSR Approved |  | 2025-03-09 | 2025-04-14 |  | 2025-04-22 |  | Closed | 2025-04-23 | 2025-09-29 | E//Hannah | 2025-09-23 | SQ202503140104-Trintel | DU00002861067 |  |  | 2025-09-02 | 2025-08-23 |  | Tower | Tower | 100 | Add A9732 M1821x1+R9264M M1821x3+R8852E S9000x1+R8854 S2600x1, Dismantle R8894E M1821(A8A)x3 | 2 | 3
9095A | Batu Niah Junction (SACOFA) | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | NA | Trintel | 4.6 TSSR Approved |  | 2025-03-09 |  | 2025-04-18 |  | 2025-04-22 |  | 2025-04-25 | 2025-09-10 | E//John | 2025-05-22 | SQ202502050142-Trintel | DU00002861068 |  |  |  |  | 2025-08-27 |  | Tower
9096A | Niah National Park | Sarawak |  | Decomm, MOCN By Other Vendor | Decomm->On Hold->Decomm->On Hold->Decomm | 2025 | AD | Trintel | 4.6 TSSR Approved |  | 2025-05-02 |  | 2025-05-30 |  | 2025-06-16 |  | 2025-06-16 | 2025-10-17 | E//John | 2025-06-17 | SQ202505270561-Trintel | DU00002861069 |  |  |  |  | 2025-11-15 |  | Tower
3015A | Jln Desa Cahaya | Central |  | Site Out (Modernization) | Modernization->Site Out->Replacement, Site Out (Modernization) | 2024 Q4 |  | GTSB | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2025-07-15 |  | 2025-07-03 |  |  | To be Submitted |  |  |  |  | SQ202506170074 | DU00002861070 |  |  |  |  | 2025-08-05 |  | 30m Monopole |  |  | 23 | 0
9159A | Dalat(SACOFA) | Sarawak |  | Modernization |  | 2024 Q4(single site MOCN)-L2126 SSM | ZB | Magicell | 4.6 TSSR Approved |  | 2023-10-07 | 2023-10-10 |  | 2023-10-16 |  | Closed | 2024-10-18 | 2024-10-21 | E//Hannah | 2024-10-21 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231009 | DU00002861071 |  |  | 2024-11-11 | 2024-10-31 |  | Monopole | Tower | 60 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 234 | 0
9162A | Kg. Karu | Sarawak |  | Modernization |  | 2025 Q1 | AD | Magicell | 4.6 TSSR Approved |  | 2023-10-18 | 2025-05-06 |  | 2023-11-07 |  | Under Approval | 2025-01-02 | 2025-03-10 | E//John | 2025-06-17 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231019 | DU00002861072 | Remarks: Solution TSSR/BOM Changed | Solution Changed | 2025-06-25 | 2025-06-23 |  | Tower | 76m Tower | 78M | Add R8894E M1821x4+R8854 S2600x1, Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3+R8862A S2600(A4A)x1 | 0 | 3
9196A | Sg. Entinggan | Sarawak |  | Modernization |  | 2024 Q2 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-10-11 | 2023-10-13 |  | 2023-10-23 |  | Closed | 2024-02-26 | 2024-02-27 | E//Hannah | 2024-02-26 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231013 | DU00002861073 |  |  | 2024-03-31 | 2024-03-12 |  | Monopole | 45m 3 Legged Tower | 77 | Add R8894E M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3 | 0 | 0
2320A | Jln Reko Kajang | Central |  | Modernization |  | 2024 Additional | MA | YPTT | 4.6 TSSR Approved |  | 2024-04-17 | 2024-04-18 |  | 2024-11-24 |  | Closed | 2024-12-24 | 2025-01-09 | E//Sumitra | 2025-01-07 | CelcomDigi_RAN_YPTT_TSS_Central_20240513 | DU00002861074 | Remarks: Solution TSSR/BOM Changed |  | 2025-05-27 | 2025-05-22 |  | Tower | 45m 3 Legged Tower | 45 | Add R8894E M1821x3+R8854 S2600x3.,Dismantle R8862A S2600 x3 | 0 | 123
9257A | Balai Ringin | Sarawak |  | Modernization |  | 2025 Q3 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-10-16 | 2023-10-19 |  | 2023-10-23 |  | Closed | 2023-10-25 | 2023-11-17 | E//Hannah | 2025-04-23 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231017 | DU00002861075 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed | 2025-04-12 | 2025-03-26 |  | Tower | 45m 3 Legged Tower | 77 | Add R8852E S9000x1+R8862A S2601x4+R8894E M1821x1 | 0 | 0
9258A | Kg Rasau | Sarawak |  | Modernization |  | 2025 Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2023-10-12 | 2023-10-19 |  | 2023-10-23 |  | Closed | 2023-10-23 | 2023-11-15 | E//Hannah | 2025-04-14 |  | DU00002861076 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed | 2025-04-30 | 2025-04-26 |  | Tower | 60m 3 Legged Tower | 60 | Add R8894E M1821x1 | 0 | 1
3228A | Jalan Jelatek Streetlight | Central |  | Modernization |  | 2024 Q1 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-12-12 | 2023-12-15 |  | 2023-12-29 |  | Closed | 2024-01-02 | 2024-01-03 | E//Sumitra | 2024-01-03 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231213 | DU00002861077 |  |  | 2024-05-02 | 2024-04-30 |  | Lampole | 24m Lampole | 19m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
9286A | Limbang KM6(SACOFA) | Sarawak |  | Modernization |  | 2025 Q2 | AD | Datasco | 4.6 TSSR Approved |  | 2024-02-27 | 2025-03-25 |  | 2025-04-15 |  | Under Approval | 2025-04-17 | 2025-05-23 | E//Hannah | 2025-05-08 | Celcom Digi_RAN-Datasco-Standard PR TSS-Sarawak-20240302 | DU00002861078 |  |  | 2025-07-06 | 2025-06-14 |  | Tower | Tower | 76 | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8882 S1800(B)x2+R8862A S1800(B6A)x1 | 0 | 0
4464B | Lawin (Maxis) | Northern |  | Remote MOCN | Modernization->On Hold->Modernization->Remote MOCN | 2025 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-10-26 | 2023-11-02 |  | 2025-02-25 |  | Closed | 2025-03-12 | 2025-07-17 | E//Hazida | 2025-03-17 | Celcom Digi_RAN-GTSB-TSS-Northern-20231214-0077 | DU00002861079 | [5 empty] | Tower | 60m 3 Legged Tower | 60M | Reuse Existing RRU | 0 | 0
9292A | Mount Mulu Hotel | Sarawak |  | Remote MOCN | Modernization->On Hold->Modernization->Remote MOCN | 2025 Q2 | AI | Trintel | 14.0 TSSR Not Required (Reuse Existing BBU/RRU) |  | 2025-02-21 | 2025-02-24 |  | 2025-03-06 |  | Under Approval |  |  |  |  | SQ202501070293-Trintel | DU00002861080 | [5 empty] | Minimast | 3m Bipod (RT) | 13 | Reuse Existing RRU | 0 | 0
9319A | Lundu | Sarawak |  | Decomm | Decomm->On Hold->Decomm->On Hold->Decomm | 2024 Q2 | NA | South Pacific | 4.6 TSSR Approved |  | 2024-01-23 |  |  |  | 2024-01-31 |  | 2025-05-20 | 2026-01-07 | E//John | 2025-05-22 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20240124 | DU00002861081 |  |  |  |  | 2025-10-29 |  | 45m 3 Legged Tower
4425B | Jalan Medan | Northern |  | Modernization |  | 2024 Q2 | ZA | GCI | 4.6 TSSR Approved | ¦ 0228 - Listed for solution change, pending confirmed solution ¦ 0129 - GCI: WP informed TSSR not required as solution is Reuse BBU n RRU, only need add Filter 900 | 2023-10-07 | 2023-10-27 |  | 2024-03-07 |  | Rectificating | 2024-03-08 | 2024-03-18 | E//Ajay | 2024-03-15 | Celcom Digi_RAN-GCI-TSS-Northern-2023111-0057 | DU00002861082 |  |  | 2024-04-05 | 2024-03-30 |  | In-Building System | 3m RT (Wall Mounted Pole) | 8 | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R9224E M1821(AAB) x3 | 13 | 0
9367A | Matu | Sarawak |  | Modernization |  | 2025 Q2 | AD | Magicell | 4.6 TSSR Approved |  | 2023-10-12 | 2023-10-13 |  | 2023-10-23 |  | Closed | 2023-10-26 | 2023-11-15 | E//Hannah | 2025-03-17 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231013 | DU00002861083 |  | Remarks: Solution Changed | 2025-03-13 | 2025-03-08 |  | Tower | 30m Monopole | 76m | Reuse Existing RRU | 0 | 0
9376A | Politeknik Mukah | Sarawak |  | Modernization |  | 2025 Q2 | SM | Magicell | 4.6 TSSR Approved |  | 2023-10-07 | 2023-10-10 |  | 2023-10-16 |  | Closed | 2023-10-16 | 2023-11-03 | E//Hannah | 2025-05-18 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231009 | DU00002861084 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed | 2025-03-15 | 2025-03-14 |  | Tower | 45m 3 Legged Tower | 60M | Add R8852E S9000x2+R8894E M1821x3+R8862A S2601x1, Dismantle R8882-GUL1812x1+R8862A S1800(B6A)x2+R8862A S2100(A6A)x3+R8862A S2600(A4A)x1 | 0 | 0
9378A | Kemantan-Julau Junction | Sarawak |  | Modernization |  | 2025 Q2 | SHA | Datasco | 4.6 TSSR Approved |  | 2023-10-17 | 2023-10-25 |  | 2023-10-31 |  | Under Approval | 2025-01-02 | 2025-01-09 | E//Yanie | 2025-01-03 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231019 | DU00002861085 |  |  | 2025-03-15 | 2025-03-14 |  |  | 45m 3 Legged Tower | 77 | Add R8894E M1821x3, Dismantle R8862A S1800(B6A)x3 | 0 | 0
2727B | Tmn Puchong Indah 2 LP | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-15 | 2024-01-17 |  | 2024-04-22 |  | Closed | 2024-04-29 | 2024-05-06 | E//Razif | 2024-05-03 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240116 | DU00002861086 |  |  | 2024-06-22 | 2024-06-18 |  | Lampole | 24m Lampole | 31 | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 3 | 0
7420B | Mile 20 Sdk | Sabah |  | Modernization |  | 2024 Q4 | MS | Futong | 4.6 TSSR Approved |  | 2024-03-21 | 2024-03-22 |  | 2024-06-07 |  | Closed | 2024-06-11 | 2024-06-20 |  | 2024-06-13 | Celcom Digi_RAN-Futong-Standard PR TSS-Sabah-20240531 | DU00002861087 |  |  | 2024-06-30 | 2024-06-24 |  | Tower | Tower | 76 | Add R8862A S9000 x2+R9224E M1821 x4+R8854 S2600 x1,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R8862A S2601(A6A) x1 | 0 | 1
9434A | Sg Pinang | Sarawak |  | Modernization |  | 2024 Q2 | SH | Datasco | 4.6 TSSR Approved |  | 2023-10-18 | 2023-11-10 |  | 2024-01-10 |  | Closed | 2024-01-17 | 2024-01-19 | E//Hannah | 2024-01-19 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231019 | DU00002861088 |  |  | 2024-06-06 | 2024-05-20 |  | Tower | Tower | 75 | Add R8862A S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8862A S2600(A4A) x1+R8892E M1821(BAA) x3 |  | 2
9503A | Bekenu | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | AI | Trintel | 4.6 TSSR Approved |  | 2025-02-20 |  | 2025-03-20 |  | 2025-04-04 |  | 2025-04-25 | 2025-09-10 | E//Hannah | 2025-05-29 | SQ202502050142-Trintel | DU00002861089 |  |  |  |  | 2025-06-28 |  | Tower
9504A | Bekenu Junction | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | HW | Trintel | 4.6 TSSR Approved |  | 2025-02-26 |  | 2025-05-08 |  | 2025-05-13 |  | 2025-05-14 | 2026-01-19 | E//John | 2025-05-22 | SQ202502050142-Trintel | DU00002861090 |  |  |  |  | 2025-11-11 |  | Tower
9505A | Beluru Junction | Sarawak |  | Decomm, MOCN By Other Vendor | Decomm->On Hold->Decomm->On Hold->Decomm | 2025 | AD | Trintel | 4.6 TSSR Approved |  | 2025-05-02 |  | 2025-05-08 |  | 2025-05-13 |  | 2025-05-16 | 2025-10-17 | E//John | 2025-05-27 | SQ202505270561-Trintel | DU00002861091 |  |  |  |  | 2025-11-12 |  | 60m 3 Legged Tower
9507A | Bakam | Sarawak |  | Modernization |  | 2025 Q2 | AD | GTSB | 4.6 TSSR Approved |  | 2023-10-18 | 2023-11-09 |  | 2023-11-20 |  | Under Approval | 2025-01-02 | 2025-10-16 | E//Hannah | 2025-05-06 | Celcom Digi_RAN-GTSB-TSS-Sarawak-20231019 | DU00002861092 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed | 2025-07-06 | 2025-04-05 |  | Tower | Tower | 76M | Add R8894E M1821x4+R8854 S2600x1, Dismantle R8882-GUL1812x2+R8862A S1800(B6A)x1+R8854D S2100(A4A)x3+R8862A S2600(A4A)x1 | 0 | 2
3836A | Kembung Ulu Bangi (Lekas HW) | Central |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | SY1 | YPTT | 4.6 TSSR Approved |  | 2024-04-18 | 2024-04-29 |  | 2024-05-17 |  | Closed | 2024-10-21 | 2024-12-10 | E//Sumitra | 2024-12-10 | CelcomDigi_RAN_YPTT_TSS_Central_20240513 | DU00002861093 |  |  | 2025-04-14 | 2025-04-12 |  | Tower | 60m Tower | 60 | Add R8862A S9000 x3+R8894E M1821 x4+R8854 S2600x1,Dismantle R8882 S1800(B) x1+R8882 S1800B(B6B) x1+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3+R8862A S2600(A4A)x1 | 0 | 1
9509A | Sg Rait | Sarawak |  | Modernization |  | 2025 Q2 | AI | Trintel | 4.6 TSSR Approved |  | 2025-02-20 | 2025-04-10 |  | 2025-04-21 |  | Under Approval | 2025-04-29 | 2025-05-21 | E//Hannah | 2025-05-08 | SQ202502170093-Trintel | DU00002861094 |  |  | 2025-08-26 | 2025-08-18 |  | Tower | 45m 3 Legged Tower | 45m | Add R8852E S9000x2+R8894E M1821x3, Dismantle R8882-GUL1812x2+R8862A S1800(B6A)x1+R8854D S2100(A4A)x3 | 0 | 0
9511A | Jlnlambirmyy | Sarawak |  | Modernization |  | 2025 Q2 | HW | Trintel | 4.6 TSSR Approved |  | 2025-02-24 | 2025-04-09 |  | 2025-04-14 |  | Under Approval | 2025-04-16 | 2025-05-19 | E//Hannah | 2025-05-08 | SQ202502050142-Trintel | DU00002861095 |  |  | 2025-07-06 | 2025-06-20 |  | Tower | 45m 3 Legged Tower | 76m | Add R8894E M1821x3, Dismantle R8882 S1800B(B6B)x3 | 0 | 0
9523A | RIAMROADBYPASS | Sarawak |  | Modernization |  | 2025 Q1 | AI | Datasco | 4.6 TSSR Approved |  | 2023-12-08 | 2024-04-25 |  | 2025-02-03 |  | Closed | 2025-03-05 | 2025-04-08 | E//Hannah | 2025-03-17 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231212 | DU00002861096 |  |  | 2025-07-06 | 2025-03-24 |  | Tower | Tower | 45 | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8882 S1800B(B6B)x3 | 0 | 0
9524A | TM Tanjung Lobang | Sarawak |  | Modernization |  | 2025 Q1 | SM | Trintel | 4.6 TSSR Approved |  | 2023-10-17 | 2023-10-23 |  | 2023-10-27 |  | Closed | 2023-10-27 | 2023-11-15 | E//Hannah | 2025-02-25 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231017 | DU00002861097 |  | Remarks: Solution Changed | 2025-07-06 | 2025-05-16 |  | Tower | 76m Tower | 74 | Add R8852E S9000x3+R9264M M1821x3, Dismantle R8882-GUL1812x2+R8882 S1800B(B6B)x3+R8862A S1800(B6A)x1+R8840-U216x3 | 0 | 0
9539A | Lambir Miri Trunk | Sarawak |  | Decomm, MOCN By Other Vendor | Decomm->On Hold->Decomm->On Hold->Decomm | 2025 | AD | Magicell | 4.6 TSSR Approved |  | 2025-11-13 |  |  |  | 2025-11-25 |  | 2025-12-04 | 2026-01-19 | E//Zamri | 2025-12-05 | SQ202507250423-Magicell | DU00002861098 |  |  |  |  | 2025-11-24 |  | Tower
9545A | Kg Sepurau Miri | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | AI | Trintel | 4.6 TSSR Approved |  | 2025-03-09 |  | 2025-03-17 |  | 2025-04-09 |  | 2025-04-15 | 2025-10-13 | E//Hannah | 2025-07-18 | SQ202502050142-Trintel | DU00002861099 |  |  |  |  | 2025-07-19 |  | Tower
9549A | Bakam Celcom | Sarawak |  | Modernization |  | 2025 Q2 | HW | Trintel | 4.6 TSSR Approved |  | 2025-02-20 | 2025-04-09 |  | 2025-04-14 |  | Under Approval | 2025-04-14 | 2025-04-24 | E//Hannah | 2025-04-21 | SQ202502050142-Trintel | DU00002861100 |  |  | 2025-08-26 | 2025-08-20 |  | Tower | 45m 3 Legged Tower | 76m | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8882-GUL1812x3+R8854D S2100(A4A)x3 | 0 | 0
3852A | KPUSAHAWAN_WPPJ_OUTDOOR | Central |  | Decomm | Modernization->Decomm | 2024 Q3 | BY | GTSB | 4.6 TSSR Approved |  | 2024-06-19 |  | 2024-07-01 |  | 2024-07-01 |  | 2024-07-02 | 2025-10-01 | E//Razif | 2024-07-16 | 0624Central-GTSB-BOQ Template (template) | DU00002861101 |  |  |  |  | 2024-10-16 |  | 3m Bipod (RT)
4711A | Pasir Puteh(REL) | Northern |  | Modernization |  | 2024 Q2 |  | YPTT | 4.6 TSSR Approved |  | 2023-12-26 | 2023-12-27 |  | 2024-01-08 |  | Rectificating | 2024-01-09 | 2024-01-11 |  | 2024-01-10 | Celcom Digi_RAN-YPTT-TSS-Northern-20231229-0049 | DU00002861102 |  |  | 2024-02-26 | 2024-02-17 |  | Lampole | 30m Monopole | 30M | Add R8862A S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882 S1800(B) x3+R8862A S2100(A6A) x3+R8862A S2600(A4A) x1 |  | 2
3243A | Alam Damai | Central |  | Modernization |  | 2024 Q3 | SY1 | Magicell | 4.6 TSSR Approved |  | 2024-07-24 | 2024-08-14 |  | 2024-08-16 |  | Closed | 2024-10-10 | 2024-10-14 | E//Sumitra | 2024-10-11 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240510 | DU00002861103 |  |  | 2024-11-22 | 2024-11-19 |  | Petronas Pylon | 24m Pylon | 25 | Add R8894E M1821 x3+R8862A S2601 x3,Dismantle R8882 S1800(B) x3+R8862A S2100(A6A) x3+R8882 S2600(B4A) x3 | 0 | 0
2325A | Tmn Rakan Cheras | Central |  | Modernization | Modernization->On Hold->Modernization | 2024 Q4(single site MOCN)-L26 SSM | SY1 | YPTT | 4.6 TSSR Approved |  | 2024-07-25 | 2024-07-30 |  | 2024-08-02 |  | Closed | 2025-03-14 | 2024-08-13 | E//Sumitra | 2024-08-13 | 0730CD-Central-YPTT-BOQ Template(new contract) | DU00002861104 | Remarks: Solution TSSR/BOM Changed |  | 2025-09-02 | 2025-08-23 |  | Petronas Pylon | 24m Pylon | 30 | Add R9264M M1821x3+R8862A S2601x1,Dismantle R8894E M1821(A8A)x3+R8882 S2600(B4A)x1 | 0 | 0
3425A | TMNDELIMA1 | Central |  | Modernization |  | 2024 Q4 | CR | GCI | 4.6 TSSR Approved |  | 2023-11-10 | 2023-11-03 |  | 2024-05-15 |  | Closed | 2024-05-23 | 2024-05-30 | E//Sumitra | 2024-05-30 | CelcomDigi_RAN_GCI_TSS_Central_20231214 | DU00002861105 |  |  | 2024-09-20 | 2024-09-19 |  | In-Building System | 3m Bipod (RT) | 9 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
9119B | Kg Bratan | Sarawak |  | Modernization |  | 2025 Q1 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-10-17 | 2023-10-19 |  | 2023-10-24 |  | Closed | 2023-10-25 | 2023-11-15 | E//Hannah | 2023-11-08 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231019 | DU00002861106 | Remarks: Solution TSSR/BOM Changed |  | 2023-11-24 | 2023-11-15 |  | Tower | Tower | 62 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
3711A | Jalil Jaya | Central |  | Modernization |  | 2024 Q3 | MA | GTSB | 4.6 TSSR Approved |  | 2023-10-31 | 2023-11-14 |  | 2024-03-21 |  | Closed | 2024-03-25 | 2024-04-01 | E//Sumitra | 2024-04-01 | CelcomDigi_RAN_GTSB_TSS_Central_20231101 | DU00002861107 |  |  | 2024-06-30 | 2024-06-22 |  | In-Building System | 3m Bipod (RT) | 8 | Add R9264H M901821 x3,Dismantle R9224E M1821(AAB) x3 | 0 | 0
3734A | Lebuh Puteri | Central |  | Modernization |  | 2024 Q3 | SH | Magicell | 4.6 TSSR Approved |  | 2023-12-10 | 2023-12-14 |  | 2024-04-23 |  | Closed | 2024-05-06 | 2024-05-07 | E//Kok Keen | 2024-05-07 | CelcomDigi_RAN_Magicell_TSS_Central_20231214 | DU00002861108 |  |  | 2024-06-28 | 2024-06-26 |  | In-Building System | Tower | 6 | Add R8894E M1821 x4,Dismantle R8882 S1800B(B6B) x4+R8862A S2100(A6A) x4 | 0 | 0
3845A | PRESINT 17 | Central |  | Modernization |  | 2024 Q3 | SH | Magicell | 4.6 TSSR Approved |  | 2024-01-05 | 2024-01-11 |  | 2024-04-19 |  | Closed | 2024-05-07 | 2024-05-14 | E//Kok Keen | 2024-05-14 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240110 | DU00002861109 |  |  | 2024-07-02 | 2024-06-24 |  | In-Building System | 3m Bipod (RT) | 3M | Add R8862A S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 | 0 | 2
3846A | PRESINT 18 | Central |  | Modernization |  | 2024 Q3 | SH | Magicell | 4.6 TSSR Approved |  | 2024-01-10 | 2024-01-19 |  | 2024-04-22 |  | Closed | 2024-05-20 | 2024-05-28 | E//Kok Keen | 2024-05-28 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240115 | DU00002861110 |  |  | 2024-06-25 | 2024-06-25 |  | In-Building System | 3m RT (Wall Mounted Pole) |  | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R8862A S1800(B6A) x3++R8881 S2100 x3+ | 2 | 0
7384B | Kg. Bakapit | Sabah |  | Modernization |  | 2024 Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-10-26 | 2023-10-27 |  | 2023-11-03 |  | Under Approval | 2024-10-07 | 2024-10-07 | E//Hannah | 2024-10-07 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231028 | DU00002861111 |  |  | 2024-10-17 | 2024-10-10 |  |  | 60m 3 Legged Tower | 60m | Add R8894E M1821 x2 | 0 | 12
4570B | Jalan Dato Sagor | Northern |  | Modernization |  | 154 single site MOCN | SM | GTSB | 4.6 TSSR Approved |  | 2023-10-15 | 2023-10-27 |  | 2024-08-26 |  | Rectificating | 2024-08-27 | 2024-09-23 | E//Hazida | 2024-09-23 | Celcom Digi_RAN-GTSB-TSS-Northern-20231015-0049 | DU00002861112 |  |  | 2024-09-12 | 2024-09-06 |  | Floor Mount Boom | 3m Boom (RT) | 6 | Add R8852E S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882-GUL1812 x3+R8862A S2600(A4A) x1 |  | 3
4065C | East Menglembu Industry | Northern |  | Modernization |  | 2024 Q2 | BY | Magicell | 4.6 TSSR Approved |  | 2023-10-30 | 2023-11-03 |  | 2024-01-08 |  | Rectificating | 2024-01-08 | 2024-01-11 | E//Ajay | 2024-01-10 | Celcom Digi_RAN-Magicell-TSS-Northern-20231101-0002 | DU00002861113 |  |  | 2024-01-19 | 2024-01-12 |  | Lampole | 24m Lampole | 27 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882 S1800(B) x1+R8882 S1800B(B6B) x2++R8881 S2100 x3+
4083C | Bougainvillea Ipoh | Northern |  | Modernization |  | 2024 Q2 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-10-11 | 2023-10-16 |  | 2024-01-11 |  | Closed | 2024-01-17 | 2024-01-29 | E//Hazida | 2024-01-25 | Celcom Digi_RAN-GCI-TSS-Northern-20231013-0058 | DU00002861114 |  |  | 2024-02-09 | 2024-02-05 |  | In-Building System | 45m 3 Legged Tower | 5 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882 S1800(B) x3+R8881 S2100 x3
3011A | Jalan Permaisuri | Central |  | Modernization |  | 2024 Q3 | CR | Ascentrack | 4.6 TSSR Approved |  | 2023-11-03 | 2023-11-07 |  | 2023-12-02 |  | Closed | 2024-05-13 | 2024-05-24 | E//Sumitra | 2024-05-24 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231104 | DU00002861115 |  |  | 2024-05-12 | 2024-05-08 |  | Lampole | 24m Lampole | 24 | Add R9264H M901821 x3,Dismantle R8862A S9000(A6A) x3+R8862A S1800(B6A) x3++R8881 S2100 x3+ | 0 | 0
3625A | ILSAS KM7 | Central |  | Modernization |  | 2024 Q3 | SHA | YPTT | 4.6 TSSR Approved |  | 2024-05-10 | 2024-05-30 |  | 2024-06-10 |  | Under Approval | 2024-06-12 | 2024-07-01 | E//Sumitra | 2024-06-19 | CelcomDigi_RAN_YPTT_TSS_Central_20240513 | DU00002861116 |  |  | 2024-11-25 | 2024-11-22 |  | Lampole | 30m Monopole | 30 | Add R8862A S9000 x4+R8894E M1821 x4+R8862A S2601 x4,Dismantle R8862A S1800(B6A) x3+R8862A S2600(A4A) x3+R8862A S2601(A6A) x1+R8892N M1821(BAB) x1 | 0 | 0
1275B | Tmn Cheras Utama | Central |  | Modernization |  | 2024 Q4 | SY1 | Solusi | 4.6 TSSR Approved |  | 2024-03-28 | 2024-03-01 |  | 2024-05-27 |  | Closed | 2024-09-27 | 2024-09-30 | E//Sumitra | 2024-09-30 | BOQ CelcomDigi_RAN_Solusi_Standard PR TSS_Central_20240329 | DU00002861117 |  |  | 2024-11-21 | 2024-11-19 |  | In-Building System | 3m Bipod (RT) | 3M | Add R8852E S9000 x3+R8894E M1821 x2 | 0 | 13
3718A | Jln Kelantan (REL) | Central |  | Modernization | Modernization->On Hold->Modernization->On Hold->Modernization | 2024 Q2 | SS | CCSMY | 4.6 TSSR Approved | 13/3- R9264H cannot fit in RRU cabinet ¦¦CLUSTER ANTENNA | 2023-11-21 | 2023-11-23 |  | 2024-03-12 |  | Under Approval | 2024-03-18 | 2024-03-19 |  | 2024-03-18 | CelcomDigi_RAN_CCSMY_TSS_Central_20231119 | DU00002861118 |  |  | 2025-05-13 | 2025-05-07 |  | Pole | 18m Lampole | 15M | Add R9264M M1821 x3,Dismantle R8892E M1821(BAA) x3 | 0 | 0
3709A | Surau Al Ikhlasiah | Central |  | Modernization |  | 2024 Q1 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-12-27 | 2024-01-24 |  | 2024-01-26 |  | Closed | 2024-01-31 | 2024-02-06 | E//Sumitra | 2024-02-06 | CelcomDigi_RAN_Ascentrak_TSS_Central_20231230 | DU00002861119 |  |  | 2024-03-08 | 2024-03-04 |  | Lampole | 24m Lampole | 25m | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3
9198B | Tmn Kiong Soon | Sarawak |  | Modernization |  | 2025 Q2 | AD | Trintel | 4.6 TSSR Approved |  | 2025-04-02 | 2025-04-25 |  | 2025-05-02 |  | Under Approval | 2025-05-07 | 2025-05-21 | E//John | 2025-05-19 | SQ202503030411-Trintel | DU00002861120 |  |  | 2025-06-26 | 2025-06-24 |  | Monopole | 30m Rapole | 15 | Add R9264M M1821x3, Dismantle R8894E M1821(A8A)x3 | 0 | 0
9585A | TM Jalan Taman Tunku | Sarawak |  | Modernization |  | 2026 | AD | Magicell | 4.6 TSSR Approved |  | 2025-04-09 | 2025-05-16 |  | 2025-05-20 |  | Under Approval | 2025-05-21 | 2025-05-23 | E//John | 2025-05-23 | SQ202502050300-Magicell | DU00002861121 | [5 empty] | Tower | Guyed Mast | 25 | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8882 S1800(B)x3+R8862A S2100(A6A)x3 | 0 | 0
9123B | Taman Hill view | Sarawak |  | Modernization |  | 2024 Q2 | SH | Magicell | 4.6 TSSR Approved |  | 2023-10-04 | 2023-10-09 |  | 2023-10-13 |  | Closed | 2023-10-13 | 2023-11-03 | E//Hannah | 2023-11-01 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231006 | DU00002861122 |  |  | 2023-11-13 | 2023-11-07 |  | Monopole | Rapole | 30 | Add R9264M M1821 x1+R9264H M901821 x4+R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R9224E M1821(AAB) x1 | 0 | 3
9199B | Kpg Belawai | Sarawak |  | Modernization |  | 2025 Q1 | SM | Magicell | 4.6 TSSR Approved | 0218 - Emailedplaning on CD comment | 2024-01-27 | 2024-02-14 |  | 2025-02-06 |  | Rectificating | 2025-02-07 | 2025-02-25 | E//Hannah | 2025-02-24 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20240123 | DU00002861123 |  |  | 2025-03-24 | 2025-03-24 |  | Tower | Tower | 75M | Add R8894E M1821x1 | 0 | 3
4084C | Tmn Lapangan Terbang Ipoh | Northern |  | Modernization |  | 2024 Q2 |  | GCI | 4.6 TSSR Approved |  | 2023-10-11 | 2023-10-20 |  | 2024-01-09 |  | Closed | 2024-01-13 | 2024-01-18 | E//Hazida | 2024-01-17 | Celcom Digi_RAN-GCI-TSS-Northern-20231013-0058 | DU00002861124 |  |  | 2024-01-29 | 2024-01-26 |  | Wall mount boom | 3m RT (Wall Mounted Pole) | 5 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882 S1800B(B6B) x3++R8881 S2100 x3+
7511B | Driving Range Sandakan | Sabah |  | Modernization |  | 2024 Q3 | AD | GTSB | 4.6 TSSR Approved | 16/4: 5/4: Trigger ZTE Rollout for PE structure analysis | 2024-01-31 | 2024-03-20 |  | 2024-04-15 |  | Closed | 2024-04-16 | 2024-04-22 | E//Hannah | 2024-04-22 | Celcom Digi_RAN-GTSB-TSS-Sabah-20240204 | DU00002861125 |  |  | 2024-06-26 | 2024-06-18 |  | In-Building System | 6m Unipole RT | 7 | Add R8862A S9000 x3+A9732 M1821 x3,Dismantle R8882 S1800(B) x3+R8862A S2100(A6A) x3 | 123 | 0
4739A | Kg Bkt Lembu | Northern |  | Modernization |  | 2025 Q2 | AD | GTSB | 4.6 TSSR Approved |  | 2025-01-21 | 2025-01-27 |  | 2025-02-04 |  | Under Approval | 2025-02-14 | 2025-03-09 | E//Hazida | 2025-02-25 | SQ202501030229 - gtsb | DU00002861126 |  |  | 2025-03-04 | 2025-02-20 |  | In-Building System | 3m Bipod (RT) | 7M | Reuse Existing RRU | 0 | 0
4743A | Simpang Kenyum | Northern |  | Decomm | Modernization->On Hold->Decomm | 131 single site mocn | HW | GTSB | 4.6 TSSR Approved | ¦ 0910 - pBTS: emailed planner, not able for MM UPG | 2024-08-29 | 2024-09-06 | 2025-03-16 | 2025-02-18 | 2025-03-19 | Rectificating | 2025-06-16 |  | E//Hazida | 2025-06-17 | 0809CD-Northern-GTSB-BOQ Template(new contract) | DU00002861127 |  | No Photo NE/FE TX part |  |  | 2025-03-27 | Tower | 30m Monopole | 30M | Add R8862A S9000x3+A9732 M1821x2+R8854 S2600x1, Dismantle R8894E M1821(A8A)x1+R8862A S2600(A4A)x1 | 12 | 3
4744A | TM Kuah | Northern |  | Decomm | Modernization->On Hold->Decomm | 131 single site mocn | SM | CCSMY | 4.6 TSSR Approved | ¦ 0816 - Triggered rollout for PE study. | 2023-10-13 | 2023-10-16 | 2025-05-28 | 2023-10-23 |  | Closed | 2024-08-16 | 2024-08-19 | E//Hazida | 2024-08-19 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231016-0055/SQ202510220217 | DU00002861128 |  |  |  |  | 2025-05-22 | In-Building System | 3m Bipod (RT) | 5m | Add R8862A S9000x4+R8894E M1821x3 | 0 | 123
4768A | Tmn Desa Darat | Northern |  | Modernization |  | 154 single site MOCN | SM | GTSB | 4.6 TSSR Approved |  | 2024-01-13 | 2024-01-16 |  | 2024-08-21 |  | Rectificating | 2024-08-23 | 2024-09-05 | E//Hazida | 2024-09-05 | Celcom Digi_RAN-GTSB-TSS-Northern-202401114-0085 | DU00002861129 |  |  | 2024-09-10 | 2024-09-03 |  | Lampole | 4 Legged Tower | 30 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3++R8881 S2100 x3+
4920A | Pekan Baru Drl Ridzuan | Northern |  | Modernization |  | 2024 Additional | SM | GTSB | 4.6 TSSR Approved |  | 2024-12-18 | 2024-12-27 |  | 2024-12-31 |  | Rectificating | 2025-01-02 | 2025-01-14 | E//Hazida | 2025-01-14 | SQ202412060099 - GTSB | DU00002861130 |  |  | 2025-01-13 | 2025-01-13 |  | Unipole | 6m Unipole RT | 8 | Add R9264H M901821x3, Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3 | 0 | 0
7769B | Kampung Mawao | Sabah |  | Modernization |  | 2025 Q2 | SM | Seri Pancar | 4.6 TSSR Approved |  | 2023-10-31 | 2023-11-03 |  | 2025-01-14 |  | Rectificating | 2025-02-20 | 2025-02-25 | E//Hannah | 2025-02-24 | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231221 | DU00002861131 |  |  | 2025-03-25 | 2025-03-21 |  | Tower | Tower | 60 | Add R8894E M1821x1 | 0 | 2
2341A | Taman Kinrara 2 | Central |  | Modernization |  | 2024 Q3 | CR | GCI | 4.6 TSSR Approved |  | 2023-10-24 | 2023-10-31 |  | 2024-04-19 |  | Closed | 2024-04-28 | 2024-05-02 | E//Sumitra | 2024-05-02 | CelcomDigi_RAN_GCI_TSS_Central_20231214 | DU00002861132 |  |  | 2024-10-21 | 2024-10-17 |  | Lampole | 24m Lampole | 24 | Add R8862A S9000 x1+R8894E M1821 x4,Dismantle R8882 S1800B(B6B) x3+R8862A S1800(B6A) x1+R8862A S2100(A6A) x4 | 0 | 0
2385A | Jln Bayan LP | Central |  | Modernization |  | 2024 Q3 | SH | Magicell | 4.6 TSSR Approved |  | 2024-01-09 | 2024-01-15 |  | 2024-04-22 |  | Closed | 2024-05-07 | 2024-05-15 | E//Kok Keen | 2024-05-15 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240110 | DU00002861133 |  |  | 2024-06-15 | 2024-06-12 |  | In-Building System | 3m RT (Wall Mounted Pole) | 3m | Add R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882 S1800(B) x3+R8862A S2600(A4A) x1++R8881 S2100 x3+ | 0 | 2
1312B | Surau La Cottage Putra Perdana 14 | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002861134 | [6 empty] | 24m Lampole |  |  | 12
3218A | Tmn Lembah Keramat | Central |  | Modernization |  | 2024 Q1 | SS | YPTT | 4.6 TSSR Approved |  | 2023-10-21 | 2023-10-24 |  | 2023-12-29 |  | Closed | 2024-01-02 | 2024-01-05 | E//Sumitra | 2024-01-04 | CelcomDigi_RAN_YPTT_TSS_Central_20231025 | DU00002861135 |  |  | 2024-05-03 | 2024-04-30 |  | In-Building System | 3m Bipod (RT) | 5 | Add R9264H M901821 x3,Dismantle R8882 S1800(B) x3
2649B | Lestari Sanctuary | Central |  | Modernization |  | 2024 Q3 | MA | Solusi | 4.6 TSSR Approved |  | 2024-01-16 | 2024-01-22 |  | 2024-04-30 |  | Closed | 2024-05-06 | 2024-07-11 | E//Sumitra | 2024-07-11 | CelcomDigi_RAN_Solusi_TSS_Central_20240124 | DU00002861136 |  |  | 2024-06-24 | 2024-06-24 |  | H-bracket pole | 3m Boom (RT) | 6m | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R9224E M1821(AAB) x3 | 3 | 0
2965A | Ampang Permai Petronas | Central |  | Modernization | Modernization>On Hold->Modernizatin | 2024 Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-12-27 | 2024-01-05 |  | 2025-03-19 |  | Under Approval | 2025-03-19 | 2025-05-27 | E//Sumitra | 2025-04-18 | CelcomDigi_RAN_GTSB_TSS_Central_20231230 | DU00002861137 | Remarks: Solution TSSR/BOM Changed |  | 2025-05-07 | 2025-05-06 |  | Petronas Pylon | 24m Pylon | 29 | Reuse Existing RRU | 0 | 3
4157C | USP_Jln Bkt Malut 1 | Northern |  | Modernization |  | 2025 Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2025-01-27 | 2025-02-23 |  | 2025-02-26 |  | Closed | 2025-02-28 | 2025-03-10 | E//Hazida | 2025-03-28 | SQ202501030229 - gtsb | DU00002861138 |  |  | 2025-03-21 | 2025-03-10 |  | Tower | 30m Monopole | 60m | Add R8894E M1821x1 | 0 | 3
3912B | Jalan Perusahaan Tengah Setapak | Central |  | Modernization |  | 2024 Q1 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-01-22 | 2024-02-23 |  | 2024-03-04 |  | Closed | 2024-03-07 | 2024-03-07 | CD//Sapian | 2024-03-07 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240128 | DU00002861139 |  |  | 2024-05-13 | 2024-05-08 |  | Pole | 3m Bipod (RT) | 5m | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
3907B | Serdang Jaya | Central |  | Modernization |  | 2024 Q3 | CR | GCI | 4.6 TSSR Approved |  | 2024-02-19 | 2024-02-26 |  | 2024-04-23 |  | Closed | 2024-05-28 | 2024-06-04 | E//Sumitra | 2024-06-04 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240225 | DU00002861140 |  |  | 2024-08-31 | 2024-08-21 |  | In-Building System | 3m Boom (RT) | 5 | Reuse exisiting RRU | 0 | 0
4573B | Senggang | Northern |  | Modernization | Modernization->On Hold->Modernization | 2025 Q3 | AD | GCI | 4.6 TSSR Approved |  | 2023-10-27 | 2023-11-03 |  | 2025-02-25 |  | Under Approval | 2025-04-09 | 2025-05-23 | E//Hazida | 2025-04-23 | Celcom Digi_RAN-GCI-TSS-Northern-20231028-0067 | DU00002861141 |  |  | 2025-04-22 | 2025-04-16 |  | Tower | 60m 3 Legged Tower | 60 | Add R8894E M1821x3, Dismantle R8862A S1800(B6A)x3 | 0 | 0
3106B | Jalan Vivekananda (HSR) | Central |  | Modernization |  | 2024 Q2 | XH | CCSMY | 4.6 TSSR Approved |  | 2023-10-24 | 2023-10-30 |  | 2024-01-10 |  | Closed | 2024-01-29 | 2024-02-06 | E//Sumitra | 2024-02-06 | CelcomDigi_RAN_CCSMY_TSS_Central_20231025 | DU00002861142 |  |  | 2024-04-30 | 2024-04-04 |  | In-Building System | 3m Boom (RT) | 6M | Add R9264H M901821 x3,Dismantle R8882 S1800B(B6B) x3++R8881 S2100 x3+
3107B | Jalan Thamby (HSR) | Central |  | Modernization |  | 2024 Q2 | MA | CCSMY | 4.6 TSSR Approved |  | 2023-10-24 | 2023-10-27 |  | 2024-03-04 |  | Closed | 2024-03-15 | 2024-03-19 | E//Kok Keen | 2024-03-19 | CelcomDigi_RAN_CCSMY_TSS_Central_20231025 | DU00002861143 |  |  | 2024-05-25 | 2024-05-24 |  | In-Building System | 3m RT (Wall Mounted Pole) | 3 | Add R8852E S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882 S1800B(B6B) x3+R8854D S2100(A4A) x3+R8862A S2600(A4A) x1 | 0 | 2
3120B | Pasar Kampung Baru Salak Selatan | Central |  | Modernization |  | 2024 Q3 | SH | DATASCO | 4.6 TSSR Approved |  | 2023-11-16 | 2023-11-23 |  | 2024-03-25 |  | Closed | 2024-03-27 | 2024-04-15 | E//Kok Keen | 2024-04-05 | CelcomDigi_RAN_Datasco_TSS_Central_20231119 | DU00002861144 |  |  | 2024-06-04 | 2024-05-27 |  | Lampole | TT DOTCOM SDN BHD | 18 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
3125B | Taman Desa Utara (HSR) | Central |  | Modernization |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-12-26 | 2024-01-22 |  | 2024-02-01 |  | Closed | 2024-04-01 | 2024-04-18 | E//Sumitra | 2024-04-18 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231227 | DU00002861145 |  |  | 2024-04-30 | 2024-04-24 |  | Pole | 3m Bipod (RT) | 8m | Add R9264M M1821 x3,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3
3747A | Assunta Hospital RT (HSR) | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-03-18 | 2024-03-21 |  | 2024-03-27 |  | Closed | 2024-03-27 | 2024-03-29 | E//Kok Keen | 2024-03-27 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240323 | DU00002861146 |  |  | 2024-05-30 | 2024-05-29 |  | In-Building System | 3m Bipod (RT) | 6m | Add R9264H M901821 x3,Dismantle R8882 S1800B(B6B) x3+R8854D S2100(A4A) x3 | 0 | 0
3132B | PJS3 (HSR) | Central |  | Modernization |  | 2024 Q3 | MA | GTSB | 4.6 TSSR Approved |  | 2023-11-10 | 2023-11-15 |  | 2024-04-17 |  | Closed | 2024-04-23 | 2024-04-24 | E//Kok Keen | 2024-04-24 | CelcomDigi_RAN_GTSB_TSS_Central_20231113 | DU00002861147 |  |  | 2024-04-13 | 2024-04-03 |  | A-bracket pole | 3m Bipod (RT) | 3m | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882 S1800B(B6B) x3+R8881 S2100 x3] | 0 | 0
3679A | SGLONG31 | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4 |  |  | 14.3 Drop (Done Survey + TSSR) |  | 2023-09-29 | 2023-11-24 |  | 2023-11-30 |  | Under Approval | [5 empty] | DU00002861148 | [5 empty] | In-Building System | 24m Lampole | 12 | Reuse Existing RRU | 123 | 0
2940A | Damai Indah Kajang | Central |  | Modernization |  | 2024 Q4 | SM | GTSB | 4.6 TSSR Approved |  | 2024-01-10 | 2024-02-22 |  | 2024-05-16 |  | Under Approval | 2024-05-31 | 2024-09-20 | E//Sumitra | 2024-09-20 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240115 | DU00002861149 |  |  | 2024-09-10 | 2024-09-07 |  | In-Building System | 3m RT (Wall Mounted Pole) | 5m | Add R9264M M1821 x3+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x4 | 1 | 0
3727A | Taman Perindustrian Oug | Central |  | Modernization |  | 2024 Q3 | MA | GTSB | 4.6 TSSR Approved |  | 2023-11-16 | 2023-11-23 |  | 2024-04-16 |  | Closed | 2024-04-23 | 2024-04-25 | E//Sumitra | 2024-04-25 | CelcomDigi_RAN_GTSB_TSS_20231119 | DU00002861150 |  |  | 2024-04-19 | 2024-04-18 |  | A-bracket pole | 6m Unipole RT | 5m | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle R8862A S2600(A4A) x1 | 0 | 3
7953A | HospitalKotaMarudu | Sabah |  | Modernization |  | 2025 Q3 | HW | GTSB | 4.6 TSSR Approved |  | 2025-01-09 | 2025-02-25 |  | 2025-03-14 |  | Under Approval | 2025-03-17 | 2025-04-24 | E//Hannah | 2025-04-16 | SQ202501030028 - GTSB | DU00002861151 |  |  | 2025-04-10 | 2025-04-09 |  | Tower | 45m 3 Legged Tower | 60 | Add R8852E S9000x3 | 0 | 1
9265A | Poliklinik Sarikei | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-12-08 |  |  |  | 2024-01-05 |  | 2024-02-19 | 2025-10-31 | E//Hannah | 2025-10-28 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231212 | DU00002861152 |  |  |  |  | 2025-10-29 |  | 35m Tower
3703A | Jalan Suarasa | Central |  | Modernization |  | 2024 Q4 | SHA | Solusi | 4.6 TSSR Approved |  | 2024-01-11 | 2024-01-15 |  | 2024-05-27 |  | Closed | 2024-05-31 | 2024-06-12 | E//Sumitra | 2024-06-11 | BOQ CelcomDigi_RAN_Solusi_Standard PR TSS_Central_20240117 | DU00002861153 |  |  | 2024-09-20 | 2024-09-20 |  | In-Building System | 3m Bipod (RT) | 5 | Add R8862A S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2600(A4A) x1++R8881 S2100 x3+ | 0 | 2
3228B | Jln Cahaya 20 | Central |  | Modernization |  | 2024 Q2 | MA | YPTT | 4.6 TSSR Approved |  | 2024-02-02 | 2024-02-15 |  | 2024-02-29 |  | Closed | 2024-03-01 | 2024-03-06 | E//Sumitra | 2024-03-06 | BOQ_Celcom Digi_RAN-YPTT-Standard PR TSS-20240212 | DU00002861154 |  |  | 2024-05-14 | 2024-05-09 |  | In-Building System | 3m Bipod (RT) | 6 | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 1 | 0
3733A | Masjid Bandar Bukit Puchong 2 | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-22 | 2024-02-02 |  | 2024-04-19 |  | Closed | 2024-04-25 | 2024-04-26 | E//Razif | 2024-04-25 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240128 | DU00002861155 |  |  | 2024-05-09 | 2024-05-08 |  | Lampole | 24m Lampole | 24m | Add R9264H M901821 x3,Dismantle R8882 S1800B(B6B) x3++R8881 S2100 x3+ | 0 | 0
3739A | Wisma Mutiara Puchong | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-17 | 2023-11-22 |  | 2024-04-17 |  | Closed | 2024-04-19 | 2024-04-18 | E//Sumitra | 2024-04-18 | CelcomDigi_RAN_GTSB_TSS_20231119 | DU00002861156 |  |  | 2024-05-04 | 2024-05-04 |  | Wall mount boom | 3m Bipod (RT) | 5m | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 | 3 | 0
3974B | Taman Jelita | Central |  | Modernization |  | 2024 Q4 | CR | Magicell | 4.6 TSSR Approved |  | 2023-12-20 | 2023-12-27 |  | 2024-04-16 |  | Closed | 2024-04-17 | 2024-04-23 | E//Sumitra | 2024-04-23 | CelcomDigi_RAN_Magicell_TSS_Central_20231224 | DU00002861157 |  |  | 2024-08-23 | 2024-08-19 |  | In-Building System | 3m Bipod (RT) | 6 | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x2 | 23 | 0
7134A | Taman Mawar | Sabah |  | Modernization |  | 2024 Q4 | MS | Futong | 4.6 TSSR Approved |  | 2024-03-13 | 2024-03-19 |  | 2024-04-04 |  | Rectificating | 2024-04-24 | 2024-05-13 | E//Hannah | 2024-05-13 | Celcom Digi_RAN-Futong-Standard PR TSS-Sabah-20240313 | DU00002861158 |  |  | 2024-06-23 | 2024-06-18 |  | Unipole | 3m RT (Minimast) | 5 | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 23 | 0
3676A | PARAMONTSEAPARK1 | Central |  | Modernization |  | 2024 Q3 | IE | DATASCO | 4.6 TSSR Approved |  | 2024-04-06 | 2024-04-19 |  | 2024-04-22 |  | Closed | 2024-04-23 | 2024-04-24 | E//Kok Keen | 2024-04-24 | CelcomDigi_RAN_Datasco_TSS_Central_20231126 | DU00002861159 |  |  | 2024-05-25 | 2024-05-21 |  | Minimast | 3m Bipod (RT) | 6.5 | Add R9264M M1821 x3,Dismantle R8882 S1800(B) x3+R8882 S1800B(B6B) x3++R8881 S2100 x3+ | 0 | 0
3247B | Jln Tmn Melati (REL) | Central |  | Modernization |  | 2024 Q1 | XH | DATASCO | 4.6 TSSR Approved |  | 2023-11-04 | 2023-11-09 |  | 2023-11-16 |  | Closed | 2023-12-27 | 2023-12-28 | E//Kok Keen | 2023-12-28 | CelcomDigi_RAN_Datasco_TSS_Central_20231113 | DU00002861160 |  |  | 2024-04-02 | 2024-03-27 |  | In-Building System | 3m Boom (RT) | 6 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
9236B | Kpg Telian | Sarawak |  | Modernization |  | 2025 Q2 | AD | AllStar | 4.6 TSSR Approved |  | 2023-11-02 | 2023-11-07 |  | 2024-04-04 |  | Closed | 2024-04-05 | 2024-05-09 | E//Hannah | 2025-02-25 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20231214 | DU00002861161 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed | 2025-03-10 | 2025-03-07 |  | Monopole | 45m 3 Legged Tower | 30 | Reuse Existing RRU | 0 | 0
9218B | Taman Uni Samarahan | Sarawak |  | Modernization |  | 2024 Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-11-14 | 2024-03-27 |  | 2024-03-28 |  | Closed | 2024-04-03 | 2024-04-18 | E//Hannah | 2024-04-18 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231019 | DU00002861162 |  |  | 2024-06-12 | 2024-06-10 |  | Monopole | 30m Rapole | 15m | Add R9264M M1821 x4,Dismantle R8882 S1800B(B6B) x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3+R8894E M1821(A8A) x1 | 0 | 0
9118B | Kg Opar | Sarawak |  | Modernization | Modernization->On Hold->Modernization | 2026 | SM | Magicell | 4.6 TSSR Approved |  | 2024-01-18 | 2024-02-02 |  | 2025-02-07 |  | Rectificating | 2025-02-24 | 2025-02-28 | E//Hannah | 2025-02-28 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20240123 | DU00002861163 |  |  | 2025-04-27 | 2025-04-17 |  | Tower | Tower | 64M | Add R8894E M1821 x1 | 0 | 3
9207B | Samar Indah | Sarawak |  | Modernization |  | 2024 Q2 | ZB | Magicell | 4.6 TSSR Approved | 20/03_Digi has reached maximum RF capacity on site | 2023-10-21 | 2023-10-30 |  | 2023-12-15 |  | Closed | 2024-03-08 | 2024-06-12 | E//Hannah | 2024-06-12 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231024 | DU00002861164 |  |  | 2024-12-19 | 2024-11-18 |  | Monopole | 30m Rapole | 17 | Add R8862A S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 23 | 0
9208B | Kolej Alamanda | Sarawak |  | Modernization |  | 2024 Q2 | SH | AllStar | 4.6 TSSR Approved | 5/2 TSSR submitted with Bisector solution. AAU Cannot Install-Change MM to BI¦sacofa rampole not allow to add AAU | 2023-10-16 | 2023-10-18 |  | 2023-10-24 |  | Closed | 2024-02-05 | 2024-02-26 | E//Hannah | 2024-02-26 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20231017 | DU00002861165 |  |  | 2024-04-03 | 2024-03-26 |  | Monopole | 24m Lampole | 30 | Add R8894E M1821 x5+R8854 S2600 x1,Dismantle R8882 S1800(B) x3+R8862A S1800(B6A) x1+R8862A S2100(A6A) x4+R8862A S2600(A4A) x1 | 0 | 4
9209B | Kolej Bunga Raya | Sarawak |  | Modernization |  | 2024 Q2 | SH | AllStar | 4.6 TSSR Approved |  | 2023-10-17 | 2023-10-23 |  | 2023-11-06 |  | Closed | 2024-03-04 | 2024-03-11 | E//Hannah | 2024-03-08 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20231024 | DU00002861166 |  |  | 2024-03-27 | 2024-03-16 |  | Monopole | 30m Rapole | 30 | Add R8894E M1821 x6+R8854 S2600 x3,Dismantle R8882 S1800(B) x3+R8862A S2600(A4A) x3++R8881 S2100 x3+ | 0 | 123
9211B | Apple Green | Sarawak |  | Modernization |  | 2024 Q2 | SH | DATASCO | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦sacofa rampole not allow to add AAU | 2023-10-09 | 2023-10-23 |  | 2024-01-08 |  | Rectificating | 2024-03-07 | 2024-03-13 | E//Hannah | 2024-03-08 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231013 | DU00002861167 |  | Pending BBU & RRU Solution | 2024-04-26 | 2024-04-05 |  | Tower | 30m Rapole | 45 | Add R8862A S9000 x3+R8894E M1821 x2+R8854 S2600 x2,Dismantle R8862A S2600(A4A) x2 | 0 | 23
9267A | Kpg Selalang | Sarawak |  | Modernization |  | 2025 Q1 | AI | Trintel | 4.6 TSSR Approved |  | 2025-03-11 | 2025-03-20 |  | 2025-03-26 |  | Closed | 2025-03-27 | 2025-04-21 | E//Hannah | 2025-04-07 | SQ202503030411-Trintel | DU00002861168 |  |  | 2025-05-04 | 2025-04-15 |  | Tower | 45m 3 Legged Tower | 76 | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8882 S1800B(B6B)x3 | 0 | 0
1912B | SILK Sg Long KM12 | Central |  | Modernization |  | 2024 Q4 | SHA | YPTT | 4.6 TSSR Approved |  | 2024-04-16 | 2024-05-23 |  | 2024-05-29 |  | Closed | 2024-05-29 | 2024-06-07 |  | 2024-06-07 | CelcomDigi_RAN_YPTT_TSS_Central_20240513 | DU00002861169 |  |  | 2024-09-21 | 2024-06-21 |  | Tower | 60m 4 Legged Tower | 60 | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 3 | 0
9192B | Jalan Teo Chee Beng | Sarawak |  | Modernization |  | 2025 Q3 | HW | Trintel | 4.6 TSSR Approved |  | 2025-03-17 | 2025-04-04 |  | 2025-04-09 |  | Under Approval | 2025-04-10 | 2025-04-24 | E//Hannah | 2025-04-21 | SQ202503030411-Trintel | DU00002861170 |  |  | 2025-07-06 | 2025-05-29 |  | Tower | Tower | 106m | Add R8894E M1821x1 | 0 | 3
1826B | STC MMU | Central |  | Modernization |  | 2024 Q3 | MA | Magicell | 4.6 TSSR Approved |  | 2024-02-20 | 2024-02-27 |  | 2024-04-22 |  | Closed | 2024-05-08 | 2024-05-09 |  | 2024-05-09 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240225 | DU00002861171 |  |  | 2024-11-18 | 2024-07-12 |  | In-Building System | 3m RT (Wall Mounted Pole) | 3m | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8882 S1800(B) x3+R8854D S2100(A4A) x3 | 13 | 0
4676A | Taman saga | Northern |  | Decomm | Modernization->On Hold->Decomm | 2024 Q3(single site MOCN) | BY | GCI | 4.6 TSSR Approved |  | 2024-01-10 | 2024-01-19 | 2025-04-04 |  | 2025-04-09 |  | 2024-05-09 | 2024-06-05 | E//Hazida | 2024-06-05 | Celcom Digi_RAN-GCI-TSS-Northern-20240116-0089/0823CD-Northern-GCI-BOQ Template(new contract) | DU00002861172 |  |  |  |  | 2024-11-28 | Pole | 60m 4 Legged Tower | 6
3620B | Desa Bakti Flyover | Central |  | Modernization |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-10-30 | 2023-11-09 |  | 2024-03-27 |  | Under Approval | 2024-03-28 | 2024-10-22 | E//Sumitra | 2024-10-22 | CelcomDigi_RAN_Datasco_TSS_Central_20231101 | DU00002861173 |  |  | 2024-08-21 | 2024-08-21 |  | BillBoard | Billboard | 5m | Add R8894E M1821 x5,Dismantle R8862A S1800(B6A) x5+R8854D S2100(A4A) x5 | 0 | 12
3631B | Kuchai Business Centre | Central |  | Modernization |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-01-12 | 2024-01-30 |  | 2024-02-09 |  | Closed | 2024-04-01 | 2024-04-15 | E//Sumitra | 2024-04-08 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240115 | DU00002861174 |  |  | 2024-05-11 | 2024-05-08 |  | Pole | Rooftop | 6m | Add R8862A S9000 x3+R8854E S1800 x3+R9224E M1821 x3,Dismantle R8894E M1821(A8A) x3
3880B | Surau Al-Abqori | Central |  | Modernization |  | 131 single site mocn | SHA | YPTT | 4.6 TSSR Approved |  | 2024-05-10 | 2024-05-23 |  | 2024-05-31 |  | Closed | 2024-06-04 | 2024-06-12 | E//Sumitra | 2024-06-11 | CelcomDigi_RAN_YPTT_TSS_Central_20240513 | DU00002861175 |  |  | 2024-08-21 | 2024-08-19 |  | Lampole | 24m Lampole | 25m | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8882 S1800B(B6B) x3++R8881 S2100 x3+ | 3 | 0
3683B | Century Square | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-03-06 | 2024-03-11 |  | 2024-04-22 |  | Closed | 2024-09-18 | 2024-09-19 | E//Razif | 2024-09-19 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240311 | DU00002861176 |  |  | 2025-07-25 | 2025-07-21 |  | Unipole | 24m Lampole | 4 | Add R8894E M1821x3+R8862A S2601 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2600(A4A) x3 | 0 | 0
3874B | Persiaran Ceria | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-15 | 2023-11-16 |  | 2024-04-26 |  | Closed | 2024-07-09 | 2024-07-18 | E//Razif | 2026-04-17 | CelcomDigi_RAN_GTSB_TSS_Central_20231116 | DU00002861177 |  |  | 2024-12-10 | 2024-12-06 |  | H-bracket pole | 3m Bipod (RT) | 6 | Add R8862A S9000x3+R8894E M1821x4, Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3 | 0 | 1
3238B | Wisma MK | Central |  | Decomm | Modernization>On Hold->Decomm | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-03-08 | 2024-03-15 | 2025-06-18 | 2024-04-22 | 2025-06-23 | Under Approval | 2024-07-02 | 2024-07-18 | E//Razif | 2025-07-03 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240311 | DU00002861178 | SOW Changed from Mod to Decomm | SOW Changed from Modernization to Decomm |  |  | 2025-07-17 | In-Building System | 3m Boom (RT) | 5 | Add R8862A S9000x3+R8894E M1821x3+A9732 M1821x1, Dismantle R8882 S1800B(B6B)x3+R8862A S2100(A6A)x3 | 1 | 2
2246A | RMC | Central |  | Modernization |  | 2024 Q3 | CR | Magicell | 4.6 TSSR Approved |  | 2023-11-27 | 2023-12-01 |  | 2024-03-21 |  | Closed | 2024-03-22 | 2024-04-04 | E//Sumitra | 2024-04-03 | CelcomDigi_RAN_Magicell_TSS_Central_20231201 | DU00002861179 |  |  | 2024-06-10 | 2024-06-07 |  | Monopole | 45m Monopole | 45M | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 13 | 0
3965B | Surau An-Naim Samudra | Central |  | Modernization |  | 2024 Q1 | SS | Magicell | 4.6 TSSR Approved |  | 2023-12-01 | 2023-12-04 |  | 2023-12-29 |  | Closed | 2024-01-02 | 2024-01-03 | E//Kok Keen | 2024-01-03 | CelcomDigi_RAN_Magicell_TSS_Central_20231203 | DU00002861180 |  |  | 2024-03-30 | 2024-03-22 |  | Monopole | 30m Monopole | 20 | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
3967B | Bandar Mahkota Cheras 2 | Central |  | Modernization |  | 2024 Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2024-04-30 | 2024-05-02 |  | 2024-05-08 |  | Closed | 2024-10-04 | 2024-10-11 | E//Sumitra | 2024-10-11 | CelcomDigi_RAN_YPTT_TSS_Central_20240513 | DU00002861181 |  |  | 2025-07-03 | 2025-07-01 |  | Monopole | 40m Monopole | 45m | Add R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
7955A | RNR Langkon | Sabah |  | Modernization |  | 2025 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2025-02-06 | 2025-01-28 |  | 2025-02-18 |  | Under Approval | 2025-03-03 | 2025-03-24 | E//Hannah | 2025-03-16 | SQ202501030028 - GTSB | DU00002861182 | Remarks: Solution TSSR/BOM Changed |  | 2025-04-04 | 2025-03-18 |  | Monopole | 30m Monopole | 30 | Add R8852E S9000x1+R8894E M1821x1+R8854 S2600x1 | 0 | 0
3697B | Jalan Cengal 2 (REL) | Central |  | Modernization |  | 2024 Q1 | CR | GCI | 4.6 TSSR Approved |  | 2023-11-03 | 2023-11-06 |  | 2024-01-02 |  | Closed | 2024-01-02 | 2024-01-03 | E//Kok Keen | 2024-01-03 | CelcomDigi_RAN_GCI_TSS_Central_20231104 | DU00002861183 |  |  | 2024-03-30 | 2024-03-28 |  | Lampole | 24m Lampole | 24 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
7278B | Cenderawasih | Sabah |  | Modernization |  | 2024 Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-10-26 | 2023-12-19 |  | 2024-07-17 |  | Closed | 2024-07-18 | 2024-07-19 | E//Hannah | 2024-07-19 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231028 | DU00002861184 |  |  | 2024-08-14 | 2024-08-10 |  | Lampole | 30m Monopole | 30 | Add A9732 M1821 x1,Dismantle R8894E M1821(A8A) x1 | 3 | 0
4738A | BERAS TERBAKAR (REL) | Northern |  | Modernization | Modernization->On Hold->Modernization | 154 single site MOCN | SHA | GTSB | 4.6 TSSR Approved |  | 2024-09-03 | 2024-09-09 |  | 2024-09-13 |  | Under Approval | 2024-09-20 | 2024-10-01 | E//Vijay | 2024-09-23 | 0809CD-Northern-GTSB-BOQ Template(new contract) | DU00002861185 |  |  | 2024-11-13 | 2024-11-09 |  | Monopole | 30m Monopole | 46M | Add R8852E S9000 x3+R8894E M1821 x2+A9732 M1821 x1,Dismantle R8882 S1800(B) x2+R8882 S1800B(B6B) x1+R8854D S2100(A4A) x3 | 2 | 0
3450B1 | pBTS Bukit Merah (HW) | Northern |  | Modernization | Modernization->On Hold->Modernization | 2025 Q1 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-11-29 | 2023-11-02 |  | 2025-02-06 |  | Rectificating | 2025-02-10 | 2025-02-24 | E//Hazida | 2025-02-21 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231130-0074 | DU00002861186 |  |  | 2025-02-19 | 2025-02-19 |  | Watertank | 25m pBTS | 24m | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8882 S1800(B)x3+R8854D S2100(A4A)x3 | 0 | 0
4035C | Changkat Ibol | Northern |  | Modernization |  | 2024 Q2 | BY | GCI | 4.6 TSSR Approved | ¦ 0228 - Listed for solution change, pending confirmed solution | 2023-10-19 | 2023-10-23 |  | 2024-01-09 |  | Closed | 2024-03-08 | 2024-03-13 | E//Hazida | 2024-03-11 | Celcom Digi_RAN-GCI-TSS-Northern-20231019-0062 | DU00002861187 |  |  | 2024-04-05 | 2024-03-30 |  | Tower | 4 Legged Tower | 63 | Add R8852E S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882 S1800B(B6B) x3+R8854D S2100(A4A) x3+R8862A S2600(A4A) x1 | 0 | 3
4191C | Kg Singkir | Northern |  | Modernization |  | 154 single site MOCN | SHA | GCI | 4.6 TSSR Approved |  | 2024-03-03 | 2024-02-27 |  | 2024-08-16 |  | Under Approval | 2024-09-03 | 2024-09-06 | E//Ajay | 2024-09-05 | Celcom Digi_RAN-GCI-TSS-Northern-20240303-0099 | DU00002861188 |  |  | 2024-08-28 | 2024-08-27 |  | Lampole | 30m Lampole | 30m | Add R9264H M901821 x3+R8854 S2600 x1,Dismantle R8862A S2601(A6A) x1+R8892E M1821(BAA) x3 |  | 3
3837A | Lekas2 | Central |  | Modernization |  | 2024 Additional | AI | DATASCO | 4.6 TSSR Approved |  | 2024-09-02 | 2024-09-25 |  | 2024-11-20 |  | Closed | 2024-12-18 | 2024-12-27 | E//Sumitra | 2024-12-27 | CelcomDigi_RAN_Datasco_TSS_Central_20231224 | DU00002861189 |  |  | 2024-12-13 | 2024-12-10 |  | Tower | Tower | 30 | Add R8852E S9000 x3+R8894E M1821 x1+R8862A S2601 x1 | 0 | 0
4579B | Kg Jerlun RCC | Northern |  | Modernization |  | 2025 Q3 | AD | GCI | 4.6 TSSR Approved |  | 2023-10-17 | 2023-10-18 |  | 2025-02-24 |  | Under Approval | 2023-10-25 | 2023-10-27 | E//Hazida | 2025-04-21 | Celcom Digi_RAN-GCI-TSS-Northern-20231018-0061 | DU00002861190 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed | 2025-05-20 | 2025-05-15 |  | Tower | Tower | 60M | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8862A S1800(B6A)x1+R8862A S2100(A6A)x1+R8892E M1821(BAA)x2 | 0 | 0
3724B | Persiaran Mahkota Cheras | Central |  | Modernization |  | 2024 Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2024-04-25 | 2024-04-26 |  | 2024-05-08 |  | Closed | 2024-05-09 | 2024-05-15 | E//Sumitra | 2024-05-15 | CelcomDigi_RAN_YPTT_TSS_Central_20240513 | DU00002861191 |  |  | 2024-07-19 | 2024-07-16 |  | In-Building System | 3m Bipod (RT) | 6 | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 | 0 | 0
7945A | Tanjung Batu | Sabah |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q3 | AD | GTSB | 14.0 TSSR Not Required (Reuse Existing BBU/RRU) |  | 2025-01-23 | 2025-04-07 |  | 2025-04-13 |  | Under Approval | 2025-04-14 |  | E//Hannah |  | SQ202501030028 - GTSB | DU00002861192 | [5 empty] | Tower | Tower | 60 | Reuse Existing RRU | 0 | 0
9250B | Kg Sungai Alo | Sarawak |  | Modernization |  | 2025 Q2 | SM | AllStar | 4.6 TSSR Approved | AAU Cannot Install-S3 MM change to BI¦sacofa lampole not allow to add AAU | 2023-11-02 | 2023-11-02 |  | 2024-04-02 |  | Closed | 2024-04-03 | 2024-06-13 | E//Hannah | 2025-02-28 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20231214 | DU00002861193 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed | 2025-03-10 | 2025-03-08 |  | Monopole | 30m Rapole | 30 | Add R8894E M1821x1 | 0 | 3
9254B | Kanowit Town 1 | Sarawak |  | Modernization |  | 2025 Q3 | AI | Trintel | 4.6 TSSR Approved |  | 2025-03-04 | 2025-03-13 |  | 2025-03-19 |  | Closed | 2025-03-27 | 2025-05-23 | E//Hannah | 2025-05-23 | SQ202503030411-Trintel | DU00002861194 | Remarks: Solution TSSR/BOM Changed |  | 2025-06-30 | 2025-06-24 |  | Tower | Tower | 46 | Add R8894E M1821x2 | 0 | 23
9612A | Taman Cahaya Indah | Sarawak |  | Modernization |  | 2025 Q1 | SH | Magicell | 4.6 TSSR Approved |  | 2023-10-12 | 2023-10-13 |  | 2023-10-23 |  | Closed | 2024-04-15 | 2024-04-18 | E//Hannah | 2025-01-02 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231013 | DU00002861195 | Remarks: Solution TSSR/BOM Changed |  | 2025-04-30 | 2025-04-09 |  | Monopole | Rapole | 30M | Add R8894E M1821x4+R8854 S2600x1, Dismantle R8882 S1800B(B6B)x3+R8862A S2100(A6A)x3+R8862A S2600(A4A)x1 | 0 | 3
4440C | UTP | Northern |  | Modernization |  | 2024 Q2 |  | CCSMY | 4.6 TSSR Approved | ¦ 0228 - Listed for solution change, pending confirmed solution | 2024-01-09 | 2024-01-15 |  | 2024-01-18 |  | Closed | 2024-01-23 | 2024-01-29 | E//Hazida | 2024-01-25 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240110-0085 | DU00002861196 |  |  | 2024-05-20 | 2024-03-13 |  | Lampole | 30m Lampole | 30m | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
9221B | Samarax | Sarawak |  | Modernization |  | 2024 Q2 | SH | AllStar | 4.6 TSSR Approved |  | 2023-10-12 | 2023-10-19 |  | 2023-11-02 |  | Closed | 2024-03-06 | 2024-03-08 | E//Hannah | 2024-03-08 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20231013 | DU00002861197 |  |  | 2024-07-18 | 2024-06-10 |  | Monopole | Rapole | 15 | Add R8862A S9000 x3+R8894E M1821 x5+R8854 S2600 x2,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3+R8862A S2600(A4A) x2 | 0 | 23
9256B | RPR Banting | Sarawak |  | Modernization |  | 2024 Q4(single site MOCN)-L21 SSM | SHA | Magicell | 4.6 TSSR Approved |  | 2024-10-27 | 2024-10-30 |  | 2024-11-05 |  | Under Approval | 2024-11-06 | 2024-11-11 | E//Syahriani | 2024-11-07 | CelcomDigi_RAN_Magicell_PR_TSS_Sarawak_20241031 | DU00002861198 |  |  | 2025-02-28 | 2024-12-05 |  | Lampole | 30m Monopole | 30 | Add R8894E M1821 x3 | 0 | 123
4201C | Istana Kuala Kangsar | Northern |  | Modernization |  | 2025 Q3 | HW | GTSB | 4.6 TSSR Approved |  | 2023-10-12 | 2023-10-16 |  | 2025-02-19 |  | Under Approval | 2023-10-25 | 2023-10-27 | E//Hazida | 2025-04-25 | Celcom Digi_RAN-GTSB-TSS-Northern-20231013-0048 | DU00002861199 |  | Remarks: Solution Changed | 2025-05-21 | 2025-05-17 |  | Monople Tree | 30m Monopole | 45 | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8882 S1800B(B6B)x3+R8881 S2100x3 | 0 | 0
4728A | UITM Perlis Fact | Northern |  | Modernization |  | 2024 Q4 | SM | YPTT | 4.6 TSSR Approved |  | 2023-12-05 | 2023-12-07 |  | 2024-04-22 |  | Rectificating | 2024-04-30 | 2024-05-02 | E//Hazida | 2024-05-01 | Celcom Digi_RAN-YPTT-TSS-Northern-20231225-0047 | DU00002861200 |  |  | 2024-05-25 | 2024-05-17 |  | Lampole | Tower | 30 | Add R8862A S9000 x3+R8894E M1821 x5+R8854 S2600 x2,Dismantle R8862A S1800(B6A) x3+R8862A S2600(A4A) x2++R8881 S2100 x3+ | 0 | 12
4319A | kgsahom | Northern |  | Modernization |  | 2024 Additional | SM | CCSMY | 4.6 TSSR Approved |  | 2024-11-19 | 2024-11-21 |  | 2024-11-25 |  | Rectificating | 2024-11-29 | 2024-12-16 | E//Hazida | 2024-12-15 | 1911CD-Northern-TSS-BOQ Template(new contract)_CCSMY_V2 | DU00002861201 |  |  | 2024-12-09 | 2024-12-09 |  | Tower | Tower | 75m | Add R8852E S9000 x3+R8894E M1821x4+R8854 S2600x1, Dismantle R8862A S1800(B6A)x3+R8862A S2600(A4A)x2 | 0 | 2
7598A | Durian Tunjung | Sabah |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | AD | Datasco | 4.6 TSSR Approved |  | 2024-06-11 | 2024-07-06 |  | 2024-11-01 |  | Under Approval | 2024-11-04 | 2024-11-07 | E//Hannah | 2024-11-06 | 0920CD-Sabah-Datasco-BOQ Template (old contract) | DU00002861202 |  |  | 2025-01-20 | 2025-01-17 |  | Tower | 30m Monopole | 45 | Add R8862A S9000x3+R8894E M1821x3, Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3 | 0 | 0
3023C | UKM Water Tank(JBA) (REL) | Central |  | Modernization |  | 2024 Additional | BY | YPTT | 4.6 TSSR Approved |  | 2023-11-06 | 2023-11-10 |  | 2024-11-23 |  | Closed | 2024-11-25 | 2024-11-26 | E//Sumitra | 2024-11-26 | CelcomDigi_RAN_YPTT_TSS_Central_20231112 | DU00002861203 | Remarks: Solution TSSR/BOM Changed |  | 2025-03-03 | 2025-02-17 |  | Monopole | 24m Lampole | 24 | Add R8852E S9000 x3+R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
3173C | Jalan Awan Jawa (REL) | Central |  | Modernization |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-12-12 | 2023-12-15 |  | 2024-01-03 |  | Closed | 2024-04-02 | 2024-04-15 | E//Sumitra | 2024-04-09 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231213 | DU00002861204 |  |  | 2024-05-21 | 2024-05-18 |  | Lampole | 18m Lampole | 18 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3 | 0 | 0
7343B | Kg Kebayu | Sabah |  | Remote MOCN | Modernization->On Hold->Modernization->Remote MOCN | 2025 Q3 | AD | AllStar | 4.1 Pending TSSR Submission - Subcon |  | 2023-12-01 | 2024-01-16 |  |  |  | To be Submitted |  |  |  |  | SQ202501020323 - All Star | DU00002861205 | [5 empty] | Tower | 45m 3 Legged Tower | 76 | Reuse Existing RRU | 0 | 0
7983B | Kinabalu National Park (Celcom) | Sabah |  | Modernization |  | 2025 Q3 | AD | Futong | 4.6 TSSR Approved | Subcon captured single power incoming info during TSS | 2023-11-01 | 2023-11-03 |  | 2025-02-14 |  | Under Approval | 2025-02-24 | 2025-03-09 | E//Hannah | 2025-02-26 | Celcom Digi_RAN-Futong-TSS-Sabah-20231107 | DU00002861206 |  |  | 2025-03-27 | 2025-03-26 |  | Monople Tree | 45m 3 Legged Tower | 46 | Add R8894E M1821x3, Dismantle R8862A S1800(B6A)x3 | 0 | 0
2442A | AU1 Setiawangsa | Central |  | Modernization |  | 2024 Q1 | CR | GCI | 4.6 TSSR Approved | AAU Cannot Install-S2 MM change to BI¦Minimast cant install AAU | 2023-11-20 | 2023-11-20 |  | 2024-02-28 |  | Closed | 2024-01-04 | 2024-01-09 | E//Sumitra | 2024-01-09 | CelcomDigi_RAN_GCI_TSS_Central_20231126 | DU00002861207 |  |  | 2024-05-07 | 2024-05-04 |  | In-Building System | 3m RT (Minimast) | 6m | Add R8862A S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3+R8882 S2600(B4A) x1 |  | 2
9196B | Mukah Score | Sarawak |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q2 | ZB | AllStar | 4.6 TSSR Approved |  | 2023-12-12 | 2023-12-14 |  | 2024-03-27 |  | Closed | 2024-03-27 | 2024-04-04 | E//Hannah | 2024-04-04 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20231214 | DU00002861208 | [5 empty] | Monopole | 45m 3 Legged Tower | 30 | Reuse Existing RRU | 0 | 0
3222C | Seksyen 1 Lestari Perdana | Central |  | Modernization |  | 2024 Q3 | CR | GCI | 4.6 TSSR Approved |  | 2024-01-16 | 2024-03-14 |  | 2024-04-23 |  | Closed | 2024-04-29 | 2024-05-27 | E//Sumitra | 2024-05-27 | CelcomDigi_RAN_GCI_TSS_Central_20240124 | DU00002861209 |  |  | 2024-06-05 | 2024-06-04 |  | Lampole | 24m Lampole | 30 | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 12 | 0
3152C | Jalan Fauna Cyberjaya | Central |  | Modernization |  | 2024 Q3 | BY | Magicell | 4.6 TSSR Approved |  | 2024-05-03 | 2024-05-13 |  | 2024-05-21 |  | Closed | 2024-10-09 | 2024-10-14 | E//Razif | 2024-10-11 | CelcomDigi_RAN_Magicell_TSS_Central_20240424 | DU00002861210 |  |  | 2025-09-12 | 2024-10-22 |  | In-Building System | 3m Boom (RT) | 6m | Add R9264H M901821 x4+R8862A S2601 x4,Dismantle R8862A S9000(A6A) x4+R8862A S1800(B6A) x4+R8862A S2100(A6A) x3+R8862A S2601(A6A) x4 | 0 | 0
4036C | Tmn Kaya | Northern |  | Modernization |  | 2024 Q2 | ZA | GCI | 4.6 TSSR Approved | ¦ 0228 - Listed for solution change, pending confirmed solution | 2023-10-23 | 2023-10-31 |  | 2024-02-09 |  | Closed | 2024-03-05 | 2024-03-05 | E//Ajay | 2024-03-05 | Celcom Digi_RAN-GCI-TSS-Northern-20231026-0066 | DU00002861211 |  |  | 2024-04-05 | 2024-03-30 |  | Tower | Tower | 68 | Add R8852E S9000 x3+A9732 M1821 x3,Dismantle R8862A S1800(B6A) x3 | 123 | 0
3257C | Ampang Park 2 (REL) | Central |  | Modernization |  | 2024 Q1 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-12-16 | 2023-12-20 |  | 2023-12-29 |  | Closed | 2024-01-02 | 2024-01-05 | E//Sumitra | 2024-01-04 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231224 | DU00002861212 |  |  | 2024-07-14 | 2024-07-10 |  | Lampole | 18m Lampole | 18 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
2424A | PUAS Tmn Tun Perak | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4(single site MOCN)-L26 SSM |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002861213 | [6 empty] | 30m Monopole Tree |  |  | 23
3230C | Sri Rampai | Central |  | Modernization |  | 2024 Q1 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-09 | 2023-11-14 |  | 2024-01-04 |  | Rectificating | 2024-01-04 | 2024-01-05 | E//Sumitra | 2024-01-05 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231113 | DU00002861214 |  |  | 2024-04-26 | 2024-04-22 |  | Lampole | 18m Lampole | 18 | Add R8894E M1821 x4+R8854 S2600 x1,Dismantle R8862A S2600(A4A) x1+R8892E M1821(BAA) x3 |  | 1
7527A | Kalatuan-Keningau Junction | Sabah |  | Modernization |  | 2025 Q2 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2023-11-01 | 2024-06-06 |  | 2025-01-22 |  | Under Approval | 2025-02-17 | 2025-03-09 | E//Hannah | 2025-02-26 | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231221 | DU00002861215 |  |  | 2025-06-30 | 2025-03-05 |  | Tower | Tower | 60 | Add R8852E S9000x2+R8894E M1821x3, Dismantle R8862A S1800(B6A)x3 | 0 | 0
7306A4 | pBTS Kota Marudu (C) | Sabah |  | Site Out (Modernization) | Modernization->On Hold->Site Out->Site Out (Modernization) | 2025 Q3 |  | YPTT | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2025-07-01 |  | 2025-06-30 |  |  | To be Submitted |  |  |  |  | SQ202506160230 - YPTT | DU00002861216 | [6 empty] | 25m pBTS
3292C | Kinrara Residences (REL) | Central |  | Modernization |  | 2024 Q3 | SY1 | GCI | 4.6 TSSR Approved | AAU Cannot Install-S23 MM change to BI¦Maxis rejected to add antenna | 2023-11-09 | 2023-11-10 |  | 2024-05-10 |  | Closed | 2024-12-16 | 2024-12-17 | E//Sumitra | 2024-12-17 | CelcomDigi_RAN_GCI_TSS_Central_20231113 | DU00002861217 | Remarks: Solution TSSR/BOM Changed |  | 2025-01-16 | 2025-01-13 |  | Monopole | 30m Monopole Tree | 30 | Add R9264H M901821+R8854 S2600x3, Dismantle R8862A S2600(A4A)x3 | 0 | 123
3270C | Stadium Bukit Jalil Parking (REL) | Central |  | Modernization |  | 2024 Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2024-02-28 | 2024-03-07 |  | 2024-04-02 |  | Under Approval | 2024-04-03 | 2024-07-16 | E//Sumitra | 2024-07-16 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240303 | DU00002861218 |  |  | 2024-07-25 | 2024-07-05 |  | BillBoard | Billboard | 6 | Add R9264M M1821 x3+A9732 M1821 x1,Dismantle R8862A S1800(B6A) x4+R8862A S2100(A6A) x4 | 3 | 0
9277A | Desa Pabahanan | Sarawak |  | Modernization |  | 2025 Q2 | SM | Datasco | 4.6 TSSR Approved |  | 2024-02-27 | 2024-04-23 |  | 2025-02-03 |  | Rectificating | 2025-02-26 | 2025-03-19 | E//Hannah | 2025-03-19 | Celcom Digi_RAN-Datasco-Standard PR TSS-Sarawak-20240302 | DU00002861219 |  |  | 2025-07-06 | 2025-06-14 |  | Lampole | 30m Rapole | 30 | Add R9264M M1821x2+A9732 M1821x1, Dismantle R8894E M1821(A8A)x3 | 1 | 23
2402A | PUAS Kesuma Lakes (KJS) | Central |  | Modernization |  | 2024 Additional | AI | DATASCO | 4.6 TSSR Approved |  | 2024-08-21 | 2024-08-10 |  | 2024-11-27 |  | Under Approval | 2024-12-27 | 2024-12-27 | E//Sumitra | 2024-12-27 | CelcomDigi_RAN_Datasco_TSS_Central_20231224 | DU00002861220 |  |  | 2024-12-20 | 2024-12-16 |  | Tower | 45m Tower | 45 | Add R8894E M1821 x5,Dismantle R8854E S1800(A6A) x4+R8854D S2100(A4A) x4 | 0 | 2
9505B | TM Sematan | Sarawak |  | Modernization |  | 2024 Q2 | SH | Magicell | 4.6 TSSR Approved |  | 2024-01-11 | 2024-01-16 |  | 2024-01-19 |  | Closed | 2024-03-09 | 2024-03-11 | E//Hannah | 2024-03-11 | Celcom Digi_RAN-Magicell-Standard PR TSS-Sarawak-20240116 | DU00002861221 |  |  | 2024-05-24 | 2024-05-16 |  | Tower | Tower | 67M | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle | 0 | 3
9280A | Kampung Seberang Baru | Sarawak |  | Modernization |  | 2025 Q2 | AI | Magicell | 4.6 TSSR Approved |  | 2024-01-23 | 2024-02-06 |  | 2025-02-07 |  | Closed | 2025-02-07 | 2025-06-13 | E//Hannah | 2025-06-11 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20240123 | DU00002861222 | Remarks: Solution TSSR/BOM Changed |  | 2025-09-08 | 2025-09-03 |  | Monopole | 30m Monopole | 30m | Add A9732 M1821x1, Dismantle R8894E M1821(A8A)x1 | 1 | 0
9300A | Celcom Simpang KJD | Sarawak |  | Modernization |  | 2025 Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2023-12-04 | 2023-12-07 |  | 2025-02-05 |  | Closed | 2025-02-06 | 2025-02-27 | E//Hannah | 2025-02-18 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20231206 | DU00002861223 |  |  | 2025-03-13 | 2025-03-11 |  | Tower | Tower | 45 | Reuse Existing RRU | 0 | 0
9312B | Shun Lee Garden (JPJ Kuching) | Sarawak |  | Modernization |  | 2024 Q4(single site MOCN)-L21 SSM | ZB | Magicell | 4.6 TSSR Approved | 17-4 - New solution BI Sector 1 updated in ML List & TSSR 15-3 - ZTE planner to update slide ¦ AAU Cannot Install-Change MM to BI¦sacofa rampole not allow to add AAU | 2023-10-13 | 2023-10-16 |  | 2023-11-01 |  | Closed | 2024-05-02 | 2024-10-24 | E//Hannah | 2024-10-24 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231016 | DU00002861224 | NIC_S1_Change MM to BI_owner reject_SACOFA SDN BHD |  | 2024-11-20 | 2024-11-16 |  | Monopole | Tower | 30M | Add R8894E M1821 x5,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 | 0 | 13
9420B | Kompleks Tentera Kuching | Sarawak |  | Modernization |  | 2024 Q2 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-11-16 | 2023-11-20 |  | 2023-12-15 |  | Closed | 2024-03-11 | 2024-03-13 | E//Hannah | 2024-03-12 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231119 | DU00002861225 |  |  | 2024-06-23 | 2024-06-19 |  | Tower | 30m Rapole | 31M | Add R8862A S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R8862A S2600(A4A) x1 | 0 | 1
9933A | Taman Interhill | Sarawak |  | Modernization |  | 2025 Q1 | AI | Trintel | 4.6 TSSR Approved |  | 2023-11-08 | 2023-11-14 |  | 2025-02-11 |  | Closed | 2025-02-14 | 2025-02-27 | E//Hannah | 2025-02-24 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231107 | DU00002861226 |  |  | 2025-03-26 | 2025-03-14 |  | Monopole | 30m Rapole | 13m | Add R9264M M1821x3, Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3 | 0 | 0
9946A | Kan Jia Garden | Sarawak |  | Modernization |  | 2025 Q1 | SH | Trintel | 4.6 TSSR Approved |  | 2023-10-10 | 2023-10-16 |  | 2023-10-23 |  | Closed | 2023-10-23 | 2023-11-15 | E//Hannah | 2023-11-08 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231013 | DU00002861227 |  |  | 2023-11-21 | 2023-11-02 |  | Monopole | 30m Rapole | 30 | Add R9264M M1821 x4+R8862A S2601 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 2
7559B | Kg Kolapis Beluran | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-04-11 |  | 2025-04-15 |  | 2025-04-21 | To be Submitted | 2025-04-25 | 2026-04-01 | E//Hannah | 2025-07-14 | SQ202504100583 - Futong | DU00002861228 |  |  |  |  | 2025-06-18 |  | 45m 3 Legged Tower
7560B | Batu 36 Sandakan | Sabah |  | Modernization |  | 2024 Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2024-04-04 | 2024-04-20 |  | 2024-05-10 |  | Closed | 2024-05-14 | 2024-06-24 | E//Hannah | 2024-06-24 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240406 | DU00002861229 |  |  | 2024-07-17 | 2024-07-13 |  | Tower | 45m 3 Legged Tower | 60m | Add R8862A S9000 x3+R8894E M1821 x2+R8854 S2600 x2,Dismantle R8862A S2601(A6A) x2 |  | 23
9540B | Kg Krokong | Sarawak |  | Modernization |  | 2024 Q2 | ZB | Datasco | 4.6 TSSR Approved |  | 2024-01-22 | 2024-02-02 |  | 2024-02-28 |  | Closed | 2024-03-18 | 2024-04-03 | E//Hannah | 2024-04-03 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20240124 | DU00002861230 |  |  | 2024-05-24 | 2024-05-07 |  | Tower | Tower | 76 | Add R8894E M1821 x2+R8854 S2600 x2 |  | 23
9542B | Kampung Git | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q1 | HW | Magicell | 4.6 TSSR Approved |  | 2025-02-22 |  | 2025-03-06 |  | 2025-04-15 |  | 2025-04-17 | 2025-10-28 | E//Hannah | 2025-05-29 | SQ202502050300-Magicell/SQ202502270609-Magicell | DU00002861231 |  |  |  |  | 2025-07-25 |  | Tower
9955A | Lapok Tinjar | Sarawak |  | Decomm | Decomm->On Hold->Decomm->On Hold->Decomm | 2025 Q3 | HW | Trintel | 4.6 TSSR Approved |  | 2025-03-04 |  | 2025-05-06 |  | 2025-05-10 | To be Submitted | 2025-05-14 | 2026-05-12 | E//Hannah | 2025-05-20 | SQ202502050142-Trintel | DU00002861232 |  |  |  |  | 2025-11-25 |  | Tower
9527B | Kpg Sri Tajo 2 | Sarawak |  | Modernization |  | 2024 Q2 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-10-23 | 2023-10-27 |  | 2023-12-14 |  | Closed | 2024-01-16 | 2024-01-22 | E//Hannah | 2024-01-19 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231024 | DU00002861233 |  |  | 2024-04-01 | 2024-03-27 |  | Monopole | Tower | 30 | Add R8862A S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3+R8862A S2600(A4A) x1 | 0 | 2
9515B | Kampung Lebur | Sarawak |  | Modernization |  | 2025 Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2023-10-17 | 2023-10-26 |  | 2024-04-15 |  | Closed | 2024-04-17 | 2025-03-10 | E//Hannah | 2025-03-04 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231019 | DU00002861234 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed | 2025-03-25 | 2025-03-11 |  | Tower | Tower | 77m | Add R8862A S9000x3+R9224E M1821 x3+R8862A S2601x1,Dismantle R8882 S1800B(B6B) x3+R8862A S2600(A4A) x2 | 0 | 0
9518B | Kampung Ensebang | Sarawak |  | Modernization |  | 2025 Q3 | AD | Magicell | 4.6 TSSR Approved |  | 2023-10-16 | 2023-10-24 |  | 2023-11-07 |  | Closed | 2024-04-17 | 2024-04-24 | E//Hannah | 2025-03-04 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231017 | DU00002861235 |  | Remarks: Solution Changed | 2025-06-28 | 2025-02-24 |  | Tower | Tower | 60 | Add R8862A S9000 x3+R9224E M1821 x3+R8862A S2601 x1,Dismantle R8882 S1800B(B6B) x3+R8854D S2100(A4A) x3+R8862A S2600(A4A) x1 | 0 | 0
9536B | Jalan Durin Kiba | Sarawak |  | Decomm, MOCN By Other Vendor | Decomm->On Hold->Decomm->On Hold->Decomm | 2025 | SH | Trintel | 4.6 TSSR Approved |  | 2023-12-21 |  |  |  | 2024-01-04 |  | 2024-02-19 | 2025-10-31 | E//Hannah | 2025-10-23 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231221 | DU00002861236 |  | Please provide clear label |  |  | 2025-12-29 |  | Tower
9959A | Beliau Ahad Sibuti | Sarawak |  | Modernization |  | 2025 Q2 | AI | Magicell | 4.6 TSSR Approved |  | 2024-05-10 | 2024-05-16 |  | 2025-02-12 |  | Closed | 2025-02-22 | 2025-02-27 | E//Hannah | 2025-02-27 | Celcom Digi_RAN-Magicell-Standard PR TSS-Sarawak-20240425 | DU00002861237 |  |  | 2025-07-06 | 2025-03-24 |  | Tower | Tower | 76 | Add R8894E M1821x1 | 0 | 2
3546C | Kampung Tasik Permai | Central |  | Modernization |  | 2024 Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-12-01 | 2023-12-07 |  | 2024-06-14 |  | Closed | 2024-06-18 | 2024-06-25 | E//Sumitra | 2024-06-25 | CelcomDigi_RAN_GTSB_TSS_Central_20231203 | DU00002861238 |  |  | 2024-07-17 | 2024-07-17 |  | Lampole | 24m Lampole | 24 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
4776A | Lambai Jerai | Northern |  | Decomm | Modernization->On Hold->Decomm | 2024 Q3(single site MOCN) | HW | GCI | 4.6 TSSR Approved |  | 2024-01-05 | 2024-01-09 | 2025-02-27 |  | 2025-03-13 |  | 2025-04-25 | 2024-05-10 | E//Hazida | 2025-04-28 | Celcom Digi_RAN-GCI-TSS-Northern-20240116-0089/0823CD-Northern-GCI-BOQ Template(new contract) | DU00002861239 |  |  |  |  | 2024-11-16 | Lampole | 24m Lampole | 24
3386C | Dataran Pandan Prima (REL) | Central |  | Modernization |  | 2024 Q2 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-12-06 | 2023-12-12 |  | 2024-01-19 |  | Closed | 2024-01-23 | 2024-01-30 | E//Sumitra | 2024-01-30 | CelcomDigi_RAN_GTSB_TSS_Central_20231208 | DU00002861240 |  |  | 2024-03-17 | 2024-03-08 |  | Lampole | 24M Lampole | 24m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
7738B | Parkview Villa | Sabah |  | Modernization |  | 2024 Q3 | BY | GTSB | 4.6 TSSR Approved |  | 2024-01-31 | 2024-03-21 |  | 2024-04-15 |  | Closed | 2024-04-23 | 2024-04-24 | E//Hannah | 2024-04-24 | Celcom Digi_RAN-GTSB-TSS-Sabah-20240204 | DU00002861241 |  |  | 2024-07-05 | 2024-07-03 |  |  | 30m Monopole | 35 | Add R9224E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
7698A | Jalan Jeti Sipitang (REL) | Sabah |  | Modernization |  | 2024 Q3(single site MOCN) | AD | Seri Pancar | 4.6 TSSR Approved |  | 2023-10-27 | 2023-10-30 |  | 2024-05-28 |  | Under Approval | 2024-07-01 | 2024-07-04 | E//Hannah | 2024-07-04 | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231101 | DU00002861242 |  |  | 2024-07-23 | 2024-07-17 |  | Monopole | 30M Monopole | 45m | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8862A S1800(B6A) x2+R8862A S2100(A6A) x2 | 0 | 13
9691A | Nanga Machan | Sarawak |  | Modernization |  | 2025 Q3 | AI | Datasco | 4.6 TSSR Approved |  | 2023-11-17 | 2023-11-20 |  | 2025-02-17 |  | Rectificating | 2025-03-05 | 2025-03-10 | E//Hannah | 2025-03-10 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231119 | DU00002861243 |  |  | 2025-05-31 | 2025-05-08 |  |  | Tower | 78 | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8892E M1821(BAA)x3 | 0 | 0
3564C | Jasmin Apartment LP | Central |  | Modernization |  | 2024 Q1 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-09 | 2023-11-14 |  | 2024-01-16 |  | Closed | 2024-01-17 | 2024-08-26 | E//Kok Keen | 2024-08-26 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231113 | DU00002861244 |  |  | 2024-03-10 | 2024-03-06 |  | Lampole | 18m Lampole | 18 | Add R8862A S9000 x3+R8894E M1821 x1+R8854 S2600 x1,Dismantle R8862A S2600(A4A) x1 |  | 3
7791A | KGMELANGKAP | Sabah |  | Modernization |  | 2025 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2025-01-23 | 2025-02-26 |  | 2025-03-14 |  | Under Approval | 2025-03-19 | 2025-04-28 | E//Hannah | 2025-04-16 | SQ202501030028 - GTSB | DU00002861245 |  |  | 2025-05-11 | 2025-04-21 |  | Tower | 45m 3 Legged Tower | 75 | Reuse Existing
4639B | Kg Kura | Northern |  | Modernization |  | 2024 Q3(single site MOCN) | SM | CCSMY | 4.6 TSSR Approved |  | 2024-04-17 | 2024-04-29 |  | 2024-05-02 |  | Rectificating | 2024-05-09 | 2024-05-10 | E//Hazida | 2024-05-10 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240422-0107 | DU00002861246 |  |  | 2024-07-24 | 2024-06-15 |  | Tower | Tower | 50 +10 = 60m | Add R8862A S2601 x2+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x2 | 12 | 0
4351C | Kolej Professional Mara Seri Iskandar | Northern |  | Modernization |  | 2024 Q2 | ZA | CCSMY | 4.6 TSSR Approved |  | 2024-02-19 | 2024-02-21 |  | 2024-02-26 |  | Closed | 2024-02-28 | 2024-03-01 | E//Ajay | 2024-03-01 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240221-0094 | DU00002861247 |  |  | 2024-03-13 | 2024-03-07 |  | Lampole | 24m Lampole | 31 | Add R8894E M1821 x5+R8854 S2600 x2,Dismantle R8862A S2600(A4A) x2+R8892N M1821(BAB) x3 |  | 23
7387B | Palm Hill Tawau | Sabah |  | Modernization |  | 2024 Q3 | MS | GTSB | 4.6 TSSR Approved |  | 2023-10-23 | 2023-10-24 |  | 2023-10-27 |  | Closed | 2024-04-15 | 2024-04-18 | E//Hannah | 2024-04-16 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231024 | DU00002861248 |  |  | 2024-06-12 | 2024-05-28 |  | Monopole | 30m Monopole | 30 | Add R9264M M1821 x1+A9732 M1821 x3,Dismantle R8894E M1821(A8A) x4 | 124 | 0
7389B | Myinn RT | Sabah |  | Modernization |  | 2024 Q3 | MS | GTSB | 4.6 TSSR Approved |  | 2023-10-20 | 2023-10-24 |  | 2023-10-27 |  | Closed | 2024-06-10 | 2024-06-12 | E//Hannah | 2024-06-11 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231024 | DU00002861249 |  |  | 2024-06-12 | 2024-06-10 |  | H-bracket pole | 3m Bipod (RT) | 4m | Add R8894E M1821 x2,Dismantle | 0 | 13
3651C | Persiaran Institusi | Central |  | Modernization | Modernization->On Hold->Modernization | 2024 Q3 | SH | YPTT | 4.6 TSSR Approved |  | 2024-04-30 | 2024-05-06 |  | 2024-05-10 |  | Under Approval | 2024-12-16 | 2024-12-17 | E//Sumitra | 2024-12-17 | CelcomDigi_RAN_YPTT_TSS_Central_20240513 | DU00002861250 |  |  | 2025-05-09 | 2024-10-04 |  | Monople Tree | 30m Monopole | 36 | Add R8862A S9000 x3+R8894E M1821 x3+R8862A S2601 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R8862A S2600(A4A) x3 | 0 | 0
9023C | Taman Delight | Sarawak |  | Modernization |  | 2025 Q1 | SH | Trintel | 4.6 TSSR Approved |  | 2023-10-08 | 2023-10-10 |  | 2023-10-16 |  | Closed | 2023-10-16 | 2023-10-27 | E//John | 2025-05-19 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231009 | DU00002861251 |  | Remarks: Solution Changed | 2025-04-13 | 2025-04-05 |  | Monopole | 30m Monopole | 30 | Add R9264M M1821x3, Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3 | 0 | 0
3764C | The Royal Selangor Polo Club (REL) | Central |  | Modernization |  | 2024 Q2 | YZ | GTSB | 4.6 TSSR Approved |  | 2023-11-24 | 2023-11-29 |  | 2024-01-12 |  | Closed | 2024-01-17 | 2024-01-29 | E//Sumitra | 2024-01-26 | CelcomDigi_RAN_GTSB_TSS_Central_20231126 | DU00002861252 |  |  | 2024-04-19 | 2024-04-17 |  | Monople Tree | 45m Monopole Tree | 45 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
7778B | Kg Kiau | Sabah |  | Modernization |  | 2025 Q3 | AD | NR services | 4.6 TSSR Approved |  | 2025-01-15 | 2025-03-17 |  | 2025-03-21 |  | Under Approval | 2025-03-27 | 2025-05-23 | E//Hannah | 2025-04-18 | SQ202501020451 - NR Service | DU00002861253 |  |  | 2025-04-29 | 2025-04-15 |  | Lampole | 30m Lampole | 30m | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3 | 0 | 0
4013D | Felda Besout | Northern |  | Modernization |  | 2025 Q1 | AD | CCSMY | 4.6 TSSR Approved |  | 2023-11-21 | 2023-11-23 |  | 2025-02-14 |  | Under Approval | 2023-12-04 | 2023-12-12 | E//Hazida | 2025-04-21 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231122-0072 | DU00002861254 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed | 2025-04-30 | 2025-04-30 |  | Tower | Tower | 31m | Add R9264M M1821x3+R8862A S2601x2+R8854 S2600x1, Dismantle R8894E M1821(A8A)x3 | 0 | 2
9591C | Kg Munggul Limo | Sarawak |  | Modernization |  | 2025 Q3 | AD | Trintel | 4.6 TSSR Approved |  | 2023-10-25 | 2023-10-26 |  | 2025-02-18 |  | Under Approval | 2025-02-20 | 2025-03-09 | E//Hannah | 2025-03-17 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231214 | DU00002861255 | Remarks: Solution TSSR/BOM Changed |  | 2025-09-12 | 2025-09-08 |  | Monopole | 30m Monopole | 30m | Add R8862A S2601x3 | 0 | 0
7770B | Taginambur Dalam | Sabah |  | Modernization |  | 2025 Q3 | AD | NR services | 4.6 TSSR Approved |  | 2025-01-22 | 2025-02-04 |  | 2025-03-10 |  | Under Approval | 2025-03-19 | 2025-05-19 | E//Hannah | 2025-05-07 | SQ202501020451 - NR Service | DU00002861256 |  |  | 2025-05-15 | 2025-05-08 |  | Tower | 76M 3L Tower | 60 | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3 | 0 | 0
7780B | Kg. Parapat Laut | Sabah |  | Decomm, MOCN By Other Vendor | Decomm->On Hold->Decomm->On Hold->Decomm | 2025 Q3 | AD | NR services | 4.6 TSSR Approved |  | 2025-02-05 |  | 2025-02-20 |  | 2025-03-24 |  | 2025-04-30 | 2025-10-31 | E//Faiz | 2025-10-27 | SQ202504100592 - NR Service | DU00002861257 |  |  |  |  | 2025-10-06 |  | 76m 3 legged tower
7745B | Sime Darby | Sabah |  | Modernization |  | 2024 Q4 | AD | NR services | 4.6 TSSR Approved |  | 2023-11-15 | 2023-11-20 |  | 2023-11-26 |  | Rectificating | 2024-07-17 | 2024-07-22 | E//Hannah | 2024-07-19 | Celcom Digi_RAN-NR Services-TSS-Sabah-20231119 | DU00002861258 |  |  | 2024-09-13 | 2024-08-15 |  |  | 60m 4 Legged Tower | 60 | Add R8862A S9000 x3+R8894E M1821 x1+A9732 M1821 x2,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 23 | 0
7746B | Kg Suan Lamba | Sabah |  | Modernization |  | 2024 Q4 | AD | NR services | 4.6 TSSR Approved | Solution changed MM>Bi | 2023-11-22 | 2023-12-08 |  | 2024-07-18 |  | Under Approval | 2024-08-12 | 2024-08-19 | E//Hannah | 2024-08-19 | Celcom Digi_RAN-NR Services-TSS-Sabah-20231107 | DU00002861259 |  |  | 2024-09-10 | 2024-09-03 |  | Tower | 72m 4 Legged Tower | 63 | Add R8862A S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R8862A S2600(A4A) x1 | 0 | 3
7747B | By Tunku Estate | Sabah |  | Modernization |  | 2024 Q4 | SH | NR services | 4.6 TSSR Approved |  | 2023-11-16 | 2024-02-19 |  | 2024-08-01 |  | Under Approval | 2024-08-02 | 2024-08-14 | E//Hannah | 2024-08-12 | Celcom Digi_RAN-NR Services-TSS-Sabah-20231119 | DU00002861260 |  |  | 2024-10-09 | 2024-09-20 |  | Tower | 60m 4 Legged Tower | 76m | Add R8862A S9000 x3+R8894E M1821 x2+A9732 M1821 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 1 | 0
7748B | By Tigowis Estate | Sabah |  | Modernization |  | 2024 Q4 | AD | NR services | 4.6 TSSR Approved |  | 2023-11-17 | 2023-11-22 |  | 2024-07-19 |  | Rectificating | 2024-09-30 | 2024-09-30 | E//Hannah | 2024-09-30 | Celcom Digi_RAN-NR Services-TSS-Sabah-20231119 | DU00002861261 |  |  | 2024-09-25 | 2024-09-07 |  | Tower | 60m 4 Legged Tower | 64 | Add R8862A S9000 x3+R8894E M1821 x4,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 3
7756B | Sogo-Sogo | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-04-14 |  | 2025-04-15 |  | 2025-04-22 | To be Submitted | 2025-04-28 | 2026-04-01 | E//Hannah | 2025-07-14 | SQ202504100583 - Futong | DU00002861262 |  |  |  |  | 2025-10-31 |  | Tower
7757B | Tongkabira | Sabah |  | Modernization |  | 131 single site mocn | AD | GTSB | 4.6 TSSR Approved |  | 2024-04-23 | 2024-04-30 |  | 2024-05-13 |  | Closed | 2024-05-15 | 2024-06-04 | E//Hannah | 2024-06-04 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240503 | DU00002861263 |  |  | 2024-06-25 | 2024-06-15 |  | Tower | Tower | 75 | Add R8852E S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3+R8862A S2600(A4A) x1 | 0 | 1
7765B | Kg Minihas | Sabah |  | Modernization |  | 2025 Q3 | AD | NR services | 4.6 TSSR Approved |  | 2025-01-20 | 2025-03-17 |  | 2025-03-21 |  | Under Approval | 2025-03-24 | 2025-05-23 | E//Hannah | 2025-04-18 | SQ202501020451 - NR Service | DU00002861264 |  |  | 2025-05-29 | 2025-04-21 |  | Tower | 60m 4 Legged Tower | 60m | Add R9264M M1821x2+A9732 M1821x1, Dismantle R8894E M1821(A8A)x3 | 3 | 0
3177A | Jln 31_20 | Central |  | Modernization |  | 2024 Q3 | CR | GCI | 4.6 TSSR Approved |  | 2023-11-10 | 2023-11-17 |  | 2024-04-04 |  | Closed | 2024-04-05 | 2024-04-05 | E//Kok Keen | 2024-04-05 | CelcomDigi_RAN_GCI_TSS_Central_20231113 | DU00002861265 |  |  | 2024-04-23 | 2024-04-03 |  | Tower | 45m Tower | 30 | Add R8862A S9000 x3+R8894E M1821 x3+R8854 S2600 x3,Dismantle R8862A S2600(A4A) x3 | 0 | 123
3246A | PPR Pinggiran Bkt Jalil | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-10-24 | 2023-10-30 |  | 2024-04-16 |  | Closed | 2024-04-16 | 2024-04-18 | E//Sumitra | 2024-04-18 | CelcomDigi_RAN_GTSB_TSS_Central_20231025 | DU00002861266 |  |  | 2024-05-24 | 2024-05-24 |  | Lampole | Lampole 30m | 30m | Add R9264M M1821 x4,Dismantle R8892E M1821(BAA) x4 | 0 | 0
1465A | JBA Tmn Segar | Central |  | Modernization |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-07 | 2023-12-22 |  | 2024-03-27 |  | Closed | 2024-03-29 | 2024-04-02 | E//Sumitra | 2024-04-02 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231113 | DU00002861267 |  |  | 2024-06-26 | 2024-06-22 |  | Minimast | 15m Monopole | 20 | Add R9264M M1821 x4,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8862A S2100(A6A) x4 | 0 | 0
9055C | Kampung Pahlawan | Sarawak |  | Decomm, MOCN By Other Vendor | Decomm->On Hold->Decomm->On Hold->Decomm | 2025 | AI | CCSMY | 4.6 TSSR Approved |  | 2025-07-10 |  | 2025-07-14 |  | 2025-09-25 |  | 2025-10-23 | 2026-01-22 |  | 2025-12-03 | SQ202506060165-CCSMY | DU00002861268 |  |  |  |  | 2025-11-19 |  | Tower
1740A | Cheras Perdana | Central |  | Modernization |  | 2024 Q4 | MA | Solusi | 4.6 TSSR Approved |  | 2024-01-09 | 2024-01-17 |  | 2024-04-30 |  | Closed | 2024-05-02 | 2024-07-11 | E//Sumitra | 2024-07-11 | BOQ CelcomDigi_RAN_Solusi_Standard PR TSS_Central_20240110 | DU00002861269 |  |  | 2024-06-11 | 2024-06-06 |  | In-Building System | 3m RT (Minimast) | 11M | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 2 | 0
4009D | Tmn Semesti (REL) | Northern |  | Modernization |  | 2025 Q1 | AD | GCI | 4.6 TSSR Approved |  | 2025-01-13 | 2025-02-10 |  | 2025-02-25 |  | Under Approval | 2025-03-11 | 2025-05-27 | E//Hazida | 2025-03-17 | SQ202501030261 - GCI | DU00002861270 |  |  | 2025-04-28 | 2025-04-08 |  | Tower | 45m Tower | 45m | Add R8852E S9000x3+R8894E M1821x4+R8854 S2600x1, Dismantle R8862A S1800(B6A)x3+R8854D S2100(A4A)x3+R8862A S2600(A4A)x1 | 0 | 1
1139C | JALAN DAMANSARA PERMAI | Central |  | Modernization |  | 2024 Q2 | MA | CCSMY | 4.6 TSSR Approved |  | 2023-10-25 | 2023-11-02 |  | 2024-03-04 |  | Closed | 2024-03-24 | 2024-03-26 | E//Kok Keen | 2024-03-25 | CelcomDigi_RAN_CCSMY_TSS_Central_20231025 | DU00002861271 |  |  | 2024-08-17 | 2024-05-18 |  | Lampole | 18m Lampole | 19M | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3 | 0 | 0
1151C | Jalan Midah Timur | Central |  | Modernization |  | 2024 Q1 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-07 | 2023-11-09 |  | 2024-01-04 |  | Closed | 2024-01-04 | 2024-01-05 | E//Kok Keen | 2024-01-05 | CelcomDigi_RAN_GTSB_TSS_Central_20231113 | DU00002861272 |  |  | 2024-04-25 | 2024-04-23 |  | Monopole | 18m Lampole | 18 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3
1152C | Jalan Semerah Padi | Central |  | Modernization |  | 2024 Q3 | SS | CCSMY | 4.6 TSSR Approved | 22/3-existing RRU install in DPC cabinet...need to swap RRU to R9264H | 2023-10-25 | 2023-10-30 |  | 2024-03-21 |  | Closed | 2024-03-29 | 2024-04-03 | E//Sumitra | 2024-04-03 | CelcomDigi_RAN_CCSMY_TSS_Central_20231025 | DU00002861273 |  |  | 2024-05-31 | 2024-05-24 |  | Lampole | 18m Lampole | 19M | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3 | 0 | 0
4235B | Unimap Pauh 2 | Northern |  | Modernization |  | 154 single site MOCN | SH | CCSMY | 4.6 TSSR Approved |  | 2023-11-05 | 2023-11-17 |  | 2024-08-19 |  | Under Approval | 2024-08-29 | 2024-08-30 | E//Hazida | 2024-08-30 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231106-0068 | DU00002861274 |  |  | 2024-08-28 | 2024-08-24 |  | Tower | 60M 3L ToweR | 61m | Add R8852E S9000 x3+A9732 M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 123 | 0
9629B | Mukah Kampung Datu | Sarawak |  | Modernization | Modernization->On Hold->Modernization | 2025 Q2 | AD | AllStar | 4.6 TSSR Approved |  | 2023-11-07 | 2023-11-09 |  | 2024-04-05 |  | Closed | 2024-04-17 | 2024-04-25 | E//Hannah | 2026-04-17 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20231112 | DU00002861275 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed | 2025-03-11 | 2025-03-11 |  | Monopole | 30m Rapole | 30 | Reuse Existing RRU | 0 | 0
7448B | Harbour Mall RT | Sabah |  | Modernization |  | 2026 | MS | GTSB | 4.3 Pending TSSR Resubmission - ZTE | Solution changed from BI > Normal in 2026 | 2024-07-23 | 2024-07-27 |  | 2024-08-02 |  | Under Approval | 2024-12-17 | 2024-08-26 | E//Hannah |  | 0725Sabah-GTSB-BOQ Template(new contract) | DU00002861276 | Remarks: Solution TSSR/BOM Changed | [5 empty] | 3m Bipod (RT) | 3 | Add R8862A S9000x3 | 0 | 0
9534A | Kg Riam Jaya | Sarawak |  | Modernization |  | 2025 Q1 | AD | Datasco | 4.6 TSSR Approved |  | 2023-10-17 | 2023-10-27 |  | 2025-02-06 |  | Under Approval | 2025-02-14 | 2025-03-09 | E//Hannah | 2025-02-24 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231019 | DU00002861277 |  |  | 2025-03-23 | 2025-03-14 |  | Tower | 35m Tower | 36 | Add R9264M M1821x4, Dismantle R8882 S1800(B)x3+R8862A S1800(B6A)x1+R8854D S2100(A4A)x4 | 0 | 0
1180C | Jalan 3_93 Cheras | Central |  | Modernization |  | 2024 Q3 | CR | Ascentrack | 4.6 TSSR Approved | 29/03/24 - CD require to swap existing cabinet to Dualbay cabinet | 2023-11-15 | 2023-11-16 |  | 2023-12-21 |  | Closed | 2024-03-29 | 2024-04-05 | E//Sumitra | 2024-04-05 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231113 | DU00002861278 |  |  | 2025-06-19 | 2025-06-10 |  | Lampole | 18m Lampole | 18 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3 | 0 | 0
1123C | Taman Ikan Emas | Central |  | Modernization |  | 2024 Q3 | SS | YPTT | 4.6 TSSR Approved |  | 2024-02-08 | 2024-02-14 |  | 2024-03-22 |  | Closed | 2024-03-25 | 2024-03-26 | E//Sumitra | 2024-03-26 | BOQ_Celcom Digi_RAN-YPTT-Standard PR TSS-20240218 | DU00002861279 |  |  | 2024-07-23 | 2024-07-23 |  | Lampole | 30m Monopole | 30m | Add R8862A S9000 x3+R8894E M1821 x4,Dismantle R8862A S1800(B6A) x4+R8862A S2100(A6A) x4 | 0 | 2
1028B | Shoplot Jalan Tun Sambathan | Central |  | Modernization | Modernization->On hold->Site out->Modernization | 2024 Q2 | YZ | CCSMY | 4.6 TSSR Approved |  | 2023-10-24 | 2023-11-02 |  | 2024-01-10 |  | Closed | 2024-01-16 | 2024-01-30 | E//Sumitra | 2024-01-23 | CelcomDigi_RAN_CCSMY_TSS_Central_20231025 | DU00002861280 | Remarks: Solution TSSR/BOM Changed |  | 2025-05-15 | 2025-05-08 |  | H-bracket pole | 3m RT (Wall Mounted Pole) | 4m | Add R9264H M901821x3+R8862A S2601x3, Dismantle R8882-GUL1812x1+R8862A S1800(B6A)x2+R8854D S2100(A4A)x3+R8882-L268x3 | 0 | 0
9379B | Rh Abi | Sarawak |  | Decomm | Decomm->On Hold->Decomm->On Hold->Decomm | 2025 | NA | Trintel | 4.6 TSSR Approved |  | 2025-03-27 |  | 2025-04-23 |  | 2025-05-06 |  | 2025-05-07 | 2025-12-15 | E//John | 2025-05-20 | SQ202503240175-Trintel | DU00002861281 |  |  |  |  | 2025-10-30 |  | 45m 3 Legged Tower
1204C | LRT Bukit Jalil | Central |  | Modernization |  | 2024 Q3 | IE | Magicell | 4.6 TSSR Approved |  | 2024-01-23 | 2024-02-26 |  | 2024-03-26 |  | Closed | 2024-03-26 | 2024-04-02 | E//Sumitra | 2024-04-02 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240128 | DU00002861282 |  |  | 2024-07-22 | 2024-07-22 |  | Monopole | 24m Lampole | 30 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
1271C | Villa Wangsamas Condominium | Central |  | Modernization |  | 2024 Q1 | XH | DATASCO | 4.6 TSSR Approved | 29/01 RRU install inside cabinet,3 RRU on top, have temperature alarm according to technical team | 2023-11-05 | 2023-11-10 |  | 2023-11-20 |  | Closed | 2023-12-27 | 2024-05-16 | E//Kok Keen | 2024-05-13 | CelcomDigi_RAN_Datasco_TSS_Central_20231113 | DU00002861283 |  |  | 2024-03-07 | 2024-01-11 |  | Lampole | 18m Lampole | 19 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
4190D | SBC Bunga Raya Rekabina | Northern |  | Modernization |  | 2024 Additional | SHA | CCSMY | 4.6 TSSR Approved |  | 2024-11-19 | 2024-11-27 |  | 2024-12-02 |  | Under Approval | 2024-12-03 | 2024-12-06 | E//Hazida | 2024-12-06 | 1911CD-Northern-TSS-BOQ Template(new contract)_CCSMY_V2 | DU00002861284 |  |  | 2024-12-12 | 2024-12-11 |  | Tower | 70M 3L Tower | 60 | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3 | 0 | 0
3750C4 | pBTS Taman Aman Jaya (KM) | Sabah |  | Site Out (Modernization) | Modernization->On Hold->Decomm->Site Out->Replacement, Site Out (Modernization) | 2024 Q3 | MS | Datasco | 4.6 TSSR Approved |  | 2024-04-17 | 2024-04-30 | 2024-09-09 |  | 2024-09-10 |  | 2024-09-11 | 2025-10-17 | CD//Thanniya | 2024-09-12 | 0823CD-Sabah-Datasco-BOQ Template(new contract) | DU00002861285 |  |  |  |  | 2025-04-29 | Watertank | 25m pBTS | 30 |  | 3 | 0
1260C | Batu 21 Jalan Seremban (Maxis) | Central |  | Modernization |  | 2024 Additional | AI | YPTT | 4.6 TSSR Approved |  | 2024-04-01 | 2024-04-04 |  | 2024-11-25 |  | Closed | 2024-12-04 | 2024-12-10 | E//Sumitra | 2024-12-09 | BOQ_Celcom Digi_RAN-YPTT-Standard PR TSS-20240403 | DU00002861286 | Remarks: Solution TSSR/BOM Changed |  | 2025-02-06 | 2025-01-25 |  | Tower | 75m 4 Legged Tower | 75 | Add R8852E S9000 x3 | 0 | 0
1575B7 | pBTS NTT MSC | Central |  | Modernization | Modernization->On Hold->Modernization | 2024 Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2024-03-07 | 2024-03-13 |  | 2024-11-11 |  | Rectificating | 2024-11-14 | 2024-11-15 | E//Razif | 2024-11-15 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240311 | DU00002861287 |  |  | 2024-11-26 | 2024-11-25 |  | Guide mast | 25m pBTS | 24m | Add R8894E M1821x3, Dismantle R8862A S1800(B6A)x3+R8881 S2100x3 | 0 | 0
3215B | KL Sentral RT | Central |  | Modernization |  | 2024 Q2 | SS | CCSMY | 4.6 TSSR Approved |  | 2024-01-24 | 2024-02-02 |  | 2024-02-24 |  | Closed | 2024-02-26 | 2024-02-27 | E//Sumitra | 2024-02-27 | BOQ CelcomDigi_RAN_CCSMY_Standard PR TSS_Central_20240128 | DU00002861288 |  |  | 2024-03-23 | 2024-03-13 |  | Pole | 3m Boom (RT) | 5 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
3216B | 1 Sentral Carpark | Central |  | Modernization | Modernization->On Hold->Modernization | 2024 Q2 | SS | YPTT | 4.6 TSSR Approved |  | 2024-02-27 | 2024-03-20 |  | 2024-03-27 |  | Closed | 2024-03-27 | 2024-07-25 | E//Kok Keen | 2024-07-24 | BOQ_Celcom Digi_RAN-YPTT-Standard PR TSS-20240303 | DU00002861289 |  |  | 2024-07-21 | 2024-07-21 |  | Wall mount boom | 3m RT (Wall Mounted Pole) | 3 | Add R9264H M901821 x4+R8862A S2601 x4,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3+R8862A S2600(A4A) x3
1315C | Suasana Lumayan | Central |  | Modernization |  | 2024 Q3 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-10-23 | 2023-10-27 |  | 2024-03-22 |  | Closed | 2024-03-25 | 2024-03-26 | E//Sumitra | 2024-03-26 | CelcomDigi_RAN_CCSMY_TSS_Central_20231025 | DU00002861290 |  |  | 2024-05-13 | 2024-05-09 |  | Lampole | 18m Lampole | 18M | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
7351C | Jalan Bak Bak | Sabah |  | Modernization |  | 2025 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2023-11-14 | 2023-11-20 |  | 2025-02-19 |  | Under Approval | 2025-02-28 | 2025-05-27 | E//Hannah | 2025-03-16 | Celcom Digi_RAN-YPTT-Standard PR TSS-Sabah-20240813 | DU00002861291 |  |  | 2025-06-30 | 2025-05-27 |  | Monopole | 30M Lampole | 30 | Reuse Existing RRU | 0 | 0
1384C | WISMA BELIA (REL) | Central |  | Modernization |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-04-22 | 2024-06-21 |  | 2024-06-25 |  | Under Approval | 2024-06-26 | 2024-07-03 | E//Sumitra | 2024-07-03 | CelcomDigi_RAN_Datasco_TSS_Central_20231101 | DU00002861292 |  |  | 2024-07-25 | 2024-07-25 |  | In-Building System | Land site | 9 | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x4 | 0 | 0
4638B | Dusun Pengapit | Northern |  | Modernization |  | 2024 Q3(single site MOCN) | BY | GTSB | 4.6 TSSR Approved |  | 2024-04-16 | 2024-04-18 |  | 2024-04-23 |  | Closed | 2024-05-09 | 2024-05-13 | E//Hazida | 2024-05-10 | Celcom Digi_RAN-GTSB-TSS-Northern-20240417-0103 | DU00002861293 |  |  | 2024-06-20 | 2024-06-15 |  | Tower | Tower | 45m | Add R8862A S2601 x3+A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123 | 0
4349C | Bandar University Iskandar | Northern |  | Modernization |  | 2024 Q2 | BY | GTSB | 4.6 TSSR Approved |  | 2024-03-06 | 2024-03-11 |  | 2024-03-14 |  | Closed | 2024-03-15 | 2024-03-29 | E//Ajay | 2024-03-27 | Celcom Digi_RAN-GTSB-TSS-Northern-20240310-0096 | DU00002861294 |  |  | 2024-04-08 | 2024-04-02 |  | Minaret | 30m Monopole | 30m | Add R8894E M1821 x5+R8854 S2600 x2,Dismantle R8862A S1800(B6A) x3+R8862A S2600(A4A) x2+R8881 S2100 x3 |  | 13
1694C | Masreca 19 | Central |  | Modernization |  | 2024 Q3 | CR | Magicell | 4.6 TSSR Approved |  | 2024-02-23 | 2024-03-20 |  | 2024-04-25 |  | Rectificating | 2024-05-30 | 2024-05-31 | E//Razif | 2024-05-31 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240303 | DU00002861295 |  |  | 2024-11-26 | 2024-10-02 |  |  | Land site | 5m | Add R9264H M901821 x4+R8862A S2601 x4,Dismantle R8862A S2601(A6A) x4+R8894E M1821(A8A) x4 | 0 | 0
3287C | Semarak Api - MCD | Central |  | Modernization |  | 2024 Q3 | CR | Magicell | 4.6 TSSR Approved |  | 2024-05-31 | 2024-06-07 |  | 2024-06-13 |  | Under Approval | 2024-06-18 | 2024-06-25 | E//Razif | 2024-06-25 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240510 | DU00002861296 |  |  | 2024-09-04 | 2024-08-30 |  | Lampole | Land site | 20 | Add R8862A S9000 x3+R8894E M1821 x1+R8862A S2601 x2+R8854 S2600 x1,Dismantle R8862A S2601(A6A) x3 | 0 | 1
1654C | Kompleks Kerajaan Parcel F - RT | Central |  | Modernization | Modernization->Decomm->Modernization | 2024 Q3 | CR | Magicell | 4.6 TSSR Approved |  | 2024-01-18 | 2024-02-05 |  | 2024-08-08 | 2024-06-05 | Under Approval | 2024-09-05 | 2024-09-05 | E//Razif | 2024-09-05 | Wireless+ Malaysia CD+TSS+ Magicell-3 site SQ202410310160 | DU00002861297 |  | Please verify the topo | 2025-01-22 | 2025-01-20 |  | In-Building System | 3M Boom - RT | 3M | Add R8862A S9000x4 | 0 | 0
1691C | Flora Rosa (DRAN) | Central |  | Modernization | Modernization->Decomm->Modernization | 2024 Q3 | AI | Magicell | 4.6 TSSR Approved |  | 2024-11-22 | 2024-11-29 |  | 2024-12-03 |  | Under Approval | 2024-12-03 | 2024-12-05 | E//Razif | 2024-12-05 | 0813CD-Central-Magicell-BOQ Template(new contract) | DU00002861298 |  |  | 2024-12-12 | 2024-12-09 |  | Monopole | 45M Tower | 30 | Add R9264H M901821 x4,Dismantle R8894E M1821(A8A) x3 | 0 | 0
3123B | Jalan Semarak 2 (HSR) | Central |  | Modernization |  | 2024 Q1 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-10-27 | 2023-12-12 |  | 2024-01-04 |  | Closed | 2024-01-05 | 2024-01-11 | E//Sumitra | 2024-01-11 | CelcomDigi_RAN_CCSMY_TSS_Central_20231028 | DU00002861299 |  |  | 2024-06-05 | 2024-06-04 |  | In-Building System | 3m Bipod (RT) | 4 | Add R9264M M1821 x3,Dismantle R8882 S1800B(B6B) x3
1576C | LRT Kerinchi | Central |  | Modernization |  | 2024 Q2 | CR | GCI | 4.6 TSSR Approved |  | 2024-02-08 | 2024-02-07 |  | 2024-03-05 |  | Closed | 2024-03-18 | 2024-03-19 | E//Kok Keen | 2024-03-18 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240212 | DU00002861300 |  |  | 2024-05-07 | 2024-05-04 |  | Monopole | LRT | 24 | Add R8862A S9000 x3+R9224E M1821 x1+R8854 S2600 x1,Dismantle |  | 1
4411D | Masjid Pekan Baling | Northern |  | Modernization | Modernization->On Hold->Modernization | 2025 Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-10-27 | 2023-11-02 |  | 2025-02-26 |  | Closed | 2025-04-14 | 2025-07-17 | E//Hazida | 2026-04-17 | Celcom Digi_RAN-GTSB-TSS-Northern-20231028-0057 | DU00002861301 | Remarks: Solution TSSR/BOM Changed |  | 2025-06-19 | 2025-05-31 |  | Monopole | 30M RDS | 30 | Add R8862A S9000x3+R8894E M1821x1+R8862A S2601x2+R8854 S2600x1 | 0 | 2
9001B2 | pBTS Kampung Jemukan | Sarawak |  | Modernization | Modernization->On Hold->Modernization | 2024 Q2 | SH | Magicell | 4.6 TSSR Approved |  | 2023-11-04 | 2023-11-08 |  | 2023-12-15 |  | Under Approval | 2024-01-19 | 2024-02-01 | E//Hannah | 2024-01-31 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231107 | DU00002861302 | Remarks: Solution TSSR/BOM Changed |  | 2024-12-16 | 2024-11-25 |  | Watertank | 25m pBTS | 24 | Add R8862A S9000x3+R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8840-U216 x3 | 0 | 0
3246D | Surau Al-Amin Setapak (REL) | Central |  | Modernization |  | 2024 Q1 | CR | GTSB | 4.6 TSSR Approved | 29/01 RRU install inside cabinet, have temperature alarm according to technical team | 2023-11-04 | 2023-11-06 |  | 2024-01-06 |  | Closed | 2024-01-18 | 2024-04-05 | E//Kok Keen | 2024-04-05 | CelcomDigi_RAN_GTSB_TSS_Central_20231113 | DU00002861303 |  |  | 2024-03-07 | 2024-03-06 |  | Lampole | 18m Lampole | 18m | Add R8862A S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R8862A S2600(A4A) x1 |  | 2
3958B2 | pBTS SK Kuala Teriang | Northern |  | Modernization | Modernization->On Hold->Modernization | 154 single site MOCN | SM | GTSB | 4.6 TSSR Approved |  | 2024-11-14 | 2024-11-13 |  | 2024-11-14 |  | Rectificating | 2024-11-15 | 2024-11-29 | E//Hazida | 2024-11-29 | Celcom Digi_RAN-GTSB-TSS-Northern-20241112_New Contract | DU00002861304 |  |  | 2024-11-24 | 2024-11-18 |  | Guide mast | 25m pBTS | 30m | Add R8894E M1821x3, Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3 | 0 | 0
7353C | Kimanis | Sabah |  | Modernization |  | 2025 Q2 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2023-11-13 | 2023-11-14 |  | 2025-01-15 |  | Under Approval | 2025-01-17 | 2025-02-18 | E//Yanie | 2025-01-20 | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231221 | DU00002861305 |  |  | 2025-03-13 | 2025-03-06 |  | Tower | 76M 4 Legged Tower | 76 | Add R8894E M1821x1 | 0 | 1
9832B | Kampung Rebak | Sarawak |  | Modernization |  | 2024 Q2 | ZB | Magicell | 4.6 TSSR Approved | 15-3 - ZTE planner to update slide ¦ 01/17 Config has change to BI Sector 3 12/18 - Sacofa rejected : Antenna qty is reached maximum capacity at this site. | 2023-10-19 | 2023-10-26 |  | 2023-11-07 |  | Closed | 2024-04-16 | 2024-04-18 | E//Hannah | 2024-04-16 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231020 | DU00002861306 |  |  | 2024-06-20 | 2024-06-15 |  | Monopole | Rapole | 30M | Add R8894E M1821(A8A) x1+R8854 S2600 x1 |  | 3
2670C | LRT Awan Besar | Central |  | Modernization |  | 2024 Q3 | SH | GTSB | 4.6 TSSR Approved |  | 2023-11-27 | 2023-11-30 |  | 2024-03-25 |  | Closed | 2024-03-27 | 2024-04-15 | E//Kok Keen | 2024-04-05 | CelcomDigi_RAN_GTSB_TSS_Central_20231201 | DU00002861307 |  |  | 2024-08-09 | 2024-08-03 |  | Lampole | Lampole | 30m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
2088A | Saba Islamic | Central |  | Modernization |  | 2024 Q1 | CR | GCI | 4.6 TSSR Approved |  | 2023-11-20 | 2023-11-22 |  | 2024-02-28 |  | Closed | 2024-01-05 | 2024-01-29 | E//Sumitra | 2024-01-26 | CelcomDigi_RAN_GCI_TSS_Central_20231126 | DU00002861308 |  |  | 2024-04-23 | 2024-04-16 |  | In-Building System | 3m Bipod (RT) | 3 | Add R9264M M1821 x1+A9732 M1821 x3,Dismantle R8882-L268 x1+R8854 S2600(A4A) x1+R8894E M1821(A8A) x6 | 234
3004A9 | pBTS Sandakan Prison Quarters | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2024 Q3 | MS | Datasco | 4.6 TSSR Approved |  | 2024-04-17 | 2024-05-16 |  | 2024-11-07 |  | Under Approval | 2024-11-25 | 2024-11-27 | E//Hannah | 2024-11-27 | Celcom Digi_RAN-Datasco-Standard PR TSS-Sabah-20241112 | DU00002861309 |  |  | 2024-12-13 | 2024-12-05 |  | Watertank | PBTS | 24 | Add R8894E M1821x3, Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3 | 0 | 0
3497A9 | pBTS Kg Biuang (REL) | Sabah |  | Decomm | Modernization->On Hold->Decomm | 2024 Q4(single site MOCN)-L2126 SSM | AD | GTSB | 4.6 TSSR Approved |  | 2023-11-23 | 2023-11-24 | 2024-09-02 |  | 2024-09-05 | To be Submitted | 2024-09-06 |  | E//Hannah | 2024-09-26 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231126/0823CD-Sabah-GTSB-BOQ Template(new contract) | DU00002861310 |  |  |  |  | 2025-12-04 | Watertank | 24M PBTS | 25m |  | 0 | 0
A00062 | A036B_A00062OD_TROLAKTIMUR | Northern |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2025 Q1 |  | NR services | 1.1 Pending Survey - Subcon |  |  |  | 2025-10-23 |  |  | To be Submitted |  |  |  |  | SQ202504230465-NR services | DU00002861311 |  |  |  |  | 2025-11-28 |  | TOWER
A00822 | A037B_A00822OD_MN_KGAYERKUNING | Northern | 4136P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN->Swap | 2025 Q3 | HW | GCI | 4.6 TSSR Approved |  | 2025-04-18 | 2025-04-24 |  | 2025-05-05 |  | Under Approval | 2025-05-06 | 2025-05-27 | E//Hazida | 2025-05-23 | SQ202504260145-GCI | DU00002861312 |  |  | 2025-06-07 | 2025-05-17 |  | Tower | #N/A | 76m | Add R8852E S9000x3+R8894E M1821x4+R8862A S2601x2+R8854 S2600x1, Dismantle | 0 | 3
2075A | Metro Center Tasik Selatan | Central |  | Modernization |  | 2024 Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2024-01-15 | 2024-01-18 |  | 2024-04-04 |  | Closed | 2024-04-04 | 2024-04-15 | E//Sumitra | 2024-04-09 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240116 | DU00002861313 |  |  | 2024-07-20 | 2024-06-23 |  | In-Building System | 3m Boom (RT) | 3 | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 1 | 0
A00492 | A042A_A00492OD_RANTAUPJG_RDD | Northern |  | Decomm | Decomm->On Hold->Decomm | 2025 Q1 | SM | YPTT | 4.6 TSSR Approved |  | 2024-01-19 |  |  |  | 2024-01-24 |  | 2025-02-12 | 2026-02-04 | CD//Affendi | 2025-02-13 | Celcom Digi_RAN-YPTT-TSS-Northern-20240124-0056 | DU00002861314 | TSSR is ok. However, lets wait for the pair site to be implemented first before I approve this tssr. | CD zulakmar-TSSR is ok. However, lets wait for the pair site to be implemented first before I approve this tssr. |  |  | 2025-05-21 |  | TOWER
A00550 | A041A_A00550OD_FELDALASAH2 | Northern |  | Decomm | Decomm->On Hold->Decomm | 2025 Q3 | HW | CCSMY | 4.6 TSSR Approved |  | 2023-11-22 |  |  |  | 2023-12-06 |  | 2025-02-27 | 2025-07-29 | CD//Zulakmar | 2025-03-05 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231127-0073/Celcom Digi_RAN-CCSMY-TSS Decomm-Northern-20240131-0091 | DU00002861315 |  |  |  |  | 2025-05-14 |  | TOWER
A00797 | A042A_A00797OD_MN_SGDENDANG | Northern | 4157P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q1 | SM | GTSB | 4.6 TSSR Approved |  | 2025-02-07 | 2025-02-17 |  | 2025-02-27 |  | Rectificating | 2025-03-05 | 2025-05-19 | CD//Zulakmar | 2025-05-13 | SQ202501030330 - GTSB | DU00002861316 |  |  | 2025-05-09 | 2025-05-01 |  | Tower | TOWER | 76M | Add R8852E S9000x3+R8894E M1821x6, Dismantle | 0 | 0
9584A | Taman Jelita | Sarawak |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | SHA | Datasco | 4.6 TSSR Approved |  | 2024-01-17 | 2024-03-25 |  | 2024-11-04 |  | Under Approval | 2024-11-05 | 2024-11-11 | E//Syahriani | 2024-11-08 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20240124 | DU00002861317 |  |  | 2025-05-14 | 2024-11-19 |  | Lampole | 30m Rapole | 15 | Add R8862A S9000x3+R8894E M1821x6, Dismantle R8854E S1800(A6A)x3 | 0 | 123
3439A | DESASRIPUTRI1 | Central |  | Modernization |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-06-20 | 2024-07-05 |  | 2024-07-09 |  | Under Approval | 2024-07-10 | 2024-07-18 | E//Sumitra | 2024-07-18 | 0624Central-DATASCO-BOQ Template (template) | DU00002861318 |  |  | 2024-09-25 | 2024-09-13 |  | Pole | 3m Boom (RT) | 7 | Add R9264M M1821 x3+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x4 | 4 | 0
2123A | Persiaran Kemajuan | Central |  | Modernization |  | 2024 Q3 | CR | GTSB | 4.6 TSSR Approved |  | 2024-06-05 | 2024-06-12 |  | 2024-06-19 |  | Under Approval | 2024-12-13 | 2024-12-17 | E//Sumitra | 2024-12-17 | 0607Central-GTSB-BOQ Template | DU00002861319 |  |  | 2024-12-22 | 2024-12-19 |  | In-Building System | 30m 4 Legged Tower | 5M | Add R8852E S9000x3+R8862A S2601x2+R8854 S2600x1+R8894E M1821x3+A9732 M1821x1, Dismantle R8862A S9000(A6A)x3+R8862A S2600(A4A)x3+R8892E M1821(BAA)x2+R8892N M1821(BAB)x1 | 2 | 1
3440A | JLN_MEGA_MENDUNG | Central |  | Modernization |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-12-04 | 2024-04-26 |  | 2024-04-29 |  | Closed | 2024-04-30 | 2024-06-25 | E//Sumitra | 2024-06-25 | CelcomDigi_RAN_Datasco_TSS_Central_20231208 | DU00002861320 |  |  | 2024-05-19 | 2024-05-17 |  | Pole | 3m Bipod (RT) | 8m (315 inch) | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3 | 1 | 0
A00834 | A036B_A00834OD_MN_FELCRACHANGKAT | Northern | 4158P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q1 | HW | GTSB | 4.6 TSSR Approved |  | 2025-03-26 | 2025-04-08 |  | 2025-04-14 |  | Under Approval | 2025-04-15 | 2025-04-24 | CD//Zulakmar | 2025-04-23 | SQ202501030330 - GTSB | DU00002861321 |  |  | 2025-05-04 | 2025-04-24 |  | Tower | TOWER | 76M | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
A00835 | A037B_A00835OD_MN_KGSGSAMAK | Northern | 4194P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861322 | [6 empty] | #N/A
A00836 | A036B_A00836OD_CB_MN_KGSGBIL | Northern | 4215P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861323 | [6 empty] | TOWER
A00964 | A037B_A00964OD_T3_KGTANJUNGSARI | Northern | 4125P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN->Swap | 2025 | HW | GTSB | 4.6 TSSR Approved |  | 2025-04-11 | 2025-04-17 |  | 2025-04-21 |  | Under Approval | 2025-04-23 | 2025-05-02 | CD//Zulakmar | 2025-04-28 | SQ202504180262-GTSB | DU00002861324 |  |  | 2025-06-15 | 2025-06-10 |  | Tower | TOWER | 76M | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
3281B | Universiti LRT Station | Central |  | Modernization |  | 2024 Q2 | MA | GCI | 4.6 TSSR Approved |  | 2024-06-19 | 2024-06-25 |  | 2024-06-28 |  | Under Approval | 2024-06-28 | 2024-07-02 |  | 2024-07-01 | 0624Central-GCI-BOQ Template (template) | DU00002861325 |  |  | 2024-08-29 | 2024-08-26 |  | In-Building System | 3m Boom (RT) | 7 | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8862A S1800(B6A) x4+R8862A S2100(A6A) x4+R8862A S2600(A4A) x1 | 2 | 0
A00965 | A037B_A00965OD_T3_KGTANAHLALANGDARAT | Northern | 4191P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861326 | [6 empty] | TOWER
A00966 | A037A_A00966OD_T3_KGSGTUKANG_SIDIN | Northern | 4199P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861327 | [6 empty] | TOWER
A00967 | A037B_A00967OD_T3_SUNGAIPERGAM | Northern | 4192P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861328 | [6 empty] | TOWER
A00968 | A037B_A00968OD_T3_KGTELUKBHARU | Northern | 4200P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861329 | [6 empty] | TOWER
A00969 | A037B_A00969OD_T3_BGNSGBELUKANG | Northern | 4193P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861330 | [6 empty] | TOWER
A00971 | A036B_A00971OD_T3_KGSGTERAS | Northern | 4195P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861331 | [6 empty] | TOWER
A00973 | A036B_A00973OD_T3_KGMENDERANG | Northern | 4159P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q1 | AD | GCI | 4.6 TSSR Approved |  | 2025-01-09 | 2025-01-13 |  | 2025-02-07 |  | Closed | 2025-02-13 | 2025-03-09 | CD//Zulakmar | 2025-02-26 | SQ202501030328 - GCI | DU00002861332 |  |  | 2025-05-09 | 2025-04-25 |  | Tower | TOWER | 75m | Add R8852E S9000x3+R8862A S1800x3+R8894E M1821x3, Dismantle | 0 | 0
A00974 | A036B_A00974OD_T3_RPSJERNANG | Northern | 4124P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q1 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861333 | [6 empty] | TOWER
A01064 | A036A_A01064OD_T3_JERAMMENGKUANG | Northern | 4160P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q1 | SM | CCSMY | 4.6 TSSR Approved |  | 2025-01-25 | 2025-02-04 |  | 2025-02-19 |  | Rectificating | 2025-02-21 | 2025-02-26 | CD//Zulakmar | 2025-02-25 | SQ202501030318 - CCSMY | DU00002861334 |  |  | 2025-05-04 | 2025-04-30 |  | Tower | TOWER | 75M | Add R8852E S9000x3+R8854E S1800x3+R8894E M1821x3, Dismantle | 0 | 0
A01292 | KG. BATU 10_BATU 12 (T3-0629) | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q1 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861335 | [6 empty] | TOWER
A01182 | Kg Telok Seribu | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861336 | [6 empty] | TOWER
A01186 | T3E_0618_Jalan Gula | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861337 | [6 empty] | TOWER
A01190 | Kampung Rasau Slim River | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861338 | [6 empty] | TOWER
A01191 | Kg. Alor Setanggol | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861339 | [6 empty] | TOWER
A01192 | Kg Poh Bidor | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861340 | [6 empty] | TOWER
A01193 | Kg. Seri Kampar _ Kg Redang Ponggor | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861341 | [6 empty] | TOWER
A01194 | Kg. Tebing Rebak_ Kg. Sg. Dulang Dalam | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861342 | [6 empty] | TOWER
A01197 | Pos Keding _ Pos Tibang | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861343 | [6 empty] | TOWER
9166A | Bandar Baru Siburan | Sarawak |  | Modernization |  | 2024 Q4(single site MOCN)-L2126 SSM | SH | Datasco | 4.6 TSSR Approved |  | 2023-10-13 | 2023-10-25 |  | 2024-10-23 |  | Under Approval | 2024-10-21 | 2024-10-24 | E//Hannah | 2024-10-24 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231016 | DU00002861344 |  |  | 2024-11-15 | 2024-11-14 |  | Tower | Rapole | 47 | Add R9264M M1821 x2+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x4 | 23 | 0
A01228 | Parit 9 | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861345 | [6 empty] | TOWER
A01229 | Kg Parit 4 Sg Sumun | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861346 | [6 empty] | TOWER
A01230 | Kg Sg Batang | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861347 | [6 empty] | TOWER
A01231 | Kg Tebuk Imam Tasir | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861348 | [6 empty] | TOWER
A01232 | Parit 19 | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861349 | [6 empty] | TOWER
A01244 | JALAN KAMPAR - CHANGKAT JONG | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861350 | [6 empty] | TOWER
A01246 | KG SUNGAI KERAWAI | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861351 | [6 empty] | TOWER
A01247 | KG SENDI LIMA | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861352 | [6 empty] | TOWER
A01248 | RISDA CHANGKAT SULAIMAN BATANG PADANG | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861353 | [6 empty] | TOWER
A01250 | KG CHANGKAT SERUNAI | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861354 | [6 empty] | TOWER
A01251 | KG BULUH SERUAS | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861355 | [6 empty] | TOWER
A01252 | KG TITI IJOK | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861356 | [6 empty] | TOWER
3300B | Jln 1_13a (REL) | Central |  | Modernization |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-11-28 | 2024-01-05 |  | 2024-04-01 |  | Under Approval | 2024-04-03 | 2024-07-02 | E//Sumitra | 2024-07-02 | CelcomDigi_RAN_Datasco_TSS_Central_20231201 | DU00002861357 |  |  | 2024-04-30 | 2024-04-30 |  | Pole | 3m Boom (RT) | 6.5 m ( 256 inch ) | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8882 S1800(B) x2+R8882 S1800B(B6B) x1+R8862A S1800(B6A) x1+R8862A S2100(A6A) x4+R8862A S2601(A6A) x1 | 23 | 0
A01253 | LANDASAN KERETAPI GUNUNG SEMANGGOL | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861358 | [6 empty] | TOWER
3691A | Bangsar Utama (REL) | Central |  | Modernization |  | 2024 Q2 | SS | CCSMY | 4.6 TSSR Approved |  | 2024-02-20 | 2024-02-22 |  | 2024-03-11 |  | Closed | 2024-03-05 | 2024-03-06 | E//Kok Keen | 2024-03-06 | CelcomDigi_RAN_CCSMY_TSS_Central_20231028 | DU00002861359 |  |  | 2024-04-13 | 2024-04-04 |  | In-Building System | 3m Boom (RT) | 9 | Add R9264M M1821 x4,Dismantle R8882 S1800(B) x2+R8882 S1800B(B6B) x6+R8862A S2100(A6A) x4
A01256 | Kg Sungai Baru | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861360 | [6 empty] | TOWER
A01257 | Matang Kunda | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861361 | [6 empty] | TOWER
9235B | Chelsea Height | Sarawak |  | Modernization |  | 2025 Q3 | AD | Trintel | 4.6 TSSR Approved |  | 2025-10-14 | 2025-10-13 |  | 2025-10-14 |  | Under Approval | 2025-10-16 | 2025-10-24 | E//John | 2025-10-16 | SQ202507250435-Trintel | DU00002861362 |  |  | 2025-10-23 | 2025-10-20 |  | Monopole | 30m Rapole | 16 | Add A9732 M1821x1,Dismantle R8894E M1821(A8A) x1 | 1 | 0
7517B | Taman Mawar Lorong 35 | Sabah |  | Modernization |  | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2024-03-14 | 2024-03-20 |  | 2024-04-05 |  | Closed | 2024-04-08 | 2024-04-19 | E//Hannah | 2024-04-19 | Celcom Digi_RAN-Futong-TSS-Sabah-20240324 | DU00002861363 |  |  | 2024-06-13 | 2024-06-10 |  | Monopole | 30m Monopole | 30 | Add A9732 M1821 x2,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x2+R9224E M1821(AAB) x2 | 12 | 0
3373B | Jalan Pantai Permai 1 | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q2 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002861364 | [6 empty] | 24m Lampole |  |  |  | 12
7594A | Rancha Rancha 2 | Sabah |  | Modernization |  | 2025 Q1 | AI | Seri Pancar | 4.6 TSSR Approved |  | 2023-12-15 | 2023-12-26 |  | 2024-05-19 |  | Under Approval | 2025-01-07 | 2025-02-27 | E//Yanie | 2025-01-20 | Celcom Digi_RAN-Seri Pancar-Standard PR TSS-Sabah-20240109 | DU00002861365 |  |  | 2025-02-26 | 2025-02-07 |  | Monopole | 30m Monopole | 30 | Add R8852E S9000x3+R9264M M1821x3, Dismantle R8894E M1821(A8A)x3 | 0 | 0
3404B | Syabas Bangi Lama | Central |  | Remote MOCN | Modernization->Remote MOCN | 131 single site mocn |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002861366 | [6 empty] | Tower |  |  | 12
3466B | Surau Al-Azizah (REL) | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q1 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002861367 | [6 empty] | 24m Lampole |  |  |  | 123
9272A | Bintangor Sacofa | Sarawak |  | Modernization | Modernization->On Hold->Modernization | 2025 Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2023-10-10 | 2023-10-19 |  | 2023-11-07 |  | Closed | 2025-03-28 | 2025-05-19 | E//Hannah | 2025-04-14 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20231013 | DU00002861368 |  |  | 2025-07-06 | 2025-05-22 |  | Tower | 4 Legged Tower | 60 | Add A9732 M1821x1+R9264M M1821x2, Dismantle R8894E M1821(A8A)x3 | 1 | 23
3576B | Danau Kota 23E | Central |  | Modernization |  | 2024 Q1 | CR | GCI | 4.6 TSSR Approved | AAU Cannot Install-S23 MM change to BI¦unipole,full of antenna,share with other operator,space comstraint for AAU(too wide) | 2023-11-23 | 2023-11-28 |  | 2024-01-02 |  | Closed | 2024-01-04 | 2024-01-05 | E//Kok Keen | 2024-01-04 | CelcomDigi_RAN_GCI_TSS_Central_20231126 | DU00002861369 |  |  | 2024-03-31 | 2024-03-28 |  | In-Building System | 6m Unipole RT | 6 | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle R8862A S2600(A4A) x1 | 0 | 3
7531B | Jalan Mile 14 _ Jalil Alip | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2024-03-19 | 2024-03-22 |  | 2025-02-05 |  | Under Approval | 2025-02-18 | 2025-03-09 | E//Hannah | 2025-02-27 | Celcom Digi_RAN-Futong-TSS-Sabah-20240324 | DU00002861370 |  |  | 2025-03-24 | 2025-03-18 |  | Tower | Tower | 60 | Add R8852E S9000 x3+R8894E M1821 x3,Dismantle R8882 S1800B(B6B) x3 | 0 | 0
3884B | Lake Edge Puchong (Watertank) | Central |  | Modernization |  | 2024 Q3 | CR | Magicell | 4.6 TSSR Approved |  | 2023-11-09 | 2023-12-21 |  | 2024-04-26 |  | Closed | 2024-05-15 | 2024-05-21 | E//Sumitra | 2024-05-21 | CelcomDigi_RAN_Magicell_TSS_Central_20231214 | DU00002861371 |  |  | 2024-06-15 | 2024-06-12 |  | Monople Tree | 30m Monopole | 40M | Reuse exisiting RRU | 0 | 0
3879B | Masjid Al-Ikhwaniah | Central |  | Modernization | Modernization->On Hold->Modernization | 2024 Q4(single site MOCN)-L26 SSM | SY1 | Solusi | 4.6 TSSR Approved |  | 2024-02-05 | 2024-08-27 |  | 2024-08-31 |  | Closed | 2024-09-03 | 2024-10-18 | E//Sumitra | 2024-12-10 | 0827CD-Central-Solusi-BOQ Template(new contract) | DU00002861372 |  |  | 2025-02-18 | 2025-02-17 |  | Lampole | 24m Lampole | 25 | Add R8894E M1821 x2 | 0 | 12
3904B | Surau Saidina Abu Bakar | Central |  | Modernization |  | 2024 Q3 | MA | Solusi | 4.6 TSSR Approved |  | 2024-03-28 | 2024-02-20 |  | 2024-04-22 |  | Closed | 2024-05-06 | 2024-07-11 | E//Sumitra | 2024-07-11 | BOQ CelcomDigi_RAN_Solusi_Standard PR TSS_Central_20240329 | DU00002861373 |  |  | 2024-06-12 | 2024-06-12 |  | Lampole | 24m Lampole | 25 | Add R8862A S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 | 2 | 0
3603B | Jln Wangsa Delima 13 | Central |  | Modernization |  | 2024 Q1 | XH | DATASCO | 4.6 TSSR Approved |  | 2023-11-01 | 2023-11-09 |  | 2023-11-17 |  | Closed | 2023-12-27 | 2023-12-28 | E//Kok Keen | 2023-12-28 | CelcomDigi_RAN_Datasco_TSS_Central_20231104 | DU00002861374 |  |  | 2024-02-26 | 2024-02-23 |  | In-Building System | 3m Bipod (RT) | S1 - 5M S2&3 - 6M | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3
1741A | Tmn Bkt Belimbing | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  |  | 14.2 Drop (Done Survey) | AAU Cannot Install-Change MM to BI¦NOK,structure issue,can not support 5 Antenna;Suggest to change to bi-sector | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002861375 | BAU_S2_Change MM to BI_Space constraint_Digi OB | [5 empty] | 3m Boom (RT) |  |  |  | 23
1245B | Taman Sri Jati | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002861376 | [6 empty] | Billboard |  |  |  | 123
3975B | Taman Sri Reko | Central |  | Modernization |  | 2024 Q4 | SH | Magicell | 4.6 TSSR Approved |  | 2023-12-26 | 2024-01-04 |  | 2024-05-13 |  | Closed | 2024-05-14 | 2024-05-21 | E//Kok Keen | 2024-05-21 | CelcomDigi_RAN_Magicell_TSS_Central_20231227 | DU00002861377 |  |  | 2024-08-21 | 2024-08-14 |  | In-Building System | 3m Boom (RT) | 6M | Add R8894E M1821 x5+R8854 S2600 x2,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3+R8862A S2600(A4A) x2 | 0 | 13
7122A | Menara MPS | Sabah |  | Modernization |  | 2024 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2024-05-03 | 2024-06-25 |  | 2024-06-28 |  | Under Approval | 2024-07-02 | 2024-07-12 | E//Hannah | 2024-07-12 | Celcom Digi_RAN-YPTT-Standard PR TSS-Sabah-20240510 | DU00002861378 |  |  | 2024-07-30 | 2024-07-25 |  | In-Building System | 6m RT (Wall Mounted Pole) | 6 | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x3+R8894E M1821(A8A) x3+R9224E M1821(AAB) x3 | 123 | 0
7957A | Simpang Empat | Sabah |  | Modernization |  | 2025 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2025-01-23 | 2025-01-28 |  | 2025-03-04 |  | Under Approval | 2025-03-28 | 2025-05-23 | E//Hannah | 2025-04-18 | SQ202501030028 - GTSB | DU00002861379 |  |  | 2025-04-14 | 2025-04-10 |  | Monople Tree | 30m Monopole | 30 | Add R9264M M1821x2+A9732 M1821x1 | 2 | 1
7958A | Taman Marudu | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2024 Q3(single site MOCN) | SHA | Seri Pancar | 4.6 TSSR Approved |  | 2024-07-01 | 2024-07-14 |  | 2024-12-08 |  | Under Approval | 2024-12-11 | 2024-12-24 | E//Yanie | 2024-12-24 | Celcom Digi RAN Seri Pancar Standard PR TSS-Sabah-20241205 | DU00002861380 |  |  | 2025-01-27 | 2025-01-21 |  | Monopole | 30m Monopole | 45 | Add R8862A S9000 x3+A9732 M1821x1, Dismantle R8854 S2600(A4A)x1+R8894E M1821(A8A)x1 | 2 | 13
7245B | Taman Rimba | Sabah |  | Modernization |  | 2024 Q3 | MS | GTSB | 4.6 TSSR Approved |  | 2024-03-25 | 2024-04-06 |  | 2024-04-22 |  | Closed | 2024-04-23 | 2024-05-24 | E//Hannah | 2024-05-24 | Celcom Digi_RAN-GTSB-TSS-Sabah-20240329 | DU00002861381 |  |  | 2024-06-15 | 2024-06-12 |  | Monople Tree | 30m Monopole | 30 | Add R9224E M1821 x2+R8862A S2601 x2,Dismantle | 0 | 13
3770B | Jalan Yaakob Latif | Central |  | Modernization |  | 2024 Q3 | SS | CCSMY | 4.6 TSSR Approved | 29/3:- R9264H CANNOT FIT IN DPC CABINET | 2023-10-24 | 2023-10-27 |  | 2024-03-25 |  | Closed | 2024-03-29 | 2024-04-05 | E//Sumitra | 2024-04-05 | CelcomDigi_RAN_CCSMY_TSS_Central_20231025 | DU00002861382 |  |  | 2024-05-13 | 2024-05-09 |  | Lampole | 18m Lampole | 18M | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3 | 0 | 0
7262B | Kg Salimandut | Sabah |  | Modernization |  | 2024 Q3(single site MOCN) | AD | Seri Pancar | 4.6 TSSR Approved |  | 2024-06-20 | 2024-06-28 |  | 2024-07-05 |  | Under Approval | 2024-07-09 | 2024-07-12 | E//Hannah | 2024-07-12 | 0624Sabah-Seri Pancar-4BOQ Template (template) | DU00002861383 |  |  | 2024-08-05 | 2024-07-26 |  | Tower | 45m 3 Legged Tower | 76 | Add R8862A S2601 x2+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x2 | 12 | 0
7026A | Kg Kaban Melamam | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | AD | Datasco | 4.6 TSSR Approved |  | 2025-03-13 |  | 2025-04-25 |  | 2025-05-06 | To be Submitted | 2025-05-07 |  | E//Hannah | 2025-07-14 | SQ202504100595 - Datasco | DU00002861384 |  |  |  |  | 2025-10-31 |  | 30m Rapole
9246B | Beverly Garden | Sarawak |  | Modernization |  | 2024 Q4(single site MOCN)-L21 SSM | SHA | Datasco | 4.6 TSSR Approved | AAU Cannot Install-S4 MM change to BI¦SACOFA lampole/rampole not allow to add AAU | 2023-10-16 | 2023-11-23 |  | 2024-10-21 |  | Under Approval | 2024-10-25 | 2024-10-25 | E//Syahriani | 2024-10-25 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231017 | DU00002861385 |  |  | 2024-11-08 | 2024-11-06 |  | Monopole | 30m Rapole | 45 | Add R8862A S9000 x4+R8894E M1821 x7,Dismantle R8862A S2100(A6A)x4+R8862A S1800(B6A)x4 | 0 | 134
9611A | Kampung Riih | Sarawak |  | Modernization |  | 2024 Q4(single site MOCN)-L21 SSM | SHA | Magicell | 4.6 TSSR Approved |  | 2023-10-13 | 2023-10-23 |  | 2023-11-01 |  | Under Approval | 2024-10-16 | 2024-10-24 | E//Hannah | 2024-10-24 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231016 | DU00002861386 |  |  | 2024-11-14 | 2024-10-31 |  | Tower | Tower | 77M | Add R8862A S9000 x3+R8894E M1821 x5,Dismantle R8892E M1821(BAA) x3 | 0 | 23
3710A | Jalan Enggang Timur 7 | Central |  | Modernization |  | 2024 Q1 | CR | GCI | 4.6 TSSR Approved |  | 2023-11-06 | 2023-11-15 |  | 2024-01-03 |  | Closed | 2024-01-08 | 2024-01-09 | E//Sumitra | 2024-01-09 | CelcomDigi_RAN_GCI_TSS_Central_20231113 | DU00002861387 |  |  | 2024-05-09 | 2024-05-04 |  | In-Building System | 30m Monopole | 6 | Add R9264H M901821 x3,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3
1825B | Jalan Chan Sow Lin | Central |  | Modernization |  | 2024 Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2024-01-22 | 2024-02-14 |  | 2024-03-23 |  | Closed | 2024-03-25 | 2024-04-01 | E//Sumitra | 2024-04-01 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240128 | DU00002861388 |  |  | 2024-06-21 | 2024-06-16 |  | In-Building System | 3m Bipod (RT) | 4M | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
2227A | PUSPAKOM Wangsa Maju | Central |  | Modernization |  | 2024 Q1 | IE | GCI | 4.6 TSSR Approved |  | 2023-11-20 | 2023-11-21 |  | 2024-01-05 |  | Closed | 2024-01-11 | 2024-05-17 | E//Kok Keen | 2024-05-17 | CelcomDigi_RAN_GCI_TSS_Central_20231126 | DU00002861389 |  |  | 2024-04-23 | 2024-04-22 |  | Monopole | 24m Lampole | 24 | Add R9264M M1821 x3,Dismantle R8892E M1821(BAA) x3
3413B | Aman Apartment | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-11 | 2024-01-19 |  | 2024-04-19 |  | Closed | 2024-04-24 | 2024-04-25 | E//Razif | 2024-04-25 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240115 | DU00002861390 |  |  | 2024-06-29 | 2024-06-26 |  | Pole | 3m Bipod (RT) | 6m | Add R8862A S9000 x3+A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123 | 0
7545A | Sg Bedaun | Sabah |  | Modernization |  | 2025 Q1 | AI | YPTT | 4.6 TSSR Approved |  | 2025-01-12 | 2025-01-28 |  | 2025-01-31 |  | Closed | 2025-02-03 | 2025-02-10 |  | 2025-02-10 | SQ202501030041 - YPTT | DU00002861391 |  |  | 2025-02-26 | 2025-02-18 |  | Tower | Rapole | 40 | Add R8894E M1821x3, Dismantle R8862A S1800(B6A)x3 | 0 | 0
3007C | Kompleks Ostia Kajang | Central |  | Modernization |  | 2024 Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-17 | 2024-02-06 |  | 2024-05-15 |  | Closed | 2024-12-17 | 2024-05-23 | E//Sumitra | 2025-04-28 | CelcomDigi_RAN_GTSB_TSS_Central_20240124 | DU00002861392 |  |  | 2024-09-20 | 2024-09-20 |  | H-bracket pole | 3m Boom (RT) | 6m | Add R8852E S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 13 | 0
3117C | Taman Kobena Flat | Central |  | Modernization |  | 2024 Q3 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-11-21 | 2023-11-27 |  | 2024-04-02 |  | Closed | 2024-04-04 | 2024-04-16 | E//Sumitra | 2024-04-16 | CelcomDigi_RAN_CCSMY_TSS_Central_20231126 | DU00002861393 |  |  | 2024-06-05 | 2024-06-04 |  | Lampole | 24m Lampole | 24 | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 1 | 0
3126C | Menara Ikhlas (Presint 3) | Central |  | Decomm | Modernization->Decomm | 2024 Q3 | SHA | GTSB | 4.6 TSSR Approved |  | 2024-06-27 |  | 2024-07-05 |  | 2024-07-10 |  | 2024-07-15 | 2025-10-01 | E//Razif | 2024-07-18 | 0628Central-GTSB-BOQ Template (template) | DU00002861394 |  |  |  |  | 2024-09-11 |  | 3m Boom (RT)
1317A | Tmn Saga V5 | Central |  | Modernization |  | 2024 Q4 | BY | GTSB | 4.6 TSSR Approved |  | 2023-11-20 | 2023-11-23 |  | 2024-05-15 |  | Closed | 2024-05-21 | 2024-05-29 | E//Sumitra | 2024-05-29 | CelcomDigi_RAN_GTSB_TSS_Central_20231126 | DU00002861395 |  |  | 2024-06-05 | 2024-06-01 |  | H-bracket pole | 6m RT (Boom) | 6m | Add R8894E M1821 x2,Dismantle | 0 | 12
1772A | Tmn Semarak | Central |  | Modernization |  | 2024 Q4 | SH | Magicell | 4.6 TSSR Approved |  | 2023-11-02 | 2023-12-21 |  | 2024-05-10 |  | Closed | 2024-09-27 | 2024-11-27 | E//Sumitra | 2024-10-03 | CelcomDigi_RAN_Magicell_TSS_Central_20231214 | DU00002861396 |  |  | 2024-09-24 | 2024-09-13 |  | In-Building System | 3m RT (Wall Mounted Pole) | 3 | Add A9732 M1821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 123 | 0
K00646 | Kg. Batu 8 | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861397 | [6 empty] | #N/A
K00649 | Kg Telok Temelah | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861398 | [6 empty] | #N/A
K00651 | Kg Bukit Hijau | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861399 | [6 empty] | #N/A
K00652 | Kg Kuala Kuang | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861400 | [6 empty] | #N/A
K00653 | Kg. Ayer Merah | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861401 | [6 empty] | #N/A
K00804 | K002A_K00804OD_T3_KG_SELARONG_KEJAI | Northern | 4161P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q2 | AD | GCI | 4.6 TSSR Approved |  | 2025-01-09 | 2025-02-14 |  | 2025-02-25 |  | Under Approval | 2025-02-27 | 2025-03-09 | CD//Zulakmar | 2025-03-07 | SQ202501030328 - GCI | DU00002861402 |  |  | 2025-06-07 | 2025-05-14 |  | Monopole | MONOPOLE | 30 | Add R8852E S9000x3+R8854E S1800x3+R8894E M1821x3, Dismantle | 0 | 0
K00805 | K002A_K00805OD_T3_KG_HULU_BAKAI | Northern | 4162P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q2 | HW | GCI | 4.6 TSSR Approved |  | 2025-01-09 | 2025-04-08 |  | 2025-04-11 |  | Under Approval | 2025-04-14 | 2025-04-24 | CD//Zulakmar | 2025-04-23 | SQ202501030328 - GCI | DU00002861403 |  |  | 2025-04-30 | 2025-04-25 |  | Tower | TOWER | 76 | Add R8852E S9000x3+R8862A S1800x3+R8894E M1821x4, Dismantle | 0 | 1
K00806 | K002A_K00806OD_T3_KG_DALAM_WANG | Northern | 4163P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q2 | SM | CCSMY | 4.6 TSSR Approved |  | 2025-01-13 | 2025-01-20 |  | 2025-01-23 |  | Rectificating | 2025-02-19 | 2025-03-04 | CD//Zulakmar | 2025-03-03 | SQ202501030318 - CCSMY | DU00002861404 |  |  | 2025-05-17 | 2025-04-29 |  | Tower | TOWER | 75M | Add R8852E S9000x3+R8894E M1821x4, Dismantle | 0 | 3
K00809 | K002A_K00809OD_T3_KG_KUALA_KULI | Northern | 4183P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861405 | [6 empty] | TOWER
1281A | Pandan Indah | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002861406 | [6 empty] | 6m RT (Wall Mounted Pole) |  |  |  | 123
K00810 | K002A_K00810OD_T3_KG_TIAK | Northern | 4184P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861407 | [6 empty] | MONOPOLE
7717B | Taman Indah Jaya Ph7 | Sabah |  | Modernization |  | 2024 Q3 | MS | GTSB | 4.6 TSSR Approved |  | 2024-03-11 | 2024-03-20 |  | 2024-04-18 |  | Rectificating | 2024-04-23 | 2024-06-21 | E//Hannah | 2024-06-06 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240313 | DU00002861408 |  |  | 2024-07-09 | 2024-07-03 |  | Monople Tree | 30m Monopole | 40 | Add R8862A S9000 x4+R9224E M1821 x6+R8854 S2600 x1,Dismantle R8862A S1800(B6A) x4+R8862A S2100(A6A) x4 | 0 | 23
7723B | PPR Lintas (WTK) | Sabah |  | Modernization |  | 2024 Q4 | MS | Futong | 4.6 TSSR Approved |  | 2024-03-10 | 2024-03-14 |  | 2024-04-05 |  | Closed | 2024-04-15 | 2024-04-19 | E//Hannah | 2024-04-19 | Celcom Digi_RAN-Futong-Standard PR TSS-Sabah-20240313 | DU00002861409 |  |  | 2024-06-27 | 2024-06-22 |  | Tower | 30m Monopole | 60 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123 | 0
K00863 | Hutan Lipur Sg Sedim | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861410 | [6 empty] | TOWER
K00871 | K002A_K00871OD_CB_KG_KEJAI | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861411 | [6 empty] | TOWER
K00929 | Kg. KEDA Keledang | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861412 | [6 empty] | TOWER
K00935 | Kg Bakong Asam Jawa | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861413 | [6 empty] | TOWER
K00936 | Kg Charok Kapas | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861414 | [6 empty] | TOWER
K00946 | Kg Ayer Kepal | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861415 | [6 empty] | TOWER
K00947 | Kg Kuala Nau | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861416 | [6 empty] | TOWER
K00948 | Kg Ulu Seputeh | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861417 | [6 empty] | TOWER
K00951 | Kg Sri Kelengga | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861418 | [6 empty] | TOWER
K01004 | Kg Lubuk Batu | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861419 | [6 empty] | TOWER
K01005 | Kg Teluk Sg Durian | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861420 | [6 empty] | TOWER
K01007 | Kg Padang Besar | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861421 | [6 empty] | TOWER
K01012 | Kg Budi | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861422 | [6 empty] | TOWER
K01013 | Kg Bk Sebelah | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861423 | [6 empty] | TOWER
4622C | PR1MA Kuala Ketil | Northern |  | Modernization |  | 2024 Q3(single site MOCN) | ZA | GCI | 4.6 TSSR Approved |  | 2023-10-12 | 2023-10-20 |  | 2023-11-01 |  | Closed | 2024-04-18 | 2024-04-22 | E//Hazida | 2024-04-19 | Celcom Digi_RAN-GCI-TSS-Northern-20231013-0058 | DU00002861424 |  |  | 2024-06-27 | 2024-06-15 |  | Lampole | 24m Lampole | 30 | Add R8852E S9000 x3+A9732 M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 123 | 0
K01014 | Kg Binjoi Luar | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861425 | [6 empty] | TOWER
K01015 | Kg Belida | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861426 | [6 empty] | TOWER
K01016 | Kg Kuala Kijang | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861427 | [6 empty] | TOWER
K01019 | Kg Bk Pak Kuning | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861428 | [6 empty] | TOWER
K01020 | Kg Kuala Darat | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861429 | [6 empty] | TOWER
K01023 | Kg Terabak | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861430 | [6 empty] | TOWER
K01119 | Kg Kuala Bakung | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861431 | [6 empty] | #N/A
K01121 | Ladang Kim Seng Batu 5 | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861432 | [6 empty] | #N/A
4601C | Masjid Raja Dr Nazrin Shah | Northern |  | Modernization |  | 2024 Q2 |  | GCI | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦Space issue cant install AAU | 2023-10-17 | 2023-10-20 |  | 2024-01-11 |  | Closed | 2024-01-18 | 2024-01-29 | E//Hazida | 2024-01-24 | Celcom Digi_RAN-GCI-TSS-Northern-20231019-0062 | DU00002861433 |  |  | 2024-02-24 | 2024-02-20 |  | Minaret | Tower | 30 | Add R8862A S9000 x3+R8894E M1821 x5+R8854 S2600 x2,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R8862A S2600(A4A) x2 |  | 12
9545B | Lundu Town | Sarawak |  | Modernization |  | 2024 Q2 | SH | Magicell | 4.6 TSSR Approved | 15-3 - ZTE planner to update slide ¦ AAU Cannot Install-Change MM to BI¦ owner Sacofa reject our TP of adding AAU. | 2024-01-04 | 2024-01-10 |  | 2024-01-12 |  | Closed | 2024-01-17 | 2024-05-13 | E//Hannah | 2024-05-10 | Celcom Digi_RAN-Magicell-Standard PR TSS-Sarawak-20240109 | DU00002861434 |  |  | 2024-05-27 | 2024-05-15 |  | Monopole | 3m Bipod (RT) | 31 | Add R9264M M1821 x1+A9732 M1821 x3,Dismantle R8894E M1821(A8A) x4 | 134 | 0
9528B | Kampung Endap | Sarawak |  | Modernization |  | 2024 Q2 | SH | AllStar | 4.6 TSSR Approved |  | 2023-10-24 | 2023-11-06 |  | 2023-12-19 |  | Closed | 2024-03-18 | 2024-03-19 | E//Hannah | 2024-03-19 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20231028 | DU00002861435 |  |  | 2024-04-27 | 2024-03-16 |  | Tower | Tower | 76 | Add R8852E S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3+R8862A S2600(A4A) x1 | 0 | 2
9296B | Kampung Sungai Mata | Sarawak |  | Modernization |  | 2024 Q2 | ZB | DATASCO | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦sacofa rampole not allow to add AAU | 2023-10-10 | 2023-10-17 |  | 2023-10-25 |  | Closed | 2024-02-28 | 2024-03-05 | E//Hannah | 2024-03-05 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231013 | DU00002861436 | NIC_S1_Change MM to BI_owner reject_SACOFA SDN BHD |  | 2024-07-09 | 2024-07-01 |  |  | Rapole | 30 | Add R8862A S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R8862A S2600(A4A) x1 | 0 | 2
9583B | UITM Mukah | Sarawak |  | Modernization |  | 2025 Q2 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-10-06 | 2023-10-09 |  | 2023-10-13 |  | Closed | 2023-10-13 | 2023-11-03 | E//Hannah | 2023-11-01 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231009 | DU00002861437 |  |  | 2023-11-06 | 2023-10-31 |  | Tower | Tower | 46M | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R9224E M1821(AAB) x3 | 2 | 0
9578B | Jambusan 2 | Sarawak |  | Modernization |  | 2024 Q2 | SH | Datasco | 4.6 TSSR Approved |  | 2023-10-20 | 2023-10-26 |  | 2023-11-01 |  | Closed | 2024-02-08 | 2024-02-21 | E//Hannah | 2024-02-21 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231024 | DU00002861438 |  |  | 2024-03-14 | 2024-03-09 |  | Monopole | Tower | 45 | Add R8894E M1821 x2,Dismantle |  | 12
3412C | Kompleks Kemajuan (REL) | Central |  | Modernization |  | 2024 Q3 | CR | GCI | 4.6 TSSR Approved |  | 2023-12-11 | 2023-12-15 |  | 2024-03-28 |  | Closed | 2024-04-17 | 2024-04-18 | E//Kok Keen | 2024-04-17 | CelcomDigi_RAN_GCI_TSS_Central_20231214 | DU00002861439 |  |  | 2024-05-31 | 2024-05-28 |  | In-Building System | 3m Bipod (RT) | 6 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3++R8881 S2100 x3+ | 0 | 0
1230C | Cahaya | Central |  | Modernization |  | 2024 Q2 | YZ | YPTT | 4.6 TSSR Approved |  | 2024-02-07 | 2024-02-27 |  | 2024-03-04 |  | Closed | 2024-03-05 | 2024-03-13 | E//Sumitra | 2024-03-12 | BOQ_Celcom Digi_RAN-YPTT-Standard PR TSS-20240218 | DU00002861440 |  |  | 2024-07-25 | 2024-07-25 |  | Monopole | 30m Monopole | 30 | Add R8852E S9000 x3+A9732 M1821 x3,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 | 123 | 0
Q00187 | Q131A_Q00187OD_TMKUALAIGAN | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | AD | Trintel | 4.6 TSSR Approved |  | 2025-05-27 |  | 2025-06-06 |  | 2025-06-16 |  | 2025-06-19 | 2025-10-28 | E//John | 2025-06-23 | SQ202509040331-Trintel | DU00002861441 |  |  |  |  | 2025-09-19 |  | TOWER
Q00268 | Q132A_Q00268OD_CB_TT844 | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861442 | [6 empty] | BOOM
Q00371 | Q132A_Q00371OD_CB_PAKAT | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | HW | Trintel | 4.6 TSSR Approved |  | 2025-02-28 |  | 2025-05-06 |  | 2025-05-10 |  | 2025-05-14 | 2025-12-15 | CD//John | 2025-09-26 | SQ202502050142-Trintel | DU00002861443 |  |  |  |  | 2025-11-13 |  | TOWER
Q00386 | Q137A_Q00386OD_TGMANIS | Sarawak | 9478P | Swap | Swap->On Hold->Swap | 2027 | HW | Trintel | 4.6 TSSR Approved |  | 2025-03-24 | 2025-03-27 |  | 2025-04-14 |  | Under Approval | 2025-04-16 | 2025-04-24 | CD//John | 2025-04-17 | SQ202501070293-Trintel | DU00002861444 |  |  | 2025-07-06 | 2025-06-10 |  | Tower | TOWER | 106m | Add R8852E S9000x3+R9264M M1821x3+R8862A S2601x3, Dismantle | 0 | 0
Q00465 | Q138A_Q00465OD_CB_RHJAMES | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | AD | Trintel | 4.6 TSSR Approved |  | 2025-05-22 |  | 2025-05-28 |  | 2025-06-02 |  | 2025-06-03 | 2025-10-28 | E//John | 2025-06-04 | SQ202505020084-Trintel | DU00002861445 | 23/1/2025: SOW Changed from On Hold to Decomm |  |  |  | 2025-08-27 |  | TOWER
Q00478 | Q115A_Q00478OD_KGSEROPAK | Sarawak | 9466P | Swap | Swap->On Hold->Swap | 2024 Q2 | SH | Magicell | 4.6 TSSR Approved |  | 2023-11-02 | 2023-11-16 |  | 2024-01-11 |  | Under Approval | 2024-01-16 | 2024-01-18 | CD//John | 2024-01-17 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231107 | DU00002861446 |  |  | 2025-04-25 | 2025-04-19 |  | Tower | TOWER | 76m | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle | 0 | 0
1264B | Golden Sun Kuchai | Central |  | Modernization |  | 2024 Q3 | HQ 1 | DATASCO | 4.6 TSSR Approved |  | 2023-12-09 | 2024-01-30 |  | 2024-04-02 |  | Closed | 2024-04-02 | 2024-04-15 | E//Sumitra | 2024-04-08 | CelcomDigi_RAN_Datasco_TSS_Central_20231213 | DU00002861447 |  |  | 2024-04-21 | 2024-04-17 |  | Lampole | 24m Lampole | 26m | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle R8862A S2600(A4A) x1 | 0 | 1
Q00489 | Q123A_Q00489OD_JLNSELIRIK | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q3 | NA | Trintel | 4.6 TSSR Approved |  | 2025-03-11 |  | 2025-05-08 |  | 2025-05-09 |  | 2025-05-19 | 2025-12-15 | CD//John | 2025-05-27 | SQ202503030411-Trintel | DU00002861448 |  |  |  |  | 2025-11-12 |  | LAMP_POLE
3506C | Kg Gate Bahru (REL) | Central |  | Modernization |  | 2024 Q1 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-11-04 | 2023-11-10 |  | 2023-12-29 |  | Closed | 2024-01-02 | 2024-02-27 | E//Sumitra | 2024-02-27 | CelcomDigi_RAN_Datasco_TSS_Central_20231113 | DU00002861449 |  |  | 2024-03-05 | 2024-03-02 |  | Monople Tree | 30m Monopole | 47 | Add R9264M M1821 x3+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x4 | 1
Q00499 | Q132C_Q00499OD_SEPUPOK | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | AD | Magicell | 4.6 TSSR Approved |  | 2025-02-13 |  | 2025-04-29 |  | 2025-05-09 | To be Submitted | 2025-05-14 |  | E//John | 2025-07-29 | SQ202502050300-Magicell/SQ202502180438-Magicell | DU00002861450 |  |  |  |  | 2025-10-01 |  | TOWER
Q00507 | Q133A_Q00507OD_SPADMUKAH1 | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | AI | Trintel | 4.6 TSSR Approved |  | 2025-05-13 |  | 2025-06-19 |  | 2025-07-04 |  | 2025-07-07 |  | E//John | 2025-07-10 | SQ202505020084-Trintel | DU00002861451 |  | Pending Planner |  |  | 2025-08-15 |  | TOWER
Q00547 | Q130A_Q00547OD_JLNSGPASIR | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | NA | Trintel | 4.6 TSSR Approved |  | 2025-02-24 |  | 2025-05-08 |  | 2025-05-10 |  | 2025-05-13 | 2025-12-15 | CD//John | 2025-05-27 | SQ202502050142-Trintel | DU00002861452 |  |  |  |  | 2025-11-15 |  | TOWER
Q00561 | Q119A_Q00561OD_PKNOYA | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | AD | Trintel | 4.6 TSSR Approved |  | 2025-05-26 |  | 2025-05-28 |  | 2025-06-02 |  | 2025-06-03 |  | E//John | 2025-07-18 | SQ202505020084-Trintel | DU00002861453 |  |  |  |  | 2025-07-21 |  | TOWER
Q00639 | Q130A_Q00639OD_CB_BELURU | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q3 | NA | Trintel | 4.6 TSSR Approved |  | 2025-02-28 |  | 2025-04-29 |  | 2025-05-05 |  | 2025-05-06 | 2026-04-14 | CD//John | 2025-05-27 | SQ202502050142-Trintel | DU00002861454 |  |  |  |  | 2025-07-16 |  | TOWER
3601C | Taman Damai Mewah (REL) | Central |  | Modernization |  | 2024 Q4 | BY | GTSB | 4.6 TSSR Approved |  | 2024-01-31 | 2024-02-15 |  | 2024-05-23 |  | Closed | 2024-06-11 | 2024-06-14 | E//Sonia | 2024-06-13 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240202 | DU00002861455 |  |  | 2024-08-20 | 2024-08-15 |  | H-bracket pole | 24m Lampole | 6m | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 2 | 0
1165B | JBA Pinggiran Putra 2 | Central |  | Modernization |  | 2024 Q3 | CR | GCI | 4.6 TSSR Approved |  | 2023-10-30 | 2023-11-03 |  | 2024-04-25 |  | Rectificating | 2024-05-15 | 2024-05-21 | E//Sumitra | 2024-05-21 | CelcomDigi_RAN_GCI_TSS_Central_20231214 | DU00002861456 |  |  | 2024-06-05 | 2024-05-28 |  | Monople Tree | 45m Monopole | 45 | Add R8862A S9000 x3,Dismantle | 0 | 3
Q00657 | Q121A_Q00657OD_PKNJULAU | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 | HW | Trintel | 4.6 TSSR Approved |  | 2025-06-30 |  | 2025-07-21 |  | 2025-07-23 |  | 2025-09-26 | 2026-01-20 | E//John | 2025-09-26 | SQ202506060240-Trintel | DU00002861457 |  |  |  |  | 2025-10-24 |  | TOWER
Q00661 | Q131A_Q00661OD_SGKUT | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | AD | Trintel | 4.6 TSSR Approved |  | 2025-05-27 |  | 2025-05-28 |  | 2025-06-02 | To be Submitted | 2025-06-03 |  | E//John | 2025-06-04 | SQ202505020084-Trintel | DU00002861458 |  | FE to confirm |  |  | 2025-11-11 |  | TOWER
9964A | Unimas (REL) | Sarawak |  | Modernization |  | 2024 Q2 | SH | AllStar | 4.6 TSSR Approved | 15/3 - ZTE Planning to prepare slide | 2023-10-21 | 2023-11-06 |  | 2023-12-14 |  | Closed | 2024-03-11 | 2024-03-13 | E//Hannah | 2024-03-12 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20231024 | DU00002861459 |  |  | 2024-04-18 | 2024-04-15 |  | Tower | 60m 4 Legged Tower | 60 | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x5 | 123 | 0
3610C | Jalan Kinrara 2 (REL) | Central |  | Modernization |  | 2024 Q3 | SH | GCI | 4.6 TSSR Approved |  | 2023-11-10 | 2023-11-15 |  | 2024-04-29 |  | Closed | 2024-05-03 | 2024-05-14 | E//Kok Keen | 2024-05-14 | CelcomDigi_RAN_GCI_TSS_Central_20231214 | DU00002861460 |  |  | 2024-06-15 | 2024-06-12 |  | Lampole | 30m Rapole | 25 | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle R8862A S2600(A4A) x1 | 0 | 1
Q00790 | Q115A_Q00790OD_KGPANGKALAN | Sarawak | 9469P | Swap | Swap->On Hold->Swap | 2024 Q2 | AI | Magicell | 4.6 TSSR Approved |  | 2024-01-15 | 2024-01-18 |  | 2025-02-06 |  | Closed | 2025-02-07 | 2025-02-10 | CD//John | 2025-02-10 | Celcom Digi_RAN-Magicell-Standard PR TSS-Sarawak-20240116 | DU00002861461 |  |  | 2025-04-27 | 2025-04-10 |  | Tower | TOWER | 68M | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle | 0 | 0
Q01136 | Q130A_Q01136OD_CB_SGPEKING | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861462 | [6 empty] | #N/A
Q01141 | Q130A_Q01141OD_T3_LONGTERAWAN | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861463 | [6 empty] | #N/A
Q01144 | Q130A_Q01144OD_T3_SGSTAPANG | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861464 | [6 empty] | #N/A
Q01146 | Q122A_Q01146OD_T3_NGBAT | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861465 | [6 empty] | #N/A
1163C | Jalan Senohong | Central |  | Modernization |  | 2024 Q3 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-10-23 | 2023-10-30 |  | 2024-04-03 |  | Closed | 2024-04-04 | 2024-04-16 | E//Sumitra | 2024-04-16 | CelcomDigi_RAN_CCSMY_TSS_Central_20231025 | DU00002861466 |  |  | 2024-06-22 | 2024-06-20 |  | Monopole | 18m Lampole | 18 | Add R8862A S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 3 | 0
Q01262 | Q132A_Q01262OD_KGTUSAN | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm->On Hold->MOCN Decomm->MOCN Decomm(Dismantle Passive) | 2024 Q4 |  | Magicell | 14.1 TSSR Not Required (Decomm by CD) | 10/2/2026: Confirmed by Magicell, during survey team found out site already dismantled | 2025-08-05 |  | 2025-08-08 |  |  | To be Submitted |  |  |  |  | SQ202507160538-Magicell | DU00002861467 |  |  |  |  | 2025-11-17 |  | TOWER
3641C | Taman Kinrara Section 4 | Central |  | Modernization |  | 2024 Q3 | CR | GCI | 4.6 TSSR Approved |  | 2023-11-10 | 2023-10-25 |  | 2024-04-19 |  | Closed | 2024-04-29 | 2024-05-07 | E//Sumitra | 2024-05-07 | CelcomDigi_RAN_GCI_TSS_Central_20231214 | DU00002861468 |  |  | 2024-07-25 | 2024-07-23 |  | Unipole | 24m Lampole | 13m | Add R8862A S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8862A S2601(A6A) x2+R8894E M1821(A8A) x5 | 23 | 0
3648C | Syabas Bandar Puteri Bangi | Central |  | Modernization |  | 131 single site mocn | MA | YPTT | 4.6 TSSR Approved |  | 2024-04-18 | 2024-04-22 |  | 2024-05-09 |  | Closed | 2024-12-10 | 2024-12-10 | E//Sumitra | 2024-12-10 | CelcomDigi_RAN_YPTT_TSS_Central_20240513 | DU00002861469 |  |  | 2024-11-16 | 2024-10-26 |  | Monople Tree | Tower | 45 | Add R9264H M901821 x2+A9732 M1821 x2,Dismantle R8862A S9000(A6A) x2+R8894E M1821(A8A) x4 | 12 | 0
3633C | Kg Seri Andalas | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-26 | 2024-01-29 |  | 2024-04-29 |  | Under Approval | 2024-05-10 | 2024-05-15 | E//Razif | 2024-05-15 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240128 | DU00002861470 |  |  | 2024-10-26 | 2024-10-10 |  | Lampole | Tower | 26m | Add R8862A S9000 x3+A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123 | 0
3659C | Taman Puncak Saujana | Central |  | Modernization |  | 2024 Q4 | MA | YPTT | 4.6 TSSR Approved |  | 2024-04-04 | 2024-04-22 |  | 2024-05-07 |  | Closed | 2024-05-08 | 2024-05-15 | E//Sumitra | 2024-05-15 | BOQ_Celcom Digi_RAN-YPTT-Standard PR TSS-20240407 | DU00002861471 |  |  | 2024-06-21 | 2024-06-21 |  | Monopole | 30M Lampole | 30 | Add R9264H M901821 x4,Dismantle R8894E M1821(A8A) x4 | 0 | 0
Q01481 | Q123A_Q01481OD_ULUKAPIT | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q3 | HW | Trintel | 4.6 TSSR Approved |  | 2025-03-11 |  | 2025-05-14 |  | 2025-05-15 |  | 2025-05-15 | 2025-12-15 | CD//John | 2025-05-15 | SQ202503030411-Trintel | DU00002861472 |  |  |  |  | 2025-11-21 |  | RAMO
4002D | UiTM Tapah | Northern |  | Modernization |  | 2024 Additional | SM | GTSB | 4.6 TSSR Approved | ¦ 1126 - Emailed rollout on major CME required ¦ 0314 - Site owner replied with comments not involving loading. Loading issue resolved. ¦ 0312 - TP resubmitted to owner for approval as pair site decomm TP is approved ¦ 0206 - Pending CD revert ¦ 0130 - Follow up done to Duan/RF on solution. ¦ 0110 - Owner rejected due to loading issue. | 2023-10-26 | 2023-11-08 |  | 2024-11-21 |  | Rectificating | 2024-11-26 | 2024-12-16 | E//Hazida | 2024-12-15 | Celcom Digi_RAN-GTSB-TSS-Northern-20231028-0057//2111CD-Northern-TSS-BOQ Template(new contract)_GTSB | DU00002861473 | Remarks: Solution TSSR/BOM Changed |  | 2025-10-21 | 2025-09-13 |  | Monople Tree | 30m Monopole | 45 | Add R8852E S9000x4+R8894E M1821x7+R8854 S2600x3, Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3+R8862A S2600(A4A)x3+R8892N M1821(BAB)x1 | 0 | 123
Q01549 | Q132C_Q01549OD_CB_RHSIKUN | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861474 | [6 empty] | TOWER
7046C | Taman Era Mas | Sabah |  | Modernization |  | 2024 Q3(single site MOCN) | AD | Seri Pancar | 4.6 TSSR Approved |  | 2023-10-29 | 2023-11-20 |  | 2024-06-11 |  | Closed | 2024-06-12 | 2024-06-14 | E//Hannah | 2024-06-13 | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231221 | DU00002861475 |  |  | 2024-08-30 | 2024-08-21 |  | Lampole | 30m Monopole | 30 | Add R8894E M1821 x2+R8854 S2600 x2,Dismantle R8862A S2600(A4A) x2 | 0 | 12
Q01659 | Q128A_Q01659OD_CB_KGTELUKMELANO | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2024 Q2 | NA | Trintel | 4.6 TSSR Approved |  | 2025-04-09 |  | 2025-04-17 |  | 2025-04-25 |  | 2025-05-02 |  | CD//John | 2025-05-04 | SQ202505020084-Trintel | DU00002861476 |  | No MW Info |  |  | 2025-08-02 |  | TOWER
9032C | Midway Crescent Garden | Sarawak |  | Modernization |  | 2024 Q2 | SH | Magicell | 4.6 TSSR Approved |  | 2023-10-09 | 2023-10-19 |  | 2023-10-23 |  | Closed | 2024-04-26 | 2024-04-30 | E//Hannah | 2024-04-29 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231009 | DU00002861477 |  |  | 2024-05-18 | 2024-04-23 |  | Monopole | 30m Rapole | 30 | Add R8894E M1821 x5+R8854 S2600 x2,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R8862A S2601(A6A) x2 | 0 | 12
9030C | Aiman Commercial (Kg Melaban) | Sarawak |  | Modernization |  | 2024 Q2 | SH | AllStar | 4.6 TSSR Approved |  | 2023-10-26 | 2023-10-26 |  | 2023-11-09 |  | Closed | 2024-03-01 | 2024-03-04 | E//Hannah | 2024-03-04 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20231028 | DU00002861478 |  |  | 2024-04-06 | 2024-04-03 |  | Monopole | Tower | 30 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
Q01698 | Q132A_Q01698OD_CB_BTULUMBERDEV | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861479 | [6 empty] | TOWER
Q01707 | T3_0224 - KG JEGOI | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861480 | [6 empty] | TOWER
Q01720 | Q132A_Q01720OD_CB_RHRANGGONG | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861481 | [6 empty] | TOWER
Q01721 | Q132A_Q01721OD_CB_KGIRAN | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861482 | [6 empty] | TOWER
Q01722 | Q132A_Q01722OD_CB_KGBARU | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861483 | [6 empty] | TOWER
Q01723 | Q132A_Q01723OD_CB_RHMAT | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861484 | [6 empty] | TOWER
Q01724 | Q132A_Q01724OD_CB_RHKUPANG | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861485 | [6 empty] | TOWER
Q01725 | Q132A_Q01725OD_CB_RHSUYONG | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861486 | [6 empty] | TOWER
Q01726 | Q132A_Q01726OD_CB_KGPELAPI | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861487 | [6 empty] | TOWER
Q01727 | Q132A_Q01727OD_CB_KUALASIBUTI | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861488 | [6 empty] | TOWER
Q01728 | Q132A_Q01728OD_CB_KGKEJAPIL | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861489 | [6 empty] | TOWER
3655C | Puchong Utama 8 | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-09 | 2024-01-17 |  | 2024-04-26 |  | Closed | 2024-05-03 | 2024-05-07 | E//Razif | 2024-05-06 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240110 | DU00002861490 |  |  | 2024-06-29 | 2024-06-26 |  | Unipole | 3m Boom (RT) | 6 | Add R8862A S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 3 | 0
Q01729 | Q132A_Q01729OD_CB_KGTIRIS | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861491 | [6 empty] | TOWER
Q01731 | Q132A_Q01731OD_CB_MILE38MYYNIAHROAD | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | NA | Trintel | 4.6 TSSR Approved |  | 2025-03-09 |  | 2025-05-09 |  | 2025-05-13 |  | 2025-05-13 | 2025-12-15 | CD//John | 2025-05-27 | SQ202502050142-Trintel | DU00002861492 |  |  |  |  | 2025-11-12 |  | TOWER
Q01737 | Q132A_Q01737OD_CB_KGLAJONG | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861493 | [6 empty] | TOWER
Q01741 | Q130A_Q01741OD_KGPEMINDAHAN | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | HW | Trintel | 4.6 TSSR Approved |  | 2025-02-26 |  | 2025-04-18 |  | 2025-04-22 |  | 2025-04-23 | 2025-05-02 | CD//John | 2025-04-24 | SQ202502050142-Trintel | DU00002861494 |  |  |  |  | 2025-07-23 |  | RAPOLE
Q01953 | KG DURAS | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 Q1 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861495 | [6 empty] | TOWER
3733C | Cornersek17 (REL) | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002861496 | [6 empty] | 3m Boom (RT) |  |  | 23
3714C | Sek17PJ (REL) | Central |  | Modernization |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-04-17 | 2024-04-19 |  | 2024-04-22 |  | Closed | 2024-04-24 | 2024-04-24 | E//Kok Keen | 2024-04-24 | CelcomDigi_RAN_Datasco_TSS_Central_20231126 | DU00002861497 |  |  | 2024-05-25 | 2024-05-21 |  | Minimast | 3m Boom (RT) | 6m & 4m | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
7766B | Kg Narinang | Sabah |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | AD | Futong | 4.6 TSSR Approved |  | 2023-10-27 | 2023-10-30 |  | 2023-11-01 |  | Closed | 2024-10-24 | 2024-11-11 | E//Hannah | 2024-11-07 | Celcom Digi_RAN-Futong-TSS-Sabah-20231028 | DU00002861498 | Remarks: Solution TSSR/BOM Changed |  | 2025-01-24 | 2024-11-22 |  | Tower | 60m 4 Legged Tower | 60 | Add R8862A S9000x3+R8894E M1821x4, Dismantle R8862A S1800(B6A)x3+R8854D S2100(A4A)x3 | 0 | 1
Q02012 | T3E_0301_Kampung Medong Hilir Medong Hulu | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861499 | [6 empty] | TOWER
Q02014 | T3E_0309_Kampung Sekai | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861500 | [6 empty] | TOWER
Q02015 | T3E_0310_Mukah - Selangau road | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861501 | [6 empty] | TOWER
4012D | ISTANA BUKIT MALUT (CELCOM) | Northern |  | Modernization |  | 154 single site MOCN | AI | GTSB | 4.6 TSSR Approved |  | 2023-10-17 | 2023-10-23 |  | 2023-10-25 |  | Under Approval | 2024-08-27 | 2024-09-30 | E//Hazida | 2024-09-28 | Celcom Digi_RAN-GTSB-TSS-Northern-20231018-0051 | DU00002861502 |  |  | 2024-10-13 | 2024-10-07 |  | Tower | 60m 4 Legged Tower | 60m | Add R8852E S9000 x3+R8894E M1821 x2+R8862A S2601 x1+A9732 M1821 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 2 | 0
Q02018 | T3E_0307_Rumah Sandin Rumah Janin Rumah Lili Ru | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861503 | [6 empty] | TOWER
Q02035 | Q132AD_Q02035OD_T3_COASTALHIGHWAY5 | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861504 | [6 empty] | TOWER
Q02036 | Q132A_Q02036OD_T3_RHLINGU | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861505 | [6 empty] | TOWER
Q02037 | Q132A_Q02037OD_T3_KGBUNGAI | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861506 | [6 empty] | TOWER
Q02038 | Kg Selanyau | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861507 | [6 empty] | TOWER
9604C | Sungai Arang | Sarawak |  | Modernization |  | 2024 Q4(single site MOCN)-L21 SSM | SHA | Magicell | 4.6 TSSR Approved |  | 2024-04-22 | 2024-04-25 |  | 2024-10-28 |  | Under Approval | 2024-10-29 | 2024-11-11 | E//Syahriani | 2024-11-07 | Celcom Digi_RAN-Magicell-Standard PR TSS-Sarawak-20240425 | DU00002861508 |  |  | 2024-12-07 | 2024-11-09 |  | Tower | Tower | 76 | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle | 0 | 1
Q02039 | Q132A_Q02039OD_T3_JLNBEKENUMIRI | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861509 | [6 empty] | TOWER
Q02042 | Q130A_Q02042OD_T3_RHSERING | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861510 | [6 empty] | TOWER
S00178 | S091A_S00178OD_CB_PONTIAN | Sabah | 7146P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN->Swap | 2024Q4 | HW | GTSB | 4.6 TSSR Approved |  | 2025-05-14 | 2025-05-23 |  | 2025-05-26 |  | Under Approval | 2025-05-27 | 2025-07-17 | E//Hannah | 2025-05-30 | SQ202505050115 - GTSB | DU00002861511 |  |  | 2025-08-13 | 2025-06-17 |  | Tower | TOWER | 60 | Add R8852E S9000x3+R8894E M1821x4+R8862A S2601x2+R8854 S2600x1, Dismantle | 0 | 2
S00321 | S098C_S00321OD_CB_SILABUKAN | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861512 | [6 empty] | TOWER
S00328 | S091A_S00328OD_CB_KGPARIS | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861513 | [6 empty] | TOWER
S00342 | S098C_S00342OD_SPGJEROCO | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-03-15 |  | 2025-03-19 |  | 2025-04-16 |  | 2025-04-18 | 2025-09-10 | CD//Sharidah | 2025-04-21 | SQ202503270530 - Futong | DU00002861514 |  |  |  |  | 2025-05-22 |  | TOWER
S00383 | S104A_S00383OD_CB_KGNABUTAN | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861515 | [6 empty] | TOWER
S00385 | S094A_S00385OD_CB_KGTIGAMAN | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2025 Q3 | HW | NR services | 4.6 TSSR Approved |  | 2025-02-06 |  | 2025-02-17 |  | 2025-02-27 |  | 2025-02-28 | 2025-09-10 | CD//Sharidah | 2025-03-05 | SQ202504100592 - NR Service | DU00002861516 |  |  |  |  | 2025-07-24 |  | TOWER
S00454 | TAKON | Sabah | 7139P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN->Swap | 2024Q4 | AD | NR services | 4.6 TSSR Approved |  | 2025-05-02 | 2025-05-28 |  | 2025-06-07 |  | Rectificating | 2025-06-10 | 2025-06-19 | E//Hannah | 2025-06-19 | SQ202504140266 - NR Service | DU00002861517 | [5 empty] | Tower | TOWER | 106 | Add R8852E S9000x3+R8894E M1821x4, Dismantle | 0 | 1
S00486 | S098B_S00486OD_CB_TAMANMAJU | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-03-10 |  | 2025-03-16 |  | 2025-03-24 |  | 2025-04-13 | 2025-09-10 | CD//Sharidah | 2025-04-28 | SQ202503270530 - Futong | DU00002861518 |  |  |  |  | 2025-08-19 |  | TOWER
S00489 | S102A_S00489OD_CB_KGKANIBONGAN | Sabah | 7103P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2025-02-06 | 2025-03-07 |  | 2025-03-21 |  | Under Approval | 2025-03-27 | 2025-05-23 | CD//Sharidah | 2025-04-08 | SQ202501020343 - GTSB | DU00002861519 |  |  | 2025-07-06 | 2025-05-22 |  | Tower | TOWER | 75 | Add R8852E S9000x3+R8894E M1821x4, Dismantle | 0 | 3
S00492 | S111A_S00492OD_KUALATOMANI | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | HW | YPTT | 4.6 TSSR Approved |  | 2025-03-05 |  | 2025-03-07 |  | 2025-03-10 |  | 2025-03-11 | 2025-09-10 | CD//Sharidah | 2025-03-14 | SQ202504140301 - YPTT | DU00002861520 |  |  |  |  | 2025-09-19 |  | LAMP_POLE
S00495 | CBTMPITAS | Sabah | 7134P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q3 |  | YPTT | 14.7 Drop (Site Out) | Done under USP | [5 empty] | To be Submitted |  |  |  |  | Raised under USP Project | DU00002861521 | proceed under CD USP | [5 empty] | BOOM |  | Add R8852E S9000x3+R8894E M1821x5+R8862A S2601x1+R8854 S2600x2, Dismantle | 0 | 23
S00508 | S098C_S00508OD_SEGANGAN | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-03-07 |  | 2025-03-12 |  | 2025-03-24 |  | 2025-04-13 | 2025-09-10 | CD//Sharidah | 2025-04-22 | SQ202503270530 - Futong | DU00002861522 |  |  |  |  | 2025-05-19 |  | TOWER
S00543 | S088A_S00543OD_CB_LUMADAN | Sabah | 7290P | Swap | Swap->On Hold->Swap | 2025 Q2 | AD | DATASCO | 4.6 TSSR Approved |  | 2025-01-09 | 2025-03-17 |  | 2025-03-20 |  | Under Approval | 2025-03-23 | 2025-04-28 | CD//Sharidah | 2025-03-24 | SQ202501020331 - Datasco | DU00002861523 |  |  | 2025-04-27 | 2025-04-24 |  | Tower | TOWER | 76 | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
S00546 | S098A_S00546OD_JERAGANBISTARI | Sabah | 7147P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN->Swap | 2024Q4 | AI | NR services | 4.6 TSSR Approved |  | 2025-04-10 | 2025-05-06 |  | 2025-05-12 |  | Under Approval | 2025-05-13 | 2025-05-21 | CD//Sharidah | 2025-05-20 | SQ202504140266 - NR Service | DU00002861524 |  |  | 2025-10-17 | 2025-06-17 |  | Tower | TOWER | 76 | Add R8852E S9000x3+R8894E M1821x4, Dismantle | 0 | 2
S00549 | S098A_S00549OD_CB_TGLABIAN | Sabah | 7148P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN->Swap | 2024Q4 | HW | NR services | 4.6 TSSR Approved |  | 2025-04-10 | 2025-05-14 |  | 2025-05-18 |  | Under Approval | 2025-05-21 | 2025-05-27 | E//Hannah | 2025-05-26 | SQ202504140266 - NR Service | DU00002861525 |  |  | 2025-09-26 | 2025-06-16 |  | Tower | TOWER | 60 | Add R8862A S9000x3+R8894E M1821x4, Dismantle | 0 | 1
3816C | Pusat Perniagaan Suadamai | Central |  | Modernization |  | 2024 Q4 | CR | GCI | 4.6 TSSR Approved |  | 2024-03-03 | 2024-03-04 |  | 2024-05-27 |  | Closed | 2024-05-29 | 2024-06-06 | E//Sumitra | 2024-06-06 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240311 | DU00002861526 |  |  | 2024-07-19 | 2024-07-16 |  | In-Building System | 3m Tripod (RT) | 4 | Add R8852E S9000 x3+R8894E M1821 x4+R8862A S2601 x1+R8854 S2600 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R8862A S2600(A4A) x2 | 0 | 3
S00568 | S104A_S00568OD_CB_KGMURUK | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2025 Q3 | NA | NR services | 4.6 TSSR Approved |  | 2025-04-08 |  | 2025-02-10 |  | 2025-04-16 |  | 2025-04-28 | 2025-10-13 | CD//Sharidah | 2025-09-27 | SQ202504100592 - NR Service | DU00002861527 |  |  |  |  | 2025-10-23 |  | TOWER
S00574 | S098A_S00574OD_TELISAI | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-03-19 |  | 2025-03-20 |  | 2025-04-17 |  | 2025-04-18 | 2025-10-28 | CD//Sharidah | 2025-04-21 | SQ202503270530 - Futong | DU00002861528 |  |  |  |  | 2025-08-24 |  | TOWER
S00592 | T3_0878 - KG MERUNGIN | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861529 | [6 empty] | TOWER
S00600 | S091A_S00600OD_SKSANDAU | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-03-13 |  | 2025-03-13 |  | 2025-03-25 |  | 2025-04-13 | 2025-09-10 | CD//Sharidah | 2025-04-22 | SQ202503270530 - Futong | DU00002861530 |  |  |  |  | 2025-09-28 |  | BOOM
S00646 | S102A_S00646OD_CB_KGRUKOMLUYONG | Sabah | 7135P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2025-01-07 | 2025-01-31 |  | 2025-02-17 |  | Under Approval | 2025-03-19 | 2025-05-27 | CD//Sharidah | 2025-03-24 | SQ202501020343 - GTSB | DU00002861531 |  |  | 2025-04-30 | 2025-04-24 |  | Tower | TOWER | 75 | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
S00688 | S098B_S00688OD_CB_KGBUMIPUTERA | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-03-12 |  | 2025-03-16 |  | 2025-03-25 |  | 2025-04-14 | 2025-09-10 | CD//Sharidah | 2025-04-22 | SQ202503270530 - Futong | DU00002861532 |  |  |  |  | 2025-05-18 |  | TOWER
S00766 | S092A_S00766OD_CB_KGDUDAR | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861533 | [6 empty] | TOWER
S00773 | S102A_S00773OD_T3_KGRANGGAL | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861534 | [6 empty] | TOWER
S00775 | S102A_S00775OD_T3_KGLAUTTANDAWAN | Sabah | 7202P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN->Swap | 2025 Q3 | AD | Seri Pancar | 4.6 TSSR Approved | 5/8- Wk34 plan | 2025-08-14 | 2025-08-19 |  | 2025-08-20 |  | Under Approval | 2025-08-25 | 2025-09-20 | E//Hannah | 2025-09-10 |  | DU00002861535 |  |  | 2025-11-19 | 2025-09-23 |  | Tower | TOWER | 76 | Add R8852E S9000x3+R9264M M1821x4 | 0 | 3
S00784 | S102A_S00784OD_T3_KGDELIMA | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861536 | [6 empty] | TOWER
S00801 | S104A_S00801OD_LABANRATA | Sabah | 7297P | Swap | Swap->On Hold->Swap | 2025 Q3 | AD | NR services | 4.6 TSSR Approved |  | 2025-03-03 | 2025-03-27 |  | 2025-04-09 |  | Under Approval | 2025-04-11 | 2025-05-23 | CD//Sharidah | 2025-04-21 | SQ202501020340 - NR Service | DU00002861537 |  |  | 2025-12-24 | 2025-12-11 |  | Wall mount boom | BOOM | 10 | Add R8852E S9000x2+R8894E M1821x2, Dismantle | 0 | 0
S00905 | S104A_S00905OD_CB_KGKIBAS | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861538 | [6 empty] | TOWER
S00916 | Kg Taburan | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861539 | [6 empty] | TOWER
S00917 | Sg Koyah | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861540 | [6 empty] | 0
S00945 | S094A_S00945OD_T3_BUKITIJAI | Sabah | 7136P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q3 | AD | NR services | 4.6 TSSR Approved |  | 2025-09-28 | 2025-09-30 |  | 2025-10-02 |  | Under Approval | 2025-10-03 | 2025-10-16 | E//Hannah | 2025-10-07 | SQ202510070085 - NR Service | DU00002861541 |  |  | 2025-10-21 | 2025-10-16 |  | Tower | TOWER | 76 | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
S00949 | S094A_S00949OD_T3_KGTALAMASON | Sabah | 7167P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN->Swap | 2025 Q3 | AD | Seri Pancar | 4.6 TSSR Approved | 5/8- Wk34 plan | 2025-08-14 | 2025-08-20 |  | 2025-08-21 |  | Under Approval | 2025-08-25 | 2025-09-20 | E//Hannah | 2025-09-17 |  | DU00002861542 |  |  | 2025-10-27 | 2025-09-20 |  | Tower | TOWER | 76m | Add R8852E S9000x3+R9264M M1821x4 | 0 | 1
S00957 | S094A_S00957OD_KGMARAKPARAK | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2025 Q3 | AD | NR services | 4.6 TSSR Approved | 250701 - NR chow revert need special 4wheel | 2025-08-22 |  | 2025-09-23 |  | 2025-09-24 | To be Submitted | 2025-09-26 |  | E//Hannah | 2025-10-06 | SQ202508220446 - NR Service | DU00002861543 |  |  |  |  | 2025-10-06 |  | TOWER
S01009 | S092A_S01009OD_CB_KGSAYAP | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861544 | [6 empty] | TOWER
3873C | Jalan Puah | Central |  | Modernization |  | 2024 Q1 | CR | GCI | 4.6 TSSR Approved |  | 2023-11-16 | 2023-11-20 |  | 2024-01-02 |  | Closed | 2024-01-04 | 2024-01-05 | E//Kok Keen | 2024-01-04 | Celcom Digi_RAN-GCI-TSS-Central-20231119 | DU00002861545 |  |  | 2024-04-03 | 2024-03-29 |  | Lampole | 24m Lampole | 30 | Add R8862A S9000 x3+R8894E M1821 x1,Dismantle |  | 3
S01234 | Bulusbikang | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861546 | [6 empty] | #N/A
S01235 | Dusun | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861547 | [6 empty] | #N/A
S01236 | Silabukan Forest Reserve | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861548 | [6 empty] | #N/A
S01237 | Division 10 Tomaco | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861549 | [6 empty] | #N/A
S01238 | Kg Bulu Telu | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861550 | [6 empty] | #N/A
S01239 | kg Jawa Lahad Datu Sabah | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861551 | [6 empty] | #N/A
S01242 | Kg Lama | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861552 | [6 empty] | #N/A
S01243 | Kg Mensuli | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861553 | [6 empty] | #N/A
S01244 | Kg. Paris Tiga | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861554 | [6 empty] | #N/A
S01246 | Kg Segama | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861555 | [6 empty] | #N/A
S01247 | Kg Makuao | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861556 | [6 empty] | #N/A
S01249 | S. Tungku | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861557 | [6 empty] | #N/A
S01250 | Division 11 Tomaco | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861558 | [6 empty] | #N/A
S01251 | Simpang Bakapit | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861559 | [6 empty] | #N/A
S01255 | Unico Estate | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861560 | [6 empty] | #N/A
3913B | LORONG TITIWANGSA 2 | Central |  | Modernization |  | 2024 Q1 | SS | CCSMY | 4.6 TSSR Approved | 29/01 RRU install inside cabinet, 3 RRU on top, have temperature alarm according to technical team | 2023-11-06 | 2023-11-15 |  | 2024-01-02 |  | Closed | 2024-01-03 | 2024-01-09 | E//Sumitra | 2024-01-09 | CelcomDigi_RAN_CCSMY_TSS_Central_20231113 | DU00002861561 |  |  | 2024-05-02 | 2024-04-30 |  | Lampole | 18m Lampole | 19 | Add R9264H M901821 x3,Dismantle R8892N M1821(BAB) x3
7306C | Menumbok Port | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2025 Q1 | AD | DATASCO | 4.6 TSSR Approved |  | 2025-03-06 |  | 2025-04-24 |  | 2025-05-13 |  | 2025-05-16 | 2025-10-13 | E//Hannah | 2025-09-23 | SQ202504100595 - Datasco | DU00002861562 |  |  |  |  | 2025-08-14 |  | 60m 4 Legged Tower
1244C | IOI Conezion | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002861563 | [6 empty] | Building |  | Reuse Existing RRU | 0 | 1
7031C | Kampung Landung Ayang | Sabah |  | Modernization |  | 2024 Q3(single site MOCN) | AD | YPTT | 4.6 TSSR Approved |  | 2023-11-14 | 2023-11-20 |  | 2024-06-24 |  | Under Approval | 2024-07-03 | 2024-07-30 | E//Hannah | 2024-07-29 | Celcom Digi_RAN-YPTT-Standard PR TSS-Sabah-20240621 | DU00002861564 |  |  | 2024-08-31 | 2024-08-13 |  | Monopole | 30m Rapole | 30 | Add R8862A S9000 x3+A9732 M1821 x3,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x5 | 123 | 0
7029C | Kampung Jawa 2 | Sabah |  | Modernization |  | 2024 Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-10-23 | 2023-10-27 |  | 2024-04-05 |  | Rectificating | 2024-04-16 | 2024-06-21 | E//Hannah | 2024-06-06 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231024 | DU00002861565 |  |  | 2024-06-10 | 2024-06-04 |  | Lampole | 30m Monopole | 30 | Add R8894E M1821 x2,Dismantle | 0 | 23
1129C | Kayu Ara | Central |  | Modernization | Modernization->On Hold->Modernization->Modernization | 2026 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-04-20 | 2024-05-13 |  | 2024-05-14 |  | Closed | 2024-05-16 | 2024-05-17 | E//Kok Keen | 2024-05-17 | CelcomDigi_RAN_Datasco_TSS_Central_20231101 | DU00002861566 | Remarks: Solution TSSR/BOM Changed |  | 2026-02-11 | 2026-01-27 |  | Monopole | 30m Monopole | 31m | Add R9264H M901821 x3+R8854 S2600x1,Dismantle R8862A S2600(A4A) x1+R8894E M1821(A8A) x3 | 0 | 2
1067C | Puchong Perdana Watertank | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  |  | 14.2 Drop (Done Survey) | AAU Cannot Install-Change MM to BI¦owner reject AAU can not install | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002861567 | BAU_S2_Change MM to BI_owner reject_MAXIS | [5 empty] | 60m 4 Legged Tower |  |  |  | 13
1195C | Abdullah Hukum | Central |  | Modernization |  | 2024 Q2 | MA | GCI | 4.6 TSSR Approved |  | 2024-06-13 | 2024-06-14 |  | 2024-06-18 |  | Closed | 2024-06-19 | 2024-06-20 | E//Kok Keen | 2024-06-19 | 0618Central-GCI-BOQ Template (template) | DU00002861568 |  |  | 2024-09-04 | 2024-08-21 |  | In-Building System | 6m Unipole RT | 6 | Add R9264H M901821 x4,Dismantle R9224E M1821(AAB) x4
S01464 | S092A_S01464OD_CB_KGSARANG | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861569 | [6 empty] | TOWER
7021C | Kg Pangaraban | Sabah |  | Modernization |  | 2024 Q3(single site MOCN) | AD | YPTT | 4.6 TSSR Approved |  | 2023-11-03 | 2023-11-14 |  | 2024-06-24 |  | Under Approval | 2024-07-03 | 2024-07-12 | E//Hannah | 2024-07-12 | Celcom Digi_RAN-YPTT-Standard PR TSS-Sabah-20240621 | DU00002861570 |  |  | 2024-08-05 | 2024-07-26 |  | Tower | 45m Tower | 45 | Add R8862A S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 | 13 | 0
S01469 | S092A_S01469OD_CB_KGMELANGKAP | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861571 | [6 empty] | TOWER
S01483 | S091A_S01483OD_CB_KGTENAGANG | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861572 | [6 empty] | TOWER
S01567 | S091A_S01567OD_CB_TUNGHUPMILLS | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-03-08 |  | 2025-03-13 |  | 2025-03-25 |  | 2025-04-14 | 2025-09-10 | CD//Sharidah | 2025-04-22 | SQ202504100583 - Futong | DU00002861573 |  |  |  |  | 2025-10-31 |  | TOWER
S01568 | S091A_S01568OD_CB_KGTAKALA | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861574 | [6 empty] | TOWER
S01573 | S091A_S01573OD_CB_LDGMORISEM | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4 | MNO | GTSB | 4.6 TSSR Approved |  | 2025-07-10 |  | 2025-07-10 |  | 2025-07-15 | To be Submitted | 2025-07-17 |  | CD//Ray Amos | 2025-09-30 | SQ202508120138 - GTSB | DU00002861575 |  |  |  |  | 2025-10-31 |  | TOWER
S01671 | Morisem 2 | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861576 | [6 empty] | TOWER
S01677 | T3_0699_Kg Botition | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861577 | [6 empty] | TOWER
S01679 | T3E_0218_ Sabang Mill | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861578 | [6 empty] | TOWER
4180D | Lebuh Bandar U Utama | Northern |  | Modernization |  | 2024 Q2 | BY | GTSB | 4.6 TSSR Approved |  | 2024-03-05 | 2024-03-07 |  | 2024-03-12 |  | Closed | 2024-03-13 | 2024-03-18 | E//Ajay | 2024-03-15 | Celcom Digi_RAN-GTSB-TSS-Northern-20240310-0096 | DU00002861579 |  |  | 2024-04-05 | 2024-04-01 |  | Lampole | 24m Lampole | 25m | Add R8862A S9000 x3+A9732 M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 123
S01687 | T3E_0227_ Linddale Estate | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861580 | [6 empty] | TOWER
S01691 | T3E_0230_ Tundun Bohangin | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861581 | [6 empty] | TOWER
S01692 | T3_0698_IOI Bimbingan 2 Plantation | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861582 | [6 empty] | TOWER
S01697 | T3_0697_IOI Unico Desa Plantation | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861583 | [6 empty] | TOWER
S01698 | T3_0695_Kg Upak Ulu Segama | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861584 | [6 empty] | TOWER
S01707 | Kg Dandun Pusat | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861585 | [6 empty] | TOWER
S01708 | Kg Pahu | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861586 | [6 empty] | TOWER
S01709 | SK Nampasan | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861587 | [6 empty] | TOWER
S01711 | Kg Narawang | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861588 | [6 empty] | TOWER
S01738 | Tiong Ratau | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861589 | [6 empty] | TOWER
S01741 | Tomis | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861590 | [6 empty] | TOWER
9970A | Miri Airport (Rel) | Sarawak |  | Modernization |  | 2025 Q1 | SH | Datasco | 4.6 TSSR Approved |  | 2023-10-17 | 2023-10-19 |  | 2023-10-23 |  | Closed | 2023-10-30 | 2023-11-15 | E//Hannah | 2025-03-05 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231019 | DU00002861591 |  | Remarks: Solution Changed | 2025-07-06 | 2025-03-06 |  | Tower | 30m Rapole | 30 | Add R8852E S9000x3+R9264M M1821x3, Dismantle R9224E M1821(AAB)x3 | 0 | 0
S01773 | FC1_117 Kg Rungus Nahaba | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861592 | [6 empty] | TOWER
S01775 | FC1_138 Turong Puteh | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861593 | [6 empty] | TOWER
S01788 | FC1_132 Kg Kebatasan (Jln Pitas - Kanibongan_1) | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861594 | [6 empty] | TOWER
S01829 | FC1_134 Kg Mengkapon Pitas | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861595 | [6 empty] | TOWER
S01846 | T3_0095 - KG PAKA | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861596 | [6 empty] | TOWER
S01851 | T3_0897 - KINABALU PARK | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861597 | [6 empty] | TOWER
4302D | Taman Bistari Jaya (REL) | Northern |  | Modernization |  | 2025 Q3 | HW | GCI | 4.6 TSSR Approved |  | 2025-01-13 | 2025-03-03 |  | 2025-03-14 |  | Under Approval | 2025-04-28 | 2025-05-02 | E//Hazida | 2025-04-30 | SQ202501030261 - GCI | DU00002861598 |  |  | 2025-05-22 | 2025-05-15 |  | Tower | 24m Lampole | 30m | Add R8852E S9000x4+R9264M M1821x4, Dismantle R8894E M1821(A8A)x4 | 0 | 0
S01852 | T3_0902 - KG TIBABAR | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861599 | [6 empty] | TOWER
1339C | Jalan Langkawi | Central |  | Modernization |  | 2024 Q1 | CR | GCI | 4.6 TSSR Approved | 27/02/24 - TSSR submit, change RRU solution 06/02/24 - Edotco feedback to swap dualbay cabinet under CD following DBCK specification 06/02/24 - Email to SA regarding SO Cabinet and RRU Location | 2023-11-16 | 2023-11-20 |  | 2024-01-02 |  | Closed | 2024-01-04 | 2024-04-05 | E//Kok Keen | 2024-04-05 | Celcom Digi_RAN-GCI-TSS-Central-20231119 | DU00002861600 |  |  | 2024-05-31 | 2024-05-29 |  | Lampole | 18m Lampole | 18 | Add R9264H M901821 x3+R8854 S2600 x1,Dismantle R8862A S2600(A4A) x1+R8894E M1821(A8A) x3 |  | 2
S01855 | Kg Sri Ganda | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861601 | [6 empty] | TOWER
S01859 | SK Sangau | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861602 | [6 empty] | TOWER
S01863 | Masjid Sipitang | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861603 | [6 empty] | MONOPOLE
S01868 | FC1_131 Kg Sosop Bai | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861604 | [6 empty] | TOWER
S01869 | FC1_127 Kg Bilangau Kecil | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861605 | [6 empty] | TOWER
S01870 | FC1_128 Kg Salungkapit | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861606 | [6 empty] | TOWER
S01871 | FC1_130 Kg Pandan Mandamai | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861607 | [6 empty] | TOWER
S01872 | FC1_129 Kg Tutuwoon | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861608 | [6 empty] | TOWER
S01884 | FC1_139 Kg Naruntung | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861609 | [6 empty] | TOWER
S01885 | FC1_133 Kg Ampungai | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861610 | [6 empty] | TOWER
S01886 | FC1_135 Kg Petani Baru | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861611 | [6 empty] | TOWER
S01887 | FC1_136 Kg Pituru | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861612 | [6 empty] | TOWER
S01898 | FC1_137 Kg Bawing | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861613 | [6 empty] | TOWER
1427C | Diamond Square RT | Central |  | Modernization |  | 2024 Q1 | CR | GCI | 4.6 TSSR Approved |  | 2023-11-25 | 2023-11-30 |  | 2024-01-02 |  | Closed | 2024-01-03 | 2024-06-24 | E//Kok Keen | 2024-06-24 | CelcomDigi_RAN_GCI_TSS_Central_20231126 | DU00002861614 |  |  | 2024-04-01 | 2024-03-29 |  | In-Building System | Land site | 7 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
3421C | Jalan Tun Razak (REL) | Central |  | Modernization |  | 2024 Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2024-07-01 | 2024-07-09 |  | 2024-07-15 |  | Closed | 2024-07-16 | 2024-07-18 | E//Sumitra | 2024-07-18 | 0619Central-GTSB-BOQ Template (template) | DU00002861615 |  |  | 2024-07-27 | 2024-07-24 |  | Lampole | 18m Lampole | 19M | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
3435D | BKTSWANGSA (REL) | Central |  | Modernization |  | 2024 Q1 | SS | YPTT | 4.6 TSSR Approved |  | 2023-12-02 | 2023-12-07 |  | 2023-12-27 |  | Closed | 2024-01-02 | 2024-03-26 | E//Kok Keen | 2024-03-26 | CelcomDigi_RAN_YPTT_TSS_Central_202031203 | DU00002861616 |  |  | 2024-03-05 | 2024-02-22 |  | Lampole | Land site | 19m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1570C | LRT Taman Jaya | Central |  | Modernization | Modernization->On Hold->Modernization | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-04-22 | 2024-04-24 |  | 2024-04-29 |  | Closed | 2024-04-30 | 2024-06-06 | E//Kok Keen | 2024-06-06 | CelcomDigi_RAN_Datasco_TSS_Central_20240513 | DU00002861617 |  |  | 2024-06-29 | 2024-06-25 |  | Minimast | Minimast Rooftop 6M | 8 | Add R9264H M901821 x4+R8862A S2601 x1,Dismantle R8894E M1821(A8A) x3
1359C | Hotel Mezzo | Central |  | Modernization |  | 2024 Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2024-04-23 | 2024-04-25 |  | 2024-05-02 |  | Closed | 2024-05-04 | 2024-11-27 | E//Sumitra | 2024-11-27 | CelcomDigi_RAN_YPTT_TSS_Central_20240513 | DU00002861618 |  |  | 2024-07-23 | 2024-07-16 |  | In-Building System | Building | 6 | Add R8862A S9000 x3+R8894E M1821 x1+R8854 S2600 x2,Dismantle | 0 | 12
3684B | Cottage Walk CJ | Central |  | Modernization |  | 2024 Q3 | CR | GTSB | 4.6 TSSR Approved |  | 2024-01-30 | 2024-02-01 |  | 2024-04-22 |  | Under Approval | 2024-06-10 | 2024-11-11 | E//Razif | 2024-11-07 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240202 | DU00002861619 |  |  | 2024-11-23 | 2024-11-21 |  | In-Building System | Land site | 12 | Add R8862A S9000x3+R8894E M1821x1 | 0 | 3
1697C | Lakefront Cyberjaya | Central |  | Modernization |  | 2024 Q3 | AI | Magicell | 4.6 TSSR Approved |  | 2024-05-28 | 2024-06-07 |  | 2024-06-13 |  | Under Approval | 2024-12-05 | 2024-12-06 | E//Razif | 2024-12-06 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240510 | DU00002861620 |  |  | 2024-10-27 | 2024-10-25 |  | Lampole | Land site | 17 | Add R8862A S9000x3+R8894E M1821x1 | 0 | 2
3081C | PRIMA Presint 11 | Central |  | Decomm | Modernization->Decomm | 2024 Q3 | SY1 | YPTT | 4.6 TSSR Approved |  | 2024-05-31 |  |  |  | 2024-06-04 |  | 2024-06-05 | 2025-03-07 | E//Razif | 2024-06-05 | BOQ_Celcom Digi_RAN-YPTT-Standard PR TSS-20240605 | DU00002861621 |  |  |  |  | 2024-12-19 |  | Land site
S01252 | Simpang Jeragan | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861622 | [6 empty] | #N/A
S01248 | Mercu Puspita | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861623 | [6 empty] | #N/A
W00008 | W066V_W00008OD_BKTBANDARAYA | Central |  | Decomm |  | 2024 Q2 | ZB | Ascentrack | 4.6 TSSR Approved |  | 2023-11-29 |  |  |  | 2023-12-12 |  | 2024-01-16 | 2025-06-17 | CD//Sapian | 2024-02-25 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231201 | DU00002861624 |  |  |  |  | 2024-08-10 |  | BOOM
B00516 | B061S_B00516OD_KAMDAR | Central |  | Decomm |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-02-16 |  |  |  | 2024-02-19 |  | 2024-02-19 | 2024-09-25 | CD//Sapian | 2024-02-27 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240217 | DU00002861625 |  |  |  |  | 2024-07-31 |  | BOOM
W00235 | W066T_W00235OD_DESABUSPARK | Central |  | Decomm |  | 2024 Q3 | BY | AllStar | 4.6 TSSR Approved |  | 2024-02-02 |  |  |  | 2024-02-16 |  | 2024-07-25 | 2025-03-11 | CD//Norhaliza | 2024-08-02 | BOQ CelcomDigi_RAN_AllStar_Standard PR TSS_Central_202400202 | DU00002861626 |  |  |  |  | 2024-05-24 |  | BOOM
B02156 | B064A_B02156OD_MJDPKNBT14ULULANGAT | Central |  | Decomm |  | 2024 Additional | CR | GCI | 4.6 TSSR Approved |  | 2023-10-25 |  |  |  | 2023-12-01 |  | 2023-12-08 | 2025-03-21 | CD//Norhaliza | 2024-12-13 | CelcomDigi_RAN_GCI_TSS_Central_20231028 | DU00002861627 |  |  |  |  | 2025-03-17 |  | LAMP_POLE
B00387 | B061J_B00387OD_PUCHONGJAYA3 | Central |  | Decomm |  | 2024 Q3 | SM | Magicell | 4.6 TSSR Approved |  | 2024-02-28 |  |  |  | 2024-03-11 |  | 2024-04-17 | 2025-03-14 | CD//Ali Akaram | 2024-05-13 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240303 | DU00002861628 |  |  |  |  | 2024-11-05 |  | BOOM
W01541 | W066G_W01541OD_MEDANIDAMAN2 | Central |  | Decomm |  | 2024 Q1 | SY1 | GTSB | 4.6 TSSR Approved |  | 2024-06-15 | 2024-08-06 |  |  | 2024-07-11 |  | 2024-07-15 | 2024-09-25 | CD//Sapian | 2024-09-09 | Wireless+ Malaysia CD+TSS+ GTSB+9 site SQ202410310159 | DU00002861629 |  |  |  |  | 2024-08-12 | Lampole | LAMP_POLE | 18
W01205 | W066Q_W01205OD_LINK_EASTWEST_SOUTHSALAK | Central |  | Decomm |  | 2024 Q3 | SY1 | GCI | 4.6 TSSR Approved |  | 2024-09-30 |  | 2024-10-02 |  | 2024-10-06 |  | 2024-10-07 |  | CD//Sapian | 2024-10-14 | 0809CD-Central-GCI-BOQ Template(new contract) | DU00002861630 |  |  |  |  | 2024-09-29 |  | TOWER
B00688 | B064E_B00688OD_KJGUTAMA | Central |  | Decomm |  | 2024 Q4(single site MOCN)-L26 SSM | AI | GCI | 4.6 TSSR Approved |  | 2024-10-21 |  | 2024-10-23 |  | 2024-11-15 |  | 2024-11-18 | 2024-12-31 | CD//Sapian | 2024-11-26 | 0924CD-Central-GCI-BOQ Template(new contract) | DU00002861631 |  |  |  |  | 2024-10-28 |  | BOOM
W00818 | W066S_W00818OD_TMNGEMBIRA3 | Central |  | Decomm |  | 2024 Q3 | BY | GCI | 4.6 TSSR Approved |  | 2024-02-16 |  |  |  | 2024-02-23 |  | 2024-03-27 | 2025-03-21 | CD//Sapian | 2024-04-17 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240217 | DU00002861632 |  |  |  |  | 2024-08-19 |  | MONOPOLE
W01480 | W066AA_W01480OD_MEDANSELERA_BDRSRIPERMAISURI | Central |  | Decomm | Decomm-On Hold->Decomm | 2024 Q3 | BY | AllStar | 4.6 TSSR Approved |  | 2024-02-01 |  |  |  | 2024-02-15 |  | 2024-03-27 | 2024-07-12 | CD//Norhaliza | 2024-06-10 | BOQ CelcomDigi_RAN_AllStar_Standard PR TSS_Central_20240128 | DU00002861633 |  |  |  |  | 2025-05-28 |  | LAMP_POLE
9722B | Kampung Luak | Sarawak |  | Modernization | Modernization->On Hold->Modernization | 2025 Q1 | AI | Trintel | 4.6 TSSR Approved |  | 2023-10-19 | 2023-10-27 |  | 2025-04-30 |  | Closed | 2025-04-30 | 2025-05-20 | E//Hannah | 2025-05-08 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231017 | DU00002861634 |  |  | 2025-05-19 | 2025-05-16 |  | Monopole | In-Building System | 30 | Add R8852E S9000x3+R9264M M1821x3, Dismantle R8894E M1821(A8A)x3 | 0 | 0
W00022 | W066J_W00022OD_WANGSAMELAWATI | Central |  | Decomm |  | 2024 Q1 | SH | GTSB | 4.6 TSSR Approved |  | 2024-03-14 |  |  |  | 2024-03-26 |  | 2024-03-28 | 2024-07-12 | CD//Norhaliza | 2024-06-06 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240316 | DU00002861635 |  |  |  |  | 2024-03-23 |  | BOOM
B01521 | W066I_B01521OD_PSSBKTABANGSA | Central |  | Decomm | Decomm->On Hold->Decomm | 2024 Q1 | AI | Magicell | 4.6 TSSR Approved | 2/9 pending PTW approval// 14/8 - skylift to confirm, team pending revert // 5/8- Team revert need skylift, | 2025-09-19 |  | 2025-09-24 |  | 2025-09-29 |  | 2025-10-03 |  | CD//Sapian | 2025-10-06 | SQ202506210252 | DU00002861636 |  |  |  |  | 2025-10-16 |  | PYLON
B01971 | W066J_B01971OD_TMNPERMATAINDAHRD | Central |  | Decomm | Decomm->On Hold->Decomm | 2024 Q1 | AI | GTSB | 14.1 TSSR Not Required (Decomm by CD) | [6 empty] | To be Submitted |  |  | CD//Sapian |  | 0809CD-Central-GTSB-BOQ Template(new contract) | DU00002861637 |  |  |  |  | 2024-11-25 |  | MINI STRUCTURE
W00051 | W066R_W00051OD_STCSGBESI | Central |  | Decomm |  | 2024 Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2023-11-06 |  |  |  | 2023-11-27 |  | 2023-12-06 | 2025-03-14 | CD//Ali Akaram | 2024-07-17 | CelcomDigi_RAN_Magicell_TSS_Central_20231113 | DU00002861638 |  |  |  |  | 2024-08-28 |  | SHARING STRC DIGI
W01021 | W066H_W01021OD2_PUNCAKWANGSA | Central |  | Decomm |  | 2024 Q1 | SS | YPTT | 4.6 TSSR Approved |  | 2023-12-07 |  |  |  | 2023-12-15 |  | 2024-01-05 | 2024-02-15 | CD//Norhaliza | 2024-01-23 | CelcomDigi_RAN_YPTT_TSS_Central_20231224 | DU00002861639 |  |  |  |  | 2024-07-12 |  | UNIPOLE
W00378 | W066N_W00378OD_WISMACENTRAL | Central | 1234K | Decomm |  | 2024 Q2 | SHA | Magicell | 4.6 TSSR Approved |  | 2024-02-13 |  |  |  | 2024-02-15 |  | 2024-08-23 | 2024-12-31 | CD//Sapian | 2024-09-10 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240218 | DU00002861640 |  |  |  |  | 2024-08-24 |  | BOOM
B00542 | B064A_B00542OD_TMNSUNTEX | Central |  | Decomm |  | 2024 Q4 | SM | GTSB | 4.6 TSSR Approved |  | 2024-03-13 |  |  |  | 2024-03-18 |  | 2024-05-16 | 2025-05-27 | CD//Norhaliza | 2024-08-23 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240316 | DU00002861641 |  |  |  |  | 2024-10-23 |  | BOOM
B00429 | B064E_B00429OD_TMNBKTMEWAH2 | Central | 1906K | Swap | Decomm->On Hold->Swap | 2024 Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-05 | 2025-06-26 |  | 2025-06-28 | 2024-01-17 | Closed | 2024-01-18 | 2024-09-25 | CD//Sapian | 2025-07-03 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240108 | DU00002861642 | SOW Changed from On Hold to Swap, previously Decomm TSSR submitted |  | 2025-08-22 | 2025-08-21 |  | Minimast | TRIPOD | 9m | Add R8862A S9000x3+R8894E M1821x3, Dismantle
W01554 | B057D_W01554OD_TMNKOPERASIPOLIS3 | Central |  | Decomm |  | 2024 Q1 | SM | Magicell | 4.6 TSSR Approved |  | 2023-12-08 |  |  |  | 2023-12-15 |  | 2024-01-17 | 2024-10-29 | CD//Norhaliza | 2024-01-30 | CelcomDigi_RAN_Magicell_TSS_Central_20231214 | DU00002861643 |  |  |  |  | 2024-04-01 |  | LAMP_POLE
W01035 | W066V_W01035OD_RD_SHOPLOTJALANTELAWIRD | Central |  | Decomm |  | 2024 Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-29 |  |  |  | 2023-12-04 |  | 2023-12-06 |  | CD//Sapian | 2023-12-12 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231201 | DU00002861644 |  | Missing antenna TX photo at NE & Missing FE part |  |  | 2024-07-17 |  | Rooftop
4468D | TM Pendang | Northern |  | Modernization |  | 131 single site mocn | SM | GTSB | 4.6 TSSR Approved |  | 2024-11-02 | 2024-11-05 |  | 2024-11-07 |  | Rectificating | 2024-11-08 | 2024-11-14 | E//Hazida | 2024-11-12 | 0809CD-Northern-GTSB-BOQ Template(new contract) | DU00002861645 |  |  | 2025-04-14 | 2024-08-28 |  | Tower | 60M 4 LEGGED Tower | 60M | Add R8862A S9000 x3+A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123 | 0
B00815 | B064C_B00815OD_TMNUNIVINDAH | Central |  | Decomm |  | 2024 Q3 | CR | GCI | 4.6 TSSR Approved |  | 2024-03-18 |  |  |  | 2024-03-20 |  | 2024-04-17 | 2024-12-09 | CD//Sapian | 2024-05-08 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240323 | DU00002861646 |  |  |  |  | 2024-08-28 |  | TRIPOD
B00233 | W066BB_B00233OD_ALAMJAYA | Central |  | Decomm |  | 2024 Q4 | BY | GTSB | 4.6 TSSR Approved |  | 2024-01-04 |  |  |  | 2024-01-09 |  | 2024-05-16 | 2024-07-19 | CD//Ali Akaram | 2024-07-18 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240108 | DU00002861647 |  |  |  |  | 2024-10-26 |  | BOOM
W01385 | W066BB_W01385OD_KETUMBARHILL_CHERASUTAMA | Central |  | Decomm |  | 2024 Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-11-20 |  |  |  | 2023-11-25 |  | 2023-11-27 | 2024-01-22 | CD//Norhaliza | 2024-01-05 | CelcomDigi_RAN_AllStar_TSS_Central_20231120 | DU00002861648 |  |  |  |  | 2024-07-27 |  | LAMP_POLE
W00928 | W066R_W00928OD_KEMSGBESI4 | Central |  | Decomm |  | 2024 Q3 | SY1 | Magicell | 4.6 TSSR Approved |  | 2024-07-29 |  | 2024-08-06 |  | 2024-08-13 |  | 2024-08-13 | 2025-01-14 | CD//Norhaliza | 2024-10-03 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240510 - Decomm | DU00002861649 |  |  |  |  | 2024-12-27 |  | AESTHETIC MONOPOLE
W01020 | W066T_W01020OD_TMNGEMBIRA | Central |  | Decomm |  | 2024 Q3 | ZA | AllStar | 4.6 TSSR Approved |  | 2023-12-22 |  |  |  | 2023-12-28 |  | 2024-01-18 | 2024-02-15 | CD//Norhaliza | 2024-02-06 | CelcomDigi_RAN_AllStar_TSS_Central_20231224 | DU00002861650 |  |  |  |  | 2024-05-24 |  | LAMP_POLE
B00603 | W066Y_B00603OD_TMNMELUR | Central |  | Decomm |  | 2024 Q4 | BY | GTSB | 4.6 TSSR Approved |  | 2024-03-14 |  |  |  | 2024-03-18 |  | 2024-07-23 | 2024-07-30 | CD//Sapian | 2024-07-24 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240316 | DU00002861651 |  |  |  |  | 2024-08-24 |  | BOOM
W00597 | W066H_W00597OD_BKTWANGSAMAS | Central |  | Decomm |  | 2024 Q1 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-01-12 |  |  |  | 2024-01-31 |  | 2024-02-01 |  | CD//Sapian | 2024-02-07 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240115 | DU00002861652 |  | Missing FE part |  |  | 2024-05-03 |  | SHARING STRC DIGI
W00977 | W066Q_W00977OD_SMARTTUNELOFFICE | Central |  | Decomm |  | 2024 Q3 | BY | Ascentrack | 4.6 TSSR Approved |  | 2024-02-14 |  |  |  | 2024-02-17 |  | 2024-03-27 | 2024-04-24 | CD//Ali Akaram | 2024-04-03 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240217 | DU00002861653 |  |  |  |  | 2025-01-28 |  | TRIPOD
B01236 | B061J_B01236OD_BDRPCHGJAYA2 | Central |  | Decomm |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-12-19 |  |  |  | 2024-01-24 |  | 2024-04-17 |  | CD//Norhaliza | 2024-08-09 | CelcomDigi_RAN_Datasco_TSS_Central_20231227 | DU00002861654 |  | Missing antenna TX photo at NE Missing FE part |  |  | 2024-09-27 |  | LAMP_POLE
B00702 | B064G_B00702OD_TMNUNIVKJG2 | Central |  | Decomm | Decomm->On Hold->Decomm->On Hold->Decomm | 2024 Q4 | SS | GTSB | 4.6 TSSR Approved |  | 2024-08-30 |  | 2024-09-18 |  | 2024-11-06 |  | 2024-11-29 | 2024-12-31 | CD//Sapian | 2024-12-04 | 0919CD-Central-GTSB-BOQ Template(new contract) 2 | DU00002861655 |  |  |  |  | 2025-06-24 |  | SHARING STRC MAXIS
B01956 | B061J_B01956OD_MAWARPUCHONG | Central |  | Decomm |  | 2024 Q3 | CR | Datasco | 15.3 Decomm Done without TSSR |  | 2024-01-31 |  |  |  |  | To be Submitted |  |  | CD//Sapian |  | 0809CD-Central-Datasco-BOQ Template(new contract) | DU00002861656 |  | Missing antenna tx photo at NE & FE part |  |  | 2024-10-01 |  | UNIPOLE
B01072 | B064G_B01072OD_KAMSISKAUSARUKM | Central |  | Decomm |  | 2024 Additional | AI | GTSB | 4.6 TSSR Approved |  | 2024-09-23 |  | 2024-09-27 |  | 2024-10-21 |  | 2024-11-20 | 2025-01-14 | CD//Norhaliza | 2024-12-09 | 0925CD-Central-GTSB-BOQ Template(new contract) | DU00002861657 |  |  |  |  | 2025-04-18 |  | AESTHETIC MONOPOLE
B00766 | B064G_B00766OD_KOLEJKERISMAS | Central |  | Decomm |  | 2024 Additional | SM | GTSB | 4.6 TSSR Approved |  | 2024-08-30 |  | 2024-09-18 |  | 2024-09-23 |  | 2024-12-09 | 2025-01-14 | CD//Sapian | 2024-12-12 | 0919CD-Central-GTSB-BOQ Template(new contract) 2 | DU00002861658 |  |  |  |  | 2025-04-23 |  | TOWER
B00521 | B061Q_B00521OD_IJM | Central |  | Decomm |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-03-07 |  |  |  | 2024-05-14 |  | 2024-05-16 | 2024-07-12 | CD//Sapian | 2024-05-29 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240311 | DU00002861659 | [6 empty] | BOOM
B00386 | B061P_B00386OD_SS24PJ | Central |  | Decomm |  | 2024 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2024-02-23 |  |  |  | 2024-04-30 |  | 2024-05-07 | 2024-05-27 | CD//Sapian | 2024-05-16 | CelcomDigi_RAN_GTSB_TSS_Central_20240509 | DU00002861660 |  |  |  |  | 2024-07-04 |  | MINI STRUCTURE
B00740 | B061T_B00740OD_SENTOSASEK17PJ | Central | 1888K | Swap | Decomm->Swap->On Hold->Swap | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-06-05 | 2024-06-12 |  | 2024-06-14 |  | Under Approval | 2024-06-14 | 2024-09-25 | CD//Sapian | 2024-09-25 | 0619Central-CCSMY-BOQ Template (template) | DU00002861661 |  |  | 2024-09-20 | 2024-09-13 |  | Minimast | BOOM | 4.5 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle | 0 | 0
B02248 | B061O_B02248OD_SS22KDUDSARAJAYA | Central |  | Decomm |  | 2024 Q3 | SM | DATASCO | 4.6 TSSR Approved |  | 2024-05-03 |  |  |  | 2024-05-17 |  | 2024-05-20 |  | CD//Norhaliza | 2024-07-17 | CelcomDigi_RAN_Datasco_TSS_Central_20240513 | DU00002861662 |  |  |  |  | 2024-08-26 |  | BOOM
B00047 | B061K_B00047OD_PCHGUTAMA | Central |  | Decomm |  | 2024 Q3 | SM | Magicell | 4.6 TSSR Approved |  | 2024-03-05 |  |  |  | 2024-03-10 |  | 2024-04-17 | 2024-07-10 | CD//Ali Akaram | 2024-05-10 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240311 | DU00002861663 |  |  |  |  | 2024-09-26 |  | BOOM
B01957 | B061P_B01957OD_SS23PJ | Central |  | Decomm |  | 2024 Q3 | SM | Magicell | 4.6 TSSR Approved |  | 2023-11-07 |  |  |  | 2024-01-05 |  | 2024-03-26 |  | CD//Ali Akaram | 2024-04-02 | CelcomDigi_RAN_Magicell_TSS_Central_20231113 | DU00002861664 |  | 3) Missing FE part |  |  | 2024-06-04 |  | UNIPOLE
B00172 | B061H_B00172OD_TMNSRIMANJA | Central |  | Decomm |  | 2024 Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2024-03-13 |  |  |  | 2024-05-17 |  | 2024-05-21 | 2024-07-19 | CD//Sapian | 2024-06-04 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240316 | DU00002861665 |  |  |  |  | 2024-05-30 |  | MINI MONOPOLE
W00148 | W066T_W00148OD_BT3JKL | Central |  | Decomm |  | 2024 Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2024-01-22 |  |  |  | 2024-02-01 |  | 2024-02-05 | 2024-02-23 | CD//Norhaliza | 2024-02-15 | BOQ CelcomDigi_RAN_AllStar_Standard PR TSS_Central_20240128 | DU00002861666 |  |  |  |  | 2024-08-12 |  | BOOM
W01034 | W066T_W01034OD_RD_GOLDENBRIGHTRD | Central |  | Decomm |  | 2024 Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-12-05 |  |  |  | 2023-12-07 |  | 2023-12-08 | 2024-07-12 | CD//Ali akaram | 2024-06-10 | CelcomDigi_RAN_Allstar_TSS_Central_20231208 | DU00002861667 |  |  |  |  | 2024-05-24 |  | UNIPOLE
W00083 | W066BB_W00083OD_TMNCHERAS | Central |  | Decomm |  | 2024 Q3 | SM | AllStar | 4.6 TSSR Approved |  | 2023-11-28 |  |  |  | 2024-01-24 |  | 2024-03-26 | 2024-04-24 | CD//Sapian | 2024-04-08 | CelcomDigi_RAN_AllStar_TSS_Central_20231126 | DU00002861668 |  |  |  |  | 2024-07-30 |  | MINI STRUCTURE
B01660 | B064B_B01660OD_TMNSETIA2BALAKONG | Central |  | Decomm |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-02-06 |  |  |  | 2024-02-14 |  | 2024-04-18 | 2024-09-25 | CD//Norhaliza | 2024-08-09 | CelcomDigi_RAN_GTSB_TSS_Central_20231201 | DU00002861669 |  |  |  |  | 2024-08-28 |  | UNIPOLE
B00333 | W066J_B00333OD_AU2C | Central |  | Decomm |  | 2024 Q1 | CR | In-House | 14.1 TSSR Not Required (Decomm by CD) | [6 empty] | To be Submitted |  |  | CD//Sapian |  | 0809CD-Central-GCI-BOQ Template(new contract) | DU00002861670 |  |  |  |  | 2024-11-25 |  | BOOM
W00176 | W066H_W00176OD_WANGSAMAJU | Central |  | Decomm |  | 2024 Q1 | AD | Ascentrack | 4.6 TSSR Approved |  | 2024-01-15 |  |  |  | 2024-02-02 |  | 2024-02-07 | 2025-03-25 | CD//Norhaliza | 2024-02-14 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240116 | DU00002861671 |  |  |  |  | 2024-05-18 | Tower | 3 Legged Tower
W00274 | W066V_W00274OD_KOLEJKINABALU | Central |  | Decomm | Decomm->On Hold->Decomm | 2024 Q3 | SS | YPTT | 4.6 TSSR Approved |  | 2023-11-21 |  |  |  | 2023-11-24 |  | 2023-11-28 | 2024-04-24 | CD//Ali Akaram | 2023-12-07 | CelcomDigi_RAN_YPTT_TSS_Central_20231126 | DU00002861672 |  |  |  |  | 2024-08-17 |  | MINI STRUCTURE
W00133 | W066AA_W01536OD_LNJAYABTR2 | Central |  | Decomm | Decomm-Site Out->Decomm | 2024 Q3 | AI | GCI | 15.3 Decomm Done without TSSR |  | 2025-07-04 |  | 2025-07-10 |  |  | To be Submitted |  |  | CD//Sapian |  | SQ202506140192 | DU00002861673 |  |  |  |  | 2025-06-25 |  | TRIPOD
W00236 | W066T_W00236OD_PR_JLKUCHAILAMA | Central |  | Decomm |  | 2024 Q3 | AD | AllStar | 4.6 TSSR Approved |  | 2023-12-08 |  |  |  | 2024-03-13 |  | 2024-03-18 | 2024-09-05 | CD//Ali Akaram | 2024-04-03 | BOQ CelcomDigi_RAN_AllStar_Standard PR TSS_Central_20240128 | DU00002861674 |  |  |  |  | 2024-05-24 |  | TRIPOD
W00034 | W066V_W00034OD_JLNARABANGSAR | Central |  | Decomm |  | 2024 Q2 | ZB | Ascentrack | 4.6 TSSR Approved |  | 2023-11-30 |  |  |  | 2023-12-13 |  | 2024-01-21 |  | CD//Sapian | 2024-01-27 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231203 | DU00002861675 |  | Missing FE part |  |  | 2024-08-16 |  | BOOM
W01114 | W066H_W01114OD_JLNAYERMADU | Central |  | Decomm |  | 2024 Q1 | CR | GTSB | 4.6 TSSR Approved |  | 2024-06-12 | 2024-06-14 |  |  | 2024-06-18 |  | 2024-06-21 | 2024-10-29 | CD//Norhaliza | 2024-10-03 | SQ202411080530 | DU00002861676 |  |  |  |  | 2024-08-07 | In-Building System | BOOM | 3M
W01013 | W066E_W01013OD_MSJD JAMIUL EHSAN | Central | 1864K | Swap | Decomm->On hold->Swap | 2024 Q1 | AI | Ascentrack | 4.6 TSSR Approved |  | 2024-01-15 | 2024-09-23 |  | 2024-11-22 | 2024-01-27 | Under Approval | 2024-11-25 | 2025-01-15 | CD//Sapian | 2024-04-17 | SQ202411070022 | DU00002861677 |  |  | 2025-02-26 | 2025-02-13 |  | Minaret | E-MINARATE | 33 | Add R8852E S9000 x3+R8894E M1821 x3,Dismantle | 0 | 0
B00893 | B061K_B00893OD_BDRPUTERIPCHG2 | Central |  | Decomm |  | 2024 Q3 | AD | Magicell | 4.6 TSSR Approved |  | 2024-03-09 |  |  |  | 2024-03-14 |  | 2024-04-04 | 2024-07-26 | CD//Sapian | 2024-05-28 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240311 | DU00002861678 |  |  |  |  | 2024-09-25 |  | BOOM
W00214 | W066S_W00214OD_KM48KESASOUG | Central |  | Decomm |  | 2024 Q3 | BY | GTSB | 4.6 TSSR Approved |  | 2024-01-29 |  |  |  | 2024-03-01 |  | 2024-03-14 | 2024-07-12 | CD//Norhaliza | 2024-06-06 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240202 | DU00002861679 |  |  |  |  | 2024-09-30 |  | SHARING STRC DIGI
B01835 | B061P_B01835OD_PR_TMNMAYANEMAS | Central |  | Decomm |  | 2024 Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2024-02-01 |  |  |  | 2024-02-05 |  | 2024-03-26 | 2024-07-12 | CD//Norhaliza | 2024-06-06 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240212 | DU00002861680 |  |  |  |  | 2024-05-29 |  | Rooftop
B00617 | B061L_B00617OD_MERANTIJAYA2 | Central |  | Decomm |  | 2024 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2024-03-04 |  |  |  | 2024-04-18 |  | 2024-05-07 | 2025-03-21 | CD//Norhaliza | 2024-08-22 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240311 | DU00002861681 |  |  |  |  | 2024-08-30 |  | TRIPOD
W00234 | W066V_W00234OD_INSTSISWAZAHUM | Central |  | Decomm | Decomm->On Hold->Decomm | 2024 Q3 | AI | Solusi | 4.6 TSSR Approved |  | 2024-11-07 |  |  |  | 2024-11-14 |  | 2024-11-15 |  | CD//Norhaliza | 2024-12-09 | 0924CD-Central-CCSMY-BOQ Template(new contract) | DU00002861682 |  | No Cisco Router photo |  |  | 2025-01-04 |  | BOOM
B02459 | B061P_B02459OD_TAMAN_MAYANGJAYA_SCT | Central |  | Decomm |  | 2024 Q3 | BY | GTSB | 4.6 TSSR Approved |  | 2024-02-01 |  |  |  | 2024-02-20 |  | 2024-02-22 | 2024-04-24 | CD//Ali Akaram | 2024-04-01 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240212 | DU00002861683 |  |  |  |  | 2024-05-30 |  | BOOM
B00016 | B061T_B00016OD_SEK11PJ | Central |  | Decomm |  | 2024 Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2024-07-24 |  | 2024-07-30 |  | 2024-08-01 |  | 2024-08-02 | 2025-03-11 | CD//Sapian | 2024-08-05 | 0725Central-GTSB-BOQ Template(new contract) | DU00002861684 |  |  |  |  | 2024-08-27 |  | MINI STRUCTURE
B01961 | B061Q_B01961OD_JLNGASING | Central |  | Decomm |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-30 |  |  |  | 2023-12-11 |  | 2023-12-12 | 2024-10-29 | CD//Sapian | 2024-02-20 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231203 | DU00002861685 |  |  |  |  | 2024-07-04 |  | TRIPOD
B02374 | B061S_B02374OD_SEKSYEN22_PJ | Central |  | Decomm |  | 2024 Q3 | SM | GTSB | 4.6 TSSR Approved | ¦ 0503 - Emailed planning team on CD query | 2024-02-14 |  |  |  | 2024-02-15 |  | 2024-12-04 | 2025-03-21 | CD//Ali Akaram | 2024-12-16 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240217 | DU00002861686 |  |  |  |  | 2024-05-31 |  | LAMP_POLE
B01077 | B061L_B01077OD_TMNPUTRAPRIMA | Central |  | Decomm |  | 2024 Q3 | BY | Magicell | 4.6 TSSR Approved |  | 2024-02-21 |  |  |  | 2024-02-22 |  | 2024-06-04 | 2024-07-10 | CD//Ali akaram | 2024-07-02 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240225 | DU00002861687 |  |  |  |  | 2024-09-27 |  | TRIPOD
B01483 | B061J_B01483OD_BK4BDRKINRARA | Central |  | Decomm | Decomm->On Hold->Decomm->On Hold->Decomm | 2024 Q3 | HW | GTSB | 4.6 TSSR Approved |  | 2025-01-24 |  | 2025-02-14 |  | 2025-02-24 |  | 2025-02-26 |  | CD//Sapian | 2025-03-05 | S1MY2024071003WBF1-1407 | DU00002861688 |  | Pls provide TX Antenna photo at NE & FE part |  |  | 2025-03-17 |  | LAMP_POLE
B01227 | B061K_B01227OD_BDRPUTERIPCHG3 | Central |  | Decomm |  | 2024 Q3 | SM | Magicell | 4.6 TSSR Approved |  | 2024-03-19 |  |  |  | 2024-03-24 |  | 2024-04-23 | 2024-07-10 | CD//Ali Akaram | 2024-05-13 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240323 | DU00002861689 |  |  |  |  | 2024-09-26 |  | TRIPOD
B00773 | B061L_B00773OD_PCHGJAYA2 | Central |  | Decomm |  | 2024 Q3 | SHA | Magicell | 4.6 TSSR Approved |  | 2023-10-20 |  |  |  | 2024-07-18 |  | 2024-07-19 |  | CD//Sapian | 2024-07-30 | CelcomDigi_RAN_Magicell_TSS_Central_20231021 | DU00002861690 |  |  |  |  | 2024-09-29 |  | MINI STRUCTURE
W00060 | W066AA_W00060OD_TMNMIDAH2 | Central |  | Decomm | Decomm->On Hold->Decomm | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-03 |  |  |  | 2023-11-17 |  | 2023-11-20 | 2024-02-07 | CD//Sapian | 2023-11-27 | 0923CD-Central-Ascentrak-BOQ Template(new contract) | DU00002861691 |  |  |  |  | 2024-09-25 |  | MINI MONOPOLE
B01827 | W066X_B01827OD_RD_TMNBKTAMPANG | Central |  | Decomm |  | 2024 Q4 | BY | GTSB | 4.6 TSSR Approved |  | 2024-01-29 |  |  |  | 2024-03-01 |  | 2024-03-14 | 2024-07-19 | CD//Ali Akaram | 2024-07-19 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240202 | DU00002861692 |  |  |  |  | 2024-08-26 |  | UNIPOLE
B00451 | W066X_B00451OD_TMNKOSAS2 | Central |  | Decomm |  | 2024 Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-07 |  |  |  | 2023-11-10 |  | 2023-11-14 | 2023-11-29 | CD//Sapian | 2023-11-19 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231113 | DU00002861693 |  |  |  |  | 2024-08-22 |  | TRIPOD
B00334 | W066I_B00334OD_KYOTOGARDEN | Central |  | Decomm |  | 2024 Q1 | SY1 | DATASCO | 4.6 TSSR Approved |  | 2024-07-10 |  | 2024-08-11 |  | 2024-07-12 |  | 2024-07-15 |  | CD//Ali akaram | 2024-07-22 | 0725Central-Datasco-BOQ Template(old contract) | DU00002861694 |  |  |  |  | 2024-07-25 |  | BOOM
W00127 | W066S_W00127OD_TMNTANYEWLAI | Central |  | Decomm |  | 2024 Q3 | SH | GTSB | 4.6 TSSR Approved |  | 2024-03-21 |  |  |  | 2024-03-26 |  | 2024-03-28 | 2024-07-12 | CD//Ali Akaram | 2024-04-08 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240323 | DU00002861695 |  |  |  |  | 2024-05-29 |  | BOOM
B02786 | B061J_B02786OD_SUPERTREAD_TS | Central |  | Decomm |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-01-26 |  |  |  | 2024-01-31 |  | 2024-02-05 |  | CD//Ali Akaram | 2024-07-29 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240202 | DU00002861696 |  | Missing FE part |  |  | 2024-09-27 |  | UNIPOLE
W00697 | W066V_W00697OD_JLNBANGKONG | Central |  | Decomm |  | 2024 Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-29 |  |  |  | 2023-12-01 |  | 2023-12-12 | 2024-10-29 | CD//Sapian | 2023-12-21 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231201 | DU00002861697 |  |  |  |  | 2024-07-22 |  | LAMP_POLE
L00148 | S113A_L00148OD_BKTKUDA | Sabah |  | Decomm |  | 2025 Q1 | HW | Datasco | 4.6 TSSR Approved |  | 2024-06-07 | 2024-06-13 |  |  | 2025-01-24 | To be Submitted | 2025-03-12 |  | CD//Sharidah | 2025-03-17 | SQ202501020441 - Datasco / SQ202501070240 - Datasco | DU00002861698 |  |  |  |  | 2025-03-20 | Monopole | LAMP_POLE | 30
B01410 | B061L_B01410OD_BDRBKTPCHG4 | Central |  | Decomm |  | 2024 Q3 | SH | GTSB | 4.6 TSSR Approved |  | 2024-01-10 |  |  |  | 2024-05-23 |  | 2024-05-30 | 2024-07-12 | CD//Ali akaram | 2024-06-14 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240115 | DU00002861699 |  |  |  |  | 2024-08-28 |  | LAMP_POLE
W00200 | W066BB_W00200OD_TMNBILLION | Central |  | Decomm | Decomm->On Hold->Site Out->Decomm | 2024 Q3 | SM | AllStar | 4.6 TSSR Approved |  | 2024-01-17 |  |  |  | 2024-01-30 |  | 2024-03-27 | 2024-04-24 | CD//Sapian | 2024-04-17 | CelcomDigi_RAN_AllStar_TSS_Central_20231126 | DU00002861700 |  |  |  |  | 2024-07-31 |  | MINI STRUCTURE
W01001 | W066V_W01001OD_JLNKERINCHI | Central |  | Decomm |  | 2024 Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2023-12-28 |  |  |  | 2024-01-18 |  | 2024-01-22 | 2024-05-27 | CD//Sapian | 2024-05-06 | BOQ CelcomDigi_RAN_AllStar_Standard PR TSS_Central_20240108 | DU00002861701 |  |  |  |  | 2024-09-09 |  | LAMP_POLE
B02237 | W066I_B02237OD_SYABASMELAWATI | Central |  | Decomm |  | 2024 Q1 | BY | GTSB | 4.6 TSSR Approved |  | 2024-03-09 |  |  |  | 2024-04-05 |  | 2024-04-15 | 2024-05-31 | CD//Sapian | 2024-05-06 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240311 | DU00002861702 |  |  |  |  | 2024-04-30 |  | MONOPOLE
B00265 | W066I_B00265OD_FASA4MELAWATI | Central |  | Decomm |  | 2024 Q1 | BY | GTSB | 4.6 TSSR Approved |  | 2024-03-13 |  |  |  | 2024-04-06 |  | 2024-04-15 | 2025-03-21 | CD//Norhaliza | 2024-08-09 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240316 | DU00002861703 |  |  |  |  | 2024-03-26 |  | BOOM
B00724 | B064E_B00724OD_KJGPRIMA | Central |  | Decomm |  | 2024 Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-16 |  |  |  | 2024-06-20 |  | 2024-06-21 | 2025-03-07 | CD//Norhaliza | 2024-08-09 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240117 | DU00002861704 |  |  |  |  | 2024-10-11 |  | BOOM
9699C | Kapit Town (REL) | Sarawak |  | Modernization |  | 2025 Q3 | AI | Trintel | 4.6 TSSR Approved |  | 2025-03-17 | 2025-04-23 |  | 2025-05-23 |  | Under Approval | 2025-05-07 | 2025-05-21 | E//John | 2025-05-19 | SQ202503030411-Trintel | DU00002861705 |  |  | 2025-06-28 | 2025-05-29 |  |  | In-Building System | 2 | Add R8862A S9000x3,Dismantle R8854 S2600(A4A) x1+R9224E M1821(AAB) x1 | 0 | 0
B00230 | B064H_B00230OD_CIOIPALACE | Central | 1844K | Swap | Decomm->Swap | 2024 Q3 | CR | GCI | 4.6 TSSR Approved |  | 2024-05-13 | 2024-05-24 |  | 2024-06-21 |  | Rectificating | 2024-07-15 | 2024-07-25 | CD//Sapian | 2024-07-25 | CelcomDigi_RAN_GCI_TSS_Central_20240517 | DU00002861706 |  |  | 2024-12-22 | 2024-11-04 |  | In-Building System | BOOM | 5 | Add R8862A S9000 x1+R9264H M901821 x3+R8862A S2601 x4+A9732 M1821 x1,Dismantle | 2 | 0
2803C | Taman Perindustrian Puchong (EB) | Central |  | Modernization |  | 2024 Q3 |  | Solusi | 4.6 TSSR Approved |  | 2024-03-28 | 2024-02-19 |  | 2024-04-22 |  | Closed | 2024-05-06 | 2024-07-11 | E//Sumitra | 2024-07-11 | BOQ CelcomDigi_RAN_Solusi_Standard PR TSS_Central_20240329 | DU00002861707 |  |  | 2024-06-23 | 2024-06-23 |  | Lampole | Land site | 30 | Add R8862A S9000 x3+R9224E M1821 x1+R8854 S2600 x1,Dismantle | 0 | 3
B00149 | W067A_B00149OD_PR_CYBERDAIL | Central |  | Decomm |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-23 |  |  |  | 2024-02-23 |  | 2024-04-17 | 2024-07-19 | CD//Sapian | 2024-05-11 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240128 | DU00002861708 |  |  |  |  | 2024-11-22 |  | LAMP_POLE
B00113 | B064H_B00113OD_UNITEN | Central |  | Decomm |  | 2024 Q3 | HW | GTSB | 4.6 TSSR Approved |  | 2025-01-16 |  | 2025-01-23 | 2025-02-14 | 2025-02-17 | Under Approval | 2025-02-18 | 2025-03-11 | CD//Sapian | 2025-02-21 | 0924CD-Central-Solusi-BOQ Template(new contract) | DU00002861709 |  |  |  |  | 2025-04-24 |  | TRIPOD
B00061 | B064D_B00061OD_SGLONG4 | Central |  | Decomm |  | 2024 Q4 | SH | YPTT | 4.6 TSSR Approved |  | 2024-02-15 |  |  |  | 2024-02-15 |  | 2024-05-20 |  | CD//Sapian | 2024-06-12 | BOQ_Celcom Digi_RAN-YPTT-Standard PR TSS-20240218 | DU00002861710 |  |  |  |  | 2024-09-26 |  | TOWER
W00598 | W066AA_W00598OD_BDRPERMAISURI | Central |  | Decomm |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-15 |  |  |  | 2024-01-30 |  | 2024-02-02 | 2024-09-25 | CD//Ali Akaram | 2024-02-15 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231116 | DU00002861711 |  |  |  |  | 2024-07-30 |  | MINI MONOPOLE
B00788 | B061Q_B00788OD_PR_JLNGASING2 | Central |  | Decomm |  | 2024 Q3 | SH | GTSB | 4.6 TSSR Approved |  | 2024-02-22 |  |  |  | 2024-03-12 |  | 2024-03-28 | 2024-07-12 | CD//Norhaliza | 2024-06-06 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240225 | DU00002861712 |  |  |  |  | 2024-05-29 |  | TRIPOD
B00170 | B064C_B00170OD_TMNBKTSERDANG | Central |  | Decomm |  | 2024 Q3 | SHA | GTSB | 4.6 TSSR Approved |  | 2024-09-20 |  | 2024-08-08 |  | 2024-10-02 |  | 2024-10-04 | 2025-10-01 | CD//Sapian | 2024-10-14 | 0925CD-Central-GTSB-BOQ Template(new contract) | DU00002861713 |  |  |  |  | 2024-09-25 |  | TOWER
W01041 | W066Q_W01041OD_SALAKSELATAN2 | Central |  | Decomm |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-01-10 |  |  |  | 2024-01-15 |  | 2024-03-27 | 2024-04-24 | CD//Ali Akaram | 2024-04-08 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240115 | DU00002861714 |  |  |  |  | 2024-07-29 |  | UNIPOLE
B00458 | B064C_B00458OD_PALACESERDANG | Central | 1233K | Decomm | Decomm-On Hold->Decomm | 2024 Q3 | BY | Magicell | 4.6 TSSR Approved |  | 2023-12-21 |  |  |  | 2024-01-23 |  | 2024-04-17 |  | CD//Norhaliza | 2024-08-09 | CelcomDigi_RAN_Magicell_TSS_Central_20231224 | DU00002861715 |  | TSSR showing IBc site not Outdoor site |  |  | 2025-06-19 |  | TRIPOD
B01147 | W066X_B01147OD_TMNHIJAUAMPANG | Central |  | Decomm |  | 2024 Q4 | SH | Ascentrack | 4.6 TSSR Approved |  | 2024-01-10 |  |  |  | 2024-01-10 |  | 2024-01-30 | 2024-02-23 | CD//Ali Akaram | 2024-02-19 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240115 | DU00002861716 |  |  |  |  | 2024-08-22 |  | LAMP_POLE
W00251 | W066V_W00251OD_BSAROUTDOOR | Central |  | Decomm | Decomm->On hold->Site Out | 2024 Q2 | SH | Ascentrack | 4.6 TSSR Approved |  | 2023-12-15 |  |  |  | 2023-12-20 |  | 2024-01-20 | 2024-10-29 | CD//Sapian | 2024-10-21 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231224 | DU00002861717 |  |  |  |  | 2024-10-31 |  | BOOM
W00417 | W066V_W00417OD_PR_NST | Central |  | Decomm |  | 2024 Q2 | AI | AllStar | 4.6 TSSR Approved | 1/3- Need old IBC TSSR for solution preparation. SA Halim support on TSSR collection. | 2024-01-19 |  |  |  | 2024-01-26 |  | 2024-02-01 | 2025-07-04 | CD//Norhaliza | 2024-02-13 | BOQ CelcomDigi_RAN_AllStar_Standard PR TSS_Central_20240128 | DU00002861718 |  |  |  |  | 2024-09-10 |  | BOOM
W00273 | W066Q_W00273OD_TMNSGBESI | Central |  | Decomm |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-02-19 |  |  |  | 2024-02-21 |  | 2024-12-04 | 2025-03-21 | CD//Sapian | 2024-12-10 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240225 | DU00002861719 |  |  |  |  | 2024-08-30 |  | MINI STRUCTURE
B01073 | B064F_B01073OD_TMNSRIKENARI | Central |  | Decomm |  | 2024 Q4 | SS | Magicell | 4.6 TSSR Approved |  | 2023-11-30 |  |  |  | 2023-12-07 |  | 2024-08-13 | 2024-05-27 | CD//Sapian | 2024-09-23 | CelcomDigi_RAN_Magicell_TSS_Central_20231203 | DU00002861720 |  |  |  |  | 2024-09-30 |  | TRIPOD
W01025 | W066BB_W01025OD_TMNSEGARBRANCH | Central |  | Decomm |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-01-10 |  |  |  | 2024-01-26 |  | 2024-06-10 | 2026-01-21 | CD//Norhaliza | 2024-08-09 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240115 | DU00002861721 |  |  |  |  | 2024-07-27 |  | UNIPOLE
B00690 | B063A_B00690OD_SGPELEK2 | Central |  | Decomm |  | 2024 Additional | HW | Solusi | 4.6 TSSR Approved |  | 2025-06-13 |  |  |  | 2025-06-19 |  | 2025-09-26 |  | CD//Sapian | 2025-06-30 | SQ202503110146 | DU00002861722 |  |  |  |  | 2025-06-19 |  | BOOM
B01319 | B063B_B01319OD_PR_KM10KLIA | Central |  | Decomm | Decomm->On Hold->Decomm | 2024 Additional | BY | GTSB | 4.6 TSSR Approved |  | 2024-02-26 |  |  |  | 2024-03-09 |  | 2024-05-17 | 2024-11-26 | CD//Norhaliza | 2024-11-21 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240303 | DU00002861723 |  |  |  |  | 2025-02-28 |  | LAMP_POLE
L00026 | S113A_L00026OD_MATRIKULASILABUAN | Sabah |  | Decomm |  | 2024 | AD | DATASCO | 4.6 TSSR Approved |  | 2025-01-14 |  | 2024-11-29 |  | 2025-02-11 |  | 2025-02-22 | 2025-05-02 | CD//Sharidah | 2025-02-24 | Celcom Digi_RAN-Datasco-Standard PR TSS-Sabah-20241030 | DU00002861724 |  |  |  |  | 2025-03-08 |  | BOOM
B01720 | W066X_B01720OD_SURAUUBUDIAH | Central |  | Decomm |  | 2024 Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-28 |  |  |  | 2023-11-29 |  | 2023-12-12 | 2024-11-26 | CD//Norhaliza | 2024-10-03 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231201 | DU00002861725 |  |  |  |  | 2024-08-22 |  | MINARATE
B00055 | W066I_B00055OD_TMNBKTMULIA | Central |  | Decomm |  | 2024 Q1 | BY | GTSB | 4.6 TSSR Approved |  | 2024-07-17 |  | 2024-07-30 |  | 2024-08-02 |  | 2024-08-06 | 2024-11-26 | CD//Norhaliza | 2024-09-09 | 0719Central-GTSB-BOQ Template | DU00002861726 |  |  |  |  | 2024-08-10 |  | SHARING STRC SBC
A00511 | A037B_A00511OD_SGSUMUN | Northern | 4255K | Swap | Swap->On Hold->Swap | 2024 Additional | SM | PERNEC | 4.6 TSSR Approved |  | 2025-01-24 | 2025-02-05 |  | 2025-02-10 |  | Under Approval | 2025-02-17 | 2025-02-25 | CD//Zulakmar | 2025-02-24 | SQ202501030333 - PERNEC | DU00002861727 |  |  | 2025-04-14 | 2025-03-11 |  | Tower | TOWER | 60 | Add R8852E S9000x3+R8894E M1821 x3+R8862A S2601x3, Dismantle | 0 | 0
W00136 | W066G_W00136OD_TMNBUNGARAYA | Central |  | Decomm |  | 2024 Q1 | SH | Ascentrack | 4.6 TSSR Approved |  | 2023-11-20 |  |  |  | 2023-12-26 |  | 2024-01-20 | 2024-07-12 | CD//Sapian | 2024-01-27 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231126 | DU00002861728 |  |  |  |  | 2024-05-11 |  | TRIPOD
W00758 | W066J_W00758OD_BKTSWANGSA3 | Central |  | Decomm |  | 2024 Q1 | MS | GCI | 4.6 TSSR Approved |  | 2024-01-23 |  |  |  | 2024-02-08 |  | 2024-02-14 | 2025-03-14 | CD//Norhaliza | 2024-08-09 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240128 | DU00002861729 |  |  |  |  | 2024-08-02 |  | LAMP_POLE
A00553 | FELDABESOUT2 | Northern | 4175P | Swap | Swap->On Hold->Swap | 2025 Q1 | SM | PERNEC | 4.6 TSSR Approved |  | 2025-02-18 | 2025-02-13 |  | 2025-02-18 |  | Under Approval | 2025-02-21 | 2025-02-26 | CD//Zulakmar | 2025-02-25 | SQ202501030333 - PERNEC | DU00002861730 |  |  | 2025-04-27 | 2025-03-19 |  | Tower | TOWER | 60 | Add R8852E S9000x3+R8894E M1821x3+R8862A S2601x3, Dismantle | 0 | 0
B01977 | B064D_B01977OD_TMNSEKAMAT | Central |  | Decomm |  | 2024 Q4 | AD | GCI | 4.6 TSSR Approved |  | 2024-10-21 |  | 2024-10-23 |  | 2024-10-24 |  | 2024-12-05 |  | CD//Sapian | 2024-12-06 | 0924CD-Central-GCI-BOQ Template(new contract) | DU00002861731 |  |  |  |  | 2024-10-25 |  | BOOM
B02719 | W066BB_B02719OD_JLNBS9_TMN_BKTSEGAR | Central |  | Decomm |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-08 |  |  |  | 2023-11-24 |  | 2023-11-28 |  | CD//Sapian | 2023-12-04 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231113 | DU00002861732 |  | Wrong FE |  |  | 2024-07-31 |  | UNIPOLE
B00597 | W066J_B00597OD_KUALAAMPG | Central |  | Decomm |  | 2024 Q1 | CR | GCI | 4.6 TSSR Approved |  | 2024-01-17 |  |  |  | 2024-01-22 |  | 2024-01-30 | 2024-02-15 | CD//Sapian | 2024-02-07 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240128 | DU00002861733 |  |  |  |  | 2024-07-26 |  | BOOM
B00123 | W066X_B00123OD_MENARAIMPIAN | Central |  | Decomm |  | 2024 Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-10 |  |  |  | 2024-02-13 |  | 2024-05-20 | 2025-03-14 | CD//Norhaliza | 2024-10-03 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231113 | DU00002861734 |  |  |  |  | 2024-09-12 |  | TRIPOD
B01051 | W066I_B01051OD_JLNMELAWATI | Central |  | Decomm |  | 2024 Q1 | SM | GTSB | 4.6 TSSR Approved |  | 2024-03-26 |  |  |  | 2024-04-03 |  | 2024-04-15 | 2024-05-27 | CD//Ali Akaram | 2024-05-02 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240329 | DU00002861735 |  |  |  |  | 2024-03-26 |  | LAMP_POLE
B02470 | B064G_B02470OD_BANGI_PERDANA | Central |  | Decomm | Decomm->On Hold->Decomm | 2024 Q3 | SH | GTSB | 15.4 Decomm Done without TSSR Approval |  | 2024-09-06 |  | 2024-09-10 |  | 2024-09-12 | To be Submitted | 2024-09-20 |  | CD//Ali Akaram |  | 0925CD-Central-GTSB-BOQ Template(new contract) | DU00002861736 |  | Possible to relocate fiber to 2321A ? |  |  | 2025-06-05 |  | RAMO
B01577 | B064G_B01577OD_SEK7BBBANGI2 | Central |  | Decomm |  | 2024 Q4 | SH | Magicell | 4.6 TSSR Approved |  | 2024-02-20 |  |  |  | 2024-02-26 |  | 2024-05-20 | 2024-07-19 | CD//Ali Akaram | 2024-07-17 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240225 | DU00002861737 |  |  |  |  | 2024-09-30 |  | TRIPOD
B02559 | B061L_B02559OD_JLNTPP5PCHGIND | Central |  | Decomm |  | 2024 Q3 | SY1 | Solusi | 4.6 TSSR Approved |  | 2024-09-09 |  |  |  | 2024-09-13 |  | 2024-09-18 | 2024-10-29 | CD//Norhaliza | 2024-10-03 | 0724Central-Solusi-BOQ Template | DU00002861738 |  |  |  |  | 2024-11-15 |  | LAMP_POLE
B01058 | B061O_B01058OD_BDRUTAMA11 | Central |  | Decomm |  | 2024 Q3 | SH | GTSB | 4.6 TSSR Approved |  | 2024-02-01 |  |  |  | 2024-02-26 |  | 2024-03-28 | 2024-07-12 | CD//Sapian | 2024-06-11 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240212 | DU00002861739 |  |  |  |  | 2024-06-12 |  | LAMP_POLE
B02591 | B064G_B02591OD_BANGISEKSYEN3_SURAU_TS | Central |  | Decomm |  | 2024 Q3 | SY1 | DATASCO | 4.6 TSSR Approved |  | 2024-02-01 |  |  |  | 2024-10-15 |  | 2024-10-17 | 2025-01-14 | CD//Sapian | 2024-10-23 | 0809CD-Central-Datasco-BOQ Template(new contract) | DU00002861740 |  |  |  |  | 2024-11-15 |  | TOWER
B00224 | B064I_B00224OD_TMNTSKSEMENYEH2 | Central |  | Decomm |  | 2025 Q2 | HW | GCI | 4.6 TSSR Approved |  | 2025-02-10 |  | 2025-03-06 |  | 2025-03-18 |  | 2025-03-21 | 2025-03-26 | CD//Sapian | 2025-03-26 | SQ202501100412 | DU00002861741 |  |  |  |  | 2025-04-16 |  | TOWER
B01139 | B064I_B01139OD_UNIVNOTTINGHAM | Central |  | Decomm |  | 2024 Additional | NA | GCI | 4.6 TSSR Approved |  | 2024-12-23 |  | 2025-04-23 |  | 2025-04-25 |  | 2025-04-29 | 2026-01-21 | E//Ali | 2025-10-29 | SQ202501100412 | DU00002861742 |  |  |  |  | 2025-05-08 |  | TOWER
B00980 | W067A_B00980OD_APP8WPPJ | Central | 1848K | Swap | Decomm->Swap | 2024 Q3 | SY1 | Magicell | 4.6 TSSR Approved |  | 2024-08-01 | 2024-08-06 |  | 2024-08-08 | 2023-12-08 | Closed | 2024-08-09 | 2024-09-09 | CD//Norhaliza | 2024-09-09 | CelcomDigi_RAN_Magicell_TSS_Central_20231208/Celcom Digi_RAN-Magicell-Standard PR TSS-Central-20241016 | DU00002861743 |  |  | 2024-11-14 | 2024-11-11 |  | Wall mount boom | BOOM | 2 | Add R8862A S9000 x3+R8894E M1821 x4+R8862A S2601 x2+R8854 S2600 x1,Dismantle | 0 | 3
B00736 | B061Q_B00736OD_JLNSULTANPJ | Central |  | Decomm |  | 2024 Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2024-05-07 |  | 2024-07-20 |  | 2024-07-26 |  | 2024-07-31 | 2025-10-01 | CD//Ali Akaram | 2024-08-06 | CelcomDigi_RAN_GTSB_TSS_Central_20240423 | DU00002861744 |  |  |  |  | 2024-08-28 |  | BOOM
L00017 | S113A_L00017OD_HOTELGLOBAL | Sabah |  | Decomm |  | 2025 Q1 | AD | Datasco | 4.6 TSSR Approved |  | 2024-06-07 |  |  |  | 2024-06-08 |  | 2025-01-03 | 2025-05-02 | CD//Sharidah | 2025-02-04 | SQ202501020441 - Datasco | DU00002861745 |  |  |  |  | 2025-08-27 |  | BOOM
W00241 | W066U_W00241OD_SEPUTEH | Central |  | Decomm |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-02-07 |  |  |  | 2024-02-19 |  | 2024-03-27 |  | CD//Ali Akaram | 2024-04-08 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240212 | DU00002861746 |  | MISSING FE PART |  |  | 2025-02-26 |  | MONOPOLE
B01499 | B063B_B01499OD_KLIAEXCHANGE | Central |  | Decomm | Decomm->On Hold->Decomm | 2024 Additional | SHA | GTSB | 4.6 TSSR Approved |  | 2024-04-15 |  |  |  | 2024-04-17 |  | 2024-12-09 | 2025-01-07 | CD//Norhaliza | 2024-12-13 | 0715Central-GTSB-BOQ Template | DU00002861747 |  |  |  |  | 2024-12-19 |  | MINI STRUCTURE
W00849 | W066R_W00849OD_PR_BKTKOMANWEL | Central |  | Decomm |  | 2024 Q3 | SY1 | Magicell | 4.6 TSSR Approved |  | 2023-12-14 |  |  |  | 2023-12-18 |  | 2024-01-11 | 2025-02-21 | CD//Ali akaram | 2024-12-18 | CelcomDigi_RAN_Magicell_TSS_Central_20231215 | DU00002861748 |  |  |  |  | 2024-11-27 |  | GUYED MAST
B01558 | B061L_B01558OD_KGSRIPCHG | Central |  | Decomm |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-02-26 |  |  |  | 2024-02-28 |  | 2024-08-13 | 2025-01-14 | CD//Norhaliza | 2024-09-11 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240303 | DU00002861749 |  |  |  |  | 2024-10-29 |  | MINI MONOPOLE
W00791 | W066Y_W00791OD_PANDANINDAH3 | Central |  | Decomm |  | 2024 Q3 | BY | Ascentrack | 4.6 TSSR Approved |  | 2023-11-22 |  |  |  | 2023-12-22 |  | 2024-03-29 | 2025-03-14 | CD//Sapian | 2024-04-23 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231126 | DU00002861750 |  |  |  |  | 2024-07-25 |  | BOOM
W00255 | W066T_W00255OD_DESASEPUTEH | Central |  | Decomm |  | 2024 Q3 | BY | Ascentrack | 4.6 TSSR Approved |  | 2024-01-30 |  |  |  | 2024-02-08 |  | 2024-03-29 |  | CD//Norhaliza | 2024-06-06 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240202 | DU00002861751 |  | Missing FE part |  |  | 2024-05-24 |  | BOOM
W01040 | W066S_W01040OD_JLNMESRARIAOUG | Central |  | Decomm |  | 2024 Q3 | BY | Ascentrack | 4.6 TSSR Approved |  | 2024-01-12 |  |  |  | 2024-01-28 |  | 2024-04-01 | 2025-03-21 | CD//Norhaliza | 2024-08-09 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240115 | DU00002861752 |  |  |  |  | 2024-05-27 |  | UNIPOLE
W00450 | W066S_W00450OD_PR_TMNGEMBIRA2 | Central |  | Decomm |  | 2024 Q3 | SH | AllStar | 4.6 TSSR Approved |  | 2023-12-27 |  |  |  | 2024-06-13 |  | 2024-04-01 | 2024-09-05 | CD//Ali Akaram | 2024-04-23 | CelcomDigi_RAN_AllStar_TSS_Central_20231230 | DU00002861753 |  |  |  |  | 2024-05-31 |  | SHARING STRC SBC
B00382 | B061T_B00382OD_TMPJCENTRAL | Central |  | Decomm |  | 2024 Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2024-08-14 |  | 2024-09-08 |  | 2024-10-07 |  | 2024-10-08 |  | CD//Norhaliza | 2024-11-06 | BOQ CelcomDigi_RAN_CCSMY_Standard PR TSS_Central_20240429 | DU00002861754 |  |  |  |  | 2024-08-26 |  | BOOM
S00295 | S100A_S00295OD_CB_KIMANIS | Sabah | 7283K | Swap | Decomm->On Hold->Swap | 2025 Q2 | AD | YPTT | 4.6 TSSR Approved |  | 2025-01-22 | 2025-01-31 |  | 2025-02-04 |  | Under Approval | 2025-03-11 | 2025-05-27 | CD//Sharidah | 2025-03-17 | SQ202501030045 - YPTT | DU00002861755 |  |  | 2025-07-06 | 2025-06-12 |  | Tower | GUYED MAST | 60 | Add R8852E S9000x3+R8894E M1821x4, Dismantle | 0 | 1
W01196 | W066BB_W01196OD_DESATUNRAZAKINDUSTRI | Central |  | Decomm |  | 2024 Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2023-11-14 |  |  |  | 2023-11-22 |  | 2023-11-28 |  | CD//Norhaliza | 2024-01-05 | CelcomDigi_RAN_Magicell_TSS_Central_20231116 | DU00002861756 |  | 1) Missing antenna tx photo at NE 2) Missing FE part |  |  | 2024-07-31 |  | WALL MOUNTED BOOM
A01044 | A039B_A01044_CB_LDGSOONLEE | Northern |  | Decomm |  | 2024 Q4 | SHA | GTSB | 4.6 TSSR Approved |  | 2023-12-27 |  |  |  | 2024-01-02 |  | 2024-09-30 | 2024-10-03 | CD//Zulakmar | 2024-10-02 | Celcom Digi_RAN-GTSB-TSS-Northern-20231229-0081/Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20240305-0096 | DU00002861757 |  |  |  |  | 2024-12-27 |  | TOWER
S00345 | S098B_S00345OD_CB_DEWATA | Sabah |  | Decomm |  | 2024 Q4(single site MOCN)-L2126 SSM | MS | Datasco | 4.6 TSSR Approved |  | 2024-11-11 | [5 empty] | 2024-11-12 | 2024-11-29 | Sharidah | 2024-11-12 | 0809MW-Sabah-Datasco-BOQ Template(new contract)/0809CD-Sabah-Datasco-BOQ Template(new contract) | DU00002861758 |  |  |  |  | 2024-12-11 |  | TOWER
S00439 | S098A_S00439OD_CB_LADANGBAGAHAK | Sabah | 7100P | Swap | Maintain USP MOCN->On Hold->Swap | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-03-09 | 2025-03-14 |  | 2025-03-17 |  | Under Approval | 2025-03-23 | 2025-05-27 | CD//Sharidah | 2025-03-24 | SQ202501020392 - Futong | DU00002861759 |  |  | 2025-06-14 | 2025-05-27 |  | Tower | TOWER | 60m | Add R8852E S9000x3+R9224E M1821x7, Dismantle | 0 | 3
W00595 | W066BB_W00595OD_ALAMDAMAI | Central |  | Decomm |  | 2024 Q3 | BY | Magicell | 4.6 TSSR Approved |  | 2023-12-06 |  |  |  | 2023-12-14 |  | 2024-03-29 | 2024-07-26 | CD//Ali Akaram | 2024-04-24 | CelcomDigi_RAN_Magicell_TSS_Central_20231208 | DU00002861760 |  |  |  |  | 2024-08-27 |  | SHARING STRC DIGI
W01329 | W066BB_W01329OD_JLN_DAMAI_PERDANA | Central |  | Decomm |  | 2024 Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2023-11-14 |  |  |  | 2023-11-29 |  | 2023-12-06 | 2024-05-27 | CD//Norhaliza | 2024-01-18 | CelcomDigi_RAN_Magicell_TSS_Central_20231116 | DU00002861761 |  |  |  |  | 2024-07-29 |  | BOOM
B00144 | W066I_B00144OD_UKAYPERDANA | Central |  | Decomm |  | 2024 Q1 | CR | GCI | 4.6 TSSR Approved |  | 2023-11-14 |  |  |  | 2023-11-20 |  | 2023-11-21 | 2024-09-25 | CD//Sapian | 2024-02-27 | CelcomDigi_RAN_GCI_TSS_Central_20231116 | DU00002861762 |  |  |  |  | 2024-07-27 |  | MINI MONOPOLE
W01209 | W066AA_W01209OD_TAMAN IKHSAN CHERAS | Central |  | Decomm | Decomm->On Hold->Site Out->Decomm | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-08 |  |  |  | 2023-11-14 |  | 2023-11-20 | 2026-01-21 | CD//Sapian | 2026-03-31 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231113 | DU00002861763 |  |  |  |  | 2024-07-27 |  | LAMP_POLE
B00783 | B063A_B00783OD_BGNLALANG | Central |  | Decomm |  | 2024 Additional | AI | GTSB | 4.6 TSSR Approved |  | 2025-08-19 |  | 2025-07-01 |  | 2025-08-19 |  | 2025-10-07 |  | CD//Sapian | 2025-10-23 | SQ202503110146 | DU00002861764 |  | Missing FE part |  |  | 2025-06-19 |  | TOWER
B00040 | W066I_B00040OD_TMNMELAWATI2 | Central |  | Decomm |  | 2024 Q1 | SHA | GCI | 4.6 TSSR Approved |  | 2024-07-02 |  |  |  | 2024-07-16 |  | 2024-07-19 | 2024-09-25 | CD//Sapian | 2024-07-30 | PR raised | DU00002861765 |  |  |  |  | 2024-10-16 |  | TRIPOD
B00223 | B064F_B00223OD_TMNTEKNOLOGI2 | Central |  | Decomm |  | 2024 | AI | GTSB | 4.6 TSSR Approved |  | 2024-09-13 |  | 2024-09-18 |  | 2024-10-07 |  | 2024-11-19 | 2024-12-31 | CD//Sapian | 2024-11-29 | 0919CD-Central-GTSB-BOQ Template(new contract) 2 | DU00002861766 |  |  |  |  | 2024-11-05 |  | MINI STRUCTURE
B01160 | W067A_B01160OD_PARCELEWPPJ | Central | 1849K | Swap | Decomm->Swap | 2024 Q3 | AI | Magicell | 4.6 TSSR Approved |  | 2024-08-09 | 2024-08-14 |  | 2024-08-19 | 2024-02-23 | Closed | 2024-08-20 | 2024-08-27 | CD//Sapian | 2024-08-27 | 0619Central-Magicell-BOQ Template (template) | DU00002861767 |  |  | 2024-12-20 | 2024-11-05 |  | Wall mount boom | BOOM | 2 | Add R8862A S9000 x3+R8894E M1821 x4+R8862A S2601 x2+R8854 S2600 x1,Dismantle | 0 | 1
B00400 | B061J_B00400OD_LDGKINRARA | Central |  | Decomm |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-12-20 |  |  |  | 2024-05-02 |  | 2024-05-06 |  | CD//Ali Akaram | 2024-05-17 | CelcomDigi_RAN_Datasco_TSS_Central_20231224 | DU00002861768 |  | Missing antenna tx part at NE & FE part |  |  | 2024-09-27 |  | BOOM
B00121 | W066J_B00121OD_AU5 | Central |  | Decomm |  | 2024 Q1 | AD | YPTT | 4.6 TSSR Approved |  | 2024-01-11 |  |  |  | 2024-01-15 |  | 2024-01-17 | 2024-02-15 | CD//Ali akaram | 2024-01-23 | BOQ_Celcom Digi_RAN-YPTT-Standard PR TSS-20240115 | DU00002861769 |  |  |  |  | 2024-10-24 |  | TOWER
B00381 | B061T_B00381OD_LRGUNIVPJ | Central |  | Decomm |  | 2024 Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2024-05-22 |  |  |  | 2024-05-25 |  | 2024-05-27 |  | CD//Sapian | 2024-06-11 | CelcomDigi_RAN_YPTT_TSS_Central_20240528 | DU00002861770 |  |  |  |  | 2024-07-11 |  | MINI MONOPOLE
B00612 | B064C_B00612OD_SERDANGPDANA | Central |  | Decomm |  | 2024 Q3 | BY | GTSB | 4.6 TSSR Approved |  | 2024-06-05 | 2024-06-25 | 2024-06-21 |  | 2024-06-28 |  | 2024-07-03 | 2025-01-14 | CD//Norhaliza | 2024-08-07 | 0607Central-GTSB-BOQ Template | DU00002861771 |  |  |  |  | 2024-10-30 | In-Building System | TRIPOD | 6
B00418 | B061S_B00418OD_SS2PJ | Central |  | Decomm |  | 2024 Q3 | CR | GCI | 4.6 TSSR Approved |  | 2024-03-18 |  |  |  | 2024-03-16 |  | 2024-03-30 | 2024-10-29 | CD//Sapian | 2024-04-25 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240323 | DU00002861772 |  |  |  |  | 2024-07-05 |  | BOOM
W00204 | W066BB_W00204OD_MUTIARARAYA | Central |  | Decomm |  | 2024 Q3 | SH | AllStar | 4.6 TSSR Approved |  | 2023-11-16 |  |  |  | 2024-01-15 |  | 2024-04-02 | 2024-05-27 | CD//Sapian | 2024-04-30 | CelcomDigi_RAN_AllStar_TSS_Central_20231119 | DU00002861773 |  |  |  |  | 2024-09-13 |  | MINI STRUCTURE
W00096 | W066U_W00096OD_KUMPULANCHALK | Central |  | Decomm |  | 2024 Q2 | AD | YPTT | 4.6 TSSR Approved |  | 2024-03-04 |  |  |  | 2024-03-06 |  | 2024-03-13 | 2024-09-25 | CD//Norhaliza | 2024-06-05 | BOQ_Celcom Digi_RAN-YPTT-Standard PR TSS-20240311 | DU00002861774 |  |  |  |  | 2024-07-23 |  | BOOM
B00207 | W066X_B00207OD_PUTRASULAIMAN | Central |  | Decomm |  | 2024 Q2 | IE | YPTT | 4.6 TSSR Approved |  | 2023-12-02 |  |  |  | 2023-12-07 |  | 2023-12-08 | 2024-05-27 | CD//Norhaliza | 2024-05-03 | CelcomDigi_RAN_YPTT_TSS_Central_202031203 | DU00002861775 |  |  |  |  | 2024-07-25 |  | MINI STRUCTURE
W01377 | W066R_W01377OD_JLNTASIKDAMAI_SGBESI | Central | 1874K | Swap | Decomm->Swap | 2024 Q3 | SY1 | Magicell | 4.6 TSSR Approved |  | 2024-07-16 | 2024-07-18 |  | 2024-07-23 | 2023-12-11 | Closed | 2024-07-31 | 2024-08-05 | CD//Ali Akaram | 2024-08-05 | 0802CD-Central-Magicell-BOQ Template(new contract) | DU00002861776 |  | Missing FE part | 2025-09-24 | 2025-09-22 |  | Lampole | LAMP_POLE | 19M | Add R9264H M901821x3+R8862A S2601x3,Dismantle |  | 13
K00325 | K011A_K00325OD_CB_KGNAWA | Northern |  | Decomm |  | 2024 Q4 | HW | CCSMY | 4.6 TSSR Approved |  | 2024-10-22 |  | 2025-05-08 |  | 2025-05-14 | To be Submitted | 2025-05-16 |  | E//Hazida | 2025-05-19 | 0927CD-Northern-GCI-BOQ Template(new contract) | DU00002861777 |  |  |  |  | 2024-10-29 |  | TOWER
K00466 | K012A_K00466OD_BENDANGMAN | Northern | 4123P | Swap | Swap->On Hold->Swap | 2025 Q3 | HW | CCSMY | 4.6 TSSR Approved |  | 2025-01-12 | 2025-01-16 |  | 2025-03-04 |  | Under Approval | 2025-04-08 | 2025-05-19 | CD//Zulakmar | 2025-04-17 | SQ202501030318 - CCSMY | DU00002861778 |  |  | 2025-06-20 | 2025-06-17 |  | Tower | TOWER | 75M | Add R8852E S9000x2+R8854E S1800x2+R8894E M1821x3, Dismantle | 0 | 2
A00079 | A037B_A00079OD_CKTJONG | Northern |  | Decomm |  | 2024 Q3(single site MOCN) | SM | GTSB | 4.6 TSSR Approved |  | 2024-06-18 | 2024-06-21 | 2024-07-06 |  | 2024-07-05 |  | 2024-07-10 | 2024-10-01 | CD//Rohizam | 2024-07-10 | 0919MW-Northern-GTSB-BOQ Template (old contract) | DU00002861779 |  | Missing FE Info |  |  | 2025-11-28 | Tower | TOWER | 45M
A00318 | A040D_A00318OD_TMBTGAJAH | Northern |  | Decomm |  | 2024 Additional | HW | CCSMY | 4.6 TSSR Approved |  | 2025-04-09 |  | 2025-04-08 |  | 2025-04-21 |  | 2025-04-25 | 2025-10-28 | CD//Zulakmar | 2025-04-30 | SQ202502100375 | DU00002861780 |  |  |  |  | 2025-10-13 |  | TOWER
A00324 | A040C_A00324OD_WPAAVAI_RCC | Northern |  | Decomm |  | 2024 Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2023-12-07 |  |  |  | 2023-12-07 |  | 2023-12-13 | 2024-02-15 | CD//Rohizam | 2024-01-30 | Celcom Digi_RAN-GTSB-TSS-Northern-20231207-0073 | DU00002861781 |  |  |  |  | 2024-04-16 |  | MINI STRUCTURE
A00506 | A038A_A00506OD_CB_KOTABHARU | Northern |  | Decomm |  | 2024 Q4 |  | GTSB | 4.6 TSSR Approved |  | 2024-10-25 |  | 2024-10-15 |  | 2024-10-25 |  | 2024-11-05 | 2026-02-16 | CD//Zulakmar | 2024-11-05 | 0927CD-Northern-GTSB-BOQ Template(new contract)/0927MW-Northern-GTSB-BOQ Template(new contract) | DU00002861782 |  |  |  |  | 2024-11-05 |  | TOWER
A00308 | A040B_A00308OD_RAPATPERDANA_RCC | Northern |  | Decomm |  | 2024 Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2023-12-18 |  |  |  | 2023-12-18 |  | 2023-12-20 | 2024-01-22 | CD//Rohizam | 2023-12-20 | Celcom Digi_RAN-GTSB-TSS-Northern-20231219-0078 | DU00002861783 |  |  |  |  | 2024-04-19 |  | BOOM
A00668 | A036A_A00668OD_MAMBANGDIAWAN2_RDD | Northern |  | Decomm |  | 2024 Additional | MS | GTSB | 4.6 TSSR Approved |  | 2023-12-21 |  |  |  | 2024-01-02 |  | 2024-11-20 | 2025-07-29 | CD//Zulakmar | 2024-12-24 | Celcom Digi_RAN-GTSB-TSS-Northern-20231225-0080 | DU00002861784 |  |  |  |  | 2024-12-17 |  | TOWER
A00415 | A036B_A00415OD_CB_KGKUALASLIM | Northern | 4148P | Swap | Swap->On Hold->Swap | 2024 Additional | AI | GCI | 4.6 TSSR Approved |  | 2025-01-09 | 2025-01-13 |  | 2025-02-05 |  | Closed | 2025-02-06 | 2025-02-27 | CD//Zulakmar | 2025-02-26 | SQ202501030328 - GCI | DU00002861785 | Remarks: Solution TSSR/BOM Changed |  | 2025-05-12 | 2025-05-07 |  | Tower | TOWER | 60m | Add R8852E S9000x3+R8854E S1800x3+R8894E M1821x4, Dismantle | 0 | 3
A00544 | A036B_A00544OD_SGKLAH | Northern |  | Decomm |  | 2024 Additional | AD | CCSMY | 4.6 TSSR Approved |  | 2025-02-05 |  | 2025-02-14 |  | 2025-02-25 |  | 2025-02-25 | 2025-04-14 | CD//Zulakmar | 2025-02-27 | SQ202502100375 | DU00002861786 |  |  |  |  | 2025-02-05 |  | TOWER
A00339 | A039B_A00339OD_CB_KM195BMERAH | Northern |  | Decomm |  | 2025 Q1 | SM | Magicell | 4.6 TSSR Approved | 0108 - Panoramic photo 210-330 offset by 30 deg (ie. 210 photo shows 180-190deg. Please check and make corrections. Pair site haven’t implemented, decom tssr approval will be on hold. | 2024-01-13 |  |  |  | 2024-01-16 |  | 2025-01-06 | 2025-03-26 | CD//Zulakmar | 2025-03-03 | Celcom Digi_RAN-Magicell-TSS-Northern-20240116-0011//SQ202501030105 - Magicell | DU00002861787 |  | CD Hazwan reviewed but Hold wait for upg tssr ready first |  |  | 2025-03-26 |  | TOWER
A00688 | A041A_A00688OD_CB_JLNMANONGKK | Northern |  | Decomm |  | 2025 Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-10-19 |  |  |  | 2023-10-19 |  | 2023-10-25 | 2025-05-14 | CD//Rohizam | 2023-10-25 | Celcom Digi_RAN-GCI-TSS-Northern-20231020-0063//SQ202501030261 - GCI | DU00002861788 |  | Missing TX info and Photo |  |  | 2025-02-26 |  | TOWER
A00008 | A042A_A00008OD_CB_KUBUGAJAH_RDD | Northern |  | Decomm |  | 2024 Q4 | MS | GCI | 4.6 TSSR Approved |  | 2023-12-22 |  |  |  | 2024-03-26 |  | 2024-09-12 | 2025-10-01 | CD//Zulakmar | 2024-09-18 | Celcom Digi_RAN-GCI-TSS-Northern-20231202-0079 | DU00002861789 |  |  |  |  | 2024-09-24 |  | TOWER
A00132 | A042D_A00132OD_BKTNAGA_RCC | Northern | 4018P | Swap | Swap->On Hold->Swap | 2024 Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2024-01-22 | 2024-01-22 |  | 2025-01-20 |  | Rectificating | 2025-01-21 | 2025-02-26 | CD//Zulakmar | 2025-02-26 | Celcom Digi_RAN-GTSB-TSS-Northern-20240124-0088 | DU00002861790 |  |  | 2025-05-30 | 2024-02-22 |  | Tower | TOWER | 75m | Add R8852E S9000x3+R8854E S1800x3+R8894E M1821x5+R8862A S2601x1+R8854 S2600x2, Dismantle | 0 | 23
A01049 | A037B_A01049OD_CB_CHENDERONGBALAI(CDBI) | Northern |  | Decomm |  | 2024 Q4 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-11-29 |  |  |  | 2023-12-13 |  | 2023-12-14 | 2024-02-15 | CD//Rohizam | 2024-01-30 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231130-0074 | DU00002861791 |  |  |  |  | 2024-09-30 |  | TOWER
A00477 | A040D_A00477OD_JLNSPGPULAI | Northern |  | Decomm |  | 2024 Q2 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-11-20 |  |  |  | 2023-11-21 |  | 2023-11-22 | 2023-11-29 | CD//Rohizam | 2023-11-24 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231122-0072 | DU00002861792 |  |  |  |  | 2024-04-03 |  | MONOPOLE
A00219 | A040D_A00219OD_CB_CKTLARANG_RCD | Northern |  | Decomm |  | 2024 Q2 | ZA | GTSB | 4.6 TSSR Approved | ¦ 0216 - YPTT: site cancel from YPTT | 2024-02-25 |  |  |  | 2024-03-04 |  | 2024-03-06 | 2024-04-23 | CD//Rohizam | 2024-03-06 | Celcom Digi_RAN-GTSB-TSS-Northern-20240226-0094 | DU00002861793 |  |  |  |  | 2024-04-24 |  | TOWER
A00584 | A040C_A00584OD_SILIBININDUSTRI | Northern |  | Decomm |  | 2024 Q2 | SM | GCI | 4.6 TSSR Approved |  | 2024-02-28 |  |  |  | 2024-03-14 |  | 2024-03-15 | 2024-03-22 | CD//Rohizam | 2024-03-15 | Celcom Digi_RAN-GCI-TSS-Northern-20240315-0101/0612Northern-GCI-BOQ Template (template) | DU00002861794 |  |  |  |  | 2024-03-19 |  | TOWER
A00740 | A040D_A00740OD_STATION18_RDD | Northern |  | Decomm |  | 2024 Q2 | ZA | CCSMY | 4.6 TSSR Approved |  | 2024-02-27 |  |  |  | 2024-02-29 |  | 2024-03-01 | 2024-03-22 | CD//Rohizam | 2024-03-01 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240229-0097 | DU00002861795 |  | Missing xC Cabinet |  |  | 2024-06-04 |  | SHARING STRC DIGI
A00691 | A037A_A00691OD_SGMANIK_RDC | Northern |  | Decomm |  | 2024 Q4 | SM | GCI | 4.6 TSSR Approved |  | 2023-12-11 |  |  |  | 2023-12-15 |  | 2023-12-19 | 2024-10-01 | CD//Rohizam | 2023-12-20 | Celcom Digi_RAN-GCI-TSS-Northern-20231212-0082 | DU00002861796 |  |  |  |  | 2024-09-13 |  | #N/A
A00145 | A044A_A00145OD_CB_LAYANGLAYANGKANAN_RDD | Northern | 4149P | Swap | Swap->On Hold->Swap | 2024 Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2024-01-14 | 2024-01-15 |  | 2025-01-21 |  | Under Approval | 2025-02-06 | 2025-03-04 | E//Hazida | 2025-05-14 | Celcom Digi_RAN-GTSB-TSS-Northern-202401114-0085 | DU00002861797 |  | Remarks: Solution Changed | 2025-05-25 | 2025-05-17 |  | Tower | TOWER | 50m | Add R8852E S9000x3+R8854E S1800x3+R8894E M1821x4,Dismantle | 0 | 2
A00182 | A037A_A00182OD_KGBANJAR | Northern |  | Decomm |  | 2025 Q1 | HW | GTSB | 4.6 TSSR Approved |  | 2025-02-12 |  | 2025-02-18 |  | 2025-03-27 | To be Submitted | 2025-04-28 |  | CD//Zulakmar | 2025-04-30 | SQ202501060259 - GTSB | DU00002861798 |  |  |  |  | 2025-06-19 |  | TOWER
A00306 | A040B_A00306OD_KINTAJAYA | Northern |  | Decomm |  | 2024 Q2 | ZA | GCI | 4.6 TSSR Approved |  | 2023-10-17 |  |  |  | 2023-11-02 |  | 2023-11-02 | 2023-12-18 | CD//Rohizam | 2023-11-02 | Celcom Digi_RAN-GCI-TSS-Northern-20231019-0062 | DU00002861799 |  |  |  |  | 2024-06-11 |  | MONOPOLE
R00005 | R001A_R00005OD_TITITINGGI | Northern |  | Decomm |  | 2024 Q4 | SM | GCI | 4.6 TSSR Approved |  | 2023-10-13 |  | 2025-07-04 |  | 2023-10-20 |  | 2023-10-23 | 2025-10-01 | CD//Rohizam | 2023-11-21 | Celcom Digi_RAN-GCI-TSS-Northern-20231017-0060/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240529-0109 | DU00002861800 |  | Missing all TX photo and info |  |  | 2024-09-26 |  | TOWER
R00131 | R001A_R00131OD_CB_MRSMBESERI | Northern |  | Decomm |  | 2025 Q3 | HW | YPTT | 4.6 TSSR Approved |  | 2024-03-07 |  |  |  | 2024-03-12 |  | 2025-02-23 |  | CD//Hazwan | 2025-02-28 | Celcom Digi_RAN-YPTT-TSS-Northern-20240310-0063// SQ202501030072 -YPTT | DU00002861801 |  |  |  |  | 2025-04-28 |  | TOWER
B01293 | B061S_B01293OD_JLN224BAIDURI | Central |  | Decomm |  | 2024 Q3 | SH | GTSB | 4.6 TSSR Approved |  | 2024-02-14 |  |  |  | 2024-02-26 |  | 2024-04-01 | 2024-09-05 | CD//Sapian | 2024-04-29 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240217 | DU00002861802 |  |  |  |  | 2024-05-29 |  | LAMP_POLE
K00012 | K002A_K00012OD_CHAROKKELIAN | Northern |  | Decomm |  | 2024 Q4 | SHA | CCSMY | 4.6 TSSR Approved |  | 2024-10-05 |  | 2024-10-08 |  | 2024-10-09 |  | 2024-10-10 | 2024-10-29 | CD//Zulakmar | 2024-10-14 | 0927CD-Northern-CCSMY-BOQ Template(new contract)/0927MW-Northern-CCSMY-BOQ Template(new contract) | DU00002861803 |  |  |  |  | 2024-11-14 |  | TOWER
K00378 | K013A_K00378OD_GUARCHEMPEDAKTOWN | Northern | 4612K | Swap | Decomm->On Hold-Swap | 2025 Q2 | SM | CCSMY | 4.6 TSSR Approved |  | 2025-02-13 | 2025-02-19 |  | 2025-02-28 |  | Rectificating | 2025-03-07 | 2025-03-13 | CD//Zulakmar | 2025-03-11 | SQ202501030037 - CCSMY | DU00002861804 |  |  | 2025-03-29 | 2025-03-27 |  | Monopole | LAMP_POLE | 30M | Add R8852E S9000x3+A9732 M1821x2+R9264M M1821x1, Dismantle | 23 | 0
A00086 | A044A_A00086OD_PARIT_RCC | Northern |  | Decomm |  | 2024 Q2 | ZA | CCSMY | 4.6 TSSR Approved |  | 2024-01-18 |  |  |  | 2024-01-30 |  | 2024-01-31 | 2024-02-16 | CD//Rohizam | 2024-01-31 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240124-0089 | DU00002861805 |  | Missing xC OB fiber equipment for Relocate |  |  | 2024-05-22 |  | TOWER
A01046 | A040B_A01046_CB_TMN INDAH JAYA_IPH | Northern |  | Decomm |  | 2024 Q2 | BY | GCI | 4.6 TSSR Approved |  | 2023-10-26 |  |  |  | 2024-03-28 |  | 2023-11-03 | 2024-06-07 | CD//Rohizam | 2023-11-21 | Celcom Digi_RAN-GCI-TSS-Northern-20231028-0067/GCI Northern TX TSS | DU00002861806 |  |  |  |  | 2024-03-29 |  | UNIPOLE | 30m
R00007 | R001A_R00007OD_CB_CHUPING | Northern |  | Decomm |  | 2024 Q4 | SM | GTSB | 4.6 TSSR Approved |  | 2023-12-18 |  |  |  | 2023-12-18 |  | 2023-12-20 | 2024-01-22 | CD//Rohizam | 2023-12-20 | Celcom Digi_RAN-GTSB-TSS-Northern-20231219-0078 | DU00002861807 |  |  |  |  | 2024-11-13 |  | TOWER
K00179 | K003A_K00179OD_BUKITSGKECIL | Northern |  | Decomm |  | 2024 | HW | GCI | 4.6 TSSR Approved |  | 2024-12-31 |  | 2025-02-26 |  | 2025-03-03 |  | 2025-03-07 |  | CD//Zulakmar | 2025-03-11 | 1101CD Conso-Northern-GCI-BOQ Template(new contract) | DU00002861808 |  |  |  |  | 2024-12-06 |  | TOWER
A00455 | A036B_A00455OD_FELDABESOUT5 | Northern |  | Decomm |  | 2025 Q1 | SM | CCSMY | 4.6 TSSR Approved | 0108: TSSR is ok. However, lets wait for the pair site to be implemented first before I approve this tssr. | 2024-01-19 |  | 2025-10-30 |  | 2024-01-26 |  | 2025-01-06 | 2026-01-21 | CD//Zulakmar | 2026-03-31 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240124-0089//SQ202501030037 | DU00002861809 |  |  |  |  | 2025-06-03 |  | TOWER
A00548 | A036B_A00548OD_PEKANTROLAK | Northern |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Additional | AI | NR services | 4.6 TSSR Approved |  | 2025-11-03 |  | 2025-11-11 |  | 2025-11-09 | To be Submitted | 2026-01-26 | 2026-05-07 |  | 2026-05-07 | SQ202504230465-NR services | DU00002861810 |  |  |  |  | 2025-11-28 |  | TOWER
A00155 | A038A_A00155OD_MALIMNAWAR_RCC | Northern |  | Decomm |  | 2025 Q3 | HW | GTSB | 4.6 TSSR Approved |  | 2025-02-23 |  | 2025-03-06 |  | 2025-03-21 | To be Submitted | 2025-04-18 |  | CD//Zulakmar | 2025-05-02 | SQ202501060259 - GTSB | DU00002861811 |  |  |  |  | 2025-09-23 |  | TOWER
A00408 | A042A_A00408OD_CB_LDGMALAYA | Northern |  | Decomm |  | 2025 Q1 | SM | GCI | 4.6 TSSR Approved |  | 2023-11-22 |  |  |  | 2023-11-24 |  | 2023-11-27 | 2024-10-16 | CD//Rohizam | 2023-11-28 | Celcom Digi_RAN-GCI-TSS-Northern-20231127-0076/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240529-0109//SQ202501030261 - GCI | DU00002861812 |  |  |  |  | 2025-06-30 |  | TOWER
K00449 | K008A_K00449OD_KGTOKSENIK | Northern |  | Decomm |  | 2025 Q2 | HW | GTSB | 4.6 TSSR Approved |  | 2025-01-26 |  | 2025-02-12 |  | 2025-03-19 | To be Submitted | 2025-04-13 |  | CD//Zulakmar | 2025-04-17 | SQ202501060259 - GTSB | DU00002861813 |  |  |  |  | 2025-04-30 |  | TOWER
K00273 | K002A_K00273OD_TAWAR | Northern |  | Decomm |  | 2024 Q4 | SM | CCSMY | 4.6 TSSR Approved |  | 2024-01-30 |  |  |  | 2024-02-01 |  | 2024-09-27 | 2024-10-01 | CD//Zulakmar | 2024-09-30 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240202-0091 | DU00002861814 |  |  |  |  | 2024-11-04 |  | 60m 3-Legged Tower Angle Leg
K00072 | K010A_K00072OD_CB_POKOKTAI | Northern |  | Decomm |  | 2024 Q4 |  | CCSMY | 4.6 TSSR Approved |  | 2024-10-24 |  | 2024-10-30 |  | 2024-11-11 |  | 2024-11-19 | 2025-07-29 | CD//Zulakmar | 2024-12-05 | 0927CD-Northern-GCI-BOQ Template(new contract)/0927MW-Northern-GCI-BOQ Template(new contract)/SQ202504180279 | DU00002861815 |  |  |  |  | 2024-10-10 |  | TOWER
K00463 | K002A_K00463OD_KGBADANG | Northern |  | Decomm |  | 2024 Q4 | HW | GCI | 4.6 TSSR Approved |  | 2025-01-21 |  | 2025-07-09 |  | 2025-02-21 |  | 2025-04-29 | 2025-05-02 | CD//Zulakmar | 2025-04-30 | 0927CD-Northern-GCI-BOQ Template(new contract)/0927MW-Northern-GCI-BOQ Template(new contract) | DU00002861816 |  | Missing MW photo (NE/FE) |  |  | 2024-12-06 |  | TOWER
K00084 | K011A_K00084OD_CB_BKTTAMPOI | Northern |  | Decomm |  | 2025 Q2 | NA | GCI | 4.6 TSSR Approved |  | 2025-04-14 |  | 2025-04-23 |  | 2025-04-28 |  | 2025-05-05 |  | CD//Zulakmar | 2025-05-06 | SQ202501060244 - GCI | DU00002861817 |  |  |  |  | 2025-09-23 |  | TOWER
K00399 | K002A_K00399OD_BINJUL | Northern |  | Decomm |  | 2025 Q2 | NA | GCI | 4.6 TSSR Approved |  | 2025-04-12 |  | 2025-04-18 |  | 2025-04-24 | To be Submitted | 2025-05-05 |  | CD//Zulakmar | 2025-05-06 | SQ202501030261 - GCI | DU00002861818 |  |  |  |  | 2025-04-24 |  | TOWER
W00811 | W066V_W00811OD_PANTAIHILLPARK | Central |  | Decomm |  | 2024 Q2 | ZA | AllStar | 4.6 TSSR Approved |  | 2023-12-28 |  |  |  | 2024-01-12 |  | 2024-02-28 | 2024-04-24 | CD//Ali akaram | 2024-03-29 | BOQ CelcomDigi_RAN_AllStar_Standard PR TSS_Central_20240108 | DU00002861819 |  |  |  |  | 2024-11-25 |  | BOOM
S00494 | S095A_S00494OD_KABUNAU | Sabah |  | Decomm |  | 2025 Q1 | AI | YPTT | 4.6 TSSR Approved |  | 2025-01-05 |  | 2025-01-09 | 2025-01-24 | 2025-02-17 | Under Approval | 2025-02-22 | 2025-09-10 | CD//Sharidah | 2025-02-24 | SQ202501030034 - YPTT | DU00002861820 |  |  |  |  | 2025-09-11 |  | TOWER
S01565 | S108A_S01565OD_CB_KGNILASAN | Sabah |  | Decomm |  | 2025 Q3 | HW | NR services | 4.6 TSSR Approved |  | 2025-01-27 |  | 2025-02-03 | 2025-03-04 | 2025-03-04 | Under Approval | 2025-03-07 | 2025-09-10 | CD//Sharidah | 2025-03-26 | SQ202501020449 - NR Service / SQ202501070289 - NR Service | DU00002861821 |  |  |  |  | 2025-07-28 |  | TOWER
S00272 | S088A_S00272OD_CB_WESTON | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2025 Q2 | AD | Datasco | 4.6 TSSR Approved |  | 2025-07-07 |  | 2025-07-10 |  | 2025-09-10 |  | 2025-09-25 | 2025-10-31 | E//Hannah | 2025-10-06 | SQ202506100762 - Datasco /SQ202507010433 - Datasco | DU00002861822 |  |  |  |  | 2025-09-26 |  | TOWER
S00310 | S095A_S00310OD_KGKIKANSA | Sabah |  | Decomm |  | 2024 Q4 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2024-01-11 |  |  |  | 2024-01-18 |  | 2024-09-30 | 2025-05-02 | CD//Mohidi Jaan | 2024-09-30 | Celcom Digi_RAN-Seri Pancar-Standard PR TSS-Sabah-20240116 | DU00002861823 |  |  |  |  | 2024-10-23 |  | TOWER
S00510 | S104A_S00510OD_CB_BCCMCAMP | Sabah | 7090P | Swap | Maintain USP MOCN->On Hold->Swap | 2025 Q3 | HW | NR services | 4.6 TSSR Approved |  | 2025-01-09 | 2025-01-28 |  | 2025-03-12 |  | Under Approval | 2025-03-13 | 2025-03-14 | CD//Sharidah | 2025-03-14 | SQ202501020340 - NR Service | DU00002861824 |  |  | 2025-07-06 | 2025-05-23 |  | Tower | TOWER | 60 | Add R8852E S9000x3+R9224E M1821x7, Dismantle | 0 | 3
L00019 | S113A_L00019OD_FOOCHOW | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2025 Q1 | AD | YPTT | 4.6 TSSR Approved |  | 2025-01-22 |  | 2024-07-15 |  | 2025-04-07 |  | 2025-04-17 | 2025-09-10 | CD//Sharidah | 2025-04-21 | SQ202501030034 - YPTT | DU00002861825 |  |  |  |  | 2025-03-27 |  | MINI MONOPOLE
S01131 | S091A_S01131OD_CB_BUKITGOLD | Sabah | 7110P | Swap | Maintain USP MOCN->On Hold->Swap | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-02-06 | 2025-02-10 |  | 2025-02-12 |  | Under Approval | 2025-03-11 | 2025-05-26 | CD//Sharidah | 2025-03-18 | SQ202501020392 - Futong / SQ202502170264 - Futong | DU00002861826 |  |  | 2025-07-06 | 2025-05-21 |  | Monopole | TOWER | 45m | Add R8852E S9000x3+R8854E S1800x3+R8894E M1821x5, Dismantle | 0 | 12
S00346 | S098A_S00346OD_TUNGKU | Sabah |  | Decomm |  | 2024 Q4(single site MOCN)-L2126 SSM | AD | Datasco | 4.6 TSSR Approved |  | 2024-07-29 |  | 2024-08-05 |  | 2024-08-06 |  | 2024-08-07 | 2024-09-26 | CD//Sharidah | 2024-08-09 | 0730CD-Sabah-Datasco-BOQ Template(new contract) | DU00002861827 |  |  |  |  | 2024-12-06 |  | TOWER
S00844 | S100A_S00844OD_PEKANKIMANIS | Sabah |  | Decomm |  | 2025 Q2 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2024-01-11 |  |  |  | 2024-01-17 |  | 2025-01-09 | 2025-05-02 | CD//Sharidah | 2025-01-09 | Celcom Digi_RAN-Seri Pancar-Standard PR TSS-Sabah-20240116 / SQ202501020446 - Seri Pancar / SQ202501070297 - Seri Pancar | DU00002861828 |  |  |  |  | 2025-06-25 |  | TOWER
S00659 | S105B_S00659OD_SANDAKANAIRPORT | Sabah |  | Decomm |  | 2024 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2024-04-30 |  |  |  | 2024-05-02 |  | 2024-05-03 | 2024-05-24 | CD//Mohidi Jaan | 2024-05-13 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240503 | DU00002861829 |  |  |  |  | 2024-09-06 |  | BOOM
S00208 | S105B_S00208OD_GUMGUM | Sabah |  | Decomm |  | 2025 Q2 | ZB | Futong | 4.6 TSSR Approved |  | 2024-03-25 |  |  |  | 2024-03-26 |  | 2024-04-04 | 2024-08-09 | CD//Mohidi Jaan | 2024-04-04 | Celcom Digi_RAN-Futong-TSS-Sabah-20240329 / SQ202501020444 - Futong | DU00002861830 |  |  |  |  | 2024-07-19 |  | TOWER
S00807 | S111A_S00807OD_PEKANTENOM | Sabah |  | Decomm |  | 2024 | MS | Seri Pancar | 4.6 TSSR Approved |  | 2024-11-12 |  | 2024-11-20 |  | 2024-11-21 |  | 2024-11-22 | 2024-12-13 | CD//Mohidi Jaan | 2024-11-25 | Celcom Digi_RAN-Seri Pancar-Standard PR TSS-Sabah-20241030 | DU00002861831 |  |  |  |  | 2024-12-31 |  | TRIPOD
S00271 | S107A_S00271OD_CB_TAMPALAGUS | Sabah | 7091P | Swap | Maintain USP MOCN->On Hold->Swap | 2025 Q2 | AD | DATASCO | 4.6 TSSR Approved |  | 2025-01-15 | 2025-03-20 |  | 2025-03-26 |  | Under Approval | 2025-03-27 | 2025-05-27 | CD//Sharidah | 2025-04-08 | SQ202501020331 - Datasco | DU00002861832 |  |  | 2025-08-13 | 2025-08-13 |  | Tower | TOWER | 75 | Add R8852E S9000x3+R8894E M1821x7, Dismantle | 0 | 3
S00611 | S107A_S00611OD_KGMERINTMN | Sabah |  | Decomm |  | 2025 Q2 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2024-01-11 |  |  |  | 2024-01-21 |  | 2025-01-09 | 2025-05-02 | CD//Sharidah | 2025-01-09 | Celcom Digi_RAN-Seri Pancar-Standard PR TSS-Sabah-20240116 / SQ202501020446 - Seri Pancar | DU00002861833 |  |  |  |  | 2025-06-19 |  | TOWER
S00566 | S104A_S00566OD_CB_NALAPAK | Sabah | 7112P | Swap | Maintain USP MOCN->On Hold->Swap | 2025 Q3 | HW | NR services | 4.6 TSSR Approved |  | 2025-01-07 | 2025-02-03 |  | 2025-03-11 |  | Under Approval | 2025-03-12 | 2025-03-14 | CD//Sharidah | 2025-03-14 | SQ202501020340 - NR Service | DU00002861834 |  |  | 2025-07-06 | 2025-05-25 |  | Tower | TOWER | 76 | Add R8852E S9000x3+R9224E M1821x7, Dismantle | 0 | 3
S01560 | S108A_S01560OD_CB_KGTUNGOU | Sabah |  | MOCN By Other Vendor | Maintain USP MOCN->On Hold->Maintain USP MOCN->On Hold->MOCN By Other Vendor | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861835 | [6 empty] | TOWER
S00799 | S088A_S00799OD_KGBRUNEI | Sabah |  | Decomm |  | 2025 Q2 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2024-01-11 |  |  |  | 2024-03-14 |  | 2025-01-09 | 2025-05-02 | CD//Sharidah | 2025-01-09 | Celcom Digi_RAN-Seri Pancar-Standard PR TSS-Sabah-20240116 / SQ202501020446 - Seri Pancar / SQ202501070297 - Seri Pancar | DU00002861836 |  |  |  |  | 2025-06-25 |  | TOWER
Q00685 | Q132A_Q00685OD_RHANDUH | Sarawak |  | Decomm |  | 2025 Q3 | NA | Trintel | 4.6 TSSR Approved |  | 2025-03-09 |  | 2025-05-08 |  | 2025-05-09 |  | 2025-05-17 | 2025-10-28 | CD//John | 2025-05-27 | SQ202501070293-Trintel | DU00002861837 |  |  |  |  | 2025-07-17 |  | TOWER
S01140 | S107A_S01140OD_KGKUALAMENGALONG | Sabah |  | Decomm |  | 2025 Q2 | HW | Seri Pancar | 4.6 TSSR Approved |  | 2024-01-11 |  |  |  | 2025-02-18 |  | 2025-02-21 | 2025-05-02 | CD//Sharidah | 2025-02-26 | Celcom Digi_RAN-Seri Pancar-Standard PR TSS-Sabah-20240116 / SQ202501020446 - Seri Pancar / SQ202501070297 - Seri Pancar | DU00002861838 |  |  |  |  | 2025-04-23 |  | TOWER
S00576 | S096A_S00576OD_CB_BKTKARAKIT | Sabah |  | Decomm |  | 2025 Q3 | AD | GCI | 4.6 TSSR Approved | Pending CR Boat | 2025-10-01 |  | 2025-10-08 |  | 2025-10-28 | To be Submitted | 2025-11-06 |  | E//Ali | 2025-11-18 | SQ202509220660 - GCI | DU00002861839 |  |  |  |  | 2025-10-23 |  | TOWER
S00424 | S109A_S00424OD_KGKELAWAT | Sabah |  | Decomm |  | 2025 Q3 | HW | NR services | 4.6 TSSR Approved |  | 2025-01-07 |  | 2025-01-22 |  | 2025-02-16 |  | 2025-02-23 | 2025-05-02 | CD//Sharidah | 2025-02-24 | SQ202501020449 - NR Service | DU00002861840 |  |  |  |  | 2025-05-25 |  | TOWER
L00022 | S113A_L00022OD_SGLADA | Sabah |  | Decomm |  | 2025 Q1 | AD | Datasco | 4.6 TSSR Approved |  | 2024-05-26 |  | 2024-08-12 |  | 2024-06-05 |  | 2025-01-03 | 2025-05-02 | CD//Sharidah | 2025-02-04 | SQ202501020441 - Datasco | DU00002861841 |  |  |  |  | 2025-03-24 |  | TOWER
L00147 | S113A_L00147OD_KOMPLEKKASTAM | Sabah |  | Decomm |  | 2025 Q1 | AD | Datasco | 4.6 TSSR Approved |  | 2024-05-25 |  |  |  | 2024-06-08 |  | 2025-01-03 | 2025-05-02 | CD//Sharidah | 2025-02-04 | SQ202501020441 - Datasco | DU00002861842 |  |  |  |  | 2025-03-18 |  | TOWER
L00010 | S113A_L00010OD_KGSEGUMAU | Sabah |  | Decomm |  | 2025 Q1 | HW | YPTT | 4.6 TSSR Approved |  | 2025-01-24 |  | 2025-02-14 |  | 2025-02-18 |  | 2025-02-21 | 2025-05-02 | CD//Sharidah | 2025-02-26 | SQ202501030034 - YPTT | DU00002861843 |  |  |  |  | 2025-08-28 |  | TOWER
L00131 | S113A_L00131OD_LABUANBO | Sabah |  | Decomm |  | 2025 Q1 | HW | YPTT | 4.6 TSSR Approved |  | 2025-01-15 |  | 2025-01-27 |  | 2025-02-05 |  | 2025-02-21 |  | CD//Sharidah | 2025-02-26 | SQ202501030034 - YPTT | DU00002861844 |  |  |  |  | 2025-03-16 |  | BOOM
S00594 | S098A_S00594OD_CB_EMBARABUDI | Sabah | 7113P | Swap | Maintain USP MOCN->On Hold->Swap | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-03-15 | 2025-03-20 |  | 2025-03-26 |  | Under Approval | 2025-03-27 | 2025-05-27 | CD//Sharidah | 2025-04-08 | SQ202501020392 - Futong | DU00002861845 |  |  | 2025-06-14 | 2025-05-21 |  | Tower | TOWER | 76m | Add R8852E S9000x3+R9224E M1821x8, Dismantle | 0 | 13
S00347 | S098A_S00347OD_MEMBATU | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 | HW | GTSB | 4.6 TSSR Approved |  | 2025-07-14 |  | 2025-07-16 |  | 2025-07-22 |  | 2025-09-10 | 2026-01-20 | E//Hannah | 2025-09-18 | SQ202506100849 - GTSB / SQ202507010442 - GTSB | DU00002861846 |  |  |  |  | 2025-11-26 |  | TOWER
S00335 | S098A_S00335OD_CB_KEMBARASAKTI | Sabah | 7114P | Swap | Maintain USP MOCN->On Hold->Swap | 2026 | AD | Futong | 4.6 TSSR Approved |  | 2025-03-16 | 2025-03-20 |  | 2025-03-26 |  | Under Approval | 2025-03-27 | 2025-05-27 | CD//Sharidah | 2025-04-08 | SQ202501020392 - Futong | DU00002861847 | Remarks: Solution TSSR/BOM Changed |  | 2025-07-06 | 2025-05-21 |  | Tower | TOWER | 76m | Add R8852E S9000x4+R8854E S1800x4+R8894E M1821x5, Dismantle | 0 | 2
S00211 | S105A_S00211OD_KGGAS | Sabah |  | Decomm |  | 2024 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2024-04-28 |  |  |  | 2024-05-03 |  | 2024-05-07 | 2024-07-24 | CD//Mohidi Jaan | 2024-05-09 | Celcom Digi_RAN-YPTT-Standard PR TSS-Sabah-20240503 | DU00002861848 |  |  |  |  | 2024-09-09 |  | TOWER
S00063 | S105A_S00063OD_JLNCECILY | Sabah |  | Decomm |  | 2024 Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2024-04-27 |  |  |  | 2024-05-09 |  | 2024-05-09 | 2024-08-09 | CD//Mohidi Jaan | 2024-05-10 | Celcom Digi_RAN-YPTT-Standard PR TSS-Sabah-20240503 | DU00002861849 |  |  |  |  | 2024-09-04 |  | TOWER
S00584 | S089A_S00584OD_CB_KOTAPAMOL | Sabah | 7115P | Swap | Maintain USP MOCN->On Hold->Swap | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-01-20 | 2025-02-07 |  | 2025-02-10 |  | Under Approval | 2025-02-20 | 2025-03-09 | CD//Sharidah | 2025-02-21 | SQ202501020392 - Futong | DU00002861850 |  |  | 2025-07-06 | 2025-05-24 |  | Tower | TOWER | 76m | Add R8852E S9000x3+R9224E M1821x8, Dismantle | 0 | 13
S00062 | S098A_S00062OD_FAJARHARAPAN | Sabah |  | Decomm |  | 2024 Q4(single site MOCN)-L26 SSM | SH | Datasco | 4.6 TSSR Approved |  | 2024-07-29 |  | 2024-08-05 |  | 2024-08-07 |  | 2024-08-09 | 2024-09-26 | CD//Mohidi Jaan | 2024-08-12 | 0730CD-Sabah-Datasco-BOQ Template(new contract) | DU00002861851 |  |  |  |  | 2024-12-06 |  | TOWER
S00384 | S094A_S00384OD_CB_KGTAGAROH | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2025 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2025-06-14 |  | 2025-07-30 |  | 2025-07-31 |  | 2025-09-09 | 2025-10-29 | E//Hannah | 2025-09-18 | SQ202506100836 - YPTT / SQ202507010450 - YPTT | DU00002861852 |  |  |  |  | 2025-10-27 |  | TOWER
S00146 | S102A_S00146OD_CB_PINGGANPINGGAN | Sabah | 7116P | Swap | Maintain USP MOCN->On Hold->Swap | 2025 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2025-02-25 | 2025-02-24 |  | 2025-03-10 |  | Under Approval | 2025-04-07 | 2025-05-27 | CD//Sharidah | 2025-04-08 | SQ202501020343 - GTSB | DU00002861853 |  |  | 2025-07-06 | 2025-05-25 |  | Tower | TOWER | 75 | Add R8852E S9000x3+R9224E M1821x8+R8862A S2601x1+R8854 S2600x2, Dismantle | 0 | 12
S00163 | S094A_S00163OD_TAMANBERINGIN | Sabah |  | Decomm |  | 2025 Q3 | HW | GTSB | 4.6 TSSR Approved |  | 2025-01-09 |  | 2025-02-25 |  | 2025-03-13 |  | 2025-03-13 | 2025-09-10 | CD//Sharidah | 2025-03-14 | SQ202501020455 - GTSB | DU00002861854 |  |  |  |  | 2025-04-29 |  | TOWER
S00134 | LANGKON K.MARUDU SBC | Sabah | 7138P | Remote MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN->Swap->Remote MOCN | 2025 Q3 | AD | GTSB | 14.1 Drop (No Survey) |  | 2025-07-17 |  |  |  |  | To be Submitted |  |  |  |  | SQ202504140236 - GTSB | DU00002861855 | [6 empty] | TOWER |  | Add R9264H M901821x3+R8854E S1800x3, Dismantle | 0 | 0
S00569 | S094A_S00569OD_KGMARUDU | Sabah |  | Decomm |  | 2024 | MS | Seri Pancar | 4.6 TSSR Approved |  | 2024-11-07 |  | 2024-11-11 |  | 2024-11-12 |  | 2024-11-13 | 2024-12-13 | CD//Mohidi Jaan | 2024-11-13 | Celcom Digi_RAN-Seri Pancar-Standard PR TSS-Sabah-20241030 | DU00002861856 |  |  |  |  | 2025-02-17 |  | TOWER
S00630 | S104A_S00630OD_PEKANNABALU | Sabah |  | Decomm |  | 2025 Q3 | HW | NR services | 4.6 TSSR Approved |  | 2025-01-08 |  | 2025-01-21 |  | 2025-02-11 |  | 2025-02-23 |  | CD//Sharidah | 2025-02-24 | SQ202501020449 - NR Service | DU00002861857 |  | Refer email |  |  | 2025-06-21 |  | TOWER
K00095 | K008A_K00095OD_TLKEWA | Northern |  | Decomm |  | 2024 Q4 | HW | CCSMY | 4.6 TSSR Approved |  | 2024-10-13 |  | 2024-10-18 |  | 2025-04-09 |  | 2025-04-28 | 2025-05-02 | CD//Zulakmar | 2025-04-30 | 0927CD-Northern-CCSMY-BOQ Template(new contract)/0927MW-Northern-CCSMY-BOQ Template(new contract) | DU00002861858 |  | FE Tx Part Missing |  |  | 2024-10-15 |  | TOWER
S00529 | S091A_S00529OD_CB_TABINWILDLIFE | Sabah |  | MOCN By Other Vendor | Maintain USP MOCN->On Hold->Maintain USP MOCN->On Hold->MOCN By Other Vendor | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861859 | [6 empty] | TOWER
W00005 | W066R_W00005OD_PR_BKTJALIL | Central |  | Decomm |  | 2024 Q3 | BY | GTSB | 4.6 TSSR Approved |  | 2024-05-24 |  |  |  | 2024-07-02 |  | 2024-07-04 | 2024-11-26 | CD//Ali Akaram | 2024-07-18 | CelcomDigi_RAN_GTSB_TSS_Central_20240423 | DU00002861860 |  |  |  |  | 2024-08-21 |  | TOWER
B02010 | B061J_B02010OD_PUJ7PUNCAKJALIL | Central |  | Decomm |  | 2024 Q3 | SHA | GTSB | 4.6 TSSR Approved |  | 2024-11-12 |  | 2024-11-13 |  | 2024-11-14 |  | 2024-11-15 |  | CD//Ali akaram | 2024-12-02 | 0815Central-GTSB-BOQ Template (template) - reraise | DU00002861861 |  | Propose to relo TM NGBH LL to colo site 3243B |  |  | 2024-11-18 |  | PYLON
Q00699 | Q135A_Q00699OD_KGEMPILA | Sarawak |  | Decomm |  | 2024 Q2 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-11-18 |  |  |  | 2023-11-21 |  | 2023-11-21 | 2023-11-28 | CD//John | 2023-11-22 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231119/Celcom Digi_RAN-Magicell-Standard PR TSS DECOMM-Sarawak-20231229/CelcomDigi_RAN_Magicell_TSS_Sarawak_20241018 | DU00002861862 |  |  |  |  | 2025-08-07 |  | TOWER
Q00555 | Q135A_Q00555OD_PASARBT10 | Sarawak |  | Decomm |  | 2025 Q1 | SH | South Pacific | 4.6 TSSR Approved |  | 2024-02-02 |  |  |  | 2024-02-02 |  | 2024-02-05 | 2024-03-05 | CD//John | 2024-02-27 | Celcom Digi_RAN-South Pacific-TSS-Sarawak-20240204 | DU00002861863 |  |  |  |  | 2025-05-28 |  | TOWER
Q00672 | Q141A_Q00672OD_CB_PKNSIMUNJAN | Sarawak | 9286P | Swap | Maintain USP MOCN->On Hold->Swap | 2025 | AI | Magicell | 4.6 TSSR Approved |  | 2025-04-09 | 2025-04-10 |  | 2025-04-21 |  | Closed | 2025-04-24 | 2025-04-26 | CD//John | 2025-04-24 | SQ202503170852-Magicell | DU00002861864 |  |  | 2025-07-06 | 2025-06-10 |  | Tower | TOWER | 76 | Add R8852E S9000x3+R8854E S1800x3+R8894E M1821x6+R8854 S2600x3, Dismantle | 0 | 123
Q00793 | Q128A_Q00793OD_CB_KGBIAWAK | Sarawak | 9243P | Swap | Maintain USP MOCN->On Hold->Swap | 2024 Q2 | SM | Magicell | 4.6 TSSR Approved |  | 2025-02-06 | 2025-02-14 |  | 2025-02-24 |  | Rectificating | 2025-02-27 | 2025-02-28 | CD//John | 2025-02-28 | SQ202501070146-Magicell | DU00002861865 |  |  | 2025-07-06 | 2025-05-28 |  | Tower | TOWER | 76 | Add R8852E S9000x3+R8854E S1800x3+R8894E M1821x4, Dismantle | 0 | 2
Q00390 | Q135A_Q00390OD_SGSUI | Sarawak |  | Decomm |  | 2024 Q2 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-12-08 |  |  |  | 2023-12-14 |  | 2024-01-22 | 2024-02-15 | CD//John | 2024-01-24 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231212/Celcom Digi_RAN-Magicell-Standard PR TSS DECOMM-Sarawak-20231229/CelcomDigi_RAN_Magicell_TSS_Sarawak_20241018 | DU00002861866 |  |  |  |  | 2025-02-24 |  | TOWER
Q01690 | Q141A_Q01690OD_CB_PKNSIMUNJAN2 | Sarawak | 9287P | Swap | Maintain USP MOCN->On Hold->Swap | 2025 | HW | Magicell | 4.6 TSSR Approved |  | 2025-04-09 | 2025-04-11 |  | 2025-04-18 |  | Under Approval | 2025-04-23 | 2025-04-26 | CD//John | 2025-04-24 | SQ202503170852-Magicell | DU00002861867 |  |  | 2025-07-06 | 2025-06-10 |  | Tower | TOWER | 45 | Add R8852E S9000x3+R8854E S1800x3+R8894E M1821x4, Dismantle | 0 | 2
Q00044 | Q135A_Q00044OD_KGMELAYU | Sarawak |  | Decomm |  | 2024 Q2 | SH | Magicell | 4.6 TSSR Approved |  | 2023-11-16 |  |  |  | 2023-11-27 |  | 2023-11-27 | 2024-01-22 | CD//John | 2023-11-28 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231119/Celcom Digi_RAN-Magicell-Standard PR TSS DECOMM-Sarawak-20231229/CelcomDigi_RAN_Magicell_TSS_Sarawak_20241018 | DU00002861868 |  |  |  |  | 2025-06-14 |  | TOWER
Q00037 | Q135A_Q00037OD_TMNRIVERIA | Sarawak |  | Decomm |  | 2024 Q2 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-11-18 |  |  |  | 2023-11-21 |  | 2023-11-22 | 2023-11-28 | CD//John | 2023-11-22 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231119 | DU00002861869 |  |  |  |  | 2025-09-27 |  | TOWER
Q00341 | Q132C_Q00341OD_TMNHILLTOP | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q1 | SH | Trintel | 4.6 TSSR Approved |  | 2024-04-23 |  |  |  | 2024-04-25 |  | 2024-04-26 | 2024-05-24 | CD//John | 2024-04-29 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240503 | DU00002861870 |  |  |  |  | 2025-11-25 |  | TRIPOD
Q00337 | Q132C_Q00337OD_JLNKGLUAK | Sarawak |  | Decomm |  | 2025 Q1 | SH | Trintel | 4.6 TSSR Approved |  | 2023-10-13 |  |  |  | 2023-10-16 |  | 2023-10-16 | 2023-11-18 | CD//John | 2023-10-16 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231016 | DU00002861871 |  |  |  |  | 2025-10-14 |  | TOWER
Q00368 | Q132C_Q00368OD_CB_SPGNIAH | Sarawak | 9177P | Swap | Maintain USP MOCN->On Hold->Swap | 2025 Q2 | HW | Trintel | 4.6 TSSR Approved |  | 2025-03-09 | 2025-04-09 |  | 2025-04-16 |  | Under Approval | 2025-05-09 | 2025-05-19 | E//John | 2025-05-09 | SQ202501070293-Trintel | DU00002861872 |  |  | 2025-08-21 | 2025-08-09 |  | Tower | TOWER | 76M | R8852E S9000x3+R8854E S1800x3+R8894E M1821x3+R8862A S2601x3 | 0 | 0
Q00579 | Q124F_Q00579OD_CB_TNNIAH | Sarawak |  | MOCN By Other Vendor | Maintain USP MOCN->On Hold->Maintain USP MOCN->On Hold->MOCN By Other Vendor | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861873 | [6 empty] | TOWER
Q00749 | Q137A_Q00749OD_CB_JAKAR | Sarawak |  | Decomm |  | 2025 Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-12-21 |  |  |  | 2023-12-27 |  | 2024-01-25 | 2024-02-09 | CD//John | 2024-01-25 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231221 | DU00002861874 |  |  |  |  | 2025-06-17 |  | TOWER
Q00389 | Q141A_Q00389OD_CB_TMSEBUYAU | Sarawak | 9201P | Swap | Maintain USP MOCN->On Hold->Swap | 2025 | AD | Magicell | 4.6 TSSR Approved |  | 2025-04-22 | 2025-07-04 |  | 2025-07-08 |  | Under Approval | 2025-07-08 | 2025-09-20 | E//Zamri | 2026-04-17 | SQ202503170852-Magicell | DU00002861875 |  |  | 2025-10-27 | 2025-10-25 |  | Tower | TOWER | 124 | Add R8852E S9000x3+R9264M M1821x1+A9732 M1821x2,Dismantle | 13 | 0
Q00025 | Q135A_Q00025OD_TMSAMARAHAN | Sarawak |  | Decomm |  | 2024 Q2 | SH | Magicell | 4.6 TSSR Approved |  | 2023-11-14 |  |  |  | 2023-11-23 |  | 2023-11-23 | 2024-02-15 | CD//John | 2023-11-24 | Celcom Digi_RAN-Maagicell-TSS-Sarawak-20231119/Celcom Digi_RAN-Magicell-Standard PR TSS DECOMM-Sarawak-20231229 | DU00002861876 |  |  |  |  | 2025-08-11 |  | TOWER
Q00373 | Q137A_Q00373OD_CB_JLNREPOK | Sarawak | 9449P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN->On Hold->Swap | 2025 Q2 | AD | Trintel | 4.6 TSSR Approved | 14/8 - tomorrow enter// 8/8 - team transport issue // 5/8- Wk33 plan | 2025-08-18 | 2025-08-26 |  | 2025-08-29 |  | Under Approval | 2025-09-19 | 2025-10-16 | E//John | 2025-09-19 | SQ202508110312-Trintel | DU00002861877 |  |  | 2025-10-20 | 2025-10-13 |  | Tower | TOWER | 60 | Add R8852E S9000x3+R8894E M1821x3+R9264M M1821x3+R8862A S2601x3, Dismantle | 0 | 0
Q00318 | Q126A_Q00318OD_CB_TEDUNGAN | Sarawak | 9245P | Swap | Maintain USP MOCN->On Hold->Swap | 2025 Q2 | AI | DATASCO | 4.6 TSSR Approved |  | 2025-02-04 | 2025-03-26 |  | 2025-04-19 |  | Closed | 2025-04-21 | 2025-04-22 | CD//John | 2025-04-21 | SQ202501070453-Datasco | DU00002861878 |  |  | 2025-10-21 | 2025-10-13 |  | Tower | TOWER | 80 | Add R8852E S9000x3+R8854E S1800x3+R8894E M1821x4, Dismantle | 0 | 1
Q00319 | Q130A_Q00319OD_PKNMARUDI | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | AI | Trintel | 4.6 TSSR Approved |  | 2025-02-21 |  | 2025-04-03 |  | 2025-04-10 |  | 2025-04-15 | 2025-05-02 | CD//John | 2025-04-16 | SQ202501070293-Trintel | DU00002861879 |  |  |  |  | 2025-08-20 |  | BOOM
Q00938 | Q128A_Q00938OD_CB_LUNDU2 | Sarawak | 9447P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN->On Hold->Swap | 2024 Q2 | HW | Trintel | 4.6 TSSR Approved | 8/8 - team transport issue // 5/8- Wk33 plan | 2025-08-13 | 2025-08-28 |  | 2025-09-03 |  | Under Approval | 2025-09-04 | 2025-09-26 | E//John | 2025-09-06 | SQ202508110312-Trintel | DU00002861880 |  |  | 2025-09-26 | 2025-09-24 |  |  | TOWER | 45 | Add R8852E S9000x3+R8894E M1821x6, Dismantle | 0 | 0
Q00223 | Q138A_Q00223OD_CB_SELANGAU | Sarawak | 9246P | Swap | Maintain USP MOCN->On Hold->Swap | 2025 Q2 | AI | Trintel | 4.6 TSSR Approved |  | 2025-02-26 | 2025-02-07 |  | 2025-03-07 |  | Closed | 2025-03-27 | 2025-05-19 | CD//John | 2025-03-28 | SQ202501070293-Trintel | DU00002861881 |  |  | 2025-11-24 | 2025-11-17 |  | Tower | TOWER | 76 | Add R8852E S9000x3+R8854E S1800x3+R9264M M1821x4+R8862A S2601x4, Dismantle | 0 | 1
Q00583 | Q133A_Q00583OD_MUKAHCOMM | Sarawak |  | Decomm |  | 2024 Q4(single site MOCN)-L21 SSM | ZB | Trintel | 4.6 TSSR Approved |  | 2024-02-28 |  |  |  | 2024-03-01 |  | 2024-03-07 | 2024-03-21 | CD//John | 2024-03-11 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240302 | DU00002861882 |  |  |  |  | 2024-12-10 |  | TOWER
Q00566 | Q115A_Q00566OD_CB_KGDAUN | Sarawak |  | Decomm |  | 2024 Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2024-02-07 |  |  |  | 2024-02-08 |  | 2024-02-08 | 2024-02-15 | CD//John | 2024-02-09 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240213 | DU00002861883 |  |  |  |  | 2024-06-10 |  | TOWER
Q00068 | Q115A_Q00068OD_SGPINANGKCH | Sarawak |  | Decomm |  | 2024 Q2 | ZB | Trintel | 4.6 TSSR Approved |  | 2024-01-29 |  |  |  | 2024-01-29 |  | 2024-02-06 | 2024-02-15 | CD//John | 2024-02-07 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20240204 | DU00002861884 |  |  |  |  | 2024-06-21 |  | LAMP_POLE
B00099 | W066Y_B00099OD_KGBARUAMPANG | Central |  | Decomm |  | 2024 Q2 | BY | YPTT | 4.6 TSSR Approved |  | 2024-03-04 |  |  |  | 2024-03-06 |  | 2024-04-01 | 2024-07-12 | CD//Ali Akaram | 2024-04-02 | BOQ_Celcom Digi_RAN-YPTT-Standard PR TSS-20240311 | DU00002861885 |  |  |  |  | 2024-07-25 |  | TRIPOD
Q00477 | Q115A_Q00477OD_KGSERASOT | Sarawak |  | Decomm |  | 2024 Q2 | ZB | Trintel | 4.6 TSSR Approved |  | 2024-01-29 |  |  |  | 2024-01-30 |  | 2024-01-30 | 2024-06-21 | CD//John | 2024-02-02 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20240204/Celcom Digi_RAN-Trintel-Standard PR TSS DECOMM-Sarawak-20240314 | DU00002861886 |  |  |  |  | 2024-06-27 |  | TOWER
Q00563 | Q132A_Q00563OD_CB_BEKENU | Sarawak | 9247P | Swap | Maintain USP MOCN->On Hold->Swap | 2025 Q2 | AI | Trintel | 4.6 TSSR Approved |  | 2025-02-20 | 2025-04-07 |  | 2025-04-21 |  | Closed | 2025-04-21 | 2025-04-22 | CD//John | 2025-04-21 | SQ202501070293-Trintel | DU00002861887 |  |  | 2025-05-19 | 2025-05-08 |  | Tower | TOWER | 60 | Add R8852E S9000x3+R8854E S1800x3+R8894E M1821x4+R8862A S2601x2+R8854 S2600x1, Dismantle | 0 | 1
Q00306 | Q132A_Q00306OD_CB_SPGBEKENU | Sarawak | 9248P | Swap | Maintain USP MOCN->On Hold->Swap | 2025 Q2 | AI | Trintel | 4.6 TSSR Approved |  | 2025-02-26 | 2025-03-21 |  | 2025-04-04 |  | Closed | 2025-04-21 | 2025-04-22 | CD//John | 2025-04-21 | SQ202501070293-Trintel | DU00002861888 |  |  | 2025-09-25 | 2025-09-23 |  | Tower | TOWER | 76 | Add R8852E S9000x3+R8854E S1800x3+R9264M M1821x4+R8862A S2601x4, Dismantle | 0 | 3
Q00569 | Q132A_Q00569OD_CB_SPGBELURU | Sarawak |  | MOCN By Other Vendor | Maintain USP MOCN->On Hold->Maintain USP MOCN->On Hold->MOCN By Other Vendor | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861889 | [6 empty] | TOWER
Q01733 | Q132A_Q01733OD_CB_KGBAKAM | Sarawak |  | Decomm |  | 2025 Q2 | AI | Trintel | 4.6 TSSR Approved |  | 2025-02-20 |  | 2025-05-06 |  | 2025-05-10 |  | 2025-05-13 | 2025-10-28 | CD//John | 2025-05-27 | SQ202501070293-Trintel | DU00002861890 |  |  |  |  | 2025-08-09 |  | TOWER
Q00630 | Q132C_Q00630OD_MYYBYPASS | Sarawak |  | Decomm |  | 2025 Q1 | ZB | Trintel | 4.6 TSSR Approved |  | 2024-04-22 |  |  |  | 2024-04-22 |  | 2024-04-26 | 2024-05-24 | CD//John | 2024-05-13 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240503 | DU00002861891 |  |  |  |  | 2025-06-12 |  | TOWER
Q01732 | Q132A_Q01732OD_CB_LAMBIRMIRITRUNK | Sarawak |  | MOCN By Other Vendor | Maintain USP MOCN->On Hold->Maintain USP MOCN->On Hold->MOCN By Other Vendor | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861892 | [6 empty] | TOWER
Q00687 | Q132A_Q00687OD_CB_KGSEPURAU | Sarawak | 9182P | Swap | Maintain USP MOCN->On Hold->Swap | 2025 Q2 | AD | Trintel | 4.6 TSSR Approved |  | 2025-02-26 | 2025-04-17 |  | 2025-04-22 |  | Under Approval | 2025-04-24 | 2025-04-26 | CD//John | 2025-04-25 | SQ202501070293-Trintel | DU00002861893 |  |  | 2025-07-06 | 2025-06-09 |  | Tower | TOWER | 60m | Add R8852E S9000x3+R8854E S1800x3+R8894E M1821x3, Dismantle | 0 | 0
Q00578 | Q132A_Q00578OD_BAKAM | Sarawak |  | Decomm |  | 2025 Q2 | AD | Trintel | 4.6 TSSR Approved |  | 2025-02-20 |  | 2025-05-16 |  | 2025-05-24 |  | 2025-05-30 | 2025-10-28 | CD//John | 2025-05-30 | SQ202501070293-Trintel | DU00002861894 |  |  |  |  | 2025-09-26 |  | TOWER
Q00362 | Q125A_Q00362OD_CB_SUNDAR | Sarawak | 9174P | Swap | Maintain USP MOCN->On Hold->Swap | 2025 Q2 | AI | DATASCO | 4.6 TSSR Approved |  | 2025-02-04 | 2025-05-16 |  | 2025-05-23 |  | Closed | 2025-05-26 | 2025-06-24 | E//John | 2025-05-28 | SQ202501070453-Datasco | DU00002861895 |  |  | 2025-07-06 | 2025-06-14 |  | Tower | TOWER | 76 | Add R8852E S9000x3+R8894E M1821x7, Dismantle | 0 | 3
B01070 | B064D_B01070OD_TMNRAKANKJG | Central |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4(single site MOCN)-L26 SSM | SY1 | GCI | 4.6 TSSR Approved |  | 2024-10-02 |  | 2024-10-15 |  | 2024-10-08 |  | 2024-10-09 | 2025-07-14 | CD//Ali Akaram | 2025-03-07 | 0924CD-Central-GCI-BOQ Template(new contract) | DU00002861896 |  |  |  |  | 2025-09-10 |  | LAMP_POLE
B00659 | W066BB_B00659OD_TMNDELIMA | Central |  | Decomm |  | 2024 Q4 | CR | GCI | 4.6 TSSR Approved |  | 2023-11-10 |  |  |  | 2023-11-08 |  | 2023-12-06 | 2025-03-21 | CD//Ali Akaram | 2024-07-29 | CelcomDigi_RAN_GCI_TSS_Central_20231113 | DU00002861897 |  |  |  |  | 2024-10-24 |  | BOOM
B00355 | B061T_B00355OD_JLN20SEK14PJ | Central |  | Decomm |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-05-15 |  |  |  | 2024-05-15 |  | 2024-05-17 |  | CD//Ali Akaram | 2024-05-23 | CelcomDigi_RAN_Datasco_TSS_Central_20240517 | DU00002861898 |  |  |  |  | 2024-06-04 |  | TRIPOD
B00089 | W066X_B00089OD_AMPGJAYA | Central |  | Decomm |  | 2024 Q4 | MS | Ascentrack | 4.6 TSSR Approved |  | 2024-01-26 |  |  |  | 2024-01-29 |  | 2024-02-05 | 2024-02-23 | CD//Norhaliza | 2024-02-15 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240128 | DU00002861899 |  |  |  |  | 2024-08-26 |  | TOWER
B00637 | B064G_B00637OD_SGTANGKAS | Central |  | Decomm |  | 2024 Additional | SHA | GTSB | 4.6 TSSR Approved |  | 2024-08-29 |  | 2024-09-09 |  | 2024-09-24 |  | 2024-11-20 |  | CD//Norhaliza | 2024-12-09 | 0919CD-Central-GTSB-BOQ Template(new contract) 2 | DU00002861900 |  | This site having childsite B02277, pls update in the TP what is the plan for the cs and update topo too |  |  | 2025-06-17 |  | TOWER
W00814 | W066J_W00814OD_LRTJELATEK | Central |  | Decomm | Decomm->On hold->Decomm | 2024 Q1 | AI | GCI | 4.6 TSSR Approved |  | 2025-05-14 |  | 2025-05-21 |  | 2025-06-13 |  | 2025-09-03 |  | CD//Sapian | 2025-09-08 | SQ202506250633 | DU00002861901 |  |  |  |  | 2025-06-24 |  | BOOM
B02348 | B061L_B02348OD_SURAUALTAUBAHPCHGINDAH | Central |  | Decomm |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-15 |  |  |  | 2024-07-26 |  | 2024-08-06 | 2025-01-14 | CD//Ali Akaram | 2024-12-16 | CelcomDigi_RAN_GTSB_TSS_Central_20240509 | DU00002861902 |  |  |  |  | 2024-10-24 |  | LAMP_POLE
W01204 | W066S_W01204OD_JALANJALILPERKASA | Central |  | Decomm |  | 2024 Q3 | SH | GTSB | 4.6 TSSR Approved |  | 2024-02-05 |  |  |  | 2024-02-14 |  | 2024-04-01 | 2024-09-25 | CD//Norhaliza | 2024-08-21 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240212 | DU00002861903 |  |  |  |  | 2024-08-22 |  | LAMP_POLE
B00921 | W067A_B00921OD_MENARA_USAHAWAN_WPPJ | Central | 1843K | Swap | Decomm->Swap | 2024 Q3 | SY1 | GTSB | 4.6 TSSR Approved |  | 2024-06-19 | 2024-06-24 |  | 2024-06-27 |  | Closed | 2024-07-05 | 2024-07-11 | CD//Sapian | 2024-07-11 | 0624Central-GTSB-BOQ Template (template) | DU00002861904 |  |  | 2024-08-10 | 2024-08-05 |  | In-Building System | UNIPOLE | 6M | Add R8862A S9000 x3+R8862A S2601 x3+A9732 M1821 x3,Dismantle | 123 | 0
B00208 | W066I_B00208OD_TMNSRIUKAY | Central |  | Decomm |  | 2024 Q1 | BY | GTSB | 4.6 TSSR Approved |  | 2024-07-24 |  | 2024-07-30 |  | 2024-08-01 |  | 2024-08-02 | 2025-03-11 | CD//Norhaliza | 2024-09-12 | 0725Central-GTSB-BOQ Template(new contract) | DU00002861905 |  |  |  |  | 2024-08-19 |  | MONOPOLE
W00655 | B057D_W00655OD_TMNCEMERLANG | Central |  | Decomm |  | 2024 Q1 | MS | GTSB | 4.6 TSSR Approved |  | 2024-02-22 |  |  |  | 2024-02-26 |  | 2024-02-27 | 2024-05-27 | CD//Sapian | 2024-03-13 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240225 | DU00002861906 |  |  |  |  | 2024-04-02 |  | TOWER
A00052 | A040B_A00052OD_TMNSRIRAPAT | Northern |  | Decomm |  | 2024 Q2 | ZA | GCI | 4.6 TSSR Approved |  | 2023-10-19 |  |  |  | 2023-10-21 |  | 2023-10-26 | 2024-04-23 | CD//Rohizam | 2023-10-27 | Celcom Digi_RAN-GCI-TSS-Northern-20231020-0063/GCI Northern TX TSS | DU00002861907 |  | Missing TX info and Photo |  |  | 2024-03-29 |  | BOOM
A00646 | A040B_A00646OD_DCAIPOH | Northern | 4615K | Swap | Decomm->On Hold->Swap | 2024 Q2 | SHA | GCI | 4.6 TSSR Approved | ¦1123 - Emailed planning on owner rejection ¦ 1004 - Emailed Rollout on CME requirement ¦ 0809 - Changed anchor, SOW changed to SWAP ¦ 0422 - Izzat: Based on prediction plot, NIC NNS 4716D can cover up to Institut latihan Tentera Udara Ipoh and Kampung Rapat Jaya. Area A cannot be cover by A00528 15m height 1.2km away. ¦ 0313 - SOW changed to On Hold ¦15-3- ZTE planner to start study ¦& revert ¦ 0221 - Planner to justify, CD Quah:Please help to justify why the anchor site 4084C height is less than half of the planned decom xC site According to ookla, the coverage of celcom is better than digi in this area | 2023-12-18 | 2024-09-06 |  | 2025-05-15 | 2024-01-08 | Under Approval | 2024-10-04 | 2024-10-10 | CD//Zulakmar | 2024-10-09 | Celcom Digi_RAN-GCI-TSS-Northern-20231225-0085/Celcom Digi_RAN-GCI-TSS-Northern-20240130-0092/0813CD-Northern-GCI-BOQ Template(new contract) | DU00002861908 |  |  | 2025-05-21 | 2024-10-22 |  | Monopole | LAMP_POLE | 30 | Add R9264H M901821x3+R8862A S2601x1+R8854 S2600x2,Dismantle | 0 | 12
S01072 | S105B_S01072OD_SERIHARAPANIJM | Sabah | 7282K | Swap | Decomm->On hold->Swap | 2024 Q3 | MS | GTSB | 4.6 TSSR Approved |  | 2024-07-02 | 2024-10-23 | 2024-07-08 | 2024-11-08 |  | Under Approval | 2024-11-12 | 2024-11-14 | CD//Sharidah | 2024-11-13 | PR raised as per design team | DU00002861909 |  |  | 2025-02-28 | 2025-02-27 |  | Lampole | RAPOLE | 18 | Add R8862A S9000x3+R8894E M1821x3, Dismantle | 0 | 0
B00614 | W066X_B00614OD_TASIKTAMBAHAN | Central |  | Decomm | Decomm>On Hold->Decomm | 2024 Q4 | SM | GTSB | 4.6 TSSR Approved |  | 2023-12-27 |  |  |  | 2024-04-18 |  | 2024-05-23 | 2025-10-01 | CD//Sapian | 2024-06-06 | CelcomDigi_RAN_GTSB_TSS_Central_20231230 | DU00002861910 |  |  |  |  | 2025-05-20 |  | BOOM
W01216 | W0066AA_W01216OD_JLN_SRI_PERMAISURI | Central |  | Decomm |  | 2024 Q3 | BY | Ascentrack | 4.6 TSSR Approved |  | 2023-11-16 |  |  |  | 2023-12-25 |  | 2024-04-01 |  | CD//Ali Akaram | 2024-08-27 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231119 | DU00002861911 |  | Missing FE part |  |  | 2024-08-08 |  | LAMP_POLE
B01467 | B064H_B01467OD_ILSASBANGI | Central |  | Decomm |  | 2024 Q3 | CR | Solusi | 4.6 TSSR Approved |  | 2024-10-29 |  |  |  | 2024-10-29 |  | 2024-11-07 | 2025-10-01 | CD//Sapian | 2024-11-12 | 0924CD-Central-Solusi-BOQ Template(new contract) | DU00002861912 |  |  |  |  | 2024-11-25 |  | BOOM
B00251 | B064B_B00251OD_DAMAIPERDANA | Central |  | Decomm |  | 2024 Q4 | SH | Solusi | 4.6 TSSR Approved |  | 2024-07-04 |  |  |  | 2024-09-09 |  | 2024-09-10 |  | CD//Ali akaram | 2024-09-26 | 0709Central-Solusi-BOQ Template | DU00002861913 |  | Pls provide all idu photo with clear label. Refer attachment |  |  | 2024-12-05 |  | MINI MONOPOLE
Q01280 | T3_0335 - KG OPAR | Sarawak |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q2 |  | Trintel | 14.1 TSSR Not Required (Decomm by CD) |  | 2025-10-08 |  | 2025-07-09 |  |  | To be Submitted |  |  |  |  | SQ202506060240-Trintel | DU00002861914 | Confirm by FF/OSS, no xC equipment onsite |  |  |  | 2025-10-08 |  | TOWER
Q01274 | Q137A_Q01274OD_JLNENGTAI | Sarawak |  | Decomm |  | 2025 Q2 | ZB | Trintel | 4.6 TSSR Approved |  | 2023-12-08 |  |  |  | 2023-12-13 |  | 2023-12-13 | 2023-12-20 | CD//John | 2023-12-14 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231212 | DU00002861915 |  |  |  |  | 2025-08-28 |  | UNIPOLE
Q01703 | Q120A_Q01703OD_CB_KGBELAWAI | Sarawak |  | Decomm |  | 2025 Q1 | SH | Magicell | 4.6 TSSR Approved |  | 2024-01-27 |  |  |  | 2024-02-12 |  | 2024-02-14 | 2024-02-16 | CD//John | 2024-02-15 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20240204 | DU00002861916 |  |  |  |  | 2025-04-10 |  | TOWER
B00212 | B057D_B00212OD_HOTELSRIAMAN | Central |  | Decomm |  | 2024 Q1 | AI | GTSB | 4.6 TSSR Approved |  | 2024-02-16 |  |  |  | 2024-02-20 |  | 2024-08-13 | 2024-09-25 | CD//Ali Akaram | 2024-08-16 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240217 | DU00002861917 |  |  |  |  | 2024-05-13 |  | BOOM
B01341 | B061L_B01341OD_PCHGUTAMA3 | Central |  | Decomm |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-02-09 |  |  |  | 2024-02-14 |  | 2024-04-19 | 2024-05-27 | CD//Ali Akaram | 2024-05-13 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240212 | DU00002861918 |  |  |  |  | 2024-09-03 |  | SHARING STRC SBC
B02247 | B061J_B02247OD_TMN_POK_SIONG | Central |  | Decomm |  | 2024 Q3 | CR | GCI | 4.6 TSSR Approved |  | 2024-01-16 |  |  |  | 2024-01-24 |  | 2024-04-24 | 2024-10-29 | CD//Norhaliza | 2024-09-12 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240128 | DU00002861919 |  |  |  |  | 2024-10-25 |  | UNIPOLE
B00506 | B061O_B00506OD_DMANSARAJAYA | Central |  | Decomm |  | 2024 Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2023-11-21 |  |  |  | 2023-11-30 |  | 2023-12-06 | 2024-03-22 | CD//Sapian | 2024-02-22 | CelcomDigi_RAN_Magicell_TSS_Central_20231126 | DU00002861920 |  |  |  |  | 2024-05-31 |  | MINI STRUCTURE
B00536 | B061S_B00536OD_JBASS2PJ | Central |  | Decomm |  | 2024 Q3 | CR | GCI | 4.6 TSSR Approved |  | 2024-03-19 |  |  |  | 2024-03-20 |  | 2024-03-21 | 2025-03-07 | CD//Norhaliza | 2024-06-05 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240323 | DU00002861921 |  |  |  |  | 2024-05-31 |  | TOWER
B00038 | W066J_B00038OD_AU5C | Central |  | Decomm |  | 2024 Q1 | SS | YPTT | 4.6 TSSR Approved |  | 2023-11-22 |  |  |  | 2023-12-18 |  | 2024-01-05 | 2025-10-01 | CD//Ali Akaram | 2024-01-16 | CelcomDigi_RAN_YPTT_TSS_Central_20231126 | DU00002861922 |  |  |  |  | 2024-07-18 |  | MINI STRUCTURE
B02545 | B064F_B02545OD_JLN_SIMPANGBALAK_KJG | Central |  | Decomm | Decomm-On Hold->Decomm | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-03-20 |  |  |  | 2024-04-08 |  | 2024-04-18 | 2025-03-21 | CD//Sapian | 2024-05-11 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240323 | DU00002861923 |  |  |  |  | 2025-06-13 |  | LAMP_POLE
B00776 | B064C_B00776OD_SERDANGJAYA | Central |  | Decomm |  | 2024 Q3 | CR | GCI | 4.6 TSSR Approved |  | 2024-03-18 |  |  |  | 2024-04-19 |  | 2024-04-24 | 2024-09-25 | CD//Ali Akaram | 2024-05-13 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240323 | DU00002861924 |  |  |  |  | 2024-08-28 |  | BOOM
A00209 | A041A_A00209OD_BENDANGKERING_RCD | Northern |  | Decomm |  | 2025 Q3 | SM | YPTT | 4.6 TSSR Approved | 0123 - CD Zul: TSSR is ok. However, lets wait for the pair site to be implemented first before I approve this tssr. | 2024-01-16 |  |  |  | 2024-01-23 |  | 2025-01-08 | 2026-02-06 | CD//Zulakmar | 2025-03-03 | Celcom Digi_RAN-YPTT-TSS-Northern-20240124-0056// SQ202501030072 -YPTT | DU00002861925 |  | CD Hazwan reviewed but Hold wait for upg tssr ready first |  |  | 2025-07-10 |  | TOWER
W00155 | W066U_W00155OD_BRICKFIELDS2 | Central |  | Decomm |  | 2024 Q2 | ZB | CCSMY | 4.6 TSSR Approved |  | 2023-12-09 |  |  |  | 2023-12-18 |  | 2024-01-21 | 2024-02-15 | CD//Norhaliza | 2024-02-06 | CelcomDigi_RAN_CCSMY_TSS_Central_20231213 | DU00002861926 |  |  |  |  | 2024-07-31 |  | BOOM
W00108 | W066U_W00108OD_BGNVERAPPAN | Central |  | Decomm |  | 2024 Q2 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-12-11 |  |  |  | 2024-01-04 |  | 2024-01-11 | 2024-01-22 | CD//Sapian | 2024-01-19 | CelcomDigi_RAN_CCSMY_TSS_Central_20231214 | DU00002861927 |  |  |  |  | 2024-07-29 |  | MINI MONOPOLE
W01227 | W066Q_W01227OD_SALAKSELATAN_NEW_VILLAGE1 | Central |  | Decomm | Decomm->On Hold->Site Out->Decomm | 2024 Q3 | MNO | GTSB | 4.6 TSSR Approved |  | 2024-07-18 |  | 2024-07-30 |  | 2024-08-01 |  | 2025-07-07 | 2026-01-21 | CD//Sapian | 2025-07-17 | 0730CD-Central-GTSB-BOQ Template(new contract) | DU00002861928 |  |  |  |  | 2025-06-26 |  | LAMP_POLE
W00197 | W066J_W00197OD_JLNSEMARAK | Central |  | Decomm |  | 2024 Q1 | SM | YPTT | 4.6 TSSR Approved |  | 2024-02-20 |  |  |  | 2024-02-20 |  | 2024-02-21 | 2025-03-21 | CD//Norhaliza | 2024-05-13 | BOQ_Celcom Digi_RAN-YPTT-Standard PR TSS-20240225 | DU00002861929 |  |  |  |  | 2024-07-31 |  | BOOM
B01130 | B061Q_B01130OD_JLNTEMPLERPJ | Central |  | Decomm |  | 2024 Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2024-03-15 |  |  |  | 2024-05-17 |  | 2024-05-21 | 2024-09-25 | CD//Norhaliza | 2024-09-12 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240316 | DU00002861930 |  |  |  |  | 2024-07-05 |  | BOOM
B00672 | B061Q_B00672OD_PJOLDTOWN | Central |  | Decomm |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-03-14 |  |  |  | 2024-04-22 |  | 2024-06-24 | 2024-09-25 | CD//Norhaliza | 2024-09-12 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240316 | DU00002861931 |  |  |  |  | 2024-05-29 |  | MINI STRUCTURE
B01060 | B064G_B01060OD_SEK42BBBANGI | Central |  | Decomm |  | 2024 Q3 | SY1 | Solusi | 4.6 TSSR Approved |  | 2024-10-10 |  |  |  | 2024-10-18 |  | 2024-10-22 | 2025-01-14 | CD//Sapian | 2024-11-05 | 0924CD-Central-GCI-BOQ Template(new contract) | DU00002861932 |  |  |  |  | 2024-09-30 |  | MINI STRUCTURE
S01488 | S104A_S01488OD_CB_KGKINARASAN | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2025 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2025-08-11 |  | 2025-08-18 |  | 2025-08-23 |  | 2025-09-09 | 2025-10-29 | E//Hannah | 2025-09-18 | SQ202506100836 - YPTT / SQ202507010450 - YPTT | DU00002861933 |  |  |  |  | 2025-09-28 |  | TOWER
B00234 | B064D_B00234OD_SGLONG3 | Central |  | Decomm |  | 2024 Q4 | SM | GTSB | 4.6 TSSR Approved |  | 2024-09-11 |  | 2024-09-18 |  | 2024-10-04 |  | 2024-10-07 | 2025-01-14 | CD//Norhaliza | 2024-11-21 | 0924CD-Central-GTSB-BOQ Template(new contract) | DU00002861934 |  |  |  |  | 2025-03-20 |  | MINI STRUCTURE
Q00815 | Q137A_Q00815OD_CB_JLNTAPAH | Sarawak | 9251P | Swap | Maintain USP MOCN->On Hold->Swap | 2025 Q2 | HW | Trintel | 4.6 TSSR Approved |  | 2025-02-20 | 2025-04-14 |  | 2025-04-24 |  | Under Approval | 2025-05-05 | 2025-05-19 | E//John | 2025-05-07 | SQ202501070293-Trintel | DU00002861935 |  |  | 2025-06-30 | 2025-06-12 |  | Tower | TOWER | 36 | Add R8852E S9000x3+R8894E M1821x3+R9264M M1821x3+R8862A S2601x3, Dismantle | 0 | 0
S01210 | S105B_S01210OD_TMNMAWARRD | Sabah |  | Decomm |  | 2025 Q2 | SH | Futong | 4.6 TSSR Approved |  | 2024-03-26 |  |  |  | 2024-03-27 |  | 2024-04-04 | 2024-07-12 | CD//Mohidi Jaan | 2024-04-04 | Celcom Digi_RAN-Futong-TSS-Sabah-20240329 / SQ202501020444 - Futong | DU00002861936 |  |  |  |  | 2024-07-16 |  | MONOPOLE
W00604 | W066Q_W00604OD_DESASRIPUTRI | Central |  | Decomm |  | 2024 Q3 | BY | DATASCO | 4.6 TSSR Approved |  | 2024-06-20 |  |  |  | 2024-06-28 |  | 2024-07-03 | 2024-08-22 | CD//Ali Akaram | 2024-07-18 | 0624Central-DATASCO-BOQ Template (template) | DU00002861937 |  |  |  |  | 2024-10-04 |  | MONOPOLE
B00692 | B061S_B00692OD_PARAMONTSP | Central |  | Decomm |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-05-23 |  |  |  | 2024-05-23 |  | 2024-05-27 |  | CD//Norhaliza | 2024-06-19 | CelcomDigi_RAN_Datasco_TSS_Central_20240528 | DU00002861938 |  | MISSING FE INFO |  |  | 2024-06-15 |  | BOOM
A00640 | A040B_A00640OD_WIRAJAYA | Northern |  | Decomm |  | 2024 Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2023-12-20 |  |  |  | 2023-12-28 |  | 2024-01-03 | 2024-05-24 | CD//Affendi | 2024-01-05 | Celcom Digi_RAN-GTSB-TSS-Northern-20231225-0080 | DU00002861939 |  | Change SOW due different structure can't relocate |  |  | 2024-06-04 |  | LAMP_POLE
W00116 | W066E_W00116OD_JLNSETAPAK | Central |  | Decomm |  | 2024 Q1 | BY | DATASCO | 4.6 TSSR Approved |  | 2024-01-24 |  |  |  | 2024-02-21 |  | 2024-02-22 |  | CD//Sapian | 2024-03-06 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240128 | DU00002861940 |  | MISSING FE |  |  | 2024-05-15 |  | TRIPOD
B00759 | B057D_B00759OD_GBKSETIA | Central |  | Decomm |  | 2024 Q1 | AI | GTSB | 4.6 TSSR Approved |  | 2024-02-16 |  |  |  | 2024-02-20 |  | 2024-02-29 | 2024-04-24 | CD//Sapian | 2024-03-13 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240217 | DU00002861941 |  |  |  |  | 2024-04-04 |  | BOOM
W01538 | W066V_W01538OD_JLNBKTPANTAISL4 | Central |  | Decomm | Decomm->On hold->Decomm | 2024 Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2024-10-23 |  |  |  | 2024-02-15 |  | 2024-02-15 |  | CD//Ali akaram | 2024-06-13 | 0923CD-Central-Allstar-BOQ Template(new contract) | DU00002861942 |  | MISSING FE PART |  |  | 2024-10-26 |  | LAMP_POLE
Q01350 | Q135A_Q01350OD_TMNUNI | Sarawak |  | Decomm |  | 2024 Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-11-14 |  |  |  | 2023-11-20 |  | 2023-11-20 | 2023-11-22 | CD//John | 2023-11-20 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231019/Celcom Digi_RAN-Trintel-TSS DECOMM-Sarawak-20231130 | DU00002861943 |  |  |  |  | 2025-09-26 |  | RAPOLE
W00685 | W066V_W00685OD_IPTARRTM | Central |  | Decomm |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-01-30 |  |  |  | 2024-02-01 |  | 2024-05-15 | 2024-09-25 | CD//Sapian | 2024-02-19 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240202 | DU00002861944 |  |  |  |  | 2024-05-25 |  | BOOM
W00053 | W066R_W00053OD_PR_TPM | Central |  | Decomm |  | 2024 Q3 | SH | GTSB | 4.6 TSSR Approved |  | 2024-02-08 |  |  |  | 2024-02-13 |  | 2024-04-01 | 2025-10-01 | CD//Sapian | 2024-04-29 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240212 | DU00002861945 |  |  |  |  | 2024-08-19 |  | SHARING STRC SBC
Q01277 | Q137A_Q01277OD_HOSPITALSARIKEI | Sarawak |  | Decomm |  | 2025 Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-12-08 |  |  |  | 2023-12-14 |  | 2023-12-14 | 2023-12-20 | CD//John | 2023-12-14 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231212 | DU00002861946 |  |  |  |  | 2025-11-10 |  | LAMP_POLE
B02269 | B064B_B02269OD_MASJIDALIKHWANIAHCHRSUTAMA | Central |  | Decomm |  | 2024 Q4(single site MOCN)-L26 SSM | SHA | Magicell | 4.6 TSSR Approved |  | 2024-09-19 |  | 2024-09-30 |  | 2024-10-03 |  | 2024-10-07 | 2025-03-03 | CD//Sapian | 2024-10-17 | 0924CD-Central-Magicell-BOQ Template(new contract) | DU00002861947 |  |  |  |  | 2025-02-26 |  | LAMP_POLE
B02410 | W067A_B02410OD_CENTURY_SQUARE_CBJ | Central |  | Decomm |  | 2024 Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2024-03-05 |  |  |  | 2024-03-12 |  | 2024-05-21 | 2024-10-29 | CD//Sapian | 2024-06-03 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240311 | DU00002861948 |  |  |  |  | 2025-08-04 |  | POLE
B02235 | B061K_B02235OD_SURAUALMUSTAQQIMLESTARIPUTRA | Central |  | Decomm | Decomm-On Hold->Decomm | 2024 Q3 | HW | Solusi | 4.6 TSSR Approved |  | 2024-07-09 |  |  |  | 2025-06-03 |  | 2025-06-04 | 2025-07-14 | CD//Sapian | 2025-06-05 | 0724Central-Solusi-BOQ Template | DU00002861949 | 22/5/25: SOW Changed from On Hold to Decomm |  |  |  | 2025-06-23 |  | LAMP_POLE
B02303 | W067A_B02303OD_PDGBOLAPRSNT14WPPJ | Central |  | Decomm |  | 2024 Q3 | CR | Solusi | 4.6 TSSR Approved |  | 2024-07-18 |  |  |  | 2024-10-21 | To be Submitted | 2024-11-07 |  | CD//Norhaliza | 2024-11-21 | 0924CD-Central-GTSB-BOQ Template(new contract) | DU00002861950 |  |  |  |  | 2024-11-29 |  | PYLON
W01235 | B064C_W01235OD_RMC_SG_BESI | Central |  | Decomm |  | 2024 Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2023-11-27 |  |  |  | 2023-12-05 |  | 2023-12-13 | 2024-07-26 | CD//Sapian | 2023-12-22 | CelcomDigi_RAN_Magicell_TSS_Central_20231201 | DU00002861951 |  |  |  |  | 2024-08-28 |  | MONOPOLE
B00430 | B061H_B00430OD_TMNKANAGAPURAM | Central |  | Decomm |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-02-20 |  | 2024-08-06 |  | 2024-08-02 |  | 2024-08-06 | 2024-11-26 | CD//Sapian | 2024-08-12 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240225 | DU00002861952 |  |  |  |  | 2024-08-27 |  | BOOM
B02264 | B057D_B02264OD_SURAUANNAIMTMNSAMUDRAGBK | Central |  | Decomm |  | 2024 Q1 | SS | Magicell | 4.6 TSSR Approved |  | 2023-12-01 |  |  |  | 2023-12-06 |  | 2023-12-13 | 2024-04-24 | CD//Norhaliza | 2024-01-18 | CelcomDigi_RAN_Magicell_TSS_Central_20231203 | DU00002861953 |  |  |  |  | 2024-04-04 |  | RAPOLE
B01260 | B064C_B01260OD_SYABASSGLONG | Central |  | Decomm |  | 2024 Q4 | SY1 | GTSB | 4.6 TSSR Approved |  | 2024-09-04 |  | 2024-09-09 |  | 2024-09-11 |  | 2024-09-18 |  | CD//Ali Akaram | 2024-09-24 | 0924CD-Central-GTSB-BOQ Template(new contract) | DU00002861954 |  | Propose to relocate TM LL and PTN to 3967B |  |  | 2025-07-18 |  | MONOPOLE
S01759 | S094A_S01759OD_DGSPGEMPATPEKANGOSEN | Sabah |  | Decomm |  | 2025 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2025-01-23 |  | 2025-02-12 |  | 2025-02-21 |  | 2025-05-05 | 2025-10-28 | E//Sharidah | 2025-05-06 | SQ202501020455 - GTSB | DU00002861955 |  |  |  |  | 2025-07-10 |  | MONOPOLE
S00326 | S098A_S00326OD_CENDRAWASIH | Sabah |  | Decomm |  | 2024 Q4 | MS | Datasco | 4.6 TSSR Approved |  | 2024-07-29 |  | 2024-08-05 |  | 2024-08-08 |  | 2024-08-08 | 2024-09-13 | CD//Mohidi Jaan | 2024-08-11 | 0730CD-Sabah-Datasco-BOQ Template(new contract)/0730MW-Sabah-Datasco-BOQ Template(new contract) | DU00002861956 |  |  |  |  | 2024-12-11 |  | GUYED MAST
A00420 | A042C_A00420OD_CB_KGCHENGALJANTANG9 | Northern |  | Decomm |  | 2024 Q2 | ZA | GCI | 4.6 TSSR Approved |  | 2023-10-18 |  |  |  | 2023-10-20 |  | 2023-10-26 | 2024-05-24 | CD//Affendi | 2023-10-27 | Celcom Digi_RAN-GCI-TSS-Northern-20231020-0063/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240529-0109 | DU00002861957 |  | Missing TX info and Photo |  |  | 2024-05-20 |  | TOWER
S00513 | S094A_S00513OD_TGBATUMARUDU | Sabah |  | Decomm |  | 2025 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2025-01-23 |  | 2025-03-12 |  | 2025-04-09 |  | 2025-05-05 | 2025-10-28 | E//Sharidah | 2025-05-06 | SQ202501020455 - GTSB / SQ202501070280 - GTSB | DU00002861958 |  |  |  |  | 2025-07-09 |  | TOWER
S00555 | S107A_S00555OD_CB_KGKABANMELAMAM | Sabah | 7117P | Swap | Maintain USP MOCN->On Hold->Swap | 2025 Q2 | AD | DATASCO | 4.6 TSSR Approved |  | 2025-01-17 | 2025-03-13 |  | 2025-03-21 |  | Under Approval | 2025-03-23 | 2025-05-27 | CD//Sharidah | 2025-03-24 | SQ202501020331 - Datasco | DU00002861959 |  |  | 2025-09-23 | 2025-09-12 |  | Tower | TOWER | 75 | Add R8852E S9000x3+R8894E M1821x7, Dismantle | 0 | 2
B00607 | W066Y_B00607OD_TMNMEGAJAYA | Central |  | Decomm |  | 2024 Q3 | AI | YPTT | 4.6 TSSR Approved |  | 2024-08-14 |  | 2024-08-19 |  | 2024-08-23 |  | 2024-08-27 |  | CD//Ali Akaram | 2024-09-11 | 0809CD-Central-YPTT-BOQ Template(new contract) | DU00002861960 |  |  |  |  | 2024-09-21 |  | BOOM
Q01848 | Q122A_Q01848OD_KGMUHIBBAHKANOWIT | Sarawak |  | Decomm |  | 2025 Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2023-12-20 |  |  |  | 2023-12-27 |  | 2024-01-25 | 2024-02-09 | CD//John | 2024-01-26 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231221 | DU00002861961 |  |  |  |  | 2025-08-28 |  | RAPOLE
A00218 | A038A_A00218OD_KGSAHOM | Northern |  | Decomm |  | 2024 Additional | SHA | CCSMY | 4.6 TSSR Approved |  | 2024-01-23 |  | 2025-10-30 |  | 2024-01-26 |  | 2024-11-20 | 2026-01-21 | CD//Zulakmar | 2026-03-31 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240124-0089 | DU00002861962 |  |  |  |  | 2025-03-10 |  | TOWER
B00088 | W066J_B00088OD_TMNKERAMAT | Central |  | Decomm |  | 2024 Q1 | CR | GCI | 4.6 TSSR Approved |  | 2024-01-04 |  |  |  | 2024-01-18 |  | 2024-01-22 | 2025-03-12 | CD//Norhaliza | 2024-02-07 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240108 | DU00002861963 |  |  |  |  | 2024-07-25 |  | TRIPOD
W00879 | W066P_W00879OD_JLNCHANSOWLIN | Central |  | Decomm |  | 2024 Q3 | SM | Magicell | 4.6 TSSR Approved |  | 2024-01-22 |  |  |  | 2024-02-13 |  | 2024-03-27 |  | CD//Ali Akaram | 2024-04-08 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240128 | DU00002861964 |  |  |  |  | 2024-09-11 |  | TRIPOD
W00185 | W066H_W00185OD_PUSPAKOMWMJ | Central |  | Decomm |  | 2024 Q1 | CR | GCI | 4.6 TSSR Approved |  | 2023-11-22 |  |  |  | 2023-11-29 |  | 2023-11-30 | 2025-10-01 | CD//Ali Akaram | 2023-12-07 | CelcomDigi_RAN_GCI_TSS_Central_20231126 | DU00002861965 |  |  |  |  | 2024-05-04 |  | TOWER
B02326 | W067A_B02326OD_MENARA_IKHLAS_PRESINT3 | Central | 1850K | Swap | Decomm->Swap | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-06-27 | 2024-07-04 |  | 2024-07-05 |  | Under Approval | 2024-07-09 | 2024-07-30 | CD//Ali Akaram | 2024-07-30 | 0628Central-GTSB-BOQ Template (template) | DU00002861966 |  |  | 2024-08-10 | 2024-08-09 |  | Pole | POLE | 3m | Add R8862A S9000 x1+R9264H M901821 x3+R8862A S2601 x4+A9732 M1821 x1,Dismantle | 1 | 0
W01365 | W066S_W01365OD_JLNAWANJAWA_TMNYARL | Central |  | Decomm |  | 2024 Q3 | SM | Ascentrack | 4.6 TSSR Approved |  | 2024-01-31 |  |  |  | 2024-02-09 |  | 2024-03-29 | 2024-08-20 | CD//Sapian | 2024-04-23 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240202 | DU00002861967 |  |  |  |  | 2024-05-27 |  | LAMP_POLE
S01463 | S092A_S01463OD_CB_KGKEBAYAU | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2025 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2025-08-11 |  | 2025-08-18 |  | 2025-08-22 |  | 2025-09-09 | 2025-10-29 | E//Hannah | 2025-09-18 | SQ202506100836 - YPTT / SQ202507010450 - YPTT | DU00002861968 |  | Missing FE part |  |  | 2025-09-24 |  | TOWER
K00665 | K008A_K00665OD_JLNDATAI3 | Northern |  | Decomm |  | 2024 Additional | AD | GTSB | 15.4 Decomm Done without TSSR Approval |  | 2024-12-03 |  | 2024-12-13 |  | 2024-12-16 | To be Submitted | 2024-12-19 |  | CD//Zulakmar |  | SQ202412090105 - GTSB | DU00002861969 |  |  |  |  | 2025-02-21 |  | TOWER
W01457 | W066R_W01457OD_STDBKTJALIL_OD_BILLBOARD | Central |  | Decomm |  | 2024 Q3 | ZA | Magicell | 4.6 TSSR Approved |  | 2024-02-28 |  |  |  | 2024-03-06 |  | 2024-03-27 | 2024-04-24 | CD//Sapian | 2024-04-21 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240303 | DU00002861970 |  |  |  |  | 2024-08-07 |  | BILLBOARD
S01355 | S105A_S01355OD_TMNINDAHJAYAPH7 | Sabah |  | Decomm |  | 2024 Q3 | BY | GTSB | 4.6 TSSR Approved |  | 2024-03-11 |  |  |  | 2024-03-20 |  | 2024-04-03 | 2024-05-14 | CD//Mohidi Jaan | 2024-04-03 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240313/0612Sabah-GTSB-BOQ Template (template) | DU00002861971 |  |  |  |  | 2024-08-09 |  | AESTHETIC MONOPOLE
S00941 | KGBINTASAN | Sabah |  | Decomm |  | 2025 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2025-04-22 |  | 2025-05-08 |  | 2025-06-17 | To be Submitted | 2025-06-19 |  | E//Hannah | 2025-07-14 | SQ202501020455 - GTSB / SQ202501070280 - GTSB | DU00002861972 |  |  |  |  | 2025-10-12 |  | TOWER
S00554 | S089A_S00554OD_CB_KGKOLAPIS | Sabah | 7118P | Swap | Maintain USP MOCN->On Hold->Swap | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-01-20 | 2025-01-28 |  | 2025-02-03 |  | Under Approval | 2025-02-06 | 2025-02-18 | CD//Sharidah | 2025-02-07 | SQ202501020392 - Futong | DU00002861973 |  |  | 2025-06-07 | 2025-05-23 |  | Tower | TOWER | 65m | Add R8852E S9000x3+R8854E S1800x3+R8894E M1821x4, Dismantle | 0 | 1
S00657 | S098C_S00657OD_MPOBOFFICE | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4 | AD | Datasco | 4.6 TSSR Approved |  | 2024-07-29 |  | 2024-08-06 |  | 2024-08-09 |  | 2024-08-09 | 2024-09-19 | CD//Mohidi Jaan | 2024-08-11 | 0730CD-Sabah-Datasco-BOQ Template(new contract) | DU00002861974 |  |  |  |  | 2025-08-25 |  | TRIPOD
Q01006 | Q124E_Q01006OD_CB_KGGIT | Sarawak | 9252P | Swap | Maintain USP MOCN->On Hold->Swap | 2025 Q1 | AI | Magicell | 4.6 TSSR Approved |  | 2025-01-22 | 2025-02-27 |  | 2025-03-04 |  | Under Approval | 2025-03-24 | 2025-05-21 | CD//John | 2025-03-25 | SQ202501070146-Magicell | DU00002861975 |  |  | 2025-06-07 | 2025-05-13 |  | Tower | TOWER | 75m | Add R8852E S9000x3+R8854E S1800x3+R8894E M1821x4, Dismantle | 0 | 3
Q00949 | Q130A_Q00949OD_CB_LAPOKTINJAR | Sarawak | 9184P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN->On Hold->Swap | 2025 Q3 | HW | Trintel | 4.6 TSSR Approved | 14/8 - 16/8 plan go in// 8/8 - team transport issue // 5/8- Wk33 plan | 2025-08-18 | 2025-09-02 |  | 2025-09-04 |  | Under Approval | 2025-09-05 | 2025-09-26 | E//John | 2025-09-12 | SQ202508110312-Trintel | DU00002861976 |  |  | 2025-10-18 | 2025-10-09 |  | Tower | TOWER | 76 | Add R8852E S9000x4+R8894E M1821x8, Dismantle | 0 | 0
Q01382 | Q131A_Q01382OD_KGTIAN | Sarawak |  | Decomm |  | 2025 Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2024-03-20 |  |  |  | 2024-03-22 |  | 2024-03-25 | 2024-05-24 | CD//John | 2024-03-25 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20240324 | DU00002861977 |  |  |  |  | 2025-07-14 |  | RAPOLE
Q01495 | Q114A_Q01495OD_KGSRITAJO | Sarawak |  | Decomm |  | 2024 Q2 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-12-08 |  |  |  | 2023-12-14 |  | 2024-01-22 | 2024-02-09 | CD//John | 2024-01-24 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231212/Celcom Digi_RAN-Magicell-Standard PR TSS DECOMM-Sarawak-20231229/CelcomDigi_RAN_Magicell_TSS_Sarawak_20241018 | DU00002861978 |  |  |  |  | 2024-07-07 |  | TOWER
Q00693 | Q135A_Q00693OD_T3_KGENDAP | Sarawak |  | Decomm |  | 2024 Q2 | SH | Magicell | 4.6 TSSR Approved |  | 2023-12-21 |  |  |  | 2024-01-03 |  | 2024-01-08 | 2024-01-22 | CD//John | 2024-01-09 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231231/Celcom Digi_RAN-Magicell-Standard PR TSS DECOMM-Sarawak-20231229/CelcomDigi_RAN_Magicell_TSS_Sarawak_20241018 | DU00002861979 |  |  |  |  | 2025-08-07 |  | TOWER
B00819 | B061S_B00819OD_SEK19PJ | Central |  | Decomm |  | 2024 Q3 | CR | GCI | 4.6 TSSR Approved |  | 2024-03-18 |  |  |  | 2024-03-21 |  | 2024-03-30 | 2024-09-25 | CD//Ali Akaram | 2024-04-18 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240323 | DU00002861980 |  |  |  |  | 2024-08-23 |  | TRIPOD
A00840 | A040D_A00840OD_MENGLEMBUTOWN_RCD | Northern |  | Decomm |  | 2024 Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2023-12-03 |  |  |  | 2023-12-12 |  | 2023-12-15 | 2024-01-22 | CD//Affendi | 2023-12-15 | Celcom Digi_RAN-GTSB-TSS-Northern-20231204-0071 | DU00002861981 |  |  |  |  | 2024-06-05 |  | BOOM
W01534 | W066V_W01534OD_TMNLUCKYBGSR2 | Central |  | Decomm |  | 2024 Q2 | MA | YPTT | 4.6 TSSR Approved |  | 2024-05-23 |  |  |  | 2024-05-27 |  | 2024-05-28 | 2025-03-12 | CD//Ali Akaram | 2024-06-04 | CelcomDigi_RAN_YPTT_TSS_Central_20240528 | DU00002861982 |  |  |  |  | 2024-07-23 |  | LAMP_POLE
B01295 | B064C_B01295OD_PR_KM18KLWPPJHWY | Central |  | Decomm |  | 2024 Q3 | MA | GCI | 4.6 TSSR Approved |  | 2023-10-30 |  |  |  | 2023-11-20 |  | 2024-01-26 | 2025-03-14 | CD//Ali Akaram | 2023-11-29 | CelcomDigi_RAN_GCI_TSS_Central_20231101 | DU00002861983 |  |  |  |  | 2024-08-28 |  | TOWER
A00778 | A044A_A00778OD_KPMSI | Northern |  | Decomm |  | 2024 Q2 | SM | CCSMY | 4.6 TSSR Approved |  | 2024-02-19 |  |  |  | 2024-02-20 |  | 2024-02-21 | 2024-06-07 | CD//Affendi | 2024-02-26 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240221-0094 | DU00002861984 |  |  |  |  | 2024-06-19 |  | LAMP_POLE
B02181 | B061L_B02181OD_MJDKGSERILANGKASPCHG | Central |  | Decomm |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-26 |  |  |  | 2024-02-01 |  | 2024-02-02 | 2024-04-24 | CD//Norhaliza | 2024-02-08 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240128 | DU00002861985 |  |  |  |  | 2024-11-12 |  | Lampole
Q01766 | Q135A_Q01766OD_CENTRALTOWNKSN | Sarawak |  | Decomm |  | 2024 Q2 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-11-04 |  |  |  | 2023-11-08 |  | 2023-11-14 | 2023-11-22 | CD//John | 2023-11-14 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231107/Celcom Digi_RAN-Magicell-Standard PR TSS DECOMM-Sarawak-20231229/CelcomDigi_RAN_Magicell_TSS_Sarawak_20241018 | DU00002861986 |  |  |  |  | 2025-10-10 |  | RAPOLE
B01315 | B061L_B01315OD_BDRBKTPCHG | Central |  | Decomm | Decomm->On Hold->Decomm | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-10 |  | 2024-07-20 |  | 2024-09-12 |  | 2024-12-16 | 2024-12-21 | CD//Ali akaram | 2024-12-17 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240115 | DU00002861987 |  |  |  |  | 2024-11-26 |  | BOOM
B00551 | B061T_B00551OD_SEK17PJ | Central |  | Decomm |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-05-03 |  |  |  | 2024-05-09 |  | 2024-05-10 | 2024-07-26 | CD//Sapian | 2024-05-21 | CelcomDigi_RAN_Datasco_TSS_Central_20240513 | DU00002861988 |  |  |  |  | 2024-08-21 |  | MINI STRUCTURE
W01511 | W066W_W01511OD_RAINTREEPOLO | Central |  | Decomm |  | 2024 Q2 | AD | GTSB | 4.6 TSSR Approved |  | 2024-02-08 |  |  |  | 2024-02-26 |  | 2024-02-27 | 2025-10-01 | CD//Norhaliza | 2024-04-03 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240212 | DU00002861989 |  |  |  |  | 2024-06-26 |  | AESTHETIC MONOPOLE
S01471 | S092A_S01471OD_CB_KGNARINANG | Sabah |  | Decomm |  | 2024 | MS | Seri Pancar | 4.6 TSSR Approved |  | 2024-11-18 |  | 2024-11-19 |  | 2024-11-20 |  | 2024-11-21 | 2024-12-13 | CD//Jahganathan | 2024-11-21 | Celcom Digi_RAN-Seri Pancar-Standard PR TSS-Sabah-20241030 | DU00002861990 |  |  |  |  | 2025-02-06 |  | TOWER
S01473 | S104A_S01473OD_CB_KGKIAU | Sabah |  | Decomm |  | 2025 Q3 | AD | NR services | 4.6 TSSR Approved |  | 2025-01-15 |  | 2025-02-12 |  | 2025-03-27 |  | 2025-04-30 | 2025-10-28 | E//Sharidah | 2025-05-08 | SQ202501020449 - NR Service / SQ202501070289 - NR Service | DU00002861991 |  |  |  |  | 2025-08-15 |  | LAMP_POLE
S00901 | S091A_S00901OD_IOISYARIMO7 | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 | HW | GTSB | 4.6 TSSR Approved |  | 2025-07-12 |  | 2025-07-14 |  | 2025-07-14 |  | 2025-09-10 | 2026-01-20 | E//Hannah | 2025-09-23 | SQ202506100849 - GTSB / SQ202507010442 - GTSB | DU00002861992 | [6 empty] | BOOM
S00940 | S096A_S00940OD_CB_KGPARAPATLAUT | Sabah |  | MOCN By Other Vendor | Maintain USP MOCN->On Hold->Maintain USP MOCN->On Hold->MOCN By Other Vendor | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861993 | [6 empty] | TOWER
S00177 | S091A_S00177OD_SIMEDARBY | Sabah |  | Decomm |  | 2024 Q4 | MS | NR services | 4.6 TSSR Approved |  | 2024-07-22 |  | 2024-08-12 |  | 2024-08-13 |  | 2024-08-14 | 2025-10-28 | CD//Sharidah | 2024-08-15 | 0725Sabah-NR-BOQ Template(new contract)/0725MW-Sabah-NR-BOQ Template(new contract) | DU00002861994 |  |  |  |  | 2024-12-19 |  | TOWER | 60
S01337 | S105A_S01337OD_SIMEDARBYTUNKUESTATE | Sabah |  | Decomm |  | 2024 Q4(single site MOCN)-L26 SSM | AD | NR services | 4.6 TSSR Approved |  | 2024-07-22 |  | 2024-08-15 |  | 2024-08-19 |  | 2024-08-20 | 2024-11-22 | CD//Thanniya | 2024-08-20 | 0725Sabah-NR-BOQ Template(new contract)/0725MW-Sabah-NR-BOQ Template(new contract) | DU00002861995 |  |  |  |  | 2024-12-17 | Tower | TOWER | 76
S01338 | S105A_S01338OD_SIMEDARBYTIGOWISESTATE | Sabah |  | Decomm |  | 2024 Q4(single site MOCN)-L26 SSM | AD | GTSB | 4.6 TSSR Approved |  | 2024-07-24 |  | 2024-07-26 |  | 2024-07-29 |  | 2024-07-31 | 2024-11-22 | CD//Ray Amos | 2024-08-05 | 0725Sabah-GTSB-BOQ Template(new contract)/0725MW-Sabah-GTSB-BOQ Template(new contract) | DU00002861996 |  |  |  |  | 2024-12-15 |  | TOWER
S00186 | S112A_S00186OD_CB_SOGOSOGO | Sabah | 7097P | Swap | Maintain USP MOCN->On Hold->Swap | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-01-16 | 2025-01-23 |  | 2025-01-31 |  | Under Approval | 2025-02-03 | 2025-02-18 | CD//Sharidah | 2025-02-05 | SQ202501020392 - Futong | DU00002861997 |  |  | 2025-05-25 | 2025-05-23 |  | Tower | TOWER | 76m | Add R8852E S9000x3+R9264M M1821x9, Dismantle | 0 | 123
B01557 | B064B_B01557OD_BTHO2 | Central |  | Decomm |  | 2024 Q4 | CR | GCI | 4.6 TSSR Approved |  | 2024-02-22 |  |  |  | 2024-02-27 |  | 2024-05-15 | 2025-03-07 | CD//Norhaliza | 2024-08-21 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240303 | DU00002861998 |  |  |  |  | 2024-10-23 |  | TRIPOD
Q02076 | Q126A_Q02076OD_CB_PAHLAWAN2 | Sarawak |  | MOCN By Other Vendor | Maintain USP MOCN->On Hold->Maintain USP MOCN->On Hold->MOCN By Other Vendor | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002861999 | [6 empty] | TOWER
S01646 | S091A_S01646OD_KGPELANGI | Sabah |  | Decomm |  | 2024 Q4 | ZB | Seri Pancar | 4.6 TSSR Approved |  | 2024-07-23 |  | 2024-07-31 |  | 2024-08-06 |  | 2024-08-07 | 2024-09-26 | CD//Sharidah | 2024-08-11 | 0725Sabah-Seri Pancar-BOQ Template(new contract)/0725MW-Sabah-Seri Pancar-BOQ Template(new contract) | DU00002862000 |  |  |  |  | 2025-01-07 |  | TOWER
W01362 | W066G_W01362OD_JALAN_MELATI_6 | Central |  | Decomm |  | 2024 Q1 | BY | GTSB | 4.6 TSSR Approved |  | 2024-02-06 |  |  |  | 2024-02-23 |  | 2024-02-27 | 2024-04-24 | CD//Ali Akaram | 2024-03-06 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240212 | DU00002862001 |  |  |  |  | 2024-05-09 |  | LAMP_POLE
W01374 | W066Z_W01374OD_JLNSEMARAHPADI_TMNPERTAMA | Central |  | Decomm |  | 2024 Q3 | SY1 | Solusi | 4.6 TSSR Approved |  | 2024-10-11 |  |  |  | 2024-10-21 |  | 2024-10-23 |  | CD//Ali Akaram | 2024-11-08 | 0809CD-Central-YPTT-BOQ Template(new contract) | DU00002862002 |  |  |  |  | 2024-09-27 |  | LAMP_POLE
S00280 | S095A_S00280OD_CB_MENUMBOK | Sabah | 7120P | Swap | Maintain USP MOCN->On Hold->Swap | 2025 Q1 | AD | YPTT | 4.6 TSSR Approved |  | 2025-01-08 | 2025-01-13 |  | 2025-01-15 |  | Under Approval | 2025-01-22 | 2025-02-18 | CD//Sharidah | 2025-02-04 | SQ202501020336 - YPTT | DU00002862003 |  |  | 2025-07-06 | 2025-05-25 |  | Tower | TOWER | 76 | Add R8852E S9000x3+R9224E M1821x8, Dismantle | 0 | 13
W01328 | W066U_W01328OD_WISMALEOPARD_JLNTUNSAMBATHAN | Central |  | Decomm | Decomm->On Hold->Decomm | 2024 Q2 | AD | YPTT | 4.6 TSSR Approved |  | 2024-02-15 |  |  |  | 2024-02-20 |  | 2024-02-22 | 2024-07-16 | CD//Norhaliza | 2024-05-28 | BOQ_Celcom Digi_RAN-YPTT-Standard PR TSS-20240225 | DU00002862004 |  |  |  |  | 2025-05-21 |  | UNIPOLE
Q00482 | Q138A_Q00482OD_CB_RHABI | Sarawak | 9222P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN->On Hold->Swap | 2025 | AD | Trintel | 4.6 TSSR Approved | 14/8 - 16/8 plan go in// 8/8 - team transport issue // 5/8- Wk33 plan | 2025-08-18 | 2025-08-26 |  | 2025-08-28 |  | Under Approval | 2025-08-29 | 2025-09-20 | E//John | 2025-09-02 | SQ202508110312-Trintel | DU00002862005 |  |  | 2025-09-19 | 2025-09-10 |  |  | TOWER | 76 | Add R8852E S9000x3+R8894E M1821x6, Dismantle | 0 | 0
W01326 | W066R_W01326OD_LRT_BKTJALIL | Central |  | Decomm |  | 2024 Q3 | ZA | Magicell | 4.6 TSSR Approved |  | 2024-01-23 |  |  |  | 2024-02-21 |  | 2024-03-27 | 2025-03-20 | CD//Norhaliza | 2024-06-05 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240128 | DU00002862006 |  |  |  |  | 2024-08-13 |  | MONOPOLE
W00226 | W066J_W00226OD_LRTDAMAI | Central |  | Decomm |  | 2024 Q1 | SM | YPTT | 4.6 TSSR Approved | ¦ 0312 - CD AliAkram: No RF data detail for pairing site 1208C in ML 20240311 v1 / BAU | 2024-02-14 |  |  |  | 2024-02-16 |  | 2024-02-19 | 2024-10-08 | CD//Ali Akaram | 2024-07-26 | BOQ_Celcom Digi_RAN-YPTT-Standard PR TSS-20240218 | DU00002862007 |  |  |  |  | 2024-10-09 |  | BOOM
B01233 | B064I_B01233OD_SEMENYIH | Central |  | Decomm |  | 2024 Additional | AI | GTSB | 4.6 TSSR Approved |  | 2025-03-17 |  | 2025-03-24 |  | 2025-04-07 |  | 2025-04-17 |  | CD//Ali Akaram | 2025-04-23 | SQ202502180534 | DU00002862008 |  |  |  |  | 2025-04-23 |  | MONOPOLE
W00812 | W066G_W00812OD_DIAMONDSQUARE | Central |  | Decomm |  | 2024 Q1 | MA | GCI | 4.6 TSSR Approved |  | 2023-12-07 |  |  |  | 2023-12-05 |  | 2024-01-11 | 2024-01-22 | CD//Ali Akaram | 2024-01-16 | CelcomDigi_RAN_GCI_TSS_Central_20231214 | DU00002862009 |  |  |  |  | 2024-05-10 |  | MINI MONOPOLE
K00259 | K012A_K00259OD_CB_GULAU | Northern | 4150P | Swap | Swap->On Hold->Swap | 2025 Q3 | HW | GCI | 4.6 TSSR Approved |  | 2025-01-13 | 2025-01-16 |  | 2025-02-27 |  | Under Approval | 2025-03-27 | 2025-05-19 | CD//Zulakmar | 2025-04-08 | SQ202501030328 - GCI | DU00002862010 |  |  | 2025-06-28 | 2025-06-20 |  | Tower | TOWER | 60m | Add R8852E S9000x3+R8854E S1800x3+R8894E M1821x3, Dismantle | 0 | 0
W01468 | W066N_W01468OD_BOMBAYPALACE2 | Central |  | Decomm |  | 2024 Q2 | SHA | GCI | 4.6 TSSR Approved |  | 2024-10-09 |  |  |  | 2024-11-11 |  | 2024-11-13 | 2025-01-14 | CD//Ali Akaram | 2024-11-19 | SQ202502130564 | DU00002862011 |  |  |  |  | 2024-10-10 |  | LAMP_POLE
W01553 | W066U_W01553OD_JLNROBSON_MCOBA | Central |  | Decomm |  | 2024 Q3 | MS | DATASCO | 4.6 TSSR Approved |  | 2024-07-18 |  |  |  | 2024-09-05 |  | 2024-09-06 | 2024-09-25 | CD//Ali Akaram | 2024-09-11 | 0725Central-DATASCO-BOQ Template(new contract) | DU00002862012 |  |  |  |  | 2024-09-21 |  | UNIPOLE
W01543 | W066H_W01543OD_BKTSWANGSA2 | Central |  | Decomm |  | 2024 Q1 | SS | YPTT | 4.6 TSSR Approved |  | 2023-12-05 |  |  |  | 2023-12-05 |  | 2024-01-08 | 2024-02-15 | CD//Norhaliza | 2024-01-30 | CelcomDigi_RAN_YPTT_TSS_Central_202031203 | DU00002862013 |  |  |  |  | 2024-07-16 |  | LAMP_POLE
B02540 | B061Q_B02540OD_LRT_TMNJAYA | Central |  | Decomm | On Hold->Decomm | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-06-21 |  |  |  | 2024-06-24 |  | 2024-06-26 | 2024-07-12 | CD//Ali Akaram | 2024-07-02 | 0701Central-DATASCO-BOQ Template (template) | DU00002862014 |  |  |  |  | 2024-08-06 |  | MINIMAST
W01115 | W066V_W01115OD_KERINCHILINK | Central |  | Decomm |  | 2024 Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-01-26 |  |  |  | 2024-01-29 |  | 2024-02-01 | 2024-11-26 | CD//Norhaliza | 2024-02-15 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240128 | DU00002862015 |  |  |  |  | 2024-08-28 |  | LAMP_POLE
K00882 | K002A_K00882OD_RAPOLE_DWNRIDZWANIAH_BLNG | Northern |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | HW | NR services | 4.6 TSSR Approved |  | 2025-09-25 |  |  |  | 2025-09-25 | To be Submitted | 2025-10-31 |  | E//Hazida | 2025-11-04 | SQ202504260150-NR Services | DU00002862016 |  |  |  |  | 2025-10-31 |  | RAPOLE
S01617 | S094A_S01617OD_KGRANAU | Sabah |  | Decomm |  | 2025 Q3 | HW | GTSB | 4.6 TSSR Approved |  | 2025-01-09 |  | 2025-02-25 |  | 2025-03-13 |  | 2025-03-13 | 2025-09-10 | CD//Sharidah | 2025-03-14 | SQ202501020455 - GTSB / SQ202501070280 - GTSB | DU00002862017 |  |  |  |  | 2025-04-29 |  | TOWER
S00586 | S100A_S00586OD_BSKIMANIS | Sabah |  | Decomm |  | 2025 Q2 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2024-01-11 |  | 2024-07-07 |  | 2024-07-09 |  | 2025-01-09 | 2025-05-02 | CD//Sharidah | 2025-01-09 | Celcom Digi_RAN-Seri Pancar-Standard PR TSS-Sabah-20240116 / SQ202501020446 - Seri Pancar / SQ202501070297 - Seri Pancar | DU00002862018 |  |  |  |  | 2025-06-25 |  | TOWER
Q01384 | Q114A_Q01384OD_KGREBAK | Sarawak |  | Decomm |  | 2024 Q2 | SH | Magicell | 4.6 TSSR Approved |  | 2023-12-20 |  |  |  | 2023-12-21 |  | 2024-01-08 | 2024-01-12 | CD//John | 2024-01-09 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231221/Celcom Digi_RAN-Magicell-Standard PR TSS DECOMM-Sarawak-20231229/CelcomDigi_RAN_Magicell_TSS_Sarawak_20241018 | DU00002862019 |  |  |  |  | 2024-11-30 |  | RAPOLE
A01143 | A040D_A01143OD_DATARAN_KLEDANG5_IPH | Northern |  | Decomm |  | 2024 Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2023-12-07 |  |  |  | 2023-12-08 |  | 2023-12-13 | 2024-01-22 | CD//Affendi | 2023-12-14 | Celcom Digi_RAN-GTSB-TSS-Northern-20231207-0073 | DU00002862020 |  |  |  |  | 2024-03-20 |  | TOWER
S01963 | 098C_S01963OD_RAMOTENGAHNIPAH2 | Sabah |  | Site Out (Decomm) | Decomm->On Hold->Swap->Site Out->Site Out (Decomm) | 2024 Q4(single site MOCN)-L2126 SSM | AD | GTSB | 15.3 Decomm Done without TSSR |  | 2024-11-08 |  |  |  |  | To be Submitted |  |  | CD//Ray Amos |  | 0925CD-Sabah-Seri Pancar-BOQ Template(new contract) | DU00002862021 |  |  |  |  | 2025-04-29 |  | TBC |  | Add R8862A S9000x3+R8894E M1821x3+R8862A S2601x3, Dismantle | 0 | 0
9538A | Ancharang Niah Trunk Road | Sarawak |  | Maintain USP MOCN | MOCN As-Is->On Hold->MOCN As-Is->Maintain USP MOCN | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862022 | [6 empty] | Tower
7075Z | T3_Kg. Sunduron | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862023 | [6 empty] | #N/A
9249Z | KG. LONG LUTENG | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->Site Out->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862024 | [6 empty] | 76M Tower
9250Z | KG. BA MUBOI | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->Site Out->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862025 | [6 empty] | 76M 3 Legged Tower
9251Z | Long Liam | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->Site Out->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862026 | [6 empty] | 45M 3 Legged Tower
9261Z | Pa Umor | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->Site Out->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862027 | [6 empty] | 76M 3 Legged Tower
3560C | Jln Midah 8 | Central |  | Modernization |  | 2024 Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-11-08 | 2023-11-17 |  | 2024-03-21 |  | Closed | 2024-03-21 | 2024-08-27 | E//Sumitra | 2024-08-27 | CelcomDigi_RAN_Allstar_TSS_Central_20231113 | DU00002862028 |  |  | 2024-05-26 | 2024-05-23 |  | Monopole | 18m Lampole | 18 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
1336C | Taman Naga Emas | Central |  | Modernization |  | 2024 Q3 | SS | Ascentrack | 4.6 TSSR Approved |  | 2023-11-08 | 2023-11-09 |  | 2023-11-23 |  | Closed | 2024-03-26 | 2024-04-04 | E//Sumitra | 2024-04-04 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231113 | DU00002862029 | SO reject Dualbay Cabinet Swap |  | 2024-05-14 | 2024-05-09 |  | Lampole | 18m Lampole | 18m | Add R8852E S9000 x3+R8894E M1821 x1+R8854 S2600 x1,Dismantle R8862A S2601(A6A) x1 | 0 | 3
1304C | Jalan Ketumbar | Central |  | Modernization |  | 2024 Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-11-09 | 2023-11-15 |  | 2024-04-03 |  | Closed | 2024-04-03 | 2024-04-15 | E//Sumitra | 2024-04-09 | CelcomDigi_RAN_Allstar_TSS_Central_20231113 | DU00002862030 |  |  | 2024-05-27 | 2024-05-23 |  | Monopole | 18m Lampole | 18 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
1034C | Jalan Medang Tanduk | Central |  | Modernization |  | 2024 Q2 | MA | Ascentrack | 4.6 TSSR Approved | 29/01 RRU install inside cabinet,3 RRU on top, have temperature alarm according to technical team | 2023-11-11 | 2023-11-16 |  | 2024-03-02 |  | Closed | 2024-03-04 | 2024-04-23 | E//Kok Keen | 2024-04-23 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231113 | DU00002862031 |  |  | 2024-03-10 | 2024-03-06 |  | Lampole | 18m Lampole | 18m | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
1040B | Pinggiran Ukay | Central |  | Modernization |  | 2024 Q1 | AI | DATASCO | 4.6 TSSR Approved |  | 2023-11-06 | 2023-11-17 |  | 2024-01-02 |  | Closed | 2024-01-03 | 2024-01-09 | E//Sumitra | 2024-01-09 | CelcomDigi_RAN_Datasco_TSS_Central_20231113 | DU00002862032 |  |  | 2024-05-07 | 2024-05-03 |  | Pole | 5m RT (Wall Mounted Pole) | 6 & 6.5 | Add R8862A S9000 x4,Dismantle
1057B | Jalan Istana | Central |  | Modernization |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-12-28 | 2024-01-04 |  | 2024-03-19 |  | Closed | 2024-03-21 | 2024-03-26 | E//Sumitra | 2024-03-25 | CelcomDigi_RAN_Ascentrak_TSS_Central_20231230 | DU00002862033 |  |  | 2024-06-22 | 2024-06-21 |  | Monople Tree | 24m Monopole | 25m | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 0 | 0
1146B | Cheras Business Center | Central |  | Modernization |  | 2024 Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-11-17 | 2023-12-06 |  | 2024-04-01 |  | Closed | 2024-04-01 | 2024-04-15 | E//Sumitra | 2024-04-09 | CelcomDigi_RAN_AllStar_TSS_Central_20231119 | DU00002862034 |  |  | 2024-11-15 | 2024-06-24 |  |  | 6m RT (Boom) | 2 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3 | 0 | 0
1227A | Bestness Motor | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-17 | 2023-11-20 |  | 2023-11-29 |  | Closed | 2023-11-30 | 2023-11-30 | E//Kok Keen | 2023-11-30 | CelcomDigi_RAN_GTSB_TSS_20231119 | DU00002862035 |  |  | 2024-04-05 | 2024-04-03 |  | Pole | 3m Boom (RT) | 6m | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x2+R8862A S2100(A6A) x3 | 0 | 0
1234B | PJU1 Lamp Pole (KJS) | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-06 | 2023-11-14 |  | 2024-03-30 |  | Closed | 2024-04-02 | 2024-04-04 | E//Kok Keen | 2024-04-04 | CelcomDigi_RAN_GTSB_TSS_Central_20231113 | DU00002862036 |  |  | 2024-05-17 | 2024-05-14 |  | Lampole | 30m Lampole | 30M | Add R9264H M901821 x3,Dismantle R8882 S1800(B) x3 | 0 | 0
1273B | Damai Murni | Central |  | Modernization |  | 2024 Q3 | AI | Magicell | 4.6 TSSR Approved |  | 2023-11-08 | 2023-11-14 |  | 2024-04-03 |  | Closed | 2024-04-15 | 2024-04-16 | E//Sumitra | 2024-04-16 | CelcomDigi_RAN_Magicell_TSS_Central_20231113 | DU00002862037 |  |  | 2024-06-13 | 2024-06-11 |  | In-Building System | 3m Bipod (RT) | 4m | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3++ | 0 | 0
1274B | Tmn Bukit Permai | Central |  | Modernization |  | 2024 Q3 | SS | YPTT | 4.6 TSSR Approved |  | 2023-10-31 | 2023-11-02 |  | 2024-03-21 |  | Closed | 2024-03-25 | 2024-04-01 | E//Sumitra | 2024-04-01 | CelcomDigi_RAN_YPTT_TSS_Central_20231101 | DU00002862038 |  |  | 2024-06-06 | 2024-06-01 |  | Monopole | 30m Monopole | 30 | Add R9264M M1821 x2,Dismantle R8882-GUL1812 x2+R8862A S2100(A6A) x2 | 0 | 0
1307A | Desa Gembira | Central |  | Modernization |  | 2024 Q3 | CR | AllStar | 4.6 TSSR Approved |  | 2023-12-20 | 2023-12-29 |  | 2024-03-29 |  | Closed | 2024-03-30 | 2024-04-02 | E//Sumitra | 2024-04-02 | CelcomDigi_RAN_AllStar_TSS_Central_20231224 | DU00002862039 |  |  | 2024-04-28 | 2024-04-24 |  |  | 3m Bipod (RT) | 6 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x2+R8840-U216 x3++
1310B | Kompleks Puchong Perdana | Central |  | Modernization | Modernization->Remote MOCN->Modernization | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-04 | 2024-01-09 |  | 2024-04-22 |  | Closed | 2024-10-22 | 2024-12-05 | E//Razif | 2024-12-05 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240108 | DU00002862040 |  |  | 2025-06-24 | 2025-06-24 |  | In-Building System | 3m Bipod (RT) | 6m | Add R8862A S2601x3, Dismantle R8882-L268x3 | 0 | 0
1390A | Paramount Garden | Central |  | Modernization |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-11-23 | 2023-12-01 |  | 2024-04-04 |  | Rectificating | 2024-04-16 | 2024-05-27 | E//Kok Keen | 2024-05-27 | CelcomDigi_RAN_Datasco_TSS_Central_20231126 | DU00002862041 |  |  | 2024-04-13 | 2024-04-02 |  | Pole | 6m RT (Boom) | 9m BH + 6m POLE = (600inch = 15m) | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3++ | 0 | 0
1404A | Bdr Bukit Puchong | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-05 | 2024-01-08 |  | 2024-04-19 |  | Closed | 2024-05-03 | 2024-05-07 | E//Razif | 2024-05-06 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240108 | DU00002862042 |  |  | 2024-06-23 | 2024-06-23 |  | In-Building System | 3m Bipod (RT) | 6m | Add R8894E M1821 x3,Dismantle R8882-GUL1812 x4+R8840-U216 x3++ | 0 | 0
1441A | Tmn Nirwana | Central |  | Modernization |  | 2024 Q2 | SS | YPTT | 4.6 TSSR Approved |  | 2023-10-26 | 2023-11-02 |  | 2024-01-09 |  | Closed | 2024-01-10 | 2024-01-17 | E//Sumitra | 2024-01-16 | CelcomDigi_RAN_YPTT_TSS_Central_20231028 | DU00002862043 |  |  | 2024-05-03 | 2024-04-30 |  | In-Building System | 3m Bipod (RT) | 4m & 6m | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3
1447A | Kg Tasik permai | Central |  | Modernization |  | 2024 Q4 | BY | AllStar | 4.6 TSSR Approved |  | 2023-12-08 | 2024-02-20 |  | 2024-05-09 |  | Closed | 2024-05-16 | 2024-05-27 | E//Sumitra | 2024-05-24 | CelcomDigi_RAN_AllStar_TSS_Central_20231224 | DU00002862044 |  |  | 2024-06-12 | 2024-06-06 |  |  | 3m Bipod (RT) | 6 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3 | 0 | 0
1472A | Kg Pandan KL | Central |  | Modernization |  | 2024 Q2 | YZ | GTSB | 4.6 TSSR Approved |  | 2023-11-23 | 2023-11-27 |  | 2024-01-18 |  | Closed | 2024-01-19 | 2024-01-23 | E//Sumitra | 2024-01-23 | CelcomDigi_RAN_GTSB_TSS_Central_20231126 | DU00002862045 |  |  | 2024-05-09 | 2024-05-06 |  | Minimast | 3m Boom (RT) | 12m | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8840-U216 x3++
1560BF | pBTS Taman Harmoni Kajang | Central |  | Modernization | Modernization->On Hold->Modernization | 2024 Additional | AI | YPTT | 4.6 TSSR Approved |  | 2025-01-24 | 2025-02-18 |  | 2025-02-21 |  | Closed | 2025-02-22 | 2025-03-04 | E//Sumitra | 2025-03-04 | SQ202506110242 | DU00002862046 | Remarks: Solution TSSR/BOM Changed |  | 2025-03-19 | 2025-03-13 |  | Watertank | 25m pBTS | 30m | Add R8894E M1821x3, Dismantle R8882-GUL1812x3+R8862A S2100(A6A)x3 | 0 | 0
1747A | Jln Besar Ampang | Central |  | Modernization |  | 2024 Q2 | SS | YPTT | 4.6 TSSR Approved |  | 2023-11-05 | 2023-11-09 |  | 2024-03-07 |  | Under Approval | 2024-03-11 | 2024-07-10 | E//Sumitra | 2024-07-10 | CelcomDigi_RAN_YPTT_TSS_Central_20231112 | DU00002862047 |  |  | 2024-04-19 | 2024-04-16 |  | In-Building System | 3m Bipod (RT) | 3 | Add R8894E M1821 x4,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3 | 0 | 1
1774A | Sri Jaya Bakti | Central |  | Modernization |  | 2024 Q3 | SH | DATASCO | 4.6 TSSR Approved |  | 2023-11-12 | 2023-11-20 |  | 2024-04-26 |  | Closed | 2024-05-13 | 2024-05-21 | E//Sumitra | 2024-05-21 | CelcomDigi_RAN_Datasco_TSS_Central_20231214 | DU00002862048 |  |  | 2024-06-21 | 2024-06-21 |  | Wall mount boom | 3m Boom (RT) | 6m | Add R8894E M1821 x2,Dismantle R8882-GUL1812 x2+R8840-U216 x1+R8840-U216 x1++ | 0 | 0
1812A | Cascadium | Central |  | Modernization |  | 2024 Q2 | MA | GTSB | 4.6 TSSR Approved |  | 2024-05-03 | 2024-05-06 |  | 2024-05-09 |  | Closed | 2024-05-13 | 2024-05-14 | E//Kok Keen | 2024-05-14 | CelcomDigi_RAN_GTSB_TSS_Central_20240513 | DU00002862049 |  |  | 2024-06-10 | 2024-06-08 |  | Wall mount boom | 3m Boom (RT) | 2.5 | Add R9264M M1821 x2+R8862A S2601 x1,Dismantle R8882-GUL1812 x1+R8882 S1800(B) x1+R8840-U216 x1+R8881 S2100 x1+ | 0 | 0
1822B | Mardi(ZED) | Central |  | Modernization |  | 2024 Q3 | SHA | YPTT | 4.6 TSSR Approved |  | 2024-05-09 | 2024-05-10 |  | 2024-05-15 |  | Closed | 2024-05-20 | 2024-05-27 | E//Sumitra | 2024-05-27 | CelcomDigi_RAN_YPTT_TSS_Central_20240513 | DU00002862050 |  |  | 2024-06-24 | 2024-06-22 |  | Tower | 60m 3 Legged Tower | 48 | Add R8862A S9000 x3,Dismantle | 0 | 0
1859B | Ukay Blvd REL | Central |  | Modernization |  | 2024 Q1 | SS | YPTT | 4.6 TSSR Approved | 02/01 - CD Nik agreed to maintain existing antenna drop 900 ¦ 31/1: pylon site, site owner not allow to swap atenna due tu space limitation | 2023-12-08 | 2023-12-27 |  | 2024-01-03 |  | Closed | 2024-03-26 | 2024-04-04 | E//Sumitra | 2024-04-03 | CelcomDigi_RAN_YPTT_TSS_Central_20231224 | DU00002862051 |  |  | 2024-07-13 | 2024-07-10 |  | Petronas Pylon | Tower | 30 | Add R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8840 U216 x3
1997A | Taman Rasmi Jaya 2 | Central |  | Modernization |  | 2024 Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-12-21 | 2023-12-26 |  | 2024-05-07 |  | Closed | 2024-05-09 | 2024-05-15 | E//Sumitra | 2024-05-15 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231224 | DU00002862052 |  |  | 2024-07-17 | 2024-07-16 |  | Pole | 3m Boom (RT) | 3.5m/4m | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3++ | 0 | 0
2014B | Bandar Kinrara 5 | Central |  | Modernization |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-11-17 | 2023-11-27 |  | 2024-04-26 |  | Closed | 2024-05-16 | 2024-05-24 | E//Sumitra | 2024-05-23 | CelcomDigi_RAN_Datasco_TSS_Central_20231214 | DU00002862053 |  |  | 2024-06-22 | 2024-06-18 |  | In-Building System | 6m RT (Boom) | 4 | Reuse exisiting RRU | 0 | 0
2019A | LDPSS21 | Central |  | Modernization |  | 2024 Q3 | MA | GCI | 4.6 TSSR Approved |  | 2023-10-25 | 2023-10-31 |  | 2024-04-15 |  | Closed | 2024-04-15 | 2024-04-16 | E//Kok Keen | 2024-04-16 | CelcomDigi_RAN_GCI_TSS_Central_20231028 | DU00002862054 |  |  | 2024-05-17 | 2024-05-14 |  | Monopole | 45m Monopole | 26 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3++ | 0 | 0
2033A | South MRR2 | Central |  | Modernization |  | 2024 Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-11-16 | 2023-12-06 |  | 2024-04-04 |  | Closed | 2024-04-04 | 2024-04-16 | E//Sumitra | 2024-04-16 | CelcomDigi_RAN_AllStar_TSS_Central_20231119 | DU00002862055 |  |  | 2024-05-03 | 2024-05-03 |  | In-Building System | 3m Bipod (RT) | 4 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3++ | 0 | 0
2152A | SS22 (REL) | Central |  | Modernization |  | 2024 Q3 | MA | GTSB | 4.6 TSSR Approved |  | 2023-10-27 | 2023-11-01 |  | 2024-03-22 |  | Closed | 2024-03-25 | 2024-03-26 | E//Kok Keen | 2024-03-26 | CelcomDigi_RAN_GTSB_TSS_Central_20231028 | DU00002862056 |  |  | 2024-05-03 | 2024-04-27 |  | H-bracket pole | 6m RT (Boom) | 6m | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3++ | 0 | 0
2209A | Jln Kg Pandan | Central |  | Modernization |  | 2024 Q2 | YZ | GTSB | 4.6 TSSR Approved |  | 2023-12-13 | 2023-12-19 |  | 2024-01-16 |  | Closed | 2024-01-18 | 2024-01-29 | E//Sumitra | 2024-01-24 | CelcomDigi_RAN_GTSB_TSS_Central_20231214 | DU00002862057 |  |  | 2024-03-18 | 2024-03-08 |  | Unipole | 3m Bipod (RT) | 6 | Add R9264M M1821 x3,Dismantle R8882 S1800(B) x3+R8862A S2100(A6A) x3
2239A | Jln Amanputra 3 | Central |  | Modernization |  | 2024 Q3 | SH | Magicell | 4.6 TSSR Approved |  | 2023-11-07 | 2024-01-10 |  | 2024-04-22 |  | Closed | 2024-04-25 | 2024-06-14 | E//Hannah | 2024-06-13 | CelcomDigi_RAN_Magicell_TSS_Central_20231214 | DU00002862058 |  |  | 2024-05-15 | 2024-05-09 |  | Monople Tree | 30m Monopole | 31 | Add R8894E M1821 x4,Dismantle R8882 S1800(B) x3+R8862A S1800(B6A) x1+R8862A S2100(A6A) x4 | 0 | 0
2250A | Jln Kuari Cheras | Central |  | Modernization |  | 2024 Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-11-04 | 2023-11-09 |  | 2024-03-25 |  | Closed | 2024-03-26 | 2024-04-02 | E//Sumitra | 2024-04-02 | CelcomDigi_RAN_Allstar_TSS_Central_20231113 | DU00002862059 |  |  | 2024-06-23 | 2024-06-23 |  |  | 3m Bipod (RT) | 10 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3 | 0 | 0
2313A | Jln Melawa | Central |  | Modernization |  | 2024 Q1 | CR | GCI | 4.6 TSSR Approved |  | 2023-11-22 | 2023-11-27 |  | 2024-01-18 |  | Closed | 2024-01-22 | 2024-01-29 | E//Sumitra | 2024-01-24 | CelcomDigi_RAN_GCI_TSS_Central_20231126 | DU00002862060 |  |  | 2024-05-08 | 2024-05-04 |  | In-Building System | 6m Unipole RT | 5 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882 S1800(B) x3
2318A | Jln Bunga Raya | Central |  | Modernization |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-15 | 2023-12-26 |  | 2023-12-29 |  | Closed | 2024-06-01 | 2024-06-04 | E//Sumitra | 2024-06-04 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231116 | DU00002862061 |  |  | 2024-06-15 | 2024-06-12 |  | In-Building System | 3m Boom (RT) | 5 | Add R9224E M1821 x4,Dismantle R8882 S1800(B) x1+R8882 S1800B(B6B) x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x4 | 0 | 2
2329A | Balakong Jaya 2 | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-10-20 | 2023-10-26 |  | 2024-04-25 |  | Closed | 2024-04-26 | 2024-04-30 | E//Sumitra | 2024-04-30 | CelcomDigi_RAN_GTSB_TSS_Central_20231021 | DU00002862062 |  |  | 2024-05-10 | 2024-05-08 |  | Unipole | 6m RT (Boom) | 6m | Add R8862A S9000 x3+R8894E M1821 x2+R8854 S2600 x2,Dismantle R8862A S2600(A4A) x2 | 0 | 12
1241B | Hap Seng | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-17 | 2023-11-20 |  | 2023-12-26 |  | Closed | 2024-04-01 | 2024-04-03 | E//Kok Keen | 2024-04-03 | CelcomDigi_RAN_GTSB_TSS_20231119 | DU00002862063 |  |  | 2024-05-07 | 2024-05-07 |  | H-bracket pole | 6m RT (Boom) | 4m | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3
2395A | Jln SS 2_4a | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-02 | 2023-11-14 |  | 2024-04-15 |  | Closed | 2024-04-15 | 2024-04-16 | E//Kok Keen | 2024-04-16 | CelcomDigi_RAN_GTSB_TSS_Central_20231104 | DU00002862064 |  |  | 2024-05-20 | 2024-05-13 |  | Unipole | 6m Unipole RT | 8 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3 | 0 | 0
2634A | North MRR II 2 | Central |  | Modernization |  | 2024 Q1 | CR | GTSB | 4.6 TSSR Approved |  | 2023-11-07 | 2023-11-10 |  | 2024-01-08 |  | Closed | 2024-01-09 | 2024-01-11 | E//Kok Keen | 2024-01-10 | CelcomDigi_RAN_GTSB_TSS_Central_20231113 | DU00002862065 |  |  | 2024-03-16 | 2024-03-08 |  | BillBoard | Billboard | 25m | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3
2635A | Peninsular Residences | Central |  | Modernization |  | 2024 Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-01-29 | 2024-02-08 |  | 2024-02-24 |  | Closed | 2024-02-26 | 2024-02-27 | E//Kok Keen | 2024-02-27 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240202 | DU00002862066 |  |  | 2024-06-13 | 2024-06-08 |  | Wall mount boom | 6m RT (Boom) + IBS | 2m | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x1++
2704B | Taman Desa Air Hitam | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-17 | 2024-01-30 |  | 2024-04-25 |  | Closed | 2024-05-13 | 2024-05-14 | E//Razif | 2024-05-14 | CelcomDigi_RAN_GTSB_TSS_Central_20240124 | DU00002862067 |  |  | 2024-06-24 | 2024-06-21 |  | Lampole | 24m Lampole | 24m | Add R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882 S1800(B) x3+R8882 S2600(B4A) x1++R8881 S2100 x3+ | 0 | 3
2709B | TMN BUKIT SERDANG | Central |  | Modernization |  | 2024 Q3 | CR | GCI | 4.6 TSSR Approved |  | 2023-10-19 | 2023-10-27 |  | 2024-04-22 |  | Closed | 2024-04-27 | 2024-04-30 | E//Sumitra | 2024-04-30 | CelcomDigi_RAN_GCI_TSS_Central_20231020 | DU00002862068 |  |  | 2024-06-21 | 2024-06-19 |  | H-bracket pole | 3m Bipod (RT) | 3 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882-GUL1812 x2+R8882 S1800B(B6B) x1+R8840-U216 x3++ | 0 | 0
2713B | Jln Sg Long 7_5 | Central |  | Modernization |  | 2024 Q4 | AI | YPTT | 4.6 TSSR Approved |  | 2024-05-05 | 2024-05-20 |  | 2024-05-29 |  | Closed | 2024-05-29 | 2024-06-06 | E//Sumitra | 2024-06-06 | CelcomDigi_RAN_YPTT_TSS_Central_20240513 | DU00002862069 |  |  | 2024-07-17 | 2024-07-17 |  | Lampole | 30m Monopole | 30 | Add R9264H M901821 x3,Dismantle R8882 S1800(B) x3++R8881 S2100 x3+ | 0 | 0
2733B | Tmn Bkt Angsana Cheras | Central |  | Modernization |  | 2024 Q4 | BY | GCI | 4.6 TSSR Approved |  | 2024-01-04 | 2024-03-04 |  | 2024-05-22 |  | Closed | 2024-05-24 | 2024-06-07 | E//Sumitra | 2024-06-07 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240108 | DU00002862070 |  |  | 2024-07-17 | 2024-07-16 |  | In-Building System | 30m Monopole | 6 | Add R8852E S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8862A S2100(A6A) x4+R8862A S2600(A4A) x1+R8862A S2601(A6A) x1 | 0 | 3
2759A | Kolej TAR Hostel | Central |  | Site Out (Modernization) | Modernization->Site Out->Replacement, Site Out (Modernization) | 2024 Q1 | MA | GTSB | 15.3 Decomm Done without TSSR |  | 2025-07-15 |  |  |  |  | To be Submitted |  |  |  |  | SQ202506170074 | DU00002862071 |  |  |  |  | 2025-08-05 |  | 3m Bipod (RT)
2762B | Jalan Padang Tembak | Central |  | Modernization |  | 2024 Q1 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-12-12 | 2023-12-19 |  | 2024-01-04 |  | Closed | 2024-01-04 | 2024-01-09 | E//Sumitra | 2024-01-09 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231213 | DU00002862072 |  |  | 2024-05-02 | 2024-04-30 |  |  | 18m Lampole | 18 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
7349A | USP Kg.Garas | Sabah |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q4 | AD | NR services | 2.1 Pending ETSS Submission - Subcon |  | 2025-09-04 |  |  |  |  | To be Submitted |  |  |  |  | SQ202501020451 - NR Service | DU00002862073 | [6 empty] | 60m 4 Legged Tower |  | Reuse Existing RRU
2981A | Stadium Putra Bukit Jalil | Central |  | Modernization |  | 2024 Q3 | CR | Magicell | 4.6 TSSR Approved |  | 2024-01-02 | 2024-01-04 |  | 2024-03-21 |  | Closed | 2024-03-25 | 2024-03-26 | E//Sumitra | 2024-03-26 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240108 | DU00002862074 |  |  | 2024-05-16 | 2024-05-09 |  | Monopole | 24m monopole | 20M | Add R8894E M1821 x4,Dismantle R8882-GUL1812 x2+R8882 S1800B(B6B) x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x5+R8882 S2600(B4A) x1 | 0 | 3
3016A | Jln Seri Cheras 8 | Central |  | Modernization |  | 2024 Q4 | SM | GCI | 4.6 TSSR Approved |  | 2023-11-10 | 2023-11-03 |  | 2024-05-22 |  | Rectificating | 2024-05-23 | 2024-06-06 | E//Sumitra | 2024-06-06 | CelcomDigi_RAN_GCI_TSS_Central_20231214 | DU00002862075 |  |  | 2024-07-19 | 2024-07-16 |  | In-Building System | 3m Boom (RT) | 6 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
3017A | BT 9 TMN CHERAS PERDANA RIA | Central |  | Modernization |  | 2024 Q4 | BY | Solusi | 4.6 TSSR Approved |  | 2024-01-10 | 2024-01-15 |  | 2024-05-27 |  | Closed | 2024-05-31 | 2024-06-12 |  | 2024-06-11 | BOQ CelcomDigi_RAN_Solusi_Standard PR TSS_Central_20240117 | DU00002862076 |  |  | 2024-07-17 | 2024-07-17 |  | Minimast | 3m Boom (RT) | 6.6 | Add R9264M M1821 x4,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8862A S2100(A6A) x4 | 0 | 0
3028A | Jln Utama 2_26 | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-13 | 2024-01-15 |  | 2024-04-20 |  | Closed | 2024-04-23 | 2024-04-25 | E//Razif | 2024-04-25 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240115 | DU00002862077 |  |  | 2024-06-24 | 2024-06-24 |  | Pole | 3m Bipod (RT) | 5m | Add R8894E M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8840-U216 x3++ | 0 | 0
3064A | Jln Gasing (REL) | Central |  | Modernization |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-01-05 | 2024-01-24 |  | 2024-03-27 |  | Closed | 2024-04-01 | 2024-04-02 | E//Kok Keen | 2024-04-01 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240108 | DU00002862078 |  |  | 2024-05-17 | 2024-05-14 |  | Lampole | 25m pBTS | 26 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8840-U216 x3++ | 0 | 0
3212A | Pangsapuri Harmonis | Central |  | Modernization |  | 2024 Q1 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-06 | 2023-11-10 |  | 2024-01-03 |  | Closed | 2024-01-03 | 2024-01-03 | E//Kok Keen | 2024-01-03 | CelcomDigi_RAN_GTSB_TSS_Central_20231113 | DU00002862079 |  |  | 2024-01-15 | 2024-01-11 |  | H-bracket pole | 3m Boom (RT) | 6m | Add R8862A S9000 x3,Dismantle
3224A | Jalan Awan | Central |  | Modernization |  | 2024 Q1 | CR | GCI | 4.6 TSSR Approved |  | 2023-11-09 | 2023-11-14 |  | 2024-01-02 |  | Closed | 2024-01-03 | 2024-01-09 | E//Sumitra | 2024-01-09 | CelcomDigi_RAN_GCI_TSS_Central_20231113 | DU00002862080 |  |  | 2024-01-14 | 2024-01-11 |  | In-Building System | 3m Bipod (RT) | 7 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
2716B | KAMPUNG BARU SALAK SELATAN | Central |  | Modernization |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-15 | 2023-11-29 |  | 2024-03-22 |  | Closed | 2024-03-22 | 2024-03-26 | E//Sumitra | 2024-03-26 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231116 | DU00002862081 |  |  | 2024-05-13 | 2024-05-09 |  | Lampole | 30m Lampole | 30 | Add R8852E S9000 x3+R8894E M1821 x1+R8854 S2600 x1,Dismantle R8862A S2600(A4A) x1 | 0 | 3
3231A | KOLAM AIR LAMA | Central |  | Modernization |  | 2024 Q4 | SHA | Ascentrack | 4.6 TSSR Approved |  | 2023-12-21 | 2023-12-26 |  | 2024-05-17 |  | Closed | 2024-05-23 | 2024-05-30 | E//Sumitra | 2024-05-30 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231224 | DU00002862082 |  |  | 2024-07-18 | 2024-07-16 |  | In-Building System | 3m Bipod (RT) | 5M | Add R9264H M901821 x3,Dismantle R8882 S1800(B) x3++R8881 S2100 x3+ | 0 | 0
3233A | Jln 6_14 | Central |  | Modernization |  | 2024 Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2023-12-08 | 2024-02-16 |  | 2024-05-08 |  | Closed | 2024-05-10 | 2024-05-16 | E//Sumitra | 2024-05-15 | CelcomDigi_RAN_Allstar_TSS_Central_20231208 | DU00002862083 |  |  | 2024-07-18 | 2024-07-18 |  | Unipole | 3m Bipod (RT) | 10 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
3292A2 | pBTS Taman Kajang Impian (M) | Central |  | Modernization | Modernization->On Hold->Modernization | 2024 Q4 | AI | DATASCO | 4.6 TSSR Approved |  | 2023-11-11 | 2023-11-15 |  | 2025-01-13 |  | Closed | 2025-01-16 | 2025-04-29 | E//Sumitra | 2025-04-28 | CelcomDigi_RAN_Datasco_TSS_Central_20231214 | DU00002862084 | Remarks: Solution TSSR/BOM Changed |  | 2025-02-20 | 2025-02-20 |  | Watertank | 25m pBTS | 31 | Reuse Existing RRU | 0 | 0
4893B | MH Unilodge RT | Northern |  | Modernization |  | 2024 Additional | SM | GTSB | 4.6 TSSR Approved |  | 2025-01-03 | 2025-01-14 |  | 2025-01-20 |  | Rectificating | 2025-01-21 | 2025-02-19 | E//Hazida | 2025-02-19 | 1911CD-Northern-TSS-BOQ Template(new contract)_GTSB | DU00002862085 |  |  | 2025-02-13 | 2025-02-05 |  | Unipole | 3m Boom (RT) | 9m | Add R8894E M1821x3, Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3 | 0 | 0
4410B | NS KM369 NB(ZED) | Northern |  | Modernization |  | 2024 Additional |  | CCSMY | 4.6 TSSR Approved |  | 2024-12-11 | 2024-12-16 |  | 2024-12-18 |  | Closed | 2024-12-20 | 2024-12-24 |  | 2024-12-23 | 1911CD-Northern-TSS-BOQ Template(new contract)_CCSMY_V2 | DU00002862086 |  |  | 2025-01-31 | 2025-01-09 |  | Tower | 45m 4 Legged Tower | 60m | Reuse existing RRU | 0 | 0
4444B | Pekan Getah Tapah | Northern |  | Modernization |  | 2024 Additional |  | GTSB | 4.6 TSSR Approved |  | 2023-11-21 | 2023-12-12 |  | 2023-12-14 |  | Closed | 2023-12-15 | 2023-12-20 |  | 2023-12-17 | Celcom Digi_RAN-GTSB-TSS-Northern-20231122-0067 | DU00002862087 |  |  | 2024-12-10 | 2024-11-22 |  | Tower | 60m 3 Legged Tower | 60 | Add R8894E M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3 | 0 | 0
4509B | Rasi Jaya | Northern |  | Modernization |  | 2024 Q2 | HQ 1 | GTSB | 4.6 TSSR Approved |  | 2023-10-10 | 2023-10-12 |  | 2024-01-08 |  | Closed | 2024-01-10 | 2024-01-12 | E//Hazida | 2024-01-12 | Celcom Digi_RAN-GTSB-TSS-Northern-20231011-0046 | DU00002862088 |  |  | 2024-01-19 | 2024-01-15 |  | In-Building System | 3m RT (Minimast) | 15 | Add R8894E M1821 x5+R8854 S2600 x2,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8854D S2100(A4A) x4+R8882 S2600(B4A) x2 |  | 23
4533A | Tmn Pengkalan | Northern |  | Modernization |  | 2024 Q2 |  | GTSB | 4.6 TSSR Approved |  | 2023-10-19 | 2023-10-25 |  | 2024-01-11 |  | Closed | 2024-01-13 | 2024-01-18 | E//Hazida | 2024-01-17 | Celcom Digi_RAN-GTSB-TSS-Northern-20231020-0053 | DU00002862089 |  |  | 2024-02-04 | 2024-01-26 |  | In-Building System | 3m Tripod (RT) | 6 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3
4537B | Medan Pasir Ria | Northern |  | Modernization |  | 2024 Q2 | BY | YPTT | 4.6 TSSR Approved |  | 2023-12-05 | 2023-11-06 |  | 2024-01-08 |  | Closed | 2024-01-10 | 2024-01-12 | E//Ajay | 2024-01-11 | Celcom Digi_RAN-YPTT-TSS-Northern-20231030-0041 | DU00002862090 |  |  | 2024-01-28 | 2024-01-28 |  | In-Building System | 60m 4 Legged Tower | 3 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3
4603A | Hock Moh Leong | Northern |  | Modernization |  | 2024 Q4 | SM | GTSB | 4.6 TSSR Approved |  | 2023-10-17 | 2023-11-16 |  | 2024-04-18 |  | Rectificating | 2024-04-23 | 2024-04-24 | E//Ajay | 2024-04-24 | Celcom Digi_RAN-GTSB-TSS-Northern-20231018-0051 | DU00002862091 |  |  | 2024-05-17 | 2024-05-11 |  | In-Building System | 60m 4 Legged Tower | 3 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8840 U216 x3 | 0 | 0
2109B | Jln SS2_35 | Central |  | Site Out (Modernization) | Modernization->Site Out->Replacement, Site Out (Modernization) | 2024 Q3 | CR | GCI | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2025-07-04 | 2025-07-14 |  |  |  | To be Submitted |  |  |  |  | SQ202506140192 | DU00002862092 |  |  |  |  | 2025-08-05 |  | 3m Bipod (RT) |  |  | 0 | 0
2682A1 | pBTS Tmn Wawasan | Central |  | Modernization | Modernization->On Hold->Modernization | 2024 Q3 | AI | Magicell | 14.0 TSSR Not Required (Reuse Existing BBU/RRU) |  | 2023-11-24 | 2023-12-28 |  |  |  | To be Submitted |  |  |  |  | CelcomDigi_RAN_Magicell_TSS_Central_20231214 | DU00002862093 |  |  | 2025-06-27 | 2025-02-15 |  | Watertank | 25m pBTS | 25M | Reuse Existing RRU | 0 | 0
4731A | Trolak (Trunk) | Northern |  | Modernization |  | 2024 Additional | BY | Magicell | 4.6 TSSR Approved |  | 2023-11-15 | 2023-11-24 |  | 2023-11-30 |  | Closed | 2023-12-05 | 2023-12-12 | E//Ajay | 2023-12-08 | Celcom Digi_RAN-Magicell-TSS-Northern-20231122-0004 | DU00002862094 |  |  | 2024-11-26 | 2024-11-26 |  | Tower | 60m 4 Legged Tower | 75 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8860E-GU908 x2+R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8840-U216 x3 | 0 | 0
4878B | Bukit Chabang (REL) | Northern |  | Modernization |  | 2025 Q3 | AD | CCSMY | 4.6 TSSR Approved |  | 2023-11-03 | 2023-11-07 |  | 2025-02-18 |  | Under Approval | 2025-03-12 | 2025-05-27 | E//Hazida | 2025-03-13 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231106-0068 | DU00002862095 |  |  | 2025-04-11 | 2025-04-11 |  | Tower | Tower | 61m | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8882-GUL1812x2+R8862A S1800(B6A)x1+R8854D S2100(A4A)x3 | 0 | 0
7369B | USP Kg.UluTaburi | Sabah |  | Modernization |  | 2024 Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-10-26 | 2023-11-08 |  | 2024-07-18 |  | Under Approval | 2024-07-19 | 2024-09-20 | E//Hannah | 2024-09-06 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231028 | DU00002862096 |  |  | 2024-10-28 | 2024-10-09 |  | Tower | 45m 4 Legged Tower | 45M | Reuse exsiting RRU | 0 | 0
7459B | Kg. Telupid SBC | Sabah |  | Modernization |  | 2024 Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2024-04-08 | 2024-04-20 |  | 2024-05-09 |  | Closed | 2024-05-10 | 2024-05-17 | E//Hannah | 2024-05-16 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240420 | DU00002862097 |  |  | 2024-06-22 | 2024-06-15 |  | Tower | Tower | 60m | Reuse exsiting RRU | 0 | 0
7453B | Tmn BDC | Sabah |  | Site Out (Modernization) | Modernization->Site out->Site Out (Modernization) | 2024 Q3 | MS | Datasco | [SiteOut]- 2.1 Pending ETSS Submission - Subcon |  | 2024-05-20 |  |  |  |  | To be Submitted |  |  |  |  | Celcom Digi_RAN-Datasco-Standard PR TSS-Sabah-20240521 | DU00002862098 | [6 empty] | 24m Lampole |  | Add R8862A S9000 x3+R9264H M901821 x1+A9732 M1821 x3,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x5 | 234 | 0
1144C | Sri Petaling | Central |  | Modernization |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-12-11 | 2023-12-14 |  | 2024-03-20 |  | Closed | 2024-03-21 | 2024-03-26 | E//Sumitra | 2024-03-26 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231213 | DU00002862099 |  |  | 2024-05-30 | 2024-05-28 |  | Lampole | 18m Lampole | 18 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
7526A | Kg Mandahan Kimanis | Sabah |  | Modernization |  | 2025 Q2 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2023-11-14 | 2023-11-20 |  | 2025-01-22 |  | Under Approval | 2025-02-20 | 2025-03-09 | E//Hannah | 2025-02-24 | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231221 | DU00002862100 |  |  | 2025-04-27 | 2025-03-05 |  | Tower | Tower | 64 | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8882-GUL1812x3+R8862A S2100(A6A)x3 | 0 | 0
3414B | Bukit Angkat 1 | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-03 | 2024-01-11 |  | 2024-04-22 |  | Closed | 2024-04-25 | 2024-04-30 | E//Sumitra | 2024-04-30 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240108 | DU00002862101 |  |  | 2024-05-13 | 2024-05-08 |  | In-Building System | 3m Bipod (RT) | 4m | Add R8894E M1821 x6+R8854 S2600 x2,Dismantle R8882 S1800(B) x3+R8862A S1800(B6A) x1+R8854D S2100(A4A) x4+R8862A S2600(A4A) x1+R8862A S2601(A6A) x1 | 0 | 13
3294A2 | pBTS Kaw Perindustrian Beranang (REL) | Central |  | Remote MOCN | Modernization->On Hold->Remote MOCN | 2024 Additional |  | DATASCO | 14.2 Drop (Done Survey) |  | 2023-12-13 | 2023-12-19 |  |  |  | To be Submitted |  |  |  |  | CelcomDigi_RAN_Datasco_TSS_Central_20231224 | DU00002862102 | [5 empty] | Watertank | 25m pBTS | 30 | Reuse Existing RRU | 0 | 23
4163C | Kg Ewa | Northern |  | Modernization |  | 2024 Additional | AD | GTSB | 4.6 TSSR Approved |  | 2024-12-02 | 2024-12-04 |  | 2024-12-06 |  | Under Approval | 2024-12-06 | 2024-12-19 | E//Hazida | 2024-12-18 | SQ202411290524 - GTSB | DU00002862103 |  |  | 2024-12-27 | 2024-12-12 |  | Monopole | Tower | 45m | Add R8894E M1821x1 | 0 | 2
3290A | PUDU_HULU1 | Central |  | Site Out (Modernization) | Modernization->Site Out->Replacement, Site Out (Modernization) | 2024 Q3 | MA | GTSB | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2025-07-15 |  | 2025-07-03 |  |  | To be Submitted |  |  |  |  | SQ202506170074 | DU00002862104 | [6 empty] | 3m Boom (RT) |  |  | 0 | 0
9303A | 10th Mile Bazaar | Sarawak |  | Modernization |  | 2025 Q2 | SH | Magicell | 4.6 TSSR Approved |  | 2023-10-11 | 2023-10-18 |  | 2023-10-23 |  | Closed | 2023-10-24 | 2023-11-15 | E//Hannah | 2025-03-05 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231013 | DU00002862105 | Remarks: Solution TSSR/BOM Changed | Remarks: Solution Changed | 2025-03-21 | 2025-03-12 |  | Tower | 45m 4 Legged Tower | 46M | Add R8852E S9000 x3+R9264M M1821 x3, Dismantle R8860E-GU908x1+R8882-GUL1812x1+R8862A S1800(B6A)x2+R8862A S2100(A6A)x3+R8862A S2600(A4A)x1 | 0 | 0
2254A | Desa Pahlawan Ampang | Central |  | Modernization |  | 2024 Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-03 | 2024-01-05 |  | 2024-01-18 |  | Closed | 2024-01-24 | 2024-01-31 | E//Sumitra | 2024-01-30 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240108 | DU00002862106 |  |  | 2024-05-10 | 2024-05-08 |  | Lampole | 24m Lampole | 20m | Add R9264H M901821 x3,Dismantle R8892E M1821(BAA) x3
3009A | Madrasah Al-Ihsaniah Ampang LP | Central |  | Modernization |  | 2024 Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-28 | 2023-11-30 |  | 2024-05-13 |  | Closed | 2024-05-14 | 2024-05-21 | E//Sumitra | 2024-05-21 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231201 | DU00002862107 |  |  | 2024-05-20 | 2024-05-18 |  | Lampole | 24m Lampole | 25 | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 2 | 0
K00221 | K012A_K00221OD_BATU5SIK | Northern |  | Decomm | Decomm->On Hold->Decomm | 2024 Q3(single site MOCN) | AI | GCI | 4.6 TSSR Approved |  | 2025-06-20 |  | 2025-07-29 |  | 2025-07-24 | To be Submitted | 2026-02-16 |  | CD//Zulakmar | 2026-02-19 | SQ202502100379 | DU00002862108 |  |  |  |  | 2025-06-23 |  | TOWER
K00413 | K009A_K00413OD_CB_KGPERIK | Northern |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2024 Q4 | HW | GCI | 4.6 TSSR Approved |  | 2025-08-14 |  | 2025-08-26 |  | 2025-10-02 |  | 2025-10-03 | 2026-01-22 | E//Hazida | 2025-10-05 | SQ202504230429-GCI | DU00002862109 |  |  |  |  | 2025-10-27 |  | TOWER
2247A | Jalan Prima Selayang 7 | Central |  | Site Out (Modernization) | Modernization->Site Out->Replacement, Site Out (Modernization) | 2024 Q4 | AI | YPTT | 4.6 TSSR Approved |  | 2024-01-22 | 2024-02-16 |  | 2024-06-06 |  | Under Approval | 2024-06-06 | 2024-06-13 | E//Kok Keen | 2024-06-13 | BOQ_Celcom Digi_RAN-YPTT-Standard PR TSS-20240202 | DU00002862110 | [5 empty] | Lampole | 20m Monopole | 20
4063C | Buntong Jaya | Northern |  | Modernization |  | 2024 Q2 | WP | GTSB | 4.6 TSSR Approved |  | 2023-10-10 | 2023-10-18 |  | 2023-10-24 |  | Closed | 2024-01-08 | 2024-01-16 |  | 2024-01-10 | Celcom Digi_RAN-GTSB-TSS-Northern-20231011-0046 | DU00002862111 |  |  | 2024-02-24 | 2024-02-14 |  | In-Building System | 6m Unipole RT | 6M | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 3
2280A | Tmn Desa Permai Sg Long | Central |  | Site Out (Modernization) | Modernization->Site Out->Replacement, Site Out (Modernization) | 2024 Q4 | SY1 | YPTT | 4.6 TSSR Approved |  | 2024-02-07 | 2024-02-20 |  | 2024-06-11 |  | Closed | 2024-06-13 | 2024-09-06 | E//Sumitra | 2024-06-19 | BOQ_Celcom Digi_RAN-YPTT-Standard PR TSS-20240218 | DU00002862112 | [5 empty] | Monopole | 20m Monopole | 18
3210A | Surau Muhammad Al Fateh | Central |  | Modernization |  | 2024 Q1 | AI | Magicell | 4.6 TSSR Approved |  | 2024-03-08 | 2024-03-11 |  | 2024-03-12 |  | Closed | 2024-03-12 | 2024-05-16 | E//Kok Keen | 2024-03-12 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240311 | DU00002862113 |  |  | 2024-04-07 | 2024-04-03 |  | Monopole | 24m Lampole | 24m | Add R9264H M901821 x4,Dismantle R8894E M1821(A8A) x4
3216A | Tmn Wangsa Maju | Central |  | Modernization |  | 2024 Q1 | XH | DATASCO | 4.6 TSSR Approved |  | 2023-11-06 | 2023-11-16 |  | 2023-12-28 |  | Closed | 2023-12-30 | 2024-01-02 | E//Kok Keen | 2024-01-02 | CelcomDigi_RAN_Datasco_TSS_Central_20231113 | DU00002862114 |  |  | 2024-02-27 | 2024-02-26 |  | Lampole | 24m Lampole | 25m | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
1263B | Tmn Desa Utama | Central |  | Modernization |  | 2024 Q3 | CR | AllStar | 4.6 TSSR Approved |  | 2023-12-08 | 2023-12-20 |  | 2024-03-29 |  | Closed | 2024-03-30 | 2024-04-04 | E//Sumitra | 2024-04-03 | CelcomDigi_RAN_AllStar_TSS_Central_20231224 | DU00002862115 |  |  | 2024-05-15 | 2024-05-15 |  | Lampole | 24m Lampole | 18 | Add R9264H M901821 x3,Dismantle R8892N M1821(BAB) x3 | 0 | 0
3708A | Jln 1_27a | Central |  | Modernization |  | 2024 Q1 | YZ | DATASCO | 4.6 TSSR Approved | 29/01 TI done. RRU install inside cabinet, have temperature alarm according to technical team | 2023-11-05 | 2023-11-14 |  | 2023-12-29 |  | Closed | 2024-01-02 | 2024-04-05 | E//Kok Keen | 2024-04-05 | CelcomDigi_RAN_Datasco_TSS_Central_20231113 | DU00002862116 |  |  | 2024-01-18 | 2024-01-11 |  | Lampole | 18m Lampole | 19 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3
3717A | Shell Bangsar Baru | Central |  | Modernization |  | 2024 Q2 | SY1 | YPTT | 4.6 TSSR Approved |  | 2024-06-04 | 2024-06-10 |  | 2024-06-12 |  | Closed | 2024-06-12 | 2024-06-13 | E//Kok Keen | 2024-06-12 | BOQ_Celcom Digi_RAN-YPTT-Standard PR TSS-20240428 | DU00002862117 |  |  | 2024-08-14 | 2024-07-30 |  | Petronas Pylon | 24m Pylon | 25m | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
4928A | Gedong Estate | Northern |  | Modernization |  | 2024 Additional | BY | CCSMY | 4.6 TSSR Approved |  | 2023-11-21 | 2023-11-21 |  | 2023-11-24 |  | Closed | 2023-12-05 | 2023-12-20 | E//Ajay | 2023-12-17 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231122-0072 | DU00002862118 |  |  | 2024-12-02 | 2024-11-26 |  | Tower | 30m Monopole | 61 | Add R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
4020C | Kg Baru Sg Kroh | Northern |  | Modernization |  | 2024 Additional | SHA | GTSB | 4.6 TSSR Approved | ¦ 0213 - TM reject, GTSB to revise details, Lat/Long, RRU proposal wording | 2023-11-17 | 2023-11-20 |  | 2024-11-22 |  | Under Approval | 2024-11-26 | 2024-12-16 | E//Hazida | 2024-12-15 | Celcom Digi_RAN-GTSB-TSS-Northern-20231118-0066//2111CD-Northern-TSS-BOQ Template(new contract)_GTSB | DU00002862119 | Remarks: Solution TSSR/BOM Changed |  | 2024-12-09 | 2024-12-04 |  | Tower | 45m 3 Legged Tower | 60 | Add R8852E S9000 x3+R8894E M1821 x3,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 | 0 | 0
4793A | Cenang | Northern |  | Modernization |  | 2025 Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2025-01-24 | 2025-02-10 |  | 2025-02-18 |  | Closed | 2025-02-19 | 2025-02-27 | E//Hazida | 2025-02-19 | SQ202501030229 - gtsb | DU00002862120 | Remarks: Solution TSSR/BOM Changed |  | 2025-03-10 | 2025-03-03 |  | In-Building System | 3m Bipod (RT) | 4M | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8882 S1800B(B6B)x3+R8854D S2100(A4A)x3 | 0 | 0
3140B | Citi Point Puchong Utama | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-09 | 2024-01-19 |  | 2024-04-24 |  | Closed | 2024-05-13 | 2024-05-14 | E//Razif | 2024-05-14 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240110 | DU00002862121 |  |  | 2024-06-28 | 2024-06-25 |  | In-Building System | 6m Unipole RT | 7 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882 S1800B(B6B) x3++R8881 S2100 x3+ | 0 | 0
2221A | Changkat Damai | Central |  | Modernization |  | 2024 Q1 | IE | Magicell | 4.6 TSSR Approved |  | 2023-11-18 | 2023-11-21 |  | 2024-01-04 |  | Closed | 2024-03-26 | 2024-03-27 | E//Kok Keen | 2024-03-27 | CelcomDigi_RAN_Magicell_TSS_Central_20231120 | DU00002862122 |  |  | 2024-03-07 | 2024-03-04 |  | Lampole | 30m Monopole | 20M | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x3+R8894E M1821(A8A) x4+R9224E M1821(AAB) x2 | 123
4177C | UTAR BlOCK A | Northern |  | Modernization |  | 2024 Additional | AI | GCI | 4.6 TSSR Approved |  | 2024-12-09 | 2024-12-17 |  | 2024-12-26 |  | Closed | 2024-12-27 | 2025-02-07 | E//Hazida | 2025-01-14 | 1911CD-Northern-TSS-BOQ Template(new contract)_GCI_V2 | DU00002862123 |  |  | 2025-01-13 | 2025-01-13 |  | In-Building System | 6m Unipole RT | 15 | Add R9264M M1821x4, Dismantle R8862A S1800(B6A)x4+R8862A S2100(A6A)x4 | 0 | 0
3108B | Seputeh OKD (HSR) | Central |  | Modernization |  | 2024 Q3 | CR | AllStar | 4.6 TSSR Approved |  | 2023-12-06 | 2023-12-19 |  | 2024-03-29 |  | Closed | 2024-03-30 | 2024-04-02 | E//Sumitra | 2024-04-02 | CelcomDigi_RAN_Allstar_TSS_Central_20231208 | DU00002862124 |  |  | 2024-04-27 | 2024-04-24 |  | Unipole | 3m Bipod (RT) | 6 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
3182B1 | pBTS Bkt Serdang Ind (M) | Central |  | Modernization | Modernization->On Hold->Modernization | 2024 Q3 | AD | GCI | 4.6 TSSR Approved |  | 2023-10-19 | 2023-10-25 |  | 2023-11-01 |  | Rectificating | 2024-11-14 | 2024-11-26 | E//Sumitra | 2024-11-26 | CelcomDigi_RAN_GCI_TSS_Central_20231020 | DU00002862125 |  |  | 2024-11-23 | 2024-11-21 |  | Watertank | 25m pBTS | 24 | Add R8894E M1821x3, Dismantle R8882 S1800(B)x1+R8882 S1800B(B6B)x2+R8881 S2100x3 | 0 | 0
1979B | KG CHERAS BARU 2 (REL) | Central |  | Modernization |  | 2024 Q3 | AI | YPTT | 4.6 TSSR Approved |  | 2023-10-21 | 2023-10-26 |  | 2024-04-03 |  | Closed | 2024-04-15 | 2024-04-16 | E//Sumitra | 2024-04-16 | CelcomDigi_RAN_YPTT_TSS_Central_20231023 | DU00002862126 |  |  | 2024-06-07 | 2024-06-01 |  | Lampole | 24m Lampole | 25 | Add R9264M M1821 x4,Dismantle R8882 S1800B(B6B) x3+R8862A S1800(B6A) x1++R8881 S2100 x3+ | 0 | 0
2014A | Tmn Setia (LP) | Central |  | Modernization |  | 2024 Q1 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-06 | 2023-11-10 |  | 2024-01-03 |  | Closed | 2024-01-04 | 2024-01-05 | E//Kok Keen | 2024-01-04 | CelcomDigi_RAN_GTSB_TSS_Central_20231113 | DU00002862127 |  |  | 2024-01-12 | 2024-01-11 |  | Lampole | 45m Monopole | 20M | Resuse exsiting RRU
4206C | Kerian Sentral Mall | Northern |  | Site Out (Modernization) | Modernization->Site Out->Replacement, Site Out (Modernization) | 2026 |  | GTSB | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862128 | [6 empty] | 3m Boom (RT)
3617A | Kelab Aman (REL) | Central |  | Modernization |  | 2024 Q1 | XH | Ascentrack | 4.6 TSSR Approved |  | 2023-11-09 | 2023-11-14 |  | 2023-12-28 |  | Closed | 2023-12-28 | 2024-01-03 | E//Sumitra | 2024-01-03 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231113 | DU00002862129 |  |  | 2024-05-08 | 2024-05-06 |  | Lampole | 24m Lampole | 25m | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
3401B | Condo Karunmas | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-11 | 2024-01-15 |  | 2024-04-25 |  | Closed | 2024-05-03 | 2024-05-10 | E//Sumitra | 2024-05-09 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240115 | DU00002862130 |  |  | 2024-06-08 | 2024-06-05 |  | A-bracket pole | 3m Boom (RT) | 7m | Add R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
3495B | Jalan Gembira (REL) | Central |  | Modernization |  | 2024 Q3 | SS | AllStar | 4.6 TSSR Approved |  | 2023-12-04 | 2023-12-06 |  | 2023-12-13 |  | Closed | 2024-04-19 | 2024-04-23 | E//Sumitra | 2024-04-23 | CelcomDigi_RAN_Allstar_TSS_Central_20231208 | DU00002862131 |  |  | 2024-04-04 | 2024-04-02 |  | Lampole | 18m Lampole | 18 | Add R8862A S9000 x3+RR9264M M1821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
3509B | Syabas Tmn Melati | Central |  | Modernization |  | 2024 Q1 | CR | GTSB | 4.6 TSSR Approved |  | 2023-11-08 | 2023-11-14 |  | 2024-01-06 |  | Closed | 2024-01-18 | 2024-01-19 | E//Kok Keen | 2024-01-18 | CelcomDigi_RAN_GTSB_TSS_Central_20231113 | DU00002862132 |  |  | 2024-02-29 | 2024-02-27 |  | Lampole | 24m Lampole | 30m | Add R8894E M1821 x4+R8854 S2600 x1,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3+R8862A S2600(A4A) x1 |  | 3
3551B | Midfields Square West (REL) | Central |  | Modernization |  | 2024 Q3 | SH | DATASCO | 4.6 TSSR Approved |  | 2023-10-30 | 2023-11-03 |  | 2024-03-25 |  | Closed | 2024-03-27 | 2024-04-15 | E//Kok Keen | 2024-04-05 | CelcomDigi_RAN_Datasco_TSS_Central_20231101 | DU00002862133 |  |  | 2024-06-20 | 2024-06-18 |  | In-Building System | Land site | 6m | Add R9264H M901821 x4,Dismantle R9224E M1821(AAB) x4 | 0 | 0
7035B | Matunggong | Sabah |  | Modernization |  | 2025 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2023-10-31 | 2023-11-03 |  | 2025-02-19 |  | Under Approval | 2025-02-28 | 2025-03-26 | E//Hannah | 2025-03-16 | Celcom Digi_RAN-YPTT-Standard PR TSS-Sabah-20240813 | DU00002862134 |  |  | 2025-03-30 | 2025-03-18 |  | Tower | Tower | 60 | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8882 S1800B(B6B)x3 | 0 | 0
3175B4 | pBTS Kg Luak Miri (M ) | Sarawak |  | Remote MOCN | Modernization->On Hold->Remote MOCN | 2027 | SH | Trintel | 4.6 TSSR Approved |  | 2023-10-11 | 2023-10-12 |  | 2023-10-22 |  | Closed | 2023-10-23 | 2023-11-07 | E//Hannah | 2023-11-07 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231017 | DU00002862135 | [5 empty] | Watertank | 25m pBTS | 30 | Reuse Existing RRU | 0 | 0
K00855 | CBKGKUALAMERAH | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862136 | [6 empty] | TOWER
3914B | LRT Chan Sow Lin | Central |  | Modernization |  | 2024 Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2023-11-23 | 2023-11-27 |  | 2024-03-21 |  | Closed | 2024-03-22 | 2024-03-26 | E//Sumitra | 2024-03-26 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240303 | DU00002862137 |  |  | 2024-08-23 | 2024-08-21 |  | In-Building System | LRT | 3M | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
K00857 | K009A_K00857OD_CB_KG_PINANG_PEDU | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862138 | [6 empty] | TOWER
3513B | Masjid Kg Pulau Meranti | Central |  | Modernization |  | 2024 Q3 | SY1 | Solusi | 4.6 TSSR Approved |  | 2024-03-03 | 2024-08-27 |  | 2024-08-30 |  | Closed | 2024-09-03 | 2024-09-06 | E//Razif | 2024-09-06 | 0827CD-Central-Solusi-BOQ Template(new contract) | DU00002862139 |  |  | 2024-11-14 | 2024-11-09 |  | Lampole | 24m Lampole | 25 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882 S1800B(B6B) x2+R8862A S1800(B6A) x1+R8881 S2100 x3 | 0 | 0
3941B | Lorong Utara Kecil (Billboard) | Central |  | Modernization |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-02-27 | 2024-03-04 |  | 2024-04-04 |  | Closed | 2024-04-05 | 2024-04-15 | E//Kok Keen | 2024-04-08 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240303 | DU00002862140 |  |  | 2024-04-25 | 2024-04-23 |  | BillBoard | Billboard | 5m | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
3851B | Surau Darul Ikhlas BU (REL) | Central |  | Modernization |  | 2024 Q3 | AI | GCI | 4.6 TSSR Approved |  | 2023-10-22 | 2023-10-25 |  | 2024-03-26 |  | Under Approval | 2024-03-26 | 2024-07-12 | E//Kok Keen | 2024-07-12 | CelcomDigi_RAN_GCI_TSS_Central_20231023 | DU00002862141 |  |  | 2024-05-17 | 2024-05-14 |  |  | 24m Lampole | 25 | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
K00623 | K009A_K00623OD_MN_KGMACHANG | Northern | 4115P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q3 | AD | CCSMY | 4.6 TSSR Approved |  | 2025-01-04 | 2025-01-09 |  | 2025-02-20 |  | Under Approval | 2025-04-14 | 2025-05-27 | CD//Zulakmar | 2025-04-23 | SQ202501030318 - CCSMY | DU00002862142 |  |  | 2025-04-29 | 2025-04-25 |  | Tower | #N/A | 75 | Add R8852E S9000x3+R8894E M1821x4+R8862A S2601x2+R8854 S2600x1, Dismantle | 0 | 2
3853B | Jalan PJS 2_1 | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-18 | 2023-11-21 |  | 2023-12-18 |  | Closed | 2024-08-13 | 2024-08-21 | E//Sumitra | 2024-08-21 | CelcomDigi_RAN_GTSB_TSS_20231119 | DU00002862143 |  |  | 2024-05-19 | 2024-05-15 |  | Lampole | Building | 24m | Add R8862A S9000 x3+R8862A S2601 x2+R8894E M1821 x1+R8854 S2600 x1,Dismantle | 0 | 1
3856B | Kg Pandan Showroom | Central |  | Modernization |  | 2024 Q2 | YZ | GTSB | 4.6 TSSR Approved |  | 2023-12-05 | 2023-12-12 |  | 2024-01-15 |  | Closed | 2024-01-18 | 2024-01-29 | E//Sumitra | 2024-01-24 | CelcomDigi_RAN_GTSB_TSS_Central_20231208 | DU00002862144 |  |  | 2024-03-08 | 2024-03-06 |  | Lampole | 24m Lampole | 24m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
3746B | Jalan Kerinchi Kiri 3 | Central |  | Modernization |  | 2024 Q2 | AI | AllStar | 4.6 TSSR Approved | ¦ 0329 : Existing using cluster antenna, proposed to add bracket for new normal antenna | 2024-02-05 | 2024-03-25 |  | 2024-03-29 |  | Closed | 2024-03-29 | 2024-04-01 | E//Kok Keen | 2024-03-29 | BOQ CelcomDigi_RAN_AllStar_Standard PR TSS_Central_20240128 | DU00002862145 |  |  | 2024-11-27 | 2024-08-22 |  | Lampole | 18m Lampole | 18 | Add R9264M M1821 x2,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
3769B | Jalan Kuari | Central |  | Modernization |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-24 | 2023-12-01 |  | 2024-03-22 |  | Closed | 2024-03-25 | 2024-04-01 | E//Sumitra | 2024-04-01 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231126 | DU00002862146 |  |  | 2024-06-06 | 2024-06-01 |  | Lampole | 30m Monopole | 18 | Add R9264M M1821 x3,Dismantle R8892E M1821(BAA) x3 | 0 | 0
4463C | Langkap Town | Northern |  | Modernization |  | 2027 |  | GCI | 4.1 Pending TSSR Submission - Subcon |  | 2025-11-15 | 2025-11-21 |  |  |  | To be Submitted |  |  |  |  | SQ202511050343 | DU00002862147 | [5 empty] | Portables BTS | 4 Legged Tower | 8m | Add R8852E S9000x3+R9264M M1821x3, Dismantle R8862A S2600(A4A)x1+R9224E M1821(AAB)x4 | 0 | 0
7397B | Kampung Durian | Sabah |  | Modernization |  | 2024 Q3 | MS | GTSB | 4.6 TSSR Approved |  | 2023-10-23 | 2023-10-30 |  | 2023-11-03 |  | Closed | 2024-04-15 | 2024-06-12 | E//Hannah | 2024-06-11 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231024 | DU00002862148 |  |  | 2024-06-15 | 2024-06-08 |  |  | Tower | 30 | Add R8894E M1821 x3+R8854 S2600 x3,Dismantle R8862A S2600(A4A) x3 | 0 | 123
3581B | Taman Tenaga | Central |  | Modernization |  | 2024 Q3 | SS | Ascentrack | 4.6 TSSR Approved | AAU Cannot Install-S13 MM change to BI¦Unipole sites can add only 1 AAU(Y-bracket),Space constraint between S1 and S3(There is a MW) | 2023-11-09 | 2023-11-27 |  | 2023-12-09 |  | Closed | 2024-03-29 | 2024-04-03 | E//Sumitra | 2024-04-03 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231113 | DU00002862149 |  |  | 2024-07-02 | 2024-06-23 |  | In-Building System | 3m Bipod (RT) | 6.5m | Add R8894E M1821 x5+R8854 S2600 x2,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3+R8862A S2600(A4A) x2 | 0 | 13
3516B | Taman Alam Putra | Central |  | Modernization |  | 2024 Q3 | SH | GCI | 4.6 TSSR Approved |  | 2023-10-25 | 2023-11-02 |  | 2024-04-29 |  | Under Approval | 2024-08-14 | 2024-08-21 | E//Kok Keen | 2024-08-21 | CelcomDigi_RAN_GCI_TSS_Central_20231214 | DU00002862150 |  |  | 2024-06-23 | 2024-06-20 |  | In-Building System | 3m Bipod (RT) | 6 | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 | 13 | 0
3006C | Masjid Al-Mustaqim Ampang | Central |  | Modernization |  | 2024 Q2 | XH | YPTT | 4.6 TSSR Approved |  | 2023-11-03 | 2023-11-10 |  | 2024-01-10 |  | Closed | 2024-01-24 | 2024-01-31 | E//Kok Keen | 2024-01-30 | CelcomDigi_RAN_YPTT_TSS_Central_20231028 | DU00002862151 |  |  | 2024-03-06 | 2024-03-04 |  | Lampole | 24m Lampole | 24 | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
1324A | Bangsarheight | Central |  | Modernization |  | 2024 Q2 | YZ | AllStar | 4.6 TSSR Approved |  | 2024-01-04 | 2024-01-16 |  | 2024-01-24 |  | Closed | 2024-01-29 | 2024-02-02 | E//Kok Keen | 2023-01-29 | BOQ CelcomDigi_RAN_AllStar_Standard PR TSS_Central_20240108 | DU00002862152 |  |  | 2024-03-27 | 2024-03-19 |  |  | 3m Bipod (RT) | 3 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
3124C | Perdana Lakeview East | Central |  | Modernization |  | 2024 Q3 | SY1 | GTSB | 4.6 TSSR Approved |  | 2024-01-24 | 2024-02-01 |  | 2024-10-09 |  | Under Approval | 2024-10-14 | 2024-10-17 | E//Razif | 2024-10-17 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240128 | DU00002862153 |  |  | 2025-07-21 | 2025-07-21 |  | Lampole | 3m Boom (RT) | 21M | Add R8894E M1821x3+R8862A S2601x3,Dismantle R8862A S2600(A4A) x3+R8892E M1821(BAA) x3 | 0 | 0
3262C | Kg Lembah Jaya (REL) | Central |  | Modernization |  | 2024 Q4 | AI | AllStar | 4.6 TSSR Approved |  | 2023-11-27 | 2023-12-27 |  | 2024-05-20 |  | Closed | 2024-05-23 | 2024-05-30 | E//Sumitra | 2024-05-30 | CelcomDigi_RAN_Allstar_TSS_Central_20231101 | DU00002862154 |  |  | 2024-07-23 | 2024-07-17 |  |  | 3m Boom (RT) | 4 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
4567C | Taman Onn | Northern |  | Modernization |  | 2024 Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2023-10-11 | 2023-10-12 |  | 2024-01-09 |  | Rectificating | 2024-01-11 | 2024-01-22 | E//Hazida => E//Ajay | 2024-01-19 | Celcom Digi_RAN-GTSB-TSS-Northern-20231012-0047 | DU00002862155 |  |  | 2024-02-21 | 2024-02-16 |  | In-Building System | 30m Monopole | 5 | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3
7557B | Unicorn Temple (REL) | Sabah |  | Site Out (Modernization) | Modernization->Site Out->Site Out (Modernization) | 2024 Q3 | AD | YPTT | [SiteOut]- 4.1 Pending TSSR Submission - Subcon | 4/4: Site Dismantled as informed by SA and survey team. Reference photos attached in email | 2025-06-21 |  | 2025-06-24 | [7 empty] | SQ202506160230 - YPTT | DU00002862156 | [6 empty] | 30m Monopole
3302C | Taman Seri Budiman | Central |  | Site Out (Modernization) | Modernization->Site Out->Replacement, Site Out (Modernization) | 2024 Q4 | SY1 | YPTT | 4.6 TSSR Approved |  | 2024-01-30 | 2024-02-15 | 2025-08-12 | 2024-06-04 |  | Closed | 2024-08-26 | 2024-08-28 | E//Sumitra | 2024-08-28 | BOQ_Celcom Digi_RAN-YPTT-Standard PR TSS-20240202 | DU00002862157 | [5 empty] | Lampole | 3m Bipod (RT) | 24m | Add R9264H M901821 x3,Dismantle R8892E M1821(BAA) x3 | 0 | 0
1283A | Tmn Kencana | Central |  | Modernization |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-08 | 2023-11-10 |  | 2023-11-20 |  | Closed | 2024-03-29 | 2024-04-02 | E//Sumitra | 2024-04-02 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231113 | DU00002862158 |  |  | 2024-06-06 | 2024-06-04 |  | Minimast | Tower | 6.5 | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 2 | 0
2073B | Jln Genting Klang | Central |  | Modernization |  | 2024 Q1 | AI | DATASCO | 4.6 TSSR Approved |  | 2024-01-26 | 2024-02-26 |  | 2024-03-04 |  | Closed | 2024-03-05 | 2024-03-06 | E//Kok Keen | 2024-03-06 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240128 | DU00002862159 |  |  | 2024-04-29 | 2024-04-28 |  | In-Building System | 3m Boom (RT) | 6M | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
1370B | Seksyen 6B Bdr. Kinrara | Central |  | Modernization |  | 2024 Q3 | SH | GTSB | 4.6 TSSR Approved |  | 2023-10-29 | 2023-11-03 |  | 2024-04-05 |  | Closed | 2024-04-16 | 2024-07-26 | E//Kok Keen | 2024-07-26 | CelcomDigi_RAN_GTSB_TSS_Central_20231101 | DU00002862160 |  |  | 2024-06-05 | 2024-06-01 |  | Monopole | 24m Lampole | 13 | Add R9264H M901821 x3,Dismantle R8892E M1821(BAA) x3+R8862A S9000(A6A) x3 | 0 | 0
7352B | Kg Podos | Sabah |  | Modernization |  | 2025 Q3 | AD | NR services | 4.6 TSSR Approved |  | 2025-01-22 | 2025-02-07 |  | 2025-03-10 |  | Under Approval | 2025-03-19 | 2025-05-27 | E//Hannah | 2025-05-07 | SQ202501020451 - NR Service | DU00002862161 |  |  | 2025-04-16 | 2025-04-11 |  | Tower | Tower | 76 | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3 | 0 | 0
9544B | Kpg Sebigo 2 | Sarawak |  | Modernization |  | 2024 Q2 | SH | Magicell | 4.6 TSSR Approved |  | 2023-10-24 | 2023-10-25 |  | 2024-01-09 |  | Closed | 2024-03-07 | 2024-03-25 | E//Hannah | 2024-03-22 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231214 | DU00002862162 |  |  | 2024-05-21 | 2024-05-09 |  | Tower | Tower | 60 | Add R8894E M1821 x2+R8854 S2600 x2,Dismantle | 0 | 23
9551B | Kpg Tebero | Sarawak |  | Modernization |  | 2024 Q2 | SH | Magicell | 4.6 TSSR Approved |  | 2023-10-25 | 2023-10-27 |  | 2024-01-10 |  | Closed | 2024-01-11 | 2024-01-17 | E//Hannah | 2024-01-16 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231214 | DU00002862163 |  |  | 2024-03-06 | 2024-03-06 |  | Tower | Tower | 60 | Reuse existing RRU
4449B | NS KM310.6 | Northern |  | Modernization |  | 2024 Additional | AD | CCSMY | 4.6 TSSR Approved |  | 2024-12-11 | 2024-12-16 |  | 2024-12-18 |  | Under Approval | 2024-12-19 | 2024-12-20 | E//Hazida | 2024-12-20 | 1911CD-Northern-TSS-BOQ Template(new contract)_CCSMY_V2 | DU00002862164 |  |  | 2025-01-13 | 2025-01-13 |  | Tower | 76m 3 Legged Tower | 60m | Reuse Existing RRU | 0 | 0
3571B | National Stadium Bkt Jalil IB | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 | SS | Magicell | 14.2 Drop (Done Survey) |  | 2024-02-28 | 2024-03-05 | [8 empty] | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240303 | DU00002862165 | [5 empty] | Portables BTS | In-building system
3461C | National Stadium Bkt Jalil IB 2 | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 | SS | Magicell | 14.2 Drop (Done Survey) |  | 2024-01-08 | 2024-01-15 | [8 empty] | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240110 | DU00002862166 | [6 empty] | 24m Lampole
9591B | Long Laput | Sarawak |  | Modernization | Modernization | 2026 |  | Redtone | 1.1 Pending Survey - Subcon | [6 empty] | To be Submitted |  |  |  |  | SQ202605080538 - Redtone | DU00002862167 | [5 empty] | Tower | Tower |  | Add R8862A S2601x3
2661A10 | pBTS Jalan Seri Emas | Central |  | Remote MOCN | Modernization->On Hold->Remote MOCN | 2024 Q4 |  | Magicell | 3.4 SOW/Solution On Hold |  | 2023-11-20 | 2023-12-20 |  |  |  | To be Submitted |  |  |  |  | CelcomDigi_RAN_Magicell_TSS_Central_20231214 | DU00002862168 | [5 empty] | Watertank | 25m pBTS | 24 | Add R9264H M901821 x3,Dismantle R8882 S1800(B)x1+R8882 S1800B(B6B)x2+R8862A S2100(A6A)x3 | 0 | 0
1567B3 | pBTS Hartalega Sepang | Central |  | Modernization | Modernization->On Hold->Modernization | 2025 Q1 | AI | GCI | 14.0 TSSR Not Required (Reuse Existing BBU/RRU) |  | 2025-06-24 | 2025-07-10 |  |  |  | To be Submitted |  |  |  |  | SQ202508140671 | DU00002862169 |  |  | 2025-06-24 | 2025-05-28 |  | Tower | 25m pBTS | 28m | Reuse Existing RRU | 0 | 0
3597C | SK Seri Indah (REL) | Central |  | Modernization |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved | 4/3 RRU install inside cabinet, 6pcs// 29/01 RRU install inside cabinet, 3 RRU on top,have temperature alarm according to technical team | 2023-12-09 | 2023-12-13 |  | 2023-12-18 |  | Closed | 2024-05-13 | 2024-05-17 | E//Sumitra | 2024-05-17 | CelcomDigi_RAN_Datasco_TSS_Central_20231213 | DU00002862170 |  |  | 2024-04-15 | 2024-04-02 |  | Lampole | 18M Lampole | 19 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
4994C | Taman Pengkalan Cemerlang | Northern |  | Modernization |  | 2024 Q2 | SM | GCI | 4.6 TSSR Approved |  | 2023-10-05 | 2023-10-17 |  | 2024-01-10 |  | Rectificating | 2024-01-15 | 2024-01-23 | E//Hazida | 2024-01-21 | Celcom Digi_RAN-GCI-TSS-Northern-2023111-0057 | DU00002862171 |  |  | 2024-04-22 | 2024-03-28 |  | In-Building System | 30m Monopole | 9 | Add R8894E M1821 x6+R8854 S2600 x2,Dismantle R8862A S1800(B6A) x4+R8862A S2100(A6A) x4+R8862A S2600(A4A) x2 |  | 23
4978C | Kledang Permai | Northern |  | Modernization |  | 2024 Q2 |  | GTSB | 4.6 TSSR Approved |  | 2023-10-11 | 2023-10-16 |  | 2024-01-08 |  | Closed | 2024-01-09 | 2024-01-11 |  | 2024-01-10 | Celcom Digi_RAN-GTSB-TSS-Northern-20231012-0047 | DU00002862172 |  |  | 2024-02-10 | 2024-01-26 |  | In-Building System | 30m Monopole | 6m | Add R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
4949C | Taman Seri Manis | Northern |  | Modernization |  | 2024 Q4 | HQ 1 | GCI | 4.6 TSSR Approved |  | 2023-10-09 | 2023-10-17 |  | 2023-10-23 |  | Closed | 2023-10-25 | 2023-10-30 | E//Hazida | 2023-10-27 | Celcom Digi_RAN-GCI-TSS-Northern-2023111-0057 | DU00002862173 |  |  | 2024-05-29 | 2024-05-17 |  | Lampole | Tower | 31M | Add R8862A S9000 x1+R9264H M901821 x3+A9732 M1821 x1,Dismantle R8892N M1821(BAB) x4 | 4 | 0
3625C | Flat Puchong Permai | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-18 | 2024-01-30 |  | 2024-04-23 |  | Closed | 2024-04-25 | 2024-04-26 | E//Razif | 2024-04-25 | CelcomDigi_RAN_GTSB_TSS_Central_20240124 | DU00002862174 |  |  | 2024-05-13 | 2024-05-08 |  | Lampole | 24m Lampole | 25m | Add R8862A S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x3+R9224E M1821(AAB) x2 | 13 | 0
3661C | Masjid Nurul Iman Kg. Tengah | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-02-18 | 2024-02-21 |  | 2024-04-20 |  | Closed | 2024-05-03 | 2024-05-07 | E//Razif | 2024-05-06 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240225 | DU00002862175 |  |  | 2024-06-01 | 2024-05-31 |  | Lampole | 24m Lampole | 25m | Add R8862A S9000 x3,Dismantle | 0 | 0
9601C | Kampung Bugu | Sarawak |  | Modernization |  | 2027 | AI | Magicell | 14.0 TSSR Not Required (Reuse Existing BBU/RRU) |  | 2023-10-30 | 2023-11-01 |  | 2025-04-20 |  | Under Approval |  |  |  |  | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231214 | DU00002862176 | [5 empty] | Tower | Tower | 47M | Reuse Existing RRU
4075D | Mambang Diawan Shoplot (REL) | Northern |  | Modernization |  | 2024 Additional | SHA | GCI | 4.6 TSSR Approved |  | 2024-12-15 | 2024-12-16 |  | 2024-12-24 |  | Under Approval | 2024-12-27 | 2024-12-27 | E//Hazida | 2024-12-27 | 1911CD-Northern-TSS-BOQ Template(new contract)_GCI | DU00002862177 |  |  | 2025-02-28 | 2025-02-14 |  | Tower | 21m Minaret | 21m | Add R9264M M1821x3, Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3 | 0 | 0
7367B2 | pBTS Kg Sim-Sim (KM) | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2024 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2024-03-14 | 2025-02-19 |  | 2025-03-13 |  | Under Approval | 2025-03-26 | 2025-04-15 | E//Hannah | 2025-04-02 | Celcom Digi_RAN-YPTT-TSS-Sabah-20240324 | DU00002862178 | Remarks: Solution TSSR/BOM Changed |  | 2025-04-14 | 2025-04-09 |  | Watertank | 25m pBTS | 25 | Reuse Existing RRU | 0 | 12
3863C | Taman Bukit Angkasa | Central |  | Modernization |  | 2024 Q2 | SH | AllStar | 4.6 TSSR Approved |  | 2024-02-05 | 2024-03-29 |  | 2024-04-05 |  | Closed | 2024-04-18 | 2024-04-19 | E//Kok Keen | 2024-04-19 | BOQ CelcomDigi_RAN_AllStar_Standard PR TSS_Central_20240128 | DU00002862179 |  |  | 2024-11-27 | 2024-08-24 |  | Lampole | 18m Lampole | 21 | Add R9264M M1821 x2,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
9006B3 | pBTS Sri Datai Office | Sarawak |  | Modernization | Modernization->On Hold->Modernization | 2025 Q2 | AD | Trintel | 4.6 TSSR Approved |  | 2025-03-17 | 2025-04-18 |  | 2025-04-22 |  | Under Approval | 2025-04-24 | 2025-05-21 | E//Hannah | 2025-05-08 | SQ202503030116-Trintel | DU00002862180 | Remarks: Solution TSSR/BOM Changed |  | 2025-05-26 | 2025-05-24 |  | Watertank | 25m pBTS | 30 | Add R8894E M1821x3, Dismantle R8882 S1800(B)x2+R8882 S1800B(B6B)x1+R8862A S2100(A6A)x3 | 0 | 0
1140C | Jalan Permaisuri | Central |  | Modernization |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-02 | 2023-11-06 |  | 2023-11-25 |  | Closed | 2024-04-01 | 2024-04-15 | E//Sumitra | 2024-04-08 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231104 | DU00002862181 |  |  | 2024-05-29 | 2024-05-29 |  |  | 18m Lampole | 18 | Add R8862A S9000 x1+R9264H M901821 x2+R8862A S2601 x1+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 3 | 0
1155C | JALAN GEMBIRA | Central |  | Modernization |  | 2024 Q3 | MA | DATASCO | 4.6 TSSR Approved |  | 2024-04-01 | 2024-03-20 |  | 2024-04-02 |  | Closed | 2024-04-02 | 2024-04-15 | E//Sumitra | 2024-04-08 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_202400403 | DU00002862182 |  |  | 2024-05-23 | 2024-05-22 |  | Lampole | 18m Lampole | 18 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
2736B | Taman Midah Cheras | Central |  | Modernization |  | 2024 Q3 | MA | GTSB | 4.6 TSSR Approved |  | 2024-04-24 | 2024-05-03 |  | 2024-05-24 |  | Closed | 2024-05-25 | 2024-06-07 | E//Sumitra | 2024-06-07 | CelcomDigi_RAN_GTSB_TSS_Central_20240513 | DU00002862183 |  |  | 2024-06-19 | 2024-06-15 |  | Lampole | Building | 18 | Add R9264H M901821 x3,Dismantle R9224E M1821(AAB) x3 | 0 | 0
1034B | Tmn Len Seng Cheras | Central |  | Modernization |  | 2024 Q3 | MA | Magicell | 4.6 TSSR Approved |  | 2023-11-04 | 2023-11-08 |  | 2024-04-02 |  | Closed | 2024-06-10 | 2024-07-12 | E//Sumitra | 2024-07-12 | CelcomDigi_RAN_Magicell_TSS_Central_20231113 | DU00002862184 |  |  | 2024-06-27 | 2024-06-26 |  | In-Building System | 6m RT (Wall Mounted Pole) | 6 | Add R8894E M1821 x1,Dismantle | 0 | 1
1146C | Jln Indah 7 | Central |  | Modernization |  | 2024 Q4 | SM | GTSB | 4.6 TSSR Approved |  | 2023-11-22 | 2023-11-27 |  | 2024-05-15 |  | Under Approval | 2024-05-17 | 2024-05-29 | E//Sumitra | 2024-05-29 | CelcomDigi_RAN_GTSB_TSS_Central_20231126 | DU00002862185 |  |  | 2024-05-25 | 2024-05-25 |  | Lampole | 18m Lampole | 18m | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3 | 0 | 0
7064C | Kg.Jawa | Sabah |  | Modernization |  | 2024 Q3 | MS | GTSB | 4.6 TSSR Approved |  | 2023-10-20 | 2023-10-25 |  | 2023-10-28 |  | Closed | 2023-10-30 | 2023-11-14 | E//Hannah | 2023-11-08 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231024 | DU00002862186 |  |  | 2024-06-06 | 2024-05-25 |  | Monopole | 30m Lampole | 30 | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 2 | 0
1050C | Jalan BK 3_2 | Central |  | Modernization |  | 2024 Q3 | MA | DATASCO | 4.6 TSSR Approved |  | 2023-11-17 | 2023-11-24 |  | 2024-05-02 |  | Closed | 2024-05-03 | 2024-07-11 | E//Sumitra | 2024-07-11 | CelcomDigi_RAN_Datasco_TSS_Central_20231214 | DU00002862187 |  |  | 2024-06-15 | 2024-06-15 |  | Lampole | 24m Lampole | 24m | Add R8862A S9000 x3,Dismantle | 0 | 0
4165D | Jalan Manggis Teluk Intan | Northern |  | Site Out (Modernization) | Modernization->Site Out->Replacement, Site Out (Modernization) | 2025 Q1 |  | GCI | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2025-01-13 | 2025-10-28 | [8 empty] | SQ202501030261 - GCI | DU00002862188 | [6 empty] | 3m Boom (RT) |  | Add R8852E S9000 x3+R9264M M1821 x3, Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3 | 0 | 0
4168D | Masjid Hutan Melintang | Northern |  | Modernization |  | 2027 | AI | CCSMY | 4.6 TSSR Approved |  | 2025-02-08 | 2025-02-12 |  | 2025-03-04 |  | Closed | 2025-11-11 | 2026-01-22 |  | 2025-11-18 | SQ202501030037 - CCSMY | DU00002862189 | [5 empty] | Minaret | 30M Minaret | 30M | Add R8852E S9000x2, Dismantle R9224E M1821(AAB)x2
4182D | Kawasan Perusahaan Menglembu 2 | Northern |  | Modernization |  | 2024 Q2 |  | CCSMY | 4.6 TSSR Approved |  | 2023-11-26 | 2023-11-28 |  | 2024-01-09 |  | Closed | 2024-01-10 | 2024-01-12 | E//Hazida | 2024-01-12 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231127-0073 | DU00002862190 |  |  | 2024-02-02 | 2024-01-22 |  | Monopole | 30m Monopole | 32M | Add R8862A S9000 x4,Dismantle
7960B | Jalan Dam | Sabah |  | Modernization |  | 2024 Q3 | MS | GTSB | 4.6 TSSR Approved |  | 2023-10-23 | 2023-10-26 |  | 2023-10-31 |  | Closed | 2024-04-22 | 2024-04-29 | E//Hannah | 2024-04-29 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231024 | DU00002862191 |  |  | 2024-06-04 | 2024-05-24 |  | Monopole | 30m Lampole | 30 | Add R8894E M1821 x1,Dismantle | 0 | 2
9005B9 | pBTS Kampung Siburan | Sarawak |  | Modernization | Modernization->On Hold->Modernization | 2025 Q2 | SH | Datasco | 4.6 TSSR Approved |  | 2023-10-18 | 2023-10-24 |  | 2023-10-30 |  | Closed | 2023-10-30 | 2023-11-15 | E//Hannah | 2026-04-17 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231019 | DU00002862192 |  | Remarks: Solution Changed | 2025-03-07 | 2025-03-06 |  | Tower | 25m pBTS | 35 | Reuse Existing RRU | 0 | 0
4814C | Padang Gong (REL) | Northern |  | Modernization |  | 2025 Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2023-10-23 | 2023-10-17 |  | 2023-10-23 |  | Rectificating | 2025-02-04 | 2025-02-19 | E//Hazida | 2025-02-19 | Celcom Digi_RAN-GTSB-TSS-Northern-20231214-0077 | DU00002862193 |  |  | 2025-03-22 | 2025-02-20 |  | Tower | 60m 4 Legged Tower | 75 | Add R8852E S9000x4+R9264M M1821x4, Dismantle R8862A S1800(B6A)x4+R8862A S2100(A6A)x4 | 0 | 0
3057C8 | pBTS Taman Mutiara Sandakan (KM) | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2024 Q3 | MS | Datasco | 14.0 TSSR Not Required (Reuse Existing BBU/RRU) |  | 2024-04-19 | 2024-05-07 |  |  |  | To be Submitted |  |  |  |  | S1MY2021071001WBF1-5645 | DU00002862194 |  |  | 2025-06-15 | 2025-06-15 |  | Watertank | 25m pBTS | 24 | Reuse Existing RRU | 0 | 0
3478C3 | pBTS IJM Sandakan Phase 4 (KM) | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2024 Q3 | MS | Datasco | 4.6 TSSR Approved |  | 2024-04-19 | 2024-05-09 |  | 2024-11-07 |  | Under Approval | 2024-11-08 | 2024-11-22 | E//Hannah | 2024-11-21 | Celcom Digi_RAN-Datasco-Standard PR TSS-Sabah-20241112 | DU00002862195 |  |  | 2025-01-24 | 2025-01-24 |  | Watertank | 25m pBTS | 30 | Add R8894E M1821x3, Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3 | 0 | 0
3645A10 | pBTS Villaraya | Central |  | Modernization | Modernization->On Hold->Modernization | 2024 Q4(single site MOCN)-L26 SSM | AD | YPTT | 4.6 TSSR Approved |  | 2023-10-20 | 2023-11-20 |  | 2024-11-12 |  | Under Approval | 2024-11-14 | 2024-11-20 | E//Sumitra | 2024-11-19 | BOQ_Celcom Digi_RAN-YPTT-Standard PR TSS-20240202 | DU00002862196 |  |  | 2024-11-22 | 2024-11-20 |  | Watertank | 25m pBTS | 24 | Add R8894E M1821 x2, Dismantal R8882-GUL1812x1+R8862A S1800(B6A)x1 | 0 | 0
3045C6 | pBTS Kampung Bugis (KM) | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2024 Q3 | AD | GTSB | 14.0 TSSR Not Required (Reuse Existing BBU/RRU) | AAU Cannot Install-Change MM to BI¦pBTS loading issue,AAU cannot install | 2023-10-18 | 2023-10-23 |  | 2023-10-31 |  | Under Approval |  |  |  |  | Celcom Digi_RAN-GTSB-TSS-Sabah-20231019 | DU00002862197 |  |  | 2025-06-23 | 2025-06-17 |  | Tower | 25m pBTS | 18M | Reuse Existing RRU | 0 | 0
3452C | eMOS KLIA Eng Complex | Central |  | Modernization |  | 2024 Additional | AI | GTSB | 4.6 TSSR Approved |  | 2024-07-02 | 2024-07-05 |  | 2024-07-11 |  | Under Approval | 2024-09-30 | 2024-10-01 | E//Razif | 2024-10-01 | 0920CD-Central-GTSB-BOQ Template (old contract) | DU00002862198 |  |  | 2024-11-06 | 2024-11-05 |  | Watertank | 20m eMOS | 16m | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
9679B | Kampung Landeh | Sarawak |  | Modernization |  | 2025 Q1 | SM | Magicell | 4.6 TSSR Approved |  | 2023-10-13 | 2023-10-16 |  | 2023-10-23 |  | Closed | 2023-10-24 | 2023-11-15 | E//Syahriani | 2025-03-05 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231016 | DU00002862199 |  |  | 2025-03-26 | 2025-03-17 |  | Monopole | 30m Lampole | 30M | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3 | 0 | 0
3317A4 | pBTS Taman Industri Selesa Jaya (KM) | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  |  | 14.2 Drop (Done Survey) | AAU Cannot Install-Change MM to BI¦NOK,pBTS site,can not install more antenna;Need to change to bi-sector | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002862200 | BAU_S2_Change MM to BI_loading issue_Digi OB | [5 empty] | 25m pBTS |  |  | 0 | 34
9988A | Pekan Beratok | Sarawak |  | Modernization |  | 2025 Q1 | AI | Datasco | 4.6 TSSR Approved |  | 2023-10-16 | 2023-11-27 |  | 2025-02-10 |  | Closed | 2025-02-17 | 2025-03-10 | E//Yanie | 2025-03-05 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231017 | DU00002862201 |  |  | 2025-03-11 | 2025-03-06 |  | Monopole | 60m 4 Legged Tower | 40 | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8862A S2100(A6A)x3+R8862A S1800(B6A)x3 | 0 | 0
9986A | Taman Uni Sentral | Sarawak |  | Modernization |  | 2024 Q2 | SH | Magicell | 4.6 TSSR Approved |  | 2023-10-07 | 2023-10-10 |  | 2023-10-24 |  | Closed | 2023-12-15 | 2023-12-20 | E//Hannah | 2023-12-15 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231009 | DU00002862202 |  |  | 2023-12-20 | 2023-11-28 |  | Monopole | 30M Pole | 30M | Add R8862A S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8862A S1800(B6A) x2+R8862A S2100(A6A) x2+R8862A S2601(A6A) x1+R8894E M1821(A8A) x2 | 12 | 0
1420C | The Reeds | Central |  | Site Out (Modernization) | Modernization->Site Out->Replacement, Site Out (Modernization) | 2024 Q3 | SS | GTSB | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2025-07-15 |  | 2025-06-30 |  |  | To be Submitted |  |  |  |  | SQ202506170074 | DU00002862203 |  |  |  |  | 2025-08-05 |  | 18m Lampole |  |  | 0 | 0
1546C | Taman Sri Endah Sl | Central |  | Modernization |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-11-06 | 2023-11-10 |  | 2024-04-03 |  | Closed | 2024-04-15 | 2024-05-27 | E//Sumitra | 2024-05-27 | CelcomDigi_RAN_Datasco_TSS_Central_20231113 | DU00002862204 |  |  | 2024-05-11 | 2024-05-09 |  | Lampole | 18M Lampole | 18 | Add R8862A S9000 x3+R8894E M1821 x1+R8854 S2600 x1,Dismantle | 0 | 1
1314C | Lestari Apartment | Central |  | Modernization |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-08 | 2023-11-10 |  | 2023-11-23 |  | Closed | 2024-03-27 | 2024-04-15 | E//Sumitra | 2024-04-05 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231113 | DU00002862205 |  |  | 2024-05-14 | 2024-05-08 |  | Lampole | 45M 3 legged Tower | 18m | Add R8862A S9000 x3+R8894E M1821 x1+R8854 S2600 x1,Dismantle | 0 | 3
1317C | Jalan Permaisuri 5 | Central |  | Modernization |  | 2024 Q3 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-11-18 | 2023-11-20 |  | 2024-03-25 |  | Closed | 2024-03-29 | 2024-04-05 | E//Sumitra | 2024-04-05 | CelcomDigi_RAN_CCSMY_TSS_Central_20231119 | DU00002862206 |  |  | 2024-05-10 | 2024-05-09 |  | Lampole | Land site | 19M | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
3512A7 | pBTS Palm City LD | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2024 Q3 | AD | GTSB | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦pBTS loading issue,AAU cannot install | 2023-10-18 | 2023-10-19 |  | 2023-10-23 |  | Under Approval | 2023-10-23 | 2025-05-27 | E//Hannah | 2025-02-19 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231019 | DU00002862207 |  |  | 2025-03-04 | 2025-02-22 |  | Tower | 25m pBTS | 24M | Add R8862A S9000x3 | 0 | 2
4306D | Changkat Jering (REL) | Northern |  | Modernization |  | 2024 Q2 | BY | GCI | 4.6 TSSR Approved |  | 2023-10-10 | 2023-10-18 |  | 2024-01-09 |  | Closed | 2024-01-12 | 2024-01-17 | E//Hazida | 2024-01-16 | Celcom Digi_RAN-GCI-TSS-Northern-20231012-0057 | DU00002862208 |  |  | 2024-04-05 | 2024-04-01 |  | Tower | 60m 4 Legged Tower | 60m | Add R8894E M1821 x4+R8854 S2600 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R8862A S2601(A6A) x1 |  | 1
1403C | Sunway Velocity (REL) | Central |  | Modernization |  | 2024 Q3 | AI | YPTT | 4.6 TSSR Approved |  | 2024-05-31 | 2024-06-04 |  | 2024-06-13 |  | Closed | 2024-06-20 | 2024-06-26 | E//Sumitra | 2024-06-26 | BOQ_Celcom Digi_RAN-YPTT-Standard PR TSS-20240605 | DU00002862209 |  |  | 2024-07-13 | 2024-07-13 |  | Lampole | Building | 18 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
1401C | Kg Wira Jaya (REL) | Central |  | Modernization |  | 2024 Q1 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-08 | 2023-11-10 |  | 2024-01-04 |  | Closed | 2024-04-05 | 2024-04-05 | E//Kok Keen | 2024-04-05 | CelcomDigi_RAN_GTSB_TSS_Central_20231113 | DU00002862210 |  |  | 2024-02-28 | 2024-02-22 |  | Lampole | 18m Lampole | 18M | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3
7950A | Tg.Bt.Marudu-Pingan-Pingan | Sabah |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q4 |  | GTSB | 14.0 TSSR Not Required (Reuse Existing BBU/RRU) |  | 2025-02-25 | 2025-04-07 |  |  |  | To be Submitted |  |  |  |  | SQ202501030028 - GTSB | DU00002862211 | [6 empty] | Tower | 75 | Reuse Existing RRU
2785B9 | pBTS Taman Desa Pakatan | Northern |  | Site Out (Modernization) | Modernization->Site Out->Replacement, Site Out (Modernization) | 2024 Q2 | SM | GTSB | 4.6 TSSR Approved | ¦ 0213 - TP rejected as there is no more pBTS at site as stated in your TP. The new Site ID for this site is 4677D. | 2023-10-18 | 2023-10-31 |  | 2024-01-13 |  | Rectificating | 2024-01-15 | 2024-01-23 | E//Hazida | 2024-01-21 | Celcom Digi_RAN-GTSB-TSS-Northern-20231019-0052 | DU00002862212 | [5 empty] | Tower | 24m PBTS | 24m
1580B13 | pBTS Taman Fajar Sandakan (KM) | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2024 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2024-01-31 | 2024-11-28 |  | 2024-12-06 |  | Under Approval | 2024-12-06 | 2024-12-10 | E//Hannah | 2024-12-09 | Celcom Digi_RAN-GTSB-TSS-Sabah-20240204 | DU00002862213 |  |  | 2025-02-14 | 2025-02-11 |  | Monopole | 25m pBTS | 19 | Add R8894E M1821x3, Dismantle R8882 S1800(B)x1+R8882 S1800B(B6B)x2 | 0 | 0
1564B15 | pBTS Taman Hijrah | Northern |  | Site Out (Modernization) | Modernization->On Hold->Site Out (Modernization) | 2024 Q4 |  | CCSMY | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2023-10-17 | 2023-11-02 | [8 empty] | Celcom Digi_RAN-CCSMY-TSS-Northern-20231018-0057 | DU00002862214 | [5 empty] | Tower | 25m pBTS | 28
3371A5 | pBTS Masjid Al Mursyid Guring | Northern |  | Site Out (Modernization) | Modernization->On Hold->Site Out->Replacement, Site Out (Modernization) | 2026 |  | YPTT | 14.2 Drop (Done Survey) |  | 2023-10-26 | 2023-11-08 |  |  |  | To be Submitted |  |  |  |  | Celcom Digi_RAN-YPTT-TSS-Northern-20231028-0040 | DU00002862215 | [5 empty] | Watertank | 25m pBTS | 24
3505A2 | pBTS Jalan Siakap | Northern |  | Remote MOCN | Modernization->On Hold->Remote MOCN | 2025 Q1 | SM | GTSB | 4.6 TSSR Approved |  | 2023-10-10 | 2023-10-12 |  | 2023-10-23 |  | Rectificating | 2023-10-25 | 2023-10-30 | E//Hazida | 2023-10-27 | Celcom Digi_RAN-GTSB-TSS-Northern-20231011-0046 | DU00002862216 | [5 empty] | Tower | 25m pBTS | 26 | Reuse Existing RRU | 0 | 0
1574C | LRT Miharja | Central |  | Modernization |  | 2024 Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2023-11-22 | 2023-11-29 |  | 2024-03-21 |  | Closed | 2024-03-22 | 2024-03-26 | E//Sumitra | 2024-03-26 | CelcomDigi_RAN_Magicell_TSS_Central_20231126 | DU00002862217 |  |  | 2024-08-24 | 2024-08-21 |  | In-Building System | LRT | 3 | Add R9264H M901821 x2,Dismantle R8894E M1821(A8A) x2 | 0 | 0
9721B | Jalan Mulu | Sarawak |  | Modernization |  | 2025 Q1 | AI | Datasco | 4.6 TSSR Approved |  | 2024-01-17 | 2024-03-20 |  | 2025-01-10 |  | Under Approval | 2025-01-17 | 2025-02-07 | E//Hannah | 2025-02-14 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20240124 | DU00002862218 |  |  | 2025-04-04 | 2025-03-24 |  | Lampole | In-Building System | 30 | Add R8852E S9000x4 | 0 | 0
4442D | SK Jejawi | Northern |  | Modernization |  | 2024 Q4 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-10-19 | 2023-10-25 |  | 2024-04-19 |  | Closed | 2024-04-25 | 2024-04-26 | E//Ajay | 2024-04-26 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231020-0059 | DU00002862219 |  |  | 2024-05-14 | 2024-05-11 |  | Monopole | 30M Lampole | 34 | Add R8862A S9000 x3+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x1 | 2 | 0
4410D | Kampung Teduh | Northern |  | Modernization | Modernization | 2026 | HW | CCSMY | 4.6 TSSR Approved |  | 2023-10-25 | 2023-10-27 |  | 2025-04-11 |  | Under Approval | 2025-11-09 | 2025-12-08 | E//Hazida | 2025-11-13 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231026-0062 | DU00002862220 |  |  | 2025-12-18 | 2025-12-03 |  | Tower | 45M Monopole | 46m | Add R8852E S9000x3
1568B11 | pBTS Kg Nyior Chabang | Northern |  | Modernization | Modernization->On Hold->Modernization | 2025 Q2 | HW | GTSB | 4.6 TSSR Approved |  | 2025-03-14 | 2025-03-20 |  | 2025-03-25 |  | Under Approval | 2025-03-26 | 2025-05-02 | E//Hazida | 2025-04-30 | S1MY2024071003WBF1-2046 | DU00002862221 |  |  | 2025-04-16 | 2025-04-10 |  | Tower | 25m pBTS | 24M | Add R8894E M1821x3, Dismantle R8882-GUL1812x3 | 0 | 0
3047C5 | pBTS Surau At Taqwa Ampang | Central |  | Modernization | Modernization->On Hold->Modernization | 2024 Q4(single site MOCN)-L2126 SSM | AI | GTSB | 4.6 TSSR Approved |  | 2023-12-06 | 2023-12-08 |  | 2025-05-30 |  | Closed | 2025-06-10 | 2025-07-17 |  | 2026-04-17 | CelcomDigi_RAN_GTSB_TSS_Central_20231208 | DU00002862222 |  |  | 2025-06-17 | 2025-06-17 |  | Tower | 25m pBTS | 24M | Add R9224E M1821x4, Dismantle R8854D S2100(A4A)x4+R8862A S1800(B6A)x4 | 0 | 0
3509A7 | pBTS Bagan Serai | Northern |  | Modernization | Modernization->On Hold->Remote MOCN->Modernization | 2026 | AI | CCSMY | 4.6 TSSR Approved |  | 2023-10-22 | 2023-10-30 |  | 2026-03-30 |  | Under Approval | 2026-03-31 | 2026-04-06 |  | 2026-04-06 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231022-0060 | DU00002862223 |  |  | 2026-04-28 | 2026-04-20 |  | Tower | 25m pBTS | 25M | Add R9264M M1821x3, Dismantle R8882-GUL1812x2+R8862A S1800(B6A)x1R8862A S2100(A6A)x3
3370A11 | pBTS IOI Unicon Deployment(BB) | Sabah |  | Site Out (Modernization) | Modernization->On Hold->Modernization | 2024 Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-11-20 | 2023-11-28 |  | 2025-01-24 |  | Under Approval | 2025-02-03 | 2025-02-18 | E//Yanie | 2025-02-18 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231126 | DU00002862224 | Remarks: Solution TSSR/BOM Changed |  | 2026-01-12 | 2025-02-21 |  | Watertank | 24m PBTS | 24 | Reuse Existing RRU | 0 | 0
4361D | Tanjung Seberang (REL) | Northern |  | Modernization |  | 2024 Additional | SM | GTSB | 4.6 TSSR Approved |  | 2024-12-05 | 2024-12-09 |  | 2024-12-12 |  | Rectificating | 2024-12-13 | 2024-12-16 | E//Hazida | 2024-12-15 | 1911CD-Northern-TSS-BOQ Template(new contract)_GTSB | DU00002862225 |  |  | 2025-01-04 | 2025-01-02 |  | Tower | 30M RDS | 31M | Add R8852E S9000 x3 | 0 | 0
4385D | Chandan Puteri 2 (REL) | Northern |  | Modernization | Modernization | 2026 | HW | CCSMY | 4.6 TSSR Approved |  | 2023-10-28 | 2023-11-01 |  | 2025-04-09 |  | Under Approval | 2025-11-09 | 2025-12-29 | E//Hazida | 2025-11-13 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231028-0063 | DU00002862226 |  |  | 2025-11-30 | 2025-11-19 |  | Tower | 30M Lampole | 31 | Add R8852E S9000x3
4052B7 | pBTS Kg Sg Protan | Northern |  | Site Out (Modernization) | Modernization->Site Out->Replacement, Site Out (Modernization) | 2026 |  | GCI | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862227 | [6 empty] | 25m pBTS
3439B14 | pBTS Ulu Basir & Changkat Mentri Estate Office | Northern |  | Modernization | Modernization->On Hold->Modernization | 2026 | ZA | GCI | 4.6 TSSR Approved |  | 2023-11-04 | 2023-11-08 |  | 2023-11-30 |  | Under Approval | 2023-12-04 | 2023-12-15 | E//Hazida | 2023-12-14 | Celcom Digi_RAN-GCI-TSS-Northern-20231106-0072 | DU00002862228 | Remarks: Solution TSSR/BOM Changed |  | 2026-03-19 | 2026-03-13 |  | Watertank | 24m PBTS | 25 | Add R8862A S9000x3+R8894E M1821x3+R8862A S2601 x3, Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3
1704C | OUG Parklane SL (REL) | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved | 29/01 RRU propose inside cabinet, 3 RRU on top, have temperature alarm from technical team | 2023-11-27 | 2023-11-29 |  | 2023-12-19 |  | Closed | 2023-12-26 | 2024-01-03 | E//Sumitra | 2024-01-03 | CelcomDigi_RAN_GTSB_TSS_Central_20231201 | DU00002862229 |  |  | 2024-04-22 | 2024-04-20 |  | Lampole | Land site | 18m | Add R8862A S9000 x3+R8854E S1800 x3+R9224E M1821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
3171B4 | pBTS Sandakan Mile 8 | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2024 Q4(single site MOCN)-L2126 SSM | SM | Futong | 14.0 TSSR Not Required (Reuse Existing BBU/RRU) | 0219 - E//Hannah - Requested full band with 1 sector bisector, emailed to ZTE planning. | 2024-03-14 | 2024-03-20 |  | 2025-01-14 |  | Under Approval | 2025-01-15 |  | E//Hannah |  | Celcom Digi_RAN-Futong-TSS-Sabah-20240324 | DU00002862230 |  |  | 2025-02-14 | 2025-02-11 |  | Watertank | 25m pBTS | 25 | Reuse Existing RRU | 0 | 0
2690C | PJH New Building | Central |  | Modernization |  | 2024 Q3 | CR | GTSB | 4.6 TSSR Approved |  | 2024-06-20 | 2024-06-25 |  | 2024-07-31 |  | Under Approval | 2024-07-02 | 2024-07-24 | E//Razif | 2024-07-24 | 0626Central-GTSB-BOQ Template (template) | DU00002862231 |  |  | 2024-08-01 | 2024-07-20 |  | In-Building System | IBC | 4 | Add R8862A S9000 x1+R9264H M901821 x3+R8862A S2601 x1+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x4 | 1 | 0
1558B6 | pBTS Hospital Cyberjaya | Central |  | Site Out (Modernization) | Modernization->On Hold->Site Out->Replacement, Site Out (Modernization) | 2024 Q3 |  | Magicell | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2024-01-03 | 2024-01-10 | [8 empty] | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240108 | DU00002862232 | [5 empty] | Tower | PBTS | 24 | Add R8862A S9000x3 | 0 | 0
3158B3 | pBTS Surau Desa Anggerik (KM) | Northern |  | Modernization | Modernization->On Hold->Modernization | 2026 | HW | GCI | 4.6 TSSR Approved |  | 2023-10-19 | 2023-10-23 |  | 2023-10-31 |  | Under Approval | 2025-11-27 | 2025-12-29 | E//Hazida | 2025-12-01 | Celcom Digi_RAN-GCI-TSS-Northern-20231023-0064 | DU00002862233 |  |  | 2026-01-14 | 2025-12-31 |  |  | 24M PBTS | 25 | Add R8852E S9000 x3 R8894E M1821x3, Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3
3422B2 | Laman View | Central |  | Modernization | Modernization->On Hold->Modernization | 2024 Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2024-01-12 | 2024-01-15 |  | 2024-11-12 |  | Rectificating | 2024-11-14 | 2024-11-15 | E//Razif | 2024-11-15 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240115 | DU00002862234 |  |  | 2024-11-23 | 2024-11-21 |  | Tower | 25M PBTS | 25m | Add R8894E M1821x3, Dismantle R8882 S1800(B)x3+R8862A S2100(A6A)x3 | 0 | 0
3495A2 | pBTS Surau RPA Arau (KM) | Northern |  | Remote MOCN | Modernization->On Hold->Remote MOCN | 2024 Q4 |  | YPTT | 3.4 SOW/Solution On Hold |  | 2023-12-05 | 2023-10-30 |  |  |  | To be Submitted |  |  |  |  | Celcom Digi_RAN-YPTT-TSS-Northern-20231225-0047 | DU00002862235 | [5 empty] | Watertank | 24M PBTS | 26 | Add R8852E S9000x3+R8894E M1821x3,Dismantle R8862A S1800(B6A)x2+R8862A S2100(A6A)x3+R8882 S1800(B)x1 | 0 | 0
4066B19 | pBTS Bandar Cyber (KM) | Northern |  | Site Out (Modernization) | Modernization->Site Out->Replacement, Site Out (Modernization) | 2024 Q2 |  | CCSMY | [SiteOut]- 1.0 Pending Survey - Subcon | ¦ 0222 - CD Raju: Yes you can proceed to 4439D Bandar Cyber that belong to Riyyalcom. | [5 empty] | To be Submitted | [5 empty] | DU00002862236 | [6 empty] | PBTS
3160B8 | pBTS Brainy Bunch Raudhah City (EB) | Central |  | Site Out (Modernization) | Modernization->On Hold->Modernization->Site Out->Replacement, Site Out (Modernization) | 2024 Q3 | AI | Magicell | 4.6 TSSR Approved |  | 2024-01-03 | 2024-01-10 | 2025-08-12 | 2025-01-15 |  | Closed | 2025-01-16 | 2025-01-16 | E//Razif | 2026-04-17 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240108 | DU00002862237 | [5 empty] | Tower | PBTS | 24 | Reuse Existing RRU | 0 | 0
9682C | Berangan Height | Sarawak |  | Modernization |  | 2024 Q2 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-10-05 | 2023-10-06 |  | 2023-10-13 |  | Closed | 2023-10-13 | 2023-11-03 | E//Hannah | 2023-11-02 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231006 | DU00002862238 |  |  | 2023-11-23 | 2023-11-20 |  | Monopole | In-Building System | 30 | Add R8852E S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 23 | 0
9685C | SJK Chung Hua Batu 35 Tarat | Sarawak |  | Modernization |  | 2025 Q3 | SH | Magicell | 4.6 TSSR Approved |  | 2023-10-10 | 2023-10-12 |  | 2023-10-23 |  | Closed | 2023-10-24 | 2023-11-06 | E//Hannah | 2023-11-06 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231013 | DU00002862239 |  |  | 2023-12-12 | 2023-11-20 |  | Monopole | In-Building System | 30 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
9697C | Jln Muhibbah | Sarawak |  | Modernization |  | 2027 | AI | AllStar | 4.6 TSSR Approved |  | 2023-10-09 | 2023-11-08 |  | 2025-05-23 |  | Under Approval | 2025-11-04 | 2026-01-22 | E//John | 2025-11-06 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20231009 | DU00002862240 | [5 empty] | Pole | In-Building System | 30 | Add R8852E S9000x3 | 0 | 0
4454D | PCMH (REL) | Northern |  | Modernization |  | 2024 Q2 |  | CCSMY | 4.6 TSSR Approved | ¦ 0315 - Revised TSSR submitted ¦ 0227 - Space constraint, revise d BOM to use AEKY4 and relocate UBR to top for S3. | 2023-10-18 | 2023-10-20 |  | 2024-01-08 |  | Closed | 2024-01-09 | 2024-01-11 |  | 2024-01-10 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231019-0058 | DU00002862241 |  |  | 2024-03-06 | 2024-02-20 |  | Pole | Lampole | 35 | Add R8862A S9000 x3+R9224E M1821 x1+R8854 S2600 x1,Dismantle R8862A S2601(A6A) x1 |  | 3
Q00222 | Q115A_Q00222OD_CB_KGSTINGGANG | Sarawak | 9278K | Swap | Swap->On Hold->Swap | 2024 Q2 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-12-23 | 2024-01-12 |  | 2024-01-17 |  | Rectificating | 2024-01-17 | 2024-01-18 | CD//John | 2024-01-18 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231231 | DU00002862242 |  | 1701 Wrong pano | 2025-05-14 | 2025-05-07 |  | Tower | TOWER | 78M | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle | 0 | 0
2682C | Tmn Orkid Desa (REL) | Central |  | Modernization |  | 2024 Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2024-03-11 | 2024-03-20 |  | 2024-03-22 |  | Closed | 2024-03-25 | 2024-03-26 | E//Sumitra | 2024-03-26 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240316 | DU00002862243 |  |  | 2024-05-31 | 2024-05-28 |  | Lampole | Land site | 26M | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
4528D | Taman Pelangi Teluk Intan | Northern |  | Modernization |  | 2025 Q1 | SM | CCSMY | 4.6 TSSR Approved |  | 2025-01-22 | 2025-02-04 |  | 2025-02-20 |  | Under Approval | 2025-02-21 | 2025-02-27 | E//Hazida | 2025-02-27 | SQ202501030037 - CCSMY | DU00002862244 | Remarks: Solution TSSR/BOM Changed |  | 2025-03-29 | 2025-03-27 |  | Monople Tree | 30M Monopole | 30M | Add R8852E S9000x3+R9264M M1821x2+A9732 M1821x1, Dismantle R8894E M1821(A8A)x3 | 2 | 0
3452B12 | pBTS Masjid Bagan Datoh | Northern |  | Modernization | Modernization->On Hold->Modernization | 2024 Additional | AD | GCI | 4.6 TSSR Approved |  | 2025-01-15 | 2025-01-17 |  | 2025-02-06 |  | Under Approval | 2025-02-14 | 2025-03-09 | E//Hazida | 2025-02-25 | SQ202504180288-GCI | DU00002862245 | Remarks: Solution TSSR/BOM Changed |  | 2025-03-03 | 2025-03-03 |  | Tower | PBTS | 30m | Reuse Existing RRU | 0 | 0
Q00293 | Q133A_Q00293OD_CB_TMBALINGIAN | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | AD | Trintel | 4.6 TSSR Approved |  | 2025-05-27 |  | 2025-05-28 |  | 2025-06-02 |  | 2025-06-04 |  | E//John | 2025-06-09 | SQ202505020084-Trintel | DU00002862246 |  |  |  |  | 2025-10-09 |  | TOWER
Q00314 | Q125A_Q00314OD_LONGTUMA | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | AD | CCSMY | 4.6 TSSR Approved |  | 2025-06-05 |  | 2025-08-11 |  | 2025-08-12 | To be Submitted | 2025-08-21 |  | E//John | 2025-10-16 | SQ202506060165-CCSMY | DU00002862247 |  |  |  |  | 2025-10-22 |  | TOWER
Q00323 | Q125A_Q00323OD_CB_TMSIANGSIANG | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | AD | CCSMY | 4.6 TSSR Approved |  | 2025-06-06 |  | 2025-08-11 |  | 2025-08-12 |  | 2025-08-25 | 2025-10-17 | CD//John | 2025-08-26 | SQ202506060165-CCSMY | DU00002862248 |  |  |  |  | 2025-11-27 |  | TOWER
3469C5 | pBTS Taman Indah Jaya | Central |  | Modernization | Modernization->On Hold->Modernization | 2024 Q3 | XH | GTSB | 4.6 TSSR Approved |  | 2023-11-24 | 2023-11-28 |  | 2023-12-01 |  | Closed | 2023-12-05 | 2023-12-12 | E//Kok Keen | 2023-12-08 | CelcomDigi_RAN_GTSB_TSS_Central_20231126 | DU00002862249 | Remarks: Solution TSSR/BOM Changed |  | 2024-11-23 | 2024-11-21 |  | Watertank | PBTS | 27 | Reuse exisiting RRU | 0 | 0
Q00329 | Q130A_Q00329OD_LONGLAMA | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | NA | Trintel | 4.6 TSSR Approved | Reject. Pls confirm this argus cabinet belong to celcom or not ? Is there argus batttery here? | 2025-03-04 |  | 2025-04-07 |  | 2025-04-12 |  | 2025-05-02 |  | CD//John | 2025-05-04 | SQ202502050142-Trintel | DU00002862250 |  | No MW info |  |  | 2025-06-19 |  | TOWER
1046C | Bkt Kajang Baru (REL) | Central |  | Modernization |  | 2024 Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-19 | 2024-02-05 |  | 2024-05-14 |  | Closed | 2024-06-27 | 2024-07-16 | E//Sumitra | 2024-07-16 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240128 | DU00002862251 |  |  | 2024-07-25 | 2024-07-25 |  | Monopole | Land site | 25m | Add R8852E S9000 x3+R9224E M1821 x1+R8854 S2600 x1,Dismantle | 0 | 3
Q00369 | Q128A_Q00369OD_KGPUEH | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2024 Q2 | HW | South Pacific | 4.6 TSSR Approved |  | 2024-02-06 |  |  |  | 2024-02-07 |  | 2025-02-19 | 2025-05-02 | CD//John | 2025-02-27 | S1MY2021071012WBF1-183-South Pac | DU00002862252 |  |  |  |  | 2025-07-29 |  | TOWER
2684A17 | pBTS Telupid Town | Sabah |  | Modernization |  | 2024 Q4 | MS | YPTT | 4.6 TSSR Approved |  | 2024-02-06 | 2024-02-08 |  | 2024-02-09 |  | Closed | 2024-02-13 | 2024-02-21 |  | 2024-02-21 | Celcom Digi_RAN-YPTT-Standard PR TSS-Sabah-20240213 | DU00002862253 |  |  | 2024-03-06 | 2024-02-29 |  | Watertank | 24M PBTS | 26 | Add R8852E S9000 x3,Dismantle | 0 | 0
Q00466 | Q138A_Q00466OD_CB_RHMAWAR | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | HW | Trintel | 4.6 TSSR Approved |  | 2025-05-22 |  | 2025-05-22 |  | 2025-05-26 |  | 2025-05-26 | 2025-10-28 | E//John | 2025-05-27 | SQ202505020084-Trintel | DU00002862254 |  |  |  |  | 2025-09-28 |  | TOWER
3055C4 | pBTS Unico 2 (EB) | Sabah |  | Remote MOCN | Modernization->On Hold->Remote MOCN | 2024 Q4(single site MOCN)-L2126 SSM |  | GTSB | 4.1 Pending TSSR Submission - Subcon |  | 2023-12-29 | 2023-12-29 | [8 empty] | Celcom Digi_RAN-GTSB-TSS-Sabah-20231231 | DU00002862255 | [5 empty] | Watertank | 24M PBTS | 24m | Reuse exisiting RRU | 0 | 0
1678H | 99 Speedmart PK Bdr Behrang | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862256 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
Q00494 | Q125A_Q00494OD_KUALALAWAS | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | AD | DATASCO | 4.6 TSSR Approved |  | 2025-04-28 |  | 2025-05-20 |  | 2025-06-06 |  | 2025-06-12 | 2026-01-06 | E//John | 2025-06-13 | SQ202502050346-Datasco | DU00002862257 |  |  |  |  | 2025-10-22 |  | TOWER
Q00515 | Q131A_Q00515OD_KUALAIGAN | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | AD | Trintel | 4.6 TSSR Approved |  | 2025-05-27 |  | 2025-05-28 |  | 2025-06-02 |  | 2025-06-04 | 2025-12-15 | E//John | 2025-06-09 | SQ202505020084-Trintel | DU00002862258 |  |  |  |  | 2025-11-14 |  | TOWER
4259H | 99 Speedmart PK Bdr Universiti | Northern |  | MOCN As-Is |  | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862259 | [6 empty] | Small Cell
Q00577 | Q126A_Q00577OD_BTBIAH | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | AI | DATASCO | 4.6 TSSR Approved |  | 2025-04-28 |  | 2025-05-06 | 2025-05-26 | 2025-05-27 | Under Approval | 2025-05-27 |  | CD//John | 2025-10-07 | SQ202502050346-Datasco | DU00002862260 |  | Pls provide FE drawing |  |  | 2025-08-27 |  | TOWER
1255H | 99 Speedmart AMBER BUSINESS PLAZA | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862261 | [6 empty] | Small Cell
Q00679 | Q128A_Q00679OD_KGSTUNGGANG | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2024 Q2 | HW | South Pacific | 4.6 TSSR Approved |  | 2024-02-06 |  |  |  | 2024-02-07 |  | 2025-02-19 | 2025-05-02 | CD//John | 2025-03-04 | S1MY2021071012WBF1-183-South Pac | DU00002862262 |  |  |  |  | 2025-08-28 |  | TOWER
1254H | 99 Speedmart BDR SRI PERMAISURI 1 | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862263 | [6 empty] | Small Cell
1309H | 99 Speedmart TMN BANGSAR | Central |  | MOCN As-Is |  | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862264 | [6 empty] | Small Cell
1263H | 99 Speedmart JLN PUDU ULU | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862265 | [6 empty] | Small Cell
1419H | 99 Speedmart TMN DESA PETALING | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862266 | [6 empty] | Small Cell
4236H | 99 Speedmart PK Jalan Bagan Datoh | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862267 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
1250H | 99 Speedmart ALAM JAYA | Central |  | MOCN As-Is |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862268 | [6 empty] | Small Cell
4208H | 99 Speedmart PK Jln Panggung Wayang Bidor | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862269 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
1408H | 99 Speedmart BDR SRI PERMAISURI 2 | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862270 | [6 empty] | Small Cell
4170H | 99 Speedmart PK JLN PASAR TELUK INTAN | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862271 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
1279H | 99 Speedmart TMN PETALING UTAMA | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862272 | [6 empty] | Small Cell
1394H | 99 Speedmart TMN CONNAUGHT | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862273 | [6 empty] | Small Cell
4189H | 99 Speedmart PK LANGKAP | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862274 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
4177H | 99 Speedmart PK MEDAN NIAGA LAGENDA | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862275 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
4247H | 99 Speedmart PK Pekan Baru Telok Intan | Northern |  | MOCN As-Is |  | 2026 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862276 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
4186H | 99 Speedmart PK PEKAN SLIM RIVER | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862277 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
4242H | 99 Speedmart PK Pp Air Kuning | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862278 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
7135H | 99 Speedmart Kota Marudu Town | Sabah |  | MOCN As-Is |  | 2025 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862279 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
4221H | 99 Speedmart PK Pusat Bdr Baru Bagan Serai | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862280 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
4250H | 99 Speedmart PK Slim River | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862281 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
1143H | V Mobile Communications | Central |  | Site Out (Modernization) | MOCN As-IS->Site Out->Site Out (Modernization) | 2024 Q3 |  | GTSB | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2025-07-15 |  | 2025-06-30 |  |  | To be Submitted |  |  |  |  | SQ202506170074 | DU00002862282 |  |  |  |  | 2025-08-05 |  | Small Cell
1190H | 99 Speedmart BDR PUCHONG JAYA 2 | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862283 | [6 empty] | Small Cell
1192H | 99 Speedmart PANDAN JAYA 3 | Central |  | MOCN As-Is |  | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862284 | [6 empty] | Small Cell
1232H | 99 Speedmart TMN MIDAH 1 | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862285 | [6 empty] | Small Cell
1242H | 99 Speedmart TMN MULIA | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862286 | [6 empty] | Small Cell
1249H | 99 Speedmart TMN BUNGA CEMPAKA | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862287 | [6 empty] | Small Cell
1253H | 99 Speedmart DATARAN MESTIKA | Central |  | Site Out (Modernization) | MOCN As-Is->Site Out->Site Out (Modernization) | 2024 Q3 |  | GTSB | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2025-07-15 |  | 2025-06-30 |  |  | To be Submitted |  |  |  |  | SQ202506170074 | DU00002862288 |  |  |  |  | 2025-08-05 |  | Small Cell
1273H | 99 Speedmart TMN LEMBAH MAJU | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862289 | [6 empty] | Small Cell
1285H | 99 Speedmart SRI MANJA 1 | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862290 | [6 empty] | Small Cell
1288H | 99 Speedmart PANDAN UTAMA | Central |  | MOCN As-Is |  | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862291 | [6 empty] | Small Cell
1293H | 99 Speedmart DESA BUSINESS PARK | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862292 | [6 empty] | Small Cell
1295H | 99 Speedmart SUNWAY MAS | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862293 | [6 empty] | Small Cell
1302H | 99 Speedmart PJ SS 2 (1) | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862294 | [6 empty] | Small Cell
1307H | 99 Speedmart AMPANG HILIR | Central |  | MOCN As-Is |  | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862295 | [6 empty] | Small Cell
1313H | 99 Speedmart PJ NEW TOWN | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862296 | [6 empty] | Small Cell
1330H | 99 Speedmart KAYU ARA 1 | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862297 | [6 empty] | Small Cell
4253H | 99 Speedmart PK Taman Mesra | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862298 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
4190H | 99 Speedmart PK TMN BIDOR BOTANI | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862299 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
4237H | 99 Speedmart PK Tmn Ceria | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862300 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
4164H | 99 Speedmart PK TMN IMPIANA | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862301 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
4241H | 99 Speedmart PK Tmn Intanova | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862302 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
7040H | 99 Speedmart KIaburi Plaza | Sabah |  | MOCN As-Is |  | 2026 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862303 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
Q01719 | Q132A_Q01719OD_CB_KGBRAYA | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862304 | [6 empty] | TOWER
Q01730 | Q132A_Q01730OD_CB_RHUNDIAN | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862305 | [6 empty] | TOWER
Q01736 | Q132C_Q01736OD_CB_COASTALHIGHWAY | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862306 | [6 empty] | TOWER
Q01775 | Q120A_Q01775OD_CB_JLNDAROTEBAAN | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | AD | Trintel | 4.6 TSSR Approved |  | 2025-05-22 |  | 2025-05-23 |  | 2025-05-28 |  | 2025-05-30 | 2025-12-15 | CD//John | 2025-05-30 | SQ202505020084-Trintel | DU00002862307 |  |  |  |  | 2025-11-14 |  | RAPOLE
1225H | 99 Speedmart KL TMN SERI SENTOSA | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862308 | [6 empty] | Small Cell
1261H | 99 Speedmart PANDAN INDAH 1 | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862309 | [6 empty] | Small Cell
1298H | 99 Speedmart PANDAN MEWAH | Central |  | MOCN As-Is |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862310 | [6 empty] | Small Cell
1305H | 99 Speedmart TMN MALURI | Central |  | MOCN As-Is |  | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862311 | [6 empty] | Small Cell
1306H | 99 Speedmart AMPANG MEWAH | Central |  | MOCN As-Is |  | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862312 | [6 empty] | Small Cell
1243H | 99 Speedmart TMN DAGANG | Central |  | MOCN As-Is |  | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862313 | [6 empty] | Small Cell
1392H | 99 Speedmart ALAM DAMAI 2 | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862314 | [6 empty] | Small Cell
1393H | 99 Speedmart PANDAN PERDANA 1 | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862315 | [6 empty] | Small Cell
1409H | 99 Speedmart LEMBAH JAYA | Central |  | MOCN As-Is |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862316 | [6 empty] | Small Cell
1410H | 99 Speedmart TMN MUDA | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862317 | [6 empty] | Small Cell
1421H | 99 Speedmart AMPANG MULIA | Central |  | MOCN As-Is |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862318 | [6 empty] | Small Cell
1423H | 99 Speedmart TMN MIDAH 2 | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862319 | [6 empty] | Small Cell
1428H | 99 Speedmart PANDAN PERDANA 2 | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862320 | [6 empty] | Small Cell
1436H | 99 Speedmart TMN SEGAR CHERAS | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862321 | [6 empty] | Small Cell
1441H | 99 Speedmart PANDAN PERDANA 3 | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862322 | [6 empty] | Small Cell
1444H | 99 Speedmart PANDAN JAYA 2 | Central |  | MOCN As-Is |  | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862323 | [6 empty] | Small Cell
1482H | 99 Speedmart TMN SEPAKAT INDAH | Central |  | MOCN As-Is |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862324 | [6 empty] | iMacro |  | Remain iMacro AAU
1484H | 99 Speedmart TMN UKAY PERDANA | Central |  | MOCN As-Is |  | 2024 Q1 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862325 | [6 empty] | Small Cell
1513H | 99 Speedmart DESA TUN RAZAK | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862326 | [6 empty] | Small Cell
1514H | 99 Speedmart PANDAN JAYA 1 | Central |  | MOCN As-Is |  | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862327 | [6 empty] | Small Cell
1517H | 99 Speedmart TMN LEN SEN | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862328 | [6 empty] | iMacro
1519H | 99 Speedmart TMN BKT PANDAN | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862329 | [6 empty] | Small Cell
1523H | 99 Speedmart TMN SERI CENDEKIA | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862330 | [6 empty] | Small Cell
7024H | Wisma UCIA LD | Sabah |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862331 | [6 empty] | Small Cell
1525H | Biforst | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862332 | [6 empty] | Small Cell
1574H | 99 Speedmart KG TASIK TAMBAHAN | Central |  | MOCN As-Is |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862333 | [6 empty] | Small Cell
1589H | 99 Speedmart MIDFIELDS SQUARE EAST | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862334 | [6 empty] | Small Cell
1663H | 99 Speedmart Zest Point | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862335 | [6 empty] | Small Cell
4263H | 99 Speedmart PK Tmn Seri Pongsu | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862336 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
4255H | 99 Speedmart PK Tmn Sungkai Perdana | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862337 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
4153H | 99 Speedmart PK TMN UNIVERSITI WALLAGONIA | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862338 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
4276H | 99 Speedmart PK Tmn Orkid | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862339 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
4280H | 99 Speedmart PK PP Sungkai | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862340 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
4281H | 99 Speedmart PK Kuala Gula | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862341 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
1782H | 99 Speedmart Tulin 28 | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862342 | [6 empty] | iMacro
1745H | 99 Speedmart Ampang Avenue | Central |  | Site Out (Modernization) | MOCN As-Is->Site Out->Site Out (Modernization) | 2024 Q4 |  | GTSB | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2025-07-15 |  | 2025-06-30 |  |  | To be Submitted |  |  |  |  | SQ202506170074 | DU00002862343 |  |  |  |  | 2025-08-05 |  | Small Cell
1738H | 99 Speedmart Tmn Pasir Emas | Central |  | MOCN As-Is |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862344 | [6 empty] | iMacro |  | Remain iMacro AAU
1734H | 99 Speedmart Tmn Kosas | Central |  | MOCN As-Is |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862345 | [6 empty] | Small Cell |  | Remain iMacro AAU
1733H | 99 Speedmart Pusat Hentian Kajang | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862346 | [6 empty] | Small Cell
1728H | 99 Speedmart Pantai Dalam | Central |  | MOCN As-Is |  | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862347 | [6 empty] | Small Cell
1724H | 99 Speedmart Tmn Pantai Indah | Central |  | MOCN As-Is |  | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862348 | [6 empty] | iMacro
1720H | 99 Speedmart Bdr Tasik Selatan | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862349 | [6 empty] | Small Cell
1719H | 99 Speedmart Sri Petaling 3 | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862350 | [6 empty] | Small Cell
1716H | 99 Speedmart Tmn Overseas Union | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862351 | [6 empty] | iMacro
1714H | 99 Speedmart Kuchai Lama 1 | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862352 | [6 empty] | iMacro
1708H | 99 Speedmart Pj Sek 17 (1) | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862353 | [6 empty] | Small Cell
4318H | 99 Speedmart PK Tmn Kurau Sentosa | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862354 | [6 empty] | iMacro |  | Remain iMacro AAU | 0 | 0
4317H | 99 Speedmart PK Tmn Golf | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862355 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
4301H | 99 Speedmart PK Tmn Perkasa | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862356 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
7214H | 99 Speedmart Langkon Commercial Centre | Sabah |  | MOCN As-Is |  | 2025 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862357 | [6 empty] | iMacro |  | Remain iMacro AAU | 0 | 0
7177H | 99 Speedmart Kg Nalapak | Sabah |  | MOCN As-Is |  | 2026 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862358 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
7170H | 99 Speedmart Ranau Town | Sabah |  | MOCN As-Is |  | 2025 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862359 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
7169H | 99 Speedmart Kota Marudu Town 2 | Sabah |  | MOCN As-Is |  | 2026 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862360 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
1560H | Jalan Ss 21_39 | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862361 | [6 empty] | Small Cell
7090H | Kien Hong Shopping Centre | Sabah |  | MOCN As-Is |  | 2025 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862362 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
7200H | Kg Muhibah | Sabah |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862363 | [6 empty] | Small Cell
4335H | Bagan Serai DSE Funtech | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862364 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
1810H | Persiaran Impian Gemilang | Central |  | MOCN As-Is |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862365 | [6 empty] | Small Cell |  | Remain iMacro AAU
7245H | iMacro VCKY KM (REL) | Sabah |  | MOCN As-Is |  | 2026 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862366 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
1799H | Pangsapuri Cemara 1 & 2 | Central |  | MOCN As-Is |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862367 | [6 empty] | iMacro |  | Remain iMacro AAU
S00147 | S094A_S00147OD_MENGGARIS | Sabah |  | MOCN Decomm(Dismantle Passive) | MOCN Decomm(Dismantle Passive)->On Hold->MOCN Decomm(Dismantle Passive) | 2025 | AD | YPTT | 4.6 TSSR Approved |  | 2025-10-03 |  | 2025-10-13 |  | 2025-10-14 |  | 2025-10-23 | 2025-10-31 | E//Hannah | 2025-10-29 | SQ202506100836 - YPTT / SQ202507010450 - YPTT | DU00002862368 |  |  |  |  | 2025-10-23 | Tower | TOWER
4239H | 99 Speedmart PK Tmn Desa Bernam Baru | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862369 | [6 empty] | iMacro |  | Remain iMacro AAU | 0 | 0
1640H | 99 Speedmart Tmn Naga Emas | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862370 | [6 empty] | iMacro
1644H | 99 Speedmart Bdr Bkt Mahkota | Central |  | MOCN As-Is |  | 2025 Q1 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862371 | [6 empty] | iMacro |  | Remain iMacro AAU | 0 | 0
1819H | Blok 2 Jalan 2 Kg Tasek Tambahan | Central |  | MOCN As-Is |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862372 | [6 empty] | iMacro |  | Remain iMacro AAU
S00268 | S111A_S00268OD_KGSIMPANGAN | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | HW | YPTT | 4.6 TSSR Approved |  | 2025-03-07 |  | 2025-03-12 |  | 2025-03-13 |  | 2025-03-14 | 2025-10-28 | CD//Sharidah | 2025-03-17 | SQ202504140301 - YPTT | DU00002862373 |  |  |  |  | 2025-08-13 |  | TOWER
1859H | 99 Speedmart Kajnag Utama 3 | Central |  | MOCN As-Is |  | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862374 | [6 empty] | iMacro |  | Remain iMacro AAU
4346H | 99 Speedmart PG Tmn Pekaka | Northern |  | MOCN As-Is |  | 2025 Q1 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862375 | [6 empty] | iMacro |  | Remain iMacro AAU | 0 | 0
S00297 | Q125A_S00297OD_CB_TMSINDUMIN | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | AD | Seri Pancar | 4.6 TSSR Approved | 14/8 - team to submit WNL today // 8/8 Dero award SeriPancar, TM access to reapply today // 7/15- TM sites, team dont have Niosh and request Dero to change subcon | 2025-09-02 |  | 2025-09-09 |  | 2025-09-10 | To be Submitted | 2025-09-17 |  | E//Hannah | 2025-09-26 | SQ202510090252 / SQ202510130961- Seri Pancar | DU00002862376 |  |  |  |  | 2025-11-14 |  | TOWER
4387H | 99 Speedmart PK Behrang Residen | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862377 | [6 empty] | iMacro |  | Remain iMacro AAU | 0 | 0
4381H | 99 Speedmart PK Tmn Piandang Indah | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862378 | [6 empty] | iMacro |  | Remain iMacro AAU | 0 | 0
1898H | 7e Damansara Utama | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862379 | [6 empty] | Small Cell
S00352 | S098A_S00352OD_LADANGSEBERANG | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2024 Q3(single site MOCN) | AD | Futong | 4.6 TSSR Approved |  | 2025-03-07 |  | 2025-03-12 |  | 2025-03-24 |  | 2025-04-13 | 2025-09-10 | CD//Sharidah | 2025-04-22 | SQ202503270530 - Futong | DU00002862380 |  |  |  |  | 2025-08-24 |  | TOWER
4377H | 99 Speedmart PK Tmn Harmoni | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862381 | [6 empty] | iMacro |  | Remain iMacro AAU | 0 | 0
4380H | 99 Speedmart PK Tmn Mawar Lestari | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862382 | [6 empty] | iMacro |  | Remain iMacro AAU | 0 | 0
1905H | Sri Petaling iMacro (REL) | Central |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862383 | [6 empty] | Small Cell
4376H | 99 SM PK TMN LANGKAP | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862384 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
S00481 | S095A_S00481OD_CB_KGSINAPOKAN | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2025 Q1 | AD | DATASCO | 4.6 TSSR Approved |  | 2025-03-06 |  | 2025-04-24 |  | 2025-04-27 | To be Submitted | 2025-05-08 | 2026-04-06 | E//Hannah | 2025-05-09 | SQ202504100595 - Datasco | DU00002862385 |  |  |  |  | 2025-10-01 |  | TOWER
1001Q | G Tower (Q-Cell) | Central |  | MOCN As-Is |  | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862386 | [6 empty] | Qcell
3306Q | Midvalley CAS 2 | Central |  | MOCN As-Is |  | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | E//Nazrul |  |  | DU00002862387 | [6 empty] | Qcell
1002T24 | mBTS Cyber South | Central |  | Modernization | Modernization->On Hold->Modernization | 2024 Q4(single site MOCN)-L26 SSM | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-13 | 2024-01-15 |  | 2025-01-09 |  | Closed | 2025-01-14 | 2025-02-07 | E//Razif | 2025-01-14 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240115 | DU00002862388 | Remarks: Solution TSSR/BOM Changed |  | 2025-02-14 | 2025-02-14 |  | Guide mast | mBTS | 12M | Add R8894E M1821x3, Dismantle R8892E M1821(BAA)x3 | 0 | 0
A00021 | A041A_A00021OD_CB_JENALIK | Northern | 4257K | Swap | Swap | 2026 | HW | GCI | 4.6 TSSR Approved |  | 2023-10-18 | 2023-10-25 |  | 2023-10-31 |  | Under Approval | 2025-11-27 | 2025-12-29 | E//Hazida | 2025-12-01 | Celcom Digi_RAN-GCI-TSS-Northern-20231020-0063 | DU00002862389 |  |  | 2026-04-06 | 2026-04-06 |  |  | TOWER | 60 | Add R8862A S9000x3+R8894E M1821x3+R8862A S2601x3, Dismantle
S00561 | S089A_S00561OD_CB_MILE56 | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-04-15 |  | 2025-04-16 |  | 2025-04-23 | To be Submitted | 2025-04-28 | 2026-04-01 | CD//Sharidah | 2025-04-30 | SQ202504100583 - Futong | DU00002862390 |  |  |  |  | 2025-10-31 |  | TOWER
A00049 | A036B_A00049OD_TMTROLAKSOUTH | Northern | 4259K | Swap |  | 2026 | AI | GCI | 1.1 Pending Survey - Subcon | [6 empty] | To be Submitted |  |  | CD//Zulakmar |  | 1911CD-Northern-TSS-BOQ Template(new contract)_GCI | DU00002862391 | [6 empty] | TOWER |  | Add R8852E S9000 x3+R8894E M1821 x3+R8862A S2601 x3,Dismantle | 0 | 0
A00075 | A036B_A00075OD_TROLAK | Northern | 4262K | Swap |  | 2024 Additional | SM | Magicell | 4.6 TSSR Approved |  | 2024-01-03 | 2024-01-04 |  | 2024-11-25 |  | Rectificating | 2024-11-26 | 2024-11-27 | CD//Zulakmar | 2024-11-27 | Celcom Digi_RAN-Magicell-TSS-Northern-20240108-0008 | DU00002862392 | Remarks: Solution TSSR/BOM Changed |  | 2025-01-18 | 2025-01-03 |  | Tower | TOWER | 76 | Add R8862A S9000 x3+R8894E M1821 x3+R8862A S2601 x3,Dismantle | 0 | 0
A00143 | A037B_A00143OD_BGNDATOK | Northern | 4265K | Swap |  | 2024 Additional | AD | CCSMY | 4.6 TSSR Approved |  | 2024-12-11 | 2024-12-17 |  | 2024-12-19 |  | Under Approval | 2025-01-07 | 2025-02-18 | CD//Zulakmar | 2025-01-16 | SQ202411290550 - CCSMY | DU00002862393 |  |  | 2025-02-08 | 2025-01-26 |  | Tower | TOWER | 70M | Add R8852E S9000 x3+R8894E M1821x3,Dismantle | 0 | 0
S00590 | S104A_S00590OD_CB_BKTKIMANDAU | Sabah | 7296P | Swap | Swap->On Hold->Swap | 2025 Q3 | AD | AllStar | 4.6 TSSR Approved |  | 2023-11-28 | 2024-01-15 |  | 2025-02-16 |  | Under Approval | 2025-03-19 | 2025-05-27 | CD//Sharidah | 2025-03-24 | SQ202501020323 - All Star | DU00002862394 |  |  | 2025-07-06 | 2025-05-25 |  | Tower | TOWER | 45 | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
S00591 | S104A_S00591OD_CB_TIMBUA | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862395 | [6 empty] | TOWER
A00164 | A036A_A00164OD_CB_TNBJOR | Northern | 4266K | Swap |  | 2024 Additional | SM | Magicell | 4.6 TSSR Approved |  | 2023-12-28 | 2024-01-02 |  | 2024-03-29 |  | Rectificating | 2024-11-20 | 2024-11-25 | CD//Zulakmar | 2024-11-25 | 1911CD-Northern-TSS-BOQ Template(new contract)_Magicell | DU00002862396 |  |  | 2024-12-20 | 2024-12-16 |  | In-Building System | BOOM | 6 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle | 0 | 0
A00217 | A039B_A00217OD_ALORPONGSU | Northern | 4527K | Swap |  | 2024 Q3(single site MOCN) | SM | GTSB | 4.6 TSSR Approved |  | 2023-12-04 | 2023-12-06 |  | 2024-04-19 |  | Rectificating | 2024-06-20 | 2024-07-05 | CD//Rohizam | 2024-07-01 | Celcom Digi_RAN-GTSB-TSS-Northern-20231204-0071 | DU00002862397 |  |  | 2024-07-19 | 2024-07-12 |  | Tower | TOWER | 60 | Add R8862A S9000 x3+R9224E M1821 x1+R8862A S2601 x3+A9732 M1821 x2,Dismantle | 12 | 0
A00220 | A036A_A00220OD_LDGBIKAM | Northern | 4267K | Swap |  | 2024 Additional | MS | Magicell | 4.6 TSSR Approved |  | 2024-01-08 | 2024-01-10 |  | 2024-03-29 |  | Closed | 2024-11-20 | 2024-11-25 | CD//Zulakmar | 2024-11-25 | 1911CD-Northern-TSS-BOQ Template(new contract)_Magicell | DU00002862398 |  |  | 2025-03-30 | 2025-03-16 |  | Tower | TOWER | 60 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle | 0 | 0
A00227 | A041A_A00227OD_PDGRENGAS2 | Northern | 4270K | Swap |  | 2027 |  | Magicell | 1.1 Pending Survey - Subcon | [6 empty] | To be Submitted |  |  | CD//Zulakmar |  | SQ202501030105 - Magicell | DU00002862399 | [6 empty] | TOWER |  | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
A00236 | A039B_A00236OD_TMSEMANGGOL | Northern | 4528K | Swap |  | 131 single site mocn | SHA | GCI | 4.6 TSSR Approved |  | 2023-11-15 | 2023-11-16 |  | 2024-08-16 |  | Under Approval | 2026-04-17 | 2024-08-20 | CD//Zulakmar | 2024-08-20 | Celcom Digi_RAN-GCI-TSS-Northern-20231122-0075 | DU00002862400 |  |  | 2025-07-06 | 2025-06-09 |  |  | TOWER | 61 | Add R8862A S9000x3+R8894E M1821x5+R8862A S2601x1+R8854 S2600x2,Dismantle | 0 | 23
A00257 | A037B_A00257OD_TMCDRBALAI | Northern | 4271K | Swap |  | 2025 Q1 | AI | CCSMY | 4.6 TSSR Approved |  | 2025-05-17 | 2025-05-21 |  | 2025-05-26 |  | Closed | 2025-05-26 | 2025-05-27 | CD//Zulakmar | 2025-05-27 | SQ202501030037 - CCSMY | DU00002862401 |  |  | 2025-08-29 | 2025-08-22 |  | Tower | TOWER | 60m | Add R8852E S9000x3+R8894E M1821x4+R8862A S2601x2+R8854 S2600x1, Dismantle | 0 | 2
S00641 | S095A_S00641OD_CB_KGKILUGUS | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2025 Q1 | AD | DATASCO | 4.6 TSSR Approved |  | 2025-03-06 |  | 2025-04-24 |  | 2025-05-06 | To be Submitted | 2025-05-08 |  | E//Hannah | 2025-05-09 | SQ202504100595 - Datasco | DU00002862402 |  |  |  |  | 2025-08-18 |  | TOWER
A00343 | A042A_A00343OD_TMSELAMA | Northern | 4533K | Swap |  | 2025 Q1 | AI | YPTT | 4.6 TSSR Approved |  | 2024-01-18 | 2024-02-08 |  | 2025-01-17 |  | Under Approval | 2025-01-17 | 2025-02-07 | CD//Zulakmar | 2025-01-28 | Celcom Digi_RAN-YPTT-TSS-Northern-20240124-0056 | DU00002862403 |  |  | 2025-12-04 | 2025-03-06 |  | Tower | BOOM | 46 | Add R8852E S9000x3+R8894E M1821x4, Dismantle | 0 | 3
A00501 | A037B_A00501OD_SELEKOH | Northern | 4285K | Swap |  | 2024 Additional | SHA | CCSMY | 4.6 TSSR Approved |  | 2024-12-08 | 2024-12-17 |  | 2024-12-19 |  | Under Approval | 2024-12-20 | 2024-12-24 | CD//Zulakmar | 2024-12-24 | SQ202411290550 - CCSMY | DU00002862404 |  |  | 2025-01-26 | 2025-01-26 |  | Tower | TOWER | 60m | Add R8852E S9000 x3+R8894E M1821x3,Dismantle | 0 | 0
A00527 | A041A_A00527OD_KGKLEDANG | Northern | 4287K | Swap |  | 2025 Q3 | AD | Magicell | 4.6 TSSR Approved |  | 2023-12-13 | 2023-11-23 |  | 2025-02-18 |  | Under Approval | 2025-04-24 | 2025-05-06 | CD//Zulakmar | 2025-05-02 | Celcom Digi_RAN-Magicell-TSS-Northern-20240205-0013//SQ202501030105 - Magicell | DU00002862405 |  |  | 2025-06-12 | 2024-07-05 |  | Tower | TOWER | 62m | Add R8862A S9000x3+R8894E M1821x3, Dismantle | 0 | 0
A00529 | A041A_A00529OD_KGJAYASETIAG9 | Northern | 4241P | Swap |  | 2025 Q3 | HW | GCI | 4.6 TSSR Approved |  | 2023-12-19 | 2024-01-05 |  | 2025-02-27 |  | Under Approval | 2025-03-27 | 2025-04-24 | CD//Zulakmar | 2025-04-14 | Celcom Digi_RAN-GCI-TSS-Northern-20231225-0085 | DU00002862406 |  |  | 2025-04-28 | 2025-04-24 |  | Tower | TOWER | 60 | Add R8852E S9000x3+R8894E M1821x4, Dismantle | 0 | 2
A00729 | A037B_A00729OD_KG_ATTADURI | Northern | 4293K | Swap |  | 2025 | HW | CCSMY | 4.6 TSSR Approved |  | 2025-01-23 | 2025-02-03 |  | 2025-02-25 |  | Under Approval | 2025-03-06 | 2025-05-19 | CD//Zulakmar | 2025-03-26 | SQ202501030037 - CCSMY | DU00002862407 |  |  | 2025-05-14 | 2025-04-26 |  | Lampole | LAMP_POLE | 30M | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
A01090 | A036B_A01090OD_CB_FELDA_SG_KLAH | Northern | 4255P | Swap |  | 2024 Additional | AD | CCSMY | 4.6 TSSR Approved |  | 2024-12-12 | 2024-12-16 |  | 2024-12-18 |  | Under Approval | 2024-12-19 | 2024-12-24 | CD//Zulakmar | 2024-12-23 | 1911CD-Northern-TSS-BOQ Template(new contract)_CCSMY_V2 | DU00002862408 |  |  | 2025-01-19 | 2025-01-19 |  | Tower | TOWER | 60M | Add R8852E S9000 x3+R8894E M1821 x3,Dismantle | 0 | 0
A01092 | A039B_A01092OD_TMN_LEMBAH_BERIAH | Northern | 4583K | Swap |  | 2027 | HW | GCI | 4.6 TSSR Approved |  | 2024-01-20 | 2024-02-14 |  | 2025-03-03 |  | Under Approval | 2025-11-27 | 2025-12-29 | E//Hazida | 2025-12-01 | Celcom Digi_RAN-GCI-TSS-Northern-20240124-0090 | DU00002862409 | [5 empty] | Minaret | MINARET | 30 | Add R8852E S9000x3+R8894E M1821x3, Dismantle
A01135 | A040D_A01135OD_PSRN_PKLNTIMUR_KGPINJI | Northern | 4313K | Swap |  | 2024 Q2 | BY | CCSMY | 4.6 TSSR Approved | ¦ 0304 - Need revise TSSR due to 900 RRU model not available | 2024-02-21 | 2024-02-23 |  | 2024-02-27 |  | Closed | 2024-02-28 | 2024-03-07 | CD//Rohizam | 2024-03-06 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240223-0095 | DU00002862410 |  |  | 2024-03-24 | 2024-03-15 |  | Lampole | LAMP_POLE | 30m | Add R8862A S9000 x3+R8894E M1821 x3+R8862A S2601 x3,Dismantle
A01216 | A036A_A01216OD_T3E_KGMASJID | Northern | 4196P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862411 | [6 empty] | TOWER
A01217 | A036A_A01217OD_T3E_KGHJARIFF | Northern | 4197P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2026 |  | GTSB | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862412 | [6 empty] | TOWER
A01218 | A038A_A01218OD_T3E_KG_BATU_7_1BY2 | Northern | 4593K | Swap |  | 2024 Additional | MS | GTSB | 4.6 TSSR Approved |  | 2024-01-14 | 2024-01-16 |  | 2024-11-21 |  | Under Approval | 2024-11-22 | 2024-11-27 | CD//Zulakmar | 2024-11-27 | Celcom Digi_RAN-GTSB-TSS-Northern-202401114-0085 | DU00002862413 |  |  | 2025-02-08 | 2025-01-02 |  | Tower | TOWER | 75m | Add R8852E S9000 x3+R8894E M1821x5, Dismantle | 0 | 23
A01222 | A037B_A01222OD_T3E_KGSCREDANG_PONGGOR | Northern | 4201P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862414 | [6 empty] | TOWER
A01223 | A038A_A01223OD_T3E_KG_CHANGKAT_TUALANG | Northern | 4595K | Swap |  | 154 single site MOCN | SHA | CCSMY | 4.6 TSSR Approved | ¦ 0820 - CD Zul: Propose to change azimuth from 45/180/300 to 30/180/280 | 2024-01-15 | 2024-01-17 |  | 2024-08-16 |  | Under Approval | 2024-08-21 | 2024-08-22 | CD//Zulakmar | 2024-08-22 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240116-0087 | DU00002862415 |  |  | 2024-10-10 | 2024-10-10 |  | Tower | TOWER | 60m | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle | 0 | 0
A01269 | TROLAK SELATAN | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862416 | [6 empty] | TOWER
S01011 | S089A_S01011OD_CB_LDGHASSAN | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862417 | [6 empty] | TOWER
A01273 | KG. FELDA BESOUT (T3_0631) | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862418 | [6 empty] | TOWER
A01274 | KG. PASIR SG MUDA (T3_0628) | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862419 | [6 empty] | TOWER
S01137 | S088A_S01137OD_KGPADASDAMIT | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2025 Q1 | AD | DATASCO | 4.6 TSSR Approved |  | 2025-03-13 |  | 2025-04-25 |  | 2025-05-06 | To be Submitted | 2025-05-06 |  | CD//Sharidah | 2025-05-08 | SQ202504100595 - Datasco | DU00002862420 |  | 1. Pls show mw location in NE dwg. 2. Pls provide FE part and FE drawing |  |  | 2025-08-15 |  | TOWER
A01276 | KG. BATU 18 (T3-0630) | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862421 | [6 empty] | TOWER
A01287 | KG.SG BILL (T3_0627) | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862422 | [6 empty] | TOWER
A01288 | KG. CGKT SULAIMAN SUNGKAI (T3_0633) | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862423 | [6 empty] | TOWER
A01289 | KG. BATU 14 (T3-0632) | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862424 | [6 empty] | TOWER
A01290 | KG. JAMBI_KG KENOH T3_0642 | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862425 | [6 empty] | TOWER
A01291 | KG. BATU 6_BATU 8 (T3-0641) | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862426 | [6 empty] | TOWER
B00004 | B061S_B00004OD_SS272PJ | Central | 1215K | Swap |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-11-21 | 2023-11-27 |  | 2024-03-22 |  | Under Approval | 2024-03-25 | 2024-07-23 | CD//Norhaliza | 2024-07-23 | CelcomDigi_RAN_Datasco_TSS_Central_20231126 | DU00002862427 |  |  | 2024-06-20 | 2024-05-27 |  | Unipole | BOOM | 5 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle | 0 | 0
B00120 | W066J_B00120OD_KELUMPUKTERATAI | Central | 1351K | Swap |  | 2024 Q1 | SS | YPTT | 4.6 TSSR Approved |  | 2024-02-21 | 2024-03-07 |  | 2024-03-15 |  | Closed | 2024-03-21 | 2024-04-04 | CD//Ali Akaram | 2024-04-04 | BOQ_Celcom Digi_RAN-YPTT-Standard PR TSS-20240225 | DU00002862428 |  |  | 2024-07-13 | 2024-07-10 |  | In-Building System | TRIPOD | 11m (SH is punchthru,SH measure from the rooftop) | Add R9264M M1821 x1+R9264H M901821 x3+R8862A S2601 x2+R8854 S2600 x1,Dismantle |  | 3
B00202 | W066Y_B00202OD_TMNBKTTERATAI | Central | 1607K | Swap |  | 2024 Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-12-23 | 2024-01-04 |  | 2024-05-17 |  | Closed | 2024-05-23 | 2024-09-19 | CD//Norhaliza | 2024-09-12 | CelcomDigi_RAN_GTSB_TSS_Central_20231224 | DU00002862429 |  |  | 2024-08-21 | 2024-08-21 |  | Monople Tree | FLOOD LIGHT | 20M | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle | 0 | 0
B00452 | W066Z_B00452OD_TMNMAJUJAYA2 | Central | 1618K | Swap |  | 2024 Q3 | AI | CCSMY | 4.6 TSSR Approved |  | 2024-07-10 | 2024-07-16 |  | 2024-07-17 |  | Closed | 2024-07-18 | 2024-07-30 | CD//Sapian | 2024-07-29 | 0725Central-CCSMY-BOQ Template(old contract) | DU00002862430 |  |  | 2024-08-16 | 2024-08-02 |  | Tower | MINI STRUCTURE | 18M | Add R9264M M1821 x1+R9264H M901821 x3+R8862A S2601 x2+R8854 S2600 x1,Dismantle | 0 | 2
B00482 | W066Y_B00482OD_TMNKENCANA | Central | 1619K | Swap |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-20 | 2024-04-22 |  | 2024-04-04 |  | Closed | 2024-04-04 | 2024-05-10 | CD//Ali Akaram | 2024-05-10 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231126 | DU00002862431 |  |  | 2024-07-23 | 2024-07-21 |  | In-Building System | BOOM | 8 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle | 0 | 0
B00515 | B061T_B00515OD_ASIAJAYA | Central | 1252K | Swap |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-01-26 | 2024-02-08 |  | 2024-03-25 |  | Closed | 2024-03-26 | 2024-04-15 | CD//Sapian | 2024-04-08 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240128 | DU00002862432 |  |  | 2024-06-29 | 2024-05-28 |  | Pole | BOOM | 5.1m | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle | 0 | 0
B00592 | W066X_B00592OD_BKTBELACAN | Central | 1628K | Swap |  | 2024 Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-12-28 | 2024-01-03 |  | 2024-05-14 |  | Closed | 2024-05-17 | 2024-09-19 | CD//Norhaliza | 2024-09-12 | CelcomDigi_RAN_GTSB_TSS_Central_20231230 | DU00002862433 |  |  | 2024-08-22 | 2024-08-20 |  | Minimast | MINI STRUCTURE | 4.6m | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle | 0 | 0
B01062 | B061O_B01062OD_LEBUHBDRUTAMA | Central | 1265K | Swap |  | 2024 Q3 | MA | DATASCO | 4.6 TSSR Approved |  | 2023-11-22 | 2023-11-24 |  | 2024-03-26 |  | Closed | 2024-03-26 | 2024-04-16 | CD//Ali Akaram | 2024-04-15 | CelcomDigi_RAN_Datasco_TSS_Central_20231201 | DU00002862434 |  |  | 2024-06-20 | 2024-05-27 |  | Monopole | MONOPOLE | 16m | Add R9264H M901821 x3,Dismantle | 0 | 0
B01131 | B057D_B01131OD_TMNPERWIRAINDAH | Central | 1267K | Swap |  | 2024 Q1 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-30 | 2023-12-12 |  | 2024-01-02 |  | Closed | 2024-01-03 | 2024-01-16 | CD//Ali Akaram | 2024-01-16 | CelcomDigi_RAN_GTSB_TSS_Central_20231203 | DU00002862435 |  |  | 2024-04-06 | 2024-03-27 |  | Lampole | LAMP_POLE | 21 | Add R8862A S9000 x3+R8894E M1821 x3+R8862A S2601 x3,Dismantle
B01317 | B062A_B01317OD_LUBUKPUSING | Central | 1651K | Swap |  | 2024 Additional | AI | Solusi | 4.6 TSSR Approved |  | 2024-07-20 | 2024-11-21 |  | 2025-01-22 |  | Under Approval | 2024-11-27 | 2024-12-12 | CD//Ali akaram | 2024-12-12 | 0730CD-Central-Solusi-BOQ Template(new contract) | DU00002862436 |  |  | 2025-01-13 | 2025-01-07 |  | Tower | TOWER | 62M | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
B01395 | B061O_B01395OD_DAMANSARAUTAMA | Central | 1271K | Swap |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-04-20 | 2024-04-30 |  | 2024-05-03 |  | Under Approval | 2024-05-06 | 2024-07-09 | CD//Norhaliza | 2024-07-09 | CelcomDigi_RAN_Datasco_TSS_Central_20231126 | DU00002862437 |  |  | 2024-06-20 | 2024-05-27 |  | Monopole | MONOPOLE | 12m | Add R8862A S9000 x3+R8894E M1821 x4+R8862A S2601 x2+R8854 S2600 x1,Dismantle | 0 | 3
B01464 | B064G_B01464OD_KLJPOLIMARABGI | Central | 1653K | Swap |  | 2024 Q3 | CR | GTSB | 4.6 TSSR Approved |  | 2024-06-15 | 2024-06-28 |  | 2024-07-04 |  | Under Approval | 2024-07-15 | 2024-09-26 | CD//Norhaliza | 2024-09-25 | SQ202411080530 | DU00002862438 |  |  | 2024-12-09 | 2024-11-09 |  | Monopole | LAMP_POLE | 24 | Add R8862A S9000x3+R8894E M1821x3+R8862A S2601x3,Dismantle | 0 | 0
B01491 | B061J_B01491OD_PUJ8PCKJALIL | Central | 1655K | Swap |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-12-01 | 2023-12-14 |  | 2024-04-25 |  | Under Approval | 2024-04-28 | 2024-11-07 | CD//Norhaliza | 2024-11-06 | CelcomDigi_RAN_Datasco_TSS_Central_20231203 | DU00002862439 |  |  | 2024-08-29 | 2024-08-26 |  | In-Building System | MINI MONOPOLE | 5M | Add R8862A S9000 x3+R8894E M1821 x3+R8862A S2601 x3,Dismantle | 0 | 0
B01646 | W066I_B01646OD_TMNSIERRAUKAY | Central | 1659K | Swap |  | 2024 Q1 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-02-28 | 2024-03-08 |  | 2024-03-13 |  | Under Approval | 2024-03-15 | 2024-11-07 | CD//Norhaliza | 2024-11-06 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240303 | DU00002862440 |  |  | 2024-07-26 | 2024-07-09 |  | Watertank | LAMP_POLE | 24 | Add R8862A S9000 x3+R8894E M1821 x3+R8862A S2601 x3,Dismantle
B01926 | B061H_B01926OD_PJS1PJ | Central | 1280K | Swap |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-12-07 | 2024-04-29 |  | 2023-12-20 |  | Closed | 2024-05-08 | 2024-05-16 | CD//Sapian | 2024-05-16 | CelcomDigi_RAN_GTSB_TSS_Central_20231208 | DU00002862441 |  |  | 2024-05-23 | 2024-05-23 |  | In-Building System | UNIPOLE | 9M | Add R8862A S9000 x3+R9224E M1821 x4+R8862A S2601 x2+R8854 S2600 x1,Dismantle |  | 2
B02016 | W066I_B02016OD_MJDBKTANTARABANGSA | Central | 1667K | Swap |  | 2024 Q1 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-11-07 | 2023-11-14 |  | 2024-01-03 |  | Closed | 2024-01-04 | 2024-01-11 | CD//Sapian | 2024-01-10 | CelcomDigi_RAN_Datasco_TSS_Central_20231113 | DU00002862442 |  |  | 2024-07-11 | 2024-07-11 |  | Lampole | LAMP_POLE | 20 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle
B02063 | B057D_B02063OD_TMNMUTIARAGBK | Central | 1284K | Swap |  | 2024 Q1 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-23 | 2023-11-27 |  | 2023-12-27 |  | Closed | 2024-01-02 | 2024-03-18 | CD//Norhaliza | 2024-03-15 | CelcomDigi_RAN_GTSB_TSS_Central_20231126 | DU00002862443 |  |  | 2024-04-01 | 2024-03-29 |  | In-Building System | BOOM | 7m | Add R8862A S9000 x3+R8894E M1821 x3+R8862A S2601 x3,Dismantle
B02446 | W066J_B02446OD_LRT_STATION_SETIAWANGSA | Central | 1298K | Swap |  | 2024 Q1 | SHA | GCI | 4.6 TSSR Approved |  | 2024-07-21 | 2024-07-22 |  | 2024-07-29 |  | Under Approval | 2024-08-12 | 2024-08-14 | CD//Sapian | 2024-08-13 | 0725Central-GCI-BOQ Template(new contract) | DU00002862444 |  |  | 2024-11-13 | 2024-10-04 |  | In-Building System | MINI STRUCTURE | 7 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle
B02503 | B064H_B02503OD_KUIS | Central | 1691K | Swap |  | 2024 Additional | SM | GTSB | 4.6 TSSR Approved | Owner not allow add AAU | 2024-08-14 | 2024-08-20 |  | 2024-12-06 |  | Closed | 2024-12-09 | 2024-12-16 | CD//Sapian | 2024-12-16 | 0815CD-Central-GTSB-BOQ Template(new contract) | DU00002862445 | Remarks: Solution TSSR/BOM Changed |  | 2025-05-05 | 2025-04-29 |  | Monopole | LAMP_POLE | 30M | Add R9264H M901821x3+R8862A S2601x1+R8854 S2600x2,Dismantle | 0 | 12
B02665 | B061Q_B02665OD_CELCOM_AXIATA_PJ | Central | 1216K | Swap |  | 2024 Q3 | CR | Ascentrack | 4.6 TSSR Approved |  | 2024-04-15 | 2024-05-09 |  | 2024-05-10 |  | Closed | 2024-05-11 | 2024-05-21 | CD//Sapian | 2024-05-21 | CelcomDigi_RAN_Ascentrack_TSS_Central_20240513 | DU00002862446 |  |  | 2024-06-30 | 2024-05-28 |  | In-Building System | INBUILDING | 2.5 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle
B02692 | B064G_B02692OD_PSIARAN_KEMAJUAN_BBBANGI | Central | 1705K | Swap |  | 2024 Q3 | SY1 | YPTT | 4.6 TSSR Approved |  | 2023-11-25 | 2023-11-29 |  | 2024-04-22 |  | Under Approval | 2024-05-09 | 2024-11-07 | CD//Norhaliza | 2024-11-06 | CelcomDigi_RAN_YPTT_TSS_Central_20231126 | DU00002862447 |  |  | 2024-11-14 | 2024-11-07 |  | Monopole | LAMP_POLE | 24 | Add R8862A S9000x3+R8894E M1821x3+R8862A S2601x3,Dismantle | 0 | 0
B02717 | W066S_B02717OD_BDR_KINRARA9 | Central | 1352K | Swap |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-28 | 2023-11-30 |  | 2024-04-16 |  | Closed | 2024-05-27 | 2024-11-12 | CD//Norhaliza | 2024-11-11 | CelcomDigi_RAN_GTSB_TSS_Central_20231201 | DU00002862448 |  |  | 2024-08-20 | 2024-08-14 |  | Lampole | LAMP_POLE | 18m | Add R9264H M901821 x3+R8862A S2601 x2+R8854 S2600 x1,Dismantle | 0 | 2
B02787 | B061S_B02787OD_DIRECTD_PJ | Central | 1314K | Swap |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-12-20 | 2023-12-26 |  | 2024-03-29 |  | Closed | 2024-03-29 | 2024-04-26 | CD//Sapian | 2024-04-25 | CelcomDigi_RAN_GTSB_TSS_Central_20231224 | DU00002862449 |  |  | 2024-05-28 | 2024-05-18 |  | Unipole | LAMP_POLE | 6m | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle | 0 | 0
K00094 | K008A_K00094OD_PDGLALANG | Northern | 4400K | Swap |  | 131 single site mocn | ZB | GTSB | 4.6 TSSR Approved |  | 2024-08-29 | 2024-09-06 |  | 2024-09-10 |  | Under Approval | 2024-09-10 | 2024-09-12 | CD//Zulakmar | 2024-09-11 | 0809CD-Northern-GTSB-BOQ Template(new contract) | DU00002862450 |  |  | 2024-11-02 | 2024-10-30 |  | Tower | TOWER | 40M | Add R8852E S9000 x3+R8894E M1821 x3,Dismantle | 0 | 0
K00251 | K005D_K00251OD_CB_BKT858 | Northern | 4416K | Swap |  | 2027 |  | GCI | 1.1 Pending Survey - Subcon | [6 empty] | To be Submitted |  |  | CD//Zulakmar |  | SQ202501030261 - GCI | DU00002862451 | [6 empty] | TOWER |  | Add R8852E S9000x3+A9732 M1821x1+R9264M M1821x2, Dismantle | 1 | 0
K00283 | A045A_K00283OD_BUKITPALONG | Northern | 4598K | Swap |  | 2024 Q3(single site MOCN) | BY | GTSB | 4.6 TSSR Approved |  | 2023-10-23 | 2023-11-01 |  | 2024-04-17 |  | Closed | 2024-04-18 | 2024-04-19 | CD//Rohizam | 2024-04-18 | Celcom Digi_RAN-GTSB-TSS-Northern-20231025-0055 | DU00002862452 |  |  | 2024-07-26 | 2024-07-15 |  | Tower | TOWER | 60m | Add R8862A S9000 x3+R9224E M1821 x1+R8862A S2601 x3+A9732 M1821 x2,Dismantle | 23 | 0
K00320 | K002A_K00320OD_KGPAYABESRHOTST | Northern | 4422K | Swap |  | 131 single site mocn | AI | GTSB | 4.6 TSSR Approved | ¦ 0828 - CD Zul: Missing sector 3 label in drawing | 2023-11-02 | 2023-12-27 |  | 2024-08-20 |  | Closed | 2024-09-10 | 2024-09-12 | CD//Zulakmar | 2024-09-11 | Celcom Digi_RAN-GTSB-TSS-Northern-20231103-0062 | DU00002862453 |  |  | 2024-10-12 | 2024-10-02 |  | Tower | TOWER | 45 | Add R8852E S9000 x3+R8894E M1821 x3+R8862A S2601 x3,Dismantle | 0 | 0
K00346 | K002A_K00346OD_CB_KGBESAH | Northern | 4428K | Swap |  | 2025 Q2 | SM | GCI | 4.6 TSSR Approved |  | 2024-02-03 | 2024-02-08 |  | 2025-02-12 |  | Under Approval | 2025-02-19 | 2025-03-04 | CD//Zulakmar | 2025-03-03 | Celcom Digi_RAN-GCI-TSS-Northern-20240205-0094 | DU00002862454 |  |  | 2025-03-16 | 2025-02-26 |  | Tower | TOWER | 60 | Add R8852E S9000x3+A9732 M1821x1+R9264M M1821x2, Dismantle | 2 | 0
K00445 | K002A_K00445OD_ULULEGONG | Northern | 4185P | Maintain USP MOCN(Dismantle Passive) | Maintain USP MOCN(Dismantle Passive)->On Hold->Maintain USP MOCN(Dismantle Passive) | 2025 Q2 | HW | GCI | 4.6 TSSR Approved |  | 2025-07-11 |  | 2025-07-21 |  | 2025-09-19 |  | 2025-09-29 | 2026-01-22 | E//Hazida | 2025-10-03 | SQ202504230429-GCI | DU00002862455 |  |  |  |  | 2025-10-10 |  | TOWER
K00698 | K012A_K00698OD_KGTGBELIT | Northern | 4461K | Swap |  | 2027 | HW | GTSB | 4.6 TSSR Approved |  | 2025-02-19 | 2025-02-25 |  | 2025-03-21 |  | Under Approval | 2025-11-04 | 2025-12-29 | E//Hazida | 2025-11-06 | SQ202501030229 - gtsb | DU00002862456 | [5 empty] | Tower | TOWER | 45M | Add R8852E S9000x3+A9732 M1821x1+R9264M M1821x2, Dismantle | 2 | 13
K00785 | K002A_K00785OD_CB_KGRAMBONG_BLNG | Northern | 4473K | Swap |  | 2025 Q2 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-10-15 | 2023-10-20 |  | 2023-10-30 |  | Rectificating | 2025-02-04 | 2025-02-24 | CD//Zulakmar | 2025-02-21 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231016-0055 | DU00002862457 |  |  | 2025-03-04 | 2025-02-18 |  | Tower | TOWER | 46m | Add R8852E S9000x3+R8894E M1821x4, Dismantle | 0 | 2
K00794 | K005D_K00794OD_CB_KG_GUAR_STESEN | Northern | 4475K | Swap |  | 154 single site MOCN | SHA | GCI | 4.6 TSSR Approved |  | 2024-01-06 | 2024-01-12 |  | 2024-08-19 |  | Under Approval | 2024-08-27 | 2024-08-29 | CD//Zulakmar | 2024-08-29 | Celcom Digi_RAN-GCI-TSS-Northern-20240116-0089 | DU00002862458 |  |  | 2024-10-04 | 2024-09-27 |  | Tower | TOWER | 45 | Add R8862A S9000 x3+R8862A S2601 x3+A9732 M1821 x3,Dismantle | 123 | 0
K00797 | K003A_K00797OD_CB_BT18_SERDANG_KDH | Northern | 4477K | Swap |  | 154 single site MOCN | ZB | CCSMY | 4.6 TSSR Approved |  | 2023-11-29 | 2023-11-14 |  | 2024-08-19 |  | Under Approval | 2024-08-26 | 2024-09-06 | CD//Zulakmar | 2024-09-06 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231130-0074 | DU00002862459 |  |  | 2024-09-25 | 2024-09-07 |  | Tower | TOWER | 45m | Add R8862A S9000 x3+R8894E M1821 x1+R8862A S2601 x3+A9732 M1821 x2,Dismantle | 12
K00829 | K004B_K00829OD_KG_BALAI_KKEDAH | Northern | 4487K | Swap |  | 2025 Q3 | AD | GCI | 4.6 TSSR Approved |  | 2025-01-13 | 2025-01-27 |  | 2025-02-26 |  | Under Approval | 2025-04-14 | 2025-05-06 | CD//Zulakmar | 2025-05-02 | SQ202501030261 - GCI | DU00002862460 |  |  | 2025-07-31 | 2025-07-31 |  | Tower | TOWER | 46m | Add R8852E S9000x3+R8894E M1821x4, Dismantle | 0 | 3
K00833 | K009A_K00833OD_PEKAN_NAKA | Northern | 4489K | Swap |  | 2024 Q3(single site MOCN) | SHA | GCI | 4.6 TSSR Approved |  | 2024-05-14 | 2024-05-14 |  | 2024-06-19 |  | Under Approval | 2024-06-21 | 2024-06-28 | CD//Rohizam | 2024-06-28 | Celcom Digi_RAN-GCI-TSS-Northern-20240519-0107 | DU00002862461 |  |  | 2024-10-29 | 2024-10-24 |  | Tower | TOWER | 45M | Add R8862A S9000 x3+R9224E M1821 x1+R8862A S2601 x3+A9732 M1821 x2,Dismantle | 23 | 0
K00899 | K010A_K00899OD_KG_CHINA_PNDG | Northern | 4503K | Swap |  | 154 single site MOCN | SHA | CCSMY | 4.6 TSSR Approved |  | 2024-08-16 | 2024-08-20 |  | 2024-08-27 |  | Under Approval | 2024-08-29 | 2024-09-05 | CD//Zulakmar | 2024-09-04 | 0809CD-Northern-CCSMY-BOQ Template(new contract) | DU00002862462 |  |  | 2024-10-21 | 2024-10-21 |  | Tower | TOWER | 40m | Add R8862A S9000 x3+R8894E M1821 x3+R8862A S2601 x3,Dismantle | 0 | 0
K00905 | K002A_K00905OD_KG_SG_TEMBAK | Northern | 4505K | Swap |  | 2024 Q3(single site MOCN) | BY | GCI | 4.6 TSSR Approved |  | 2023-12-15 | 2023-12-18 |  | 2024-04-17 |  | Closed | 2024-04-18 | 2024-04-19 | CD//Rohizam | 2024-04-18 | Celcom Digi_RAN-GCI-TSS-Northern-20231225-0085 | DU00002862463 |  |  | 2024-07-29 | 2024-07-20 |  | Tower | TOWER | 60 | Add R8862A S9000 x3+R9224E M1821 x4+R8862A S2601 x2+R8854 S2600 x1,Dismantle | 0 | 1
L00011 | S113A_L00011OD_TMLABUANCARRIER | Sabah | 7233K | Swap |  | 2025 Q1 | AD | YPTT | 4.6 TSSR Approved |  | 2025-02-19 | 2025-02-23 |  | 2025-02-26 |  | Under Approval | 2025-02-27 | 2025-03-09 | CD//Sharidah | 2025-03-03 | SQ202501030045 - YPTT | DU00002862464 |  |  | 2025-05-28 | 2025-05-23 |  | Tower | TOWER | 45 | Add R8852E S9000x3+R9264M M1821x3, Dismantle | 0 | 0
Q00143 | Q135A_Q00143OD_BT10KCH | Sarawak | 9287K | Swap |  | 2026 | AI | Datasco | 4.6 TSSR Approved |  | 2023-10-25 | 2023-10-31 |  | 2025-05-13 |  | Closed | 2025-05-15 | 2025-05-23 | E//John | 2025-05-22 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231028 | DU00002862465 |  |  | 2025-09-28 | 2025-09-25 |  | Tower | GUYED MAST | 50 | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
Q00311 | Q132C_Q00311OD_CB_ANCHARANG | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862466 | [6 empty] | TOWER
Q00328 | CBTMBKTMAS | Sarawak | 9291P | Maintain USP MOCN | Swap->Maintain USP MOCN | 2026 | SH | Datasco | 4.6 TSSR Approved |  | 2024-02-06 | 2024-04-17 |  | 2024-04-22 |  | Closed | 2024-04-26 | 2024-04-29 | CD//John | 2025-02-27 | Celcom Digi_RAN-Datasco-Standard PR TSS-Sarawak-20240213 | DU00002862467 | Remarks: Solution TSSR/BOM Changed |  |  |  |  | Tower | BOOM | 120 | Add R8894E x3 |  | 123
Q00342 | Q132C_Q00342OD_JLNBRIGHTON | Sarawak | 9159K | Swap |  | 2027 | SH | Magicell | 4.6 TSSR Approved |  | 2023-10-13 | 2023-10-23 |  | 2023-10-25 |  | Closed | 2023-10-26 | 2023-10-27 | CD//John | 2023-10-26 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231016 | DU00002862468 | [5 empty] | In-Building System | BOOM | 16 | Add R8852E S9000 x3+R8894E x3,Dismantle
Q00375 | Q129A_Q00375OD_BINTANGOR | Sarawak | 9165K | Swap |  | 2027 | SM | Datasco | 4.6 TSSR Approved |  | 2023-11-23 | 2023-11-28 |  | 2025-02-13 |  | Rectificating | 2025-02-18 | 2025-02-24 | CD//John | 2025-02-21 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231126 | DU00002862469 | [5 empty] | Tower | TOWER | 65 | Add R8852E S9000 x3+R9264M M1821 x3,Dismantle
Q00486 | Q130A_Q00486OD_LAPOK | Sarawak | 9175K | Swap |  | 2027 | AD | Datasco | 4.2 Pending TSSR Resubmission - Subcon |  | 2024-01-05 | 2024-03-04 |  | 2024-04-18 |  | Rectificating |  |  | CD//John |  | Celcom Digi_RAN-Datasco-Standard PR TSS-Sarawak-20240109 | DU00002862470 | [6 empty] | GUYED MAST | 24 | Add R8862A S9000x3+R8894E M1821 x3, Dismantle
Q00781 | Q132A_Q00781OD_CB_TAWAKALMEGAH | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862471 | [6 empty] | TOWER
Q01055 | Q132C_Q01055OD_JLNARU | Sarawak | 9197K | Swap |  | 2027 | AI | Magicell | 4.6 TSSR Approved |  | 2023-10-12 | 2023-10-31 |  | 2025-02-06 |  | Closed | 2025-02-20 | 2025-03-10 | CD//John | 2025-03-04 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231013 | DU00002862472 | [5 empty] | In-Building System | LAMP_POLE | 3m | Add R8852E S9000 x3+R8894E x3,Dismantle
Q01057 | Q126A_Q01057OD_JLNBUANGSIOL | Sarawak | 9317K | Swap |  | 2027 | AI | Datasco | 4.6 TSSR Approved |  | 2024-01-25 | 2024-03-01 |  | 2025-02-14 |  | Closed | 2025-03-13 | 2025-05-19 | CD//John | 2025-03-17 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20240204 | DU00002862473 | [6 empty] | TOWER | 30 | Add R8852E S9000 x3+R9264M M1821 x3,Dismantle
Q01075 | Q135A_Q01075OD_DESAILMU3 | Sarawak | 9318K | Swap |  | 2024 Q2 | SH | Datasco | 4.6 TSSR Approved |  | 2023-10-27 | 2023-12-05 |  | 2023-12-12 |  | Closed | 2023-12-14 | 2023-12-15 | CD//John | 2023-12-15 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231028 | DU00002862474 |  |  | 2025-06-30 | 2025-06-05 |  |  | TRIPOD | 10 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle | 0 | 0
Q01128 | Q130A_Q01128OD_T3_RHPEGABANG | Sarawak | 9199K | Swap |  | 2025 | ZB | GTSB | 4.6 TSSR Approved |  | 2023-10-13 | 2023-10-18 |  | 2023-10-25 |  | Closed | 2023-10-26 | 2023-10-30 | CD//John | 2023-10-27 | Celcom Digi_RAN-GTSB-TSS-Sarawak-20231016 | DU00002862475 |  |  | 2025-08-28 | 2025-08-20 |  | Tower | #N/A | 76m | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
Q01129 | Q130A_Q01129OD_T3_RHLINGGI | Sarawak | 9200K | Swap | Swap | 2026 | AI | Magicell | 4.6 TSSR Approved | Solution changed add L26 in 2026 | 2024-05-02 | 2024-05-14 |  | 2025-02-18 |  | Under Approval | 2025-02-25 | 2025-03-10 | CD//John | 2025-03-04 | Celcom Digi_RAN-Magicell-Standard PR TSS-Sarawak-20240425 | DU00002862476 |  |  | 2026-04-11 | 2026-03-24 |  | Tower | #N/A | 76 | Add R8862A S9000x3+R8894E M1821x3+R8862A S2601x3, Dismantle
Q01130 | Q130A_Q01130OD_CB_LONGTERU | Sarawak | 9201K | Swap |  | 2027 |  | Magicell | 1.1 Pending Survey - Subcon | [6 empty] | To be Submitted |  |  | CD//John |  |  | DU00002862477 | [6 empty] | TOWER
Q01131 | Q130A_Q01131OD_CB_SGBRIT | Sarawak | 9202K | Swap |  | 2024 Q4(single site MOCN)-L21 SSM | SHA | YPTT | 4.6 TSSR Approved |  | 2024-10-24 | 2024-10-30 |  | 2024-11-04 |  | Under Approval | 2024-11-04 | 2024-11-06 | CD//John | 2024-11-05 | PR raised as per design team | DU00002862478 |  |  | 2025-03-12 | 2024-11-21 |  | Tower | #N/A | 77 | Add R8862A S9000x3+R8894E M1821x3+R8862A S2601x3, Dismantle | 0 | 0
Q01133 | Q130A_Q01133OD_CB_LONGPELUAN | Sarawak | 9204K | Swap | Swap->Site Out->Swap->On Hold->Swap | 2027 |  | Magicell | 1.1 Pending Survey - Subcon | [6 empty] | To be Submitted |  |  | CD//John |  |  | DU00002862479 | [6 empty] | #N/A
Q01134 | Q130A_Q01134OD_T3_SGBOK | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862480 | [6 empty] | #N/A
Q01135 | Q130A_Q01135OD_CB_LOAGANBUNUT | Sarawak | 9205K | Swap |  | 2027 |  | Datasco | 4.1 Pending TSSR Submission - Subcon |  | 2024-01-03 | 2024-02-23 |  |  |  | To be Submitted |  |  | CD//John |  | Celcom Digi_RAN-Datasco-Standard PR TSS-Sarawak-20240109 | DU00002862481 | [5 empty] | Tower | TOWER | 76
Q01139 | Q130A_Q01139OD_T3_LONGPANAI | Sarawak | 9208K | Swap |  | 2027 |  | Magicell | 1.1 Pending Survey - Subcon | [6 empty] | To be Submitted |  |  | CD//John |  |  | DU00002862482 | [6 empty] | #N/A
Q01140 | Q130A_Q01140OD_CB_LONGBEMANG | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862483 | [6 empty] | TOWER
Q01142 | Q130A_Q01142OD_CB_LONGBANYOK | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862484 | [6 empty] | TOWER
Q01143 | Q130A_Q01143OD_CB_KGSGTERAJA | Sarawak | 9209K | Swap |  | 2027 |  | Magicell | 1.1 Pending Survey - Subcon | [6 empty] | To be Submitted |  |  | CD//John |  |  | DU00002862485 | [6 empty] | #N/A |  | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
Q01145 | Q130A_Q01145OD_CB_SGAMBUNTERU | Sarawak | 9210K | Swap |  | 2027 |  | Datasco | 4.1 Pending TSSR Submission - Subcon |  | 2024-01-03 | 2024-02-15 |  |  |  | To be Submitted |  |  | CD//John |  | Celcom Digi_RAN-Datasco-Standard PR TSS-Sarawak-20240109 | DU00002862486 | [5 empty] | Tower | #N/A | 76
Q01150 | Q122A_Q01150OD_T3_BKTMELAPI | Sarawak | 9225P | Swap | Maintain USP MOCN->On Hold->Swap | 2025 Q3 | AI | Trintel | 4.6 TSSR Approved |  | 2025-03-11 | 2025-05-08 |  | 2025-05-13 |  | Under Approval | 2025-05-13 | 2025-05-21 | E//John | 2025-05-20 | SQ202501070293-Trintel | DU00002862487 |  |  | 2025-07-06 | 2025-06-28 |  | Tower | #N/A | 76 | Add R8852E S9000x3+R8894E M1821x8,Dismantle | 0 | 12
Q01160 | Q121A_Q01160OD_CB_JLNMELUAN | Sarawak | 9213K | Swap |  | 2027 | AI | Datasco | 4.6 TSSR Approved |  | 2023-10-21 | 2023-11-07 |  | 2025-02-17 |  | Closed | 2025-02-17 | 2025-03-10 | CD//John | 2025-03-04 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231024 | DU00002862488 | [5 empty] | Tower | TOWER | 76 | Add R8852E S9000 x3+R8894E x3,Dismantle
Q01174 | Q131A_Q01174OD_T3_KGSGILAS | Sarawak | 9321K | Swap |  | 2027 |  | Trintel | 1.0 TSS Concurrent TI - Hardcore Access | [6 empty] | To be Submitted |  |  | CD//John |  |  | DU00002862489 | [6 empty] | TOWER |  | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
Q01278 | Q124E_Q01278OD_PULASAR | Sarawak | 9328K | Swap |  | 2027 | AI | Datasco | 4.6 TSSR Approved |  | 2023-11-17 | 2023-12-14 |  | 2025-01-13 |  | Under Approval | 2025-01-14 | 2025-02-07 | CD//John | 2025-01-14 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231119 | DU00002862490 | [6 empty] | WATERTANK | 6 | Add R8852E S9000 x3+R8894E x3,Dismantle
Q01490 | Q126A_Q01490OD_NANGADAMIT | Sarawak | 9338K | Swap |  | 2025 | HW | Datasco | 4.6 TSSR Approved |  | 2024-01-26 | 2024-02-28 |  | 2025-04-14 |  | Under Approval | 2025-04-16 | 2025-04-24 | CD//John | 2025-04-17 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20240204 | DU00002862491 |  |  | 2025-10-21 | 2025-10-13 |  | Watertank | RAMO | 30 | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
Q01493 | Q132C_Q01493OD_RHSINJU | Sarawak | 9233K | Swap |  | 2027 | SM | GTSB | 4.6 TSSR Approved |  | 2023-10-18 | 2023-10-23 |  | 2023-11-01 |  | Rectificating | 2025-02-18 | 2025-02-24 | CD//John | 2025-02-21 | Celcom Digi_RAN-GTSB-TSS-Sarawak-20231019 | DU00002862492 | [5 empty] | Watertank | RAMO | 30m | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
Q01734 | Q132A_Q01734OD_CB_PATIDEPOMYY | Sarawak | 9237K | Swap | Swap | 2026 | AD | Magicell | 4.6 TSSR Approved |  | 2025-12-03 | 2026-01-28 |  | 2026-03-05 |  | Under Approval | 2026-03-07 | 2026-04-20 | E//John | 2026-03-09 | SQ202511040109 - Magicell | DU00002862493 |  |  |  | 2026-04-15 |  | Tower | RAPOLE | 48 | Add R8862A S9000x3+R8894E M1821x3+R8862A S2601x3, Dismantle
Q01826 | Q130A_Q01826OD_LDGEMPRESSA | Sarawak | 9246K | Swap |  | 2025 Q3 | AD | Trintel | 4.6 TSSR Approved |  | 2025-03-09 | 2025-04-08 |  | 2025-04-15 |  | Under Approval | 2025-04-17 | 2025-05-27 | CD//John | 2025-04-22 | SQ202502050142-Trintel | DU00002862494 | Remarks: Solution TSSR/BOM Changed |  | 2025-07-06 | 2025-06-14 |  | Tower | TOWER | 60M | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
Q01872 | Q137A_Q01872ODA_CB_JLNMERUTON | Sarawak | 9259K | Swap |  | 2026 | AI | AllStar | 4.6 TSSR Approved |  | 2023-10-17 | 2023-10-31 |  | 2023-11-13 |  | Under Approval | 2025-04-25 | 2025-05-02 | CD//John | 2025-04-28 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20231019 | DU00002862495 |  |  | 2025-06-28 | 2025-05-21 |  | Tower | TOWER | 45 | Add R8852E S9000x3+R8894E M1821x4, Dismantle | 0 | 1
Q01875 | Q132A_Q01875OD_CB_RHENGKAS | Sarawak | 9260K | Swap |  | 2025 Q2 | SM | Magicell | 4.6 TSSR Approved |  | 2024-05-03 | 2024-05-09 |  | 2025-02-06 |  | Rectificating | 2025-02-14 | 2025-02-24 | CD//John | 2025-02-21 | Celcom Digi_RAN-Magicell-Standard PR TSS-Sarawak-20240425 | DU00002862496 |  |  | 2025-07-06 | 2025-04-11 |  | Tower | TOWER | 45 | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
Q01876 | Q141A_Q01876OD_CB_KGENSENGEI | Sarawak | 9366K | Swap |  | 2026 | AI | Trintel | 4.6 TSSR Approved |  | 2023-10-30 | 2023-11-07 |  | 2025-04-29 |  | Under Approval | 2025-04-29 | 2025-05-02 | CD//John | 2025-04-30 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231028 | DU00002862497 |  |  | 2025-07-06 | 2025-05-28 |  | Tower | RAPOLE | 76 | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
Q01885 | Q137A_Q01885OD_JLNHUAEE | Sarawak | 9262K | Swap |  | 2026 | AI | AllStar | 4.6 TSSR Approved |  | 2023-10-23 | 2023-10-25 |  | 2023-11-08 |  | Closed | 2025-03-14 | 2025-05-19 | CD//John | 2025-03-17 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20231024 | DU00002862498 |  |  | 2025-05-18 | 2025-05-16 |  | Tower | TOWER | 60 | Add R8852E S9000x3+R8894E M1821x4, Dismantle | 0 | 3
R00001 | R001A_R00001OD_CB_TASOH | Northern | 4317K | Swap |  | 2025 Q3 | AD | GCI | 4.6 TSSR Approved |  | 2024-05-03 | 2024-05-09 |  | 2025-02-18 |  | Under Approval | 2025-04-09 | 2025-05-27 | CD//Zulakmar | 2025-04-15 | Celcom Digi_RAN-GCI-TSS-Northern-20240512-0106 | DU00002862499 |  |  | 2025-06-28 | 2025-05-31 |  | Tower | TOWER | 45M | Add R8862A S9000x3+R8894E M1821x3, Dismantle | 0 | 0
R00003 | R001A_R00003OD_SANTAN | Northern | 4318K | Swap |  | 131 single site mocn | SHA | GCI | 4.6 TSSR Approved | ¦ 0820 - CD Zul: Propose to change azimuth from 30/160/270 to 20/140/240. Possible need to change antenna from tower leg D to C for better position for 240deg azimuth. | 2024-05-03 | 2024-05-14 |  | 2024-08-16 |  | Under Approval | 2024-08-21 | 2024-08-22 | CD//Zulakmar | 2024-08-22 | Celcom Digi_RAN-GCI-TSS-Northern-20240512-0106 | DU00002862500 |  |  | 2024-09-27 | 2024-09-12 |  | Tower | TOWER | 60M | Add R8852E S9000 x3+R8894E M1821 x4+R8862A S2601 x2+R8854 S2600 x1,Dismantle |  | 1
R00029 | R001A_R00029OD_BUKITKETERI | Northern | 4324K | Swap | Swap | 2026 | HW | CCSMY | 4.6 TSSR Approved |  | 2023-10-31 | 2023-11-07 |  | 2025-02-14 |  | Under Approval | 2025-11-09 | 2025-12-08 | E//Hazida | 2025-11-13 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231031-0064 | DU00002862501 |  |  | 2026-01-08 | 2025-11-29 |  | Tower | TOWER | 25m | Add R8852E S9000x3+R8894E M1821x3, Dismantle
R00030 | R001B_R00030OD_KANGAROFFICE | Northern | 4325K | Swap |  | 2024 Q4 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-10-31 | 2023-11-10 |  | 2024-04-23 |  | Closed | 2024-04-30 | 2024-05-02 | CD//Rohizam | 2024-05-02 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231101-0065 | DU00002862502 |  |  | 2024-05-29 | 2024-05-29 |  | In-Building System | BOOM | 6m | Add R8862A S9000 x3+R8894E M1821 x3+R8862A S2601 x3,Dismantle | 0 | 0
R00053 | R001A_R00053OD_KGSYEDABDAN | Northern | 4330K | Swap | Swap | 2027 | HW | CCSMY | 4.6 TSSR Approved |  | 2024-01-13 | 2024-01-17 |  | 2024-06-20 |  | Rectificating | 2025-11-21 | 2025-12-29 | E//Hazida | 2025-11-27 | SQ202501030105 - Magicell | DU00002862503 | [5 empty] | Tower | TOWER | 71 | Add R8852E S9000x3+R8894E M1821x3,Dismantle
R00071 | R001B_R00071OD_TMNMUTIARA | Northern | 4335K | Swap |  | 2024 Q4 | SM | GCI | 4.6 TSSR Approved |  | 2023-12-05 | 2023-12-08 |  | 2024-04-30 |  | Under Approval | 2024-05-10 | 2024-05-15 | CD//Rohizam | 2024-05-10 | Celcom Digi_RAN-GCI-TSS-Northern-20231206-0080 | DU00002862504 |  |  | 2024-05-29 | 2024-05-21 |  | Lampole | LAMP_POLE | 30M | Add R8862A S9000 x2+R9264H M901821 x1+R8862A S2601 x3+A9732 M1821 x2,Dismantle | 23 | 0
R00075 | R001C_R00075OD_KGTANAHTIMBUL | Northern | 4339K | Swap |  | 2024 Q4 | SM | GCI | 4.6 TSSR Approved |  | 2023-12-14 | 2023-12-18 |  | 2024-04-30 |  | Rectificating | 2024-05-03 | 2024-05-06 | CD//Rohizam | 2024-05-03 | Celcom Digi_RAN-GCI-TSS-Northern-20231225-0085 | DU00002862505 |  |  | 2024-05-29 | 2024-05-23 |  | Lampole | LAMP_POLE | 30 | Add R8862A S9000 x3+R8894E M1821 x2+R8862A S2601 x3+A9732 M1821 x1,Dismantle | 2 | 0
R00080 | R001A_R00080OD_CB_KGBARUBKTCABANG | Northern | 4341K | Swap |  | 2027 |  | CCSMY | 4.4 Pending TSSR Review - Design Team |  | 2023-11-03 | 2023-11-08 |  | 2025-02-21 |  | Under Approval |  |  | CD//Zulakmar |  | Celcom Digi_RAN-CCSMY-TSS-Northern-20231106-0068 | DU00002862506 | [5 empty] | Tower | TOWER | 47m | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
R00092 | R001A_R00092OD_KG_KOLAM_PDGBESAR | Northern | 4350K | Swap |  | 154 single site MOCN | SM | YPTT | 4.6 TSSR Approved |  | 2023-12-05 | 2023-11-10 |  | 2024-04-19 |  | Rectificating | 2024-08-15 | 2024-08-15 | CD//Rohizam | 2024-08-15 | Celcom Digi_RAN-YPTT-TSS-Northern-20231225-0047 | DU00002862507 |  |  | 2024-09-20 | 2024-09-20 |  |  | LAMP_POLE | 31 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle | 0 | 0
R00099 | R001B_R00099OD_KG_PDGPAUH_PS | Northern | 4355K | Swap |  | 2025 Q3 | HW | GTSB | 4.6 TSSR Approved |  | 2023-11-11 | 2023-11-14 |  | 2025-03-13 |  | Under Approval | 2025-03-14 | 2025-05-19 | CD//Zulakmar | 2025-04-10 | Celcom Digi_RAN-GTSB-TSS-Northern-20231115-0065 | DU00002862508 |  |  | 2025-05-27 | 2025-05-20 |  | Monopole | LAMP_POLE | 30 | Add R8852E S9000x3+R8894E M1821x4, Dismantle | 0 | 3
R00130 | R001A_R00130OD_CB_KUBANG3 | Northern | 4358K | Swap |  | 2027 | HW | GCI | 4.6 TSSR Approved |  | 2023-12-06 | 2023-12-08 |  | 2025-02-19 |  | Under Approval | 2026-02-19 | 2026-02-19 | CD//Zulakmar | 2025-12-01 | Celcom Digi_RAN-GCI-TSS-Northern-20231207-0081 | DU00002862509 | [5 empty] | Tower | TOWER | 60m | Add R8852E S9000x3+R8894E M1821x3, Dismantle
S00130 | S104A_S00130OD_CB_KGMATAN | Sabah | 7166K | Swap |  | 2024 Q3(single site MOCN) | AD | Futong | 4.6 TSSR Approved |  | 2024-02-16 | 2024-02-19 |  | 2024-06-12 |  | Rectificating | 2024-06-12 | 2024-06-20 | CD//Mohidi Jaan | 2024-06-19 | Celcom Digi_RAN-Futong-Standard PR TSS-Sabah-20240223 | DU00002862510 |  |  | 2024-12-07 | 2024-08-26 |  | Guide mast | GUYED MAST | 46 | Add R8862A S9000 x3+R9224E M1821 x5+R8862A S2601 x1+R8854 S2600 x2,Dismantle | 0 | 13
S00139 | S102A_S00139OD_CB_PITAS | Sabah | 7121P | Swap | Maintain USP MOCN->On Hold->Swap | 2025 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2025-01-23 | 2025-01-31 |  | 2025-02-27 |  | Under Approval | 2025-04-07 | 2025-05-27 | CD//Sharidah | 2025-04-08 | SQ202501020343 - GTSB | DU00002862511 |  |  | 2025-05-29 | 2025-05-19 |  | Tower | TOWER | 45 | Add R8852E S9000x3+R8854E S1800x3+R8894E M1821x5,Dismantle | 0 | 12
S00298 | S088A_S00298OD_TMBEAUFORT | Sabah | 7178K | Swap |  | 2025 Q2 | AD | DATASCO | 4.6 TSSR Approved |  | 2025-01-22 | 2025-04-23 |  | 2025-04-24 |  | Under Approval | 2025-04-29 | 2025-05-02 | CD//Sharidah | 2025-04-30 | SQ202501020441 - Datasco | DU00002862512 |  |  | 2025-09-30 | 2025-09-06 |  | Tower | BOOM | 23M | Add R8862A S9000x3+R8894E M1821x3, Dismantle | 0 | 0
S00324 | S098C_S00324OD_SEGAMA | Sabah | 7101K | Swap |  | 2024 Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2023-11-21 | 2023-11-28 |  | 2024-07-18 |  | Under Approval | 2024-09-30 | 2024-09-30 | CD//Ray Amos | 2024-09-30 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231126 | DU00002862513 |  |  | 2025-01-24 | 2025-01-16 |  | Tower | GUYED MAST | 45m | Add R8852E S9000 x3+R8894E M1821 x3+R8862A S2601 x3,Dismantle | 0 | 0
S00336 | S098A_S00336OD_CB_SAHABAT20 | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862514 | [6 empty] | TOWER
S00338 | S098B_S00338OD_SMKSEPAGAYA | Sabah | 7103K | Swap |  | 2024 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2023-10-26 | 2023-11-08 |  | 2024-04-16 |  | Closed | 2024-06-05 | 2024-06-10 | CD//Mohidi Jaan | 2024-06-09 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231028 | DU00002862515 |  |  | 2024-07-06 | 2024-06-15 |  | Pole | Water Tank | 6 | Add R8862A S9000 x3+R9224E M1821 x4+R8862A S2601 x2+R8854 S2600 x1,Dismantle | 0 | 1
S00774 | S102A_S00774OD_KGBONGKOL | Sabah | 7191K | Swap |  | 131 single site mocn | SH | YPTT | 4.6 TSSR Approved |  | 2024-08-15 | 2024-09-02 |  | 2024-09-07 |  | Under Approval | 2024-09-10 | 2024-09-11 | CD//Mohidi Jaan | 2024-09-10 | 0809CD-Sabah-YPTT-BOQ Template(new contract) | DU00002862516 |  |  | 2024-11-09 | 2024-10-08 |  | Tower | TOWER | 76 | Add R8852E S9000 x3+R8894E M1821 x3+R8862A S2601 x3,Dismantle | 0 | 0
S00776 | S102A_S00776OD_T3_KGMANGKUBAULAUT | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862517 | [6 empty] | TOWER
S00777 | S102A_S00777OD_T3_KGKIRIMAN | Sabah | 7069P | Swap | Maintain USP MOCN->On Hold->Swap | 2025 Q3 | HW | GTSB | 4.6 TSSR Approved |  | 2025-04-17 | 2025-05-14 |  | 2025-05-16 |  | Under Approval | 2025-05-20 | 2025-07-17 | E//Hannah | 2025-06-09 | SQ202501020343 - GTSB | DU00002862518 |  |  | 2025-08-19 | 2025-08-14 |  | Tower | TOWER | 76 | Add R8852E S9000x3+R8894E M1821x7, Dismantle | 0 | 2
S00778 | S102A_S00778OD_T3_KGLADAP | Sabah | 7123P | Swap | Maintain USP MOCN->On Hold->Swap | 2025 Q3 | HW | GTSB | 4.6 TSSR Approved |  | 2025-04-17 | 2025-05-19 |  | 2025-05-22 |  | Under Approval | 2025-06-03 | 2025-07-17 | E//Hannah | 2025-06-09 | SQ202501020343 - GTSB | DU00002862519 |  |  | 2025-09-10 | 2025-08-13 |  | Tower | TOWER | 76 | Add R8852E S9000x3+R8894E M1821x7+R8862A S2601x2+R8854 S2600x1, Dismantle | 0 | 2
S00779 | S102A_S00779OD_T3_KGMEMPAKAD | Sabah | 7070P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q3 | HW | GTSB | 4.6 TSSR Approved |  | 2025-01-23 | 2025-03-06 |  | 2025-03-14 |  | Under Approval | 2025-03-25 | 2025-05-19 |  | 2025-04-09 | SQ202501020343 - GTSB | DU00002862520 |  |  | 2025-06-09 | 2025-05-23 |  | Tower | TOWER | 75 | Add R8852E S9000x3+R9224E M1821x7, Dismantle | 0 | 2
S00780 | S102A_S00780OD_T3_KGDATONG | Sabah | 7125P | Swap | Maintain USP MOCN->On Hold->Swap | 2025 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2025-02-06 | 2025-02-26 |  | 2025-03-13 |  | Under Approval | 2025-04-07 | 2025-05-27 | CD//Sharidah | 2025-04-08 | SQ202501020343 - GTSB | DU00002862521 |  |  | 2025-05-31 | 2025-05-19 |  | Tower | TOWER | 60 | Add R8852E S9000x3+R8854E S1800x3+R8894E M1821x4, Dismantle | 0 | 3
S00781 | S102A_S00781OD_T3_KGROKAM | Sabah | 7192K | Swap |  | 131 single site mocn | SH | YPTT | 4.6 TSSR Approved |  | 2024-08-14 | 2024-09-02 |  | 2024-09-08 |  | Under Approval | 2024-09-10 | 2024-09-11 | CD//Mohidi Jaan | 2024-09-10 | 0809CD-Sabah-YPTT-BOQ Template(new contract) | DU00002862522 |  |  | 2024-10-23 | 2024-10-23 |  | Tower | TOWER | 76 | Add R8852E S9000 x3+R8894E M1821 x3,Dismantle | 0 | 0
S00782 | S102A_S00782OD_CB_KGMINITAMPAK | Sabah | 7071P | Swap | Maintain USP MOCN->On Hold->Swap | 2025 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2025-01-23 | 2025-01-31 |  | 2025-02-18 |  | Under Approval | 2025-04-07 | 2025-05-27 | CD//Sharidah | 2025-04-08 | SQ202501020343 - GTSB | DU00002862523 |  |  | 2025-06-28 | 2025-05-24 |  | Tower | TOWER | 75 | Add R8852E S9000x3+R8854E S1800x3+R8894E M1821x4, Dismantle | 0 | 2
S00783 | S102A_S00783OD_KGTARADAS | Sabah | 7193K | Swap |  | 2027 | AD | GTSB | 4.6 TSSR Approved |  | 2025-01-23 | 2025-03-06 |  | 2025-03-14 |  | Under Approval | 2025-12-01 | 2026-01-13 | E//Faiz | 2025-12-15 | SQ202501030033 - GTSB | DU00002862524 | [5 empty] | Tower | TOWER | 60 | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
S00909 | S105B_S00909OD_RANCANGANPADAS | Sabah | 7120K | Swap |  | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2024-04-18 | 2024-04-24 |  | 2024-04-30 |  | Closed | 2024-06-05 | 2024-06-10 | CD//Mohidi Jaan | 2024-06-09 | Celcom Digi_RAN-Futong-Standard PR TSS-Sabah-20240420 | DU00002862525 |  |  | 2024-06-30 | 2024-06-18 |  |  | BOOM | 60 | Add R8862A S9000 x3+R9224E M1821 x4+R8862A S2601 x2+R8854 S2600 x1,Dismantle | 0 | 2
S00950 | S096A_S00950OD_KGTAJAULAUT | Sabah | 7198K | Swap |  | 2027 | AD | YPTT | 4.6 TSSR Approved |  | 2023-11-14 | 2023-11-20 |  | 2025-04-14 |  | Under Approval | 2025-12-01 | 2026-01-13 | E//Faiz | 2025-12-15 | Celcom Digi_RAN-YPTT-TSS-Sabah-20231119 | DU00002862526 | [5 empty] | Tower | TOWER | 76 | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
S01112 | S104A_S01112OD_KGLOHAN | Sabah | 7199K | Swap |  | 2025 Q3 | AD | NR services | 4.6 TSSR Approved |  | 2025-01-08 | 2025-02-03 |  | 2025-03-06 |  | Under Approval | 2025-03-26 | 2025-05-20 | CD//Sharidah | 2025-04-08 | SQ202501020453 - NR Service | DU00002862527 |  |  | 2025-06-30 | 2025-05-10 |  | Monopole | LAMP_POLE | 24 | Add R8852E S9000x3+R8894E M1821x5,Dismantle | 0 | 13
S01127 | S089A_S01127OD_TMNSGLABUK | Sabah | 7200K | Swap |  | 131 single site mocn | MS | GTSB | 4.6 TSSR Approved |  | 2024-04-08 | 2024-04-21 |  | 2024-05-10 |  | Closed | 2024-05-23 | 2024-05-27 | CD//Mohidi Jaan | 2024-05-27 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240420 | DU00002862528 |  |  | 2024-08-30 | 2024-08-23 |  | Watertank | LAMP_POLE | 30 | Add R8862A S9000 x3+R8894E M1821 x2+R8862A S2601 x3+A9732 M1821 x1,Dismantle | 3 | 0
S01142 | S105A_S01142OD_PEKANTONGOD | Sabah | 7202K | Swap |  | 2024 Q4(single site MOCN)-L26 SSM | MS | GTSB | 4.6 TSSR Approved |  | 2024-04-23 | 2024-05-23 |  | 2024-05-27 |  | Closed | 2024-09-09 | 2024-09-10 | CD//Mohidi Jaan | 2024-09-10 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240503 | DU00002862529 |  |  | 2024-12-13 | 2024-11-26 |  | Tower | LAMP_POLE | 28 | Add R8852E S9000 x3+R8894E M1821 x1+R8862A S2601 x3+A9732 M1821 x2,Dismantle | 23 | 0
S01245 | Kg. Salyawak | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862530 | [6 empty] | #N/A
S01317 | S096A_S01317OD_KGSUANGPAI | Sabah | 7203K | Swap |  | 2024 Q3(single site MOCN) | MS | YPTT | 4.6 TSSR Approved |  | 2023-11-14 | 2023-11-21 |  | 2024-06-11 |  | Closed | 2024-06-11 | 2024-06-14 | CD//Mohidi Jaan | 2024-06-14 | Celcom Digi_RAN-YPTT-TSS-Sabah-20231119 | DU00002862531 |  |  | 2024-11-04 | 2024-10-18 |  | Tower | TOWER | 45 | Add R8862A S9000 x3+R9224E M1821 x3+R8862A S2601 x3,Dismantle | 0 | 0
S01343 | S112A_S01343OD_KGGAMBARONWEST | Sabah | 7206K | Swap |  | 2024 Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2024-04-08 | 2024-04-21 |  | 2024-05-13 |  | Closed | 2024-05-13 | 2024-05-14 | CD//Mohidi Jaan | 2024-05-14 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240420 | DU00002862532 |  |  | 2024-09-19 | 2024-09-12 |  | Monopole | RAPOLE | 30m | Add R8852E S9000 x3+R8894E M1821 x3+R8862A S2601 x3,Dismantle | 0 | 0
S01408 | S105A_S01408OD_SESBKARAMUNTING | Sabah | 7131K | Swap |  | 2024 Q3 | MS | GTSB | 4.6 TSSR Approved |  | 2024-07-09 | 2024-07-12 |  | 2024-07-18 |  | Under Approval | 2024-07-19 | 2024-07-22 | CD//Mohidi Jaan | 2024-07-22 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240813 | DU00002862533 |  |  | 2024-08-31 | 2024-08-16 |  | Monopole | POLE | 30 | Add R8862A S9000 x2+R9264H M901821 x1+R8862A S2601 x3+A9732 M1821 x2,Dismantle | 12 | 0
S01605 | S104A_S01605OD_CB_KGKEYEP | Sabah | 7215K | Swap |  | 2024 Q3(single site MOCN) | AD | Seri Pancar | 4.6 TSSR Approved |  | 2024-08-09 | 2024-08-26 |  | 2024-08-29 |  | Under Approval | 2024-09-03 | 2024-09-04 | CD//Mohidi Jaan | 2024-09-04 | 0809CD-Sabah-Seri Pancar-BOQ Template(new contract) | DU00002862534 |  |  | 2024-12-11 | 2024-12-03 |  | Tower | TOWER | 60 | Add R8862A S9000 x3+R9224E M1821 x3+R8862A S2601 x3,Dismantle | 0 | 0
S01610 | S104A_S01610OD_PORINGHOTSPRING | Sabah | 7216K | Swap |  | 2025 Q3 | AD | NR services | 4.6 TSSR Approved |  | 2025-01-06 | 2025-01-28 |  | 2025-03-13 |  | Under Approval | 2025-03-24 | 2025-05-20 | CD//Sharidah | 2025-04-09 | SQ202501020453 - NR Service | DU00002862535 |  |  | 2025-05-19 | 2025-05-15 |  | Tower | TOWER | 76 | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
S01615 | S105B_S01615OD_MRSMSANDAKAN | Sabah | 7140K | Swap |  | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2024-04-23 | 2024-04-25 |  | 2024-04-30 |  | Closed | 2024-06-05 | 2024-06-10 | CD//Mohidi Jaan | 2024-06-09 | Celcom Digi_RAN-Futong-Standard PR TSS-Sabah-20240503 | DU00002862536 |  |  | 2024-06-28 | 2024-06-18 |  | Tower | TOWER | 60 | Add R8862A S9000 x3+R9224E M1821 x5+R8862A S2601 x1+R8854 S2600 x2,Dismantle | 0 | 12
S01619 | S098B_S01619OD_AUMKARAUMPALMESTATE | Sabah | 7142K | Swap |  | 2024 Q3(single site MOCN) | MS | GTSB | 4.6 TSSR Approved |  | 2023-12-07 | 2023-12-29 |  | 2024-06-10 |  | Under Approval | 2024-06-13 | 2024-06-20 | CD//Mohidi Jaan | 2024-06-19 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231212 | DU00002862537 |  |  | 2024-09-21 | 2024-08-24 |  | Tower | TOWER | 60m | Add R8862A S9000 x3+R9224E M1821 x4+R8854 S2600 x1,Dismantle | 0 | 2
S01651 | S094A_S01651OD_CB_KGGANA | Sabah | 7225K | Swap |  | 131 single site mocn | MS | YPTT | 4.6 TSSR Approved |  | 2024-08-14 | 2024-08-26 |  | 2024-08-29 |  | Under Approval | 2024-09-02 | 2024-09-02 | CD//Mohidi Jaan | 2024-09-02 | 0809CD-Sabah-YPTT-BOQ Template(new contract) | DU00002862538 |  |  | 2024-10-23 | 2024-10-23 |  | Tower | TOWER | 30 | Add R8852E S9000 x3+R8894E M1821 x4+R8862A S2601 x2+R8854 S2600 x1,Dismantle | 0 | 3
S01662 | S104A_S01662OD_CB_KGMOHIMBOYON2 | Sabah | 7226K | Swap |  | 131 single site mocn | MS | Futong | 4.6 TSSR Approved |  | 2024-10-16 | 2024-10-21 |  | 2024-10-21 |  | Under Approval | 2024-10-23 | 2024-11-07 | CD//Mohidi Jaan | 2024-11-05 | 0809CD-Sabah-Futong-BOQ Template(new contract) | DU00002862539 |  |  | 2024-10-30 | 2024-10-30 |  | Tower | TOWER | 60M | Add R8862A S9000x3+R8862A S2601x3+R8894E M1821x2+A9732 M1821x1, Dismantle | 1 | 0
W00004 | W066V_W00004OD_UM25THKOLEJ | Central | 1353K | Swap |  | 2024 Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2024-04-22 | 2024-05-07 |  | 2024-05-08 |  | Closed | 2024-05-13 | 2024-07-09 | CD//Norhaliza | 2024-07-09 | CelcomDigi_RAN_YPTT_TSS_Central_20240513 | DU00002862540 |  |  | 2024-08-13 | 2024-08-12 |  | Pole | TRIPOD | s1 2 & 3=5m(wall mount boom-refer drawing for more detail) , s4=6m | Add R8862A S9000 x4+R8894E M1821 x5+R8862A S2601 x3+R8854 S2600 x1,Dismantle | 0 | 2
W00006 | W066U_W00006OD_JLNSYEDPUTRA | Central | 1354K | Swap |  | 2024 Q2 | MA | CCSMY | 4.6 TSSR Approved |  | 2024-06-07 | 2024-06-11 |  | 2024-06-12 |  | Closed | 2024-07-05 | 2024-07-10 | CD//Sapian | 2024-07-10 | CelcomDigi_RAN_CCSMY_TSS_Central_20240528 | DU00002862541 |  |  | 2024-07-29 | 2024-07-26 |  | BillBoard | MINI STRUCTURE | 22M | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle
W00023 | W066H_W00023OD_JLNAIRPANAS | Central | 1356K | Swap |  | 2024 Q1 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-02-26 | 2024-03-08 |  | 2024-03-14 |  | Closed | 2024-03-15 | 2024-04-02 | CD//Ali Akaram | 2024-04-01 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240303 | DU00002862542 |  |  | 2024-05-14 | 2024-05-08 |  | Pole | TRIPOD | 3m & 5m | Add R9264M M1821 x1+R9264H M901821 x3+R8862A S2601 x2+R8854 S2600 x1,Dismantle |  | 1
W00041 | W066S_W00041OD_BT5KLANGLAMA | Central | 1360K | Swap |  | 2024 Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-12-27 | 2024-02-21 |  | 2024-04-04 |  | Closed | 2024-04-05 | 2024-05-07 | CD//Sapian | 2024-05-06 | CelcomDigi_RAN_AllStar_TSS_Central_20231230 | DU00002862543 |  |  | 2024-07-13 | 2024-07-02 |  | In-Building System | BOOM | 6 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle
W00049 | W066Y_W00049OD_KGCHRSBARU | Central | 1726K | Decomm | Swap->Site Out->Decomm | 2024 Q3 | SS | YPTT | 4.6 TSSR Approved |  | 2023-10-30 | 2023-11-10 | 2025-07-10 | 2023-11-21 | 2025-07-24 | Closed | 2024-04-03 | 2024-05-09 | CD//Ali Akaram | 2024-05-09 | CelcomDigi_RAN_YPTT_TSS_Central_20231101 | DU00002862544 |  |  |  |  | 2025-07-09 | In-Building System | TRIPOD | 6 | Add R8862A S9000 x3+R9224E M1821 x4+R8862A S2601 x2+R8854 S2600 x1,Dismantle | 0 | 1
W00072 | W066H_W00072OD_TMWANGSAMAJU | Central | 1368K | Swap |  | 2024 Q1 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-03-27 | 2024-04-05 |  | 2024-04-09 |  | Closed | 2024-04-15 | 2024-05-07 | CD//Sapian | 2024-05-06 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240329 | DU00002862545 |  |  | 2024-08-27 | 2024-08-20 |  | In-Building System | BOOM | 6 | Add R8862A S9000 x3+R8894E M1821 x4+R8862A S2601 x2+R8854 S2600 x1,Dismantle |  | 3
W00084 | W066BB_W00084OD_BKTANGGERIKCHRS | Central | 1320K | Swap |  | 2024 Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2023-12-08 | 2023-12-12 |  | 2024-03-21 |  | Under Approval | 2024-03-26 | 2024-07-25 | CD//Norhaliza | 2024-07-25 | CelcomDigi_RAN_Magicell_TSS_Central_20231214 | DU00002862546 |  |  | 2024-07-27 | 2024-07-26 |  | Minimast | BOOM | 4 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle | 0 | 0
W00087 | W066AA_W00087OD_TMTMNMIDAH | Central | 1369K | Swap |  | 2024 Q3 | AI | GCI | 4.6 TSSR Approved |  | 2024-05-08 | 2024-05-30 |  | 2024-06-06 |  | Closed | 2024-06-07 | 2024-06-14 | CD//Sapian | 2024-06-13 | CelcomDigi_RAN_GCI_TSS_Central_20240513 | DU00002862547 |  |  | 2024-10-25 | 2024-10-19 |  | In-Building System | MINI STRUCTURE | 7 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle | 0 | 0
W00090 | W066R_W00090OD_TMBKTJALIL | Central | 1371K | Swap |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-26 | 2024-01-29 |  | 2024-03-25 |  | Closed | 2024-03-26 | 2024-04-15 | CD//Ali Akaram | 2024-04-15 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240128 | DU00002862548 |  |  | 2024-08-23 | 2024-08-15 |  | Minimast | BOOM | 6m | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle | 0 | 0
W00110 | W066K_W00110OD_TMTTC | Central | 1378K | Swap |  | 2026 | AI | CCSMY | 4.6 TSSR Approved |  | 2024-11-25 | 2024-11-27 |  | 2024-11-28 |  | Under Approval | 2024-12-01 | 2025-07-25 | CD//Norhaliza | 2025-04-28 | 0809CD-Central-CCSMY-BOQ Template(new contract) | DU00002862549 |  |  |  | 2025-02-22 |  | In-Building System | BOOM | 3 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle
W00115 | W066K_W00115OD_TMSETAPAK | Central | 1380K | Swap |  | 2024 Q1 | AI | CCSMY | 4.6 TSSR Approved |  | 2024-08-13 | 2024-08-15 |  | 2024-08-19 |  | Closed | 2024-08-20 | 2024-10-24 | CD//Ali Akaram | 2024-10-24 | 0809CD-Central-CCSMY-BOQ Template(new contract) | DU00002862550 |  |  | 2025-02-28 | 2025-02-24 |  | In-Building System | BOOM | 7m | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle
W00132 | W066U_W00132OD_JLNTRAVERS | Central | 1382K | Swap |  | 2024 Q2 | SS | CCSMY | 4.6 TSSR Approved |  | 2024-01-03 | 2024-01-19 |  | 2024-01-29 |  | Closed | 2024-02-02 | 2024-02-28 | CD//Ali Akaram | 2024-02-28 | BOQ CelcomDigi_RAN_CCSMY_Standard PR TSS_Central_20240110 | DU00002862551 |  |  | 2024-07-18 | 2024-07-04 |  | Pole | BOOM | 6 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle
W00212 | W066S_W00212OD_KINRARA | Central | 1391K | Swap |  | 2024 Q3 | MA | GTSB | 4.6 TSSR Approved |  | 2023-12-05 | 2023-12-07 |  | 2024-03-21 |  | Closed | 2024-03-25 | 2024-05-03 | CD//Ali Akaram | 2024-05-03 | CelcomDigi_RAN_GTSB_TSS_Central_20231208 | DU00002862552 |  |  | 2024-08-17 | 2024-08-14 |  | In-Building System | BOOM | 7 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle | 0 | 0
W00229 | W066Q_W00229OD_PR_SALAKSELATAN | Central | 1392K | Swap |  | 2024 Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-11-16 | 2023-11-27 |  | 2024-03-25 |  | Closed | 2024-03-26 | 2024-04-15 | CD//Sapian | 2024-04-08 | CelcomDigi_RAN_AllStar_TSS_Central_20231119 | DU00002862553 |  |  | 2024-07-16 | 2024-07-12 |  | In-Building System | BOOM | 6 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle | 0 | 0
W00238 | B064C_W00238OD_MINTHOTEL | Central | 1727K | Swap |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-03-14 | 2024-03-20 |  | 2024-04-25 |  | Closed | 2024-04-28 | 2024-05-16 | CD//Ali Akaram | 2024-05-16 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240316 | DU00002862554 |  |  | 2025-01-07 | 2025-01-03 |  | In-Building System | MINI STRUCTURE | 5 | Add R8862A S9000 x3+R8894E M1821 x3+R8862A S2601 x3,Dismantle | 0 | 0
W00258 | W066P_W00258OD_JLNSGBESI | Central | 1753K | Swap |  | 2024 Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2023-12-23 | 2023-12-28 |  | 2024-03-21 |  | Under Approval | 2024-03-26 | 2024-07-25 | CD//Norhaliza | 2024-07-25 | CelcomDigi_RAN_Magicell_TSS_Central_20231224 | DU00002862555 |  |  | 2024-08-27 | 2024-08-24 |  | Minimast | BOOM | 5 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle | 0 | 0
W00260 | W066J_W00260OD_SWANGSA2 | Central | 1397K | Swap |  | 2024 Q1 | CR | GCI | 4.6 TSSR Approved |  | 2024-02-21 | 2024-03-15 |  | 2024-05-27 |  | Under Approval | 2024-05-29 | 2024-07-03 | CD//Ali akaram | 2024-07-03 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240225 | DU00002862556 |  |  | 2024-12-28 | 2024-07-24 |  | H-bracket pole | TOWER | 8 | Add R9264H M901821 x4+R8862A S2601 x4,Dismantle
W00268 | W066R_W00268OD_PR_SEKBKTJALIL | Central | 1398K | Swap | Swap->On Hold->Swap | 2026 | AI | Magicell | 4.6 TSSR Approved |  | 2024-01-04 | 2024-01-16 |  | 2024-03-22 |  | Closed | 2024-03-26 | 2024-04-18 | CD//Ali Akaram | 2024-04-18 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240108 | DU00002862557 | [6 empty] | WATER TANK | 24m | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle | 0 | 0
W00511 | W066P_W00511OD_PR_SOONFATT | Central | 1754K | Swap |  | 2024 Q2 | AD | GTSB | 4.6 TSSR Approved |  | 2023-12-15 | 2023-12-26 |  | 2024-01-10 |  | Closed | 2024-01-22 | 2024-02-13 | CD//Ali akaram | 2024-02-09 | CelcomDigi_RAN_GTSB_TSS_Central_20231224 | DU00002862558 |  |  | 2024-06-25 | 2024-06-25 |  | In-Building System | RT Minimast | 9 | Add R8862A S9000 x3+R8894E M1821 x5+R8862A S2601 x1+R8854 S2600 x2,Dismantle |  | 23
W00584 | W066U_W00584OD_PR_JLNISTANA2 | Central | 1408K | Swap |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-01-16 | 2024-01-29 |  | 2024-04-04 |  | Closed | 2024-04-15 | 2024-12-24 | CD//Norhaliza | 2024-12-23 | 0920CD-Central-Ascentrack-BOQ Template (old contract) | DU00002862559 |  |  | 2024-08-25 | 2024-08-23 |  | Monople Tree | SHARING STRC SBC | 30 | Add R8862A S9000 x3+R9224E M1821 x4+R8862A S2601 x2+R8854 S2600 x1,Dismantle | 0 | 1
W00589 | KEM SG BESI 3 | Central | 1409K | Decomm | Swap->On hold->Decomm | 2024 Q3 | AI | Magicell | 4.6 TSSR Approved |  | 2024-07-24 |  | 2024-08-01 |  | 2024-08-08 |  | 2024-12-23 | 2025-01-14 | CD//Norhaliza | 2024-12-31 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240510 - Decomm | DU00002862560 |  |  |  |  | 2024-11-29 |  | MONOPOLE
W00590 | W066S_W00590OD_KELABOUG | Central | 1410K | Swap |  | 2024 Q3 | SH | AllStar | 4.6 TSSR Approved |  | 2023-12-12 | 2023-12-29 |  | 2024-04-05 |  | Closed | 2024-04-18 | 2024-05-13 | CD//Ali Akaram | 2024-05-13 | CelcomDigi_RAN_AllStar_TSS_Central_20231224 | DU00002862561 |  |  | 2024-06-30 | 2024-05-17 |  | Monopole | LAMP_POLE | 24 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle | 0 | 0
W00594 | W066U_W00594OD_TMBKTPETALING | Central | 1411K | Swap |  | 2024 Q3 | MA | GCI | 4.6 TSSR Approved |  | 2024-05-30 | 2024-06-05 |  | 2024-06-13 |  | Under Approval | 2024-06-14 | 2024-11-12 | CD//Norhaliza | 2024-11-11 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240605 | DU00002862562 |  |  | 2024-11-22 | 2024-11-11 |  | In-Building System | BOOM | 11 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle | 0 | 0
W00641 | W066N_W00641OD_ISTANATGANU | Central | 1756K | Swap |  | 2024 Q2 | SS | Magicell | 4.6 TSSR Approved |  | 2024-01-29 | 2024-02-01 |  | 2024-02-15 |  | Under Approval | 2024-02-19 | 2024-07-26 | CD//Norhaliza | 2024-07-25 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240202 | DU00002862563 |  |  | 2024-09-02 | 2024-08-28 |  | Lampole | LAMP_POLE | 20 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle
W00780 | W066V_W00780OD_PSSBKTBANDARAYA | Central | 1417K | Swap |  | 2024 Q2 | MA | Ascentrack | 4.6 TSSR Approved | 15-3 - ZTE planner to update slide ¦ 06022024 discussed with Ammar, cannot swap antenna due to pylon door will blok antenna//26012024 no space to swap antenna inside pylon petronas | 2024-01-08 | 2024-01-18 |  | 2024-01-24 |  | Closed | 2024-02-05 | 2024-06-20 | CD//Sapian | 2024-06-18 | 0920CD-Central-Ascentrack-BOQ Template (old contract) | DU00002862564 |  |  | 2024-07-04 | 2024-07-02 |  | Petronas Pylon | PYLON | 25 | Add R9264M M1821 x3+R8862A S2601 x3,Dismantle | 0 | 0
W00848 | W066C_W00848OD_KM2E33DUKEHWY | Central | 1418K | Swap |  | 2024 Q1 | MA | Magicell | 4.6 TSSR Approved |  | 2024-03-01 | 2024-03-07 |  | 2024-03-08 |  | Closed | 2024-03-08 | 2024-03-29 | CD//Ali Akaram | 2024-03-29 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240303 | DU00002862565 |  |  | 2024-04-29 | 2024-04-28 |  | Tower | GUYED MAST | 24M | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle
W01128 | W066W_W01128OD_JALANUTHANT | Central | 1757K | Swap | Swap->On Hold->Swap->On Hold->Site Out->Swap | 2024 Q2 | SS | Magicell | 4.6 TSSR Approved | 13/3- R9264H cannot fit in RRU cabinet ¦¦ 29/1 - Cluster Antenna: propose major CME Structure on top by site Owner | 2023-12-22 | 2023-12-28 |  | 2024-01-22 |  | Under Approval | 2024-04-04 | 2024-04-15 | CD//Sapian | 2024-04-08 | CelcomDigi_RAN_Magicell_TSS_Central_20231224 | DU00002862566 |  |  | 2026-01-14 | 2025-11-05 |  | Monopole | LAMP_POLE | 17M | Add R8894E M1821x3+R8862A S2601x3,Dismantle
W01138 | W066V_W01138OD_UMPALAPES | Central | 1432K | Swap |  | 2024 Q2 | MA | GTSB | 4.6 TSSR Approved |  | 2024-04-26 | 2024-05-15 |  | 2024-05-17 |  | Closed | 2024-05-17 | 2024-05-24 | CD//Ali Akaram | 2024-05-24 | CelcomDigi_RAN_GTSB_TSS_Central_20240513 | DU00002862567 |  |  | 2024-07-11 | 2024-06-28 |  | Monople Tree | MONOPOLE | 24 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle
W01184 | W066H_W01184OD_JLN4A27ASEK2WANGSAMAJU | Central | 1434K | Swap |  | 2024 Q1 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-23 | 2023-11-29 |  | 2023-12-29 |  | Closed | 2024-01-03 | 2024-01-11 | CD//Sapian | 2024-01-09 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231126 | DU00002862568 |  |  | 2024-04-30 | 2024-04-30 |  | In-Building System | BOOM | 6 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle
W01191 | W066W_W01191OD_JLNLANGGAKGOLF | Central | 1758K | Swap |  | 2024 Q2 | SS | Magicell | 4.6 TSSR Approved |  | 2024-02-26 | 2024-03-01 |  | 2024-03-05 |  | Closed | 2024-03-08 | 2024-03-21 | CD//Sapian | 2024-03-21 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240303 | DU00002862569 |  |  | 2024-08-29 | 2024-08-26 |  | In-Building System | TRIPOD | 6m | Add R9264H M901821 x3,Dismantle
W01294 | W066V_W01294OD_JLN_MAAROF_BANGSAR | Central | 1446K | Swap |  | 2024 Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-11 | 2023-11-16 |  | 2024-03-08 |  | Closed | 2024-09-18 | 2024-11-27 | CD//Sapian | 2024-11-27 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231113 | DU00002862570 |  |  | 2024-09-29 | 2024-09-29 |  | Lampole | LAMP_POLE | 18m | Add R9264M M1821 x3+R8862A S2601 x3,Dismantle | 0 | 0
W01306 | W066S_W01306OD_JLN_JALIL_PERKASA2 | Central | 1448K | Swap |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved | ¦ 0404 : Antenna direct mounted on lampole, proposed new bracket c/w boom | 2023-11-25 | 2023-12-01 |  | 2024-03-25 |  | Closed | 2024-04-05 | 2024-05-07 | CD//Sapian | 2024-05-06 | CelcomDigi_RAN_GTSB_TSS_Central_20231126 | DU00002862571 |  |  | 2024-09-11 | 2024-09-05 |  | Lampole | STREET POLE | 17 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle | 0 | 0
W01309 | W066J_W01309OD_JLNMAKTAB_UTMKL | Central | 1450K | Swap |  | 2024 Q1 | MA | Ascentrack | 4.6 TSSR Approved | 21/3- New strcuture already available//20/3 - Cluster Antenna: propose major CME Structure on top by site Owner. | 2024-03-01 | 2024-03-15 |  | 2024-03-29 |  | Closed | 2024-03-29 | 2024-11-12 | CD//Norhaliza | 2024-11-11 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240303 | DU00002862572 |  |  | 2024-08-04 | 2024-08-02 |  | Lampole | STREET POLE | 18m | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle
W01340 | W066T_W01340OD_KM16_NPEHWY2 | Central | 1453K | Swap |  | 2024 Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-12-07 | 2023-12-15 |  | 2024-04-15 |  | Closed | 2024-04-15 | 2024-05-13 | CD//Ali Akaram | 2024-05-13 | CelcomDigi_RAN_Allstar_TSS_Central_20231208 | DU00002862573 |  |  | 2024-05-23 | 2024-05-23 |  |  | LAMP_POLE | 18 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle | 0 | 0
W01342 | W066V_W01342OD_JLNJELUTONG_OF_JLNDSARA | Central | 1454K | Swap |  | 2024 Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-07 | 2023-11-10 |  | 2023-11-25 |  | Closed | 2024-01-08 | 2024-01-15 | CD//Sapian | 2024-01-15 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231113 | DU00002862574 |  |  | 2025-09-23 | 2025-09-13 |  | Lampole | LAMP_POLE | 18 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle
W01348 | W066U_W01348OD_TMN_SEPUTEH | Central | 1456K | Swap |  | 2024 Q3 | AI | Ascentrack | 4.6 TSSR Approved |  | 2023-11-10 | 2023-11-14 |  | 2023-11-22 |  | Closed | 2024-04-04 | 2024-11-12 | CD//Norhaliza | 2024-11-11 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231113 | DU00002862575 |  |  | 2024-08-25 | 2024-08-23 |  | Lampole | LAMP_POLE | 18m | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle | 0 | 0
W01363 | W066V_W01363OD_KG_PANTAIDALAM | Central | 1460K | Swap |  | 2024 Q2 | YZ | Solusi | 4.6 TSSR Approved |  | 2023-11-23 | 2023-11-24 |  | 2024-03-01 |  | Under Approval | 2024-03-05 | 2024-09-23 | CD//Norhaliza | 2024-09-21 | BOQ CelcomDigi_RAN_Solusi_Standard PR TSS_Central_20240128 | DU00002862576 |  |  | 2024-09-09 | 2024-07-20 |  | Lampole | LAMP_POLE | 19 | Add R8862A S9000 x3+R8894E M1821 x4+R8862A S2601 x2+R8854 S2600 x1,Dismantle | 0 | 2
W01366 | W066AA_W01366OD_JLNMIDAHBESAR_TMNMIDAH | Central | 1461K | Swap |  | 2024 Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-11-15 | 2023-11-29 |  | 2024-04-15 |  | Closed | 2024-04-16 | 2024-05-07 | CD//Sapian | 2024-05-07 | CelcomDigi_RAN_AllStar_TSS_Central_20231116 | DU00002862577 |  |  | 2024-07-16 | 2024-07-13 |  | Lampole | LAMP_POLE | 18 | Add R8862A S9000 x3+R9224E M1821 x4+R8862A S2601 x2+R8854 S2600 x1,Dismantle | 0 | 3
W01535 | B057D_W01535OD_TMNKOPERASIPOLIS1 | Central | 1326K | Swap |  | 2024 Q1 | SS | Magicell | 4.6 TSSR Approved |  | 2023-11-24 | 2023-11-27 |  | 2024-01-02 |  | Closed | 2024-01-09 | 2024-03-18 | CD//Norhaliza | 2024-03-15 | CelcomDigi_RAN_Magicell_TSS_Central_20231126 | DU00002862578 |  |  | 2024-03-30 | 2024-03-26 |  | Lampole | LAMP_POLE | 18 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle
W01536 | W066AA_W01536OD_LNJAYABTR2 | Central | 1512K | Swap |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-24 | 2023-11-29 |  | 2024-04-16 |  | Closed | 2024-04-20 | 2024-08-15 | CD//Norhaliza | 2024-08-15 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231126 | DU00002862579 |  |  | 2024-07-25 | 2024-07-25 |  | Lampole | LAMP_POLE | 18 | Add R8862A S9000 x3+R9224E M1821 x5+R8862A S2601 x1+R8854 S2600 x2,Dismantle | 0 | 13
W01539 | W066Z_W01539OD_PR_KM1MEXHWY2 | Central | 1763K | Swap |  | 2024 Q2 | AD | GTSB | 4.6 TSSR Approved | 4/3 RRU propose 3 on top 3 in cabinet//Dualbay cabinet, space limitation to install R9264H//0201- Email sent to SA to request SO to provide Cabinet Spec// 0122 - TSSR rejected, power solution wrong. | 2023-12-28 | 2024-01-02 |  | 2024-01-17 |  | Closed | 2024-03-04 | 2024-03-15 | CD//Sapian | 2024-03-15 | CelcomDigi_RAN_GTSB_TSS_Central_20231230 | DU00002862580 |  |  | 2024-06-26 | 2024-06-19 |  | Lampole | 20m Lampole | 18 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle
W01545 | W066V_W01545OD_BULATANUM2 | Central | 1513K | Swap |  | 2024 Q2 | AI | AllStar | 4.6 TSSR Approved | 0304 RRU proceed install 3 on top, 3 in cabinet//¦ 0201 : No space issue to add RRU inside cabinet, only cooling system required upgrade | 2024-01-05 | 2024-01-24 |  | 2024-01-26 |  | Closed | 2024-02-01 | 2024-02-08 | CD//Sapian | 2024-02-08 | BOQ CelcomDigi_RAN_AllStar_Standard PR TSS_Central_20240110 | DU00002862581 |  |  | 2024-08-27 | 2024-07-26 |  | Lampole | LAMP_POLE | 18 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle
W01531 | W066V3_W01531IB_TNBPLATINUM | Central | 1516K | Swap |  | 2024 Q2 | AI | GCI | 4.6 TSSR Approved |  | 2024-04-02 | 2024-04-17 |  | 2024-05-07 |  | Closed | 2024-05-10 | 2024-08-22 | CD//Sofiah | 2024-08-22 | CelcomDigi_RAN_GCI_TSS_Central_20240513 | DU00002862582 |  |  | 2024-07-18 | 2024-07-16 |  | Portables BTS | INBUILDING |  | Add R8862A S2100 x6+R8862A S2601 x6+R8862A S1800 x6,Dismantle | 0 | 0
B01289 | B01289OD_CRYSTAL_CROWN_HOTEL_4G | Central | 1329K | Swap |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-03-21 | 2024-04-01 |  | 2024-04-04 |  | Under Approval | 2024-04-05 | 2024-06-20 | CD//Norhaliza | 2024-06-19 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240323 | DU00002862583 |  |  | 2024-05-31 | 2024-05-29 |  | In-Building System | TRIPOD | 4m & 5.5m | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle | 0 | 0
1108B | SMARTTUNNEL | Central |  | MOCN As-Is | Modernization->Site Out->MOCN As-Is | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-10-27 | 2023-11-07 |  | 2024-03-05 |  | Closed | 2024-03-07 | 2024-03-07 | E//Nazrul | 2024-03-07 | CelcomDigi_RAN_Datasco_TSS_Central_20231028 | DU00002862584 | [5 empty] | Portables BTS | In-building system |  | Reuse Existing RRU
1174B | Damansara Uptown 1 IB (Maxis) | Central |  | Modernization | Modernization->On hold->Modernization | 2024 Q3 | CR | GCI | 4.6 TSSR Approved |  | 2024-03-13 | 2024-03-20 |  | 2024-04-19 |  | Under Approval | 2024-04-24 | 2024-07-26 | E//Nazrul | 2024-07-26 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240316 | DU00002862585 |  |  | 2024-10-29 | 2024-10-17 |  | Portables BTS | In-building system |  | Add R8862A S2100 x1,Dismantle
1175B | Damansara Uptown 2 IB | Central |  | Modernization |  | 2024 Q3 | SS | GCI | 4.6 TSSR Approved |  | 2023-11-10 | 2023-11-15 |  | 2024-04-18 |  | Closed | 2024-04-19 | 2024-04-22 | E//Nazrul | 2024-04-19 | CelcomDigi_RAN_GCI_TSS_Central_20231113 | DU00002862586 |  |  | 2024-05-28 | 2024-05-28 |  |  | In-building system |  | Add R8894E M1821 x1,Dismantle R8882-GUL1812 x1+R8862A S2100(A6A) x1
1246B | Jaya 33 IB | Central |  | Decomm | Modernization->Site out->Decomm | 2024 Q3 | AI | GCI | 4.6 TSSR Approved |  | 2024-03-31 | 2024-04-05 | 2025-07-29 | 2024-04-08 | 2025-07-02 | Under Approval | 2024-04-15 | 2025-10-17 | E//Nazrul | 2025-07-02 | SQ202506120286 | DU00002862587 |  |  |  |  | 2025-09-25 | Portables BTS | In-building system | NA
1488B | Menara Exxon Mobil IB | Central |  | Modernization | Modernization->TBD->On Hold->Modernization | 2024 Q2 | AI | CCSMY | 4.6 TSSR Approved |  | 2024-06-07 | 2024-06-10 |  | 2024-06-11 |  | Closed | 2024-06-12 | 2024-06-12 | E//Nazrul | 2024-06-12 | 0607Central-CCSMY-BOQ Template | DU00002862588 |  |  | 2025-04-25 | 2025-04-23 |  | Portables BTS | In-building system |  | Add R8862A S2100 x1+R8862A S2601 x2+R8862A S1800 x2,Dismantle R8882-GUL1812 x1
1721B | Menara PKNS PJ IB | Central |  | Modernization |  | 2024 Q3 | BY | DATASCO | 4.6 TSSR Approved |  | 2024-03-29 | 2024-04-02 |  | 2024-04-08 |  | Closed | 2024-04-09 | 2024-04-15 |  | 2024-04-09 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_202400403 | DU00002862589 |  |  | 2024-04-30 | 2024-04-24 |  | Portables BTS | In-building system | NA | Add R8862A S9000 x1+R8892N M1821 x1,Dismantle R8882-GUL1812 x1+R8862A S2100(A6A) x1 | 0 | 0
W00973 | W066Q_W00973OD_MASJID_ALKHASYIIN_DESAPETALING | Central |  | Decomm |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-01-11 |  |  |  | 2024-02-01 |  | 2024-02-02 |  | CD//Ali Akaram | 2024-02-15 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240115 | DU00002862590 |  | Missing FE part |  |  | 2024-07-29 |  | MINARATE
B00726 | B064B_B00726OD_CHERASJAYA1 | Central |  | Decomm |  | 2024 Q4 | MS | Solusi | 4.6 TSSR Approved |  | 2024-07-13 |  |  |  | 2024-09-04 |  | 2024-09-06 | 2025-01-14 | CD//Ali Akaram | 2024-09-12 | 0724Central-Solusi-BOQ Template | DU00002862591 |  |  |  |  | 2024-09-11 |  | TOWER
1745B | Bangsar Shopping Complex IB | Central |  | Modernization | Modernization->On hold->Modernization | 2024 Q2 | AI | YPTT | 15.2 TI Done without TSSR approval |  | 2024-05-15 | 2024-05-17 |  | 2024-05-22 |  | Closed | 2024-05-23 |  | E//Nazrul |  | CelcomDigi_RAN_YPTT_TSS_Central_20240517 | DU00002862592 |  |  | 2024-07-27 | 2024-07-23 |  |  | In-building system |  | Add R8862A S2100 x3,Dismantle
1825A | KLIA Contact Pier | Central |  | Decomm | Modernization->On hold->Decomm | 2025 Q1 | AI | GCI | 4.6 TSSR Approved |  | 2025-04-23 |  | 2025-05-16 | 2025-06-17 | 2025-06-17 | Under Approval | 2025-06-20 | 2025-07-14 | E//Nazrul | 2025-06-23 | 0924CD-Central-GCI-BOQ Template(new contract) | DU00002862593 | [6 empty] | In-building system |  | Add R8852E S9000x2+R8894E M1821x2+R8862A S2601x2, Dismantle R8860E-GU908x1+R8882-GUL1812x1+R8862A S2100(A6A)x2 | 0 | 0
1848A | Ampang Park LRT | Central |  | Modernization | Modernization->On hold->Decomm->Decomm->On Hold->Modernization | 2024 Q2 | AI | Magicell | 4.6 TSSR Approved |  | 2024-01-31 | 2024-08-13 |  | 2024-08-21 | 2024-03-19 | Under Approval | 2024-09-26 | 2024-09-27 | E//Nazrul | 2024-09-27 | 0813CD-Central-Magicell-BOQ Template(new contract) | DU00002862594 |  |  | 2024-12-22 | 2024-12-17 |  | Portables BTS | In-building system | NA | Add R8862A S9000 x1+R8894E M1821 x1,Dismantle R8882-GUL1812 x1+R8862A S2100(A6A) x1 | 0 | 0
2068A | One Utama Phase 3 IB | Central |  | Modernization |  | 2024 Q3 | BY | GCI | 4.6 TSSR Approved |  | 2023-12-18 | 2023-12-22 |  | 2024-03-07 |  | Under Approval | 2024-03-07 | 2024-12-10 | E//Nazrul | 2024-12-09 | CelcomDigi_RAN_GCI_TSS_Central_20231224 | DU00002862595 |  |  | 2024-08-21 | 2024-08-16 |  | Portables BTS | In-building system |  | Add R8862A S2100 x4+R8894E M1821 x1+R8862A S2601 x4+R8862A S1800 x4,Dismantle R8882-GUL1812 x4+R8882-L268 x4+R8892E M1821(BAA) x1+R8840 U216 x4
2118A | VIVA MALL IB | Central |  | Modernization |  | 2024 Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2023-10-17 | 2023-10-18 |  | 2023-10-23 |  | Closed | 2023-11-21 | 2023-11-22 |  | 2023-11-21 | CelcomDigi_RAN_Magicell_TSS_Central_20231018 | DU00002862596 |  |  | 2023-11-16 | 2023-10-24 |  | In-Building System | In-building system |  | Reuse exisiting IBC RRU | 0 | 0
2201A | TESCO Scott Garden IB | Central |  | Modernization |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-12-04 | 2024-01-05 |  | 2024-03-05 |  | Closed | 2024-04-05 | 2024-04-05 | E//Nazrul | 2024-04-05 | CelcomDigi_RAN_Datasco_TSS_Central_20231208 | DU00002862597 |  |  | 2024-05-03 | 2024-04-24 |  | Portables BTS | In-building system | NA | Add R8862A S2100 x2+R8892N M1821 x1+R8862A S1800 x2,Dismantle R8882 S1800(B) x2+R8881 S2100 x2+R8892E M1821(BAA) x1 | 0 | 0
2563A | Menara IGB | Central |  | Decomm | Modernization->Site out->Decomm | 2024 Q2 | AI | GCI | 4.6 TSSR Approved |  | 2025-07-19 |  | 2025-07-29 |  | 2025-08-26 | To be Submitted | 2025-09-08 |  |  | 2025-09-08 | SQ202512150587 | DU00002862598 |  |  |  |  | 2025-09-25 |  | In-building system
2607A | Damansara Uptown 3 IB | Central |  | Modernization | Modernization->On hold->Modernization | 2024 Q3 | MA | GCI | 4.6 TSSR Approved |  | 2024-03-13 | 2024-03-20 |  | 2024-04-04 |  | Closed | 2024-04-04 | 2024-04-15 | E//Nazrul | 2024-04-05 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240316 | DU00002862599 |  |  | 2024-06-19 | 2024-06-05 |  | Portables BTS | In-building system |  | Add R8862A S9000 x1+R8894E M1821 x1,Dismantle R8882-GUL1812 x1+R8862A S2100(A6A) x1
2800A | KLCC Suria Indoor(Maxis) | Central |  | Modernization | Modernization->On hold->Modernization | 2024 Q2 | AI | Magicell | 4.6 TSSR Approved |  | 2024-04-23 | 2024-04-29 |  | 2024-04-30 |  | Closed | 2024-04-30 | 2024-05-07 | E//Nazrul | 2024-05-06 | CelcomDigi_RAN_Magicell_TSS_Central_20240424 | DU00002862600 |  |  | 2024-11-25 | 2024-10-10 |  | Portables BTS | In-building system |  | Add R8862A S2100 x4+R8894E M1821 x2+R8862A S1800 x3,Dismantle R8882-GUL1812 x2+R8892E M1821(BAA) x2
2839B | South City Plaza Indoor -CAS | Central |  | Modernization |  | 2024 Q3 | SS | GCI | 4.6 TSSR Approved |  | 2023-10-30 | 2023-11-03 |  | 2023-11-29 |  | Closed | 2024-04-17 | 2024-04-23 |  | 2024-04-17 | CelcomDigi_RAN_GCI_TSS_Central_20231101 | DU00002862601 |  |  | 2024-08-07 | 2024-08-05 |  | Portables BTS | In-building system | NA | Add R8894E M1821 x2,Dismantle R8892E M1821(BAA) x1
S01484 | S091A_S01484OD_CB_KGGABAN | Sabah |  | Decomm |  | 2024 Q3(single site MOCN) | AD | Seri Pancar | 4.6 TSSR Approved |  | 2024-06-13 |  |  |  | 2024-06-22 |  | 2024-06-24 | 2024-08-01 | CD//Ray Amos | 2024-06-26 | 0618Sabah-Seri Pancar-BOQ Template (template) | DU00002862602 |  |  |  |  | 2024-10-21 |  | TOWER
S01570 | S091A_S01570OD_CB_KGPARISKWANTAS | Sabah |  | Decomm |  | 2024 Q3(single site MOCN) | SHA | Seri Pancar | 4.6 TSSR Approved |  | 2024-06-14 |  |  |  | 2024-07-05 |  | 2024-07-11 | 2024-08-16 | CD//Ray Amos | 2024-07-12 | 0618Sabah-Seri Pancar-BOQ Template (template) | DU00002862603 |  |  |  |  | 2024-09-13 |  | TOWER
S00573 | S091A_S00573OD_GENTINGTANJUNGESTATE | Sabah |  | Decomm |  | 2024 Q3(single site MOCN) | SHA | Seri Pancar | 4.6 TSSR Approved |  | 2024-06-13 |  |  |  | 2024-07-10 |  | 2024-07-11 | 2024-08-16 | CD//Ray Amos | 2024-07-12 | 0618Sabah-Seri Pancar-BOQ Template (template) | DU00002862604 |  |  |  |  | 2024-09-18 |  | TOWER
2879A | Carrefour Cheras IB | Central |  | Modernization |  | 2024 Q3 | SHA | YPTT | 4.6 TSSR Approved |  | 2024-07-18 | 2024-07-22 |  | 2024-07-30 |  | Under Approval | 2024-07-31 | 2024-08-01 | E//Nazrul | 2024-08-01 | 0725Central-YPTT-BOQ Template(new contract) | DU00002862605 |  |  | 2024-11-08 | 2024-11-05 |  | In-Building System | In-building system |  | Add R8862A S9000 x1+R8894E M1821 x1,Dismantle R8892E M1821(BAA) x1
S01211 | S091A_S01211OD_KGLUNGMANIS | Sabah |  | Decomm |  | 2024 Q4(single site MOCN)-L2126 SSM | MS | Seri Pancar | 4.6 TSSR Approved |  | 2024-08-02 |  | 2024-08-05 |  | 2024-08-07 |  | 2024-08-08 | 2024-10-31 | CD//Ray Amos | 2024-08-09 | 0802CD-Sabah-Seri Pancar-BOQ Template(new contract)/0802MW-Sabah-Seri Pancar-BOQ Template(new contract) | DU00002862606 |  |  |  |  | 2025-11-29 |  | TOWER
2887A | Hilton Hotel KL Sentral Indoor | Central |  | Modernization | Modernization->On hold->Decomm->Modernization | 2024 Q2 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-01-02 | 2024-03-26 |  | 2024-06-11 |  | Closed | 2024-06-12 | 2024-06-12 | E//Nazrul | 2024-06-12 | 0626Central-Datasco-BOQ Template (template) | DU00002862607 |  |  | 2024-07-04 | 2024-07-04 |  |  | In-building system |  | Add R8894E M1821 x3+R8862A S1800 x1,Dismantle R8882-GUL1812 x1+R8892E M1821(BAA) x3 | 0 | 0
2901B | The Village Shopping Center | Central |  | Modernization | Modernization->On hold->Modernization | 2024 Q2 | AI | YPTT | 4.6 TSSR Approved |  | 2024-04-03 | 2024-04-17 |  | 2024-04-23 |  | Closed | 2024-04-24 | 2024-04-24 | E//Nazrul | 2024-04-24 | BOQ_Celcom Digi_RAN-YPTT-Standard PR TSS-20240407 | DU00002862608 |  |  | 2024-06-22 | 2024-06-07 |  |  | In-building system | IBC | Reuse existing RRU, need to check and reconnect RRU
2973B | PJC | Central |  | Modernization | Modernization->Decomm->Modernization | 2024 Q3 | SHA | DATASCO | 4.6 TSSR Approved |  | 2024-07-09 | 2024-08-12 | 2024-07-14 | 2024-08-14 | 2024-07-16 | Under Approval | 2024-09-03 | 2024-09-04 | E//Nazrul | 2024-09-03 | 0813CD-Central-Datasco-BOQ Template(new contract) | DU00002862609 |  |  | 2024-12-19 | 2024-12-16 |  | Pole | In-building system |  | Add R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 0 | 0
3039A | Grand Hyatt Hotel KL IBC | Central |  | Modernization |  | 2024 Q2 | SY1 | Magicell | 4.6 TSSR Approved |  | 2024-02-22 | 2024-02-27 |  | 2024-03-04 |  | Closed | 2024-03-06 | 2024-03-07 | E//Nazrul | 2024-03-07 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240225 | DU00002862610 |  |  | 2024-07-22 | 2024-07-18 |  | Portables BTS | In-building system |  | Add R8894E M1821 x3+R8862A S2601 x3,Dismantle R8882 S1800(B) x1+R8862A S1800(A6A) x1+R8862A S2100(A6A) x3+R8892E M1821(BAA) x1
3570A | PPUM OBSTETRIC & PAEDIATRIC IB | Central |  | Modernization | Modernization->On hold->Modernization | 2024 Q3 | SS | YPTT | 4.6 TSSR Approved |  | 2024-02-07 | 2024-02-16 |  | 2024-03-04 |  | Closed | 2024-03-14 | 2024-06-04 |  | 2024-06-04 | BOQ_Celcom Digi_RAN-YPTT-Standard PR TSS-20240218 | DU00002862611 |  |  | 2024-05-27 | 2024-05-27 |  |  | In-building system |  | Add R8894E M1821 x4,Dismantle R8892E M1821(BAA) x4
W01397 | W066V_W01397OD_JLNBKTPANTAI_TMNBKTPANTAI | Central |  | Decomm |  | 2024 Q2 | MS | Ascentrack | 4.6 TSSR Approved |  | 2023-11-22 |  |  |  | 2023-12-25 |  | 2024-01-16 |  | CD//Norhaliza | 2024-01-30 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231126 | DU00002862612 |  | Missing FE part |  |  | 2024-07-17 |  | LAMP_POLE
3822A | Jaya Shopping Complex IB | Central |  | Decomm | Modernization->Site out->Decomm | 2024 Q3 |  | GCI | 4.6 TSSR Approved |  | 2023-11-09 | 2023-11-10 |  | 2023-11-28 |  | Under Approval | 2023-11-30 | 2023-12-04 | E//Nazrul | 2025-07-08 | CelcomDigi_RAN_GCI_TSS_Central_20231113 | DU00002862613 |  | SOW Changed p to Decomm TSSR Mod/Swap submitted by Subcon |  |  | 2025-05-23 | Portables BTS | In-building system | IBC
1496B | NSTP Building IB | Central |  | Modernization | Modernization->On hold->Modernization | 2024 Q2 | MA | Ascentrack | 4.6 TSSR Approved | 1/3- Need old IBC TSSR for solution preparation. SA Halim support on TSSR collection. | 2024-04-19 | 2024-04-25 |  | 2024-04-25 |  | Closed | 2024-05-06 | 2024-07-23 | E//Nazrul | 2024-07-23 | CelcomDigi_RAN_Ascentrack_TSS_Central_20240513 | DU00002862614 |  |  | 2024-09-24 | 2024-09-23 |  |  | In-building system | IBC | Add R8894E M1821 x2,Dismantle R8892E M1821(BAA) x1
1884A | Amcorp Mall | Central |  | Modernization | Modernization->On hold->Modernization | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-04-06 | 2024-04-22 |  | 2024-04-23 |  | Closed | 2024-04-24 | 2024-04-24 | E//Nazrul | 2024-04-24 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_202400407 | DU00002862615 |  |  | 2024-05-31 | 2024-05-07 |  | Wall mount boom | In-building system |  | Add R8894E M1821 x3+R8862A S2601 x3,Dismantle R8882-GUL1812 x1+R8882 S1800B(B6B) x1+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3
9876A | New Summer Mall Kota Samarahan | Sarawak |  | Modernization |  | 2024 Q2 | SH | AllStar | 4.6 TSSR Approved |  | 2023-10-09 | 2023-10-16 |  | 2023-10-19 |  | Closed | 2023-10-19 | 2023-10-24 | E//Nazrul | 2023-10-20 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20231013 | DU00002862616 |  |  | 2023-11-25 | 2023-11-23 |  | Portables BTS | In-building system |  | Add R8862A S2100 x3+R8862A S1800 x3,Dismantle R8882 S1800(B) x3 | 0 | 0
S00154 | S094A_S00154OD_CB_TMKOTAMARUDU | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2024 Q3(single site MOCN) | AD | Seri Pancar | 4.6 TSSR Approved |  | 2024-07-25 |  | 2024-08-15 |  | 2024-08-20 |  | 2024-08-20 | 2024-08-29 | CD//Sharidah | 2024-08-20 | 0725Sabah-Seri Pancar-BOQ Template(new contract)/0725MW-Sabah-Seri Pancar-BOQ Template(new contract)/0912CD-Sabah-Seri PAncar-BOQ Template(new contract) | DU00002862617 |  |  |  |  | 2025-08-18 | Tower | TOWER | 45m
2510A | Northpoint Midvalley IB (Celcom) | Central |  | Modernization | Modernization->On hold->Modernization | 2024 Q2 | CR | GCI | 4.6 TSSR Approved |  | 2024-05-20 | 2024-05-23 |  | 2024-05-27 |  | Closed | 2024-05-29 | 2024-06-10 | E//Nazrul | 2024-06-10 | CelcomDigi_RAN_GCI_TSS_Central_20240528 | DU00002862618 |  |  | 2024-07-30 | 2024-07-20 |  | Portables BTS | In-building system |  | Add R8862A S2100 x3,Dismantle
2784B | QUILL 7 IB | Central |  | Modernization | Modernization->On hold->Modernization | 2024 Q2 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-12-20 | 2023-12-28 |  | 2024-01-22 |  | Closed | 2024-01-23 | 2024-01-24 | E//Nazrul | 2024-01-23 | CelcomDigi_RAN_Datasco_TSS_Central_20231224 | DU00002862619 |  |  | 2024-07-14 | 2024-06-28 |  | Portables BTS | In-building system | NA | Add R8862A S2100 x3
3219B | Cheras Sentral IB | Central |  | Decomm | Modernization->Site out->Decomm | 2024 Q3 | SS | Magicell | 15.4 Decomm Done without TSSR Approval |  | 2024-04-05 | 2024-04-17 |  |  | 2025-07-03 | To be Submitted | 2025-07-07 |  |  |  | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240407 | DU00002862620 |  |  |  |  | 2025-09-25 | Portables BTS | In-building system
3232B | The Troika IB | Central |  | Decomm | Modernization->Site out->Decomm | 2024 Q2 | SS | Magicell | 4.6 TSSR Approved |  | 2024-04-05 | 2024-04-17 |  |  | 2025-07-03 | To be Submitted | 2025-07-07 |  |  | 2025-07-10 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240407 | DU00002862621 |  |  |  |  | 2025-11-18 | Portables BTS | In-building system
4249C | AEON Big Ipoh IB | Northern |  | Modernization |  | 2024 Q2 |  | CCSMY | 4.6 TSSR Approved |  | 2023-11-28 | 2023-12-04 |  | 2024-01-09 |  | Closed | 2024-01-09 | 2024-01-11 |  | 2024-01-10 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231130-0074 | DU00002862622 |  |  | 2024-03-06 | 2024-01-22 |  | In-Building System | In-building system | IBC | Add R8862A S1800 x3,Dismantle
B02445 | B061R_B02445OD_LRT_TMNBAHAGIA | Central |  | Decomm |  | 2024 Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2023-12-06 |  |  |  | 2023-12-13 |  | 2024-01-12 | 2024-02-15 | CD//Sapian | 2024-01-22 | CelcomDigi_RAN_Magicell_TSS_Central_20231208 | DU00002862623 |  |  |  |  | 2024-12-06 |  | MINI STRUCTURE
3571A | NU Sentral (KL Sentral Lot G) | Central |  | Modernization | Modernization->On hold->Modernization | 2024 Q2 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-12-28 | 2024-01-17 |  | 2024-02-07 |  | Rectificating | 2024-02-21 | 2024-02-22 | E//Nazrul | 2024-02-21 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240128 | DU00002862624 |  |  | 2024-10-14 | 2024-04-29 |  | Wall mount boom | In-building system |  | Add R8862A S2100 x6+R8862A S1800 x6,Dismantle R8882 S1800(B) x5++R8881 S2100 x6+
B02891 | B064I_B02891OD_JPJSEMENYIH2 | Central |  | Decomm | Decomm->On Hold->Decomm->On Hold->Decomm | 2024 Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2025-04-10 |  | 2025-04-15 |  | 2025-04-17 |  | 2025-04-27 | 2026-01-21 | CD//Ali Akaram | 2026-03-31 | SQ202504210083 | DU00002862625 |  |  |  |  | 2025-05-06 |  | TOWER
3826A | St Regis Hotel KL (KL Sentral) | Central |  | Modernization | Modernization->On hold->Modernization | 2024 Q2 | MA | DATASCO | 4.6 TSSR Approved |  | 2023-12-18 | 2024-04-25 |  | 2024-05-02 |  | Closed | 2024-05-03 | 2024-05-08 | E//Nazrul | 2024-05-08 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240128 | DU00002862626 |  |  | 2024-07-05 | 2024-05-17 |  | Portables BTS | In-building system | NA | Add R8862A S2100 x4+R8894E M1821 x1,Dismantle R8892E M1821(BAA) x1
A00153 | A039A_A00153OD_PARITBUNTAR | Northern |  | Decomm |  | 2024 | SM | GTSB | 4.6 TSSR Approved |  | 2023-12-07 |  |  |  | 2023-12-12 |  | 2023-12-15 | 2024-01-22 | CD//Affendi | 2023-12-18 | Celcom Digi_RAN-GTSB-TSS-Northern-20231207-0073 | DU00002862627 |  |  |  |  | 2024-12-06 |  | TRIPOD
2968B | K Pertanian 4G1 | Central |  | Modernization | Modernization->Decomm->Modernization | 2024 Q3 | SY1 | DATASCO | 4.6 TSSR Approved |  | 2024-07-29 | 2024-08-07 |  | 2024-08-09 |  | Closed | 2024-08-12 | 2024-08-13 | E//Razif | 2024-08-13 | 0813CD-Central-Datasco-BOQ Template(new contract) | DU00002862628 |  |  | 2024-10-19 | 2024-10-08 |  | Portables BTS | In-building system | NA | Add R8862A S9000 x1+R8894E M1821 x1,Dismantle R8882-GUL1812 x1+R8862A S2100(A6A) x1 | 0 | 0
2857B | Parcel B Indoor(Celcom) | Central |  | Modernization | Modernization->TBD->Decomm->Decomm->On Hold->Modernization | 2024 Q3 | SHA | CCSMY | 4.6 TSSR Approved |  | 2024-07-17 | 2024-07-19 |  | 2024-07-23 |  | Under Approval | 2024-07-30 | 2024-08-01 | E//Nazrul | 2024-08-01 | 0719Central-CCSMY-BOQ Template | DU00002862629 |  |  | 2024-12-20 | 2024-12-16 |  | Portables BTS | In-building system |  | Add R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3
A01132 | A040B_A01132OD_TMN_SONGCHOON_IPH | Northern |  | Decomm |  | 2024 Q2 | BY | GCI | 4.6 TSSR Approved | ¦ 0216 - YPTT: unsafe condition | 2024-04-06 |  |  |  | 2024-05-10 |  | 2024-05-14 | 2024-06-07 | CD//Affendi | 2024-05-15 | Celcom Digi_RAN-GCI-TSS-Northern-20240512-0106 | DU00002862630 |  |  |  |  | 2024-06-12 |  | MINARET
3923A | Kem. Kemajuan Luar Bandar & Wilayah | Central |  | Decomm | Modernization->Decomm | 2024 Q3 | SHA | YPTT | 4.6 TSSR Approved |  | 2024-06-27 |  | 2024-07-20 |  | 2024-07-26 |  | 2024-07-30 | 2024-12-09 |  | 2024-07-30 | 0709Central-YPTT-BOQ Template | DU00002862631 |  |  |  |  | 2025-09-11 |  | In-building system
2882B | MOF Putrajaya Indoor 2 | Central |  | Modernization | Modernization->TBD->Decomm->Decomm->On Hold->Modernization | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-07-06 | 2024-07-14 |  | 2024-07-16 |  | Closed | 2024-07-19 | 2024-07-22 | E//Nazrul | 2024-07-22 | PR raised | DU00002862632 |  |  | 2024-12-10 | 2024-12-04 |  | Portables BTS | In-building system |  | Add R8894E M1821 x1,Dismantle R8892E M1821(BAA) x1
2862B | Parcel E6 7 10 11 (Celcom) | Central |  | Decomm | Modernization->TBD->Decomm->Decomm | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-07-15 |  | 2024-07-24 |  | 2024-07-26 |  | 2024-08-14 | 2024-12-09 | E//Nazrul | 2024-08-14 | CelcomDigi_RAN_GTSB_TSS_Central_20240423 | DU00002862633 |  |  |  |  | 2024-12-27 |  | In-building system
3846B | Pantai Medical Bangsar IB | Central |  | Modernization |  | 2024 Q2 | SH | CCSMY | 4.6 TSSR Approved |  | 2023-11-22 | 2023-12-04 |  | 2024-01-15 |  | Closed | 2024-01-20 | 2024-01-23 |  | 2024-01-21 | CelcomDigi_RAN_CCSMY_TSS_Central_20231126 | DU00002862634 |  |  | 2024-05-04 | 2024-05-03 |  |  | In-building system |  | Add R8862A S2100 x3,Dismantle
3847B | Pantai Medical Bangsar New Wing IB | Central |  | Modernization |  | 2024 Q2 | SH | CCSMY | 4.6 TSSR Approved |  | 2023-11-22 | 2023-12-07 |  | 2024-01-18 |  | Closed | 2024-02-06 | 2024-02-07 |  | 2024-02-06 | CelcomDigi_RAN_CCSMY_TSS_Central_20231126 | DU00002862635 |  |  | 2024-11-26 | 2024-08-14 |  | Portables BTS | In-building system |  | Add R8894E M1821x3,Dismantle R8862A S1800(B6A) x3+R8862A S2600(A4A) x3 | 0 | 0
W01354 | W066Z_W01354OD_JLNSHAMELIN_NIAGA1 | Central |  | Decomm |  | 2024 Q3 | SM | Ascentrack | 4.6 TSSR Approved |  | 2023-11-16 |  |  |  | 2023-12-27 |  | 2024-03-29 | 2025-03-25 | CD//Norhaliza | 2024-06-04 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231119 | DU00002862636 |  |  |  |  | 2024-07-26 |  | LAMP_POLE
B00343 | B061Q_B00343OD_JLNTANDANGPJ | Central |  | Decomm |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-02-22 |  |  |  | 2024-02-28 |  | 2024-03-29 | 2024-11-26 | CD//Norhaliza | 2024-06-04 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240225 | DU00002862637 |  |  |  |  | 2024-08-22 |  | MINI STRUCTURE
2850B | MOF Putrajaya Indoor(Celcom) | Central |  | Decomm | Modernization->On Hold->Decomm | 2024 Q3 | SHA | GTSB | 4.6 TSSR Approved |  | 2024-06-28 |  | 2024-07-05 |  | 2024-07-10 |  | 2024-07-16 | 2024-12-09 | E//Razif | 2024-07-16 | 0701Central-GTSB-BOQ Template (template) | DU00002862638 |  |  |  |  | 2025-01-27 |  | In-building system
3396C | Axiata Arena IB | Central |  | Modernization |  | 2024 Q3 | MA | Magicell | 4.6 TSSR Approved |  | 2024-01-30 | 2024-02-07 |  | 2024-03-12 |  | Closed | 2024-03-13 | 2024-03-13 | E//Nazrul | 2024-03-13 | CelcomDigi_RAN_Magicell_TSS_Central_20240424 | DU00002862639 |  |  | 2024-09-05 | 2024-09-04 |  | Portables BTS | In-building system | NA | Add R8894E M1821 x6,Dismantle R8892E M1821(BAA) x6
A01028 | A044A_A01028OD_PERSIARANSIBC9 | Northern |  | Decomm |  | 2024 Q2 | BY | CCSMY | 4.6 TSSR Approved | ¦ 0216 - YPTT: site cancel from YPTT | 2024-02-26 |  |  |  | 2024-03-07 |  | 2024-03-08 | 2024-04-16 | CD//Affendi | 2024-04-02 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240229-0097 | DU00002862640 |  |  |  |  | 2024-05-22 |  | UNIPOLE
2969B | K Sum Asli & Alam Sekitar (4G3) | Central |  | Modernization | Modernization->Decomm->Modernization | 2024 Q3 | SH | GCI | 4.6 TSSR Approved |  | 2023-11-06 | 2023-11-08 |  | 2023-11-27 | 2024-05-28 | Under Approval | 2024-06-06 | 2024-08-09 | E//Nazrul | 2024-04-17 | 0626Central-GCI-BOQ Template (template) | DU00002862641 |  |  | 2024-12-20 | 2024-12-11 |  | Portables BTS | In-building system |  | Add R8894E M1821 x1,Dismantle R8882-GUL1812 x1+R8862A S2100(A6A) x1
2090A | K Pertanian 4G2 | Central |  | Modernization | Modernization->Decomm->Modernization | 2024 Q3 | SH | GCI | 4.6 TSSR Approved |  | 2023-11-03 | 2023-11-06 |  | 2023-11-27 | 2024-05-29 | Under Approval | 2024-06-06 | 2024-08-09 | E//Nazrul | 2024-04-02 | 0626Central-GCI-BOQ Template (template) | DU00002862642 |  | Please verify the topo. | 2024-10-08 | 2024-10-05 |  | Portables BTS | In-building system | INBUILDING | Add R8894E M1821 x1,Dismantle R8892E M1821(BAA) x1
B01981 | W066X_B01981OD_APTPERMAIRIAAMPG | Central |  | Decomm |  | 2024 Q4 | SH | AllStar | 4.6 TSSR Approved |  | 2023-12-02 |  |  |  | 2024-03-02 |  | 2024-05-28 | 2024-07-19 | CD//Ali Akaram | 2024-07-19 | BOQ CelcomDigi_RAN_AllStar_Standard PR TSS_Central_20240128 | DU00002862643 |  |  |  |  | 2024-08-22 |  | MINI STRUCTURE
2964B | Bgn Hal Ehwal Undang-Undang | Central |  | Modernization | Modernization->Decomm->Modernization | 2024 Q3 | AD | GCI | 4.6 TSSR Approved |  | 2023-11-03 | 2023-11-08 |  | 2023-11-27 | 2024-06-04 | Under Approval | 2024-06-05 | 2024-08-09 | E//Nazrul | 2024-04-16 | 0626Central-GCI-BOQ Template (template) | DU00002862644 |  |  | 2024-12-17 | 2024-12-15 |  | Portables BTS | In-building system |  | Add R8894E M1821 x1,Dismantle R8892E M1821(BAA) x1
9835A | Miri Marriot IB | Sarawak |  | Decomm | Modernization->On hold->Decomm->On Hold->Decomm | 2025 Q1 | SH | Trintel | 4.6 TSSR Approved |  | 2023-11-07 | 2023-11-14 |  | 2024-05-08 | 2024-04-19 | Under Approval | 2024-04-19 | 2025-05-02 | E//Nazrul | 2025-02-25 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240406 | DU00002862645 |  |  |  |  | 2025-11-22 |  | In-building system |  | Add R8894E M1821x1+R8862A S2601 x1, Dismantle R8882-GUL1812x1+R8862A S2100(A6A)x1 | 0 | 0
W00281 | W066G_W00281OD_LRTTMNMELATI | Central |  | Decomm |  | 2024 Q1 | AD | GTSB | 4.6 TSSR Approved |  | 2024-03-07 |  |  |  | 2024-03-13 |  | 2024-04-02 | 2024-05-27 | CD//Sapian | 2024-04-02 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240311 | DU00002862646 |  |  |  |  | 2024-08-26 |  | BOOM
1062C | Four Season Place IB | Central |  | Modernization |  | 2024 Q2 | SS | Magicell | 4.6 TSSR Approved |  | 2024-01-24 | 2024-01-30 |  | 2024-02-05 |  | Closed | 2024-02-06 | 2024-04-01 | E//Nazrul | 2024-04-01 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240128 | DU00002862647 |  |  | 2024-06-10 | 2024-05-29 |  | Portables BTS | In-building system |  | Add R8862A S2100 x3,Dismantle
1338C | Southpoint Midvalley IB | Central |  | Modernization |  | 2024 Q2 | AI | CCSMY | 4.6 TSSR Approved |  | 2023-12-26 | 2023-12-29 |  | 2024-01-19 |  | Closed | 2024-03-26 | 2024-03-27 | E//Nazrul | 2024-03-26 | CelcomDigi_RAN_CCSMY_TSS_Central_20231230 | DU00002862648 |  |  | 2025-06-28 | 2024-08-15 |  | Portables BTS | In-building system |  | Add R8862A S2100 x6,Dismantle
K00834 | K011A_K00834OD_KGSGDURIAN_PSENA | Northern |  | Decomm |  | 2024 Q3(single site MOCN) | SM | CCSMY | 4.6 TSSR Approved |  | 2024-01-12 |  |  |  | 2024-01-16 |  | 2024-05-20 | 2024-10-01 | CD//Affendi | 2024-05-27 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240114-0086 | DU00002862649 |  |  |  |  | 2024-08-30 |  | TOWER
2957B | K Pemb Usahawan 2G6 (Maxis) | Central |  | Decomm | Modernization->Decomm | 2024 Q3 | AD | GCI | 4.6 TSSR Approved |  | 2023-11-03 | 2023-11-08 |  | 2023-11-28 | 2024-06-04 | Under Approval | 2024-06-05 | 2024-12-09 | E//Nazrul | 2024-06-05 | 0626Central-GCI-BOQ Template (template) | DU00002862650 |  |  |  |  | 2024-09-06 | Portables BTS | In-building system
2848B | Parcel D5 Indoor(Celcom) | Central |  | Decomm | Modernization->TBD->Decomm->Decomm | 2024 Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2024-04-17 |  |  |  | 2024-04-23 |  | 2024-05-16 | 2025-03-21 | E//Nazrul | 2024-12-05 | CelcomDigi_RAN_GTSB_TSS_Central_20240509 | DU00002862651 |  |  |  |  | 2024-12-27 |  | In-building system
B00582 | B058E_B00582OD_PR_KM7KLIA | Central |  | Decomm |  | 2024 | AI | GCI | 4.6 TSSR Approved |  | 2025-02-28 |  | 2025-04-07 |  | 2025-04-10 |  | 2025-04-27 | 2026-01-21 | CD//Ali Akaram | 2026-03-31 | Wireless+ Malaysia CD+TSS+ CCSMY+5 site SQ202410310156 | DU00002862652 |  |  |  |  | 2025-04-23 |  | BILLBOARD
2847B | Parcel D3 Indoor(Celcom) | Central |  | Decomm | Modernization->TBD->Decomm->Decomm | 2024 Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2024-04-24 |  |  |  | 2024-04-29 |  | 2024-05-16 |  | E//Nazrul | 2024-05-16 | CelcomDigi_RAN_GTSB_TSS_Central_20240423 | DU00002862653 |  |  |  |  | 2024-12-27 |  | In-building system
W01310 | W066S_W01310OD_JLNMESRARIA_SRIPETALING | Central |  | Decomm |  | 2024 Q3 | SH | AllStar | 4.6 TSSR Approved |  | 2023-12-27 |  |  |  | 2024-03-12 |  | 2024-07-25 | 2024-10-24 | CD//Norhaliza | 2024-10-03 | CelcomDigi_RAN_AllStar_TSS_Central_20231230 | DU00002862654 |  |  |  |  | 2024-05-24 |  | STREET POLE
2971B | Mahkamah Putrajaya (3G3) | Central |  | Modernization | Modernization->On hold->Modernization->Decomm->On Hold->Modernization | 2024 Q3 | BY | GCI | 4.6 TSSR Approved |  | 2023-12-08 | 2024-01-09 |  | 2024-03-26 | 2024-07-19 | Under Approval | 2024-08-09 | 2024-08-09 | E//Nazrul | 2024-08-09 | CelcomDigi_RAN_GCI_TSS_Central_20231214 | DU00002862655 |  |  | 2024-10-08 | 2024-10-08 |  | In-Building System | In-building system |  | Reuse existing RRU, need to check and reconnect RRU
1724C | KL East Mall IB | Central |  | Remote MOCN | Modernization->On hold->Modernization->Remote MOCN->Modernization | 2024 Q1 | AI | GTSB | 4.6 TSSR Approved |  | 2024-08-06 | 2024-08-08 |  | 2024-08-08 |  | Closed | 2024-08-14 | 2024-08-15 | E//Nazrul | 2024-08-14 | 0808CD-Central-GTSB-BOQ Template(new contract) | DU00002862656 | [5 empty] | Portables BTS | In-building System |  | Resuse exsiting RRU
B00146 | B064A_B00146OD_BT21PANGSUN | Central |  | Decomm |  | 2024 | CR | GCI | 4.6 TSSR Approved |  | 2023-10-30 |  |  |  | 2023-11-21 |  | 2023-11-22 | 2025-03-21 | CD//Ali Akaram | 2023-11-29 | CelcomDigi_RAN_GCI_TSS_Central_20231101 | DU00002862657 |  | approve with comment, to reroute childsite |  |  | 2024-10-30 |  | TOWER
1495B | Intercontinental KL IB | Central |  | Decomm | Modernization->Site out->Decomm | 2024 Q2 | CR | GCI | 4.6 TSSR Approved |  | 2023-12-05 | 2023-12-07 |  | 2024-01-09 |  | Closed | 2024-01-10 | 2024-01-11 | E//Nazrul | 2024-01-10 | CelcomDigi_RAN_GCI_TSS_Central_20231208 | DU00002862658 |  |  |  |  | 2025-07-09 | Portables BTS | In-building system
2606A | Bangsar Village Phase 2 IB | Central |  | Modernization |  | 2024 Q2 | ZB | CCSMY | 4.6 TSSR Approved |  | 2023-12-15 | 2023-12-26 |  | 2024-01-15 |  | Closed | 2024-01-21 | 2024-01-22 |  | 2024-01-22 | CelcomDigi_RAN_CCSMY_TSS_Central_20231224 | DU00002862659 |  |  | 2024-07-27 | 2024-07-13 |  | Portables BTS | In-building system |  | Add R8862A S2100 x1,Dismantle +R8840-U216 x1+R8881 S2100 x1+
2877A | Eastin Hotel | Central |  | Modernization |  | 2024 Q3 | SS | YPTT | 4.6 TSSR Approved |  | 2024-04-03 | 2023-11-02 |  | 2024-03-06 |  | Closed | 2024-04-16 | 2024-04-16 | E//Nazrul | 2024-04-16 | CelcomDigi_RAN_YPTT_TSS_Central_20231104 | DU00002862660 |  |  | 2024-05-16 | 2024-05-04 |  |  | In-building system |  | Add R8894E M1821 x1,Dismantle R8882-GUL1812 x1+R8862A S2100(A6A) x1
W01405 | W066AA_W01405OD_PSRNMEWAH_BDRTUNRAZAK | Central |  | Decomm |  | 2024 Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-11-20 |  |  |  | 2023-11-22 |  | 2023-11-24 | 2024-01-22 | CD//Sapian | 2023-12-04 | CelcomDigi_RAN_AllStar_TSS_Central_20231120 | DU00002862661 |  |  |  |  | 2024-07-31 |  | LAMP_POLE
R00050 | R001B_R00050OD_KGPDGBEHOR | Northern |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4 | SM | GTSB | 4.6 TSSR Approved |  | 2024-02-13 |  |  |  | 2024-02-13 |  | 2024-04-29 | 2024-05-10 | CD//Affendi | 2024-05-09 | Celcom Digi_RAN-GTSB-TSS-Northern-20240223-0093 | DU00002862662 |  |  |  |  | 2025-05-26 |  | TOWER
2853B | GARDENS NORTH TOWER IB | Central |  | Modernization |  | 2024 Q2 | MA | Magicell | 4.6 TSSR Approved |  | 2024-04-03 | 2024-04-04 |  | 2024-04-15 |  | Closed | 2024-04-15 | 2024-04-16 | E//Nazrul | 2024-04-16 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240407 | DU00002862663 |  |  | 2023-11-17 | 2023-10-24 |  | Portables BTS | In-building system |  | Reuse exisiting IBC RRU | 0 | 0
7528B | Four Points Sandakan | Sabah |  | Modernization |  | 2024 Q3 | MS | GTSB | 4.6 TSSR Approved |  | 2024-07-23 | 2024-08-05 |  | 2024-08-09 |  | Under Approval | 2024-08-09 | 2024-08-09 | E//Nazrul | 2024-08-09 | 0725Sabah-GTSB-BOQ Template(new contract) | DU00002862664 |  |  | 2025-01-06 | 2024-08-16 |  | In-Building System | In-building system |  | Add R8862A S2100 x1+R8862A S2601 x1+R8862A S1800 x1,Dismantle R8882 S2600(B4A) x1
W01299 | W066G_W01299OD_LRT_WANGSAMAJU_VBT | Central |  | Decomm |  | 2024 Q1 | MA | GCI | 4.6 TSSR Approved |  | 2024-07-02 |  | 2024-07-08 |  | 2024-07-10 |  | 2024-07-11 | 2024-08-27 | CD//Sapian | 2024-07-23 | 0918CD-Central-GCI-BOQ Template (old contract) | DU00002862665 |  |  |  |  | 2024-10-09 |  | MINIMAST
3619B | IB Tower IB | Central |  | Modernization |  | 2024 Q2 | SS | Magicell | 4.6 TSSR Approved |  | 2023-11-23 |  |  | 2023-11-23 |  | Closed | 2023-11-27 | 2023-11-29 | E//Nazrul | 2023-11-27 | CelcomDigi_RAN_Magicell_TSS_Central_20231126 | DU00002862666 |  |  | 2023-10-30 | 2023-10-24 |  |  | In-building system |  | Reuse exisiting IBC RRU | 0 | 0
3129C | The Starling Mall IBC | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  | In-House | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862667 | [6 empty] | TT DOTCOM SDN BHD |  | Reuse existing RRU,
1264C | Menara Etiqa Bangsar IB | Central |  | Modernization |  | 2024 Q2 | MA | CCSMY | 4.6 TSSR Approved |  | 2023-12-26 | 2024-01-02 |  | 2024-01-16 |  | Closed | 2024-03-18 | 2024-03-19 | E//Nazrul | 2024-03-18 | CelcomDigi_RAN_CCSMY_TSS_Central_20231230 | DU00002862668 |  |  | 2024-06-25 | 2024-06-14 |  | Portables BTS | In-building system |  | Add R8862A S2100 x2,Dismantle
W00376 | W066V_W00376OD_TMPANTAI | Central | 1834K | Swap | Decomm->On hold->Swap | 2024 Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2024-03-06 | 2024-03-20 |  | 2024-03-27 |  | Closed | 2024-03-27 | 2024-04-18 | CD//Ali Akaram | 2024-04-17 | BOQ CelcomDigi_RAN_AllStar_Standard PR TSS_Central_20240316 | DU00002862669 |  |  | 2024-08-31 | 2024-08-20 |  | Wall mount boom | BOOM | 3 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle | 0 | 0
3105C | KPJ Ampang Puteri IB | Central |  | Modernization |  | 2024 Q4 | SS | Magicell | 4.6 TSSR Approved |  | 2023-11-01 | 2023-11-03 |  | 2023-11-22 |  | Closed | 2023-11-27 | 2023-11-29 | E//Nazrul | 2023-11-27 | CelcomDigi_RAN_Magicell_TSS_Central_20231104 | DU00002862670 |  |  | 2023-10-30 | 2023-10-24 |  |  | In-building system |  | Reuse exisiting IBC RRU | 0 | 0
B00214 | B064I_B00214OD_SEMENYEH2 | Central |  | Decomm | Decomm->On Hold->Decomm | 2024 | CR | YPTT | 4.6 TSSR Approved |  | 2024-07-29 |  | 2024-08-19 |  | 2024-08-19 |  | 2024-11-07 | 2025-01-14 | CD//Ali Akaram | 2024-11-29 | 0802CD-Central-YPTT-BOQ Template(new contract) | DU00002862671 |  |  |  |  | 2024-12-20 |  | BOOM
3593C | UOA Nexus Bangsar South IB | Central |  | Modernization |  | 2024 Q2 | SS | Magicell | 4.6 TSSR Approved |  | 2023-11-23 |  |  | 2023-11-23 |  | Closed | 2023-11-23 | 2023-11-24 | E//Nazrul | 2023-11-23 | CelcomDigi_RAN_Magicell_TSS_Central_20231126 | DU00002862672 |  |  | 2023-10-28 | 2023-10-24 |  |  | In-building system |  | Reuse exisiting IBC RRU | 0 | 0
W00150 | W066J_W00150OD_UTMSEMARAK | Central | 1840K | Swap | Decomm->On Hold->Swap | 2024 Q1 | AI | Ascentrack | 4.6 TSSR Approved |  | 2023-11-16 | 2024-08-14 |  | 2024-08-16 | 2024-02-28 | Closed | 2024-08-16 | 2024-10-02 | CD//Ali akaram | 2024-10-02 | 0813CD-Central-Ascentrack-BOQ Template(new contract) | DU00002862673 |  |  | 2024-10-23 | 2024-10-11 |  | Pole | BOOM | 6 | Add R8862A S9000 x4+R8894E M1821 x5+R8862A S2601 x3+R8854 S2600 x1,Dismantle | 0 | 3
B00039 | B057D_B00039OD_SPG3GBK | Central |  | Decomm |  | 2024 Q1 | SS | Magicell | 4.6 TSSR Approved |  | 2024-01-26 |  |  |  | 2024-02-07 |  | 2024-02-08 | 2024-08-20 | CD//Ali Akaram | 2024-03-04 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240128 | DU00002862674 |  |  |  |  | 2024-04-01 |  | BOOM
B01982 | B064E_B01982OD_KAJANGBARU | Central |  | Decomm |  | 2024 Q4 | SH | GTSB | 4.6 TSSR Approved |  | 2024-01-15 |  | 2024-09-18 |  | 2024-09-18 |  | 2024-09-20 |  | CD//Norhaliza | 2024-10-03 | Wireless+ Malaysia CD+TSS+ GTSB+9 site SQ202410310159 | DU00002862675 |  | Pls provide CELCOM TM LL B01982 photo |  |  | 2024-10-11 |  | UNIPOLE
B00029 | B064B_B00029OD_BTUNHUSSIEN3 | Central |  | Decomm |  | 2024 Q4(single site MOCN)-L26 SSM | SH | Solusi | 4.6 TSSR Approved |  | 2024-06-24 |  |  |  | 2024-09-09 |  | 2024-09-10 |  | CD//Ali Akaram | 2024-09-12 | SQ202411070024 | DU00002862676 |  |  |  |  | 2024-11-15 |  | RAPOLE
1031C | Capri Bangsar South IB | Central |  | Site Out (Modernization) | Modernization->Site Out->Site Out (Modernization) | 2024 Q2 | MA | GCI | [SiteOut]- 1.0 Pending Survey - Subcon | [6 empty] | To be Submitted |  |  |  |  | SQ202506140192 | DU00002862677 | [6 empty] | In-building system
1290C | Mercu 3 KL Eco City IB | Central |  | Modernization |  | 2024 Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-12-20 | 2023-12-22 |  | 2024-01-09 |  | Closed | 2024-01-10 | 2024-01-11 |  | 2024-01-11 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231224 | DU00002862678 |  |  | 2024-03-16 | 2024-03-14 |  | In-Building System | In-building system | IBC | Add R8862A S2100 x2,Dismantle
B00914 | W067A_B00914OD_PR_R2WPPJ | Central |  | Decomm |  | 2024 Q3 | SY1 | GTSB | 4.6 TSSR Approved |  | 2024-09-25 |  | 2024-10-07 |  | 2024-10-14 |  | 2024-10-15 | 2025-03-21 | CD//Ali Akaram | 2024-10-17 | 0924CD-Central-GTSB-BOQ Template(new contract) | DU00002862679 |  |  |  |  | 2024-12-20 |  | MONOPOLE
B00718 | W067A_B00718OD_PR_TMCYBERJAYA | Central |  | Decomm |  | 2024 Q3 | SH | GTSB | 4.6 TSSR Approved |  | 2024-05-16 |  |  |  | 2024-05-27 |  | 2024-05-30 |  | CD//Ali Akaram | 2024-06-04 | CelcomDigi_RAN_GTSB_TSS_Central_20240423 | DU00002862680 |  | No IDU and Cisco Photo in EPMS TSSR |  |  | 2025-09-25 |  | TOWER
B00141 | B064G_B00141OD_TERASJERNANG | Central |  | Decomm |  | 2024 | AI | GTSB | 4.6 TSSR Approved |  | 2024-09-21 |  | 2024-09-27 |  | 2024-09-30 |  | 2024-11-19 | 2025-03-21 | CD//Sapian | 2025-03-07 | 0925CD-Central-GTSB-BOQ Template(new contract) | DU00002862681 |  |  |  |  | 2024-11-05 |  | TOWER
B00091 | B064F_B00091OD_SGRAMALLUAR | Central |  | Decomm |  | 2024 Q4(single site MOCN)-L2126 SSM | SY1 | GTSB | 4.6 TSSR Approved |  | 2024-09-03 |  | 2024-09-06 |  | 2024-10-11 |  | 2024-10-15 |  | CD//Norhaliza | 2024-11-12 | 0906CD-Central-GTSB-BOQ Template(new contract) | DU00002862682 |  |  |  |  | 2024-11-05 |  | TOWER
B00238 | B064D_B00238OD_SGLONG2 | Central |  | Decomm | Decomm->On hold->Decomm | 2024 Q4 | SY1 | GTSB | 4.6 TSSR Approved |  | 2024-09-03 |  | 2024-09-25 |  | 2024-10-03 |  | 2024-10-16 | 2025-03-21 | CD//Sapian | 2024-10-22 | 0924CD-Central-GTSB-BOQ Template(new contract) | DU00002862683 |  |  |  |  | 2025-03-27 |  | TOWER
B00739 | B061T_B00739OD_MHS | Central | 1808K | Decomm |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-08-26 |  | 2024-09-08 |  | 2024-10-07 |  | 2024-10-16 |  | CD//Norhaliza | 2024-12-13 | 0903CD-Central-GTSB-BOQ Template(new contract) | DU00002862684 |  |  |  |  | 2024-10-28 |  | BOOM
B00887 | B061S_B00887IB_WISMAACADEMY | Central | 1331K | Swap |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-03-13 | 2024-03-20 |  | 2024-03-27 |  | Closed | 2024-03-28 | 2024-04-04 | CD//Sofiah | 2024-04-04 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240316 | DU00002862685 |  |  | 2024-04-30 | 2024-04-29 |  | Portables BTS | BOOM | NA | Add R8862A S9000 x1+R8862A S2100 x1,Dismantle | 0 | 0
B01376 | B061O_B01376IB_SRIPENTASTV3 | Central | 1333K | Swap |  | 2024 Q3 | BY | GCI | 4.6 TSSR Approved |  | 2023-12-20 | 2024-01-08 |  | 2024-03-07 |  | Closed | 2024-04-04 | 2024-04-05 | CD//Sofiah | 2024-04-05 | CelcomDigi_RAN_GCI_TSS_Central_20231224 | DU00002862686 |  |  | 2024-05-31 | 2024-05-27 |  | Portables BTS | BOOM |  | Add R8862A S2100 x2+R8862A S2601 x2+R8862A S1800 x2,Dismantle
B01997 | B061T_B01997IB_VSQPJ | Central | 1340K | Swap |  | 2024 Q3 | MA | DATASCO | 4.6 TSSR Approved |  | 2024-04-05 | 2024-04-16 |  | 2024-04-18 |  | Closed | 2024-04-23 | 2024-04-30 | CD//Sofiah | 2024-04-29 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_202400407 | DU00002862687 |  |  | 2024-07-16 | 2024-06-07 |  |  | IN-BUILDING |  | Add R8862A S2100 x3+R8862A S2601 x3+R8862A S1800 x3,Dismantle | 0 | 0
B01815 | W066Y_B01815OD_TMNLEMBAHMAJU | Central |  | Decomm |  | 2024 Q3 | SM | Ascentrack | 4.6 TSSR Approved |  | 2024-01-11 |  |  |  | 2024-01-24 |  | 2024-03-29 | 2025-03-21 | CD//Sapian | 2024-04-24 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240115 | DU00002862688 |  |  |  |  | 2024-07-25 |  | MONOPOLE
B02174 | B061Q_B02174IB_PJXSHAHTOWER | Central | 1341K | Swap |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-04-04 | 2024-04-08 |  | 2024-04-09 |  | Closed | 2024-04-20 | 2024-04-19 | CD//Sofiah | 2024-04-19 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240407 | DU00002862689 |  |  | 2024-06-05 | 2024-05-31 |  |  | IN-BUILDING | IBC | Add R8862A S2100 x3+R8862A S2601 x3+R8862A S1800 x3,Dismantle | 0 | 0
A00091 | A045A_A00091OD_KROH | Northern |  | Decomm |  | 2024 Additional | AI | GTSB | 4.6 TSSR Approved |  | 2024-12-27 |  | 2025-07-21 |  | 2025-10-15 |  | 2026-02-11 | 2026-02-16 | CD//Zulakmar | 2026-02-19 | SQ202501070513 - GTSB (RAN+MW) | DU00002862690 |  |  |  |  | 2025-01-24 |  | TOWER
B02666 | B061T_B02666IB_Sheraton_PJ_Hotel | Central | 1343K | Swap |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-04-04 | 2024-04-05 |  | 2024-04-06 |  | Closed | 2024-09-06 | 2024-11-29 | CD//Sofiah | 2024-11-29 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240407 | DU00002862691 |  |  | 2024-06-28 | 2024-05-30 |  |  | IN-BUILDING | IBC | Add R8862A S2100 x6+R8862A S2601 x6+R8862A S1800 x6,Dismantle | 0 | 0
B02345 | W066W_B02345OD_PSSMRR2AMPANG | Central |  | Decomm |  | 2024 Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2024-05-15 |  | 2024-07-15 |  | 2024-07-10 |  | 2024-07-12 | 2025-10-01 | CD//Norhaliza | 2024-08-07 | CelcomDigi_RAN_GTSB_TSS_Central_20240423 | DU00002862692 |  |  |  |  | 2024-09-12 |  | PSS PYLON
Q01107 | Q132C_Q01107IB_MERDEKAMALL | Sarawak | 9275K | Swap |  | 2027 | SH | Magicell | 4.6 TSSR Approved |  | 2023-10-16 | 2023-10-17 |  | 2023-10-24 |  | Closed | 2023-10-26 | 2023-10-27 | CD//John | 2023-10-26 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231017 | DU00002862693 | [5 empty] | Portables BTS | IN-BUILDING |  | Add R8862A S1800 x1+R8862A S2100 x1,Dismantle
Q01224 | Q135A_Q01224IB_UNIPAVILLION | Sarawak | 9378K | Swap |  | 2024 Q2 | ZB | Trintel | 4.6 TSSR Approved |  | 2023-10-18 | 2023-10-26 |  | 2023-11-20 |  | Closed | 2024-01-23 | 2024-02-23 | CD//John | 2024-02-23 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231019 | DU00002862694 |  |  | 2025-04-27 | 2025-04-19 |  | Portables BTS | IN-BUILDING |  | Add R8862A S2100 x2+R8862A S2601 x2+R8862A S1800 x2,Dismantle | 0 | 0
W00320 | W066V_W00663IB2_TMWHOLESALE | Central | 1518K | Swap |  | 2024 Q2 | BY | GCI | 4.6 TSSR Approved |  | 2024-05-13 | 2024-05-16 |  | 2024-05-21 |  | Under Approval | 2024-05-24 | 2024-08-05 | CD//Sofiah | 2024-08-01 | CelcomDigi_RAN_GCI_TSS_Central_20240517 | DU00002862695 |  |  | 2024-11-17 | 2024-11-07 |  | Portables BTS | BOOM |  | Add R8862A S2100 x5+R8862A S1800 x5,Dismantle
W00350 | W066N_W00350IB1_PTTTOWER | Central | 1203K | Remote MOCN | Swap->Remote MOCN | 2024 Q2 | SS | In-House | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  | CD//Sofiah |  |  | DU00002862696 | [6 empty] | UNIPOLE |  | move to BAU
W00361 | W066R_W00361IB_STADIUM_AQUATIC | Central | 1525K | Swap |  | 2024 Q3 | YZ | Magicell | 4.6 TSSR Approved |  | 2024-01-10 | 2024-01-17 |  | 2024-03-04 |  | Closed | 2024-03-08 | 2024-04-04 | CD//Sofiah | 2024-04-04 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240115 | DU00002862697 |  |  | 2024-05-03 | 2024-04-29 |  | Portables BTS | BOOM |  | Add R8862A S2100 x3+R8862A S2601 x3+R8862A S1800 x3,Dismantle
W00430 | W066R_W00430IB1_STDNASIONALBKTJALILID1 | Central | 1549K | Decomm | Swap->On Hold->Decomm | 2024 Q3 | AI | Magicell | 4.6 TSSR Approved |  | 2024-05-09 | 2024-01-16 |  | 2024-05-15 | 2025-06-19 | Closed | 2025-10-31 |  | CD//Sofiah | 2025-10-31 | SQ202411140058 | DU00002862698 |  |  |  |  | 2025-07-09 |  | IN-BUILDING |  | Add R8862A S2100 x19+R8862A S2601 x19+R8862A S1800 x19,Dismantle
W00615 | W066BB_W00615IB_CHERASLSRMALL | Central | 1562K | Swap |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-01-05 | 2024-01-10 |  | 2024-02-01 |  | Closed | 2024-07-25 | 2024-07-26 | CD//Sofiah | 2024-07-26 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240108 | DU00002862699 |  |  | 2025-01-25 | 2024-10-26 |  | Portables BTS | SHARING STRC MAXIS |  | Add R8862A S2100 x1+R8862A S2601 x1+R8862A S1800 x1,Dismantle
W00832 | W066N_W00832IB_MENARATANTAN | Central | 1769K | Swap |  | 2024 Q2 | SS | Magicell | 4.6 TSSR Approved |  | 2024-01-05 | 2024-01-10 |  | 2024-01-12 |  | Closed | 2024-01-22 | 2024-02-01 | CD//Sofiah | 2024-01-31 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240110 | DU00002862700 |  |  | 2024-07-23 | 2024-07-18 |  | Portables BTS | INBUILDING |  | Add R8862A S2100 x1+R8862A S1800 x1,Dismantle
W00998 | W066N_W00998IB_PTT3KLCC | Central | 1770K | Swap |  | 2024 Q2 | SS | Magicell | 4.6 TSSR Approved |  | 2024-02-09 | 2024-02-13 |  | 2024-02-23 |  | Under Approval | 2024-09-27 | 2024-11-29 | CD//Sofiah | 2024-11-29 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240225 | DU00002862701 |  |  | 2024-11-25 | 2024-10-01 |  | Portables BTS | IN-BUILDING |  | Add R8862A S2100 x7+R8862A S2601 x7+R8862A S1800 x7,Dismantle
W01007 | W066V_W01007IB_MENARAUOA | Central | 1576K | Swap | Swap->On Hold->Swap | 2024 Q2 | AI | GCI | 4.6 TSSR Approved |  | 2024-03-13 | 2024-03-04 |  | 2024-03-11 |  | Closed | 2024-03-20 | 2024-04-04 | CD//Sofiah | 2024-04-04 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240316 | DU00002862702 |  |  | 2025-04-15 | 2025-04-15 |  | Portables BTS | IBC + Rooftop | NA | Add R8862A S2100 x3+R8862A S1800 x3,Dismantle
W01136 | W066U_W01136IB_PLATINUMSENTRAL | Central | 1583K | Swap |  | 2024 Q2 | SS | CCSMY | 4.6 TSSR Approved |  | 2024-01-17 | 2024-01-22 |  | 2024-02-08 |  | Closed | 2024-02-14 | 2024-04-04 | CD//Sofiah | 2024-04-04 | CelcomDigi_RAN_CCS_TSS_Central_20240124 | DU00002862703 |  |  | 2024-05-07 | 2024-05-03 |  |  | IN-BUILDING |  | Add R8862A S2100 x3+R8862A S2601 x3+R8862A S1800 x3,Dismantle
W01167 | W066U_W01167IB_NU_TOWER | Central | 1584K | Swap |  | 2024 Q2 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-01-18 | 2024-01-24 |  | 2024-02-07 |  | Closed | 2024-03-11 | 2024-04-05 | CD//Sofiah | 2024-04-04 | CelcomDigi_RAN_DATASCO_TSS_Central_20240124 | DU00002862704 |  |  | 2024-07-23 | 2024-06-28 |  |  | IN-BUILDING |  | Add R8862A S2100 x6+R8862A S2601 x6+R8862A S1800 x6,Dismantle
W01188 | W066V_W01188IB_MENARAUEMBANGSARSOUTH | Central | 1587K | Swap |  | 2024 Q2 | AI | GCI | 4.6 TSSR Approved |  | 2024-03-13 | 2024-03-20 |  | 2024-04-04 |  | Closed | 2024-04-16 | 2024-04-19 | CD//Sofiah | 2024-04-19 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240316 | DU00002862705 |  |  | 2024-07-22 | 2024-07-17 |  | Portables BTS | INBUILDING | NA | Add R8862A S2100 x3+R8862A S2601 x3+R8862A S1800 x3,Dismantle
W01199 | W066W_W01199IB_MENARA_PERKESO | Central | 1772K | Swap |  | 2024 Q2 | SS | Magicell | 4.6 TSSR Approved |  | 2024-01-16 | 2024-01-17 |  | 2024-01-19 |  | Closed | 2024-01-23 | 2024-03-11 | CD//Sofiah | 2024-03-11 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240117 | DU00002862706 |  |  | 2024-09-20 | 2024-09-05 |  |  | IN-BUILDING |  | Add R8862A S2100 x2+R8862A S2601 x2+R8862A S1800 x2,Dismantle
B00615 | B061J_B00615OD_PR_JALILHEIGHT | Central |  | Decomm |  | 2024 Q3 | SHA | Solusi | 4.6 TSSR Approved |  | 2024-07-25 |  |  |  | 2024-08-08 |  | 2024-08-13 |  | CD//Ali Akaram | 2024-08-14 | 0724Central-Solusi-BOQ Template | DU00002862707 |  |  |  |  | 2024-08-24 |  | LAMP_POLE
W01273 | W066U_W01273IB_ALOFTHOTEL | Central | 1589K | Swap |  | 2024 Q2 | BY | DATASCO | 4.6 TSSR Approved |  | 2024-01-05 | 2024-01-12 |  | 2024-01-23 |  | Closed | 2024-01-24 | 2024-02-20 | CD//Sofiah | 2024-02-19 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240110 | DU00002862708 |  |  | 2024-05-17 | 2024-05-15 |  | In-Building System | IN-BUILDING | IBC | Add R8862A S2100 x3+R8862A S2601 x3+R8862A S1800 x3,Dismantle
W01275 | W066U_W01275IB_1SENTRUM | Central | 1590K | Swap |  | 2024 Q2 | SHA | DATASCO | 4.6 TSSR Approved |  | 2024-01-11 | 2024-01-18 |  | 2024-01-24 |  | Under Approval | 2024-10-07 | 2024-10-10 | CD//Sofiah | 2024-10-09 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240115 | DU00002862709 |  |  | 2024-08-30 | 2024-07-27 |  | In-Building System | IN-BUILDING | IBC | Add R8862A S2100 x3+R8862A S2601 x3+R8862A S1800 x3,Dismantle
W01331 | W066W_W01331IB_Gleneagles_Hospital_New_Wing | Central | 1592K | Decomm | Swap->Decomm | 2024 Q1 | SHA | GCI | 4.6 TSSR Approved |  | 2024-01-04 | 2024-01-03 |  | 2024-04-23 | 2024-07-22 | Rectificating | 2024-07-23 | 2024-12-21 | CD//Sofiah | 2024-07-26 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240108 | DU00002862710 |  |  |  |  | 2024-10-18 | Portables BTS | IN-BUILDING
W01338 | W066Z_W01338IB_SUNWAY_VELOCITY_HOTEL | Central | 1773K | Swap |  | 2024 Q3 | CR | Magicell | 4.6 TSSR Approved |  | 2024-04-22 | 2024-04-25 |  | 2024-04-26 |  | Closed | 2024-04-30 | 2024-05-07 | CD//Sofiah | 2024-05-07 | CelcomDigi_RAN_Magicell_TSS_Central_20240424 | DU00002862711 |  |  | 2024-08-30 | 2024-08-27 |  |  | IN-BUILDING |  | Add R8862A S2100 x3+R8862A S2601 x3+R8862A S1800 x3,Dismantle
W01347 | W066V_W01347IB_PusatPerubatan(UM)_ext | Central | 1593K | Swap |  | 2024 Q3 | SS | YPTT | 4.6 TSSR Approved |  | 2024-02-07 | 2024-02-15 |  | 2024-03-01 |  | Rectificating | 2024-03-08 | 2024-07-10 | CD//Sofiah | 2024-07-10 | BOQ_Celcom Digi_RAN-YPTT-Standard PR TSS-20240218 | DU00002862712 |  |  | 2024-07-04 | 2024-05-29 |  | Portables BTS | INBUILDING |  | Add R8862A S2100 x3+R8862A S2601 x3+R8862A S1800 x3,Dismantle
W01393 | W066V_W01393IB_TOWER6_AVENUE5_BANGSARSOUTH | Central | 1594K | Swap |  | 2024 Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2024-01-24 | 2024-01-30 |  | 2024-01-31 |  | Closed | 2024-02-05 | 2024-05-06 | CD//Sofiah | 2024-05-06 | BOQ CelcomDigi_RAN_AllStar_Standard PR TSS_Central_20240128 | DU00002862713 |  |  | 2024-07-01 | 2024-06-15 |  |  | IN-BUILDING |  | Add R8862A S2100 x3+R8862A S2601 x3+R8862A S1800 x3,Dismantle
W01011 | W066Q_W01011OD_DESAPETALING | Central |  | Decomm |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-15 |  |  |  | 2023-11-17 |  | 2023-11-20 | 2024-01-22 | CD//Ali Akaram | 2023-12-08 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231116 | DU00002862714 |  |  |  |  | 2024-07-27 |  | UNIPOLE
W01412 | W066N_W01412IB2_NAZA_PLATINUMBLOCKB | Central | 1774K | Swap |  | 2026 | AI | Magicell | 4.6 TSSR Approved |  | 2024-06-18 | 2024-06-25 |  | 2024-06-28 |  | Under Approval | 2024-09-10 | 2025-10-06 | CD//Sofiah | 2025-10-06 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240311 | DU00002862715 | [5 empty] | Portables BTS | IN-BUILDING |  | Add R8894E M1821x8+R8862A S2601x8,Dismantle
W01458 | W066V_W01458OD_TNBBANGSAR2 | Central | 1227K | Swap |  | 2024 Q2 | CR | GCI | 4.6 TSSR Approved |  | 2024-06-04 | 2024-06-06 |  | 2024-06-12 |  | Closed | 2024-06-10 | 2024-06-20 | CD//Sapian | 2024-06-19 | CelcomDigi_RAN_GCI_TSS_Central_20240528 | DU00002862716 |  |  | 2024-09-13 | 2024-09-11 |  | In-Building System | IN-BUILDING | 6 | Add R9264H M901821 x3+R8862A S2601 x3,Dismantle
W01513 | W066J_W01513IB_CELCOMIC5GUTM | Central | 1597K | Site Out (Swap) | Swap->Site Out->Site Out (Swap) | 2024 Q1 | MA | CCSMY | [SiteOut]- 1.0 Pending Survey - Subcon | [6 empty] | To be Submitted |  |  | CD//Sofiah |  | SQ202506170753 | DU00002862717 | [6 empty] | BOOM
W01515 | W066N_W01515IB_KLCONVENTION_CENTRE_LOT91 | Central | 1775K | On Hold | Swap->On Hold->Decomm | 2024 Q2 |  | Magicell | 4.6 TSSR Approved |  | 2024-02-28 | 2024-03-11 |  | 2024-03-13 | 2025-06-19 | Under Approval | 2025-07-07 | 2025-09-30 | CD//Sofiah | 2025-07-08 | SQ202411140058 | DU00002862718 | [5 empty] | Portables BTS | INBUILDING |  | Add R8894E M1821 x3+R8862A S2601 x3,Dismantle
W01533 | W066BB_W01533IB_EKOCHERAS_MALL | Central |  | Decomm |  | 2024 Q3 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-11-14 |  |  |  | 2023-11-28 |  | 2023-12-18 | 2024-02-23 | CD//Sofiah | 2024-02-15 | CelcomDigi_RAN_CCSMY_TSS_Central_20231116 | DU00002862719 |  |  |  |  | 2024-10-11 |  | INBUILDING
W00635 | W066N_W00635IB_SMARTTUNNEL | Central |  | Decomm |  | 2024 Q3 | CR | YPTT | 4.6 TSSR Approved |  | 2025-05-21 |  | 2025-05-16 |  | 2025-05-21 |  | 2025-05-22 | 2025-07-14 | CD//Sofiah | 2026-04-17 | 0924CD-Central-Magicell-BOQ Template(new contract) | DU00002862720 |  |  |  |  | 2025-11-28 |  | IN-BUILDING
B01568 | B061O_B01568IB_UPTOWN2 | Central |  | Decomm |  | 2024 Q3 | CR | GCI | 4.6 TSSR Approved |  | 2023-11-10 |  |  |  | 2023-11-20 |  | 2024-01-23 | 2024-09-25 | CD//Sofiah | 2024-03-26 | CelcomDigi_RAN_GCI_TSS_Central_20231113 | DU00002862721 |  |  |  |  | 2024-06-06 |  | BOOM
B01380 | B061T_B01380IB_JAYA33 | Central |  | Decomm | Decomm->Site out->Decomm | 2024 Q3 | SM | GCI | 4.6 TSSR Approved |  | 2024-03-30 |  |  |  | 2024-04-05 |  | 2024-04-15 |  | CD//Sofiah | 2024-05-07 | S1MY2021071007WBF1-3892 / SQ202506120286 | DU00002862722 |  | MISSING FE PART |  |  | 2025-09-25 |  | IN-BUILDING
B01280 | B061T_B01280IB_JAYAONE | Central |  | Decomm | Decomm->On Hold->Swap->Decomm | 2024 Q3 | SHA | GCI | 4.6 TSSR Approved |  | 2024-03-31 |  | 2024-07-01 |  | 2024-07-04 |  | 2024-07-19 | 2025-03-20 | CD//Sofiah | 2024-07-22 | SQ202512150587 | DU00002862723 |  |  |  |  | 2025-06-23 | Portables BTS | BOOM
B01133 | B064I_B01133OD_SGTEKALA | Central |  | Decomm |  | 2024 | SH | GCI | 4.6 TSSR Approved |  | 2024-02-16 |  |  |  | 2024-03-08 |  | 2024-05-28 | 2025-03-21 | CD//Ali Akaram | 2024-06-19 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240217 | DU00002862724 |  |  |  |  | 2024-10-30 |  | TOWER
B01161 | W067A_B01161OD_PR_PRESINT9WPPJ | Central | 1851K | Swap | Decomm->Swap | 2024 Q3 | AI | Magicell | 4.6 TSSR Approved |  | 2024-08-12 | 2024-08-15 |  | 2024-08-16 | 2024-03-28 | Closed | 2024-08-20 | 2024-08-26 | CD//Sapian | 2024-08-23 | CelcomDigi_RAN_Magicell_TSS_Central_20240424 | DU00002862725 |  |  | 2024-11-12 | 2024-11-07 |  | In-Building System | BOOM | 3 | Add R8862A S9000 x1+R9264H M901821 x2+R8862A S2601 x3+A9732 M1821 x1,Dismantle | 3 | 0
B02271 | B064C_B02271OD_G23FKLTPERTANIAN | Central |  | Decomm |  | 2024 Q3 | SY1 | GTSB | 4.6 TSSR Approved |  | 2024-09-02 |  | 2024-09-08 |  | 2024-09-18 |  | 2024-09-19 | 2024-10-28 | CD//Norhaliza | 2024-10-03 | 0924CD-Central-GTSB-BOQ Template(new contract) | DU00002862726 |  |  |  |  | 2024-10-24 |  | AESTHETIC MONOPOLE
B00863 | B061Q_B00863IB_MENARAPKNSPJ | Central |  | Decomm |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-03-29 |  |  |  | 2024-05-08 |  | 2024-05-09 | 2024-07-12 | CD//Sofiah | 2024-05-23 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_202400403 | DU00002862727 |  |  |  |  | 2024-05-21 |  | BOOM
B00118 | B064B_B00118OD_TANMENGJAYA2 | Central |  | Decomm |  | 2024 Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2024-03-15 |  |  |  | 2024-04-26 |  | 2024-05-07 | 2024-07-12 | CD//Ali Akaram | 2024-05-17 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240316 | DU00002862728 |  |  |  |  | 2024-08-28 |  | TRIPOD
B00889 | B061J_B00889IB_IOIMALL | Central |  | Decomm | Decomm->On hold->Decomm | 2024 Q3 | BY | Magicell | 4.6 TSSR Approved |  | 2024-03-20 |  |  |  | 2024-03-22 |  | 2024-04-17 | 2024-05-27 | CD//Sofiah | 2024-07-24 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240323 | DU00002862729 |  |  |  |  | 2024-10-18 |  | BOOM
B00871 | B064C_B00871IB_MINESEXHIBITION | Central |  | Decomm | Decomm->On hold->Decomm | 2024 Q3 | BY | Magicell | 4.6 TSSR Approved |  | 2024-02-14 |  |  |  | 2024-02-18 |  | 2024-04-17 | 2024-05-27 | CD//Sofiah | 2024-06-11 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240311 | DU00002862730 |  |  |  |  | 2025-03-26 |  | BOOM
W00460 | W066U_W00460IB1_MIDVALLEY | Central |  | Decomm |  | 2024 Q2 | SH | CCSMY | 4.6 TSSR Approved |  | 2023-12-26 |  | 2025-10-30 |  | 2024-01-03 |  | 2024-07-25 | 2026-01-21 | CD//Sofiah | 2026-03-31 | CelcomDigi_RAN_CCSMY_TSS_Central_20231230 | DU00002862731 |  |  |  |  | 2025-01-21 |  | UNIPOLE
W00366 | W066H_W00366IB_ALPHAANGLE | Central |  | Decomm | Decomm->On hold->Decomm | 2024 Q1 | AI | Magicell | 4.6 TSSR Approved | 1/3- Need old IBC TSSR for solution preparation. SA Halim support on TSSR collection. | 2024-10-28 |  | 2024-11-01 |  | 2024-11-08 |  | 2024-11-11 | 2024-12-31 | CD//Sofiah | 2024-12-17 | 0924CD-Central-Magicell-BOQ Template(new contract) | DU00002862732 |  |  |  |  | 2025-01-03 |  | SHARING STRC MAXIS
W00444 | W066H_W00444IB_CARREFOURWMJ | Central |  | Decomm |  | 2024 Q1 | SY1 | GTSB | 4.6 TSSR Approved |  | 2024-06-29 |  | 2024-07-03 |  | 2024-07-11 |  | 2024-07-27 |  | CD//Sofiah | 2024-08-01 | 0701Central-GTSB-BOQ Template (template) | DU00002862733 |  | Pls provide TM LL photo |  |  | 2024-08-13 |  | IN-BUILDING
B00959 | B061O_B00959IB_ONEWORLDHTL | Central |  | Decomm |  | 2024 Q3 | SY1 | GCI | 4.6 TSSR Approved |  | 2023-12-20 |  |  |  | 2023-12-26 |  | 2024-01-11 | 2026-01-21 | CD//Sofiah | 2026-03-31 | CelcomDigi_RAN_GCI_TSS_Central_20231224 | DU00002862734 |  |  |  |  | 2024-09-13 |  | INBUILDING
W00978 | W066T_W00978IB_TESCOSCOTTGARDEN | Central |  | Decomm |  | 2024 Q3 | SY1 | GCI | 4.6 TSSR Approved |  | 2024-09-27 |  | 2024-09-30 |  | 2024-10-02 |  | 2024-10-03 | 2024-11-08 | CD//Sofiah | 2024-11-07 | 0925CD-Central-GCI-BOQ Template(new contract) | DU00002862735 |  |  |  |  | 2024-09-27 |  | IBC
B00801 | B063B_B00801OD_PKNSALAK | Central |  | Decomm | Decomm->On Hold->Decomm | 2025 Q3 | CR | GCI | 4.6 TSSR Approved |  | 2024-03-18 |  |  |  | 2024-03-19 |  | 2024-03-21 |  | CD//Sapian | 2024-04-03 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240323 | DU00002862736 |  | MISSING FE PART |  |  | 2025-05-15 |  | MINI STRUCTURE
W00323 | W066U_W00323IB_IGBMIDVALLEY | Central |  | Decomm | Decomm->Site out->Decomm | 2024 Q2 | AI | GCI | 4.6 TSSR Approved |  | 2025-07-16 |  | 2025-07-29 |  | 2025-08-08 | To be Submitted | 2025-09-10 |  | CD//Sofiah | 2025-10-22 | SQ202508140671 | DU00002862737 |  |  |  |  | 2025-10-21 |  | UNIPOLE
W00642 | W066U_W00642IB1_MVGARDENS | Central |  | Decomm |  | 2024 Q2 | SY1 | YPTT | 4.6 TSSR Approved |  | 2024-06-24 |  | 2024-07-01 |  | 2024-07-02 |  | 2024-08-13 | 2025-01-14 | CD//Sofiah | 2024-12-18 | 0628Central-YPTT-BOQ Template (template) | DU00002862738 |  |  |  |  | 2024-11-28 |  | IN-BUILDING
B01153 | B064B_B01153IB_JUSCOCHRSSLTN | Central |  | Decomm |  | 2024 Q4(single site MOCN)-L26 SSM | SY1 | Solusi | 4.6 TSSR Approved |  | 2024-07-17 |  |  |  | 2024-09-09 |  | 2024-09-10 |  | CD//Sofiah | 2024-09-11 | 0724Central-Solusi-BOQ Template | DU00002862739 |  |  |  |  | 2024-11-22 |  | SHARING STRC MAXIS
B01355 | B063C_B01355OD_KOTAWARISAN | Central |  | Decomm |  | 2024 | AI | GTSB | 15.4 Decomm Done without TSSR Approval |  | 2025-03-21 |  | 2025-03-27 |  | 2025-04-07 | To be Submitted | 2025-04-21 |  | CD//Ali Akaram |  | Wireless+ Malaysia CD+TSS+ CCSMY+5 site SQ202410310156 | DU00002862740 |  |  |  |  | 2025-05-14 |  | TOWER
B01154 | B064C_B01154IB_JJTMNEQUINE | Central |  | Decomm |  | 2024 Q3 | CR | GCI | 4.6 TSSR Approved |  | 2024-02-20 |  |  |  | 2024-02-29 |  | 2024-04-26 | 2024-08-29 | CD//Sofiah | 2024-05-07 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240303 | DU00002862741 |  |  |  |  | 2024-10-16 |  | INBUILDING
B01294 | B064C_B01294OD_PR_KM20.4KLPJHWY | Central |  | Decomm |  | 2024 Q3 | CR | GTSB | 4.6 TSSR Approved |  | 2024-06-07 |  | 2024-06-20 |  | 2024-06-14 |  | 2024-06-21 | 2024-07-12 | CD//Sapian | 2024-07-03 | 0610Central-GTSB-BOQ Template (template) | DU00002862742 |  |  |  |  | 2024-08-30 |  | TOWER
B02529 | B061L_B02529OD_NUSAPUTRAPDANA | Central |  | Decomm | Decomm-On Hold-Decomm | 2024 Q3 | CR | Magicell | 4.6 TSSR Approved |  | 2024-03-05 |  |  |  | 2024-05-14 |  | 2024-05-23 | 2024-05-31 | CD//Ali Akaram | 2024-05-28 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240316 | DU00002862743 |  |  |  |  | 2024-12-13 |  | LAMP_POLE
B00177 | B064F_B00177OD_KAJANGUTAMA3 | Central |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4(single site MOCN)-L2126 SSM | HW | GTSB | 4.6 TSSR Approved |  | 2024-09-11 |  | 2025-03-12 |  | 2025-03-13 |  | 2025-03-14 | 2025-07-14 | CD//Sapian | 2025-03-17 | 0809CD-Central-YPTT-BOQ Template(new contract) | DU00002862744 |  |  |  |  | 2025-03-27 |  | MINARATE
B00947 | W066X_B00947IB_APGPOINTIND | Central |  | Decomm | Decomm->On hold->Decomm | 2024 Q4 | SH | GCI | 4.6 TSSR Approved |  | 2024-06-10 |  | 2024-06-20 |  | 2024-06-18 |  | 2024-07-25 | 2024-09-25 | CD//Sofiah | 2024-07-29 | 0618Central-GCI-BOQ Template (template) | DU00002862745 |  |  |  |  | 2024-08-24 |  | BOOM
W00411 | W066S_W00411IB_PEARLPOINT | Central |  | Decomm | Decomm->On hold->Decomm | 2024 Q3 | CR | GCI | 4.6 TSSR Approved |  | 2024-06-05 |  | 2024-06-20 |  | 2024-06-21 |  | 2024-06-24 | 2024-09-25 | CD//Sofiah | 2024-07-01 | 0809CD-Central-GCI-BOQ Template(new contract) | DU00002862746 |  |  |  |  | 2024-07-23 |  | BOOM
B00891 | W066Y_B00891IB_PANDANCAPITOL | Central |  | Decomm | Decomm->On hold->Decomm | 2024 Q3 | ZA | Magicell | 4.6 TSSR Approved |  | 2024-04-04 |  |  |  | 2024-04-17 |  | 2024-04-17 | 2024-05-12 | CD//Sofiah | 2024-04-24 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240407 | DU00002862747 |  |  |  |  | 2024-08-10 |  | BOOM
B00896 | B061Q_B00896IB_PJHILTON | Central |  | Decomm | Decomm->On hold->Decomm | 2024 Q3 | AD | GCI | 4.6 TSSR Approved | 1/3- Need old IBC TSSR for solution preparation. SA Halim support on TSSR collection. | 2024-10-25 |  | 2024-10-30 |  | 2024-11-22 |  | 2024-11-27 |  | CD//Sofiah | 2024-12-18 | 0925CD-Central-GCI-BOQ Template(new contract) | DU00002862748 |  | Can we study to relocate the OB to 2830A |  |  | 2024-12-06 |  | BOOM
W00650 | W066U_W00650IB_PLAZASENTRAL2 | Central | 1837K | Swap | Decomm->On hold->Swap | 2024 Q2 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-12-27 | 2024-02-09 |  | 2024-02-26 | 2024-01-05 | Under Approval | 2024-02-28 | 2024-07-11 | CD//Sofiah | 2024-07-11 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240128 | DU00002862749 |  | 1) Please provide clear label photo for IDU | 2024-05-08 | 2024-04-27 |  | Portables BTS | BOOM | NA | Add R8862A S2100 x3+R8862A S2601 x3+R8862A S1800 x3,Dismantle
W00454 | W066V_W00454IB_BANGSARVLGE | Central |  | Decomm | Decomm->On hold->Decomm | 2024 Q2 | AD | CCSMY | 4.6 TSSR Approved |  | 2023-12-21 |  |  | 2024-02-05 | 2024-02-07 | Rectificating | 2024-02-16 | 2024-04-24 | CD//Sofiah | 2024-03-15 | BOQ CelcomDigi_RAN_CCSMY_Standard PR TSS_Central_20240128 | DU00002862750 |  |  |  |  | 2024-07-15 |  | In Building - SHARING STRC MAXIS
B01116 | B061L_B01116OD_PR_PUTRAPDANA4 | Central |  | Decomm | Decomm->On Hold->Decomm | 2024 Q3 | SH | Magicell | 4.6 TSSR Approved |  | 2024-03-21 |  |  |  | 2024-05-10 |  | 2024-05-20 |  | CD//Norhaliza | 2024-10-04 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240323 | DU00002862751 |  | Wrong FE |  |  | 2024-09-30 |  | MINARATE
W01300 | W066BB_W01300IB_GIANT_TMN_CONNAUGHT | Central |  | Decomm |  | 2024 Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2024-04-03 |  |  |  | 2024-04-16 |  | 2024-04-16 | 2024-07-10 | CD//Sofiah | 2024-04-19 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240407 | DU00002862752 |  |  |  |  | 2024-08-12 |  | IN-BUILDING
W00705 | W066N_W00705IB1_KLCONVENTION | Central |  | Decomm |  | 2024 Q2 | MS | GCI | 4.6 TSSR Approved |  | 2024-01-04 |  |  |  | 2024-02-07 |  | 2024-02-20 | 2024-09-25 | CD//Sofiah | 2024-05-06 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240108 | DU00002862753 |  |  |  |  | 2025-05-07 |  | IN-BUILDING
W01012 | W066N_W01012IB_GRANDHYATT | Central |  | Decomm |  | 2024 Q2 | MS | Magicell | 4.6 TSSR Approved |  | 2024-02-23 |  |  |  | 2024-03-08 |  | 2024-03-14 | 2024-08-29 | CD//Sofiah | 2024-06-10 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240303 | DU00002862754 |  |  |  |  | 2024-09-25 |  | INBUILDING
B02438 | B061T_B02438IB_JAYA_SHOPPING_CENTER | Central |  | Decomm | Decomm->Site out->Decomm | 2024 Q3 | SS | GCI | 4.6 TSSR Approved |  | 2023-11-04 |  |  |  | 2023-11-20 |  | 2023-11-22 |  | CD//Sofiah | 2023-11-24 | Celcom Digi_RAN-GCI-TSS-Central-20231119 | DU00002862755 |  | 1) Missing FE part |  |  | 2025-05-26 |  | IN-BUILDING
B01832 | B061H_B01832OD_RD_PTUTAMARD | Central |  | Decomm |  | 2024 Q3 | SH | GTSB | 4.6 TSSR Approved |  | 2024-05-03 |  |  |  | 2024-06-12 |  | 2024-06-20 | 2024-08-29 | CD//Ali Akaram | 2024-06-24 | CelcomDigi_RAN_GTSB_TSS_Central_20240423 | DU00002862756 |  |  |  |  | 2024-07-01 |  | UNIPOLE
S00329 | S098B_S00329OD_CENTREPOINTLHDID | Sabah |  | Decomm | Decomm->On Hold | 2024 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2024-05-15 |  | 2024-09-02 |  | 2024-05-17 |  | 2024-05-21 | 2024-07-29 | CD//Ray Amos | 2024-05-23 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240519 | DU00002862757 |  |  |  |  | 2024-12-06 |  | BOOM
B00867 | B061T_B00867IB_PHILEODAMANSARA | Central |  | Decomm | Decomm->On hold->Decomm | 2024 Q3 | CR | Magicell | 4.6 TSSR Approved |  | 2024-04-04 |  |  |  | 2024-04-16 |  | 2024-07-22 | 2024-08-13 | CD//Sofiah | 2024-07-24 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240407 | DU00002862758 |  |  |  |  | 2024-06-19 |  | BOOM
B00872 | B061Q_B00872IB_AMCORPMALL | Central |  | Decomm | Decomm->On hold->Decomm | 2024 Q3 | SH | DATASCO | 4.6 TSSR Approved | 19/3- SA Halim revert TSSR received. 1/3- Need old IBC TSSR for solution preparation. SA Halim support on TSSR collection. | 2024-04-24 |  |  |  | 2024-05-21 |  | 2024-05-23 |  | CD//Sofiah | 2024-06-24 | CelcomDigi_RAN_Datasco_TSS_Central_20240513 | DU00002862759 |  |  |  |  | 2024-08-24 |  | BOOM
W00707 | W066U_W00707IB_NORTHTWRMVG | Central |  | Decomm | Decomm->On hold->Decomm | 2024 Q2 | AI | Magicell | 4.6 TSSR Approved |  | 2024-08-02 |  | 2024-08-14 |  | 2024-08-16 |  | 2024-09-03 |  | CD//Sofiah | 2024-09-04 | 0801CD-Central-Magicell-BOQ Template(new contract) | DU00002862760 |  |  |  |  | 2024-09-25 |  | IN-BUILDING
W00728 | W066U_W00728IB_UEM | Central |  | Decomm | Decomm->TBD->Swap->On Hold->Decomm | 2024 Q2 | SHA | CCSMY | 4.6 TSSR Approved |  | 2024-04-30 | 2024-05-08 |  | 2024-05-10 | 2024-10-22 | Closed | 2024-11-13 |  | CD//Sofiah | 2024-12-18 | 0813CD-Central-CCSMY-BOQ Template(new contract) | DU00002862761 |  | Latest plan, this site using xC XMT |  |  | 2025-06-11 | Portables BTS | BOOM
W01144 | W066U_W01144IB_MENARASHELLKLSENTRAL | Central |  | Decomm |  | 2024 Q2 | SS | DATASCO | 4.6 TSSR Approved |  | 2024-01-24 |  |  |  | 2024-01-31 |  | 2024-02-05 |  | CD//Sofiah | 2024-03-11 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240128 | DU00002862762 |  | PHOTO NOT COMPLETE |  |  | 2024-11-14 |  | IN-BUILDING
W01002 | W066U_W01002IB_CIMBKLSENTRAL | Central |  | Decomm | Decomm->On hold->Decomm | 2024 Q2 | SY1 | Datasco | 4.6 TSSR Approved |  | 2024-06-13 |  | 2024-07-20 |  | 2024-10-09 |  | 2024-10-10 | 2025-01-14 | CD//Sofiah | 2024-12-18 | 0918CD-Central-Datasco-BOQ Template (old contract) | DU00002862763 |  |  |  |  | 2025-01-27 |  | IN-BUILDING
W00216 | W066V_W00216OD_UNIVHOSPITAL | Central |  | Decomm |  | 2024 Q3 | AD | Solusi | 4.6 TSSR Approved |  | 2024-11-07 |  |  |  | 2024-11-14 |  | 2024-11-18 | 2025-03-07 | CD//Norhaliza | 2024-12-06 | 0924CD-Central-CCSMY-BOQ Template(new contract) | DU00002862764 |  |  |  |  | 2024-12-05 |  | BOOM
W01211 | W066BB_W01211IB_CHERASCENTRAL | Central |  | Decomm | Decomm->Site out->Decomm | 2024 Q3 | SM | Magicell | 4.6 TSSR Approved |  | 2024-04-05 |  |  |  | 2024-04-08 |  | 2024-04-15 | 2024-09-06 | CD//Sofiah | 2024-07-10 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240407 | DU00002862765 |  | RAN SOW Change to Site Out |  |  | 2025-05-28 |  | IN-BUILDING
A01149 | A040C_A01149IB_AEONBIG_IPOH | Northern |  | Decomm |  | 2024 Q2 | SM | CCSMY | 4.6 TSSR Approved |  | 2024-01-09 |  |  |  | 2024-01-11 |  | 2024-01-19 | 2024-02-15 | CD//Affendi | 2024-01-30 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240110-0085 | DU00002862766 |  |  |  |  | 2024-07-03 |  | IN-BUILDING
W01137 | W066U_W01137IB_NUSENTRAL | Central |  | Decomm | Decomm->On hold->Decomm | 2024 Q2 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-12-28 |  |  |  | 2024-01-12 |  | 2024-02-05 | 2024-05-27 | CD//Sofiah | 2024-05-06 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240128 | DU00002862767 |  |  |  |  | 2024-12-20 |  | IN-BUILDING
W00823 | W066V_W00823IB_BANGSARSOUTH | Central |  | Decomm | Decomm->On hold->Decomm | 2024 Q2 | BY | Magicell | 4.6 TSSR Approved |  | 2024-04-19 |  |  |  | 2024-04-23 |  | 2024-05-21 | 2025-03-07 | CD//Sofiah | 2024-05-29 | CelcomDigi_RAN_Magicell_TSS_Central_20240424 | DU00002862768 |  |  |  |  | 2025-04-23 |  | BOOM
W01159 | W066U_W01159IB_STREGISKL | Central |  | Decomm | Decomm->On hold->Decomm | 2024 Q2 | SY1 | DATASCO | 4.6 TSSR Approved |  | 2023-12-18 |  | 2024-07-08 |  | 2024-07-12 |  | 2024-07-15 | 2024-08-20 | CD//Sofiah | 2024-07-22 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240128 | DU00002862769 |  |  |  |  | 2024-08-07 |  | IBC
B02009 | W067A_B02009IB_KPKTWPPJ | Central |  | Decomm | Decomm->Swap->Decomm | 2024 Q3 | SHA | Magicell | 4.6 TSSR Approved |  | 2024-06-05 | 2024-06-13 | 2024-08-13 | 2024-06-18 | 2024-08-15 | Under Approval | 2024-08-19 | 2024-10-28 | CD//Sofiah | 2024-10-24 | 0808CD-Central-Magicell-BOQ Template(new contract) | DU00002862770 |  |  |  |  | 2025-03-11 | Watertank | IN-BUILDING | NA
A00751 | A039A_A00751OD_PARITBUNTARIND_RDD | Northern |  | Decomm |  | 2024 Q3(single site MOCN) | SM | GTSB | 4.6 TSSR Approved |  | 2023-12-07 |  |  |  | 2023-12-27 |  | 2023-12-28 | 2024-01-22 | CD//Affendi | 2023-12-28 | Celcom Digi_RAN-GTSB-TSS-Northern-20231207-0073 | DU00002862771 |  |  |  |  | 2024-08-14 |  | MONOPOLE
W01413 | W066V_W01413IB_UOATOWERHQBANGSARSOUTH | Central |  | Decomm |  | 2024 Q2 | SS | CCSMY | 4.6 TSSR Approved |  | 2024-01-17 |  |  |  | 2024-01-23 |  | 2024-01-24 | 2024-04-24 | CD//Sofiah | 2024-04-22 | CelcomDigi_RAN_CCS_TSS_Central_20240124 | DU00002862772 |  |  |  |  | 2025-10-21 |  | IN-BUILDING
B01978 | B061T_B01978OD_CRYSTALPLAZA | Central |  | Decomm |  | 2024 Q3 | AD | Ascentrack | 4.6 TSSR Approved |  | 2024-01-19 |  |  |  | 2024-01-31 |  | 2024-02-05 | 2025-01-14 | CD//Sapian | 2024-02-19 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240128 | DU00002862773 |  |  |  |  | 2024-08-26 |  | RT - Wall Mount Boom | 5m
W01155 | W066V_W01155IB_Pantai_Hospital_Bangsar | Central |  | Decomm |  | 2024 Q2 | SH | CCSMY | 4.6 TSSR Approved |  | 2023-11-29 |  | 2025-10-30 |  | 2023-12-07 |  | 2024-02-22 |  | CD//Sofiah | 2024-05-06 | CelcomDigi_RAN_CCSMY_TSS_Central_20231201 | DU00002862774 |  | Missing FE part |  |  | 2024-08-08 |  | IN-BUILDING
B00041 | B061O_B00041OD_DSARAUPTOWN | Central |  | Decomm |  | 2024 Q3 | SHA | DATASCO | 4.6 TSSR Approved |  | 2024-05-23 |  |  |  | 2024-07-24 |  | 2024-07-25 | 2024-09-25 | CD//Ali Akaram | 2024-07-30 | CelcomDigi_RAN_Datasco_TSS_Central_20240528 | DU00002862775 |  |  |  |  | 2024-08-15 |  | BOOM
B00426 | B061L_B00426OD_PCHGPERMAI | Central |  | Decomm |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-04 |  |  |  | 2024-03-12 |  | 2024-04-18 | 2025-03-20 | CD//Sapian | 2024-05-11 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240108 | DU00002862776 |  |  |  |  | 2024-10-23 |  | BOOM
W01349 | W066V_W01349IB_Pantai_Medical_Center_New_Wing(BlockA) | Central |  | Decomm |  | 2024 Q2 | MS | CCSMY | 4.6 TSSR Approved |  | 2023-11-29 |  | 2025-10-30 | 2023-12-04 | 2023-12-04 | Under Approval | 2024-01-17 |  | CD//Sofiah | 2024-01-23 | CelcomDigi_RAN_CCSMY_TSS_Central_20231201 | DU00002862777 |  |  |  |  | 2025-04-16 |  | INBUILDING
W01542 | W066V_W01542OD_PR_JLNBPANTAISL3 | Central |  | Decomm |  | 2024 Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2024-01-19 |  |  |  | 2024-02-14 |  | 2024-02-15 |  | CD//Ali Akaram | 2024-03-13 | BOQ CelcomDigi_RAN_AllStar_Standard PR TSS_Central_20240128 | DU00002862778 |  | MISSING FE PART |  |  | 2024-08-30 |  | LAMP_POLE
W00547 | W066R_W00547IB_AXIATAARENASTADIUM | Central |  | Decomm |  | 2024 Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2024-01-22 |  |  |  | 2024-01-31 |  | 2024-03-21 | 2024-04-24 | CD//Sofiah | 2024-03-27 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240128 | DU00002862779 |  |  |  |  | 2024-01-30 |  | IN-BUILDING
B02685 | B061S_B02685OD_WISMAGAM_TS | Central |  | Decomm |  | 2024 Q3 | SHA | GTSB | 4.6 TSSR Approved |  | 2024-05-03 |  |  |  | 2024-06-20 |  | 2024-06-20 | 2024-11-26 | CD//Ali Akaram | 2024-06-21 | CelcomDigi_RAN_GTSB_TSS_Central_20240423 | DU00002862780 |  |  |  |  | 2024-06-25 |  | BOOM
Q00361 | Q132C_Q00361OD_MARRIOT | Sarawak |  | Decomm |  | 2025 Q1 | SH | Trintel | 4.6 TSSR Approved |  | 2023-11-07 |  |  |  | 2023-11-08 |  | 2023-11-08 | 2023-11-18 | CD//John | 2023-11-08 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231107 | DU00002862781 |  |  |  |  | 2025-11-22 |  | BOOM
W01312 | W066N_W01312IB_FOURSEASON_MALL_HOTEL | Central |  | Decomm |  | 2024 Q2 | SS | Magicell | 4.6 TSSR Approved |  | 2024-01-24 |  |  |  | 2024-02-09 |  | 2024-02-13 | 2024-05-12 | CD//Sofiah | 2024-04-24 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240128 | DU00002862782 |  |  |  |  | 2024-09-13 |  | IN-BUILDING
W01449 | W066U_W01449IB_SOUTH_POINT_MID_VALLEY | Central |  | Decomm |  | 2024 Q2 | SY1 | YPTT | 4.6 TSSR Approved |  | 2024-06-14 |  | 2024-07-01 |  | 2024-07-10 | To be Submitted | 2024-07-11 |  | CD//Sofiah | 2024-07-23 | 0618Central-YPTT-BOQ Template (template) | DU00002862783 |  | No Cisco Router photo |  |  | 2025-09-25 |  | IN-BUILDING
B00217 | B063B_B00217OD_PR_LABULANJUT | Central |  | Decomm |  | 2024 | CR | GCI | 4.6 TSSR Approved |  | 2024-01-22 |  |  |  | 2024-01-25 |  | 2024-01-30 | 2025-03-21 | CD//Norhaliza | 2024-02-15 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240128 | DU00002862784 |  |  |  |  | 2024-10-31 |  | TOWER
B00216 | B063B_B00216OD_TMKLIA | Central | 1889K | Swap | Decomm->On Hold->Swap | 154 single site MOCN | AI | GTSB | 4.6 TSSR Approved |  | 2024-05-13 | 2024-08-27 |  | 2024-09-02 | 2024-07-01 | Closed | 2024-12-05 | 2024-12-06 | CD//Ali Akaram | 2024-12-06 | 0823CD-Central-GTSB-BOQ Template(new contract)(1) | DU00002862785 |  |  | 2024-11-21 | 2024-11-18 |  | Tower | TOWER | 40m | Add R8862A S9000 x2 + A9732 M1821 x2 + R9264H M901821 x1+R8862A S2601 x3, Dismantle Celcom RRU | 23
B01829 | B061T_B01829OD_BGNLUXORPJ | Central |  | Decomm |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-05-09 |  |  |  | 2024-05-09 |  | 2024-05-16 |  | CD//Ali Akaram | 2024-05-23 | CelcomDigi_RAN_Datasco_TSS_Central_20240513 | DU00002862786 |  | Missing antenna tx photo at NE & FE part |  |  | 2024-06-06 |  | UNIPOLE
W01131 | W066V_W01131OD_KGPANTAIDALAM | Central |  | Decomm |  | 2024 Q2 | MA | Solusi | 4.6 TSSR Approved |  | 2024-05-27 |  |  |  | 2024-05-30 |  | 2024-05-31 | 2024-11-26 | CD//Ali Akaram | 2024-06-04 | BOQ CelcomDigi_RAN_Solusi_Standard PR TSS_Central_20240605 | DU00002862787 |  |  |  |  | 2024-08-30 |  | Lampole
W01427 | W066Q_W01427OD_JLN1C_149_SRIPETALING | Central |  | Decomm |  | 2024 Q3 | SM | Ascentrack | 4.6 TSSR Approved |  | 2024-02-07 |  |  |  | 2024-02-16 |  | 2024-04-01 | 2025-03-21 | CD//Ali Akaram | 2024-05-06 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240212 | DU00002862788 |  |  |  |  | 2024-07-30 |  | LAMP_POLE
B00709 | B061H_B00709OD_TMNMEDAN2 | Central |  | Decomm |  | 2024 Q3 | SH | GTSB | 4.6 TSSR Approved |  | 2024-04-03 |  |  |  | 2024-05-20 |  | 2024-05-21 | 2024-07-12 | CD//Ali Akaram | 2024-05-28 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240415 | DU00002862789 |  |  |  |  | 2024-05-30 |  | SHARING STRC OTHERS MINARATE
W01000 | W066N_W01000IB_WISMAMCA | Central |  | Decomm | Decomm->On hold->Decomm | 2024 Q2 | CR | Magicell | 4.6 TSSR Approved |  | 2024-03-25 |  |  |  | 2024-03-29 |  | 2024-03-29 | 2024-07-10 | CD//Sofiah | 2024-04-03 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240329 | DU00002862790 |  |  |  |  | 2025-01-13 |  | Rooftop
B01088 | B063A_B01088OD_KGULUCHUCHUH | Central |  | Decomm |  | 2024 | AI | GTSB | 4.6 TSSR Approved |  | 2025-03-17 |  | 2025-03-26 |  | 2025-04-07 | To be Submitted | 2025-04-17 |  | CD//Ali Akaram | 2025-04-24 | Wireless+ Malaysia CD+TSS+ CCSMY+5 site SQ202410310156 | DU00002862791 |  |  |  |  | 2025-04-23 |  | TOWER
W00071 | W066W_W00071OD_AMPWALKOD2 | Central |  | Decomm |  | 2024 Q1 | AD | Ascentrack | 4.6 TSSR Approved |  | 2024-01-31 |  |  |  | 2024-02-02 |  | 2024-02-05 |  | CD//Norhaliza | 2024-02-08 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240202 | DU00002862792 |  | Missing FE part |  |  | 2024-09-06 |  | RT - Bipod Boom | 3m
B01553 | B064D_B01553OD_TSAUJANAIMPIAN | Central |  | Decomm |  | 2024 Q4 | SY1 | GCI | 4.6 TSSR Approved |  | 2024-09-12 |  | 2024-09-20 |  | 2024-09-26 |  | 2024-10-02 | 2025-01-14 | CD//Sapian | 2024-10-13 | 0924CD-Central-GCI-BOQ Template(new contract) | DU00002862793 |  |  |  |  | 2024-10-04 |  | LAMP_POLE
B01110 | B064D_B01110OD_TMNKANTANPERMAI | Central |  | Decomm |  | 2024 Q4 | SY1 | GCI | 4.6 TSSR Approved |  | 2024-10-02 |  |  |  | 2024-10-18 |  | 2024-10-21 | 2025-07-14 | CD//Ali Akaram | 2024-10-23 | 0924CD-Central-GCI-BOQ Template(new contract) | DU00002862794 |  |  |  |  | 2024-10-02 |  | LAMP_POLE
W01193 | W066M_W01193OD_JUNCTIONJLNAMPANGMRR2 | Central |  | Decomm |  | 2024 Q1 | SM | GCI | 4.6 TSSR Approved |  | 2024-08-05 |  | 2024-08-07 |  | 2024-08-08 |  | 2024-08-12 | 2024-09-25 | CD//Ali Akaram | 2024-08-21 | 0806CD-Central-GCI-BOQ Template(new contract) | DU00002862795 |  |  |  |  | 2024-08-27 |  | WALL MOUNTED BOOM
W01239 | W066U_W01239OD_JLN_TUN_SAMBANTHAN | Central | 1876K | Swap | Decomm->On Hold-Swap | 2024 Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2024-08-20 | 2024-08-26 |  | 2024-08-29 |  | Closed | 2024-08-30 | 2024-10-02 | CD//Ali Akaram | 2024-10-02 | 0809CD-Central-GTSB-BOQ Template(new contract) | DU00002862796 |  |  | 2024-12-17 | 2024-12-09 |  | In-Building System | POLE | 7M | Add R8862A S9000 x1+R9264H M901821 x2+R8862A S2601 x3+A9732 M1821 x1,Dismantle | 2 | 0
B02004 | B064B_B02004OD_DAMAIPERDANA2 | Central |  | Decomm |  | 2024 Q4(single site MOCN)-L2126 SSM | SY1 | Magicell | 4.6 TSSR Approved |  | 2024-09-09 |  | 2024-09-10 |  | 2024-09-11 |  | 2024-09-12 | 2025-01-14 | CD//Ali Akaram | 2024-09-25 | 0919CD-Central-Magicell-BOQ Template(new contract) 2 | DU00002862797 |  |  |  |  | 2024-11-15 |  | MONOPOLE
W01177 | W066Z_W01177OD_APRT_SRI_SHAMELIN_CHRS | Central | 1899K | Swap | Decomm->On Hold->Swap | 2026 | AI | CCSMY | 4.6 TSSR Approved |  | 2025-01-13 | 2025-01-17 |  | 2025-02-04 | 2024-02-08 | Closed | 2025-02-05 | 2025-02-10 | CD//Norhaliza | 2025-02-10 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240128 | DU00002862798 | [6 empty] | BOOM | 3 | Add R9264H M901821x3+R8862A S2601x3, Dismantle | 0 | 0
A00029 | A040D_A00029OD_PUSINGIND | Northern |  | Decomm |  | 2024 Q2 | BY | GTSB | 4.6 TSSR Approved |  | 2024-01-26 |  |  |  | 2024-02-05 |  | 2024-02-06 | 2024-04-23 | CD//Affendi | 2024-02-07 | Celcom Digi_RAN-GTSB-TSS-Northern-20240124-0089 | DU00002862799 |  |  |  |  | 2024-06-25 |  | TOWER
W01575 | W066S_W01575IB1_PAVILION_BUKIT_JALIL | Central |  | Decomm | Decomm->On hold->Decomm | 2024 Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2024-04-01 |  |  |  | 2024-04-06 |  | 2024-04-15 | 2024-07-12 | CD//Sofiah | 2024-04-29 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240403 | DU00002862800 |  |  |  |  | 2024-12-06 |  | IN-BUILDING
4466B | Ulu Chegar | Northern |  | Modernization | Maintain USP MOCN->On Hold->Maintain USP MOCN->Modernization | 2024 Q4 | HW | GTSB | 4.6 TSSR Approved |  | 2025-08-05 | 2025-08-22 |  | 2025-08-25 |  | Under Approval | 2025-08-26 | 2025-09-26 | E//Hazida | 2025-09-22 | SQ202508270460 | DU00002862801 |  |  | 2025-10-27 | 2025-10-27 |  | Tower | Tower | 60m | Add R8894E M1821x1, Dismantle R8862A S9000(A6A)x2+R8854E S1800(A6A)x3 | 0 | 0
4436B | Lempor Hilir RCC | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862802 | [6 empty] | Tower |  | Reuse Existing RRU | 0 | 0
W00017 | W066K_W00017OD_IJN | Central |  | Decomm |  | 2024 Q1 | ZA | AllStar | 4.6 TSSR Approved |  | 2024-01-11 |  |  |  | 2024-01-13 |  | 2024-01-18 | 2024-07-12 | CD//Norhaliza | 2024-05-31 | BOQ CelcomDigi_RAN_AllStar_Standard PR TSS_Central_20240115 | DU00002862803 |  |  |  |  | 2024-09-26 |  | BOOM
4437A | Lintang Sg Siput RDD | Northern |  | Maintain USP MOCN | Modernization->On Hold->Maintain USP MOCN | 2025 Q3 |  | CCSMY | 14.2 Drop (Done Survey) |  | 2024-01-07 | 2024-01-09 |  |  |  | To be Submitted |  |  |  |  | Celcom Digi_RAN-CCSMY-TSS-Northern-20240108-0084 | DU00002862804 |  |  |  | 2025-02-20 |  | Tower | Tower | 60 | Reuse Existing RRU | 0 | 0
4440A | FELDA Lasah RDD | Northern |  | Modernization | Modernization->On Hold->Modernization | 2025 Q3 | AI | CCSMY | 4.6 TSSR Approved |  | 2024-01-07 | 2024-01-10 |  | 2025-02-19 |  | Closed | 2025-03-12 | 2025-05-19 | E//Hazida | 2025-03-13 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240108-0084 | DU00002862805 |  |  | 2025-04-14 | 2025-04-11 |  | Tower | Tower | 60 | Add R8894E M1821x1 | 0 | 3
4371A | Manong | Northern |  | Modernization | Maintain USP MOCN->On Hold->Maintain USP MOCN->Modernization | 2024 Q4 | HW | GTSB | 4.6 TSSR Approved |  | 2025-08-05 | 2025-08-25 |  | 2025-08-27 |  | Under Approval | 2025-09-02 | 2025-09-26 | E//Hazida | 2025-09-03 | SQ202508270460 | DU00002862806 |  |  | 2025-09-14 | 2025-09-14 |  | Tower | 60m 4 Legged Tower | 60m | Dismantle R8862A S9000(A6A)x3+R8854E S1800(A6A)x3 | 0 | 0
B00534 | B064B_B00534OD_BALAKONG | Central |  | Decomm |  | 2024 Q3 | ZA | Magicell | 4.6 TSSR Approved |  | 2024-03-18 |  |  |  | 2024-03-21 |  | 2024-04-17 | 2025-10-01 | CD//Sapian | 2024-05-11 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240323 | DU00002862807 |  |  |  |  | 2024-09-25 |  | BOOM
B02696 | B061P_B02696OD_JLNPJU1_KGCEMPAKA | Central |  | Decomm |  | 2024 Q3 | ZA | Magicell | 4.6 TSSR Approved |  | 2024-02-23 |  |  |  | 2024-02-26 |  | 2024-03-27 | 2024-04-24 | CD//Sapian | 2024-04-21 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240303 | DU00002862808 |  |  |  |  | 2024-05-31 |  | UNIPOLE
4061Z | KGBATU11 | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862809
B00409 | B061L_B00409OD_KUALASGBARU | Central |  | Decomm |  | 2024 Q3 | BY | GTSB | 4.6 TSSR Approved |  | 2024-02-28 |  |  |  | 2024-03-01 |  | 2024-05-07 | 2025-03-07 | CD//Sapian | 2024-05-16 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240303 | DU00002862810 |  |  |  |  | 2024-10-23 |  | TOWER
B00818 | B061L_B00818OD_PR_SGRASAUHULU | Central |  | Decomm |  | 2024 Q3 | AI | Solusi | 4.6 TSSR Approved |  | 2024-06-26 |  |  |  | 2024-07-05 |  | 2024-08-07 |  | CD//Sapian | 2024-08-13 | 0709Central-Solusi-BOQ Template | DU00002862811 |  | Pls provide all TX EQ with clear label photo |  |  | 2024-10-09 |  | TOWER
A00113 | A037B_A00113OD_LANGKAP | Northern |  | Decomm |  | 2024 Q3(single site MOCN) | SM | CCSMY | 4.6 TSSR Approved |  | 2023-11-23 |  |  |  | 2023-12-06 |  | 2023-12-15 | 2024-10-01 | CD//Affendi | 2023-12-18 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231127-0073 | DU00002862812 |  |  |  |  | 2024-08-12 |  | TOWER
W00581 | W066T_W00581OD_PR_KUCHAIENTPARK | Central |  | Decomm |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-02-02 |  |  |  | 2024-04-16 |  | 2024-04-17 |  | CD//Norhaliza | 2024-06-19 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240212 | DU00002862813 |  | Not Enough TX Photo. Need include Fiber equipment photo in TSSR e.g. Cisco Router |  |  | 2024-05-30 |  | MINI MONOPOLE
4070Z | KGJAWANG | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862814
4066Z | KGBAWONG | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862815
4077Z | POS PERWOR(Kg Satut) | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862816
B00142 | B064C_B00142OD_PSRBORONGSG | Central |  | Decomm |  | 2024 Q3 | SY1 | GTSB | 4.6 TSSR Approved |  | 2024-08-27 |  | 2024-09-08 |  | 2024-10-24 |  | 2024-10-03 | 2025-01-14 | CD//Ali akaram | 2024-11-22 | 0903CD-Central-GTSB-BOQ Template(new contract) | DU00002862817 |  |  |  |  | 2024-09-26 |  | TOWER
A00199 | A044A_A00199OD_BBSRIISKANDAR_RCC | Northern |  | Decomm |  | 2024 Q2 | BY | CCSMY | 4.6 TSSR Approved | ¦ 0216 - YPTT: site cancel from YPTT | 2024-02-26 |  |  |  | 2024-03-07 |  | 2024-03-08 | 2024-03-13 | CD//Affendi | 2024-03-11 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240229-0097 | DU00002862818 |  |  |  |  | 2024-05-25 |  | TOWER
4067Z | PERLOP 1 | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862819
4082Z | T3E_0622_KgJong | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862820 | [6 empty] | 76m 4 Legged Tower
B00605 | W066Y_B00605OD_TMNCEMPAKA | Central |  | Decomm |  | 2024 Q2 | SHA | YPTT | 4.6 TSSR Approved |  | 2024-07-29 |  | 2024-08-01 |  | 2024-08-05 |  | 2024-08-06 | 2025-10-01 | CD//Ali Akaram | 2024-08-09 | 0731CD-Central-YPTT-BOQ Template(new contract) | DU00002862821 |  |  |  |  | 2024-08-17 |  | BOOM
4093Z | Paya Renggam | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862822
4095Z | Kg Ulu Piol | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862823
4094Z | Kg Cheh Hulu | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862824
S00203 | S105B_S00203OD_KGBATUPUTIH | Sabah |  | Decomm |  | 2024 Q3 | AD | Datasco | 4.6 TSSR Approved |  | 2024-04-27 |  |  |  | 2024-05-03 |  | 2024-05-07 | 2024-07-24 | CD//Ray Amos | 2024-05-09 | Celcom Digi_RAN-Datasco-Standard PR TSS-Sabah-20240503 | DU00002862825 |  |  |  |  | 2024-07-25 |  | TOWER
4153Z | Kg.Pechah Batu | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862826
B00151 | B061K_B00151OD_SAUJANAPCHG | Central |  | Decomm |  | 2024 Q3 | SY1 | Solusi | 4.6 TSSR Approved |  | 2024-07-15 |  |  |  | 2024-08-12 |  | 2024-08-14 | 2025-01-14 | CD//Ali akaram | 2024-12-16 | 0724Central-Solusi-BOQ Template | DU00002862827 |  |  |  |  | 2024-08-19 |  | TOWER
B02782 | B064C_B02782OD_PUTRA_PERMAI_TS | Central |  | Decomm |  | 2024 Q3 | SS | DATASCO | 4.6 TSSR Approved |  | 2024-01-26 |  |  |  | 2024-01-31 |  | 2024-02-05 | 2024-05-27 | CD//Ali Akaram | 2024-05-02 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240202 | DU00002862828 |  |  |  |  | 2024-08-28 |  | UNIPOLE
4081R | KG JARAU | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862829
W00130 | W066V_W00130OD_TMNSRISENTOSA | Central |  | Decomm |  | 2024 Q3 | BY | GTSB | 4.6 TSSR Approved |  | 2024-05-06 |  | 2024-07-08 |  | 2024-07-25 |  | 2024-07-30 | 2024-08-29 | CD//Sapian | 2024-08-05 | CelcomDigi_RAN_GTSB_TSS_Central_20240423 | DU00002862830 |  |  |  |  | 2024-08-17 |  | BOOM
4083R | KG PPMS PERLOP 1 | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862831
4078R | KG BENDANG SELINSING | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862832
4079R | KG JALONG | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862833
4012R | Kg Kelubong | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862834
4089R | PENGKALAN IKAN TALAPIA | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862835
B01958 | B061L_B01958OD_RD_BT12PCHG | Central |  | Decomm |  | 2024 Q3 | BY | GTSB | 4.6 TSSR Approved |  | 2024-01-05 |  |  |  | 2024-10-24 |  | 2024-05-08 | 2025-03-21 | CD//Ali Akaram | 2024-05-20 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240108 | DU00002862836 |  |  |  |  | 2024-10-23 |  | UNIPOLE
R00133 | R001C_R00133OD_PAUH | Northern |  | Decomm |  | 2025 Q3 | HW | GTSB | 4.6 TSSR Approved |  | 2023-12-28 |  |  |  | 2024-01-17 | To be Submitted | 2025-02-23 |  | CD//Hazwan | 2025-02-28 | Celcom Digi_RAN-GTSB-TSS-Northern-20231229-0081//SQ202501030229 - gtsb | DU00002862837 |  |  |  |  | 2025-08-20 |  | TOWER
B02791 | B061S_B02791OD_BICMA_TS | Central |  | Decomm |  | 2024 Q3 | SHA | GTSB | 4.6 TSSR Approved |  | 2024-05-03 |  |  |  | 2024-06-20 |  | 2024-06-20 | 2024-07-12 | CD//Ali Akaram | 2024-06-21 | CelcomDigi_RAN_GTSB_TSS_Central_20240423 | DU00002862838 |  |  |  |  | 2024-07-19 |  | UNIPOLE
B00653 | B061O_B00653OD_DSARAUTAMA3 | Central |  | Decomm |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-05-23 |  | 2024-08-14 |  | 2024-08-16 |  | 2024-08-19 | 2025-03-20 | CD//Norhaliza | 2024-12-13 | CelcomDigi_RAN_Datasco_TSS_Central_20240528 | DU00002862839 |  |  |  |  | 2024-08-19 |  | BOOM
B00073 | B061K_B00073OD_LESTARIPUCHONG | Central |  | Decomm |  | 2024 Q3 | SY1 | Solusi | 4.6 TSSR Approved |  | 2024-08-15 |  |  |  | 2024-08-29 |  | 2024-08-30 |  | CD//Ali Akaram | 2024-09-12 | 0924CD-Central-CCSMY-BOQ Template(new contract) | DU00002862840 |  |  |  |  | 2024-09-06 |  | TOWER
B01124 | B061J_B01124OD_BK5BDRKINRARA | Central |  | Decomm |  | 2024 Q3 | CR | GCI | 4.6 TSSR Approved |  | 2024-01-23 |  |  |  | 2024-03-07 |  | 2024-03-11 | 2025-03-20 | CD//Norhaliza | 2024-06-04 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240128 | DU00002862841 |  |  |  |  | 2024-09-27 |  | LAMP_POLE
W01031 | W066Z_W01031OD_TMNMIHARJA | Central |  | Decomm |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-23 |  |  |  | 2023-11-28 |  | 2023-12-06 | 2024-01-22 | CD//Norhaliza | 2024-01-18 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231126 | DU00002862842 |  |  |  |  | 2024-08-24 |  | BOOM
W00191 | W066W_W00191OD_DESAPANDAN | Central |  | Decomm |  | 2024 Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2024-03-20 |  |  |  | 2024-05-02 |  | 2024-05-13 | 2024-05-27 | CD//Ali Akaram | 2024-05-20 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240323 | DU00002862843 |  |  |  |  | 2024-08-18 |  | BOOM
B00127 | W066X_B00127OD_AMPANGPOINT | Central |  | Decomm |  | 2024 Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-01-31 |  |  |  | 2024-02-22 |  | 2024-05-15 | 2025-10-01 | CD//Norhaliza | 2024-08-21 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240202 | DU00002862844 |  |  |  |  | 2024-08-26 |  | BOOM
L00137 | S113A_L00137OD_TMNMUTIARA2 | Sabah |  | Decomm |  | 2024 |  | Datasco | 4.6 TSSR Approved |  | 2024-11-11 |  | 2024-11-20 |  | 2024-11-25 |  | 2024-11-25 | 2024-12-13 | CD//Ray Amos | 2024-11-29 | Celcom Digi_RAN-Datasco-Standard PR TSS-Sabah-20241030 | DU00002862845 |  |  |  |  | 2025-01-28 |  | TOWER
W00239 | W066Q_W00239OD_ENDAHPARADE | Central |  | Decomm |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved | 19/3- SA Halim revert TSSR received. 1/3- Need old IBC TSSR for solution preparation. SA Halim supp | 2024-05-27 |  |  |  | 2024-05-27 |  | 2024-05-29 |  | CD//Ali Akaram | 2024-06-05 | CelcomDigi_RAN_Datasco_TSS_Central_20240528 | DU00002862846 |  |  |  |  | 2024-10-18 |  | BOOM
W00082 | W066T_W00082OD_TMTMNDESA | Central |  | Decomm |  | 2024 Q3 | AI | CCSMY | 4.6 TSSR Approved | 9/9 - still pending CD revert. 3/9 - Pending CD to revert. // 18/8 - Team will share WNL by today // 14/8- 8/8 - Wk35 plan go in, Form TM submit today // 6/8 - TM site, access pending, raise up to SA to prioritize | 2025-10-16 |  | 2025-10-16 |  | 2025-10-24 | To be Submitted | 2025-10-24 |  | CD//Ali Akaram | 2025-10-28 | 0809CD-Central-CCSMY-BOQ Template(new contract) | DU00002862847 |  |  |  |  | 2025-10-27 |  | BOOM
W01479 | W066H_W01479OD_TMNDANAUKOTA_KL | Central |  | Decomm |  | 2024 Q1 | SHA | GTSB | 4.6 TSSR Approved |  | 2024-06-14 | 2024-07-15 |  |  | 2024-07-16 |  | 2024-07-19 | 2025-03-20 | CD//Ali Akaram | 2024-07-25 | Wireless+ Malaysia CD+TSS+ GTSB+9 site SQ202410310159 | DU00002862848 |  |  |  |  | 2024-08-15 | Lampole | LAMP_POLE | 18m
W01376 | W066H_W01376OD_TMN_SETAPAK_PERMAI | Central |  | Decomm |  | 2024 Q1 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-01-30 |  |  |  | 2024-02-14 |  | 2024-06-01 | 2024-08-27 | CD//Norhaliza | 2024-08-09 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240202 | DU00002862849 |  |  |  |  | 2024-05-07 |  | LAMP_POLE
W00249 | W066Z_W00249OD_PANDANSAFARI | Central |  | Decomm |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-10-02 |  | 2024-11-01 |  | 2024-10-09 |  | 2024-10-16 |  | CD//Ali Akaram | 2024-11-06 | 0924CD-Central-GTSB-BOQ Template(new contract) | DU00002862850 |  |  |  |  | 2024-10-11 |  | BOOM
B00719 | B063C_B00719OD_PR_KLIAITC | Central |  | Decomm |  | 2024 | SM | GTSB | 4.6 TSSR Approved |  | 2024-03-26 |  |  |  | 2024-04-01 |  | 2024-05-23 | 2025-03-21 | CD//Ali akaram | 2024-12-17 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240329 | DU00002862851 |  |  |  |  | 2024-11-25 |  | TOWER
B00720 | B063B_B00720DOD_CFORMULAONE | Central |  | Decomm |  | 2024 Q4 | SHA | GTSB | 4.6 TSSR Approved |  | 2023-12-28 |  | 2024-07-16 |  | 2024-08-07 |  | 2024-10-04 | 2026-01-06 | CD//Ali Akaram | 2024-11-29 | CelcomDigi_RAN_GTSB_TSS_Central_20231230 | DU00002862852 |  | . |  |  | 2025-10-27 |  | BOOM
B00437 | B063B_B00437OD_TMNDAHLIA | Central |  | Decomm |  | 2024 Additional | CR | GCI | 4.6 TSSR Approved |  | 2024-05-06 |  |  |  | 2024-05-13 |  | 2024-05-15 | 2024-11-26 | CD//Ali Akaram | 2024-11-19 | CelcomDigi_RAN_GCI_TSS_Central_20240517 | DU00002862853 |  |  |  |  | 2025-02-20 |  | BOOM
B01655 | B063B_B01655OD_MEDANSALAKTINGGI | Central |  | Decomm |  | 2025 Q3 | CR | GCI | 4.6 TSSR Approved |  | 2024-03-18 |  |  |  | 2024-03-15 |  | 2024-05-15 | 2024-09-03 | CD//Sapian | 2024-05-28 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240323 | DU00002862854 |  |  |  |  | 2025-02-20 |  | MINI STRUCTURE
B00057 | B064B_B00057OD_BDRHUSSIENONN4 | Central |  | Decomm |  | 2024 Q3 | ZA | Magicell | 4.6 TSSR Approved |  | 2023-12-25 |  |  |  | 2024-02-08 |  | 2024-04-17 | 2024-05-27 | CD//Ali Akaram | 2024-04-26 | CelcomDigi_RAN_Magicell_TSS_Central_20231227 | DU00002862855 |  |  |  |  | 2024-09-11 |  | MINI STRUCTURE
B02220 | B061L_B02220OD_WTBDRBKTPCHG | Central |  | Decomm |  | 2024 Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2024-02-08 |  |  |  | 2024-04-18 |  | 2024-05-13 | 2024-09-05 | CD//Sapian | 2024-05-21 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240212 | DU00002862856 |  |  |  |  | 2024-09-18 |  | AESTHETIC MONOPOLE
B00723 | B063C_B00723OD_ALTJENDERAM | Central |  | Decomm | Decomm->On hold->Decomm | 2024 | AD | GTSB | 4.6 TSSR Approved |  | 2024-01-10 |  |  |  | 2024-08-06 |  | 2024-11-22 | 2025-03-24 | CD//Ali Akaram | 2024-12-31 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240115 | DU00002862857 |  |  |  |  | 2024-10-24 |  | TOWER
W00139 | W066Q_W00139OD_PR_BBSRIPETALING | Central |  | Decomm |  | 2024 Q3 | MA | YPTT | 14.1 TSSR Not Required (Decomm by CD) | [6 empty] | To be Submitted |  |  | CD//Ali Akaram |  | 0809CD-Central-YPTT-BOQ Template(new contract) | DU00002862858 |  |  |  |  | 2024-11-25 |  | TRIPOD
W00002 | W066V_W00002OD_UM1LIBRARY | Central |  | Decomm |  | 2024 Q3 | IE | YPTT | 4.6 TSSR Approved |  | 2023-11-22 |  |  |  | 2023-11-28 |  | 2023-12-08 | 2024-01-22 | CD//Ali Akaram | 2024-01-05 | CelcomDigi_RAN_YPTT_TSS_Central_20231126 | DU00002862859 |  |  |  |  | 2024-08-27 |  | TRIPOD
W00248 | W066Z_W00248OD_SHAMELINPERK | Central |  | Decomm | Decomm->On Hold->Site Out->Decomm | 2024 Q3 | ZB | Ascentrack | 4.6 TSSR Approved |  | 2024-02-01 |  |  |  | 2024-02-09 |  | 2024-04-01 | 2025-03-21 | CD//Sapian | 2024-04-29 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240202 | DU00002862860 |  |  |  |  | 2025-06-26 |  | TRIPOD
B02680 | B064C_B02680OD_DESA_SERDANG | Central |  | Decomm |  | 2024 Q3 | CR | GTSB | 4.6 TSSR Approved |  | 2024-10-15 |  | 2024-10-17 |  | 2024-10-21 |  | 2024-11-07 | 2025-01-14 | CD//Sapian | 2024-11-12 | 0924CD-Central-GTSB-BOQ Template(new contract) | DU00002862861 |  |  |  |  | 2024-09-30 |  | UNIPOLE
K00545 | K004B_K00545OD_TMNKOMUDA | Northern |  | Decomm |  | 2024 Q3(single site MOCN) |  | CCSMY | 4.6 TSSR Approved |  | 2024-10-23 |  | 2024-10-27 |  | 2024-11-01 |  | 2024-11-26 |  | CD//Zulakmar | 2024-12-05 | 0809MW-Northern-CCSMY-BOQ Template(new contract)/0809CD-Northern-CCSMY-BOQ Template(new contract) | DU00002862862 |  | Missing TX Info |  |  | 2024-11-07 |  | TOWER
4969B | Guar Napai | Northern |  | Modernization | Modernization->On Hold->Modernization | 2024 Q3 | SM | GTSB | 4.6 TSSR Approved | 0224 -Requested planning team advise on CD query.¦ 0221 - Cd replu with query on Freq distribution.¦ 0220 - Replied to CD ML has been updated¦ 0218 - E//Hazida - Revise ML as per sample | 2024-01-20 | 2024-01-23 |  | 2025-01-21 |  | Rectificating | 2025-01-24 | 2025-04-29 | E//Hazida | 2025-04-28 | Celcom Digi_RAN-GTSB-TSS-Northern-20240124-0088 | DU00002862863 |  |  | 2025-02-18 | 2025-02-07 |  | Tower | Tower | 45M | Add R8894E M1821x1, Dismantle R8854E S1800(A6A)x3 | 0 | 2
4026Z | Bkt Kachi Badak | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862864
4126Z | Complex CIQ | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862865
4131Z | Kg. Alor Batu | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862866
4142Z | Kg Carok Tok Lateh | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862867
4122Z | Kg Wang Perah | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862868
B00760 | B057D_B00760OD_TMNSELASIH | Central |  | Decomm |  | 2024 Q1 | AD | Magicell | 4.6 TSSR Approved |  | 2024-02-17 |  |  |  | 2024-02-20 |  | 2024-02-22 |  | CD//Sapian | 2024-04-21 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240225 | DU00002862869 |  | In TP fiber remain |  |  | 2024-04-01 |  | TRIPOD
B00082 | B064G_B00082OD_SEK4BBBANGI | Central |  | Decomm |  | 2024 Q3 | SY1 | Solusi | 4.6 TSSR Approved |  | 2024-09-25 |  | 2024-10-15 |  | 2024-10-18 |  | 2024-10-21 | 2025-03-21 | CD//Ali akaram | 2024-11-25 | 0930CD-Central-Solusi-BOQ Template(new contract) | DU00002862870 |  |  |  |  | 2024-09-29 |  | TRIPOD
B00163 | W066I_B00163OD_UKAYPERDANA2 | Central |  | Decomm |  | 2024 Q1 | CR | GCI | 4.6 TSSR Approved |  | 2023-11-15 |  |  |  | 2023-12-01 |  | 2023-12-06 | 2025-05-27 | CD//Ali Akaram | 2023-12-12 | Celcom Digi_RAN-GCI-TSS-Central-20231119 | DU00002862871 |  |  |  |  | 2024-07-25 |  | LAMP_POLE
4127Z | Akademi Binaan Malaysia sintok | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862872
4143Z | Jln Wang Kelian (New - Kg Changkat Setol) | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862873
9058R | UluSkrang | Sarawak |  | Maintain USP MOCN(Dismantle Passive) | Maintain USP MOCN(Dismantle Passive)->On Hold->Maintain USP MOCN(Dismantle Passive) | 2024 Q4 | AI | Trintel | 4.6 TSSR Approved |  | 2025-06-30 |  | 2025-07-14 |  | 2025-07-21 |  | 2025-08-06 | 2025-09-24 | E//John | 2025-08-08 | SQ202506060240-Trintel | DU00002862874 |  |  |  |  | 2025-09-24 |  | #N/A
9233A | Lubok Antu Junction | Sarawak |  | Remote MOCN | Modernization->On Hold->Modernization->Remote MOCN | 2025 Q3 | AD | Trintel | 4.6 TSSR Approved |  | 2025-02-05 | 2025-02-07 |  | 2025-02-24 |  | Under Approval | 2025-03-03 | 2025-07-16 | E//Hannah | 2025-03-10 | SQ202501070293-Trintel | DU00002862875 | [5 empty] | Tower | 45m 3 Legged Tower | 76 | Reuse Existing RRU | 0 | 0
9195A | Ulu Krain Junction | Sarawak |  | Modernization | Modernization->On Hold->Maintain USP MOCN->Modernization | 2025 Q3 | HW | YPTT | 4.6 TSSR Approved |  | 2025-04-11 | 2025-06-16 |  | 2025-06-20 |  | Under Approval | 2025-07-10 | 2025-07-21 | E//John | 2025-07-11 | SQ202503140154-YPTT | DU00002862876 |  |  | 2025-09-25 | 2025-09-24 |  | Tower | 60m 3 Legged Tower | 76 | Add R8894E M1821x1 | 0 | 2
9380A | KM6 Simpang KJD | Sarawak |  | Remote MOCN | Modernization->On Hold->Maintain USP MOCN->Remote MOCN | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862877 | [6 empty] | 45m 3 Legged Tower |  | Reuse Existing RRU | 0 | 0
9462B | Maludam | Sarawak |  | Modernization | Modernization->On Hold->Modernization | 2025 Q3 | AD | Trintel | 4.6 TSSR Approved |  | 2025-03-18 | 2025-04-17 |  | 2025-04-28 |  | Under Approval | 2025-04-29 | 2025-05-21 | E//John | 2025-05-21 | SQ202501070293-Trintel | DU00002862878 |  |  | 2025-05-23 | 2025-05-22 |  | Tower | Tower | 76 | Add R8894E M1821x1, Dismantle R8854E S1800(A6A)x3 | 0 | 3
9066R | JULAU TOWN | Sarawak |  | Maintain USP MOCN(Dismantle Passive) | Maintain USP MOCN(Dismantle Passive)->On Hold->Maintain USP MOCN(Dismantle Passive) | 2024 Q4 | HW | Trintel | 4.6 TSSR Approved |  | 2025-06-30 |  | 2025-07-09 |  | 2025-07-14 |  | 2025-09-12 | 2025-09-25 | E//John | 2025-09-12 | SQ202506060240-Trintel | DU00002862879 |  |  |  |  | 2025-11-14 |  | #N/A
B00186 | W066I_B00186OD_KEMENSAHHEIGHT | Central |  | Decomm |  | 2024 Q1 | SHA | GCI | 4.6 TSSR Approved |  | 2024-07-02 |  |  |  | 2024-07-17 |  | 2024-07-19 | 2025-03-20 | CD//Ali Akaram | 2024-07-22 | 0918MW-Central-GCI-BOQ Template (old contract) | DU00002862880 |  |  |  |  | 2024-08-17 |  | MONOPOLE
9231A | Marup | Sarawak |  | Modernization | Modernization->On Hold->Maintain USP MOCN->Modernization | 2025 Q3 | HW | YPTT | 4.6 TSSR Approved |  | 2025-03-11 | 2025-05-28 |  | 2025-06-16 |  | Under Approval | 2025-06-16 | 2025-07-21 | E//John | 2025-06-17 | SQ202503140154-YPTT | DU00002862881 |  |  | 2025-08-13 | 2025-08-11 |  |  | 45m 3 Legged Tower | 76 | Add R8894E M1821x1, Dismantle R8854E S1800(A6A)x3 | 0 | 1
B02812 | B064C_B02812OD_MINESRESORTCITY_JLNDULANGEMAS | Central |  | Decomm | Decomm->On Hold->Decomm | 2024 Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2024-03-20 |  |  |  | 2024-03-29 |  | 2024-04-17 | 2024-07-11 | CD//Sapian | 2024-05-11 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240323 | DU00002862882 |  |  |  |  | 2025-03-26 |  | UNIPOLE
9099R | NANGA TIGA | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862883 | [6 empty] | #N/A
9118R | NANGA BONG | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862884 | [6 empty] | #N/A
B00168 | B064B_B00168OD_BALAKONGJAYA | Central |  | Decomm | Decomm->On hold->Site out | 2024 Q3 | AI | GTSB | 14.1 TSSR Not Required (Decomm by CD) | [6 empty] | To be Submitted |  |  | CD//Ali Akaram |  |  | DU00002862885 |  |  |  |  | 2025-04-29 |  | TOWER
W00749 | W066Y_W00749OD_KGPANDANDALAM | Central |  | Decomm |  | 2024 Q2 | BY | Solusi | 4.6 TSSR Approved |  | 2024-05-13 |  |  |  | 2024-05-20 |  | 2024-06-05 | 2024-07-19 | CD//Ali Akaram | 2024-06-07 | CelcomDigi_RAN_Solusi_TSS_Central_20240528 | DU00002862886 |  |  |  |  | 2024-07-16 |  | SHARING STRC OTHERS MINARATE
9116R | KAMPUNG PENOM | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862887 | [6 empty] | #N/A
9117R | BATU LAPAN | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862888 | [6 empty] | #N/A
9100R | PELIKOI | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862889 | [6 empty] | #N/A
9120R | KAMPUNG EMPALING | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862890 | [6 empty] | #N/A
B00158 | B061L_B00158OD_PR_PUTRAPDANA3 | Central | 1895K | Swap | Decomm->On Hold->Swap | 2024 Q3 | AI | Magicell | 4.6 TSSR Approved |  | 2024-02-19 | 2024-12-13 |  | 2024-12-18 | 2024-02-27 | Closed | 2024-12-18 | 2024-12-24 | CD//Norhaliza | 2024-12-23 | SQ202411140058 | DU00002862891 | Remarks: Solution TSSR/BOM Changed |  | 2025-07-22 | 2025-07-04 |  | In-Building System | BOOM | 7 | Add R8852E S9000x1+R9264H M901821x3+R8862A S2601x4+A9732 M1821x1, Dismantle | 4 | 0
9127R | NANGA BAT | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862892 | [6 empty] | #N/A
B00697 | B064C_B00697OD_UPM | Central |  | Decomm |  | 2024 Q3 | CR | GTSB | 4.6 TSSR Approved |  | 2024-09-24 |  | 2024-10-07 |  | 2024-10-17 |  | 2024-11-07 |  | CD//Norhaliza | 2024-12-06 | 0924CD-Central-GTSB-BOQ Template(new contract) | DU00002862893 |  |  |  |  | 2024-10-21 |  | TOWER
B00192 | B064I_B00192OD_RINCHINGTENGAH | Central |  | Decomm |  | 2024 | HW | GCI | 4.6 TSSR Approved |  | 2024-12-23 |  | 2025-02-07 |  | 2025-02-11 |  | 2025-02-18 | 2025-05-20 | CD//Sapian | 2025-02-24 | Wireless+ Malaysia CD+TSS+ GCI+4 site SQ202410310157 | DU00002862894 |  |  |  |  | 2025-04-29 |  | TOWER
B00228 | B064G_B00228OD_BT3SEMENYIH | Central |  | Decomm |  | 2024 | SS | GTSB | 4.6 TSSR Approved |  | 2024-09-03 |  | 2024-09-25 |  | 2024-10-03 |  | 2024-11-22 | 2025-01-14 | CD//Norhaliza | 2024-12-06 | 0919CD-Central-GTSB-BOQ Template(new contract) 2 | DU00002862895 |  |  |  |  | 2024-10-09 |  | TOWER
9128R | SKROH @ SK MEGALON | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862896 | [6 empty] | #N/A
B00564 | B064F_B00564OD_KAJANGBRANCH | Central |  | Decomm | Decomm->On Hold->Decomm->On Hold->Decomm | 2024 Q4(single site MOCN)-L2126 SSM | SH | Magicell | 4.6 TSSR Approved |  | 2024-03-04 |  |  |  | 2024-03-25 |  | 2024-05-20 | 2024-08-13 | CD//Ali Akaram | 2024-07-29 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240311 | DU00002862897 |  |  |  |  | 2024-11-30 |  | MINI STRUCTURE
9104R | RUMAHABANG | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862898 | [6 empty] | #N/A
B00010 | W067A_B00010OD_PR_PRESINT11WPPJ | Central |  | Decomm | Decomm->On Hold->Decomm | 2024 Q3 | HW | YPTT | 4.6 TSSR Approved |  | 2024-10-23 |  | 2024-12-05 |  | 2025-02-20 |  | 2025-02-23 |  | CD//Sapian | 2025-05-08 | 0823CD-Central-YPTT-BOQ Template(new contract) | DU00002862899 |  | Pls provide antenna tx photo at NE & FE part |  |  | 2024-11-25 |  | TOWER
9052R | NGPERANAN | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862900 | [6 empty] | #N/A
B00200 | B063C_B00200OD_KGSEMARANG | Central |  | Decomm |  | 2024 | SH | GTSB | 4.6 TSSR Approved |  | 2024-01-15 |  |  |  | 2024-02-21 |  | 2024-05-28 | 2024-11-26 | CD//Ali Akaram | 2024-11-01 | CelcomDigi_RAN_GTSB_TSS_Central_20240124 | DU00002862901 |  |  |  |  | 2024-10-30 |  | TOWER
9012Z | NANGA YONG | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862902 | [6 empty] | #N/A
B00911 | W067A_B00911OD_MOFPUTRAJAYA | Central | 1847K | Swap | Decomm->Swap | 2024 Q3 | CR | GTSB | 4.6 TSSR Approved |  | 2024-06-28 | 2024-07-04 |  | 2024-07-05 |  | Under Approval | 2024-07-09 | 2024-08-22 | CD//Norhaliza | 2024-08-22 | 0701Central-GTSB-BOQ Template (template) | DU00002862903 |  |  | 2024-08-09 | 2024-08-05 |  | Unipole | IN-BUILDING | 4m | Add R8862A S9000 x3+R8894E M1821 x3+R8862A S2601 x3,Dismantle | 0 | 0
B00729 | B064C_B00729OD_UPM3 | Central |  | Decomm |  | 2024 Q3 | SHA | GTSB | 4.6 TSSR Approved |  | 2024-09-03 |  | 2024-09-08 |  | 2024-10-15 |  | 2024-10-16 |  | CD//Sapian | 2024-10-22 | 0924CD-Central-GTSB-BOQ Template(new contract) | DU00002862904 |  | 1) Please provide digi cabinet/rack photo 2) Missing antenna tx photo at NE 3) Missing FE part |  |  | 2024-10-01 |  | TOWER
9114R | RUMAHAJI | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862905 | [6 empty] | #N/A
B00147 | B064C_B00147OD_UPM4 | Central |  | Decomm |  | 2024 Q3 | MS | GTSB | 4.6 TSSR Approved |  | 2024-08-27 |  | 2024-09-08 |  | 2024-09-18 |  | 2024-09-20 | 2024-10-28 | CD//Ali Akaram | 2024-09-26 | 0924CD-Central-GTSB-BOQ Template(new contract) | DU00002862906 |  |  |  |  | 2024-09-27 |  | TOWER
9105R | JALANPAKANENTABAI (JLN ENTABAI) | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862907 | [6 empty] | #N/A
B01727 | W067A_B01727OD_PRESINT17WPPJ | Central |  | Decomm | Decomm->Swap->Decomm | 2024 Q3 | BY | YPTT | 4.6 TSSR Approved |  | 2024-08-01 |  | 2024-08-10 |  | 2024-08-07 |  | 2024-08-08 | 2024-09-25 | CD//Ali Akaram | 2024-08-13 | 0813CD-Central-YPTT-BOQ Template(new contract) | DU00002862908 |  |  |  |  | 2024-10-31 | Monople Tree | Lampole | 45m
9106R | NANGA GRENJANG | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862909 | [6 empty] | #N/A
9115R | RUMAH DANGKAN | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862910 | [6 empty] | #N/A
9112R | KAMPUNG SELEMAS | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862911 | [6 empty] | #N/A
9131R | SUNGAI MUPONG | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862912 | [6 empty] | #N/A
9178Z | RH Lingit | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862913 | [6 empty] | #N/A
9174Z | Kampung Tuie Kampung Dit | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862914 | [6 empty] | #N/A
K00490 | K004B_K00490OD_TANDOPUTAMA | Northern |  | Decomm |  | 2024 | HW | CCSMY | 4.6 TSSR Approved |  | 2024-12-15 |  | 2025-02-03 |  | 2025-02-12 |  | 2025-02-20 |  | CD//Hazwan | 2025-02-26 | 1101CD Conso-Northern-CCSMY-BOQ Template(new contract) | DU00002862915 |  | TSSR rejected. Wrong site info at page 1 |  |  | 2024-12-06 |  | LAMP_POLE
A00124 | BEHRANG2020 | Northern |  | Decomm |  | 2024 Additional | SM | YPTT | 4.6 TSSR Approved | ¦ 20241205 - CD Zul: Hold review due to anchor site yet NIC. | 2024-02-13 |  |  |  | 2024-02-13 | To be Submitted | 2024-11-28 |  | CD//Zulakmar | 2025-01-21 | Celcom Digi_RAN-YPTT-TSS-Northern-20240215-0060_reraise 21/6 | DU00002862916 |  |  |  |  | 2025-03-10 |  | TOWER
9180Z | Rumah Dau | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862917 | [6 empty] | #N/A
K00452 | K013A_K00452OD_PANTAIMURNI | Northern |  | Decomm |  | 2024 Q4 |  | GCI | 4.6 TSSR Approved |  | 2024-10-15 |  | 2024-10-23 |  | 2024-10-23 |  | 2024-11-14 |  | CD//Zulakmar | 2024-11-18 | 0927CD-Northern-GCI-BOQ Template(new contract)/0927MW-Northern-GCI-BOQ Template(new contract) | DU00002862918 |  | Missing TX Info |  |  | 2024-10-15 |  | TOWER
9163Z | Kg. Setambak Hilir Setambak Hulu | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862919 | [6 empty] | #N/A
B01146 | B064I_B01146OD_SUNWAYSEMENYIH | Central | 1893K | Swap | Decomm->On Hold->Swap | 154 single site MOCN | AI | CCSMY | 4.6 TSSR Approved |  | 2024-11-25 | 2024-11-27 |  | 2024-12-03 |  | Under Approval | 2024-12-02 | 2024-12-04 | CD//Ali Akaram | 2024-12-04 | S1MY2024071004WBF1-718 | DU00002862920 |  |  | 2024-12-16 | 2024-12-13 |  | Monople Tree | LAMP_POLE | 45m | Add R8852E S9000x4+R8894E M1821 x5+R8862A S2601x3+R8854 S2600Ax1, Dismantle | 0 | 2
9173Z | Nanga Bayor | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862921 | [6 empty] | #N/A
9162Z | Rumah Philip Mujah | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862922 | [6 empty] | #N/A
B01817 | B064A_B01817OD_TMNKEMACAHAYA | Central |  | Decomm |  | 2024 Additional | SS | GCI | 4.6 TSSR Approved |  | 2023-11-10 |  |  |  | 2023-11-20 |  | 2023-11-22 | 2024-08-20 | CD//Ali Akaram | 2023-11-29 | CelcomDigi_RAN_GCI_TSS_Central_20231113 | DU00002862923 |  |  |  |  | 2025-03-12 |  | UNIPOLE
9172Z | Kampung Manggut | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862924 | [6 empty] | #N/A
9181Z | Jambu Kerapa | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862925 | [6 empty] | #N/A
B00134 | B064G_B00134OD_WARTABBBANGI | Central |  | Decomm | Decomm->On Hold->Decomm | 2024 Q3 | SY1 | GTSB | 4.6 TSSR Approved |  | 2024-09-13 |  |  |  | 2024-09-24 |  | 2024-09-26 | 2025-10-01 | CD//Norhaliza | 2024-10-04 | 0924CD-Central-Solusi-BOQ Template(new contract) | DU00002862926 |  |  |  |  | 2025-02-27 |  | BOOM
B01065 | B064G_B01065OD_BT18SGTANGKAS | Central | 1816K | Site Out (Decomm) | Decomm->Swap->Site Out | 2024 Additional | SHA | DATASCO | 4.6 TSSR Approved |  | 2024-03-28 | 2024-04-26 |  | 2024-05-10 |  | Closed | 2024-12-04 | 2024-12-10 | CD//Sapian | 2024-12-09 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240329 | DU00002862927 |  |  |  |  | 2025-06-26 | Monopole | LAMP_POLE | 21m | Add R8852E S9000 x3+R8894E M1821 x4+R8862A S2601 x2+R8854 S2600 x1,Dismantle | 0 | 2
9161Z | Rumah Beduru | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862928 | [6 empty] | #N/A
9171Z | Sri Aman Lidong road | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862929 | [6 empty] | #N/A
9158Z | Kampung Seduku | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862930 | [6 empty] | #N/A
9160Z | Tanjung Bijat | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862931 | [6 empty] | #N/A
9157Z | Skrang Betong Road | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862932 | [6 empty] | #N/A
B01144 | B064B_B01144OD_TMNBALAKONGJAYA | Central |  | Decomm |  | 2024 Q3 | BY | GTSB | 4.6 TSSR Approved |  | 2024-03-05 |  |  |  | 2024-04-26 |  | 2024-05-13 | 2025-03-20 | CD//Norhaliza | 2024-08-20 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240311 | DU00002862933 |  |  |  |  | 2024-08-28 |  | LAMP_POLE
B00114 | B061T_B00114OD1_SS16PJ | Central |  | Decomm |  | 2024 Q3 | MA | YPTT | 4.6 TSSR Approved |  | 2024-05-25 |  |  |  | 2024-05-25 |  | 2024-05-28 | 2024-07-29 | CD//Ali Akaram | 2024-06-05 | CelcomDigi_RAN_YPTT_TSS_Central_20240528 | DU00002862934 |  |  |  |  | 2024-11-06 |  | BOOM
B02897 | B061S_B02897OD_DAMANSARAINTAN | Central |  | Decomm |  | 2024 Q3 | SH | DATASCO | 4.6 TSSR Approved |  | 2024-05-23 |  |  |  | 2024-09-18 |  | 2024-09-20 | 2024-10-28 | CD//Sapian | 2024-09-27 | CelcomDigi_RAN_Datasco_TSS_Central_20240528 | DU00002862935 |  |  |  |  | 2025-01-24 |  | BOOM
9156Z | Rumah Tunggang | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862936 | [6 empty] | #N/A
9155Z | Kampung Gua Dalam | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862937 | [6 empty] | #N/A
9154Z | Rh. Abdul Rahman | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862938 | [6 empty] | #N/A
9170Z | Rh. Tinchin | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862939 | [6 empty] | #N/A
9169Z | Rumah Richard | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862940 | [6 empty] | #N/A
9168Z | Rumah Silit | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862941 | [6 empty] | #N/A
9167Z | Rumah Lait | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862942 | [6 empty] | #N/A
9177Z | Kampung Pulau | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862943 | [6 empty] | #N/A
9166Z | Nanga Murat | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862944 | [6 empty] | #N/A
9165Z | Rumah Marian | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862945 | [6 empty] | #N/A
9159Z | Serubah | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862946 | [6 empty] | #N/A
9176Z | Nanga Uyau | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862947 | [6 empty] | #N/A
9164Z | Kampung Serabang Ulu Dit | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862948 | [6 empty] | #N/A
B01675 | W067A_B01675OD_PR_PRESINT92WPPJ | Central | 1852K | Swap | Decomm->Swap | 2024 Q3 | SY1 | Magicell | 4.6 TSSR Approved |  | 2024-08-20 | 2024-08-23 |  | 2024-08-27 | 2024-03-28 | Closed | 2024-08-29 | 2024-10-03 | CD//Ali Akaram | 2024-10-02 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240303 | DU00002862949 |  |  | 2025-01-23 | 2025-02-14 |  | Wall mount boom | AESTHETIC MONOPOLE | 2 | Add R8862A S9000 x2+R9264H M901821 x1+R8862A S2601 x3+A9732 M1821 x2,Dismantle | 23 | 0
9175Z | Kampung Supa | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862950 | [6 empty] | #N/A
9509B | Julau Junction (REL) | Sarawak |  | Remote MOCN | Modernization->On Hold->Maintain USP MOCN->Remote MOCN | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862951 | [6 empty] | Tower |  | Reuse Existing RRU | 0 | 0
9558B | Tanjung Manis 04 | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862952 | [6 empty] | 30m Monopole |  | Dismantle R862A S9000x3+R8854E S1800(A6A)x3 | 0 | 0
9557B | Tanjung Manis 03 | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862953 | [6 empty] | 30m Monopole |  | Dismantle R862A S9000x3+R8854E S1800(A6A)x3 | 0 | 0
9029Z | SKNangaPedanum Pakan-Pedanumroad | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862954 | [6 empty] | 45m 3 Legged Tower
9147Z | Empayang Atas (old - Empayang Baroh Empayang Pasir | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862955 | [6 empty] | #N/A
9148Z | Rumah Seminai (old - Lubok Kepayang Rumah Medol) | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862956 | [6 empty] | #N/A
9151Z | Rumah Nyelang | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862957 | [6 empty] | #N/A
W00059 | W066V_W00059OD_PANTAIDALAM | Central |  | Decomm |  | 2024 Q2 | MS | AllStar | 4.6 TSSR Approved |  | 2024-01-13 |  |  |  | 2024-01-15 |  | 2024-01-17 | 2024-02-15 | CD//Ali akaram | 2024-01-23 | BOQ CelcomDigi_RAN_AllStar_Standard PR TSS_Central_20240116 | DU00002862958 |  |  |  |  | 2024-09-03 |  | LAMP_POLE
9174R | RH NANANG | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862959 | [6 empty] | #N/A
9017R | RUMAH NYUKA | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862960 | [6 empty] | 106M 4 Legged Tower
9090R | Sjk Hua Kee | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862961 | [6 empty] | #N/A
9173R | RH JAWA | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862962 | [6 empty] | #N/A
9018R | RUMAH JANTAN | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862963 | [6 empty] | 76M 3 Legged Tower
9078R | Rh Sigat | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862964 | [6 empty] | #N/A
9172R | TG MANIS-SIBU ROAD #2 | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862965 | [6 empty] | #N/A
9016R | KAMPUNG PALOH | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862966 | [6 empty] | 76M 3 Legged Tower
9014R | SK LENGAN (TANJUNG MANIS-SIBU ROAD 1) | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862967 | [6 empty] | 76M 3 Legged Tower
9015R | TUBAU FOREST (TANJUNG MANIS-SIBU ROAD 3) | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862968 | [6 empty] | 61M Tower
9035Z | NangaDayu RumahTindin RumahSamak RumahSenabong | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862969 | [6 empty] | 45m 3 Legged Tower |  | Dismantle R8854E S1800(A6A)x3 | 0 | 0
W01116 | W066AA_W01116OD_MEDANMIDAH | Central |  | Decomm |  | 2024 Q3 | SH | Ascentrack | 4.6 TSSR Approved |  | 2024-01-11 |  |  |  | 2024-01-26 |  | 2024-12-23 | 2025-01-14 | CD//Norhaliza | 2024-12-31 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240115 | DU00002862970 |  |  |  |  | 2024-07-29 |  | UNIPOLE
9030Z | RumahEddyMadang JulauPakanroad | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862971 | [6 empty] | 45m 3 Legged Tower
9033Z | RumahBeracok SimpangWak | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862972 | [6 empty] | 45m 3 Legged Tower
9034Z | T3E_0296 Rumah George | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862973 | [6 empty] | 45m 3 Legged Tower
9036Z | SKSungaiBabai-Pakanroad RumahAnyi | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862974 | [6 empty] | 45m 3 Legged Tower
9028Z | RumahAyub RumahEnting RumahNyandang | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862975 | [6 empty] | 45m 3 Legged Tower
9037Z | RumahDana | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862976 | [6 empty] | 45m 3 Legged Tower
9057Z | RumahGani RumahAmba aRumahNyikoh | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862977 | [6 empty] | 45m 3 Legged Tower
9056Z | SKNangaMeluan RumahChuat aRumaahRandi RumahGenta | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862978 | [6 empty] | 45m 3 Legged Tower |  | Dismantle R8854E S1800(A6A)x3 | 0 | 0
9058Z | NangaJagauSettlement | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862979 | [6 empty] | 45m 3 Legged Tower
B00153 | B064D_B00153OD_PRIMASAUJANAKJG | Central |  | Decomm |  | 2024 Q4(single site MOCN)-L26 SSM | MS | GTSB | 4.6 TSSR Approved |  | 2024-02-20 |  |  |  | 2024-03-01 |  | 2024-05-23 | 2024-09-25 | CD//Ali Akaram | 2024-07-22 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240225 | DU00002862980 |  |  |  |  | 2024-10-17 |  | BOOM
W00122 | W066Q_W00122OD_TMSPETALING | Central |  | Decomm | Decomm-On Hold->Decomm | 2024 Q3 | MA | GCI | 4.6 TSSR Approved |  | 2024-05-17 |  |  |  | 2024-05-22 |  | 2024-05-23 | 2026-01-21 | CD//Sapian | 2024-06-10 | CelcomDigi_RAN_GCI_TSS_Central_20240528 | DU00002862981 |  |  |  |  | 2025-09-30 |  | BOOM
B00685 | B064A_B00685OD_BDRMAHKOTACHRS | Central |  | Decomm |  | 2024 Q4 | SY1 | GCI | 4.6 TSSR Approved |  | 2024-09-04 |  | 2024-09-08 |  | 2024-09-10 |  | 2024-09-11 |  | CD//Ali Akaram | 2024-09-12 | 0924CD-Central-GCI-BOQ Template(new contract) | DU00002862982 |  |  |  |  | 2024-09-25 |  | LAMP_POLE
9032R | KG. SEDAU | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862983 | [6 empty] | 76M 3 Legged Tower
9033R | Sk Engkabang | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862984 | [6 empty] | 76M 3 Legged Tower
9025R | Pedanom | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862985 | [6 empty] | 76M 3 Legged Tower
9027R | Bara Lubok Antu | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862986 | [6 empty] | 70M 3 Legged Tower
S01493 | S105A_S01493OD_TMNPOHING | Sabah |  | Decomm |  | 2024 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2024-07-09 |  | 2024-07-12 |  | 2024-07-18 |  | 2024-07-19 | 2024-08-29 | CD//Ray Amos | 2024-07-22 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240813 | DU00002862987 |  |  |  |  | 2024-10-07 |  | LAMP_POLE
9029R | Kg. Kedang | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862988 | [6 empty] | 76M 3 Legged Tower
9030R | KG. SG. SELIDAP | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862989 | [6 empty] | 70M 3 Legged Tower
9034R | Kg. Ulu Strass | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862990 | [6 empty] | 76M 3 Legged Tower
B01048 | B061L_B01048OD_TMNMASSEPANG | Central |  | Decomm |  | 2024 Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2023-12-05 |  |  |  | 2023-12-12 |  | 2024-04-17 | 2024-05-31 | CD//Ali Akaram | 2024-04-29 | CelcomDigi_RAN_Magicell_TSS_Central_20231208 | DU00002862991 |  |  |  |  | 2024-09-27 |  | TOWER
B00169 | B061L_B00169OD_PCHGPRIMA | Central |  | Decomm |  | 2024 Q3 | BY | GTSB | 4.6 TSSR Approved |  | 2024-01-06 |  |  |  | 2024-02-16 |  | 2024-05-13 | 2024-05-27 | CD//Ali Akaram | 2024-05-24 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240110 | DU00002862992 |  |  |  |  | 2024-11-06 |  | BOOM
9248Z | SK Nanga Entabai | Sarawak |  | Modernization | Maintain USP MOCN->On Hold->Maintain USP MOCN->Modernization | 2025 Q3 | AD | Trintel | 4.6 TSSR Approved | 14/8 - 17/8 plan go in// 8/8 - team transport issue // 5/8- Wk33 plan | 2025-09-12 | 2025-09-09 |  | 2025-09-13 |  | Under Approval | 2025-09-17 | 2025-10-16 | E//Hannah | 2025-09-19 | SQ202508110312-Trintel | DU00002862993 |  |  | 2025-10-24 |  |  | Tower | 76M Tower | 76 | Dismantle R8854E S1800(A6A)x3 | 0 | 0
B00625 | B063B_B00625OD_TMNKENANGA | Central |  | Decomm |  | 2025 Q3 | AI | GCI | 4.6 TSSR Approved |  | 2024-07-02 |  | 2024-07-14 |  | 2024-07-18 |  | 2025-02-22 |  | CD//Sapian | 2025-03-07 | S1MY2021071007WBF1-3914 / SQ202506120286 | DU00002862994 |  |  |  |  | 2025-02-19 |  | TOWER
B02341 | W067A_B02341OD_PR_VLJLNTEKNOKRAT1LIMKOKWING | Central |  | Decomm |  | 2024 Q3 | BY | GTSB | 4.6 TSSR Approved |  | 2024-01-13 |  |  |  | 2024-01-18 |  | 2024-05-08 | 2024-09-25 | CD//Norhaliza | 2024-08-19 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240115 | DU00002862995 |  |  |  |  | 2025-04-23 |  | AESTHETIC MONOPOLE
9245Z | T3E_0802_SK Batu Luking | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862996 | [6 empty] | 76M Tower
9244Z | SK Nanga Maong | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862997 | [6 empty] | 76 M Tower
9243Z | T3E_0800 Nanga Jagoi | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002862998 | [6 empty] | Tower
B00517 | B064H_B00517OD_PR_ABUBAKAR | Central |  | Decomm |  | 2024 Q3 | SY1 | GTSB | 4.6 TSSR Approved |  | 2024-09-11 |  | 2025-01-03 |  | 2024-10-07 |  | 2024-10-08 | 2025-03-11 | CD//Sapian | 2024-10-18 | 0924CD-Central-GTSB-BOQ Template(new contract) | DU00002862999 |  |  |  |  | 2024-09-27 |  | TOWER
9026R | Kg. Bungin | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863000 | [6 empty] | 76M 3 Legged Tower
9028R | Kg. Sebako | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863001 | [6 empty] | 76M 3 Legged Tower
4160Z | Kg Padang Melangit | Northern |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863002
7345A | Kg Rompon Trunk | Sabah |  | Maintain USP MOCN | Modernization->On Hold->Maintain USP MOCN | 2024 Q4 |  | Futong | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863003 | [6 empty] | 106m 4 Legged Tower |  | Reuse Existing RRU | 0 | 0
W01564 | W066R_W01564OD_DESATUNRAZAK2 | Central |  | Decomm |  | 2024 Q3 | SH | Ascentrack | 4.6 TSSR Approved |  | 2024-02-02 |  |  |  | 2024-02-16 |  | 2024-04-02 |  | CD//Ali Akaram | 2024-04-24 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240212 | DU00002863004 |  | MISSING FE PART |  |  | 2024-08-17 |  | LAMP_POLE
7346A | Kg Patau | Sabah |  | Modernization | Modernization->On Hold->Maintain USP MOCN->Modernization | 2024 Q4 | AD | YPTT | 4.6 TSSR Approved |  | 2025-05-21 | 2025-06-03 |  | 2025-06-06 |  | Under Approval | 2025-06-10 | 2025-09-20 | E//Hannah | 2025-06-13 | SQ202505190141 - YPTT | DU00002863005 | 08/04/25: SOW Changed from Maintain USP MOCN to Modernization |  | 2025-09-18 | 2025-09-13 |  | Tower | 60m 3 Legged Tower | 60 | Add A9732 M1821 x1,Dismantle R8894E M1821(A8A)x1 | 2 | 0
7505B | Kg. Melangking | Sabah |  | Remote MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN->Modernization->Remote MOCN | 2024Q4 |  |  | 14.0 TSSR Not Required (Reuse Existing BBU/RRU) | [6 empty] | To be Submitted | [5 empty] | DU00002863006 | [6 empty] | 45m 3 Legged Tower |  | Reuse Existing RRU | 0 | 0
B00777 | B064H_B00777OD_BDRSERIPUTRA | Central |  | Decomm |  | 2024 |  | GTSB | 4.6 TSSR Approved |  | 2024-09-03 |  | 2024-09-09 |  | 2024-09-23 |  | 2024-11-22 | 2025-07-25 | CD//Ali akaram | 2024-12-09 | 0919CD-Central-GTSB-BOQ Template(new contract) 2 | DU00002863007 |  |  |  |  | 2024-11-22 |  | MONOPOLE
7480B | Kg Jaya Baru | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863008 | [6 empty] | 45m 3 Legged Tower
7073R | T3_0079 - KG RAMPAYAN LAUT (KG TINAMUN) | Sabah |  | Maintain USP MOCN(Dismantle Passive) | Maintain USP MOCN(Dismantle Passive)->On Hold->Maintain USP MOCN(Dismantle Passive) | 2024 Q3 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2025-07-19 |  | 2025-07-22 |  | 2025-07-23 |  | 2025-08-05 | 2025-09-20 | E//Hannah | 2025-09-16 | SQ202508130660 - Seri Pancar | DU00002863009 |  |  |  |  | 2025-09-19 |  | #N/A
7503B | Jalan Guamantong | Sabah |  | Remote MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN->Modernization->Remote MOCN | 2024Q4 |  |  | 14.0 TSSR Not Required (Reuse Existing BBU/RRU) | [6 empty] | To be Submitted | [5 empty] | DU00002863010 | [6 empty] | 45m 3 Legged Tower |  | Reuse Existing RRU | 0 | 0
7114Z | Kg Seselongon | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863011 | [6 empty] | #N/A
7115Z | Kg Terian | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863012 | [6 empty] | #N/A
7109Z | Kg Timpangoh | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863013 | [6 empty] | #N/A
7123Z | SK Kinaluan | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863014 | [6 empty] | #N/A
B00594 | W066Y_B00594OD_PANDANMEWAH | Central |  | Decomm |  | 2024 Q4 | SHA | GTSB | 4.6 TSSR Approved |  | 2024-03-15 |  |  |  | 2024-08-05 |  | 2024-08-08 | 2024-08-27 | CD//Ali Akaram | 2024-08-13 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240316 | DU00002863015 |  |  |  |  | 2024-08-27 |  | BOOM
B00487 | W066X_B00487OD_BUKITINDAH | Central |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4 | AD | Ascentrack | 4.6 TSSR Approved |  | 2023-12-12 |  |  |  | 2024-02-01 |  | 2024-02-05 |  | CD//Sapian | 2024-02-14 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231213 | DU00002863016 |  |  |  |  | 2025-06-04 |  | 30m 3 Legged Tower | 30m
B00182 | B061K_B00182OD_PCHGUTAMA2 | Central |  | Decomm |  | 2024 Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2024-01-19 |  |  |  | 2024-02-07 |  | 2024-04-17 | 2024-05-12 | CD//Sapian | 2024-04-24 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240128 | DU00002863017 |  |  |  |  | 2024-09-26 |  | TOWER
7173Z | Kg. Ragkam | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863018 | [6 empty] | #N/A
7179Z | Kg Tuawon | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863019 | [6 empty] | #N/A
7477B | Kg Bilit | Sabah |  | Remote MOCN | Modernization->On Hold->Maintain USP MOCN->Modernization->Remote MOCN | 2024 Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2025-05-14 | 2025-08-19 |  | 2025-08-22 |  | Under Approval | 2025-08-25 | 2025-09-20 | E//Hannah | 2025-09-10 | SQ202505050115 - GTSB | DU00002863020 |  |  | 2025-09-22 |  |  | Tower | 76m 3 Legged Tower | 60 | Reuse Existing RRU | 0 | 0
S00164 | S105B_S00164OD_SDX | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2024 Q3 | ZA | GTSB | 4.6 TSSR Approved |  | 2024-03-20 |  |  |  | 2024-03-26 |  | 2024-04-15 | 2025-05-02 | CD//Ray Amos | 2024-04-24 | Celcom Digi_RAN-GTSB-TSS-Sabah-20240324 | DU00002863021 |  |  |  |  | 2024-12-06 |  | TOWER
7478B | T3_0849_KG KEMAYAN | Sabah |  | Maintain USP MOCN | Modernization->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863022 | [6 empty] | 76m 3 Legged Tower |  | Reuse Existing RRU | 0 | 0
7506B | Kg. Sg monyet | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863023 | [6 empty] | 45m 3 Legged Tower
7509B | Kg. Jawa | Sabah |  | Modernization | Maintain USP MOCN->On Hold->Maintain USP MOCN->Modernization | 2024 Q4 | AD | NR services | 4.6 TSSR Approved |  | 2025-05-02 | 2025-06-03 |  | 2025-06-04 |  | Under Approval | 2025-06-05 | 2025-06-19 | E//Hannah | 2025-06-09 | SQ202504140266 - NR Service | DU00002863024 |  |  | 2025-06-18 | 2025-06-11 |  | Tower | 45m 3 Legged Tower | 76 | Add R8894E M1821x1 | 0 | 3
7145Z | Kg Wani | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863025 | [6 empty] | #N/A
7497B | Sinar Jaya | Sabah |  | Maintain USP MOCN | Modernization->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863026 | [6 empty] | 76m 3 Legged Tower |  | Reuse Existing RRU | 0 | 0
W00099 | W066N_W00099OD_TMPEKELILING | Central |  | Decomm | Decomm->On Hold->Decomm | 2024 Q2 | SS | Magicell | 4.6 TSSR Approved |  | 2024-02-08 |  |  |  | 2024-02-13 |  | 2024-02-28 | 2025-03-20 | CD//Ali Akaram | 2024-04-01 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240218 | DU00002863027 |  |  |  |  | 2025-02-27 |  | BOOM
7586A | Kg. Suan Lamba | Sabah |  | Remote MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN->Modernization->Remote MOCN | 2024Q4 |  |  | 14.0 TSSR Not Required (Reuse Existing BBU/RRU) | [6 empty] | To be Submitted | [5 empty] | DU00002863028 | [6 empty] | 45m 3 Legged Tower |  | Reuse Existing RRU | 0 | 0
7088Z | KgBalat | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863029 | [6 empty] | 76m 4 Legged Tower
7093Z | AbaiIsland-RiverIsland | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863030 | [6 empty] | 76m 4 Legged Tower
W01386 | B057D_W01386OD_JLNMARMAR_TMNMELEWAR_KL | Central |  | Decomm |  | 2024 Q1 | BY | Magicell | 4.6 TSSR Approved |  | 2023-11-24 |  |  |  | 2023-12-07 |  | 2024-01-18 | 2024-05-27 | CD//Sapian | 2025-05-09 | CelcomDigi_RAN_Magicell_TSS_Central_20231126 | DU00002863031 |  |  |  |  | 2024-04-02 |  | LAMP_POLE
7148Z | Kg Timbang Dayang | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863032 | [6 empty] | #N/A
7140Z | Kg Pituru | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863033 | [6 empty] | #N/A
7143Z | Lasau Podi | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863034 | [6 empty] | #N/A
S01158 | S105B_S01158OD_KGTINOSA2 | Sabah |  | Decomm |  | 2024 Q3 | BY | GTSB | 4.6 TSSR Approved |  | 2024-03-25 |  |  |  | 2024-03-27 |  | 2024-04-05 | 2024-05-14 | CD//Ray Amos | 2024-04-08 | Celcom Digi_RAN-GTSB-TSS-Sabah-20240329 | DU00002863035 |  |  |  |  | 2024-09-30 |  | #N/A
7086Z | MasangEstate | Sabah |  | Modernization | Maintain USP MOCN->On Hold->Maintain USP MOCN->Modernization | 2024Q4 | AI | NR services | 4.6 TSSR Approved |  | 2025-05-02 | 2025-05-14 |  | 2025-05-16 |  | Under Approval | 2025-05-16 | 2025-05-21 | E//Hannah | 2025-05-21 | SQ202504140266 - NR Service | DU00002863036 |  |  | 2025-06-30 | 2025-06-14 |  | Tower | 76m 4 Legged Tower | 76 | Add R8894E M1821x1 | 0 | 1
7103Z | T3E_0696_Kg Tronglit | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863037 | [6 empty] | 76m 4 Legged Tower
7107Z | T3E_0694_Kg Tanjung Aru | Sabah |  | Modernization | Maintain USP MOCN->On Hold->Maintain USP MOCN->Modernization | 2024Q4 | AD | NR services | 4.6 TSSR Approved |  | 2025-09-02 | 2025-09-03 |  | 2025-09-08 |  | Under Approval | 2025-09-10 | 2025-09-30 | E//Hannah | 2025-09-19 | SQ202509190243 - NR Service | DU00002863038 |  |  | 2025-09-29 | 2025-09-24 |  | Monopole | 76m 4 Legged Tower | 30 | Add R9264M M1821x4, Dismantle | 0 | 2
7101Z | T3E_0694_S1_Kg Tanjung Batu Darat | Sabah |  | Modernization | Maintain USP MOCN->On Hold->Maintain USP MOCN->Modernization | 2024Q4 | AD | NR services | 4.6 TSSR Approved |  | 2025-09-02 | 2025-09-03 |  | 2025-09-08 |  | Under Approval | 2025-09-30 | 2025-10-13 | E//Hannah | 2025-10-08 | SQ202509190243 - NR Service | DU00002863039 |  |  | 2025-10-02 | 2025-09-25 |  | Tower | 76m 4 Legged Tower | 76 | Add R8894E M1821x1 | 0 | 3
7097Z | T3E_0692_KgLubukan | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863040 | [6 empty] | 76m 4 Legged Tower
7098Z | T3E_Kg Sg Madang | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863041 | [6 empty] | 76m 4 Legged Tower
7161Z | Jln Sipitang-Tenom | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863042 | [6 empty] | #N/A
7142Z | Lok Lunuk | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863043 | [6 empty] | #N/A
W00624 | W066Q_W00624OD_SRIPETALING2 | Central |  | Decomm |  | 2024 Q3 | SHA | GTSB | 4.6 TSSR Approved |  | 2024-07-17 |  | 2024-08-01 |  | 2024-10-01 |  | 2024-10-02 | 2024-12-23 | CD//Ali akaram | 2024-11-25 | 0719Central-GTSB-BOQ Template | DU00002863044 |  |  |  |  | 2024-09-30 |  | SHARING STRC SBC
7154Z | Kg Gonipis | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863045 | [6 empty] | #N/A
W00085 | W066BB_W00085OD_TMANGGERIK | Central |  | Decomm |  | 2024 Q3 | SY1 | Magicell | 4.6 TSSR Approved |  | 2024-08-15 |  | 2024-08-19 |  | 2024-08-22 |  | 2024-08-23 | 2025-01-14 | CD//Ali Akaram | 2024-09-10 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240510 - Decomm | DU00002863046 |  |  |  |  | 2024-12-06 |  | BOOM
7084Z | SKRanLuboh | Sabah |  | Modernization | Maintain USP MOCN->On Hold->Maintain USP MOCN->Modernization | 2024 Q4 | HW | GTSB | 4.6 TSSR Approved |  | 2025-05-14 | 2025-05-23 |  | 2025-05-26 |  | Under Approval | 2025-05-27 | 2025-06-19 | E//Hannah | 2025-05-30 | SQ202505050115 - GTSB | DU00002863047 |  |  | 2025-06-17 | 2025-06-11 |  | Tower | 76m 4 Legged Tower | 75 | Add R8894E M1821x1 | 0 | 1
7141Z | Kg Rosok Rantai | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863048 | [6 empty] | #N/A
W00815 | W066J_W00815OD_AU3SUNDINGMLM | Central |  | Decomm |  | 2024 Q1 | HW | GTSB | 4.6 TSSR Approved |  | 2025-02-19 |  | 2025-03-03 |  | 2025-03-10 |  | 2025-03-11 | 2025-07-14 | CD//Sapian | 2025-03-13 | 0924CD-Central-CCSMY-BOQ Template(new contract) | DU00002863049 |  |  |  |  | 2025-05-26 |  | BOOM
W01230 | W066J_W01230OD_WANGSA_PERDANA | Central |  | Decomm |  | 2024 Q1 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-20 |  |  |  | 2023-12-26 |  | 2024-01-05 | 2024-07-12 | CD//Sapian | 2024-01-11 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231119 | DU00002863050 |  |  |  |  | 2024-05-02 |  | LAMP_POLE
B02400 | B064F_B02400OD_TMN_BKT_MEWAH_KJG | Central |  | Decomm |  | 2024 Q4 | SY1 | GTSB | 4.6 TSSR Approved |  | 2024-10-02 |  | 2024-10-07 |  | 2024-10-09 |  | 2024-10-11 | 2025-01-14 | CD//Ali akaram | 2024-11-25 | 0924CD-Central-GTSB-BOQ Template(new contract) | DU00002863051 |  |  |  |  | 2024-10-10 |  | BOOM
B01184 | B064F_B01184OD_TMNSUTERAKJG | Central |  | Decomm |  | 2024 Q3 | BY | GTSB | 4.6 TSSR Approved |  | 2024-03-16 |  |  |  | 2024-03-18 |  | 2024-05-10 | 2024-09-25 | CD//Norhaliza | 2024-08-19 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240323 | DU00002863052 |  |  |  |  | 2024-08-30 |  | LAMP_POLE
B00556 | B064E_B00556OD_PUASKJG | Central |  | Decomm |  | 2024 Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-23 |  |  |  | 2024-02-06 |  | 2024-02-07 | 2024-10-28 | CD//Ali Akaram | 2024-09-19 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240128 | DU00002863053 |  |  |  |  | 2024-10-11 |  | TOWER
7060R | T3_0827 - KG LONTONG | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863054 | [6 empty] | #N/A
S00772 | S098C_S00772OD_KWANTASOIL | Sabah |  | Decomm |  | 2024 Q4(single site MOCN)-L2126 SSM | MS | Datasco | 4.6 TSSR Approved |  | 2024-07-29 |  | 2024-08-06 |  | 2024-08-13 |  | 2024-08-14 | 2026-02-03 | CD//Ray Amos | 2026-03-31 | 0730CD-Sabah-Datasco-BOQ Template(new contract)/0730MW-Sabah-Datasco-BOQ Template(new contract) | DU00002863055 |  |  |  |  | 2024-12-06 |  | RAPOLE
B01079 | B064B_B01079OD_KGBARUBALAKONG | Central |  | Decomm |  | 2024 Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2023-12-03 |  |  |  | 2024-02-09 |  | 2024-04-19 | 2024-07-26 | CD//Ali Akaram | 2024-04-29 | CelcomDigi_RAN_Magicell_TSS_Central_20231208 | DU00002863056 |  |  |  |  | 2024-09-26 |  | TRIPOD
7061R | T3_0834 - KG ULU MANSOK | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863057 | [6 empty] | #N/A
7064R | T3_0806 - KG KITOU (KG BOGIAN) | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863058 | [6 empty] | #N/A
7032R | T3_0808 - KG LAMAS | Sabah |  | Maintain USP MOCN(Dismantle Passive) | Maintain USP MOCN(Dismantle Passive)->On Hold->Maintain USP MOCN(Dismantle Passive) | 2024 Q4 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2025-07-18 |  | 2025-07-21 |  | 2025-07-22 |  | 2025-08-05 | 2025-10-27 | E//Hannah | 2025-09-24 | SQ202508130660 - Seri Pancar | DU00002863059 |  |  |  |  | 2025-10-11 |  | #N/A
7033R | T3_0793 - KG TIKOLOD | Sabah |  | Maintain USP MOCN(Dismantle Passive) | Maintain USP MOCN(Dismantle Passive)->On Hold->Maintain USP MOCN(Dismantle Passive) | 2024 Q4 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2025-07-18 |  | 2025-07-21 |  | 2025-07-22 |  | 2025-08-05 | 2025-10-27 | E//Hannah | 2025-09-30 | SQ202508130660 - Seri Pancar | DU00002863060 |  |  |  |  | 2025-10-27 |  | #N/A
7501B | Kg. Terusan Baru | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863061 | [6 empty] | 45m 3 Legged Tower
B01224 | W066X_B01224OD_DESALBHPERMAI | Central |  | Decomm |  | 2024 Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-01-08 |  |  |  | 2024-01-15 |  | 2024-05-14 | 2025-03-21 | CD//Norhaliza | 2024-08-19 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240110 | DU00002863062 |  |  |  |  | 2024-08-22 |  | LAMP_POLE
7500B | Kg. Mumiang | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863063 | [6 empty] | 45m 3 Legged Tower
7582A | Ladang Sukau | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863064 | [6 empty] | Tower
7540B | Kg. Bambangan | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863065 | [6 empty] | 45m 3 Legged Tower
7508B | Felcra Estet Pertama | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863066 | [6 empty] | 76m 3 Legged Tower
7063R | T3_0082 - KG TUDAN | Sabah |  | Maintain USP MOCN(Dismantle Passive) | Maintain USP MOCN(Dismantle Passive)->On Hold->Maintain USP MOCN(Dismantle Passive) | 2024 Q4 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2025-08-01 |  | 2025-08-04 |  | 2025-08-05 |  | 2025-09-09 | 2025-10-27 | E//Hannah | 2025-09-18 | SQ202508130660 - Seri Pancar | DU00002863067 |  |  |  |  | 2025-10-11 |  | #N/A
B00266 | B064F_B00266OD_DESASURADAKJG | Central |  | Decomm | Decomm->On Hold | 2024 Q4(single site MOCN)-L2126 SSM | SY1 | DATASCO | 4.6 TSSR Approved |  | 2024-08-21 |  | 2024-09-08 |  | 2024-09-12 |  | 2024-10-11 | 2025-01-14 | CD//Sapian | 2024-12-18 | 0809CD-Central-Datasco-BOQ Template(new contract) | DU00002863068 |  |  |  |  | 2025-03-13 |  | MINI MONOPOLE
B02068 | W066X_B02068OD_MJDTMNKOSASAMPG | Central | 1919K | Swap | Decomm->On Hold->Swap | 2026 | AI | GCI | 4.6 TSSR Approved |  | 2023-11-25 |  |  |  | 2023-11-30 |  | 2023-12-06 | 2025-10-28 | CD//Sapian | 2025-10-28 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231126 | DU00002863069 |  |  |  | 2026-01-16 |  |  | RAPOLE |  | Add R8852E S9000x3+R9264M M1821x3+R8862A S2600x3, Dismantle
B00620 | W066J_B00620OD_JLNENGGANG | Central |  | Decomm |  | 2024 Q1 | CR | GCI | 4.6 TSSR Approved |  | 2024-03-18 |  |  |  | 2024-02-09 |  | 2024-03-30 | 2024-10-28 | CD//Ali Akaram | 2024-04-04 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240323 | DU00002863070 |  |  |  |  | 2024-07-22 |  | TOWER
B02057 | W066X_B02057OD_SUNRISEPARK | Central |  | Decomm |  | 2024 Q2 | SY1 | YPTT | 4.6 TSSR Approved |  | 2024-08-08 |  | 2024-08-15 |  | 2024-08-28 |  | 2024-08-30 |  | CD//Ali Akaram | 2024-09-06 | 0809CD-Central-YPTT-BOQ Template(new contract) | DU00002863071 |  |  |  |  | 2024-10-10 |  | BOOM
B00510 | B063C_B00510OD_KGSGBUAHLUAR | Central |  | Decomm |  | 2024 | MS | GTSB | 4.6 TSSR Approved |  | 2024-01-24 |  |  |  | 2024-03-11 |  | 2024-05-23 | 2025-03-21 | CD//Ali akaram | 2024-12-16 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240128 | DU00002863072 |  |  |  |  | 2024-10-04 |  | TOWER
B01066 | B064G_B01066OD_BANGIINDUSTRI | Central |  | Decomm |  | 2024 Q3 | MS | GTSB | 4.6 TSSR Approved |  | 2024-09-02 |  | 2024-09-08 |  | 2024-09-19 |  | 2024-09-20 | 2024-12-21 | CD//Norhaliza | 2024-10-21 | 0906CD-Central-GTSB-BOQ Template(new contract) | DU00002863073 |  |  |  |  | 2024-11-15 |  | LAMP_POLE
B00478 | B064G_B00478OD_SEK8BBBANGI | Central |  | Decomm |  | 2024 Q3 | MS | Solusi | 4.6 TSSR Approved |  | 2024-09-11 |  |  |  | 2024-09-19 |  | 2024-09-20 |  | CD//Ali Akaram | 2024-10-01 | 0924CD-Central-Solusi-BOQ Template(new contract) | DU00002863074 |  | 1) Please provide all tx equipment photo at NE with clear label, celcom cabinet got 3 IDU, CISCO & OB FIBER 2) Missing FE part |  |  | 2024-11-15 |  | BOOM
B01074 | B064B_B01074OD_TMNIMPIANEHSAN | Central |  | Decomm | Decomm-On Hold->Decomm | 2024 Q3 | BY | GTSB | 4.6 TSSR Approved |  | 2024-01-05 |  |  |  | 2024-03-18 |  | 2024-05-13 | 2024-07-12 | CD//Sapian | 2024-05-23 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240108 | DU00002863075 |  |  |  |  | 2025-05-29 |  | SHARING STRC SBC
B02282 | B061O_B02282OD_WESTPOINT_BDRUTAMA_SCT | Central |  | Decomm |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-27 |  |  |  | 2024-01-29 |  | 2024-02-05 | 2025-05-27 | CD//Ali Akaram | 2024-04-01 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240202 | DU00002863076 |  |  |  |  | 2024-06-12 |  | LAMP_POLE
B00330 | B064I_B00330OD_SASAPANKELUBI | Central |  | Decomm |  | 2025 Q3 | AI | GCI | 4.6 TSSR Approved |  | 2024-10-21 |  | 2024-10-30 |  | 2024-11-21 |  | 2025-02-22 | 2025-05-27 | CD//Ali Akaram | 2025-04-10 | SQ202501100412 | DU00002863077 |  |  |  |  | 2024-10-30 |  | TRIPOD
B00145 | B064A_B00145OD_BT18ULULANGAT | Central |  | Decomm |  | 2024 | CR | GCI | 4.6 TSSR Approved |  | 2023-11-01 |  |  |  | 2023-11-10 |  | 2023-11-14 | 2025-03-21 | CD//Norhaliza | 2024-01-18 | CelcomDigi_RAN_GCI_TSS_Central_20231104 | DU00002863078 |  |  |  |  | 2024-10-30 |  | TOWER
B00649 | B064H_B00649OD_DESAMAHKOTA | Central |  | Decomm |  | 2024 Additional | SHA | GTSB | 4.6 TSSR Approved |  | 2024-08-29 |  | 2024-09-09 |  | 2024-09-18 |  | 2024-11-29 | 2025-01-14 | CD//Ali Akaram | 2024-12-03 | 0919CD-Central-GTSB-BOQ Template(new contract) 2 | DU00002863079 |  |  |  |  | 2025-03-10 |  | TOWER
B00195 | B064H_B00195OD_BKTUNGGULEMVILE | Central |  | Decomm |  | 2024 Additional | AI | GTSB | 4.6 TSSR Approved |  | 2024-04-23 |  |  |  | 2024-05-31 |  | 2024-06-05 | 2025-01-14 | CD//Norhaliza | 2024-12-13 | CelcomDigi_RAN_GTSB_TSS_Central_20240509 | DU00002863080 |  |  |  |  | 2024-12-23 |  | TOWER
B00908 | W067A_B00908OD_PR_PRESINT19WPPJ | Central | 1882k | Swap | Decomm->Swap | 2024 Q3 | SHA | Magicell | 4.6 TSSR Approved |  | 2024-06-25 | 2024-07-16 |  | 2024-06-30 | 2023-12-04 | Under Approval | 2024-07-17 | 2024-09-10 | CD//Sapian | 2024-09-09 | CelcomDigi_RAN_Magicell_TSS_Central_20231203 | DU00002863081 |  |  | 2024-08-08 | 2024-08-01 |  | Monople Tree | LAMP_POLE | 30M | Add R8862A S9000 x1+R9264H M901821 x3+R8862A S2601 x4+A9732 M1821 x1,Dismantle | 4 | 0
W00386 | W066E_W00386OD_KGPDGBALANG | Central |  | Decomm |  | 2024 Q1 | SS | Magicell | 4.6 TSSR Approved |  | 2023-11-11 |  |  |  | 2023-11-23 |  | 2023-11-28 | 2024-07-29 | CD//Sapian | 2023-12-04 | CelcomDigi_RAN_Magicell_TSS_Central_20231113 | DU00002863082 |  |  |  |  | 2024-04-01 |  | SHARING STRC SBC
7483B | Kg Kembara Jaya | Sabah |  | Modernization |  | 2024 Q4 | SH | Seri Pancar | 4.6 TSSR Approved |  | 2024-07-29 | 2024-08-10 |  | 2024-08-14 |  | Under Approval | 2024-08-14 | 2024-08-21 | E//Hannah | 2024-08-21 | 0730CD-Sabah-Seri Pancar-BOQ Template(new contract) | DU00002863083 |  |  | 2024-09-09 | 2024-09-03 |  | Tower | 76m 3 Legged Tower | 76m | Reuse exsiting RRU | 0 | 0
7484B | Kg Sungai Rotan | Sabah |  | Modernization |  | 2024 Q4 | SH | Seri Pancar | 4.6 TSSR Approved |  | 2024-07-23 | 2024-07-31 |  | 2024-08-06 |  | Under Approval | 2024-08-16 | 2024-08-20 | E//Hannah | 2024-08-20 | 0725Sabah-Seri Pancar-BOQ Template(new contract) | DU00002863084 |  |  | 2024-09-13 | 2024-09-07 |  | Tower | 45m 3 Legged Tower | 60 | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle | 0 | 2
7148A | Kg Lung Manis | Sabah |  | Modernization |  | 2024 Q4 | AD | Seri Pancar | 4.6 TSSR Approved | Solution changed MM>Bi | 2024-07-30 | 2024-08-05 |  | 2024-08-09 |  | Under Approval | 2024-10-03 | 2024-10-14 | E//Hannah | 2024-10-04 | 0731CD-Sabah-Seri PancarBOQ Template(new contract) | DU00002863085 |  |  | 2024-09-23 | 2024-09-13 |  | Tower | 45m 3 Legged Tower | 76 | Add R8894E M1821x3,Dismantle | 0 | 123
B00013 | B061J_B00013OD_TMNBKTKUCHAI | Central |  | Decomm |  | 2024 Q3 | AI | DATASCO | 4.6 TSSR Approved |  | 2024-07-11 |  | 2024-08-05 |  | 2024-08-15 |  | 2024-08-16 |  | CD//Ali Akaram | 2024-08-21 | 0719Central-Datasco-BOQ Template | DU00002863086 |  |  |  |  | 2024-09-27 |  | TRIPOD
9109C | Kg Hulu (REL) | Sarawak |  | Modernization |  | 2025 Q3 | AD | Magicell | 4.6 TSSR Approved |  | 2023-12-03 | 2023-12-08 |  | 2025-02-18 |  | Under Approval | 2025-02-20 | 2025-03-09 | E//Hannah | 2025-02-24 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231206 | DU00002863087 |  |  | 2025-04-29 | 2025-04-17 |  | Monopole | 30M Rapole | 32m | Add R8852E S9000 x3+R9264M M1821 x3, Dismantle R8892N M1821(BAB)x3 | 0 | 0
B00455 | B064A_B00455OD_BT14HULULANGAT | Central |  | Decomm |  | 2024 | IE | GCI | 4.6 TSSR Approved |  | 2023-11-15 |  |  |  | 2023-11-19 |  | 2024-08-01 | 2025-03-21 | CD//Sapian | 2024-08-05 | Celcom Digi_RAN-GCI-TSS-Central-20231119 | DU00002863088 |  |  |  |  | 2024-09-28 |  | TOWER
B01132 | W066I_B01132OD_KGKEMANSAH | Central |  | Decomm |  | 2024 Q1 | AI | GCI | 4.6 TSSR Approved |  | 2024-01-23 |  |  |  | 2024-02-14 |  | 2024-02-16 | 2024-08-29 | CD//Ali Akaram | 2024-03-08 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240128 | DU00002863089 |  |  |  |  | 2024-07-25 |  | LAMP_POLE
B01200 | B064F_B01200OD_TMNBUKITMEWAH3 | Central |  | Decomm |  | 2024 Additional | AD | GCI | 4.6 TSSR Approved |  | 2024-05-30 |  |  |  | 2024-06-04 |  | 2024-06-05 | 2024-11-26 | CD//Ali akaram | 2024-11-20 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240605 | DU00002863090 |  |  |  |  | 2024-12-26 |  | LAMP_POLE
W01408 | W066S_W01408OD_SRIJATICONDO_TMNSRIJATI | Central |  | Decomm |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-03-21 |  |  |  | 2024-04-24 |  | 2024-08-13 | 2024-10-28 | CD//Norhaliza | 2024-10-04 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240323 | DU00002863091 |  |  |  |  | 2024-05-22 |  | LAMP_POLE
B00434 | W066I_B00434OD_UKAYPERDANA3 | Central |  | Decomm |  | 2024 Q1 | IE | GCI | 4.6 TSSR Approved |  | 2023-11-14 |  |  |  | 2023-11-17 |  | 2023-11-21 | 2024-09-25 | CD//Ali Akaram | 2023-11-28 | CelcomDigi_RAN_GCI_TSS_Central_20231116 | DU00002863092 |  |  |  |  | 2024-08-05 |  | LAMP_POLE
B00188 | B063B_B00188OD_PR_ERLSGLABU | Central |  | Decomm |  | 2024 | SHA | GCI | 4.6 TSSR Approved |  | 2024-03-05 |  |  |  | 2024-03-05 |  | 2024-05-21 |  | CD//Sapian | 2024-06-04 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240311 | DU00002863093 |  |  |  |  | 2024-12-26 |  | MONOPOLE
L00027 | S113A_L00027OD_AIRPORTLBN | Sabah |  | Decomm |  | 2025 Q1 | HW | YPTT | 4.6 TSSR Approved |  | 2025-01-15 |  | 2025-01-27 |  | 2025-02-04 | To be Submitted | 2025-02-20 |  | CD//Sharidah | 2025-02-26 | SQ202501030034 - YPTT / SQ202501070337 - YPTT | DU00002863094 |  |  |  |  | 2025-09-02 |  | TOWER
B02296 | B061J_B02296OD_JLNRAJAWALI1APCHG | Central |  | Decomm |  | 2024 Q3 | CR | Magicell | 4.6 TSSR Approved |  | 2024-05-09 |  |  |  | 2024-05-16 |  | 2024-05-23 | 2024-07-10 | CD//Ali Akaram | 2024-06-03 | CelcomDigi_RAN_Magicell_TSS_Central_20240513 | DU00002863095 |  |  |  |  | 2024-10-01 |  | UNIPOLE
W01186 | W066BB_W01186OD_TMNTAYNTONVIEW | Central |  | Decomm |  | 2024 Q3 | SH | Ascentrack | 4.6 TSSR Approved |  | 2024-01-24 |  |  |  | 2024-01-29 |  | 2024-04-02 | 2024-05-27 | CD//Sapian | 2024-04-30 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240128 | DU00002863096 |  |  |  |  | 2024-07-30 |  | BOOM
S01608 | S098C_S01608OD_DESABAJAU | Sabah |  | Decomm |  | 2024 Q3(single site MOCN) | AD | Seri Pancar | 4.6 TSSR Approved |  | 2024-06-24 |  |  |  | 2024-07-16 |  | 2024-07-17 | 2024-08-29 | CD//Ray Amos | 2024-07-22 | 0626Sabah-Seri Pancar-BOQ Template (template) | DU00002863097 |  |  |  |  | 2024-10-28 |  | RAPOLE
B02784 | B061L_B02784OD_THEWHARFRTTS | Central |  | Decomm |  | 2024 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2024-02-28 |  |  |  | 2024-03-06 |  | 2024-05-23 | 2024-07-12 | CD//Ali Akaram | 2024-06-03 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240303 | DU00002863098 |  |  |  |  | 2024-08-28 |  | TRIPOD
K00157 | K005D_K00157OD_GURUN | Northern |  | Decomm |  | 2024 Q4 | SHA | GCI | 4.6 TSSR Approved |  | 2024-10-21 |  |  |  | 2024-12-05 |  | 2024-12-17 |  | CD//Zulakmar | 2024-12-18 | 0927CD-Northern-GCI-BOQ Template(new contract) | DU00002863099 |  |  |  |  | 2024-10-23 |  | TOWER
K00071 | K005C_K00071OD_MEDICALCOLLEGE | Northern |  | Decomm |  | 2024 Q3(single site MOCN) | BY | GCI | 4.6 TSSR Approved |  | 2024-06-07 |  | 2024-07-15 |  | 2024-07-17 |  | 2024-07-19 | 2024-10-01 | CD//Zulakmar | 2024-07-23 | 0618Northen-GCI-BOQ Template (template) | DU00002863100 |  |  |  |  | 2024-08-30 |  | TOWER
B00713 | B063B_B00713OD_KLIAFMB | Central |  | Decomm | Decomm->On hold->Decomm | 2024 | AI | GTSB | 15.4 Decomm Done without TSSR Approval |  | 2024-08-29 |  | 2024-09-08 |  | 2024-10-18 | To be Submitted | 2024-10-21 |  | CD//Ali Akaram |  | 0919CD-Central-GTSB-BOQ Template(new contract) 2 | DU00002863101 |  |  |  |  | 2025-02-25 |  | BOOM
K00271 | K002A_K00271OD_KGLALANG | Northern |  | Decomm |  | 2024 Q4 | SM | GCI | 4.6 TSSR Approved |  | 2024-11-04 |  | 2024-10-30 |  | 2024-11-13 |  | 2024-11-15 |  | CD//Zulakmar | 2024-11-18 | 0927CD-Northern-GCI-BOQ Template(new contract)/0927MW-Northern-GCI-BOQ Template(new contract) | DU00002863102 |  |  |  |  | 2024-10-30 |  | TOWER
B00232 | B064A_B00232OD_TMCHERAS | Central |  | Decomm |  | 2024 Q4(single site MOCN)-L2126 SSM | SY1 | GCI | 4.6 TSSR Approved |  | 2024-08-23 |  | 2024-08-29 |  | 2024-08-30 |  | 2024-09-02 | 2025-03-11 | CD//Ali Akaram | 2024-09-03 | 0809CD-Central-GCI-BOQ Template(new contract) | DU00002863103 |  |  |  |  | 2024-12-20 |  | BOOM
B00884 | B064G_B00884OD_SEK7BBBANGI | Central |  | Decomm |  | 2024 Q4 | SH | Magicell | 4.6 TSSR Approved |  | 2024-03-04 |  |  |  | 2024-03-05 |  | 2024-05-21 | 2025-07-25 | CD//Norhaliza | 2024-11-12 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240311 | DU00002863104 |  |  |  |  | 2024-09-24 |  | BOOM
B02238 | B061L_B02238OD_TMNPCHGTEKALI | Central |  | Decomm | Decomm->On Hold->Decomm | 2024 Q3 | SH | GTSB | 4.6 TSSR Approved |  | 2024-02-26 |  |  |  | 2024-05-24 |  | 2024-05-30 | 2024-07-26 | CD//Ali Akaram | 2024-06-05 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240303 | DU00002863105 |  |  |  |  | 2025-05-26 |  | MONOPOLE
B02190 | B064G_B02190OD_SURAUALUKHWANSEK4BBBANGI | Central |  | Decomm |  | 2024 Q3 | CR | GCI | 4.6 TSSR Approved |  | 2024-10-11 |  | 2024-10-18 | 2024-10-21 | 2024-10-22 | Under Approval | 2024-11-07 |  | CD//Ali Akaram | 2024-11-13 | 0924CD-Central-GCI-BOQ Template(new contract) | DU00002863106 |  |  |  |  | 2024-10-19 |  | LAMP_POLE
W00389 | W066S_W00389OD_KLINDJKL | Central |  | Decomm |  | 2024 Q3 | AI | Magicell | 4.6 TSSR Approved | 14/8- target tomorrow TSS // 11/8 BM approved, plan Wed. // 8/8 - Pending access BM | 2025-08-15 |  | 2025-08-20 |  | 2025-08-28 | To be Submitted | 2025-09-18 |  | CD//Ali Akaram | 2026-04-17 | SQ202508190105 / SQ202508190058 | DU00002863107 |  |  |  |  | 2025-10-23 |  | BOOM
B01111 | B064A_B01111OD_TMNCHRSMAS | Central |  | Decomm |  | 2024 Q4(single site MOCN)-L26 SSM | CR | GCI | 4.6 TSSR Approved |  | 2023-12-22 |  |  |  | 2024-01-18 |  | 2024-05-16 | 2025-05-27 | CD//Norhaliza | 2024-08-19 | CelcomDigi_RAN_GCI_TSS_Central_20231224 | DU00002863108 |  |  |  |  | 2024-11-21 |  | LAMP_POLE
B00070 | W066BB_B00070OD_PGACHERAS | Central |  | Decomm |  | 2024 Q4 | SM | GTSB | 4.6 TSSR Approved |  | 2024-03-30 |  |  |  | 2024-05-21 |  | 2024-05-28 | 2025-03-20 | CD//Ali Akaram | 2024-07-23 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240403 | DU00002863109 |  |  |  |  | 2024-10-26 |  | MONOPOLE
B00008 | B061J_B00008OD_BDRPCHGJAYA | Central | 1875K | Swap | Decomm->On Hold->Swap | 2024 Q3 | SHA | GCI | 4.6 TSSR Approved |  | 2024-07-21 | 2024-06-24 |  | 2024-07-23 | 2024-02-15 | Under Approval | 2024-07-31 | 2024-08-09 | CD//Norhaliza | 2024-08-08 | 0619Central-GCI-BOQ Template (template) | DU00002863110 |  |  | 2024-11-18 | 2024-11-15 |  | In-Building System | TRIPOD | 5 | Add R9264H M901821 x3,Dismantle | 0 | 0
K00772 | K003A_K00772OD_CB_KM169NSE_NB | Northern |  | Decomm |  | 2024 Q4 | HW | CCSMY | 4.6 TSSR Approved |  | 2024-12-18 |  | 2025-01-03 |  | 2025-02-12 |  | 2025-02-20 | 2025-05-06 | CD//Hazwan | 2025-02-26 | 0927CD-Northern-CCSMY-BOQ Template(new contract)/0927MW-Northern-CCSMY-BOQ Template(new contract) | DU00002863111 |  |  |  |  | 2024-12-06 |  | MONOPOLE
A00109 | A039B_A00109OD_BGNSERAITOWN | Northern |  | Decomm |  | 2024 Q4 | BY | GTSB | 4.6 TSSR Approved |  | 2023-12-07 |  |  |  | 2023-12-12 |  | 2023-12-13 | 2024-01-22 | CD//Affendi | 2023-12-14 | Celcom Digi_RAN-GTSB-TSS-Northern-20231207-0073 | DU00002863112 |  |  |  |  | 2024-09-30 |  | BOOM
B00189 | B063B_B00189OD_PR_PANPACKLIA | Central |  | Decomm | Decomm->On Hold->Decomm | 2024 | SM | GTSB | 4.6 TSSR Approved |  | 2024-03-01 |  |  |  | 2024-07-29 |  | 2024-12-09 | 2025-01-14 | CD//Ali Akaram | 2024-12-10 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240303 | DU00002863113 |  |  |  |  | 2024-12-06 |  | BOOM
1189A | Serisetia | Central |  | Modernization |  | 2024 Q1 | XH | Magicell | 4.6 TSSR Approved |  | 2023-11-22 | 2023-12-08 |  | 2024-01-03 |  | Closed | 2024-01-03 | 2024-01-05 |  | 2024-01-04 | CelcomDigi_RAN_Magicell_TSS_Central_20231126 | DU00002863114 |  |  | 2024-03-15 | 2024-03-12 |  | In-Building System | 3m Boom (RT) | 5M | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x5+R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3
S00935 | S094A_S00935OD_KGDALAMASON | Sabah |  | Decomm |  | 2024 Q3(single site MOCN) | AD | Seri Pancar | 4.6 TSSR Approved |  | 2024-06-13 |  |  |  | 2024-06-26 |  | 2024-07-01 | 2024-08-09 | CD//Ray Amos | 2024-07-01 | 0618Sabah-Seri Pancar-BOQ Template (template) | DU00002863115 |  |  |  |  | 2024-10-16 |  | TOWER
W00117 | W066H_W00117OD_WISMAKAUTHAR | Central |  | Decomm |  | 2024 Q1 | SHA | DATASCO | 4.6 TSSR Approved |  | 2024-01-24 |  | 2024-07-20 |  | 2024-07-22 |  | 2024-07-23 | 2025-10-01 | CD//Norhaliza | 2024-10-04 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240128 | DU00002863116 |  |  |  |  | 2024-08-17 |  | BOOM
A00233 | A041A_A00233OD_TMKKANGSAR | Northern |  | Decomm |  | 2024 Q4 | SM | GTSB | 4.6 TSSR Approved |  | 2024-01-19 |  |  |  | 2024-01-19 |  | 2024-09-30 | 2025-07-29 | CD//Zulakmar | 2024-10-09 | Celcom Digi_RAN-GTSB-TSS-Northern-20240124-0088 | DU00002863117 |  |  |  |  | 2025-08-14 |  | GUYED MAST
1201A | Stellar | Central |  | Modernization |  | 2024 Q1 | SS | Magicell | 4.6 TSSR Approved |  | 2024-01-05 | 2024-01-18 |  | 2024-01-22 |  | Closed | 2024-01-30 | 2024-04-23 | E//Kok Keen | 2024-04-22 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240110 | DU00002863118 |  |  | 2024-04-23 | 2024-04-01 |  | In-Building System | 3m RT (Minimast) | 9m | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3
1223A | Kg Tunku | Central |  | Modernization |  | 2024 Q1 | XH | Magicell | 4.6 TSSR Approved |  | 2023-11-22 | 2023-11-24 |  | 2023-12-29 |  | Closed | 2024-01-03 | 2024-01-05 |  | 2024-01-04 | CelcomDigi_RAN_Magicell_TSS_Central_20231126 | DU00002863119 |  |  | 2024-05-02 | 2024-04-01 |  | In-Building System | 3m Boom (RT) | 6 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8882 S1800B(B6B) x3+R8840-U216 x3
W00979 | B064C_W00979OD_PR_KM13MEXHWY | Central |  | Decomm |  | 2024 Q3 | SHA | GTSB | 4.6 TSSR Approved |  | 2024-06-10 | 2024-06-28 |  |  | 2024-07-15 |  | 2024-07-19 | 2024-09-25 | CD//Ali Akaram | 2024-07-25 | Wireless+ Malaysia CD+TSS+ GTSB+9 site SQ202410310159 | DU00002863120 |  |  |  |  | 2024-08-30 | Monople Tree | TOWER | 30
1231B | Ara Hill Shoplots | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q1 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002863121 | [6 empty] | 3m Boom (RT) |  |  |  | 3
A00128 | A037A_A00128OD_TLKINTAN | Northern |  | Decomm |  | 2024 Q4 | SM | GCI | 4.6 TSSR Approved |  | 2023-10-19 |  |  |  | 2023-10-26 |  | 2023-10-30 | 2024-10-01 | CD//Affendi | 2024-01-30 | Celcom Digi_RAN-GCI-TSS-Northern-20231020-0063 | DU00002863122 |  |  |  |  | 2024-09-30 |  | TRIPOD
B02262 | B064G_B02262OD_TMNIKSBBBANGI | Central |  | Decomm |  | 2024 Q3 | SH | Solusi | 4.6 TSSR Approved |  | 2024-09-05 |  |  |  | 2024-09-09 |  | 2024-12-23 |  | CD//Ali Akaram | 2024-12-24 | 0924CD-Central-Solusi-BOQ Template(new contract) | DU00002863123 |  |  |  |  | 2024-11-15 |  | BOOM
B00148 | W067A_B00148OD_PR_KM4CBJ | Central |  | Decomm |  | 2024 Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2023-12-13 |  |  |  | 2023-12-26 |  | 2024-04-19 | 2024-05-27 | CD//Norhaliza | 2024-07-17 | CelcomDigi_RAN_Magicell_TSS_Central_20231214 | DU00002863124 |  |  |  |  | 2024-12-06 |  | TOWER
W00145 | W066E_W00145OD_BT4JLNGOMBAK | Central |  | Decomm |  | 2024 Q1 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-05-09 |  |  |  | 2024-05-09 |  | 2024-05-10 |  | CD//Ali Akaram | 2024-05-20 | CelcomDigi_RAN_Datasco_TSS_Central_20240513 | DU00002863125 |  | 1) Missing antenna tx photo at NE 2) Missing FE part |  |  | 2024-05-27 |  | LAMP_POLE
B02569 | B063C_B02569OD_BKTTAMPOI_REL_SCT | Central |  | Decomm |  | 2024 Additional | AD | GTSB | 4.6 TSSR Approved |  | 2024-01-03 |  |  |  | 2024-01-09 |  | 2024-05-23 | 2024-07-12 | CD//Sapian | 2024-06-06 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240108 | DU00002863126 |  |  |  |  | 2025-02-20 |  | TOWER
A00315 | A040D_A00315OD_CB_TMTGTUALANG | Northern |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4 | HW | GTSB | 4.6 TSSR Approved | 8/8 - team retract, Rollout to reassign // 6/8 - TM site, access pending, raise up to SA to prioritize | 2025-09-19 |  | 2025-09-25 |  | 2025-09-30 |  | 2025-10-01 | 2026-02-16 | E//Hazida | 2025-10-15 | SQ202508270693 | DU00002863127 |  |  |  |  | 2025-11-28 |  | BOOM
B01435 | W066I_B01435OD_TMN_SERING_UKAYPERDANA | Central | 1863K | Swap | Decomm->On hold->Swap | 2024 Q1 | AI | GTSB | 4.6 TSSR Approved |  | 2024-12-13 | 2024-12-23 |  | 2025-01-03 |  | Closed | 2025-01-03 | 2025-02-07 | CD//Ali Akaram | 2025-01-28 | SQ202411150110 | DU00002863128 |  |  | 2025-02-21 | 2025-02-17 |  | Lampole | LAMP_POLE | 18 | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
B00611 | W066J_B00611OD_AU2 | Central |  | Decomm |  | 2024 Q1 | SM | GCI | 4.6 TSSR Approved |  | 2024-01-11 |  |  |  | 2024-02-20 |  | 2024-02-22 | 2024-08-29 | CD//Ali Akaram | 2024-05-21 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240115 | DU00002863129 |  |  |  |  | 2024-11-26 |  | TOWER
B00262 | W066X_B00262OD_KGDATOMUFTI | Central |  | Decomm |  | 2024 Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-30 |  |  |  | 2023-12-18 |  | 2024-01-29 | 2024-02-15 | CD//Norhaliza | 2024-02-07 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231203 | DU00002863130 |  |  |  |  | 2024-08-24 |  | BOOM
1362B | Kelana Business Centre | Central |  | Modernization |  | 2024 Q1 | AI | DATASCO | 4.6 TSSR Approved |  | 2023-10-25 | 2023-10-30 |  | 2023-12-29 |  | Closed | 2024-01-02 | 2024-01-03 | E//Kok Keen | 2024-01-03 | CelcomDigi_RAN_Datasco_TSS_Central_20231028 | DU00002863131 |  |  | 2024-03-25 | 2024-03-15 |  | In-Building System | 6m RT (Boom) | 3.5 | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle R8862A S2600(A4A) x1 |  | 3
W00889 | W066BB_W00889OD_TMNWANGSACHERAS | Central |  | Decomm |  | 2024 Q4(single site MOCN)-L2126 SSM | SM | GTSB | 4.6 TSSR Approved |  | 2024-02-26 |  |  |  | 2024-05-23 |  | 2024-05-28 | 2024-07-12 | CD//Sapian | 2024-06-18 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240303 | DU00002863132 |  |  |  |  | 2024-10-23 |  | AESTHETIC MONOPOLE
B02669 | W066X_B02669OD_AVENUE_AMPANG | Central |  | Decomm |  | 2024 Q4 | BY | GTSB | 4.6 TSSR Approved |  | 2024-03-19 |  |  |  | 2024-04-26 |  | 2024-05-23 | 2024-09-25 | CD//Norhaliza | 2024-09-06 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240323 | DU00002863133 |  |  |  |  | 2024-08-27 |  | UNIPOLE
B01484 | B064B_B01484OD_CHERASPDANA2 | Central |  | Decomm |  | 2024 Q4 | SY1 | Solusi | 4.6 TSSR Approved |  | 2024-07-26 |  |  |  | 2024-08-23 |  | 2024-08-26 | 2025-03-20 | CD//Ali akaram | 2024-09-11 | 0724Central-Solusi-BOQ Template | DU00002863134 |  |  |  |  | 2024-09-24 |  | TRIPOD
B00598 | W066W_B00598OD_DESAPANDAN2 | Central |  | Decomm | Decomm->Site Out | 2024 Q2 | BY | GTSB | 4.6 TSSR Approved |  | 2024-03-19 |  | 2025-07-09 |  | 2024-04-23 |  | 2024-05-23 | 2024-09-06 | CD//Sapian | 2024-06-11 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240323 | DU00002863135 |  |  |  |  | 2025-04-29 |  | TRIPOD
B00743 | B061P_B00743OD_SS25PJ | Central |  | Decomm |  | 2024 Q3 | IE | Magicell | 4.6 TSSR Approved |  | 2023-11-30 |  |  |  | 2023-12-05 |  | 2023-12-06 | 2024-01-22 | CD//Norhaliza | 2024-01-18 | CelcomDigi_RAN_Magicell_TSS_Central_20231203 | DU00002863136 |  |  |  |  | 2024-05-29 |  | BOOM
1395A | Semaipadu | Central |  | Modernization |  | 2024 Q1 | MS | DATASCO | 4.6 TSSR Approved |  | 2023-11-10 | 2024-01-30 |  | 2024-02-07 |  | Closed | 2024-02-08 | 2024-02-20 |  | 2024-02-20 | CelcomDigi_RAN_Datasco_TSS_Central_20231116 | DU00002863137 |  |  | 2024-03-12 | 2024-03-02 |  | In-Building System | 3m Boom (RT) | 7.5 | Add R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882-GUL1812 x3+R8882 S2600(B4A) x1+R8840-U216 x3++ |  | 2
B00136 | B064B_B00136OD_TMNJUARAJAYA | Central |  | Decomm |  | 2024 Q3 | AD | Magicell | 4.6 TSSR Approved |  | 2023-12-28 |  |  |  | 2024-02-08 |  | 2024-04-19 | 2025-07-25 | CD//Ali Akaram | 2024-05-02 | CelcomDigi_RAN_Magicell_TSS_Central_20231230 | DU00002863138 |  |  |  |  | 2024-08-30 |  | BOOM
B01482 | B061K_B01482OD_BDRPUTERIPCHG5 | Central |  | Decomm |  | 2024 Q3 | AD | Magicell | 4.6 TSSR Approved |  | 2024-02-21 |  |  |  | 2024-04-17 |  | 2024-04-19 | 2024-08-03 | CD//Sapian | 2024-05-12 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240225 | DU00002863139 |  |  |  |  | 2024-10-02 |  | BOOM
B02317 | B064D_B02317OD_SMKJLNCHERASKAJANG | Central |  | Decomm |  | 2024 Q4(single site MOCN)-L2126 SSM | BY | GTSB | 4.6 TSSR Approved |  | 2024-04-01 |  |  |  | 2024-04-26 |  | 2024-05-23 | 2024-09-25 | CD//Ali Akaram | 2024-07-23 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240403 | DU00002863140 |  |  |  |  | 2025-01-23 |  | LAMP_POLE
1406A | Kg Tunku Shoplot | Central |  | Modernization |  | 2024 Q1 | SS | Magicell | 4.6 TSSR Approved |  | 2023-11-17 | 2023-11-20 |  | 2024-01-02 |  | Closed | 2024-01-04 | 2024-03-15 |  | 2024-03-13 | CelcomDigi_RAN_Magicell_TSS_Central_20231120 | DU00002863141 |  |  | 2024-04-03 | 2024-03-29 |  | Minimast | 3m RT (Minimast) | 15 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1
B00910 | W067A_B00910OD_PR_DENGKIL | Central |  | Decomm |  | 2024 | AD | GTSB | 4.6 TSSR Approved |  | 2024-02-08 |  |  |  | 2024-02-14 |  | 2024-05-23 | 2025-01-14 | CD//Sapian | 2024-06-06 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240212 | DU00002863142 |  |  |  |  | 2024-09-30 |  | TOWER
B01950 | B063C_B01950OD_KG_SRI_TANJUNG | Central |  | Decomm |  | 2024 Additional | AI | GTSB | 4.6 TSSR Approved |  | 2025-03-19 |  | 2025-03-25 |  | 2025-04-07 |  | 2025-04-13 |  | CD//Sapian | 2025-05-08 | SQ202502180534 | DU00002863143 |  |  |  |  | 2025-08-25 |  | MONOPOLE
B00571 | B061H_B00571OD_TMNDATOHARUN | Central |  | Decomm |  | 2024 Q3 | SH | GTSB | 4.6 TSSR Approved |  | 2024-03-14 |  |  |  | 2024-05-23 |  | 2024-05-28 | 2024-07-12 | CD//Norhaliza | 2024-06-19 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240316 | DU00002863144 |  |  |  |  | 2024-06-05 |  | MINI STRUCTURE
W00609 | B061Q_W00609OD_TMNGASINGINDAH | Central |  | Decomm |  | 2024 Q2 | SY1 | Solusi | 4.6 TSSR Approved |  | 2024-03-11 |  |  |  | 2024-06-28 |  | 2024-07-01 | 2025-03-20 | CD//Sapian | 2024-07-04 | CelcomDigi_RAN_Solusi_TSS_Central_20240513 | DU00002863145 |  |  |  |  | 2024-08-30 |  | MINI STRUCTURE
W01560 | W066I_W01560OD_DESAMELAWATI2 | Central |  | Decomm | Decomm->On Hold->Site Out->Decomm | 2024 Q1 | MA | GTSB | 14.1 TSSR Not Required (Decomm by CD) | 18/8 - Site fully decomm 14/8- Wait OSS to revert, 8/8 - team enter today// 6/8 - Team plan Wk33 | 2025-10-03 |  | 2025-10-13 |  | 2025-10-22 | To be Submitted |  |  | CD//Sapian |  | SQ202506170753 | DU00002863146 |  |  |  |  | 2025-10-03 |  | LAMP_POLE
W00201 | W066Z_W00201OD_BT2JLNCHERAS | Central |  | Decomm |  | 2024 Q3 | SH | Ascentrack | 4.6 TSSR Approved |  | 2024-02-01 |  |  |  | 2024-02-15 |  | 2024-04-02 |  | CD//Sapian | 2024-06-11 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240202 | DU00002863147 |  | 1) Pls provide digi cabinet/rack photo 2) missing antenna tx photo at NE & FE part |  |  | 2024-08-27 |  | BOOM
W00202 | W066Z_W00202OD_WISMADANI | Central |  | Decomm |  | 2024 Q2 | SH | GTSB | 4.6 TSSR Approved |  | 2024-04-17 |  |  |  | 2024-05-31 |  | 2024-06-07 | 2024-10-28 | CD//Norhaliza | 2024-10-04 | CelcomDigi_RAN_GTSB_TSS_Central_20240509 | DU00002863148 |  |  |  |  | 2024-08-07 |  | BOOM
1426B | Masjid Al-Hidayah KJ | Central |  | Modernization |  | 2024 Q1 | SS | Magicell | 4.6 TSSR Approved |  | 2023-11-28 | 2023-12-01 |  | 2024-01-02 |  | Closed | 2024-01-04 | 2024-01-05 |  | 2024-01-04 | CelcomDigi_RAN_Magicell_TSS_Central_20231201 | DU00002863149 |  |  | 2024-04-21 | 2024-03-27 |  |  | 45m Monopole | 25 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1
W01132 | W066S_W01132OD_DE_EARTH_PUCHONG | Central |  | Decomm |  | 2024 Q3 | SHA | GTSB | 4.6 TSSR Approved |  | 2024-03-08 |  | 2024-07-20 |  | 2024-10-11 |  | 2024-10-14 | 2025-01-14 | CD//Norhaliza | 2024-11-12 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240311 | DU00002863150 |  |  |  |  | 2024-09-26 |  | TOWER
A00310 | A040D_A00310OD_KGKEPAYANG | Northern |  | Decomm |  | 2025 Q3 | HW | GTSB | 4.6 TSSR Approved |  | 2025-07-24 |  | 2025-07-29 |  | 2025-08-07 | To be Submitted | 2025-08-12 |  | E//Hazida | 2025-08-15 | SQ202501060259 - GTSB | DU00002863151 |  |  |  |  | 2025-08-27 |  | TOWER
A00534 | A038A_A00534OD_MAMBANGINDUSTRY | Northern |  | Decomm |  | 2024 Q3(single site MOCN) | SM | GCI | 4.6 TSSR Approved |  | 2024-07-08 |  | 2024-07-14 |  | 2024-07-16 |  | 2024-07-17 | 2024-10-01 | CD//Zulakmar | 2024-07-18 | 0918CD-Northern-GCI-BOQ Template (old contract) | DU00002863152 |  |  |  |  | 2024-08-13 |  | TOWER
9186A | Saratok Town(SACOFA) | Sarawak |  | Modernization |  | 2025 Q3 | AI | Datasco | 4.6 TSSR Approved |  | 2023-10-20 | 2023-10-27 |  | 2025-02-26 |  | Closed | 2025-03-05 | 2025-03-10 | E//Hannah | 2025-03-10 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231024 | DU00002863153 |  |  | 2025-05-17 | 2025-04-15 |  | Tower | Tower | 75 | Add R9264M M1821x2+A9732 M1821x1, Dismantle R8894E M1821(A8A)x3 | 1 | 23
A00078 | A036A_A00078OD_BIDOR | Northern |  | Decomm |  | 2025 Q1 | SM | CCSMY | 4.6 TSSR Approved | 0116 - CD Zul: TSSR is ok. However, lets wait for the pair site to be implemented first before I approve this tssr. | 2024-01-24 |  |  |  | 2024-01-31 |  | 2025-01-06 | 2025-07-25 | CD//Zulakmar | 2025-03-03 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240124-0089//SQ202501030037 | DU00002863154 |  | CD Hazwan reviewed but Hold wait for upg tssr ready first |  |  | 2025-07-21 |  | BOOM
K00249 | K008A_K00249OD_KISAP | Northern |  | Decomm |  | 2024 Q4 | SM | CCSMY | 4.6 TSSR Approved |  | 2024-10-09 |  | 2024-10-14 |  | 2024-10-16 |  | 2024-10-17 | 2025-07-25 | CD//Zulakmar | 2024-10-23 | 0927CD-Northern-CCSMY-BOQ Template(new contract) | DU00002863155 |  |  |  |  | 2024-11-05 |  | TOWER
P00390 | P032A_P00390OD_TRANSKRIAN | Northern |  | Decomm |  | 2024 Q4 | MS | YPTT | 4.6 TSSR Approved | ¦ 0910 - Pending ZTE revise, MS | 2024-02-04 |  |  |  | 2024-02-09 | To be Submitted | 2024-09-18 |  | CD//Zulakmar | 2024-10-02 | Celcom Digi_RAN-YPTT-TSS-Northern-20240207-0059_reraise 21/6 | DU00002863156 |  |  |  |  | 2024-09-26 |  | TOWER
K00278 | K003A_K00278OD_CB_SUNGAIDURI | Northern |  | Decomm |  | 2025 Q3 | HW | GTSB | 4.6 TSSR Approved |  | 2025-02-19 |  | 2025-03-03 |  | 2025-03-06 | To be Submitted | 2025-03-07 |  | CD//Zulakmar | 2025-03-13 | SQ202501060259 - GTSB | DU00002863157 |  |  |  |  | 2025-09-23 |  | TOWER
R00064 | R001B_R00064OD_JLNSYEDALWI | Northern |  | Decomm |  | 2024 Q4 | SM | CCSMY | 4.6 TSSR Approved |  | 2024-02-28 |  |  |  | 2024-03-11 |  | 2024-04-29 | 2024-05-10 | CD//Affendi | 2024-05-09 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240229-0097 | DU00002863158 |  |  |  |  | 2024-06-13 |  | TOWER
K00382 | K008A_K00382OD_PLKNLANGKAWI | Northern |  | Decomm |  | 2024 Q3(single site MOCN) | SM | CCSMY | 4.6 TSSR Approved |  | 2024-08-09 |  | 2024-08-13 |  | 2024-08-14 |  | 2024-08-26 | 2024-10-01 | CD//Zulakmar | 2024-08-26 | 0809CD-Northern-CCSMY-BOQ Template(new contract) | DU00002863159 |  |  |  |  | 2024-12-18 |  | TOWER
K00411 | K008A_K00411OD_BKTPENARAK | Northern |  | Decomm |  | 2024 Q3(single site MOCN) | SM | CCSMY | 4.6 TSSR Approved | ¦ 1205 - ZTE Amin RF: Hi Gobi Please help to issue CR for this site which is already CD MOCN. Proposing to add sector to match xC coverage instead of changing to xC anchor ¦ 1205 - replied to Li Jie actual antenna height. ¦ 1009 - Fup done to planning ¦ 1001 - Fup done to Planning ¦ 0910 - CD Zul: Please get latest MR plot and compare to xC plot, Emailed to planning team | 2024-08-11 |  | 2024-08-15 |  | 2024-08-21 |  | 2024-09-06 | 2026-01-21 | CD//Zulakmar | 2026-03-31 | 0809CD-Northern-CCSMY-BOQ Template(new contract) | DU00002863160 |  |  |  |  | 2024-10-21 |  | TOWER
K00521 | K011A_K00521OD_TMNBDRBARU | Northern |  | Decomm |  | 2024 Q3(single site MOCN) | SM | GCI | 4.6 TSSR Approved |  | 2024-04-28 |  |  |  | 2024-05-03 |  | 2024-05-20 | 2024-10-01 | CD//Affendi | 2024-05-27 | Celcom Digi_RAN-GCI-TSS-Northern-20240512-0106 | DU00002863161 |  |  |  |  | 2025-07-14 |  | MONOPOLE
K00147 | K010A_K00147OD_CB_MDPPENDANG | Northern |  | Decomm |  | 2024 Q4 | SHA | GCI | 4.6 TSSR Approved |  | 2024-10-23 |  | 2024-10-30 |  | 2024-11-21 |  | 2024-11-22 | 2025-07-25 | CD//Zulakmar | 2024-12-24 | 0927CD-Northern-GCI-BOQ Template(new contract)/0927MW-Northern-GCI-BOQ Template(new contract) | DU00002863162 |  |  |  |  | 2024-10-28 |  | BOOM
A00213 | A036A_A00213OD_BIDOREXIT | Northern |  | Decomm |  | 2024 Additional | SHA | CCSMY | 4.6 TSSR Approved |  | 2024-01-19 |  |  |  | 2024-01-31 |  | 2024-12-16 | 2025-07-25 | CD//Zulakmar | 2024-12-18 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240124-0089 | DU00002863163 |  |  |  |  | 2025-01-14 |  | TOWER
A00097 | A037B_A00097OD_HUTANMELINTANG | Northern |  | Decomm |  | 2024 Q3(single site MOCN) | SM | GTSB | 4.6 TSSR Approved |  | 2024-06-19 |  | 2024-07-20 |  | 2024-07-22 |  | 2024-07-24 |  | CD//Zulakmar | 2024-07-26 | Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20240924_New Contract | DU00002863164 |  | Missing Digi Cabinet |  |  | 2024-08-16 | Tower | TOWER | 60m
A00081 | A036A_A00081OD_CB_BIDOR2 | Northern |  | Decomm |  | 2024 Q4 | MS | CCSMY | 4.6 TSSR Approved | ¦ 1001 - Replied to Zul anntenna relocateion will be done upon CR, requesting to approved decomm TSSR. ¦ 0910 - CD Zul: Propose to relocate pair site antenna 4317A from 60m to A00081 antenna height 70m. | 2024-01-19 |  |  |  | 2024-01-22 |  | 2024-09-18 | 2024-10-03 | CD//Zulakmar | 2024-10-02 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240124-0089 | DU00002863165 |  |  |  |  | 2024-10-24 |  | TOWER
A00053 | A040D_A00053OD_BEMBAN_RDD | Northern |  | Decomm |  | 2024 Q3(single site MOCN) | BY | GTSB | 4.6 TSSR Approved |  | 2024-07-22 |  | 2024-07-11 |  | 2024-07-23 |  | 2024-07-24 | 2025-10-01 | CD//Zulakmar | 2024-07-24 | 0725Northern-GTSB-BOQ Template(new contract)/0725Northen-GTSB-BOQ Template(new contract) | DU00002863166 |  |  |  |  | 2024-08-14 |  | TOWER
A00271 | A044A_A00271OD_CB_TITIGANTUNG_RCC | Northern |  | Decomm |  | 2024 Q2 | ZA | GTSB | 4.6 TSSR Approved |  | 2024-01-29 |  |  |  | 2024-02-05 |  | 2024-02-06 |  | CD//Affendi | 2024-02-07 | Celcom Digi_RAN-GTSB-TSS-Northern-20240202-0090 | DU00002863167 |  | Missing Celcom cabinet photo 4/6: No all TX info |  |  | 2024-06-10 |  | TOWER
A00460 | A044A_A00460OD_CKTCHERMIN_RCC | Northern |  | Decomm |  | 2024 Q2 | BY | GTSB | 4.6 TSSR Approved |  | 2024-01-26 |  |  |  | 2024-02-06 |  | 2024-02-07 | 2024-05-10 | CD//Affendi | 2024-02-15 | Celcom Digi_RAN-GTSB-TSS-Northern-20240124-0089 | DU00002863168 |  |  |  |  | 2024-05-22 |  | TOWER
A00129 | A044A_A00129OD_CB_SRIISKANDAR_RCC | Northern |  | Decomm |  | 2024 Q2 | ZA | GCI | 4.6 TSSR Approved |  | 2024-01-16 |  |  |  | 2024-02-05 |  | 2024-02-06 | 2024-10-01 | CD//Affendi | 2024-02-07 | Celcom Digi_RAN-GCI-TSS-Northern-20240202-0093/0612Northern-GCI-BOQ Template (template) | DU00002863169 |  |  |  |  | 2024-07-04 |  | TOWER
A00540 | A044A_A00540OD_BOTAKANAN_RDC | Northern |  | Decomm |  | 2024 Q2 | ZA | GTSB | 4.6 TSSR Approved |  | 2024-01-29 |  |  |  | 2024-02-02 |  | 2024-02-06 | 2024-04-23 | CD//Affendi | 2024-02-06 | Celcom Digi_RAN-GTSB-TSS-Northern-20240202-0090 | DU00002863170 |  |  |  |  | 2024-06-21 |  | #N/A
A01057 | A039B_A01057OD_CB_SGSEMAMBU | Northern |  | Decomm |  | 2024 | SM | GTSB | 4.6 TSSR Approved |  | 2023-12-27 |  |  |  | 2023-12-29 |  | 2024-01-03 | 2024-01-22 | CD//Affendi | 2024-01-05 | Celcom Digi_RAN-GTSB-TSS-Northern-20231229-0081 | DU00002863171 |  |  |  |  | 2024-12-06 |  | TOWER
A00391 | A039B_A00391OD_CB_MASJIDTINGGI | Northern |  | Decomm |  | 2024 Q4 | SH | GTSB | 4.6 TSSR Approved |  | 2023-12-27 |  |  |  | 2024-01-22 |  | 2024-09-12 | 2025-10-01 | CD//Zulakmar | 2024-09-18 | Celcom Digi_RAN-GTSB-TSS-Northern-20231229-0081 | DU00002863172 |  |  |  |  | 2024-11-16 |  | TOWER
A00177 | A039B_A00177OD_KGKERETAPI_RCC | Northern |  | Decomm |  | 2025 Q1 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-11-29 |  |  |  | 2023-12-21 |  | 2023-12-28 | 2024-01-22 | CD//Affendi | 2023-12-28 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231130-0074//SQ202501030037 | DU00002863173 |  |  |  |  | 2025-05-21 |  | TOWER
A00746 | A039B_A00746OD_CB_KUALAKURAUTOWN_RDD | Northern |  | Decomm |  | 2024 | SHA | GCI | 4.6 TSSR Approved |  | 2023-12-21 |  |  |  | 2024-01-02 |  | 2024-11-15 | 2025-07-25 | CD//Zulakmar | 2024-11-18 | Celcom Digi_RAN-GCI-TSS-Northern-20231225-0085/Celcom Digi_RAN-GCI-TSS-Northern-20240130-0092 | DU00002863174 |  |  |  |  | 2024-11-22 |  | TOWER
A00051 | A039B_A00051OD_KUALAKURAU | Northern |  | Decomm |  | 2024 Additional | SM | CCSMY | 4.6 TSSR Approved |  | 2023-11-30 |  |  |  | 2023-12-18 |  | 2023-12-20 | 2024-01-22 | CD//Affendi | 2023-12-26 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231201-0075 | DU00002863175 |  |  |  |  | 2025-01-24 |  | TOWER
A00559 | A042C_A00559OD_JLNBKTGANTANG_RCC | Northern |  | Decomm |  | 2024 Q2 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-11-19 |  |  |  | 2023-11-21 |  | 2023-11-22 | 2024-02-15 | CD//Affendi | 2023-12-01 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231122-0072 | DU00002863176 |  |  |  |  | 2024-04-29 |  | TOWER
A00115 | A040B_A00115OD_WKOTAMAS | Northern |  | Decomm |  | 2024 Q2 | ZA | GCI | 4.6 TSSR Approved |  | 2023-10-17 |  |  |  | 2023-10-25 |  | 2023-10-26 | 2024-05-10 | CD//Affendi | 2023-10-27 | Celcom Digi_RAN-GCI-TSS-Northern-20231019-0062/GCI Northern TX TSS | DU00002863177 |  | Missing TX info and photo |  |  | 2024-03-21 |  | BOOM
A00214 | A038A_A00214OD_KGJELINTOH_RDD | Northern |  | Decomm |  | 2024 Q4 | HW | CCSMY | 4.6 TSSR Approved |  | 2024-10-10 |  | 2024-10-23 |  | 2025-04-09 |  | 2025-04-27 |  | CD//Zulakmar | 2025-04-30 | 0927CD-Northern-CCSMY-BOQ Template(new contract) | DU00002863178 |  | Missing IDU photo (NE) |  |  | 2024-10-29 |  | TOWER
A00311 | A038A_A00311OD_TMGOPENG | Northern |  | Decomm |  | 2024 Q3(single site MOCN) | BY | GTSB | 4.6 TSSR Approved |  | 2024-07-22 |  | 2024-07-14 |  | 2024-07-23 |  | 2024-07-24 | 2024-10-01 | CD//Zulakmar | 2024-07-24 | 0725Northern-GTSB-BOQ Template(new contract)/0725Northen-GTSB-BOQ Template(new contract) | DU00002863179 |  |  |  |  | 2024-08-22 |  | TOWER
A00259 | A040D_A00259OD_KM293SPGPULAI_RCD | Northern |  | Decomm |  | 2024 Q4 | SM | GTSB | 4.6 TSSR Approved |  | 2024-02-20 |  |  |  | 2024-02-20 |  | 2024-09-27 | 2024-10-01 | CD//Zulakmar | 2024-09-30 | Celcom Digi_RAN-GTSB-TSS-Northern-20240221-0092 | DU00002863180 |  |  |  |  | 2025-10-29 |  | 45m 3-Legged Tower Pipe Leg
A00290 | A040D_A00290OD_JLNPPUTEH | Northern |  | Decomm |  | 2024 Q2 | SM | Magicell | 4.6 TSSR Approved |  | 2023-12-19 |  |  |  | 2023-12-19 |  | 2023-12-20 | 2024-02-29 | CD//Affendi | 2023-12-26 | Celcom Digi_RAN-Magicell-TSS-Northern-20240124-0012/Celcom Digi_RAN-Magicell-TSS-Northern-20231225-0006 | DU00002863181 |  |  |  |  | 2024-03-20 |  | BOOM
A00102 | A040D_A00102OD_PASIRPUTEHIPOH_RCC | Northern |  | Decomm |  | 2024 Q2 | BY | GTSB | 4.6 TSSR Approved |  | 2023-12-03 |  |  |  | 2023-12-12 |  | 2023-12-13 | 2024-05-24 | CD//Affendi | 2023-12-14 | Celcom Digi_RAN-GTSB-TSS-Northern-20231204-0071 | DU00002863182 |  | IDU Missing Label |  |  | 2024-06-04 |  | BOOM
A00099 | A040C_A00099OD_SILIBIN_RCC | Northern |  | Decomm |  | 2024 Q2 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-11-21 |  |  |  | 2023-11-22 |  | 2023-11-24 | 2024-06-07 | CD//Affendi | 2023-12-05 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231122-0072 | DU00002863183 |  | missing Digi Cabinet/Rack for dismantle, please recheck drawing as wrong possition cabinet xC & xD |  |  | 2024-06-10 |  | TOWER
A00260 | A038A_A00260OD_KGJAHANG_RCD | Northern |  | Decomm |  | 2024 Additional | HW | GCI | 4.6 TSSR Approved |  | 2025-05-05 |  | 2025-05-08 |  | 2025-05-12 |  | 2025-05-14 | 2025-10-28 | E//Hazida | 2025-05-20 | SQ202502100378 | DU00002863184 |  |  |  |  | 2025-05-19 |  | TOWER
A00313 | A038A_A00313OD_TMKAMPAR | Northern |  | Decomm |  | 2024 Q4 |  | CCSMY | 15.3 Decomm Done without TSSR | 8/8- Unsafe for TSS, beehive.// 6/8 - TM site, access pending, raise up to SA to prioritize | [5 empty] | To be Submitted |  |  | CD//Zulakmar |  | 0927CD-Northern-CCSMY-BOQ Template(new contract) | DU00002863185 |  |  |  |  | 2025-11-28 |  | TOWER
A00334 | A044A_A00334OD_TMSBRGPERAK | Northern |  | Decomm |  | 2024 Q2 | BY | GTSB | 4.6 TSSR Approved |  | 2024-03-06 |  |  |  | 2024-03-07 |  | 2024-03-08 | 2024-03-13 | CD//Affendi | 2024-03-11 | Celcom Digi_RAN-GTSB-TSS-Northern-20240310-0096 | DU00002863186 |  |  |  |  | 2024-06-28 |  | TOWER
A00340 | A044A_A00340OD_UITMKGGAJAH | Northern |  | Decomm |  | 2024 Q2 | BY | GCI | 4.6 TSSR Approved |  | 2024-03-22 |  |  |  | 2024-04-08 |  | 2024-04-15 | 2024-07-19 | CD//Affendi | 2024-04-19 | Celcom Digi_RAN-GCI-TSS-Northern-20240325-0103/0612Northern-GCI-BOQ Template (template) | DU00002863187 |  | 1)Missing Font in drawing, 2)Missing FE info |  |  | 2024-06-04 |  | TOWER
A00018 | A044A_A00018OD_TELUKSAREH_RDD | Northern |  | Decomm |  | 2024 Q2 | SM | GCI | 4.6 TSSR Approved |  | 2024-01-21 |  |  |  | 2024-01-29 |  | 2024-01-30 | 2024-03-13 | CD//Affendi | 2024-02-07 | Celcom Digi_RAN-GCI-TSS-Northern-20240124-0090/0612Northern-GCI-BOQ Template (template) | DU00002863188 |  |  |  |  | 2024-05-23 |  | TOWER
A00096 | A044A_A00096OD_KGGAJAH_PRK | Northern |  | Decomm |  | 2024 Q2 | ZA | CCSMY | 4.6 TSSR Approved |  | 2024-01-14 |  |  |  | 2024-01-18 |  | 2024-01-24 | 2024-06-19 | CD//Affendi | 2024-01-30 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240114-0086 | DU00002863189 |  | Please include all TX equipment |  |  | 2024-04-19 |  | TOWER
A00383 | A038A_A00383OD_UTARKAMPAR | Northern |  | Decomm |  | 2024 Q3(single site MOCN) | SM | CCSMY | 4.6 TSSR Approved | ¦ 0918 - CCS: Pending TSS FE | 2024-09-08 |  | 2024-09-18 |  | 2024-10-24 |  | 2024-11-14 |  | CD//Zulakmar | 2024-11-18 | 0809MW-Northern-CCSMY-BOQ Template(new contract)/0809CD-Northern-CCSMY-BOQ Template(new contract) | DU00002863190 |  | Missing Celcom Cabinet for relocation |  |  | 2024-10-29 |  | TOWER
A00488 | A038A_A00488OD_TMNKAMPARPERDANA | Northern |  | Decomm |  | 2024 Additional | SM | NR services | 4.6 TSSR Approved |  | 2024-12-03 |  | 2025-01-03 | 2025-10-16 | 2025-01-06 | Under Approval | 2025-01-20 |  | CD//Zulakmar | 2025-02-26 | SQ202501070548-NR (RAN+MW) | DU00002863191 |  | Missing FE Part |  |  | 2025-01-27 |  | TOWER
A00069 | A041A_A00069OD_LAPTALANG_RDD | Northern |  | Decomm |  | 2024 Q4 | SM | GCI | 4.6 TSSR Approved |  | 2023-12-20 |  |  |  | 2023-12-28 |  | 2024-01-02 | 2025-07-29 | CD//Affendi | 2024-01-02 | Celcom Digi_RAN-GCI-TSS-Northern-20231225-0085/Celcom Digi_RAN-GCI-TSS-Northern-20240130-0092 | DU00002863192 |  |  |  |  | 2024-09-19 |  | TOWER
A00390 | A039B_A00390OD_CB_SGGEDUNG | Northern |  | Decomm |  | 2024 Q4 | SM | GTSB | 4.6 TSSR Approved |  | 2024-11-14 |  | 2024-10-18 |  | 2024-11-25 |  | 2024-11-27 | 2025-07-29 | CD//Zulakmar | 2024-12-05 | 0927CD-Northern-GTSB-BOQ Template(new contract)/0927MW-Northern-GTSB-BOQ Template(new contract) | DU00002863193 |  |  |  |  | 2024-11-26 |  | TOWER
A00675 | A039A_A00675OD_CB_TGPIANDANG | Northern |  | Decomm |  | 2024 Q4 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-11-28 |  |  |  | 2023-12-18 |  | 2023-12-21 | 2024-01-22 | CD//Affendi | 2023-12-26 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231130-0074 | DU00002863194 |  |  |  |  | 2024-10-21 |  | #N/A
A00216 | A039B_A00216OD_MATANGGERDU_RDD | Northern |  | Decomm |  | 2024 Q4 | MS | GTSB | 4.6 TSSR Approved | ¦ 0910 - Pending ZTE revise, MS | 2023-12-27 |  |  |  | 2024-01-02 |  | 2024-09-11 | 2024-10-01 | CD//Zulakmar | 2024-09-27 | Celcom Digi_RAN-GTSB-TSS-Northern-20231229-0081 | DU00002863195 |  |  |  |  | 2024-09-25 |  | TOWER
A00119 | A039A_A00119OD_CB_BAGANTIANG_RCD | Northern |  | Decomm |  | 2024 Q3(single site MOCN) | SM | GCI | 4.6 TSSR Approved |  | 2023-12-23 |  |  |  | 2024-01-03 |  | 2024-05-20 | 2024-10-01 | CD//Affendi | 2024-05-27 | Celcom Digi_RAN-GCI-TSS-Northern-20231225-0085/Celcom Digi_RAN-GCI-TSS-Northern-20240130-0092 | DU00002863196 |  |  |  |  | 2024-08-30 |  | TOWER
A00042 | A039A_A00042OD_CB_TITISERONG_RCC | Northern |  | Decomm |  | 2024 Q4 | MS | GCI | 4.6 TSSR Approved |  | 2023-12-23 |  |  |  | 2024-01-04 |  | 2024-09-11 | 2024-10-01 | CD//Zulakmar | 2024-09-13 | Celcom Digi_RAN-GCI-TSS-Northern-20231225-0085/Celcom Digi_RAN-GCI-TSS-Northern-20240130-0092 | DU00002863197 |  | 1) Please include cabinet digi for relocate IDU NT06152, 2) IDU RTN910 missing Label, 3)Please update drawing to show location Cabinet Digi |  |  | 2024-10-25 |  | TOWER
A00136 | A039B_A00136OD_CB_KUALAGULA_RDD | Northern |  | Decomm |  | 2025 Q1 | SM | GTSB | 4.6 TSSR Approved | 0123 - CD Zul: TSSR is ok. However, lets wait for the pair site to be implemented first before I approve this tssr. | 2023-12-28 |  |  |  | 2024-01-02 |  | 2025-01-09 | 2025-07-29 | CD//Zulakmar | 2025-03-03 | Celcom Digi_RAN-GTSB-TSS-Northern-20231229-0081//SQ202501030229 - gtsb | DU00002863198 |  | CD Hazwan reviewed but Hold wait for upg tssr ready first |  |  | 2025-06-03 |  | TOWER
A00080 | A036B_A00080OD_SLIMRIVER | Northern |  | Decomm |  | 2024 Q3(single site MOCN) | BY | YPTT | 4.6 TSSR Approved | ¦ 0705 - CD Affendi: TSSR approved. Thank you ¦ 0704 - Replied with RF justification ¦ 0527 - CD Affendi:Any additional sector 4411A to cover existing S1 A00080 after decomm. | 2024-02-13 |  |  |  | 2024-02-13 |  | 2024-05-20 | 2024-10-01 | CD//Affendi | 2024-07-05 | Celcom Digi_RAN-YPTT-TSS-Northern-20240215-0060_reraise 21/6 | DU00002863199 |  |  |  |  | 2024-08-09 |  | TOWER
A00336 | A036B_A00336OD_BEHRANG_HOTSITE | Northern |  | Decomm | Decomm->On Hold | 2024 Additional | SHA | YPTT | 15.4 Decomm Done without TSSR Approval |  | 2024-02-14 |  |  |  | 2024-02-14 | To be Submitted | 2024-12-17 |  | CD//Zulakmar |  | Celcom Digi_RAN-YPTT-TSS-Northern-20240215-0060_reraise 21/6 | DU00002863200 |  | Include Clear photo for ID label for each IDU to our planner identify activity -some photo IDU missing |  |  | 2025-09-11 |  | TOWER
A00077 | A036B_A00077OD_SUNGKAI | Northern |  | Decomm | Decomm->On Hold->Decomm | 2024 Q3(single site MOCN) | HW | Magicell | 4.6 TSSR Approved |  | 2023-12-13 |  |  |  | 2023-11-20 | To be Submitted | 2025-04-13 |  | CD//Zulakmar | 2025-04-17 | SQ202504220372 | DU00002863201 |  |  |  |  | 2025-04-22 |  | TOWER
7583A | Gua Gomantong | Sabah |  | Modernization |  | 2024 Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2024-07-24 | 2024-08-10 |  | 2024-08-14 |  | Closed | 2024-08-15 | 2024-08-21 | E//Hannah | 2024-08-21 | 0725Sabah-GTSB-BOQ Template(new contract) | DU00002863202 |  |  | 2024-09-13 | 2024-08-27 |  | Tower | Tower | 75m | Reuse exsiting RRU | 0 | 0
A00500 | A036B_A00500OD_CB_CHANGKATSULAIMAN | Northern |  | Decomm |  | 2024 Additional | SHA | CCSMY | 4.6 TSSR Approved |  | 2024-01-24 |  | 2025-10-30 |  | 2024-02-01 |  | 2024-11-20 | 2026-01-21 | CD//Zulakmar | 2026-03-31 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240124-0089 | DU00002863203 |  |  |  |  | 2025-01-15 |  | TOWER
A00263 | A036B_A00263OD_KM356BIKAM | Northern |  | Decomm |  | 2025 Q1 | SHA | Magicell | 4.6 TSSR Approved |  | 2024-01-05 |  |  |  | 2024-01-11 |  | 2025-01-06 | 2025-03-26 | CD//Zulakmar | 2025-03-03 | Celcom Digi_RAN-Magicell-TSS-Northern-20240114-0010//SQ202501030105 - Magicell | DU00002863204 |  | CD Hazwan reviewed but Hold wait for upg tssr ready first |  |  | 2025-07-04 |  | TOWER
A00211 | A041A_A00211OD_RNRSGPERAK_RDD | Northern |  | Decomm |  | 2025 Q3 | BY | GTSB | 4.6 TSSR Approved |  | 2023-12-20 |  |  |  | 2023-12-26 |  | 2023-12-28 | 2024-10-16 | CD//Affendi | 2023-12-28 | Celcom Digi_RAN-GTSB-TSS-Northern-20231225-0080SQ202501030229 - gtsb | DU00002863205 |  |  |  |  | 2025-09-18 |  | TOWER
A00019 | A039A_A00019OD_CB_BT5PARITBUNTAR_RCD | Northern |  | Decomm |  | 2024 Q4 | SH | GCI | 4.6 TSSR Approved | ¦ 1001 - Replied to Zul anntenna relocateion will be done upon CR, requesting to approved decomm TSSR. ¦ 0918 - CD Zul: Propose to relocate 4423A antenna height from 46m to 52m (A00019 antenna height position) | 2023-12-23 |  |  |  | 2024-01-05 |  | 2024-09-12 | 2024-10-03 | CD//Zulakmar | 2024-10-02 | Celcom Digi_RAN-GCI-TSS-Northern-20231225-0085/Celcom Digi_RAN-GCI-TSS-Northern-20240130-0092 | DU00002863206 |  |  |  |  | 2024-09-27 |  | TOWER
A00596 | A039B_A00596OD_GNGSEMANGGOL | Northern |  | Decomm |  | 2025 Q1 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-11-28 |  |  |  | 2023-12-15 |  | 2023-12-21 | 2024-01-22 | CD//Affendi | 2023-12-26 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231130-0074//SQ202501030037 | DU00002863207 |  |  |  |  | 2025-04-23 |  | TOWER
A00562 | A039B_A00562OD_CB_KGSGPEROTANG9_RCC | Northern |  | Decomm |  | 2024 Q3(single site MOCN) | BY | Magicell | 4.6 TSSR Approved |  | 2024-01-04 |  |  |  | 2024-01-08 |  | 2024-06-27 | 2024-10-01 | CD//Affendi | 2024-07-01 | Celcom Digi_RAN-Magicell-TSS-Northern-20240108-0008 | DU00002863208 |  |  |  |  | 2024-09-04 |  | TOWER
A00157 | A041A_A00157OD_BKTCHANDAN | Northern |  | Decomm | Decomm->On Hold->Decomm | 2024 Q3(single site MOCN) | BY | GTSB | 4.6 TSSR Approved |  | 2023-12-12 |  |  |  | 2023-12-12 |  | 2023-12-13 | 2025-10-01 | CD//Affendi | 2023-12-14 | Celcom Digi_RAN-GTSB-TSS-Northern-20231213-0076 | DU00002863209 |  | Have 17x IDU Extra |  |  | 2024-08-14 |  | TOWER
A01031 | A041A_A01031OD_JLNRAJAIDRISKK | Northern |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4 | BY | GTSB | 4.6 TSSR Approved |  | 2023-12-20 |  |  |  | 2023-12-27 |  | 2023-12-28 | 2024-01-22 | CD//Affendi | 2023-12-28 | Celcom Digi_RAN-GTSB-TSS-Northern-20231225-0080 | DU00002863210 |  |  |  |  | 2024-11-12 |  | RAPOLE
A00331 | A036A_A00331OD_TMTAPAHW900 | Northern |  | Decomm |  | 2024 Q4 | SH | GCI | 4.6 TSSR Approved |  | 2024-01-11 |  |  |  | 2024-01-12 |  | 2024-09-12 | 2024-10-01 | CD//Zulakmar | 2024-09-18 | Celcom Digi_RAN-GCI-TSS-Northern-20240116-0089 | DU00002863211 |  |  |  |  | 2024-10-25 |  | BOOM
A00076 | TAPAH | Northern |  | Decomm |  | 2024 Q4 | BY | GTSB | 4.6 TSSR Approved |  | 2023-11-30 |  |  |  | 2023-12-13 |  | 2023-12-14 | 2025-07-29 | CD//Affendi | 2023-12-15 | Celcom Digi_RAN-GTSB-TSS-Northern-20231201-0070/Celcom Digi_RAN-GTSB-TSS Decomm-Northern-20240305-0096 | DU00002863212 |  |  |  |  | 2024-09-19 |  | TOWER
A00326 | RNRTAPAH_4G | Northern |  | Decomm | Decomm->On Hold->Decomm | 2024 Additional | HW | CCSMY | 4.6 TSSR Approved |  | 2024-01-23 |  |  |  | 2024-01-26 |  | 2025-02-23 | 2025-07-29 | CD//Hazwan | 2025-02-28 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240124-0089 | DU00002863213 |  |  |  |  | 2025-06-03 |  | TOWER
A00238 | A042B_A00238OD_TMTPG | Northern |  | Decomm |  | 2024 Q2 | ZA | GTSB | 4.6 TSSR Approved |  | 2024-01-19 |  |  |  | 2024-01-22 |  | 2024-01-24 | 2024-04-23 | CD//Affendi | 2024-01-30 | Celcom Digi_RAN-GTSB-TSS-Northern-20240124-0088 | DU00002863214 |  |  |  |  | 2024-08-02 |  | MINI STRUCTURE
A00179 | A042C_A00179OD_BKTBERAPIT_RCC | Northern |  | Decomm |  | 2024 Q2 | BY | GTSB | 4.6 TSSR Approved |  | 2023-12-18 |  |  |  | 2024-01-12 |  | 2024-01-18 | 2024-05-10 | CD//Affendi | 2024-01-19 | Celcom Digi_RAN-GTSB-TSS-Northern-20231219-0078 | DU00002863215 |  | Missing xC OB FIBER Equipment |  |  | 2024-07-23 |  | TOWER
A00127 | A042C_A00127OD_CB_COP_RCC | Northern |  | Decomm |  | 2024 Q2 | BY | GTSB | 4.6 TSSR Approved |  | 2023-12-18 |  |  |  | 2024-01-02 |  | 2024-01-05 | 2024-05-10 | CD//Affendi | 2024-01-09 | Celcom Digi_RAN-GTSB-TSS-Northern-20231219-0078 | DU00002863216 |  | Please Confirm Digi using cabinet inside cabin 18/4: Missing equipment Celcom IDU |  |  | 2024-07-25 |  | TOWER
A00234 | A045A_A00234OD_TMLENGGONG | Northern | 4238P | Swap | Decomm->On Hold->Swap | 2024 Q4 | HW | GTSB | 4.6 TSSR Approved |  | 2025-04-03 | 2025-04-10 |  | 2025-04-15 |  | Under Approval | 2025-04-15 | 2025-04-24 | CD//Zulakmar | 2025-04-23 | Celcom Digi_RAN-GTSB-TSS-Northern-20241112_New Contract | DU00002863217 | Remarks: Solution TSSR/BOM Changed |  | 2025-08-06 | 2025-07-19 |  | Tower | TOWER | 120m | Add R8852E S9000x3+R8894E M1821x3+R8862A S2601x3, Dismantle | 0 | 0
A00134 | A042A_A00134OD_SELAMA_RCC | Northern |  | Decomm |  | 2024 Q3(single site MOCN) | SM | GCI | 4.6 TSSR Approved |  | 2023-11-16 |  |  |  | 2023-11-23 |  | 2023-11-24 | 2025-10-28 | CD//Affendi | 2023-12-05 | Celcom Digi_RAN-GCI-TSS-Northern-20231122-0075/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240529-0109 | DU00002863218 |  |  |  |  | 2024-09-03 |  | TOWER
A00144 | A037B_A00144OD_BGNDATOK2 | Northern |  | Decomm | Decomm->On Hold->Decomm->On Hold->Decomm | 2024 Q4 | BY | GTSB | 4.6 TSSR Approved |  | 2023-11-30 |  |  |  | 2023-12-13 |  | 2023-12-15 | 2025-07-29 | CD//Affendi | 2023-12-15 | Celcom Digi_RAN-GTSB-TSS-Northern-20231201-0070 | DU00002863219 |  |  |  |  | 2024-12-06 |  | TOWER
A00770 | A037A_A00770OD_DURIANSEBATANG_RDC | Northern |  | Decomm |  | 2024 Q4 | BY | GCI | 4.6 TSSR Approved |  | 2023-12-06 |  |  |  | 2023-12-12 |  | 2023-12-13 | 2025-10-28 | CD//Affendi | 2023-12-14 | Celcom Digi_RAN-GCI-TSS-Northern-20231207-0081/Celcom Digi_RAN-GCI-TSS-Northern-20241017_New Contract | DU00002863220 |  |  |  |  | 2024-10-08 |  | TOWER
A00001 | A037B_A00001OD_KGTLKBULOH | Northern |  | Decomm |  | 2024 Q4 | MS | GTSB | 4.6 TSSR Approved | ¦ 1001 - Replied to Zul anntenna relocateion will be done upon CR, requesting to approved decomm TSSR. ¦ 0918 - CD Zul: We are dismantling higher antenna. Pair site 4473A antenna height = 45m. Propose to change 4473A antenna height to A00001 antenna height = 50m. | 2024-01-29 |  |  |  | 2024-02-15 |  | 2024-09-12 | 2024-10-03 | CD//Zulakmar | 2024-10-02 | Celcom Digi_RAN-GTSB-TSS-Northern-20240202-0090 | DU00002863221 |  |  |  |  | 2024-09-30 |  | TOWER
A00172 | A037A_A00172OD_CB_CHIKUS | Northern |  | Decomm |  | 2024 Q4 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-11-23 |  |  |  | 2023-12-06 |  | 2023-12-13 | 2024-01-22 | CD//Affendi | 2023-12-14 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231127-0073 | DU00002863222 |  |  |  |  | 2024-09-30 |  | TOWER
A00187 | A037A_A00187OD_KGBAHAGIA | Northern |  | Decomm |  | 2024 Q4 | SM | GCI | 4.6 TSSR Approved |  | 2023-12-11 |  |  |  | 2023-12-14 |  | 2023-12-18 | 2024-10-01 | CD//Affendi | 2023-12-18 | Celcom Digi_RAN-GCI-TSS-Northern-20231212-0082 | DU00002863223 |  |  |  |  | 2024-09-13 |  | TOWER
A00690 | A037A_A00690OD_JLNSULTANABDULLAH_RDC | Northern |  | Decomm |  | 2024 Q4 | SM | GTSB | 4.6 TSSR Approved |  | 2024-10-25 |  |  |  | 2024-10-25 |  | 2024-11-13 | 2025-07-29 | CD//Zulakmar | 2024-11-18 | 0927CD-Northern-GTSB-BOQ Template(new contract)/0927MW-Northern-GTSB-BOQ Template(new contract) | DU00002863224 |  |  |  |  | 2024-10-14 |  | UNIPOLE
4576B | Perak Hanjoong RDD | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q3 | AD | CCSMY | 4.6 TSSR Approved |  | 2023-11-16 | 2023-11-20 |  | 2025-02-14 |  | Under Approval | 2025-03-12 | 2025-07-16 | E//Hazida | 2025-04-23 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231118-0071 | DU00002863225 | [5 empty] | Tower | 45m 3 Legged Tower | 45m | Reuse Existing RRU | 0 | 0
A00312 | A040B_A00312OD_TMGRAPAT | Northern |  | Decomm |  | 2024 Q2 | BY | GTSB | 4.6 TSSR Approved |  | 2024-01-23 |  |  |  | 2024-01-24 |  | 2024-01-29 | 2024-05-24 | CD//Affendi | 2024-01-30 | Celcom Digi_RAN-GTSB-TSS-Northern-20240124-0088 | DU00002863226 |  |  |  |  | 2024-05-30 |  | BOOM
A00103 | A040B_A00103OD_WISMAPECKHUA | Northern |  | Decomm |  | 2024 Q2 | BY | GCI | 4.6 TSSR Approved |  | 2023-11-10 |  |  |  | 2023-11-16 |  | 2023-11-16 | 2023-12-18 | CD//Affendi | 2023-11-24 | Celcom Digi_RAN-GCI-TSS-Northern-20231115-0074 | DU00002863227 |  |  |  |  | 2024-03-20 |  | BOOM
A00857 | A040B_A00857OD_TMNIPOHJAYA | Northern |  | Decomm |  | 2024 Q2 | SM | Magicell | 4.6 TSSR Approved |  | 2023-11-09 |  |  |  | 2023-11-21 |  | 2023-11-22 | 2024-02-29 | CD//Affendi | 2023-12-01 | Celcom Digi_RAN-Magicell-TSS-Northern-20231115-0003 | DU00002863228 |  |  |  |  | 2024-04-01 |  | BOOM
A00448 | A040D_A00448OD_PINJIMEWAH_RCC | Northern |  | Decomm |  | 2024 Q2 | ZA | Magicell | 4.6 TSSR Approved |  | 2023-12-27 |  |  |  | 2024-01-21 |  | 2024-01-24 | 2024-07-05 | CD//Affendi | 2024-01-30 | BOQ_Celcom Digi_RAN-Magicell-TSS-Northern-20231229-0006_reraise | DU00002863229 |  | Missing Digi Cabinet |  |  | 2024-04-16 |  | TOWER
B00392 | B061K_B00392OD_PR_TMPCHG | Central |  | Decomm |  | 2024 Q3 | AD | Magicell | 15.4 Decomm Done without TSSR Approval |  | 2024-04-01 |  |  |  | 2024-04-18 |  | 2024-04-24 |  | CD//Sapian |  | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240407 | DU00002863230 |  | MISSING FE PART |  |  | 2024-09-29 |  | TOWER
A00089 | A040D_A00089OD_PERAKXCHANGE | Northern |  | Decomm |  | 2024 Q2 | BY | GTSB | 4.6 TSSR Approved |  | 2023-12-08 |  |  |  | 2023-12-12 |  | 2023-12-14 |  | CD//Affendi | 2024-01-30 | Celcom Digi_RAN-GTSB-TSS-Northern-20231212-0075 | DU00002863231 |  | Mising Celcom equipment, CISCO ROUTER |  |  | 2025-09-26 |  | TOWER
A00593 | A040B_A00593OD_BDRSERIBOTANI | Northern |  | Decomm |  | 2024 Q2 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-11-29 |  |  |  | 2023-12-18 |  | 2023-12-21 | 2024-01-22 | CD//Affendi | 2023-12-26 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231130-0074 | DU00002863232 |  | Please include 1xIDU Photo with label |  |  | 2024-04-02 |  | TOWER
A00337 | A040D_A00337OD_PASABENA_RCD | Northern |  | Decomm |  | 2024 Q2 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-11-27 |  |  |  | 2023-12-13 |  | 2023-12-15 | 2024-01-22 | CD//Affendi | 2023-12-15 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231130-0074 | DU00002863233 |  |  |  |  | 2024-06-11 |  | BOOM
A00682 | A040D_A00682OD_SPGPULAISHOPLOT_RDD | Northern |  | Decomm |  | 2024 Q2 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-11-24 |  |  |  | 2023-12-08 |  | 2023-12-14 | 2024-01-22 | CD//Shamsul | 2023-12-15 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231127-0073 | DU00002863234 |  |  |  |  | 2024-04-30 |  | #N/A
A00672 | A040B_A00672OD_JLNPANGLIMA_RDD | Northern |  | Decomm |  | 2024 Q2 | SM | YPTT | 4.6 TSSR Approved |  | 2024-01-15 |  |  |  | 2024-01-19 |  | 2024-01-29 | 2024-02-16 | CD//Shamsul | 2024-01-31 | Celcom Digi_RAN-YPTT-TSS-Northern-20240117-0055 | DU00002863235 |  |  |  |  | 2024-03-07 |  | #N/A
A00742 | A040B_A00742OD_IIOM_RDD | Northern |  | Decomm |  | 2024 Q2 | BY | GCI | 4.6 TSSR Approved |  | 2023-12-14 |  |  |  | 2023-12-19 |  | 2023-12-28 | 2024-06-19 | CD//Shamsul | 2023-12-29 | Celcom Digi_RAN-GCI-TSS-Northern-20231225-0085/Celcom Digi_RAN-GCI-TSS-Northern-20240130-0092 | DU00002863236 |  |  |  |  | 2024-05-31 |  | SHARING STRC DIGI
A00208 | A040B_A00208OD_MEDANGOPENG | Northern |  | Decomm |  | 2024 Q2 | ZA | YPTT | 4.6 TSSR Approved |  | 2024-01-22 |  |  |  | 2024-01-23 |  | 2024-01-29 | 2024-02-16 | CD//Shamsul | 2024-01-31 | Celcom Digi_RAN-YPTT-TSS-Northern-20240124-0056 | DU00002863237 |  |  |  |  | 2024-07-11 |  | TOWER
A01048 | A040D_A01048OD_BDRLAHATBARU | Northern |  | Decomm |  | 2024 Q2 | ZA | CCSMY | 4.6 TSSR Approved |  | 2024-01-21 |  |  |  | 2024-01-22 |  | 2024-01-24 | 2024-02-15 | CD//Shamsul | 2024-01-26 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240124-0089 | DU00002863238 |  |  |  |  | 2024-04-29 |  | MINARET
A00293 | A040B_A00293OD_TMIPOH | Northern |  | Decomm |  | 2024 Q2 | ZA | GTSB | 4.6 TSSR Approved |  | 2024-01-21 |  |  |  | 2024-01-24 |  | 2024-01-29 | 2024-02-15 | CD//Shamsul | 2024-01-31 | Celcom Digi_RAN-GTSB-TSS-Northern-20240124-0088 | DU00002863239 |  | missing Leaseline equipment & TM equipment |  |  | 2024-07-30 |  | TOWER
A00752 | A040D_A00752OD_MENGLEMBUTIMUR_RDD | Northern |  | Decomm |  | 2024 Q2 | ZA | GTSB | 4.6 TSSR Approved |  | 2024-03-03 |  |  |  | 2024-03-04 |  | 2024-03-06 | 2024-03-13 | CD//Shamsul | 2024-03-07 | Celcom Digi_RAN-GTSB-TSS-Northern-20240303-0095 | DU00002863240 |  |  |  |  | 2024-07-10 |  | TOWER
2494A | Damansara Ara | Central |  | Site Out (Modernization) | Modernization->On hold->Site out->Site Out (Modernization) | 2024 Q1 | AI | GTSB | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2025-07-15 |  | 2025-06-30 |  |  | To be Submitted |  |  |  |  | SQ202506170074 | DU00002863241 |  |  |  |  | 2025-08-05 |  | 3m Bipod (RT)
A00320 | A040D_A00320OD_TMMENGLEMBU | Northern |  | Decomm | Decomm->On Hold->Decomm | 2024 Q2 | BY | CCSMY | 4.6 TSSR Approved |  | 2024-01-09 |  |  |  | 2024-01-15 |  | 2024-01-18 | 2024-02-15 | CD//Shamsul | 2024-01-19 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240110-0085/0709MW-Northern-CCSMY-BOQ Template | DU00002863242 |  |  |  |  | 2024-08-09 |  | BOOM
A00261 | A040D_A00261OD_PINJIPERDANA | Northern |  | Decomm |  | 2024 Q2 | BY | GTSB | 4.6 TSSR Approved |  | 2023-12-07 |  |  |  | 2023-12-07 |  | 2023-12-14 | 2024-01-22 | CD//Shamsul | 2023-12-15 | Celcom Digi_RAN-GTSB-TSS-Northern-20231207-0073 | DU00002863243 |  |  |  |  | 2024-05-31 |  | TOWER
A00328 | A036A_A00328OD_TMCKTREMBIAN | Northern | 4639K | Swap | Decomm->On Hold->Swap | 2025 Q1 | HW | GCI | 4.6 TSSR Approved |  | 2023-12-28 | 2025-05-27 |  | 2025-06-16 | 2024-01-03 | Under Approval | 2025-06-17 | 2025-09-26 | E//Hazida | 2025-06-23 | Celcom Digi_RAN-GCI-TSS-Northern-20240108-0088 | DU00002863244 | 22/5/2025: SOW Changed from On Hold to Modernization 18/11/24: SOW Changed Decomm to OnHold |  | 2025-09-09 | 2025-08-23 |  | Portables BTS | BOOM | 19m | Add R8862A S9000x3+R8894E M1821x5+R8862A S2601x1+R8854 S2600x2, Dismantle | 0 | 12
A00262 | A036A_A00262OD_KM334BIDOR | Northern | 4632K | Swap | Decomm->On Hold->Swap | 2024 Additional | HW | CCSMY | 4.6 TSSR Approved |  | 2024-02-01 | 2025-03-17 |  | 2025-03-21 | 2024-02-02 | Under Approval | 2025-03-25 | 2025-03-26 | CD//Shamsul | 2025-03-26 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240202-0091 | DU00002863245 |  |  | 2025-05-19 | 2025-05-16 |  | Tower | TOWER | 76M | Add R8852E S9000x3+R8894E M1821x4, Dismantle | 0 | 3
A00185 | A037B_A00185OD_BT10HTNMLTG | Northern |  | Decomm |  | 2025 Q1 | HW | GTSB | 4.6 TSSR Approved |  | 2025-01-18 |  | 2025-01-27 |  | 2025-02-20 |  | 2025-02-21 |  | CD//Hazwan | 2025-02-26 | SQ202501060259 - GTSB | DU00002863246 |  |  |  |  | 2025-03-11 |  | TOWER
A00239 | A042D_A00239OD_TMTRONG | Northern | 4613K | Swap | Decomm->On Hold-Swap | 2024 Q2 | AI | CCSMY | 4.6 TSSR Approved | ¦ 0809 - Changed anchor, SOW changed to SWAP ¦ 0313 - SOW changed to On Hold ¦15-3- ZTE planner to start study ¦& revert¦ ¦ 0208 - Li Jie: Izzat to inlude this site in change anchor list ¦ 0206 - fup done to Izzat/Khai ¦ 0122 - BY emailed ZTE RF, pending Solution ¦ 0122 - CD Shamsul:Not agreed to decom A00239, because RF antenna higher than site 4581A, and will be more affected on coverage degraded because neighbor site 4256H height only 5m. Proposed change anchor to site A01134. | 2024-01-04 | 2025-03-27 |  | 2025-04-07 | 2024-01-05 | Closed | 2025-04-17 | 2025-04-29 | CD//Zulakmar | 2025-04-28 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240108-0084/0821CD-Northern-CCSMY-BOQ Template(new contract) | DU00002863247 | Remarks: Solution TSSR/BOM Changed |  | 2025-07-06 | 2025-06-10 |  | Tower | TOWER | 76m | Add R8862A S9000x4+R8894E M1821x7,Dismantle | 0 | 123
A00270 | A037A_A00270OD_PDGTEMBAK | Northern |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4 | SM | GCI | 4.6 TSSR Approved |  | 2024-01-08 |  |  |  | 2024-01-26 |  | 2024-11-20 | 2025-07-29 | CD//Zulakmar | 2024-11-25 | Celcom Digi_RAN-GCI-TSS-Northern-20240116-0089 | DU00002863248 |  |  |  |  | 2024-11-29 |  | TOWER
A00317 | A040D_A00317OD_PUSING | Northern |  | Decomm |  | 2024 Q2 | BY | GTSB | 4.6 TSSR Approved |  | 2024-01-26 |  |  |  | 2024-02-02 |  | 2024-02-02 |  | CD//Shamsul | 2024-02-02 | Celcom Digi_RAN-GTSB-TSS-Northern-20240124-0089 | DU00002863249 |  | TSSR reject Pls verify SOW for mw link to A01070 |  |  | 2024-07-19 |  | TOWER
A00043 | A044A_A00043OD_ULUDEDAP | Northern |  | Decomm |  | 2024 Q2 | BY | CCSMY | 4.6 TSSR Approved |  | 2024-02-27 |  |  |  | 2024-03-07 |  | 2024-03-11 | 2024-03-13 | CD//Shamsul | 2024-03-11 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240229-0097 | DU00002863250 |  |  |  |  | 2024-05-15 |  | TOWER
A00160 | A037A_A00160OD_TMNCECILY | Northern |  | Decomm |  | 2024 Q4 | ZA | GCI | 4.6 TSSR Approved |  | 2023-10-19 |  |  |  | 2023-10-25 |  | 2023-10-26 | 2023-12-18 | CD//Shamsul | 2023-10-27 | Celcom Digi_RAN-GCI-TSS-Northern-20231023-0064 | DU00002863251 |  | Missing other TX equipment photo |  |  | 2024-09-30 |  | TRIPOD
A00017 | A044A_A00017OD_FELCRANASARUDDIN_RDC | Northern |  | Decomm |  | 2024 Q2 | ZA | GCI | 4.6 TSSR Approved |  | 2024-01-18 |  |  |  | 2024-01-25 |  | 2024-01-29 | 2024-07-19 | CD//Shamsul | 2024-01-31 | Celcom Digi_RAN-GCI-TSS-Northern-20240124-0090 | DU00002863252 |  |  |  |  | 2024-06-04 |  | TOWER
A00629 | A044A_A00629OD_VILLAGE4_UTP | Northern |  | Decomm |  | 2024 Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2024-08-16 |  | 2024-08-21 |  | 2024-08-30 |  | 2024-09-06 | 2026-03-11 | CD//Zulakmar | 2024-09-10 | 0809MW-Norhtern-GTSB-BOQ Template(new contract)/0809CD-Northern-GTSB-BOQ Template(new contract) | DU00002863253 |  |  |  |  | 2024-10-25 |  | LAMP_POLE
R00084 | R001C_R00084OD_KG_RAMA_PS | Northern |  | Decomm |  | 2024 Q4 | SM | CCSMY | 4.6 TSSR Approved |  | 2024-02-29 |  |  |  | 2024-03-14 |  | 2024-04-29 | 2024-05-06 | CD//Shamsul | 2024-04-30 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240303-0098 | DU00002863254 |  |  |  |  | 2024-06-24 |  | TOWER
R00002 | R001B_R00002OD_KAYANGANSQUARE | Northern |  | Decomm |  | 2024 Q4 | SM | CCSMY | 4.6 TSSR Approved |  | 2024-02-29 |  |  |  | 2024-03-13 |  | 2024-04-25 | 2024-05-06 | CD//Shamsul | 2024-04-26 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240303-0098 | DU00002863255 |  |  |  |  | 2024-06-12 |  | TRIPOD
R00013 | R001A_R00013OD_CIMA | Northern |  | Decomm |  | 2024 Q4 | SM | GCI | 4.6 TSSR Approved |  | 2024-10-07 |  | 2024-10-14 |  | 2024-10-25 |  | 2024-11-13 | 2025-07-29 | CD//Zulakmar | 2024-11-18 | 0927CD-Northern-GCI-BOQ Template(new contract)/0927MW-Northern-GCI-BOQ Template(new contract) | DU00002863256 |  |  |  |  | 2024-11-12 |  | TOWER
R00027 | R001C_R00027OD_MATRIKULASIARAU | Northern |  | Decomm |  | 2024 Q4 | SM | GCI | 4.6 TSSR Approved |  | 2024-03-30 |  |  |  | 2024-04-05 |  | 2024-04-29 | 2024-05-06 | CD//Shamsul | 2024-04-30 | Celcom Digi_RAN-GCI-TSS-Northern-20240512-0106 | DU00002863257 |  | 1)Missing Font in drawing |  |  | 2024-05-28 |  | BOOM
R00006 | R001C_R00006OD_CB_TAMBUNTULANG | Northern |  | Decomm |  | 2024 Q4 | SM | GCI | 4.6 TSSR Approved |  | 2024-03-26 |  |  |  | 2024-04-04 |  | 2024-04-23 | 2024-05-06 | CD//Shamsul | 2024-04-29 | Celcom Digi_RAN-GCI-TSS-Northern-20240512-0106 | DU00002863258 |  | 1)Missing Font in drawing |  |  | 2024-06-11 |  | TOWER
R00012 | R001C_R00012OD_SPG4PERLIS | Northern |  | Decomm |  | 2024 Q4 | SM | GTSB | 4.6 TSSR Approved |  | 2024-02-13 |  |  |  | 2024-02-13 |  | 2024-04-25 | 2024-05-06 | CD//Shamsul | 2024-04-26 | Celcom Digi_RAN-GTSB-TSS-Northern-20240223-0093 | DU00002863259 |  |  |  |  | 2024-07-12 |  | TOWER
R00135 | R001B_R00135OD_SERIAP | Northern |  | Decomm |  | 2024 Q4 | BY | GCI | 4.6 TSSR Approved |  | 2023-11-30 |  |  |  | 2024-03-05 |  | 2024-04-18 | 2024-04-23 | CD//Shamsul | 2024-04-18 | Celcom Digi_RAN-GCI-TSS-Northern-20240310-0100 | DU00002863260 |  |  |  |  | 2024-06-11 |  | TOWER
R00024 | R001B_R00024OD_KANGARKWSP | Northern |  | Decomm |  | 2024 Q4 | SM | GCI | 4.6 TSSR Approved |  | 2024-02-29 |  |  |  | 2024-03-05 |  | 2024-04-23 | 2024-05-24 | CD//Shamsul | 2024-04-29 | Celcom Digi_RAN-GCI-TSS-Northern-20240321-0102 | DU00002863261 |  |  |  |  | 2024-07-15 |  | BOOM
K00274 | K012A_K00274OD_JENIANG2 | Northern |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4 | HW | GCI | 4.6 TSSR Approved |  | 2025-01-21 |  | 2025-02-21 |  | 2025-03-07 |  | 2025-03-11 | 2025-07-29 | CD//Zulakmar | 2025-03-13 | 0927CD-Northern-GCI-BOQ Template(new contract)/0927MW-Northern-GCI-BOQ Template(new contract) | DU00002863262 |  |  |  |  | 2024-11-29 |  | TOWER
K00597 | K012A_K00597OD_PEKANSIK_RDC | Northern |  | Decomm |  | 2024 Q4 | SHA | GCI | 4.6 TSSR Approved |  | 2024-10-15 |  | 2024-10-17 |  | 2024-11-05 |  | 2024-11-14 | 2024-12-02 | CD//Shamsul | 2024-11-18 | 0927CD-Northern-GCI-BOQ Template(new contract)/0927MW-Northern-GCI-BOQ Template(new contract) | DU00002863263 |  |  |  |  | 2024-10-30 |  | TOWER
K00045 | K005D_K00045OD_PADANGLEMBU | Northern |  | Decomm |  | 2025 Q3 | HW | GCI | 4.6 TSSR Approved |  | 2025-05-05 |  | 2025-05-08 |  | 2025-05-13 |  | 2025-05-15 | 2025-10-28 | E//Hazida | 2025-05-23 | SQ202501060244 - GCI | DU00002863264 |  |  |  |  | 2025-05-22 |  | TOWER
K00250 | K002A_K00250OD_TMKUALAKETILTOWN | Northern |  | Decomm | Decomm->On Hold-Decomm | 2024 Q3(single site MOCN) | ZA | GCI | 4.6 TSSR Approved |  | 2023-10-28 |  |  |  | 2023-11-02 |  | 2023-11-06 | 2024-01-22 | CD//Shamsul | 2023-11-08 | Celcom Digi_RAN-GCI-TSS-Northern-20231030-0068 | DU00002863265 |  |  |  |  | 2024-08-27 |  | TOWER
K00025 | K013A_K00025OD_CB_TANJUNGJAGA | Northern |  | Decomm |  | 2024 Q4 | SM | CCSMY | 4.6 TSSR Approved |  | 2024-01-16 |  |  |  | 2024-01-29 |  | 2024-09-30 | 2024-10-03 | CD//Zulakmar | 2024-10-01 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240117-0088 | DU00002863266 |  |  |  |  | 2024-09-25 |  | 90m 4-Legged Tower (Angle Leg)
K00105 | K008A_K00105OD_KILIM | Northern |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4 | HW | CCSMY | 4.6 TSSR Approved |  | 2024-12-19 |  | 2025-01-15 |  | 2025-02-17 |  | 2025-02-18 | 2025-04-14 | CD//Hazwan | 2025-02-24 | 0927CD-Northern-CCSMY-BOQ Template(new contract) | DU00002863267 |  |  |  |  | 2024-12-20 |  | TOWER
K00233 | K008A_K00233OD_PDGSAGA | Northern |  | Decomm |  | 2024 Q4 | SM | CCSMY | 4.6 TSSR Approved |  | 2024-10-09 |  | 2024-11-20 |  | 2024-12-03 |  | 2024-12-06 |  | CD//Zulakmar | 2024-12-12 | 0927CD-Northern-CCSMY-BOQ Template(new contract) | DU00002863268 |  |  |  |  | 2024-10-10 |  | TOWER
K00232 | K008A_K00232OD_LKW_SEAVIEW | Northern |  | Decomm |  | 2024 Q4 | HW | CCSMY | 4.6 TSSR Approved |  | 2024-10-09 |  | 2025-05-14 |  | 2025-05-29 |  | 2025-06-04 |  | CD//Zulakmar | 2025-06-05 | 0927CD-Northern-CCSMY-BOQ Template(new contract) | DU00002863269 |  |  |  |  | 2025-09-06 |  | BOOM
K00581 | K008A_K00581OD_LANGKASUKAHOTEL_RDC | Northern |  | Decomm |  | 2024 Q3(single site MOCN) | SHA | CCSMY | 4.6 TSSR Approved |  | 2024-08-09 |  | 2024-08-13 |  | 2024-08-15 |  | 2024-08-16 | 2024-10-01 | CD//Affendi | 2024-08-21 | 0809CD-Northern-CCSMY-BOQ Template(new contract) | DU00002863270 |  |  |  |  | 2024-11-06 |  | #N/A
K00134 | K008A_K00134OD_GNGNRAYA | Northern |  | Decomm |  | 2025 Q2 | HW | GTSB | 4.6 TSSR Approved |  | 2025-02-02 |  | 2025-02-12 |  | 2025-02-14 |  | 2025-02-18 |  | CD//Hazwan | 2025-02-28 | SQ202501060259 - GTSB | DU00002863271 |  | CD Hazwan reviewed but Hold wait for upg tssr ready first |  |  | 2025-04-30 |  | TOWER
K00583 | K008A_K00583OD_PANTAICENANG_RDC | Northern |  | Decomm |  | 2025 Q2 | HW | GTSB | 4.6 TSSR Approved |  | 2025-03-18 |  | 2025-03-21 |  | 2025-03-24 | To be Submitted | 2025-04-29 |  | CD//Zulakmar | 2025-04-30 | SQ202501060259 - GTSB | DU00002863272 |  |  |  |  | 2025-05-07 |  | TOWER
K00237 | K008A_K00237OD_AIRPORTLKW | Northern |  | Decomm |  | 2024 Q4 | HW | CCSMY | 4.6 TSSR Approved |  | 2025-03-27 |  | 2025-04-23 |  | 2025-05-07 | To be Submitted | 2025-05-08 |  | CD//Zulakmar | 2025-07-15 | 0927CD-Northern-CCSMY-BOQ Template(new contract)/0927MW-Northern-CCSMY-BOQ Template(new contract) | DU00002863273 |  |  |  |  | 2025-08-19 |  | BOOM
K00235 | K008A_K00235OD_TMNSLGKW | Northern |  | Decomm |  | 2024 Q3(single site MOCN) | SM | CCSMY | 4.6 TSSR Approved |  | 2024-08-09 |  | 2024-08-13 |  | 2024-08-14 |  | 2024-08-28 | 2024-10-01 | CD//Zulakmar | 2024-08-29 | 0809CD-Northern-CCSMY-BOQ Template(new contract) | DU00002863274 |  |  |  |  | 2024-10-21 |  | BOOM
K00209 | K008A_K00209OD_HOSPLANGKAWI | Northern |  | Decomm |  | 2025 Q2 |  | GTSB | 1.1 Pending Survey - Subcon | 14/8 - Replan Wk35, Owner not allowed, have issue with CD, GTSB to send email // 6/8 - No plan, no team at island | [5 empty] | To be Submitted |  |  | CD//Zulakmar |  | SQ202501030229 - gtsb | DU00002863275 | [6 empty] | TOWER
K00245 | K008A_K00245OD_TMPDGLALANG | Northern |  | Decomm |  | 2024 Q3(single site MOCN) | HW | CCSMY | 4.6 TSSR Approved | 18/8 - Team will share WNL by today// 14/8-Ptw expired, team no go in, to reapply access 8/8 - team retract, Rollout to reassign // 6/8 - TM site, access pending, raise up to SA to prioritize | 2025-10-07 |  | 2025-10-14 |  | 2025-10-22 | To be Submitted | 2025-10-23 |  | E//Hazida | 2025-10-24 | 0809CD-Northern-CCSMY-BOQ Template(new contract) | DU00002863276 |  |  |  |  | 2025-10-09 |  | TOWER
K00121 | K009A_K00121OD_PADANGTERAP | Northern |  | Decomm |  | 2024 Q4 | HW | GCI | 4.6 TSSR Approved |  | 2025-01-21 |  | 2025-01-03 |  | 2025-02-20 |  | 2025-02-21 | 2025-03-24 | CD//Hazwan | 2025-02-26 | 0927CD-Northern-GCI-BOQ Template(new contract)/0927MW-Northern-GCI-BOQ Template(new contract) | DU00002863277 |  | NE/FE - Missing Tx part (No Mw photo and Info) |  |  | 2024-11-29 |  | TOWER
K00364 | K010A_K00364OD_SGTIANG2 | Northern |  | Decomm |  | 2024 Q4 | SHA | GCI | 4.6 TSSR Approved |  | 2024-10-18 |  | 2024-10-30 |  | 2024-11-04 |  | 2024-11-14 | 2024-12-02 | CD//Shamsul | 2024-11-18 | 0927CD-Northern-GCI-BOQ Template(new contract)/0927MW-Northern-GCI-BOQ Template(new contract) | DU00002863278 |  |  |  |  | 2024-10-28 |  | TOWER
K00211 | K010A_K00211OD_TANAHMERAH | Northern |  | Decomm |  | 2024 Q4 |  | GCI | 4.6 TSSR Approved |  | 2024-10-18 |  | 2024-10-27 |  | 2024-10-30 |  | 2024-11-14 |  | CD//Zulakmar | 2024-11-18 | 0927CD-Northern-GCI-BOQ Template(new contract)/0927MW-Northern-GCI-BOQ Template(new contract) | DU00002863279 |  |  |  |  | 2024-12-02 |  | TOWER
K00163 | K003A_K00163OD_KGRELAU | Northern |  | Decomm | Decomm->On Hold->Decomm | 2025 Q3 | HW | CCSMY | 4.6 TSSR Approved |  | 2025-03-24 |  | 2025-04-03 |  | 2025-04-09 | To be Submitted | 2025-04-27 |  | CD//Zulakmar | 2025-04-30 | SQ202501060201 - CCSMY | DU00002863280 |  |  |  |  | 2025-06-25 |  | TOWER
K00062 | K005D_K00062OD_BT4JENIANG | Northern |  | Decomm |  | 2024 Q4 | SM | GCI | 4.6 TSSR Approved |  | 2024-10-21 |  |  |  | 2024-12-12 |  | 2024-12-13 | 2025-10-28 | CD//Zulakmar | 2024-12-18 | 0927CD-Northern-GCI-BOQ Template(new contract)/0927MW-Northern-GCI-BOQ Template(new contract) | DU00002863281 |  |  |  |  | 2024-10-21 |  | TOWER
4661B | Kolej Guthrie | Northern |  | Modernization |  | 2024 Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2024-04-15 | 2024-04-17 |  | 2024-04-19 |  | Rectificating | 2024-04-19 | 2024-04-22 | E//Hazida | 2024-04-22 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240408-0103 | DU00002863282 |  |  | 2024-04-29 | 2024-04-23 |  | Monopole | 30m Monopole | 30 | Add R8862A S9000 x3+R9224E M1821 x6+R8854 S2600 x3,Dismantle R8862A S2600(A4A) x3+R8892N M1821(BAB) x3 | 0 | 123
9192A | Spaoh Junction(TM-Sacofa) | Sarawak |  | Modernization |  | 2025 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2025-04-11 | 2025-08-08 |  | 2025-08-15 |  | Under Approval | 2025-08-18 | 2025-09-11 | E//John | 2025-08-19 | SQ202502190399-YPTT | DU00002863283 |  |  | 2025-09-10 | 2025-09-08 |  | Tower | 60m 4 Legged Tower | 120 | Reuse Existing RRU | 0 | 0
A00791 | A042B_A00791OD_KGSGTUPAI | Northern |  | Decomm |  | 2024 Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2023-12-18 |  |  |  | 2023-12-30 |  | 2024-01-04 | 2024-04-23 | CD//Shamsul | 2024-01-05 | Celcom Digi_RAN-GTSB-TSS-Northern-20231219-0078 | DU00002863284 |  |  |  |  | 2024-06-11 |  | TOWER
K00167 | K009A_K00167OD_KGTANJUNG | Northern |  | Decomm |  | 2025 Q3 | HW | GCI | 4.6 TSSR Approved |  | 2025-04-15 |  | 2025-04-21 |  | 2025-04-29 |  | 2025-05-02 | 2025-09-18 | CD//Zulakmar | 2025-05-08 | SQ202501060244 - GCI | DU00002863285 |  |  |  |  | 2025-07-18 |  | TOWER
A00542 | A036A_A00542OD_TAPAHROAD_RDC | Northern |  | Decomm |  | 2024 Q4 | BY | GTSB | 4.6 TSSR Approved |  | 2023-11-30 |  |  |  | 2023-12-15 |  | 2023-12-28 | 2024-10-01 | CD//Shamsul | 2023-12-29 | Celcom Digi_RAN-GTSB-TSS-Northern-20231201-0070 | DU00002863286 |  |  |  |  | 2024-09-13 |  | TOWER
3026A | Dataran Ara Damansara | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q1 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002863287 | [6 empty] | 3m Boom (RT) |  |  |  | 34
A00011 | TGBAYAN | Northern |  | Decomm |  | 2024 Q4 | BY | GTSB | 4.6 TSSR Approved |  | 2023-12-07 |  |  |  | 2023-12-07 |  | 2023-12-15 | 2024-01-22 | CD//Shamsul | 2023-12-15 | Celcom Digi_RAN-GTSB-TSS-Northern-20231207-0073 | DU00002863288 |  |  |  |  | 2024-09-30 |  | TOWER
A00518 | A037A_A00518OD_SARANGTIONG | Northern |  | Decomm |  | 2025 Q1 | SHA | GTSB | 4.6 TSSR Approved |  | 2023-12-18 |  |  |  | 2024-01-17 | To be Submitted | 2025-01-06 |  | CD//Zulakmar | 2025-03-03 | Celcom Digi_RAN-GTSB-TSS-Northern-20231219-0078//SQ202501030229 - gtsb | DU00002863289 |  | CD Hazwan reviewed but Hold wait for upg tssr ready first |  |  | 2025-04-29 |  | TOWER
A00335 | A037A_A00335OD_TMTLKINTAN | Northern | 4611K | Swap | Decomm->On Hold->Swap->On Hold->Swap | 2024 Q3(single site MOCN) | BY | GCI | 4.6 TSSR Approved | ¦ 0710 - Scoped changed, pending Survey | 2023-11-01 | 2024-08-08 |  | 2024-08-13 |  | Under Approval | 2024-08-15 | 2024-08-19 | CD//Shamsul | 2024-08-19 | Celcom Digi_RAN-GCI-TSS-Northern-20240310-0100 | DU00002863290 |  |  | 2025-08-30 | 2024-11-26 |  | Tower | TOWER | 76 | Add R8852E S9000 x1+R9264H M901821 x2+R8862A S2601 x1+A9732 M1821 x1,Dismantle | 1 | 0
A00056 | A037B_A00056OD_CB_BGNPASIRLAUT | Northern |  | Decomm |  | 2024 Q4 | BY | GTSB | 4.6 TSSR Approved |  | 2023-12-07 |  |  |  | 2023-12-13 |  | 2023-12-15 | 2024-02-16 | CD//Shamsul | 2023-12-15 | Celcom Digi_RAN-GTSB-TSS-Northern-20231207-0073 | DU00002863291 |  |  |  |  | 2024-09-30 |  | TOWER
A00517 | A037B_A00517OD_CB_LABUKUBONG | Northern |  | Decomm |  | 2025 Q1 | SM | GCI | 4.6 TSSR Approved |  | 2023-10-20 |  |  |  | 2023-11-02 |  | 2023-11-03 | 2024-10-16 | CD//Shamsul | 2023-11-08 | Celcom Digi_RAN-GCI-TSS-Northern-20231025-0065/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240529-0109//SQ202501030261 - GCI | DU00002863292 |  |  |  |  | 2025-04-28 |  | TOWER
A00014 | A037B_A00014OD_PRTNIBONG | Northern |  | Decomm |  | 2024 Q4 | BY | GTSB | 4.6 TSSR Approved |  | 2023-11-30 |  |  |  | 2023-12-15 |  | 2023-12-28 |  | CD//Shamsul | 2023-12-29 | Celcom Digi_RAN-GTSB-TSS-Northern-20231201-0070 | DU00002863293 |  | pls indicate which link to dismantle & relocate as per network topology |  |  | 2024-11-20 |  | TOWER
K00093 | K008A_K00093OD_TGMALAI | Northern |  | Decomm |  | 2025 Q2 | HW | GTSB | 4.6 TSSR Approved |  | 2025-01-26 |  | 2025-02-12 |  | 2025-04-16 | To be Submitted | 2025-04-17 |  | CD//Zulakmar | 2025-04-25 | SQ202501060259 - GTSB | DU00002863294 |  |  |  |  | 2025-04-30 |  | TOWER
A01102 | A042C_A01102OD_CB_JLN_TMN_KAYA_TPG | Northern |  | Decomm |  | 2024 Q2 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-11-26 |  |  |  | 2023-12-13 |  | 2023-12-15 | 2024-01-22 | CD//Shamsul | 2023-12-18 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231127-0073 | DU00002863295 |  |  |  |  | 2024-06-12 |  | MONOPOLE
K00128 | K010A_K00128OD_PENDANG | Northern |  | Decomm |  | 2024 Q4 | AD | GCI | 4.6 TSSR Approved |  | 2024-10-19 |  | 2024-10-23 |  | 2024-12-11 |  | 2024-12-16 |  | CD//Zulakmar | 2024-12-23 | 0927CD-Northern-GCI-BOQ Template(new contract)/0927MW-Northern-GCI-BOQ Template(new contract) | DU00002863296 |  |  |  |  | 2024-10-28 |  | TOWER
K00076 | BKTTEMBAGA | Northern |  | Decomm |  | 2024 Q4 | HW | CCSMY | 4.6 TSSR Approved |  | 2025-01-16 |  | 2025-01-09 |  | 2025-04-09 | To be Submitted | 2025-04-27 |  | CD//Zulakmar | 2025-04-30 | 0927CD-Northern-GCI-BOQ Template(new contract)/0927MW-Northern-GCI-BOQ Template(new contract) | DU00002863297 |  |  |  |  | 2024-10-01 |  | TOWER
R00004 | R001A_R00004OD_PDGBESAR | Northern | 4614K | Swap | Decomm->On Hold-Swap | 2025 Q3 | HW | CCSMY | 4.6 TSSR Approved |  | 2024-01-13 | 2025-05-06 |  | 2025-05-08 | 2024-01-19 | Under Approval | 2025-05-09 | 2025-05-19 | CD//Zulakmar | 2025-05-14 | S1MY2024071004WBF1-1191 | DU00002863298 |  |  | 2025-09-10 | 2025-09-06 |  | Tower | GUYED MAST | 35m | Add R8862A S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle | 0 | 2
K00129 | K013A_K00129OD_BKTBESAR | Northern |  | Decomm |  | 2024 Q4 | SM | GTSB | 4.6 TSSR Approved |  | 2024-01-23 |  |  |  | 2024-01-27 |  | 2024-09-30 | 2024-10-03 | CD//Zulakmar | 2024-10-02 | Celcom Digi_RAN-GTSB-TSS-Northern-20240124-0088 | DU00002863299 |  |  |  |  | 2024-09-30 |  | 75m 4-Legged Tower (Angle Leg)
R00047 | R001C_R00047OD_KGPDGNYU | Northern |  | Decomm |  | 2024 Q4 | BY | GTSB | 4.6 TSSR Approved |  | 2024-02-13 |  |  |  | 2024-02-13 |  | 2024-04-18 | 2024-04-23 | CD//Shamsul | 2024-04-18 | Celcom Digi_RAN-GTSB-TSS-Northern-20240223-0093 | DU00002863300 |  |  |  |  | 2024-06-04 |  | TOWER
R00038 | R001A_R00038OD_CB_KGPDGSIDING | Northern |  | Decomm |  | 2025 Q3 | HW | GCI | 4.6 TSSR Approved |  | 2025-03-26 |  | 2025-03-12 |  | 2025-03-19 |  | 2025-04-25 | 2025-10-28 | CD//Zulakmar | 2025-04-30 | SQ202501030261 - GCI | DU00002863301 |  | No NE/FE TX PART |  |  | 2025-03-20 |  | TOWER
A00521 | FELDABESOUT4 | Northern |  | Decomm |  | 2025 Q1 | SM | GCI | 4.6 TSSR Approved |  | 2023-12-11 |  |  |  | 2023-12-12 |  | 2023-12-18 | 2024-10-16 | CD//Shamsul | 2023-12-20 | Celcom Digi_RAN-GCI-TSS-Northern-20231212-0082//SQ202501030261 - GCI | DU00002863302 |  |  |  |  | 2025-06-30 |  | TOWER
A00504 | AIRHITAMBIDOR | Northern |  | Decomm |  | 2024 Q4 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-11-24 |  |  |  | 2023-12-13 |  | 2023-12-18 | 2024-01-22 | CD//Shamsul | 2023-12-18 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231127-0073 | DU00002863303 |  | Please include photo other 2 IDU |  |  | 2024-10-29 |  | TOWER
A00449 | A045A_A00449OD_CB_KELIANINTAN | Northern |  | Decomm |  | 2024 Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2025-01-15 |  | 2024-11-01 |  | 2025-01-15 |  | 2025-01-17 |  | CD//Zulakmar | 2025-01-28 | Celcom Digi_RAN-GTSB-TSS-Northern-20241017_New Contract | DU00002863304 |  | missing photo -ODF -OB Fiber |  |  | 2024-12-05 |  | TOWER
S00453 | S096A_S00453OD_KUAP | Sabah |  | Decomm |  | 2025 Q3 | HW | GTSB | 4.6 TSSR Approved |  | 2025-02-06 |  | 2025-02-10 |  | 2025-02-24 |  | 2025-02-26 | 2025-09-10 | CD//Sharidah | 2025-03-03 | SQ202501020455 - GTSB | DU00002863305 |  |  |  |  | 2025-04-29 |  | TOWER
K00080 | K002A_K00080OD_CB_MENGKUANGHUJUNG | Northern |  | Decomm |  | 2025 Q2 | AD | CCSMY | 4.6 TSSR Approved |  | 2024-02-14 |  |  |  | 2024-02-14 |  | 2025-01-10 | 2025-07-29 | CD//Zulakmar | 2025-04-17 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240215-0093//SQ202501030037 | DU00002863306 |  |  |  |  | 2025-07-31 |  | TOWER
R00137 | R001C_R00137OD_CB_PADANGKERRIA | Northern |  | Decomm |  | 2024 Q4 | BY | GCI | 4.6 TSSR Approved |  | 2024-03-30 |  |  |  | 2024-04-24 |  | 2024-05-07 | 2024-06-07 | CD//Shamsul | 2024-06-06 | Celcom Digi_RAN-GCI-TSS-Northern-20240512-0106 | DU00002863307 |  |  |  |  | 2024-06-06 |  | TOWER
R00034 | R001B_R00034OD_LONGBOH | Northern |  | Decomm |  | 2024 Q4 | ZA | GTSB | 4.6 TSSR Approved |  | 2024-02-13 |  |  |  | 2024-02-13 |  | 2024-02-27 | 2024-02-29 | CD//Shamsul | 2024-02-28 | Celcom Digi_RAN-GTSB-TSS-Northern-20240223-0093 | DU00002863308 |  |  |  |  | 2024-06-12 |  | TOWER
K00406 | K009A_K00406OD_KGKTEKAI | Northern |  | Decomm |  | 2025 Q3 | HW | GCI | 4.6 TSSR Approved |  | 2025-04-13 |  | 2025-04-23 |  | 2025-04-30 |  | 2025-05-02 |  | CD//Zulakmar | 2025-05-08 | SQ202501060244 - GCI | DU00002863309 |  |  |  |  | 2025-06-19 |  | TOWER
3335A | TMN_MAYANG1 | Central |  | Modernization |  | 2024 Q1 | AI | DATASCO | 4.6 TSSR Approved |  | 2024-02-20 | 2024-02-21 |  | 2024-03-04 |  | Closed | 2024-03-05 | 2024-03-06 | E//Kok Keen | 2024-03-06 | CelcomDigi_RAN_Datasco_TSS_Central_20231116 | DU00002863310 |  |  | 2024-04-23 | 2024-04-22 |  | Pole | 3m Bipod (RT) | 6 | Add R9264M M1821 x3,Dismantle R9224E M1821(AAB) x3
R00045 | R001B_R00045OD_CB_KGWANGULU | Northern |  | Decomm |  | 2024 Q4 | SM | GCI | 4.6 TSSR Approved |  | 2024-03-22 |  |  |  | 2024-03-27 |  | 2024-04-24 | 2025-10-28 | CD//Shamsul | 2024-04-29 | Celcom Digi_RAN-GCI-TSS-Northern-20240329-0104 | DU00002863311 |  |  |  |  | 2024-06-12 |  | TOWER
A01174 | A036A_A01174_BATU3_JLN_PAHANG_TPH | Northern |  | Decomm |  | 2024 Additional | SHA | CCSMY | 4.6 TSSR Approved | ¦ 20241125 - CD Zul: Pair site 4908B yet modernized. Lets hold this tssr review until implementation first. | 2024-01-26 |  |  |  | 2024-01-29 |  | 2024-11-20 | 2025-07-29 | CD//Zulakmar | 2025-01-21 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240124-0090 | DU00002863312 |  |  |  |  | 2024-12-17 |  | TOWER
A00114 | A036A_A00114OD_AIRKUNING_RCC | Northern |  | Decomm |  | 2024 Additional | SM | GTSB | 4.6 TSSR Approved |  | 2023-12-18 |  |  |  | 2023-12-29 |  | 2024-01-04 |  | CD//Shamsul | 2024-01-05 | Celcom Digi_RAN-GTSB-TSS-Northern-20231219-0078 | DU00002863313 |  | Please Include all TX Equipment in cabinet/Rack |  |  | 2024-12-13 |  | TOWER
A01050 | A044A_A01050OD_CB_KGBANDARAYER | Northern |  | Decomm |  | 2024 Q2 | ZA | GTSB | 4.6 TSSR Approved |  | 2024-02-06 |  |  |  | 2024-02-07 |  | 2024-02-08 | 2024-04-23 | CD//Shamsul | 2024-02-09 | Celcom Digi_RAN-GTSB-TSS-Northern-20240207-0091 | DU00002863314 |  |  |  |  | 2024-05-04 |  | TOWER
K00265 | K002A_K00265OD_BAUBAK | Northern |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4 | HW | CCSMY | 4.6 TSSR Approved |  | 2025-04-09 |  | 2024-12-13 |  | 2025-04-09 | To be Submitted | 2025-04-27 |  | CD//Zulakmar | 2025-04-30 | 0927CD-Northern-CCSMY-BOQ Template(new contract)/0927MW-Northern-CCSMY-BOQ Template(new contract) | DU00002863315 |  | Missing TX part (NE/FE) |  |  | 2024-12-03 |  | TOWER
K00426 | K004B_K00426OD_CB_TEBENGAU | Northern |  | Decomm |  | 2024 Q4 | SM | GCI | 4.6 TSSR Approved |  | 2024-10-19 |  | 2024-10-23 |  | 2024-11-11 |  | 2024-11-15 | 2025-07-29 | CD//Zulakmar | 2024-11-18 | 0927CD-Northern-GCI-BOQ Template(new contract)/0927MW-Northern-GCI-BOQ Template(new contract) | DU00002863316 |  |  |  |  | 2024-10-21 |  | BOOM
S01147 | S104A_S01147OD_KUNDASANGTOWN | Sabah |  | Decomm |  | 2024 Q4 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2024-10-03 |  | 2024-10-14 |  | 2024-10-15 |  | 2024-10-16 | 2024-10-25 | CD//Ray Amos | 2024-10-17 | 0928MW-Sabah-SeriPancar-BOQ Template(new contract)/0928CD-Sabah-SeriPancar-BOQ Template(new contract) | DU00002863317 |  |  |  |  | 2024-11-04 |  | LAMP_POLE
K00773 | K033A_K00773OD_CB_KM177NSE_NB | Northern |  | Decomm |  | 2025 Q3 | HW | GCI | 4.6 TSSR Approved |  | 2024-01-12 |  |  |  | 2024-01-31 |  | 2025-02-24 | 2025-10-28 | CD//Zulakmar | 2025-02-28 | Celcom Digi_RAN-GCI-TSS-Northern-20240116-0089//SQ202501030261 - GCI | DU00002863318 |  |  |  |  | 2025-08-20 |  | TOWER
K00262 | K003A_K00262OD_CB_KSELAMA | Northern |  | Decomm |  | 2024 Q4 | SM | CCSMY | 4.6 TSSR Approved |  | 2024-02-20 |  |  |  | 2024-02-21 |  | 2024-02-27 | 2024-03-05 | CD//Shamsul | 2024-02-27 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240221-0094 | DU00002863319 |  |  |  |  | 2024-11-14 |  | TOWER
K00184 | K002A_K00184OD_KUALAPEGANG | Northern |  | Decomm |  | 2024 Q4 | SHA | CCSMY | 4.6 TSSR Approved |  | 2024-10-05 |  | 2024-10-08 |  | 2024-10-09 |  | 2024-10-10 | 2025-07-29 | CD//Zulakmar | 2024-10-14 | 0927CD-Northern-CCSMY-BOQ Template(new contract) | DU00002863320 |  |  |  |  | 2024-11-14 |  | SHARING STRC SBC
K00075 | K010A_K00075OD_PDGDURIAN | Northern |  | Decomm |  | 2024 Q4 | SHA | GCI | 4.6 TSSR Approved |  | 2024-10-19 |  | 2024-10-30 |  | 2024-11-11 |  | 2024-12-16 |  | CD//Zulakmar | 2024-12-18 | 0927CD-Northern-GCI-BOQ Template(new contract)/0927MW-Northern-GCI-BOQ Template(new contract) | DU00002863321 |  | Missing Antenna Photo for 1 link |  |  | 2024-11-25 |  | TOWER
K00087 | K002A_K00087OD_KGHANGUS | Northern |  | Decomm |  | 2024 Q3(single site MOCN) | SM | GTSB | 4.6 TSSR Approved |  | 2024-09-04 |  | 2024-08-13 |  | 2024-09-05 |  | 2024-09-11 | 2026-03-11 | CD//Zulakmar | 2024-09-18 | 0809MW-Norhtern-GTSB-BOQ Template(new contract)/0809CD-Northern-GTSB-BOQ Template(new contract) | DU00002863322 |  |  |  |  | 2024-12-04 |  | TOWER
K00352 | K011A_K00352OD_KAMPUNGYOOI | Northern |  | Decomm |  | 2024 Q4 | SM | GCI | 4.6 TSSR Approved |  | 2024-10-19 |  |  |  | 2024-11-13 | To be Submitted | 2024-11-20 |  | CD//Zulakmar | 2024-11-25 | 0927CD-Northern-GCI-BOQ Template(new contract) | DU00002863323 |  |  |  |  | 2024-11-11 |  | TOWER
K00067 | K002A_K00067OD_BONGOR | Northern |  | Decomm |  | 2024 Q3(single site MOCN) | HW | CCSMY | 4.6 TSSR Approved |  | 2025-03-10 |  | 2024-10-15 |  | 2025-04-09 |  | 2025-04-27 | 2025-07-29 | CD//Zulakmar | 2025-04-30 | 0809MW-Northern-CCSMY-BOQ Template(new contract)/0809CD-Northern-CCSMY-BOQ Template(new contract) | DU00002863324 |  |  |  |  | 2024-12-06 |  | TOWER
K01003 | K013A_K01003OD_SGLIMAUDALAM | Northern |  | Decomm |  | 2024 Q4 | SM | GCI | 4.6 TSSR Approved |  | 2024-11-15 |  | 2024-11-26 |  | 2024-11-26 |  | 2024-12-06 | 2025-07-29 | CD//Zulakmar | 2024-12-12 | 0927CD-Northern-GCI-BOQ Template(new contract)/0927MW-Northern-GCI-BOQ Template(new contract) | DU00002863325 |  |  |  |  | 2024-11-06 |  | TOWER
K00340 | K013A_K00340OD_CB_KGPERIGI | Northern |  | Decomm |  | 2024 Q4 | HW | GCI | 4.6 TSSR Approved |  | 2024-11-15 |  | 2024-12-04 |  | 2025-02-11 |  | 2025-02-20 | 2025-10-28 | CD//Hazwan | 2025-02-26 | 0927CD-Northern-GCI-BOQ Template(new contract)/0927MW-Northern-GCI-BOQ Template(new contract) | DU00002863326 |  | Missing Digi IDU and MW celcom link |  |  | 2024-11-06 |  | TOWER
K00431 | K013A_K00431OD_CB_DULANGKCL | Northern |  | Decomm |  | 2025 Q3 | HW | CCSMY | 4.6 TSSR Approved |  | 2025-03-06 |  | 2025-01-27 |  | 2025-04-09 | To be Submitted | 2025-04-14 |  | CD//Zulakmar | 2025-04-25 | SQ202501060201 - CCSMY | DU00002863327 |  | missing TX Part (NE/FE) |  |  | 2025-07-17 |  | TOWER
K00429 | K013A_K00429OD_PMTGBULUH | Northern |  | Decomm |  | 2024 Q4 | AD | GCI | 4.6 TSSR Approved |  | 2024-10-15 |  | 2024-10-23 |  | 2024-12-11 |  | 2024-12-16 |  | CD//Zulakmar | 2024-12-23 | 0927CD-Northern-GCI-BOQ Template(new contract)/0927MW-Northern-GCI-BOQ Template(new contract) | DU00002863328 |  |  |  |  | 2024-10-21 |  | TOWER
K00577 | K013A_K00577OD_PDGLUMAT_RDC | Northern |  | Decomm |  | 2025 Q3 | HW | GCI | 4.6 TSSR Approved |  | 2025-05-05 |  | 2025-05-08 |  | 2025-05-14 |  | 2025-05-16 | 2025-10-28 | E//Hazida | 2025-05-19 | SQ202501060244 - GCI | DU00002863329 |  |  |  |  | 2025-09-09 |  | TOWER
K00161 | K011A_K00161OD_KEBUN500 | Northern |  | Decomm |  | 2025 Q2 | HW | CCSMY | 4.6 TSSR Approved |  | 2025-02-03 |  | 2025-02-05 |  | 2025-02-19 |  | 2025-02-20 | 2025-10-28 | CD//Hazwan | 2025-02-28 | SQ202501060201 - CCSMY | DU00002863330 |  | CD Hazwan reviewed but Hold wait for upg tssr ready first |  |  | 2025-07-29 |  | TOWER
K00258 | K010A_K00258OD_PAYAMATINSUN | Northern |  | Decomm |  | 2025 Q2 | HW | GTSB | 4.6 TSSR Approved |  | 2025-02-22 |  | 2025-03-04 |  | 2025-03-14 | To be Submitted | 2025-03-17 |  | CD//Zulakmar | 2025-03-24 | SQ202501060259 - GTSB | DU00002863331 |  | CD Zulakmar- TSSR reviewed and is ok. However, lets wait for the pair site to be implemented first before I approve this tssr.// No FE TX Part |  |  | 2025-08-13 |  | TOWER
K00079 | K010A_K00079OD_CB_TOBIAR | Northern |  | Decomm |  | 2024 Q4 | SM | GCI | 4.6 TSSR Approved |  | 2024-10-18 |  | 2024-10-27 |  | 2024-11-20 |  | 2024-11-21 | 2025-10-28 | CD//Zulakmar | 2024-12-05 | 0927CD-Northern-GCI-BOQ Template(new contract)/0927MW-Northern-GCI-BOQ Template(new contract) | DU00002863332 |  |  |  |  | 2024-10-24 |  | TOWER
K00206 | K009A_K00206OD_NAKA | Northern |  | Decomm |  | 2024 Q3(single site MOCN) | BY | GCI | 4.6 TSSR Approved |  | 2024-07-08 |  | 2024-07-15 |  | 2024-07-17 |  | 2024-08-07 | 2025-10-28 | CD//Shamsul | 2024-08-08 | 0918MW-Northern-GCI-BOQ Template (old contract) | DU00002863333 |  |  |  |  | 2024-09-03 |  | TOWER
K00158 | K003A_K00158OD_BAGANSAMAK | Northern |  | Decomm |  | 2024 Q4 | SHA | GTSB | 4.6 TSSR Approved |  | 2024-01-18 |  |  |  | 2024-01-22 |  | 2024-10-11 | 2024-10-16 | CD//Zulakmar | 2024-10-14 | Celcom Digi_RAN-GTSB-TSS-Northern-20240124-0088 | DU00002863334 |  | Have 2 IDU extra |  |  | 2024-12-06 |  | TOWER
K00252 | K003A_K00252OD_SERDANG | Northern |  | Decomm |  | 2024 Q4 | SM | CCSMY | 4.6 TSSR Approved |  | 2024-10-29 |  | 2024-11-29 |  | 2024-11-29 |  | 2024-12-02 |  | CD//Zulakmar | 2024-12-05 | 0927CD-Northern-CCSMY-BOQ Template(new contract)/0927MW-Northern-CCSMY-BOQ Template(new contract) | DU00002863335 |  |  |  |  | 2024-12-06 |  | TOWER
K00432 | K005D_K00432OD_JLNJENIANG | Northern |  | Decomm |  | 2024 Q4 | SM | GCI | 4.6 TSSR Approved |  | 2024-10-15 |  | 2024-11-01 |  | 2024-11-20 |  | 2024-11-21 | 2025-10-28 | CD//Zulakmar | 2024-12-05 | 0927CD-Northern-GCI-BOQ Template(new contract)/0927MW-Northern-GCI-BOQ Template(new contract) | DU00002863336 |  |  |  |  | 2024-10-22 |  | TOWER
K00255 | K003A_K00255OD_CB_SGTENGAS | Northern |  | Decomm |  | 2025 Q3 | HW | CCSMY | 4.6 TSSR Approved |  | 2024-09-13 |  | 2025-05-08 |  | 2025-05-13 |  | 2025-05-15 | 2025-10-28 | E//Hazida | 2025-05-19 | Celcom Digi_RAN-CCS-TSS Decomm-Northern-20240925_New Contract | DU00002863337 |  |  |  |  | 2025-10-15 |  | TOWER
K00170 | K003A_K00170OD_BDRBARU_RCC | Northern |  | Decomm |  | 2024 Q4 | SHA | GCI | 4.6 TSSR Approved | ¦ 1002 - CD Zul: Please relocate 4992B antenna to 55m. | 2024-02-12 |  |  |  | 2024-03-13 |  | 2024-09-30 | 2024-10-16 | CD//Zulakmar | 2024-10-08 | Celcom Digi_RAN-GCI-TSS-Northern-20240321-0102/Celcom Digi_RAN-GCI-TSS-Northern-20241017_New Contract | DU00002863338 |  |  |  |  | 2024-09-18 |  | TOWER
K00600 | K004B_K00600OD_KOTASRGSEMUT_RDC | Northern |  | Decomm |  | 2024 Q4 |  | GCI | 4.6 TSSR Approved |  | 2024-10-10 |  | 2024-10-18 |  | 2024-10-29 |  | 2024-11-13 | 2025-07-29 | CD//Zulakmar | 2024-11-15 | 0927CD-Northern-GCI-BOQ Template(new contract) | DU00002863339 |  |  |  |  | 2024-10-24 |  | TOWER
K00081 | K002A_K00081OD_CB_KGTEMBAK | Northern |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4 | HW | GCI | 4.6 TSSR Approved |  | 2023-12-22 |  |  |  | 2024-01-17 |  | 2026-01-21 | 2026-01-22 | CD//Shamsul | 2025-03-13 | Celcom Digi_RAN-GCI-TSS-Northern-20231225-0085/Celcom Digi_RAN-GCI-TSS-Northern-20240130-0092 | DU00002863340 |  |  |  |  | 2025-03-27 |  | TOWER
K00688 | K005D_K00688OD_TMNMURNIGRN | Northern |  | Decomm |  | 2024 Q3(single site MOCN) | SM | GCI | 4.6 TSSR Approved |  | 2024-06-07 |  | 2024-07-20 |  | 2024-07-24 |  | 2024-07-25 | 2024-10-01 | CD//Shamsul | 2024-07-25 | 0618Northen-GCI-BOQ Template (template) | DU00002863341 |  |  |  |  | 2024-08-14 |  | TOWER
A00026 | A040D_A00026OD_ARAPAYUNG_RDD | Northern |  | Decomm |  | 2024 Q3(single site MOCN) | SHA | GCI | 4.6 TSSR Approved |  | 2024-06-07 |  |  |  | 2024-06-27 |  | 2024-06-28 | 2025-10-28 | CD//Affendi | 2024-07-01 | 0618Northen-GCI-BOQ Template (template) | DU00002863342 |  |  |  |  | 2025-02-28 |  | TOWER
K00110 | K004B_K00110OD_CB_SPG4KANGKONG | Northern |  | Decomm |  | 2025 Q3 | HW | CCSMY | 4.6 TSSR Approved |  | 2025-02-01 |  | 2025-02-05 |  | 2025-02-18 |  | 2025-02-24 | 2025-10-28 | CD//Zulakmar | 2025-02-28 | SQ202501060201 - CCSMY | DU00002863343 |  |  |  |  | 2025-07-17 |  | TOWER
4226A | KKBDA | Northern |  | Modernization |  | 2024 Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-10-12 | 2023-10-20 |  | 2024-04-04 |  | Closed | 2024-04-16 | 2024-04-19 | E//Ajay | 2024-04-19 | Celcom Digi_RAN-GCI-TSS-Northern-20231015-0059 | DU00002863344 |  |  | 2024-04-25 | 2024-04-20 |  | In-Building System | 6m Tripod (RT) | 4.9 | Add R8852E S9000 x3+R8894E M1821 x5+R8854 S2600 x2,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2600(A4A) x2 | 0 | 23
4322A | Batamas Sdn Bhd RDD | Northern |  | Modernization |  | 2024 Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2023-10-11 | 2023-10-13 |  | 2024-01-09 |  | Rectificating | 2024-01-10 | 2024-01-11 | E//Hazida | 2024-01-11 | Celcom Digi_RAN-GTSB-TSS-Northern-20231012-0047 | DU00002863345 |  |  | 2024-02-18 | 2024-02-05 |  | Tower | 6m Unipole RT | 45 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x2+R8862A S2100(A6A) x3
4432B | Sg Siput Utara | Northern |  | Modernization |  | 2025 Q3 | HW | GCI | 4.6 TSSR Approved |  | 2023-10-16 | 2023-11-08 |  | 2025-03-03 |  | Under Approval | 2025-03-27 | 2025-05-19 | E//Hazida | 2025-04-23 | Celcom Digi_RAN-GCI-TSS-Northern-20231018-0061 | DU00002863346 |  |  | 2025-05-13 | 2025-04-24 |  | Monople Tree | 30m Monopole | 40 | Add R8852E S9000x3+R8894E M1821x4, Dismantle R8882 S1800B(B6B)x3+R8862A S2100(A6A)x3 | 0 | 3
K00608 | K008A_K00608OD_JLNULUMELAKA | Northern |  | Decomm |  | 2024 Q4 | SM | CCSMY | 4.6 TSSR Approved | ¦ 1014 - Need clarify between CCS n GTSB, CCS Done TSS on 13.10.2024 | 2024-10-13 |  | 2024-10-21 |  | 2024-10-24 |  | 2024-11-13 | 2025-07-29 | CD//Zulakmar | 2024-11-18 | 0927CD-Northern-CCSMY-BOQ Template(new contract) | DU00002863347 |  |  |  |  | 2024-10-15 |  | TOWER
B00231 | B064I_B00231OD_BDRTASIKKESUMA | Central |  | Decomm |  | 2024 | AD | GCI | 4.6 TSSR Approved |  | 2024-10-11 |  | 2024-10-16 |  | 2024-10-22 |  | 2024-11-22 | 2025-01-14 | CD//Sapian | 2024-12-03 | Celcom Digi_RAN-GCI-Standard PR TSS-Central-20241016/Celcom Digi_RAN-GCI-Standard PR TSS-Central-20241016 | DU00002863348 |  |  |  |  | 2024-09-30 |  | BOOM
7434B | Labuk Bay | Sabah |  | Modernization |  | 2024 Q4 | MS | Futong | 4.6 TSSR Approved |  | 2024-03-21 | 2024-03-25 |  | 2024-04-04 |  | Closed | 2024-04-05 | 2024-04-19 | E//Hannah | 2024-04-19 | Celcom Digi_RAN-Futong-TSS-Sabah-20240324 | DU00002863349 |  |  | 2024-06-07 | 2024-06-04 |  | Tower | Tower | 60 | Add ,Dismantle | 0 | 0
W01442 | W066G_W01442OD_BT414_JLNGOMBAK | Central |  | Decomm |  | 2024 Q1 | SHA | GTSB | 4.6 TSSR Approved |  | 2024-07-01 |  | 2024-08-06 |  | 2024-07-17 |  | 2024-07-22 | 2025-01-14 | CD//Norhaliza | 2024-10-04 | 0701Central-GTSB-BOQ Template (template) | DU00002863350 |  |  |  |  | 2024-08-26 |  | LAMP_POLE
4504B | Pulai Heights RCC | Northern |  | Modernization |  | 2024 Q2 |  | CCSMY | 4.6 TSSR Approved |  | 2023-10-19 | 2023-10-25 |  | 2024-01-08 |  | Closed | 2024-01-09 | 2024-01-11 |  | 2024-01-10 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231020-0059 | DU00002863351 |  |  | 2024-02-14 | 2024-01-26 |  | Tower | 60m 3 Legged Tower | 46m | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3
4654B | TmnDarulAman | Northern |  | Modernization |  | 2024 Q3 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-10-11 | 2023-10-13 |  | 2023-10-23 |  | Rectificating | 2023-10-31 | 2024-05-23 | E//Hazida | 2023-10-31 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231012-0053 | DU00002863352 |  |  | 2024-04-19 | 2024-04-18 |  | Tower | 45m Monopole Tree | 53m | Add R9264M M1821 x3+R9264H M901821 x3+R8862A S2600 x3,Dismantle R8882-GUL1812 x2+R8882 S1800(B) x1+R8854D S2100(A4A) x3 | 0 | 123
4673B | Kangar Highway | Northern |  | Modernization |  | 2024 Q3 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-10-12 | 2023-12-12 |  | 2024-03-21 |  | Closed | 2024-04-01 | 2024-04-03 | E//Hazida | 2024-04-02 | Celcom Digi_RAN-GTSB-TSS-Northern-20231013-0048 | DU00002863353 |  |  | 2024-04-18 | 2024-04-12 |  | Tower | 60m 3 Legged Tower | 60 | Add R8862A S9000 x1+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882 S1800(B) x2 | 0 | 2
S00263 | S088A_S00263OD_LUTH | Sabah |  | Decomm |  | 2024 Q3(single site MOCN) | AD | Seri Pancar | 4.6 TSSR Approved |  | 2024-06-07 |  |  |  | 2024-06-26 |  | 2024-06-26 | 2025-01-31 | CD//Ray Amos | 2024-07-01 | 0610Sabah-Seri Pancar-BOQ Template (template) | DU00002863354 |  |  |  |  | 2024-09-27 |  | BOOM
4724B | Tualang Palas | Northern |  | Modernization |  | 2024 Q3 | SM | CCSMY | 4.6 TSSR Approved | ¦ 0319 - Previous TSSR subcon submitted, have solution changes | 2023-10-12 | 2023-10-18 |  | 2023-10-24 |  | Closed | 2024-03-29 | 2024-04-01 | E//Ajay | 2024-04-01 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231013-0054 | DU00002863355 |  |  | 2024-04-19 | 2024-04-15 |  | Tower | Tower | 72m | Add R8894E M1821 x5+R8854 S2600 x2,Dismantle R8862A S1800(B6A) x3+R8862A S2601(A6A) x2+R8840-U216 x3++ | 0 | 23
4726B | Tunku Sarina | Northern |  | Modernization |  | 2024 Q3 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-10-12 | 2023-10-18 |  | 2023-10-24 |  | Closed | 2024-04-04 | 2024-04-05 | E//Ajay | 2024-04-05 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231013-0054 | DU00002863356 |  |  | 2024-04-26 | 2024-04-20 |  | Tower | Tower | 73m | Add A9732 M1821 x3,Dismantle R8892N M1821(BAB) x3 | 123 | 0
S00131 | S096A_S00131OD_KUDATTOWN | Sabah |  | Decomm |  | 2024 Q4 | MS | Seri Pancar | 4.6 TSSR Approved |  | 2024-08-23 |  | 2024-09-08 |  | 2024-09-10 |  | 2024-09-11 | 2024-11-15 | CD//Ray Amos | 2024-09-12 | 0828CD-Sabah-Seri Pancar-BOQ Template(new contract) | DU00002863357 |  |  |  |  | 2024-11-01 |  | GUYED MAST
S00153 | TMNKUDAT | Sabah |  | Decomm |  | 2024 | MS | Seri Pancar | 4.6 TSSR Approved |  | 2024-11-08 |  | 2024-11-11 |  | 2024-11-12 |  | 2024-11-13 | 2024-12-13 | CD//Ray Amos | 2024-11-13 | Celcom Digi_RAN-Seri Pancar-Standard PR TSS-Sabah-20241030 | DU00002863358 |  |  |  |  | 2025-02-14 |  | RAPOLE
S00133 | BUKITKELAPA | Sabah |  | Decomm |  | 2024 Q3(single site MOCN) | ZB | Seri Pancar | 4.6 TSSR Approved |  | 2024-06-27 |  | 2024-07-11 |  | 2024-07-22 |  | 2024-07-23 | 2025-01-31 | CD//Ray Amos | 2024-07-30 | 0701Sabah-Seri Pancar-BOQ Template (template) | DU00002863359 |  |  |  |  | 2024-10-16 |  | TOWER
4728B | Pdg Pekan (maxis ) | Northern |  | Modernization |  | 2024 Q3 | BY | GTSB | 4.6 TSSR Approved |  | 2024-03-27 | 2024-03-29 |  | 2024-04-03 |  | Closed | 2024-04-04 | 2024-04-15 | E//Hazida | 2024-04-08 | Celcom Digi_RAN-GTSB-TSS-Northern-20240329-0098 | DU00002863360 |  |  | 2024-04-25 | 2024-04-18 |  | Tower | 45m 3 Legged Tower | 40m | Add R8852E S9000 x3+R9224E M1821 x5+R8854 S2600 x2,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3+R8862A S2600(A4A) x2 | 0 | 12
S00144 | S096A_S00144OD_KGSIKUATI | Sabah |  | Decomm |  | 2024 Q3(single site MOCN) | AD | Seri Pancar | 4.6 TSSR Approved |  | 2024-06-25 |  |  |  | 2024-07-04 |  | 2024-07-09 | 2024-09-13 | CD//Ray Amos | 2024-07-10 | 0626Sabah-Seri Pancar-BOQ Template (template) | DU00002863361 |  |  |  |  | 2024-10-09 |  | TOWER
S01318 | S096A_S01318OD_KUDATOLDTOWN | Sabah |  | Decomm |  | 2024 Q3(single site MOCN) | AD | Seri Pancar | 4.6 TSSR Approved |  | 2024-06-30 |  | 2024-07-31 |  | 2024-08-08 |  | 2024-08-12 | 2024-09-26 | CD//Sharidah | 2024-08-12 | 0701Sabah-Seri Pancar-BOQ Template (template) | DU00002863362 |  |  |  |  | 2024-10-24 |  | BOOM
S00157 | S104A_S00157OD_CB_TMKINADUSAN | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4 | AD | NR services | 4.6 TSSR Approved |  | 2025-03-12 |  | 2025-03-28 |  | 2025-03-31 | To be Submitted | 2025-04-30 |  | E//Sharidah | 2025-05-08 | Celcom Digi_RAN YPTT Standard PR TSS-Sabah-20241128 | DU00002863363 |  |  |  |  | 2025-11-29 |  | TOWER
S00585 | S104A_S00585OD_GNGKINABALU | Sabah |  | Decomm |  | 2024 | AD | GTSB | 4.6 TSSR Approved |  | 2024-11-27 |  | 2025-02-07 |  | 2025-02-21 | To be Submitted | 2025-02-22 |  | CD//Sharidah | 2025-02-24 | Celcom Digi_RAN GTSB-Standard PR TSS-Sabah-20241126 | DU00002863364 |  |  |  |  | 2026-01-28 |  | TOWER
B00373 | B061H_B00373OD_TMNMEDANPJ | Central |  | Decomm |  | 2024 Q3 | BY | GTSB | 4.6 TSSR Approved |  | 2024-03-20 |  |  |  | 2024-05-18 |  | 2024-05-20 | 2024-09-25 | CD//Sapian | 2024-05-31 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240323 | DU00002863365 |  |  |  |  | 2024-05-30 |  | BOOM
7421B | Kg. Suan Lamba SBC | Sabah |  | Modernization |  | 2024 Q4 | MS | GTSB | 4.6 TSSR Approved | Solution changed MM>Bi | 2024-08-01 | 2024-08-19 |  | 2024-08-22 |  | Under Approval | 2024-08-23 | 2024-09-06 | E//Hannah | 2024-09-06 | 0730CD-Sabah-GTSB-BOQ Template(new contract) | DU00002863366 |  |  | 2025-01-21 | 2025-01-11 |  | Tower | Tower | 75m | Add R8854 S2600 x1+R8894E M1821 x1 | 0 | 2
4870B | Ulu Wang2 | Northern |  | Modernization |  | 2024 Q4 | SM | GCI | 4.6 TSSR Approved |  | 2023-10-06 | 2023-12-08 |  | 2024-04-23 |  | Under Approval | 2024-04-29 | 2024-05-13 | E//Ajay | 2024-05-01 | Celcom Digi_RAN-GCI-TSS-Northern-2023111-0057 | DU00002863367 |  |  | 2024-05-25 | 2024-05-17 |  | Tower | Tower | 76 | Add R8862A S9000 x3+R8862A S2601 x3+A9732 M1821 x3,Dismantle R8860E-GU908 x1+R8882-GUL1812 x1+R8862A S1800(B6A) x1+R8894E M1821(A8A) x3 | 123 | 0
L00007 | S113A_L00007OD_WISMAWWL | Sabah |  | Decomm |  | 2025 Q1 | AD | YPTT | 4.6 TSSR Approved |  | 2025-05-18 | [5 empty] | 2025-04-21 | 2025-09-10 | CD//Sharidah | 2025-04-23 | SQ202501030034 - YPTT | DU00002863368 |  |  |  |  | 2025-03-26 |  | BOOM
L00133 | S113A_L00133OD_PENGKALANKAPUR | Sabah |  | Decomm |  | 2025 Q1 | HW | YPTT | 4.6 TSSR Approved |  | 2025-01-24 |  | 2025-02-03 |  | 2025-02-05 |  | 2025-02-21 | 2025-05-02 | CD//Sharidah | 2025-02-26 | SQ202501030034 - YPTT | DU00002863369 |  |  |  |  | 2025-03-13 |  | LAMP_POLE
L00146 | S113A_L00146OD_WISMAKOSANRD | Sabah |  | Decomm |  | 2025 Q1 | AD | YPTT | 4.6 TSSR Approved |  | 2025-01-15 |  | 2025-01-17 |  | 2025-02-18 |  | 2025-02-22 | 2025-05-02 | CD//Sharidah | 2025-02-24 | SQ202501030034 - YPTT | DU00002863370 |  |  |  |  | 2025-03-27 |  | TOWER
L00149 | S113A_L00149OD_TMNFULLIWA | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2025 Q1 | AD | YPTT | 4.6 TSSR Approved |  | 2025-03-16 |  | 2024-11-20 |  | 2025-04-14 |  | 2025-04-28 | 2025-10-28 | CD//Sharidah | 2025-09-30 | SQ202504140301 - YPTT | DU00002863371 |  |  |  |  | 2025-08-25 |  | LAMP_POLE
L00016 | S113A_L00016OD_IOFC | Sabah |  | Decomm |  | 2024 Q3(single site MOCN) | MS | Seri Pancar | 4.6 TSSR Approved |  | 2024-01-22 |  |  |  | 2024-08-12 |  | 2024-08-16 | 2025-01-31 | CD//Ray Amos | 2024-08-16 | Celcom Digi_RAN-Seri Pancar-Standard PR TSS-Sabah-20240213 | DU00002863372 |  |  |  |  | 2025-01-13 |  | BOOM
L00008 | S113A_L00008OD_SGBANGAT | Sabah |  | Decomm |  | 2025 Q1 | AD | YPTT | 4.6 TSSR Approved |  | 2025-01-24 |  | 2024-07-07 |  | 2025-04-10 |  | 2025-04-17 |  | CD//Sharidah | 2025-04-21 | SQ202501030034 - YPTT | DU00002863373 |  |  |  |  | 2025-04-24 |  | TOWER
B01490 | W066Y_B01490OD_PANDANINDAH2 | Central |  | Decomm |  | 2024 Q3 | ZB | Ascentrack | 4.6 TSSR Approved |  | 2024-01-31 |  |  |  | 2024-02-04 |  | 2024-08-12 | 2024-10-29 | CD//Norhaliza | 2024-10-04 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240202 | DU00002863374 |  |  |  |  | 2024-08-08 |  | BOOM
4935B | Felda Bkt Tangga | Northern |  | Modernization |  | 2024 Q3 | BY | YPTT | 4.6 TSSR Approved |  | 2023-10-26 | 2023-10-31 |  | 2023-11-06 |  | Closed | 2024-04-04 | 2024-04-23 | E//Hazida | 2024-04-22 | Celcom Digi_RAN-YPTT-TSS-Northern-20231028-0040 | DU00002863375 |  |  | 2024-04-24 | 2024-04-20 |  | Tower | Tower | 60m | Add R8852E S9000 x3+R9224E M1821 x1+A9732 M1821 x2,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 13 | 0
S00337 | S098C_S00337OD_TMLAHADDATU | Sabah |  | Decomm |  | 2024 Q3 | MS | Futong | 4.6 TSSR Approved |  | 2024-07-18 |  | 2024-07-24 |  | 2024-07-26 |  | 2024-07-30 | 2024-11-15 | CD//Ray Amos | 2024-07-30 | 0719Sabah-Futong-BOQ Template/0719MW-Sabah-Futong-BOQ Template | DU00002863376 |  |  |  |  | 2024-09-05 |  | TOWER
S00323 | S098B_S00323OD_SEPAGAYA | Sabah |  | Decomm |  | 2024 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2024-05-08 |  |  |  | 2024-05-13 |  | 2024-05-15 | 2024-05-24 | CD//Ray Amos | 2024-05-16 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240510 | DU00002863377 |  |  |  |  | 2024-07-17 |  | TOWER
4936B | Felda Bt8 | Northern |  | Modernization |  | 2024 Q3 | BY | GTSB | 4.6 TSSR Approved |  | 2023-10-11 | 2023-10-17 |  | 2024-04-03 |  | Closed | 2024-04-16 | 2024-04-23 | E//Ajay | 2024-04-17 | Celcom Digi_RAN-GTSB-TSS-Northern-20231012-0047 | DU00002863378 |  |  | 2024-04-24 | 2024-04-20 |  | Tower | Tower | 60 | Add R8862A S2601 x1+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x1 | 1 | 0
S00325 | S098B_S00325OD_TABANAK | Sabah |  | Decomm |  | 2024 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2024-05-08 |  |  |  | 2024-05-10 |  | 2024-05-13 | 2024-07-29 | CD//Ray Amos | 2024-05-16 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240510 | DU00002863379 |  |  |  |  | 2024-07-24 |  | TRIPOD
S00344 | S098A_S00344OD_ANJUNGTEDUH | Sabah |  | Decomm |  | 2024 Q3(single site MOCN) | SHA | Seri Pancar | 4.6 TSSR Approved |  | 2024-06-11 |  | 2024-07-03 |  | 2024-07-05 |  | 2024-07-09 | 2024-08-09 | CD//Ray Amos | 2024-07-10 | 0618Sabah-Seri Pancar-BOQ Template (template) | DU00002863380 |  |  |  |  | 2024-09-09 |  | TOWER
S00732 | S098B_S00732OD_JLNASSAM | Sabah |  | Decomm |  | 2024 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2024-05-15 |  |  |  | 2024-05-17 |  | 2024-05-21 | 2024-08-01 | CD//Ray Amos | 2024-05-23 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240519 | DU00002863381 |  |  |  |  | 2024-08-07 |  | TOWER
S00410 | S098B_S00410OD_BATALION17 | Sabah |  | Decomm |  | 2024 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2024-05-08 |  |  |  | 2024-05-10 |  | 2024-05-13 | 2024-07-29 | CD//Ray Amos | 2024-05-14 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240510 | DU00002863382 |  |  |  |  | 2024-07-16 |  | TOWER
S00685 | S098A_S00685OD_CB_DESAKENCANA | Sabah |  | Decomm |  | 2024 Q3(single site MOCN) | AD | Seri Pancar | 4.6 TSSR Approved |  | 2024-06-11 |  | 2024-07-03 |  | 2024-07-03 |  | 2024-07-04 | 2024-08-29 | CD//Ray Amos | 2024-07-10 | 0618Sabah-Seri Pancar-BOQ Template (template) | DU00002863383 |  |  |  |  | 2024-10-11 |  | TOWER
S00343 | S091A_S00343OD_KGPARIS3 | Sabah |  | Decomm |  | 2024 Q4(single site MOCN)-L2126 SSM | MS | Seri Pancar | 4.6 TSSR Approved |  | 2024-07-22 |  | 2024-07-27 |  | 2024-07-30 |  | 2024-08-02 | 2024-11-22 | CD//Sharidah | 2024-08-06 | 0725Sabah-Seri Pancar-BOQ Template(new contract) | DU00002863384 |  |  |  |  | 2024-11-14 |  | TOWER
S01114 | S105B_S01114OD_SEDCOINDUSTRY | Sabah |  | Decomm |  | 2024 Q3 | BY | GTSB | 4.6 TSSR Approved |  | 2024-03-13 |  |  |  | 2024-03-20 |  | 2024-04-05 | 2024-05-14 | CD//Ray Amos | 2024-04-08 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240313 | DU00002863385 |  |  |  |  | 2024-08-14 |  | BOOM
S00166 | S105A_S00166OD_TRIGHILL | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2024 Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2024-03-20 |  |  |  | 2024-03-21 |  | 2024-04-05 |  | CD//Ray Amos | 2024-04-08 | Celcom Digi_RAN-GTSB-TSS-Sabah-20240324 | DU00002863386 |  | No MW part info (NE/FE) |  |  | 2024-10-23 |  | TOWER
S00185 | S105A_S00185OD_WISMAHARBOUR | Sabah |  | Decomm |  | 2024 Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2024-04-26 |  |  |  | 2024-05-08 |  | 2024-05-10 | 2024-09-13 | CD//Ray Amos | 2024-05-13 | Celcom Digi_RAN-YPTT-Standard PR TSS-Sabah-20240503 | DU00002863387 |  |  |  |  | 2025-02-27 |  | BOOM
S00192 | S105B_S00192OD_KIMFUNG | Sabah |  | Decomm |  | 2024 Q3 | SH | GTSB | 4.6 TSSR Approved |  | 2024-03-19 |  |  |  | 2024-04-03 |  | 2024-04-04 | 2024-09-26 | CD//Ray Amos | 2024-04-04 | Celcom Digi_RAN-GTSB-TSS-Sabah-20240324 | DU00002863388 |  |  |  |  | 2024-08-15 |  | BOOM
S00172 | S105A_S00172OD_RAMAIRAMAI | Sabah |  | Decomm | Decomm->On Hold->Decomm->On Hold->Swap->Decomm | 2024 Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2024-04-26 | 2025-04-07 |  | 2025-05-08 | 2024-05-02 | Under Approval | 2024-05-03 | 2024-05-24 | E//Hannah | 2025-05-09 | Celcom Digi RAN YPTT Standard PR TSS-Sabah-20241205 | DU00002863389 |  | SOW Changed from Decomm to Swap |  |  | 2025-09-05 | In-Building System | BOOM | 6 | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
S00196 | S105B_S00196OD_TMNUNUYAN | Sabah |  | Decomm |  | 2024 Q3 | AD | Futong | 4.6 TSSR Approved |  | 2024-07-16 |  | 2024-07-20 |  | 2024-07-23 |  | 2024-07-30 | 2024-10-25 | CD//Ray Amos | 2024-08-05 | 0719Sabah-Futong-BOQ Template | DU00002863390 |  |  |  |  | 2024-08-23 |  | TOWER
4991A | UUM | Northern |  | Modernization |  | 2024 Q3 | SM | YPTT | 4.6 TSSR Approved |  | 2023-10-26 | 2023-10-27 |  | 2023-11-01 |  | Closed | 2024-04-05 | 2024-04-15 | E//Hazida | 2024-04-05 | Celcom Digi_RAN-YPTT-TSS-Northern-20231028-0040 | DU00002863391 |  |  | 2024-04-22 | 2024-04-18 |  | Tower | 48m 3 Legged Tower | 60m | Add R8852E S9000 x3+R9224E M1821 x2+R8854 S2600 x2,Dismantle R8862A S2600(A4A) x2 | 0 | 12
4993A | Bandar Darul Aman(ZED) | Northern |  | Modernization |  | 2024 Q3 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-10-12 | 2023-10-26 |  | 2024-03-21 |  | Closed | 2024-03-22 | 2024-03-25 |  | 2024-03-22 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231013-0054 | DU00002863392 |  |  | 2024-04-17 | 2024-04-16 |  | Tower | 45m 3 Legged Tower | 69 | Add R8862A S9000 x3+A9732 M1821 x3,Dismantle R8860E-GU908 x2+R8882-GUL1812 x3+R8862A S2100(A6A) x6 | 123 | 0
S00191 | S105A_S00191OD_TMBTSAPI | Sabah | 7286K | Swap | Decomm->On Hold->Swap | 2024 Q3 | AD | Datasco | 4.6 TSSR Approved |  | 2024-06-19 | 2024-06-28 |  | 2024-07-12 |  | Under Approval | 2024-10-16 | 2024-10-17 | CD//Ray Amos | 2024-10-17 | Celcom Digi_RAN-Datasco-Standard PR TSS-Sabah-20240621 | DU00002863393 |  |  | 2024-11-28 | 2024-11-18 |  | Tower | TOWER | 60 | Add R8862A S9000 x3+R8894E M1821 x5+R8862A S2601 x1+R8854 S2600 x2,Dismantle | 0 | 23
S01101 | S105B_S01101OD_PASARBT8 | Sabah |  | Decomm |  | 2025 Q2 | MS | Futong | 4.6 TSSR Approved |  | 2024-04-30 |  |  |  | 2024-04-30 |  | 2024-05-08 | 2024-09-26 | CD//Ray Amos | 2024-05-09 | Celcom Digi_RAN-Futong-Standard PR TSS-Sabah-20240503 / SQ202501020444 - Futong | DU00002863394 |  |  |  |  | 2024-07-29 |  | UNIPOLE
S00214 | S105B_S00214OD_BDRINDAH | Sabah |  | Decomm |  | 2024 Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2024-03-19 |  |  |  | 2024-03-20 |  | 2024-04-08 | 2024-11-22 | CD//Ray Amos | 2024-04-08 | Celcom Digi_RAN-GTSB-TSS-Sabah-20240324 | DU00002863395 |  |  |  |  | 2024-08-16 |  | BOOM
S00206 | S105B_S00206OD_JLNAIRPORTSDK | Sabah | 7284K | Swap | Decomm->On Hold->Decomm->On Hold->Swap | 2024 Q3 | AD | Datasco | 4.6 TSSR Approved |  | 2024-04-18 | 2025-04-04 |  | 2025-04-16 | 2024-04-25 | Under Approval | 2025-04-21 | 2025-04-22 | CD//Sharidah | 2025-04-22 | Celcom Digi_RAN-Datasco-Standard PR TSS-Sabah-20240420 | DU00002863396 |  |  | 2025-07-06 | 2025-05-28 |  | Tower | TOWER | 60 | Add R8852E S9000x4+R9264M M1821x3+A9732 M1821x1+R8854 S2600x3+R8862A S2601x1, Dismantle | 3 | 12
S00189 | S105A_S00189OD_SIMSIM | Sabah |  | Decomm |  | 2024 Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2024-04-27 |  |  |  | 2024-05-03 |  | 2024-05-07 | 2024-05-24 | CD//Ray Amos | 2024-05-10 | Celcom Digi_RAN-YPTT-Standard PR TSS-Sabah-20240503 | DU00002863397 |  |  |  |  | 2024-10-04 |  | SHARING STRC OTHERS MINARATE
S01561 | S089A_S01561OD_CB_BELURANTOWN | Sabah |  | Decomm |  | 2024 Q3(single site MOCN) | MS | GTSB | 4.6 TSSR Approved |  | 2024-04-30 | 2024-06-20 |  |  | 2024-05-28 |  | 2024-06-25 | 2024-11-15 | CD//Ray Amos | 2024-06-26 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240503 | DU00002863398 |  |  |  |  | 2024-09-30 | Tower | TOWER | 75
S00266 | S111A_S00266OD_CB_PERKASATENOM | Sabah |  | Decomm |  | 2025 Q2 | AI | YPTT | 4.6 TSSR Approved |  | 2025-01-07 |  | 2025-01-14 |  | 2025-01-24 |  | 2025-02-22 | 2025-09-10 | CD//Sharidah | 2025-03-07 | SQ202501030034 - YPTT | DU00002863399 |  |  |  |  | 2025-08-14 | In-Building System | BOOM | 3.5
S00306 | S111A_S00306OD_CB_TMSAPONG | Sabah |  | Decomm |  | 2024 Q4 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2024-11-12 |  | 2024-11-13 |  | 2024-11-14 |  | 2024-11-15 | 2024-12-13 | CD//Sharidah | 2024-11-18 | 0928MW-Sabah-SeriPancar-BOQ Template(new contract)//0928CD-Sabah-SeriPancar-BOQ Template(new contract) | DU00002863400 |  |  |  |  | 2025-11-29 |  | TOWER
S00312 | S107A_S00312OD_BKTTUNGGUL | Sabah |  | Decomm |  | 2025 Q2 | SHA | Seri Pancar | 4.6 TSSR Approved |  | 2024-01-11 |  |  |  | 2024-06-28 |  | 2025-01-06 | 2025-01-07 | CD//Sharidah | 2025-01-07 | Celcom Digi_RAN-Seri Pancar-Standard PR TSS-Sabah-20240116 / SQ202501020446 - Seri Pancar | DU00002863401 |  |  |  |  | 2025-04-21 |  | TOWER
B00486 | W066Z_B00486OD_PANDANJAYA | Central |  | Decomm |  | 2024 Q2 | MS | GTSB | 4.6 TSSR Approved |  | 2024-03-13 |  |  |  | 2024-04-18 |  | 2024-07-18 | 2025-01-14 | CD//Norhaliza | 2024-10-04 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240316 | DU00002863402 |  |  |  |  | 2024-08-10 |  | TOWER
9205A | Sebangkoi | Sarawak |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q2 | SM | Magicell | 4.6 TSSR Approved |  | 2024-01-02 | 2024-02-13 |  | 2025-02-06 |  | Under Approval | 2025-02-07 | 2025-02-18 | E//Hannah | 2025-02-18 | Celcom Digi_RAN-Magicell-Standard PR TSS-Sarawak-20240109 | DU00002863403 | [5 empty] | Tower | Tower | 88 | Reuse Existing RRU | 0 | 0
S01587 | S104A_S01587OD_CB_KGMARAKAURANAU | Sabah |  | Decomm |  | 2024 Q3(single site MOCN) | MS | Seri Pancar | 4.6 TSSR Approved |  | 2024-06-18 |  |  |  | 2024-06-21 |  | 2024-06-24 | 2024-08-01 | CD//Ray Amos | 2024-06-26 | Celcom Digi_RAN-Seri Pancar-Standard PR TSS-Sabah-20240621 | DU00002863404 |  |  |  |  | 2024-10-14 |  | TOWER
X00192 | S104A_X00192OD_PDRMRANAU | Sabah |  | Decomm |  | 2025 Q3 | HW | NR services | 4.6 TSSR Approved |  | 2025-01-07 |  | 2025-01-28 |  | 2025-02-05 |  | 2025-02-24 | 2025-05-02 | CD//Sharidah | 2025-02-26 | SQ202501020449 - NR Service / SQ202501070289 - NR Service | DU00002863405 |  |  |  |  | 2025-04-28 |  | #N/A
S00140 | S104A_S00140OD_CB_TANAHMERAH | Sabah | 7291K | Swap | Decomm->On hold->Swap | 2024 Q3(single site MOCN) | MS | Seri Pancar | 4.6 TSSR Approved |  | 2024-06-18 | 2024-10-14 |  | 2024-10-16 |  | Under Approval | 2024-10-17 | 2024-10-29 | CD//Ray Amos | 2024-10-29 | 0923CD-Sabah-Seri Pancar-BOQ Template(new contract) | DU00002863406 |  |  | 2024-12-13 | 2024-10-28 |  | Tower | TOWER | 76 | Add R8852E S9000 x3+R8894E M1821 x6+R8854 S2600 x3,Dismantle | 0 | 123
S00148 | S104A_S00148OD_PORING | Sabah |  | Decomm |  | 2024 Q4 |  | NR services | 4.6 TSSR Approved |  | 2024-09-11 | 2026-02-14 | 2024-09-08 |  |  |  | 2024-09-11 | 2025-10-28 | CD//Sharidah | 2024-09-18 | Celcom Digi_RAN NR Service Standard PR TSS-Sabah-20241119 | DU00002863407 |  |  |  |  | 2024-11-01 |  | TOWER
S00502 | S104A_S00502OD_CB_BUNDUTUHAN | Sabah |  | Decomm |  | 2025 Q3 | HW | NR services | 4.6 TSSR Approved |  | 2025-01-08 |  | 2025-01-27 |  | 2025-02-07 |  | 2025-02-23 | 2025-09-12 | CD//Sharidah | 2025-02-24 | SQ202501020449 - NR Service | DU00002863408 |  |  |  |  | 2025-07-28 |  | TOWER
S00159 | S104A_S00159OD_CB_MASILAU | Sabah |  | Decomm |  | 2024 Q4 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2024-10-03 |  | 2024-10-14 |  | 2024-10-15 |  | 2024-10-16 | 2024-12-13 | CD//Ray Amos | 2024-10-17 | 0928CD-Sabah-SeriPancar-BOQ Template(new contract) | DU00002863409 |  |  |  |  | 2024-11-05 |  | TOWER
S00393 | S098A_S00393OD_CB_TAMBISAN | Sabah |  | Decomm |  | 2024 Q3(single site MOCN) | AD | Seri Pancar | 4.6 TSSR Approved |  | 2024-06-13 |  |  |  | 2024-06-22 |  | 2024-06-24 | 2024-08-29 | CD//Ray Amos | 2024-06-26 | 0618Sabah-Seri Pancar-BOQ Template (template) | DU00002863410 |  |  |  |  | 2024-10-22 |  | TOWER
S00706 | S098B_S00706OD_KGKATAGADAN | Sabah |  | Decomm |  | 2024 Q3(single site MOCN) | MS | Seri Pancar | 4.6 TSSR Approved |  | 2024-06-11 |  |  |  | 2024-06-23 |  | 2024-06-25 | 2024-09-26 | CD//Ray Amos | 2024-06-26 | 0618Sabah-Seri Pancar-BOQ Template (template) | DU00002863411 |  |  |  |  | 2024-09-11 |  | TOWER
S00449 | S098C_S00449OD_JLNSEGAMA | Sabah |  | Decomm |  | 2024 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2024-05-15 |  |  |  | 2024-05-17 |  | 2024-05-21 | 2024-06-28 | CD//Ray Amos | 2024-05-23 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240519 | DU00002863412 |  |  |  |  | 2024-07-15 |  | TOWER
S00281 | S088A_S00281OD_BANDAU | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | MNO | Datasco | 4.6 TSSR Approved |  | 2025-05-19 |  | 2025-07-09 |  | 2025-07-17 |  | 2025-07-26 | 2025-10-13 | CD//Ray Amos | 2025-09-23 | SQ202504100595 - Datasco | DU00002863413 |  |  |  |  | 2025-08-21 |  | GUYED MAST
S00299 | S088A_S00299OD_CB_TMMEMBAKUT | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4 | AD | DATASCO | 4.6 TSSR Approved |  | 2025-01-20 |  | 2025-02-26 |  | 2025-04-10 |  | 2025-04-29 | 2025-10-28 | CD//Sharidah | 2025-04-30 | SQ202504140321 - Datasco | DU00002863414 |  |  |  |  | 2025-10-15 |  | BOOM
S00548 | S098B_S00548OD_KGSARIP | Sabah |  | Decomm |  | 2024 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2024-05-15 |  |  |  | 2024-05-20 |  | 2024-05-21 | 2024-11-15 | CD//Ray Amos | 2024-05-23 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240519 | DU00002863415 |  |  |  |  | 2024-07-16 |  | TOWER
S00461 | S092A_S00461OD_TAGINAMBUR | Sabah |  | Decomm |  | 2024 Q3(single site MOCN) | AD | Seri Pancar | 4.6 TSSR Approved |  | 2024-06-25 |  |  |  | 2024-06-28 |  | 2024-07-02 | 2024-09-05 | CD//Ray Amos | 2024-07-02 | 0626Sabah-Seri Pancar-BOQ Template (template) | DU00002863416 |  |  |  |  | 2025-02-08 |  | TOWER
S00334 | CBRICHARDLIND | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2024 Q3(single site MOCN) | AD | Seri Pancar | 4.6 TSSR Approved |  | 2024-06-27 |  | 2024-07-15 |  | 2024-10-14 |  | 2024-10-15 | 2025-10-28 | CD//Sharidah | 2024-10-16 | PR raised as per design team | DU00002863417 |  |  |  |  | 2024-12-18 |  | TOWER
S00533 | S089A_S00533OD_CB_MILE75 | Sabah |  | Decomm |  | 2024 Q3(single site MOCN) | AD | GTSB | 4.6 TSSR Approved |  | 2024-04-08 |  |  |  | 2026-01-13 |  | 2024-07-01 |  | CD//Ray Amos | 2024-07-01 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240420 | DU00002863418 |  | Please provide FE drawing. |  |  | 2024-10-16 |  | TOWER
S00578 | S091A_S00578OD_CB_PINBESAR | Sabah |  | Decomm |  | 2024 Q4(single site MOCN)-L2126 SSM | SH | Seri Pancar | 4.6 TSSR Approved |  | 2024-07-22 |  | 2024-07-31 |  | 2024-08-02 |  | 2024-08-05 | 2024-09-13 | CD//Ray Amos | 2024-08-06 | 0725Sabah-Seri Pancar-BOQ Template(new contract)/0725MW-Sabah-Seri Pancar-BOQ Template(new contract) | DU00002863419 |  |  |  |  | 2024-11-27 |  | TOWER
S00412 | S105B_S00412OD_TMNMEGAHSDK | Sabah |  | Decomm |  | 2024 Q3 | MS | GTSB | 4.6 TSSR Approved |  | 2024-03-25 |  |  |  | 2024-04-02 |  | 2024-04-03 | 2024-11-15 | CD//Ray Amos | 2024-04-30 | Celcom Digi_RAN-GTSB-TSS-Sabah-20240329 | DU00002863420 |  |  |  |  | 2024-08-05 |  | TOWER
R00051 | R001B_R00051OD_BT2KANGAR | Northern |  | Decomm |  | 2024 Q4 | SH | GCI | 4.6 TSSR Approved | ¦ 0918 - CD Zul: Please confirm the structure height. This is co-located pairing sites. R00051 structure height = 45m, antenna at 35m. Pair site 4612A structure height = 50m, antenna at = 48m. Please confirm that serving site antenna is at the highest position. Missing pair site info in master list. | 2024-05-03 |  |  |  | 2024-05-06 |  | 2024-09-27 | 2024-10-01 | CD//Zulakmar | 2024-09-30 | Celcom Digi_RAN-GCI-TSS-Northern-20240512-0106 | DU00002863421 |  |  |  |  | 2024-09-24 |  | TOWER
L00025 | S113A_L00025OD_RANCHARANCHA | Sabah |  | Decomm |  | 2024 Q3(single site MOCN) | AD | Datasco | 4.6 TSSR Approved |  | 2024-07-10 |  | 2024-08-05 |  | 2024-08-09 |  | 2024-08-12 | 2024-09-26 | CD//Sharidah | 2024-08-12 | 0920CD-Sabah-Datasco-BOQ Template (old contract) | DU00002863422 |  |  |  |  | 2024-11-13 |  | TOWER
L00028 | S113A_L00028OD_TGARULBN | Sabah |  | Decomm |  | 2024 | MS | Datasco | 4.6 TSSR Approved |  | 2024-11-11 |  | 2024-11-14 |  | 2024-11-20 |  | 2024-11-21 | 2024-12-13 | CD//Ray Amos | 2024-11-21 | Celcom Digi_RAN-Datasco-Standard PR TSS-Sabah-20241030 | DU00002863423 |  |  |  |  | 2025-04-24 |  | TOWER
S00179 | S089A_S00179OD_CB_ULUSAPI | Sabah |  | Decomm |  | 2024 Q3(single site MOCN) | MS | GTSB | 4.6 TSSR Approved |  | 2024-04-08 |  |  |  | 2024-04-22 |  | 2024-04-30 | 2025-05-02 | CD//Ray Amos | 2024-05-01 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240420 | DU00002863424 |  |  |  |  | 2024-10-15 |  | TOWER
S01139 | S091A_S01139OD_MORISEM | Sabah |  | Decomm |  | 2024 Q3(single site MOCN) | SHA | Seri Pancar | 4.6 TSSR Approved |  | 2024-06-13 |  |  |  | 2024-07-09 |  | 2024-07-12 | 2024-09-26 | CD//Ray Amos | 2024-07-15 | 0618Sabah-Seri Pancar-BOQ Template (template) | DU00002863425 |  |  |  |  | 2024-10-14 |  | TOWER
S01208 | RL10103_FAJARHOTELDU | Sabah |  | Decomm |  | 2024 Q3 | MS | GTSB | 4.6 TSSR Approved |  | 2024-05-08 |  |  |  | 2024-05-14 |  | 2024-05-20 | 2024-06-28 | CD//Ray Amos | 2024-06-05 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240510 | DU00002863426 |  |  |  |  | 2024-07-24 |  | Rooftop
B00485 | W066Y_B00485OD_TMNMAWAR | Central |  | Decomm |  | 2024 Q3 | AI | YPTT | 4.6 TSSR Approved |  | 2024-06-04 |  | 2024-07-01 |  | 2024-07-04 |  | 2024-07-24 | 2024-09-25 | CD//Sapian | 2024-07-31 | 0607Central-YPTT-BOQ Template | DU00002863427 |  |  |  |  | 2024-08-27 |  | BOOM
S00487 | S098C_S00487OD_KGKOKOS | Sabah |  | Decomm |  | 2024 Q3(single site MOCN) | MS | Seri Pancar | 4.6 TSSR Approved |  | 2024-06-11 |  |  |  | 2024-06-23 |  | 2024-06-25 | 2024-08-09 | CD//Ray Amos | 2024-06-26 | 0618Sabah-Seri Pancar-BOQ Template (template) | DU00002863428 |  |  |  |  | 2024-09-09 |  | TOWER
S00528 | S098C_S00528OD_KGWAWASAN | Sabah |  | Decomm |  | 2024 Q3(single site MOCN) | MS | Seri Pancar | 4.6 TSSR Approved |  | 2024-06-11 |  |  |  | 2024-07-05 |  | 2024-07-09 | 2024-11-29 | CD//Ray Amos | 2024-07-10 | 0618Sabah-Seri Pancar-BOQ Template (template) | DU00002863429 |  |  |  |  | 2024-10-15 |  | TOWER
S00202 | S105B_S00202OD_TMNMERPATI | Sabah |  | Decomm |  | 2024 Q3 | AD | Datasco | 4.6 TSSR Approved |  | 2024-04-19 |  |  |  | 2024-05-01 |  | 2024-05-02 | 2024-05-24 | CD//Ray Amos | 2024-05-03 | Celcom Digi_RAN-Datasco-Standard PR TSS-Sabah-20240420 | DU00002863430 |  |  |  |  | 2024-07-26 |  | SHARING STRC DIGI
S00465 | S105B_S00465OD_KGTINOSA | Sabah |  | Decomm |  | 2024 Q3 | AD | Datasco | 4.6 TSSR Approved |  | 2024-04-27 |  |  |  | 2024-05-03 |  | 2024-05-08 | 2024-07-24 | CD//Ray Amos | 2024-05-09 | Celcom Digi_RAN-Datasco-Standard PR TSS-Sabah-20240503 | DU00002863431 |  |  |  |  | 2024-07-29 |  | TOWER
S00168 | S105B_S00168OD_TMNSIBUGA | Sabah |  | Decomm |  | 2024 | MS | Futong | 4.6 TSSR Approved |  | 2024-03-23 |  |  |  | 2024-03-25 |  | 2024-03-29 | 2024-05-24 | CD//Ray Amos | 2024-04-04 | Celcom Digi_RAN-Futong-TSS-Sabah-20240329 | DU00002863432 |  |  |  |  | 2025-02-27 |  | TOWER
S01204 | S089A_S01204OD_KGGARINONO | Sabah |  | Decomm |  | 2025 Q2 | MS | Futong | 4.6 TSSR Approved |  | 2024-04-24 |  |  |  | 2024-04-25 |  | 2024-04-25 | 2024-08-29 | CD//Ray Amos | 2024-05-08 | Celcom Digi_RAN-Futong-Standard PR TSS-Sabah-20240503 / SQ202501020444 - Futong / SQ202501070242 - Futong | DU00002863433 |  |  |  |  | 2024-09-20 |  | RAPID ASSEMBLY POLE (RAPOLE)
S00511 | S105B_S00511OD_KGSGBATANG | Sabah |  | Decomm |  | 2025 Q2 | MS | Futong | 4.6 TSSR Approved |  | 2024-03-26 |  |  |  | 2024-04-01 |  | 2024-04-01 | 2024-09-13 | CD//Ray Amos | 2024-04-04 | Celcom Digi_RAN-Futong-Standard PR TSS-Sabah-20240406 / SQ202501020444 - Futong / SQ202501070242 - Futong | DU00002863434 |  |  |  |  | 2024-07-23 |  | TOWER
S00562 | S089A_S00562OD_CB_MILE46 | Sabah |  | Decomm |  | 2024 Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2024-04-04 |  |  |  | 2024-05-08 |  | 2024-05-09 | 2024-08-09 | CD//Ray Amos | 2024-05-10 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240406 | DU00002863435 |  |  |  |  | 2024-10-15 |  | TOWER
S00518 | S091A_S00518OD_KGPARIS2 | Sabah |  | Decomm |  | 2024 Q3(single site MOCN) | MS | Seri Pancar | 4.6 TSSR Approved |  | 2024-06-13 |  |  |  | 2024-06-22 |  | 2024-06-24 | 2024-08-01 | CD//Ray Amos | 2024-06-26 | 0618Sabah-Seri Pancar-BOQ Template (template) | DU00002863436 |  |  |  |  | 2024-09-12 |  | TOWER
S00209 | S091A_S00209OD_SEGALIUD | Sabah |  | Decomm |  | 2024 Q4(single site MOCN)-L2126 SSM | MS | GTSB | 4.6 TSSR Approved |  | 2024-07-25 |  | 2024-08-06 |  | 2024-08-08 |  | 2024-08-09 | 2024-11-29 | CD//Ray Amos | 2024-08-11 | 0725Sabah-GTSB-BOQ Template(new contract) | DU00002863437 |  |  |  |  | 2024-12-05 |  | TOWER
S00320 | S098B_S00320OD_CB_MTSILAM | Sabah |  | Decomm |  | 2024 Q3(single site MOCN) | MS | Seri Pancar | 4.6 TSSR Approved |  | 2024-06-27 |  |  |  | 2024-07-05 |  | 2024-07-11 | 2024-11-15 | CD//Ray Amos | 2024-07-12 | 0701Sabah-Seri Pancar-BOQ Template (template) | DU00002863438 |  |  |  |  | 2024-09-27 |  | TOWER
B01361 | B064F_B01361OD_REKOSENTRAL | Central |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4(single site MOCN)-L2126 SSM | AI | GTSB | 4.6 TSSR Approved |  | 2024-10-01 |  | 2024-10-07 |  | 2024-10-17 |  | 2024-11-20 | 2024-12-31 | CD//Sapian | 2024-12-02 | SQ202411190433 | DU00002863439 |  |  |  |  | 2024-11-30 |  | BOOM
B02840 | B057C_B02840OD_BILLBOARD_GIANTBTCAVES | Central |  | Decomm |  | 2024 Q1 | BY | Magicell | 4.6 TSSR Approved |  | 2024-02-02 |  |  |  | 2024-02-22 |  | 2024-02-23 | 2024-05-12 | CD//Sapian | 2024-03-11 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240212 | DU00002863440 |  |  |  |  | 2024-04-05 |  | BILLBOARD
7039A | Donggongon | Sabah |  | Modernization |  | 2024 Q3 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2023-10-24 | 2023-10-26 |  | 2023-11-02 |  | Closed | 2024-04-02 | 2024-04-05 | E//Hannah | 2024-04-05 | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231028 | DU00002863441 |  |  | 2024-04-30 | 2024-04-26 |  | Tower | 45m 4 Legged Tower | 45 | Resue existing RRU | 0 | 123
S00556 | S107A_S00556OD_SPGMANDULONG | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4 | MS | Seri Pancar | 4.6 TSSR Approved |  | 2024-10-04 |  | 2024-10-15 |  | 2024-10-15 |  | 2024-10-17 | 2025-10-28 | CD//Ray Amos | 2024-10-16 | 0928CD-Sabah-SeriPancar-BOQ Template(new contract) | DU00002863442 |  |  |  |  | 2024-11-06 |  | TOWER
S00291 | S100A_S00291OD_BONGAWAN | Sabah |  | Site Out (Decomm) | Decomm->On Hold->Decomm->Site Out->Site Out (Decomm) | 2024 Q3(single site MOCN) | MS | Seri Pancar | 4.6 TSSR Approved | Site cannot maintained | 2024-06-10 |  |  |  | 2024-06-26 |  | 2024-06-26 | 2025-10-17 | CD//Ray Amos | 2024-08-26 | 0610Sabah-Seri Pancar-BOQ Template (template) | DU00002863443 |  |  |  |  | 2025-06-26 |  | TOWER
L00002 | S113A_L00002OD_TIMBALAI | Sabah |  | Decomm | Decomm->On hold->Swap->On hold->Decomm | 2024 Q3(single site MOCN) | AD | Datasco | 4.6 TSSR Approved |  | 2024-08-02 |  | 2024-11-25 |  | 2024-11-26 |  | 2024-11-27 | 2025-01-31 | CD//Sharidah | 2024-11-27 | Celcom Digi_RAN Datasco Standard PR TSS-Sabah-20241118 (SQ202411180096) | DU00002863444 |  |  |  |  | 2025-02-04 |  | TOWER
S00143 | S094A_S00143OD_LOTONG | Sabah |  | Decomm |  | 2025 Q3 | HW | GTSB | 4.6 TSSR Approved |  | 2025-01-09 |  | 2025-03-06 |  | 2025-03-14 |  | 2025-03-14 | 2025-05-02 | CD//Sharidah | 2025-03-17 | SQ202501020455 - GTSB / SQ202501070280 - GTSB | DU00002863445 |  |  |  |  | 2025-04-29 |  | TOWER
S00610 | S088A_S00610OD_JKRBEAUFORT | Sabah |  | Decomm |  | 2024 Q3(single site MOCN) | MS | Seri Pancar | 4.6 TSSR Approved |  | 2024-06-10 |  |  |  | 2024-06-26 |  | 2024-06-26 | 2024-08-09 | CD//Ray Amos | 2024-07-01 | 0610Sabah-Seri Pancar-BOQ Template (template) | DU00002863446 |  |  |  |  | 2024-09-26 |  | TOWER
7231A | Sabah Credit Corp | Sabah |  | Modernization |  | 2024 Q3 | AD | Seri Pancar | 4.6 TSSR Approved | 5/4: Trigger ZTE Rollout for PE structure analysis | 2023-10-25 | 2023-11-24 |  | 2024-04-02 |  | Closed | 2024-04-04 | 2024-04-05 | E//Hannah | 2024-04-05 | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231028 | DU00002863447 |  |  | 2024-10-04 | 2024-09-20 |  | In-Building System | 3m RT (Minimast) | 9 | Add A9732 M1821 x3,Dismantle R9224E M1821(AAB) x4 | 123 | 0
7277A | Jln KK-Tambunan (Moyong) | Sabah |  | Modernization |  | 2024 Q3 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2023-10-25 | 2023-10-26 |  | 2023-10-31 |  | Closed | 2024-03-25 | 2024-04-05 | E//Hannah | 2024-04-05 | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231028 | DU00002863448 |  |  | 2024-04-30 | 2024-04-24 |  | Tower | 76m 3 Legged Tower | 76 | Add R8862A S9000 x1+R8894E M1821 x1+R8862A S2601 x1,Dismantle | 0 | 0
7279A | Babagon | Sabah |  | Modernization |  | 2024 Q3 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2023-10-24 | 2023-10-27 |  | 2023-11-02 |  | Closed | 2024-04-04 | 2024-04-05 | E//Hannah | 2024-04-05 | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231028 | DU00002863449 |  |  | 2024-05-16 | 2024-05-07 |  | Tower | Tower | 76 | Add A9732 M1821 x2,Dismantle R8894E M1821(A8A) x2 | 13 | 0
7289A | Limbanak | Sabah |  | Modernization |  | 2024 Q3 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2023-10-25 | 2023-10-27 |  | 2023-11-01 |  | Closed | 2024-03-27 | 2024-04-05 | E//Hannah | 2024-04-05 | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231028 | DU00002863450 |  |  | 2024-05-03 | 2024-04-24 |  | Tower | Tower | 60 | Add R8894E M1821 x2+R8854 S2600 x2,Dismantle R8862A S2600(A4A) x2 | 0 | 13
7291A | Kasigui Housing | Sabah |  | Modernization |  | 2024 Q3 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2023-10-23 | 2023-10-30 |  | 2023-11-01 |  | Closed | 2024-04-02 | 2024-04-05 | E//Hannah | 2024-04-05 | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231024 | DU00002863451 |  |  | 2024-05-06 | 2024-04-27 |  | Tower | Tower | 60m | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3 | 13 | 0
7320A | KG NAMPASAN | Sabah |  | Modernization |  | 2024 Q3 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2023-11-13 | 2023-11-15 |  | 2023-11-22 |  | Closed | 2024-04-03 | 2024-04-15 | E//Hannah | 2024-04-08 | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231119 | DU00002863452 |  |  | 2024-05-14 | 2024-05-08 |  | Tower | 45m 4 Legged Tower | 45m | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123 | 0
7343A | SMK Tambunan | Sabah |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | MS | Futong | 4.6 TSSR Approved |  | 2023-10-30 | 2023-11-03 |  | 2024-10-29 |  | Rectificating | 2024-11-26 | 2024-11-27 | E//Syahriani | 2024-11-27 | Celcom Digi_RAN-Futong-TSS-Sabah-20231101 | DU00002863453 |  |  | 2024-12-27 | 2024-11-26 |  | Tower | 45m 3 Legged Tower | 45 | Add A9732 M1821 x3, Dismantle R8894E M1821(A8A)x3 | 234 | 0
7347A | Sinsuron | Sabah |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | MS | Futong | 4.6 TSSR Approved |  | 2023-10-27 | 2023-10-30 |  | 2023-11-01 |  | Under Approval | 2024-10-21 | 2025-05-27 | E//Hannah | 2025-05-26 | Celcom Digi_RAN-Futong-TSS-Sabah-20231028 | DU00002863454 |  |  | 2024-11-12 | 2024-11-12 |  | Tower | Tower | 65 | Add A9732 M1821x1, Dismantle R8894E M1821(A8A)x1 | 2 | 0
7403A | Kg Wokok | Sabah |  | Modernization |  | 2024 Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-10-24 | 2023-11-01 |  | 2024-03-27 |  | Closed | 2024-03-28 | 2024-04-02 | E//Hannah | 2024-04-02 | Celcom Digi_RAN-YPTT-TSS-Sabah-20231028 | DU00002863455 |  |  | 2024-05-18 | 2024-05-07 |  | Tower | 76m Tower | 49 | Add R8862A S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8854D S2100(A4A) x3+R8862A S2600(A4A) x1 | 0 | 3
7406A | Kg Rajunah | Sabah |  | Modernization |  | 2024 Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-10-24 | 2024-03-20 |  | 2024-04-03 |  | Closed | 2024-04-04 | 2024-04-16 | E//Hannah | 2024-04-16 | Celcom Digi_RAN-YPTT-TSS-Sabah-20231024 | DU00002863456 |  |  | 2024-04-30 | 2024-04-26 |  | Tower | 60m 3 Legged Tower | 60 | Add R9224E M1821 x4+R8854 S2600 x1,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3+R8862A S2601(A6A) x1 | 0 | 2
7414A | Jln K.Belud-K.Ambai | Sabah |  | Modernization |  | 2024 Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-10-22 | 2023-10-24 |  | 2023-10-26 |  | Closed | 2024-03-25 | 2024-04-19 | E//Hannah | 2024-04-19 | Celcom Digi_RAN-YPTT-TSS-Sabah-20231024 | DU00002863457 |  |  | 2024-05-06 | 2024-04-30 |  | Tower | 76m Tower | 60 | Add R8862A S9000 x3+A9732 M1821 x2,Dismantle R8862A S2601(A6A) x2+R8894E M1821(A8A) x4 | 12 | 0
7415A | USP Kg. Bangkahak | Sabah |  | Modernization |  | 2024 Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-10-27 | 2023-11-14 |  | 2024-03-28 |  | Closed | 2024-04-02 | 2024-04-19 | E//Hannah | 2024-04-19 | Celcom Digi_RAN-YPTT-TSS-Sabah-20231028 | DU00002863458 |  |  | 2024-05-20 | 2024-05-08 |  | Tower | 57m 4 Legged Tower | 30 | Add R8862A S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882-GUL1812 x3+R8862A S2600(A4A) x1 | 0 | 1
7464B | Kg. Dandulit _ Sg. Beruang | Sabah |  | Modernization |  | 2024 Q4 | MS | Futong | 4.6 TSSR Approved |  | 2024-03-18 | 2024-03-20 |  | 2024-04-04 |  | Closed | 2024-04-05 | 2024-06-21 | E//Hannah | 2024-06-06 | 0610Sabah-Futong-BOQ Template (template) | DU00002863459 |  |  | 2024-06-13 | 2024-06-04 |  | Tower | 60m 4 Legged Tower | 60 | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle | 0 | 3
7571A | Sepilok Land | Sabah |  | Modernization |  | 2024 Q4 | MS | Futong | 4.6 TSSR Approved |  | 2024-03-18 | 2024-03-20 |  | 2024-04-05 |  | Closed | 2024-06-10 | 2024-06-14 | E//Hannah | 2024-06-11 | Celcom Digi_RAN-Futong-TSS-Sabah-20240324 | DU00002863460 |  |  | 2024-06-12 | 2024-06-04 |  | Tower | Tower | 75 | Add R8862A S9000 x2+R9224E M1821 x4+R8854 S2600 x1,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x2+R8862A S2100(A6A) x3+R8862A S2601(A6A) x1 | 0 | 1
7532B | Trusjaya Sukau | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-02-06 | 2025-02-10 |  | 2025-02-12 |  | Under Approval | 2025-02-19 | 2025-03-09 | E//Hannah | 2025-02-24 | SQ202501020392 - Futong | DU00002863461 |  |  | 2025-03-13 | 2025-03-06 |  | Tower | Tower | 60m | Add R8894E M1821 x1 | 0 | 1
K00219 | K002A_K00219OD_PRTPANJANG | Northern |  | Decomm |  | 2024 Q4 | SHA | CCSMY | 4.6 TSSR Approved |  | 2023-12-04 |  |  |  | 2024-09-27 |  | 2024-09-30 | 2024-10-03 | CD//Zulakmar | 2024-10-02 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231204-0076 | DU00002863462 |  |  |  |  | 2024-11-04 |  | TOWER
Q01538 | Q123A_Q01538OD_CB_TMNBKTGORAM2 | Sarawak |  | Decomm |  | 2025 Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2024-03-20 |  |  |  | 2024-03-25 |  | 2024-03-25 | 2024-09-05 | CD//John | 2024-03-25 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20240324 | DU00002863463 |  |  |  |  | 2025-06-28 |  | RAMO
Q01038 | Q135A_Q01038OD_TMNMAKMUR | Sarawak |  | Decomm |  | 2024 Q2 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-11-20 |  |  |  | 2023-11-30 |  | 2023-12-01 | 2024-03-21 | CD//John | 2023-12-01 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231126 | DU00002863464 |  |  |  |  | 2025-06-14 |  | TOWER
Q00092 | Q139A_Q00092OD_AYERMANIS | Sarawak |  | Decomm |  | 2025 Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2024-02-27 |  |  |  | 2024-02-29 |  | 2024-03-01 | 2024-04-24 | CD//John | 2024-04-03 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240302 | DU00002863465 |  |  |  |  | 2025-04-29 |  | TOWER
Q00026 | Q135A_Q00026OD_KSNBYPASS | Sarawak |  | Decomm |  | 2024 Q2 | ZB | Magicell | 4.6 TSSR Approved |  | 2024-01-18 |  |  |  | 2023-11-14 |  | 2024-01-18 | 2024-02-09 | CD//John | 2024-01-20 | CelcomDigi_RAN_Magicell_TSS_Central_20240124 | DU00002863466 |  |  |  |  | 2025-02-03 |  | GUYED MAST
Q00110 | Q135A_Q00110OD_UNIMAS2 | Sarawak |  | Decomm |  | 2024 Q2 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-11-21 |  |  |  | 2023-11-23 |  | 2023-11-24 | 2023-12-16 | CD//John | 2023-11-25 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231126 | DU00002863467 |  |  |  |  | 2024-12-28 |  | TOWER
Q00273 | Q141A_Q00273OD_KGSEMERA | Sarawak |  | Decomm |  | 2024 Q2 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-11-05 |  |  |  | 2023-11-08 |  | 2023-11-14 | 2023-11-22 | CD//John | 2023-11-14 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231107/Celcom Digi_RAN-Magicell-Standard PR TSS DECOMM-Sarawak-20231229/CelcomDigi_RAN_Magicell_TSS_Sarawak_20241018 | DU00002863468 |  |  |  |  | 2024-06-28 |  | TOWER
Q00490 | Q135A_Q00490OD_DESAILMU | Sarawak |  | Decomm |  | 2024 Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-11-16 |  |  |  | 2023-11-16 |  | 2023-11-16 | 2023-11-22 | CD//John | 2023-11-16 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231119 | DU00002863469 |  |  |  |  | 2025-08-19 |  | TOWER
Q00358 | Q132C_Q00358OD_TMNOCEAN | Sarawak |  | Decomm |  | 2025 Q1 | SH | Trintel | 4.6 TSSR Approved |  | 2023-10-31 |  |  | 2023-11-14 | 2023-11-08 | Closed | 2023-11-08 | 2023-12-16 | CD//John | 2023-11-08 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231101 | DU00002863470 |  |  |  |  | 2025-11-22 |  | TOWER
Q00608 | Q132C_Q00608ODA_BTNIAH | Sarawak |  | Decomm |  | 2025 Q2 | HW | Trintel | 4.6 TSSR Approved |  | 2025-03-04 |  | 2025-03-14 |  | 2025-03-18 |  | 2025-03-21 | 2025-12-15 | CD//John | 2025-03-24 | SQ202501070293-Trintel | DU00002863471 |  |  |  |  | 2025-11-17 |  | TOWER
Q00344 | Q132A_Q00344OD_CB_TMLAMBIR | Sarawak |  | Decomm |  | 2025 Q2 | AD | Trintel | 4.6 TSSR Approved |  | 2025-11-13 |  | 2026-01-26 |  | 2026-01-27 | To be Submitted | 2026-03-07 |  | CD//Zamri | 2026-03-09 | SQ202505150459-Trintel | DU00002863472 |  |  |  |  | 2025-11-22 |  | TOWER
Q00340 | Q132A_Q00340OD_CB_LAKUMYY | Sarawak |  | Decomm |  | 2024 | SH | Trintel | 4.6 TSSR Approved |  | 2024-04-24 |  |  |  | 2024-04-25 |  | 2024-04-26 | 2024-08-01 | CD//John | 2024-04-29 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240503 | DU00002863473 |  |  |  |  | 2024-12-14 |  | TOWER
Q00495 | Q132A_Q00495OD_SGDALAM | Sarawak |  | Decomm |  | 2025 Q1 | ZB | Trintel | 4.6 TSSR Approved |  | 2024-04-30 |  |  |  | 2024-05-06 |  | 2024-05-06 | 2024-05-24 | CD//John | 2024-05-06 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240503 | DU00002863474 |  |  |  |  | 2025-10-23 |  | TOWER
Q00214 | Q133A_Q00214OD_TMMUKAH | Sarawak |  | Decomm |  | 2025 Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2024-03-14 |  |  |  | 2024-03-15 |  | 2024-03-18 | 2024-07-29 | CD//John | 2024-03-18 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20240324 | DU00002863475 |  |  |  |  | 2025-04-29 |  | TOWER
Q00378 | Q137A_Q00378OD_KGSEBERANG | Sarawak |  | Decomm |  | 2025 Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-12-28 |  |  |  | 2024-01-04 |  | 2024-01-25 | 2024-04-24 | CD//John | 2024-01-26 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231231 | DU00002863476 |  |  |  |  | 2025-06-17 |  | TOWER
Q00232 | Q119A_Q00232OD_TMDALAT | Sarawak |  | Decomm |  | 2024 Q4(single site MOCN)-L21 SSM | ZB | Trintel | 4.6 TSSR Approved |  | 2024-03-20 |  |  |  | 2024-03-20 |  | 2024-03-22 | 2024-07-29 | CD//John | 2024-03-22 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20240324 | DU00002863477 |  |  |  |  | 2024-12-11 |  | TOWER
Q00653 | Q124E_Q00653OD_KGSIMPOK | Sarawak |  | Decomm |  | 2025 Q1 | ZB | South Pacific | 4.6 TSSR Approved |  | 2024-02-07 |  |  |  | 2024-02-08 |  | 2024-02-14 | 2024-03-21 | CD//John | 2024-02-15 | Celcom Digi_RAN-South Pacific-Standard PR TSS-Sarawak-20240213 | DU00002863478 |  |  |  |  | 2025-08-25 |  | TOWER
Q00042 | Q124E_Q00042OD_SIBURAN | Sarawak |  | Decomm |  | 2024 | ZB | South Pacific | 4.6 TSSR Approved |  | 2024-02-08 |  |  |  | 2024-02-14 |  | 2024-02-14 | 2024-08-16 | CD//John | 2024-02-15 | Celcom Digi_RAN-South Pacific-Standard PR TSS-Sarawak-20240213 | DU00002863479 |  |  |  |  | 2024-12-31 |  | TOWER
4725B | Wang Tepus | Northern |  | Modernization | Modernization->Site Out->Modernization | 2024 Q3 | HW | YPTT | 4.6 TSSR Approved |  | 2023-10-26 | 2023-11-24 |  | 2025-04-15 |  | Under Approval | 2025-04-15 | 2025-05-19 | E//Hazida | 2025-04-23 | N/A - Site OUT | DU00002863480 |  |  | 2025-04-30 | 2025-04-30 |  | Tower | Tower | 60m | Reuse Existing RRU
Q00587 | Q135A_Q00587OD_CB_SGENTINGGAN | Sarawak |  | Decomm |  | 2024 Q2 | SH | Magicell | 4.6 TSSR Approved |  | 2024-01-09 |  |  |  | 2024-01-10 |  | 2024-01-10 | 2024-01-22 | CD//John | 2024-01-11 | Celcom Digi_RAN-Magicell-Standard PR TSS-Sarawak-20240116/Celcom Digi_RAN-Magicell-Standard PR TSS DECOMM-Sarawak-20231229/CelcomDigi_RAN_Magicell_TSS_Sarawak_20241018 | DU00002863481 |  |  |  |  | 2025-04-29 |  | TOWER
Q00629 | Q135A_Q00629OD_JLNDTMUSA | Sarawak |  | Decomm |  | 2024 Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-11-17 |  |  |  | 2023-11-17 |  | 2023-11-17 | 2023-11-22 | CD//John | 2023-11-17 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231119 | DU00002863482 |  |  |  |  | 2025-08-20 |  | MONOPOLE
Q00510 | Q141A_Q00510OD_GEDONG | Sarawak |  | Decomm |  | 2025 Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2024-02-29 |  |  |  | 2024-03-06 |  | 2024-03-07 | 2024-11-29 | CD//John | 2024-04-03 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240302 | DU00002863483 |  |  |  |  | 2025-06-20 |  | TOWER
Q00719 | Q137A_Q00719OD_JLNABDRAZAK | Sarawak |  | Decomm |  | 2025 Q2 | ZB | Trintel | 4.6 TSSR Approved |  | 2023-12-19 |  |  |  | 2023-12-21 |  | 2024-01-22 | 2024-02-09 | CD//John | 2024-01-24 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231220 | DU00002863484 |  |  |  |  | 2025-06-18 |  | TOWER
9185A | Betong(SACOFA) | Sarawak |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | SHA | Magicell | 4.6 TSSR Approved |  | 2024-04-20 | 2024-05-03 |  | 2024-10-28 |  | Under Approval | 2024-10-31 | 2024-11-11 | E//Hannah | 2024-11-08 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20240123 | DU00002863485 |  |  | 2024-12-20 | 2024-11-26 |  | Tower | Tower | 76M | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123 | 0
9190A | Desa Ria | Sarawak |  | Modernization |  | 2025 Q3 | SM | AllStar | 4.6 TSSR Approved |  | 2023-11-15 | 2023-11-15 |  | 2025-02-18 |  | Under Approval | 2025-02-24 | 2025-02-27 | E//Hannah | 2025-02-27 |  | DU00002863486 |  |  | 2025-05-18 | 2025-03-22 |  | Tower | Tower | 76 | Add R8894E M1821x3, Dismantle R8862A S1800(B6A)x3 | 0 | 0
9193A | Spaoh | Sarawak |  | Modernization |  | 2025 Q3 | SM | Magicell | 4.6 TSSR Approved |  | 2024-06-10 | 2024-06-14 |  | 2025-02-19 |  | Rectificating | 2025-02-25 | 2025-03-19 | E//Hannah | 2025-03-19 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20240123 | DU00002863487 | Remarks: Solution TSSR/BOM Changed |  | 2025-07-06 | 2025-04-09 |  | Tower | 60m 3 Legged Tower | 78 | Add R8894E M1821x2 | 0 | 13
Q01039 | Q135A_Q01039OD_FAKULTISAINS | Sarawak | 9382K | Swap | Decomm->On hold->Swap | 2024 Q2 | AD | Magicell | 4.6 TSSR Approved |  | 2023-11-22 | 2025-09-29 |  | 2025-09-24 | 2023-11-27 | Under Approval | 2025-10-01 | 2025-10-16 | CD//John | 2025-10-03 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231126/Celcom Digi_RAN-Magicell-Standard PR TSS DECOMM-Sarawak-20231229/Celcom Digi_RAN_Magicell_TSS_Sarawak_20241107 | DU00002863488 |  |  |  | 2026-04-06 |  | In-Building System | #N/A | 1.5m | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
9197A | Debak Junction(Celcom) | Sarawak |  | Modernization |  | 2025 Q3 | AI | Trintel | 4.6 TSSR Approved |  | 2025-05-09 | 2025-05-19 |  | 2025-05-22 |  | Closed | 2025-06-11 | 2025-09-24 | E//Zamri | 2025-06-11 | SQ202505270561-Trintel | DU00002863489 |  |  | 2025-09-26 | 2025-09-25 |  | Tower | Tower | 106 | Add R8894E M1821x3, Dismantle R8862A S1800(B6A)x3 | 0 | 0
9198A | Saratok 2 (TM-Sacofa) | Sarawak |  | Modernization |  | 2025 Q3 | AI | Trintel | 4.6 TSSR Approved |  | 2025-06-09 | 2025-06-18 |  | 2025-07-02 |  | Closed | 2025-07-07 | 2025-09-08 | E//John | 2025-07-16 | SQ202505270561-Trintel | DU00002863490 |  |  | 2025-09-06 | 2025-09-04 |  | Tower | 60m 4 Legged Tower | 106 | Add R8894E M1821x1 | 0 | 3
9199A | Kabong Bazaar | Sarawak |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | AD | Datasco | 4.6 TSSR Approved | Propose Open Battery Caging under CelcomDigi | 2023-10-25 | 2023-10-30 |  | 2024-10-22 |  | Under Approval | 2024-11-07 | 2024-11-11 |  | 2024-11-07 | Celcom Digi_RAN-Datasco-TSS-Sabah-20231028 | DU00002863491 |  |  | 2024-12-03 | 2024-11-24 |  | Tower | 76m Tower | 76 | Add A9732 M1821x2+R8894E M1821x1, DismantleR8862A S1800(A6A)x3 | 12 | 0
9223A | Temudok Sri Aman-Core(Celcom) | Sarawak |  | Modernization |  | 2025 Q3 | AD | Magicell | 4.6 TSSR Approved |  | 2023-11-25 | 2023-11-30 |  | 2024-04-17 |  | Under Approval | 2025-02-26 | 2025-03-09 | E//Hannah | 2025-03-04 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231126 | DU00002863492 | Remarks: Solution TSSR/BOM Changed |  | 2025-07-06 | 2025-04-11 |  | Tower | Tower | 75M | Add R8862A S9000 x4+R9224E M1821 x4+R8862A S2601 x4, Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3+R8862A S2600(A4A) x3 | 0 | 0
9225A | SMK Sri Aman | Sarawak |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | ZB | Magicell | 4.6 TSSR Approved |  | 2023-11-29 | 2023-12-06 |  | 2024-04-18 |  | Closed | 2024-10-23 | 2024-10-24 | E//Hannah | 2024-10-24 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231206 | DU00002863493 |  |  | 2024-11-10 | 2024-10-31 |  | Tower | 45m 4 Legged Tower | 62m | Add R9264M M1821 x1+A9732 M1821 x3,Dismantle R8894E M1821(A8A) x4 | 123 | 0
9236A | Kg Hilir | Sarawak |  | Modernization |  | 2025 Q3 | SM | Magicell | 4.6 TSSR Approved |  | 2023-11-28 | 2023-11-30 |  | 2024-04-18 |  | Rectificating | 2025-02-06 | 2025-02-18 | E//Hannah | 2025-02-18 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231206 | DU00002863494 | Remarks: Solution TSSR/BOM Changed |  | 2025-07-06 | 2025-03-22 |  | Tower | 45m 3 Legged Tower | 78M | Add R9264H M901821 x1+R8862A S2601 x2+A9732 M1821 x2,Dismantle R8882-GUL1812 x1+R8862A S2100(A6A) x3+R8862A S2600(A4A) x2 | 12 | 0
Q00227 | Q139A_Q00227OD_KGRASAU | Sarawak |  | Decomm |  | 2025 Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2023-10-12 |  |  |  | 2023-10-16 |  | 2023-10-16 | 2024-06-21 | CD//John | 2023-10-16 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231013 | DU00002863495 |  |  |  |  | 2025-06-20 |  | TOWER
Q00932 | Q125A_Q00932OD_CB_PKNLAWAS | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | AD | DATASCO | 4.6 TSSR Approved |  | 2025-05-12 |  | 2025-05-28 |  | 2025-06-06 | To be Submitted | 2025-06-12 |  | E//John | 2025-06-13 | SQ202501070453-Datasco | DU00002863496 |  | No FE Drawing |  |  | 2025-11-27 |  | TOWER
Q00313 | Q125A_Q00313OD_CB_BKTTIONG | Sarawak |  | Decomm |  | 2025 Q2 | AD | CCSMY | 4.6 TSSR Approved |  | 2025-06-06 |  | 2025-06-19 |  | 2025-06-20 | To be Submitted | 2025-06-23 |  | E//John | 2025-06-24 | SQ202506060165-CCSMY | DU00002863497 |  |  |  |  | 2025-08-27 |  | TOWER
Q00315 | Q126A_Q00315OD_BKTMAS | Sarawak |  | Decomm |  | 2024 | HW | Magicell | 4.6 TSSR Approved |  | 2024-11-21 |  |  |  | 2025-02-17 | To be Submitted | 2025-02-18 |  | CD//John | 2025-02-19 | CelcomDigi_RAN_Magicell_PR_TSS_Sarawak_20241101 | DU00002863498 |  |  |  |  | 2025-03-27 |  | TOWER
Q00322 | Q126A_Q00322OD_PURNAMAHOTEL | Sarawak |  | Decomm |  | 2025 Q2 | AD | CCSMY | 4.6 TSSR Approved | 18/8 - 21 go in , BM approved // 14/8 - site in limbang, plan to reaccess in 21/8 // 11/8- Plan Wed 13/8 // 8/8 - ???????? 5/8 - Escalation done, team no response,. Other team unable to cover this region. only CCSMY | 2025-08-20 |  | 2025-08-22 |  | 2025-08-26 | To be Submitted | 2025-08-29 |  | E//John | 2025-09-02 | SQ202506060165-CCSMY | DU00002863499 |  |  |  |  | 2025-11-22 |  | BOOM
Q00388 | Q124E_Q00388OD_PKNTAPAH | Sarawak |  | Decomm |  | 2025 Q1 | SH | South Pacific | 4.6 TSSR Approved |  | 2024-02-07 |  |  |  | 2024-02-08 |  | 2024-02-09 | 2024-07-12 | CD//John | 2024-04-03 | Celcom Digi_RAN-South Pacific-Standard PR TSS-Sarawak-20240213 | DU00002863500 |  |  |  |  | 2025-06-26 |  | BOOM
Q00097 | Q124C_Q00097OD_CB_DESAMOYAN | Sarawak |  | Decomm |  | 2024 Q2 | ZB | Trintel | 4.6 TSSR Approved |  | 2024-01-31 |  |  |  | 2024-02-05 |  | 2024-02-08 | 2024-07-05 | CD//John | 2024-02-15 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20240204 | DU00002863501 |  |  |  |  | 2024-07-14 |  | TRIPOD
Q00056 | Q135A_Q00056OD_KUAP | Sarawak |  | Decomm |  | 2024 Q2 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-11-25 |  |  |  | 2023-11-30 |  | 2023-12-01 | 2023-12-16 | CD//John | 2023-12-01 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231126 | DU00002863502 |  |  |  |  | 2025-05-14 |  | TOWER
Q00111 | Q135A_Q00111OD_MERDANGGAYAM | Sarawak |  | Decomm |  | 2024 Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-11-18 |  |  |  | 2023-11-24 |  | 2023-11-27 | 2023-12-08 | CD//John | 2023-11-28 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231119 | DU00002863503 |  |  |  |  | 2024-12-22 |  | TOWER
Q00028 | Q115A_Q00028OD_TMBAU | Sarawak |  | Decomm |  | 2024 Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2024-01-23 |  |  |  | 2024-01-23 |  | 2024-01-24 | 2024-02-09 | CD//John | 2024-01-26 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20240124 | DU00002863504 |  |  |  |  | 2024-06-25 |  | TOWER
Q00294 | Q124E_Q00294OD_KSKB | Sarawak |  | Decomm |  | 2024 | ZB | South Pacific | 4.6 TSSR Approved |  | 2024-02-13 |  |  |  | 2024-02-16 |  | 2024-02-19 | 2024-08-16 | CD//John | 2024-03-18 | Celcom Digi_RAN-South Pacific-Standard PR TSS-Sarawak-20240220 | DU00002863505 |  |  |  |  | 2025-02-26 |  | TOWER
B02763 | W066Z_B02763OD_LRT_PANDANJAYA | Central |  | Decomm |  | 2024 Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-12-29 |  |  |  | 2024-02-08 |  | 2024-02-13 | 2024-07-12 | CD//Ali akaram | 2024-06-10 | CelcomDigi_RAN_GTSB_TSS_Central_20231230 | DU00002863506 |  |  |  |  | 2024-08-16 |  | RAMO
Q00887 | Q135A_Q00887OD_ILPKCH | Sarawak |  | Decomm |  | 2024 Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-10-23 |  |  |  | 2023-10-24 |  | 2023-10-25 | 2023-11-06 | CD//John | 2023-10-26 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231019 | DU00002863507 |  |  |  |  | 2025-07-29 |  | BOOM
Q00617 | Q142A_Q00617OD_PKNSONG | Sarawak |  | Decomm |  | 2025 Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2024-04-24 |  |  |  | 2024-04-25 |  | 2024-04-26 | 2024-08-16 | CD//John | 2024-04-29 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240503 The Wireless RAN Dismantle HLD of Q00617 is RELOCATE CELCOM SACOFA LL Q00617 DUE TO USP MOCN,pls submit application under the TX Rollou model.And the Cluster Sequence of these sites are: 2025 (swap out sarawak cluster or single sit). This type of site survey and design fee settlement method is being communicated with the customer, and the submission of PR will be held on. | DU00002863508 |  |  |  |  | 2025-11-11 |  | TOWER
Q00206 | Q122A_Q00206OD_TMKANOWIT | Sarawak |  | Decomm |  | 2025 Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2023-12-20 |  |  |  | 2024-01-03 |  | 2024-01-29 | 2024-09-05 | CD//John | 2024-01-29 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231221 | DU00002863509 |  |  |  |  | 2025-08-19 |  | TOWER
Q00618 | Q120A_Q00618OD_PKNDARO | Sarawak |  | Decomm |  | 2024 | ZB | Trintel | 4.6 TSSR Approved |  | 2024-03-20 |  |  |  | 2024-03-20 |  | 2024-03-22 | 2024-07-29 | CD//John | 2024-03-22 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20240324 | DU00002863510 |  |  |  |  | 2024-12-22 |  | TOWER
Q00316 | Q126A_Q00316OD_LBGAIRPORT | Sarawak |  | Decomm |  | 2025 Q2 | AI | DATASCO | 4.6 TSSR Approved |  | 2025-05-05 |  | 2025-05-08 | 2025-05-26 | 2025-05-27 | Under Approval | 2025-06-04 | 2026-02-23 | CD//John | 2025-06-10 | SQ202501070453-Datasco | DU00002863511 |  |  |  |  | 2025-08-27 |  | TOWER
9399B | Maktab Perguruan Bintangor | Sarawak |  | Modernization |  | 2025 Q2 | SH | Datasco | 4.6 TSSR Approved |  | 2023-10-19 | 2023-10-23 |  | 2023-10-27 |  | Closed | 2023-10-30 | 2023-11-15 | E//Hannah | 2023-11-09 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231020 | DU00002863512 |  |  | 2023-11-24 | 2023-11-20 |  | Tower | 76m Tower | 76 | Add R9264M M1821 x1+R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 1
Q00228 | Q123A_Q00228OD_TMKAPITTV | Sarawak |  | Decomm |  | 2024 | SH | Trintel | 4.6 TSSR Approved |  | 2024-04-01 |  |  |  | 2024-04-03 |  | 2024-04-03 | 2024-07-24 | CD//John | 2024-04-04 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240406 | DU00002863513 |  |  |  |  | 2025-08-15 |  | TOWER
S00212 | S089A_S00212OD_MILE20 | Sabah |  | Decomm |  | 2025 Q2 | MS | Futong | 4.6 TSSR Approved |  | 2024-04-29 |  |  |  | 2024-04-29 |  | 2024-05-08 | 2024-07-24 | CD//Jahganathan | 2024-05-09 | Celcom Digi_RAN-Futong-Standard PR TSS-Sabah-20240503 / SQ202501020444 - Futong / SQ202501070242 - Futong | DU00002863514 |  |  |  |  | 2024-08-06 |  | TOWER
Q00132 | Q124E_Q00132OD_TMNINDAHKCH | Sarawak |  | Decomm |  | 2025 Q1 | ZB | Trintel | 4.6 TSSR Approved |  | 2023-12-22 |  |  |  | 2023-12-29 |  | 2024-01-22 | 2024-07-29 | CD//John | 2024-01-24 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231231 | DU00002863515 |  |  |  |  | 2024-02-19 |  | TOWER
9460B | Saka | Sarawak |  | Modernization |  | 2025 Q3 | SM | AllStar | 4.6 TSSR Approved |  | 2023-11-15 | 2023-11-16 |  | 2024-04-16 |  | Rectificating | 2025-02-26 | 2025-05-27 | E//Hannah | 2025-03-19 |  | DU00002863516 |  |  | 2025-07-06 | 2025-06-20 |  | Tower | 45m 3 Legged Tower | 75 | Add R8862A S9000 x3+R9224E M1821 x2+A9732 M1821 x1,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x2 | 1 | 0
9463B | Kg Sepinang | Sarawak |  | Modernization | Modernization->On Hold->Modernization | 2025 Q3 | HW | Trintel | 4.6 TSSR Approved |  | 2025-05-07 | 2025-05-16 |  | 2025-05-21 |  | Under Approval | 2025-05-22 | 2025-05-23 | E//John | 2025-05-22 | SQ202506170396-Trintel | DU00002863517 |  |  | 2025-07-06 | 2025-06-20 |  | Tower | Tower | 76 | Add R8894E M1821x1 | 0 | 1
W00628 | W066G_W00628OD_PR_TMNPRIMASTPK | Central |  | Decomm |  | 2024 Q1 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-01-23 |  |  |  | 2024-07-22 |  | 2024-02-28 | 2025-03-20 | CD//Sapian | 2024-03-13 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240128 | DU00002863518 |  |  |  |  | 2024-05-09 |  | MINI MONOPOLE
B01140 | W066X_B01140OD_AMPGLOOKOUT | Central |  | Decomm |  | 2024 Additional | AD | GCI | 4.6 TSSR Approved |  | 2024-07-02 |  |  |  | 2024-06-04 |  | 2024-11-20 | 2025-03-21 | CD//Norhaliza | 2024-12-06 | 0619Central-GCI-BOQ Template (template) | DU00002863519 |  |  |  |  | 2024-12-12 |  | LAMP_POLE
Q00825 | Q132C_Q00825OD_MORSJAYACOMM | Sarawak |  | Decomm |  | 2024 | ZB | Trintel | 4.6 TSSR Approved |  | 2024-04-22 |  |  |  | 2024-04-22 |  | 2024-04-26 | 2024-05-24 | CD//John | 2024-05-13 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240503 | DU00002863520 |  |  |  |  | 2024-12-11 |  | TOWER
Q00727 | Q132C_Q00727OD_JLNTMNRAJA | Sarawak |  | Decomm |  | 2024 Q4(single site MOCN)-L21 SSM | ZB | Trintel | 4.6 TSSR Approved |  | 2024-04-18 |  |  |  | 2024-04-18 |  | 2024-04-18 | 2024-05-24 | CD//John | 2024-05-13 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240420 | DU00002863521 |  |  |  |  | 2024-12-11 |  | TOWER
Q00726 | Q132A_Q00726OD_TMNTUNKU2 | Sarawak |  | Decomm |  | 2024 | SH | Trintel | 4.6 TSSR Approved |  | 2024-04-17 |  |  |  | 2024-04-17 |  | 2024-04-17 | 2024-04-24 | CD//John | 2024-04-18 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240420 | DU00002863522 |  |  |  |  | 2025-06-14 |  | LAMP_POLE
Q00942 | Q132A_Q00942OD_SPGTMNTUNKU | Sarawak |  | Decomm |  | 2025 Q1 | SH | Trintel | 4.6 TSSR Approved |  | 2024-04-23 |  |  |  | 2024-04-23 |  | 2024-04-24 | 2024-05-24 | CD//John | 2024-04-24 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240503 | DU00002863523 |  |  |  |  | 2025-06-25 |  | TOWER
Q00885 | Q132A_Q00885OD_JLNTUKAU | Sarawak |  | Decomm |  | 2025 Q1 | SH | Trintel | 4.6 TSSR Approved |  | 2023-10-07 |  |  |  | 2023-10-10 |  | 2023-10-10 | 2024-05-14 | CD//John | 2023-10-11 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231009 | DU00002863524 |  |  |  |  | 2025-06-23 |  | MONOPOLE
Q00297 | Q132C_Q00297OD_TGLOBANG | Sarawak |  | Decomm |  | 2025 Q1 | SH | Trintel | 4.6 TSSR Approved |  | 2023-10-17 |  |  |  | 2023-10-18 |  | 2023-10-18 | 2025-10-28 | CD//John | 2023-10-21 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231017 | DU00002863525 |  |  |  |  | 2025-05-26 |  | TOWER
B00491 | B064C_B00491OD_SRIKEMBANGAN | Central |  | Decomm |  | 2024 Q3 | SHA | DATASCO | 4.6 TSSR Approved |  | 2024-07-11 |  | 2024-11-06 |  | 2024-11-08 |  | 2024-11-13 | 2025-03-07 | CD//Norhaliza | 2024-12-23 | 0712Central-DATASCO-BOQ Template | DU00002863526 |  |  |  |  | 2024-11-16 |  | TOWER
A00792 | A040D_A00792OD_MASJIDABIDINIPOH | Northern |  | Decomm |  | 2024 Q2 | ZA | YPTT | 4.6 TSSR Approved |  | 2024-01-25 |  |  |  | 2024-01-30 |  | 2024-01-31 | 2024-02-16 | CD//Shamsul | 2024-01-31 | Celcom Digi_RAN-YPTT-TSS-Northern-20240124-0057 | DU00002863527 |  |  |  |  | 2024-03-08 |  | MONOPOLE
B00453 | W066Y_B00453OD_TMNLMBHMAJU2 | Central |  | Decomm |  | 2024 Q3 | BY | Ascentrack | 4.6 TSSR Approved |  | 2024-01-26 |  |  |  | 2024-01-29 |  | 2024-04-01 | 2024-10-28 | CD//Ali Akaram | 2024-05-20 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240128 | DU00002863528 |  |  |  |  | 2024-07-31 |  | TOWER
W00021 | W066G_W00021OD_TMNTERATAIMEWAH | Central |  | Decomm |  | 2024 Q1 | SY1 | GTSB | 4.6 TSSR Approved |  | 2024-06-20 |  | 2024-07-03 |  | 2024-07-11 |  | 2024-07-12 | 2024-08-27 | CD//Ali akaram | 2024-07-25 | 0624Central-GTSB-BOQ Template (template) | DU00002863529 |  |  |  |  | 2024-07-30 |  | BOOM
W00857 | W066BB_W00857OD_PSSALAMDAMAI | Central |  | Decomm |  | 2024 Q3 | SM | Magicell | 4.6 TSSR Approved |  | 2024-07-24 |  | 2024-08-05 |  | 2024-08-08 |  | 2024-08-12 | 2024-10-28 | CD//Norhaliza | 2024-10-21 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240510 - Decomm | DU00002863530 |  |  |  |  | 2024-11-30 |  | LAMP_POLE
B00593 | W066BB_B00593OD_TMNSEGARPERDANA | Central |  | Decomm |  | 2024 Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2024-01-08 |  |  |  | 2024-02-07 |  | 2024-05-24 | 2024-10-29 | CD//Ali akaram | 2024-09-25 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240110 | DU00002863531 |  |  |  |  | 2024-12-19 |  | TRIPOD
7420A | TAMAN NIKMAT | Sabah |  | Modernization |  | 2024 Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-10-22 | 2023-10-24 |  | 2023-10-27 |  | Closed | 2024-03-26 | 2024-03-26 | E//Hannah | 2024-03-26 | Celcom Digi_RAN-YPTT-TSS-Sabah-20231024 | DU00002863532 |  |  | 2024-05-09 | 2024-05-07 |  | Tower | Tower | 60 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 | 0 | 0
W01486 | B064B_W01486OD_JLNDESACAHAYA_SCT | Central |  | Site Out (Decomm) | Decomm->On Hold->Site Out->Replacement, Site Out (Decomm) | 2024 Q4 | SS | GTSB | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2025-07-15 |  | 2025-07-03 |  |  | To be Submitted |  |  | CD//Sapian |  | SQ202506170074 | DU00002863533 |  |  |  |  | 2025-06-26 |  | TOWER
A00070 | A042B_A00070OD_TPGTOWN | Northern |  | Decomm |  | 2024 Q2 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-11-19 |  |  |  | 2023-11-21 |  | 2023-11-22 | 2023-11-29 | CD//Shamsul | 2023-11-23 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231122-0072 | DU00002863534 |  |  |  |  | 2024-05-10 |  | MINI STRUCTURE
B02712 | B061K_B02712OD_JLNPUTERIPCHG | Central |  | Decomm |  | 2024 Q3 | AD | Magicell | 4.6 TSSR Approved |  | 2023-12-23 |  |  |  | 2024-04-17 |  | 2024-04-19 | 2024-05-14 | CD//Norhaliza | 2024-05-13 | CelcomDigi_RAN_Magicell_TSS_Central_20231224 | DU00002863535 |  |  |  |  | 2024-09-30 |  | BOOM
B01991 | B064I_B01991OD_LEKASSEMENYEHIT | Central |  | Decomm |  | 2024 | HW | GCI | 4.6 TSSR Approved |  | 2024-12-23 |  | 2025-01-10 |  | 2025-02-12 |  | 2025-02-18 | 2025-10-01 | CD//Sapian | 2025-02-24 | Wireless+ Malaysia CD+TSS+ GCI+4 site SQ202410310157 | DU00002863536 |  |  |  |  | 2025-04-23 |  | TOWER
K00136 | K008A_K00136OD_MOFAZ | Northern |  | Decomm |  | 2024 Q4 | SM | CCSMY | 4.6 TSSR Approved |  | 2024-10-12 |  | 2024-10-17 |  | 2024-10-23 |  | 2024-11-11 | 2025-07-25 | CD//Zulakmar | 2024-12-24 | 0927CD-Northern-CCSMY-BOQ Template(new contract) | DU00002863537 |  |  |  |  | 2025-03-13 |  | TOWER
B02300 | W067A_B02300OD_APRT17RK1PRESINT17WPPJ | Central |  | Decomm |  | 2024 Q3 | AD | Magicell | 4.6 TSSR Approved |  | 2024-01-05 |  |  |  | 2024-01-10 |  | 2024-07-19 | 2024-10-29 | CD//Norhaliza | 2024-10-04 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240110 | DU00002863538 |  |  |  |  | 2024-12-17 |  | WALL-MOUNTED
B02302 | W067A_B02302OD_APRTFASA18R12PRESINT18 | Central |  | Decomm |  | 2024 Q3 | MS | Magicell | 4.6 TSSR Approved |  | 2024-01-05 |  |  |  | 2024-07-09 |  | 2024-02-21 | 2024-10-28 | CD//Ali Akaram | 2024-04-30 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240110 | DU00002863539 |  |  |  |  | 2024-08-16 |  | WALL MOUNTED BOOM
B02196 | W067A_B02196OD_JLNP8PRESINT8 | Central | 1872K | Swap | Decomm->Swap | 2024 Q3 | AI | Magicell | 4.6 TSSR Approved |  | 2024-08-01 | 2024-08-12 |  | 2024-08-15 | 2024-02-27 | Closed | 2024-08-19 | 2024-10-24 | CD//Norhaliza | 2024-10-24 | 0619Central-Magicell-BOQ Template (template) | DU00002863540 |  |  | 2024-11-13 | 2024-11-12 |  | In-Building System | BOOM | 2 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle | 0 | 0
B02307 | W067A_B02307OD_APRT_FASA5_PRESINT5 | Central |  | Decomm |  | 2024 Q3 | AD | GCI | 4.6 TSSR Approved |  | 2024-02-23 |  |  |  | 2024-03-01 |  | 2024-05-24 | 2024-07-12 | CD//Sapian | 2024-06-10 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240303 | DU00002863541 |  |  |  |  | 2024-12-17 |  | BOOM
L00144 | S113A_L00144OD_KIANSAM | Sabah |  | Decomm |  | 2025 Q1 | AD | Datasco | 4.6 TSSR Approved |  | 2024-05-28 |  | 2024-08-16 |  | 2024-08-27 |  | 2025-01-03 | 2025-09-10 | CD//Sharidah | 2025-02-04 | SQ202501020441 - Datasco | DU00002863542 |  |  |  |  | 2025-04-21 |  | RAPOLE
A00961 | A041A_A00961OD_JLNKKANGSAR_KK | Northern |  | Decomm |  | 2024 Q4 | SM | Magicell | 4.6 TSSR Approved |  | 2024-10-25 |  |  |  | 2025-01-13 |  | 2024-11-13 |  | CD//Zulakmar | 2024-11-18 | 1511CD-Northern-Magicell-BOQ Template(new contract) | DU00002863543 |  | missing celcom idu n FE part |  |  | 2024-11-14 |  | BOOM
B02283 | B061L_B02283OD_KGPULAUMERANTI | Central |  | Decomm |  | 2024 Q3 | AD | Solusi | 4.6 TSSR Approved |  | 2024-11-05 |  | 2024-11-11 |  | 2024-11-14 |  | 2024-11-18 |  | CD//Norhaliza | 2024-12-06 | 0924CD-Central-CCSMY-BOQ Template(new contract) | DU00002863544 |  | 1.Pls provide Digi Cabinet/Rack photo for DISMANTLE DIGI MICROWAVE LINK 2651B-2057A 2. Pls check the TX Antenna photo link 2651B-2057A 3. Missing FE part |  |  | 2024-11-16 |  | MONOPOLE
S01358 | S105B_S01358OD_IJMTMNUTAMA1 | Sabah |  | Decomm |  | 2024 Q3 | MS | GTSB | 4.6 TSSR Approved |  | 2024-03-25 |  |  |  | 2024-04-02 |  | 2024-04-03 | 2024-07-19 | CD//Jahganathan | 2024-04-04 | Celcom Digi_RAN-GTSB-TSS-Sabah-20240329 | DU00002863545 |  |  |  |  | 2024-08-29 |  | MINI MONOPOLE
S00680 | S105B_S00680OD_BDRLEETAT | Sabah |  | Decomm |  | 2024 Q3 | MS | GTSB | 4.6 TSSR Approved |  | 2024-03-19 |  |  |  | 2024-03-25 |  | 2024-03-29 | 2024-06-28 | CD//Jahganathan | 2024-04-03 | Celcom Digi_RAN-GTSB-TSS-Sabah-20240324 | DU00002863546 |  |  |  |  | 2024-08-19 |  | TRIPOD
7753B | Pulau Mantanani | Sabah |  | Modernization |  | 2024 Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-11-14 | 2023-11-20 |  | 2024-03-29 |  | Closed | 2024-04-02 | 2024-06-25 | E//Hannah | 2024-06-24 | Celcom Digi_RAN-YPTT-TSS-Sabah-20231119 | DU00002863547 |  |  | 2024-06-10 | 2024-05-23 |  | Tower | Tower | 76 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
4751A | Tmn Siswa Kedah | Northern |  | Modernization |  | 2024 Q3 | ZA | GCI | 4.6 TSSR Approved |  | 2023-10-12 | 2023-10-20 |  | 2024-03-26 |  | Closed | 2024-04-01 | 2024-04-16 | E//Ajay | 2024-04-16 | Celcom Digi_RAN-GCI-TSS-Northern-20231015-0059 | DU00002863548 |  |  | 2024-04-22 | 2024-04-13 |  | Monopole | 30M Lampole | 30 | Add R8852E S9000 x1+R9264H M901821 x3+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x4 | 2 | 0
4756A | Kg Siputih | Northern |  | Modernization |  | 2024 Q3 | SM | GCI | 4.6 TSSR Approved | ¦0508 - replied to E// Ajay: Kindly refer to latest ML. Please be informed that S4 Pair Height is blank due to xC only have existing 3 sector. | 2024-04-26 | 2024-04-25 |  | 2024-05-02 |  | Rectificating | 2024-05-06 | 2024-06-28 | E//Ajay | 2024-06-27 | Celcom Digi_RAN-GCI-TSS-Northern-20240512-0106 | DU00002863549 |  |  | 2025-03-21 | 2024-10-19 |  | Tower | 4 Legged Tower | 60 | Add R8862A S9000 x4+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x2 | 23 | 0
B02192 | B061L_B02192OD_SURAULACOTTAGEPUTRAPDANA | Central |  | Decomm |  | 2024 Q3 | AD | Magicell | 4.6 TSSR Approved |  | 2024-03-29 |  |  |  | 2024-04-04 |  | 2024-04-19 | 2025-10-01 | CD//Sapian | 2024-05-12 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240403 | DU00002863550 |  |  |  |  | 2024-10-11 |  | LAMP_POLE
W00583 | W066R_W00583OD_KEMSGBESI | Central | 1883K | Swap | Decomm->On hold->Swap | 2024 Q3 | BY | Magicell | 4.6 TSSR Approved |  | 2024-07-22 | 2024-07-25 |  | 2024-07-31 |  | Under Approval | 2024-08-01 | 2025-03-10 | CD//Norhaliza | 2025-03-07 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240510 | DU00002863551 |  |  | 2025-06-30 | 2025-06-23 |  |  | MONOPOLE | 19M | Add R8862A S9000 x3+R8862A S2601 x3+A9732 M1821 x3,Dismantle | 123 | 0
W01305 | W066J_W01305OD_JLN_AYER_KEROH_SETAPAK | Central |  | Decomm |  | 2024 Q1 | SM | GCI | 4.6 TSSR Approved |  | 2024-02-16 |  |  |  | 2024-02-20 |  | 2024-02-22 | 2025-10-01 | CD//Ali Akaram | 2024-03-12 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240217 | DU00002863552 |  |  |  |  | 2024-05-08 |  | STREET POLE
B02319 | B064C_B02319OD_LESTARI_PERDANA | Central |  | Decomm |  | 2024 Q3 | SY1 | Solusi | 4.6 TSSR Approved |  | 2024-07-26 |  |  |  | 2024-08-27 |  | 2024-08-28 | 2025-01-14 | CD//Norhaliza | 2024-09-06 | 0724Central-Solusi-BOQ Template | DU00002863553 |  |  |  |  | 2024-09-13 |  | UNIPOLE
W00586 | W066S_W00586OD_OUGIP | Central |  | Decomm |  | 2024 Q3 | BY | GTSB | 4.6 TSSR Approved |  | 2024-03-20 |  |  |  | 2024-05-18 |  | 2024-05-20 | 2024-09-25 | CD//Norhaliza | 2024-08-23 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240323 | DU00002863554 |  |  |  |  | 2024-05-24 |  | MINI MONOPOLE
B01485 | B064B_B01485OD_BTHOSUARASA | Central |  | Decomm |  | 2024 Q4(single site MOCN)-L26 SSM | SHA | GCI | 4.6 TSSR Approved |  | 2024-09-18 |  |  |  | 2024-10-04 |  | 2024-10-07 | 2025-01-14 | CD//Ali Akaram | 2024-10-17 | 0924CD-Central-GCI-BOQ Template(new contract) | DU00002863555 |  |  |  |  | 2024-11-20 |  | TRIPOD
B01267 | B064F_B01267OD_KJGCNTRYHGHT | Central |  | Decomm |  | 2024 Q4 | SY1 | DATASCO | 4.6 TSSR Approved |  | 2024-02-28 |  | 2024-09-08 |  | 2024-09-20 |  | 2024-09-23 | 2025-01-14 | CD//Sapian | 2024-10-01 | 0802CD-Central-Datasco-BOQ Template(new contract) | DU00002863556 |  |  |  |  | 2025-03-13 |  | LAMP_POLE
W00001 | W066J_W00001OD_KERAMATJAYA | Central |  | Decomm |  | 2024 Q1 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-02-02 |  |  |  | 2024-02-07 |  | 2024-02-09 | 2024-07-12 | CD//Sapian | 2024-06-07 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240212 | DU00002863557 |  |  |  |  | 2024-07-31 |  | LAMP_POLE
B01412 | B061L_B01412OD_BDRBKTPCHG5 | Central |  | Decomm |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-24 |  |  |  | 2024-02-02 |  | 2024-02-05 | 2024-02-23 | CD//Norhaliza | 2024-02-15 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240128 | DU00002863558 |  |  |  |  | 2024-09-03 |  | Lampole
W00037 | W066S_W00037OD_BT5PUCHONG | Central |  | Decomm |  | 2024 Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2024-03-25 |  |  |  | 2024-05-24 |  | 2024-05-28 | 2024-07-19 | CD//Ali akaram | 2024-06-13 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240329 | DU00002863559 |  |  |  |  | 2024-06-20 |  | BOOM
Q01275 | Q135A_Q01275OD_SAMARINDAH | Sarawak |  | Decomm |  | 2024 Q2 | ZB | Magicell | 4.6 TSSR Approved |  | 2024-04-05 |  |  |  | 2024-04-16 |  | 2024-04-17 | 2024-09-11 | CD//John | 2024-04-18 | Celcom Digi_RAN-Magicell-Standard PR TSS-Sarawak-20240221/Celcom Digi_RAN-Magicell-Standard PR TSS DECOMM-Sarawak-20231229/CelcomDigi_RAN_Magicell_TSS_Sarawak_20241018 | DU00002863560 |  |  |  |  | 2024-12-06 |  | LAMP_POLE
7422A | Kg Ambong | Sabah |  | Modernization |  | 2024 Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-10-19 | 2023-11-03 |  | 2024-03-26 |  | Closed | 2024-04-24 | 2024-05-08 | E//Hannah | 2024-05-06 | Celcom Digi_RAN-YPTT-TSS-Sabah-20231020 | DU00002863561 |  |  | 2024-05-17 | 2024-05-07 |  | Tower | 45m 3 Legged Tower | 60 | Add R8894E M1821 x2+R8854 S2600 x2,Dismantle | 0 | 23
Q01502 | Q135A_Q01125OD_KOLEJBUNGARAYA | Sarawak |  | Decomm |  | 2024 Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-11-30 |  |  |  | 2023-12-01 |  | 2023-12-01 | 2023-12-08 | CD//John | 2023-12-01 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231206/0612Sarawak-Trintel-BOQ Template (template) | DU00002863562 |  |  |  |  | 2024-11-28 |  | RAPOLE
Q01788 | Q135A_Q01788OD_CB_KGMERANEK | Sarawak |  | Decomm |  | 2024 Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-11-29 |  |  |  | 2023-11-29 |  | 2023-12-04 | 2023-12-08 | CD//John | 2023-12-05 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231206/0612Sarawak-Trintel-BOQ Template (template) | DU00002863563 |  |  |  |  | 2025-06-11 |  | RAPOLE
Q00772 | Q139A_Q00772OD_PKNSERIAN | Sarawak |  | Decomm |  | 2025 Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2024-03-02 |  |  |  | 2024-03-04 |  | 2024-03-04 | 2025-05-02 | CD//John | 2024-04-03 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240302 | DU00002863564 |  |  |  |  | 2025-05-21 |  | TOWER
7423A | Kg Sembirai | Sabah |  | Modernization |  | 2024 Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-10-22 | 2024-01-09 |  | 2024-03-28 |  | Closed | 2024-04-02 | 2024-04-16 | E//Hannah | 2024-04-16 | Celcom Digi_RAN-YPTT-TSS-Sabah-20231024 | DU00002863565 |  |  | 2024-06-05 | 2024-05-17 |  | Tower | 30m Rapole | 61 | Add R8862A S9000 x3+R8894E M1821 x4,Dismantle R8882 S1800B(B6B) x1+R8862A S1800(B6A) x3+R8862A S2100(A6A) x4 | 0 | 1
Q00357 | Q132A_Q00357OD_TMTMNTUNKU | Sarawak |  | Decomm |  | 2025 Q1 | ZB | Trintel | 4.6 TSSR Approved |  | 2024-04-26 |  |  |  | 2024-04-30 |  | 2024-05-02 | 2024-09-05 | CD//John | 2024-05-02 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240503 | DU00002863566 | [6 empty] | TOWER
Q00233 | Q123A_Q00233OD_KAPIT | Sarawak |  | Decomm |  | 2025 Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2024-03-21 |  |  |  | 2024-03-21 |  | 2024-03-22 | 2024-08-29 | CD//John | 2024-03-22 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20240324 | DU00002863567 |  |  |  |  | 2025-10-28 |  | TOWER
2310A | Tmn rekreasi AU2 | Central |  | Modernization |  | 2024 Q1 | SY1 | GCI | 4.6 TSSR Approved |  | 2024-04-15 | 2024-05-16 |  | 2024-05-31 |  | Closed | 2024-12-16 | 2024-12-17 | E//Sumitra | 2024-12-17 | CelcomDigi_RAN_GCI_TSS_Central_20240513 | DU00002863568 |  |  | 2024-11-15 | 2024-11-11 |  | In-Building System | 3m Boom (RT) | 5 | Add R8862A S9000x3+R8894E M1821x2+A9732 M1821x1, Dismantle R8882-GUL1812x3+R8854D S2100(A4A)x3 | 2 | 0
W00119 | W066AA_W00119OD_JBATUNRAZAK | Central |  | Decomm |  | 2024 Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-11-20 |  |  |  | 2023-11-21 |  | 2024-08-13 | 2025-03-20 | CD//Norhaliza | 2024-10-24 | CelcomDigi_RAN_AllStar_TSS_Central_20231120 | DU00002863569 |  |  |  |  | 2024-08-12 |  | BOOM
2590B | Syabas Ara Damansara | Central |  | Modernization |  | 2024 Q1 | CR | GTSB | 4.6 TSSR Approved |  | 2023-11-21 | 2023-11-27 |  | 2024-01-06 |  | Closed | 2024-01-09 | 2024-01-11 | E//Kok Keen | 2024-01-10 | CelcomDigi_RAN_GTSB_TSS_Central_20231126 | DU00002863570 |  |  | 2024-03-06 | 2024-03-04 |  | Monople Tree | 30m Monopole | 45 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3
2913A | SS3 Syabas (REL) | Central |  | Modernization |  | 2024 Q1 | SS | Magicell | 4.6 TSSR Approved |  | 2024-01-25 | 2024-03-07 |  | 2024-03-12 |  | Closed | 2024-03-13 | 2024-03-14 |  | 2024-03-13 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240202 | DU00002863571 |  |  | 2024-04-24 | 2024-04-20 |  | Monopole | 30m Monopole | 30 | Add R9264M M1821 x3,Dismantle R8882 S1800B(B6B) x3++R8881 S2100 x3+
3203A | Oasis Ara Damansara | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q1 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002863572 | [6 empty] | 3m Boom (RT) |  |  | 12
4572B | Sayong (Maxis) RDD | Northern |  | Modernization |  | 2025 Q3 | AI | YPTT | 4.6 TSSR Approved |  | 2023-12-27 | 2023-12-29 |  | 2025-02-20 |  | Under Approval | 2025-02-20 | 2025-02-27 | E//Hazida | 2025-02-27 | Celcom Digi_RAN-YPTT-TSS-Northern-20231229-0049 | DU00002863573 |  |  | 2025-06-28 | 2025-03-04 |  | Tower | 60m 3 Legged Tower | 60M | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8882-GUL1812x3+R8862A S2100(A6A)x3 | 0 | 0
R00049 | R001C_R00049OD_PLANTERSHEIGHT | Northern |  | Decomm |  | 2024 Q4 | BY | GCI | 4.6 TSSR Approved |  | 2024-05-03 |  |  |  | 2024-05-28 |  | 2024-05-29 | 2024-06-19 | CD//Shamsul | 2024-06-06 | Celcom Digi_RAN-GCI-TSS-Northern-20240512-0106 | DU00002863574 |  |  |  |  | 2024-05-24 |  | LAMP_POLE
K00231 | K008A_K00231OD_CHANDEKKURA | Northern |  | Decomm |  | 2025 Q2 | HW | GTSB | 4.6 TSSR Approved |  | 2025-01-27 |  | 2025-01-23 |  | 2025-03-12 |  | 2025-03-13 |  | CD//Hazwan | 2025-03-13 | SQ202501060259 - GTSB | DU00002863575 |  | No NE/FE TX Part |  |  | 2025-04-30 |  | BOOM
K00247 | K008A_K00247OD_ULUMELAKA | Northern | 4627K | Swap | Decomm->On Hold->Swap | 2024 Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2024-12-09 | 2024-12-03 |  | 2024-12-09 |  | Under Approval | 2024-12-09 | 2024-12-12 | CD//Zulakmar | 2024-12-12 | Celcom Digi_RAN-GTSB-TSS-Northern-20241112_New Contract | DU00002863576 |  |  | 2025-02-22 | 2025-01-23 |  | Monopole | MONOPOLE | 30 | Add R8852E S9000x4+R8894E M1821 x2+R8862A S2601x4+A9732 M1821x2, Dismantle | 13 | 0
K00244 | K008A_K00244OD_TMKUAH | Northern | 4628K | Swap | Decomm->On Hold->Swap | 2024 Q4 | HW | GTSB | 4.6 TSSR Approved |  | 2025-03-04 | 2025-03-14 |  | 2025-03-17 |  | Under Approval | 2025-03-21 | 2025-04-24 | CD//Zulakmar | 2025-04-08 | SQ202412120674 - GTSB | DU00002863577 |  |  | 2025-05-20 | 2025-05-17 |  | Tower | TOWER | 30 | Add R8862A S9000x4+R8894E M1821 x4+R8862A S2601x3+R8854 S2600Ax1+A9732 M1821x1, Dismantle | 3 | 1
3093B | PJ SS9 | Central |  | Modernization |  | 2024 Q1 | HQ 1 | Magicell | 4.6 TSSR Approved | Pending Resurvey | 2024-04-01 | 2024-04-08 |  | 2024-04-09 |  | Under Approval | 2024-04-15 | 2024-12-17 | E//Kok Keen | 2024-12-17 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240403 | DU00002863578 |  |  | 2025-02-28 | 2025-02-28 |  | Minaret | 30m Minaret | 3 | Add R8862A S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 | 12
K00102 | K004B_K00102OD_LENCONGBARAT | Northern |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4 | HW | GTSB | 4.6 TSSR Approved | 1223 - GTSB plan Re-TSS 26/12 | 2024-01-23 |  |  |  | 2024-01-26 |  | 2025-03-12 | 2025-07-25 | CD//Zulakmar | 2025-03-13 | Celcom Digi_RAN-GTSB-TSS-Northern-20240124-0088 | DU00002863579 |  |  |  |  | 2024-12-06 |  | TOWER
W00751 | W066J_W00751OD_JELATEKPARK | Central |  | Decomm |  | 2024 Q1 | CR | GCI | 4.6 TSSR Approved |  | 2023-11-20 |  |  |  | 2023-11-23 |  | 2023-12-06 | 2024-10-28 | CD//Ali Akaram | 2024-01-17 | CelcomDigi_RAN_GCI_TSS_Central_20231201 | DU00002863580 |  |  |  |  | 2024-07-24 |  | TRIPOD
A00200 | A037A_A00200OD_PKNBARU | Northern |  | Decomm |  | 2024 Additional | HW | NR services | 4.6 TSSR Approved |  | 2025-04-30 |  | 2025-04-07 |  | 2025-04-30 |  | 2025-05-02 | 2025-10-28 | CD//Zulakmar | 2025-05-08 | SQ202502100379 | DU00002863581 |  |  |  |  | 2025-08-13 |  | MINI STRUCTURE
A00454 | A036B_A00454OD_TROLAKUTARA | Northern |  | Decomm |  | 2024 Q3(single site MOCN) | BY | Magicell | 4.6 TSSR Approved |  | 2023-12-13 |  |  |  | 2023-11-22 |  | 2024-06-27 | 2024-10-16 | CD//Zulakmar | 2024-06-27 | Celcom Digi_RAN-Magicell-TSS-Northern-20231214-0005_reraise/Celcom Digi_RAN-Magicell-TSS-Northern-20240205-0013 | DU00002863582 |  |  |  |  | 2024-08-16 |  | TOWER
A00241 | A042C_A00241OD_PKLNINDTAIPING | Northern |  | Decomm |  | 2024 Q2 | ZA | GCI | 4.6 TSSR Approved |  | 2023-10-25 |  |  |  | 2023-10-25 |  | 2023-10-27 | 2024-05-24 | CD//Quah | 2023-11-21 | Celcom Digi_RAN-GCI-TSS-Northern-20231028-0067/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240529-0109 | DU00002863583 |  | Missing TX Info |  |  | 2024-05-21 |  | TOWER
W00461 | B064A_W00461OD_TMNTUNPERAK | Central |  | Decomm |  | 2024 Q4(single site MOCN)-L26 SSM | BY | GCI | 4.6 TSSR Approved |  | 2024-05-30 |  |  |  | 2024-07-22 |  | 2024-07-23 | 2024-08-29 | CD//Ali Akaram | 2024-07-30 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240605 | DU00002863584 |  |  |  |  | 2024-10-23 | Monopole | SHARING STRC SBC | 30m
A00628 | A039A_A00628OD_TMNDAMAI | Northern |  | Decomm | Decomm->On Hold->Decomm->On Hold->Decomm | 2024 Q3(single site MOCN) | BY | GTSB | 4.6 TSSR Approved |  | 2023-12-07 |  |  |  | 2023-12-15 |  | 2023-12-28 | 2024-02-15 | CD//Quah | 2024-02-06 | Celcom Digi_RAN-GTSB-TSS-Northern-20231207-0073 | DU00002863585 |  |  |  |  | 2025-06-03 |  | TOWER
B02554 | B064B_B02554OD_JLNKPB7_PRDUSTRIAN_BALAKONG | Central |  | Decomm |  | 2024 Q3 | MA | Magicell | 4.6 TSSR Approved |  | 2024-02-28 |  |  |  | 2024-03-07 |  | 2024-04-26 |  | CD//Ali Akaram | 2024-05-15 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240303 | DU00002863586 |  | Missing antenna tx photo at NE |  |  | 2024-08-30 |  | BOOM
R00138 | R001C_R00138OD_SGBAHARU | Northern |  | Decomm |  | 2024 Q4 | BY | CCSMY | 4.6 TSSR Approved |  | 2024-03-07 |  |  |  | 2024-03-13 |  | 2024-04-23 | 2024-05-10 | CD//Quah | 2024-05-07 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240310-0099/0612Northern-CCSMY-BOQ Template (template) | DU00002863587 |  |  |  |  | 2024-06-07 |  | TOWER
B01123 | B064I_B01123OD_BTASIKKESUMA2 | Central |  | Decomm |  | 2024 Additional | AD | DATASCO | 4.6 TSSR Approved |  | 2024-07-18 |  | 2024-08-05 |  | 2024-08-20 |  | 2024-11-20 |  | CD//Ali akaram | 2024-12-02 | 0730CD-Datasco-Central-Datasco-BOQ Template(new contract) | DU00002863588 |  | Kindly maintain this fiber |  |  | 2025-02-26 |  | TOWER
7426A | Kg Tengkurus | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2024 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2025-02-25 | 2025-04-07 |  | 2025-04-10 |  | Under Approval | 2025-04-11 | 2025-04-24 | E//Hannah | 2025-04-21 | SQ202501020343 - GTSB | DU00002863589 |  |  | 2025-04-25 | 2025-04-23 |  | Tower | 45m 3 Legged Tower | 75 | Add R8894E M1821x1 | 0 | 2
L00152 | S113A_L00152OD_HOTELTIARA | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2025 Q1 | AD | YPTT | 4.6 TSSR Approved |  | 2025-01-15 |  | 2025-04-18 |  | 2025-04-21 |  | 2025-04-21 |  | CD//Sharidah | 2025-04-23 | SQ202501030034 - YPTT / SQ202501070337 - YPTT | DU00002863590 |  |  |  |  | 2025-03-26 |  | LAMP_POLE
L00006 | RL10049_LAZENDA | Sabah |  | Decomm |  | 2024 | MS | Datasco | 4.6 TSSR Approved |  | 2024-11-12 |  | 2024-11-25 |  | 2024-11-27 |  | 2024-11-28 | 2024-12-13 | CD//Jahganathan | 2024-11-28 | Celcom Digi_RAN-Datasco-Standard PR TSS-Sabah-20241030 | DU00002863591 |  |  |  |  | 2024-12-26 |  | BOOM
S01609 | S098C_S01609OD_PALMHEIGHTLDU | Sabah |  | Decomm | Decomm->On Hold->Decomm->On Hold->Decomm | 2024 Q3 | MS | GTSB | 4.6 TSSR Approved | Change anchor | 2024-05-15 |  |  |  | 2024-05-17 |  | 2024-05-20 | 2025-10-31 | CD//Jahganathan | 2025-10-29 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240519 | DU00002863592 |  |  |  |  | 2025-11-29 |  | TOWER
S01555 | S098B_S01555OD_HOSPLAHADDATU | Sabah |  | Decomm |  | 2024 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2024-05-15 |  |  |  | 2024-05-20 |  | 2024-05-23 | 2024-08-01 | CD//Jahganathan | 2024-05-27 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240519 | DU00002863593 |  |  |  |  | 2024-08-22 |  | RAPOLE
W00515 | W066J_W00515OD_TMKERAMAT | Central |  | Decomm |  | 2024 Q1 | CR | GCI | 4.6 TSSR Approved |  | 2024-04-04 |  |  |  | 2024-04-16 |  | 2024-05-24 | 2025-03-07 | CD//Sapian | 2024-05-28 | CelcomDigi_RAN_GCI_TSS_Central_20240513 | DU00002863594 |  |  |  |  | 2024-12-20 |  | BOOM
9268A | Kampung Muhibbah | Sarawak |  | Modernization |  | 2025 Q3 | SM | Magicell | 4.6 TSSR Approved |  | 2023-12-15 | 2023-12-21 |  | 2025-02-21 |  | Rectificating | 2025-03-04 | 2025-03-10 | E//Hannah | 2025-05-23 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231218 | DU00002863595 | Remarks: Solution TSSR/BOM Changed |  | 2025-06-29 | 2025-03-19 |  | Monopole | 30m Rapole | 17 | Add R8852E S9000x3+R8894E M1821x4+R8854 S2600x1, Dismantle R8882 S1800B(B6B)x3+R8862A S2601(A6A)x1 | 0 | 3
B02263 | B064G_B02263OD_JLNBG38-6BANGIGATEWAY | Central |  | Decomm |  | 2024 Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2024-03-01 |  |  |  | 2024-03-15 |  | 2024-03-15 | 2025-03-17 | CD//Norhaliza | 2024-06-04 | BOQ CelcomDigi_RAN_AllStar_Standard PR TSS_Central_20240128 | DU00002863596 |  |  |  |  | 2024-12-06 |  | BOOM
B00171 | B061J_B00171OD_JLNTEMPUAPCHG | Central |  | Decomm |  | 2024 Q3 | MA | Magicell | 4.6 TSSR Approved |  | 2024-03-07 |  |  |  | 2024-04-05 |  | 2024-04-26 | 2024-07-29 | CD//Sapian | 2024-05-14 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240316 | DU00002863597 |  |  |  |  | 2024-10-11 |  | BOOM
9269A | Hospital Sarikei Rapole | Sarawak |  | Modernization |  | 2025 Q2 | HW | Trintel | 4.6 TSSR Approved |  | 2025-04-02 | 2025-04-09 |  | 2025-04-12 |  | Under Approval | 2025-05-07 | 2025-05-23 | E//John | 2025-05-23 | SQ202503030411-Trintel | DU00002863598 | Remarks: Solution TSSR/BOM Changed |  | 2025-05-29 | 2025-05-16 |  | Monopole | 30m Rapole | 15m | Add R8862A S2601x3 | 0 | 0
W00169 | W066BB_W00169OD_TMNSEGAR | Central |  | Decomm |  | 2024 Q3 | BY | Ascentrack | 4.6 TSSR Approved |  | 2024-01-30 |  |  |  | 2024-02-14 |  | 2024-04-01 |  | CD//Sapian | 2024-04-30 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240202 | DU00002863599 |  | MISSING FE PART |  |  | 2024-07-31 |  | TOWER
W00929 | W066R_W00929OD_PSSBDRTUNRAZAK | Central |  | Decomm |  | 2024 Q3 | BY | GTSB | 4.6 TSSR Approved |  | 2024-07-31 |  | 2024-08-05 |  | 2024-08-06 |  | 2024-08-07 | 2024-10-28 | CD//Sapian | 2024-09-09 | 0802CD-Central-GTSB-BOQ Template(new contract) | DU00002863600 |  |  |  |  | 2024-08-14 |  | PETRONAS PYLON
9270A | Engkelili Town | Sarawak |  | Modernization |  | 2025 Q3 | SM | Magicell | 4.6 TSSR Approved |  | 2023-12-14 | 2023-12-18 |  | 2025-02-20 |  | Rectificating | 2025-03-05 | 2025-03-10 | E//Hannah | 2025-03-09 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231215 | DU00002863601 | Remarks: Solution TSSR/BOM Changed |  | 2025-07-06 | 2025-04-22 |  | Tower | 25m pBTS | 47M | Add R8894E M1821x2+R8862A S2601x1+R8854 S2600x2 | 0 | 12
B00222 | B064H_B00222OD_SENTOSATJERNANG | Central |  | Decomm |  | 2024 Q3 | SHA | GTSB | 4.6 TSSR Approved |  | 2024-09-11 |  | 2025-01-03 |  | 2024-10-04 |  | 2024-10-07 |  | CD//Sapian | 2024-10-17 | 0925CD-Central-GTSB-BOQ Template(new contract) | DU00002863602 |  |  |  |  | 2024-11-15 |  | BOOM
B01833 | B064B_B01833OD_CHERASPDANA | Central |  | Decomm |  | 2024 Q4 | CR | Solusi | 4.6 TSSR Approved |  | 2024-07-25 |  |  |  | 2024-09-06 |  | 2024-09-09 | 2024-10-28 | CD//Norhaliza | 2024-10-21 | 0724Central-Solusi-BOQ Template | DU00002863603 |  |  |  |  | 2024-09-19 |  | Rooftop
K00613 | K008A_K00613OD_LEBUHRAYA166 | Northern |  | Decomm |  | 2024 Q4 |  | CCSMY | 4.6 TSSR Approved |  | 2024-10-10 |  | 2024-10-15 |  | 2024-10-18 |  | 2024-11-05 | 2025-07-25 | CD//Zulakmar | 2024-11-07 | 0927CD-Northern-CCSMY-BOQ Template(new contract) | DU00002863604 |  |  |  |  | 2024-11-06 |  | TOWER
K00683 | K008A_K00683OD_AKADEMIKASTAMLKW | Northern |  | Decomm |  | 2024 Q3(single site MOCN) | SHA | CCSMY | 4.6 TSSR Approved | ¦ 0819 - CD Zul: Possible for 4164C pair site’s antennas to replace K00683 antenna height position? TSSR for decomm approved. | 2024-08-11 |  | 2024-08-13 |  | 2024-08-15 |  | 2024-08-16 | 2024-10-01 | CD//Zulakmar | 2024-08-19 | 0809MW-Northern-CCSMY-BOQ Template(new contract)/0809CD-Northern-CCSMY-BOQ Template(new contract) | DU00002863605 |  |  |  |  | 2024-11-05 |  | RAPOLE
R00052 | R001C_R00052OD_UNIMAPMAINCAMPUS | Northern |  | Decomm |  | 2024 Q4 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-12-10 |  |  |  | 2023-12-20 |  | 2023-12-28 | 2024-02-15 | CD//Quah | 2024-02-06 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231212-0080 | DU00002863606 |  |  |  |  | 2024-09-18 |  | TOWER
7429A | SMK Pekan 2 | Sabah |  | Modernization |  | 2024 Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-10-24 | 2023-10-25 |  | 2023-10-30 |  | Closed | 2024-04-02 | 2024-04-19 | E//Hannah | 2024-04-19 | Celcom Digi_RAN-YPTT-TSS-Sabah-20231024 | DU00002863607 |  |  | 2024-05-27 | 2024-05-17 |  | Tower | Tower | 60 | Add R8862A S9000 x3+R9224E M1821 x4+R8854 S2600 x1,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3+R8862A S2600(A4A) x1 | 0 | 3
S00216 | S105A_S00216OD_JALANBANDAR | Sabah |  | Decomm |  | 2024 Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2024-04-27 |  |  |  | 2024-05-03 |  | 2024-05-07 | 2024-05-24 | CD//Jahganathan | 2024-05-08 | Celcom Digi_RAN-YPTT-Standard PR TSS-Sabah-20240503 | DU00002863608 | [6 empty] | BOOM
Q00822 | Q132C_Q00822OD_JLNRIAM | Sarawak |  | Decomm |  | 2025 Q1 | SH | Trintel | 4.6 TSSR Approved |  | 2024-04-17 |  |  |  | 2024-04-18 |  | 2024-04-19 | 2024-05-24 | CD//John | 2024-04-23 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240420 | DU00002863609 |  |  |  |  | 2025-11-11 |  | MONOPOLE
W01484 | W066R_W01484OD_DESATASIK3_SRAALBAIHAQI | Central |  | Decomm |  | 2024 Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2024-04-04 |  |  |  | 2024-04-16 |  | 2024-04-16 | 2024-07-10 | CD//Sapian | 2024-05-08 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240407 | DU00002863610 |  |  |  |  | 2024-08-27 |  | LAMP_POLE
W00923 | W066H_W00923OD_JLNAYERJERNIH2 | Central |  | Decomm |  | 2024 Q1 | BY | DATASCO | 4.6 TSSR Approved |  | 2024-01-22 |  |  |  | 2024-06-24 |  | 2024-02-23 | 2024-09-25 | CD//Norhaliza | 2024-04-03 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240128 | DU00002863611 |  |  |  |  | 2024-05-24 |  | TRIPOD
3626B | Eve Suite | Central |  | Modernization |  | 2024 Q1 | CR | GTSB | 4.6 TSSR Approved |  | 2023-11-25 | 2023-11-28 |  | 2024-01-07 |  | Under Approval | 2024-01-09 | 2024-01-11 | E//Kok Keen | 2024-01-10 | CelcomDigi_RAN_GTSB_TSS_Central_20231126 | DU00002863612 |  |  | 2024-03-22 | 2024-03-16 |  | Lampole | 30m Lampole | 30m | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
W00348 | W066U_W00348OD1_KLSENTRALSL | Central |  | Decomm |  | 2024 Q2 | BY | CCSMY | 4.6 TSSR Approved |  | 2024-02-22 |  |  |  | 2024-02-22 |  | 2024-02-23 | 2024-07-12 | CD//Ali Akaram | 2024-04-16 | BOQ CelcomDigi_RAN_CCSMY_Standard PR TSS_Central_20240225 | DU00002863613 |  |  |  |  | 2024-07-31 |  | BOOM
W01056 | W066V_W01056OD_BALAIPOLISTRAVERS | Central |  | Decomm | Decomm->On hold->Decomm | 2024 Q2 | AI | DATASCO | 4.6 TSSR Approved |  | 2024-11-04 |  | 2024-11-26 |  | 2024-11-25 |  | 2024-12-03 | 2025-03-21 | CD//Norhaliza | 2024-12-05 | Celcom Digi_RAN-Datasco-Standard PR TSS-Central-20241016 | DU00002863614 |  |  |  |  | 2024-12-19 |  | BOOM
A00474 | A044A_A00474OD_CKTMELINTANG | Northern |  | Decomm |  | 2024 Q2 | ZA | GCI | 4.6 TSSR Approved |  | 2024-01-16 |  |  |  | 2024-02-05 |  | 2024-02-06 | 2024-10-01 | CD//Quah | 2024-02-26 | Celcom Digi_RAN-GCI-TSS-Northern-20240124-0091/0612Northern-GCI-BOQ Template (template) | DU00002863615 |  |  |  |  | 2024-06-28 |  | TOWER
A01036 | A044A_A01036OD_BDR UNIVERSITI SRI ISKANDAR3 | Northern |  | Decomm |  | 2024 Q2 | ZA | CCSMY | 4.6 TSSR Approved |  | 2024-02-28 |  |  |  | 2024-03-07 |  | 2024-03-08 | 2024-03-13 | CD//Quah | 2024-03-11 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240229-0097 | DU00002863616 |  |  |  |  | 2024-05-25 |  | MINARET
W00067 | W066T_W00067OD_TMNDANAUDESA | Central |  | Decomm |  | 2024 Q3 | ZA | Ascentrack | 4.6 TSSR Approved |  | 2024-01-17 |  |  |  | 2024-02-22 |  | 2024-04-01 | 2024-07-12 | CD//Norhaliza | 2024-06-13 | CelcomDigi_RAN_Ascentrack_TSS_Central_20240124 | DU00002863617 |  |  |  |  | 2024-05-28 |  | BOOM
Q01503 | Q135A_Q01503OD_KOLEJRAFFLESIA1 | Sarawak |  | Decomm |  | 2024 Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-11-30 |  |  |  | 2023-11-30 |  | 2023-11-30 | 2023-12-08 | CD//John | 2023-11-30 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231206/0612Sarawak-Trintel-BOQ Template (template) | DU00002863618 |  |  |  |  | 2024-12-28 |  | RAPOLE
B00811 | B064E_B00811OD_TMNSRIJERLOK | Central |  | Decomm |  | 2024 Q4 | AD | GTSB | 4.6 TSSR Approved |  | 2024-01-11 |  |  |  | 2024-05-15 |  | 2024-05-24 | 2025-07-25 | CD//Norhaliza | 2024-10-04 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240115 | DU00002863619 |  |  |  |  | 2024-10-15 |  | TOWER
W01032 | W066J_W01032OD_SWANGSA | Central |  | Decomm |  | 2024 Q1 | CR | GCI | 4.6 TSSR Approved |  | 2023-11-18 |  |  |  | 2023-11-24 |  | 2023-12-08 | 2024-01-22 | CD//Sapian | 2023-12-21 | CelcomDigi_RAN_GCI_TSS_Central_20231201 | DU00002863620 |  |  |  |  | 2024-07-20 |  | UNIPOLE
S00444 | S094A_S00444OD_HOSPITALMARU | Sabah |  | Decomm |  | 2025 Q3 | HW | GTSB | 4.6 TSSR Approved |  | 2025-01-09 |  | 2025-02-23 |  | 2025-03-07 |  | 2025-03-10 | 2025-09-10 | CD//Sharidah | 2025-03-17 | SQ202501020455 - GTSB | DU00002863621 |  |  |  |  | 2025-05-18 |  | TOWER
S00339 | S098B_S00339OD_JAGOKOTA | Sabah |  | Decomm |  | 2024 Q3 | MS | GTSB | 4.6 TSSR Approved |  | 2024-05-08 |  |  |  | 2024-05-14 |  | 2024-05-20 | 2024-11-22 | CD//Jahganathan | 2024-05-21 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240510 | DU00002863622 |  |  |  |  | 2024-07-23 |  | BOOM
Q00377 | Q137A_Q00377OD_WAHMAN | Sarawak |  | Decomm |  | 2025 Q2 | ZB | Trintel | 4.6 TSSR Approved |  | 2023-12-22 |  |  |  | 2023-12-28 |  | 2023-12-28 | 2024-01-05 | CD//John | 2023-12-28 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231231 | DU00002863623 |  |  |  |  | 2025-08-29 |  | TOWER
Q01798 | Q132A_Q01798OD_TMNJELITA4 | Sarawak |  | Decomm |  | 2024 Q4(single site MOCN)-L21 SSM | SH | Trintel | 4.6 TSSR Approved |  | 2024-04-23 |  |  |  | 2024-04-24 |  | 2024-04-24 | 2024-05-24 | CD//John | 2024-04-24 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240503 | DU00002863624 |  |  |  |  | 2025-03-27 |  | RAPOLE
W01285 | W066R_W01285OD_DESATASIK2 | Central |  | Decomm |  | 2024 Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2024-03-13 |  |  |  | 2024-03-14 |  | 2024-07-22 | 2024-11-26 | CD//Norhaliza | 2024-11-12 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240316 | DU00002863625 |  |  |  |  | 2024-08-27 |  | UNIPOLE
B00090 | W066X_B00090OD_INDAHSQUARE | Central |  | Decomm |  | 2024 Q2 | MS | YPTT | 4.6 TSSR Approved |  | 2024-07-29 |  | 2024-08-16 |  | 2024-09-23 |  | 2024-09-25 |  | CD//Sapian | 2024-10-02 | 0731CD-Central-YPTT-BOQ Template(new contract) | DU00002863626 |  |  |  |  | 2024-09-30 |  | BOOM
Q01261 | Q132A_Q01261OD_TMNJELITA2 | Sarawak |  | Decomm |  | 2024 | ZB | Trintel | 4.6 TSSR Approved |  | 2024-05-06 |  |  |  | 2024-05-06 |  | 2024-05-06 | 2024-05-24 | CD//John | 2024-05-06 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240510 The Cluster Sequence of this site is: 2025 (swap out sarawak cluster). This type of site survey and design fee settlement method is being communicated with the customer, and the submission of PR will be held on. | DU00002863627 |  |  |  |  | 2025-05-16 |  | LAMP_POLE
B00264 | B064F_B00264OD_TMNJELITA | Central |  | Decomm |  | 2024 Q4 | MS | Magicell | 4.6 TSSR Approved |  | 2024-02-28 |  |  |  | 2024-02-29 |  | 2024-12-16 | 2025-01-14 | CD//Norhaliza | 2024-12-23 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240303 | DU00002863628 |  |  |  |  | 2024-09-29 |  | BOOM
B00533 | B063A_B00533OD_BDRSEPANG | Central |  | Decomm |  | 2024 Additional | HW | GCI | 4.6 TSSR Approved |  | 2024-12-23 |  | 2025-05-30 |  | 2025-06-17 |  | 2025-06-19 |  | CD//Sapian | 2025-06-25 | SQ202507020090 | DU00002863629 |  |  |  |  | 2025-07-09 |  | TOWER
B00813 | B064G_B00813OD_SEK6BBBANGI | Central |  | Decomm |  | 2024 Q3 | CR | GTSB | 4.6 TSSR Approved |  | 2024-06-05 | 2024-06-27 |  |  | 2024-07-02 |  | 2024-07-03 | 2025-03-07 | CD//Ali Akaram | 2024-07-25 | 0607Central-GTSB-BOQ Template | DU00002863630 |  |  |  |  | 2025-01-06 | In-Building System | MINI STRUCTURE | 4M
W00146 | W066S_W00146OD_JLNMEGAMENDUNG | Central |  | Decomm |  | 2024 Q3 | SH | DATASCO | 4.6 TSSR Approved |  | 2024-05-03 |  |  |  | 2024-05-29 |  | 2024-05-30 |  | CD//Sapian | 2024-06-12 | CelcomDigi_RAN_Datasco_TSS_Central_20240513 | DU00002863631 |  |  |  |  | 2024-08-28 |  | BOOM
W01241 | W066V_W01241OD_LRT_UNIVERSITI | Central |  | Decomm |  | 2024 Q2 | MA | GCI | 4.6 TSSR Approved |  | 2024-07-02 |  |  |  | 2024-07-03 |  | 2024-07-04 | 2024-08-20 | CD//Sapian | 2024-07-18 | 0918CD-Central-GCI-BOQ Template (old contract) | DU00002863632 |  |  |  |  | 2024-09-24 |  | UNIPOLE
B00503 | B063B_B00503OD_PR_KLIA | Central |  | Decomm |  | 2024 | AD | GTSB | 4.6 TSSR Approved |  | 2024-03-07 |  |  |  | 2024-04-01 |  | 2024-05-24 | 2025-03-17 | CD//Ali akaram | 2024-12-06 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240311 | DU00002863633 | [6 empty] | TOWER
7257B | Kg Linau | Sabah |  | Modernization |  | 2024 Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-10-27 | 2023-11-01 |  | 2024-03-26 |  | Closed | 2024-03-27 | 2024-04-02 | E//Hannah | 2024-04-02 | Celcom Digi_RAN-YPTT-TSS-Sabah-20231028 | DU00002863634 |  |  | 2024-06-08 | 2024-05-17 |  | Tower | 45m 3 Legged Tower | 45 | Add R8862A S9000 x3+R8894E M1821 x2,Dismantle | 0 | 13
Q02091 | Q124E_Q02091OD_KGSINJOK2 | Sarawak |  | Decomm |  | 2024 Q4(single site MOCN)-L21 SSM | ZB | South Pacific | 4.6 TSSR Approved |  | 2024-02-13 |  |  |  | 2024-02-14 |  | 2024-02-16 | 2024-05-24 | CD//John | 2024-03-18 | Celcom Digi_RAN-South Pacific-Standard PR TSS-Sarawak-20240220 | DU00002863635 |  |  |  |  | 2024-11-22 |  | RAPOLE
9388B | Rh Semop | Sarawak |  | Modernization | Modernization->Remote MOCN->Modernization | 2025 Q1 | AI | Magicell | 4.6 TSSR Approved |  | 2024-01-31 | 2024-02-13 |  | 2025-02-06 |  | Closed | 2025-02-07 | 2025-06-28 | E//Hannah | 2025-03-10 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20240123 | DU00002863636 | Remarks: Solution TSSR/BOM Changed |  | 2025-07-06 | 2025-06-28 |  | Tower | Tower | 75M | Add R8862A S2601x3 | 0 | 0
W00147 | W066T_W00147OD_PBANKOUG | Central |  | Decomm |  | 2024 Q3 | AI | Magicell | 4.6 TSSR Approved | 6/8 - Team plan wk33 | 2025-08-07 |  | 2025-08-11 |  | 2025-08-18 | To be Submitted | 2025-09-18 |  | CD//Sapian | 2025-11-04 | SQ202508190105 | DU00002863637 |  |  |  |  | 2025-10-23 |  | MINI STRUCTURE
W01288 | W066V_W01288OD_LRT_BANGSAR | Central |  | Decomm | Decomm->On Hold->Decomm | 2024 Q2 | MS | YPTT | 4.6 TSSR Approved |  | 2024-03-07 |  |  |  | 2024-03-07 |  | 2024-03-14 | 2024-07-12 | CD//Norhaliza | 2024-07-05 | BOQ_Celcom Digi_RAN-YPTT-Standard PR TSS-20240311 | DU00002863638 |  |  |  |  | 2024-12-06 |  | UNIPOLE
Q01376 | Q133A_Q01376OD_KGTELIAN | Sarawak |  | Decomm |  | 2025 Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2024-02-28 |  |  |  | 2024-02-29 |  | 2024-03-01 | 2024-04-24 | CD//John | 2024-03-21 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240302/Celcom Digi_RAN-Trintel-Standard PR TSS DECOMM-Sarawak-20240314 | DU00002863639 |  |  |  |  | 2025-06-14 |  | RAPOLE
Q01342 | Q123A_Q01342OD_CHELSEAHEIGHT | Sarawak |  | Decomm |  | 2025 Q3 | ZB | Trintel | 4.6 TSSR Approved |  | 2024-04-24 |  |  |  | 2024-04-30 |  | 2024-05-06 | 2024-05-24 | CD//John | 2024-05-08 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240503 | DU00002863640 |  |  |  |  | 2025-10-25 |  | RAPOLE
B01083 | B064I_B01083OD_KM13SILKHWY | Central |  | Decomm |  | 2024 Q4(single site MOCN)-L2126 SSM | AD | GCI | 4.6 TSSR Approved |  | 2024-11-08 |  |  |  | 2024-11-22 |  | 2024-11-27 |  | CD//Sapian | 2024-12-04 | 0924CD-Central-GCI-BOQ Template(new contract) | DU00002863641 |  | 1) Pls provide antenna TX photo at NE 2) Missing FE part |  |  | 2024-11-08 |  | TOWER
B01098 | B061K_B01098OD_BDRPUTERIPCHG | Central |  | Decomm |  | 2024 Q3 | MA | Magicell | 4.6 TSSR Approved |  | 2024-03-30 |  |  |  | 2024-04-08 |  | 2024-04-29 | 2025-03-07 | CD//Sapian | 2024-05-15 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240403 | DU00002863642 |  | Please amend the TSSR to mention dish size at FE required to be dismantled: |  |  | 2024-09-26 |  | MINI STRUCTURE
S00205 | S105B_S00205OD_TMNMAWAR | Sabah |  | Decomm |  | 2025 Q2 | MS | GTSB | 4.6 TSSR Approved |  | 2024-07-09 |  | 2024-07-15 |  | 2024-07-24 |  | 2024-07-29 | 2024-09-05 | CD//Jahganathan | 2024-07-30 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240813 | DU00002863643 |  |  |  |  | 2024-08-15 |  | LAMP_POLE
W01369 | W066V_W01369OD_JLNPANTAIPERMAI | Central |  | Decomm |  | 2024 Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-01-29 |  |  |  | 2024-01-30 |  | 2024-02-01 | 2024-08-29 | CD//Sapian | 2024-02-26 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240202 | DU00002863644 |  |  |  |  | 2024-08-30 |  | LAMP_POLE
L00162 | S113A_L00162OD_LNBRANCHARANCHA2 | Sabah |  | Decomm |  | 2025 Q1 | SM | Seri Pancar | 4.6 TSSR Approved |  | 2024-01-22 |  | 2024-07-11 |  | 2024-07-14 |  | 2025-01-03 | 2025-05-02 | CD//Sharidah | 2025-02-07 | SQ202501020446 - Seri Pancar / SQ202501070297 - Seri Pancar | DU00002863645 |  |  |  |  | 2025-03-20 |  | #N/A
B00247 | B064H_B00247OD_BANGILAMA2 | Central |  | Decomm |  | 2024 | SHA | GTSB | 4.6 TSSR Approved |  | 2024-08-28 |  | 2024-09-12 |  | 2024-09-18 |  | 2024-11-21 | 2025-10-01 | CD//Norhaliza | 2024-12-06 | 0919CD-Central-GTSB-BOQ Template(new contract) 2 | DU00002863646 |  |  |  |  | 2024-11-14 |  | TOWER
B00651 | B064G_B00651OD_BANGILAMA | Central |  | Decomm |  | 2024 | SHA | GTSB | 4.6 TSSR Approved |  | 2024-09-14 |  | 2024-09-20 |  | 2024-09-25 |  | 2024-11-21 | 2025-03-07 | CD//Ali akaram | 2024-12-03 | 0919CD-Central-GTSB-BOQ Template(new contract) 2 | DU00002863647 |  |  |  |  | 2024-11-05 |  | TOWER
B02453 | B064F_B02453OD_TMN_TEKNOLOGI_KJG | Central |  | Decomm |  | 2024 | CR | GCI | 4.6 TSSR Approved |  | 2024-01-23 |  |  |  | 2024-02-05 |  | 2024-05-17 | 2024-08-29 | CD//Sapian | 2024-05-30 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240128 | DU00002863648 |  |  |  |  | 2024-10-01 |  | POLE
B01025 | B064A_B01025OD_BKTTEMPEYEK | Central | 1896K | Swap | Decomm->On Hold->Swap | 131 single site mocn | AI | GTSB | 4.6 TSSR Approved |  | 2024-10-14 |  | 2024-10-17 | 2024-12-05 | 2024-11-12 | Closed | 2024-12-06 | 2024-12-10 | CD//Sapian | 2024-12-10 | S1MY2024071003WBF1-1056 | DU00002863649 |  | Pls provide cisco router photo | 2025-08-29 | 2025-09-09 |  |  | TOWER |  | Add R8862A S9000x3+R9264M M1821x1+R8862A S2601x3+A9732 M1821x2, Dismantle | 23 | 0
9264A | Hoover Height | Sarawak |  | Modernization | Modernization->On Hold->Modernization | 2025 Q3 | AD | Magicell | 4.6 TSSR Approved |  | 2023-12-12 | 2023-12-15 |  | 2025-10-01 |  | Under Approval | 2025-10-03 | 2025-10-14 | E//John | 2025-10-03 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231214 | DU00002863650 |  |  | 2025-10-12 | 2025-10-11 |  | Monopole | 30m Rapole | 33M | Add R8862A S2601x3 | 0 | 0
B02434 | W066J_B02434OD_SURAUALAZIZIAH_TMNKERAMAT | Central |  | Decomm |  | 2024 Q1 | CR | GCI | 4.6 TSSR Approved |  | 2024-01-11 |  |  |  | 2024-01-26 |  | 2024-01-30 | 2025-03-17 | CD//Sapian | 2024-02-27 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240115 | DU00002863651 |  |  |  |  | 2024-07-23 |  | LAMP_POLE
9465B | Betong New Township | Sarawak |  | Modernization |  | 2025 Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2023-11-09 | 2023-11-10 |  | 2025-02-19 |  | Closed | 2025-03-28 | 2025-04-29 | E//Hannah | 2025-04-14 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20231112 | DU00002863652 |  |  | 2025-05-04 | 2025-04-25 |  | Monopole | 30m Rapole | 30 | Add R8894E M1821x1 | 0 | 2
B00744 | W067A_B00744OD_PR_MMUCYBERJAYA | Central |  | Decomm |  | 2024 Q3 | MA | Magicell | 4.6 TSSR Approved |  | 2024-02-20 |  |  |  | 2024-02-25 |  | 2024-04-30 | 2024-05-27 | CD//Ali Akaram | 2024-05-15 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240225 | DU00002863653 |  |  |  |  | 2024-11-29 |  | BOOM
7334B | Kg Sorob | Sabah |  | Modernization |  | 2024 Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-10-25 | 2023-11-04 |  | 2024-04-03 |  | Closed | 2024-04-18 | 2024-04-15 | E//Hannah | 2024-04-05 | Celcom Digi_RAN-YPTT-TSS-Sabah-20231028 | DU00002863654 |  |  | 2024-05-20 | 2024-05-11 |  | Monopole | 45m 3 Legged Tower | 45 | Add R8862A S9000 x3+R9224E M1821 x4+R8854 S2600 x1,Dismantle R8882 S1800B(B6B) x3+R8862A S2600(A4A) x1++R8881 S2100 x3+ | 0 | 2
7338B | Kg Kuala Ibai | Sabah |  | Modernization |  | 2024 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2023-10-22 | 2023-10-24 |  | 2023-10-26 |  | Closed | 2024-03-26 | 2024-04-15 | E//Hannah | 2024-04-08 | Celcom Digi_RAN-YPTT-TSS-Sabah-20231024 | DU00002863655 |  |  | 2024-05-10 | 2024-05-08 |  | Monopole | 30m Rapole | 30 | Add R8862A S9000 x3+R8894E M1821 x2+A9732 M1821 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 3 | 0
7339B | Kg Tambulion | Sabah |  | Modernization |  | 2024 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2023-10-25 | 2023-11-01 |  | 2024-03-26 |  | Closed | 2024-03-27 | 2024-04-15 | E//Hannah | 2024-04-06 | Celcom Digi_RAN-YPTT-TSS-Sabah-20231028 | DU00002863656 |  |  | 2024-05-06 | 2024-04-30 |  | Monopole | 45m Monopole | 45 | Add R8862A S9000 x3+R8894E M1821 x1,Dismantle | 0 | 3
7332B | Kg Nahaba | Sabah |  | Remote MOCN | Modernization->On Hold->Modernization->Remote MOCN | 2024 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2025-02-25 | 2025-04-07 |  | 2025-04-13 |  | Under Approval | 2025-04-14 | 2025-07-16 | E//Hannah | 2025-04-21 | SQ202501020343 - GTSB | DU00002863657 | [6 empty] | 45m 3 Legged Tower | 75 | Reuse Existing RRU | 0 | 0
7259B | Kg Rampayan Ulu | Sabah |  | Modernization |  | 2024 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2024-01-24 | 2024-04-01 |  | 2024-04-05 |  | Closed | 2024-04-08 | 2024-04-19 | E//Hannah | 2024-04-19 | Celcom Digi_RAN-GTSB-TSS-Sabah-20240204 | DU00002863658 |  |  | 2024-05-27 | 2024-05-08 |  | Lampole | 45m 3 Legged Tower | 30 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882 S1800B(B6B) x3 | 0 | 0
Q00636 | Q129A_Q00636OD_PKNBINTANGOR | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-12-19 |  |  |  | 2024-01-03 |  | 2024-01-24 | 2024-08-29 | CD//John | 2024-01-26 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231218 | DU00002863659 |  |  |  |  | 2025-05-29 |  | TOWER
W01277 | W066G_W01277OD_PLATINUMWALK | Central |  | Decomm |  | 2024 Q1 | CR | GCI | 4.6 TSSR Approved |  | 2023-11-23 |  |  |  | 2023-11-27 |  | 2023-11-28 | 2024-09-25 | CD//Sapian | 2023-12-04 | CelcomDigi_RAN_GCI_TSS_Central_20231126 | DU00002863660 |  |  |  |  | 2024-05-15 |  | UNIPOLE
K00458 | K004B_K00458OD_TAMANSAGA | Northern | 4618K | Swap | Decomm->On Hold->Swap | 2024 Q3(single site MOCN) | SM | GCI | 4.6 TSSR Approved | ¦ 1009 - CD Zul: Propose new azimuth for better separation: 80/170/240/330 | 2024-01-08 | 2024-09-24 |  | 2024-10-03 | 2024-03-11 | Rectificating | 2024-10-11 | 2024-10-14 | CD//Zulakmar | 2024-10-14 | Celcom Digi_RAN-GCI-TSS-Northern-20240116-0089/0823CD-Northern-GCI-BOQ Template(new contract) | DU00002863661 |  |  | 2024-11-19 | 2024-11-05 |  | Lampole | LAMP_POLE | 24 | Add R8862A S9000 x4+R8862A S2601 x2+A9732 M1821 x2+R8894E M1821x2,Dismantle | 13 | 0
7349B | Bukit X (REL) | Sabah |  | Modernization |  | 2024 Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-10-22 | 2023-10-24 |  | 2023-10-27 |  | Closed | 2024-04-04 | 2024-04-16 | E//Hannah | 2024-04-16 | Celcom Digi_RAN-YPTT-TSS-Sabah-20231024 | DU00002863662 |  |  | 2024-06-08 | 2024-05-11 |  | Tower | Tower | 76 | Add R8862A S9000 x3+R8894E M1821 x1+R8854 S2600 x1,Dismantle R8881 S9000 x3+R8862A S2600(A4A) x1 | 0 | 2
W00297 | W066U_W00297OD_PR_JLNDESABAKTI | Central |  | Decomm |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-08-10 |  | 2024-08-13 |  | 2024-08-23 |  | 2024-08-27 | 2025-01-14 | CD//Sapian | 2024-09-02 | 0809CD-Central-GTSB-BOQ Template(new contract) | DU00002863663 |  |  |  |  | 2024-09-11 |  | MONOPOLE
B00347 | B061Q_B00347OD_TMTMNPETALING | Central |  | Decomm |  | 2024 Q3 | CR | GTSB | 4.6 TSSR Approved |  | 2024-07-17 |  | 2024-08-01 |  | 2024-08-15 |  | 2024-08-19 | 2025-03-07 | CD//Sapian | 2024-08-23 | CelcomDigi_RAN_GTSB_TSS_Central_20240423 | DU00002863664 |  |  |  |  | 2024-12-31 |  | TOWER
B00215 | B064G_B00215OD_TMNTENAGA | Central |  | Decomm |  | 2024 Q3 | SM | GCI | 4.6 TSSR Approved |  | 2024-09-26 |  |  |  | 2024-10-01 |  | 2024-10-02 | 2025-03-07 | CD//Ali Akaram | 2024-10-22 | 0924CD-Central-GCI-BOQ Template(new contract) | DU00002863665 |  |  |  |  | 2024-09-30 |  | MINI STRUCTURE
W00026 | W066T_W00026OD_TMKUALAPAUH | Central |  | Decomm |  | 2024 Q3 | MS | GCI | 4.6 TSSR Approved |  | 2024-09-10 |  | 2024-09-18 |  | 2024-09-19 |  | 2024-09-20 | 2025-01-14 | CD//Sapian | 2024-09-27 | 0906CD-Central-GCI-BOQ Template(new contract) | DU00002863666 |  |  |  |  | 2024-09-10 |  | BOOM
B02487 | B061J_B02487OD_LAKEEDGEPCHG | Central |  | Decomm |  | 2024 Q3 | MA | Magicell | 4.6 TSSR Approved |  | 2023-11-08 |  |  |  | 2024-02-09 |  | 2024-04-30 | 2025-03-07 | CD//Sapian | 2024-05-15 | CelcomDigi_RAN_Magicell_TSS_Central_20231113 | DU00002863667 |  |  |  |  | 2024-09-27 |  | AESTHETIC MONOPOLE
B02241 | B064G_B02241OD_SURAUALBOORITMNUNIVERSITIKJG | Central |  | Decomm |  | 2024 | AD | GTSB | 4.6 TSSR Approved |  | 2024-10-03 |  | 2024-10-07 |  | 2024-10-14 |  | 2024-11-21 | 2025-03-07 | CD//Norhaliza | 2024-12-06 | 1007CD-Central-GTSB-BOQ Template(new contract) | DU00002863668 |  |  |  |  | 2024-10-17 |  | LAMP_POLE
B02228 | B063C_B02228OD_SURAUAL-IMANDENGKIL | Central |  | Decomm |  | 2025 Q3 | SH | GTSB | 4.6 TSSR Approved |  | 2024-02-26 |  |  |  | 2024-02-29 |  | 2024-05-24 | 2024-09-25 | CD//Sapian | 2024-06-10 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240303 | DU00002863669 |  |  |  |  | 2025-02-19 |  | RAPOLE
7433A | Masjid Nurul Iman Tambunan (REL) | Sabah |  | Site Out (Modernization) | Modernization->Site Out->Site Out (Modernization) | 2024 Q4 | MS | YPTT | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2025-06-21 |  | 2025-06-20 | [7 empty] | SQ202506160230 - YPTT | DU00002863670 | [6 empty] | 3m Boom (RT)
B02157 | W067A_B02157OD_PERSIARANCERIACBJ | Central |  | Decomm |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-02-05 |  | 2024-07-30 |  | 2024-08-02 |  | 2024-08-06 | 2025-03-11 | CD//Norhaliza | 2024-10-04 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240212 | DU00002863671 |  |  |  |  | 2024-12-20 |  | BOOM
B01119 | B064B_B01119OD_TMNBKTBELIMBING | Central |  | Decomm | Decomm->On Hold->Decomm | 2024 Q3 | MA | Magicell | 4.6 TSSR Approved |  | 2024-02-13 |  |  |  | 2024-02-14 |  | 2024-05-03 | 2025-02-21 | CD//Norhaliza | 2024-12-13 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240218 | DU00002863672 |  |  |  |  | 2024-11-25 |  | MINI STRUCTURE
B02064 | W067A_B02064OD_AIACYBERJAYA | Central | 1900K | Swap | Decomm->On Hold->Swap | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-12-27 | 2025-01-08 |  | 2025-01-16 | 2024-05-10 | Closed | 2025-01-24 | 2025-03-10 | CD//Norhaliza | 2025-02-18 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240311 | DU00002863673 |  |  | 2025-05-27 | 2025-05-27 |  | In-Building System | BOOM | 5M | Add R8852E S9000x3+R9264M M1821x2+R8862A S2601x2+R8854 S2600x1+A9732 M1821x1, Dismantle | 1 | 2
W01394 | W066E_W01394OD_JLNPELANGI1_TMNPELANGI | Central |  | Decomm |  | 2024 Q1 | SS | Magicell | 4.6 TSSR Approved |  | 2024-02-03 |  |  |  | 2024-02-07 |  | 2024-02-08 | 2024-05-12 | CD//Sapian | 2024-04-24 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240212 | DU00002863674 |  |  |  |  | 2024-04-02 |  | LAMP_POLE
9939A | Betong State Complex | Sarawak |  | Modernization | Modernization->Remote MOCN->Modernization | 2025 Q3 | AD | Magicell | 4.6 TSSR Approved |  | 2024-03-28 | 2024-04-01 |  | 2025-02-20 |  | Under Approval | 2025-02-21 | 2025-03-09 | E//Hannah | 2025-03-17 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20240123 | DU00002863675 | Remarks: Solution TSSR/BOM Changed |  | 2025-08-15 | 2025-08-14 |  | Monopole | 30m Rapole | 30 | Add R8862A S2601x3 | 0 | 0
B00227 | B064F_B00227OD_KAJANGUTAMA2 | Central |  | Decomm |  | 2024 Q4(single site MOCN)-L26 SSM | SH | Magicell | 4.6 TSSR Approved |  | 2024-02-28 |  |  |  | 2024-02-29 |  | 2024-05-21 | 2024-07-19 | CD//Ali Akaram | 2024-07-17 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240303 | DU00002863676 |  |  |  |  | 2024-10-23 |  | BOOM
W01510 | W066S_W01510OD_SRIRAKYATAPRT_BKTJALIL | Central |  | Decomm | Decomm-On Hold->Decomm | 2024 Q3 | ZA | GTSB | 4.6 TSSR Approved |  | 2024-02-06 |  |  |  | 2024-02-14 |  | 2024-04-01 | 2024-05-27 | CD//Ali Akaram | 2024-05-13 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240212 | DU00002863677 |  |  |  |  | 2025-05-26 |  | LAMP_POLE
A00170 | A039A_A00170OD_CB_JLNTGPIANDANG | Northern |  | Decomm |  | 2024 Q3(single site MOCN) | SHA | CCSMY | 4.6 TSSR Approved |  | 2024-02-09 |  |  |  | 2024-02-09 |  | 2024-06-27 | 2024-10-01 | CD//Zulakmar | 2024-06-28 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240215-0093 | DU00002863678 |  |  |  |  | 2024-08-21 |  | TOWER
S00165 | S105A_S00165OD_MPS | Sabah |  | Decomm |  | 2024 Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2024-04-27 |  |  |  | 2024-05-08 |  | 2024-05-09 | 2024-08-09 | CD//Jahganathan | 2024-05-10 | Celcom Digi_RAN-YPTT-Standard PR TSS-Sabah-20240503 | DU00002863679 |  |  |  |  | 2024-10-02 |  | BOOM
S00673 | S094A_S00673OD_MARUDUTOWN | Sabah |  | Decomm | Decomm->On Hold->Decomm | 2024 Q3(single site MOCN) | AD | Seri Pancar | 4.6 TSSR Approved |  | 2024-07-01 |  | 2024-07-07 |  | 2024-07-13 |  | 2024-12-06 | 2025-05-02 | CD//Sharidah | 2024-12-10 | S1MY2023083001WBF1-132 | DU00002863680 |  |  |  |  | 2025-09-09 |  | TOWER
W01224 | W066G_W01224OD_JALAN_CENGAL_SETAPAK | Central |  | Decomm |  | 2024 Q1 | SS | GCI | 4.6 TSSR Approved |  | 2023-11-10 |  |  |  | 2023-11-20 |  | 2023-11-22 | 2025-03-17 | CD//Ali Akaram | 2024-02-20 | CelcomDigi_RAN_GCI_TSS_Central_20231113 | DU00002863681 |  |  |  |  | 2024-05-11 |  | LAMP_POLE
9561B | Celcom Betong | Sarawak |  | Modernization |  | 2025 Q3 | AD | AllStar | 4.6 TSSR Approved |  | 2023-11-10 | 2023-11-15 |  | 2025-02-20 |  | Under Approval | 2025-02-27 | 2025-04-22 | E//Hannah | 2025-03-10 | Celcom Digi_RAN-Allstar-TSS-Sarawak-20231112 | DU00002863682 |  |  | 2025-05-04 | 2025-04-16 |  | Tower | Tower | 45 | Reuse Existing RRU | 0 | 0
K00685 | K008A_K00685OD_PDGMASIRAT | Northern |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4 | HW | CCSMY | 4.6 TSSR Approved |  | 2025-01-19 |  | 2025-01-03 |  | 2025-04-09 |  | 2025-04-25 | 2025-07-25 | CD//Zulakmar | 2025-05-09 | 0927CD-Northern-CCSMY-BOQ Template(new contract)0927MW-Northern-CCSMY-BOQ Template(new contract) | DU00002863683 |  |  |  |  | 2024-12-19 |  | MONOPOLE
A00085 | A039B_A00085OD_CB_BKTMERAH2 | Northern | 4629K | Swap | Decomm->On Hold->Swap | 2025 Q1 | HW | CCSMY | 4.6 TSSR Approved |  | 2023-11-21 | 2025-03-17 |  | 2025-03-21 | 2023-12-08 | Under Approval | 2025-03-29 | 2025-05-19 | CD//Zulakmar | 2025-04-10 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231122-0072//SQ202501030037 | DU00002863684 | Remarks: Solution TSSR/BOM Changed |  | 2025-06-11 | 2025-06-10 |  | Tower | TOWER | 32M | Add R8862A S9000x3+R9264M M1821x3, Dismantle | 0 | 0
9533B | Skrang 2 | Sarawak |  | Modernization |  | 2025 Q3 | HW | YPTT | 4.6 TSSR Approved |  | 2025-03-11 | 2025-05-29 |  | 2025-06-15 |  | Under Approval | 2025-06-16 | 2025-07-21 | E//John | 2025-06-17 | SQ202502190399-YPTT | DU00002863685 |  |  | 2025-09-09 | 2025-09-08 |  | Tower | Tower | 45 | Add R8894E M1821x1 | 0 | 2
9514B | CBKGSENGKUANG | Sarawak |  | Maintain USP MOCN | Modernization->Maintain USP MOCN | 2025 Q3 | SM | Magicell | 4.6 TSSR Approved |  | 2023-12-11 | 2023-12-15 |  | 2025-02-18 |  | Rectificating | 2025-02-26 | 2025-05-27 | E//Hannah | 2025-03-19 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231212 | DU00002863686 | [5 empty] | Tower | Tower | 62 | Reuse Existing RRU | 0 | 0
R00039 | R001B_R00039OD_KGWAIKECIL | Northern |  | Decomm |  | 2024 Q4 | SM | GTSB | 4.6 TSSR Approved |  | 2024-02-09 |  |  |  | 2024-02-09 |  | 2024-04-24 | 2024-05-24 | CD//Quah | 2024-05-21 | Celcom Digi_RAN-GTSB-TSS-Northern-20240223-0093 | DU00002863687 |  |  |  |  | 2024-06-13 |  | TOWER
K00849 | K013A_K00849OD_KG_SINGKIR_DARAT | Northern | 4630K | Swap | Decomm->On Hold->Swap->On Hold->Decomm->On Hold->Swap | 2026 | AI | GCI | 4.6 TSSR Approved | ¦ 1002 - CD Zul: Propose to analyze current MR with pre xC MR to compare, finding any coverage lost occuring. | 2024-05-02 | 2024-12-12 |  | 2025-05-13 | 2024-05-02 | Under Approval | 2024-12-30 | 2024-12-30 | CD//Zulakmar | 2024-12-30 | 2211CD-Northern-TSS-BOQ Template(new contract)_GCI//Celcom Digi_RAN-GCI-TSS-Northern-20240512-0106/SQ202504180288 | DU00002863688 |  |  | 2026-01-26 | 2026-01-22 |  | Tower | TOWER | 50 | Add R8862A S9000x3+R8894E M1821 x4+R8862A S2601x2+R8854 S2600Ax1, Dismantle | 0 | 3
K00819 | K008A_K00819OD_KG_BUBUR_LKW | Northern | 4633K | Swap | Decomm->On Hold->Swap | 2025 Q2 | AD | GTSB | 4.6 TSSR Approved |  | 2025-03-25 | 2025-03-26 |  | 2025-03-28 |  | Under Approval | 2025-04-02 | 2025-05-27 | CD//Zulakmar | 2025-04-07 | S1MY2024071003WBF1-2046 | DU00002863689 |  |  | 2025-04-29 | 2025-04-29 |  | Tower | TOWER | 45 | Add R8852E S9000x3+R8894E M1821x3+R8862A S2601x3, Dismantle | 0 | 0
9512B | Nanga Klassen | Sarawak |  | Modernization |  | 2025 Q3 | SM | Magicell | 4.6 TSSR Approved |  | 2023-11-27 | 2023-11-29 |  | 2025-02-18 |  | Rectificating | 2025-03-03 | 2025-05-27 | E//Hannah | 2025-04-07 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231206 | DU00002863690 |  |  | 2025-06-23 | 2025-06-20 |  | Tower | Tower | 77 | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8882 S1800B(B6B)x3 | 0 | 0
B01992 | B064I_B01992OD_LEKASRNR | Central |  | Decomm |  | 2024 Additional | SM | DATASCO | 4.6 TSSR Approved |  | 2024-07-18 |  | 2024-12-05 |  | 2024-12-07 |  | 2024-12-09 | 2025-03-11 | CD//Sapian | 2024-12-12 | SQ202411150407 | DU00002863691 |  |  |  |  | 2025-02-26 |  | MONOPOLE
7737B | Kg Tanaki (REL) | Sabah |  | Modernization |  | 2024 Q3 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2023-10-30 | 2023-11-10 |  | 2024-04-02 |  | Closed | 2024-04-03 | 2024-05-27 | E//Hannah | 2024-05-27 | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231101 | DU00002863692 |  |  | 2024-05-23 | 2024-05-09 |  | Lampole | 30m Monopole | 29 | Add R9224E M1821 x5+R8854 S2600 x2,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R8862A S2600(A4A) x2 | 0 | 13
B02280 | B064D_B02280OD_JLNRESIDENCE_MAHKOTACHRS | Central |  | Decomm |  | 2024 Q4 | SY1 | GCI | 4.6 TSSR Approved |  | 2024-09-18 |  | 2024-09-20 |  | 2024-09-26 |  | 2024-09-30 | 2025-01-14 | CD//Sapian | 2024-10-03 | 0924CD-Central-GCI-BOQ Template(new contract) | DU00002863693 |  |  |  |  | 2024-09-29 |  | POLE
S01341 | S105B_S01341OD_TMNRIMBA | Sabah |  | Decomm |  | 2024 Q3 | MS | GTSB | 4.6 TSSR Approved |  | 2024-03-25 |  |  |  | 2024-03-29 |  | 2024-03-29 | 2024-05-14 | CD//Jahganathan | 2024-04-03 | Celcom Digi_RAN-GTSB-TSS-Sabah-20240329 | DU00002863694 |  |  |  |  | 2024-09-18 |  | MONOPOLE
W01173 | W066AA_W01173OD_JLNYAACOBLATIFCHRS | Central |  | Decomm | Decomm->On Hold->Decomm | 2024 Q3 | AI | GCI | 4.6 TSSR Approved |  | 2025-03-23 |  | 2025-04-07 |  | 2025-04-12 |  | 2025-04-27 | 2025-05-27 | CD//Sapian | 2025-05-08 | SQ202506300546 | DU00002863695 |  |  |  |  | 2025-05-09 |  | LAMP_POLE
S00951 | S094A_S00951OD_KGSALIMANDUT | Sabah |  | Decomm |  | 2024 Q3(single site MOCN) | SH | Seri Pancar | 4.6 TSSR Approved |  | 2024-06-20 |  |  |  | 2024-07-22 |  | 2024-07-23 | 2024-08-29 | CD//Jahganathan | 2024-07-30 | 0624Sabah-Seri Pancar-4BOQ Template (template) | DU00002863696 |  |  |  |  | 2024-09-09 |  | TOWER
Q00129 | Q124E_Q00129OD_BT12KCH | Sarawak |  | Decomm |  | 2024 Q4(single site MOCN)-L21 SSM | ZB | Trintel | 4.6 TSSR Approved |  | 2024-03-08 |  |  |  | 2024-03-08 |  | 2024-03-18 | 2024-09-05 | CD//John | 2024-03-18 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240313 | DU00002863697 |  |  |  |  | 2024-12-22 |  | GUYED MAST
Q01036 | Q124E_Q01036OD_BT13KCH | Sarawak |  | Decomm |  | 2024 Q4(single site MOCN)-L21 SSM | SH | Trintel | 4.6 TSSR Approved |  | 2024-03-01 |  |  |  | 2024-03-06 |  | 2024-03-07 | 2024-04-24 | CD//John | 2024-04-03 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240302/Celcom Digi_RAN-Trintel-Standard PR TSS DECOMM-Sarawak-20240314 | DU00002863698 |  |  |  |  | 2025-01-15 |  | RAPOLE
Q01671 | Q133A_Q01671OD_KGSGALO2 | Sarawak |  | Decomm |  | 2025 Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2024-03-06 |  |  |  | 2024-03-07 |  | 2024-03-07 | 2024-04-24 | CD//John | 2024-03-21 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240313 | DU00002863699 |  |  |  |  | 2025-04-29 |  | RAPOLE
Q00503 | Q139A_Q00503OD_CB_KGRIIH | Sarawak |  | Decomm |  | 2024 Q4(single site MOCN)-L21 SSM | ZB | Trintel | 4.6 TSSR Approved |  | 2024-03-05 |  |  |  | 2024-03-07 |  | 2024-03-18 | 2024-09-05 | CD//John | 2024-03-18 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240313 | DU00002863700 |  |  |  |  | 2024-11-30 |  | TOWER
Q01362 | Q124E_Q01362OD_KGLANDEH | Sarawak |  | Decomm |  | 2025 Q1 | SH | Trintel | 4.6 TSSR Approved |  | 2024-02-26 |  |  |  | 2024-02-26 |  | 2024-02-26 | 2024-09-05 | CD//John | 2024-03-18 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240302/Celcom Digi_RAN-Trintel-Standard PR TSS DECOMM-Sarawak-20240314 | DU00002863701 |  |  |  |  | 2025-08-25 |  | RAPOLE
A01100 | A040D_A01100OD_CB_TMN_IMPIANA_ADRIL_IPH | Northern |  | Decomm |  | 2024 Q2 | ZA | CCSMY | 4.6 TSSR Approved |  | 2024-01-15 |  |  |  | 2024-01-17 |  | 2024-01-18 | 2024-02-23 | CD//Quah | 2024-02-21 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240116-0087 | DU00002863702 |  |  |  |  | 2024-06-04 |  | MINARET
4950C | Kampung Behor Ganchiar | Northern |  | Modernization |  | 2024 Q4 | SM | GCI | 4.6 TSSR Approved |  | 2023-10-12 | 2023-12-06 |  | 2024-04-19 |  | Rectificating | 2024-05-02 | 2024-05-03 | E//Hazida | 2024-05-03 | Celcom Digi_RAN-GCI-TSS-Northern-20231015-0059 | DU00002863703 |  |  | 2024-05-29 | 2024-05-17 |  | Lampole | Tower | 30 | Add R8862A S9000 x3+R9264H M901821 x1+R8862A S2601 x3+A9732 M1821 x3,Dismantle R9224E M1821(AAB) x4 | 123 | 0
4951C | Kampung Bukit Lagi | Northern |  | Modernization |  | 2024 Q4 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-10-18 | 2023-11-21 |  | 2024-05-02 |  | Closed | 2024-05-10 | 2024-05-16 | E//Ajay | 2024-05-16 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231019-0058 | DU00002863704 |  |  | 2024-05-22 | 2024-05-17 |  | In-Building System | Tower | 8 | Add R8862A S9000 x2+R9264H M901821 x2+R8862A S2600 x2+A9732 M1821 x2,Dismantle R8862A S1800(B6A) x4+R8854D S2100(A4A) x4 | 12 | 0
Q01266 | Q135A_Q01266OD_TMNSAMARAX | Sarawak |  | Decomm |  | 2024 Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2024-01-15 |  |  |  | 2024-02-15 |  | 2024-02-16 | 2024-10-11 | CD//John | 2024-02-16 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240116/Celcom Digi_RAN-Trintel-Standard PR TSS DECOMM-Sarawak-20240314 | DU00002863705 |  |  |  |  | 2024-12-28 |  | LAMP_POLE
Q01358 | Q125A_Q01358OD_RPRBANTING | Sarawak |  | Decomm |  | 2024 Q4(single site MOCN)-L21 SSM | SHA | Magicell | 4.6 TSSR Approved |  | 2024-11-06 |  | 2024-11-11 |  | 2024-11-13 |  | 2024-11-14 | 2024-11-22 | CD//John | 2024-11-17 | PR raised as per design team | DU00002863706 |  |  |  |  | 2024-12-20 |  | RAPOLE
W01371 | W066V_W01371OD_VISTAANGKASA _BKTKERINCHI | Central |  | Decomm |  | 2024 Q2 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-01-12 |  |  |  | 2024-02-01 |  | 2024-02-02 |  | CD//Norhaliza | 2024-02-15 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240115 | DU00002863707 |  | Missing FE part |  |  | 2024-08-28 |  | BOOM
A01037 | A036A_A01037OD_KG PAHANG_TPH | Northern |  | Decomm |  | 2024 Q4 | SM | GCI | 4.6 TSSR Approved |  | 2023-12-04 |  |  |  | 2023-12-06 |  | 2023-12-19 | 2024-01-22 | CD//Quah | 2023-12-22 | Celcom Digi_RAN-GCI-TSS-Northern-20231206-0080 | DU00002863708 |  |  |  |  | 2024-11-29 |  | UNIPOLE
B02567 | B061L_B02567OD_PANGSAPURIAMANPCHGPRIMA | Central |  | Decomm |  | 2024 Q3 | MA | GTSB | 4.6 TSSR Approved |  | 2024-01-11 |  |  |  | 2024-02-27 |  | 2024-04-17 | 2024-09-25 | CD//Norhaliza | 2024-08-09 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240115 | DU00002863709 |  |  |  |  | 2024-10-23 |  | WALL MOUNTED BOOM
L00014 | S113A_L00014OD_DURIANTUNJONG | Sabah |  | Decomm |  | 2024 | MS | Datasco | 4.6 TSSR Approved |  | 2024-11-11 |  | 2024-07-20 |  | 2024-11-12 |  | 2024-11-13 | 2024-12-13 | CD//Jahganathan | 2024-11-13 | Celcom Digi_RAN-Datasco-Standard PR TSS-Sabah-20241030 | DU00002863710 |  |  |  |  | 2025-02-27 |  | TOWER
7776B | Kg Pirasan | Sabah |  | Modernization |  | 2024 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2023-10-24 | 2023-10-30 |  | 2023-11-02 |  | Closed | 2024-04-03 | 2024-04-15 | E//Hannah | 2024-04-08 | Celcom Digi_RAN-YPTT-TSS-Sabah-20231028 | DU00002863711 |  |  | 2024-05-20 | 2024-05-08 |  | Tower | 60m 4 Legged Tower | 45 | Add R8862A S9000 x3+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x2 | 13 | 0
7774B | Kg Suang Punggur | Sabah |  | Modernization |  | 2024 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2023-10-22 | 2023-11-20 |  | 2024-03-28 |  | Closed | 2024-03-29 | 2024-04-02 | E//Hannah | 2024-04-02 | Celcom Digi_RAN-YPTT-TSS-Sabah-20231024 | DU00002863712 |  |  | 2024-05-10 | 2024-05-08 |  | Tower | 60m 4 Legged Tower | 45 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
7784B | Kg Kelawat | Sabah |  | Modernization |  | 2024 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2023-10-19 | 2023-10-23 |  | 2023-10-25 |  | Closed | 2024-03-26 | 2024-04-15 | E//Hannah | 2024-04-06 | Celcom Digi_RAN-YPTT-TSS-Sabah-20231020 | DU00002863713 |  |  | 2024-05-14 | 2024-05-08 |  | Tower | 60M 3L Tower | 60 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
7771B | Kuala Abai Upper | Sabah |  | Modernization |  | 2024 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2023-10-22 | 2023-10-24 |  | 2023-10-27 |  | Closed | 2024-03-29 | 2024-04-03 | E//Hannah | 2024-04-03 | Celcom Digi_RAN-YPTT-TSS-Sabah-20231024 | DU00002863714 |  |  | 2024-05-31 | 2024-05-10 |  | Tower | 60m 4 Legged Tower | 60 | Add R8862A S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R8862A S2601(A6A) x1 | 0 | 1
9592C | TM Lingga | Sarawak |  | Modernization |  | 2025 Q3 | AI | Trintel | 4.6 TSSR Approved |  | 2023-11-13 | 2023-11-16 |  | 2025-02-19 |  | Closed | 2025-02-21 | 2025-02-27 | E//Hannah | 2025-02-27 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231119 | DU00002863715 | Remarks: Solution TSSR/BOM Changed |  | 2025-07-06 | 2025-04-09 |  | Tower | Tower | 45m | Add R8894E M1821x2+R8862A S2601x1+R8854 S2600x2 | 0 | 23
7767B | Kg.Kinasaraban | Sabah |  | Modernization |  | 2024 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2023-10-24 | 2023-10-25 |  | 2023-10-27 |  | Closed | 2024-04-03 | 2024-04-15 | E//Zulakmar | 2024-04-08 | Celcom Digi_RAN-YPTT-TSS-Sabah-20231024 | DU00002863716 |  |  | 2024-05-20 | 2024-05-10 |  | Monopole | 30m Lampole | 30 | Add R8862A S9000 x3+R9224E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
B02176 | B064E_B02176OD_OSTIA_KAJANG | Central |  | Decomm | Decomm->On Hold | 2024 Q4(single site MOCN)-L26 SSM | SH | GTSB | 4.6 TSSR Approved |  | 2024-01-24 |  |  |  | 2024-02-05 |  | 2024-05-24 | 2024-09-25 | CD//Ali akaram | 2024-09-24 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240128 | DU00002863717 |  |  |  |  | 2025-01-04 |  | MINIMAST
B00757 | B064G_B00757OD_UKM | Central |  | Decomm |  | 2024 Additional | AD | GTSB | 4.6 TSSR Approved |  | 2024-09-21 |  | 2024-09-25 |  | 2024-09-30 |  | 2024-11-20 | 2024-12-21 | CD//Sapian | 2024-12-02 | 0925CD-Central-GTSB-BOQ Template(new contract) | DU00002863718 |  |  |  |  | 2025-04-23 |  | BOOM
W01537 | W066Z_W01537OD_TMNKOBENA2 | Central |  | Decomm |  | 2024 Q3 | SS | YPTT | 4.6 TSSR Approved |  | 2024-08-22 |  | 2024-08-19 |  | 2024-08-22 |  | 2024-08-22 |  | CD//Ali akaram | 2024-09-10 | 0809CD-Central-YPTT-BOQ Template(new contract) | DU00002863719 |  |  |  |  | 2024-08-25 |  | LAMP_POLE
7773B | Komplex Sukan Kb | Sabah |  | Modernization |  | 2024 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2023-10-27 | 2023-10-30 |  | 2023-11-03 |  | Closed | 2024-03-29 | 2024-04-03 | E//Hannah | 2024-04-03 | Celcom Digi_RAN-YPTT-TSS-Sabah-20231028 | DU00002863720 |  |  | 2024-05-14 | 2024-05-08 |  | Tower | Tower | 45 | Add R8862A S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R8862A S2600(A4A) x1 | 0 | 1
7775B | Kg. Siasai Kb | Sabah |  | Modernization |  | 2024 Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2023-10-24 | 2023-11-01 |  | 2024-04-03 |  | Closed | 2024-04-04 | 2024-04-19 | E//Hannah | 2024-04-19 | Celcom Digi_RAN-YPTT-TSS-Sabah-20231024 | DU00002863721 |  |  | 2024-05-10 | 2024-05-08 |  | Lampole | 30m Lampole | 30 | Add R8862A S9000 x3+R9224E M1821 x1+R8854 S2600 x1,Dismantle R8862A S2600(A4A) x1 | 0 | 1
7751B | Kg. Mampisas | Sabah |  | Modernization |  | 2025 Q2 | AD | Futong | 4.6 TSSR Approved |  | 2023-10-31 | 2023-11-03 |  | 2025-01-14 |  | Under Approval | 2025-01-17 | 2025-02-18 | E//Yanie | 2025-01-20 | Celcom Digi_RAN-Futong-TSS-Sabah-20231101 | DU00002863722 |  |  | 2025-07-06 | 2025-05-13 |  | Tower | Tower | 76 | Reuse Existing RRU | 0 | 0
B02301 | W067A_B02301OD_MENARAZ10PRESINT1WPPJ | Central |  | Decomm |  | 2024 Q3 | MA | Magicell | 4.6 TSSR Approved |  | 2024-01-12 |  |  |  | 2024-01-16 |  | 2024-05-06 | 2024-05-27 | CD//Ali Akaram | 2024-05-20 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240115 | DU00002863723 |  |  |  |  | 2024-12-27 |  | BOOM
7048B | Taman Doggonggon | Sabah |  | Modernization |  | 2024 Q3 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2023-10-23 | 2023-11-02 |  | 2023-11-17 |  | Closed | 2024-03-26 | 2024-04-15 | E//Hannah | 2024-04-06 | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231024 | DU00002863724 |  |  | 2024-04-30 | 2024-04-25 |  | Wall mount boom | Tower | 6m | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
B02334 | W067A_B02334OD_AYER8PRESINT8 | Central | 1853K | Swap | Decomm->Swap | 2024 Q3 | CR | Magicell | 4.6 TSSR Approved |  | 2024-06-21 | 2024-06-28 |  | 2024-07-02 | 2024-02-06 | Under Approval | 2024-07-04 | 2024-07-10 | CD//Sapian | 2024-07-10 | 0704CD-Central-Magicell-BOQ Template (template) | DU00002863725 |  |  | 2025-02-23 | 2024-08-01 |  | In-Building System | BOOM | 3 | Add R9264M M1821 x2+R9264H M901821 x4+R8862A S2601 x2+R8854 S2600 x2,Dismantle | 0 | 14
B00204 | W066Y_B00204OD_TMNSAGA | Central |  | Decomm |  | 2024 Q4 | SHA | GTSB | 4.6 TSSR Approved |  | 2024-03-13 |  | 2024-07-06 |  | 2024-08-05 |  | 2024-08-08 | 2024-09-25 | CD//Ali Akaram | 2024-08-15 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240316 | DU00002863726 |  |  |  |  | 2024-08-27 |  | MINI STRUCTURE
7435A | Kg Timbou Tambunan | Sabah |  | Modernization |  | 2025 Q2 | SM | Futong | 4.6 TSSR Approved |  | 2023-10-26 | 2023-10-30 |  | 2023-11-02 |  | Rectificating | 2025-01-14 | 2025-01-21 | E//Hannah | 2025-01-21 | Celcom Digi_RAN-Futong-TSS-Sabah-20231028 | DU00002863727 |  |  | 2025-02-24 | 2025-02-18 |  | Tower | 60m 3 legged tower | 65 | Add R8852E S9000x4+R8894E M1821x5+R8854 S2600x1, Dismantle R8862A S1800(B6A)x4+R8862A S2100(A6A)x4+R8862A S2601(A6A)x1 | 0 | 1
A00004 | A045A_A00004OD_TMPENGKALANHULU | Northern | 4634K | Swap | Decomm->On Hold->Swap | 2024 Q3(single site MOCN) | HW | GTSB | 4.6 TSSR Approved |  | 2025-04-14 | 2025-04-21 |  | 2025-04-23 |  | Under Approval | 2025-04-24 | 2025-04-26 | CD//Zulakmar | 2025-04-25 | SQ202412190138 - GTSB | DU00002863728 |  |  | 2025-07-20 | 2025-07-05 |  | Tower | BOOM | 62m | Add R8852E S9000x3+A9732 M1821x1+R8894E M1821x3, Dismantle | 1 | 2
B02207 | B064C_B02207OD_JLNPP42BDRPUTRAPERMAI | Central | 1877K | Swap | Decomm->On hold->Swap | 2024 Q3 | SHA | GCI | 4.6 TSSR Approved |  | 2024-03-27 | 2024-08-06 |  | 2024-11-28 | 2024-04-22 | Under Approval | 2024-08-12 | 2025-03-06 | CD//Norhaliza | 2025-03-03 | 0813CD-Central-GCI-BOQ Template(new contract) | DU00002863729 |  |  | 2025-02-24 | 2025-02-21 |  | Monopole | POLE | 30 | Add R8862A S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle | 0 | 3
B02408 | W067A_B02408OD_SYIMPHONY_HILL_CBJ | Central |  | Decomm |  | 2024 Q3 | SHA | Magicell | 4.6 TSSR Approved |  | 2024-05-03 |  | 2024-07-04 |  | 2024-07-12 |  | 2024-07-12 | 2026-01-21 | CD//Sapian | 2024-07-24 | CelcomDigi_RAN_Magicell_TSS_Central_20240424 | DU00002863730 |  |  |  |  | 2024-11-22 |  | POLE
2942B | Kelana Park View | Central |  | Modernization |  | 2024 Q1 | CR | GCI | 4.6 TSSR Approved |  | 2023-11-16 | 2023-11-22 |  | 2024-01-02 |  | Closed | 2024-01-03 | 2024-01-04 | E//Kok Keen | 2024-01-03 | Celcom Digi_RAN-GCI-TSS-Central-20231119 | DU00002863731 |  |  | 2024-04-04 | 2024-04-02 |  | In-Building System | In-building system | 6 | Add R9264H M901821 x3,Dismantle R8840-U216 x1+R8894E M1821(A8A) x3
9188A | Pusa (Celcom) | Sarawak |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | SHA | Datasco | 4.6 TSSR Approved |  | 2023-11-01 | 2023-12-06 |  | 2024-10-25 |  | Under Approval | 2024-10-28 | 2024-12-16 | E//Syahriani | 2024-11-19 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231107 | DU00002863732 |  |  | 2024-11-28 | 2024-11-24 |  | Tower | 45m 3 Legged Tower | 75 | Add R8894E M1821x2 | 0 | 13
W00431 | W066W_W00431OD_INTERMARK | Central |  | Decomm | Decomm->On Hold->Decomm | 2024 Q1 | AD | Ascentrack | 4.6 TSSR Approved | 0207 - TSSR Rejected due to Quality issue | 2024-01-12 |  |  |  | 2024-01-31 |  | 2024-02-16 | 2025-10-17 | CD//Sapian | 2025-05-15 | BoQ CelcomDigi_RAN_Ascentrack_Standard PR TSS_Central_20240115 | DU00002863733 |  |  |  |  | 2025-05-05 |  | RT - 3m Wall Mount Pole
9633B | Taman Mayfair | Sarawak |  | Modernization |  | 2025 Q3 | SM | Magicell | 4.6 TSSR Approved |  | 2024-01-02 | 2023-12-04 |  | 2025-02-19 |  | Rectificating | 2025-03-03 | 2025-03-10 | E//Hannah | 2025-03-07 | Celcom Digi_RAN-Magicell-Standard PR TSS-Sarawak-20240109 | DU00002863734 | Remarks: Solution TSSR/BOM Changed |  | 2025-03-22 | 2025-03-19 |  | Monopole | 30m Rapole | 32M | Add R9264M M1821x3, Dismantle R8894E M1821(A8A)x3 | 0 | 0
B00812 | B064F_B00812OD_TMNSEMARAKKJG | Central |  | Decomm |  | 2024 Q4 | SHA | Magicell | 4.6 TSSR Approved |  | 2023-11-02 |  | 2024-08-05 |  | 2024-08-13 |  | 2024-08-13 | 2024-10-29 | CD//Norhaliza | 2024-10-04 | CelcomDigi_RAN_Magicell_TSS_Central_20231113 | DU00002863735 |  |  |  |  | 2024-10-10 |  | MINI STRUCTURE
W00813 | W066H_W00813OD_DESAPUTRAWMJ | Central |  | Decomm |  | 2024 Q1 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-29 |  |  |  | 2023-12-08 |  | 2023-12-12 |  | CD//Sapian | 2023-12-21 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231201 | DU00002863736 |  | 1) Pls provide cabinet/rack digi photo (DISMANTLE DIGI MICROWAVE LINK 3230C-2945A) 2) Missing FE part |  |  | 2024-04-30 |  | LAMP_POLE
W01409 | W066F_W01409OD_JLNWANKADIR_TTDI | Central |  | Decomm |  | 2024 Q3 | CR | GCI | 4.6 TSSR Approved |  | 2023-11-22 |  |  |  | 2023-12-01 |  | 2023-12-06 |  | CD//Sapian | 2023-12-13 | CelcomDigi_RAN_GCI_TSS_Central_20231126 | DU00002863737 |  | Missing FE part |  |  | 2024-07-01 |  | LAMP_POLE
B01047 | B061J_B01047OD_BK6BDRKINRARA | Central |  | Decomm |  | 2024 Q3 | CR | GCI | 4.6 TSSR Approved |  | 2023-11-10 |  |  |  | 2024-03-12 |  | 2024-04-23 | 2024-08-20 | CD//Norhaliza | 2024-08-09 | CelcomDigi_RAN_GCI_TSS_Central_20231113 | DU00002863738 |  |  |  |  | 2025-01-23 |  | MONOPOLE
1208C | Damai | Central |  | Modernization |  | 2024 Q1 | MA | CCSMY | 4.6 TSSR Approved |  | 2024-06-14 | 2024-06-25 |  | 2024-06-27 |  | Closed | 2024-08-01 | 2024-08-09 | E//Sumitra | 2024-08-06 | 0618Central-CCSMY-BOQ Template (template) | DU00002863739 |  |  | 2024-08-17 | 2024-07-29 |  | Wall mount boom | 3m Boom (RT) |  | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
1209C | Dato Keramat | Central |  | Modernization |  | 2024 Q1 | MA | CCSMY | 4.6 TSSR Approved |  | 2024-01-25 | 2024-03-21 |  | 2024-03-26 |  | Closed | 2024-03-26 | 2024-04-04 | E//Sumitra | 2024-04-04 | BOQ CelcomDigi_RAN_CCSMY_Standard PR TSS_Central_20240128 | DU00002863740 |  |  | 2024-09-25 | 2024-09-25 |  | Wall mount boom | 3m Boom (RT) |  | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
Q01646 | Q132C_Q01646OD_KGBKTBERANGAN2 | Sarawak |  | Decomm |  | 2024 Q2 | SH | Magicell | 4.6 TSSR Approved |  | 2023-11-24 |  |  |  | 2023-11-29 |  | 2023-11-29 | 2024-02-15 | CD//John | 2023-11-30 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231126 | DU00002863741 |  |  |  |  | 2024-12-28 |  | TOWER
Q00930 | Q135A_Q00930OD_TMNBESTARI | Sarawak |  | Decomm |  | 2024 Q2 | ZB | YPTT | 4.6 TSSR Approved |  | 2023-12-19 |  |  |  | 2024-01-08 |  | 2024-01-22 | 2024-08-29 | CD//John | 2024-02-28 | Celcom Digi_RAN-YPTT-Standard PR TSS-Sarawak-20240109 | DU00002863742 |  |  |  |  | 2024-11-28 |  | MONOPOLE
9637B | Jalan Brayun | Sarawak |  | Modernization |  | 2025 Q3 | AD | Magicell | 4.6 TSSR Approved |  | 2024-01-02 | 2023-12-07 |  | 2025-02-20 |  | Under Approval | 2025-02-21 | 2025-03-09 | E//Hannah | 2025-02-27 | Celcom Digi_RAN-Magicell-Standard PR TSS-Sarawak-20240109 | DU00002863743 |  |  | 2025-03-24 | 2025-03-24 |  | Pole | 30m Rapole | 31 | Add R9264M M1821x3, Dismantle R8894E M1821(A8A)x3 | 0 | 0
A00845 | A041A_A00845OD_KGBUAYAKK | Northern |  | Decomm |  | 2024 Q4 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-11-23 |  |  |  | 2023-12-13 |  | 2023-12-15 | 2024-01-22 | CD//Quah | 2023-12-22 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231127-0073 | DU00002863744 |  |  |  |  | 2024-09-25 |  | TOWER
7963B | Delta Height Bundusan | Sabah |  | Modernization |  | 2024 Q3 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2023-10-24 | 2023-10-25 |  | 2023-10-31 |  | Closed | 2024-04-02 | 2024-04-15 | E//Hannah | 2024-04-08 | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231028 | DU00002863745 |  |  | 2024-04-30 | 2024-04-27 |  | Tower | 30m Lampole | 30m | Add R8862A S9000 x3+A9732 M1821 x3,Dismantle R8854 S2600(A4A) x3+R8894E M1821(A8A) x3+R9224E M1821(AAB) x3 | 123 | 0
9566C | Baladdin (REL) | Sarawak |  | Modernization |  | 2024 Q4(single site MOCN)-L2126 SSM | SHA | Magicell | 4.6 TSSR Approved |  | 2024-06-19 | 2024-07-24 |  | 2024-10-28 |  | Under Approval | 2024-10-30 | 2024-12-17 | E//Syahriani | 2024-12-17 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20240123 | DU00002863746 |  |  | 2024-11-08 | 2024-11-06 |  | Tower | 30m Rapole | 45 | Add A9732 M1821x3, Dismantle R8854 S2600(A4A)x2+R8894E M1821(A8A)x4+R9224E M1821(AAB)x1 | 123 | 0
B00493 | W066Y_B00493OD_PANDANINDAH | Central |  | Decomm |  | 2024 Q3 | SM | CCSMY | 4.6 TSSR Approved |  | 2023-12-11 |  |  |  | 2023-12-20 |  | 2024-03-29 | 2024-07-12 | CD//Norhaliza | 2024-06-04 | CelcomDigi_RAN_CCSMY_TSS_Central_20231214 | DU00002863747 |  |  |  |  | 2024-08-05 |  | MINI STRUCTURE
B02726 | W066X_B02726OD_KEMBOJAAPRT_BBAMPANG | Central |  | Decomm |  | 2024 Q2 | SS | YPTT | 4.6 TSSR Approved |  | 2023-12-08 |  |  |  | 2023-12-14 |  | 2024-01-11 |  | CD//Norhaliza | 2024-01-30 | CelcomDigi_RAN_YPTT_TSS_Central_20231224 | DU00002863748 |  | Missing FE part |  |  | 2024-07-17 |  | BOOM
S01596 | S105B_S01596OD_ANGGERIKAPARTMENT | Sabah |  | Decomm |  | 2025 Q2 | MS | Futong | 4.6 TSSR Approved |  | 2024-04-30 |  |  |  | 2024-05-06 |  | 2024-05-08 | 2024-06-21 | CD//Jahganathan | 2024-06-19 | Celcom Digi_RAN-Futong-Standard PR TSS-Sabah-20240510 / SQ202501020444 - Futong / SQ202501070242 - Futong | DU00002863749 |  |  |  |  | 2024-07-17 |  | TOWER
S01498 | S105B_S01498OD_JLNAIRPORTPERIMETER | Sabah |  | Decomm |  | 2024 Q3 | MS | GTSB | 4.6 TSSR Approved |  | 2024-03-25 |  |  |  | 2024-03-29 |  | 2024-03-29 | 2025-10-28 | CD//Jahganathan | 2024-04-03 | Celcom Digi_RAN-GTSB-TSS-Sabah-20240329 | DU00002863750 |  |  |  |  | 2024-08-19 |  | LAMP_POLE
Q01767 | Q137A_Q01767OD_KGSEBERANGBARU | Sarawak |  | Decomm |  | 2025 Q2 | AD | Trintel | 4.6 TSSR Approved |  | 2025-03-18 |  |  |  | 2025-05-06 |  | 2025-05-30 |  | CD//John | 2025-12-03 | SQ202503030411-Trintel | DU00002863751 |  | not enough info at NE and Missing Dwg at FE |  |  | 2025-09-22 |  | RAPOLE
Q01909 | Q124E_Q01909OD_JPJBT12 | Sarawak |  | Decomm |  | 2024 Q4(single site MOCN)-L21 SSM | SH | Trintel | 4.6 TSSR Approved |  | 2024-03-01 |  |  |  | 2024-03-01 |  | 2024-03-01 | 2024-04-24 | CD//John | 2024-04-03 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240302/Celcom Digi_RAN-Trintel-Standard PR TSS DECOMM-Sarawak-20240314 | DU00002863752 |  |  |  |  | 2024-11-29 |  | RAPOLE
Q01351 | Q135A_Q01351OD_KEMMUARATUANG | Sarawak |  | Decomm |  | 2024 Q2 | SH | Magicell | 4.6 TSSR Approved |  | 2023-11-20 |  |  |  | 2023-11-23 |  | 2023-11-24 | 2023-12-16 | CD//John | 2023-11-28 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231126/Celcom Digi_RAN-Magicell-Standard PR TSS DECOMM-Sarawak-20231229/CelcomDigi_RAN_Magicell_TSS_Sarawak_20241018 | DU00002863753 |  |  |  |  | 2025-04-28 |  | RAPOLE
Q01853 | Q141A_Q01853OD_CB_KGSEMERALAUT | Sarawak |  | Decomm |  | 2024 Q2 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-11-06 |  |  |  | 2023-11-09 |  | 2023-11-13 | 2023-11-18 | CD//John | 2023-11-13 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231107/Celcom Digi_RAN-Magicell-Standard PR TSS DECOMM-Sarawak-20231229/CelcomDigi_RAN_Magicell_TSS_Sarawak_20241018 | DU00002863754 |  |  |  |  | 2024-06-29 |  | RAPOLE
K00894 | K002A_K00894OD_TMN_DESABIDARA_KKETIL | Northern |  | Decomm |  | 2024 Q3(single site MOCN) | SHA | GCI | 4.6 TSSR Approved |  | 2023-12-22 |  |  |  | 2024-01-08 |  | 2024-06-27 | 2024-10-01 | CD//Zulakmar | 2024-07-02 | Celcom Digi_RAN-GCI-TSS-Northern-20231225-0085/Celcom Digi_RAN-GCI-TSS-Northern-20240130-0092 | DU00002863755 |  |  |  |  | 2024-08-14 | Lampole | LAMP_POLE | 30
1577C | LRT Gombak | Central |  | Modernization |  | 2024 Q1 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-28 | 2023-12-01 |  | 2024-01-05 |  | Closed | 2024-01-05 | 2024-08-13 | E//Kok Keen | 2024-08-13 | CelcomDigi_RAN_GTSB_TSS_Central_20231201 | DU00002863756 |  |  | 2024-04-02 | 2024-03-25 |  | Minimast | 3m RT boom | 9m | Add R8862A S9000 x3+R8894E M1821 x1,Dismantle |  | 1
A01086 | A040D_A01086OD_KGRAPATJAYATAMBAHAN | Northern |  | Decomm |  | 2024 Q2 | ZA | GCI | 4.6 TSSR Approved |  | 2023-10-16 |  |  |  | 2023-10-25 |  | 2023-10-27 | 2024-04-23 | CD//Quah | 2023-11-21 | Celcom Digi_RAN-GCI-TSS-Northern-20231019-0062/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240529-0109 | DU00002863757 |  | Missing antenna photo, FE info and Photo |  |  | 2024-03-29 |  | MINARET
R00010 | R001B_R00010OD_KPERLISTOWN | Northern |  | Decomm |  | 2024 Q4 | BY | GTSB | 4.6 TSSR Approved |  | 2024-02-08 |  |  |  | 2024-02-09 |  | 2024-04-23 | 2024-05-24 | CD//Quah | 2024-05-21 | Celcom Digi_RAN-GTSB-TSS-Northern-20240223-0093/0612Northern-GTSB-BOQ Template (template) | DU00002863758 |  |  |  |  | 2024-07-02 |  | BOOM
K00467 | K009A_K00467OD_KOLEJMARAKUALANERANG | Northern |  | Decomm |  | 2025 Q3 | HW | GCI | 4.6 TSSR Approved |  | 2025-04-15 |  | 2025-04-23 |  | 2025-04-30 |  | 2025-05-02 | 2026-02-16 | CD//Zulakmar | 2025-05-08 | SQ202501060244 - GCI | DU00002863759 |  |  |  |  | 2025-10-21 |  | MONOPOLE
K00700 | K012A_K00700OD_BBBERISJAYA | Northern | 4619K | Swap | Decomm->On hold->Swap | 2024 Q3(single site MOCN) | SM | GCI | 4.6 TSSR Approved |  | 2024-10-13 | 2024-10-24 |  | 2024-10-30 |  | Under Approval | 2024-11-21 | 2024-11-26 | CD//Zulakmar | 2024-11-26 | 0925CD-Northern-GCI-BOQ Template(new contract) | DU00002863760 |  |  | 2024-11-14 | 2024-11-08 |  | Lampole | LAMP_POLE | 30 | Add R9264H M901821 x3,Dismantle | 0 | 0
S00199 | S089A_S00199OD_CB_TMMILE36 | Sabah |  | Decomm |  | 2024 Q4(single site MOCN)-L26 SSM | MS | Seri Pancar | 4.6 TSSR Approved |  | 2024-08-21 |  | 2024-09-02 |  | 2024-09-05 |  | 2024-09-05 | 2024-11-15 | CD//Jahganathan | 2024-09-05 | 0809CD-Sabah-Seri Pancar-BOQ Template(new contract) | DU00002863761 |  |  |  |  | 2025-10-31 |  | TOWER
4303D | UNIMAP Perlis Dewan Kuliah (REL) | Northern |  | Modernization |  | 154 single site MOCN | SH | YPTT | 4.6 TSSR Approved |  | 2023-12-15 | 2023-12-21 |  | 2024-08-19 |  | Under Approval | 2024-08-29 | 2024-08-30 | E//Hazida | 2024-08-30 | Celcom Digi_RAN-YPTT-TSS-Northern-20231225-0047 | DU00002863762 |  |  | 2024-09-04 | 2024-08-24 |  | Lampole | 24m Lampole | 30 | Add R8852E S9000 x3+R8862A S2601 x2+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x2 | 12
4467D | Surau Taman Jitra | Northern |  | Modernization |  | 2024 Q3 | BY | CCSMY | 4.6 TSSR Approved | ¦ 0319 - Previous TSSR subcon submitted, have solution changes | 2023-10-11 | 2023-10-16 |  | 2023-10-23 |  | Closed | 2024-03-29 | 2024-04-04 | E//Hazida | 2024-04-04 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231012-0053 | DU00002863763 |  |  | 2024-04-16 | 2024-04-16 |  | Lampole | 30M Pole | 45m | Add R8852E S9000 x3+A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123 | 0
9833B | Kpg Lebaan | Sarawak |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q2 | AI | AllStar | 4.6 TSSR Approved |  | 2023-12-06 | 2023-12-18 |  | 2025-02-06 |  | Closed | 2025-02-07 | 2025-02-27 | E//Hannah | 2025-02-12 |  | DU00002863764 | [5 empty] | Tower | In-Building System | 76 | Reuse Existing RRU | 0 | 0
Q01680 | Q128A_Q01680OD_CB_PKNLUNDU | Sarawak |  | Decomm |  | 2024 Q2 | ZB | Trintel | 4.6 TSSR Approved |  | 2024-03-14 |  |  |  | 2024-05-08 |  | 2024-03-25 | 2024-05-24 | CD//John | 2024-03-26 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20240324 | DU00002863765 |  |  |  |  | 2024-06-10 |  | RAPOLE
Q00497 | Q133A_Q00497OD_KGTEGAK | Sarawak |  | Decomm |  | 2024 | SH | Trintel | 4.6 TSSR Approved |  | 2024-03-14 |  |  |  | 2024-03-15 |  | 2024-03-18 | 2024-04-24 | CD//John | 2024-03-18 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20240324 | DU00002863766 |  |  |  |  | 2025-01-11 |  | TOWER
Q01407 | Q135A_Q01407OD_KGSGMATA | Sarawak |  | Decomm |  | 2024 Q2 | SH | YPTT | 4.6 TSSR Approved | TSSR REJECT | 2023-12-18 |  |  |  | 2024-01-08 |  | 2024-02-01 | 2024-03-05 | CD//John | 2024-02-02 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20231221 | DU00002863767 |  |  |  |  | 2025-05-12 |  | N-MINARATE
Q01008 | Q139A_Q01008OD_CB_LEBUR | Sarawak |  | Decomm |  | 2025 Q3 | SH | Trintel | 4.6 TSSR Approved |  | 2023-10-17 |  |  |  | 2023-10-19 |  | 2023-10-19 | 2024-09-05 | CD//John | 2023-10-21 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231017 | DU00002863768 |  |  |  |  | 2025-11-17 |  | TOWER
Q01011 | Q139A_Q01011OD_CB_KGENSEBANG | Sarawak |  | Decomm |  | 2025 Q3 | ZB | Trintel | 4.6 TSSR Approved |  | 2024-03-01 |  |  |  | 2024-03-05 |  | 2024-03-07 | 2024-03-21 | CD//John | 2024-03-07 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240302/Celcom Digi_RAN-Trintel-Standard PR TSS DECOMM-Sarawak-20240314 | DU00002863769 |  |  |  |  | 2025-06-09 |  | TOWER
Q01854 | Q133A_Q01854OD_CB_UITMMUKAH | Sarawak |  | Decomm |  | 2025 Q2 | ZB | Trintel | 4.6 TSSR Approved |  | 2024-03-20 |  |  |  | 2024-03-21 |  | 2024-03-22 | 2024-04-24 | CD//John | 2024-03-22 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20240324 | DU00002863770 |  |  |  |  | 2025-06-25 |  | TOWER
Q01735 | Q132A_Q01735OD_CB_KGMJDTIRIS | Sarawak |  | Decomm |  | 2025 Q2 | SH | Magicell | 4.6 TSSR Approved |  | 2024-05-15 |  |  |  | 2024-05-24 |  | 2024-06-21 | 2025-05-02 | CD//John | 2025-02-22 | S1MY2021071016WBF1-1354 & S1MY2021071016WBF1-1355-Magicell | DU00002863771 |  |  |  |  | 2025-08-09 |  | RAPOLE
Q01108 | Q115A_Q01108OD_CB_TMNMUTIARA1 | Sarawak |  | Decomm |  | 2024 Q2 | ZB | Trintel | 4.6 TSSR Approved |  | 2024-01-29 |  |  |  | 2024-02-21 |  | 2024-02-21 | 2024-03-21 | CD//John | 2024-02-22 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20240124/Celcom Digi_RAN-Trintel-Standard PR TSS DECOMM-Sarawak-20240314 | DU00002863772 |  |  |  |  | 2024-07-31 |  | POLE
B02818 | W066X_B02818OD_SURAU_Al_IMAN_AMPANG | Central |  | Decomm |  | 2024 Q4 | SH | GTSB | 4.6 TSSR Approved |  | 2024-02-07 |  |  |  | 2024-03-05 |  | 2024-05-24 | 2024-07-12 | CD//Sapian | 2024-06-11 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240212 | DU00002863773 |  |  |  |  | 2024-08-22 |  | LAMP_POLE
K00845 | K005D_K00845OD_DESA_AMAN_G_CHEMPEDAK | Northern | 4620K | Swap | Decomm->On Hold->Swap | 2024 Q3(single site MOCN) | SHA | GTSB | 4.6 TSSR Approved |  | 2024-01-26 | 2024-09-24 |  | 2024-10-02 | 2024-01-27 | Under Approval | 2024-10-03 | 2024-10-10 | CD//Zulakmar | 2024-10-09 | Celcom Digi_RAN-GTSB-TSS-Northern-20240124-0089/0823CD-Northern-GTSB-BOQ Template(new contract) | DU00002863774 |  |  | 2024-11-07 | 2024-11-02 |  | Tower | TOWER | 45M | Add R8862A S9000 x4+R8862A S2601 x2+A9732 M1821 x2+R8894E M1821x2,Dismantle | 14 | 0
W00924 | B057D_W00924OD_MRR2KARAKITC | Central |  | Decomm |  | 2024 Q1 | SH | GTSB | 4.6 TSSR Approved |  | 2024-02-29 |  |  |  | 2024-04-24 |  | 2024-04-30 | 2024-10-28 | CD//Norhaliza | 2024-10-04 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240303 | DU00002863775 |  |  |  |  | 2024-04-04 |  | LAMP_POLE
B00450 | W066W_B00450OD_PANDANJAYA2 | Central |  | Decomm |  | 2024 Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2024-03-14 |  |  |  | 2024-04-29 |  | 2024-05-14 | 2025-03-17 | CD//Norhaliza | 2024-07-05 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240316 | DU00002863776 |  |  |  |  | 2024-08-15 |  | MINI STRUCTURE
A01072 | A037A_A01072OD_TMNDESABAKTI_TI | Northern |  | Decomm |  | 2024 Q4 | SHA | GTSB | 4.6 TSSR Approved |  | 2024-10-30 |  |  |  | 2024-10-30 |  | 2024-11-15 | 2025-07-25 | CD//Zulakmar | 2024-11-18 | Celcom Digi_RAN-GTSB-TSS-Northern-20241017_New Contract | DU00002863777 |  |  |  |  | 2024-10-23 |  | MINARET
B02375 | W066Y_B02375OD_LRT_CAHAYA | Central |  | Decomm |  | 2024 Q2 | SS | YPTT | 4.6 TSSR Approved |  | 2024-02-13 |  |  |  | 2024-02-13 |  | 2024-02-14 | 2024-09-25 | CD//Norhaliza | 2024-08-19 | BOQ_Celcom Digi_RAN-YPTT-Standard PR TSS-20240218 | DU00002863778 |  |  |  |  | 2024-08-12 |  | MONOPOLE
W00700 | W066AA_W00700OD_CMX6 | Central |  | Decomm |  | 2024 Q3 | ZA | AllStar | 4.6 TSSR Approved |  | 2024-01-16 |  |  |  | 2024-02-08 |  | 2024-04-01 | 2025-07-01 | CD//Sapian | 2024-04-30 | CelcomDigi_RAN_Allstar_TSS_Central_20240124 | DU00002863779 |  |  |  |  | 2024-08-08 |  | BOOM
S00269 | S107A_S00269OD_SIPITANGSFI | Sabah |  | Decomm | Decomm->On hold->Swap->On hold->Decomm | 2024 Q3(single site MOCN) | MS | Seri Pancar | 4.6 TSSR Approved | Unpair xC & xD | 2024-06-10 |  |  |  | 2024-06-21 |  | 2024-06-24 | 2025-07-04 | CD//Sharidah | 2025-05-16 | 0610Sabah-Seri Pancar-BOQ Template (template) | DU00002863780 |  |  |  |  | 2025-03-04 |  | GUYED MAST
A00068 | SGSIPUT | Northern |  | Decomm |  | 2024 Q4 | SM | GTSB | 4.6 TSSR Approved |  | 2023-12-21 |  |  |  | 2023-12-27 |  | 2023-12-29 |  | CD//Quah | 2024-02-07 | Celcom Digi_RAN-GTSB-TSS-Northern-20231225-0080 | DU00002863781 |  |  |  |  | 2024-09-30 |  | TOWER
W00088 | W066AA_W00088OD_TMTUNRAZAK | Central |  | Decomm | Decomm->On Hold->Site Out->Decomm | 2024 Q3 | MNO | GCI | 4.6 TSSR Approved |  | 2024-07-29 |  | 2024-08-11 |  | 2025-06-19 |  | 2025-07-07 | 2025-07-14 | CD//Sapian | 2025-07-08 | SQ202504210116 | DU00002863782 |  |  |  |  | 2025-10-27 | In-Building System | BOOM | 5m
4542D | Tmn Rasi (REL) | Northern |  | Modernization |  | 2024 Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2023-10-10 | 2023-10-12 |  | 2024-01-10 |  | Rectificating | 2024-01-11 | 2024-01-22 | E//Hazida | 2024-01-21 | Celcom Digi_RAN-GTSB-TSS-Northern-20231011-0046 | DU00002863783 |  |  | 2024-02-21 | 2024-02-19 |  |  | 45M Tower | 45 | Add R8862A S9000 x4+R8894E M1821 x1,Dismantle |  | 3
4612D | Felda Chuping | Northern |  | Modernization |  | 2025 Q3 | AD | CCSMY | 4.6 TSSR Approved |  | 2023-11-02 | 2023-11-08 |  | 2025-02-21 |  | Under Approval | 2025-03-11 | 2025-05-27 | E//Hazida | 2025-03-16 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231103-0067 | DU00002863784 |  |  | 2025-05-19 | 2025-05-15 |  | Tower | 60M 3 Legged Tower | 61M | Add R8852E S9000x3 | 0 | 0
W01228 | W066T_W01228OD_JALAN_GEMBIRA | Central |  | Decomm |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-12-09 |  |  |  | 2023-12-13 |  | 2023-12-21 | 2024-09-25 | CD//Sapian | 2024-07-25 | CelcomDigi_RAN_Datasco_TSS_Central_20231213 | DU00002863785 |  |  |  |  | 2024-05-24 |  | POLE
W01174 | W066H_W01174OD_WTHOWTHORDNWMJ | Central |  | Decomm |  | 2024 Q1 | SHA | GTSB | 4.6 TSSR Approved |  | 2024-06-25 |  | 2024-07-03 |  | 2024-07-09 |  | 2024-07-12 | 2024-09-25 | CD//Norhaliza | 2024-08-07 | 0628Central-GTSB-BOQ Template (template) | DU00002863786 |  |  |  |  | 2024-07-19 |  | AESTHETIC MONOPOLE
W01223 | W066H_W01223OD_SRI_RAMPAI_BUSINES_PARK | Central |  | Decomm |  | 2024 Q1 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-17 |  |  |  | 2023-12-27 |  | 2024-01-05 | 2024-07-12 | CD//Norhaliza | 2024-01-23 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231119 | DU00002863787 |  |  |  |  | 2024-04-30 |  | LAMP_POLE
S00942 | KGMELANGKAP | Sabah |  | Decomm |  | 2025 Q3 | HW | GTSB | 4.6 TSSR Approved |  | 2025-01-23 |  | 2025-02-25 |  | 2025-03-07 |  | 2025-03-10 | 2025-09-10 | CD//Sharidah | 2025-03-17 | SQ202501020455 - GTSB / SQ202501070280 - GTSB | DU00002863788 |  |  |  |  | 2025-05-19 |  | TOWER
7027D | Kg Pogunon (REL) | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2024 Q3 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2023-10-24 | 2023-10-24 |  | 2023-10-26 |  | Closed | 2024-03-25 | 2024-04-15 | E//Hannah | 2024-04-06 | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231028 | DU00002863789 |  |  | 2024-11-18 | 2024-11-13 |  | Watertank | 60M Tower | 30 | Reuse existing RRU | 0 | 0
B01998 | B064E_B01998OD_TMN_DAMAI_MEWAH_KJG | Central |  | Decomm |  | 2024 Q4(single site MOCN)-L26 SSM | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-31 |  | 2024-07-06 |  | 2024-08-23 |  | 2024-08-27 | 2025-03-11 | CD//Norhaliza | 2024-10-11 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240202 | DU00002863790 |  |  |  |  | 2024-10-26 |  | POLE
B02289 | B064E_B02289OD_JELOK_INDAH_KJG | Central |  | Decomm |  | 2024 Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2024-03-07 |  | 2024-07-15 |  | 2024-07-04 |  | 2024-08-15 | 2025-03-11 | CD//Norhaliza | 2024-10-11 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240311 | DU00002863791 |  |  |  |  | 2024-10-15 |  | MINARATE
A00278 | A041A_A00278OD_LEMPURHULU_RCC | Northern | 4128P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863792 | [6 empty] | TOWER
A00798 | A042D_A00798OD_MN_KGBATU11 | Northern | 4213P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863793 | [6 empty] | TOWER
Q01807 | Q135A_Q01807OD_JLNUNIMAS2 | Sarawak |  | Decomm |  | 2024 Q2 | SH | YPTT | 4.6 TSSR Approved | TSSR REJECT | 2023-12-16 |  |  |  | 2024-01-08 |  | 2024-02-01 | 2024-03-21 | CD//John | 2024-02-02 | Celcom Digi_RAN-YPTT-TSS-Sarawak-20231221 | DU00002863794 |  |  |  |  | 2024-12-20 |  | TOWER
W01028 | B061J_W01028OD_JLNKINRARA2BDRKINRARA | Central |  | Decomm |  | 2024 Q3 | CR | GCI | 4.6 TSSR Approved |  | 2023-11-10 |  |  |  | 2023-11-21 |  | 2023-11-22 | 2025-03-12 | CD//Norhaliza | 2024-08-19 | CelcomDigi_RAN_GCI_TSS_Central_20231113 | DU00002863795 |  |  |  |  | 2024-09-28 |  | LAMP_POLE
A00819 | A041A_A00819OD_MN_KGJAWANG | Northern | 4202P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863796 | [6 empty] | #N/A
A00820 | A041A_A00820OD_MN_KGBAWONG | Northern | 4129P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863797 | [6 empty] | #N/A
A00825 | A041A_A00825OD_MN_POSPERWOR | Northern | 4203P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863798 | [6 empty] | #N/A
A00826 | A041A_A00826OD_MN_PERLOP1 | Northern | 4204P | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863799 | [6 empty] | #N/A
A01167 | T3_0622_Kg Jong | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863800 | [6 empty] | TOWER
A01178 | Paya Renggam | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863801 | [6 empty] | TOWER
A01180 | T3E_0614_Kg Ulu Piol | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863802 | [6 empty] | TOWER
A01181 | T3E_0613_Kg Cheh Hulu | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863803 | [6 empty] | TOWER
A01201 | T3E_0050_Kg.Pechah Batu | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863804 | [6 empty] | TOWER
W01370 | W066Z_W01370OD_JLNSENOHONG_TMNBKTRIA | Central |  | Decomm |  | 2024 Q3 | SM | YPTT | 4.6 TSSR Approved |  | 2024-02-23 |  |  |  | 2024-02-23 |  | 2024-03-27 | 2024-07-12 | CD//Sapian | 2024-04-22 | BOQ_Celcom Digi_RAN-YPTT-Standard PR TSS-20240225 | DU00002863805 |  |  |  |  | 2024-07-27 |  | LAMP_POLE
K00417 | K012A_K00417OD_KGKURA | Northern |  | Decomm |  | 2024 Q3(single site MOCN) | SHA | CCSMY | 4.6 TSSR Approved |  | 2024-09-25 |  | 2024-09-06 |  | 2024-09-27 |  | 2024-09-30 | 2024-10-16 | CD//Zulakmar | 2024-10-02 | 0809MW-Northern-CCSMY-BOQ Template(new contract)/0809CD-Northern-CCSMY-BOQ Template(new contract) | DU00002863806 |  |  |  |  | 2024-11-08 |  | TOWER
A01241 | KG JARAU | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863807 | [6 empty] | TOWER
A01243 | KG PPMS PERLOP 1 | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863808 | [6 empty] | TOWER
A01254 | KG BENDANG SELINSING | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863809 | [6 empty] | TOWER
A01255 | KG JALONG | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863810 | [6 empty] | TOWER
A01258 | Kg Kelubong | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863811 | [6 empty] | TOWER
A01286 | PENGKALAN IKAN TALAPIA | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863812 | [6 empty] | TOWER
B00162 | B064H_B00162OD_KM301BANGI3 | Central |  | Decomm | Decomm->On Hold->Decomm | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2025-02-07 |  | 2025-02-18 |  | 2025-04-07 |  | 2025-04-13 |  | CD//Sapian | 2025-04-23 | 0924CD-Central-Solusi-BOQ Template(new contract) | DU00002863813 |  |  |  |  | 2025-05-20 |  | TOWER
B02689 | W066X_B02689OD_SURAUALIKHLAS_KGMELAYUAMPANG | Central |  | Decomm |  | 2024 Q4 | ZA | AllStar | 4.6 TSSR Approved |  | 2024-01-03 |  |  |  | 2024-01-05 |  | 2024-01-22 | 2024-02-15 | CD//Norhaliza | 2024-02-07 | BOQ CelcomDigi_RAN_AllStar_Standard PR TSS_Central_20240108 | DU00002863814 |  |  |  |  | 2024-08-22 |  | LAMP_POLE
B02257 | B061J_B02257OD_TMNKINRARASEK4 | Central |  | Decomm |  | 2024 Q3 | CR | GCI | 4.6 TSSR Approved |  | 2024-01-04 |  |  |  | 2024-02-13 |  | 2024-04-24 | 2025-10-01 | CD//Ali Akaram | 2024-05-13 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240108 | DU00002863815 |  |  |  |  | 2024-10-10 |  | UNIPOLE
B01362 | B064H_B01362OD_BDRBKTMAHKOTA | Central |  | Decomm |  | 2024 | AD | GTSB | 4.6 TSSR Approved |  | 2024-09-06 |  | 2024-09-09 |  | 2024-09-19 |  | 2024-11-21 | 2025-01-14 | CD//Ali akaram | 2024-12-03 | 0919CD-Central-GTSB-BOQ Template(new contract) 2 | DU00002863816 |  |  |  |  | 2024-11-15 |  | MONOPOLE
A01159 | A036A_A01159OD_UITM_TAPAH2 | Northern |  | Decomm |  | 2024 Additional | BY | GTSB | 4.6 TSSR Approved |  | 2023-11-30 |  |  |  | 2023-12-14 |  | 2023-12-15 | 2024-03-05 | CD//Quah | 2023-12-22 | Celcom Digi_RAN-GTSB-TSS-Northern-20231201-0070 | DU00002863817 |  |  |  |  | 2025-11-18 |  | AESTHETIC MONOPOLE
S01509 | S088A_S01509OD_TMNERAMAS | Sabah |  | Decomm |  | 2024 Q3(single site MOCN) | MS | Seri Pancar | 4.6 TSSR Approved |  | 2024-01-11 | 2024-06-06 |  |  | 2024-03-14 |  | 2024-04-30 | 2024-06-21 | CD//Jahganathan | 2024-06-19 | Celcom Digi_RAN-Seri Pancar-Standard PR TSS-Sabah-20240116 | DU00002863818 |  |  |  |  | 2024-09-20 | Lampole | RAPOLE | 30
S01670 | DOCHOSPITAL2SDK | Sabah |  | Decomm |  | 2024 Q3 | MS | GTSB | 4.6 TSSR Approved |  | 2024-05-08 |  |  |  | 2024-05-13 |  | 2024-05-14 | 2024-06-28 | CD//Jahganathan | 2024-05-15 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240510 | DU00002863819 |  |  |  |  | 2024-08-28 |  | TOWER
Q01668 | Q132A_Q01668OD_TMNDELIGHTMYY | Sarawak |  | Decomm |  | 2025 Q1 | SH | Trintel | 4.6 TSSR Approved |  | 2023-10-08 |  |  |  | 2023-10-09 |  | 2023-10-09 | 2023-12-16 |  | 2023-10-10 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231009 | DU00002863820 |  |  |  |  | 2025-11-10 |  | RAPOLE
R00070 | R001B_R00070OD_TMNMASRIA | Northern |  | Decomm |  | 2024 Q4 | BY | GCI | 4.6 TSSR Approved |  | 2024-03-22 |  |  |  | 2024-03-28 |  | 2024-04-23 | 2024-05-24 | CD//Quah | 2024-05-21 | Celcom Digi_RAN-GCI-TSS-Northern-20240329-0104 | DU00002863821 |  |  |  |  | 2024-05-29 |  | LAMP_POLE
R00077 | R001B_R00077OD_TAMANPERLIS_KGR | Northern | 4616K | Swap | Decomm->On Hold->Swap | 2024 Q4 | SHA | CCSMY | 4.6 TSSR Approved | ¦ 0912 - Emailed Rollout on Major CME requirement ¦ 0809 - Changed anchor, SOW changed to SWAP | 2024-02-28 | 2024-08-06 |  | 2024-08-20 | 2024-03-11 | Under Approval | 2024-09-30 | 2024-10-01 | CD//Zulakmar | 2024-10-01 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240229-0097/0813CD-Northern-CCSMY-BOQ Template(new contract) | DU00002863822 |  |  | 2024-10-04 | 2024-10-02 |  | Monopole | LAMP_POLE | 33m | Add R8862A S9000 x2+R9264H M901821 x2+R8862A S2601 x2+A9732 M1821 x2,Dismantle | 12 | 0
S01578 | KGTIANG | Sabah |  | Decomm |  | 2025 Q3 | HW | NR services | 4.6 TSSR Approved |  | 2025-01-08 |  | 2025-02-03 |  | 2025-02-11 |  | 2025-02-24 | 2025-05-02 | CD//Sharidah | 2025-02-26 | SQ202501020449 - NR Service / SQ202501070289 - NR Service | DU00002863823 |  |  |  |  | 2025-06-28 |  | TOWER
B02305 | B061K_B02305OD_SETIAWALKPCHG | Central |  | Decomm |  | 2024 Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2024-03-04 |  |  |  | 2024-03-07 |  | 2024-03-13 | 2024-07-29 | CD//Sapian | 2024-03-26 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240311 | DU00002863824 |  |  |  |  | 2024-10-09 |  | BOOM
B02278 | B061T_B02278OD_HAPPYMANSIONSEK17PJ | Central |  | Decomm |  | 2024 Q3 | SY1 | GCI | 4.6 TSSR Approved |  | 2024-07-02 |  | 2024-06-20 |  | 2024-07-19 |  | 2024-07-22 | 2025-03-20 | CD//Ali Akaram | 2024-07-30 | 0918CD-Central-GCI-BOQ Template (old contract) | DU00002863825 |  |  |  |  | 2024-08-17 |  | BOOM
K00813 | K008A_K00813OD_CB_JLN_ISTANABKT_MALUT | Northern |  | Decomm |  | 2024 Q4 | HW | CCSMY | 4.6 TSSR Approved |  | 2024-10-13 |  | 2025-05-14 |  | 2025-05-29 | To be Submitted | 2025-06-04 |  | CD//Zulakmar | 2025-06-05 | 0927CD-Northern-CCSMY-BOQ Template(new contract)/0927MW-Northern-CCSMY-BOQ Template(new contract) | DU00002863826 |  |  |  |  | 2024-12-17 |  | TOWER
A00954 | A036B_A00954OD_FELDABESOUT | Northern |  | Decomm |  | 2025 Q1 | SHA | CCSMY | 4.6 TSSR Approved |  | 2024-01-19 |  |  |  | 2024-01-26 |  | 2025-01-07 | 2025-07-25 | CD//Zulakmar | 2025-04-30 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240124-0089//SQ202501030037 | DU00002863827 |  | CD Hazwan reviewed but Hold wait for upg tssr ready first |  |  | 2025-05-15 |  | LAMP_POLE
Q01126 | Q130A_Q01126OD_CB_T3SGARANG | Sarawak |  | Decomm |  | 2024 Q4(single site MOCN)-L21 SSM | SH | Magicell | 4.6 TSSR Approved |  | 2024-04-23 |  |  |  | 2024-04-29 |  | 2024-04-29 | 2024-09-05 | CD//John | 2024-05-02 | Celcom Digi_RAN-Magicell-Standard PR TSS-Sarawak-20240503 | DU00002863828 |  |  |  |  | 2024-12-17 |  | TOWER
Q01855 | Q139A_Q01855OD_KGTANGGA | Sarawak |  | Decomm |  | 2025 Q3 | ZB | Trintel | 4.6 TSSR Approved |  | 2024-03-02 |  |  |  | 2024-03-07 |  | 2024-03-27 | 2024-09-05 | CD//John | 2024-03-29 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240302/Celcom Digi_RAN-Trintel-Standard PR TSS DECOMM-Sarawak-20240314 | DU00002863829 |  |  |  |  | 2025-11-26 |  | TOWER
S00648 | S091A_S00648OD_KGSUANLAMBA | Sabah |  | Decomm |  | 2024 Q4(single site MOCN)-L2126 SSM | ZB | GTSB | 4.6 TSSR Approved |  | 2024-07-26 |  | 2024-07-31 |  | 2024-08-02 |  | 2024-08-05 | 2024-09-13 | CD//Jahganathan | 2024-08-13 | 0730CD-Sabah-GTSB-BOQ Template(new contract)/0730MW-Sabah-GTSB-BOQ Template(new contract) | DU00002863830 |  |  |  |  | 2024-12-19 |  | TOWER
S00219 | S112A_S00219OD_CB_TONGKABIRA | Sabah |  | Decomm |  | 2024 | MS | GTSB | 4.6 TSSR Approved |  | 2024-04-30 |  |  |  | 2024-05-02 |  | 2024-05-08 | 2024-07-05 | CD//Jahganathan | 2024-05-09 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240503 | DU00002863831 |  |  |  |  | 2024-10-14 |  | TOWER
S01594 | S104A_S01594OD_KGLOHAN1 | Sabah |  | Decomm |  | 2025 Q3 | HW | NR services | 4.6 TSSR Approved |  | 2025-01-09 |  | 2025-02-14 |  | 2025-02-18 |  | 2025-02-24 | 2025-05-02 | CD//Sharidah | 2025-02-26 | SQ202501020449 - NR Service / SQ202501070289 - NR Service | DU00002863832 |  |  |  |  | 2025-07-04 |  | TOWER
A00986 | A040D_A00986OD_RTC_GOPENG | Northern | 4631K | Swap | Decomm->On Hold->Swap | 2024 Q4 | SM | GCI | 4.6 TSSR Approved |  | 2024-11-29 | 2024-12-04 |  | 2024-12-09 |  | Rectificating | 2024-12-13 | 2024-12-18 | CD//Zulakmar | 2024-12-18 | 2211CD-Northern-TSS-BOQ Template(new contract)_GCI//Celcom Digi_RAN-GCI-TSS-Northern-20241112_New Contract | DU00002863833 |  |  | 2025-02-03 | 2025-02-03 |  | Watertank | LAMP_POLE | 30 | Add R8852E S9000x2+R9264H M901821 x1+R8862A S2601x3+A9732 M1821x2, Dismantle | 12 | 0
B01437 | B064G_B01437OD_GMIBANGI | Central |  | Decomm | Decomm->On Hold->Decomm->On Hold->Decomm | 2025 | HW | YPTT | 4.6 TSSR Approved |  | 2025-05-23 |  | 2025-05-14 | 2025-06-16 |  | Under Approval | 2025-06-19 |  | CD//Sapian | 2025-07-15 | SQ202506120190 | DU00002863834 |  |  |  |  | 2025-08-04 |  | RAMO
W01444 | W066E_W01444OD_KGPUAH_GOMBAK | Central |  | Decomm |  | 2024 Q1 | CR | GCI | 4.6 TSSR Approved |  | 2023-11-11 |  |  |  | 2023-11-17 |  | 2023-11-20 | 2024-05-27 | CD//Sapian | 2024-02-19 | CelcomDigi_RAN_GCI_TSS_Central_20231113 | DU00002863835 |  |  |  |  | 2024-05-08 |  | LAMP_POLE
A00066 | A042B_A00066OD_TAIPING2 | Northern |  | Decomm |  | 2024 Q2 | BY | YPTT | 4.6 TSSR Approved |  | 2024-01-22 |  |  |  | 2024-01-29 |  | 2024-01-30 | 2024-05-10 | CD//Quah | 2024-02-26 | Celcom Digi_RAN-YPTT-TSS-Northern-20240124-0056 | DU00002863836 |  |  |  |  | 2024-07-01 |  | BOOM
Q00937 | Q132A_Q00937OD_TMNJELITA | Sarawak |  | Decomm |  | 2024 | AD | Trintel | 4.6 TSSR Approved |  | 2025-07-16 |  | 2025-08-18 |  | 2025-08-21 |  | 2025-08-25 | 2025-10-17 | CD//John | 2025-08-26 | SQ202507250435-Trintel | DU00002863837 |  |  |  |  | 2025-11-24 |  | GUYED MAST
W01358 | W066V_W01358OD_JLN_DSARAPERMAI | Central |  | Decomm |  | 2024 Q2 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-11-17 |  |  |  | 2023-11-22 |  | 2023-11-28 | 2024-01-22 | CD//Norhaliza | 2024-01-05 | CelcomDigi_RAN_CCSMY_TSS_Central_20231119 | DU00002863838 |  |  |  |  | 2024-08-22 |  | LAMP_POLE
B02646 | B064H_B02646OD_IOI_CONEZION | Central |  | Decomm |  | 2024 Q3 | MS | Solusi | 4.6 TSSR Approved |  | 2024-09-12 |  |  |  | 2024-09-23 |  | 2024-09-25 |  | CD//Norhaliza | 2024-10-11 | 0924CD-Central-Solusi-BOQ Template(new contract) | DU00002863839 |  |  |  |  | 2025-05-05 |  | WALL MOUNTED BOOM
S01322 | S096A_S01322OD_KGLANDUNGAYANG | Sabah |  | Decomm |  | 2024 Q3(single site MOCN) | AD | Seri Pancar | 4.6 TSSR Approved |  | 2024-06-11 |  |  |  | 2024-06-26 |  | 2024-07-02 | 2024-08-09 | CD//Jahganathan | 2024-07-02 | 0618Sabah-Seri Pancar-BOQ Template (template) | DU00002863840 |  |  |  |  | 2024-09-23 |  | RAPOLE
S00863 | S098B_S00863OD_SRIPANDU | Sabah |  | Decomm |  | 2024 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2024-05-15 |  |  |  | 2024-05-20 |  | 2024-05-23 | 2024-08-01 | CD//Jahganathan | 2024-05-23 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240519 | DU00002863841 |  |  |  |  | 2024-09-18 |  | RAPOLE
Q00186 | Q133A_Q00186OD_MUKAH | Sarawak |  | Decomm | Decomm->On Hold->Decomm | 2025 Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2024-03-14 |  |  |  | 2024-03-19 |  | 2024-03-20 | 2024-05-14 | CD//John | 2024-03-23 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20240324 | DU00002863842 |  |  |  |  | 2025-06-26 |  | GUYED MAST
B02803 | B061O_B02803OD_KGSG_KAYUARA | Central |  | Decomm | Decomm->On Hold->Decomm | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-05-09 |  |  |  | 2024-05-17 |  | 2024-05-21 |  | CD//Sapian | 2024-06-04 | CelcomDigi_RAN_Datasco_TSS_Central_20231101 | DU00002863843 |  | Pls provide FE part |  |  |  |  | MONOPOLE
W01341 | W066AA_W01341OD_TMNIKANEMAS_CHERAS | Central |  | Decomm |  | 2024 Q3 | AI | YPTT | 4.6 TSSR Approved |  | 2024-08-20 |  | 2024-08-19 |  | 2024-08-20 |  | 2024-08-21 |  | CD//Ali akaram | 2024-09-11 | 0809CD-Central-YPTT-BOQ Template(new contract) | DU00002863844 |  |  |  |  | 2024-08-26 |  | LAMP_POLE
B00706 | B061L_B00706OD_PUCHONPDANA | Central |  | Decomm |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-03-07 |  | 2024-08-05 |  | 2024-08-09 |  | 2024-08-13 | 2025-03-11 | CD//Norhaliza | 2024-10-11 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240311 | DU00002863845 |  |  |  |  | 2024-10-25 |  | TOWER
W00593 | W066V_W00593OD_LRT_ABDULLAHUKUM | Central |  | Decomm |  | 2024 Q2 | MA | GCI | 4.6 TSSR Approved |  | 2024-07-02 |  |  |  | 2024-07-09 |  | 2024-07-11 | 2024-08-20 | CD//Sapian | 2024-07-18 | 0918CD-Central-GCI-BOQ Template (old contract) | DU00002863846 |  |  |  |  | 2024-11-30 |  | UNIPOLE
S01752 | S096A_S01752OD_KGPANGARABAN | Sabah |  | Decomm |  | 2024 Q3(single site MOCN) | AD | Seri Pancar | 4.6 TSSR Approved |  | 2024-06-11 |  |  |  | 2024-06-26 |  | 2024-07-02 | 2024-08-09 | CD//Jahganathan | 2024-07-02 | 0618Sabah-Seri Pancar-BOQ Template (template) | DU00002863847 |  |  |  |  | 2024-09-27 |  | TOWER
B00827 | B057D_B00827OD_TMNSAMUDERA | Central |  | Decomm |  | 2024 Q1 | MS | Magicell | 4.6 TSSR Approved |  | 2024-01-26 |  |  |  | 2024-02-06 |  | 2024-02-07 | 2024-05-12 | CD//Sapian | 2024-04-24 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240128 | DU00002863848 |  |  |  |  | 2024-04-01 |  | MINI STRUCTURE
K00638 | T3_0256_Bukit Kachi | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863849 | [6 empty] | #N/A
K00838 | Kg Kota Mengkuang | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863850 | [6 empty] | TOWER
K00930 | Kg. Alor Batu | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863851 | [6 empty] | TOWER
A01073 | A044A_A01073OD_BDR_UNI_LAKEVILLE | Northern |  | Decomm |  | 2024 Q2 | SM | GCI | 4.6 TSSR Approved |  | 2024-04-25 |  |  |  | 2024-04-29 |  | 2024-05-02 | 2024-10-01 | CD//Quah | 2024-05-21 | Celcom Digi_RAN-GCI-TSS-Northern-20240512-0106 | DU00002863852 |  |  |  |  | 2024-06-20 |  | LAMP_POLE
K00931 | Kg Carok Tok Lateh | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863853 | [6 empty] | TOWER
K00937 | Kg Wang Perah | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863854 | [6 empty] | TOWER
K00945 | T3E_0657_Akademi Binaan Malaysia Sintok | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863855 | [6 empty] | TOWER
K00956 | T3E_0064_Kg Changkat Setol | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q3 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863856 | [6 empty] | TOWER
A01045 | A041A_A01045OD_CB_RPTSRIKLEDANG | Northern |  | Decomm |  | 2024 Q4 | ZA | GCI | 4.6 TSSR Approved |  | 2023-10-21 |  |  |  | 2023-10-24 |  | 2023-10-27 | 2024-10-01 | CD//Quah | 2023-11-21 | Celcom Digi_RAN-GCI-TSS-Northern-20231025-0065/Celcom Digi_RAN-GCI-TSS Decomm-Northern-20240529-0109 | DU00002863857 |  | Missing antenna photo, FE info and Photo |  |  | 2024-09-30 |  | UNIPOLE
Q00121 | Q143A_Q00121OD_CB_KGSELEPONG | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863858 | [6 empty] | TOWER
Q00200 | Q143A_Q00200OD_SPGBETONG | Sarawak | 9472P | Swap | Swap->On Hold->Swap | 2025 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2025-03-11 | 2025-08-12 |  | 2025-08-17 |  | Under Approval | 2025-08-18 | 2025-09-20 | E//John | 2025-09-08 | SQ202502190399-YPTT | DU00002863859 |  |  | 2025-09-26 | 2025-09-24 |  | Tower | TOWER | 76 | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
Q00271 | Q137A_Q00271OD_CB_SGRUSA | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863860 | [6 empty] | TOWER
Q00476 | Q136A_Q00476OD_CB_KGSESSANG | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863861 | [6 empty] | TOWER
S01373 | S105B_S01373OD_TMNAMANJAYA | Sabah | 7290K | Swap | Decomm->On Hold->Swap | 2024 Q3 | MS | GTSB | 4.6 TSSR Approved |  | 2024-04-08 | 2024-09-02 |  | 2024-09-10 | 2024-04-16 | Rectificating | 2024-04-17 | 2024-10-10 | CD//Jahganathan | 2024-10-09 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240420/0823CD-Sabah-GTSB-BOQ Template(new contract) | DU00002863862 |  |  | 2025-01-31 | 2024-12-16 |  | Tower | RAPOLE | 30 | Add R8862A S9000 x1 + A9732 M1821 x1 + R9264H M901821 x3+R8862A S2601 x4, Dismantle Celcom RRU | 3
Q00614 | Q136A_Q00614OD_CB_KGALIT | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863863 | [6 empty] | TOWER
Q01899 | Q132C_Q01899OD_JLNHOMELITE | Sarawak |  | Decomm |  | 2025 Q1 | SH | Trintel | 4.6 TSSR Approved |  | 2024-04-26 |  |  |  | 2024-04-29 |  | 2024-04-30 | 2024-05-24 | CD//John | 2024-05-02 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240503 | DU00002863864 |  |  |  |  | 2025-06-20 |  | RAPOLE
Q00786 | Q143A_Q00786OD_CB_KGAPING | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863865 | [6 empty] | TOWER
Q00791 | Q137A_Q00791OD_CB_BULAT | Sarawak | 9272P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q2 | AI | Trintel | 4.6 TSSR Approved |  | 2025-02-21 | 2025-03-07 |  | 2025-03-17 |  | Closed | 2025-03-20 | 2025-05-19 | CD//John | 2025-03-24 | SQ202501070293-Trintel | DU00002863866 |  |  | 2025-05-23 | 2025-05-15 |  | Tower | TOWER | 76 | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
Q00876 | Q143A_Q00876OD_CB_KGBTLINTANG | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863867 | [6 empty] | TOWER
Q00878 | Q137A_Q00878OD_CB_SGPAOH | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863868 | [6 empty] | TOWER
Q00966 | Q117A_Q00966OD_T3_NGTIGA | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863869 | [6 empty] | TOWER
Q00968 | Q117A_Q00968OD_CB_NGBONG | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863870 | [6 empty] | TOWER
Q00970 | Q117A_Q00970OD_CB_KGPENOM | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863871 | [6 empty] | TOWER
Q00971 | Q117A_Q00971OD_CB_BATULAPAN | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863872 | [6 empty] | TOWER
Q00974 | Q117A_Q00974OD_T3_PELIKOI | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863873 | [6 empty] | TOWER
Q00990 | Q143A_Q00990OD_CB_KGEMPALING | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863874 | [6 empty] | TOWER
Q00993 | Q143A_Q00993OD_T3_SPGJAONG | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863875 | [6 empty] | TOWER
Q00994 | PANGGIL | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) |  |  | 2025-02-07 |  |  |  | To be Submitted | [5 empty] | DU00002863876 | [5 empty] | Tower | TOWER | 61 | USP Upgrade
Q01148 | Q122A_Q01148OD_T3_SKROH | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863877 | [6 empty] | TOWER
Q01153 | Q121A_Q01153OD_T3_RHABANG | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863878 | [6 empty] | TOWER
Q01156 | Q122A_Q01156OD_T3_NGPERANAN | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863879 | [6 empty] | TOWER
K00853 | K004B_K00853OD_TMN_BISTARI_JAYA_AS | Northern |  | Decomm |  | 2025 Q3 | HW | GCI | 4.6 TSSR Approved |  | 2025-04-16 |  | 2025-04-23 |  | 2025-05-05 |  | 2025-05-06 | 2025-10-28 | E//Hazida | 2025-05-13 | SQ202501060244 - GCI | DU00002863880 |  |  |  |  | 2025-06-23 |  | UNIPOLE
Q01542 | Q122A_Q01542OD_MN_NANGAYONG | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863881 | [6 empty] | TOWER
Q01157 | Q122A_Q01157OD_T3_NGLIPUS | Sarawak | 9273P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q3 | AD | Trintel | 4.6 TSSR Approved |  | 2025-03-24 | 2025-04-18 |  | 2025-04-24 |  | Under Approval | 2025-04-25 | 2025-05-27 | CD//John | 2025-04-26 | SQ202501070293-Trintel | DU00002863882 |  |  | 2025-06-14 | 2025-05-21 |  | Tower | TOWER | 60 | Add R8852E S9000x3+R8894E M1821x3, Dismantle | 0 | 0
Q01161 | Q134A_Q01161OD_CB_RHAJI | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863883 | [6 empty] | TOWER
Q01166 | Q134A_Q01166OD_T3_JLNENTABAI | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863884 | [6 empty] | TOWER
Q01184 | Q136A_Q01184OD_T3_NGGRENJANG | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863885 | [6 empty] | TOWER
Q01186 | Q136A_Q01186OD_T3_KGPERPAT | Sarawak | 9240P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q3 | HW | Trintel | 4.6 TSSR Approved |  | 2025-02-17 | 2025-02-24 |  | 2025-03-21 |  | Under Approval | 2025-04-09 | 2025-05-19 | CD//John | 2025-04-23 | SQ202501070293-Trintel | DU00002863886 |  |  | 2025-07-06 | 2025-06-09 |  | Tower | TOWER | 76M | Add R8852E S9000x3+R8894E M1821x4, Dismantle | 0 | 3
Q01189 | Q136A_Q01189OD_RH_DANGKAN | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863887 | [6 empty] | TOWER
Q01192 | Q136A_Q01192OD_T3_SGSEBELAK | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863888 | [6 empty] | TOWER
Q01194 | Q136A_Q01194OD_T3_SGBURUI | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863889 | [6 empty] | TOWER
Q01195 | Q120A_Q01195OD_T3_KGJERIJEH | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863890 | [6 empty] | TOWER
Q01196 | Q137A_Q01196OD_CB_BKTKINYAU | Sarawak | 9241P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q1 |  | Trintel | 1.1 Pending Survey - Subcon | [6 empty] | To be Submitted |  |  |  |  | SQ202501070293-Trintel | DU00002863891 | [6 empty] | TOWER |  | Add R8852E S9000x3+R8894E M1821x4, Dismantle | 0 | 2
Q01209 | Q129A_Q01209OD_CB_KGSELEMAS | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863892 | [6 empty] | TOWER
Q01211 | Q129A_Q01211OD_T3_SGMUPONG | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863893 | [6 empty] | TOWER
Q01212 | Q129A_Q01212OD_T3_SGMADOR | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863894 | [6 empty] | TOWER
Q01213 | Q134A_Q01213OD_CB_SGSTASS | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863895 | [6 empty] | TOWER
Q01558 | Q117A_Q01558OD_T3_RHLINGIT | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863896 | [6 empty] | TOWER
Q01559 | Q117A_Q01559OD_T3_KGDIT | Sarawak | 9288P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN->Swap | 2024 Q4 | AD | Trintel | 4.6 TSSR Approved |  | 2025-04-22 | 2025-04-24 |  | 2025-04-28 |  | Under Approval | 2025-05-02 | 2025-09-11 | E//John | 2025-05-19 | SQ202505020084-Trintel | DU00002863897 |  |  | 2025-09-10 | 2025-09-08 |  | Tower | TOWER | 76 | Add R8852E S9000x3+R8854E S1800x3+R8894E M1821x3+R8862A S2601x3, Dismantle | 0 | 0
Q01560 | Q117A_Q01560OD_T3_RHDAU | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863898 | [6 empty] | TOWER
B00143 | B064I_B00143OD_SGLALANG | Central |  | Decomm |  | 2024 | AD | GCI | 4.6 TSSR Approved |  | 2024-10-17 |  | 2024-10-21 |  | 2024-11-15 |  | 2024-11-21 |  | CD//Sapian | 2024-12-03 | Wireless+ Malaysia CD+TSS+ GCI+4 site SQ202410310157 | DU00002863899 |  |  |  |  | 2024-10-22 |  | TOWER
Q01561 | Q117A_Q01561OD_T3_KGSETAMBAK | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863900 | [6 empty] | TOWER
W01431 | W066AA_W01431OD_JLN_BUDIMAN_TMNMULIA | Central |  | Decomm |  | 2024 Q3 | AI | YPTT | 4.6 TSSR Approved |  | 2024-08-07 |  | 2024-08-14 |  | 2024-08-15 |  | 2024-08-15 | 2025-03-20 | CD//Ali Akaram | 2024-08-22 | 0809CD-Central-YPTT-BOQ Template(new contract) | DU00002863901 |  |  |  |  | 2024-08-28 |  | LAMP_POLE
Q01562 | Q117A_Q01562OD_T3_NGBAYOR | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863902 | [6 empty] | TOWER
Q01563 | Q117A_Q01563OD_T3_RHPHILIPMUJAH | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863903 | [6 empty] | TOWER
Q01564 | Q117A_Q01564OD_T3_KGMANGGUT | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863904 | [6 empty] | TOWER
Q01565 | Q117A_Q01565OD_T3_JAMBUKERAPA | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863905 | [6 empty] | TOWER
Q01566 | Q117A_Q01566OD_T3_RHBEDURU | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863906 | [6 empty] | TOWER
Q01567 | Q143A_Q01567OD_T3_JLNSALIDONG | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863907 | [6 empty] | TOWER
L00155 | S113A_L00155OD_KGGERSIKLABUAN | Sabah |  | Decomm | Decomm->On Hold-Decomm | 2024 Q3(single site MOCN) | AD | Datasco | 4.6 TSSR Approved |  | 2024-11-11 |  | 2024-08-12 |  | 2024-11-13 |  | 2024-11-15 | 2024-12-13 | CD//Thanniya | 2024-11-18 | 0809MW-Sabah-Datasco-BOQ Template(new contract)/0809CD-Sabah-Datasco-BOQ Template(new contract) | DU00002863908 |  |  |  |  | 2025-01-15 |  | LAMP_POLE
Q01568 | Q143A_Q01568OD_T3_KGSEDUKU | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863909 | [6 empty] | TOWER
Q01569 | Q143A_Q01569OD_T3_TJGBIJAT | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863910 | [6 empty] | TOWER
Q01570 | Q143A_Q01570OD_T3_JLNSKRANGBETONG | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863911 | [6 empty] | TOWER
Q01571 | Q143A_Q01571OD_T3_RHTUNGGANG | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863912 | [6 empty] | TOWER
Q01572 | Q143A_Q01572OD_T3_KGGUADALAM | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863913 | [6 empty] | TOWER
Q01573 | Q143A_Q01573OD_T3_RHABDULRAHMAN | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863914 | [6 empty] | TOWER
Q01574 | Q143A_Q01574OD_T3_RHTINCHIN | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863915 | [6 empty] | TOWER
Q01575 | Q143A_Q01575OD_T3_RHRICHARD | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863916 | [6 empty] | TOWER
Q01576 | Q143A_Q01576OD_T3_RHSILIT | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863917 | [6 empty] | TOWER
Q01577 | Q143A_Q01577OD_T3_RHLAIT | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863918 | [6 empty] | TOWER
Q01578 | Q143A_Q01578OD_T3_KGPULAU | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863919 | [6 empty] | TOWER
Q01579 | Q143A_Q01579OD_T3_NGMURAT | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863920 | [6 empty] | TOWER
Q01580 | Q127A_Q01580OD_T3_RHMARIAN | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863921 | [6 empty] | TOWER
Q01581 | Q127A_Q01581OD_T3_SERUBAH | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863922 | [6 empty] | TOWER
Q01582 | Q127A_Q01582OD_T3_NGUYAU | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863923 | [6 empty] | TOWER
K00260 | K012A_K00260OD_DUSUNPENGAPIT | Northern |  | Decomm |  | 2024 Q3(single site MOCN) | SM | GTSB | 4.6 TSSR Approved |  | 2024-07-12 |  | 2024-07-07 |  | 2024-07-17 |  | 2024-07-19 |  | CD//Zulakmar | 2024-07-23 | 0715Northern-GTSB-BOQ Template_nc/0730MW-Northern-GTSB-BOQ Template(new contract) | DU00002863924 |  |  |  |  | 2024-11-20 | Tower | TOWER | 60m
B02526 | B057D_B02526OD_LRT_GOMBAK | Central |  | Decomm |  | 2024 Q1 | MS | GTSB | 4.6 TSSR Approved |  | 2024-02-08 |  |  |  | 2024-02-20 |  | 2024-02-21 | 2024-04-24 | CD//Sapian | 2024-02-27 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240212 | DU00002863925 |  |  |  |  | 2024-05-11 |  | MINI STRUCTURE
Q01583 | T3KGSERABANG | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863926 | [6 empty] | TOWER
Q01584 | Q117A_Q01584OD_T3_KGSUPA | Sarawak | 9289P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN->Swap | 2024 Q4 | AI | Trintel | 4.6 TSSR Approved |  | 2025-04-23 | 2025-04-24 |  | 2025-04-30 |  | Under Approval | 2025-04-30 | 2025-05-02 | CD//John | 2025-04-30 | SQ202505020084-Trintel | DU00002863927 |  |  | 2025-08-26 | 2025-08-20 |  | Tower | TOWER | 76 | Add R8852E S9000x3+R8894E M1821x4, Dismantle | 0 | 2
W00877 | W066J_W00877OD_LUQMANALHAKIM | Central |  | Decomm |  | 2024 Q1 | AI | Solusi | 4.6 TSSR Approved |  | 2025-03-21 |  |  |  | 2025-04-14 |  | 2025-04-27 |  | CD//Sapian | 2025-05-08 | SQ202510270687 | DU00002863928 |  | Please provide photo for sow (DISMANTLE DIGI MICROWAVE LINK 1594C-1737A) & FE part |  |  | 2025-03-24 |  | MONOPOLE
W01549 | W066Z_W01549OD_JLN_1_92C_JLN_CHERAS | Central |  | Decomm |  | 2024 Q3 | SS | YPTT | 4.6 TSSR Approved |  | 2024-08-21 |  | 2024-08-19 |  | 2024-08-21 |  | 2024-08-23 |  | CD//Sapian | 2024-09-01 | 0809CD-Central-YPTT-BOQ Template(new contract) | DU00002863929 |  |  |  |  | 2024-09-12 |  | LAMP_POLE
Q01710 | Q136A_Q01710OD_CB_SKBRAYANG | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863930 | [6 empty] | TOWER
Q01714 | Q136A_Q01714OD_CB_KELAMPIR | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863931 | [6 empty] | TOWER
Q01970 | T3E_0289_SK Nanga Pedanum Pakan-Pedanum road | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863932 | [6 empty] | TOWER
Q01971 | EMPAYANG ATAS | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863933 | [6 empty] | TOWER
Q01972 | RUMAH SEMINAI | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863934 | [6 empty] | TOWER
B00018 | B064I_B00018OD_TMNSRIHANECO | Central |  | Decomm |  | 2024 | SM | GCI | 4.6 TSSR Approved |  | 2024-10-23 |  |  |  | 2024-11-29 |  | 2024-12-03 | 2025-03-11 | CD//Ali akaram | 2024-12-10 | Wireless+ Malaysia CD+TSS+ GCI+4 site SQ202410310157 | DU00002863935 |  |  |  |  | 2024-12-06 |  | SHARING STRC OTHERS MINARATE
Q01973 | RUMAH NYELANG | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863936 | [6 empty] | TOWER
Q01974 | SIMPANG SARATOK HIGHWAY | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863937 | [6 empty] | TOWER
Q01979 | Q137A_Q01979OD_T3_RHNANANG | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863938 | [6 empty] | TOWER
Q01980 | RUMAH NYUKA | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863939 | [6 empty] | TOWER
Q01981 | Sjk Hua Kee | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863940 | [6 empty] | TOWER
Q01982 | Q137A_Q01982OD_T3_RHJAWA | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863941 | [6 empty] | TOWER
Q01983 | RUMAH JANTAN | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863942 | [6 empty] | TOWER
Q01984 | Rh Sigat | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863943 | [6 empty] | TOWER
Q01985 | Q129A_Q01985OD_T3_JLNTGMANISSIBU2 | Sarawak | 9274P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 Q2 | AI | Trintel | 4.6 TSSR Approved |  | 2025-02-24 | 2025-04-28 |  | 2025-05-02 |  | Closed | 2025-05-07 | 2025-05-21 | CD//John | 2025-05-08 | SQ202501070293-Trintel | DU00002863944 |  |  | 2025-08-28 | 2025-08-25 |  | Tower | TOWER | 76 | Add R8852E S9000x3+R8854E S1800x3+R8894E M1821x3, Dismantle | 0 | 0
Q01986 | KAMPUNG PALOH | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863945 | [6 empty] | TOWER
B02638 | W067A_B02638OD_LAKEFRONT_RESIDENCE | Central |  | Decomm |  | 2024 Q3 | MS | Magicell | 4.6 TSSR Approved |  | 2024-05-28 |  |  |  | 2024-05-30 |  | 2024-07-18 | 2024-10-28 | CD//Norhaliza | 2024-10-15 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240510 - Decomm | DU00002863946 |  |  |  |  | 2024-11-25 |  | LAMP_POLE
B02634 | W067A_B02634OD_PARCELF_BLOKF7 | Central |  | Decomm | Decomm->Swap->Decomm | 2024 Q3 | SM | Magicell | 4.6 TSSR Approved |  | 2024-07-15 | 2024-07-25 |  | 2024-07-31 | 2024-02-08 | Rectificating | 2024-08-07 | 2024-09-25 | CD//Ali Akaram | 2024-08-13 | 0619Central-Magicell-BOQ Template (template) | DU00002863947 |  |  |  |  | 2025-02-26 | In-Building System | WALL MOUNTED BOOM | 3
B02200 | W067A_B02200OD_APRTFASA12PRESINT9 | Central | 1854K | Swap | Decomm->Swap | 2024 Q3 | AI | AllStar | 4.6 TSSR Approved |  | 2024-01-18 | 2024-06-05 |  | 2024-06-06 | 2024-02-01 | Under Approval | 2024-06-06 | 2024-07-23 | CD//Ali Akaram | 2024-07-23 | Wireless_Malaysia CD_TSS_ALLSTAR_ 6 site SQ202411010178 | DU00002863948 |  |  | 2024-11-14 | 2024-11-09 |  | Wall mount boom | BOOM | 3 | Add R8862A S9000 x4+R8894E M1821 x5+R8854 S2600 x1,Dismantle | 0 | 3
B02197 | W067A_B02197OD_APRT_PRIMA_PRESINT11 | Central | 1855K | Swap | Decomm->Swap | 2024 Q3 | SHA | YPTT | 4.6 TSSR Approved |  | 2024-07-30 | 2024-08-13 |  | 2024-08-16 |  | Under Approval | 2024-09-26 | 2024-10-21 | CD//Ali akaram | 2024-10-21 | 0802CD-Central-YPTT-BOQ Template(new contract) | DU00002863949 |  |  | 2024-11-16 | 2024-11-13 |  | Wall mount boom | BOOM | 3m | Add R8862A S9000 x3+R9264H M901821 x1+R8862A S2601 x3+A9732 M1821 x3,Dismantle | 234 | 0
Q01987 | SK LENGAN (TANJUNG MANIS-SIBU ROAD 1) | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863950 | [6 empty] | TOWER
Q01988 | Tubau Forest | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863951 | [6 empty] | TOWER
Q01989 | T3E_0297_Nanga Dayu Rumah Tindin Rumah Samak Ru | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863952 | [6 empty] | TOWER
Q01990 | T3E_0292_Rumah Eddy Madang Julau Pakan road | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863953 | [6 empty] | TOWER
Q01991 | T3E_0295_ Rumah Beracok Simpang Wak | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863954 | [6 empty] | TOWER
Q01992 | T3E_0296_Rumah George Rumah Racak Rumah Empati | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863955 | [6 empty] | TOWER
Q01993 | T3E_0298_SK Sungai Babai- Pakan Road Rumah Anyi | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863956 | [6 empty] | TOWER
Q01994 | T3E_0288_Rumah Ayub Rumah Enting Rumah Nyandang | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863957 | [6 empty] | TOWER
Q01995 | T3E_0299_Rumah Dana | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863958 | [6 empty] | TOWER
Q01996 | T3E_0291_Rumah Gani Rumah Amba a Rumah Nyikoh | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863959 | [6 empty] | TOWER
Q01997 | T3E_0290_SK Nanga Meluan Rumah Chuat a Rumaah Ra | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863960 | [6 empty] | TOWER
Q02000 | T3E_0305_Nanga Jagau Settlement | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863961 | [6 empty] | TOWER
A00600 | A042C_A00600OD_CKTJERINGTOWN | Northern |  | Decomm |  | 2024 Q2 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-11-21 |  |  |  | 2023-11-22 |  | 2023-11-23 | 2024-01-22 | CD//Quah | 2023-12-22 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231122-0072 | DU00002863962 |  | Please include Celcom Cabinet for equipment relocation to Digi Cabinet 28/11: Need Amend Drawing for location Digi Cabinet |  |  | 2024-05-11 |  | MINI STRUCTURE
Q02124 | KG SEDAU | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863963 | [6 empty] | TOWER
K00846 | K008A_K00846OD_KGRANGGOTKECHIL_LKW | Northern | 4623K | Swap | Decomm->On Hold->Swap | 2024 Q3(single site MOCN) | SM | CCSMY | 4.6 TSSR Approved |  | 2024-10-10 | 2024-10-15 |  | 2024-10-22 |  | Under Approval | 2024-10-22 | 2024-10-24 | CD//Zulakmar | 2024-10-24 | 0925CD-Northern-GTSB-BOQ Template(new contract)//SQ202412160275 - CCSMY | DU00002863964 |  |  | 2024-11-09 | 2024-10-29 |  | Lampole | LAMP_POLE | 33m | Add R8894E M1821 x5 + R8862A S2601 x1 + R8854 S2600 x2 + R8862A S9000 x3,Dismantle Celcom all RRU&BBU | 0 | 13
R00088 | R001C_R00088OD_KOLEJ_TAR_UNIMAP | Northern |  | Decomm | Decomm->On Hold->Decomm | 2024 Q4 | HW | GCI | 4.6 TSSR Approved |  | 2024-10-07 |  | 2025-05-23 |  | 2025-05-26 |  | 2025-06-03 | 2025-10-28 | E//Hazida | 2025-07-15 | 0927CD-Northern-GCI-BOQ Template(new contract)/0927MW-Northern-GCI-BOQ Template(new contract) | DU00002863965 |  |  |  |  | 2025-05-26 |  | TOWER
Q02125 | Sk Engkabang | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863966 | [6 empty] | TOWER
Q01608 | Q141A_Q01608OD_KGJEMUKAN | Sarawak | 9381K | Swap | Decomm->On Hold->Swap | 2024 Q2 | ZB | Magicell | 4.6 TSSR Approved |  | 2024-09-13 | 2024-09-27 |  | 2024-10-04 | 2023-11-08 | Under Approval | 2024-10-04 | 2024-12-05 | CD//John | 2024-12-05 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231107/0823CD-Sarawak-Magicell-BOQ Template(new contract) | DU00002863967 |  |  | 2025-04-04 | 2025-03-11 |  | Watertank | TOWER | 32m | Add R8862A S9000 x3+R8894E M1821 x3+R8862A S2601 x3,Dismantle | 0 | 0
W00602 | W066G_W00602OD_TMNSETAPAKINDAH | Central |  | Decomm |  | 2024 Q1 | AI | GTSB | 4.6 TSSR Approved |  | 2024-02-23 |  |  |  | 2024-03-18 |  | 2024-03-19 | 2024-05-27 | CD//Ali Akaram | 2024-04-16 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240303 | DU00002863968 |  |  |  |  | 2024-04-02 |  | LAMP_POLE
Q02127 | PEDANOM | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863969 | [6 empty] | TOWER
K00044 | K010A_K00044OD_TMPENDANG | Northern |  | Decomm |  | 2024 Q4 | HW | GCI | 4.6 TSSR Approved | 8/8 - Safety Issue, Beehive,, 6/8 TM revert wip for beehive clearance// 6/8 - TM site, access pending, raise up to SA to prioritize | 2025-10-23 |  | 2025-10-30 |  | 2025-11-04 | To be Submitted | 2025-11-06 |  | E//Hazida | 2025-11-07 | 0927CD-Northern-GCI-BOQ Template(new contract)/0927MW-Northern-GCI-BOQ Template(new contract) | DU00002863970 |  |  |  |  | 2025-11-18 |  | BOOM
Q02128 | Bara Lubok Antu | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863971 | [6 empty] | TOWER
Q02129 | KG KEDANG | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863972 | [6 empty] | TOWER
K00904 | K008A_K00904OD_KUALA_PERIANG_LKW | Northern | 4617K | Swap | Decomm->On Hold->Swap | 154 single site MOCN | SM | GTSB | 4.6 TSSR Approved | ¦ 0919 - New solution received, triggered GTSB for revision ¦ 0913 - Emailed planning team | 2024-09-03 | 2024-09-06 |  | 2024-09-12 |  | Under Approval | 2024-09-19 | 2024-09-20 | CD//Zulakmar | 2024-09-20 | 0903CD-Northern-GTSB-BOQ Template(new contract) | DU00002863973 |  |  | 2024-10-31 | 2024-10-19 |  | Monopole | LAMP_POLE | 30M | Add R9264H M901821 x3+R8862A S2601 x2+R8854 S2600 x1,Dismantle |  | 3
Q02131 | Kg Ulu Strass | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863974 | [6 empty] | TOWER
Q02136 | NANGA ENTABAI | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863975 | [6 empty] | TOWER
Q02143 | BATU LUKING | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863976 | [6 empty] | TOWER
Q02144 | NANGA MAONG | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863977 | [6 empty] | TOWER
Q02145 | NANGA JAGOI | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863978 | [6 empty] | TOWER
Q02147 | KG BUNGIN | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863979 | [6 empty] | TOWER
Q02148 | KG SEBAKO | Sarawak |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863980 | [6 empty] | TOWER
R00102 | Kg Padang Melangit | Northern |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863981 | [6 empty] | TOWER
S00391 | S091A_S00391OD_CB_SPGSUKAU | Sabah | 7293P | Swap | Swap->On Hold->Swap | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-01-23 | 2025-01-27 |  | 2025-02-03 |  | Under Approval | 2025-02-06 | 2025-03-09 | CD//Sharidah | 2025-02-07 | SQ202501020392 - Futong | DU00002863982 |  |  | 2025-04-17 | 2025-04-09 |  | Tower | TOWER | 65m | Add R8862A S9000x3+R8894E M1821 x3,Dismantle | 0 | 0
S00500 | S091A_S00500OD_SUKAU | Sabah | 7294P | Swap | Swap->On Hold->Swap | 2024 Q4 | AD | Futong | 4.6 TSSR Approved |  | 2025-01-21 | 2025-01-23 |  | 2025-01-31 |  | Under Approval | 2025-02-03 | 2025-02-18 | CD//Sharidah | 2025-02-05 | SQ202501020392 - Futong | DU00002863983 |  |  | 2025-07-06 | 2025-05-19 |  | Tower | TOWER | 76m | Add R8862A S9000x3+R8894E M1821 x3,Dismantle | 0 | 0
S00550 | S091A_S00550OD_MALANGKINESTATE | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863984 | [6 empty] | MINI STRUCTURE
S00601 | S091A_S00601OD_CB_KGSINARJAYA | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863985 | [6 empty] | TOWER
S01007 | Kg Jaya Baru | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863986 | [6 empty] | TOWER
S01013 | S092A_S01013OD_KGRAMPAYANULU | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863987 | [6 empty] | TOWER
S01020 | S091A_S01020OD_KGBATU4 | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863988 | [6 empty] | TOWER
S01418 | S099A_S01418OD_T3_KGSESELONGON | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863989 | [6 empty] | TOWER
S01419 | S101A_S01419OD_T3_KGTERIAN | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863990 | [6 empty] | TOWER
S01420 | S101A_S01420OD_T3_KGTIMPANGOH | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863991 | [6 empty] | TOWER
S01428 | S108A_S01428OD_T3_SKKINALUAN | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863992 | [6 empty] | TOWER
W01346 | W066S_W01346OD_LRT_AWANBESAR | Central |  | Decomm |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-27 |  |  |  | 2024-01-22 |  | 2024-01-23 | 2024-04-24 | CD//Ali akaram | 2024-02-08 | CelcomDigi_RAN_GTSB_TSS_Central_20231201 | DU00002863993 |  |  |  |  | 2024-08-21 |  | RAPOLE
B02546 | B064I_B02546OD_KGPASIRBARU_SEMENYIH | Central |  | Decomm | Decomm->On Hold->Decomm | 2024 | SH | GCI | 4.6 TSSR Approved |  | 2024-02-06 |  |  |  | 2024-02-14 |  | 2024-05-24 |  | CD//Norhaliza | 2024-12-13 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240212 | DU00002863994 |  | MISSING FE PART |  |  | 2024-12-20 |  | RAPOLE
B02275 | B064F_B02275OD_TMNBERJAYAKJG | Central |  | Decomm |  | 2024 Q4(single site MOCN)-L2126 SSM | SH | Magicell | 4.6 TSSR Approved |  | 2024-03-04 |  |  |  | 2024-03-25 |  | 2024-12-10 | 2025-03-20 | CD//Norhaliza | 2024-12-23 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240311 | DU00002863995 |  |  |  |  | 2024-11-23 |  | BOOM
S01485 | S091A_S01485OD_CB_AMPLEVALLEY | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863996 | [6 empty] | TOWER
S01531 | kpg ragkam | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863997 | [6 empty] | TOWER
S01542 | kpg tuawon | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863998 | [6 empty] | TOWER
S01575 | KG SG MONYET | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002863999 | [6 empty] | TOWER
S01576 | S105B_S01576OD_CB_KGJAWASDK | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864000 | [6 empty] | TOWER
Q00229 | Q123A_Q00229OD_TMKAPITEX | Sarawak |  | Decomm |  | 2025 Q3 | ZB | Trintel | 4.6 TSSR Approved |  | 2024-04-24 |  |  |  | 2024-04-26 |  | 2024-04-26 | 2024-05-24 | CD//John | 2024-05-13 | Celcom Digi_RAN-Trintel-Standard PR TSS-Sarawak-20240503 | DU00002864001 |  |  |  |  | 2025-07-11 |  | BOOM
B02392 | B061L_B02392OD_JLNTPPPCHG | Central |  | Decomm |  | 2024 Q3 | CR | Solusi | 4.6 TSSR Approved |  | 2024-09-02 |  |  |  | 2024-09-06 |  | 2024-09-09 |  | CD//Ali akaram | 2024-09-24 | 0724Central-Solusi-BOQ Template | DU00002864002 |  |  |  |  | 2024-11-15 |  | LAMP_POLE
S01579 | Kg Wani | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864003 | [6 empty] | TOWER
S01586 | S091A_S01586OD_CB_KGKUALASUANLAMBA | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864004 | [6 empty] | TOWER
S01600 | S091A_S01600OD_CB_KGBERJAYA1 | Sabah | 7149P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN->Swap | 2024Q4 | HW | GTSB | 4.6 TSSR Approved |  | 2025-05-14 | 2025-05-21 |  | 2025-05-23 |  | Under Approval | 2025-05-26 | 2025-07-01 | E//Hannah | 2025-06-03 | SQ202505050115 - GTSB | DU00002864005 |  |  | 2025-06-30 | 2025-06-23 |  | Tower | TOWER | 60 | Add R8852E S9000x3+R8894E M1821x5, Dismantle | 0 | 23
S01688 | T3E_0228_ Kg Balat | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864006 | [6 empty] | TOWER
S01690 | T3E_0233_ Abai Island-River Island | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864007 | [6 empty] | TOWER
S01693 | Kg Timbang Dayang | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864008 | [6 empty] | TOWER
S01694 | Kg Pituru | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864009 | [6 empty] | TOWER
S01695 | Lasau Podi | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864010 | [6 empty] | TOWER
S01712 | T3E_0226_ Masang Estate | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864011 | [6 empty] | TOWER
S01713 | T3_0696_Kg Tronglit | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864012 | [6 empty] | TOWER
S01714 | T3_0694_Kg Tanjung Aru | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864013 | [6 empty] | TOWER
S01715 | T3_0694_S1_Kg Tanjung Batu Darat | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864014 | [6 empty] | MONOPOLE
S01716 | T3_0692_Kg Lubukan | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864015 | [6 empty] | TOWER
S01717 | T3_0692 S1_Kg Sg Madang | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864016 | [6 empty] | MONOPOLE
Q02075 | Q135A_Q02075OD_KOTASAMARAHAN | Sarawak |  | Decomm |  | 2024 Q2 | ZB | Magicell | 4.6 TSSR Approved |  | 2023-12-27 |  |  |  | 2023-12-18 |  | 2024-01-19 | 2024-02-15 | CD//John | 2024-01-20 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231231/Celcom Digi_RAN-Magicell-Standard PR TSS DECOMM-Sarawak-20231229/CelcomDigi_RAN_Magicell_TSS_Sarawak_20241018 | DU00002864017 |  |  |  |  | 2025-03-26 |  | TOWER
S01723 | Kg Rompon | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864018 | [6 empty] | TOWER
S01737 | Lok Lunuk | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864019 | [6 empty] | TOWER
S01739 | Kg Gonipis | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864020 | [6 empty] | TOWER
S01743 | T3E_0224_ SK Ran Luboh | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864021 | [6 empty] | TOWER
S01744 | Kg Rosok Rantai | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864022 | [6 empty] | TOWER
S01847 | T3_0827 - KG LONTONG | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864023 | [6 empty] | TOWER
S01848 | T3_0834 - KG ULU MANSOK | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864024 | [6 empty] | TOWER
S01850 | T3_0806 - KG KITOU (KG BOGIAN) | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864025 | [6 empty] | TOWER
S01853 | T3_0808 - KG LAMAS | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864026 | [6 empty] | TOWER
S01854 | T3_0793 - KG TIKOLOD | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864027 | [6 empty] | TOWER
S01857 | KG TG UPAK (KG TERUSAN BARU) | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864028 | [6 empty] | TOWER
S01858 | KG MUMIANG | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864029 | [6 empty] | TOWER
S01860 | Ladang Sukau | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864030 | [6 empty] | TOWER
S01861 | KG BAMBANGAN | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864031 | [6 empty] | TOWER
S01862 | FELCRA ESTET PERTAMA | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864032 | [6 empty] | TOWER
S01866 | T3_0082 - KG TUDAN | Sabah |  | MOCN Decomm | MOCN Decomm->On Hold->MOCN Decomm | 2024 Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864033 | [6 empty] | TOWER
2266A | Tmn Tropicana Bangi | Central |  | Modernization |  | 2024 Additional | SY1 | YPTT | 4.6 TSSR Approved |  | 2024-05-10 | 2024-05-14 |  | 2024-05-21 |  | Closed | 2024-05-23 | 2024-05-29 | E//Sumitra | 2024-05-29 | CelcomDigi_RAN_YPTT_TSS_Central_20240513 | DU00002864034 |  |  | 2024-06-22 | 2024-06-22 |  | Lampole | 25m Lampole | 25 | Add R9264H M901821 x3,Dismantle R8882 S1800(B) x3+R8854D S2100(A4A) x3 | 0 | 0
4778C | Taman Pengkalan Sentosa | Northern |  | Modernization |  | 2024 Q2 | ZA | YPTT | 4.6 TSSR Approved | ¦ 0307 - To ignore latest rejection as revise RRU model only, use previous approval as TSSR approval ¦ 0304 - Need revise TSSR due to 900 RRU model not available | 2024-01-29 | 2024-01-30 |  | 2024-02-05 |  | Closed | 2024-03-06 | 2024-02-27 | E//Hazida | 2024-02-27 | Celcom Digi_RAN-YPTT-TSS-Northern-20240202-0058 | DU00002864035 |  |  | 2024-03-12 | 2024-03-09 |  | Monopole | 30m Monopole | 30 | Add R8862A S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 3
1088C | Kampung Seri Puchong | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-06 | 2024-01-09 |  | 2024-04-24 |  | Closed | 2024-04-26 | 2024-04-29 | E//Sumitra | 2024-04-26 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240110 | DU00002864036 |  |  | 2024-06-29 | 2024-06-26 |  | In-Building System | 3m Boom (RT) | 6M | Add R8862A S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 3 | 0
1327C | Verve Suite | Central |  | Modernization |  | 2024 Q3 | XH | AllStar | 4.6 TSSR Approved |  | 2023-11-28 | 2023-12-01 |  | 2023-12-05 |  | Closed | 2023-12-12 | 2023-12-12 | E//Sumitra | 2023-12-12 | CelcomDigi_RAN_Allstar_TSS_Central_20231101 | DU00002864037 |  |  | 2024-04-07 | 2024-04-03 |  | Lampole | 18m Lampole | 18 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
7272C | Kampung Sungai | Sabah |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | AD | Datasco | 4.6 TSSR Approved |  | 2024-05-28 | 2024-05-30 |  | 2024-10-21 |  | Under Approval | 2024-10-24 | 2024-10-25 | E//Hannah | 2024-10-25 | 0920CD-Sabah-Datasco-BOQ Template (old contract) | DU00002864038 |  |  | 2024-11-20 | 2024-11-18 |  | Lampole | 30m Lampole | 30 | Add R8862A S9000x3+A9732 M1821x2, Dismantle R8854 S2600(A4A)x1+R9224E M1821(AAB)x3 | 23 | 0
9111C | Taman Samarindah 2 | Sarawak |  | Modernization |  | 2024 Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-10-19 | 2023-10-30 |  | 2024-01-09 |  | Closed | 2024-03-01 | 2024-03-04 | E//Hannah | 2024-03-04 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231019 | DU00002864039 |  |  | 2024-06-13 | 2024-06-07 |  | Lampole | 30m Rapole | 30M | Add R8862A S9000 x3+A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123 | 0
1741B | Jalan Ikan Emas KL | Central |  | Modernization |  | 2024 Q3 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-10-23 | 2023-10-30 |  | 2024-03-25 |  | Closed | 2024-03-29 | 2024-04-15 | E//Sumitra | 2024-04-09 | CelcomDigi_RAN_CCSMY_TSS_Central_20231025 | DU00002864040 |  |  | 2024-05-11 | 2024-05-09 |  |  | 18m Lampole | 18m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
1439C | Taman Semenyih Sentral | Central |  | Modernization |  | 2024 Additional | MA | CCSMY | 4.6 TSSR Approved |  | 2023-10-23 | 2023-10-31 |  | 2024-05-09 |  | Closed | 2024-05-17 | 2024-05-27 | E//Sumitra | 2024-05-27 | CelcomDigi_RAN_CCSMY_TSS_Central_20231214 | DU00002864041 |  |  | 2024-06-22 | 2024-06-12 |  |  | 24m Lampole | 24 | Add R9264H M901821 x4,Dismantle R8894E M1821(A8A) x4 | 0 | 0
3235C | Jalan Kuchai 3 | Central |  | Modernization |  | 2024 Q3 | SS | AllStar | 4.6 TSSR Approved |  | 2023-12-01 | 2023-12-05 |  | 2023-12-13 |  | Closed | 2024-02-05 | 2024-02-06 | E//Sumitra | 2024-02-06 | CelcomDigi_RAN_Allstar_TSS_Central_20231203 | DU00002864042 |  |  | 2024-04-04 | 2024-04-02 |  |  | 18m Lampole | 18 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
3740B | Sri Desa Entrepreneurs Park | Central |  | Modernization |  | 2024 Q3 | CR | GCI | 4.6 TSSR Approved |  | 2024-04-22 | 2024-05-08 |  | 2024-05-09 |  | Under Approval | 2024-05-10 | 2024-06-26 | E//Sumitra | 2024-06-26 | CelcomDigi_RAN_GCI_TSS_Central_20240513 | DU00002864043 |  |  | 2024-05-25 | 2024-05-23 |  | Monopole | 18m Lampole | 18 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
3403B | Syabas Balakong | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-10-23 | 2023-10-25 |  | 2024-04-26 |  | Closed | 2024-05-06 | 2024-05-15 | E//Sumitra | 2024-05-15 | CelcomDigi_RAN_GTSB_TSS_Central_20231201 | DU00002864044 |  |  | 2024-06-27 | 2024-06-26 |  | Tower | 45m Tower | 45m | Add R8862A S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R8862A S2601(A6A) x1 | 0 | 2
1205C | Taman Paramount | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-12-05 | 2023-12-15 |  | 2024-03-30 |  | Closed | 2024-04-05 | 2024-04-05 | E//Kok Keen | 2024-04-05 | CelcomDigi_RAN_GTSB_TSS_Central_20231208 | DU00002864045 |  |  | 2024-11-15 | 2024-11-11 |  | Minimast | 6m RT (Minimast) | 6m | Add R9264H M901821 x4,Dismantle R8862A S1800(B6A) x4+R8862A S2100(A6A) x4 | 0 | 0
1165C | Jalan Kerinchi | Central |  | Modernization |  | 2024 Q2 | MA | Ascentrack | 4.6 TSSR Approved | 0403 Proceed proposal install 3 RRU on top, 3 RRU in cabinet// 29/01 RRU propose inside cabinet,3 RRU on top, have temperature alarm from technical team | 2023-12-12 | 2023-12-14 |  | 2024-01-05 |  | Closed | 2024-01-08 | 2024-01-11 | E//Kok Keen | 2024-01-11 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231213 | DU00002864046 |  |  | 2024-05-07 | 2024-04-30 |  | Lampole | 18m Lampole | 18m | Add R9264H M901821 x3,Dismantle R8892N M1821(BAB) x3
1006B | Bdr Damai Perdana | Central |  | Modernization |  | 2024 Q4 | MA | Solusi | 4.6 TSSR Approved |  | 2024-01-09 | 2024-01-18 |  | 2024-05-21 |  | Closed | 2024-12-10 | 2024-12-10 | E//Sumitra | 2024-12-10 | BOQ CelcomDigi_RAN_Solusi_Standard PR TSS_Central_20240117 | DU00002864047 |  |  | 2024-07-22 | 2024-07-16 |  | In-Building System | 6m RT (Wall Mounted Pole) | 3 | Add R8894E M1821 x1+R8854 S2600 x2,Dismantle R8882 S2600(B4A) x2+R8862A S2601(A6A) x1 | 0 | 12
Q00695 | Q118B_Q00695OD_CB_SGSELIDAP | Sarawak |  | MOCN By Other Vendor | Maintain USP MOCN->On Hold->Maintain USP MOCN->On Hold->MOCN By Other Vendor | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864048 | [6 empty] | TOWER
1043B | Tmn Mulia Jaya(Maxis) | Central |  | Modernization |  | 2024 Q4 | BY | GTSB | 4.6 TSSR Approved |  | 2023-11-25 | 2023-12-01 |  | 2024-05-15 |  | Closed | 2024-05-21 | 2024-05-29 | E//Sumitra | 2024-05-29 | CelcomDigi_RAN_GTSB_TSS_Central_20231126 | DU00002864049 |  |  | 2024-08-24 | 2024-08-24 |  | Tower | 45m 3 Legged Tower | 46m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
A00541 | A042D_A00541OD_CB_TEMERLOK_RDD | Northern | 4182P | Swap | Swap->On Hold->Maintain USP MOCN->Swap | 2024 Q2 | HW | YPTT | 4.6 TSSR Approved |  | 2024-01-29 | 2024-03-01 |  | 2025-04-11 |  | Under Approval | 2025-04-24 | 2025-04-26 | CD//Zulakmar | 2025-04-25 | SQ202409030695/SQ202504220440 | DU00002864050 | Remarks: Solution TSSR/BOM Changed |  | 2025-07-06 | 2025-05-03 |  | Tower | TOWER | 60 | Add R8852E S9000x4+R8854E S1800x4+R8894E M1821x4+A9732 M1821x1,Dismantle | 3 | 1
A00198 | A042D_A00198OD_CB_PDGGAJAH_RDD | Northern | 4130P | Swap | Swap->On Hold->Swap | 2024 Q2 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-12-29 | 2024-01-02 |  | 2025-02-19 |  | Under Approval | 2024-01-15 | 2025-05-19 | E//Hazida | 2025-05-13 | Celcom Digi_RAN-CCSMY-TSS-Northern-20240101-0083 | DU00002864051 |  |  | 2025-05-28 | 2025-05-17 |  | Tower | TOWER | 63m | Add R8852E S9000x3+R8854E S1800x3+R8894E M1821x4, Dismantle | 0 | 2
Q00518 | Q136A_Q00518OD_CB_PKNROBAN | Sarawak | 9158P | Swap | Maintain USP MOCN->On Hold->Swap | 2025 Q3 | HW | Trintel | 4.6 TSSR Approved |  | 2025-02-05 | 2025-02-05 |  | 2025-04-09 |  | Under Approval | 2025-04-10 | 2025-05-19 | CD//John | 2025-04-23 | SQ202501070293-Trintel | DU00002864052 |  |  | 2025-09-22 | 2025-09-19 |  | Tower | TOWER | 75 | Add R8852E S9000x3+R8854E S1800x3+R9264M M1821x4, Dismantle | 0 | 3
Q00575 | Q143A_Q00575OD_CB_MELUGU | Sarawak | 9255P | Swap | Maintain USP MOCN->On Hold->Swap | 2025 Q3 | AI | Trintel | 4.6 TSSR Approved |  | 2025-02-05 | 2025-02-05 |  | 2025-03-20 |  | Closed | 2025-03-25 | 2025-05-19 | CD//John | 2025-03-25 | SQ202501070293-Trintel | DU00002864053 |  |  | 2025-07-06 | 2025-06-09 |  | Tower | TOWER | 76 | Add R8852E S9000x3+R8854E S1800x3+R9264M M1821x4, Dismantle | 0 | 2
Q00118 | Q143A_Q00118OD_CB_BAYAI | Sarawak |  | MOCN By Other Vendor | Maintain USP MOCN->On Hold->Maintain USP MOCN->On Hold->MOCN By Other Vendor | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864054 | [6 empty] | TOWER
Q00502 | Q129A_Q00502OD_CB_MERADONGPASI | Sarawak |  | MOCN By Other Vendor | Maintain USP MOCN->On Hold->Maintain USP MOCN->On Hold->MOCN By Other Vendor | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864055 | [6 empty] | TOWER
Q00519 | Q127A_Q00519OD_CB_PKNLUBOKANTU | Sarawak | 9232P | Swap | Maintain USP MOCN->On Hold->Swap | 2025 Q3 | AI | Trintel | 4.6 TSSR Approved |  | 2025-02-05 | 2025-03-14 |  | 2025-04-15 |  | Under Approval | 2025-04-15 | 2025-05-19 | CD//John | 2025-04-16 | SQ202501070293-Trintel | DU00002864056 |  |  | 2025-09-19 | 2025-09-17 |  | Tower | TOWER | 86 | Add R8852E S9000x3+R8854E S1800x3+R9264M M1821x4+R8862A S2601x4, Dismantle | 0 | 2
1175A | Desakiara | Central |  | Modernization |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-04-03 | 2024-05-03 |  | 2024-05-07 |  | Closed | 2024-05-08 | 2024-05-08 | E//Kok Keen | 2024-05-08 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_202400403 | DU00002864057 |  |  | 2024-07-23 | 2024-07-18 |  | Pole | 3m Boom (RT) | 7 | Add R8894E M1821 x2+R8854 S2600 x2,Dismantle R8882-L268 x2 | 0 | 12
Q01078 | Q143A_Q01078OD_CB_PKNLACHAU | Sarawak | 9257P | Swap | Maintain USP MOCN->On Hold->Swap | 2025 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2025-03-11 | 2025-07-16 |  | 2025-07-21 |  | Under Approval | 2025-07-26 | 2025-09-20 | E//John | 2025-07-28 | SQ202502190399-YPTT | DU00002864058 |  |  | 2025-09-19 | 2025-09-17 |  |  | TOWER | 76 | Add R8852E S9000x3+R8854E S1800x3+R8894E M1821x3, Dismantle | 0 | 0
Q00969 | Q117A_Q00969OD_CB_KGTRISO | Sarawak | 9258P | Swap | Maintain USP MOCN->On Hold->Swap | 2025 Q3 | HW | Trintel | 4.6 TSSR Approved |  | 2025-03-19 | 2025-04-06 |  | 2025-04-11 |  | Under Approval | 2025-04-15 | 2025-04-24 | CD//John | 2025-04-16 | SQ202501070293-Trintel | DU00002864059 |  |  | 2025-07-06 | 2025-06-28 |  |  | TOWER | 76 | Add R8862A S9000x3+R8854E S1800x3+R8894E M1821x3, Dismantle | 0 | 0
Q01170 | Q140C_Q01170OD_T3_JLNDURINKIBA | Sarawak |  | MOCN By Other Vendor | Maintain USP MOCN->On Hold->Maintain USP MOCN->On Hold->MOCN By Other Vendor | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864060 | [6 empty] | TOWER
Q00991 | Q143A_Q00991OD_CB_T3SGBESAIASAL | Sarawak | 9456P | Swap | Maintain USP MOCN->On Hold->Maintain USP MOCN->On Hold->Swap | 2025 | AD | Trintel | 4.6 TSSR Approved | 8/8- 9/8 team go in // 5/8- Wk33 plan | 2025-08-11 | 2025-08-26 |  | 2025-09-02 |  | Under Approval | 2025-09-19 | 2025-09-26 | E//John | 2025-09-19 | SQ202508110312-Trintel | DU00002864061 |  |  | 2025-09-26 | 2025-09-25 |  | Tower | TOWER | 60 | Add R8852E S9000x3+R8894E M1821x6, Dismantle | 0 | 0
1196A | JBA Puchong | Central |  | Modernization |  | 2024 Q3 | SH | DATASCO | 4.6 TSSR Approved |  | 2023-11-18 | 2023-11-27 |  | 2024-04-26 |  | Closed | 2024-05-03 | 2024-05-14 | E//Sumitra | 2024-05-14 | CelcomDigi_RAN_Datasco_TSS_Central_20231214 | DU00002864062 |  |  | 2024-07-11 | 2024-06-14 |  | Tower | Tower | 30 | Add R8894E M1821 x1,Dismantle | 0 | 1
Q00997 | Q143A_Q00997OD_CB_KGBAKONG | Sarawak | 9259P | Swap | Maintain USP MOCN->On Hold->Swap | 2025 Q3 | AI | Trintel | 4.6 TSSR Approved |  | 2025-02-05 | 2025-02-05 |  | 2025-02-24 |  | Under Approval | 2025-03-24 | 2025-04-28 | CD//John | 2025-03-25 | SQ202501070293-Trintel | DU00002864063 |  |  | 2025-06-07 | 2025-04-22 |  | Tower | TOWER | 76 | Add R8852E S9000x3+R8862A S1800x3+R8894E M1821x3, Dismantle | 0 | 0
Q00119 | Q143A_Q00119OD_CB_SANKEMANTAN | Sarawak |  | MOCN By Other Vendor | Maintain USP MOCN->On Hold->Maintain USP MOCN->On Hold->MOCN By Other Vendor | 2025 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864064 | [6 empty] | TOWER
Q01187 | Q136A_Q01187OD_T3_NGBUDU | Sarawak |  | MOCN By Other Vendor | Maintain USP MOCN->On Hold->Maintain USP MOCN->On Hold->MOCN By Other Vendor | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864065 | [6 empty] | TOWER
Q01185 | Q136A_Q01185OD_T3_WONGBESI | Sarawak |  | MOCN By Other Vendor | Maintain USP MOCN->On Hold->Maintain USP MOCN->On Hold->MOCN By Other Vendor | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864066 | [6 empty] | TOWER
Q02096 | Q143A_Q02096OD_CB_TMBKTBEGUNAN | Sarawak |  | MOCN By Other Vendor | Maintain USP MOCN->On Hold->Maintain USP MOCN->On Hold->MOCN By Other Vendor | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864067 | [6 empty] | TOWER
9702A | Bintangkor Trunk | Sarawak |  | MOCN As-Is | MOCN As-Is->On Hold->MOCN As-Is | 2025 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864068 | [6 empty] | Tower
9152Z | Sungai Babang (old - Rumah Sabai Nanga Derau) | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864069 | [6 empty] | #N/A
1243A | Pinescondo | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q2 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002864070 | [6 empty] | 6m RT (Boom) |  |  | 24
9001R | Luban Ulu | Sarawak |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2025 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864071 | [6 empty] | #N/A
7030R | Kg Sinua Sook | Sabah |  | Maintain USP MOCN | Maintain USP MOCN->On Hold->Maintain USP MOCN | 2024Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864072 | [6 empty] | #N/A
1271B | Mahkota Cheras S7 | Central |  | Modernization |  | 2024 Q4 | AI | YPTT | 4.6 TSSR Approved |  | 2024-04-25 | 2024-05-14 |  | 2024-05-21 |  | Closed | 2024-05-21 | 2024-05-27 | E//Sumitra | 2024-05-27 | CelcomDigi_RAN_YPTT_TSS_Central_20240513 | DU00002864073 |  |  | 2024-06-19 | 2024-06-17 |  | In-Building System | 3m Bipod (RT) | 4 | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 | 0 | 0
4098R | 4240_SungaiBaru_SBRUM1_1 | Northern |  | Maintain USP MOCN(Dismantle Passive) | Maintain USP MOCN(Dismantle Passive)->On Hold->Maintain USP MOCN(Dismantle Passive) | 2024 Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2025-10-02 |  | 2026-03-26 |  | 2025-12-22 | To be Submitted | 2026-01-23 | 2026-04-17 |  | 2026-01-26 | SQ202504230446-GTSB | DU00002864074 |  |  |  |  | 2025-11-25
1278B | Jln Tenteram Cheras | Central |  | Modernization |  | 2024 Q3 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-10-25 | 2023-10-30 |  | 2024-03-22 |  | Closed | 2024-03-26 | 2024-04-04 | E//Sumitra | 2024-04-04 | CelcomDigi_RAN_CCSMY_TSS_Central_20231028 | DU00002864075 |  |  | 2024-06-23 | 2024-06-21 |  | In-Building System | 3m Bipod (RT) | 6 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3 | 0 | 0
1281B | Market Maluri | Central |  | Modernization |  | 2024 Q2 | MS | GTSB | 4.6 TSSR Approved |  | 2023-12-14 | 2023-12-28 |  | 2024-01-23 |  | Closed | 2024-01-24 | 2024-02-06 | E//Kok Keen | 2024-02-06 | CelcomDigi_RAN_GTSB_TSS_Central_20231215 | DU00002864076 |  |  | 2024-06-22 | 2024-06-18 |  | Pole | 3m Bipod (RT) | 3 | Add R8894E M1821 x4,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8862A S2100(A6A) x4 |  | 2
7499B | Sungai Lokan | Sabah |  | Modernization |  | 2024 Q4 | MS | Seri Pancar | 4.6 TSSR Approved |  | 2024-08-01 | 2024-08-10 |  | 2024-08-15 |  | Closed | 2024-08-19 | 2024-08-21 | E//Hannah | 2024-08-21 | 0802CD-Sabah-Seri Pancar-BOQ Template(new contract) | DU00002864077 |  |  | 2024-09-10 | 2024-09-07 |  | Tower | 45m 3 Legged Tower | 76M | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle | 0 | 1
1317B | KG KERINCHI | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q2 |  |  | 14.2 Drop (Done Survey) | AAU Cannot Install-Change MM to BI¦NOK,S1 and S3 share the same boom,but the structure is weled,can not change.Suggest to change to bi-sector | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002864078 | BAU_S2_Change MM to BI_Space constraint_Digi OB | [5 empty] | 3m Bipod (RT) |  |  |  | 13
1326A | Eng Hoe Tong | Central |  | Modernization |  | 2024 Q3 | MA | DATASCO | 4.6 TSSR Approved |  | 2023-12-08 | 2023-12-15 |  | 2024-03-26 |  | Closed | 2024-03-26 | 2024-03-27 | E//Kok Keen | 2024-03-27 | CelcomDigi_RAN_Datasco_TSS_Central_20231224 | DU00002864079 |  |  | 2024-04-30 | 2024-04-25 |  | Minimast | 3m RT (Minimast) | 13 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1 | 0 | 0
1490A | SS23 B | Central |  | Modernization |  | 2024 Q3 | IE | Magicell | 4.6 TSSR Approved |  | 2023-11-16 | 2023-11-20 |  | 2024-03-22 |  | Closed | 2024-03-25 | 2024-03-26 | E//Kok Keen | 2024-03-26 | CelcomDigi_RAN_Magicell_TSS_Central_20231119 | DU00002864080 |  |  | 2024-05-18 | 2024-05-15 |  | BillBoard | 30m Monopole | 36M | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x2+R8840-U216 x3++ | 0 | 0
1158C | JALAN KUCHAI LAMA | Central |  | Modernization |  | 2024 Q3 | SS | Ascentrack | 4.6 TSSR Approved |  | 2023-12-11 | 2023-12-18 |  | 2023-12-30 |  | Closed | 2024-04-01 | 2024-07-02 | E//Sumitra | 2024-07-02 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231213 | DU00002864081 |  |  | 2024-05-21 | 2024-05-18 |  | Lampole | 18m Lampole | 18m | Add R9264H M901821 x3,Dismantle R8892N M1821(BAB) x3
1499A | Berjaya Golf | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-01 | 2023-11-08 |  | 2024-04-02 |  | Under Approval | 2024-04-02 | 2024-07-25 | E//Sumitra | 2024-07-25 | CelcomDigi_RAN_GTSB_TSS_Central_20231104 | DU00002864082 |  |  | 2024-08-09 | 2024-07-29 |  | In-Building System | 3m Bipod (RT) | 2 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x2+R8862A S2600(A4A) x2 | 0 | 0
7732B | Kg Seberang Sukau | Sabah |  | Modernization |  | 2024 Q4 | AD | NR services | 4.6 TSSR Approved |  | 2023-12-09 | 2023-12-19 |  | 2024-07-22 |  | Under Approval | 2024-07-30 | 2024-08-07 | E//Hannah | 2024-08-06 | Celcom Digi_RAN-NR Services-TSS-Sabah-20231212 | DU00002864083 |  |  | 2024-08-26 | 2024-08-19 |  | Tower | Tower | 76 | Reuse exsiting RRU | 0 | 0
1679B | Tmn Greenwood (REL) | Central |  | Modernization |  | 2024 Q1 | IE | Magicell | 4.6 TSSR Approved |  | 2023-11-17 | 2023-11-21 |  | 2024-01-03 |  | Closed | 2024-01-04 | 2024-01-05 | E//Kok Keen | 2024-01-04 | CelcomDigi_RAN_Magicell_TSS_Central_20231120 | DU00002864084 |  |  | 2024-01-18 | 2024-01-15 |  | Lampole | 20m Lampole | 22 | Add R9264H M901821 x3,Dismantle R9224E M1821(AAB) x3
1733A | Tmn Ampang Jaya | Central |  | Modernization |  | 2024 Q4 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-12-26 | 2024-02-16 |  | 2024-05-08 |  | Closed | 2024-05-13 | 2024-05-20 | E//Sumitra | 2024-05-20 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231227 | DU00002864085 |  |  | 2024-05-29 | 2024-05-29 |  | In-Building System | 3m Boom (RT) | 7 | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle R8882 S2600(B4A) x1 | 0 | 3
1737A | Bernama | Central |  | Modernization |  | 2024 Q1 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-12-18 | 2023-12-26 |  | 2024-01-08 |  | Closed | 2024-01-09 | 2024-01-11 | E//Sumitra | 2024-01-11 | CelcomDigi_RAN_CCSMY_TSS_Central_20231224 | DU00002864086 |  |  | 2024-05-29 | 2024-05-29 |  | Pole | 3m Bipod (RT) | 4m | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
1743A | Serdang Raya | Central |  | Modernization |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-11-10 | 2023-11-20 |  | 2024-04-22 |  | Closed | 2024-05-28 | 2024-06-04 | E//Sumitra | 2024-06-04 | CelcomDigi_RAN_Datasco_TSS_Central_20231214 | DU00002864087 |  |  | 2024-06-19 | 2024-06-18 |  | Minimast | 3m RT (Minimast) | 11 | Reuse exisiting RRU | 0 | 0
1775A | Kuvithiru Printers | Central |  | Modernization |  | 2024 Q4 | CR | Magicell | 4.6 TSSR Approved |  | 2023-12-29 | 2024-01-03 |  | 2024-05-09 |  | Closed | 2024-05-10 | 2024-05-16 | E//Sumitra | 2024-05-15 | CelcomDigi_RAN_Magicell_TSS_Central_20231230 | DU00002864088 |  |  | 2024-08-21 | 2024-08-14 |  | In-Building System | 3m Boom (RT) | 6 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x2+R8882 S1800(B) x1+R8862A S1800(B6A) x1+R8840-U216 x3 | 0 | 0
1831B | Taman Maju Kajang | Central |  | Modernization |  | 2024 Q4 | SM | GTSB | 4.6 TSSR Approved |  | 2024-01-12 | 2024-01-15 |  | 2024-05-15 |  | Closed | 2024-05-17 | 2024-05-29 | E//Sumitra | 2024-05-28 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240115 | DU00002864089 |  |  | 2024-09-12 | 2024-09-12 |  | In-Building System | 6m RT (Boom) | 6m | Add R9224E M1821 x1+R8854 S2600 x1,Dismantle R8882-L268 x1 | 0 | 2
1858B | Tmn Cuepacs Kajang | Central |  | Modernization |  | 2024 Q4 | SHA | YPTT | 4.6 TSSR Approved |  | 2023-10-23 | 2023-10-25 |  | 2024-06-10 |  | Under Approval | 2024-06-11 | 2024-09-20 | E//Sumitra | 2024-09-20 | CelcomDigi_RAN_YPTT_TSS_Central_20231224 | DU00002864090 |  |  | 2024-09-09 | 2024-09-06 |  | In-Building System | 3m Bipod (RT) | 4 | Add R9264M M1821 x2+R8862A S2601 x2+A9732 M1821 x1,Dismantle R8882-GUL1812 x3+R8862A S1800(B6A) x1+R8854D S2100(A4A) x4+R8882-L268 x3 | 1 | 0
3928B | Persiaran Puteri 1 | Central |  | Modernization |  | 2024 Q3 | CR | Magicell | 4.6 TSSR Approved |  | 2023-12-23 | 2024-01-09 |  | 2024-04-23 |  | Closed | 2024-04-28 | 2024-05-03 | E//Razif | 2024-05-03 | CelcomDigi_RAN_Magicell_TSS_Central_20231224 | DU00002864091 |  |  | 2024-06-27 | 2024-06-26 |  | Pole | 3m Boom (RT) | 6M | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
1967A | KAP Sport | Central |  | Modernization | Modernization->Remote MOCN | 2024 Q3 | AI | Solusi | 4.6 TSSR Approved |  | 2024-03-28 | 2024-02-09 |  | 2024-04-30 |  | Closed | 2024-11-07 | 2024-12-17 | E//Razif | 2024-12-17 | BOQ CelcomDigi_RAN_Solusi_Standard PR TSS_Central_20240329 | DU00002864092 |  |  | 2024-11-30 | 2024-11-18 |  | Minimast | 3m RT (Minimast) | 16 | Reuse exisiting RRU | 0 | 0
1985B | SS 26_26 LP (REL) | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-08-14 | 2024-08-26 |  | 2024-08-30 |  | Closed | 2024-10-22 | 2024-10-22 | E//Kok Keen | 2024-10-22 | 0809CD-Central-GTSB-BOQ Template(new contract) | DU00002864093 |  |  | 2024-11-24 | 2024-11-22 |  | Lampole | 22m Lampole | 20M | Add R8862A S9000x3+R8862A S2601x3, Dismantle R8882 S2600(B4A)x3 | 0 | 0
2029A | LDP Damansara TX REP | Central |  | Modernization |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-10-22 | 2023-11-21 |  | 2024-03-22 |  | Closed | 2024-03-25 | 2024-03-26 | E//Kok Keen | 2024-03-26 | CelcomDigi_RAN_Datasco_TSS_Central_20231023 | DU00002864094 |  |  | 2024-04-19 | 2024-04-16 |  | BillBoard | Billboard | 4 | Add R8894E M1821 x4,Dismantle R8862A S1800(B6A) x4+R8862A S2100(A6A) x4 | 0 | 3
2105A | UKM Pusanika | Central |  | Modernization |  | 2024 Additional | SY1 | YPTT | 4.6 TSSR Approved |  | 2024-05-10 | 2024-05-20 |  | 2024-05-27 |  | Closed | 2024-05-29 | 2024-06-06 | E//Sumitra | 2024-06-06 | CelcomDigi_RAN_YPTT_TSS_Central_20240513 | DU00002864095 |  |  | 2025-01-07 | 2025-01-06 |  | Lampole | 20m Lampole | 20 | Add R9264H M901821 x3,Dismantle R8882 S1800(B) x3++R8881 S2100 x3+ | 0 | 0
2112B | SS21 | Central |  | Modernization |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-10-21 | 2023-11-02 |  | 2023-11-20 |  | Closed | 2024-04-01 | 2024-04-01 | E//Kok Keen | 2024-04-01 | CelcomDigi_RAN_Datasco_TSS_Central_20231023 | DU00002864096 |  |  | 2024-04-25 | 2024-04-25 |  | H-bracket pole | 3m Boom (RT) | SECTOR 1 & 3(2.5m), SECTOR 2 (5m) | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3++ | 0 | 0
2119A | Elite KM | Central |  | Modernization |  | 2024 Q3 | AI | Magicell | 4.6 TSSR Approved |  | 2023-12-16 | 2023-12-21 |  | 2024-04-26 |  | Closed | 2024-04-26 | 2024-04-29 | E//Sumitra | 2024-04-26 | CelcomDigi_RAN_Magicell_TSS_Central_20231224 | DU00002864097 |  |  | 2024-08-17 | 2024-08-16 |  | BillBoard | 30m Monopole | 3m | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 3 | 0
2154A | Section14 (REL) | Central |  | Decomm | Modernization-Decomm | 2024 Q3 | CR | GTSB | 4.6 TSSR Approved |  | 2023-12-04 | 2023-12-05 |  | 2023-12-26 | 2024-09-02 | Closed | 2024-09-04 | 2024-04-05 | E//Kok Keen | 2024-09-04 | 0821CD-Central-GTSB-BOQ Template(new contract) | DU00002864098 |  | Please share the updated topology Please confirm if link 2787B-2154A is valid and still in active stage? As 2787B had connectivity with 2787B-6484A-6703A which is already dismantled. |  |  | 2024-12-06 | Unipole | 3m Bipod (RT) | 6m
2222A | Kampung Wira Jawa | Central |  | Modernization |  | 2024 Q1 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-08 | 2023-11-16 |  | 2024-01-07 |  | Under Approval | 2024-01-12 | 2024-01-16 | E//Kok Keen | 2024-01-15 | CelcomDigi_RAN_GTSB_TSS_Central_20231113 | DU00002864099 |  |  | 2024-02-26 | 2024-02-20 |  | Lampole | 20m Lampole | 31m | Add R9264M M1821 x3+R9264H M901821 x1,Dismantle R8882 S1800(B) x3+R8862A S1800(B6A) x1+R8854D S2100(A4A) x4
1399B | LDP Kelana Jaya | Central |  | Modernization |  | 2024 Q1 | AI | DATASCO | 4.6 TSSR Approved |  | 2023-10-24 | 2023-11-03 |  | 2024-01-04 |  | Closed | 2024-01-05 | 2024-01-05 | E//Kok Keen | 2024-01-05 | CelcomDigi_RAN_Datasco_TSS_Central_20231028 | DU00002864100 |  |  | 2024-01-17 | 2024-01-11 |  | Monopole | 30m Monopole | 24 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x3
7516B | Flat MPS karamunting | Sabah |  | Modernization |  | 2024 Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2024-03-15 | 2024-04-23 |  | 2024-04-29 |  | Closed | 2024-04-30 | 2024-05-13 | E//Hannah | 2024-05-13 | Celcom Digi_RAN-YPTT-TSS-Sabah-20240324 | DU00002864101 |  |  | 2024-06-23 | 2024-06-19 |  | Pole | Watertank Structure | 6 | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x3+R8894E M1821(A8A) x3+R9224E M1821(AAB) x3 | 123 | 0
4939A | Merbok | Northern |  | Modernization | Modernization | 2026 | HW | CCSMY | 4.6 TSSR Approved |  | 2025-01-15 | 2025-01-28 |  | 2025-02-21 |  | Under Approval | 2025-11-09 | 2025-12-29 | E//Hazida | 2025-11-13 | SQ202501030037 - CCSMY | DU00002864102 |  |  | 2026-04-23 | 2026-04-20 |  | Tower | 60m 3 Legged Tower | 65m | Add R8852E S9000x1+R8894E M1821x3, Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3
7457B | Kg Bahagia - Sandakan | Sabah |  | Modernization |  | 2024 Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2024-03-15 | 2024-05-13 |  | 2024-05-17 |  | Closed | 2024-05-23 | 2024-05-30 | E//Hannah | 2024-05-30 | Celcom Digi_RAN-YPTT-TSS-Sabah-20240324 | DU00002864103 |  |  | 2024-06-23 | 2024-06-18 |  | Monople Tree | 30m Monopole | 45 | Add A9732 M1821 x3,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x5 | 123 | 0
2387A | Seksyen 1 BK | Central |  | Modernization |  | 2024 Q3 | SH | GCI | 4.6 TSSR Approved |  | 2024-01-16 | 2024-01-19 |  | 2024-04-19 |  | Closed | 2024-05-02 | 2024-05-10 | E//Sumitra | 2024-05-09 | CelcomDigi_RAN_GCI_TSS_Central_20240124 | DU00002864104 |  |  | 2024-06-16 | 2024-06-14 |  | Lampole | 30m Lampole | 30 | Add R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882-GUL1812 x2+R8882 S1800B(B6B) x1+R8882 S2600(B4A) x1+R8892E M1821 x1 | 0 | 1
1565B7 | pBTS Beverly Hills (C ) | Sabah |  | Modernization | Modernization->On Hold->Modernization | 2024 Q3 | AD | Seri Pancar | 14.0 TSSR Not Required (Reuse Existing BBU/RRU) | AAU Cannot Install-Change MM to BI¦pBTS loading issue,AAU cannot install | 2023-10-24 | 2023-10-30 |  | 2023-11-03 |  | Under Approval |  |  |  |  | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231028 | DU00002864105 |  |  | 2025-06-21 | 2025-06-18 |  | Tower | 25m pBTS | 24M | Reuse Existing RRU | 0 | 0
2420A | Kg Sg Serai (Maxis) | Central |  | Modernization |  | 2024 Additional | SY1 | GCI | 4.6 TSSR Approved |  | 2024-01-16 | 2024-01-16 |  | 2024-05-13 |  | Closed | 2024-05-16 | 2024-05-23 | E//Sumitra | 2024-05-23 | CelcomDigi_RAN_GCI_TSS_Central_20240124 | DU00002864106 |  |  | 2025-03-09 | 2025-03-06 |  | Tower | 60m 3 Legged Tower | 60 | Add R9264H M901821 x3,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x2 | 0 | 0
2501A | Sg Buah Dengkil (Maxis) | Central |  | Modernization |  | 2024 Additional | BY | GTSB | 4.6 TSSR Approved |  | 2024-01-19 | 2024-01-30 |  | 2024-05-10 |  | Closed | 2024-05-15 | 2024-05-24 | E//Razif | 2024-05-24 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240128 | DU00002864107 |  |  | 2025-03-19 | 2025-03-11 |  | Tower | 60m 4 Legged Tower | 61m | Add R8852E S9000 x3+R8894E M1821 x3+R8862A S2601x3,Dismantle R8882-GUL1812 x3+R8882 S2600(B4A) x3+R8840-U216 x3 | 0 | 0
2508A | Puchong Jaya LP (REL) | Central |  | Modernization |  | 2024 Q3 | MA | Magicell | 4.6 TSSR Approved |  | 2023-12-14 | 2023-12-20 |  | 2024-04-19 |  | Closed | 2024-05-06 | 2024-07-11 | E//Sumitra | 2024-07-11 | CelcomDigi_RAN_Magicell_TSS_Central_20231215 | DU00002864108 |  |  | 2024-06-15 | 2024-06-12 |  | Monopole | 30m Monopole | 20 | Add R9224E M1821 x1+R8854 S2600 x1,Dismantle R8862A S2601(A6A) x1 | 0 | 1
4395A | Parit Buntar Town | Northern |  | Modernization |  | 2024 Additional | SM | CCSMY | 4.6 TSSR Approved |  | 2023-10-18 | 2023-10-20 |  | 2024-11-28 |  | Rectificating | 2024-12-23 | 2024-12-24 | E//Hazida | 2024-12-23 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231018-0057 | DU00002864109 | Remarks: Solution TSSR/BOM Changed |  | 2024-12-06 | 2024-12-06 |  | Tower | 45m 3 Legged Tower | 49m | Add A9732 M1821 x1 | 2 | 3
4729B | IKBM Jitra | Northern |  | Modernization |  | 2024 Q3 | SM | GTSB | 4.6 TSSR Approved |  | 2023-10-10 | 2023-10-18 |  | 2024-03-25 |  | Closed | 2024-04-01 | 2024-04-04 | E//Hazida | 2024-04-04 | Celcom Digi_RAN-GTSB-TSS-Northern-20231011-0046 | DU00002864110 |  |  | 2024-04-18 | 2024-04-12 |  |  | 60m 4 Legged Tower | 60m | Add R8852E S9000 x3+R8894E M1821 x3+R8854 S2600 x3,Dismantle | 0 | 123
7031B | Kg Tanjong Kapor | Sabah |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | AD | YPTT | 4.6 TSSR Approved |  | 2023-11-03 | 2023-11-15 |  | 2024-11-01 |  | Under Approval | 2024-11-04 | 2024-11-11 | E//Hannah | 2024-11-07 | Celcom Digi_RAN-YPTT-Standard PR TSS-Sabah-20240813 | DU00002864111 |  |  | 2024-12-13 | 2024-12-06 |  | Monopole | 24m Lampole | 30 | Add R8862A S9000x4+A9732 M1821 x3, Dismantle R8854 S2600(A4A)x3+R8894E M1821(A8A)x6 | 124 | 0
2742A | Tmn Megah Cheras (Maxis) | Central |  | Modernization |  | 2024 Q4 | BY | GCI | 4.6 TSSR Approved |  | 2024-04-15 | 2024-04-21 |  | 2024-05-22 |  | Closed | 2024-05-28 | 2024-06-04 |  | 2024-06-04 | CelcomDigi_RAN_GCI_TSS_Central_20240513 | DU00002864112 |  |  | 2024-09-28 | 2024-09-23 |  | Monopole | 36m Monopole | 36 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
2394A | SS 4 | Central |  | Modernization |  | 2024 Q1 | AI | DATASCO | 4.6 TSSR Approved |  | 2023-10-27 | 2023-11-10 |  | 2024-01-02 |  | Closed | 2024-01-03 | 2024-01-04 | E//Kok Keen | 2024-01-03 | CelcomDigi_RAN_Datasco_TSS_Central_20231028 | DU00002864113 |  |  | 2024-04-03 | 2024-04-01 |  | In-Building System | 3m Bipod (RT) | 3 | Add R9264M M1821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3
2939B | Giant Tmn Connaught | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002864114 | [6 empty] | In-building system |  |  | 1
3050A | Wisma Mutiara Genting (REL) | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q1 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002864115 | [6 empty] | 25m pBTS |  |  | 12
2673A3 | pBTS Omron | Central |  | Site Out (Modernization) | Modernization->On Hold->Modernization->On Hold->Modernization->Site Out->Site Out (Modernization) | 2024 Q1 | SY1 | CCSMY | 4.6 TSSR Approved |  | 2024-07-19 | 2024-07-23 |  | 2024-07-26 |  | Closed | 2024-11-11 | 2025-10-17 | E//Kok Keen | 2024-07-31 | 0725Central-CCSMY-BOQ Template(new contract) | DU00002864116 | Remarks: Solution TSSR/BOM Changed |  |  |  |  | Tower | 25m pBTS | 25m | Add R8894E M1821 x3+R8862A S2601 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3+R8882 S2600(B4A) x3 | 0 | 0
4553B | Rapat Jaya | Northern |  | Modernization |  | 2024 Q2 | WP | GCI | 4.6 TSSR Approved |  | 2023-10-26 | 2023-10-30 |  | 2023-11-02 |  | Closed | 2024-01-26 | 2024-01-30 |  | 2024-01-10 | Celcom Digi_RAN-GCI-TSS-Northern-20231028-0067 | DU00002864117 |  |  | 2024-02-21 | 2024-02-15 |  | Monopole | 30m Monopole | 30 | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 1
2960A | TAR COLLEGE SETAPAK CAMPUS | Central |  | Site Out (Modernization) | Modernization->On hold->Site out->Replacement, Site Out (Modernization) | 2024 Q1 | AI | GTSB | 15.3 Decomm Done without TSSR |  | 2025-07-15 |  |  |  |  | To be Submitted |  |  |  |  | SQ202506170074 | DU00002864118 |  |  |  |  | 2025-08-05 |  | 6m RT (Boom)
3409A | Paradigm RT | Central |  | Modernization |  | 2024 Q1 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-03-22 | 2024-03-22 |  | 2024-03-26 |  | Closed | 2024-03-27 | 2024-04-01 | E//Kok Keen | 2024-03-27 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240202 | DU00002864119 |  |  | 2024-04-30 | 2024-04-15 |  | In-Building System | 3m Bipod (RT) | 6M | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle R8882 S2600(B4A) x1 |  | 3
4270B | Felcra Lubuk Sireh | Northern |  | Modernization |  | 2025 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2023-11-21 | 2023-11-22 |  | 2025-02-18 |  | Under Approval | 2025-04-11 | 2025-05-27 | E//Hazida | 2025-06-09 | Celcom Digi_RAN-GTSB-TSS-Northern-20231122-0067 | DU00002864120 |  | Require TSSR Revision, Solution Changed | 2025-06-15 | 2024-06-24 |  | Tower | Tower | 60 | Add R8862A S9000x1+R8894E M1821x4+R8854 S2600x1,Dismantle R8862A S1800(B6A)x3+R8854D S2100(A4A)x3+R8862A S2601(A6A)x1 | 0 | 1
4281B | Felcra Weng | Northern |  | Modernization | Modernization->On Hold->Modernization | 131 single site mocn | AD | GTSB | 4.6 TSSR Approved |  | 2023-11-29 | 2023-10-26 |  | 2024-08-22 |  | Under Approval | 2024-09-12 | 2024-09-19 | E//Hazida | 2024-09-19 | Celcom Digi_RAN-GTSB-TSS-Northern-20240513-0108 | DU00002864121 |  |  | 2024-11-28 | 2024-11-01 |  | Tower | Tower | 60m | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle | 0 | 2
4394A | Tmn Sri Semarak | Northern |  | Modernization |  | 2024 Additional | SM | GTSB | 4.6 TSSR Approved |  | 2023-10-10 | 2023-10-13 |  | 2024-11-22 |  | Rectificating | 2024-11-25 | 2024-12-16 | E//Hazida | 2024-12-16 | Celcom Digi_RAN-GTSB-TSS-Northern-20231011-0046 | DU00002864122 |  |  | 2024-12-05 | 2024-12-01 |  | Tower | 60m 3 Legged Tower | 50 | Add R8852E S9000 x3+R8894E M1821x2, Dismantle R8860E-GU908x1+ | 0 | 23
4397A | Bagan Serai Town | Northern |  | Modernization | Modernization | 2026 | HW | CCSMY | 4.6 TSSR Approved |  | 2023-10-23 | 2023-10-26 |  | 2025-04-16 |  | Under Approval | 2025-11-09 | 2025-12-08 | E//Hazida | 2025-11-13 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231025-0061 | DU00002864123 |  |  | 2025-11-20 | 2025-11-20 |  | In-Building System | 6m RT (Boom) | 7 | Add R8852E S9000x3+R9264M M1821x3, Dismantle R8882-GUL1812x3R8862A S2100(A6A)x3
4417A | Kg Batu 12 | Northern |  | Modernization |  | 2027 |  | CCSMY | 4.4 Pending TSSR Review - Design Team |  | 2025-01-22 | 2025-02-04 |  | 2025-03-04 |  | Under Approval |  |  |  |  | SQ202501030037 - CCSMY | DU00002864124 | [5 empty] | Tower | 60m 3 Legged Tower | 60M | Add R8852E S9000x2+R8894E M1821x2, Dismantle R8882-GUL1812x1R8862A S1800(B6A)x1R8862A S2100(A6A)x2 | 0 | 0
4429A | Lake Town (Maxis) | Northern |  | Modernization |  | 2027 |  | GCI | 4.4 Pending TSSR Review - Design Team |  | 2023-10-10 | 2023-10-17 |  | 2023-10-24 |  | Under Approval |  |  |  |  | Celcom Digi_RAN-GCI-TSS-Northern-20231012-0057 | DU00002864125 | [5 empty] | Tower | 60m 4 Legged Tower | 61
4459A | Pokok Assam | Northern |  | Modernization |  | 2024 Q2 | BY | YPTT | 4.6 TSSR Approved |  | 2023-12-19 | 2023-12-27 |  | 2024-01-07 |  | Closed | 2024-01-09 | 2024-01-11 |  | 2024-01-09 | Celcom Digi_RAN-YPTT-TSS-Northern-20231225-0047 | DU00002864126 |  |  | 2024-04-08 | 2024-04-01 |  | In-Building System | 6m RT (Boom) | 5 | Add R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882-GUL1812 x3+R8862A S2600(A4A) x1+R8840-U216 x3++ |  | 2
4494B | Taman Rishah | Northern |  | Modernization |  | 2024 Q2 | BY | GCI | 4.6 TSSR Approved |  | 2023-10-17 | 2023-10-26 |  | 2024-01-09 |  | Closed | 2024-01-10 | 2024-01-15 | E//Ajay | 2024-01-12 | Celcom Digi_RAN-GCI-TSS-Northern-20231019-0062 | DU00002864127 |  |  | 2024-01-31 | 2024-01-26 |  |  | 6m RT (Boom) | 25 | Add R8894E M1821 x3,Dismantle R8882-GUL1812 x1+R8882 S1800(B) x1+R8862A S1800(B6A) x1+R8840-U216 x3++
4511A | Jln Lahat Shoplot | Northern |  | Modernization |  | 2024 Q2 |  | GCI | 4.6 TSSR Approved |  | 2023-10-18 | 2023-10-30 |  | 2024-01-09 |  | Closed | 2024-01-10 | 2024-01-12 | E//Hazida | 2024-01-12 | Celcom Digi_RAN-GCI-TSS-Northern-20231020-0063 | DU00002864128 |  |  | 2024-01-29 | 2024-01-26 |  | In-Building System | 3m Boom (RT) | 6 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8840-U216 x3++
4511B | Medan Pengkalan | Northern |  | Modernization |  | 2024 Q2 | SM | GCI | 4.6 TSSR Approved |  | 2023-10-09 | 2023-10-17 |  | 2024-01-08 |  | Rectificating | 2024-01-09 | 2024-01-11 |  | 2024-01-09 | Celcom Digi_RAN-GCI-TSS-Northern-2023111-0057 | DU00002864129 |  |  | 2024-01-18 | 2024-01-15 |  | In-Building System | 6m RT (Boom) | 6 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x3
4530A | Tmn Melor Shoplot | Northern |  | Modernization |  | 2024 Q2 | BY | GCI | 4.6 TSSR Approved |  | 2023-10-09 | 2023-10-16 |  | 2024-01-09 |  | Closed | 2024-01-10 | 2024-01-15 | E//Hazida | 2024-01-12 | Celcom Digi_RAN-GCI-TSS-Northern-2023111-0057 | DU00002864130 |  |  | 2024-01-22 | 2024-01-12 |  | Minimast | 6m RT (Boom) | 6.8,4.8 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882-GUL1812 x1+R8862A S1800(B6A) x2+R8840-U216 x3
4534A | Pasir Putih Shoplot | Northern |  | Modernization |  | 2024 Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2023-10-11 | 2023-10-16 |  | 2024-01-08 |  | Rectificating | 2024-01-09 | 2024-01-11 |  | 2024-01-10 | Celcom Digi_RAN-GTSB-TSS-Northern-20231012-0047 | DU00002864131 |  |  | 2024-02-27 | 2024-01-13 |  | In-Building System | 6m RT (Boom) | 8M | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle R8862A S2600(A4A) x1 |  | 3
4550A | Pengkalen Barat | Northern |  | Modernization |  | 2024 Q2 | BY | YPTT | 4.6 TSSR Approved |  | 2023-12-19 | 2023-12-29 |  | 2024-01-09 |  | Closed | 2024-01-11 | 2024-01-22 | E//Ajay | 2024-01-19 | Celcom Digi_RAN-YPTT-TSS-Northern-20231225-0047 | DU00002864132 |  |  | 2024-02-22 | 2024-02-17 |  | In-Building System | 6.5m RT (Boom) | 7m | Add R8862A S9000 x3+R8894E M1821 x1+R8854 S2600 x1,Dismantle R8862A S2600(A4A) x1 |  | 3
4599C | Jalan Raja Musa Mahadi RT | Northern |  | Modernization |  | 2024 Q2 | WP | CCSMY | 4.6 TSSR Approved | ¦ 0202 - Revised TSSR submitted ¦ 0112 - Rejctedted, Pending revision under HQ | 2023-10-20 | 2023-10-25 |  | 2024-01-09 |  | Closed | 2024-01-10 | 2024-02-06 | E//Hazida | 2024-02-05 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231022-0060 | DU00002864133 |  |  | 2024-03-03 | 2024-02-06 |  | Tower | 30m Minaret | 30m | Add R8862A S9000 x3+A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123
4589B | Simpang Tiga Selekoh | Northern |  | Modernization |  | 2024 Additional | SM | CCSMY | 4.6 TSSR Approved |  | 2024-12-11 | 2024-12-19 |  | 2025-01-02 |  | Rectificating | 2025-01-03 | 2025-01-14 | E//Hazida | 2025-01-14 | SQ202411290550 - CCSMY | DU00002864134 |  |  | 2025-01-13 | 2025-01-13 |  | Tower | 60m 3 Legged Tower | 60M | Add R8852E S9000 x3+R8894E M1821x4+R8854 S2600 x1,Dismantle R8882-GUL1812x3+R8862A S2100(A6A)x3+R8862A S2600(A4A)x1 | 0 | 1
4619A | Kg Paya(Mxs) | Northern |  | Modernization |  | 2027 | HW | GCI | 4.6 TSSR Approved |  | 2023-10-13 | 2023-10-20 |  | 2025-11-27 |  | Under Approval | 2025-12-16 | 2025-12-29 |  | 2025-12-19 | Celcom Digi_RAN-GCI-TSS-Northern-20231017-0060 | DU00002864135 | [5 empty] | Tower | 60m 3 Legged Tower | 60 | Add R8852E S9000x3+R8894E M1821x3, ,Dimantle R8882-GUL1812 x3+R8862A S2100(A6A) x3
4672A | Changloon | Northern |  | Modernization |  | 2024 Q3 | BY | CCSMY | 4.6 TSSR Approved | ¦ 0319 - Previous TSSR subcon submitted, have solution changes | 2023-10-18 | 2023-10-20 |  | 2024-01-29 |  | Closed | 2024-03-29 | 2024-04-25 | E//Ajay | 2024-04-24 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231019-0058 | DU00002864136 |  |  | 2024-04-27 | 2024-04-16 |  | Tower | 60m 4 Legged Tower | 48 | Add R8862A S2601 x1+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x1 | 1 | 0
4672B | Padang Sira | Northern |  | Modernization |  | 2024 Q3 | BY | GTSB | 4.6 TSSR Approved |  | 2023-10-11 | 2023-10-16 |  | 2024-03-22 |  | Closed | 2024-03-25 | 2024-03-29 | E//Hazida | 2024-03-28 | Celcom Digi_RAN-GTSB-TSS-Northern-20231012-0047 | DU00002864137 |  |  | 2024-04-18 | 2024-04-12 |  | Tower | 60m 3 Legged Tower | 60 | Add R8894E M1821 x2+A9732 M1821 x1,Dismantle R8882-GUL1812 x2+R8862A S1800(B6A) x1+R8862A S2100(A6A) x3 | 3 | 0
4695A | Perwaja Steel | Northern |  | Modernization |  | 2025 Q3 | AD | CCSMY | 4.6 TSSR Approved |  | 2025-01-15 | 2025-01-27 |  | 2025-02-12 |  | Under Approval | 2025-03-11 | 2025-07-16 | E//Hazida | 2025-03-16 | SQ202501030037 - CCSMY | DU00002864138 |  |  | 2025-03-26 | 2025-03-26 |  | Wall mount boom | Watertank Structure | 3m | Add R8852E S9000x1+R8894E M1821x3, Dismantle R8862A S1800(B6A)x3 | 0 | 0
4733A | Sg Durian (Trunk) | Northern |  | Modernization |  | 2024 Additional | SHA | GCI | 4.6 TSSR Approved | 0224 - CME Required emailed to rollout | 2024-12-09 | 2024-12-13 |  | 2024-12-20 |  | Under Approval | 2024-12-20 | 2024-12-24 | E//Hazida | 2024-12-23 | 1911CD-Northern-TSS-BOQ Template(new contract)_GCI_V2 | DU00002864139 |  |  | 2025-05-14 | 2025-05-14 |  | Tower | 76m Tower | 75 | Add R8894E M1821x4+R8854 S2600x1, Dismantle R8882-GUL1812x2+R8862A S1800(B6A)x1+R8854D S2100(A4A)x3+R8862A S2600(A4A)x1 | 0 | 2
4760B | Malau | Northern |  | Modernization |  | 2024 Q3 | SM | YPTT | 4.6 TSSR Approved | ¦ 0319 - Previous TSSR subcon submitted, have solution changes | 2023-10-26 | 2023-11-02 |  | 2023-11-20 |  | Closed | 2024-03-25 | 2024-03-29 | E//Hazida | 2024-03-28 | Celcom Digi_RAN-YPTT-TSS-Northern-20231028-0040 | DU00002864140 |  |  | 2024-04-17 | 2024-04-15 |  | Tower | 45m 3 Legged Tower | 60m | Add R8862A S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8860E-GU908 x3+R8882-GUL1812 x1+R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 3
4856B | Megat Dewa (Maxis) | Northern |  | Modernization |  | 2024 Q3 | ZA | GTSB | 4.6 TSSR Approved | ¦ 0319 - Previous TSSR subcon submitted, have solution changes | 2023-10-11 | 2023-10-17 |  | 2023-10-31 |  | Closed | 2024-03-27 | 2024-05-15 | E//Ajay | 2024-03-28 | Celcom Digi_RAN-GTSB-TSS-Northern-20231012-0047 | DU00002864141 |  |  | 2024-04-18 | 2024-04-12 |  | Tower | 60m 3 Legged Tower | 60 | Add R8852E S9000 x3,Dismantle | 0 | 0
4928B | Gentruck Taiping | Northern |  | Modernization |  | 2024 Q2 |  | CCSMY | 4.6 TSSR Approved | ¦ 0304 - Need revise TSSR due to 900 RRU model not available | 2023-10-25 | 2023-11-02 |  | 2024-01-08 |  | Rectificating | 2024-01-10 | 2024-01-15 | E//Hazida | 2024-01-12 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231026-0062 | DU00002864142 |  |  | 2024-03-18 | 2024-03-13 |  | In-Building System | 6m RT (Boom) | 7m | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882-GUL1812 x3+R8840-U216 x4++
4723B | Kg Kangar | Northern |  | Modernization |  | 2024 Q3 | BY | YPTT | 4.6 TSSR Approved | ¦ 0319 - Previous TSSR subcon submitted, have solution changes | 2023-10-26 | 2023-10-30 |  | 2023-11-01 |  | Closed | 2024-03-25 | 2024-03-27 | E//Ajay | 2024-03-27 | Celcom Digi_RAN-YPTT-TSS-Northern-20231028-0040 | DU00002864143 |  |  | 2024-04-19 | 2024-04-13 |  |  | Tower | 60M | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle | 0 | 3
2082B | Equine Park | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002864144 | [6 empty] | 3m Boom (RT) |  |  | 4
7223B | Kg Rampayan Laut | Sabah |  | Modernization |  | 2024 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2023-10-25 | 2023-10-30 |  | 2023-11-01 |  | Closed | 2024-03-26 | 2024-04-15 | E//Hannah | 2024-04-06 | Celcom Digi_RAN-YPTT-TSS-Sabah-20231028 | DU00002864145 |  |  | 2024-05-27 | 2024-05-17 |  | Monopole | 45m 3 Legged Tower | 45 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 | 0 | 0
4927A | Kg Tersusun | Northern |  | Modernization |  | 2024 Additional | SM | GCI | 4.6 TSSR Approved | ¦ 1127 - Emailed planning on Solution CR due to Maxis Site | 2023-11-04 | 2023-11-10 |  | 2024-11-25 |  | Rectificating | 2024-11-27 | 2024-12-16 | E//Hazida | 2024-12-15 | Celcom Digi_RAN-GCI-TSS-Northern-20231106-0072//2111CD-Northern-TSS-BOQ Template(new contract)_GCI | DU00002864146 | Remarks: Solution TSSR/BOM Changed |  | 2024-12-06 | 2024-12-06 |  | Tower | 45m 3 Legged Tower | 47 | Add R8852E S9000 x1+R9264H M901821x2+R8854 S2600x2, Dismantle R8862A S2600(A4A)x2+R8894E M1821(A8A)x2 | 0 | 12
4771B | Padang Liching | Northern |  | Modernization |  | 2024 Q4 | SM | GTSB | 4.6 TSSR Approved |  | 2023-10-16 | 2023-10-18 |  | 2023-10-24 |  | Closed | 2024-05-09 | 2024-05-10 | E//Hazida | 2024-05-10 | Celcom Digi_RAN-GTSB-TSS-Northern-20231017-0050 | DU00002864147 |  |  | 2024-05-21 | 2024-05-16 |  | Tower | Tower | 60 | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle | 0 | 3
3915A | Utusan Melayu (REL) | Central |  | Modernization |  | 2024 Q3 | SS | Magicell | 4.6 TSSR Approved |  | 2024-02-02 | 2024-02-07 |  | 2024-03-21 |  | Closed | 2024-03-26 | 2024-04-04 | E//Sumitra | 2024-04-04 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240212 | DU00002864148 |  |  | 2024-06-26 | 2024-06-22 |  | In-Building System | 3m Bipod (RT) | 3 | Add R9264M M1821 x3,Dismantle R8854E S1800(A6A) x3+R8854D S2100(A4A) x3 | 0 | 0
7104B | Megalong Donggongan | Sabah |  | Modernization |  | 2024 Q3 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2023-10-24 | 2023-10-30 |  | 2023-11-02 |  | Closed | 2024-04-04 | 2024-04-15 | E//Hannah | 2024-04-08 | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231028 | DU00002864149 |  |  | 2024-04-30 | 2024-04-27 |  | Pole | RT | 2m | Add R9224E M1821 x2,Dismantle | 0 | 23
7106A | Bandar Cenderawasih (Maxis) | Sabah |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | MS | GTSB | 4.6 TSSR Approved | AAU Cannot Install-S23 MM change to BI¦Maxis only allow 1 pcs antenna and 1 pcs RRU on top for each sector | 2023-10-26 | 2023-11-21 |  | 2024-07-17 |  | Under Approval | 2024-07-18 | 2024-07-19 | E//Hannah | 2024-07-19 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231028 | DU00002864150 |  |  | 2024-12-09 | 2024-11-29 |  | Tower | 60m 3 Legged Tower | 60 | Add R8894E M1821x2 | 0 | 23
3552C | TREC KL Streetlight (REL) | Central |  | Modernization |  | 2024 Q2 | YZ | GTSB | 4.6 TSSR Approved |  | 2023-11-22 | 2023-11-27 |  | 2024-01-18 |  | Closed | 2024-08-22 | 2024-08-27 | E//Sumitra | 2024-08-27 | CelcomDigi_RAN_GTSB_TSS_Central_20231126 | DU00002864151 |  |  | 2024-03-05 | 2024-03-02 |  | Lampole | 24m Lampole | 16m | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
7108A | SM Teknik | Sabah |  | Modernization |  | 2024 Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-10-23 | 2023-10-31 |  | 2023-11-02 |  | Under Approval | 2024-07-17 | 2024-07-19 | E//Hannah | 2024-07-19 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231024 | DU00002864152 |  |  | 2024-08-26 | 2024-08-13 |  | Tower | Tower | 76m | Add R8862A S9000 x3+R8894E M1821 x2,Dismantle R8860E-GU908 x3 | 0 | 13
7378A | USP Kg.Tamalang | Sabah |  | Modernization |  | 2025 Q3 | AD | Seri Pancar | 4.6 TSSR Approved |  | 2023-11-01 | 2023-11-10 |  | 2025-02-14 |  | Under Approval | 2025-03-22 | 2025-05-27 | E//Hannah | 2025-04-16 | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231221 | DU00002864153 |  |  | 2025-05-11 | 2025-04-08 |  |  | 57m 4 Legged Tower | 60 | Add R9224E M1821x1 | 0 | 1
7447B | Tmn Utama Sandakan | Sabah |  | Modernization |  | 2024 Q3 | MS | Datasco | 4.6 TSSR Approved |  | 2024-04-20 | 2024-05-06 |  | 2024-05-10 |  | Closed | 2024-06-10 | 2024-06-12 | E//Hannah | 2024-06-11 | Celcom Digi_RAN-Datasco-Standard PR TSS-Sabah-20240503 | DU00002864154 |  |  | 2024-06-19 | 2024-06-15 |  | In-Building System | 3m RT (Wall Mounted Pole) | 3m & 2m | Add R8862A S9000 x3+R9224E M1821 x4+R8854 S2600 x1,Dismantle R8882-GUL1812 x3+R8862A S2600(A4A) x1++R8881 S2100 x2+ | 0 | 3
7450B | Mile 1 1_2 Labuk Road | Sabah |  | Modernization |  | 2024 Q3 | AD | Datasco | 4.6 TSSR Approved |  | 2024-04-01 | 2024-03-29 |  | 2024-04-25 |  | Closed | 2024-05-03 | 2024-05-08 | E//Hannah | 2024-05-03 | Celcom Digi_RAN-Datasco-Standard PR TSS-Sabah-20240406 | DU00002864155 |  |  | 2024-06-25 | 2024-06-18 |  | Pole | 6m RT (Wall Mounted Pole) | 6 | Add R8862A S9000 x3+R9224E M1821 x3,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 0 | 0
7518A | Sri Perdana Shoplot | Sabah |  | Modernization |  | 2024 Q3 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-10-20 | 2023-10-25 |  | 2023-10-30 |  | Closed | 2024-04-16 | 2024-05-17 | E//Hannah | 2024-05-17 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231024 | DU00002864156 |  |  | 2024-06-07 | 2024-06-04 |  | In-Building System | 6m Unipole RT | 4 | Add R8862A S9000 x3+R9224E M1821 x4+R8862A S2601 x1,Dismantle R8882-GUL1812 x3+R8862A S2100(A6A) x3 | 0 | 1
7658B | PETRONAS-SEPAGAYA | Sabah |  | Modernization |  | 2024 Q3 | AD | GTSB | 4.6 TSSR Approved | AAU Cannot Install-S3 MM change to normal sector¦Petronas Pylon no space to add AAU | 2023-11-06 | 2023-11-16 |  | 2024-04-15 |  | Closed | 2024-04-16 | 2024-04-24 | E//Hannah | 2024-04-24 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231107 | DU00002864157 |  |  | 2024-06-22 | 2024-05-23 |  | Petronas Pylon | 24m Pylon | 25 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3 | 0
7704A | Menumbok | Sabah |  | Modernization |  | 2025 | AD | Seri Pancar | 14.0 TSSR Not Required (Reuse Existing BBU/RRU) |  | 2023-11-02 | 2023-11-06 |  | 2025-02-17 |  | Under Approval |  |  |  |  | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231221 | DU00002864158 |  |  | 2025-08-29 | 2025-08-28 |  | Tower | 76m 4 Legged Tower | 60m | Reuse Existing RRU | 0 | 0
3348B | NPE (Pjs 51) | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-15 | 2023-11-20 |  | 2024-04-05 |  | Closed | 2024-04-24 | 2024-04-24 | E//Kok Keen | 2024-04-24 | CelcomDigi_RAN_GTSB_TSS_Central_20231116 | DU00002864159 |  |  | 2024-04-20 | 2024-04-03 |  | BillBoard | Billboard | 33m | Add R9264H M901821 x3,Dismantle R9224E M1821(AAB) x3 | 0 | 2
9204A | Nyelong Park | Sarawak |  | Modernization |  | 2025 Q2 | AI | Magicell | 4.6 TSSR Approved |  | 2024-01-25 | 2024-02-06 |  | 2025-02-07 |  | Closed | 2025-02-14 | 2025-02-27 |  | 2025-02-24 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20240123 | DU00002864160 |  |  | 2025-03-15 | 2025-03-11 |  | Minimast | 3m RT (Minimast) | 10 | Add R9264M M1821x3, Dismantle R8894E M1821(A8A)x3 | 0 | 0
4071C | Seri Jaya | Northern |  | Modernization |  | 2024 Q2 | BY | GTSB | 4.6 TSSR Approved |  | 2023-10-12 | 2024-02-13 |  | 2024-01-10 |  | Closed | 2024-01-16 | 2024-02-14 | E//Hazida | 2024-01-21 | Celcom Digi_RAN-GTSB-TSS-Northern-20231013-0048 | DU00002864161 |  |  | 2024-02-21 | 2024-02-05 |  | Tower | 60m 4 Legged Tower | 60M | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
3293C | Desa Water Park 2 (REL) | Central |  | Modernization |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-11-15 | 2023-11-30 |  | 2023-12-15 |  | Closed | 2024-08-26 | 2024-08-28 | E//Sumitra | 2024-08-28 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231116 | DU00002864162 |  |  | 2024-04-13 | 2024-04-02 |  | Lampole | 24m Lampole | 30 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
2368A | Citta Mall OD | Central |  | Modernization |  | 2024 Q1 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-17 | 2023-11-23 |  | 2024-01-08 |  | Closed | 2024-04-16 | 2024-04-16 | E//Kok Keen | 2024-04-16 | CelcomDigi_RAN_GTSB_TSS_20231119 | DU00002864163 |  |  | 2024-04-29 | 2024-04-19 |  | Wall mount boom | 3m Bipod (RT) | 3 | Add R9264M M1821 x3+R9264H M901821 x1+R8862A S2601 x1,Dismantle R8882 S1800B(B6B) x3
9032A | Semongok | Sarawak |  | Modernization |  | 2025 Q1 | SM | Magicell | 4.6 TSSR Approved |  | 2023-10-17 | 2023-10-23 |  | 2023-11-01 |  | Rectificating | 2025-02-20 | 2025-02-25 | E//Hannah | 2025-02-24 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231019 | DU00002864164 |  |  | 2025-03-17 | 2025-03-05 |  | Tower | Tower | 46M | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8882-GUL1812x2+R8862A S1800(B6A)x1+R8862A S2100(A6A)x3 | 0 | 0
7160B | Minintod | Sabah |  | Modernization |  | 2024 Q3 | MS | Seri Pancar | 4.6 TSSR Approved |  | 2023-10-23 | 2023-10-23 |  | 2023-10-25 |  | Closed | 2024-04-02 | 2024-04-02 | E//Hannah | 2024-04-02 | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231024 | DU00002864165 |  |  | 2024-04-26 | 2024-04-24 |  | Monopole | 30m Monopole | 30 | Add R9264M M1821 x2+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 3 | 0
3240C | Cheras Zen (REL) | Central |  | Modernization |  | 2024 Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-08 | 2024-01-09 |  | 2024-05-24 |  | Closed | 2024-05-25 | 2024-06-04 | E//Sumitra | 2024-06-04 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240110 | DU00002864166 |  |  | 2024-09-03 | 2024-08-30 |  | Pole | 3m Bipod (RT) | 6m | Add R8852E S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x3+R9224E M1821(AAB) x2 | 12 | 0
9245A | Serian Town | Sarawak |  | Modernization |  | 2025 Q3 | AI | Trintel | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦pBTS loading issue,AAU cannot install | 2023-10-26 | 2023-10-31 |  | 2025-02-25 |  | Closed | 2025-03-07 | 2025-03-10 | E//Hannah | 2025-03-10 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231214 | DU00002864167 |  |  | 2025-04-27 | 2025-04-25 |  | In-Building System | 3m RT (Minimast) | 31m | Add R8852E S9000x3+R8894E M1821x1+R8854 S2600x1, Dismantle R8862A S2600(A4A)x1+R8892E M1821x3 | 0 | 1
7854A | Pusat Dagangan Donggongon | Sabah |  | Modernization |  | 2024 Q3 | MS | Seri Pancar | 4.6 TSSR Approved |  | 2023-10-22 | 2023-10-26 |  | 2023-10-30 |  | Closed | 2024-03-25 | 2024-04-19 | E//Hannah | 2024-04-19 | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231028 | DU00002864168 |  |  | 2024-05-06 | 2024-04-25 |  | Unipole | 3m Bipod (RT) | 9m | Add R8894E M1821 x3,Dismantle R8882 S1800B(B6B) x3 | 0 | 0
2223A | Kg Puah | Central |  | Modernization |  | 2024 Q1 | IE | DATASCO | 4.6 TSSR Approved |  | 2024-03-19 | 2024-03-21 |  | 2024-03-26 |  | Closed | 2024-03-26 | 2024-03-27 |  | 2024-03-26 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240323 | DU00002864169 |  |  | 2024-05-04 | 2024-04-30 |  | Petronas Pylon | 24m Pylon | 33M | Add R9264H M901821 x3,Dismantle R8854D S2100(A4A) x3+R8892E M1821(BAA) x3
2692A | Bandar Puteri 8 (REL) | Central |  | Modernization |  | 2024 Q3 | SHA | Magicell | 4.6 TSSR Approved |  | 2024-06-14 | 2024-06-27 |  | 2024-07-02 |  | Under Approval | 2024-10-15 | 2024-11-14 | E//Razif | 2024-11-13 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240510 | DU00002864170 |  |  | 2024-11-18 | 2024-11-15 |  | Petronas Pylon | Tower | 32M | Reuse existing RRU | 0 | 0
4115C | Taman Pulai Jaya | Northern |  | Modernization |  | 2024 Q2 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-10-22 | 2023-10-26 |  | 2024-01-09 |  | Closed | 2024-01-12 | 2024-01-15 |  | 2024-01-12 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231022-0060 | DU00002864171 |  |  | 2024-03-13 | 2024-02-20 |  | In-Building System | 3m Bipod (RT) | 4.7m | Add R8862A S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3+R8862A S2600(A4A) x1 |  | 3
3841A | Kesas R&R KINRARA | Central |  | Modernization |  | 2024 Q3 | SS | GTSB | 4.6 TSSR Approved |  | 2023-11-15 | 2023-11-17 |  | 2023-12-12 |  | Closed | 2023-12-15 | 2023-12-20 | E//Sumitra | 2023-12-19 | CelcomDigi_RAN_GTSB_TSS_Central_20231116 | DU00002864172 |  |  | 2024-05-18 | 2024-05-18 |  | BillBoard | Billboard | 18m | Add R9264H M901821 x3,Dismantle R9224E M1821(AAB) x3
4064C | First Garden | Northern |  | Modernization |  | 2024 Q2 |  | CCSMY | 4.6 TSSR Approved |  | 2023-10-20 | 2023-10-25 |  | 2024-01-08 |  | Closed | 2024-01-09 | 2024-01-11 |  | 2024-01-10 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231022-0060 | DU00002864173 |  |  | 2024-02-27 | 2024-02-17 |  | Tower | 30m Monopole | 4m | Add R8862A S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3+R8862A S2600(A4A) x1 |  | 3
4089C | Sg Pari 1 | Northern |  | Modernization |  | 2024 Q2 |  | CCSMY | 4.6 TSSR Approved |  | 2023-10-18 | 2023-10-23 |  | 2024-01-08 |  | Rectificating | 2024-01-10 | 2024-04-04 | E//Hazida | 2024-04-03 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231019-0058 | DU00002864174 |  |  | 2024-02-23 | 2024-02-13 |  | Unipole | 3m Bipod (RT) | 3.6m | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 12
7515B | Bandar Nasalim | Sabah |  | Modernization |  | 2024 Q3 | AD | Datasco | 4.6 TSSR Approved |  | 2024-03-30 | 2024-04-18 |  | 2024-04-22 |  | Closed | 2024-04-22 | 2024-05-02 | E//Hannah | 2024-04-24 | Celcom Digi_RAN-Datasco-Standard PR TSS-Sabah-20240406 | DU00002864175 |  |  | 2024-06-18 | 2024-06-14 |  | In-Building System | 3m Bipod (RT) | 9 | Add R9224E M1821 x3,Dismantle R8862A S1800(B6A) x3++R8881 S2100 x3+ | 0 | 0
2554B | Surau Attaufiqiah | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-17 | 2023-11-21 |  | 2023-12-01 |  | Closed | 2023-12-06 | 2024-01-11 | E//Kok Keen | 2024-01-11 | CelcomDigi_RAN_GTSB_TSS_20231119 | DU00002864176 |  |  | 2024-04-03 | 2024-04-03 |  | Monopole | 24m Lampole | 25m | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x4
3716A | Jln BK 6B_1 | Central |  | Modernization |  | 2024 Q3 | SH | GCI | 4.6 TSSR Approved |  | 2024-01-04 | 2024-01-11 |  | 2024-04-29 |  | Closed | 2024-05-02 | 2024-05-10 | E//Kok Keen | 2024-05-09 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240108 | DU00002864177 |  |  | 2024-09-13 | 2024-09-12 |  | H-bracket pole | 3m Bipod (RT) | 6m | Add R8894E M1821 x4,Dismantle R8882 S1800(B) x2+R8882 S1800B x1+R8862A S1800(B6A) x1+R8862A S2100(A6A) x4 | 0 | 0
3732A | Tmn Industri Puchong | Central |  | Modernization |  | 2024 Q3 | AI | Magicell | 4.6 TSSR Approved |  | 2024-01-11 | 2024-01-16 |  | 2024-04-24 |  | Closed | 2024-04-23 | 2024-04-25 | E//Razif | 2024-04-25 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240115 | DU00002864178 |  |  | 2024-06-26 | 2024-06-24 |  | In-Building System | 3m Boom (RT) | 10M | Add R8894E M1821 x3,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 | 0 | 0
9212B | Samarahan Industrial Park | Sarawak |  | Site Out (Modernization) | Modernization->Site out->Replacement, Site Out (Modernization) | 2024 Q2 | ZB | Datasco | [SiteOut]- 4.5 Pending TSSR Review - Customer | AAU Cannot Install-Change MM to BI¦PBTS can not install AAU | 2023-10-07 | 2023-10-13 |  | 2023-10-23 |  | Under Approval | 2024-03-11 |  | E//Hannah |  | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231016 | DU00002864179 | Remarks: Solution TSSR/BOM Changed NIC_S2_Change MM to BI_loading issue_SACOFA SDN BHD | to revise TSSR with the latest config. Change solution to BI |  |  |  | Tower | Tower | 45
7186B | Tambunan Golf Club | Sabah |  | Modernization |  | 2024 Q3 | MS | Seri Pancar | 4.6 TSSR Approved |  | 2023-10-23 | 2023-10-25 |  | 2023-10-31 |  | Closed | 2024-03-29 | 2024-04-03 | E//Hannah | 2024-04-03 | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231024 | DU00002864180 |  |  | 2024-04-26 | 2024-04-24 |  | Pole | Watertank Structure | 6m | Add R8894E M1821 x1,Dismantle | 0 | 1
4741A | Makam Mahsuri (KM Rel) | Northern |  | Modernization |  | 2025 Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2025-01-25 | 2025-02-04 |  | 2025-02-17 |  | Closed | 2025-02-19 | 2025-02-27 | E//Hazida | 2025-02-19 | SQ202501030229 - GTSB | DU00002864181 |  |  | 2025-03-11 | 2025-03-03 |  | Monopole | Tower | 46M | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8882 S1800B(B6B)x3+R8862A S2100(A6A)x3 | 0 | 0
4921A | Taman Teluk Intan | Northern |  | Modernization |  | 2024 Additional | AI | GCI | 4.6 TSSR Approved |  | 2024-12-09 | 2024-12-20 |  | 2024-12-26 |  | Closed | 2024-12-27 | 2024-12-31 | E//Hazida | 2024-12-31 | SQ202501070076 - GCi | DU00002864182 |  |  | 2025-02-03 | 2025-02-03 |  | In-Building System | 3m Bipod (RT) | 8m | Add R9264H M901821x3, Dismantle R8894E M1821(A8A)x3 | 0 | 0
2342A | PJS 4 LP | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002864183 | [6 empty] | 24m Lampole |  |  | 14
7542A | Kg Palau Palau | Sabah |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | MS | Datasco | 4.6 TSSR Approved |  | 2024-05-28 | 2024-05-30 |  | 2024-10-22 |  | Under Approval | 2024-10-25 | 2024-11-04 | E//Hannah | 2024-11-04 | 0920CD-Sabah-Datasco-BOQ Template (old contract) | DU00002864184 |  |  | 2024-11-25 | 2024-11-18 |  | Monopole | 30m Lampole | 30 | Add R8862A S9000x3+R8894E M1821 x1 | 0 | 2
4293C | Persiaran Wira Jaya Barat Candidate 1 | Northern |  | Modernization |  | 2024 Q2 | BY | YPTT | 4.6 TSSR Approved |  | 2023-10-26 | 2023-11-02 |  | 2024-01-08 |  | Closed | 2024-01-09 | 2024-01-11 |  | 2024-01-10 | Celcom Digi_RAN-YPTT-TSS-Northern-20231028-0040 | DU00002864185 |  |  | 2024-01-31 | 2024-01-12 |  | In-Building System | 3m Bipod (RT) | 3.5 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882 S1800B(B6B) x3+R8854D S2100(A4A) x3
3298B | Scott Garden Outdoor | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002864186 | [6 empty] | 3m Bipod (RT) |  |  | 123
2226A | Perusahaan pkns | Central |  | Modernization |  | 2024 Q1 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-10-31 | 2023-11-08 |  | 2024-01-03 |  | Closed | 2024-01-04 | 2024-01-05 | E//Kok Keen | 2024-01-04 | CelcomDigi_RAN_Datasco_TSS_Central_20231126 | DU00002864187 |  |  | 2024-04-01 | 2024-03-29 |  | H-bracket pole | 3m Boom (RT) | 5 | Add R9264M M1821 x4,Dismantle R8894E M1821(A8A) x4
3205B | KL Sentral Outdoor | Central |  | Modernization |  | 2024 Q2 | CR | DATASCO | 4.6 TSSR Approved |  | 2024-01-08 | 2024-01-16 |  | 2024-01-29 |  | Closed | 2024-02-02 | 2024-02-06 | E//Sumitra | 2024-02-06 | BOQ CelcomDigi_RAN_Datasco_Standard PR TSS_Central_20240110 | DU00002864188 |  |  | 2024-06-16 | 2024-06-14 |  | In-Building System | 3m Bipod (RT) | 2.5 | Add R9264H M901821 x3,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3
3109B | Old Klang Road (HSR) | Central |  | Modernization |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2024-04-18 | 2024-04-24 |  | 2024-04-24 |  | Closed | 2024-04-25 | 2024-04-30 | E//Sumitra | 2024-04-30 | CelcomDigi_RAN_Ascentrack_TSS_Central_20240513 | DU00002864189 |  |  | 2024-05-23 | 2024-05-22 |  | In-Building System | 3m RT (Wall Mounted Pole) | 3 | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle R8862A S2600(A4A) x1 | 0 | 2
3985A | New World Hotel RT | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q1 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002864190 | [6 empty] | In-building system |  |  | 123
7431A | Usukan | Sabah |  | Site Out (Modernization) | Modernization->On Hold->Site Out->Replacement, Site Out (Modernization) | 2024 Q3 | AD | YPTT | [SiteOut]- 1.0 Pending Survey - Subcon | [6 empty] | To be Submitted | [5 empty] | DU00002864191 | [6 empty] | 45m 3 Legged Tower
2205A | Al-ikhwan Keramat | Central |  | Modernization |  | 2024 Q1 | SS | CCSMY | 4.6 TSSR Approved |  | 2024-01-18 | 2024-01-19 |  | 2024-01-29 |  | Closed | 2024-01-30 | 2024-02-06 | E//Sumitra | 2024-02-06 | CelcomDigi_RAN_CCS_TSS_Central_20240124 | DU00002864192 |  |  | 2024-08-07 | 2024-08-06 |  | Unipole | 3m Bipod (RT) | 6 | Add R8894E M1821 x4,Dismantle R8882-GUL1812 x3+R8854D S2100(A4A) x3 |  | 4
2278A | Psiaran Sg Long 7A | Central |  | Modernization |  | 2024 Q4 | SY1 | YPTT | 4.6 TSSR Approved |  | 2024-05-12 | 2024-05-15 |  | 2024-05-24 |  | Closed | 2024-05-25 | 2024-06-07 | E//Sumitra | 2024-06-06 | CelcomDigi_RAN_YPTT_TSS_Central_20240517 | DU00002864193 |  |  | 2024-08-19 | 2024-08-15 |  | In-Building System | 3m RT (Wall Mounted Pole) | 6 | Add R8852E S9000 x1+R9264H M901821 x3+A9732 M1821 x1,Dismantle R8862A S2600(A4A) x1+R8894E M1821(A8A) x4+R9224E M1821(AAB) x1 | 2 | 0
3089B | Pangsapuri Angsana | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-13 | 2024-01-15 |  | 2024-04-24 |  | Closed | 2024-04-26 | 2024-04-29 | E//Sumitra | 2024-04-26 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240115 | DU00002864194 |  |  | 2024-06-26 | 2024-06-26 |  | Monopole | 30m Monopole | 31m | Add R9264M M1821 x3,Dismantle R8882 S1800B(B6B) x3++R8881 S2100 x3+ | 0 | 0
3286B | Federal HW (NPE Interchange) | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q2 |  |  | 14.2 Drop (Done Survey) | AAU Cannot Install-Change MM to BI¦Space issue cant install AAU | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002864195 | [6 empty] | 3m Bipod (RT) |  |  |  | 14
4239C | Kampus West City | Northern |  | Modernization |  | 2024 Additional | SHA | CCSMY | 4.6 TSSR Approved |  | 2024-12-08 | 2024-12-17 |  | 2024-12-18 |  | Under Approval | 2024-12-19 | 2024-12-20 | E//Hazida | 2024-12-20 | 1911CD-Northern-TSS-BOQ Template(new contract)_CCSMY_V2 | DU00002864196 |  |  | 2025-01-11 | 2025-01-06 |  | In-Building System | 3m Bipod (RT) | 5m | Add R8894E M1821x3, Dismantle R8882 S1800(B)x3+R8881 S2100x3 | 0 | 0
7292B | ITCC (REL) | Sabah |  | Modernization |  | 2024 Q3 | MS | Seri Pancar | 4.6 TSSR Approved |  | 2023-10-25 | 2023-10-30 |  | 2023-11-02 |  | Closed | 2024-05-10 | 2024-11-28 | E//Hannah | 2024-11-28 | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231028 | DU00002864197 |  |  | 2024-05-31 | 2024-05-09 |  | In-Building System | Rooftop | 6 | Add R8862A S9000 x3+A9732 M1821 x3,Dismantle R8854 S2600(A4A) x3+R8894E M1821(A8A) x3+R9224E M1821(AAB) x3 | 123 | 0
3363B | Jalan Atmosphere 7 | Central |  | Modernization |  | 2024 Q3 | SH | DATASCO | 4.6 TSSR Approved |  | 2023-12-01 | 2023-12-13 |  | 2024-04-25 |  | Closed | 2024-05-03 | 2024-05-14 | E//Sumitra | 2024-05-14 | CelcomDigi_RAN_Datasco_TSS_Central_20231214 | DU00002864198 |  |  | 2024-06-24 | 2024-06-22 |  | Unipole | Rooftop | 7m | Add R8862A S9000 x4+R9224E M1821 x1+R8854 S2600 x1,Dismantle | 0 | 4
4349B | Rimba Panjang (REL) | Northern |  | Modernization |  | 2025 | HW | Magicell | 4.6 TSSR Approved |  | 2023-10-30 | 2023-11-02 |  | 2025-03-17 |  | Under Approval | 2025-03-24 | 2025-05-19 | E//Hazida | 2025-04-24 | Celcom Digi_RAN-Magicell-TSS-Northern-20231101-0002 | DU00002864199 |  |  | 2025-04-11 | 2025-04-11 |  | Tower | Tower | 62M | Add R8894E M1821x1 | 0 | 3
7256B | Kota Belud Town | Sabah |  | Modernization |  | 2024 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2023-10-24 | 2023-10-31 |  | 2023-11-02 |  | Closed | 2024-03-26 | 2024-04-15 | E//Hannah | 2024-04-06 | Celcom Digi_RAN-YPTT-TSS-Sabah-20231024 | DU00002864200 |  |  | 2024-04-30 | 2024-04-26 |  | In-Building System | 3m Bipod (RT) | 10 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
7229B | Kg Hubah | Sabah |  | Modernization |  | 2024 Q3 | MS | Seri Pancar | 4.6 TSSR Approved |  | 2023-10-25 | 2023-10-30 |  | 2023-11-01 |  | Rectificating | 2024-03-27 | 2024-04-02 | E//Hannah | 2024-04-02 | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231028 | DU00002864201 |  |  | 2024-05-06 | 2024-04-25 |  | Monopole | Tower | 30 | Add R8862A S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 23 | 0
3467B | Surau Al-Ansar | Central |  | Modernization |  | 2024 Q3 | AI | Magicell | 4.6 TSSR Approved |  | 2024-01-19 | 2024-01-24 |  | 2024-04-19 |  | Closed | 2024-04-19 | 2024-04-25 | E//Sumitra | 2024-04-25 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240128 | DU00002864202 |  |  | 2024-05-11 | 2024-05-09 |  | Lampole | Lampole | 30m | Add R8862A S9000 x3+R8894E M1821 x1+R8854 S2600 x2,Dismantle | 0 | 12
7293B | Taman Kasigui | Sabah |  | Modernization |  | 2024 Q3 | MS | Seri Pancar | 4.6 TSSR Approved |  | 2023-11-01 | 2023-11-04 |  | 2024-03-26 |  | Closed | 2024-03-27 | 2024-04-02 | E//Hannah | 2024-04-02 | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231107 | DU00002864203 |  |  | 2024-05-09 | 2024-05-06 |  | Monopole | 30m Monopole | 30 | Add R8862A S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 2 | 0
2472A | Sekysen 9 Bkt Serdang (REL) | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002864204 | [6 empty] | 3m RT (Minimast) |  |  | 12
7295B | Kg Tanaki | Sabah |  | Modernization |  | 2024 Q3 | MS | Seri Pancar | 4.6 TSSR Approved |  | 2023-10-23 | 2023-10-30 |  | 2023-11-03 |  | Closed | 2024-04-04 | 2024-04-19 | E//Hannah | 2024-04-19 | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231024 | DU00002864205 |  |  | 2024-05-06 | 2024-04-30 |  | Monopole | Tower | 30 | Add R8862A S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 | 12 | 0
7260B | Kg Nanamun | Sabah |  | Modernization |  | 2024 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2023-10-25 | 2023-11-15 |  | 2024-03-29 |  | Closed | 2024-03-29 | 2024-04-03 | E//Hannah | 2024-04-03 | Celcom Digi_RAN-YPTT-TSS-Sabah-20231028 | DU00002864206 |  |  | 2024-05-28 | 2024-05-17 |  | Monopole | 45m 3 Legged Tower | 45 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8882 S1800B(B6B) x3+R8862A S2100(A6A) x3 | 0 | 0
3510B | Taman Semenyih | Central |  | Modernization |  | 2024 Additional | SHA | YPTT | 4.6 TSSR Approved |  | 2024-07-04 | 2024-07-06 |  | 2024-11-26 |  | Under Approval | 2024-12-04 | 2024-12-10 | E//Sumitra | 2024-12-10 | S1MY2021071003WBF1-2978 | DU00002864207 |  |  | 2025-04-14 | 2025-04-14 |  | Monopole | 45m Monopole | 45 | Reuse Existing RRU | 0 | 0
3545B | Jalan Sungai Long | Central |  | Modernization |  | 2024 Q4 | SY1 | YPTT | 4.6 TSSR Approved |  | 2023-10-23 | 2023-10-26 |  | 2024-06-10 |  | Closed | 2024-06-11 | 2024-06-20 | E//Sumitra | 2024-06-19 | CelcomDigi_RAN_YPTT_TSS_Central_20231224 | DU00002864208 |  |  | 2024-08-17 | 2024-08-16 |  | In-Building System | 3m Bipod (RT) | 7 | Add R9264M M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
4619C | Taman Savori | Northern |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | SM | CCSMY | 4.6 TSSR Approved |  | 2024-10-23 | 2024-11-06 |  | 2024-11-07 |  | Rectificating | 2024-11-12 | 2024-11-14 | E//Hazida | 2024-11-13 | PR raised as per design team | DU00002864209 |  |  | 2024-11-28 | 2024-11-17 |  |  | 3m Bipod (RT) | 4 | Add R8862A S9000x3 + R8894E M1821 x3, Dismantle R8862A S1800(B6A)x3+R8854D S2100(A4A)x3 | 0 | 0
4266C | Taipan Slim River | Northern |  | Modernization |  | 2024 Additional | SM | YPTT | 14.0 TSSR Not Required (Reuse Existing BBU/RRU) | ¦ 20241223 - Solution changed to reuse all RRU, only add card, can use previous TSSR approval for claiming Purposes | 2023-11-24 | 2023-12-06 |  | 2024-11-26 |  | Rectificating |  |  | E//Hazida |  | Celcom Digi_RAN-YPTT-TSS-Northern-20231127-0045//2111CD-Northern-TSS-BOQ Template(new contract)_YPTT | DU00002864210 |  |  | 2024-12-27 | 2024-12-16 |  | In-Building System | 3m Bipod (RT) | 5 | Reuse Existing RRU | 0 | 0
3601B | Jalan Bangi Semenyih | Central |  | Modernization |  | 2024 Additional | BY | YPTT | 4.6 TSSR Approved |  | 2023-10-24 | 2023-10-31 |  | 2024-11-24 |  | Under Approval | 2024-12-04 | 2024-12-12 | E//Sumitra | 2024-12-12 | CelcomDigi_RAN_YPTT_TSS_Central_20231224 | DU00002864211 | Remarks: Solution TSSR/BOM Changed |  | 2024-12-17 | 2024-12-15 |  | Monople Tree | 45m Monopole | 45 | Add R8894E M1821 x3,Dismantle R8882 S1800B(B6B) x6+R8862A S1800(B6A) x1+R8862A S2100(A6A) x4+R8862A S2600(A4A)x1 | 0 | 0
4285C | Jln Raja Musa RT | Northern |  | Modernization |  | 2024 Q2 | SM | YPTT | 4.6 TSSR Approved |  | 2023-12-19 | 2023-12-29 |  | 2024-01-10 |  | Rectificating | 2024-01-11 | 2024-01-22 | E//Hazida => E//Ajay | 2024-01-19 | Celcom Digi_RAN-YPTT-TSS-Northern-20231225-0047 | DU00002864212 |  |  | 2024-02-26 | 2024-02-13 |  | Pole | 3m Boom (RT) | 6 | Add R9224E M1821 x2+R8854 S2600 x2,Dismantle R8862A S2600(A4A) x2 |  | 12
3609B | Federal HW (Menara TM) | Central |  | Modernization |  | 2024 Q2 | MA | YPTT | 4.6 TSSR Approved | ¦ 1902 : Cluster antenna but propose 4T RRU& 900(NOT SUPPORT 900 & 4T) | 2024-02-07 | 2024-02-13 |  | 2024-02-20 |  | Closed | 2024-03-06 | 2024-08-22 | E//Kok Keen | 2024-08-22 | BOQ_Celcom Digi_RAN-YPTT-Standard PR TSS-20240218 | DU00002864213 |  |  | 2024-11-27 | 2024-08-22 |  |  | 18m Lampole | 18 | Add R9264M M1821 x2,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
7336B | Kg Kawang-Kawang | Sabah |  | Modernization |  | 2024 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2024-01-08 | 2023-11-02 |  | 2024-03-26 |  | Closed | 2024-03-27 | 2024-04-15 | E//Hannah | 2024-04-08 | Celcom Digi_RAN-YPTT-Standard PR TSS-Sabah-20240116 | DU00002864214 |  |  | 2024-05-06 | 2024-04-29 |  | Monopole | 45m 3 Legged Tower | 45 | Add R8862A S9000 x3,Dismantle | 0 | 0
1397A | Tmn Rasa Sayang | Central |  | Modernization |  | 2024 Q1 | CR | GCI | 4.6 TSSR Approved |  | 2023-11-15 | 2023-11-17 |  | 2024-01-02 |  | Closed | 2024-01-02 | 2024-01-03 | E//Sumitra | 2024-01-03 | Celcom Digi_RAN-GCI-TSS-Central-20231119 | DU00002864215 |  |  | 2024-04-01 | 2024-03-29 |  | In-Building System | 3m RT (Wall Mounted Pole) | 5 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
4753A | Tmn Rasa Sayang | Northern |  | Modernization |  | 2024 Q3 | BY | CCSMY | 4.6 TSSR Approved |  | 2023-10-11 | 2023-10-20 |  | 2023-11-03 |  | Closed | 2024-04-04 | 2024-04-23 | E//Hazida | 2024-04-22 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231012-0053 | DU00002864216 |  |  | 2024-04-21 | 2024-04-18 |  | Pole | 30m Lampole | 43m | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 3 | 0
3989B | Surau Medan Idaman | Central |  | Modernization |  | 2024 Q1 | YZ | GCI | 4.6 TSSR Approved |  | 2023-11-15 | 2023-11-20 |  | 2024-01-02 |  | Closed | 2024-01-16 | 2024-03-26 | E//Kok Keen | 2024-03-25 | Celcom Digi_RAN-GCI-TSS-Central-20231119 | DU00002864217 |  |  | 2024-03-11 | 2024-02-22 |  | Lampole | 18m Lampole | 18 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
4064B7 | pBTS Bagan Panchor (M) | Northern |  | Modernization |  | 2024 Q2 | SM | GTSB | 4.6 TSSR Approved | ¦ 0304 - Need revise TSSR due to 900 RRU model not available ¦ 0220 - pBTS will be decomm as per informed by CD | 2023-10-13 | 2023-10-17 |  | 2024-01-08 |  | Rectificating | 2024-01-10 | 2024-01-11 |  | 2024-01-10 | Celcom Digi_RAN-GTSB-TSS-Northern-20231015-0049 | DU00002864218 |  |  | 2024-03-18 | 2024-03-12 |  | Tower | 25m pBTS | 80 | Add R8862A S9000 x3,Dismantle
3966B | UTAR Sg Long | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4(single site MOCN)-L2126 SSM |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002864219 | [6 empty] | Land site |  |  | 12
3978B | Kajang Sikh Temple | Central |  | Modernization |  | 2024 Q4 | SM | Magicell | 4.6 TSSR Approved |  | 2023-11-29 | 2023-12-21 |  | 2024-05-10 |  | Closed | 2024-05-15 | 2024-05-27 | E//Sumitra | 2024-05-24 | CelcomDigi_RAN_Magicell_TSS_Central_20231214 | DU00002864220 |  |  | 2024-06-24 | 2024-06-23 |  | BillBoard | 30m Monopole | 30 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
7398B | Ladang Rimmer | Sabah |  | Modernization |  | 2024 Q4 | MS | GTSB | 4.6 TSSR Approved |  | 2023-10-26 | 2023-10-26 |  | 2023-10-31 |  | Under Approval | 2024-07-17 | 2024-08-07 | E//Hannah | 2024-08-05 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231028 | DU00002864221 |  |  | 2024-08-23 | 2024-08-12 |  | Tower | 45m 3 Legged Tower | 45M | Add A9732 M1821 x1,Dismantle R8894E M1821(A8A) x1 | 2 | 0
7675A | Glowbest Tenom (REL) | Sabah |  | Remote MOCN | Modernization->Remote MOCN | 2027 |  | YPTT | 14.1 Drop (No Survey) | [6 empty] | To be Submitted |  |  |  |  | SQ202501030041 - YPTT | DU00002864222 | [6 empty] | 30m Monopole |  | Reuse Existing RRU | 0 | 0
7956A | Kota Marudu Town | Sabah |  | Modernization |  | 2025 Q3 | HW | GTSB | 4.6 TSSR Approved |  | 2025-01-28 | 2025-02-14 |  | 2025-03-14 |  | Under Approval | 2025-03-24 | 2025-04-24 | E//Hannah | 2025-04-16 | SQ202501030028 - GTSB | DU00002864223 |  |  | 2025-04-15 | 2025-04-11 |  | Monopole | 30M Lampole | 30 | Add R8852E S9000x4 | 0 | 0
4195C | Kg Parit Menteri | Northern |  | Modernization |  | 2024 Q2 | SM | GTSB | 4.6 TSSR Approved |  | 2023-10-13 | 2023-10-16 |  | 2024-01-09 |  | Rectificating | 2024-01-10 | 2024-01-15 | E//Ajay | 2024-01-12 | Celcom Digi_RAN-GTSB-TSS-Northern-20231015-0049 | DU00002864224 |  |  | 2024-04-05 | 2024-04-01 |  | Monopole | 30m Monopole | 45 | Add R8862A S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8882 S1800B(B6B) x3+R8862A S2601(A6A) x1++R8881 S2100 x3+ |  | 2
7358A | Kg Sinisian | Sabah |  | Modernization |  | 2025 Q2 | AD | Futong | 4.6 TSSR Approved |  | 2023-10-23 | 2023-10-24 |  | 2023-10-26 |  | Closed | 2025-01-09 | 2025-02-18 | E//Syahriani | 2025-01-20 | Celcom Digi_RAN-Futong-TSS-Sabah-20231024 | DU00002864225 |  |  | 2025-06-06 | 2025-05-21 |  | Tower | Tower | 76 | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8882 S1800B(B6B)x3 | 0 | 0
3831B | Tmn Wawasan (REL) | Central |  | Modernization |  | 2024 Q3 | SH | Magicell | 4.6 TSSR Approved |  | 2023-11-28 | 2023-12-21 |  | 2024-04-19 |  | Closed | 2024-05-08 | 2024-05-15 | E//Kok Keen | 2024-05-15 | CelcomDigi_RAN_Magicell_TSS_Central_20231214 | DU00002864226 |  |  | 2024-07-31 | 2024-07-30 |  | Tower | 24m Pylon | 30 | Add R8894E M1821 x1,Dismantle | 0 | 3
3834B | Vilaraya Industrial Park | Central |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | SHA | YPTT | 4.6 TSSR Approved |  | 2024-05-10 | 2024-05-16 |  | 2024-05-23 |  | Under Approval | 2024-05-27 | 2024-11-28 | E//Sumitra | 2024-11-28 | CelcomDigi_RAN_YPTT_TSS_Central_20240513 | DU00002864227 |  |  | 2024-11-26 | 2024-11-25 |  | Monopole | 24m Lampole | 30 | Add R8852E S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R8862A S2600(A4A) x1 | 0 | 1
3383C | NZX Commercial Centre (REL) | Central |  | Modernization |  | 2024 Q1 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-09 | 2023-11-16 |  | 2023-12-27 |  | Closed | 2023-12-28 | 2023-12-29 | E//Kok Keen | 2023-12-29 | CelcomDigi_RAN_GTSB_TSS_Central_20231113 | DU00002864228 |  |  | 2024-04-03 | 2024-03-30 |  | Unipole | 3m Boom (RT) | 5 | Add R8862A S9000 x3+R8894E M1821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3
3768B | Hospital Rehabilitasi Cheras ( Watertank ) | Central |  | Modernization |  | 2024 Q3 | SH | CCSMY | 4.6 TSSR Approved |  | 2023-10-21 | 2023-10-31 |  | 2024-03-22 |  | Closed | 2024-03-27 | 2024-04-05 | E//Sumitra | 2024-04-05 | CelcomDigi_RAN_CCSMY_TSS_Central_20231023 | DU00002864229 |  |  | 2024-05-11 | 2024-05-08 |  | Lampole | 24m Lampole | 18m | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
7387A | Kg. Bingkul Beaufort | Sabah |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | MS | Seri Pancar | 4.6 TSSR Approved |  | 2023-10-31 | 2023-11-03 |  | 2024-10-22 |  | Closed | 2024-10-25 | 2024-10-30 | E//Hannah | 2024-10-30 | Celcom Digi_RAN-Seri Pancar-TSS-Sabah-20231221 | DU00002864230 |  |  | 2024-11-12 | 2024-11-07 |  | Monopole | 3m Boom (RT) | 30m | Add R8894E M1821 x1 | 0 | 3
4289C | Kg Chuar Hulu | Northern |  | Remote MOCN | Modernization->Remote MOCN | 2027 |  | Magicell | 14.2 Drop (Done Survey) |  | 2023-10-30 | 2023-11-02 |  |  |  | To be Submitted |  |  |  |  | Celcom Digi_RAN-Magicell-TSS-Northern-20231101-0002 | DU00002864231 | [5 empty] | Monopole | Tower | 48 | Reuse Existing RRU | 0 | 0
4428C | Ipoh Aeon Station 18 2 | Northern |  | Modernization |  | 2024 Q2 | BY | GTSB | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦Space issue cant install AAU | 2023-11-29 | 2023-10-25 |  | 2024-01-13 |  | Closed | 2024-01-15 | 2024-01-29 | E//Hazida | 2024-01-24 | Celcom Digi_RAN-GTSB-TSS-Northern-20231015-0049 | DU00002864232 |  |  | 2024-03-17 | 2024-03-12 |  | Minaret | 30m Minaret | 30M | Add R8862A S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3+R8862A S2600(A4A) x1 |  | 3
3744B | Bangsar Village 2 Outdoor | Central |  | Modernization |  | 2024 Q2 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-12-08 | 2023-12-21 |  | 2024-03-05 |  | Closed | 2024-03-06 | 2024-03-07 | E//Kok Keen | 2024-03-06 | CelcomDigi_RAN_CCSMY_TSS_Central_20231213 | DU00002864233 |  |  | 2024-04-23 | 2024-04-03 |  | In-Building System | 3m Bipod (RT) | 3m | Add R8852E S9000 x3+R8894E M1821 x1+R8854 S2600 x1,Dismantle R8862A S2600(A4A) x1 | 0 | 2
3742B | Resource Industrial Center | Central |  | Modernization |  | 2024 Q3 | MA | Ascentrack | 4.6 TSSR Approved |  | 2023-12-14 | 2023-12-15 |  | 2023-12-20 |  | Closed | 2023-12-21 | 2024-01-03 | E//Sumitra | 2024-01-03 | CelcomDigi_RAN_Ascentrack_TSS_Central_20231215 | DU00002864234 |  |  | 2024-04-04 | 2024-04-02 |  | Lampole | 24m Lampole | 18 | Add R9264M M1821 x3,Dismantle R8892E M1821(BAA) x3
7274B | Selasih Ria | Sabah |  | Modernization |  | 2024 Q3 | ZA | GTSB | 4.6 TSSR Approved |  | 2023-10-18 | 2023-10-25 |  | 2023-11-01 |  | Closed | 2024-04-16 | 2024-04-22 | E//Hannah | 2024-04-22 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231019 | DU00002864235 |  |  | 2024-06-13 | 2024-06-04 |  | Monopole | 30m Monopole | 30m | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle | 0 | 12
7275B | Kg Muhibbah | Sabah |  | Modernization |  | 2024 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2023-10-20 | 2023-10-24 |  | 2023-10-26 |  | Closed | 2023-10-28 | 2024-04-24 | E//Hannah | 2024-04-24 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231024 | DU00002864236 |  |  | 2024-06-07 | 2024-05-28 |  | Lampole | 30m Monopole | 30 | Add R8862A S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x5 | 12 | 0
2108B | Tmn Lembah Maju | Central |  | Modernization |  | 2024 Q4 | BY | GTSB | 4.6 TSSR Approved | AAU Cannot Install-S3 MM change to BI¦all wall-mounted pole,need extra bracing | 2023-11-28 | 2023-11-30 |  | 2024-05-16 |  | Closed | 2024-05-21 | 2024-05-29 | E//Sumitra | 2024-05-29 | CelcomDigi_RAN_GTSB_TSS_Central_20231201 | DU00002864237 |  |  | 2024-07-25 | 2024-07-25 |  | A-bracket pole | 3m RT (Wall Mounted Pole) | 4m | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle R8882-L268 x1 | 0 | 3
7061C | Sandakan Square | Sabah |  | Modernization |  | 2024 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2024-01-31 | 2024-03-14 |  | 2024-04-15 |  | Closed | 2024-04-24 | 2024-05-02 | E//Hannah | 2024-05-02 | Celcom Digi_RAN-GTSB-TSS-Sabah-20240204 | DU00002864238 |  |  | 2024-07-02 | 2024-06-20 |  | Monopole | 30m RDS | 30m | Add R9264M M1821 x1+R9264H M901821 x1+A9732 M1821 x2+R8862A S2601 x1,Dismantle R9224E M1821(AAB) x4 | 34 | 0
3515B | Mutiara Indah Puchong | Central |  | Modernization |  | 2024 Q3 | MA | Solusi | 4.6 TSSR Approved |  | 2024-03-28 | 2024-01-19 |  | 2024-04-30 |  | Closed | 2024-05-17 | 2024-05-24 | E//Razif | 2024-05-24 | BOQ CelcomDigi_RAN_Solusi_Standard PR TSS_Central_20240329 | DU00002864239 |  |  | 2024-06-05 | 2024-05-31 |  | In-Building System | 3m Bipod (RT) | 6.3 | Add R8862A S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8882 S1800B(B6B) x3++R8881 S2100 x3+ | 1 | 0
3040C | Jalan Terengganu (REL) | Central |  | Modernization |  | 2024 Q2 | YZ | CCSMY | 4.6 TSSR Approved |  | 2023-10-21 | 2023-10-30 |  | 2024-03-05 |  | Closed | 2024-03-06 | 2024-03-07 | E//Kok Keen | 2024-03-07 | CelcomDigi_RAN_CCSMY_TSS_Central_20231023 | DU00002864240 |  |  | 2024-05-23 | 2024-05-22 |  | Monopole | 18m Lampole | 18.4 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3 | 0 | 0
3239B | Bandar Tasik Kesuma | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q4(single site MOCN)-L26 SSM |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002864241 | [5 empty] | Monopole | 24m Lampole | 24m | Reuse Existing RRU |  | 13
7744B | Kg Pahu | Sabah |  | Modernization |  | 2025 Q2 | SHA | Futong | 4.6 TSSR Approved |  | 2023-10-27 | 2023-10-30 |  | 2023-11-01 |  | Under Approval | 2025-01-08 | 2025-03-10 | E//Yanie | 2025-01-20 | Celcom Digi_RAN-Futong-TSS-Sabah-20231028 | DU00002864242 |  |  | 2025-07-06 | 2025-03-25 |  | Tower | 60m 4 Legged Tower | 60 | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3 | 0 | 0
3244C | Jalan Cengal (REL) | Central |  | Modernization |  | 2024 Q1 | YZ | GCI | 4.6 TSSR Approved | 04/03/24 - Change solution : RRU 01/2 - To confirm SO related to RRU location, Cabinet and feeder inlet | 2023-11-09 | 2023-11-14 |  | 2024-01-02 |  | Closed | 2024-01-03 | 2024-03-05 | E//Kok Keen | 2024-03-05 | CelcomDigi_RAN_GCI_TSS_Central_20231113 | DU00002864243 |  |  | 2024-03-13 | 2024-03-11 |  | Lampole | 24m Lampole | 25 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3+R8862A S9000(A6A) x3
3473B | Jalan 4_108A | Central |  | Modernization |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-11-06 | 2023-11-14 |  | 2024-04-03 |  | Closed | 2024-08-22 | 2024-08-27 | E//Sumitra | 2024-08-27 | CelcomDigi_RAN_Datasco_TSS_Central_20231113 | DU00002864244 |  |  | 2024-05-11 | 2024-05-09 |  | Lampole | 18m Lampole | 18 | Add R8862A S9000 x3+R8894E M1821 x1+R8854 S2600 x1,Dismantle R8862A S2600(A4A) x1 | 0 | 1
3296C | Surau Ampang Saujana (REL) | Central |  | Modernization |  | 2024 Q4 | AI | GTSB | 4.6 TSSR Approved |  | 2023-12-16 | 2023-12-19 |  | 2024-05-14 |  | Closed | 2024-05-17 | 2024-06-06 | E//Sumitra | 2024-06-06 | CelcomDigi_RAN_GTSB_TSS_Central_20231224 | DU00002864245 |  |  | 2024-06-07 | 2024-06-05 |  | Minaret | 30m Monopole | 24m | Add R8862A S9000 x3+R8894E M1821 x1+R8854 S2600 x1,Dismantle R8862A S2600(A4A) x1 | 0 | 2
4572C | Sri Navakali Amman (REL) | Northern |  | Modernization |  | 2024 Q2 | BY | CCSMY | 4.6 TSSR Approved | ¦ 0307 - To ignore latest rejection as revise RRU model only, use previous approval as TSSR approval ¦ 0304 - Need revise TSSR due to 900 RRU model not available | 2023-10-25 | 2023-10-30 |  | 2024-01-10 |  | Closed | 2024-01-12 | 2024-01-18 | E//Ajay | 2024-01-18 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231026-0062 | DU00002864246 |  |  | 2024-03-18 | 2024-03-13 |  | Tower | 30m Lampole | 32 | Add R8862A S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 13
9421B | Samarindah Baru | Sarawak |  | Modernization |  | 2024 Q2 | ZB | Magicell | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦sacofa rampole not allow to add AAU | 2023-10-07 | 2023-10-09 |  | 2023-10-13 |  | Closed | 2024-01-16 | 2024-01-18 | E//Hannah | 2024-01-16 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231009 | DU00002864247 | NIC_S1_Change MM to BI_owner reject_SACOFA SDN BHD |  | 2024-03-21 | 2024-03-18 |  | Monopole | 30m Monopole | 30M | Add R8894E M1821 x4+R8854 S2600 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R8862A S2600(A4A) x1 | 0 | 1
1211C | Ara Damansara | Central |  | Modernization |  | 2024 Q1 | AI | GTSB | 4.6 TSSR Approved |  | 2023-12-06 | 2023-12-14 |  | 2024-01-08 |  | Closed | 2024-01-12 | 2024-01-16 | E//Kok Keen | 2024-01-15 | CelcomDigi_RAN_GTSB_TSS_Central_20231208 | DU00002864248 |  |  | 2024-04-26 | 2024-04-22 |  | Minimast | 3m RT boom | 8 | Add R8862A S9000 x3+R8894E M1821 x5+R8854 S2600 x2,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R8862A S2601(A6A) x2 |  | 12
7354B | Kg. Tamu Darat | Sabah |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | MS | Futong | 4.6 TSSR Approved |  | 2024-10-23 | 2024-10-24 |  | 2024-10-30 |  | Closed | 2024-11-04 | 2024-12-17 | E//Hannah | 2024-12-17 | S1MY2024071007WBF1-186 | DU00002864249 |  |  | 2025-01-31 | 2024-12-16 |  | Tower | Tower | 65M | Add R8862A S9000x3+R8894E M1821x5+R8854 S2600x2, Dismantle R8862A S1800(B6A)x3+R8854D S2100(A4A)x3+R8862A S2600(A4A)x2 | 0 | 12
7562B | Kg Sukau | Sabah |  | Modernization |  | 2024 Q4 | MS | NR services | 4.6 TSSR Approved |  | 2023-10-30 | 2023-11-24 |  | 2024-07-22 |  | Closed | 2024-07-25 | 2024-08-02 | E//Hannah | 2024-08-02 | Celcom Digi_RAN-NR Services-TSS-Sabah-20231101 | DU00002864250 |  |  | 2024-08-25 | 2024-08-19 |  | Tower | Tower | 78m | Add R8862A S9000 x3+R8894E M1821 x2+A9732 M1821 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 1 | 0
2737B | Tmn Perdana | Central |  | Modernization |  | 2024 Q3 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-10-21 | 2023-10-24 |  | 2024-03-21 |  | Closed | 2024-03-22 | 2024-03-26 | E//Sumitra | 2024-03-25 | CelcomDigi_RAN_CCSMY_TSS_Central_20231023 | DU00002864251 |  |  | 2024-05-14 | 2024-05-08 |  | Monopole | Land | 24 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
3146B7 | pBTS Chandan Puteri 1 (KM) | Northern |  | Modernization | Modernization->On Hold->Modernization | 2026 | AI | GTSB | 4.1 Pending TSSR Submission - Subcon |  | 2023-10-15 | 2023-10-18 |  |  |  | To be Submitted |  |  |  |  | Celcom Digi_RAN-GTSB-TSS-Northern-20231015-0049 | DU00002864252 | [5 empty] | Tower | 25m pBTS | 30 | Add R8894E M1821x3, Dismantle R8882 S1800B(B6B)x3+R8854D S2100(A4A)x3 | 0 | 0
3550C | Billboard Seksyen 8 PJ (REL) | Central |  | Modernization |  | 2024 Q3 | SS | GTSB | 4.6 TSSR Approved |  | 2023-12-12 | 2023-12-13 |  | 2023-12-20 |  | Closed | 2024-04-01 | 2024-04-02 |  | 2024-04-01 | CelcomDigi_RAN_GTSB_TSS_Central_20231214 | DU00002864253 |  |  | 2024-05-14 | 2024-05-14 |  | BillBoard | Billboard | 36 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
3376C | Masjid Bandar Rinching | Central |  | Site Out (Modernization) | Modernization->Site Out->Replacement, Site Out (Modernization) | 2025 |  | YPTT | [SiteOut]- 4.1 Pending TSSR Submission - Subcon |  | 2024-05-05 |  |  |  |  | To be Submitted |  |  |  |  | 0715Central-YPTT-BOQ Template | DU00002864254 | [5 empty] | Lampole | 24m Lampole | 24m | Add R8862A S9000x3 | 0 | 0
3356A14 | pBTS Jln PJU 1a_46 | Central |  | Modernization | Modernization->On Hold->Modernization | 2024 Q1 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-18 | 2023-11-23 |  | 2024-01-03 |  | Under Approval | 2024-01-04 | 2025-08-04 | E//Kok Keen | 2025-06-13 | CelcomDigi_RAN_GTSB_TSS_20231119 | DU00002864255 |  |  | 2025-07-03 | 2025-06-28 |  | Watertank | 25m pBTS | 24 | Add R8894E M1821x3, Dismantle R8882-GUL1812x3+R8862A S2100(A6A)x3 | 0 | 0
7330C | Kampung Lentigi (REL) | Sabah |  | Modernization |  | 2024 Q3 | AD | YPTT | 4.6 TSSR Approved |  | 2023-10-22 | 2023-10-24 |  | 2023-10-26 |  | Closed | 2024-04-04 | 2024-04-15 | E//Hannah | 2024-04-06 | Celcom Digi_RAN-YPTT-TSS-Sabah-20231024 | DU00002864256 |  |  | 2024-04-30 | 2024-04-26 |  | Tower | 45M Slim Tower | 45 | Add R8862A S9000 x3+R9224E M1821 x4+R8854 S2600 x1,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3+R8862A S2600(A4A) x1 | 0 | 3
3481C | HUKM IB | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  |  | 14.2 Drop (Done Survey) | AAU Cannot Install-Change MM to BI¦AAU can not install,space issue | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002864257 | NIC_S3_Change MM to BI_Space constraint_REDPYNE SDN BHD | [5 empty] | 3m Bipod (RT) |  |  |  | 123
3494C | Jalan Kia Peng (REL) | Central |  | Modernization |  | 2024 Q2 | AI | Magicell | 4.6 TSSR Approved |  | 2024-05-27 | 2024-06-05 |  | 2024-06-10 |  | Closed | 2024-06-10 | 2024-06-13 | E//Sumitra | 2024-06-13 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240510 | DU00002864258 |  |  | 2024-08-29 | 2024-08-28 |  | Lampole | 18m Lampole | 18M | Add R9264H M901821 x3,Dismantle R8892N M1821(BAB) x3 | 0 | 0
3498C | Air Asia HQ IB | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Additional |  |  | 14.3 Drop (Done Survey + TSSR) |  | 2023-09-29 |  |  | 2025-02-14 |  | Under Approval | [5 empty] | DU00002864259 | [6 empty] | 6m RT (Boom) + IBS |  |  | 2
9991A | Taman Fuiyuan Saratok | Sarawak |  | Modernization |  | 2025 Q3 | SHA | Datasco | 4.6 TSSR Approved |  | 2023-10-20 | 2023-11-15 |  | 2024-11-28 |  | Under Approval | 2025-01-06 | 2025-03-10 | E//Yanie | 2025-01-13 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231024 | DU00002864260 |  |  | 2025-02-28 | 2025-01-25 |  |  | 30M Rapole | 35 | Add R8862A S9000x4
4770C | Taman Serai Emas Bagan Serai (BSSE) | Northern |  | Site Out (Modernization) | Modernization->Site Out (Modernization) | 2026 | HW | GTSB | 4.6 TSSR Approved |  | 2023-12-14 | 2023-12-18 |  | 2025-03-21 |  | Under Approval | 2025-03-28 | 2025-05-19 | E//Hazida | 2025-04-23 | Celcom Digi_RAN-GTSB-TSS-Northern-20231214-0077 | DU00002864261 | [5 empty] | Monople Tree | 30m Monopole | 45M | Add R8852E S9000x3+R9264M M1821x3, Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3 | 0 | 0
3703C | Jalan Kasturi Streetlight (REL) | Central |  | Modernization |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved | 27/04/24 - TSSR submit to CD and SO for approval. To swap existing cabinet to DualBay Cabinet | 2023-12-03 | 2023-12-06 |  | 2024-04-25 |  | Closed | 2024-04-27 | 2024-04-30 | E//Sumitra | 2024-04-30 | CelcomDigi_RAN_Datasco_TSS_Central_20231214 | DU00002864262 |  |  | 2024-06-22 | 2024-06-22 |  | Lampole | 18m Lampole | 19 | Add R8862A S9000 x3,Dismantle | 0 | 0
4011D | Jalan Tepi Sungai (REL) | Northern |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | SM | GCI | 4.6 TSSR Approved |  | 2024-11-18 | 2024-11-21 |  | 2024-11-25 |  | Rectificating | 2024-11-26 | 2024-12-16 | E//Hazida | 2024-12-15 | SQ202411060531 | DU00002864263 |  |  | 2024-12-31 | 2024-12-06 |  | Lampole | 30M Lampole | 45 | Add R8862A S9000x3+ R8894E M1821 x1+R8854 S2600x1,Dismantle R8862A S2601(A6A)x1 | 0 | 12
4336D | Seri Bourgainvillea Seri Botani | Northern |  | Modernization |  | 2024 Q2 |  | GCI | 4.6 TSSR Approved |  | 2023-10-13 | 2023-10-30 |  | 2024-01-09 |  | Closed | 2024-01-10 | 2024-01-12 | E//Hazida | 2024-01-12 | Celcom Digi_RAN-GCI-TSS-Northern-20231017-0060 | DU00002864264 |  |  | 2024-02-23 | 2024-01-24 |  | BillBoard | 30M Pylon | 32 | Add R8862A S9000 x3,Dismantle
3631C | Putra Perdana | Central |  | Modernization |  | 2024 Q3 | CR | Magicell | 4.6 TSSR Approved |  | 2023-11-25 | 2024-01-02 |  | 2024-04-22 |  | Closed | 2024-04-29 | 2024-05-03 | E//Razif | 2024-05-03 | CelcomDigi_RAN_Magicell_TSS_Central_20231214 | DU00002864265 |  |  | 2024-06-13 | 2024-06-11 |  | Lampole | 24m Lampole | 30 | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 23 | 0
4955C | Jalan Kuala Kedah | Northern |  | Modernization |  | 2025 Q3 | AD | CCSMY | 4.6 TSSR Approved |  | 2025-01-07 | 2025-01-10 |  | 2025-02-20 |  | Under Approval | 2025-03-12 | 2025-05-27 | E//Hazida | 2025-03-13 | SQ202501030037 - CCSMY | DU00002864266 |  |  | 2025-05-07 | 2025-05-07 |  | In-Building System | 3m Boom (RT) | 6M | Add R9264M M1821x3, Dismantle R8894E M1821(A8A)x3 | 0 | 0
7479B | Genting Sekong | Sabah |  | Modernization |  | 2024 Q4 | ZB | GTSB | 4.6 TSSR Approved | Solution changed MM>Bi | 2024-07-29 | 2024-08-05 |  | 2024-08-08 |  | Under Approval | 2024-10-01 | 2024-10-02 | E//Norsyahriani | 2024-10-02 | 0730CD-Sabah-GTSB-BOQ Template(new contract) | DU00002864267 |  |  | 2024-09-21 | 2024-09-13 |  | Tower | 45m 3 Legged Tower | 75m | Add R8894E M1821(A8A) x1,Dismantle | 0 | 3
4977C | Hala Permata | Northern |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | SM | GCI | 4.6 TSSR Approved |  | 2023-11-02 | 2023-11-16 |  | 2023-12-05 |  | Closed | 2024-10-23 | 2024-10-23 | E//Hazida | 2024-10-23 | Celcom Digi_RAN-GCI-TSS-Northern-20231103-0071 | DU00002864268 |  |  | 2024-11-20 | 2024-11-20 |  | Monopole | 24m Lampole | 30 | Add R8894E M1821 x1 | 0 | 4
4980C | Bandar Seri Botani | Northern |  | Modernization |  | 2024 Q2 | BY | GCI | 4.6 TSSR Approved |  | 2023-12-22 | 2024-01-04 |  | 2024-01-15 |  | Closed | 2024-01-17 | 2024-01-23 | E//Hazida | 2024-01-21 | Celcom Digi_RAN-GCI-TSS-Northern-20231225-0085 | DU00002864269 |  |  | 2024-02-21 | 2024-02-15 |  | Lampole | 30m Monopole | 25 | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8862A S1800(B6A) x3+R8854D S2100(A4A) x3 | 13
7054C | Kg. Sepagaya | Sabah |  | Modernization |  | 2024 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2023-10-20 | 2023-10-25 |  | 2023-10-30 |  | Closed | 2024-04-15 | 2024-04-18 | E//Hannah | 2024-04-18 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231024 | DU00002864270 |  |  | 2024-06-26 | 2024-06-22 |  | Lampole | Tower | 30 | Add A9732 M1821 x3,Dismantle R8894E M1821(A8A) x3 | 123 | 0
9028C | Belian Square (UITM 2) | Sarawak |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q2 |  | AllStar | 14.3 Drop (Done Survey + TSSR) | AAU Cannot Install-Change MM to BI¦sacofa rampole not allow to add AAU | 2023-10-09 | 2023-10-12 |  | 2023-11-09 |  | Under Approval |  |  |  |  | Celcom Digi_RAN-Allstar-TSS-Sarawak-20231009 | DU00002864271 | NIC_S2_Change MM to BI_owner reject_SACOFA SDN BHD |  |  |  |  | Monopole | Tower | 30 | Add R8862A S9000 x3+R8894E M1821 x5+R8854 S2600 x2,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R8862A S2600(A4A) x2 |  | 12
9029C | Kampung Mendang Laut | Sarawak |  | Modernization |  | 2024 Q2 | SH | Magicell | 4.6 TSSR Approved |  | 2023-10-11 | 2023-10-13 |  | 2023-10-20 |  | Closed | 2023-10-20 | 2023-11-15 | E//Hannah | 2023-11-10 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231013 | DU00002864272 |  |  | 2023-11-28 | 2023-11-24 |  | Monopole | 30m Lampole | 30 | Add R8852E S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 2 | 0
9026C | Lorong Spring Riam | Sarawak |  | Modernization |  | 2025 Q1 | AI | Datasco | 4.6 TSSR Approved | 15-3 - ZTE planner to update slide ¦ AAU Cannot Install-Change MM to BI¦sacofa rampole not allow to add AAU | 2023-10-17 | 2023-10-26 |  | 2025-02-11 |  | Closed | 2025-02-17 | 2025-02-27 | E//Yanie | 2025-02-25 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231019 | DU00002864273 |  |  | 2025-06-14 | 2025-03-14 |  |  | 30m Rapole | 30 | Add R8852E S9000x3+R9264M M1821x3, Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3 | 0 | 0
3624C | Orchid Apartment | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002864274 | [6 empty] | 3m Boom (RT) |  |  | 34
9599C | Tanjung Genting Sarikei | Sarawak |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | SHA | Datasco | 4.6 TSSR Approved |  | 2023-10-18 | 2023-11-09 |  | 2024-10-24 |  | Under Approval | 2024-10-28 | 2024-11-06 | E//Syahriani | 2024-11-05 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231019 | DU00002864275 |  |  | 2024-12-07 | 2024-11-11 |  | Tower | Tower | 76 | Add R8894E M1821x2 | 0 | 23
4211C | Taman Semarak (REL) | Northern |  | Modernization |  | 2024 Q2 | BY | YPTT | 4.6 TSSR Approved |  | 2023-12-27 | 2023-12-29 |  | 2024-01-10 |  | Closed | 2024-01-31 | 2024-02-02 | E//Ajay | 2024-02-01 | Celcom Digi_RAN-YPTT-TSS-Northern-20231229-0049 | DU00002864276 |  |  | 2024-03-11 | 2024-03-07 |  | Lampole | 30m Lampole | 30 | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 12
4373A | KTM Kuala Kangsar | Northern |  | Modernization |  | 2025 Q3 | HW | GCI | 4.6 TSSR Approved |  | 2023-10-17 | 2023-10-20 |  | 2025-03-03 |  | Under Approval | 2025-03-27 | 2025-05-19 | E//Hazida | 2025-04-23 | Celcom Digi_RAN-GCI-TSS-Northern-20231018-0061 | DU00002864277 |  |  | 2025-06-28 | 2025-05-30 |  | Tower | Tower | 50 | Add R8862A S9000x4+R8894E M1821x1 | 0 | 3
4089D | SK Saujana Indah | Northern |  | Modernization |  | 2024 Additional | SHA | GCI | 4.6 TSSR Approved |  | 2024-12-09 | 2024-12-24 |  | 2024-12-30 |  | Under Approval | 2024-12-31 | 2025-04-26 | E//Hazida | 2025-02-18 | 1911CD-Northern-TSS-BOQ Template(new contract)_GCI | DU00002864278 |  |  | 2025-01-17 | 2025-01-17 |  | Lampole | 24m Lampole | 30 | Add R8852E S9000x3+R8894E M1821x3, Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3+ | 0 | 0
3860C | Jalan SS2_24 (REL) | Central |  | Modernization |  | 2024 Q3 | CR | Magicell | 4.6 TSSR Approved |  | 2023-12-15 | 2023-12-20 |  | 2024-03-22 |  | Closed | 2024-03-26 | 2024-04-02 | E//Kok Keen | 2024-03-26 | CelcomDigi_RAN_Magicell_TSS_Central_20231224 | DU00002864279 |  |  | 2024-04-25 | 2024-04-24 |  | In-Building System | 3m Boom (RT) | 6M | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
1046B | Tmn Maluri 2 | Central |  | Modernization |  | 2024 Q2 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-24 | 2023-11-28 |  | 2024-01-22 |  | Closed | 2024-01-23 | 2024-01-29 | E//Sumitra | 2024-01-26 | CelcomDigi_RAN_GTSB_TSS_Central_20231126 | DU00002864280 |  |  | 2024-04-17 | 2024-04-15 |  | H-bracket pole | 3m RT (Wall Mounted Pole) | 3m | Add R9264M M1821 x3,Dismantle R8854E S1800(A6A) x3+R8854D S2100(A4A) x3
9101C | Taman Duranda Emas | Sarawak |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | SHA | Datasco | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦sacofa rampole not allow to add AAU | 2023-10-24 | 2023-11-02 |  | 2024-10-23 |  | Under Approval | 2024-10-30 | 2024-11-06 | E//Syahriani | 2024-11-05 | Celcom Digi_RAN-Datasco-TSS-Sarawak-20231214 | DU00002864281 |  |  | 2024-12-03 | 2024-11-28 |  | Monopole | 30m Rapole | 45 | Add R8862A S9000x3+R8894E M1821 x1 | 0 | 2
4556D | St Keretapi Arau | Northern |  | Modernization |  | 2024 Q4 | SM | YPTT | 4.6 TSSR Approved |  | 2023-12-05 | 2023-11-02 |  | 2024-04-21 |  | Rectificating | 2024-04-24 | 2024-04-25 | E//Hazida | 2024-04-25 | Celcom Digi_RAN-YPTT-TSS-Northern-20231225-0047 | DU00002864282 |  |  | 2024-05-31 | 2024-05-17 |  | Tower | 45M Tower | 45 | Add R8862A S9000 x3+R8894E M1821 x1+R8854 S2600 x1,Dismantle | 0 | 1
3520A14 | pBTS Kangar Town 2 | Northern |  | Remote MOCN | Modernization->On Hold->Remote MOCN | 2024 Q4 |  | GCI | 3.4 SOW/Solution On Hold |  | 2023-10-13 | 2023-10-20 |  |  |  | To be Submitted |  |  |  |  | Celcom Digi_RAN-GCI-TSS-Northern-20231017-0060 | DU00002864283 | [5 empty] | Tower | 24M PBTS | 20 | Add R8852E S9000 x3+R8894E M1821x3,Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3 | 0 | 0
1137C | PRIMA SETAPAK | Central |  | Modernization |  | 2024 Q1 | YZ | GCI | 4.6 TSSR Approved | 29/01 RRU inside cabinet, 3 rru on top. have temperature alarm according to technical team | 2023-11-09 | 2023-11-14 |  | 2023-12-29 |  | Closed | 2024-01-02 | 2024-04-05 | E//Kok Keen | 2024-04-05 | CelcomDigi_RAN_GCI_TSS_Central_20231113 | DU00002864284 |  |  | 2024-04-01 | 2024-03-29 |  | Lampole | 18m Lampole | 18 | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3
7073C | Kimbell Industrial | Sabah |  | Modernization |  | 2024 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2023-10-23 | 2023-10-23 |  | 2023-10-26 |  | Closed | 2023-10-26 | 2024-04-23 | E//Hannah | 2024-04-22 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231024 | DU00002864285 |  |  | 2024-06-10 | 2024-05-25 |  | Monopole | 30m Lampole | 30 | Add R8862A S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 23 | 0
1116C | Equator Equine | Central |  | Modernization |  | 2024 Q3 | SH | DATASCO | 4.6 TSSR Approved |  | 2023-10-25 | 2023-11-10 |  | 2024-04-30 |  | Closed | 2024-05-02 | 2024-05-10 | E//Kok Keen | 2024-05-09 | CelcomDigi_RAN_Datasco_TSS_Central_20231214 | DU00002864286 |  |  | 2024-06-04 | 2024-05-27 |  | Pole | Land | 6m | Add R8862A S9000 x4+R8894E M1821 x1+R8854 S2600 x1,Dismantle | 0 | 2
7065C | Bandar Sri Perdana | Sabah |  | Modernization |  | 2024 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2023-11-06 | 2023-11-08 |  | 2024-04-05 |  | Closed | 2024-04-16 | 2024-04-22 | E//Hannah | 2024-04-22 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231107 | DU00002864287 |  |  | 2024-06-13 | 2024-05-24 |  | Lampole | 30m Lampole | 30 | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 23 | 0
9632B | Taman Hill View 2 | Sarawak |  | Modernization |  | 2024 Q2 | ZB | Magicell | 4.6 TSSR Approved | AAU Cannot Install-Change MM to BI¦sacofa rampole not allow to add AAU | 2023-10-04 | 2023-10-05 |  | 2023-10-16 |  | Closed | 2024-03-06 | 2024-03-07 | E//Hannah | 2024-03-07 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231006 | DU00002864288 | NIC_S2_Change MM to BI_owner reject_SACOFA SDN BHD |  | 2024-03-25 | 2024-03-20 |  | Monopole | 30M Rapole | 30M | Add R8852E S9000 x3+R8894E M1821 x2+R8854 S2600 x2,Dismantle R8862A S2600(A4A) x2 | 0 | 12
4590D | Masjid Al-Aqla (REL) | Northern |  | Modernization |  | 2024 Q3 | BY | GCI | 4.6 TSSR Approved |  | 2023-12-20 | 2023-12-22 |  | 2024-03-25 |  | Closed | 2024-03-26 | 2024-03-29 | E//Hazida | 2024-03-28 | Celcom Digi_RAN-GCI-TSS-Northern-20231225-0085 | DU00002864289 |  |  | 2024-04-22 | 2024-04-13 |  | Lampole | 30M Lampole | 30M | Add R8862A S9000 x4+R8894E M1821 x1+R8854 S2600 x1,Dismantle | 0 | 3
1069C | Vista Lavender Apt | Central |  | Modernization |  | 2024 Q3 | SH | GCI | 4.6 TSSR Approved |  | 2024-01-04 | 2024-01-09 |  | 2024-04-29 |  | Closed | 2024-05-02 | 2024-05-10 | E//Kok Keen | 2024-05-09 | BOQ CelcomDigi_RAN_GCI_Standard PR TSS_Central_20240108 | DU00002864290 |  |  | 2024-06-21 | 2024-06-15 |  | Lampole | Building | 25 | Add R8862A S9000 x4,Dismantle | 0 | 0
1206C | Asia Jaya | Central |  | Modernization |  | 2024 Q3 | MA | DATASCO | 4.6 TSSR Approved |  | 2024-04-22 | 2024-05-14 |  | 2024-05-15 |  | Closed | 2024-05-15 | 2024-05-17 | E//Kok Keen | 2024-05-17 | CelcomDigi_RAN_Datasco_TSS_Central_20240513 | DU00002864291 |  |  | 2024-05-31 | 2024-05-29 |  | Minimast | 6m Unipole RT | 7m | Add R9264H M901821 x4,Dismantle R8862A S1800(B6A) x4
1217C | Puchong Prima | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2024-08-16 | 2024-08-21 |  | 2024-08-23 |  | Closed | 2024-08-26 | 2024-08-28 | E//Razif | 2024-08-28 | 0809CD-Central-GTSB-BOQ Template(new contract) | DU00002864292 | Remarks: Solution TSSR/BOM Changed |  | 2025-05-22 | 2025-05-19 |  | Unipole | 6m Unipole RT | 7 | Add R8862A S9000x1+R9264H M901821x2+A9732 M1821x1,Dismantle R8894E M1821(A8A) x3 | 2 | 0
1218C | LRT Pusat Bandar Puchong | Central |  | Modernization |  | 2024 Q3 | AI | Magicell | 4.6 TSSR Approved |  | 2024-10-09 | 2024-10-15 |  | 2024-10-17 |  | Under Approval | 2024-12-17 | 2024-12-27 | E//Sumitra | 2024-12-27 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240510 | DU00002864293 |  |  | 2025-09-19 | 2025-09-19 |  |  | Space Rental | 5 | Add R9264H M901821x3, Dismantle R8894E M1821(A8A)x3 | 0 | 0
1226C | Tun Sambanthan | Central |  | Modernization |  | 2024 Q2 | AI | GCI | 4.6 TSSR Approved |  | 2024-10-07 | 2024-10-16 |  | 2024-10-18 |  | Closed | 2024-12-16 | 2024-12-17 | E//Sumitra | 2024-12-17 | 0809CD-Central-GCI-BOQ Template(new contract) | DU00002864294 |  |  | 2025-09-25 | 2025-09-25 |  | In-Building System | 3m Boom (RT) | 2 | Add R8862A S9000x3 | 0 | 0
4159D | UTAR Compound | Northern |  | Modernization |  | 2024 Additional | SHA | GCI | 4.6 TSSR Approved |  | 2024-12-09 | 2024-12-09 |  | 2024-12-10 |  | Under Approval | 2024-12-12 | 2024-12-13 | E//Hazida | 2024-12-13 | 1911CD-Northern-TSS-BOQ Template(new contract)_GCI | DU00002864295 |  |  | 2024-12-20 | 2024-12-20 |  | Monople Tree | 24m Lampole | 45 | Add R9264H M901821x3, Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3 | 0 | 0
2831C | Masjid Kementah (REL) | Central |  | Modernization |  | 2024 Q1 | SS | CCSMY | 4.6 TSSR Approved |  | 2023-10-21 | 2023-10-25 |  | 2024-01-02 |  | Closed | 2024-01-04 | 2024-01-09 | E//Sumitra | 2024-01-09 | CelcomDigi_RAN_CCSMY_TSS_Central_20231023 | DU00002864296 |  |  | 2024-01-16 | 2024-01-16 |  |  | 18M DBKL Lampole | 24 | Add R8862A S9000 x3,Dismantle |  | 3
4166D | Masjid An-Naim Taman Sri Setia | Northern |  | Modernization |  | 2024 Additional | AD | GTSB | 4.6 TSSR Approved |  | 2024-12-04 | 2024-12-06 |  | 2024-12-12 |  | Under Approval | 2024-12-12 | 2024-12-17 | E//Hazida | 2024-12-17 | SQ202412090159 - GTSB | DU00002864297 |  |  | 2025-01-05 | 2024-12-23 |  | Minaret | 30M Minaret | 30M | Add R9264H M901821x3, Dismantle R8894E M1821(A8A)x3 | 0 | 0
9639B | Hock Seng Lee La Promenade | Sarawak |  | Modernization |  | 2024 Q2 | SH | Magicell | 4.6 TSSR Approved |  | 2023-10-10 | 2023-10-11 |  | 2023-10-20 |  | Closed | 2023-12-18 | 2023-12-20 | E//Hannah | 2023-12-18 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231013 | DU00002864298 |  |  | 2024-04-02 | 2024-03-25 |  | Lampole | 30m Lampole | 30 | Add R8852E S9000 x3+R8894E M1821 x4+R8854 S2600 x1,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R8862A S2600(A4A) x1 | 0 | 1
9661B | Masjid Al Mutaqin | Sarawak |  | Modernization |  | 2025 Q2 | AI | Magicell | 4.6 TSSR Approved |  | 2024-01-25 | 2024-02-06 |  | 2025-02-10 |  | Under Approval | 2025-02-10 | 2025-02-27 | E//Hannah | 2025-02-18 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20240123 | DU00002864299 |  |  | 2025-04-04 | 2025-03-21 |  | Monopole | 24m Lampole | 30 | Add R8894E M1821x1 | 0 | 2
1013B | Pandan Perdana | Central |  | Modernization |  | 2024 Q3 | SY1 | CCSMY | 4.6 TSSR Approved |  | 2023-10-28 | 2023-11-28 |  | 2024-04-04 |  | Under Approval | 2024-04-05 | 2024-08-01 | E//Sumitra | 2024-08-01 | CelcomDigi_RAN_CCSMY_TSS_Central_20231101 | DU00002864300 |  |  | 2024-06-15 | 2024-06-12 |  | In-Building System | 9m RT (Wall Mounted Pole) | 7 | Add R9224E M1821 x4,Dismantle R8854E S1800(A6A) x3+R8854D S2100(A4A) x4 | 0 | 3
7959B | Jalan Lohan Bongkud Ranau | Sabah |  | Modernization |  | 2025 Q3 | AD | NR services | 4.6 TSSR Approved |  | 2025-01-18 | 2025-03-07 |  | 2025-03-18 |  | Under Approval | 2025-03-22 | 2025-04-28 | E//Hannah | 2025-04-16 | SQ202501020451 - NR Service | DU00002864301 |  |  | 2025-05-04 | 2025-04-21 |  | Tower | 45m Tower | 45 | Add R8894E M1821x1 | 0 | 2
1221H | 99 Speedmart SEASONS GARDEN RESIDENSI | Central |  | MOCN As-Is |  | 2024 Q1 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864302 | [6 empty] | Small Cell
4813C | Taman Bunga Raya | Northern |  | Modernization |  | 2025 Q3 | HW | GCI | 4.6 TSSR Approved |  | 2023-11-18 | 2023-11-24 |  | 2025-03-03 |  | Under Approval | 2025-03-26 | 2025-05-19 | E//Hazida | 2025-04-25 | Celcom Digi_RAN-GCI-TSS-Northern-20231122-0075 | DU00002864303 |  |  | 2025-04-22 | 2025-04-16 |  | Lampole | 24m Lampole | 30 | Add R9264M M1821x3, Dismantle R8892E M1821(BAA)x3 | 0 | 0
7095H | iMacro Bandar Prima | Sabah |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864304 | [6 empty] | Small Cell
4969C | SUNGAI BULOH | Northern |  | Remote MOCN |  | 2026 |  | CCSMY | 4.4 Pending TSSR Review - Design Team |  | 2023-11-16 | 2023-11-20 |  | 2025-02-21 |  | Under Approval |  |  |  |  | Celcom Digi_RAN-CCSMY-TSS-Northern-20231118-0071 | DU00002864305 | [5 empty] | In-Building System | 30m Monopole | 6m | Add R9264H M901821x3, Dismantle R8862A S1800(B6A)x3+R8862A S2100(A6A)x3 | 0 | 0
1259C | Surau An-Nur | Central |  | Modernization |  | 2024 Q4(single site MOCN)-L26 SSM | SY1 | YPTT | 4.6 TSSR Approved |  | 2024-04-01 | 2024-04-04 |  | 2024-05-10 |  | Closed | 2024-05-13 | 2024-05-21 | E//Sumitra | 2024-05-21 | BOQ_Celcom Digi_RAN-YPTT-Standard PR TSS-20240403 | DU00002864306 |  |  | 2024-10-25 | 2024-10-24 |  | Minaret | 24m Minaret | 24 | Add R8862A S9000 x3,Dismantle | 0 | 0
4195H | 99 Speedmart PK DESA PERWIRA | Northern |  | MOCN As-Is |  | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864307 | [6 empty] | Small Cell
1281H | 99 Speedmart TMN SRI RAMPAI 2 | Central |  | MOCN As-Is |  | 2024 Q1 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864308 | [6 empty] | Small Cell
1003B | KG Baru Ampang | Central |  | Modernization |  | 2024 Q2 | MA | YPTT | 4.6 TSSR Approved |  | 2024-01-17 | 2024-01-24 |  | 2024-02-06 |  | Closed | 2024-02-07 | 2024-02-14 | E//Sumitra | 2024-02-14 | CelcomDigi_RAN_YPTT_TSS_Central_20240124 | DU00002864309 |  |  | 2024-03-10 | 2024-03-08 |  | In-Building System | 3m Bipod (RT) | 6 | Add R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
4184H | 99 Speedmart PK GUNUNG RAPAT | Northern |  | MOCN As-Is |  | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864310 | [6 empty] | Small Cell
1202H | 99 Speedmart BRICKFIELDS 1 | Central |  | MOCN As-Is |  | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864311 | [6 empty] | Small Cell
9676B | Sucihandal Commercial Centre | Sarawak |  | Modernization |  | 2024 Q2 | SH | Magicell | 4.6 TSSR Approved |  | 2023-10-05 | 2023-10-06 |  | 2023-10-16 |  | Closed | 2023-12-15 | 2024-01-09 | E//Hannah | 2024-01-09 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20231006 | DU00002864312 |  |  | 2024-02-23 | 2024-01-25 |  | Monopole | 30m Lampole | 30 | Add R8862A S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 13 | 0
1477H | 99 Speedmart PJ SS 5 | Central |  | MOCN As-Is |  | 2024 Q1 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864313 | [6 empty] | Small Cell
1371C | OUG Wet Market | Central |  | Modernization |  | 2024 Q3 | CR | DATASCO | 4.6 TSSR Approved |  | 2023-12-04 | 2023-12-27 |  | 2024-04-01 |  | Closed | 2024-04-03 | 2024-04-15 | E//Sumitra | 2024-04-08 | CelcomDigi_RAN_Datasco_TSS_Central_20231208 | DU00002864314 |  |  | 2024-05-20 | 2024-05-14 |  | In-Building System | Lampole | 6m | Add R8894E M1821 x1+R8854 S2600 x1,Dismantle R8862A S2601(A6A) x1 | 0 | 1
1447H | 99 Speedmart BRICKFIELDS 2 | Central |  | MOCN As-Is |  | 2024 Q2 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864315 | [6 empty] | Small Cell
4036H | VELOCITY MOBILE SERVICE CENTRE | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864316 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
4167H | 99 Speedmart PK JLN CHUNG AH MING | Northern |  | MOCN As-Is |  | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864317 | [6 empty] | Small Cell
1502C | Syabas Setia Ecohill | Central |  | Remote MOCN | Modernization->Remote MOCN | 2025 Q1 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002864318 | [6 empty] | Land site |  |  | 12
1333C | Sentosa Court | Central |  | Modernization |  | 2024 Q3 | SS | GTSB | 4.6 TSSR Approved |  | 2023-12-07 | 2023-12-26 |  | 2024-03-30 |  | Closed | 2024-04-03 | 2024-04-15 | E//Sumitra | 2024-04-09 | CelcomDigi_RAN_GTSB_TSS_Central_20231208 | DU00002864319 |  |  | 2024-05-18 | 2024-05-15 |  | Lampole | 18m Lampole | 18 | Add R9264H M901821 x3,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3 | 0 | 0
4243H | 99 Speedmart PK Lapangan Perdana | Northern |  | MOCN As-Is |  | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864320 | [6 empty] | Small Cell
4168H | 99 Speedmart PK LAPANGAN SENTRAL | Northern |  | MOCN As-Is |  | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864321 | [6 empty] | Small Cell
4217H | 99 Speedmart PK Medan Lavender | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864322 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
7648C | Kampung Mangkalinau | Sabah |  | Modernization |  | 2024 Q3 | MS | GTSB | 4.6 TSSR Approved |  | 2024-01-31 | 2024-03-15 |  | 2024-04-18 |  | Closed | 2024-04-19 | 2024-04-24 | E//Hannah | 2024-04-24 | Celcom Digi_RAN-GTSB-TSS-Sabah-20240204 | DU00002864323 |  |  | 2024-06-27 | 2024-06-22 |  | Monopole | 30m Monopole | 30 | Add R9264M M1821 x1+A9732 M1821 x3,Dismantle R8894E M1821(A8A) x4 | 134 | 0
7302C | Sandakan Town (REL) | Sabah |  | Modernization |  | 2024 Q3 | MS | YPTT | 4.6 TSSR Approved |  | 2024-03-15 | 2024-04-23 |  | 2024-04-29 |  | Closed | 2024-04-29 | 2024-05-02 | E//Hannah | 2024-05-02 | Celcom Digi_RAN-YPTT-TSS-Sabah-20240324 | DU00002864324 |  |  | 2024-06-30 | 2024-06-19 |  | In-Building System | Rooftop | 6 | Add R8862A S9000 x3+A9732 M1821 x3,Dismantle R9224E M1821(AAB) x3 | 123 | 0
4338D | Surau Seri Palma | Northern |  | Modernization |  | 2024 Q2 | BY | CCSMY | 4.6 TSSR Approved | ¦ 0213 - TP rejected and reverted back to SA, TSSR submitted is pBTS structure, SA to check who is site owner. | 2023-10-19 | 2023-10-26 |  | 2024-01-09 |  | Closed | 2024-02-28 | 2024-02-28 | E//Hazida | 2024-02-28 | Celcom Digi_RAN-CCSMY-TSS-Northern-20231020-0059 | DU00002864325 |  |  | 2024-02-27 | 2024-02-20 |  |  | 30M Minaret | 30 | Add R8862A S9000 x3+R8894E M1821 x5+R8854 S2600 x2,Dismantle R8862A S1800(B6A) x3+R8862A S2100(A6A) x3+R8862A S2601(A6A) x2 |  | 12
7006H | Ngui Sport Shop | Sabah |  | MOCN As-Is |  | 2024 Q3 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864326 | [6 empty] | Small Cell
1678C | Zoo Negara Entrance A (REL) | Central |  | Modernization |  | 2024 Q1 | YZ | GCI | 4.6 TSSR Approved |  | 2023-11-03 | 2023-11-06 |  | 2024-01-02 |  | Closed | 2024-01-03 | 2024-01-09 | E//Sumitra | 2024-01-09 | CelcomDigi_RAN_GCI_TSS_Central_20231104 | DU00002864327 |  |  | 2024-01-21 | 2024-01-20 |  | Monopole | 30m RDS | 30 | Add R8862A S9000 x3,Dismantle
9709B | UNIGARDEN | Sarawak |  | Modernization |  | 2024 Q2 | SH | Trintel | 4.6 TSSR Approved |  | 2023-10-30 | 2023-11-22 |  | 2024-01-10 |  | Closed | 2024-01-17 | 2024-02-21 | E//Hannah | 2024-02-21 | Celcom Digi_RAN-Trintel-TSS-Sarawak-20231028 | DU00002864328 |  |  | 2024-03-30 | 2024-03-15 |  | Monopole | 30m Lampole | 30m | Add R8862A S9000 x4+R8894E M1821 x5+R8854 S2600 x1,Dismantle R8862A S1800(B6A) x4+R8862A S2100(A6A) x4+R8862A S2601(A6A) x1 | 0 | 4
3145C | The ARC | Central |  | Remote MOCN | Modernization->Remote MOCN | 2024 Q3 |  |  | 14.2 Drop (Done Survey) |  | 2023-09-29 |  |  |  |  | To be Submitted | [5 empty] | DU00002864329 | [6 empty] | Land site |  |  | 1
1689C | Percing 14 Housing (parcel F9) | Central |  | Modernization |  | 2024 Q3 | AI | Magicell | 4.6 TSSR Approved |  | 2024-01-11 | 2024-01-17 |  | 2024-04-23 |  | Closed | 2024-05-15 | 2024-12-24 | E//Razif | 2024-12-24 | BOQ CelcomDigi_RAN_Magicell_Standard PR TSS_Central_20240115 | DU00002864330 |  |  | 2024-11-12 | 2024-11-02 |  | In-Building System | 6M RT - Wall Mounted Pole | 5M | Add R9264H M901821x3, Dismantle R8894E M1821(A8A)x3 | 0 | 0
1216H | 99 Speedmart TMN SETAPAK INDAH JAYA | Central |  | MOCN As-Is |  | 2024 Q1 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864331 | [6 empty] | Small Cell
1220H | 99 Speedmart WANGSA MAJU SEK 1 | Central |  | MOCN As-Is |  | 2024 Q1 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864332 | [6 empty] | Small Cell
1668C | Masjid Bdr Baru Ampang | Central |  | Modernization |  | 2024 Q4 | BY | GTSB | 4.6 TSSR Approved |  | 2024-03-15 | 2024-03-20 |  | 2024-05-23 |  | Closed | 2024-05-28 | 2024-06-12 |  | 2024-06-07 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240316 | DU00002864333 |  |  | 2024-06-07 | 2024-06-07 |  | Lampole | 24M Lampole | 24M | Add R8862A S9000 x4+R8894E M1821 x1,Dismantle | 0 | 3
1240H | 99 Speedmart TMN MELAWATI 2 | Central |  | MOCN As-Is |  | 2024 Q1 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864334 | [6 empty] | Small Cell
4234H | 99 Speedmart PK Taiping Business Centre | Northern |  | MOCN As-Is |  | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864335 | [6 empty] | Small Cell
1297H | 99 Speedmart SERI SETIA | Central |  | MOCN As-Is |  | 2024 Q1 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864336 | [6 empty] | Small Cell
1300H | 99 Speedmart TMN PERWIRA GOMBAK | Central |  | MOCN As-Is |  | 2024 Q1 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864337 | [6 empty] | iMacro
1315H | 99 Speedmart NZX ARA JAYA | Central |  | MOCN As-Is |  | 2024 Q1 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864338 | [6 empty] | Small Cell
1720C | Jalan Taman Seri Sentosa | Central |  | Modernization |  | 2024 Q3 | AI | GTSB | 4.6 TSSR Approved |  | 2023-11-18 | 2023-11-21 |  | 2023-12-18 |  | Closed | 2023-12-20 | 2024-04-04 | E//Sumitra | 2024-04-03 | CelcomDigi_RAN_GTSB_TSS_20231119 | DU00002864339 |  |  | 2024-05-18 | 2024-05-15 |  | Lampole | TT DOTCOM SDN BHD | 18m | Add R8862A S9000 x3+R9264M M1821 x3,Dismantle R8894E M1821(A8A) x3
7256C | Apartment Indah Jaya | Sabah |  | Modernization |  | 2024 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2024-03-11 | 2024-03-14 |  | 2024-04-04 |  | Closed | 2024-04-18 | 2024-04-24 | E//Hannah | 2024-04-24 | Celcom Digi_RAN-GTSB-Standard PR TSS-Sabah-20240313 | DU00002864340 |  |  | 2024-06-26 | 2024-06-21 |  | Monopole | 30M Monopole | 30m | Add R8862A S9000 x1+R9264H M901821 x2+A9732 M1821 x1,Dismantle R8894E M1821(A8A) x3 | 1 | 0
4228H | 99 Speedmart PK Taman Shatin | Northern |  | MOCN As-Is |  | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864341 | [6 empty] | Small Cell
4197H | 99 Speedmart PK TMN AMAN | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864342 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
4165H | 99 Speedmart PK Tmn Desa Aman | Northern |  | MOCN As-Is |  | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864343 | [6 empty] | Small Cell
9719B | Jalan Jelutong | Sarawak |  | Modernization |  | 2025 Q3 | AI | Magicell | 4.6 TSSR Approved |  | 2024-01-25 | 2024-02-09 |  | 2025-02-18 |  | Closed | 2025-02-20 | 2025-02-27 | E//Hannah | 2025-02-24 | Celcom Digi_RAN-Magicell-TSS-Sarawak-20240123 | DU00002864344 | Remarks: Solution TSSR/BOM Changed |  | 2025-03-17 | 2025-03-15 |  | Monopole | 30M Pole | 30 | Add R8852E S9000x3+R9264M M1821x3, Dismantle R8894E M1821(A8A)x3 | 0 | 0
7047H | 99 Speedmart TAMBUNAN TOWN | Sabah |  | MOCN As-Is |  | 2024Q4 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864345 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
4429D | Taman Cempaka | Northern |  | Modernization |  | 2024 Q2 | BY | GCI | 4.6 TSSR Approved |  | 2024-01-17 | 2024-01-23 |  | 2024-02-05 |  | Closed | 2024-02-06 | 2024-02-07 | E/Ajay | 2024-02-06 | Celcom Digi_RAN-GCI-TSS-Northern-20240124-0090 | DU00002864346 |  |  | 2024-03-15 | 2024-03-12 |  | Minaret | Minaret | 30 | Add R8862A S9000 x3+R8894E M1821 x2,Dismantle |  | 12
4365D | Surau Nurul Huda (REL) | Northern |  | Modernization |  | 2024 Q2 |  | GTSB | 4.6 TSSR Approved |  | 2024-01-08 | 2024-01-10 |  | 2024-01-16 |  | Closed | 2024-01-17 | 2024-01-30 | E//Hazida | 2024-01-23 | Celcom Digi_RAN-GTSB-TSS-Northern-20240110-0084 | DU00002864347 |  |  | 2024-03-13 | 2024-03-09 |  | Minaret | 30M MINARET | 36m | Add R8862A S9000 x2+R9264H M901821 x1+A9732 M1821 x2,Dismantle R8854 S2600(A4A) x2+R8894E M1821(A8A) x5 | 23
4233H | 99 Speedmart PK Tmn Kenas | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864348 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
4219H | 99 Speedmart PK Tmn Kuala Kangsar | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864349 | [6 empty] | iMacro |  | Remain iMacro AAU | 0 | 0
4171H | 99 Speedmart PK TMN MUHIBBAH JAYA | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864350 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
4218H | 99 Speedmart PK Tmn Pengkalan Pertama | Northern |  | MOCN As-Is |  | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864351 | [6 empty] | iMacro
4173H | 99 Speedmart PK TMN PENGKALAN SENTOSA | Northern |  | MOCN As-Is |  | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864352 | [6 empty] | Small Cell
4152H | 99 Speedmart PK TMN RENGAS JAYA | Northern |  | MOCN As-Is |  | 2027 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864353 | [6 empty] | Small Cell |  | Remain iMacro AAU | 0 | 0
7012D | Hap Seng (REL) | Sabah |  | Modernization |  | 2024 Q3 | AD | GTSB | 4.6 TSSR Approved |  | 2023-10-23 | 2023-10-24 |  | 2023-10-27 |  | Closed | 2023-10-30 | 2024-04-24 | E//Hannah | 2024-04-24 | Celcom Digi_RAN-GTSB-TSS-Sabah-20231024 | DU00002864354 |  |  | 2024-05-27 | 2024-05-23 |  | Monopole | 30M Monopole | 23 | Add R9264M M1821 x1+A9732 M1821 x2,Dismantle R8894E M1821(A8A) x3 | 12 | 0
4521D | Panorama Lapangan Perdana (REL) | Northern |  | Modernization |  | 2024 Q2 | BY | GCI | 4.6 TSSR Approved |  | 2023-10-10 | 2023-10-17 |  | 2024-01-10 |  | Closed | 2024-01-15 | 2024-01-23 | E//Hazida | 2024-01-21 | Celcom Digi_RAN-GCI-TSS-Northern-20231012-0057 | DU00002864355 |  |  | 2024-02-24 | 2024-02-20 |  | Minaret | 30M Minaret | 30 | Add R8862A S9000 x3+R8894E M1821 x1,Dismantle |  | 3
4135H | ZV Specialised | Northern |  | MOCN As-Is |  | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864356 | [6 empty] | Small Cell
4181H | Dream Max | Northern |  | MOCN As-Is |  | 2024 Q4 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864357 | [6 empty] | Small Cell
1621H | 99 Speedmart TMN GREENWOOD | Central |  | MOCN As-Is |  | 2024 Q1 |  |  | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864358 | [6 empty] | Small Cell
2811C | Surau Assobirin (REL) | Central |  | Modernization |  | 2024 Q4 | SM | GTSB | 4.6 TSSR Approved |  | 2024-01-06 | 2024-01-09 |  | 2024-05-10 |  | Closed | 2024-05-13 | 2024-05-20 | E//Sumitra | 2024-05-20 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240110 | DU00002864359 |  |  | 2024-07-04 | 2024-06-21 |  | Lampole | Lampole | 25m | Add R9264H M901821 x3,Dismantle R8894E M1821(A8A) x3 | 0 | 0
2737C | ELITE KM 33.8 (REL) | Central |  | Modernization |  | 2024 Additional | AI | GTSB | 4.6 TSSR Approved |  | 2024-01-11 | 2024-01-12 |  | 2024-05-17 |  | Closed | 2024-05-20 | 2024-05-24 | E//Razif | 2024-05-24 | BOQ CelcomDigi_RAN_GTSB_Standard PR TSS_Central_20240115 | DU00002864360 |  |  | 2024-06-07 | 2024-06-07 |  | Tower | Lampole | 47M | Add R9264H M901821 x4,Dismantle R9224E M1821(AAB) x4 | 0 | 0
4256H | 99 Speedmart PK Tmn Trong Perdana | Northern |  | MOCN As-Is |  | 2024 Q2 |  | NA | 14.1 Drop (No Survey) | [6 empty] | To be Submitted | [5 empty] | DU00002864361 | [6 empty] | Small Cell